## Sheet1
ISO | Project ID | Project Name | Availability of Studies | Transmission Owner | POI Name | County | CDR Reporting Zone | Projected COD | Technology | Capacity (MW) | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | Queue Date | Approved for Synchronization | Comment | Change Indicators
ERCOT | 15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2025-01-31 | WT | 162.1 | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | 2020-05-12 |  | COD
ERCOT | 16INR0049 | Nazareth Solar | SS Completed, FIS Completed, IA | TX Nazareth Solar, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | Castro | PANHANDLE | 2025-12-31 | PV | 204 | 2014-06-19 | 2014-07-25 | 2014-07-01 | 2023-04-17 | No | 2023-06-07
ERCOT | 16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2024-12-31 | WT | 201.6 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | 2019-12-12
ERCOT | 16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2024-06-28 | WT | 302.4 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | 2021-11-19
ERCOT | 16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, IA | Big Sampson Wind Project, LLC | tap 345kV 76015 Cedar Canyon - 7053 Noelke | Crockett | WEST | 2025-10-04 | WT | 265.4 | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2024-10-30 | Yes | 2019-11-08
ERCOT | 16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2025-09-01 | WT | 197.01 | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13
ERCOT | 17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2025-01-31 | WT | 242.6 | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | 2020-11-25 |  | COD
ERCOT | 17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2023-12-31 | WT | 44 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | 2021-03-16
ERCOT | 17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2023-12-31 | WT | 44 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | 2021-09-10
ERCOT | 17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2022-07-30 | WT | 32 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | 2021-03-04
ERCOT | 17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, IA | Nextera | 76090 Divide 345kV | Sterling | WEST | 2022-05-31 | WT | 9 | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 | No | 2008-01-15 | 2020-08-19
ERCOT | 17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WT | 7.3 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | 2017-12-20
ERCOT | 17INR0069 | Trent repower | SS Completed, FIS Completed, IA | TRENT WIND FARM LLC | 1338 Eskota 138kV | Nolan | WEST | 2025-01-30 | WT | 6.4 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | 2019-05-09 |  | COD
ERCOT | 17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | DESERT SKY WIND FARM LLC | two LCRA 138kV | Pecos | WEST | 2023-05-16 | WT | 7.2 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | 2019-09-06
ERCOT | 18INR0030 | Canyon Wind | SS Completed, FIS Completed, IA | Canyon Wind Energy, LLC | 11319 SCOSW ScurryCounty 138kV | Scurry | WEST | 2025-01-31 | WT | 308.82 | 2016-05-09 | 2016-07-22 | 2017-03-02 | 2023-03-27 | No | 2018-09-20 | 2023-12-01 |  | COD
ERCOT | 18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-12-31 | WT | 182.4 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | 2021-04-23
ERCOT | 18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2024-07-01 | WT | -7.2 | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | No | 2018-10-16 | 2020-07-28
ERCOT | 18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2023-12-31 | WT | 9.3 | 2018-05-22 | 2018-08-29 | 2018-05-22 | 2018-10-03 | No | 2018-12-04 | 2018-11-02
ERCOT | 18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WT | 3 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23
ERCOT | 18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2023-12-31 | WT | 0 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | 2019-11-13
ERCOT | 18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2023-12-31 | WT | 0 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | 2018-12-19
ERCOT | 19INR0002 | Grandfalls Solar | SS Completed, FIS Started, No IA | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2027-07-01 | PV | 178 | 2016-05-24 | 2016-06-06 | 2016-05-24
ERCOT | 19INR0022 | Monte Alto I | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2026-10-01 | WT | 141.5 | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2020-02-13
ERCOT | 19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2026-10-01 | WT | 307.9 | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2022-03-22
ERCOT | 19INR0035 | Norton Solar | SS Completed, FIS Completed, IA | TAI Norton Solar, LLC | 60451 Garnet 138kV | Runnels | WEST | 2025-10-01 | PV | 128.48 | 2017-03-06 | 2017-04-20 | 2017-11-08 | 2024-10-29 | No | 2019-06-20 |  |  | MW Size
ERCOT | 19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2024-12-31 | PV | 321.2 | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2022-01-25 |  | 2019-11-13 | 2022-12-20
ERCOT | 19INR0042 | Long Point Solar | SS Completed, FIS Started, IA | Long Point Solar, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2025-12-31 | PV | 120 | 2017-03-15 | 2017-04-20 | 2017-11-13 |  | No | 2019-10-24
ERCOT | 19INR0054 | Monte Cristo 1 Wind | SS Completed, FIS Completed, IA | Terra-Gen | Tap 345kV #8574 Pomelo - #8383 North Edinburg Ckt 2 | Hidalgo | SOUTH | 2025-08-20 | WT | 234.5 | 2017-04-11 | 2017-05-03 | 2017-07-28 | 2024-10-25 | No | 2023-05-09
ERCOT | 19INR0055 | Monte Cristo 2 Wind | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV #8574 Pomelo - #8383 North Edinburg ckt 2 | Hidalgo | SOUTH | 2026-12-31 | WT | 233.9 | 2017-04-11 | 2017-05-03 | 2017-07-28
ERCOT | 19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Brown | NORTH | 2026-09-19 | PV | 301.1 | 2017-06-23 | 2017-08-07 | 2018-02-09 |  | No
ERCOT | 19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | MESQUITE STAR SPECIAL LLC | 68001 Clayton 345kV | Fisher | WEST | 2024-10-31 | WT | 418.9 | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | No | 2018-12-05 | 2019-12-27
ERCOT | 19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2025-01-31 | PV | 141.05 | 2017-05-30 | 2017-08-11 | 2018-02-15 | 2021-04-26 | No | 2020-10-26 | 2022-06-28 |  | COD
ERCOT | 19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2024-12-31 | WT | 300 | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2020-04-03 | No | 2018-09-17 | 2020-11-12
ERCOT | 19INR0103 | Rodeo Solar | SS Completed, FIS Started, IA | Core Solar SPV I, LLC | 138kV 11273 NELSON SWITCH | Andrews | WEST | 2026-05-01 | PV | 200 | 2017-06-29 | 2017-08-04 | 2018-02-19 |  |  | 2019-08-20
ERCOT | 19INR0110 | Azalea Springs Solar | SS Completed, FIS Completed, IA | AZALEA SPRINGS SOLAR PARK LLC | tap 138kV Jim English – Lufkin Chipper Mill | Angelina | NORTH | 2025-06-13 | PV | 181 | 2017-07-26 | 2017-09-15 | 2018-03-15 | 2024-04-30 | No | 2023-09-14 |  |  | COD
ERCOT | 19INR0117 | Roadrunner Crossing Wind SLF | SS Completed, FIS Completed, IA | Roadrunner Crossing Wind Farm, LLC | 68051 Reata 345kV | Eastland | NORTH | 2025-01-31 | WT | 128 | 2017-09-08 | 2017-11-07 | 2018-03-05 | 2023-04-26 | No | 2020-04-17 | 2024-04-18
ERCOT | 19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2024-12-27 | WT | -18 | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | No | 2008-02-28 | 2020-06-09
ERCOT | 19INR0134 | Cottonwood Bayou Solar | SS Completed, FIS Completed, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2024-12-31 | PV | 351.4 | 2017-09-22 | 2017-11-17 | 2018-02-15 | 2023-04-27 | No | 2019-11-13 | 2024-05-29
ERCOT | 19INR0155 | Morrow Lake Solar | SS Completed, FIS Completed, IA | Morrow Lake Solar, LLC | 5895 Pearsall 138kV | Frio | SOUTH | 2025-01-25 | PV | 201.1 | 2017-12-05 | 2018-01-15 | 2018-02-15 | 2023-11-01 | No | 2019-08-29 | 2024-07-16 |  | COD
ERCOT | 19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2024-05-31 | WT | 0 | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | No | 2007-11-30 | 2019-06-27
ERCOT | 19INR0175 | Shifting Gale Wind | SS Completed, FIS Started, No IA | SEAWAY WIND ENERGY LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2025-12-31 | WT | 289 | 2018-04-26 | 2018-06-12 | 2018-12-06 |  | No
ERCOT | 19INR0177 | Crawfish | SS Completed, FIS Completed, IA | Prairie Switch Wind, LLC | 8679 Arroz4A 138kV | Wharton | SOUTH | 2025-01-31 | WT | 163.2 | 2018-05-09 | 2018-06-21 | 2018-05-09 | 2022-07-28 | No | 2021-07-06 | 2024-03-07 |  | COD
ERCOT | 19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2025-12-02 | PV | 40 | 2018-09-12 | 2018-10-03 |  |  | No
ERCOT | 19INR0203 | Angelo Solar | SS Completed, FIS Completed, IA | ANGELO SOLAR LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2024-10-11 | PV | 195.41 | 2018-11-20 | 2019-02-05 | 2019-01-21 | 2023-05-01 | No | 2021-12-03 | 2024-03-25
ERCOT | 20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar 75 | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2025-12-31 | PV | 40 | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No
ERCOT | 20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 17002 Garvey Rd 345kV | Young | WEST | 2024-12-17 | WT | -27 | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | No | 2018-10-17 | 2020-05-22
ERCOT | 20INR0029 | Lutum Wind | SS Completed, FIS Started, No IA | RWE | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2027-07-01 | WT | 241.5 | 2017-09-12 | 2017-11-07 | 2018-05-08 |  | No
ERCOT | 20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2025-01-31 | WT | 180.08 | 2017-10-18 | 2017-12-11 | 2018-06-14 | 2019-11-25 | No | 2020-02-21 | 2021-02-10 |  | COD
ERCOT | 20INR0035 | Angus Solar | SS Completed, FIS Completed, IA | Angus Solar, LLC | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2026-04-01 | PV | 112 | 2017-11-13 | 2018-01-02 | 2017-11-13 | 2023-04-03 |  | 2021-12-06
ERCOT | 20INR0047 | Siete | SS Completed, FIS Started, IA | Apex Clean | 345kV 8718 Triada | Webb | SOUTH | 2026-10-31 | WT | 375.06 | 2018-10-23 | 2018-12-11 | 2019-06-12 |  | No | 2022-06-30
ERCOT | 20INR0050 | Castro Solar | SS Completed, FIS Started, IA | Castro Solar One, LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2026-09-30 | PV | 222.95 | 2018-02-08 | 2018-04-09 | 2018-05-15 |  | No | 2020-11-30
ERCOT | 20INR0069 | Danish Fields Solar | SS Completed, FIS Completed, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2024-12-31 | PV | 602.8 | 2018-04-12 | 2018-06-05 | 2018-08-21 | 2022-07-25 | No | 2020-02-24 | 2023-05-04
ERCOT | 20INR0083 | Baird North Wind | SS Completed, FIS Completed, IA | BMP Wind, LLC | 68008 Latimer 345kV | Callahan | WEST | 2025-12-31 | WT | 350 | 2018-05-04 | 2018-06-12 | 2018-08-20 | 2020-10-30 | No | 2019-05-31 | 2021-08-20
ERCOT | 20INR0086 | Arroyo Solar | SS Completed, FIS Started, IA | BT Cantwell Solar, LLC | 345 KV Tap #8318 Rio Hondo - #8317 La Palma | Cameron | COASTAL | 2028-02-22 | PV | 100 | 2018-05-09 | 2018-07-09 | 2018-10-10 |  | No | 2021-09-28
ERCOT | 20INR0091 | Fagus Solar Park 1 SLF | SS Completed, FIS Completed, IA | Excel Advantage Services, LLC dba Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2026-02-11 | PV | 166.42 | 2018-05-15 | 2018-07-06 | 2018-05-15 | 2024-02-27 | No | 2019-02-21 |  |  | COD
ERCOT | 20INR0097 | El Sauz Ranch | SS Completed, FIS Completed, IA | El Sauz Ranch Wind, LLC | 8663 EL SAUZ POI 345kV | Willacy | COASTAL | 2025-03-01 | WT | 301.5 | 2018-06-19 | 2018-08-22 | 2019-01-31 | 2021-10-29 |  | 2021-01-27 | 2023-02-28 |  | COD
ERCOT | 20INR0106 | Wang Solar SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2026-03-31 | PV | 144.6 | 2018-06-14 | 2018-08-13 | 2018-08-29 |  | No
ERCOT | 20INR0127 | Walleye Solar | SS Completed, FIS Started, No IA | Sandow Lakes Ranch Solar II, LLC | 138kV Walleye Creek Switch 3712 | Milam | SOUTH | 2027-07-01 | PV | 215.2 | 2018-07-03 | 2018-09-18
ERCOT | 20INR0129 | Foxtrot Wind | SS Completed, FIS Completed, IA | Lincoln Clean | AEP 88689 Tango 345kV station | Bee | SOUTH | 2025-01-17 | WT | 268.2 | 2018-07-26 | 2018-09-14 | 2018-07-26 | 2021-07-30 | No | 2020-05-05 | 2022-03-09 |  | COD
ERCOT | 20INR0130 | Plainview Solar | SS Completed, FIS Completed, IA | Hecate Energy Ramsey LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2024-03-26 | PV | 514 | 2018-10-10 | 2018-11-21 | 2018-10-10 | 2020-10-26 | No | 2020-05-29 | 2021-07-26
ERCOT | 20INR0155 | Peyton Creek Wind II | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | 42400 Refuge 345kV | Matagorda | COASTAL | 2025-02-14 | WT | 241.2 | 2018-08-21 | 2018-11-02 | 2019-03-14 | 2024-06-25 | No | 2023-02-27
ERCOT | 20INR0162 | Diamondback solar | SS Completed, FIS Started, IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2027-12-31 | PV | 201.6 | 2018-09-13 | 2018-12-06 | 2018-11-07 |  | No | 2024-06-14
ERCOT | 20INR0203 | Pine Forest Solar | SS Completed, FIS Completed, IA | Pine Forest Solar I, LLC | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2025-12-01 | PV | 301.51 | 2018-10-04 | 2018-11-20 |  | 2024-12-18 | No | 2020-07-29
ERCOT | 20INR0205 | Roseland Solar | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2025-01-31 | PV | 254 | 2018-11-30 | 2019-02-04 | 2019-02-04 | 2021-10-25 | No | 2020-12-10 | 2022-09-26 |  | COD
ERCOT | 20INR0208 | Signal Solar | SS Completed, FIS Completed, IA | Adapture Renewables, Inc | tap 138kV 6879 Wieland - 6883 Quinlan N | Hunt | NORTH | 2025-02-24 | PV | 51.79 | 2018-11-07 | 2018-12-20 |  | 2023-09-01 | No | 2020-10-23 | 2024-11-12
ERCOT | 20INR0213 | Brushy Creek Solar SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2028-06-01 | PV | 177.09 | 2019-01-07 | 2019-03-26 | 2019-03-05 |  | No
ERCOT | 20INR0216 | Starr Solar Ranch | SS Completed, FIS Completed, IA | Starr Solar Ranch 1 LLC | 8795 Roma 138kV | Starr | SOUTH | 2024-12-27 | PV | 136.73 | 2018-11-07 | 2018-12-14 | 2018-11-07 | 2024-01-26 | No | 2020-10-01 | 2024-10-30 |  | COD
ERCOT | 20INR0217 | CAROL wind | SS Completed, FIS Completed, IA | NextERA Energy | 23906 AJ Swope 345kV | Potter | PANHANDLE | 2026-04-15 | WT | 165.42 | 2018-12-06 | 2019-01-18 | 2019-06-05 | 2023-10-30 | No | 2020-09-11
ERCOT | 20INR0222 | Tyson Nick Solar | SS Completed, FIS Completed, IA | Tyson Nick Solar Project, LLC | 1700 Toco 138kV | Lamar | NORTH | 2025-08-01 | PV | 90.5 | 2018-12-12 | 2019-02-15 | 2019-01-14 | 2024-07-29 | No | 2020-08-28
ERCOT | 20INR0230 | Markum Solar | SS Completed, FIS Completed, IA | Glory Leasing LLC | 177 Bosque 138kV | McLennan | NORTH | 2024-11-22 | PV | 161.54 | 2018-12-18 | 2019-01-03 | 2018-12-18 | 2023-11-28 |  | 2021-06-28 | 2024-09-03
ERCOT | 20INR0233 | Impala Flats Wind | SS Completed, FIS Started, No IA | Antelope Flats Wind, LLC | 79641 Farmland 345kV | Lynn | WEST | 2026-06-03 | WT | 282 | 2019-01-11 | 2019-04-03 | 2018-12-21
ERCOT | 20INR0235 | Knickerbocker Solar SLF | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2027-06-01 | PV | 241.26 | 2019-01-07 | 2019-03-15 | 2019-03-04
ERCOT | 20INR0236 | New Hickory Solar | SS Completed, FIS Completed, IA | New Hickory Solar LLC | OLD_HCKRY_5 bus 5323 345 kV | Jackson | SOUTH | 2026-07-15 | PV | 209.15 | 2019-01-25 | 2019-04-19 | 2019-08-12 | 2024-06-30 |  | 2020-06-30
ERCOT | 20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2026-04-08 | BA | 50.14 | 2019-01-14 | 2019-03-19 | 2019-04-26
ERCOT | 20INR0241 | Crowded Star Solar | SS Completed, FIS Completed, IA | Jones City Solar, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 | Jones | WEST | 2026-03-10 | PV | 218.79 | 2019-01-21 | 2019-04-19 | 2019-05-22 | 2024-11-05 | Yes | 2019-12-17 |  |  | COD
ERCOT | 20INR0242 | Anson Solar Center, Phase II | SS Completed, FIS Started, IA | Anson Solar Center 2, LLC | existing tap 345 kV 68004 Phantom Hill station | Jones | WEST | 2025-12-01 | PV | 200.9 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  | 2024-08-15
ERCOT | 20INR0244 | Montezuma Storage | SS Completed, FIS Completed, No IA | Montezuma Storage LLC | 7258 Glidden 138kV | Colorado | SOUTH | 2028-02-29 | BA | 50.6 | 2019-01-15 | 2019-07-02 | 2019-03-15 | 2023-11-30
ERCOT | 20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2028-02-29 | BA | 50.6 | 2019-01-15 | 2019-07-02 | 2019-03-15
ERCOT | 20INR0246 | Ryan Energy Storage | SS Completed, FIS Completed, IA | Ryan Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2027-03-31 | BA | 50 | 2019-01-15 | 2019-04-05 | 2019-03-15 | 2020-08-16 | No | 2021-02-18
ERCOT | 20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, No IA | Water Valley Wind Energy, LLC | 345 kV 76009 Twin Buttes to 76090 Divide Double Circuit | Tom Green | WEST | 2026-12-31 | WT | 180 | 2019-01-15 | 2019-03-29 | 2019-01-10
ERCOT | 20INR0248 | DAMAZO (Second Division) SOLAR | SS Completed, FIS Completed, IA | TX Gulf Solar 1 LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2024-12-20 | PV | 100.2 | 2019-03-28 | 2019-06-18 | 2019-07-29 | 2022-10-28 | No | 2020-10-14 | 2024-10-17
ERCOT | 20INR0255 | Renegade Project | SS Completed, FIS Started, IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2026-03-12 | PV | 515.66 | 2019-02-26 | 2019-05-17 | 2019-02-07 |  |  | 2021-01-04
ERCOT | 20INR0266 | Tres Bahias Solar | SS Completed, FIS Completed, IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2025-01-31 | PV | 195 | 2019-03-26 | 2019-06-11 | 2019-06-03 | 2022-01-21 |  | 2020-08-07 | 2023-09-12 |  | COD
ERCOT | 20INR0269 | Texas Solar Nova 2 | SS Completed, FIS Completed, IA | TEXAS SOLAR NOVA 2, LLC | 138kV 59909 WETT Nova Prime | Kent | WEST | 2024-12-31 | PV | 201.14 | 2019-06-24 | 2015-12-30 | 2019-06-19 | 2022-05-19 |  | 2021-07-16 | 2023-11-13
ERCOT | 20INR0271 | Blue Hills Wind | SS Completed, FIS Started, No IA | Greenalia Wind Power Blue Hills | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2026-06-15 | WT | 276 | 2019-05-07 | 2019-07-26 | 2019-11-21 |  | No
ERCOT | 20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2024-09-01 | CC | 21 | 2019-07-25 | 2019-10-23 | 2019-07-16 | 2019-10-23 | No | 2001-03-19
ERCOT | 20INR0296 | Sand Bluff Wind Repower | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | 1333 McDonald 138kV | Glasscock | WEST | 2025-03-01 | WT | 0.5 | 2019-11-27 | 2019-11-27 | 2019-11-19 | 2022-04-18 | No | 2006-11-11 | 2022-11-01 |  | COD
ERCOT | 21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2027-09-09 | WT | 240 | 2017-09-06 | 2019-08-19 | 2020-01-15
ERCOT | 21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2024-08-30 | ST | 14 | 2018-06-07 | 2018-08-01 |  | 2023-03-10 |  | 2020-08-07 | 2024-07-10
ERCOT | 21INR0022 | Red Holly Solar | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2027-06-01 | PV | 260 | 2018-07-11 | 2018-08-16 | 2018-07-11 |  | No | 2020-10-19
ERCOT | 21INR0029 | Red Holly Storage 1 | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2028-05-30 | BA | 50 | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | 2020-10-19
ERCOT | 21INR0031 | Indigo Solar | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | PV | 150 | 2018-09-27 | 2018-11-20 | 2019-05-15 |  | No | 2022-09-15
ERCOT | 21INR0033 | Red Holly Storage | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2028-05-30 | BA | 50 | 2018-09-27 | 2018-12-18 | 2018-12-11 |  | No | 2020-10-19
ERCOT | 21INR0203 | Eastbell Milam Solar | SS Completed, FIS Completed, IA | EDP RENEWABLES NORTH AMERICA LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2025-01-31 | PV | 244.86 | 2018-10-10 | 2018-12-09 | 2019-04-23 | 2022-10-28 | No | 2022-09-02 | 2023-11-01 |  | COD
ERCOT | 21INR0207 | Quantum Solar | SS Completed, FIS Started, IA | IP QUANTUM II, LLC | 60089 Kilby Station 345kV | Haskell | WEST | 2026-03-31 | PV | 374.4 | 2018-09-27 | 2018-11-14 | 2018-11-07 |  | No | 2023-10-26
ERCOT | 21INR0210 | Adamstown Solar | SS Completed, FIS Started, IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6111 Riley Ckt 2 | Wichita | WEST | 2027-08-31 | PV | 251.28 | 2018-11-20 | 2019-02-04 | 2019-05-16 |  | No | 2022-08-08 |  |  | COD
ERCOT | 21INR0220 | Maleza Solar | SS Completed, FIS Not Started, IA | Brush Solar LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2025-11-01 | PV | 254.94 | 2018-12-06 | 2019-01-18 |  |  | No | 2021-01-27
ERCOT | 21INR0221 | Samson Solar 1 | SS Completed, FIS Completed, IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2025-06-30 | PV | 250 | 2018-11-20 | 2019-01-04 | 2019-05-03 | 2020-06-09 | No | 2020-08-26 | 2021-08-31
ERCOT | 21INR0223 | Tulsita Solar | SS Completed, FIS Completed, IA | Ray Ranch Solar LLC | Tap 138kV 8590 Tuleta - 8595 Euler | Goliad | SOUTH | 2025-01-30 | PV | 256.2 | 2018-12-05 | 2019-02-21 | 2019-05-17 | 2024-03-01 | No | 2022-09-19 | 2024-10-30 |  | COD
ERCOT | 21INR0240 | La Casa Wind | SS Completed, FIS Completed, IA | LA CASA WIND, LLC | New switching station: 138kV Graham Plant Switch - Breckenridge - Leon Switch | Stephens | NORTH | 2025-06-30 | WT | 148.4 | 2018-12-28 | 2019-03-12 | 2018-12-29 | 2023-09-22 |  | 2023-09-07
ERCOT | 21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center 3, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2027-06-01 | PV | 200 | 2017-06-23 | 2017-08-07 | 2018-02-15
ERCOT | 21INR0253 | Ulysses Solar | SS Completed, FIS Started, IA | BNB Tennyson Solar LLC | tap 345kV 6444 Red Creek - 60040 Bluff Creek | Coke | WEST | 2026-02-23 | PV | 150 | 2019-01-25 | 2019-04-05 | 2019-05-10 |  |  | 2022-10-03
ERCOT | 21INR0256 | Amsterdam Solar | SS Completed, FIS Started, IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27, c18 | Brazoria | COASTAL | 2026-02-01 | PV | 509.88 | 2019-02-07 | 2019-04-29 | 2019-07-31 |  | No | 2022-02-17 |  |  | COD
ERCOT | 21INR0257 | Mercury Solar SLF | SS Completed, FIS Completed, IA | Mercury Solar, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2025-01-31 | PV | 206.11 | 2019-02-14 | 2019-05-03 | 2019-02-07 | 2021-10-14 |  | 2021-10-18 | 2023-10-31 |  | COD
ERCOT | 21INR0258 | Mercury Storage SLF | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2026-07-01 | BA | 0 | 2019-02-14 | 2019-05-03 | 2019-02-07
ERCOT | 21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | tap 69kV 99 Ben Hur - 107 Prairie Hill | Limestone | NORTH | 2028-02-29 | BA | 50 | 2019-03-06 | 2019-05-24 | 2019-02-11 |  | No
ERCOT | 21INR0262 | Grandfalls Storage SLF | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2027-07-01 | BA | 0 | 2019-03-25 | 2019-06-17 | 2019-02-14
ERCOT | 21INR0263 | Monarch Creek Wind | SS Completed, FIS Started, IA | Monarch Creek Wind Holdings, LLC | tap 345kV 11418 Tecumseh Creek Switch to 60515 Clear Crossing Switch | Throckmorton | WEST | 2026-12-31 | WT | 279 | 2019-04-25 | 2019-07-19 | 2019-08-05 |  | No | 2020-08-24
ERCOT | 21INR0265 | Sisters Solar | SS Completed, FIS Started, No IA | Oberon Solar LLC | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | Ector | WEST | 2027-05-31 | PV | 301.6 | 2019-02-28 | 2019-03-29 | 2019-02-20 |  | Yes
ERCOT | 21INR0268 | Greyhound Solar | SS Completed, FIS Completed, IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | Tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2026-03-31 | PV | 587.76 | 2019-03-28 | 2019-06-05 | 2019-03-21 | 2024-10-31 | No | 2022-01-15
ERCOT | 21INR0278 | Fighting Jays Solar | SS Completed, FIS Completed, IA | AP Solar Holdings, LLC | tap 345kV 44000 WA Parish - 44200 Hillje c64 | Fort Bend | HOUSTON | 2025-03-29 | PV | 351.29 | 2019-03-26 | 2019-06-17 | 2019-03-20 | 2021-06-30 | No | 2020-06-22 | 2022-03-31
ERCOT | 21INR0280 | Edgewater Storage | SS Completed, FIS Started, No IA | Edgewater Battery Storage LLC | 210 Reagor Springs 69kV | Ellis | NORTH | 2028-02-29 | BA | 50 | 2019-04-08 | 2019-07-04 | 2019-03-24 |  | No
ERCOT | 21INR0294 | Mountaineer Solar | SS Completed, FIS Started, No IA | Mustang Mountaineer Solar LLC | 1444 Brown 345 kV | Brown | NORTH | 2027-10-01 | PV | 329.64 | 2019-04-16 | 2019-06-11 | 2019-12-08 |  | No
ERCOT | 21INR0295 | Sterling Prairie Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 8608 Pavlov A 138kV | Matagorda | COASTAL | 2025-12-15 | PV | 119.91 | 2019-04-24 | 2019-07-23 | 2020-01-21 |  | No
ERCOT | 21INR0320 | Ion Solar | SS Completed, FIS Completed, No IA | GSE Group LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2026-05-29 | PV | 384 | 2019-05-17 | 2019-08-01 | 2020-01-28 | 2024-05-24
ERCOT | 21INR0324 | Board Creek Wind | SS Completed, FIS Completed, IA | Limestone Wind Project, LLC | 345kV 3386 Outlaw Switch | Navarro | NORTH | 2025-02-28 | WT | 299.2 | 2019-04-24 | 2019-07-22 | 2019-11-05 | 2022-04-26 | No | 2021-08-19 | 2022-10-06 |  | COD
ERCOT | 21INR0326 | Dove Run Solar | SS Completed, FIS Started, IA | Dove Run Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2026-07-31 | PV | 120.86 | 2019-05-07 | 2019-07-23 | 2019-05-02 |  |  | 2023-10-31
ERCOT | 21INR0334 | Nightfall Solar SLF | SS Completed, FIS Started, IA | BDPU SOLAR NIGHTFALL, LLC | Tap 138kV 8241 Razorback - 8234 Uvalde | Uvalde | SOUTH | 2026-06-30 | PV | 181.16 | 2019-05-10 | 2019-07-31 | 2020-01-24 |  |  | 2023-10-26
ERCOT | 21INR0341 | Space City Solar | SS Completed, FIS Started, IA | Apollo Solar Ranch, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2026-06-01 | PV | 609.74 | 2019-11-01 | 2020-03-06 | 2019-10-15 |  |  | 2021-01-06
ERCOT | 21INR0343 | Flag City Solar | SS Completed, FIS Started, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang c1 | Jackson | SOUTH | 2026-12-31 | PV | 167.3 | 2019-05-07 | 2019-07-29 | 2019-05-02 |  | No
ERCOT | 21INR0344 | Lunis Creek Solar SLF | SS Completed, FIS Started, IA | Lunis Creek Solar Project, LLC | tap 345 kV Static (#8676) - South Texas Project (#5915) | Jackson | SOUTH | 2026-12-31 | PV | 617.12 | 2019-05-02 | 2019-07-03 | 2019-05-02 |  |  | 2021-10-29
ERCOT | 21INR0347 | Lunis Creek Storage SLF | SS Completed, FIS Started, No IA | Lunis Creek Solar Project, LLC | tap 345kV 8956 White Point - 5915 STP | Jackson | SOUTH | 2026-12-31 | BA | 0 | 2019-05-02 | 2019-07-30 | 2019-05-02
ERCOT | 21INR0349 | Pearl Crescent Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Rock Island (57640) 138kV | Colorado | SOUTH | 2026-12-08 | PV | 208.35 | 2019-05-31 | 2019-08-26 | 2019-09-30
ERCOT | 21INR0351 | 7V Solar | SS Completed, FIS Completed, IA | 7V Solar Ranch, LLC | tap 138kV 7248 Flatonia - 7274 Plum | Fayette | SOUTH | 2025-01-31 | PV | 240.63 | 2019-04-16 | 2019-07-03 | 2019-08-16 | 2022-10-21 |  | 2020-09-01 | 2023-12-13 |  | COD
ERCOT | 21INR0353 | Big Elm Solar | SS Completed, FIS Completed, IA | Big Elm Solar, LLC | 345kV #3404 Belfalls Switch | Bell | NORTH | 2024-12-21 | PV | 201.02 | 2019-06-27 | 2019-09-23 | 2020-03-23 | 2023-07-25 | No | 2022-09-01 | 2024-05-22
ERCOT | 21INR0359 | Hickerson Solar | SS Completed, FIS Completed, IA | Hickerson Solar | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2026-03-01 | PV | 316.3 | 2019-05-29 | 2019-08-23 | 2020-02-19 | 2024-12-17 | Yes | 2023-12-18
ERCOT | 21INR0362 | Oystercatcher Solar | SS Completed, FIS Started, IA | Oystercatcher Solar, LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2026-09-17 | PV | 220.33 | 2019-05-30 | 2019-08-07 | 2019-12-20 |  | Yes | 2021-08-20
ERCOT | 21INR0368 | Eliza Solar | SS Completed, FIS Completed, IA | Ables Springs Solar, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2025-01-22 | PV | 151.7 | 2019-06-21 | 2019-08-30 | 2020-02-24 | 2023-10-30 | No | 2022-08-04 | 2024-10-22
ERCOT | 21INR0371 | HIP Solar Project | SS Completed, FIS Started, No IA | ConnectGen Operating LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 50 | Leon | NORTH | 2027-03-26 | PV | 137.6 | 2019-08-16 | 2019-11-05 | 2019-08-22
ERCOT | 21INR0379 | Ash Creek Solar | SS Completed, FIS Completed, IA | Ash Creek Solar LLC | 68090 SAM SW 345kV | Hill | NORTH | 2025-03-28 | PV | 417.74 | 2019-07-29 | 2019-10-25 | 2019-07-19 | 2024-04-16 | No | 2022-11-11 |  |  | COD
ERCOT | 21INR0380 | Charolais Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2026-12-15 | PV | 261.63 | 2019-08-05 | 2019-10-31 | 2020-04-27 |  | Yes
ERCOT | 21INR0391 | Grandslam Solar | SS Completed, FIS Started, IA | Grandslam Solar, L.L.C. | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2026-06-01 | PV | 121.89 | 2019-07-29 | 2019-10-30 | 2019-07-26 |  |  | 2021-01-29
ERCOT | 21INR0393 | Orange Grove Solar | SS Completed, FIS Completed, IA | Enbridge Solar (Orange Grove), LLC | 5660 Orange Grove 138kV | Jim Wells | SOUTH | 2025-04-30 | PV | 130.6 | 2019-07-12 | 2019-09-09 | 2019-07-08 | 2024-07-23 | No | 2022-06-08
ERCOT | 21INR0401 | Young Wind | SS Completed, FIS Completed, IA | Young Wind, LLC | Tap 345kV 60515 Clear Crossing - 1421 Willow Creek | Young | WEST | 2025-01-31 | WT | 499.14 | 2019-07-29 | 2019-10-25 | 2020-03-27 | 2021-05-28 | No | 2022-02-18 | 2022-12-08
ERCOT | 21INR0406 | Buffalo Creek | SS Completed, FIS Completed, IA | Lincoln Clean Energy Development | tap 345kV 44000 WA Parish – 44040 BAILEY | Fort Bend | HOUSTON | 2025-01-10 | PV | 438.75 | 2019-08-01 | 2019-10-30 | 2019-07-31 | 2021-04-23 | No | 2020-04-16 | 2022-01-06 |  | COD
ERCOT | 21INR0413 | Big Star Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2025-03-01 | PV | 203.1 | 2019-08-27 | 2019-11-08 | 2019-12-20 | 2021-07-19 |  | 2020-10-02 | 2022-12-19 |  | COD
ERCOT | 21INR0414 | Jayhawk Solar | SS Completed, FIS Started, No IA | Renewable Energy Ventures, LLC | tap 345kV 1030 Morgan - 76030 Gasconades | Mitchell | WEST | 2025-10-30 | PV | 101.5 | 2019-08-05 | 2019-10-31 | 2020-01-17
ERCOT | 21INR0421 | Armadillo Solar | SS Completed, FIS Started, IA | Armadillo Solar Center, LLC | 3387 Revolution 138kV | Navarro | NORTH | 2026-12-31 | PV | 200.09 | 2019-08-28 | 2019-11-22 | 2019-08-28 |  | No | 2021-02-02
ERCOT | 21INR0428 | Nabatoto Solar North | SS Completed, FIS Started, IA | CG Leon County II LLC | tap 345kV 967 Gibbons Creek - 46020 Limestone ckt 50 | Leon | NORTH | 2027-05-10 | PV | 451.35 | 2019-09-23 | 2019-12-10 | 2019-09-11 |  | No | 2021-02-26
ERCOT | 21INR0432 | Diversion Wind | SS Completed, FIS Started, No IA | Diversion Wind Development LLC | 6101 Riley 345kV | Baylor | WEST | 2024-12-30 | WT | 300 | 2019-09-10 | 2019-12-04 | 2020-06-04
ERCOT | 21INR0442 | Myrtle Storage | SS Completed, FIS Completed, IA | Myrtle Storage, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2024-12-31 | BA | 151.2 | 2019-11-04 | 2020-02-07 | 2020-07-30 | 2023-01-31 |  | 2022-06-13 | 2023-11-10
ERCOT | 21INR0443 | Cottonwood Bayou Storage | SS Completed, FIS Completed, IA | Cottonwood Bayou Storage, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2025-06-12 | BA | 153.03 | 2019-10-31 | 2020-01-23 | 2020-07-17 | 2024-03-25 | No | 2022-03-18
ERCOT | 21INR0444 | Long Point Storage | SS Completed, FIS Started, IA | Long Point Storage, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2025-12-01 | BA | 100.62 | 2019-11-01 | 2020-02-05 | 2020-09-01 |  | No | 2023-08-28
ERCOT | 21INR0446 | Knickerbocker Storage SLF | SS Completed, FIS Started, No IA | Knickerbocker Solar LLC | Tap 345kV 76003 Big Hill - 76009 Twin Buttes | Tom Green | WEST | 2027-06-01 | BA | 0 | 2019-12-19 | 2020-03-06 | 2019-12-05
ERCOT | 21INR0450 | Danish Fields Storage | SS Completed, FIS Completed, IA | Danish Fields Storage, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2024-12-31 | BA | 152.43 | 2019-10-31 | 2020-01-24 | 2020-07-17 | 2023-07-24 | No | 2022-06-13 | 2023-12-28
ERCOT | 21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2028-01-01 | BA | 100 | 2019-12-03 | 2020-02-24 | 2019-10-22
ERCOT | 21INR0456 | Maleza Storage | SS Completed, FIS Started, No IA | Brush Storage, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2025-11-01 | BA | 150.83 | 2019-10-31 | 2020-01-24 | 2020-08-18
ERCOT | 21INR0458 | Porter Solar | SS Completed, FIS Completed, IA | Porter Solar, LLC | tap 345kv 1429 Jacksboro - 1730 Krum West | Denton | NORTH | 2024-07-31 | PV | 245.83 | 2020-01-30 | 2020-04-17 | 2020-08-06 | 2023-04-28 | No | 2022-02-03 | 2023-12-11
ERCOT | 21INR0469 | Big Star Storage | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | Tap 345kV 9074 Lytton - 9073 Holman | Bastrop | SOUTH | 2025-03-01 | BA | 80 | 2020-01-02 | 2020-03-26 | 2020-08-28 | 2021-07-19 |  | 2020-10-02 | 2023-11-06 |  | COD
ERCOT | 21INR0470 | Pearl Crescent Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Rock Island (57640) 138kV | Colorado | SOUTH | 2026-12-15 | BA | 50.26 | 2019-12-20 | 2020-03-12 | 2020-04-10
ERCOT | 21INR0482 | Sisters Storage | SS Completed, FIS Started, No IA | 174 Power Global Properties | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | Ector | WEST | 2027-05-31 | BA | 208.89 | 2019-12-18 | 2020-03-11 | 2019-12-18
ERCOT | 21INR0483 | Morrow Lake Storage | SS Completed, FIS Started, No IA | Morrow Lake Storage, LLC | 5895 Pearsall 138kV | Frio | SOUTH | 2025-02-08 | BA | 201.13 | 2020-02-07 | 2020-04-30 | 2020-10-26
ERCOT | 21INR0490 | Samson Solar 2 | SS Completed, FIS Completed, IA | Samson Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2025-01-13 | PV | 203 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | 2024-10-14
ERCOT | 21INR0491 | Samson Solar 3 | SS Completed, FIS Completed, IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2025-06-30 | PV | 250 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | 2021-10-26
ERCOT | 21INR0492 | Stockyard Grid Batt | SS Completed, FIS Completed, IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2026-12-31 | BA | 150.6 | 2020-01-13 | 2020-03-30 | 2020-01-13 | 2022-07-14 | No | 2022-10-26
ERCOT | 21INR0505 | Ramsey Storage | SS Completed, FIS Started, IA | Hecate Energy Ramsey Storage LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2027-12-31 | BA | 510.4 | 2020-05-20 | 2020-07-30 | 2020-12-23 |  | No | 2022-08-11
ERCOT | 21INR0507 | Arana Creek Batt | SS Completed, FIS Started, No IA | Arana Creek LLC | 5648 Loyola 138kV | Kleberg | COASTAL | 2026-05-31 | BA | 153.5 | 2020-06-03 | 2020-08-10 | 2020-10-06
ERCOT | 21INR0508 | Angels Creek | SS Completed, FIS Started, No IA | Angels Creek LLC | 5888 Bruni 69kV | Webb | SOUTH | 2026-06-01 | BA | 31.68 | 2020-06-03 | 2020-08-18 | 2020-07-23 |  | No
ERCOT | 21INR0509 | McClure Solar | SS Completed, FIS Started, No IA | McClure Solar LLC | tap 69kV 785 Oran - 343 Morris Sheppard | Palo Pinto | NORTH | 2025-12-31 | PV | 105.73 | 2020-06-03 | 2020-08-18 | 2021-02-24 |  | No
ERCOT | 21INR0511 | Wolf Ridge Repower | SS Completed, FIS Completed, IA | Wolf Ridge Wind Energy, LLC | 730 Wolf Ridge 138kV | Cooke | NORTH | 2025-01-15 | WT | 9 | 2020-06-26 | 2020-09-14 | 2020-10-08 | 2023-05-01 | No | 2007-11-01 | 2023-10-10
ERCOT | 21INR0515 | Roadrunner Crossing Wind II SLF | SS Completed, FIS Completed, IA | Roadrunner Crossing Wind Farm, LLC | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2025-01-31 | WT | 126.72 | 2020-07-02 | 2020-09-14 | 2020-07-09 | 2023-05-01 |  | 2020-04-17 | 2024-04-18
ERCOT | 21INR0517 | Tidwell Prairie Storage 1 | SS Completed, FIS Completed, IA | Tidwell Prairie LLC | 39950 TNP ONE PLANT 345kV - 3400 TWIN OAK | Robertson | NORTH | 2025-06-01 | BA | 200.6 | 2020-07-24 | 2020-10-20 | 2020-07-16 | 2024-10-18 |  | 2022-11-03
ERCOT | 21INR0520 | Viking Solar | SS Completed, FIS Started, IA | Yellow Viking Development One, LLC | ap 345kV 1900 Comanche Peak - 11886 Timberview Switch | Somervell | NORTH | 2026-11-07 | PV | 288.99 | 2020-10-23 | 2021-01-12 | 2020-08-20 |  |  | 2022-10-25
ERCOT | 21INR0527 | Hays Energy Unit 3 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays 345kV | Hays | SOUTH | 2025-08-30 | GT | 18 | 2020-10-07 | 2020-12-30 | 2021-02-05
ERCOT | 21INR0532 | Brazos Wind Repower | SS Completed, FIS Completed, No IA | BRAZOS WIND VENTURES, LLC | 1064 Sun 138kV | Scurry | WEST | 2025-01-30 | WT | 22.4 | 2020-12-22 | 2021-03-10 | 2020-11-30 | 2022-04-01 |  |  | 2023-07-01 |  | COD
ERCOT | 21INR0534 | Midlothian Unit 2 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1939 Midlothian ELP 345kV | Ellis | NORTH | 2025-08-30 | GT | 18 | 2021-01-25 | 2021-04-30 | 2021-02-08
ERCOT | 21INR0538 | Blue Jay Solar II | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2024-12-31 | PV | 68.95 | 2021-04-13 | 2021-04-14 |  | 2021-04-26 | No | 2020-10-26 | 2021-11-19
ERCOT | 21INR0546 | Anchor Wind III | SS Completed, FIS Completed, IA | RANCHLAND WIND PROJECT LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2024-12-31 | WT | 16 | 2021-12-03 | 2022-03-01 |  | 2021-04-30 | No | 2020-11-30 | 2022-12-13
ERCOT | 22INR0202 | Delilah Solar 1 | SS Completed, FIS Completed, IA | Delilah Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2025-06-30 | PV | 300 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | 2024-03-21
ERCOT | 22INR0203 | Delilah Solar 2 | SS Completed, FIS Completed, IA | Delilah Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2025-07-26 | PV | 317.58 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22
ERCOT | 22INR0205 | Sbranch Solar | SS Completed, FIS Completed, IA | Bernard Creek Solar, LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2024-10-15 | PV | 233.52 | 2019-01-03 | 2019-03-13 | 2019-03-29 | 2021-07-29 | No | 2020-07-26 | 2023-11-21
ERCOT | 22INR0209 | Felix North Solar | SS Completed, FIS Started, No IA | Crescent Solar, LLC | 6101 Riley 345kV | Wilbarger | WEST | 2027-07-31 | PV | 100.54 | 2019-01-17 | 2019-04-02 | 2019-09-20 |  | No
ERCOT | 22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2026-01-31 | PV | 200.2 | 2019-06-24 | 2015-12-30 | 2019-06-19
ERCOT | 22INR0218 | Greyhound Solar 2 | SS Completed, FIS Started, No IA | Greyhound Solar 2 | tap 345kV dbl ckt 11010 Wolf - 1018 Moss and 11008 Wolf - 11028 Odessa | Ector | WEST | 2027-06-01 | PV | 500 | 2019-05-14 | 2019-08-05 | 2019-05-10
ERCOT | 22INR0220 | Lamkin Solar | SS Completed, FIS Completed, No IA | Commanche Solar, LLC | tap 69kV 258 Hamilton - 273 Gustine | Comanche | NORTH | 2025-12-31 | PV | 101.5 | 2019-06-24 | 2019-09-18 | 2020-03-13 | 2022-07-11
ERCOT | 22INR0237 | Dragan Solar | SS Completed, FIS Completed, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2026-06-02 | PV | 411 | 2019-11-11 | 2020-02-17 | 2019-08-23 | 2022-04-25 | No
ERCOT | 22INR0239 | Rockefeller Storage | SS Completed, FIS Started, IA | Mittel Rockefeller Storage LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2027-06-01 | BA | 206.8 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  | No | 2024-09-23
ERCOT | 22INR0242 | Bright Arrow Solar | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | 11689 CYCLONE 345 KV | Hopkins | NORTH | 2025-03-01 | PV | 305.07 | 2020-02-12 | 2020-05-01 | 2020-03-04 | 2022-04-19 | No | 2021-02-18 | 2023-11-27
ERCOT | 22INR0243 | Painted Horse Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2025-12-15 | PV | 200.58 | 2020-02-12 | 2020-05-06 | 2020-11-05
ERCOT | 22INR0244 | Razorbill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2025-12-15 | PV | 240 | 2020-01-02 | 2020-03-26 | 2020-09-16
ERCOT | 22INR0251 | Shaula I Solar | SS Completed, FIS Started, IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2026-03-31 | PV | 205.2 | 2019-12-03 | 2020-03-08 | 2019-11-20 |  | No | 2022-02-16
ERCOT | 22INR0257 | Corazon Solar Phase II | SS Completed, FIS Started, IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2028-06-01 | PV | 203.9 | 2019-12-19 | 2020-03-12 | 2019-12-04 |  | No | 2020-08-04
ERCOT | 22INR0260 | Eliza Storage | SS Completed, FIS Completed, IA | Ables Springs Storage, LLC | tap 345kV 2478 Royse - 3103 Shamburger | Kaufman | NORTH | 2025-03-11 | BA | 100.4 | 2019-12-03 | 2020-02-25 | 2020-08-19 | 2023-10-30 |  | 2022-08-04 | 2024-10-22
ERCOT | 22INR0261 | Dorado Solar | SS Completed, FIS Started, IA | Enbridge Solar (Sequoia I), LLC | 68051 Reata 345kV | Callahan | WEST | 2025-12-31 | PV | 401.35 | 2020-01-09 | 2020-03-30 | 2020-08-27 |  | Yes | 2023-06-19
ERCOT | 22INR0262 | Deville Solar | SS Completed, FIS Started, IA | Deville Solar LLC | 68051 Reata 345kV | Callahan | WEST | 2026-02-28 | PV | 425.02 | 2020-01-22 | 2020-04-08 | 2020-08-27 |  |  | 2023-08-29
ERCOT | 22INR0267 | Shaula II Solar | SS Completed, FIS Started, IA | Shaula Energy Project II, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2026-05-30 | PV | 205.2 | 2019-12-18 | 2020-03-12 | 2019-12-18 |  | No | 2022-04-27
ERCOT | 22INR0270 | Miller's Branch I | SS Completed, FIS Completed, IA | Miller's Branch Solar, LLC | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2025-12-01 | PV | 200 | 2019-12-17 | 2020-03-06 | 2020-06-19 | 2024-11-01 |  | 2021-06-14
ERCOT | 22INR0274 | Crowded Star Solar II | SS Completed, FIS Completed, IA | Jones City Solar II, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 | Jones | WEST | 2026-04-16 | PV | 190.18 | 2020-03-26 | 2020-06-05 | 2021-03-24 | 2024-11-05 | No | 2019-12-17 |  |  | COD
ERCOT | 22INR0276 | Trinidad ESS Addition | SS Completed, FIS Completed, No IA | LUMINANT GENERATION COMPANY LLC | Tap 138kV 3127 Trinidad – 3466 Kerens | Henderson | NORTH | 2026-03-20 | BA | 110 | 2019-12-11 | 2020-03-06 | 2020-09-17 | 2023-01-20 | No
ERCOT | 22INR0279 | Clutch City Solar Phase I | SS Completed, FIS Completed, IA | HZ Solar I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT #04 | Brazoria | COASTAL | 2026-10-01 | PV | 200.75 | 2020-01-22 | 2020-04-08 | 2020-02-11 | 2024-04-16 | No | 2022-09-30
ERCOT | 22INR0283 | Peregrine Solar | SS Completed, FIS Completed, IA | SP-Peregrine Solar LLC | tap 345kV 8624 Grissom – 8164 Coleto Creek | Goliad | SOUTH | 2024-12-30 | PV | 301.3 | 2020-01-07 | 2020-03-30 | 2020-05-27 | 2024-07-29 | No | 2021-06-19 | 2024-11-21
ERCOT | 22INR0301 | Fortuna Wind | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | Tap 345kV 1429 Jacksboro - 1730 WKrum | Jack | NORTH | 2026-07-01 | WT | 295.3 | 2020-03-06 | 2020-05-27 | 2020-11-24 | 2024-05-09 |  | 2024-08-08
ERCOT | 22INR0302 | Bright Arrow Storage | SS Completed, FIS Completed, IA | RWE Solar Development, LLC | 11689 CYCLONE 345 KV | Hopkins | NORTH | 2025-03-01 | BA | 103.56 | 2020-03-06 | 2020-05-05 | 2020-11-02 | 2022-08-01 |  | 2022-03-17 | 2023-11-13
ERCOT | 22INR0307 | Desert Vine Solar | SS Completed, FIS Started, IA | Desert Vine Solar LLC | Tap 138kV 8957 Lopeno - 8299 Zapata Will be TSP’s Snapdragon Station | Zapata | SOUTH | 2026-12-30 | PV | 121.29 | 2020-05-01 | 2020-07-13 | 2021-02-03 |  | No | 2022-12-16
ERCOT | 22INR0328 | Inertia BESS | SS Completed, FIS Completed, IA | Inertia Energy Storage, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2025-02-28 | BA | 13 | 2020-06-03 | 2021-02-02 | 2020-05-27 | 2022-07-25 | No | 2021-05-04 | 2024-05-08 |  | COD
ERCOT | 22INR0330 | Old Aqueduct Batt | SS Completed, FIS Completed, No IA | Old Aqueduct LLC | 23920 Blackwater 345kV | Hale | PANHANDLE | 2026-09-01 | BA | 302.94 | 2020-05-01 | 2020-07-13 | 2020-06-29 | 2021-10-06
ERCOT | 22INR0332 | Brantley Branch Batt | SS Completed, FIS Started, No IA | Brantley Branch LLC | Mt. Enterprise (Bus # 3116) – Martin Lake 345kv Line (Bus # 3100 | Rusk | NORTH | 2026-09-14 | BA | 302.35 | 2020-05-01 | 2020-07-15 | 2020-11-24 |  | No
ERCOT | 22INR0335 | Estonian Solar | SS Completed, FIS Not Started, IA | Enel Green Power Estonian Solar Project, LLC | tap 138kV 17011 Enloe POI – 1816 Commerce Switch | Delta | NORTH | 2025-01-31 | PV | 202.5 | 2020-04-22 | 2020-06-29 |  |  | No | 2021-08-12 | 2024-04-22 |  | COD
ERCOT | 22INR0337 | Skylab Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 5915 STP - 8249 Angstrom | Wharton | SOUTH | 2025-12-01 | PV | 609.74 | 2020-06-03 | 2020-08-11 | 2020-05-27 |  | No
ERCOT | 22INR0342 | Matagorda Solar | SS Completed, FIS Completed, IA | Leeward Renewable Energy Development, LLC | 5555 Shropshire 69kV | Matagorda | COASTAL | 2026-08-24 | PV | 101 | 2020-05-01 | 2020-07-15 | 2020-11-05 | 2021-09-14 |  | 2022-06-08 |  |  | COD
ERCOT | 22INR0347 | BRP Crater BESS | SS Completed, FIS Started, No IA | BRP Crater BESS LLC | tap 345kV 1025 Falcon Seaboard - 1021 Midland East | Howard | WEST | 2028-03-01 | BA | 310.31 | 2020-05-20 | 2020-07-30 | 2020-04-30
ERCOT | 22INR0349 | Antlia BESS | SS Completed, FIS Completed, IA | BRP Antlia BESS LLC | 88999 138 kV Maxwell Station | Val Verde | WEST | 2025-03-31 | BA | 72.38 | 2020-06-03 | 2020-08-11 | 2020-05-14 | 2024-05-02 | No | 2021-06-05
ERCOT | 22INR0350 | Sandow Solar | SS Completed, FIS Completed, No IA | Sandow Lakes Ranch Solar I, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2026-09-21 | PV | 287.18 | 2020-09-11 | 2021-02-08 | 2020-05-28 | 2024-07-18
ERCOT | 22INR0353 | Carina BESS | SS Completed, FIS Completed, IA | BRP Carina BESS LLC | 88479 (138 kV CRINAPOI4A) | Nueces | COASTAL | 2025-03-19 | BA | 154.11 | 2020-06-26 | 2020-09-14 | 2020-06-22 | 2021-07-06 |  | 2021-08-03
ERCOT | 22INR0354 | XE Murat [Adlong] Solar | SS Completed, FIS Completed, IA | Liberty 1 Solar | tap 138kV 40391 Crosby C66 - 40130 Atascocita | Harris | HOUSTON | 2025-01-31 | PV | 60.36 | 2020-08-04 | 2020-10-16 | 2021-01-05 | 2021-12-06 |  | 2022-03-04 | 2024-11-27
ERCOT | 22INR0356 | Jungmann Solar | SS Completed, FIS Completed, IA | BT Jungmann LLC | Tap 69kV 3643 Temp SS - 3689 Marak c1 | Milam | SOUTH | 2025-04-25 | PV | 40.21 | 2020-06-03 | 2020-08-11 | 2021-02-05 | 2024-04-25 |  | 2022-02-15 | 2024-12-23 |  | COD
ERCOT | 22INR0357 | Loma Pinta Solar | SS Completed, FIS Started, No IA | Loma Pinta Wind Energy, LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2026-05-31 | PV | 203.06 | 2020-06-03 | 2020-08-18 | 2020-05-28 |  | No
ERCOT | 22INR0363 | Hayhurst Texas Solar | SS Completed, FIS Completed, IA | Hayhurst Texas Solar, LLC | tap 138 kV Three Mile Draw Switch – Horseshoe Springs Switch Line | Culberson | WEST | 2024-07-31 | PV | 24.76 | 2020-08-21 | 2020-11-04 | 2020-08-13 | 2023-04-26 |  | 2021-09-09 | 2023-12-12
ERCOT | 22INR0364 | Painted Horse Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP - 5133 Elm Creek ckt 1 | Wilson | SOUTH | 2025-12-15 | BA | 53.22 | 2020-07-02 | 2020-09-14 | 2021-03-07
ERCOT | 22INR0365 | BRP Mensa BESS | SS Completed, FIS Started, No IA | BRP Mensa BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2027-12-01 | BA | 404.99 | 2020-06-26 | 2020-09-14 | 2020-06-22
ERCOT | 22INR0368 | Padua Grid BESS | SS Completed, FIS Completed, IA | Padua Grid, LLC | 5395 O.W Sommers 138kV | Bexar | SOUTH | 2025-04-23 | BA | 51.1 | 2020-07-10 | 2020-09-28 | 2020-06-29 | 2024-01-22 | No | 2021-11-16
ERCOT | 22INR0374 | Inertia Solar | SS Completed, FIS Started, IA | Inertia Solar Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2027-07-01 | PV | 202.39 |  | 2021-02-02 | 2020-10-13 |  |  | 2021-05-04
ERCOT | 22INR0375 | Inertia BESS 2 | SS Completed, FIS Started, IA | Inertia Energy Storage, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2027-07-01 | BA | 100.77 | 2020-10-13 | 2021-02-02 | 2020-10-13 |  |  | 2021-05-04
ERCOT | 22INR0382 | Razorbill Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 5915 STP to 44200 Hillje 345kV Ckt 64 | Matagorda | COASTAL | 2025-12-15 | BA | 120 | 2020-08-04 | 2020-10-28 | 2021-06-11
ERCOT | 22INR0383 | BRP Musca BESS | SS Completed, FIS Started, No IA | BRP Musca BESS LLC | 60361 Santa Rita 138kV | Reagan | WEST | 2027-12-01 | BA | 100.51 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No
ERCOT | 22INR0385 | BRP Pictor BESS | SS Completed, FIS Started, No IA | BRP Pictor BESS LLC | 60400 Lynx 138kV | Crane | WEST | 2025-11-01 | BA | 201.07 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No
ERCOT | 22INR0386 | BRP Octans BESS | SS Completed, FIS Started, No IA | BRP OCTANS BESS LLC | 6671 Tombstone 138kV | Pecos | WEST | 2026-06-01 | BA | 129.57 | 2020-07-24 | 2020-10-08 | 2020-08-13
ERCOT | 22INR0387 | Val Vista Grid BESS 1 | SS Completed, FIS Started, No IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2028-06-01 | BA | 209.32 | 2020-08-04 | 2020-10-16 | 2020-07-21
ERCOT | 22INR0388 | Cachi BESS | SS Completed, FIS Completed, IA | BRP Cachi BESS LLC | 7680 Clear Springs 138kV | Guadalupe | SOUTH | 2025-03-31 | BA | 205.46 | 2020-08-21 | 2020-11-10 | 2020-08-26 | 2024-07-31 |  | 2021-06-11
ERCOT | 22INR0390 | BRP Perseus BESS | SS Completed, FIS Started, No IA | BRP Perseus BESS LLC | tap 138 kV line from Lon Hill (#8452) to Bessel (#8060) | Nueces | COASTAL | 2027-12-01 | BA | 202.5 | 2020-08-21 | 2020-11-10 | 2020-08-17
ERCOT | 22INR0392 | Kalina Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | 8606 Goddard 345kV | San Patricio | COASTAL | 2026-07-01 | PV | 120 | 2020-08-04 | 2020-10-28 | 2021-03-29
ERCOT | 22INR0400 | Dragan Storage | SS Completed, FIS Started, No IA | Hecate Grid Dragan Storage LLC | 1440 Comanche 345kV | Comanche | NORTH | 2026-02-28 | BA | 408.3 | 2020-08-21 | 2020-11-04 | 2020-08-13
ERCOT | 22INR0401 | Eval Storage | SS Completed, FIS Started, IA | Hecate Grid East Valley Storage LLC | 80229 Cavazos 138kV | Cameron | COASTAL | 2028-12-31 | BA | 255 | 2020-10-23 | 2021-01-12 | 2020-11-03 |  |  | 2022-02-03
ERCOT | 22INR0402 | Frye Storage | SS Completed, FIS Started, No IA | Hecate Energy Frye Storage LLC | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2026-12-15 | BA | 503.85 | 2020-09-02 | 2020-11-19 | 2020-08-17 |  | No
ERCOT | 22INR0404 | Fence Post Solar | SS Completed, FIS Completed, IA | Fence Post Solar Project, LLC | tap 138kV 3127 Trinidad – 3483 Goodloe | Navarro | NORTH | 2024-11-29 | PV | 237.31 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2023-11-01 |  | 2021-08-12 | 2023-12-05
ERCOT | 22INR0408 | BRP Pular BESS | SS Completed, FIS Started, No IA | BRP Pular BESS LLC | 8963 Hidalgo Energy Center 138kV | Hidalgo | SOUTH | 2027-12-01 | BA | 233.1 | 2020-09-11 | 2021-06-10 | 2020-08-25
ERCOT | 22INR0409 | Stampede Solar | SS Completed, FIS Completed, IA | Stampede Solar Project, LLC | tap 345kV 1685 Farmersville - 11688 Thorn Tree ckt 1 | Hopkins | NORTH | 2025-01-10 | PV | 256.34 | 2020-11-05 | 2021-01-20 | 2020-10-21 | 2023-11-01 |  | 2021-12-15 | 2023-12-22
ERCOT | 22INR0417 | Amsterdam Storage | SS Completed, FIS Started, IA | Cottonwood Bayou II Storage, LLC | tap 345kV 43035 Oasis - 42500 Dow c27 | Brazoria | COASTAL | 2026-02-01 | BA | 201.13 | 2020-10-07 | 2020-12-30 | 2020-09-11 |  |  | 2022-04-14 |  |  | COD
ERCOT | 22INR0422 | Ferdinand Grid BESS | SS Completed, FIS Started, IA | Ferdinand Grid, LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2026-05-01 | BA | 201.2 | 2021-03-01 | 2021-05-12 | 2021-01-28 |  | No | 2022-11-28
ERCOT | 22INR0423 | Quela BESS | SS Completed, FIS Started, No IA | BRP Quela BESS LLC | Tap 138kV 5110 J.T. Deely - 5294 Martinez | Bexar | SOUTH | 2027-12-01 | BA | 301.41 | 2020-09-25 | 2020-12-16 | 2020-09-15
ERCOT | 22INR0424 | BRP Denali BESS | SS Completed, FIS Started, No IA | BRP Denali BESS LLC | Tap 138kV 5395 Sommers - 5030 Braunig East | Bexar | SOUTH | 2028-12-01 | BA | 258.41 | 2020-09-25 | 2020-12-16 | 2020-09-17
ERCOT | 22INR0425 | MAKALU SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green X LLC | Tap 138kV 977 Pruitt - 971 Greenville | Hunt | NORTH | 2026-04-15 | PV | 50.16 | 2021-01-21 | 2021-01-28 | 2021-08-10
ERCOT | 22INR0426 | LUBIO SOLAR | SS Completed, FIS Completed, IA | BDPU Solar Lubio LLC | tap 138kV 2727 Crandall - 2724 Kaufman Northwest | Kaufman | NORTH | 2026-02-01 | PV | 54.47 | 2020-10-07 | 2020-12-28 | 2021-06-28 | 2023-10-30 |  | 2024-11-08
ERCOT | 22INR0427 | BRP Kabru BESS | SS Completed, FIS Started, No IA | BRP Kabru BESS LLC | 1159 Andrew North - 11284 Blackbird 138kV | Andrews | WEST | 2025-12-01 | BA | 202.45 | 2020-10-07 | 2020-12-28 | 2020-09-22 |  | No
ERCOT | 22INR0437 | TORMES SOLAR | SS Completed, FIS Completed, IA | BDPU Solar Tormes LLC | tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2027-03-31 | PV | 382.12 | 2020-10-23 | 2021-01-12 | 2021-07-19 | 2023-10-19 |  | 2024-04-10 |  |  | SFS/NtP
ERCOT | 22INR0443 | Bowstring BESS | SS Completed, FIS Completed, No IA | Longbow Energy Storage, LLC | 8961 White Point 138kV | San Patricio | COASTAL | 2025-12-31 | BA | 155 | 2020-11-18 | 2021-02-09 | 2021-03-24 | 2023-05-30
ERCOT | 22INR0444 | Liberty Senate Solar 1 | SS Completed, FIS Completed, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2025-10-27 | PV | 202 | 2021-03-01 | 2021-05-13 | 2021-09-10 | 2023-03-31
ERCOT | 22INR0445 | SPC Bloom BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 2, LLC | 8911 Black Bayou 138kV | Victoria | SOUTH | 2024-12-01 | BA | 100 | 2020-12-03 | 2021-02-19 | 2020-11-13
ERCOT | 22INR0454 | DR Solar | SS Completed, FIS Started, IA | Delaware Ranch Solar, LLC | Delaware River SW (11112) | Culberson | WEST | 2026-02-15 | PV | 36 | 2020-12-22 | 2021-03-10 | 2020-12-17 |  |  | 2022-02-07
ERCOT | 22INR0455 | Blue Sky Sol | SS Completed, FIS Completed, IA | Blue Sky Solar LLC | 6562 Friends Ranch 138kV | Crockett | WEST | 2025-02-15 | PV | 101.2 | 2020-12-03 | 2021-02-16 | 2020-11-10 | 2023-07-05 | No | 2022-02-01
ERCOT | 22INR0457 | Anson BAT | SS Completed, FIS Started, IA | Anson II Storage LLC | tap 345 kV 68004 Phantom Hill station | Jones | WEST | 2026-05-29 | BA | 150.6 | 2020-12-03 | 2021-02-19 | 2022-02-23 |  |  | 2024-08-15 |  |  | MW Size
ERCOT | 22INR0462 | Old Aqueduct Solar | SS Completed, FIS Started, No IA | Old Aqueduct Solar | 23920 Blackwater 345kV | Hale | PANHANDLE | 2026-09-01 | PV | 511.63 | 2020-12-03 | 2021-02-19 | 2021-06-29
ERCOT | 22INR0466 | Pajarita BESS | SS Completed, FIS Started, No IA | VESI 29 LLC | 8266 Marconi 138kV | Cameron | COASTAL | 2026-06-01 | BA | 205.5 | 2021-01-25 | 2021-04-12 | 2021-12-01 |  | No
ERCOT | 22INR0467 | Bird Dog BESS | SS Completed, FIS Completed, IA | VESI 37 LLC | 5668 Mathis 69kV | Live Oak | SOUTH | 2025-12-11 | BA | 60.4 | 2021-02-04 | 2021-04-19 | 2022-05-19 | 2024-10-30 |  | 2024-02-16
ERCOT | 22INR0468 | Lower Rio BESS | SS Completed, FIS Completed, IA | VESI 38 LLC | 5792 Sioux 138kV | Hidalgo | SOUTH | 2025-03-31 | BA | 60.37 | 2021-02-09 | 2021-05-06 | 2021-11-08 | 2024-04-29 | No | 2023-07-10
ERCOT | 22INR0469 | Harper Energy Storage | SS Completed, FIS Started, No IA | VESI 31 LLC | Tap 138kV 8314 La Palma - 80229 Villa Cavazos | Cameron | COASTAL | 2026-02-02 | BA | 82.42 | 2021-12-03 | 2022-03-01 | 2022-01-27
ERCOT | 22INR0471 | MARATUA SOLAR | SS Completed, FIS Started, No IA | BDPU Solar Maratua, LLC | Tap 345kV 44645 Singleton – 44660 Skains Ckt 74 | Grimes | NORTH | 2026-12-30 | PV | 218 | 2020-12-03 | 2021-02-19 | 2021-08-13 |  | Yes
ERCOT | 22INR0473 | TAIN SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green VII LLC | tap 138kV 7216 Lockhart - 7224 Luling City | Caldwell | SOUTH | 2027-10-27 | PV | 37.54 | 2020-12-03 | 2021-02-17 | 2021-10-20
ERCOT | 22INR0480 | Pachanga Wind | SS Completed, FIS Started, No IA | Pachanga Wind LLC | tap 345kV 5966 Palmito - 80137 Stewart Rd | Cameron | COASTAL | 2027-04-01 | WT | 300 | 2021-02-09 | 2021-05-06 | 2021-04-05
ERCOT | 22INR0488 | Venture Hill Storage | SS Completed, FIS Started, No IA | KCE TX 24, LLC | 7336 Gilleland Creek 138kV | Travis | SOUTH | 2026-12-01 | BA | 70.44 | 2021-02-09 | 2021-05-06 | 2020-12-29
ERCOT | 22INR0494 | Quail Run Storage System | SS Completed, FIS Started, No IA | Quail Run Energy Partners, LP | 11016 Quail Switch 345kV | Ector | WEST | 2026-02-01 | BA | 51.56 | 2021-02-09 | 2021-05-06 | 2021-12-28
ERCOT | 22INR0497 | TEXPO | SS Completed, FIS Completed, No IA | Oklaunion Power Station, LLC | 6100 Oklaunion 345kV | Wilbarger | WEST | 2026-10-31 | ST | 680 | 2021-03-16 | 2021-05-28 | 2021-11-23 | 2024-09-17 | No
ERCOT | 22INR0499 | Aquilla Lake 3 Wind | SS Completed, FIS Started, IA | Aquilla Lake 3 Wind | tap 345 kV 68040 Kopperl to 68091 Navarro | Hill | NORTH | 2027-03-01 | WT | 304.6 | 2021-03-08 | 2021-05-28 | 2021-02-18 |  | Yes | 2024-01-24 |  |  | MW Size COD
ERCOT | 22INR0502 | Shamrock Wind SLF | SS Completed, FIS Completed, IA | Shamrock Interconnection LLC | Tap 345 kV 7053 Noelke - 76005 Schneeman | Crockett | WEST | 2025-01-31 | WT | 223.92 | 2021-03-01 | 2021-05-13 | 2021-02-24 | 2023-04-27 | No | 2022-05-13 | 2023-12-13 |  | COD
ERCOT | 22INR0503 | Tidwell Prairie II Batt | SS Completed, FIS Started, No IA | TIDWELL PRAIRIE II LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2025-12-01 | BA | 200 | 2021-03-16 | 2021-05-28 | 2021-02-17
ERCOT | 22INR0504 | Tidwell Prairie III Batt | SS Completed, FIS Started, No IA | Tidwell Prairie III LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2026-03-01 | BA | 200 | 2021-03-16 | 2021-05-28 | 2021-02-17
ERCOT | 22INR0506 | Roseland Solar II | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2025-01-31 | PV | 254 | 2021-10-05 | 2019-02-04 |  | 2021-10-25 |  | 2020-12-10 | 2022-09-26 |  | COD
ERCOT | 22INR0511 | Gransolar Texas One | SS Completed, FIS Completed, IA | Gransolar Texas One, LLC | Tap 138kV 3659 Thorndale North - 116 Salty | Milam | SOUTH | 2025-04-25 | PV | 50.8 | 2021-03-16 | 2021-06-11 | 2021-03-08 | 2022-01-24 | No | 2022-06-13 | 2024-12-23 |  | COD
ERCOT | 22INR0514 | Wang Storage SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2026-03-31 | BA | 0 | 2022-11-07 | 2023-02-03 | 2022-09-23
ERCOT | 22INR0515 | Flagtail BESS | SS Completed, FIS Started, No IA | Flagtail LLC | Tap 138kV 5 Sandy Switch - 7 Sandy | Grimes | NORTH | 2026-07-01 | BA | 203.8 | 2021-04-05 | 2021-06-24 | 2021-03-15 |  | No
ERCOT | 22INR0517 | Lane City Wind | SS Completed, FIS Completed, IA | RWE Clean Energy, LLC | 44040 Bailey 345kV | Wharton | SOUTH | 2025-06-30 | WT | 199.5 | 2021-04-26 | 2021-07-28 | 2021-04-26 | 2024-07-18 | No | 2022-05-13
ERCOT | 22INR0523 | Midlothian 4 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ANP 345kV | Ellis | NORTH | 2025-08-30 | GT | 18 | 2021-04-26 | 2021-07-28 | 2021-04-21
ERCOT | 22INR0525 | St. Gall II Energy Storage | SS Completed, FIS Completed, IA | St. Gall Energy Storage LLC | 38355 TNLeon Creek 138kV | Pecos | WEST | 2025-06-01 | BA | 100.24 | 2021-04-13 | 2021-07-02 | 2021-04-08 | 2024-10-22 | No | 2024-10-31
ERCOT | 22INR0526 | Pine Forest BESS | SS Completed, FIS Completed, IA | Pine Forest Hybrid I, LLC | tap 345kV 1696 Monticello SES - 2514 Allen Switch | Hopkins | NORTH | 2025-10-29 | BA | 200.74 | 2021-05-04 | 2021-07-30 | 2021-07-19 | 2024-12-18 |  | 2024-04-10
ERCOT | 22INR0533 | Temple Generation I Repower | SS Completed, FIS Completed, IA | Panda Temple Power | 3413 Knob Creek 345kV | Bell | NORTH | 2024-09-01 | CC | 67 | 2021-04-26 | 2021-05-13 | 2021-04-22 | 2021-09-30 |  | 2012-06-21
ERCOT | 22INR0540 | Walstrom BESS | SS Completed, FIS Completed, IA | Sealy Power LLC | 46220 Peters 138kV | Austin | SOUTH | 2025-04-15 | BA | 200 | 2021-07-08 | 2021-10-04 | 2021-06-03 | 2024-03-07 |  | 2023-06-30
ERCOT | 22INR0541 | ALWEST BESS | SS Completed, FIS Started, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2026-05-04 | BA | 208.63 | 2021-08-24 | 2021-11-15 | 2021-06-03
ERCOT | 22INR0543 | Midlothian Unit 3 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ELP 345kV | Ellis | NORTH | 2025-08-30 | GT | 18 | 2021-05-24 | 2021-08-06 | 2021-05-11
ERCOT | 22INR0546 | Enchanted Rock NEWPP | SS Completed, FIS Completed, IA | Generate ER-NG, LLC | 40475 Deusen 138kV | Harris | HOUSTON | 2025-06-06 | IC | 30 | 2021-11-10 | 2022-01-17 | 2022-07-13 | 2024-04-19 | No | 2024-04-30
ERCOT | 22INR0549 | Tanzanite Storage | SS Completed, FIS Completed, IA | Tanzanite Energy Storage LLC | 6867 NORTH ATHENS 138kV | Henderson | NORTH | 2025-03-20 | BA | 265.8 | 2021-09-01 | 2021-11-18 | 2021-08-16 | 2023-12-14 | No | 2022-07-15
ERCOT | 22INR0552 | Sowers Storage | SS Completed, FIS Started, IA | Sowers Energy Storage LLC | 6894 Rose Hill_RC Sub 138 kV | Kaufman | NORTH | 2026-04-10 | BA | 204.96 | 2021-08-18 | 2021-11-05 | 2021-08-18 |  | No | 2022-04-22
ERCOT | 22INR0554 | Platinum Storage | SS Completed, FIS Completed, IA | Platinum Energy Storage LLC | 1729 Valley South 345kV | Fannin | NORTH | 2025-03-03 | BA | 309.53 | 2021-09-02 | 2021-11-18 | 2021-08-31 | 2024-07-31 | No | 2022-11-17
ERCOT | 22INR0555 | TE Smith Storage | SS Completed, FIS Completed, IA | BT Smith Storage, LLC | 2483 Royse Switch 345kV | Rockwall | NORTH | 2025-07-15 | BA | 125.36 | 2021-09-02 | 2021-11-18 | 2021-08-26 | 2024-05-16 | No | 2023-11-08
ERCOT | 22INR0558 | Callisto II Energy Center | SS Completed, FIS Started, IA | Callisto II Energy Center LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2025-12-10 | BA | 406.06 | 2021-10-07 | 2021-12-08 | 2021-09-29 |  |  | 2023-12-11
ERCOT | 22INR0559 | Honeycomb Solar SLF | SS Completed, FIS Started, IA | Honeycomb Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2026-03-03 | PV | 61.1 | 2021-11-16 | 2022-01-17 | 2021-11-02 |  | No | 2023-05-01 |  |  | COD
ERCOT | 22INR0586 | Hays Energy Unit 2 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Haysen 345kV | Hays | SOUTH | 2025-08-30 | GT | 18 | 2022-02-21 | 2022-05-21 | 2022-11-15
ERCOT | 22INR0605 | Camino Santiago Solar | SS Completed, FIS Completed, IA | Camino Solar Project, LLC | Tap 345kV 3687 Bell County East Switch – 39950 TNP One Plant Ckt 2 (North Circuit). | Milam | SOUTH | 2027-02-18 | PV | 196.3 | 2022-09-02 | 2022-11-30 |  | 2024-09-05 | No | 2024-12-06 |  |  | COD
ERCOT | 23INR0006 | Sierra Madre Solar | SS Completed, FIS Started, No IA | Sierra Madre Solar LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2027-12-01 | PV | 255.15 | 2020-01-22 | 2020-04-08 | 2020-10-05 |  | No
ERCOT | 23INR0007 | Outpost Solar | SS Completed, FIS Completed, IA | Hecate Energy Outpost Solar LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2025-09-05 | PV | 517.3 | 2019-12-06 | 2020-02-25 | 2019-12-02 | 2024-02-01 | No | 2022-01-11 |  |  | COD
ERCOT | 23INR0008 | Harley Hand Solar | SS Completed, FIS Started, No IA | HECTATE ENERGY HARLEY HAND SOLAR LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2025-08-01 | PV | 513.7 | 2019-12-16 | 2020-03-11 | 2019-12-06 |  | No
ERCOT | 23INR0009 | Shaula III Solar | SS Completed, FIS Started, No IA | Shaula Energy Project III, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2025-12-24 | PV | 205.2 | 2019-12-18 | 2020-03-11 | 2019-12-18
ERCOT | 23INR0010 | Plateau Solar | SS Completed, FIS Started, No IA | Innovative Solar 206, LLC | tap 345kV 68000 West Shackelford - 68001 Claytonville | Jones | WEST | 2025-05-31 | PV | 300 | 2019-12-06 | 2020-02-25 | 2020-08-20 |  | No
ERCOT | 23INR0015 | Scarlet Solar | SS Completed, FIS Started, No IA | Innovative Solar 416, LLC | tap 345kV 23912 Ogallala - 23910 Windmill | Castro | PANHANDLE | 2025-08-26 | PV | 180 | 2019-12-11 | 2020-03-06 | 2020-08-31
ERCOT | 23INR0021 | Hornet Solar | SS Completed, FIS Completed, IA | Hornet Solar LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2025-04-30 | PV | 602.37 | 2020-02-04 | 2020-04-29 | 2020-02-04 | 2021-10-06 | No | 2021-12-06 | 2024-08-21
ERCOT | 23INR0026 | Baker Branch Solar | SS Completed, FIS Completed, IA | Mockingbird Solar Center, LLC | tap 345kV 1692 Paris - 1690 Valley | Lamar | NORTH | 2025-03-31 | PV | 469.42 | 2020-03-26 | 2020-06-04 | 2020-03-05 | 2023-10-30 |  | 2022-02-14 | 2024-04-10 |  | COD
ERCOT | 23INR0027 | Cachena Solar SLF | SS Completed, FIS Completed, IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elm Creek - 5323 Old Hickory | Wilson | SOUTH | 2027-04-29 | PV | 600 | 2020-05-01 | 2020-07-13 | 2020-08-17 | 2023-10-02 | No | 2021-11-23
ERCOT | 23INR0029 | Cedar Bayou 5 | SS Completed, FIS Started, IA | NRG Cedar Bayou 5 LLC | 40000 Cedar Bayou 345kV | Chambers | HOUSTON | 2027-12-15 | CC | 697 | 2020-03-26 | 2020-06-04 | 2020-03-18 |  | Yes | 2022-01-10
ERCOT | 23INR0030 | Langer Solar | SS Completed, FIS Started, IA | Langer Solar LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2027-03-01 | PV | 249.8 | 2020-06-03 | 2020-08-18 | 2020-10-30 |  | Yes | 2023-08-31
ERCOT | 23INR0031 | Solace Solar | SS Completed, FIS Completed, IA | IP QUANTUM, LLC. | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2026-03-31 | PV | 374.4 | 2020-04-22 | 2020-07-09 | 2020-04-03 | 2023-10-26 |  | 2024-01-30
ERCOT | 23INR0035 | Starling Solar | SS Completed, FIS Started, IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2027-05-15 | PV | 123 | 2020-06-26 | 2020-09-14 | 2021-01-22 |  |  | 2021-12-03
ERCOT | 23INR0040 | Dori BQ Solar | SS Completed, FIS Started, IA | Sunnyside Energy, LLC | tap 138kV 47210 Holmes – 42680 Garden Villas | Harris | HOUSTON | 2025-11-30 | PV | 50.42 | 2020-06-09 | 2020-08-18 | 2021-01-29 |  | No | 2022-12-01 |  |  | COD
ERCOT | 23INR0044 | Parliament Solar | SS Completed, FIS Completed, IA | Parliament Solar LLC | Tap 345kV 44900 Zenith - 967 Gibbons Creek ckt 18 | Waller | HOUSTON | 2025-05-12 | PV | 484.56 | 2020-06-19 | 2020-09-08 | 2020-06-08 | 2024-04-25 | No | 2022-05-26
ERCOT | 23INR0045 | GP Solar | SS Completed, FIS Completed, IA | HEP Aquamarine Holdings LLC | Tap 138kV 6829 Glen Pine - 6833 Explorer | Van Zandt | NORTH | 2025-05-15 | PV | 121.97 | 2020-09-25 | 2020-12-16 | 2021-02-22 | 2021-11-10 | No | 2021-12-29
ERCOT | 23INR0047 | Charger Solar | SS Completed, FIS Completed, IA | AP Solar 4, LLC | tap 345kV 8249 Angstrom – 5915 STP | Refugio | COASTAL | 2026-06-05 | PV | 397.15 | 2020-06-19 | 2020-09-08 | 2020-06-07 | 2022-04-04 | No | 2021-06-05
ERCOT | 23INR0048 | Equinox Storage | SS Completed, FIS Started, No IA | Invenergy Storage Development LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2026-12-30 | BA | 101.2 | 2020-06-26 | 2020-09-14 | 2021-03-12
ERCOT | 23INR0054 | Tanglewood Solar | SS Completed, FIS Completed, IA | Brazoria Solar, LLC | 345kV Seabreeze Substation | Brazoria | COASTAL | 2025-09-08 | PV | 250.96 | 2020-07-10 | 2020-09-28 | 2020-11-24 | 2024-06-03 | Yes | 2022-11-01
ERCOT | 23INR0055 | Tabor Solar | SS Completed, FIS Started, No IA | Quanah Solar LLC | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2027-04-16 | PV | 506.4 | 2020-09-02 | 2020-11-19 | 2020-07-07 |  | No
ERCOT | 23INR0056 | Caliche Mound Solar | SS Completed, FIS Completed, IA | Tierra Blanco Solar LLC | tap 345kV 23906 AJSwope - 23910 Windmill | Deaf Smith | PANHANDLE | 2025-08-28 | PV | 408.21 | 2020-07-24 | 2020-09-08 | 2020-07-07 | 2023-08-22 |  | 2023-10-12
ERCOT | 23INR0057 | Duffy Solar | SS Completed, FIS Started, IA | VDA Solar Texas 1 LLC | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | Matagorda | COASTAL | 2027-12-31 | PV | 502.46 | 2020-09-11 | 2020-11-19 | 2021-02-04 |  | Yes | 2023-04-12
ERCOT | 23INR0058 | Erin Solar | SS Completed, FIS Completed, IA | Erin Solar LLC | 44040 Bailey 345 kV | Wharton | SOUTH | 2027-11-30 | PV | 202.5 | 2020-07-24 | 2020-10-08 | 2021-01-26 | 2022-05-24 | No | 2023-03-22
ERCOT | 23INR0059 | Briggs Solar | SS Completed, FIS Started, No IA | Briggs Solar, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2027-09-15 | PV | 309.6 | 2020-08-04 | 2020-10-28 | 2021-03-04
ERCOT | 23INR0061 | Noria Solar DCC | SS Completed, FIS Started, IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2026-10-13 | PV | 145 | 2020-08-04 | 2020-10-28 | 2021-03-10 |  |  | 2022-10-12
ERCOT | 23INR0062 | Noria Storage | SS Completed, FIS Started, IA | Noria Hondo Solar, LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2026-10-13 | BA | 75 | 2020-08-04 | 2020-10-28 | 2021-03-30 |  |  | 2022-10-12
ERCOT | 23INR0066 | Accalia Point Solar | SS Completed, FIS Completed, No IA | Accalia Point Solar LLC | Tap 345kV 8383 North Edingburg – 79501 Kingfisher | Cameron | COASTAL | 2027-05-31 | PV | 190.5 | 2020-10-23 | 2021-01-12 | 2021-01-27 | 2024-07-03 | No
ERCOT | 23INR0070 | Chillingham Solar | SS Completed, FIS Completed, IA | Chillingham Solar LLC | 3687 Bell County East 345kV | Bell | NORTH | 2024-12-30 | PV | 352.39 | 2020-08-04 | 2020-10-28 | 2020-08-26 | 2024-01-26 | No | 2022-02-04 | 2024-09-04
ERCOT | 23INR0071 | BRP Volans BESS | SS Completed, FIS Started, No IA | BRP Volans BESS LLC | 11189 Quarry Field SW - 1074 Wink 138kV | Winkler | WEST | 2027-12-01 | BA | 206.88 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  | No
ERCOT | 23INR0072 | Tortolas BESS | SS Completed, FIS Completed, IA | BRP Tortolas BESS LLC | 39030 Alvin 138kV | Brazoria | COASTAL | 2024-10-29 | BA | 50.3 | 2020-08-04 | 2020-10-28 | 2020-08-24 | 2021-07-30 |  | 2021-07-15 | 2024-06-05
ERCOT | 23INR0073 | BRP Galan BESS | SS Completed, FIS Started, No IA | BRP Galan BESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2027-12-01 | BA | 75.97 | 2020-08-04 | 2020-10-28 | 2020-08-17
ERCOT | 23INR0074 | BRP Ampato BESS | SS Completed, FIS Started, No IA | BRP Ampato BESS LLC | 10002 NS Crane Switch 138kV | Crane | WEST | 2027-12-01 | BA | 121.56 | 2020-08-04 | 2020-10-28 | 2020-08-24
ERCOT | 23INR0075 | BRP Rhine BESS | SS Completed, FIS Started, No IA | BRP Rhine BESS LLC | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | Ward | WEST | 2025-12-01 | BA | 206.89 | 2020-08-04 | 2020-11-02 | 2020-09-17
ERCOT | 23INR0076 | Cannon Solar SLF | SS Completed, FIS Started, No IA | Cannon Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2027-12-31 | PV | 80 | 2020-09-11 | 2020-12-07 | 2020-09-11
ERCOT | 23INR0077 | Cachena Storage SLF | SS Completed, FIS Started, No IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elmcreek - 5323 Old Hickory | Wilson | SOUTH | 2027-04-29 | BA | 0 | 2020-08-21 | 2020-10-16 | 2020-08-17
ERCOT | 23INR0078 | Shaw Solar | SS Completed, FIS Started, No IA | Rio Lago Solar, LLC | Tap 138kV 7146 Verde Creek - 7438 Bandera | Bandera | SOUTH | 2025-09-12 | PV | 124.65 | 2020-10-23 | 2021-01-12 | 2021-05-11
ERCOT | 23INR0079 | Chillingham Storage | SS Completed, FIS Completed, IA | Chillingham Storage LLC | 3687 Bell County East 345kV | Bell | NORTH | 2025-08-02 | BA | 153.93 | 2020-09-11 | 2020-11-30 | 2020-08-26 | 2021-07-22 |  | 2022-02-04
ERCOT | 23INR0082 | Bottom Grass Solar | SS Completed, FIS Started, IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-12-01 | PV | 508.61 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  | 2023-06-29
ERCOT | 23INR0083 | Bottom Grass BESS | SS Completed, FIS Started, IA | Bottom Grass Solar Project, LLC | tap 345 kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-12-01 | BA | 202.21 | 2020-11-05 | 2021-02-02 | 2020-10-21 |  |  | 2023-06-29
ERCOT | 23INR0084 | Lavaca Bay Solar | SS Completed, FIS Completed, IA | TC Energy Solar LLC | tap 345 kV REFUGE 42400 - JONES CREEK 47532 ckt 27 | Matagorda | COASTAL | 2026-12-31 | PV | 243.46 | 2020-09-11 | 2020-11-19 | 2021-03-05 | 2022-03-21 | Yes | 2022-06-15
ERCOT | 23INR0086 | Hanson Solar | SS Completed, FIS Started, IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2027-04-17 | PV | 400.58 | 2020-10-23 | 2021-02-02 | 2021-03-25 |  |  | 2023-09-20
ERCOT | 23INR0087 | Kinenos Solar | SS Completed, FIS Started, No IA | Encino del Sol Energy, LLC | tap 345kV 8905 North Edinburg - 8455 Lon Hill | Brooks | SOUTH | 2026-12-31 | PV | 203.17 | 2020-12-22 | 2021-03-10 | 2020-12-03 |  | No
ERCOT | 23INR0088 | Nockenut Springs Solar 1 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2027-05-05 | PV | 203.17 | 2020-09-25 | 2020-12-16 | 2020-09-11
ERCOT | 23INR0089 | Donegal Solar | SS Completed, FIS Started, IA | Greenalia Solar Power Donegal, LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2027-03-01 | PV | 201.68 | 2020-10-07 | 2020-12-28 | 2020-09-11 |  |  | 2022-07-25
ERCOT | 23INR0090 | Iguala Solar | SS Completed, FIS Started, No IA | Iguala Solar LLC | tap 345kV 5915 STP - 8249 Angstrom | Victoria | SOUTH | 2025-12-31 | PV | 250 | 2020-10-07 | 2020-12-28 | 2021-06-07 |  | Yes
ERCOT | 23INR0091 | Cascade Solar | SS Completed, FIS Started, IA | Cascade Solar Energy, LLC | 345kV Oasis (43035) – Seabreeze (43020) circuit 27 | Brazoria | COASTAL | 2026-02-16 | PV | 175 | 2021-02-09 | 2021-05-06 | 2021-04-28 |  | No | 2023-04-17
ERCOT | 23INR0093 | Alila Solar | SS Completed, FIS Completed, IA | Electra Energy Project, LLC | 8249 Angstrom 345kV | San Patricio | COASTAL | 2026-05-15 | PV | 256.5 | 2020-10-07 | 2020-12-30 | 2020-09-11 | 2023-03-16 | No | 2023-01-03
ERCOT | 23INR0094 | BRP Pyxis BESS | SS Completed, FIS Completed, No IA | BRP Pyxis BESS LLC | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | Ward | WEST | 2025-12-01 | BA | 206.87 | 2020-09-25 | 2020-12-16 | 2020-09-11 | 2021-09-23
ERCOT | 23INR0101 | Atria Solar | SS Completed, FIS Completed, No IA | Atria Energy Project, LLC | 40770 Hacher 138kV | Chambers | HOUSTON | 2025-12-30 | PV | 112.4 | 2020-10-23 | 2021-01-12 | 2020-09-28 | 2021-12-15
ERCOT | 23INR0103 | Burksol BESS | SS Completed, FIS Completed, IA | Burksol LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2025-03-12 | BA | 103.27 | 2020-10-23 | 2021-01-12 | 2020-09-28 | 2024-02-29 | No | 2022-11-17 | 2024-12-20
ERCOT | 23INR0104 | BRP Kamet BESS | SS Completed, FIS Started, No IA | BRP Kamet BESS LLC | Andrews North – McKenzie Draw Switch 138 kV | Andrews | WEST | 2025-12-01 | BA | 202.46 | 2020-10-07 | 2020-12-30 | 2020-09-23 |  | No
ERCOT | 23INR0111 | PHOTON SOLAR 3 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2024-12-10 | PV | 109.99 | 2020-10-23 | 2021-02-02 | 2020-11-24 | 2022-11-28 | No | 2021-10-01 | 2024-10-02
ERCOT | 23INR0113 | Cannon Storage SLF | SS Completed, FIS Started, No IA | Cannon Solar, LLC | Tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2027-12-31 | BA | 0 | 2020-11-05 | 2020-12-07 | 2020-10-29
ERCOT | 23INR0115 | BRP Pobeda BESS | SS Completed, FIS Started, No IA | BRP Pobeda BESS LLC | 44645 Singleton 345kV | Grimes | NORTH | 2024-12-01 | BA | 301.41 | 2020-11-18 | 2021-02-08 | 2020-10-27
ERCOT | 23INR0116 | Cantaloupe Solar | SS Completed, FIS Started, IA | Saragosa Del Sol Energy, LLC | 60716 Saragosa 138kV | Reeves | WEST | 2028-07-01 | PV | 303.13 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  | 2024-04-23
ERCOT | 23INR0117 | Cantaloupe Storage | SS Completed, FIS Started, IA | Saragosa Del Sol Energy, LLC | 60716 Saragosa 138kV | Reeves | WEST | 2028-07-01 | BA | 251.05 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  | 2024-04-23
ERCOT | 23INR0118 | Blevins Solar | SS Completed, FIS Completed, IA | Blevins Solar, LLC | Tap Bellfalls Switch (3404) – Lake Creek Switch (3409) | Falls | NORTH | 2025-10-30 | PV | 271.58 | 2021-02-04 | 2021-04-19 | 2021-02-12 | 2024-06-24 |  | 2023-06-17
ERCOT | 23INR0119 | Blevins Storage | SS Completed, FIS Completed, IA | Blevins Solar, LLC | Tap Bellfalls Switch (3404) – Lake Creek Switch (3409) | Falls | NORTH | 2025-07-27 | BA | 181.33 | 2021-02-04 | 2021-04-19 | 2021-02-12 | 2024-06-24 |  | 2023-06-17
ERCOT | 23INR0123 | Vaca Storage | SS Completed, FIS Started, No IA | Long Mount Storage, LLC | 138kV 8723 Cangrejo | Calhoun | COASTAL | 2027-06-01 | BA | 101 | 2021-03-26 | 2021-06-14 | 2022-05-11 |  | No
ERCOT | 23INR0126 | Sigma Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40460 Deepwater 138kV | Harris | HOUSTON | 2026-05-15 | BA | 408.4 | 2021-05-11 | 2021-07-30 | 2022-02-04 |  | No
ERCOT | 23INR0127 | Beacon Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40450 Deepwater 345kV | Harris | HOUSTON | 2026-05-15 | BA | 408.7 | 2021-05-05 | 2021-07-27 | 2022-02-28 |  | No
ERCOT | 23INR0131 | BRP Batura BESS | SS Completed, FIS Started, No IA | BRP Batura BESS LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2025-12-01 | BA | 251.65 | 2020-12-03 | 2021-02-16 | 2020-11-12
ERCOT | 23INR0132 | BRP Bonete BESS | SS Completed, FIS Started, No IA | BRP Bonete BESS LLC | 8951 Stewart Road 138kV | Hidalgo | SOUTH | 2027-12-01 | BA | 201.13 | 2020-12-03 | 2021-02-16 | 2020-11-18 |  | No
ERCOT | 23INR0135 | Elbus BESS | SS Completed, FIS Started, No IA | BRP Elbus BESS LLC | 9075 Lytton 138kV | Caldwell | SOUTH | 2027-12-01 | BA | 200.99 | 2020-12-03 | 2021-02-18 | 2020-11-25 | [5 empty] | Proj Name MW Size COD
ERCOT | 23INR0137 | BRP Diran BESS | SS Completed, FIS Completed, No IA | BRP Diran BESS LLC | 43190 South Lane City 138kV | Wharton | SOUTH | 2028-01-31 | BA | 100.63 | 2020-12-03 | 2021-02-18 | 2020-11-25 | 2022-04-15 | No |  |  |  | COD
ERCOT | 23INR0139 | BRP Passu BESS | SS Completed, FIS Started, No IA | BRP Passu BESS LLC | 6111 Riley 345kV | Wilbarger | WEST | 2024-12-01 | BA | 301.82 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No
ERCOT | 23INR0140 | Seine BESS | SS Completed, FIS Started, No IA | BRP Seine BESS LLC | 60500 Edith Clarke 345kV | Foard | WEST | 2027-12-01 | BA | 301.19 | 2020-12-03 | 2021-02-19 | 2020-11-27 |  | No
ERCOT | 23INR0143 | BRP Sepik BESS | SS Completed, FIS Started, No IA | BRP Sepik BESS LLC | tap 138kV 11342 Loraine South – 10050 Ranger Camp | Mitchell | WEST | 2028-03-01 | BA | 200.85 | 2020-12-22 | 2021-03-15 | 2020-12-01
ERCOT | 23INR0144 | Galactic Solar | SS Completed, FIS Completed, IA | UKA North America, LLC | Tap 138kV 1744 Gordonville - 11704 Sherman West | Grayson | NORTH | 2027-03-10 | PV | 205.2 | 2020-12-22 | 2021-03-10 | 2020-12-01 | 2021-12-21 | No | 2022-08-12
ERCOT | 23INR0150 | Cradle Solar | SS Completed, FIS Started, IA | Cradle Solar LLC | tap 345kV 42500 Dow - 43035 Oasis ckt 18 | Brazoria | COASTAL | 2025-12-31 | PV | 200.85 | 2021-02-04 | 2021-04-21 | 2021-03-15 |  | No | 2023-03-15
ERCOT | 23INR0153 | Mercury II Solar SLF | SS Completed, FIS Completed, IA | Mercury II Solar, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2025-01-31 | PV | 206.11 | 2021-01-26 | 2021-04-12 | 2020-12-11 | 2021-10-14 |  | 2021-10-18 | 2023-10-31 |  | COD
ERCOT | 23INR0160 | Grimes County Solar | SS Completed, FIS Completed, IA | Grimes County Solar Project, LLC | 2 Keith Switch 138kV | Grimes | NORTH | 2025-06-15 | PV | 211.25 | 2021-01-26 | 2021-04-12 | 2020-12-16 | 2024-06-17 | No | 2022-06-22
ERCOT | 23INR0162 | Redonda Solar | SS Completed, FIS Started, IA | J&R Power DevCo, LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2026-12-30 | PV | 253.21 | 2021-01-25 | 2021-04-12 | 2021-08-11 |  |  | 2021-12-28
ERCOT | 23INR0163 | Ringtail Ridge Storage | SS Completed, FIS Started, No IA | KCE TX 26, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2028-05-23 | BA | 100.57 | 2021-01-25 | 2021-04-16 | 2020-12-29
ERCOT | 23INR0164 | Steppe Reserve Storage | SS Completed, FIS Started, No IA | KCE TX 25, LLC | 8283 Asherton 138 kV | Dimmit | SOUTH | 2028-01-01 | BA | 51.9 | 2021-01-25 | 2021-04-16 | 2020-12-29
ERCOT | 23INR0166 | Great Kiskadee Storage | SS Completed, FIS Completed, IA | Great Kiskadee Storage, LLC | 8951 Stewart Rd 138kV | Hidalgo | SOUTH | 2025-01-03 | BA | 103.05 | 2021-01-26 | 2021-04-12 | 2021-08-24 | 2023-10-24 |  | 2022-06-30 | 2024-09-20 |  | COD
ERCOT | 23INR0168 | Charolais Storage | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | tap 345kV 44000 W A Parish - 5915 STP | Matagorda | COASTAL | 2026-12-15 | BA | 150 | 2021-02-09 | 2021-05-06 | 2021-06-11
ERCOT | 23INR0171 | Goodalta Solar | SS Completed, FIS Started, No IA | GoodAlta Power Center LLC | tap 138kV 3127 Trinidad - 212 Winkler | Navarro | NORTH | 2027-04-17 | PV | 220 | 2021-01-25 | 2021-04-12 | 2021-01-07 |  | No
ERCOT | 23INR0174 | Campsey Wind | SS Completed, FIS Started, No IA | RWE | tap 345kV 1458 Cobb - 1429 Jacksboro | Jack | NORTH | 2028-06-01 | WT | 238.3 | 2021-02-09 | 2021-05-06 | 2021-09-01
ERCOT | 23INR0180 | Jackalope Solar | SS Completed, FIS Completed, IA | Peacock Energy Project, LLC | 8173 Gibbs 138kV | San Patricio | COASTAL | 2024-12-10 | PV | 155.68 | 2021-02-09 | 2021-05-06 | 2021-02-02 | 2021-11-18 |  | 2021-09-30 | 2024-09-19 |  | COD
ERCOT | 23INR0181 | Starling Storage | SS Completed, FIS Completed, IA | Starling Storage, LLC | tap 138kV 7224 Luling - 7245 Gonzales | Gonzales | SOUTH | 2027-05-15 | BA | 63.6 | 2021-01-25 | 2021-04-16 | 2021-10-07 | 2023-07-31 | No | 2023-08-03
ERCOT | 23INR0183 | Pradera Storage | SS Completed, FIS Started, No IA | Pradera Storage, LLC | tap 345 kV Lobo 80219 - Fowlerton 5709 ckt #2 | Webb | SOUTH | 2027-03-31 | BA | 153.11 | 2021-01-25 | 2021-04-16 | 2021-10-13
ERCOT | 23INR0187 | Leitrim 1 Solar | SS Completed, FIS Started, No IA | Leitsol LLC | tap 138kV 3522 Hillsboro - 3546 Whitney | Hill | NORTH | 2027-04-26 | PV | 98.44 | 2021-01-26 | 2021-04-12 | 2021-03-18 |  | No
ERCOT | 23INR0190 | Cosmos Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | tap 345kV 9073 Holman - 44200 Hillje | Wharton | SOUTH | 2024-12-01 | PV | 609.74 | 2021-03-01 | 2021-05-13 | 2021-03-01
ERCOT | 23INR0194 | Pequin Energy Storage | SS Completed, FIS Started, No IA | Pequin Energy Storage, LLC | 39500 TN West Columbia 138kV | Brazoria | COASTAL | 2026-12-31 | BA | 103.4 | 2021-01-25 | 2021-04-16 | 2021-06-14
ERCOT | 23INR0195 | Desert Willow BESS | SS Completed, FIS Completed, IA | Desert Willow Energy Storage, LLC | tap 345kV 1906 Venus_S5 - 1916 LiggettA1_5 | Ellis | NORTH | 2025-03-20 | BA | 154.4 | 2021-02-04 | 2021-04-22 | 2021-06-14 | 2024-03-09 | No | 2023-05-15 |  |  | COD
ERCOT | 23INR0200 | Paradiso BESS | SS Completed, FIS Started, No IA | VESI 13 | 8203 Pleasanton 138kV | Atascosa | SOUTH | 2027-08-01 | BA | 100.92 | 2021-03-01 | 2021-05-13 | 2021-08-20 |  | No
ERCOT | 23INR0202 | Erath County Solar | SS Completed, FIS Started, IA | Erath County Solar, LLC | tap 345kV 68020 Romney1E - 68030 KopperlW | Erath | NORTH | 2026-08-27 | PV | 207.4 | 2021-03-08 | 2021-05-28 | 2021-03-06 |  | Yes | 2023-06-01
ERCOT | 23INR0204 | GALVANIC BESS | SS Completed, FIS Started, No IA | CED Development Inc | 8252 Bracketville 138kV | Kinney | SOUTH | 2026-12-30 | BA | 100 | 2021-02-09 | 2021-05-06 | 2022-05-13 | [5 empty] | COD
ERCOT | 23INR0205 | SUNSETTER BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2025-11-30 | BA | 100 | 2021-02-09 | 2021-05-06 | 2022-05-13
ERCOT | 23INR0206 | PEREGRINE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | tap 345kV 8624 Grissom - 8164 Coleto Creek | Goliad | SOUTH | 2027-07-01 | BA | 150 | 2021-02-10 | 2021-05-06 | 2022-05-13
ERCOT | 23INR0207 | El Patrimonio Solar | SS Completed, FIS Completed, IA | Heritage Solar LLC | tap 138kV 5429 Trumbo - 5260 Leon Creek | Bexar | SOUTH | 2026-09-23 | PV | 152.32 | 2021-03-16 | 2021-05-28 | 2021-11-23 | 2024-10-17 | No | 2023-12-11
ERCOT | 23INR0209 | Outpost Storage | SS Completed, FIS Started, No IA | Hecate Energy Outpost Storage LLC | Tap 345kV 80219 Lobo - 5709 Fowlerton | Webb | SOUTH | 2026-05-30 | BA | 508.1 | 2021-03-01 | 2021-05-13 | 2021-02-15
ERCOT | 23INR0211 | Rosscommon Solar | SS Completed, FIS Started, No IA | Roscsol, LLC | tap 138kV 1691 Valley Switch - 1776 Paris Switch | Lamar | NORTH | 2027-04-19 | PV | 91 | 2021-03-01 | 2021-05-13 | 2021-02-01
ERCOT | 23INR0214 | Harley Hand Storage | SS Completed, FIS Started, No IA | Hecate Energy Harley Hand Solar LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2025-08-01 | BA | 509 | 2021-03-01 | 2021-05-13 | 2022-03-22
ERCOT | 23INR0215 | Big River Solar | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2028-12-31 | PV | 104.35 | 2021-05-04 | 2021-07-27 | 2021-04-15 | [5 empty] | COD
ERCOT | 23INR0216 | Venus Mill Storage | SS Completed, FIS Started, No IA | KCE TX 14, LLC | 138 kV Tap #442 Rail Port - #1905 Griffith | Ellis | NORTH | 2026-01-20 | BA | 100.8 | 2022-03-14 | 2022-06-09 | 2022-03-04 |  | No
ERCOT | 23INR0219 | Dogfish BESS | SS Completed, FIS Completed, IA | Dogfish ESS Assets, LLC | tap 138kV 38331 TN Alamo St – 38455 TN Holiday | Pecos | WEST | 2025-04-16 | BA | 78.2 | 2021-03-16 | 2021-05-28 | 2021-09-14 | 2024-07-31 | No | 2023-06-01
ERCOT | 23INR0220 | HOPSLAM BESS | SS Completed, FIS Started, No IA | Momentum LRC Holdco LLC | 38430 White Baker TNP 138kV | Pecos | WEST | 2025-09-20 | BA | 151.11 | 2021-03-16 | 2021-05-28 | 2021-11-09
ERCOT | 23INR0222 | Sunbelt Solar | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | tap 138kV 6902 Talty - 6801 Patton | Kaufman | NORTH | 2026-12-31 | PV | 81.5 | 2021-03-16 | 2021-05-28 | 2021-09-30
ERCOT | 23INR0223 | Garcitas Creek Solar | SS Completed, FIS Started, IA | Garcitas Creek Solar LLC | Tap 345 kV 5915 South Texas Project – 8249 Angstrom | Jackson | SOUTH | 2026-12-30 | PV | 201.94 | 2021-10-05 | 2021-12-08 | 2021-10-08 |  |  | 2022-06-30
ERCOT | 23INR0224 | Morning Glory Solar | SS Completed, FIS Started, No IA | Armadillo Solar, LLC | tap 345kV 7077 Amos Creek - 76009 Twin Buttes | Tom Green | WEST | 2026-03-31 | PV | 122.4 | 2021-06-16 | 2021-09-07 | 2022-05-17
ERCOT | 23INR0225 | MRG GOODY SOLAR | SS Completed, FIS Completed, IA | MRG GOODY SOLAR PROJECT, LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2025-07-07 | PV | 171.72 | 2021-03-16 | 2021-06-11 | 2022-03-22 | 2023-11-21 |  | 2023-11-07
ERCOT | 23INR0227 | Maleza Solar II | SS Completed, FIS Started, No IA | Brush Solar, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2025-11-01 | PV | 254.94 | 2021-04-06 | 2021-06-24 | 2021-05-19
ERCOT | 23INR0228 | Hiru Solar | SS Completed, FIS Completed, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2026-05-29 | PV | 614.4 | 2021-04-21 | 2021-07-14 | 2021-08-30 | 2023-05-18 | No
ERCOT | 23INR0229 | CH Solterra LLC | SS Completed, FIS Started, No IA | CH Solterra LLC | Tap 138kV 11796 White Oak POI - 11797 Brinker POI | Hopkins | NORTH | 2026-09-30 | PV | 143 | 2021-03-19 | 2021-06-11 | 2021-03-18 |  | No |  |  |  | COD
ERCOT | 23INR0231 | Rocinante Solar | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2026-05-18 | PV | 95.29 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  | No | 2022-04-25
ERCOT | 23INR0232 | Rocinante BESS | SS Completed, FIS Started, IA | Brush Country Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2026-05-18 | BA | 33.17 | 2021-04-22 | 2021-07-14 | 2021-04-22 |  | No | 2022-04-25
ERCOT | 23INR0233 | Earthwise Solar | SS Completed, FIS Started, No IA | Quanah Solar 2 | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2026-12-31 | PV | 370.5 | 2022-03-14 | 2022-06-09 | 2022-02-25
ERCOT | 23INR0234 | Chiltepin Solar | SS Completed, FIS Started, No IA | Chiltepin Solar-Storage, LLC | 6673 Musquiz 138kV | Reeves | WEST | 2025-06-30 | PV | 200 | 2021-04-22 | 2021-07-14 | 2021-10-31
ERCOT | 23INR0235 | Hoyte Solar | SS Completed, FIS Completed, IA | Milano Solar, LLC | (3707) Cannon Switch 138kV | Milam | SOUTH | 2026-03-31 | PV | 206.75 | 2021-04-01 | 2021-07-02 | 2021-03-25 | 2022-06-07 | No | 2022-10-14
ERCOT | 23INR0237 | Big River BESS | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2028-12-31 | BA | 51.26 | 2021-05-04 | 2021-07-27 | 2021-04-15
ERCOT | 23INR0244 | Tiger Solar | SS Completed, FIS Started, IA | Vaca Del Sol, LLC | 68004 PHANTOM HILL 345KV | Jones | WEST | 2027-06-30 | PV | 255 | 2021-04-29 | 2021-07-22 | 2021-04-29 |  | Yes | 2024-10-30
ERCOT | 23INR0248 | Limewood Storage | SS Completed, FIS Started, IA | Limewood Bell Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2028-12-29 | BA | 50 | 2021-04-30 | 2021-07-22 | 2021-10-06 |  |  | 2023-02-22
ERCOT | 23INR0249 | Limewood Solar | SS Completed, FIS Started, IA | Limewood Bell Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2025-12-31 | PV | 204.6 | 2021-04-30 | 2021-07-22 | 2021-10-06 |  | No | 2023-02-22
ERCOT | 23INR0260 | Flatland Solar Project | SS Completed, FIS Started, No IA | Flatland Solar Project, LLC | 11319 Scurry County 138kV | Scurry | WEST | 2025-12-31 | PV | 182.2 | 2021-05-10 | 2021-07-30 | 2021-04-28 |  | No
ERCOT | 23INR0261 | Dodd Solar I | SS Completed, FIS Completed, No IA | Forest Grove Solar LLC | Tap 138kV 6951 Eustace Southeast Switch – 3131 Forest Grove Switch | Henderson | NORTH | 2027-09-30 | PV | 201.8 | 2021-06-24 | 2021-09-20 | 2022-04-04 | 2024-03-13
ERCOT | 23INR0266 | Langer Storage | SS Completed, FIS Started, No IA | Langer Solar, LLC | tap 345kV 68040 Kopperl - 68091 Navarro | Bosque | NORTH | 2027-03-01 | BA | 61.53 | 2021-05-10 | 2021-07-30 | 2022-02-25 |  | No
ERCOT | 23INR0272 | BRP Aras BESS | SS Completed, FIS Started, No IA | BRP Aras BESS LLC | 76595 North McCamey 138kV | Upton | WEST | 2025-12-01 | BA | 303.59 | 2021-05-31 | 2021-08-19 | 2021-05-10
ERCOT | 23INR0273 | Poco Trail Solar | SS Completed, FIS Started, No IA | Eastern Trail Solar Center, LLC | Tap 345kV 6101 Riley - 1422 Bowman Byrd Road Switch | Wilbarger | WEST | 2027-05-01 | PV | 438.75 | 2021-09-14 | 2021-11-30 | 2021-07-12 |  | No
ERCOT | 23INR0274 | BRP Parana BESS | SS Completed, FIS Started, No IA | BRP Parana BESS | 7178 Marion 138kV | Guadalupe | SOUTH | 2025-12-01 | BA | 303.67 | 2021-05-31 | 2021-08-19 | 2021-05-10
ERCOT | 23INR0275 | BRP Nile BESS | SS Completed, FIS Started, No IA | BRP Nile BESS LLC | 80220 Cenizo 345kV | Webb | SOUTH | 2027-12-01 | BA | 202.34 | 2021-05-31 | 2021-08-19 | 2021-05-10
ERCOT | 23INR0278 | Tucana BESS | SS Completed, FIS Started, No IA | BRP Tucana BESS LLC | 1157 Andrews County South 138kV | Andrews | WEST | 2028-03-01 | BA | 201.3 | 2021-06-03 | 2021-08-19 | 2021-05-10 |  | No
ERCOT | 23INR0279 | BRP Trivor BESS | SS Completed, FIS Started, No IA | BRP Trivor BESS LLC | 1272 Fullerton 138kV | Andrews | WEST | 2028-03-01 | BA | 202.34 | 2021-06-03 | 2022-03-15 | 2021-05-10 |  | No
ERCOT | 23INR0283 | Kota Battery | SS Completed, FIS Started, No IA | Kota Storage, LLC | 23900 Alibates 345kV | Carson | PANHANDLE | 2026-12-31 | BA | 200.6 | 2021-06-07 | 2021-08-27 | 2021-06-02
ERCOT | 23INR0284 | Las Moras Battery | SS Completed, FIS Started, No IA | Las Moras Storage, LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2026-06-01 | BA | 101 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  | No
ERCOT | 23INR0286 | Dry Creek Solar I | SS Completed, FIS Completed, IA | OAK HILL SOLAR LLC | tap 345kV 3100 Martin Lake - 3105 Elkton (Dorsett 345kV Switching Station) | Rusk | NORTH | 2026-01-01 | PV | 201.06 | 2021-08-18 | 2021-11-05 | 2022-03-30 | 2024-06-12 | No | 2023-11-02
ERCOT | 23INR0287 | Avila BESS | SS Completed, FIS Completed, IA | BRP Avila BESS LLC | 38340 TN Airport 138kV | Pecos | WEST | 2025-05-01 | BA | 164.28 | 2021-05-31 | 2022-01-17 | 2021-05-20 | 2024-07-22 | No | 2023-02-06
ERCOT | 23INR0289 | Skull Creek Solar | SS Completed, FIS Completed, IA | Skull Creek Solar, LLC | Tap 138kV 3281 Tennessee Colony - 3499 Blackfoot Massey Lake Switch in TSP’s Pin Oak Switch - Long Lake Substation | Anderson | NORTH | 2026-09-16 | PV | 137.26 | 2021-05-28 | 2021-08-19 | 2021-12-16 | 2023-11-22 | No | 2024-05-20
ERCOT | 23INR0290 | Zeya BESS | SS Completed, FIS Started, IA | BRP Zeya BESS LLC | 38740 Heights 138kV | Galveston | HOUSTON | 2026-06-01 | BA | 255.33 | 2021-05-31 | 2022-03-09 | 2021-05-20 |  | No | 2023-01-20
ERCOT | 23INR0295 | Sultan Solar | SS Completed, FIS Started, No IA | Lake Whitney Solar, LLC | tap 345kV 68080 Sam Switch – 68090 Kopperl | Bosque | NORTH | 2026-12-31 | PV | 206.11 | 2021-07-01 | 2021-09-27 | 2021-06-29
ERCOT | 23INR0296 | Trojan Solar SLF | SS Completed, FIS Started, IA | Compadre Solar, LLC | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2026-02-28 | PV | 150.59 | 2021-07-01 | 2021-09-22 | 2021-06-30 |  | No | 2022-10-10
ERCOT | 23INR0299 | Anole BESS | SS Completed, FIS Completed, IA | Anole Energy Storage, LLC | 2432 Tri-Corner 345kV | Dallas | NORTH | 2025-05-30 | BA | 247.1 | 2021-07-01 | 2021-09-22 | 2021-06-14 | 2024-04-03 | No | 2023-04-26
ERCOT | 23INR0300 | Greater Bryant G Solar | SS Completed, FIS Started, IA | Greater Bryant G Solar, LLC | 11165 Sloan Switch 138kV | Midland | WEST | 2026-02-15 | PV | 17.7 | 2021-06-17 | 2021-09-01 | 2021-06-16 |  | No | 2022-07-18
ERCOT | 23INR0308 | Fowler Ranch Storage | SS Completed, FIS Started, No IA | Crane BESS, LLC | 76025 Castle Mountain 138kV | Crane | WEST | 2026-02-01 | BA | 26.07 | 2021-06-21 | 2021-09-07 | 2022-05-18
ERCOT | 23INR0310 | Dunkel BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners | 59156 Yellow House Canyon 115kV | Lubbock | PANHANDLE | 2026-04-03 | BA | 225 | 2022-06-27 | 2022-09-22 | 2022-06-20
ERCOT | 23INR0312 | Hofbrau BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners, LLC | 6442 Redcreek 138kV | Tom Green | WEST | 2028-07-01 | BA | 180.72 | 2021-09-22 | 2021-12-09 | 2021-09-22 |  | No |  |  |  | COD
ERCOT | 23INR0318 | Marcelina Storage | SS Completed, FIS Completed, No IA | Marcelina Solar, LLC | Tap 345 kV 5133 Elm Creek - 5901 San Miguel | Wilson | SOUTH | 2026-12-18 | BA | 203.21 | 2021-08-09 | 2021-10-29 | 2022-04-22 | 2024-01-23
ERCOT | 23INR0322 | Columbus Storage | SS Completed, FIS Started, No IA | EDP Renewables North America LLC | 78103 Nada Substation 138kV | Colorado | SOUTH | 2026-03-15 | BA | 51.3 | 2021-08-12 | 2021-10-29 | 2022-04-06
ERCOT | 23INR0324 | Lumberjack Storage | SS Completed, FIS Completed, IA | EDP Renewables North America LLC | 138 kV Tap 3110 Stryker Creek - 3147 Troup | Cherokee | NORTH | 2026-07-01 | BA | 51.3 | 2021-08-12 | 2021-10-29 | 2022-04-06 | 2023-07-24 | No | 2024-03-20
ERCOT | 23INR0330 | BRP Snowdon BESS | SS Completed, FIS Started, No IA | BRP SNOWDON BESS LLC | 23914 Tule Canyon Substation 345kV | Briscoe | PANHANDLE | 2026-07-01 | BA | 410.94 | 2021-09-15 | 2021-11-29 | 2021-09-08
ERCOT | 23INR0331 | Orange Grove BESS | SS Completed, FIS Completed, IA | Talitha Energy Project, LLC | 5660 Orange Grove Switching Station 138 kV | Jim Wells | SOUTH | 2027-04-30 | BA | 61.39 | 2021-07-15 | 2021-09-28 | 2021-07-15 | 2022-05-03 | No | 2022-11-30
ERCOT | 23INR0332 | Backwater Solar | SS Completed, FIS Completed, No IA | Backwater Solar LLC | Tap 138 kV line from Spring (#684) - Leo(#685) | Cooke | NORTH | 2027-05-06 | PV | 80 | 2021-08-24 | 2021-11-15 | 2021-08-24 | 2023-04-24 |  |  |  |  | COD
ERCOT | 23INR0334 | Liberty Senate Energy Storage 1 | SS Completed, FIS Completed, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2025-10-27 | BA | 207.4 | 2021-10-05 | 2021-12-08 | 2021-10-03 | 2023-03-31
ERCOT | 23INR0335 | BRP Bachman BESS | SS Completed, FIS Completed, No IA | BRP Bachman BESS LLC | 44040 BAILEY 345kV | Wharton | SOUTH | 2027-12-01 | BA | 411.04 | 2021-10-05 | 2021-12-08 | 2021-09-14 | 2022-07-08
ERCOT | 23INR0336 | Bypass Battery Storage | SS Completed, FIS Started, IA | Bypass BESS LLC | 44000 W_A_P__POI5A 345 kV | Fort Bend | HOUSTON | 2025-12-15 | BA | 207.89 | 2021-08-18 | 2021-11-05 | 2022-02-03 |  | No | 2023-12-04
ERCOT | 23INR0340 | Larkspur Energy Storage | SS Completed, FIS Started, IA | Larkspur Energy Storage LLC | 71213 Benedum 138kV | Upton | WEST | 2026-05-05 | BA | 307.46 | 2021-08-02 | 2021-10-25 | 2021-07-27 |  |  | 2022-02-28
ERCOT | 23INR0342 | Brizo BESS | SS Completed, FIS Started, No IA | BRP Brizo BESS LLC | 138 kV Loop 463 Substation (#5680) | Victoria | SOUTH | 2027-12-01 | BA | 140.76 | 2021-10-05 | 2021-12-22 | 2021-09-24
ERCOT | 23INR0343 | Guajillo Energy Storage | SS Completed, FIS Completed, IA | Guajillo Energy Storage LLC | 80219 Lobo Substation 345kV | Webb | SOUTH | 2025-07-30 | BA | 204.8 | 2021-08-09 | 2021-11-01 | 2021-07-27 | 2024-10-31 | No | 2021-12-21
ERCOT | 23INR0344 | XE Hermes Solar | SS Completed, FIS Completed, IA | Bell Solar 1 LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2025-09-30 | PV | 100.36 | 2021-09-21 | 2021-12-09 | 2022-06-01 | 2024-04-19 |  | 2023-11-08 |  |  | COD
ERCOT | 23INR0345 | Elmax Power Station | SS Completed, FIS Completed, No IA | Elmax Generating, LLC | Tap 138 kV Lake Houston (#40820) - Atascocita (#40130) ckt 66 | Harris | HOUSTON | 2026-06-01 | GT | 518.83 | 2021-09-14 | 2021-11-30 | 2021-09-14 | 2024-03-29 | No
ERCOT | 23INR0348 | Aggie Energy storage | SS Completed, FIS Started, No IA | KINGFISHER ENERGY STORAGE LLC | TABOR RD (#32882) | Brazos | NORTH | 2026-06-15 | BA | 104.4 | 2021-08-16 | 2021-11-05 | 2021-08-13
ERCOT | 23INR0349 | Tokio Solar | SS Completed, FIS Started, IA | Gransolar Texas Eight, LLC | Tap 138kV 3592 Waco Atco - 170 Cotton Belt | McLennan | NORTH | 2027-08-25 | PV | 170.45 | 2021-08-12 | 2021-11-01 | 2022-04-14 |  |  | 2023-11-06
ERCOT | 23INR0350 | Fort Duncan BESS | SS Completed, FIS Completed, IA | Fort Duncan BESS LLC | 78015 Rosita Creek ROSICR 138kV will be at the new LCRA TSC Sunglow Substation | Maverick | SOUTH | 2025-06-01 | BA | 101.52 | 2021-08-17 | 2021-11-05 | 2021-08-16 | 2024-07-29 | No | 2022-12-12
ERCOT | 23INR0351 | Seven Flags BESS | SS Completed, FIS Completed, IA | Seven Flags BESS LLC | 8295 Wormser Substation 138kV | Webb | SOUTH | 2025-12-15 | BA | 102.7 | 2021-09-01 | 2021-11-22 | 2021-08-19 | 2024-12-19 | No | 2023-05-19 |  |  | COD
ERCOT | 23INR0352 | Blue Valley Solar | SS Completed, FIS Started, No IA | Blue Valley Solar, LLC | Tap on the 138 kV Comstock(#8683) - Corral Line(#60389) | Val Verde | WEST | 2027-03-15 | PV | 147.99 | 2021-11-16 | 2022-01-17 | 2021-11-04 |  | No
ERCOT | 23INR0354 | Bordertown BESS | SS Completed, FIS Started, IA | Bordertown BESS LLC | 8796 Roma 138kV | Starr | SOUTH | 2026-05-01 | BA | 106.15 | 2021-09-01 | 2021-11-22 | 2021-08-19 |  | No | 2022-10-12 |  |  | COD
ERCOT | 23INR0358 | Castor BESS | SS Completed, FIS Completed, IA | BRP Castor BESS LLC | 138 kV West Columbia Local Substation (#39530) | Brazoria | COASTAL | 2025-06-01 | BA | 205.39 | 2021-10-04 | 2021-12-22 | 2021-09-24 | 2024-07-31 | No | 2023-02-15
ERCOT | 23INR0359 | BRP Crios BESS | SS Completed, FIS Started, No IA | BRP Crios BESS LLC | Tap 138 kV 1649 HASSE_P8 - 1684 SABANA_8 | Comanche | NORTH | 2028-03-01 | BA | 87.37 | 2021-10-18 | 2022-01-07 | 2021-09-30
ERCOT | 23INR0360 | BRP Charon BESS | SS Completed, FIS Completed, No IA | BRP Charon BESS LLC | Tap Smithers (#44650) and Bellaire (#47000) 345kV | Fort Bend | HOUSTON | 2027-12-01 | BA | 410.81 | 2021-10-08 | 2021-12-22 | 2021-09-24 | 2022-10-10 | No
ERCOT | 23INR0361 | Third Coast BESS | SS Completed, FIS Completed, IA | Third Coast BESS LLC | 8125 Lolita substation 138kV | Jackson | SOUTH | 2025-12-15 | BA | 102.82 | 2021-08-24 | 2021-11-16 | 2021-09-01 | 2024-12-02 | No | 2023-05-17
ERCOT | 23INR0364 | Tierra Seca BESS | SS Completed, FIS Completed, IA | Tierra Seca BESS LLC | 138kV 8255 HAMILTON4A (Hamilton Road Substation) | Val Verde | WEST | 2025-10-01 | BA | 102.7 | 2021-08-24 | 2021-11-16 | 2021-09-01 | 2024-10-21 | No | 2023-05-18
ERCOT | 23INR0366 | Amsterdam Solar II | SS Completed, FIS Completed, No IA | Cottonwood Bayou Solar II, LLC | tap 345kV 43035 Oasis - 42500 Dow c27, c18 | Brazoria | COASTAL | 2026-02-01 | PV | 509.88 | 2021-08-12 | 2021-10-29 | 2021-11-18 | 2023-07-31 |  |  |  |  | COD
ERCOT | 23INR0367 | Fewell Solar | SS Completed, FIS Completed, IA | Fewell Solar LLC | Tap 138kV 3597 Groesbeck - 3634 Groesbeck Main | Limestone | NORTH | 2027-03-15 | PV | 203.5 | 2021-08-19 | 2021-11-05 | 2022-02-17 | 2023-04-17 | No | 2023-08-18
ERCOT | 23INR0368 | Rocking X Solar | SS Completed, FIS Started, No IA | 7100 Tin Top LLC | Tap the 345 kV Parker Switch (bus#1436) – Comanche Peak SES (bus#1900) Double-Circuit line, Circuit 1. | Parker | NORTH | 2027-04-02 | PV | 602.2 | 2023-10-04 | 2023-12-19 | 2023-09-06
ERCOT | 23INR0372 | Cross Trails Storage | SS Completed, FIS Completed, IA | Cross Trails Energy Storage Project, LLC | 60090 WKN Breaker 69kV | Scurry | WEST | 2025-05-25 | BA | 58.29 | 2021-11-03 | 2022-01-17 | 2021-10-29 | 2024-07-30 |  | 2024-07-18
ERCOT | 23INR0373 | Fronton Solar 1 | SS Completed, FIS Completed, No IA | Meshek USA Inc. | 8796 Roma Substation 138kV | Starr | SOUTH | 2026-12-14 | PV | 132.7 | 2021-10-05 | 2021-12-22 | 2021-09-17 | 2023-08-10 | No
ERCOT | 23INR0374 | Grand Acres | SS Completed, FIS Started, No IA | Meshek USA Inc. | 8359 South Santa Rosa 138 kV | Cameron | COASTAL | 2027-02-23 | PV | 153.03 | 2021-10-07 | 2021-12-22 | 2021-10-06 |  | No
ERCOT | 23INR0375 | Backwater Storage | SS Completed, FIS Completed, No IA | Backwater Solar LLC | Tap 138 kV 684 Spring - 685 Leo | Cooke | NORTH | 2027-09-15 | BA | 100 | 2021-09-17 | 2021-12-06 | 2021-09-17 | 2023-04-24
ERCOT | 23INR0376 | Cascade Storage | SS Completed, FIS Started, No IA | Oyster Creek LLC | 345kV Oasis (43035) – Seabreeze circuit 27 | Brazoria | COASTAL | 2026-01-16 | BA | 250 | 2021-09-09 | 2021-11-29 | 2021-09-09
ERCOT | 23INR0381 | Bexar ESS | SS Completed, FIS Completed, IA | Bexar ESS LLC | 5007 Alamo One 138kV | Bexar | SOUTH | 2025-08-22 | BA | 102.6 | 2021-09-21 | 2021-12-06 |  | 2024-07-08 |  | 2023-07-31
ERCOT | 23INR0382 | Outer Loop BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 40700 Greens Bayou 345kV | Harris | HOUSTON | 2027-12-06 | BA | 201.2 | 2021-09-29 | 2021-12-06 | 2022-04-19 |  | No
ERCOT | 23INR0385 | Camp Creek Solar SLF | SS Completed, FIS Completed, IA | White Rock Solar, LLC | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2026-12-16 | PV | 165.6 | 2021-12-24 | 2022-03-17 | 2021-12-09 | 2024-01-26 | Yes | 2023-07-15
ERCOT | 23INR0387 | Pioneer DJ Wind | SS Completed, FIS Completed, IA | Pioneer Hutt Wind Energy LLC | 138 kV Driver station (Bus #: 23863) | Midland | WEST | 2025-01-31 | WT | 140.32 | 2021-10-11 | 2021-12-22 | 2021-10-07 | 2023-03-28 | No | 2023-04-04 | 2024-01-09 |  | COD
ERCOT | 23INR0391 | THUNDER ROAD ENERGY STORAGE | SS Completed, FIS Started, No IA | Hecate Grid Thunder Road Storage LLC | 12491 FISH CREEK 138KV | Dallas | NORTH | 2027-05-31 | BA | 153.4 | 2021-10-22 | 2022-01-17 | 2021-12-17
ERCOT | 23INR0392 | Honeycomb Storage SLF | SS Completed, FIS Started, IA | Honeycomb Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2026-03-03 | BA | 0.37 | 2021-11-16 | 2022-01-17 | 2021-11-02 |  | No | 2023-05-01 |  |  | COD
ERCOT | 23INR0401 | Headcamp BESS | SS Completed, FIS Completed, IA | Momentum Headcamp LLC | tap 138kV 38331 TN Alamo St – 38455 TN Holiday | Pecos | WEST | 2025-06-16 | BA | 152.88 | 2021-12-03 | 2022-02-28 | 2022-01-21 | 2024-09-18 | No | 2024-02-16
ERCOT | 23INR0409 | Sunbelt Storage | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | Tap 138kV 6902 Talty - 6894 Rose Hill | Kaufman | NORTH | 2024-12-24 | BA | 52 | 2021-11-12 | 2022-02-08 | 2021-11-09
ERCOT | 23INR0414 | Flag City Storage SLF | SS Completed, FIS Started, No IA | Flag City Solar Project, LLC | tap 138kV 5588 Red Bluff - 5546 Danevang | Jackson | SOUTH | 2026-12-31 | BA | 0 | 2021-11-18 | 2022-02-08 | 2021-11-18 |  | No
ERCOT | 23INR0418 | Angelo Storage | SS Completed, FIS Completed, IA | Angelo Storage, LLC | 76009 Twin Buttes 345kV | Tom Green | WEST | 2024-11-15 | BA | 102.97 | 2021-11-22 | 2022-02-15 | 2021-11-16 | 2023-05-01 |  | 2021-12-03 | 2024-03-25
ERCOT | 23INR0419 | SOHO BESS | SS Completed, FIS Completed, IA | ESTX-PLDHOUSTON2 | 43035 Oasis 345kV | Brazoria | COASTAL | 2026-08-04 | BA | 206.32 | 2021-12-03 | 2022-02-28 | 2021-12-03 | 2022-06-28 | No | 2022-12-01 |  |  | COD
ERCOT | 23INR0421 | Tidwell Prairie IV Energy Storage | SS Completed, FIS Started, No IA | Tidwell Prairie LLC | Tap TNP ONE 39950 and Twin Oak 3400 | Robertson | NORTH | 2027-07-01 | BA | 202.88 | 2021-11-15 | 2022-02-11 | 2021-11-09
ERCOT | 23INR0422 | Masroor Storage | SS Completed, FIS Completed, No IA | Masroor Energy Storage LLC | Bus #1760 Bonham 138kV | Fannin | NORTH | 2025-06-26 | BA | 203 | 2021-11-16 | 2022-02-12 | 2021-11-16 | 2023-05-26
ERCOT | 23INR0423 | Camp Creek Storage SLF | SS Completed, FIS Completed, IA | White Rock Solar | TAP 345 KV 3400 TWIN OAK SWITCH - 46020 LIMESTONE PLANT CIRCUIT 1 | Robertson | NORTH | 2026-12-16 | BA | 0 | 2021-12-24 | 2022-03-17 | 2021-12-21 | 2024-01-26 | Yes | 2023-07-15
ERCOT | 23INR0425 | Coneflower Storage Project | SS Completed, FIS Started, IA | Coneflower Storage Project LLC | 40855 JORDON 138 kV | Chambers | HOUSTON | 2027-02-03 | BA | 178.92 | 2021-12-20 | 2022-03-11 | 2022-07-06 |  | No | 2024-03-25
ERCOT | 23INR0431 | BRP Pollux BESS | SS Completed, FIS Started, No IA | BRP Pollux BESS LLC | 138 kV Olsen Switching Station (#37460) | Bosque | NORTH | 2026-12-01 | BA | 163.42 | 2022-01-06 | 2022-03-16 | 2022-01-04 |  | No
ERCOT | 23INR0439 | Smokey Willie Solar SLF | SS Completed, FIS Completed, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2026-03-13 | PV | 200.92 | 2022-01-06 | 2022-03-31 | 2021-12-29 | 2023-09-22 | No
ERCOT | 23INR0441 | Bug Tussle Wind Project | SS Completed, FIS Completed, IA | Bug Tussle Wind, LLC | Tap 1729 Valley South and 1692 Paris | Lamar | NORTH | 2026-09-14 | WT | 396.8 | 2022-01-13 | 2022-04-11 | 2022-08-16 | 2024-01-18 |  | 2024-07-10
ERCOT | 23INR0455 | Bessie Storage | SS Completed, FIS Started, No IA | Bessie Energy Storage, LLC | Charly Egner Substation Tap 345kV 80355 Del Sol - 80368 LV4 Bridge | Starr | SOUTH | 2026-12-01 | BA | 210.8 | 2022-02-21 | 2022-05-19 | 2022-02-07 |  | No
ERCOT | 23INR0456 | Bronze Quinta Storage | SS Completed, FIS Started, No IA | KCE TX 28, LLC | S_MCALLN 8371 (S. McAllen 138kV Substation) | Hidalgo | SOUTH | 2028-01-01 | BA | 103.51 | 2022-01-13 | 2022-04-11 | 2022-01-11
ERCOT | 23INR0460 | PHOTON BESS1 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2025-02-15 | BA | 152.74 | 2022-06-02 | 2022-08-29 | 2022-05-11 | 2023-04-10 |  | 2023-03-23 | 2024-09-09 |  | COD
ERCOT | 23INR0462 | Palladium Storage | SS Completed, FIS Started, No IA | Palladium Energy Storage LLC | Tap 138 kV 8656 Luna - 8033 Pantera | Hidalgo | SOUTH | 2026-04-27 | BA | 152 | 2022-02-28 | 2022-05-27 | 2022-01-21
ERCOT | 23INR0464 | Sloan Storage | SS Completed, FIS Started, No IA | Sloan Energy Storage LLC | 3179 Pauline 138kV | Henderson | NORTH | 2026-03-27 | BA | 200.9 | 2022-02-21 | 2022-05-21 | 2022-06-29
ERCOT | 23INR0466 | Shoshana Storage | SS Completed, FIS Completed, No IA | Shoshana Storage Project LLC | Tap STP – Refuge ckt 27 | Matagorda | COASTAL | 2026-08-28 | BA | 221 | 2022-03-30 | 2022-06-26 | 2022-05-16 | 2024-03-27 | Yes
ERCOT | 23INR0467 | Lavender Storage Project | SS Completed, FIS Started, No IA | Lavender Storage Project LLC | Tap 138kV Deely (bus 5110) - Laredo (bus 5255) | Bexar | SOUTH | 2026-06-01 | BA | 231.9 | 2022-02-28 | 2022-05-27 | 2022-10-21
ERCOT | 23INR0468 | Petunia Storage Project | SS Completed, FIS Completed, No IA | Petunia Storage Project LLC | 138kV Tap 3675 Rogers - 3485 Tin Roof Pod | Milam | SOUTH | 2026-07-06 | BA | 231.86 | 2022-03-12 | 2022-06-02 | 2022-04-01 | 2024-06-26 | No
ERCOT | 23INR0469 | Big Elm Storage | SS Completed, FIS Completed, IA | Big Elm Storage, LLC | Tap 345 kV 3414 Temple Switch - 3409 Lake Creek | Bell | NORTH | 2026-08-15 | BA | 100.8 | 2022-04-18 | 2022-07-08 | 2022-10-11 | 2024-02-19 | No | 2024-05-10 |  |  | COD
ERCOT | 23INR0471 | Ophelia Solar | SS Completed, FIS Started, No IA | Ophelia Solar | Tapping the 138 kV Line from Moss Switch (Bus# 1019) to Shin Oak POD (Bus# 11128). The project has a 110 MW PUN load at the high side of the MPT (refer to the substation SLD). | Ector | WEST | 2026-01-27 | PV | 110.5 | 2022-09-02 | 2022-11-29 | 2022-08-01
ERCOT | 23INR0473 | Sepanta Solar | SS Completed, FIS Started, No IA | BREG - Belgian Renewable Energy Group | 1339 ESKOTA_9 138kV (PSS/E BUS #1339, Station Name: ESKOTA_8, kV: 138 kV) Property is adjacent (West) to the Oncor Sweetwater Eskota Switch #1339. POI would simply be on the other side of the fence of the switch. | Nolan | WEST | 2026-04-20 | PV | 217.26 | 2022-10-18 | 2023-01-13 | 2022-11-15
ERCOT | 23INR0474 | AP Greenport | SS Completed, FIS Completed, No IA | AP Greenport | Austrop – Lost Pines 345 kV transmission line (Bus #7040 – 9041) | Travis | SOUTH | 2026-02-18 | BA | 100.45 | 2022-06-10 | 2022-09-06 | 2022-06-24 | 2023-09-29 | No
ERCOT | 23INR0478 | XE Rhoda Storage | SS Completed, FIS Started, No IA | Milam Energy, LLC | Tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2027-08-04 | BA | 141.23 | 2022-04-18 | 2022-07-15 | 2022-03-18
ERCOT | 23INR0479 | Taormina Storage | SS Completed, FIS Started, No IA | Taormina Storage Project LLC | Tap 138kV VH Braunig (5025) to Valley Road 138kV (5465) | Bexar | SOUTH | 2026-06-01 | BA | 231.86 | 2022-04-18 | 2022-07-15 | 2022-10-26
ERCOT | 23INR0480 | Camellia Storage | SS Completed, FIS Started, No IA | Camellia Storage Project LLC | Tap 138 kV 8358 NORTH MERCEDES - 8327 HARLINGEN 138 kV | Hidalgo | SOUTH | 2026-06-30 | BA | 90.76 | 2022-07-05 | 2022-10-01 | 2022-07-06
ERCOT | 23INR0485 | Hacienda Storage | SS Completed, FIS Started, No IA | Galveston Energy Storage LLC | 38745 Attwater 138kV | Galveston | HOUSTON | 2026-06-09 | BA | 201.9 | 2022-05-10 | 2022-08-06 | 2022-04-04
ERCOT | 23INR0486 | Lamar Unit 1 Repower | SS Completed, FIS Started, No IA | La Frontera Holdings, LLC | 1692 Paris Switch Station 345kV | Lamar | NORTH | 2027-12-18 | CC | 66 | 2022-06-02 | 2022-08-30
ERCOT | 23INR0487 | Brightside Solar Alt POI | SS Completed, FIS Not Started, IA | Brightside Solar, LLC | 8156 Charter Substation 138kV | Live Oak | SOUTH | 2025-08-14 | PV | 50 | 2022-05-16 | 2022-08-05 |  |  |  | 2020-06-11
ERCOT | 23INR0494 | Cartwheel BESS 1 | SS Completed, FIS Completed, IA | Cartwheel BESS, LLC | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2025-07-31 | BA | 154.2 | 2022-06-02 | 2022-08-30 | 2022-05-10 | 2024-04-12 |  | 2023-11-10
ERCOT | 23INR0495 | Cartwheel BESS 2 | SS Completed, FIS Completed, No IA | RWE Renewables | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2026-06-15 | BA | 156.91 | 2022-06-02 | 2022-08-30 | 2022-05-10 | 2024-04-12 |  |  |  |  | COD
ERCOT | 23INR0496 | San Perlita BESS 1 | SS Completed, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2025-12-15 | BA | 150 | 2022-06-02 | 2022-08-29 | 2022-05-10
ERCOT | 23INR0497 | San Perlita BESS 2 | SS Completed, FIS Started, No IA | RWE Renewables | 8601 Cebolla 345kV | Willacy | COASTAL | 2025-12-15 | BA | 150 | 2022-06-02 | 2022-08-29 | 2022-05-10
ERCOT | 23INR0501 | Soda Lake BESS 1 | SS Completed, FIS Completed, IA | Mendoza Trail BESS, LLC | 138kV Soda Lake Substation (#76026) | Crane | WEST | 2025-08-31 | BA | 203.87 | 2022-09-02 | 2022-11-29 | 2022-08-09 | 2024-10-22 |  | 2018-08-20
ERCOT | 23INR0502 | Adelite Storage | SS Completed, FIS Completed, IA | Adelite Storage Project LLC | Tap 138kV Thorndale North (bus #3659) – Rookie Switch (bus #3701) | Milam | SOUTH | 2026-06-30 | BA | 231.88 | 2022-06-27 | 2022-09-22 | 2022-09-09 | 2024-05-01 |  | 2024-08-27
ERCOT | 23INR0503 | Ardesia Storage | SS Completed, FIS Started, No IA | Ardesia Storage Project LLC | Tap 138kV 7325 Mendoza - 7216 Lockhart | Caldwell | SOUTH | 2026-08-28 | BA | 100 | 2022-06-10 | 2022-09-06 | 2022-07-22
ERCOT | 23INR0524 | Temple II Repower | SS Completed, FIS Completed, IA | Panda Temple Power II | 3413 Knob Creek | Bell | NORTH | 2024-09-01 | CC | 0 | 2022-08-05 | 2022-11-01 | 2022-07-22 | 2023-01-04 |  | 2012-06-21
ERCOT | 23INR0538 | Roadrunner Crossing BESS SLF | SS Completed, FIS Started, No IA | Roadrunner Crossing BESS | 68051 Reata 354kV | Eastland | NORTH | 2026-07-01 | BA | 40 | 2022-11-15 | 2023-02-10 | 2022-10-28
ERCOT | 23INR0561 | Cascabel Wind 2 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307). | Zapata | SOUTH | 2027-12-01 | WT | 197.75 | 2023-03-13 | 2023-06-09 | 2023-02-15 | [5 empty] | COD
ERCOT | 23INR0637 | Goodnight Wind II | SS Completed, FIS Not Started, IA | FGE Goodnight II, LLC | tap 345kV 23900 Alibates - 23914 Tule Canyon CKT2 | Armstrong | PANHANDLE | 2026-06-27 | WT | 259.2 | 2023-04-19 | 2023-04-19 |  |  | No | 2019-08-18 |  |  | COD
ERCOT | 23INR0794 | Invictus Energy Storage | SS Completed, FIS Started, No IA | Indigo BESS LLC | 6390 FIREROCK4A 138kV | Coleman | WEST | 2028-05-31 | BA | 140.53 | 2024-01-03 | 2024-03-28
ERCOT | 24INR0003 | Stem Solar | SS Completed, FIS Started, No IA | Innovative Solar 134, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2025-08-26 | PV | 200 | 2020-02-04 | 2020-04-27 | 2020-10-22
ERCOT | 24INR0007 | Nockenut Springs Solar 2 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2027-05-05 | PV | 203.26 | 2020-09-25 | 2020-12-16 | 2020-09-11
ERCOT | 24INR0010 | Pinnington Solar | SS Completed, FIS Completed, IA | Hecate Energy Longhorn Solar LLC | 1506 Long Hollow Switch 345kV | Jack | NORTH | 2026-04-30 | PV | 653.7 | 2020-12-03 | 2021-02-17 | 2020-11-10 | 2024-12-17 |  | 2023-11-02 |  |  | COD
ERCOT | 24INR0011 | Pinnington Storage | SS Completed, FIS Completed, No IA | Hecate Energy Longhorn Storage LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2026-04-30 | BA | 508.7 | 2020-12-03 | 2021-02-17 | 2020-11-10 | 2023-10-18 |  |  |  |  | COD
ERCOT | 24INR0015 | Five Wells Solar | SS Completed, FIS Completed, IA | Five Wells Solar Center LLC | 3687 Bell Country East 345kV | Bell | NORTH | 2024-12-30 | PV | 322.82 | 2021-02-04 | 2021-04-21 | 2021-01-22 | 2023-03-09 |  | 2022-09-01 | 2023-10-11
ERCOT | 24INR0020 | Percy Farm Solar | SS Completed, FIS Started, No IA | Percy Farm Solar 1, LLC | Tap 345kV 8123 Blessing - 5915 STP | Matagorda | COASTAL | 2028-12-31 | PV | 198.63 | 2021-03-16 | 2021-06-11 | 2021-07-21 |  | No
ERCOT | 24INR0022 | Boxcar Solar | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2027-04-01 | PV | 355.82 | 2021-03-31 | 2021-06-17 | 2021-03-17
ERCOT | 24INR0023 | Compadre Solar | SS Completed, FIS Completed, IA | Hill Solar I, LLC | tap 345kV 68090 Sam Switch - 1907 Venus | Hill | NORTH | 2024-12-25 | PV | 406.14 | 2021-03-16 | 2021-05-28 | 2021-03-08 | 2024-01-31 | No | 2022-11-12 | 2024-11-13
ERCOT | 24INR0031 | Stoneridge Solar | SS Completed, FIS Completed, IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP Beulah Switch to tap above line | Milam | SOUTH | 2025-04-30 | PV | 201.6 | 2021-10-08 | 2022-01-03 | 2022-01-31 | 2024-05-21 | No | 2023-05-15
ERCOT | 24INR0038 | PP Jaguar Solar | SS Completed, FIS Completed, IA | PP Jaguar Solar LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2027-02-11 | PV | 300 | 2021-03-18 | 2021-06-11 | 2021-07-15 | 2022-08-30 |  | 2022-09-12 |  |  | COD
ERCOT | 24INR0039 | PP Jaguar BESS | SS Completed, FIS Completed, IA | PP Jaguar BESS LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2025-06-30 | BA | 314.25 | 2021-03-18 | 2021-06-11 | 2021-07-15 | 2024-07-30 |  | 2022-09-12
ERCOT | 24INR0040 | Rosebud Solar SLF | SS Completed, FIS Started, No IA | Rosebud Solar, LLC | Tap 69kV 67 BAGGINS - 69 BARCLAY | Falls | NORTH | 2028-01-15 | PV | 130 | 2021-04-13 | 2021-07-06 | 2022-01-10
ERCOT | 24INR0041 | Rock N' Roll Solar SLF | SS Completed, FIS Started, No IA | Rock N Roll Solar | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2026-07-31 | PV | 151.97 | 2021-05-10 | 2021-07-30 | 2022-01-20 |  | No
ERCOT | 24INR0042 | Yaupon Solar SLF | SS Completed, FIS Started, IA | Yaupon Solar, LLC | Tap 345 kV Gibson Switch (3706) – TNP One (39950) | Milam | SOUTH | 2026-06-15 | PV | 204.08 | 2021-03-30 | 2021-06-17 | 2021-11-23 |  |  | 2023-09-28
ERCOT | 24INR0044 | Miller's Branch II | SS Completed, FIS Started, No IA | Miller's Branch Solar, LLC | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2026-04-01 | PV | 200 | 2021-11-04 | 2020-03-06 | 2021-11-04
ERCOT | 24INR0056 | Pradera Solar | SS Completed, FIS Started, No IA | Pradera Solar, LLC | tap 345 kV Lobo (80219) - Fowlerton (5709) | Webb | SOUTH | 2024-10-31 | PV | 118 | 2021-07-08 | 2021-09-28 | 2021-06-23
ERCOT | 24INR0057 | Hanson Storage | SS Completed, FIS Started, IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2027-04-17 | BA | 101.39 | 2021-06-21 | 2021-09-08 | 2021-08-19 |  |  | 2023-09-20
ERCOT | 24INR0058 | Briggs Storage | SS Completed, FIS Started, No IA | Briggs Solar, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2027-09-15 | BA | 70.39 | 2021-05-31 | 2021-08-18 | 2022-03-04
ERCOT | 24INR0059 | Cuchillas Solar | SS Completed, FIS Started, IA | Gransolar Texas Two, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2026-05-01 | PV | 305.6 | 2021-06-02 | 2021-08-18 | 2022-02-11 |  | No | 2023-06-20
ERCOT | 24INR0061 | Eighteenmile Solar SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 138kV 5730 Four Corners - 5728 Choate | Goliad | SOUTH | 2026-12-01 | PV | 153.06 | 2021-08-18 | 2021-11-05 | 2021-08-24 | [5 empty] | COD
ERCOT | 24INR0062 | Eighteenmile Storage SLF | SS Completed, FIS Started, No IA | Weser Solar, LLC | Tap 5730 Four Corners to 5728 Choate 138 kV | Goliad | SOUTH | 2026-12-01 | BA | 0 | 2021-12-29 | 2022-02-08 | 2022-01-07 | [5 empty] | COD
ERCOT | 24INR0065 | Keys Hollow Solar Phase II SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2028-03-10 | PV | 204.08 | 2021-06-17 | 2021-09-01 | 2021-07-29 |  | No | 2024-10-29
ERCOT | 24INR0066 | Keys Hollow Storage Phase II SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2028-03-10 | BA | 0 | 2021-06-17 | 2021-09-01 | 2022-01-10 |  | No | 2024-10-29
ERCOT | 24INR0067 | KEYS HOLLOW SOLAR SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2028-03-10 | PV | 204.08 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  | No | 2024-10-29
ERCOT | 24INR0068 | KEYS HOLLOW STORAGE SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2028-03-10 | BA | 0 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  | No | 2024-10-29
ERCOT | 24INR0069 | Triple B Solar Alt#2 | SS Completed, FIS Started, No IA | Triple B Solar LLC | Tap 138kV 7066 Adamsville - 7064 Lampasas | Lampasas | NORTH | 2027-07-01 | PV | 150 | 2021-06-10 | 2021-09-01 | 2021-11-15
ERCOT | 24INR0070 | Sypert Branch Solar Project | SS Completed, FIS Completed, IA | Sypert Branch Solar LLC | Tap 345kV #3751 Scooter Switch - #3687 Bell County East Switch Ckt 2 | Milam | SOUTH | 2026-01-31 | PV | 261.15 | 2021-09-21 | 2021-12-06 | 2022-04-28 | 2024-10-31 | No | 2023-10-12
ERCOT | 24INR0073 | Hyacinth Storage | SS Completed, FIS Started, No IA | Hyacinth Storage, LLC | 46500 Tomball 345 kV | Harris | HOUSTON | 2030-12-25 | BA | 103.05 | 2021-07-02 | 2021-09-22 | 2022-03-21
ERCOT | 24INR0077 | Quarter Ranch Solar | SS Completed, FIS Started, No IA | Gransolar Texas Three LLC | 80223 Cenizo Substation 345kV | Zapata | SOUTH | 2026-09-30 | PV | 154.12 | 2021-07-13 | 2021-09-28 | 2022-03-23 |  | No
ERCOT | 24INR0078 | Apogee Wind II | SS Completed, FIS Started, No IA | King Creek Wind Farm 3, LLC | 60791 Perigee Substation 345kV | Throckmorton | WEST | 2026-03-31 | WT | 47.25 | 2021-07-13 | 2021-09-20 | 2021-12-14
ERCOT | 24INR0079 | Boxcar Solar 2 | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345 kV 1907 Venus N - 68091 Navarro | Ellis | NORTH | 2027-09-30 | PV | 251.3 | 2021-07-13 | 2021-09-28 | 2022-05-23 |  | Yes
ERCOT | 24INR0081 | SANJAC BESS | SS Completed, FIS Started, No IA | Castleman Power | 40270 Riverside 138kV | Harris | HOUSTON | 2027-04-04 | BA | 202.37 | 2021-07-08 | 2021-09-28 | 2021-07-08
ERCOT | 24INR0086 | Pisgah Ridge Solar 2 | SS Completed, FIS Started, No IA | Pisgah Ridge Solar 2, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2026-12-01 | PV | 101.89 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  | No
ERCOT | 24INR0087 | Pisgah Ridge Storage 3 | SS Completed, FIS Started, No IA | Pisgah Ridge 3, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2026-12-01 | BA | 101.36 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  | No
ERCOT | 24INR0088 | Tres Margaritas Solar | SS Completed, FIS Started, No IA | Gransolar Texas Six, LLC | Tap 138kV 8613 Big Wells – 8212 Dilley Switching Station | Dimmit | SOUTH | 2026-06-30 | PV | 60.95 | 2021-07-13 | 2021-10-08 | 2022-02-21 |  | No
ERCOT | 24INR0091 | BRP Springbok Solar | SS Completed, FIS Started, No IA | Antelope Solar LLC | 23920 Blackwater Draw Switching Station 345kV | Hale | PANHANDLE | 2027-12-01 | PV | 202.39 | 2021-08-25 | 2021-11-17 | 2021-08-02 |  | No
ERCOT | 24INR0093 | Oriana Solar | SS Completed, FIS Completed, IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2025-04-06 | PV | 181 | 2021-08-25 | 2021-11-17 | 2021-08-13 | 2024-07-30 |  | 2023-02-27
ERCOT | 24INR0094 | Dovetail Solar 1 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar 1 LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing Ckt 2 | Jack | NORTH | 2027-04-15 | PV | 666.1 | 2021-09-21 | 2021-12-09 | 2022-06-06
ERCOT | 24INR0095 | Dovetail Solar 2 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar 2 LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing | Jack | NORTH | 2028-03-31 | PV | 666.1 | 2021-10-26 | 2022-01-21 | 2022-07-15
ERCOT | 24INR0096 | BRP Volga BESS | SS Completed, FIS Started, No IA | BRP Volga BESS LLC | 138 kV Seagoville Switch Substation (#2434; ONCOR) | Dallas | NORTH | 2027-12-01 | BA | 174.63 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  | No
ERCOT | 24INR0097 | Dovetail Solar 3 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar Holdings LLC | Tap 345kV 1421 Willow Creek – 11523 THOMPRIC | Jack | NORTH | 2028-12-29 | PV | 666.1 | 2021-12-13 | 2022-02-08 | 2022-08-06
ERCOT | 24INR0098 | Dovetail Storage | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Storage LLC | Tap 345 KV 1421 Willow Creek-60515 Clear Crossing CKT#2 | Jack | NORTH | 2027-04-15 | BA | 508.7 | 2021-09-28 | 2021-12-03 | 2022-05-31
ERCOT | 24INR0099 | Two Rivers Solar | SS Completed, FIS Completed, No IA | Two Rivers Solar, LLC | Tap 138kV 64 Milano – 32 Robertson | Milam | SOUTH | 2027-05-10 | PV | 219.35 | 2021-07-27 | 2021-10-21 | 2021-07-22 | 2024-08-15 | No
ERCOT | 24INR0101 | Lampe Solar | SS Completed, FIS Started, No IA | Gransolar Texas Seven LLC | Tap 138 kV 7572 Gay Hill - 7573 Lyons | Washington | SOUTH | 2027-12-26 | PV | 60.24 | 2021-08-03 | 2021-10-18 | 2022-04-14 |  | No
ERCOT | 24INR0102 | Val Vista Grid BESS 2 | SS Completed, FIS Started, No IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2028-06-01 | BA | 210.56 | 2021-10-01 | 2021-12-09 | 2021-10-01 | [5 empty] | MW Size
ERCOT | 24INR0103 | Opuntia Solar SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2028-03-10 | PV | 102.04 | 2021-08-24 | 2021-11-16 | 2021-08-09
ERCOT | 24INR0104 | Braswell Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nine, LLC | Tap 69kV 147 Lorena - 3580 Eddy Substation (Will be converted to 138kV line before 3/14/25 per TSP) | McLennan | NORTH | 2026-05-30 | PV | 42.6 | 2021-08-30 | 2021-11-18 | 2022-04-08 |  | No
ERCOT | 24INR0106 | Payne Battlecreek | SS Completed, FIS Completed, IA | Gransolar Texas Ten, LLC | tap 138kV 213 Haney - 3515 Hubbard | Hill | NORTH | 2026-05-15 | PV | 84.99 | 2021-08-12 | 2021-10-29 | 2022-03-10 | 2023-04-17 | No | 2024-02-23
ERCOT | 24INR0108 | Louisa Energy Storage | SS Completed, FIS Completed, No IA | Viridity Energy Solutions Inc. | 138 kV Helotes (#5200) | Bexar | SOUTH | 2026-05-01 | BA | 102.77 | 2021-11-16 | 2022-01-17 | 2021-11-08 | 2023-07-10 | No
ERCOT | 24INR0109 | Oriana BESS | SS Completed, FIS Started, IA | Oriana Solar LLC | Tap 138kV 5502 Rayburn - 5584 Vanderbilt | Victoria | SOUTH | 2026-06-15 | BA | 60.3 | 2021-08-25 | 2021-11-17 | 2022-02-14 |  |  | 2023-02-27
ERCOT | 24INR0110 | Kildare | SS Completed, FIS Completed, No IA | Galsol, LLC | 5524 Cordele 69 Sub 69 kV | Jackson | SOUTH | 2026-09-30 | PV | 70 | 2022-01-28 | 2022-04-26 | 2022-01-18 | 2023-12-06
ERCOT | 24INR0111 | BRP Triton BESS | SS Completed, FIS Started, No IA | BRP Triton BESS LLC | 138 kV Comanche Switch Substation (#1441) | Comanche | NORTH | 2026-12-01 | BA | 205.36 | 2021-10-18 | 2022-01-12 | 2021-10-08
ERCOT | 24INR0115 | Aster Solar | SS Completed, FIS Started, No IA | Aster Solar | 7042 Zorn 345kV | Guadalupe | SOUTH | 2026-10-15 | PV | 203.52 | 2021-09-21 | 2021-12-09 | 2022-05-24
ERCOT | 24INR0116 | Hart Wind 2 | SS Completed, FIS Completed, IA | Hart Wind, LLC | Tap 345kV 23912 OGALLALA - 23920 BLACKWATER DRAW SWITCH | Castro | PANHANDLE | 2025-11-01 | WT | 163.4 | 2021-10-21 | 2022-01-17 | 2022-05-06 | 2023-11-13 |  | 2023-10-06 |  |  | MW Size
ERCOT | 24INR0117 | Utley Solar | SS Completed, FIS Started, No IA | Palmera Solar Development LLC | Tap 345kV 3381 Big Brown Switch - 3391 Jewett | Freestone | NORTH | 2027-09-30 | PV | 221.78 | 2021-09-07 | 2021-11-29 | 2022-03-09
ERCOT | 24INR0118 | Possum Kingdom Solar | SS Completed, FIS Started, No IA | PK Solar, LLC | Tap 345kV 1421 Willow Creek Switch – 11523 Thomas Price | Jack | NORTH | 2027-10-29 | PV | 262.22 | 2021-09-13 | 2021-11-29 | 2022-05-23 |  | No
ERCOT | 24INR0120 | Eytcheson Ranches Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fourteen, LLC | Tap 69kV 186 Navarro Mills – 107 Prairie Hill | Navarro | NORTH | 2028-01-01 | PV | 76.42 | 2021-09-14 | 2021-11-29 | 2022-05-26 |  | No
ERCOT | 24INR0121 | PHOTO BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2026-09-01 | BA | 75 | 2021-10-29 | 2021-12-08 | 2022-05-13
ERCOT | 24INR0122 | PHOTO BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2026-09-01 | BA | 150 | 2021-10-29 | 2021-12-08 | 2022-05-13
ERCOT | 24INR0124 | High Noon Solar | SS Completed, FIS Started, IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2027-12-01 | PV | 182 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  | 2024-05-03
ERCOT | 24INR0125 | Grasshopper Solar | SS Completed, FIS Started, No IA | Grasshopper Solar LLC | Smoky Hill 345kV Sub (Bus #6104) Locational coordinates : 33.34414; 99.624637 | Haskell | WEST | 2028-10-01 | PV | 407.68 | 2021-09-28 | 2021-12-09 | 2021-09-22
ERCOT | 24INR0126 | High Noon Storage | SS Completed, FIS Started, IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2027-12-01 | BA | 94 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  | 2024-05-08
ERCOT | 24INR0127 | Naduah Solar | SS Completed, FIS Completed, No IA | Gransolar Texas Fifteen, LLC | Tap 69kV Ben Hur (99) - Prairie Hill (107) | Limestone | NORTH | 2026-06-15 | PV | 102.3 | 2021-09-27 | 2021-12-09 | 2022-06-06 | 2024-08-02 | No
ERCOT | 24INR0128 | Desna BESS | SS Completed, FIS Completed, IA | BRP Desna BESS LLC | 39703 TNP FM524 138kV | Brazoria | COASTAL | 2025-06-01 | BA | 205.46 | 2021-12-15 | 2022-03-11 | 2021-11-29 | 2024-08-01 |  | 2023-09-15
ERCOT | 24INR0130 | BRP Artemis BESS | SS Completed, FIS Started, No IA | BRP Artemis BESS LLC | 40600 Roans Prairie Substation 345kV | Grimes | NORTH | 2028-12-01 | BA | 411.32 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  | No |  |  |  | COD
ERCOT | 24INR0131 | Zelus BESS | SS Completed, FIS Started, No IA | BRP Zelus BESS LLC | the 138 kV Zapata Substation (#8299; AEP) | Zapata | SOUTH | 2027-12-01 | BA | 201.03 | 2021-12-20 | 2022-03-16 | 2021-12-03
ERCOT | 24INR0132 | Bowhead Solar | SS Completed, FIS Started, No IA | Baffin Bay Solar, LLC | Tap 138kV 8519 Kleberg – 8518 Kingsville | Kleberg | COASTAL | 2026-01-15 | PV | 165 | 2021-11-16 | 2022-02-12 | 2022-08-09
ERCOT | 24INR0133 | BRP Hestia BESS | SS Completed, FIS Started, No IA | BRP Hestia BESS LLC | the 69 kV Rock Springs Substation (#78238, LCRA) | Edwards | SOUTH | 2028-12-01 | BA | 29.05 | 2021-12-29 | 2022-03-25 | 2021-12-28
ERCOT | 24INR0134 | BRP Hemera BESS | SS Completed, FIS Started, No IA | BRP Hemera BESS LLC | 345 kV Deaf Smith Substation (#23908, Oncor) | Deaf Smith | PANHANDLE | 2026-07-01 | BA | 206.96 | 2021-12-29 | 2022-03-25 | 2021-12-14
ERCOT | 24INR0135 | BRP Mekong BESS | SS Completed, FIS Completed, No IA | BRP Mekong BESS LLC | Tap 345 kV line from Twin Oak Switch (#3400) to TPN One Plant Switchyard (#39950) | Robertson | NORTH | 2027-12-01 | BA | 413.74 | 2021-12-20 | 2022-03-16 | 2021-12-03 | 2024-04-15
ERCOT | 24INR0136 | Eagle Springs Storage | SS Completed, FIS Started, No IA | Eagle Springs Solar, LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2025-12-31 | BA | 55.1 | 2021-10-18 | 2022-01-12 | 2022-06-13 |  | No
ERCOT | 24INR0137 | Eagle Springs Solar | SS Completed, FIS Started, No IA | Eagle Springs Solar, LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2025-12-31 | PV | 110.1 | 2021-10-18 | 2022-01-12 | 2022-06-13 |  | No
ERCOT | 24INR0138 | Midpoint Storage | SS Completed, FIS Completed, IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2025-08-30 | BA | 50.9 | 2021-10-15 | 2022-01-04 | 2022-05-11 | 2024-10-31 | No | 2023-10-31
ERCOT | 24INR0139 | Midpoint Solar | SS Completed, FIS Completed, IA | Midpoint Solar, LLC | 138 KV Tap #3518 BLUM to #237 Blanton | Hill | NORTH | 2025-08-30 | PV | 98.3 | 2021-10-15 | 2022-01-04 | 2022-05-04 | 2024-10-31 | No | 2023-10-31
ERCOT | 24INR0140 | Gaia Storage | SS Completed, FIS Started, IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2025-12-23 | BA | 76.83 | 2021-12-29 | 2022-03-23 | 2022-05-11 |  | No | 2023-11-08 |  |  | COD
ERCOT | 24INR0141 | Gaia Solar | SS Completed, FIS Started, IA | Gaia Solar, LLC | Tap 138kV 3127 Trinidad SES - 3454 Montfort Switch | Navarro | NORTH | 2025-12-23 | PV | 152.65 | 2021-12-29 | 2022-03-23 | 2022-05-11 |  | No | 2023-11-08 |  |  | COD
ERCOT | 24INR0142 | De Los Santos | SS Completed, FIS Started, No IA | BRP De Los Santos BESS LLC | 78015 Rosita Creek Substation 138kV | Maverick | SOUTH | 2027-12-01 | BA | 200.97 | 2022-05-10 | 2022-08-05 | 2022-04-18
ERCOT | 24INR0145 | Calpine Guadalupe Peakers | SS Completed, FIS Started, No IA | Guadalupe Peaking Energy Center, LLC | 7044 Marion 345kV | Guadalupe | SOUTH | 2027-05-23 | GT | 450 | 2021-11-15 | 2022-02-11 | 2021-10-18
ERCOT | 24INR0150 | Lupinus Solar 1 | SS Completed, FIS Completed, No IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2026-09-21 | PV | 164.86 | 2021-12-08 | 2022-03-04 | 2022-05-11 | 2024-07-12 | No
ERCOT | 24INR0153 | Lupinus Storage 1 | SS Completed, FIS Completed, No IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2026-09-21 | BA | 82.97 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2024-07-12 | No
ERCOT | 24INR0154 | Lupinus Solar 2 | SS Completed, FIS Completed, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | PV | 244.24 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2024-06-26 | No
ERCOT | 24INR0155 | Lupinus Storage 2 | SS Completed, FIS Completed, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | BA | 122.92 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2024-06-26 | No
ERCOT | 24INR0156 | Moonstone Solar Project | SS Completed, FIS Completed, No IA | Ignis TX Solar One LLC | Tap 138kV Eagle Creek (5132) to Floresville (5155) | Wilson | SOUTH | 2026-03-31 | PV | 145.81 | 2021-10-27 | 2022-01-24 | 2022-06-07 | 2024-01-18
ERCOT | 24INR0157 | Merope BESS | SS Completed, FIS Started, No IA | BRP Merope BESS LLC | 345 kV Corn Trail Switch Substation (#11441) | Comanche | NORTH | 2028-03-01 | BA | 401.92 | 2021-12-20 | 2022-03-16 | 2021-12-03
ERCOT | 24INR0160 | Huisache Solar | SS Completed, FIS Started, No IA | Huisache Solar, LLC | Tapping the Elm Creek to Shaula circuit 1 | Wilson | SOUTH | 2026-02-15 | PV | 125.59 | 2021-12-03 | 2022-03-01 | 2022-06-22
ERCOT | 24INR0161 | Miranda Solar Project | SS Completed, FIS Completed, IA | Miranda Solar Project, LLC | Tap 345kV 5709 Fowlerton - 5901 San Miguel Ckt 1 | McMullen | SOUTH | 2026-08-30 | PV | 261.42 | 2021-11-03 | 2022-01-07 | 2022-06-22 | 2024-09-03 |  | 2024-07-16
ERCOT | 24INR0166 | Stillhouse Solar | SS Completed, FIS Completed, IA | Stillhouse Solar LLC | tap 345 kV Bell County East Switch (3687) – Little Pond Switch (3377) | Bell | NORTH | 2025-09-01 | PV | 212.55 | 2021-11-24 | 2022-02-19 | 2021-11-23 | 2024-10-31 | No | 2023-06-07 |  |  | COD
ERCOT | 24INR0167 | OCI SunRoper | SS Completed, FIS Completed, No IA | OCI SunRoper LLC | tap138kV #43190 South Lane City to #42985 Dyann CKT#60 | Wharton | SOUTH | 2026-07-01 | PV | 265.1 | 2021-11-24 | 2022-02-19 | 2021-11-23 | 2024-05-30 | No
ERCOT | 24INR0168 | Tejano Storage | SS Completed, FIS Started, No IA | Tejano Storage, LLC | Tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2026-06-01 | BA | 152 | 2022-03-30 | 2022-06-26 | 2022-04-18 |  | No
ERCOT | 24INR0169 | Yaupon Storage SLF | SS Completed, FIS Started, IA | Yaupon Solar, LLC | to Tap 345 kV Gibson Switch (3706) – TNP One (39950) | Milam | SOUTH | 2028-07-01 | BA | 0 | 2021-11-10 | 2022-02-08 | 2022-01-10 |  |  | 2023-09-28
ERCOT | 24INR0172 | Smith Lake Solar DC | SS Completed, FIS Started, No IA | Smith Lake Solar | TAP 345 KV 44645 SINGLETON - 44900 ZENITH Ckt #99 | Grimes | NORTH | 2026-11-30 | PV | 402 | 2022-02-07 | 2022-05-06 | 2022-11-02 |  | Yes
ERCOT | 24INR0174 | Solar Star North Herty Storage | SS Completed, FIS Completed, No IA | Solar Star North Herty Storage, LLC | 3319 Redland Switch 138 kV | Angelina | NORTH | 2026-04-20 | BA | 125.4 | 2022-02-21 | 2022-05-21 | 2022-08-15 | 2024-04-08
ERCOT | 24INR0177 | Mitchell Plant Road Solar | SS Completed, FIS Started, No IA | DHI Power, LLC | 138 kV 38430 White Baker TNP | Pecos | WEST | 2026-04-01 | PV | 201.5 | 2022-02-21 | 2022-05-21 | 2022-01-28 |  | No
ERCOT | 24INR0178 | Cumulus Grid BESS | SS Completed, FIS Started, No IA | Cumulus Grid, LLC | 1906 Venus Switch Substation 345kV | Ellis | NORTH | 2028-01-01 | BA | 210.74 | 2022-03-14 | 2022-04-18 | 2022-10-18 | [5 empty] | COD
ERCOT | 24INR0179 | Bowhead Storage | SS Completed, FIS Started, No IA | Baffin Bay Solar, LLC | Tap 138kV 8519 Kleberg – 8518 Kingsville | Kleberg | COASTAL | 2026-01-15 | BA | 40 | 2021-12-03 | 2022-02-28 | 2022-08-26
ERCOT | 24INR0180 | Frio Farm | SS Completed, FIS Started, No IA | PREMIER ENGINEERING USA CORP. | 8221 BIG FOOT4A 138kV | Frio | SOUTH | 2026-06-25 | PV | 106.5 | 2021-12-20 | 2022-03-10 | 2022-09-13
ERCOT | 24INR0181 | Bynum Solar Project | SS Completed, FIS Started, IA | Bynum Solar Project, LLC | Tap 69kV 37470 Olsen - 37520 Sycamore | Coryell | NORTH | 2025-12-01 | PV | 56.4 | 2021-12-18 | 2022-03-11 | 2022-05-23 |  |  | 2023-11-22
ERCOT | 24INR0182 | DeSpain Solar Project | SS Completed, FIS Started, No IA | Gransolar Texas Thirteen LLC | 7425 Odlaw Switch 138kV | Kinney | SOUTH | 2026-07-01 | PV | 236.17 | 2021-12-05 | 2022-03-02 | 2022-06-16
ERCOT | 24INR0183 | Altamira Solar | SS Completed, FIS Started, No IA | J&R Power DevCo, LLC | 8985 San Ygnacio 138 kV Substation | Zapata | SOUTH | 2028-03-01 | PV | 150.66 | 2022-01-20 | 2022-04-18 | 2022-10-07
ERCOT | 24INR0184 | Slate Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar Three LLC | Tap 138kV 8646 Rio Bravo - 8985 San Ygancio | Zapata | SOUTH | 2027-10-30 | PV | 104.89 | 2021-12-20 | 2022-03-10 | 2022-07-13 |  | No
ERCOT | 24INR0186 | Rowdy Creek Solar | SS Completed, FIS Started, No IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2027-04-01 | PV | 351.78 | 2022-01-28 | 2022-04-27 | 2022-01-25
ERCOT | 24INR0187 | Rowdy Creek BESS | SS Completed, FIS Started, No IA | Rowdy Creek Solar LLC | Tap 345kV 1692 Paris Switch – 1690 Valley SES | Lamar | NORTH | 2027-04-01 | BA | 175.89 | 2022-01-28 | 2022-04-27 | 2022-01-25
ERCOT | 24INR0188 | Tehuacana Creek Solar SLF | SS Completed, FIS Started, IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro | Navarro | NORTH | 2026-12-31 | PV | 505.5 | 2021-12-20 | 2022-03-10 | 2021-12-09 |  |  | 2024-11-25 |  |  | SFS/NtP
ERCOT | 24INR0189 | Tehuacana Creek BESS SLF | SS Completed, FIS Completed, IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro | Navarro | NORTH | 2026-12-31 | BA | 0 | 2021-12-20 | 2022-03-10 | 2021-12-09 | 2024-04-09 |  | 2024-11-25 |  |  | SFS/NtP
ERCOT | 24INR0196 | Dori BQ BESS | SS Completed, FIS Started, IA | Sunnyside Energy LLC | 138kV line Holmes (#47210) - Garden Villas (#42680); CNP | Harris | HOUSTON | 2025-11-30 | BA | 154 | 2022-02-07 | 2022-05-06 | 2022-01-19 |  | No | 2023-05-31
ERCOT | 24INR0197 | Opuntia Storage SLF | SS Completed, FIS Started, No IA | Opuntia Solar, LLC | tap 138 kV 5607 Warburton - 8912 Medio Creek | Refugio | COASTAL | 2028-03-10 | BA | 0 | 2022-02-07 | 2022-05-07 | 2022-01-20
ERCOT | 24INR0198 | Two Forks BESS | SS Completed, FIS Started, IA | Two Forks LLC | 684 SPRING 138kV | Cooke | NORTH | 2027-07-01 | BA | 309.7 | 2022-01-28 | 2022-04-26 | 2022-10-13 |  | No | 2024-05-03
ERCOT | 24INR0200 | White Tail Solar | SS Completed, FIS Completed, No IA | Mule Deer Solar LLC | Tap 345kV Windmill (23910) – AJ Swope (23906) | Deaf Smith | PANHANDLE | 2026-04-22 | PV | 226.8 | 2022-02-07 | 2022-05-07 | 2022-10-21 | 2024-06-07
ERCOT | 24INR0201 | Short Creek Solar | SS Completed, FIS Started, IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch | Wichita | WEST | 2029-03-02 | PV | 625 | 2022-01-20 | 2022-04-18 | 2022-10-12 |  | No | 2024-10-02
ERCOT | 24INR0204 | Trigo Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar Two LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2025-12-15 | PV | 145.62 | 2022-01-07 | 2022-04-01 | 2022-07-27
ERCOT | 24INR0205 | Wensowitch Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Wensowitch LLC | Tapping 138 kV line Telico (192) to Montfort Switch (3454) | Navarro | NORTH | 2027-09-23 | PV | 146.08 | 2022-01-07 | 2022-04-01 | 2022-07-25
ERCOT | 24INR0206 | Glasgow Solar | SS Completed, FIS Completed, IA | Glasgow Solar LLC | 345kV line between BUS #2466 Big Onion to #68091 Navarro circuit | Navarro | NORTH | 2027-03-16 | PV | 203.5 | 2022-02-07 | 2022-05-07 | 2022-01-12 | 2023-09-10 | No | 2023-11-08
ERCOT | 24INR0207 | Glasgow Storage | SS Completed, FIS Completed, IA | Glasgow Solar LLC | 345kV line between BUS #2466 Big Onion to #68091 Navarro circuit | Navarro | NORTH | 2027-03-16 | BA | 101 | 2022-02-21 | 2022-05-07 | 2022-02-02 | 2023-09-10 |  | 2023-11-08
ERCOT | 24INR0208 | Eastbell Milam Solar II | SS Completed, FIS Completed, IA | Cattlemen Solar Park II LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2025-01-24 | PV | 150.6 | 2022-03-07 | 2022-06-02 | 2022-02-03 | 2024-02-01 |  | 2023-10-25 | 2024-11-20
ERCOT | 24INR0210 | Raven Storage | SS Completed, FIS Completed, No IA | Raven Storage, LLC | Tap 138kV 44740 Wallis - 44190 East Bernard CKT#65 | Wharton | SOUTH | 2026-07-31 | BA | 101.83 | 2022-01-28 | 2022-04-26 | 2022-10-18 | 2024-09-09 | No
ERCOT | 24INR0213 | Owens Solar | SS Completed, FIS Started, No IA | Owens Solar LLC | Tap 138kV line between 177 BOSQUE and 181 Cayote | Bosque | NORTH | 2025-12-31 | PV | 203.5 | 2022-02-07 | 2022-05-06 | 2022-01-12
ERCOT | 24INR0233 | St. Gall Solar | SS Completed, FIS Started, No IA | St. Gall Solar LLC | 38355 Leon Creek 138kV | Pecos | WEST | 2026-06-01 | PV | 207 | 2022-02-28 | 2022-05-27 | 2022-02-24 |  | No
ERCOT | 24INR0234 | Rock N' Roll Storage SLF | SS Completed, FIS Started, No IA | Rock N' Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2026-07-31 | BA | 0 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No
ERCOT | 24INR0235 | Rock N' Roll Storage Two | SS Completed, FIS Started, No IA | Rock N' Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2026-07-31 | BA | 206 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No
ERCOT | 24INR0238 | Appaloosa Run BESS | SS Completed, FIS Started, No IA | APPALOOSA RUN STORAGE, LLC | New Palouse 138kV (#60278) | Upton | WEST | 2026-08-30 | BA | 100 | 2022-03-07 | 2022-06-02 | 2022-03-01
ERCOT | 24INR0239 | Trojan BESS SLF | SS Completed, FIS Started, No IA | Trojan BESS | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2027-07-01 | BA | 0 | 2022-06-02 | 2022-08-30 | 2022-04-19
ERCOT | 24INR0240 | Whitethorn Solar | SS Completed, FIS Started, No IA | Greasewood III LLC | Tap 345kV 76002 Bakerfield - 60404 Solstice CKT#1 | Pecos | WEST | 2027-05-01 | PV | 274.83 | 2022-05-11 | 2022-06-29 | 2022-09-23
ERCOT | 24INR0245 | Diamondback BESS | SS Completed, FIS Started, No IA | Diamondback BESS | 80355 Del Sol 345kV | Starr | SOUTH | 2030-06-30 | BA | 203.8 | 2022-03-07 | 2022-06-02 | 2022-03-01
ERCOT | 24INR0246 | Sultan BESS | SS Completed, FIS Started, No IA | Sultan BESS | tap 345kV 68080 Sam Switch – 68090 Kopperl | Bosque | NORTH | 2027-07-08 | BA | 203.8 | 2022-03-07 | 2022-06-02 | 2022-03-01
ERCOT | 24INR0247 | Lacy Creek Energy Storage SLF | SS Completed, FIS Started, No IA | Edmondson Ranch Wind Holdings, LLC | 59907 Bernoulli 345kV | Glasscock | WEST | 2026-07-01 | BA | 0 | 2024-04-09 | 2024-07-05 | 2024-02-20
ERCOT | 24INR0249 | Hickerson BESS | SS Completed, FIS Started, No IA | Hickerson BESS | tap 345kV 68091 Navarro - 68040 Kopperl | Bosque | NORTH | 2027-07-01 | BA | 0 | 2022-03-07 | 2022-06-02 | 2022-02-24
ERCOT | 24INR0252 | Kruth Storage | SS Completed, FIS Started, No IA | Martinez Energy Storage LLC | 3319 Redland 138kV | Angelina | NORTH | 2026-03-31 | BA | 203 | 2022-02-28 | 2022-05-27 | 2022-07-22
ERCOT | 24INR0255 | Mitchell Plant Road Storage | SS Completed, FIS Started, No IA | DHI POWER, LLC | 138 kV 38430 White Baker TNP | Pecos | WEST | 2026-04-01 | BA | 201.6 | 2022-02-28 | 2022-05-21 | 2022-02-25 |  | No
ERCOT | 24INR0256 | Kennedy Solar | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2028-12-31 | PV | 101.5 | 2022-03-07 | 2022-06-02 | 2022-06-29 | [5 empty] | COD
ERCOT | 24INR0257 | Pruett Solar | SS Completed, FIS Completed, No IA | Crandall Solar LLC | Tap 138kV 587 Greenwood - 685 Leo | Wise | NORTH | 2027-05-25 | PV | 150.54 | 2022-02-28 | 2022-05-27 | 2022-04-05 | 2024-06-14
ERCOT | 24INR0258 | Zeissel Solar | SS Completed, FIS Started, IA | ZSS Power, LLC | 60700 Gauss 345 KV | Knox | WEST | 2028-07-01 | PV | 457.5 | 2022-02-28 | 2022-05-27 | 2022-04-25 |  |  | 2024-02-24
ERCOT | 24INR0260 | Lager Storage | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | 8031 Gillrina 69kV | Nueces | COASTAL | 2026-04-30 | BA | 31.1 | 2022-02-28 | 2022-05-27 | 2022-02-23 |  | No |  |  |  | MW Size
ERCOT | 24INR0263 | Cold Creek Solar | SS Completed, FIS Started, No IA | Cold Creek Solar LLC | 76003 Big Hill Substation 345kV | Schleicher | WEST | 2026-12-31 | PV | 455 | 2022-04-18 | 2022-07-08 | 2022-04-13
ERCOT | 24INR0265 | Jarvis BESS | SS Completed, FIS Completed, IA | SMT Ironman BESS LLC | 43035 Oasis Substation 345kV | Brazoria | COASTAL | 2025-01-28 | BA | 308.4 | 2022-03-14 | 2022-04-18 | 2022-03-08 | 2024-04-15 |  | 2022-12-15 | 2024-11-12 |  | COD
ERCOT | 24INR0266 | Cold Creek Storage | SS Completed, FIS Started, No IA | Cold Creek Solar LLC | 76003 Big Hill Substation 345kV | Schleicher | WEST | 2026-12-31 | BA | 172.4 | 2022-04-18 | 2022-07-08 | 2022-04-13
ERCOT | 24INR0269 | Bar Candela Solar SLF | SS Completed, FIS Completed, No IA | Bar Candela Solar Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2027-12-31 | PV | 200.3 | 2022-03-21 | 2022-06-13 | 2022-12-06 | 2024-02-09
ERCOT | 24INR0271 | Bar Candela Storage SLF | SS Completed, FIS Completed, No IA | Bar Candela Storage Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2027-12-31 | BA | 0 | 2022-03-21 | 2022-06-13 | 2022-12-05 | 2024-02-09
ERCOT | 24INR0272 | Brushy Creek Storage SLF | SS Completed, FIS Started, No IA | Brushy Creek Solar | the 345 kV San Angelo Red Creek Substation (#6444); AEP | Tom Green | WEST | 2028-06-01 | BA | 0 | 2022-03-30 | 2022-06-26 | 2022-03-08 |  | No
ERCOT | 24INR0274 | Bufflehead BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 2475 Lavon Switch 138kV | Collin | NORTH | 2026-07-06 | BA | 200 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-05-04 |  | 2024-04-10
ERCOT | 24INR0275 | Picadillo BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 23837 Buffalo 138kV | Martin | WEST | 2026-12-15 | BA | 100.83 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-06-13 |  | 2024-01-23
ERCOT | 24INR0280 | Port Bay ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8434 Rockport Substation (ROCKPORT4A) 138kV | Aransas | COASTAL | 2027-06-28 | BA | 200 | 2022-03-21 | 2022-06-16 | 2022-03-07 |  | No
ERCOT | 24INR0281 | Red Egret BESS | SS Completed, FIS Completed, IA | Red Egret LLC | 38820 FREEWAY PARK 138KV | Galveston | HOUSTON | 2025-12-31 | BA | 310.58 | 2022-03-14 | 2022-06-09 | 2022-10-13 | 2024-10-04 | No | 2023-06-07 |  |  | COD
ERCOT | 24INR0282 | Royal River BESS | SS Completed, FIS Started, No IA | Royal River LLC | Tap 138kV 42110 Angleton - 43381 West Columbia | Brazoria | COASTAL | 2027-01-11 | BA | 310.7 | 2022-03-30 | 2022-06-27 |  |  | No
ERCOT | 24INR0283 | Sunshine Solar | SS Completed, FIS Started, No IA | Sunshine Energy LLC | Tap on the 138kV Lolita (#8125) - Victoria (#8172) Line | Victoria | SOUTH | 2026-12-01 | PV | 130.72 | 2022-09-02 | 2022-11-29 | 2022-08-24
ERCOT | 24INR0285 | APV Plumwood Storage | SS Completed, FIS Completed, IA | APV Lonestar Energy LLC | Tap 138kV 40171 Baytown - 40015Cedar Bayou Plant | Chambers | HOUSTON | 2027-05-01 | BA | 200.82 | 2022-03-30 | 2022-06-26 | 2022-03-22 | 2024-04-24 | No | 2024-09-03
ERCOT | 24INR0287 | Rockridge Solar Project | SS Completed, FIS Started, No IA | Magnolia Solar Development LLC | 7225 Hickory Forest 138kV | Guadalupe | SOUTH | 2025-11-15 | PV | 221.27 | 2022-04-18 | 2022-07-12 | 2022-08-03
ERCOT | 24INR0289 | Ratcliff Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Ratcliff | Tap 138kV 3279 Long Lake Tap Switch - 3280 Long Lake | Freestone | NORTH | 2027-09-07 | PV | 85.74 | 2022-06-27 | 2022-09-23 | 2022-08-17
ERCOT | 24INR0291 | Rubicon Alpha Wind | SS Completed, FIS Started, IA | Throckmorton Wind, LLC | Tap 345kV 60791 Perigee – 6235 Abilene Mulberry Creek | Haskell | WEST | 2027-07-01 | WT | 225.6 | 2022-05-10 | 2022-08-06 | 2022-04-15 |  |  | 2024-05-08
ERCOT | 24INR0294 | Citrus Flatts BESS | SS Completed, FIS Started, IA | Citrus Flatts Energy Center, LLC | 80022 Oleander 138kV | Cameron | COASTAL | 2026-02-25 | BA | 100.8 | 2022-03-30 | 2022-06-26 | 2022-03-24 |  | No | 2023-09-08
ERCOT | 24INR0295 | Lucky Bluff BESS SLF | SS Completed, FIS Completed, IA | Lucky Bluff BESS LLC | 1652 Fullhouse 138kV tapped in 138kV 1641 Stephenville - 1636 Dublin | Erath | NORTH | 2025-10-15 | BA | 100.8 | 2022-03-30 | 2022-06-26 | 2022-03-24 | 2024-10-23 | No | 2023-11-08
ERCOT | 24INR0298 | Leighton Solar SLF | SS Completed, FIS Started, IA | Lavender Solar LLC | 99 BENHUR 69kV | Limestone | NORTH | 2026-10-17 | PV | 183 | 2022-05-11 | 2022-08-05 | 2022-03-16 |  | No | 2024-05-28
ERCOT | 24INR0302 | Pintail Pass BESS | SS Completed, FIS Completed, IA | Pintail Pass BESS, LLC | 8249 ANGSTROM 345KV | San Patricio | COASTAL | 2025-08-27 | BA | 207.25 | 2022-04-18 | 2022-06-16 | 2022-04-07 | 2024-10-15 | No | 2023-05-16
ERCOT | 24INR0303 | Erika Solar | SS Completed, FIS Started, IA | Erika Solar, LLC | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | Kaufman | NORTH | 2026-07-01 | PV | 204.08 | 2022-07-25 | 2022-10-18 | 2022-07-06 |  | No | 2023-10-12
ERCOT | 24INR0305 | MRG Goody Storage | SS Completed, FIS Completed, IA | MRG Goody Solar Project LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2025-07-07 | BA | 50.4 | 2022-05-10 | 2022-08-05 | 2022-04-11 | 2023-11-21 |  | 2023-11-07
ERCOT | 24INR0306 | Arroyo Storage | SS Completed, FIS Completed, IA | BT Cantwell Solar, LLC | Tap 345kV 8318 Rio Hondo - 8317 La Palma (New Gulch Substation ) | Cameron | COASTAL | 2025-10-22 | BA | 183.76 | 2022-05-10 | 2022-08-05 | 2022-04-26 | 2024-04-30 |  | 2022-08-10
ERCOT | 24INR0308 | Forts Trail Solar | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2027-07-29 | PV | 200.93 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  | No
ERCOT | 24INR0313 | Backbone Creek BESS | SS Completed, FIS Started, IA | Backbone Creek BESS LLC | 7351 STARCKE 138kV | Burnet | SOUTH | 2026-12-26 | BA | 120.69 | 2022-04-18 | 2022-07-08 | 2022-04-27 |  |  | 2023-12-22
ERCOT | 24INR0315 | Black Springs BESS SLF | SS Completed, FIS Completed, IA | Black Springs BESS LLC | 1571 ORAN 138KV | Palo Pinto | NORTH | 2025-10-15 | BA | 120.68 | 2022-04-18 | 2022-07-12 | 2022-05-05 | 2023-08-17 |  | 2023-10-18
ERCOT | 24INR0319 | Burro Loco Energy Storage | SS Completed, FIS Started, No IA | VESI | 8626 Resaca 69kV | Cameron | COASTAL | 2026-12-01 | BA | 25.14 | 2022-07-18 | 2022-10-14 | 2022-07-08
ERCOT | 24INR0326 | Blarney Solar | SS Completed, FIS Completed, No IA | Sligsol, LLC | tap 138kV 1815 Cumby Tap - 1819 Commerce South Sub | Hopkins | NORTH | 2026-05-04 | PV | 81 | 2022-07-05 | 2022-10-01 | 2022-04-21 | 2023-10-18
ERCOT | 24INR0329 | XE Murat Storage | SS Completed, FIS Completed, IA | Liberty 1 Solar LLC | tap the 138 kV CROSBY C66(#40391) -ATASCOCITA (#40130) Line; CNP | Harris | HOUSTON | 2025-05-05 | BA | 60.14 | 2022-06-02 | 2022-08-30 | 2022-04-28 | 2023-05-02 | No | 2023-11-01
ERCOT | 24INR0330 | TRAVIS KIMBRO BESS | SS Completed, FIS Started, IA | Travis Kimbro BESS LLC | 7337 Kimbro 138kV | Travis | SOUTH | 2028-09-18 | BA | 36.84 | 2022-09-02 | 2022-11-29 | 2022-04-25 |  |  | 2024-10-31
ERCOT | 24INR0331 | Chisme Storage | SS Completed, FIS Completed, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2027-04-13 | BA | 146 | 2023-01-17 | 2023-04-14 | 2023-01-11 | 2024-07-23 | No
ERCOT | 24INR0333 | Chisme Solar | SS Completed, FIS Completed, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2027-04-13 | PV | 147 | 2023-01-17 | 2023-04-14 | 2023-01-11 | 2024-07-23
ERCOT | 24INR0337 | Eldora Solar | SS Completed, FIS Completed, IA | Eldora Energy LLC | Tap 345 kV 5915 South Texas Project – 44200 Hillje Ckt 1 | Matagorda | COASTAL | 2026-06-30 | PV | 200.94 | 2022-06-10 | 2022-09-06 | 2022-06-01 | 2023-12-18 |  | 2023-11-15
ERCOT | 24INR0338 | Eldora BESS | SS Completed, FIS Completed, IA | Eldora Energy LLC | 345 kV South Texas Project (Bus# 5915) – Hillje (Bus# 44200) Transmission Line Ckt 1 | Matagorda | COASTAL | 2026-06-30 | BA | 201.31 | 2022-06-10 | 2022-09-06 | 2022-06-01 | 2023-12-18 |  | 2023-11-15
ERCOT | 24INR0339 | Mystic Springs Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Tawakoni Park Solar LLC | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | Kaufman | NORTH | 2027-08-31 | PV | 258.83 | 2022-05-10 | 2022-08-06 | 2022-11-28 |  | No |  |  |  | COD
ERCOT | 24INR0340 | Mystic Springs Renewable Energy Storage SLF | SS Completed, FIS Started, No IA | Tawakoni Park Storage LLC | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | Kaufman | NORTH | 2027-08-31 | BA | 0 | 2022-05-10 | 2022-08-06 | 2022-11-28 |  | No |  |  |  | COD
ERCOT | 24INR0341 | Forts Trail BESS | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2027-07-29 | BA | 200.93 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  | No
ERCOT | 24INR0352 | Guinness BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | Tap 138kV 7520 BERTRA - 7522 ANDICE | Williamson | SOUTH | 2027-04-15 | BA | 100.51 | 2022-07-25 | 2022-10-20 | 2022-09-27
ERCOT | 24INR0353 | Exodus Solar | SS Completed, FIS Started, No IA | Exodus Solar LLC. | Tap 345kV 7040 Austrop – 7042 Zorn | Caldwell | SOUTH | 2026-05-01 | PV | 181.02 | 2022-06-10 | 2022-09-06 | 2022-05-20
ERCOT | 24INR0355 | Anatole Renewable Energy Storage | SS Completed, FIS Completed, IA | Eustace Storage LLC | (Bus# 6951) Eustace Southeast 138kV Substation (owned by Rayburn Electric Cooperative) | Henderson | NORTH | 2026-01-11 | BA | 207.82 | 2022-06-02 | 2022-08-30 | 2022-12-02 | 2024-01-22 |  | 2024-05-10 |  |  | SFS/NtP
ERCOT | 24INR0356 | Cibeles Solar | SS Completed, FIS Completed, No IA | Elawan Cibeles Solar, LLC | Tap 345kV 68090 Sam Switch – 13405 Tradinghouse SES | McLennan | NORTH | 2027-06-30 | PV | 251 | 2022-05-16 | 2022-08-13 |  | 2024-11-14
ERCOT | 24INR0358 | Blanket Ranch South Solar SLF | SS Completed, FIS Started, No IA | Blanket Ranch South Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | PV | 134.7 | 2022-06-10 | 2022-09-06 | 2022-11-17 |  | No
ERCOT | 24INR0360 | Blanket Ranch North Solar SLF | SS Completed, FIS Started, No IA | Blanket Ranch North Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | PV | 230.5 | 2022-06-10 | 2022-09-06 | 2022-11-29 |  | No
ERCOT | 24INR0361 | Blanket Ranch South Storage SLF | SS Completed, FIS Started, No IA | Blanket Ranch South Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | BA | 33.8 | 2022-06-10 | 2022-09-06 | 2022-11-17 |  | No
ERCOT | 24INR0362 | Blanket Ranch North Storage SLF | SS Completed, FIS Started, No IA | Blanket Ranch North Solar, LLC | Tap 345kV 11441 CORN TRAIL SWITCH - 1444 BROWN SWITCH | Brown | NORTH | 2028-06-15 | BA | 50.1 | 2022-06-10 | 2022-09-06 | 2022-11-29 |  | No
ERCOT | 24INR0364 | Pitts Dudik II | SS Completed, FIS Started, IA | Pitts Dudik II | 138 kV Ash Creek Switch (#3473) | Hill | NORTH | 2026-01-29 | PV | 30.23 | 2022-07-18 | 2022-10-14 | 2022-08-04 |  |  | 2024-06-13
ERCOT | 24INR0365 | XE Hermes Storage | SS Completed, FIS Completed, IA | Bell Solar 1 LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2025-09-30 | BA | 100.42 | 2022-07-18 | 2022-10-12 | 2022-06-30 | 2024-04-19 |  | 2023-11-08 |  |  | COD
ERCOT | 24INR0368 | Glory Bee Solar | SS Completed, FIS Completed, No IA | Riley Solar LLC | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2026-04-14 | PV | 305 | 2022-06-10 | 2022-09-06 | 2022-06-06 | 2023-04-18
ERCOT | 24INR0369 | Glory Bee Storage | SS Completed, FIS Completed, No IA | Riley Solar LLC | Tap 345kV 1440 Comanche Switch - 1900 Comanche Peak | Erath | NORTH | 2026-04-14 | BA | 101 | 2022-06-10 | 2022-09-06 | 2022-06-06 | 2023-04-18
ERCOT | 24INR0372 | GIGA AUSTIN SOLAR | SS Completed, FIS Started, No IA | GIGA TEXAS ENERGY LLC | 7047 HORNSBY Substation 138kV | Travis | SOUTH | 2025-03-14 | PV | -53.3 | 2022-07-18 | 2022-10-14 | 2022-07-26
ERCOT | 24INR0374 | Farrier Station Energy Storage | SS Completed, FIS Completed, No IA | Farrier Station Energy Storage Project, LLC | MONTICELLO SES (BUS# 1696) - ALLEN SWITCH (BUS# 2514) | Hopkins | NORTH | 2027-12-01 | BA | 409.9 | 2023-01-17 | 2023-04-14 | 2023-01-10 | 2024-06-03 | No
ERCOT | 24INR0375 | Possum Kingdom BESS | SS Completed, FIS Started, No IA | PK Solar, LLC | Tap 345kV 1421 Willow Creek – 11523 Thomas Price | Jack | NORTH | 2027-10-29 | BA | 200.86 | 2022-09-02 | 2022-11-29 |  |  | No
ERCOT | 24INR0376 | Huisache BESS | SS Completed, FIS Started, No IA | Huisache Solar, LLC | Tapping the Elm Creek to Shaula circuit 1 | Wilson | SOUTH | 2026-02-15 | BA | 100.67 | 2022-08-05 | 2022-11-01 | 2022-11-07
ERCOT | 24INR0378 | Solara BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2026-11-30 | BA | 150 | 2022-07-05 | 2022-10-01 | 2022-07-26
ERCOT | 24INR0379 | Solara BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2026-11-30 | BA | 150 | 2022-07-05 | 2022-10-01 | 2022-07-26
ERCOT | 24INR0380 | Photo BESS 3 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie Substation 138kV | Uvalde | SOUTH | 2026-09-01 | BA | 100 | 2022-07-25 | 2022-10-21 | 2022-07-26
ERCOT | 24INR0381 | Alexandrite Storage | SS Completed, FIS Started, No IA | Johnson Energy Storage, LLC | 8359 Santa Rosa (S_SNROSA4A) 138kV | Cameron | COASTAL | 2026-12-10 | BA | 203 | 2022-06-27 | 2022-09-22 | 2022-06-15
ERCOT | 24INR0382 | Remy Jade III Power Station | SS Completed, FIS Completed, IA | Remy Jade III Generating, LLC | Tap 138kV 40390 Crosby - 40811 Highlands | Harris | HOUSTON | 2027-01-16 | GT | 102 | 2022-07-18 | 2022-10-12 | 2022-07-07 | 2023-03-14 |  | 2022-08-01 |  |  | COD
ERCOT | 24INR0386 | Black & Gold Energy Storage | SS Completed, FIS Started, IA | Black & Gold Energy Storage, LLC | 6364 Yellow Jacket Sub 138kV | Menard | WEST | 2027-06-30 | BA | 254.58 | 2022-07-18 | 2022-10-14 | 2022-08-30 |  | No | 2024-08-14
ERCOT | 24INR0387 | PaleAle BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners,LLC | Tap 138 kV Bus 7506 L_CEDAVA8_1Y - Bus 7507 L_FRIEND8_1Y | Hays | SOUTH | 2027-04-15 | BA | 75.38 | 2022-07-18 | 2022-10-14 | 2022-12-06
ERCOT | 24INR0391 | Kennedy Storage | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2028-12-31 | BA | 25.3 | 2022-07-18 | 2022-10-12 | 2022-07-06 | [5 empty] | COD
ERCOT | 24INR0392 | Riverwalk BESS | SS Completed, FIS Started, No IA | RWE Solar Developement, LLC | 5294 Martinez Substation 138kV | Bexar | SOUTH | 2026-10-31 | BA | 120 | 2022-07-18 | 2022-10-14 | 2022-07-11
ERCOT | 24INR0393 | ELECTRODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | Castillo Substation, Bus number : 76040 | Upton | WEST | 2026-12-31 | BA | 150 | 2022-07-25 | 2022-10-21 | 2022-07-12
ERCOT | 24INR0394 | CATHODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 76635 King Mountain 138kV | Upton | WEST | 2026-12-31 | BA | 150 | 2022-08-05 | 2022-11-01 | 2022-07-12
ERCOT | 24INR0395 | Berkman Storage | SS Completed, FIS Completed, IA | Berkman Storage, LLC | 138 kV League City (Bus# 38920) | Galveston | HOUSTON | 2027-05-31 | BA | 150.86 | 2022-08-05 | 2022-11-01 | 2022-07-21 | 2023-06-27 |  | 2024-01-09 |  |  | COD
ERCOT | 24INR0397 | Destiny Storage | SS Completed, FIS Completed, IA | Destiny Storage, LLC | Tap 138kV 40390 Crosby - 40680 Placid Ckt 86 | Harris | HOUSTON | 2026-01-31 | BA | 205.57 | 2022-08-16 | 2022-11-11 | 2022-07-28 | 2024-01-26 | No | 2023-09-20
ERCOT | 24INR0399 | Buzios Solar | SS Completed, FIS Completed, IA | Roaring Springs Solar, LLC | Tap between Cottonwood (#59904) and White River (#23922) | Motley | PANHANDLE | 2026-06-30 | PV | 252 | 2022-09-15 | 2022-12-13 | 2022-08-04 | 2024-11-21 |  | 2023-11-06
ERCOT | 24INR0401 | Portside Energy Center (Solar) SLF | SS Completed, FIS Started, IA | Portside Energy Center, LLC | 80064 Chocolate Bayou 138kV | Victoria | SOUTH | 2026-12-31 | PV | 41.11 | 2022-11-15 | 2023-02-10 | 2022-11-01 |  |  | 2024-04-05
ERCOT | 24INR0403 | Portside Energy Center (BESS) SLF | SS Completed, FIS Started, IA | Portside Energy Center, LLC | 80064 Chocolate Bayou 138kV | Victoria | SOUTH | 2026-12-31 | BA | 41.11 | 2022-11-15 | 2023-02-10 | 2022-11-01 |  |  | 2024-04-05
ERCOT | 24INR0404 | Tres Rios Ranch Solar | SS Completed, FIS Started, No IA | LectricWind LLC | 76008 Twelvemile 345kV | Upton | WEST | 2027-12-31 | PV | 508 | 2022-08-05 | 2022-11-01
ERCOT | 24INR0405 | Crowned Heron BESS | SS Completed, FIS Completed, IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2025-07-31 | BA | 154.2 | 2022-07-18 | 2022-10-14 | 2022-07-12 | 2023-05-17 |  | 2023-06-26
ERCOT | 24INR0407 | Mercury Solar III | SS Completed, FIS Started, No IA | Mercury Solar | 68092 Liberty Station 345kV | Hill | NORTH | 2027-12-30 | PV | 203.5 | 2022-08-16 | 2022-11-11 | 2022-08-03
ERCOT | 24INR0408 | Pruett Storage | SS Completed, FIS Completed, No IA | Crandall Solar LLC | Tap 138kV 587 Greenwood - 685 Leo | Wise | NORTH | 2027-05-25 | BA | 50.48 | 2022-07-25 | 2022-10-18 | 2022-07-15 | 2024-06-14
ERCOT | 24INR0410 | NRG Greens Bayou 6 | SS Completed, FIS Completed, No IA | NRG Texas Power | Position 1/0 PSSE 40710, Greens Bayou Substation, 138 kV | Harris | HOUSTON | 2028-05-01 | GT | 445 | 2022-08-16 | 2022-11-11 | 2022-07-21 | 2023-11-27
ERCOT | 24INR0411 | Greens Bayou Unit 9 CT 345 | SS Completed, FIS Started, No IA | NRG Texas Power LLC | Position 1/0 PSSE 40700, Greens Bayou Substation | Harris | HOUSTON | 2026-06-02 | GT | 455 | 2022-09-21 | 2022-12-19 | 2022-09-16
ERCOT | 24INR0412 | Camino Ranch Solar SLF | SS Completed, FIS Started, No IA | Camino Ranch Solar Project LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | PV | 296.42 | 2022-10-06 | 2023-01-03
ERCOT | 24INR0413 | Furay Battery Energy Storage System | SS Completed, FIS Started, No IA | Blue Topaz 1, LLC | Tap 138kV 45660 Jonte substation – 46332 Scenic Woods Tapping both radial lines. | Harris | HOUSTON | 2026-11-24 | BA | 304 | 2022-09-02 | 2022-11-29 | 2022-09-01 |  | No
ERCOT | 24INR0416 | Trelas | SS Completed, FIS Started, No IA | Trelasol, LLC | 76006 Bow Wood 345kV Bus | McCulloch | SOUTH | 2028-05-01 | BA | 200.83 | 2022-09-02 | 2022-11-29 | 2022-08-15
ERCOT | 24INR0417 | Sierra Diablo Energy Storage | SS Completed, FIS Started, No IA | SIERRA DIABLO ENERGY STORAGE LLC | Tap 138kv 1698 Sulphur Springs Switch – 3174 Canton Switch | Van Zandt | NORTH | 2026-04-20 | BA | 203.81 | 2022-08-05 | 2022-11-01 | 2022-07-26
ERCOT | 24INR0418 | Middlebrook Solar | SS Completed, FIS Started, No IA | Middlebrook Solar LLC | Tap Stryker [3109] - Lufkin [3117] 345 kV line | Nacogdoches | NORTH | 2027-06-30 | PV | 316.19 | 2022-10-18 | 2023-01-13 | 2022-10-06
ERCOT | 24INR0419 | High Plains Storage | SS Completed, FIS Started, No IA | ROBP Holdings, LLC | 45880 Hockley 138kV | Harris | HOUSTON | 2026-10-30 | BA | 157.7 | 2022-09-02 | 2022-11-29 | 2022-08-18
ERCOT | 24INR0420 | Camino Ranch Storage SLF | SS Completed, FIS Started, No IA | Camino Solar Ranch, LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | BA | 298.06 | 2022-10-18 | 2023-01-03
ERCOT | 24INR0421 | Swift Air Solar | SS Completed, FIS Completed, IA | Swift Air Solar, LLC | Tap 138kV 1019 Moss Switch – 11128 Shin Oak POD | Ector | WEST | 2025-03-19 | PV | 146.5 | 2022-11-07 | 2023-02-03 | 2022-09-01 | 2024-02-13 | No | 2024-04-30
ERCOT | 24INR0422 | Hollow Branch Creek Solar | SS Completed, FIS Completed, IA | Hollow Branch Creek Solar LLC | Tap 345kV 3390 Jewett - 44645 Singleton | Leon | NORTH | 2027-12-31 | PV | 460 | 2022-09-02 | 2022-11-29 | 2022-08-15 | 2024-10-03 | Yes | 2024-10-22
ERCOT | 24INR0423 | Hollow Branch Creek Storage | SS Completed, FIS Completed, No IA | Hollow Branch Creek Solar LLC | Jewett – Singleton 345 kV [PTI Bus # 3390 – 44645] | Leon | NORTH | 2027-12-31 | BA | 460 | 2022-09-02 | 2022-11-29 | 2022-09-16 | 2024-10-03 | Yes
ERCOT | 24INR0424 | Cascabel Wind 1 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307) | Zapata | SOUTH | 2027-12-01 | WT | 197.75 | 2023-03-13 | 2023-06-09 | 2023-02-15
ERCOT | 24INR0425 | Two Brothers Battery Energy Storage System | SS Completed, FIS Started, IA | BRP Blue Topaz 2, LLC | 8911 BLKBYU4A 138kV | Victoria | SOUTH | 2026-12-01 | BA | 152 | 2022-09-15 | 2022-12-13 | 2022-09-14 |  | No | 2024-04-22
ERCOT | 24INR0426 | Leighton BESS SLF | SS Completed, FIS Started, No IA | Lavender Solar LLC | 99 BENHUR 69kV | Limestone | NORTH | 2026-10-17 | BA | 0 | 2022-09-21 | 2022-12-19 | 2022-09-16 |  | No
ERCOT | 24INR0427 | CPS AvR CT1 Rotor Replacement | SS Completed, FIS Completed, No IA | CPS Energy | 5475 Braunig 345kV | Bexar | SOUTH | 2025-01-31 | CC | 11.3 | 2022-10-24 | 2023-01-20 | 2022-09-20 | 2023-04-18 |  |  | 2023-12-04
ERCOT | 24INR0436 | Carambola BESS | SS Completed, FIS Started, IA | SMT McAllen II LLC | North Mcallen 138 kV Substation (N_MCALLN, Bus#8368) | Hidalgo | SOUTH | 2026-05-31 | BA | 97.43 | 2022-10-18 | 2023-01-13 | 2022-10-05 |  | No | 2023-07-31
ERCOT | 24INR0440 | Starling Solar Phase II | SS Completed, FIS Started, No IA | Starling Solar, LLC | tap 138kV 7224 Luling - 7245 Gonzales. Starling Solar Phase II is a an addition of 42.24MW to the 23INR0035 (solar) filed in 2020. 23INR0181 (storage) was filed in 2021. | Gonzales | SOUTH | 2027-05-15 | PV | 43.56 | 2022-10-06 | 2022-12-28
ERCOT | 24INR0442 | Midnight Sun Energy Storage | SS Completed, FIS Started, No IA | Midnight Sun Energy Storage, LLC | 6601 Rio Pecos 138kV | Crockett | WEST | 2027-07-01 | BA | 510 | 2022-12-07 | 2023-03-04 | 2022-11-18 |  | No
ERCOT | 24INR0444 | Hiru Storage | SS Completed, FIS Started, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2028-03-31 | BA | 503.8 | 2022-11-15 | 2023-02-10
ERCOT | 24INR0445 | PSE Flores TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | TAP 138KV 8793 RIO GRANDE CITY - 8798 LAGRULLA | Starr | SOUTH | 2027-07-31 | BA | 200 | 2022-12-15 | 2023-03-13
ERCOT | 24INR0446 | PSE Gongora Hill TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8796 Roma – 7870 Escobares | Starr | SOUTH | 2027-07-31 | BA | 200 | 2023-02-27 | 2023-03-13 | 2022-11-22
ERCOT | 24INR0447 | PSE Chihuahua TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8392 Bates – 8394 Liston | Hidalgo | SOUTH | 2027-07-31 | BA | 200 | 2022-12-07 | 2023-03-06 |  |  | No
ERCOT | 24INR0448 | PSE Minnesota TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8372 North Pharr – 8906 North Alamo | Hidalgo | SOUTH | 2027-07-31 | BA | 94 | 2022-11-15 | 2023-02-09
ERCOT | 24INR0449 | PSE Richardson TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc. | TAP 138KV 8374 SOUTH EAST EDINBURG - 8029 CLOSNER | Hidalgo | SOUTH | 2027-07-31 | BA | 100 | 2022-12-07 | 2023-03-06
ERCOT | 24INR0450 | Smokey Willie BESS SLF | SS Completed, FIS Completed, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2026-12-15 | BA | 0 | 2022-11-15 | 2023-02-09 | 2022-10-28 | 2023-09-22 | No
ERCOT | 24INR0452 | Longfellow Solar I | SS Completed, FIS Started, No IA | CENTURY GAS PROCESSING, LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2026-12-01 | PV | 178.2 | 2022-11-07 | 2023-02-03
ERCOT | 24INR0453 | Longfellow BESS I | SS Completed, FIS Completed, No IA | CENTURY GAS PROCESSING, LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2025-12-01 | BA | 54.99 | 2022-11-07 | 2023-02-03 |  | 2024-12-18
ERCOT | 24INR0454 | Longfellow Solar II | SS Completed, FIS Started, No IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY2_1 138 KV | Pecos | WEST | 2026-12-01 | PV | 207.36 | 2022-11-07 | 2023-02-03
ERCOT | 24INR0455 | Longfellow BESS II | SS Completed, FIS Completed, No IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY2_1 138 KV | Pecos | WEST | 2025-12-01 | BA | 105.75 | 2022-11-07 | 2023-02-03 |  | 2024-12-18
ERCOT | 24INR0456 | FRIENDSWOOD ENERGY GENCO | SS Completed, FIS Completed, IA | Tejas Power Generation LLC | 47170 H O CLARKE 138KV | Harris | HOUSTON | 2025-07-01 | GT | 143.7 | 2022-12-07 | 2023-03-06 |  | 2024-03-21 | No | 2024-04-23
ERCOT | 24INR0459 | Exodus BESS | SS Completed, FIS Started, No IA | Exodus Solar LLC | Tap 345kV 7040 Austrop – 7042 Zorn | Caldwell | SOUTH | 2026-05-01 | BA | 201.36 | 2023-07-10 | 2023-10-05 | 2023-06-30 | [5 empty] | COD
ERCOT | 24INR0460 | Evelyn Battery Energy Storage System | SS Completed, FIS Completed, IA | Evelyn Energy Storage LLC | Hidden Lakes 138kV (38900) | Galveston | HOUSTON | 2025-05-06 | BA | 221.3 | 2023-01-03 | 2023-03-30 | 2022-12-08 | 2024-07-29 |  | 2023-09-14
ERCOT | 24INR0461 | Augie BESS | SS Completed, FIS Completed, No IA | BRP Blue Topaz 5, LLC | 46560 Waller 138kV | Waller | HOUSTON | 2026-11-30 | BA | 200.81 | 2023-01-23 | 2023-04-22 | 2023-01-18 | 2024-01-24 | No
ERCOT | 24INR0462 | Ventana Ranch Solar | SS Completed, FIS Started, No IA | Monarch Energy Development LLC | Tap 345 kV Lon Hill (Bus# 8455) -- North Edinburg (Bus# 8905) | Jim Wells | SOUTH | 2026-12-01 | PV | 502.03 | 2022-11-15 | 2023-02-10 | 2022-11-10 |  | Yes
ERCOT | 24INR0471 | McGee Storage | SS Completed, FIS Completed, No IA | BT McGee Storage, LLC | Bus #6843 at Rayburn Barton Chapel Substation | Henderson | NORTH | 2026-05-29 | BA | 151.39 | 2022-11-15 | 2023-02-09 | 2022-11-09 | 2024-05-30 | No
ERCOT | 24INR0472 | Amador Storage | SS Completed, FIS Completed, IA | BT Amador Storage, LLC | 6833 Explorer Switching Station 138kV | Van Zandt | NORTH | 2025-12-31 | BA | 102.58 | 2022-11-23 | 2023-02-17 | 2022-11-18 | 2024-12-18 | No | 2023-11-02 |  |  | SFS/NtP
ERCOT | 24INR0473 | Hooper Solar | SS Completed, FIS Completed, No IA | BT Brown Solar, LLC | Tap 138kV line between Lexington (Bus #7571) and Lyle Wolz (Bus #7567) | Lee | SOUTH | 2026-01-15 | PV | 50.48 | 2022-12-07 | 2023-03-06 | 2022-11-03 | 2024-02-20 | No
ERCOT | 24INR0474 | Hooper Storage | SS Completed, FIS Completed, No IA | BT Brown Solar, LLC | Tap 138kV line between Lexington (Bus #7571) and Lyle Wolz (Bus #7567) | Lee | SOUTH | 2026-01-15 | BA | 30.68 | 2022-12-07 | 2023-03-06 | 2022-11-23 | 2024-02-20 | No
ERCOT | 24INR0476 | DOS RIOS ENERGY STORAGE SLF | SS Completed, FIS Completed, No IA | DOS RIOS SOLAR, LLC | TAP 69 KV 61 BRANCHVILLE -- 65 SILVER CITY | Milam | SOUTH | 2027-03-15 | BA | 164.5 | 2022-11-15 | 2023-02-11 |  | 2024-10-24
ERCOT | 24INR0477 | Barrett Solar | SS Completed, FIS Completed, IA | Barrett Solar Project, LLC | Tap 6798 SNYPT_RC - 6797 LNOK_RC 138kV line | Rains | NORTH | 2025-12-31 | PV | 125.81 | 2023-02-27 | 2023-05-26 | 2023-02-22 | 2023-10-02 | No | 2023-10-05
ERCOT | 24INR0479 | NRG THW GT 138 | SS Completed, FIS Started, No IA | NRG THW GT LLC | 138 kV Bus Number: 45515, Bus Name: T_H_W__POI_8 | Harris | HOUSTON | 2026-06-05 | GT | 458 | 2022-11-22 | 2023-02-17 | 2022-11-17 |  | No
ERCOT | 24INR0482 | NRG THW GT 345 | SS Completed, FIS Completed, IA | NRG THW GT LLC | 345 kV Bus Number: 45500, Bus Name: T_H_W__POI_5 | Harris | HOUSTON | 2026-05-01 | GT | 456 | 2022-11-17 | 2023-02-09 | 2022-11-17 | 2024-02-05 | No | 2024-08-22
ERCOT | 24INR0484 | Lupinus Solar 3 | SS Completed, FIS Completed, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap 138 kV | Franklin | NORTH | 2026-09-21 | PV | 100.8 | 2023-09-23 | 2023-12-20 | 2023-09-13 | 2024-06-26 | No
ERCOT | 24INR0485 | Rutile BESS | SS Completed, FIS Started, No IA | Rutile BESS, LLC | Tap 138kV 6340 BALLINGER - 60399 WEISS | Runnels | WEST | 2028-03-31 | BA | 100.65 | 2023-01-23 | 2023-04-22 |  |  | No |  |  |  | COD
ERCOT | 24INR0488 | Forts Trail BESS 2 | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345 kV | Taylor | WEST | 2027-07-29 | BA | 201.2 | 2023-02-20 | 2023-05-20 | 2023-02-01 |  | No
ERCOT | 24INR0490 | Lupinus Storage 3 | SS Completed, FIS Completed, No IA | Lupinus Solar 2, LLC | 1794 Monticello Tap Substation 138 kV | Franklin | NORTH | 2026-09-21 | BA | 50.9 | 2023-09-23 | 2023-12-20 | 2023-09-13 | 2024-06-26 | No
ERCOT | 24INR0491 | Gunnar BESS | SS Completed, FIS Started, IA | BRP Blue Topaz 6, LLC | 8029 CLOSNER4A 138kV | Hidalgo | SOUTH | 2025-12-01 | BA | 203 | 2023-02-09 | 2023-05-05 | 2023-01-30 |  |  | 2023-09-22
ERCOT | 24INR0493 | Crowned Heron BESS 2 | SS Completed, FIS Completed, IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2025-07-31 | BA | 154.2 | 2022-11-23 | 2023-02-17 | 2022-11-15 | 2024-01-28 | No | 2024-08-20
ERCOT | 24INR0494 | Hana Springs BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II LLC | 7064 LAMPASAS 138KV | Lampasas | NORTH | 2027-12-15 | BA | 100.8 | 2022-11-23 | 2023-02-17 | 2022-11-18 | [5 empty] | COD
ERCOT | 24INR0495 | Barbers Hill BESS | SS Completed, FIS Completed, No IA | Black Mountain Energy Storage II | 40850 JORDAN 345kV | Chambers | HOUSTON | 2027-07-15 | BA | 307.72 | 2023-01-17 | 2023-04-14 | 2022-12-27 | 2024-04-05 | No
ERCOT | 24INR0496 | Indigo Storage | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | BA | 60 | 2022-12-15 | 2023-03-13
ERCOT | 24INR0498 | Fort Watt Storage | SS Completed, FIS Completed, IA | Fort Watt Storage, LLC | Tap 138kV 1933 Kennedale - 2208 Mansfield | Tarrant | NORTH | 2027-04-20 | BA | 201.4 | 2023-01-03 | 2023-03-30 | 2022-12-07 | 2024-07-09 | No | 2024-08-28
ERCOT | 24INR0500 | Claire BESS | SS Completed, FIS Completed, No IA | BRP Blue Topaz 3, LLC | 40011 Cedar Bayou 138kV | Harris | HOUSTON | 2026-11-30 | BA | 406.01 | 2023-02-09 | 2023-05-08 | 2023-01-30 | 2024-01-24
ERCOT | 24INR0505 | Corralitos Wind 1 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2027-12-01 | WT | 196.1 | 2023-01-30 | 2023-04-28 | 2023-01-19 | [5 empty] | COD
ERCOT | 24INR0506 | Corralitos Wind 2 | SS Completed, FIS Started, No IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2027-12-31 | WT | 195.4 | 2023-01-30 | 2023-04-28 | 2023-01-19 | [5 empty] | COD
ERCOT | 24INR0507 | Young Wind II SLF | SS Completed, FIS Started, No IA | Young Wind II, LLC | Oncor's Thomas Price Station (#11523) | Young | WEST | 2026-03-08 | WT | 152.28 | 2023-05-03 | 2023-07-31 | 2023-04-26
ERCOT | 24INR0508 | White Oak King Wind | SS Completed, FIS Started, No IA | White Oak Energy, LLC | To 345 kV Gauss ( Bus # 60701) | King | WEST | 2026-03-01 | WT | 606.5 | 2023-03-09 | 2023-06-05 | 2023-02-07 |  | No
ERCOT | 24INR0514 | Rogers Draw BESS | SS Completed, FIS Not Started, IA | ROGERS DRAW ENERGY STORAGE, LLC | 7751 Headwaters substation 138kV | Gillespie | SOUTH | 2026-05-10 | BA | 145.55 | 2023-01-03 | 2023-03-30 |  |  |  | 2024-02-28
ERCOT | 24INR0516 | French Riviera Storage | SS Completed, FIS Started, No IA | Arana Creek Battery Storage LLC | 5646 Riviera Substation 69kV | Kleberg | COASTAL | 2028-05-01 | BA | 75 | 2023-02-09 | 2023-05-05 | 2023-01-21
ERCOT | 24INR0519 | Roost Energy Storage | SS Completed, FIS Started, No IA | Bluff Creek Energy Storage LLC | KNDRSACRC Bus #11130 to Knapp Substation Bus #1310 | Scurry | WEST | 2026-09-15 | BA | 102.36 | 2023-01-30 | 2023-04-28 | 2023-01-21
ERCOT | 24INR0528 | Blanquilla BESS | SS Completed, FIS Not Started, IA | Blanquilla BESS LLC | Tap 138kV 8452 LON_HILL4A - 8441 NUECES_B4A | Nueces | COASTAL | 2026-05-15 | BA | 200.78 | 2023-02-09 | 2023-05-08 |  |  |  | 2024-09-05
ERCOT | 24INR0530 | Southside Energy | SS Completed, FIS Started, No IA | Southside Energy, LLC | Tap 138kV 42960 Mustang Bayou - 42100 HUDSON ckt 4 | Brazoria | COASTAL | 2026-06-15 | BA | 101.2 | 2023-02-27 | 2023-05-26
ERCOT | 24INR0532 | Timber Cove Solar SLF | SS Completed, FIS Started, No IA | Freestone Solar, LLC | Tap 138 kV 212 Winkler - 3510 Pin Oak | Freestone | NORTH | 2027-04-01 | PV | 100.5 | 2023-05-22 | 2023-08-17 | 2023-05-17
ERCOT | 24INR0533 | Padua Grid BESS Unit 2 | SS Completed, FIS Started, No IA | Padua Grid, LLC | 5395 Sommers 138kV | Bexar | SOUTH | 2026-08-31 | BA | 150.94 | 2023-06-07 | 2023-09-01 | 2023-06-01 | [5 empty] | COD
ERCOT | 24INR0534 | Lyford Energy | SS Completed, FIS Started, No IA | Lyford Energy, LLC | 5745 E Raymondville 138kV | Willacy | COASTAL | 2025-09-15 | BA | 101.2 | 2023-03-08 | 2023-06-05
ERCOT | 24INR0538 | FLIFER Solar I | SS Completed, FIS Started, No IA | FLIFER LLC | Tap 138 kV Yucca Drive Switch (bus# 1009) – Sand Tank (bus# 11197) | Ward | WEST | 2027-04-15 | PV | 84 | 2023-03-08 | 2023-06-01
ERCOT | 24INR0541 | Kinney County Energy | SS Completed, FIS Started, No IA | Kinney County Energy, LLC | Tap 138kV 8252 Brackett4A - 78255 L_PINTCR8_1Y | Kinney | SOUTH | 2027-05-15 | BA | 101.2 | 2023-03-27 | 2023-06-19
ERCOT | 24INR0543 | Thomas Cameron BESS | SS Completed, FIS Completed, No IA | Thomas Cameron BESS LLC | Tap 345kV 3424 BUCKHORN SWITCH - 3422 KILLEEN SWITCH | Lampasas | NORTH | 2027-05-03 | BA | 201.52 | 2023-06-07 | 2023-09-01 | 2023-06-02 | 2024-07-23 | No
ERCOT | 24INR0544 | Wetzel BESS | SS Completed, FIS Started, No IA | Brown ESS, LLC | Tap 138kV 1654 Zephyr – 1655 Brownwood Switch | Brown | NORTH | 2026-09-15 | BA | 185.57 | 2023-03-27 | 2023-06-20 | 2023-03-15
ERCOT | 24INR0550 | Mercedes II BESS | SS Completed, FIS Started, No IA | SMT Mercedes II, LLC | TAP NORTH MERCEDES (BUS #8358) and NORTH WESLACO (BUS# 8357) | Hidalgo | SOUTH | 2025-10-09 | BA | 227.87 | 2023-05-15 | 2023-08-11 | 2023-05-08
ERCOT | 24INR0555 | Shaula I BESS | SS Completed, FIS Started, No IA | Shaula Energy Project LLC | 5380 Shaula 345kV | DeWitt | SOUTH | 2025-12-31 | BA | 86.88 | 2023-07-10 | 2023-10-05 | 2023-07-03
ERCOT | 24INR0557 | Hovey Energy Storage | SS Completed, FIS Started, No IA | Barilla Solar, LLC | 60385 Solstice 138kV | Pecos | WEST | 2026-12-31 | BA | 23 | 2023-07-10 | 2023-10-02 | 2023-06-15 | [5 empty] | COD
ERCOT | 24INR0558 | Parthenon Energy | SS Completed, FIS Started, No IA | Parthenon Energy, LLC | Tap 138kV 88380 RGTAP4A - 8896 RACHAL4A | Hidalgo | SOUTH | 2026-06-15 | BA | 101.2 | 2023-04-19 | 2023-07-14 |  |  | No
ERCOT | 24INR0559 | Nerva Energy Storage | SS Completed, FIS Started, No IA | Nerva Energy Storage, LLC | Tap 138kV 402410 BURKE_POI_8 - 42430 EGLNST_POI_8 CKT#02 | Brazoria | COASTAL | 2026-06-15 | BA | 101.2 | 2023-04-19 | 2023-07-14 |  |  | No
ERCOT | 24INR0567 | Wolf Hollow III | SS Completed, FIS Completed, No IA | Wolf Hollow II Power LLC | 1877 Mitchell Bend 345KV | Hood | NORTH | 2026-05-31 | GT | 306.32 | 2023-06-07 | 2023-09-01 | 2023-05-30 | 2024-06-03
ERCOT | 24INR0568 | Shamrock Energy Storage (SLF) | SS Completed, FIS Completed, IA | Shamrock Interconnection LLC | 76004 Single Tree 345kV | Crockett | WEST | 2025-03-31 | BA | 0 | 2023-07-18 | 2023-10-15 | 2023-07-11 | 2024-04-30 | No | 2022-05-11 | 2024-11-13
ERCOT | 24INR0569 | Hadrian Energy Storage | SS Completed, FIS Started, No IA | Hadrian Energy Storage, LLC | Line Tap 138kV #43012 NEWGLF60T3_8 - #43190 S_LANE_B138 | Wharton | SOUTH | 2026-06-15 | BA | 101.2 | 2023-05-15 | 2023-08-11
ERCOT | 24INR0570 | Marcus Energy Storage | SS Completed, FIS Completed, No IA | Marcus Energy Storage, LLC | Tap 138kV 39500 West Columbia Main - 110505 Sweeny Co-Gen LP Ckt 1 | Brazoria | COASTAL | 2026-09-01 | BA | 201.04 | 2023-06-07 | 2023-09-01 |  | 2024-09-30
ERCOT | 24INR0572 | Harlingen III BESS | SS Completed, FIS Started, No IA | SMT Harlingen III LLC | 8320 WEST HARLINGEN 69kV | Cameron | COASTAL | 2027-07-01 | BA | 110 | 2023-06-28 | 2023-09-20 | 2023-06-26 | [5 empty] | COD
ERCOT | 24INR0576 | Boling Generation | SS Completed, FIS Started, No IA | Boling Generation | 43340 Gulftie 138kV | Wharton | SOUTH | 2027-05-20 | GT | 400 | 2023-12-04 | 2024-03-01 | 2023-11-02
ERCOT | 24INR0578 | Panther Creek 1 Repower | SS Completed, FIS Completed, No IA | Panther Creek Wind Farm I&II, LLC | 1058 Longshore 345kV | Glasscock | WEST | 2024-12-31 | WT | 11 | 2023-06-28 | 2023-09-21 | 2023-06-21 | 2024-05-03 |  |  | 2024-10-02
ERCOT | 24INR0582 | Panther Creek 2 Repower | SS Completed, FIS Completed, No IA | Panther Creek Wind Farm I&II, LLC | Longshore 345kV [Bus# 1058] | Glasscock | WEST | 2024-12-31 | WT | 8 | 2023-06-28 | 2023-09-21 | 2023-06-27 | 2024-05-03 |  |  | 2024-10-02
ERCOT | 24INR0584 | Houston IV BESS | SS Completed, FIS Completed, IA | SMT Houston IV LLC | 44140 CLODINE 138kV | Harris | HOUSTON | 2026-06-03 | BA | 168.6 | 2023-07-10 | 2023-10-05 | 2023-06-27 | 2024-04-19 |  | 2024-11-07 |  |  | SFS/NtP
ERCOT | 24INR0589 | Antoninus Energy Storage | SS Completed, FIS Started, No IA | Antoninus Energy Storage, LLC | Tap 138kV #43190 S_LANE_B138 - #42985 DYANN_POI_8 Transmission Line. | Wharton | SOUTH | 2026-06-15 | BA | 101.2 | 2023-06-28 | 2023-09-24
ERCOT | 24INR0605 | TEXAS GULF SULPHUR REPOWER | SS Completed, FIS Completed, IA | Wharton County Generation, LLC | 43340 Gulftie 138 kV | Wharton | SOUTH | 2024-06-25 | GT | 16.1 | 2023-07-31 | 2023-10-27 | 2023-07-27 | 2024-02-01 |  | 2022-03-01
ERCOT | 24INR0609 | Rodeo Ranch Energy Storage Repowering | SS Completed, FIS Completed, IA | Rodeo Ranch Energy Storage, LLC | 38021 WORSHAM 138kV | Reeves | WEST | 2024-11-12 | BA | 10 | 2023-08-22 | 2021-11-18 | 2023-10-12 | 2022-07-28 |  | 2022-02-01 | 2024-06-05
ERCOT | 24INR0616 | GridGuardian BESS | SS Completed, FIS Started, No IA | SMT Temple BESS LLC | 3412 TEMPLE PECAN CREEK 345kV | Bell | NORTH | 2027-04-19 | BA | 227.99 | 2023-09-22 | 2023-12-14 | 2023-09-11
ERCOT | 24INR0617 | Serrano Storage | SS Completed, FIS Started, No IA | Maverick ESS, LLC | 8267 GANSO Substation 138kV | Maverick | SOUTH | 2026-12-01 | BA | 185.59 | 2023-09-23 | 2023-12-20 | 2023-08-31
ERCOT | 24INR0627 | Champion Wind Repower | SS Completed, FIS Completed, IA | Champion Wind Farm, LLC | Bus# 1048 - Tonkawa | Nolan | WEST | 2025-05-09 | WT | 0.31 | 2023-09-25 | 2023-12-21 | 2023-09-13 | 2024-04-26 |  | 2007-01-19
ERCOT | 24INR0629 | Jade Storage SLF | SS Completed, FIS Completed, IA | IP LUMINA BESS, LLC | 59911 MHOS 345kV | Scurry | WEST | 2025-01-10 | BA | 0 | 2023-11-14 | 2024-02-09 | 2023-11-01 | 2024-03-29 |  | 2024-03-28 | 2024-08-09 |  | COD
ERCOT | 24INR0630 | Andromeda Storage SLF | SS Completed, FIS Completed, IA | IP Lumina II BESS, LLC | 60011 Nebulast 345kV | Scurry | WEST | 2025-02-21 | BA | 0 | 2023-10-25 | 2024-01-22 | 2023-10-17 | 2024-07-30 |  | 2024-04-18 |  |  | COD
ERCOT | 24INR0631 | Radian Storage SLF | SS Completed, FIS Started, IA | IP Radian BESS, LLC | 345 kV Brown Switch (Bus# 1444) | Brown | NORTH | 2025-02-21 | BA | 0 | 2023-10-25 | 2024-01-22 | 2023-10-17 |  | No | 2024-06-20 |  |  | COD
ERCOT | 24INR0632 | Cedro Hill Wind Repower | SS Completed, FIS Completed, IA | CEDRO HILL WIND LLC | 80439 LA QUINTA 138kV | Webb | SOUTH | 2024-12-28 | WT | 9.93 | 2023-09-28 | 2023-12-20 | 2023-09-28 | 2023-11-22 |  | 2009-09-09 | 2024-09-11
ERCOT | 24INR0635 | Ebony Energy Storage Repowering | SS Completed, FIS Started, No IA | Ebony Energy Storage, LLC | 5180 Green Mountain 138kV | Comal | SOUTH | 2024-12-02 | BA | 5 | 2021-02-04 | 2021-04-21 | 2023-10-26
ERCOT | 24INR0636 | Anemoi Energy Storage Repowering | SS Completed, FIS Started, No IA | Anemoi Energy Storage, LLC | 8574 POMELO 345kV | Hidalgo | SOUTH | 2025-02-28 | BA | 5 | 2023-10-30 | 2024-01-26 | 2023-10-23 | [5 empty] | COD
ERCOT | 24INR0763 | Team Ranch Storage | SS Completed, FIS Started, No IA | BAF Storage, LLC | 1869 Benbrook Switch 345kV | Tarrant | NORTH | 2026-10-01 | BA | 307.2 | 2024-06-13 | 2024-08-07 | 2024-06-05
ERCOT | 25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2028-07-15 | OT | 50 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  | No
ERCOT | 25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2028-07-15 | OT | 50 | 2019-01-30 | 2019-04-17 | 2019-08-09
ERCOT | 25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2028-07-15 | OT | 50 | 2019-01-30 | 2019-04-17 | 2019-08-09
ERCOT | 25INR0008 | BasRanch | SS Completed, FIS Started, No IA | CPV Basin Ranch, LLC | tap 345kV Riverton Switch - Sand Lake Switch | Ward | WEST | 2028-03-01 | CC | 1350 | 2020-08-04 | 2020-11-02 | 2021-10-28
ERCOT | 25INR0010 | Nockenut Springs Solar 3 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Gonzales | SOUTH | 2027-05-05 | PV | 203.39 | 2020-09-25 | 2020-12-16 | 2020-09-11
ERCOT | 25INR0018 | Yellow Cat Wind | SS Completed, FIS Completed, IA | Yellow Cat Wind LLC | Tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2026-09-30 | WT | 301.2 | 2021-08-17 | 2021-11-05 | 2022-03-07 | 2024-01-23 | No | 2024-07-09 |  |  | MW Size COD
ERCOT | 25INR0021 | Findley Solar | SS Completed, FIS Completed, No IA | Gransolar Texas Sixteen, LLC | 107 Prairie Hill 69 kV | Limestone | NORTH | 2028-01-01 | PV | 50.34 | 2021-10-05 | 2021-12-10 | 2022-05-24 | 2024-05-03 | No
ERCOT | 25INR0024 | Itsee Solar | SS Completed, FIS Started, No IA | Gransolar Texas Seventeen, LLC | Trinidad Switch – Long Prairie Switch 138 kV | Navarro | NORTH | 2027-07-01 | PV | 52.9 | 2021-10-12 | 2022-01-03 | 2022-05-24
ERCOT | 25INR0029 | Whistle Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nineteen, LLC | Tap 138kV 213 Haney – 3478 Navarro | Navarro | NORTH | 2026-05-30 | PV | 56.3 | 2021-11-23 | 2022-02-18 | 2022-08-05
ERCOT | 25INR0039 | Borderland ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | tap 138kV 8380 NEDIN4A – 8632 NMCALLEN4C | Hidalgo | SOUTH | 2026-06-30 | BA | 200 | 2022-02-21 | 2022-05-22 | 2022-02-08
ERCOT | 25INR0040 | McMEXICO STORAGE | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8644 Trade Zone 138kV | Hidalgo | SOUTH | 2026-12-01 | BA | 201.9 | 2022-02-28 | 2022-05-27 | 2022-02-15 |  | No
ERCOT | 25INR0045 | Smith Lake Storage DC | SS Completed, FIS Started, No IA | Smith Lake Solar | Tap 345kV 44645 Singleton - 44900 Zenith Ckt #99 | Grimes | NORTH | 2026-11-30 | BA | 65 | 2022-03-07 | 2022-05-06 | 2022-11-02 |  | Yes
ERCOT | 25INR0046 | Blue Skies BESS | SS Completed, FIS Started, IA | ACTX BESS Project LLC | 68090 SAM SW 345kV | Hill | NORTH | 2027-12-31 | BA | 309 | 2022-05-10 | 2022-08-06 | 2022-04-15 |  |  | 2024-08-12
ERCOT | 25INR0052 | SanPat Solar II | SS Completed, FIS Started, IA | CGRP 04, LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2027-07-31 | PV | 256.23 | 2022-02-28 | 2022-05-27 | 2022-07-15 |  | Yes | 2023-10-18
ERCOT | 25INR0054 | Sandman Power Storage | SS Completed, FIS Started, No IA | ALPIN HOLDING LLC | 1685 Farmersville Switch 345kV | Collin | NORTH | 2026-04-01 | BA | 100 | 2022-03-21 | 2022-06-16 | 2022-03-14 |  | No
ERCOT | 25INR0055 | Three W Solar | SS Completed, FIS Completed, IA | Three W Solar LLC | tap 138kV 3522 Hillboro1_8 - 237 Blanton CKT 1 | Hill | NORTH | 2026-06-01 | PV | 110.89 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-01-04 |  | 2023-03-28
ERCOT | 25INR0057 | Sombrero Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | Tap 345kV 76003 Big Hill - 60708 Orsted | Schleicher | WEST | 2026-05-31 | PV | 351.85 | 2022-03-30 | 2022-06-26 | 2023-01-03 |  | Yes
ERCOT | 25INR0060 | Argenta Solar | SS Completed, FIS Started, IA | Charter Oak Solar, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2027-07-01 | PV | 270 | 2022-06-27 | 2022-09-21 | 2022-07-14 |  |  | 2024-04-05
ERCOT | 25INR0061 | Argenta Storage | SS Completed, FIS Started, IA | Charter Oak Storage, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2027-07-01 | BA | 192 | 2022-06-27 | 2022-09-21 | 2022-07-13 |  |  | 2024-04-05
ERCOT | 25INR0068 | High Chap Solar | SS Completed, FIS Started, IA | HIGH CHAPARRAL SOLAR PROJECT LLC | 43035 Oasis 345kV - 42500 Dow Chemical 345 kV Ckt 18 | Brazoria | COASTAL | 2027-08-04 | PV | 152.25 | 2022-07-05 | 2022-10-01 | 2022-06-17 |  | Yes | 2023-11-21
ERCOT | 25INR0071 | Albatross BESS | SS Completed, FIS Started, No IA | Albatross Solar, LLC | From Bus #165 Windsor Switch To Bus #161 McGregor | McLennan | NORTH | 2028-02-22 | BA | 50.4 | 2022-05-16 | 2022-08-13 | 2022-10-25 |  | No |  |  |  | COD
ERCOT | 25INR0072 | High Chap Storage | SS Completed, FIS Started, No IA | HIGH CHAPARRAL SOLAR PROJECT LLC | 43035 Oasis 345kV - 42500 Dow Chemical 345 kV Ckt 18 | Brazoria | COASTAL | 2027-08-04 | BA | 71.78 | 2022-07-25 | 2022-10-21 | 2022-07-07 |  | Yes
ERCOT | 25INR0073 | Saltillo Storage | SS Completed, FIS Started, No IA | SALTILLO STORAGE | 7331 Cedarhill Substation 138kV | Bastrop | SOUTH | 2026-06-01 | BA | 101 | 2022-05-10 | 2022-08-05 | 2022-04-25
ERCOT | 25INR0076 | Violet Storage | SS Completed, FIS Started, No IA | VIOLET STORAGE | McKenzie Road (8858) 138 kV Substation | Nueces | COASTAL | 2026-07-01 | BA | 151 | 2022-05-10 | 2022-08-06 | 2022-04-14 |  | No
ERCOT | 25INR0078 | Peregrine BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 8673 RAPTOR7A 345kV | Goliad | SOUTH | 2027-07-01 | BA | 150 | 2022-08-05 | 2022-11-01 | 2022-08-02
ERCOT | 25INR0080 | Meitner Solar | SS Completed, FIS Started, IA | IP Meitner, LLC | 345 kV Gray (Bus# 79000) | Gray | PANHANDLE | 2027-12-20 | PV | 702.64 | 2022-08-05 | 2022-11-01 | 2022-07-27 |  | Yes | 2024-01-31
ERCOT | 25INR0081 | SanPat Solar I | SS Completed, FIS Started, IA | Padre Solar LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2026-12-31 | PV | 308.88 | 2022-07-18 | 2022-10-12 | 2022-07-15 |  | Yes | 2023-10-18
ERCOT | 25INR0082 | Reis Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Reis LLC | Tapping into 138 kV line (5689) Choke Canyon AEP to (5902) San Miguel Gen | Atascosa | SOUTH | 2027-08-03 | PV | 105.48 | 2022-06-02 | 2022-08-29 | 2022-09-09
ERCOT | 25INR0097 | Soleil Solar | SS Completed, FIS Started, No IA | Soleil Solar, LLC | Tap 345 kV 1730 Krum West Switch - 6111 Riley ckt 2 | Clay | WEST | 2027-10-01 | PV | 728.72 | 2022-09-02 | 2022-11-29 | 2022-08-26 |  | No
ERCOT | 25INR0098 | Soleil Storage | SS Completed, FIS Started, No IA | Soleil Solar, LLC | Tap 345 kV 1730 Krum West Switch - 6111 Riley ckt 2 | Clay | WEST | 2027-10-01 | BA | 301.64 | 2022-09-02 | 2022-11-29 | 2022-08-30 |  | No |  |  |  | COD
ERCOT | 25INR0100 | Goldeneye BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 3423 KILLEEN Switch 138 KV | Bell | NORTH | 2026-12-15 | BA | 201.6 | 2022-06-10 | 2022-09-06 | 2022-07-13 | 2023-08-18 | No | 2024-02-26
ERCOT | 25INR0101 | Mallard BESS | SS Completed, FIS Started, No IA | Mallard Energy Storage LLC | 818 Olinger 138kV | Collin | NORTH | 2026-04-01 | BA | 251 | 2022-06-02 | 2022-08-29 | 2022-06-17
ERCOT | 25INR0102 | Austin Bayou Solar | SS Completed, FIS Completed, IA | Austin Bayou Solar, LLC | Tap 345kV 42500 DOW CHEMICAL - 43035 OASIS CKT#27 | Brazoria | COASTAL | 2027-06-01 | PV | 753.4 | 2022-06-27 | 2022-09-21 | 2022-07-26 | 2023-03-29 | No | 2023-11-15
ERCOT | 25INR0103 | Elio BESS | SS Completed, FIS Completed, IA | Elio Energy LLC | Tap 138kV 42980 Nash - 44010 Wa Parish circuit 02 | Brazoria | COASTAL | 2026-12-02 | BA | 317.2 | 2022-07-05 | 2022-10-01 |  | 2024-10-31 |  | 2024-09-15
ERCOT | 25INR0105 | Diver Solar SLF | SS Completed, FIS Completed, IA | Diver Solar | Tap 345kV 3384 St Johns - 3390 Jewett | Limestone | NORTH | 2026-06-30 | PV | 225.59 | 2022-09-02 | 2022-11-29 | 2022-06-28 | 2024-11-09 | No | 2023-10-27
ERCOT | 25INR0106 | Luthor Solar | SS Completed, FIS Started, No IA | TREX US Luthor LLC | Tap 138kV 23831 Luther Station – 10032 Little Luther | Howard | WEST | 2026-09-05 | PV | 101 | 2022-06-27 | 2022-09-21
ERCOT | 25INR0109 | Sun Cactus Solar | SS Completed, FIS Started, IA | Sun Cactus Solar Project, LLC | tap 138kV 8510 Falfurrias - 8695 Crestonio | Duval | SOUTH | 2026-08-31 | PV | 120.63 | 2022-07-05 | 2022-10-01 | 2022-06-20 |  |  | 2023-11-06
ERCOT | 25INR0112 | August Draw Energy | SS Completed, FIS Started, No IA | DBR Solar, LLC | Tap 138kV 60207 Verhalen – 60808 Hoefs Road | Reeves | WEST | 2028-06-27 | PV | 250 | 2022-09-15 | 2022-12-13 |  |  | No |  |  |  | COD
ERCOT | 25INR0122 | Vial BESS | SS Completed, FIS Started, No IA | Gransolar Texas Eleven LLC | Chatt(234) - Pecan Street (3352) 138kV | Hill | NORTH | 2027-09-15 | BA | 135.18 | 2022-07-05 | 2022-10-01 | [6 empty] | COD
ERCOT | 25INR0128 | Fiji Solar | SS Completed, FIS Started, No IA | Fiji Solar | Groesbeck Main (#3634) to Mexia (#3632) 138 kV line tap (Oncor Electric Delivery) | Limestone | NORTH | 2028-08-30 | PV | 202.7 | 2022-09-27 | 2022-12-19 | 2022-09-19
ERCOT | 25INR0129 | Demeter Solar | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 LOCKHART | Caldwell | SOUTH | 2026-03-28 | PV | 88 | 2022-08-05 | 2022-11-01
ERCOT | 25INR0130 | Demeter Storage | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 Lockhart | Caldwell | SOUTH | 2026-03-28 | BA | 65 | 2022-08-05 | 2022-11-01
ERCOT | 25INR0131 | SOSA Storage | SS Completed, FIS Completed, IA | SOSA Energy Center LLC | Tap 138kV 25 North Zulch - 47 Hilltop Lakes | Madison | NORTH | 2026-03-31 | BA | 157.36 | 2022-07-25 | 2022-10-20 | 2022-07-21 | 2023-09-21 | No | 2023-12-05
ERCOT | 25INR0133 | Rose Quartz BESS | SS Completed, FIS Started, No IA | Rose Quartz BESS, LLC | Tap 138kV 8283 Asherton - 8613 Bigwells | Dimmit | SOUTH | 2026-12-01 | BA | 101.41 | 2022-09-02 | 2022-11-30 | 2022-10-14
ERCOT | 25INR0134 | Hoskins Solar | SS Completed, FIS Started, No IA | SGT HOSKINS SOLAR PROJECT, LLC | TAP 138 kV 1687 BLOSSOM_T8 - 1771 LAMARBM1_8 | Lamar | NORTH | 2026-08-31 | PV | 204.12 | 2022-10-24 | 2023-01-20
ERCOT | 25INR0135 | Hayrick BESS | SS Completed, FIS Started, No IA | Gransolar Texas Five LLC | 6351 Nicole 138kV | Coke | WEST | 2027-02-15 | BA | 113.9 | 2022-08-16 | 2022-11-11 |  |  | No
ERCOT | 25INR0138 | Champaign BESS | SS Completed, FIS Completed, No IA | Champaign BESS, LLC | Tap 138kV Shaw POD (18664) – Desert Wind Sub (11222) new station Potterson Lake Switch | Glasscock | WEST | 2026-09-14 | BA | 201.13 | 2022-09-21 | 2022-12-19 |  | 2024-08-13 | No
ERCOT | 25INR0139 | Dolce BESS | SS Completed, FIS Completed, No IA | Dolce BESS, LLC | Tap 138kV 1189 BARBER_LK1_8 - 19520 CHINAGRVX2_8 | Mitchell | WEST | 2026-09-01 | BA | 100.65 | 2022-09-27 | 2022-12-21 |  | 2024-06-26 | No
ERCOT | 25INR0140 | Seragio BESS | SS Completed, FIS Completed, No IA | Seragio BESS, LLC | 11140 ECTRCNTYN_8 138kV | Ector | WEST | 2026-09-14 | BA | 201.13 | 2022-09-15 | 2022-12-13 |  | 2024-06-20 | No
ERCOT | 25INR0141 | Fairgreen BESS | SS Completed, FIS Started, No IA | Fairgreen BESS, LLC | Tap 138kV 1322 BIGSPRIG_8 - 11351 HILLCREST_8 | Howard | WEST | 2026-09-14 | BA | 201.13 | 2022-09-15 | 2022-12-13
ERCOT | 25INR0142 | Sagewood BESS | SS Completed, FIS Completed, No IA | Sagewood BESS, LLC | Tap 138kV McDonald Road Switch (bus #1333) – Desert Wind Sub (bus #11282) | Glasscock | WEST | 2026-09-14 | BA | 100.57 | 2022-09-21 | 2022-12-19 |  | 2024-08-13 | No
ERCOT | 25INR0143 | Ariji BESS | SS Completed, FIS Started, No IA | Ariji BESS, LLC | Tap 138kV 1394 GTTYVTAP_8 - 1322 BIGSPRIG_8 | Howard | WEST | 2026-09-14 | BA | 100.32 | 2022-09-15 | 2022-12-13
ERCOT | 25INR0144 | Jasper BESS | SS Completed, FIS Completed, No IA | Jasper BESS, LLC | Tap 138kV 71230 Pleasant Farms - 1236 Pegasus South | Midland | WEST | 2026-09-14 | BA | 201.13 | 2022-09-21 | 2022-12-19 |  | 2024-07-01
ERCOT | 25INR0146 | Blue Heron BESS | SS Completed, FIS Completed, No IA | Blue Heron BESS, LLC | Tap 138kV MANSON (1094) - Riverton (11083) | Reeves | WEST | 2026-09-14 | BA | 201.08 | 2022-10-24 | 2023-01-20 |  | 2024-05-23 | No
ERCOT | 25INR0147 | Holly Branch Solar | SS Completed, FIS Started, No IA | Holly Branch Solar, LLC | Tap 345kV 967 Gibbons Creek - 3400 Twin Oak | Robertson | NORTH | 2027-06-01 | PV | 231.12 | 2023-06-07 | 2023-09-01 | 2023-05-22
ERCOT | 25INR0148 | Holly Branch Storage | SS Completed, FIS Started, No IA | Holly Branch Solar, LLC | Tap 345kV 967 Gibbons Creek - 3400 Twin Oak | Robertson | NORTH | 2027-06-01 | BA | 115.32 | 2023-06-07 | 2023-09-01 | 2023-05-30
ERCOT | 25INR0152 | Bottom Grass Solar II | SS Completed, FIS Started, No IA | Flint Rock Solar Project, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-12-01 | PV | 401.6 | 2022-11-07 | 2023-02-04 | 2022-11-02
ERCOT | 25INR0153 | Bottom Grass BESS II | SS Completed, FIS Started, No IA | Flint Rock Solar Project, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2026-12-01 | BA | 150.6 | 2022-11-07 | 2023-02-03 | 2022-11-02
ERCOT | 25INR0154 | Nymphaea Solar | SS Completed, FIS Completed, No IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2027-06-30 | PV | 120.9 | 2022-09-21 | 2022-12-19 |  | 2024-04-24 | No |  |  |  | COD
ERCOT | 25INR0155 | Nymphaea Storage | SS Completed, FIS Completed, No IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2027-06-30 | BA | 61 | 2022-09-21 | 2022-12-19 |  | 2024-04-24 | No |  |  |  | COD
ERCOT | 25INR0162 | SOHO II BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 43035 Oasis 345kV | Brazoria | COASTAL | 2026-03-02 | BA | 206.32 | 2022-08-16 | 2022-11-11 | 2022-08-10 | 2023-08-24 | No | 2023-04-15
ERCOT | 25INR0164 | Star Dairy Solar | SS Completed, FIS Started, IA | Star Dairy Solar LLC | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | Lamar | NORTH | 2026-09-14 | PV | 125.61 | 2022-11-23 | 2023-02-17 | 2022-11-09 |  | No | 2024-12-09
ERCOT | 25INR0165 | Timberlakes Solar | SS Completed, FIS Started, No IA | Donegalsol | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2026-10-31 | PV | 203.5 | 2022-11-07 | 2023-02-03 | 2022-09-02
ERCOT | 25INR0166 | Padrino Solar | SS Completed, FIS Completed, No IA | Hill Solar II, LLC | Tap 345kV 68090 Sam Switch – 3389 Fort Smith | Hill | NORTH | 2026-01-16 | PV | 201.4 | 2022-09-15 | 2022-12-13 |  | 2024-07-12 |  |  |  |  | MW Size COD
ERCOT | 25INR0167 | Padrino BESS | SS Completed, FIS Completed, No IA | Hill Solar II, LLC | Tap 345kV 68090 Sam Switch – 3389 Fort Smith | Hill | NORTH | 2026-03-23 | BA | 100.77 | 2022-09-15 | 2022-12-13 |  | 2024-07-12
ERCOT | 25INR0168 | Piedra Solar | SS Completed, FIS Completed, IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020)) | Freestone | NORTH | 2026-04-20 | PV | 300.93 | 2022-09-02 | 2022-11-30 |  | 2024-02-05 |  | 2024-07-02
ERCOT | 25INR0169 | Piedra BESS | SS Completed, FIS Completed, IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020) | Freestone | NORTH | 2026-04-20 | BA | 100.4 | 2022-09-02 | 2022-11-30 |  | 2024-02-05 |  | 2024-07-02
ERCOT | 25INR0170 | Pinewood Solar | SS Completed, FIS Started, No IA | Brazoria Solar II, LLC | 43020 Seabreeze 345kV | Brazoria | COASTAL | 2027-01-09 | PV | 150.68 | 2022-09-02 | 2022-11-30
ERCOT | 25INR0171 | Pinewood BESS | SS Completed, FIS Started, No IA | Brazoria Solar II, LLC | 43020 Seabreeze 345kV | Brazoria | COASTAL | 2027-01-09 | BA | 100.9 | 2022-09-02 | 2022-11-30
ERCOT | 25INR0172 | Wolf Spring Solar | SS Completed, FIS Started, IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | Dickens | PANHANDLE | 2027-09-16 | PV | 195.7 | 2022-12-07 | 2023-03-06 | 2022-11-30 |  | No | 2024-08-14
ERCOT | 25INR0173 | Wolf Spring Storage | SS Completed, FIS Started, IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | Dickens | PANHANDLE | 2027-09-16 | BA | 202.7 | 2022-12-15 | 2023-03-13 | 2022-12-07 |  | No | 2024-08-14
ERCOT | 25INR0174 | Concho Pearl Solar | SS Completed, FIS Started, IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2027-10-14 | PV | 171.9 | 2022-12-07 | 2023-03-06 | 2022-11-30 |  |  | 2024-07-22
ERCOT | 25INR0175 | Concho Pearl Storage | SS Completed, FIS Started, IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2027-10-14 | BA | 162.4 | 2022-12-15 | 2023-03-13 | 2022-12-07 |  |  | 2024-07-22
ERCOT | 25INR0176 | Masava Storage | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project, LLC | tap 345 kV 46020 Limestone Plant - 967 Gibbons Creek ckt 18 | Madison | NORTH | 2028-09-30 | BA | 261.51 | 2022-09-02 | 2022-11-30 | 2022-08-17
ERCOT | 25INR0177 | Triangle Ranch Alpha | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2029-07-01 | WT | 301.74 | 2022-10-06 | 2022-12-29 | 2022-09-15
ERCOT | 25INR0178 | Triangle Ranch Bravo | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2028-07-01 | WT | 200.22 | 2022-10-06 | 2022-12-29 | 2022-09-15
ERCOT | 25INR0184 | Legato BESS | SS Completed, FIS Completed, No IA | Legato Storage, LLC | 138kV #608 Crafton Substation - #620 Bowie Substation | Wise | NORTH | 2028-04-24 | BA | 202.65 | 2022-09-27 | 2022-12-21 |  | 2024-09-12 | No
ERCOT | 25INR0186 | Moonlight Sonata BESS | SS Completed, FIS Started, No IA | Samsung Solar Energy 2, LLC | 78118 LCRA Altair 138kV | Colorado | SOUTH | 2026-12-31 | BA | 201.08 | 2022-09-27 | 2022-12-22
ERCOT | 25INR0189 | Staccato BESS | SS Completed, FIS Started, No IA | Staccato Storage, LLC | 138kV WARDA #7312. | Fayette | SOUTH | 2025-12-31 | BA | 202.65 | 2022-11-07 | 2023-02-03
ERCOT | 25INR0190 | Fortissimo BESS | SS Completed, FIS Completed, No IA | Fortissimo BESS, LCC | 741 Dyemound 138kV | Montague | NORTH | 2028-04-24 | BA | 202.65 | 2022-10-18 | 2023-01-13 |  | 2024-09-12 | No
ERCOT | 25INR0192 | Palmvalley Storage | SS Completed, FIS Started, No IA | Palmvalley Energy Storage LLC | Frontera (#8980) | Hidalgo | SOUTH | 2027-05-01 | BA | 100 | 2022-09-27 | 2022-12-21 | 2022-09-16
ERCOT | 25INR0193 | Nockenut Springs Solar 4 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | The 345 kV Elm Creek - South Texas Project Line (Bus #5133 - #5915) | Gonzales | SOUTH | 2027-05-05 | PV | 201.15 | 2022-09-15 | 2022-12-13 | 2022-08-31
ERCOT | 25INR0194 | Photo Solar 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2026-05-31 | PV | 150 | 2022-09-15 | 2022-12-13 | 2022-09-15
ERCOT | 25INR0195 | Photo Solar 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 5885 Downie 138kV | Uvalde | SOUTH | 2027-05-31 | PV | 300 | 2022-09-15 | 2022-12-13 | 2022-09-15
ERCOT | 25INR0196 | Inadale Solar | SS Completed, FIS Completed, No IA | Inadale Solar, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2027-07-29 | PV | 281.03 | 2023-02-20 | 2023-05-19 | 2023-02-08 | 2024-08-01 | No |  |  |  | COD
ERCOT | 25INR0197 | Inadale BESS | SS Completed, FIS Completed, No IA | Inadale BESS, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2027-07-29 | BA | 286.66 | 2023-02-20 | 2023-05-19 | 2023-02-16 | 2024-08-01 | No |  |  |  | COD
ERCOT | 25INR0199 | XE Bonham Solar 1 | SS Completed, FIS Completed, IA | J&J Solar Ranch LLC | TAP 138 kV MEXIA_2_1_8 3632 - GROES_SE1_8 3634 | Limestone | NORTH | 2026-08-31 | PV | 138.4 | 2022-11-15 | 2023-02-09 | 2022-10-31 | 2024-02-15 | No | 2024-08-07
ERCOT | 25INR0200 | Sunbeam Solar | SS Completed, FIS Started, No IA | Buckeye Midway Solar | 80258 Mayo 138kV | San Patricio | COASTAL | 2026-08-29 | PV | 73.43 | 2024-10-29 | 2024-12-09 | 2024-10-21
ERCOT | 25INR0201 | Veer Energy | SS Completed, FIS Started, No IA | DBR Solar, LLC | TAP 69kV 38040 IH20 - 38090 Pecos | Reeves | WEST | 2026-12-31 | PV | 90.72 | 2022-12-07 | 2023-03-04
ERCOT | 25INR0202 | East West BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II, LLC | 7750 LCRA MOUNTAIN HOME SUB | Kerr | SOUTH | 2026-06-30 | BA | 120.96 | 2022-10-06 | 2022-12-29 | 2022-09-27
ERCOT | 25INR0204 | Claxton Solar | SS Completed, FIS Started, No IA | BT Claxton Solar, LLC | Tap 345kV line between Allen Switch (#2514) and Monticello (#1696) | Hopkins | NORTH | 2027-09-17 | PV | 150.64 | 2022-09-21 | 2022-12-19 | 2022-11-03
ERCOT | 25INR0205 | Claxton Storage | SS Completed, FIS Started, No IA | BT Claxton Solar, LLC | Tap 345kV line between Allen Switch (#2514) and Monticello (#1696) | Hopkins | NORTH | 2027-09-17 | BA | 75.7 | 2022-09-21 | 2022-12-19 | 2022-11-03
ERCOT | 25INR0207 | Shadow Ranch Solar | SS Completed, FIS Started, No IA | LectricWind LLC | 842 King Mountain 345kV | Upton | WEST | 2026-06-01 | PV | 807.61 | 2022-09-27 | 2023-01-12
ERCOT | 25INR0208 | Iron Belt Energy Storage | SS Completed, FIS Started, IA | Iron Belt Energy Storage Project, LLC | Long Draw (# 59900) - Volta (#59910) 345kV | Borden | WEST | 2026-07-31 | BA | 401.9 | 2023-01-03 | 2023-03-30 | 2022-12-19 |  |  | 2023-01-16
ERCOT | 25INR0214 | Burgos Solar | SS Completed, FIS Started, No IA | Twin Oaks Solar, LLC | 3701 Rookie Switch 138 kV | Milam | SOUTH | 2026-09-11 | PV | 105.52 | 2022-10-18 | 2023-01-13
ERCOT | 25INR0215 | Middlebrook BESS | SS Completed, FIS Started, No IA | Middlebrook Solar LLC | Tap Stryker [3109] - Lufkin [3117] 345 kV line | Nacogdoches | NORTH | 2027-06-30 | BA | 158.63 | 2022-10-24 | 2023-01-20 | 2022-10-11
ERCOT | 25INR0216 | Blue Sky Storage SLF | SS Completed, FIS Started, No IA | UKA North America, LLC | 138 kV Friend Ranch (Bus# 6562) | Crockett | WEST | 2025-11-15 | BA | 0 | 2022-10-24 | 2023-01-22 | 2022-10-14
ERCOT | 25INR0220 | Hector Solar | SS Completed, FIS Completed, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2025-12-31 | PV | 81.59 | 2022-10-24 | 2023-01-20 |  | 2024-04-22 | No
ERCOT | 25INR0221 | Hector Storage | SS Completed, FIS Completed, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2025-12-31 | BA | 42.69 | 2022-10-24 | 2023-01-20 |  | 2024-04-22 | No
ERCOT | 25INR0222 | Olympic BESS | SS Completed, FIS Completed, No IA | SMT Olympic BESS LLC | AIRLINE 138 kV Substation (Bus# 8490) | Nueces | COASTAL | 2027-07-01 | BA | 222.81 | 2022-10-18 | 2023-01-13 | 2022-09-29 | 2024-04-19 | No |  |  |  | COD
ERCOT | 25INR0223 | Uhland Maxwell | SS Completed, FIS Completed, IA | Lower Colorado River Authority | Clear Springs (#7050) and L_Hornsb8_1Y (#7047) | Caldwell | SOUTH | 2025-08-19 | IC | 188.4 | 2022-09-27 | 2022-12-22 | 2022-10-26 | 2023-12-04 | Yes | 2023-03-03 |  |  | COD
ERCOT | 25INR0225 | Lucy Solar | SS Completed, FIS Started, No IA | Concho County Solar 1 LLC | Tap 345kV 7077 Amos Creek - 6444 San Angelo Red Creek and 7077 Amos Creek - 76009 Twin Buttes | Concho | WEST | 2027-06-30 | PV | 351.3 | 2023-06-28 | 2023-09-20 | 2023-06-08
ERCOT | 25INR0227 | SERENGETI SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green XIV LLC | Tap 138kV Enloe Tap (bus# 11806) – Delta sub (bus# 1802) | Delta | NORTH | 2027-09-13 | PV | 76.18 | 2022-12-07 | 2023-03-06 | 2022-11-18 | [5 empty] | COD
ERCOT | 25INR0229 | OCI Cobb Creek Solar | SS Completed, FIS Completed, IA | Hillsboro Solar Energy Holdings LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2026-09-01 | PV | 203.1 | 2022-11-15 | 2023-02-09 | 2022-11-09 | 2024-05-06 | No | 2024-07-24
ERCOT | 25INR0230 | Great Rock BESS | SS Completed, FIS Started, IA | Black Mountain Energy Storage II | Tap 345kV 46020 Limestone - 967 Gibbon Creek Ckt 18 | Leon | NORTH | 2026-12-20 | BA | 300.9 | 2022-11-07 | 2023-02-04 | 2022-10-19 |  | No | 2024-08-23
ERCOT | 25INR0231 | Apache Hill BESS | SS Completed, FIS Started, IA | APACHE HILL ENERGY CENTER | 363 Hood 138kV | Hood | NORTH | 2026-11-15 | BA | 201.2 | 2022-11-07 | 2023-02-03 | 2022-10-25 |  | No | 2024-06-26
ERCOT | 25INR0232 | Isaac Solar | SS Completed, FIS Started, IA | Industrial Bravo Project LLC | 8114 Conoco 138kV | Matagorda | COASTAL | 2026-03-31 | PV | 51.6 | 2022-11-07 | 2023-02-03 | 2022-10-27 |  | No | 2023-10-18
ERCOT | 25INR0233 | OCI Cobb Creek ESS | SS Completed, FIS Completed, IA | Hillsboro Solar Energy Holdings LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2026-09-02 | BA | 201.6 | 2022-12-07 | 2023-03-04 | 2022-11-23 | 2024-05-06 | No | 2024-07-24
ERCOT | 25INR0235 | Austin Bayou Storage I | SS Completed, FIS Completed, No IA | Austin Bayou Solar, LLC | Tap 345kV 43180 Savanna - 43020 Seabreeze Ckt 27 AND 43035 Oasis - 43060 Speedway Ckt 18 | Brazoria | COASTAL | 2027-06-01 | BA | 150.68 | 2023-03-08 | 2023-06-05 | 2023-02-23 | 2024-02-14
ERCOT | 25INR0236 | Austin Bayou Storage II | SS Completed, FIS Completed, No IA | Austin Bayou Solar, LLC | Tap 345kV 43180 Savanna - 43020 Seabreeze Ckt 27 AND 43035 Oasis - 43060 Speedway Ckt 18 | Brazoria | COASTAL | 2027-06-01 | BA | 150.68 | 2023-03-08 | 2023-06-05 | 2023-02-23 | 2024-02-14
ERCOT | 25INR0237 | Austin Bayou Storage III | SS Completed, FIS Completed, No IA | Austin Bayou Solar, LLC | Tap 345kV 43180 Savanna - 43020 Seabreeze Ckt 27 AND 43035 Oasis - 43060 Speedway Ckt 18 | Brazoria | COASTAL | 2027-06-01 | BA | 150.68 | 2023-03-08 | 2023-06-05 | 2023-02-23 | 2024-02-14
ERCOT | 25INR0238 | Little Ridge Storage | SS Completed, FIS Started, No IA | TX BESS B LLC | Tap 138kV Swindell (812) - Olinger (818) | Collin | NORTH | 2025-12-11 | BA | 252 | 2023-05-15 | 2023-08-11 | 2023-04-25
ERCOT | 25INR0239 | Big Five Storage | SS Completed, FIS Started, No IA | TX BESS 3 LLC | Tap 138kV (5784) Redgtss - (8380) Nedina | Hidalgo | SOUTH | 2026-06-30 | BA | 102.18 | 2023-05-26 | 2023-08-17 | 2023-05-22 | [5 empty] | COD
ERCOT | 25INR0241 | Halcon Storage | SS Completed, FIS Started, No IA | TX BESS A LLC | Tap 138kV 8957 Central Lopeno - 80106 Falcon Dam | Starr | SOUTH | 2025-06-01 | BA | 132.65 | 2023-05-22 | 2023-08-17 | 2023-04-24
ERCOT | 25INR0242 | Pato Blanco Storage | SS Completed, FIS Started, No IA | TX BESS 4, LLC | Tap 138 kV 44010 W A Parish - 42980 NASH___S02_8 | Fort Bend | HOUSTON | 2025-12-11 | BA | 71.34 | 2023-05-15 | 2023-08-11 | 2023-04-24
ERCOT | 25INR0246 | VALDIVIAN SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green III LLC | 138kV 1816 Commerce Switch - 1809 Wolf City | Hunt | NORTH | 2026-09-26 | PV | 80.45 | 2023-02-27 | 2023-05-26 | 2023-02-22
ERCOT | 25INR0247 | Bluebonnet Prairie Wind | SS Completed, FIS Completed, No IA | Leeward Renewable Energy Development, LLC | Tap 138kV 200 CHATFIELD - 3454 MONTFTSS__8 | Navarro | NORTH | 2025-12-31 | WT | 173 | 2022-12-07 | 2023-03-06 | 2022-11-23 | 2024-08-23 | No
ERCOT | 25INR0248 | Strawberry Acres Storage | SS Completed, FIS Started, No IA | Strawberry Acres Energy Center, LLC | 5132 Eagle Creek Substation 138kV | Wilson | SOUTH | 2028-09-30 | BA | 156.73 | 2022-11-23 | 2023-02-17 | 2022-11-15 |  | No
ERCOT | 25INR0252 | Papley Storage | SS Completed, FIS Started, No IA | Papley Storage, LLC | Tap 138 kV line 8692 Maverick - 8255 Hamilton Road | Maverick | SOUTH | 2029-07-10 | BA | 102.89 | 2022-12-07 | 2023-03-06 | 2022-11-18
ERCOT | 25INR0253 | Whiskey BESS | SS Completed, FIS Completed, No IA | UR-Silo DevCo LLC | 6828 Canton Tap 138 kV | Van Zandt | NORTH | 2026-03-15 | BA | 153.72 | 2022-12-07 | 2023-03-06 |  | 2024-06-03
ERCOT | 25INR0262 | Shepard Energy Storage | SS Completed, FIS Started, IA | Shepard Energy Storage LLC | Hidden Lakes 138kV substation (Bus# 38900) | Galveston | HOUSTON | 2026-12-31 | BA | 260.22 | 2022-12-15 | 2023-03-11 | 2022-12-09 |  | No | 2024-01-17
ERCOT | 25INR0266 | East Blackland Battery Storage SLF | SS Completed, FIS Started, No IA | DERIVA ENERGY STORAGE, LLC | 7337 Kimbro 138kV | Travis | SOUTH | 2026-08-29 | BA | 75 | 2022-11-23 | 2023-02-17 | 2022-11-22
ERCOT | 25INR0270 | Harryoung Solar | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | Tap 8319 Rio Hondo - SOUTH SANTA ROSA: 8359, 138kV | Cameron | COASTAL | 2027-05-15 | PV | 190.01 | 2022-11-23 | 2023-02-17
ERCOT | 25INR0271 | City Breeze BESS | SS Completed, FIS Started, IA | City Breeze BESS LLC | 8111 MAGILL4A 138KV | Matagorda | COASTAL | 2026-07-15 | BA | 140.6 | 2022-12-15 | 2023-03-11 | 2022-12-06 |  |  | 2024-05-15
ERCOT | 25INR0273 | Horse Wrangler Solar | SS Completed, FIS Started, No IA | Horse Wrangler Solar Project, LLC | Tap 138kV 8153 Rosata Tap (Bus# ) - 8186 Kenedy Switch | Karnes | SOUTH | 2028-12-01 | PV | 251.33 | 2023-12-04 | 2024-02-26 | 2023-11-14
ERCOT | 25INR0274 | Horse Wrangler Storage | SS Completed, FIS Started, No IA | Horse Wrangler Solar Project, LLC | Tap 138kV 8153 Rosata Tap - 8186 Kenedy Switch Ckt 1 | Karnes | SOUTH | 2028-12-01 | BA | 102.07 | 2023-11-30 | 2024-02-26 | 2023-11-14
ERCOT | 25INR0275 | Texas Sage Solar SLF | SS Completed, FIS Started, No IA | Texas Sage Solar Project, LLC | 8193 LYSSY 138kV | Wilson | SOUTH | 2028-12-01 | PV | 100.7 | 2024-04-15 | 2024-07-09 | 2024-03-29
ERCOT | 25INR0276 | Texas Sage Storage SLF | SS Completed, FIS Started, No IA | Texas Sage Solar Project, LLC | 8193 LYSSY 138kV | Wilson | SOUTH | 2028-12-01 | BA | 0 | 2024-04-15 | 2024-07-09 | 2024-03-29
ERCOT | 25INR0280 | Nockenut Springs Solar 5 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | Tap 345 kV 5133 Elm Creek - 5915 South Texas Project | Gonzales | SOUTH | 2027-05-05 | PV | 201.15 | 2023-02-09 | 2023-05-08 | 2023-01-27
ERCOT | 25INR0281 | Cosper Solar | SS Completed, FIS Completed, No IA | Gransolar Texas Twenty LLC | Tap 138kV 115 Ding Dong - 3630 Copperas Cove Tu | Bell | NORTH | 2027-04-18 | PV | 148.16 | 2023-01-03 | 2023-03-30 |  | 2024-11-01
ERCOT | 25INR0282 | Hornet Solar II SLF | SS Completed, FIS Completed, IA | Hornet Solar II LLC | Ozark Trail Switch 345kV substation (Bus #23901) | Castro | PANHANDLE | 2026-06-01 | PV | 208.95 | 2023-01-03 | 2023-03-29 | 2022-12-20 | 2024-07-02 | No | 2024-08-21
ERCOT | 25INR0283 | Hornet Storage II SLF | SS Completed, FIS Completed, IA | Hornet Storage II LLC | Ozark Trail Switch 345kV substation (Bus # 23901) | Castro | PANHANDLE | 2026-06-01 | BA | 0 | 2023-01-03 | 2023-03-29 | 2022-12-20 | 2024-07-02 | No | 2024-08-21
ERCOT | 25INR0284 | Railway BESS | SS Completed, FIS Started, No IA | Grand Reserve Energy, LLC | Martin Lake Switch (3100) – Elkton (3105) 345 kV Line | Rusk | NORTH | 2026-08-28 | BA | 254.8 | 2023-01-30 | 2023-04-28 | 2023-01-23
ERCOT | 25INR0286 | Savannah Oaks Solar | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project LLC | Tap 345kV 46020 Limestone Plant - 967 Gibbons Creek | Madison | NORTH | 2028-09-30 | PV | 200.97 | 2023-01-03 | 2023-03-30 | 2022-12-02
ERCOT | 25INR0288 | Buffalo Prairie Storage | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap 345kV 975 Jack Creek - 3400 Twin Oak | Robertson | NORTH | 2028-09-30 | BA | 313.51 | 2023-01-03 | 2023-03-29 | 2022-12-02
ERCOT | 25INR0293 | TOCE BESS 1 | SS Completed, FIS Completed, No IA | TOCE BESS 1, LLC | 138 kV Danevang Switching Station (Bus# 5546) | Wharton | SOUTH | 2026-05-01 | BA | 205.2 | 2023-10-13 | 2024-01-10 | 2023-09-22 | 2024-11-07
ERCOT | 25INR0297 | RIVERBEND SOLAR SLF | SS Completed, FIS Completed, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2026-09-28 | PV | 301 | 2023-03-08 | 2023-06-05 | 2023-03-03 | 2024-07-23
ERCOT | 25INR0300 | Wizard BESS | SS Completed, FIS Completed, IA | Rocky Mountain Energy Holdings, LLC | To the 138 kV League City Substation (#38920) | Galveston | HOUSTON | 2025-10-21 | BA | 150.82 | 2023-03-27 | 2023-06-19 | 2023-03-15 | 2024-01-24 |  | 2023-08-21 |  |  | COD
ERCOT | 25INR0301 | Van Zandt Energy Storage | SS Completed, FIS Completed, No IA | Rocky Mountain Energy Holdings, LLC | 1027 Odessa EHV Switch 138 kV | Ector | WEST | 2027-04-13 | BA | 256.58 | 2023-06-07 | 2023-09-01 | 2023-04-05 | 2024-11-18 | No
ERCOT | 25INR0304 | XE Flying Kite Solar | SS Completed, FIS Started, No IA | FLYING KITE SOLAR LLC | Tap the 69kV La Pryor (#8672) - Uvalde (#8231) Line; AEP | Zavala | SOUTH | 2027-05-21 | PV | 80.38 | 2023-04-07 | 2023-07-05 | 2023-03-17
ERCOT | 25INR0306 | Red Top Solar I | SS Completed, FIS Started, No IA | Cat Red Top Solar, LLC | Tap 138kV 1431 Graham SES - Short Grass 11525 | Young | WEST | 2027-09-30 | PV | 200.59 | 2023-01-17 | 2023-04-14
ERCOT | 25INR0310 | IEP Blackhawk | SS Completed, FIS Started, No IA | IEP Texas Verde II, llc | 38740 Heights Substation 138kV | Galveston | HOUSTON | 2026-12-01 | BA | 100 | 2023-04-07 | 2023-07-05 | 2023-03-08
ERCOT | 25INR0311 | RIVERBEND STORAGE SLF | SS Completed, FIS Completed, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2026-09-28 | BA | 0 | 2023-03-08 | 2023-06-05 | 2023-03-03 | 2024-07-23
ERCOT | 25INR0313 | Staked Plains BESS | SS Completed, FIS Completed, IA | Grand Reserve Energy, LLC | 345kV Dunbar Double Mountain Switch (Bus# 23928) | Lubbock | PANHANDLE | 2028-06-01 | BA | 254.8 | 2023-03-13 | 2023-06-09 | 2023-03-02 | 2024-12-03 | No | 2024-10-29
ERCOT | 25INR0318 | Silver Fox Solar | SS Completed, FIS Started, No IA | Industrial Lima Project LLC | 12677 Haggerty Switch 138kV | Grayson | NORTH | 2026-05-31 | PV | 101.2 | 2023-07-31 | 2023-10-27 | 2023-07-24
ERCOT | 25INR0319 | Northington Solar | SS Completed, FIS Started, IA | Northington Solar, LLC | The 138 kV El Campo (#8102) - Pulsar (#8192) Line; AEP. | Wharton | SOUTH | 2027-07-15 | PV | 129.81 | 2023-02-20 | 2023-05-19 | 2023-02-02 |  |  | 2024-10-02 |  |  | COD
ERCOT | 25INR0320 | Normangee Solar | SS Completed, FIS Started, No IA | Normangee Solar LLC | Tap 345kV 3391Jewett - 44645 Singleton | Leon | NORTH | 2027-06-30 | PV | 120.68 | 2023-03-13 | 2023-06-09 | 2023-02-13
ERCOT | 25INR0321 | El Molino Solar SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | 138kV Bruni 8297 | Webb | SOUTH | 2027-09-01 | PV | 201.32 | 2023-01-17 | 2023-04-14 | 2023-03-31 |  | No
ERCOT | 25INR0322 | El Molino Storage SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | 138kV Bruni 8297 | Webb | SOUTH | 2027-09-01 | BA | 0 | 2023-01-17 | 2023-04-14 | 2023-01-13 |  | No
ERCOT | 25INR0328 | Longbow BESS | SS Completed, FIS Completed, IA | Longbow BESS, LLC | 42875 Danbury 138kV | Brazoria | COASTAL | 2025-01-11 | BA | 180.8 | 2023-01-23 | 2023-04-22 | 2023-01-16 | 2023-09-06 | No | 2023-07-18 | 2024-08-29 |  | COD
ERCOT | 25INR0329 | Project Lynx BESS | SS Completed, FIS Started, IA | Corpus Battery Storage, LLC | 138KV Tap 8921 Terra Verde - 8518 Kingsville | Nueces | COASTAL | 2026-03-14 | BA | 125.36 | 2023-03-08 | 2023-06-01 | 2023-03-01 |  |  | 2024-04-09
ERCOT | 25INR0330 | Clutch City Solar Phase II | SS Completed, FIS Completed, No IA | HZ SOLAR I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT#04 | Brazoria | COASTAL | 2026-10-01 | PV | 251.27 | 2023-02-20 | 2023-05-20 | 2023-02-10 | 2024-04-16
ERCOT | 25INR0331 | Buffalo Meadow Solar | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap Jack Creek (975) - Twin Oak (3400) 345kV line | Robertson | NORTH | 2028-09-30 | PV | 251.27 | 2023-02-27 | 2023-05-26 | 2023-01-27
ERCOT | 25INR0335 | Jaguarundi Solar | SS Completed, FIS Started, No IA | Jaguarundi Solar, LLC | NAVY KICKAPOO SWITCH (NAVYKSS1_8 #1472) | Archer | WEST | 2027-07-01 | PV | 90.29 | 2023-03-27 | 2023-06-19 | 2023-03-16
ERCOT | 25INR0337 | Butcherbird Solar | SS Completed, FIS Started, No IA | Butcherbird Solar, LLC | Tap 138 kV - Bell County #133 to Bartlett Switch #114 | Bell | NORTH | 2027-02-01 | PV | 116 | 2023-12-18 | 2024-03-15 | 2023-12-06
ERCOT | 25INR0338 | Les Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | Tap 138 kV 1326 Stanton East – 11324 Leatherwood Pod | Howard | WEST | 2028-04-30 | BA | 205.13 | 2023-02-09 | 2023-05-05
ERCOT | 25INR0339 | Fort Concho Energy storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | Tap 138 kV #76320 Schkade - #76011 Twin Buttes Line; LCRA | Tom Green | WEST | 2026-02-16 | BA | 251.15 | 2023-01-30 | 2023-04-28
ERCOT | 25INR0341 | Rosebud Storage SLF | SS Completed, FIS Started, No IA | Rosebud Storage, LLC | Tap 69 kV 67 BAGGINS - 69 BARCLAY | Falls | NORTH | 2028-01-15 | BA | 0 | 2023-03-09 | 2023-06-05
ERCOT | 25INR0342 | Nickel Spruce Solar | SS Completed, FIS Started, No IA | Nickel Spruce Solar LLC | Tap 138kV 6735 Pleasant Springs Switching Station - 6736 Middl | Leon | NORTH | 2027-12-15 | PV | 150 | 2023-01-30 | 2023-04-28
ERCOT | 25INR0346 | Cado Storage | SS Completed, FIS Started, No IA | Cado Storage, LLC | Tap 138 kV Line from Braunig East (#5030) to Highland Hills (#5205) Ckt. 1 | Bexar | SOUTH | 2029-04-06 | BA | 205.51 | 2023-03-13 | 2023-06-09 | 2023-03-07
ERCOT | 25INR0347 | Cadet Storage | SS Completed, FIS Started, No IA | TX BESS 5, LLC | Tap 69kV 32864 BRYN_ATK69 to 32873 BRYN SHADY | Brazos | NORTH | 2026-04-01 | BA | 104.42 | 2023-05-22 | 2023-08-18 | 2023-04-24
ERCOT | 25INR0353 | Marshall Spring Solar | SS Completed, FIS Started, No IA | Marshall Springs Solar, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2026-07-01 | PV | 150 | 2023-02-20 | 2023-05-18
ERCOT | 25INR0354 | Marshall Spring Storage | SS Completed, FIS Started, No IA | Marshall Springs Storage, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2026-07-01 | BA | 150 | 2023-02-20 | 2023-05-18
ERCOT | 25INR0361 | Wallie Storage | SS Completed, FIS Started, No IA | Wallie Storage, LLC | Tap 138kV 11324 Leatherwood POD - 1326 Stanton East Switch | Howard | WEST | 2027-03-31 | BA | 205.4 | 2023-03-27 | 2023-06-19 | 2023-03-02
ERCOT | 25INR0363 | Emerald Hill Energy Storage | SS Completed, FIS Completed, No IA | Emerald Hill Energy Storage LLC | Desoto Switch (2431) - Cedar Hill Switch (2420) 345kV Line | Dallas | NORTH | 2026-09-14 | BA | 261.02 | 2023-02-27 | 2023-05-26 | 2023-02-23 | 2024-08-26 | No
ERCOT | 25INR0368 | Echols Creek Solar | SS Completed, FIS Completed, No IA | BT Ferguson Solar, LLC | Tap 138kV Hawk Hollow Switch (#11768) and Lamar Blossom Switch (#11770) | Lamar | NORTH | 2026-12-31 | PV | 201.15 | 2023-04-07 | 2023-07-05 | 2023-03-22 | 2024-07-24 |  |  |  |  | Status Change INA-to-PLN
ERCOT | 25INR0369 | Echols Creek Storage | SS Completed, FIS Completed, No IA | BT Ferguson Solar, LLC | Tap 138kV Hawk Hollow Switch (#11768) and Lamar Blossom Switch (#11770) | Lamar | NORTH | 2026-12-31 | BA | 100.57 | 2023-04-07 | 2023-07-05 | 2023-03-22 | 2024-07-24 |  |  |  |  | Status Change INA-to-PLN
ERCOT | 25INR0370 | Willis Storage | SS Completed, FIS Completed, No IA | BT Willis Storage, LLC | tap 138kV Emory North 3171 to Liberty POD 1723 | Rains | NORTH | 2027-04-13 | BA | 176.13 | 2023-03-27 | 2023-06-24 | 2023-03-13 | 2024-11-08
ERCOT | 25INR0371 | McMurtre Storage | SS Completed, FIS Completed, No IA | BT McMurtre Storage, LLC | tap 138kV 1819 Commerce South - 1815 Cumby Tap | Hunt | NORTH | 2026-09-07 | BA | 176.13 | 2023-03-13 | 2023-06-09 | 2023-03-06 | 2024-07-08
ERCOT | 25INR0372 | Elan BESS | SS Completed, FIS Completed, No IA | Elan BESS, LLC | 42380 Needville 138kV | Fort Bend | HOUSTON | 2025-12-31 | BA | 202.65 | 2023-03-08 | 2023-06-05 | 2023-02-15 | 2024-03-21
ERCOT | 25INR0373 | LARISA BESS | SS Completed, FIS Started, No IA | ME USA PROJECT II LLC | Tap 345kV 6235 Mulberry Creek – 60791 Perigee | Jones | WEST | 2026-11-12 | BA | 418.49 | 2023-03-13 | 2023-06-09
ERCOT | 25INR0374 | Meridian BESS | SS Completed, FIS Completed, No IA | Navitas Energy- Meredian BESS | 319 Meridian 69 KV | Bosque | NORTH | 2027-10-01 | BA | 31.23 | 2023-03-13 | 2023-06-09 | 2023-03-10 | 2024-06-14 | No
ERCOT | 25INR0375 | NavBoot BESS | SS Completed, FIS Started, No IA | Navboot BESS LLC | 8858 MCKENZIE4A 138kV | Nueces | COASTAL | 2026-12-01 | BA | 303.7 | 2023-03-13 | 2023-06-09 | 2023-03-10
ERCOT | 25INR0376 | Hawkins BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 7, LLC | 85005 ELGATO4A 138 kV | Hidalgo | SOUTH | 2025-09-08 | BA | 150.43 | 2023-05-03 | 2023-07-28 | 2023-04-19
ERCOT | 25INR0377 | Proteus Vernon Solar SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2026-12-31 | PV | 75 | 2023-03-27 | 2023-06-19
ERCOT | 25INR0378 | Second Division Storage | SS Completed, FIS Started, No IA | Mound Creek Storage, LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2025-12-31 | BA | 0 | 2023-04-19 | 2023-07-13 | 2023-03-15
ERCOT | 25INR0379 | Starr Storage | SS Completed, FIS Started, No IA | Falcon Lake Storage, LLC | 8795 Roma 138kV | Starr | SOUTH | 2028-03-29 | BA | 0 | 2023-06-28 | 2023-09-22 | 2023-03-08
ERCOT | 25INR0380 | Fike BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 9, LLC | 5754 Aderhold 138kV | Hidalgo | SOUTH | 2025-09-01 | BA | 200.8 | 2023-05-15 | 2023-08-11 | 2023-04-19
ERCOT | 25INR0382 | HappyDogSolar | SS Completed, FIS Started, IA | Rosula Solar LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2026-09-14 | PV | 85.54 | 2023-06-07 | 2023-09-01 | 2023-05-25 |  |  | 2024-12-16
ERCOT | 25INR0384 | Zorro BESS | SS Completed, FIS Completed, No IA | UR-Silo DevCo LLC | 138 kV Ben Wheeler (Bus# 6852) | Van Zandt | NORTH | 2025-12-31 | BA | 153.69 | 2023-03-27 | 2023-06-19 |  | 2024-05-21 | No
ERCOT | 25INR0385 | Bobcat Cameron BESS | SS Completed, FIS Started, No IA | Bobcat BESS, LLC | 5764 East Rio Hondo Substation 138kV | Cameron | COASTAL | 2025-12-01 | BA | 200.78 | 2023-04-19 | 2023-07-14 | 2023-04-11
ERCOT | 25INR0386 | Diaz BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 10, LLC | 8950 Olmito 138kV | Cameron | COASTAL | 2025-09-01 | BA | 241.48 | 2023-05-22 | 2023-08-17 | 2023-05-17 |  | No
ERCOT | 25INR0389 | Stoneridge BESS | SS Completed, FIS Completed, IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP CKT 2 | Milam | SOUTH | 2025-09-01 | BA | 101.9 | 2023-03-13 | 2023-06-09 | 2023-03-09 | 2024-09-06 | No | 2024-04-19
ERCOT | 25INR0390 | Macho Creek BESS | SS Completed, FIS Started, No IA | Macho Creek BESS, LLC | Tap 138kV 8793 RIO GRANDE CITY - 8806 LAS LOMAS | Starr | SOUTH | 2027-05-31 | BA | 150.56 | 2023-06-28 | 2023-09-22 | 2023-06-06
ERCOT | 25INR0391 | Purple Sage BESS 1 | SS Completed, FIS Completed, IA | Purple Sage, LLC | Anna 345 kV Bus# 2373. | Collin | NORTH | 2027-05-30 | BA | 156 | 2023-03-08 | 2023-06-05 | 2023-03-07 | 2024-03-20 | No | 2024-10-11 |  |  | SFS/NtP
ERCOT | 25INR0392 | Purple Sage BESS 2 | SS Completed, FIS Completed, IA | Purple Sage, LLC | Anna 345 kV Bus# 2373 | Collin | NORTH | 2027-05-30 | BA | 156 | 2023-03-08 | 2023-06-05 | 2023-03-07 | 2024-03-20 | No | 2024-10-11 |  |  | SFS/NtP
ERCOT | 25INR0393 | MICOT BESS | SS Completed, FIS Started, No IA | UR-Silo DevCo LLC | Tap 345kV 44645 Singleton - 46500 Tomball Ckt 74 | Montgomery | HOUSTON | 2025-05-30 | BA | 150 | 2023-03-27 | 2023-06-23
ERCOT | 25INR0394 | Orchard Ray BESS | SS Completed, FIS Started, No IA | Pettus BESS | 8593 PETTUS2A 69kV | Bee | SOUTH | 2027-05-01 | BA | 51.85 | 2023-06-07 | 2023-09-01 | 2023-05-31
ERCOT | 25INR0395 | Hinkell BESS | SS Completed, FIS Started, No IA | Reveille BESS | 8612 Reveille 138kV | La Salle | SOUTH | 2026-05-01 | BA | 78.05 | 2023-08-21 | 2023-11-17 | 2023-08-14 |  | No
ERCOT | 25INR0396 | Stewart Grady BESS | SS Completed, FIS Completed, No IA | Grady BESS | Tap 138kV 11368 Expanse Switch – 23841 Sale Ranch | Martin | WEST | 2027-08-15 | BA | 150.5 | 2023-05-26 | 2023-08-22 | 2023-05-01 | 2024-08-23 | No |  |  |  | COD
ERCOT | 25INR0397 | Beeman BESS | SS Completed, FIS Started, No IA | Waelder BESS | 69kV Waelder Substation (7232) | Gonzales | SOUTH | 2026-05-01 | BA | 50.18 | 2023-04-19 | 2023-07-13 | 2023-03-22
ERCOT | 25INR0399 | Blossomheath BESS | SS Completed, FIS Started, No IA | Taurbeng LLC | tap VENUS SWITCH (#1907) – SAM SWITCH (#68090) 345 kV line | Ellis | NORTH | 2026-11-28 | BA | 300.78 | 2023-05-26 | 2023-08-17 | 2023-05-23
ERCOT | 25INR0400 | Maldives Solar (Alternate POI) | SS Completed, FIS Started, IA | Maldives Solar LLC | Tap 345kV 59900 Long Draw - 11318 Scurry County South | Scurry | WEST | 2027-07-01 | PV | 184 | 2023-07-18 | 2023-10-15 | 2023-07-05 |  |  | 2023-12-01
ERCOT | 25INR0401 | WOE Gyp King Wind | SS Completed, FIS Started, No IA | White Oak Energy, LLC | Tap 138kV 33798 GYP_18 – 6088 BENJ4A | King | WEST | 2026-03-15 | WT | 315 | 2023-04-19 | 2023-07-12 | 2023-04-17
ERCOT | 25INR0402 | Driet BESS | SS Completed, FIS Started, No IA | Weimar BESS | 7254 WEIMAR8 138kV | Colorado | SOUTH | 2026-06-01 | BA | 150.52 | 2023-06-07 | 2023-09-01 | 2023-05-31
ERCOT | 25INR0405 | Pledgor BESS | SS Completed, FIS Completed, No IA | Pledgor BESS | Tap Gulftie (43340) – Pledger (43120) circuit 60 | Matagorda | COASTAL | 2027-04-01 | BA | 100.33 | 2023-05-03 | 2023-07-31 | 2023-04-25 | 2024-08-27 | No
ERCOT | 25INR0414 | Rogers Creek BESS | SS Completed, FIS Started, No IA | Dialville BESS | Tap 138 KV DailVille (3160) - Neches Pump (3296) | Cherokee | NORTH | 2027-04-17 | BA | 100.33 | 2023-05-15 | 2023-08-11 | 2023-05-03
ERCOT | 25INR0416 | Proteus Vernon Storage SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2026-12-31 | BA | 0 | 2023-03-27 | 2023-06-19
ERCOT | 25INR0417 | Mesa View Storage | SS Completed, FIS Started, No IA | Mesa View Storage, LLC | Tap 345 kV KINGMTSW (#842) to NORTMC (#76000) | Upton | WEST | 2027-01-29 | BA | 251.3 | 2023-04-19 | 2023-07-12 | 2023-04-12
ERCOT | 25INR0418 | Palacios BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 11, LLC | 5767 HIWAY511SUB8 138kV | Cameron | COASTAL | 2025-09-08 | BA | 125.69 | 2023-05-15 | 2023-08-11 | 2023-05-08
ERCOT | 25INR0419 | Marengo BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 8, LLC | 8640 Kelvin Station 138kV (AEP) | Cameron | COASTAL | 2025-09-08 | BA | 120.72 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  | No
ERCOT | 25INR0420 | Houston BESS | SS Completed, FIS Completed, No IA | SMT Houston | Tap 138 kV LAUDER (#46002) - RITTENHOUSE (#46282) ckt 95 | Harris | HOUSTON | 2026-06-15 | BA | 227.9 | 2023-04-07 | 2023-07-03 | 2023-03-28 | 2024-04-04
ERCOT | 25INR0421 | Aldrin 138 BESS | SS Completed, FIS Started, IA | Aldrin Energy Storage LLC | (Bus: 39015) North Alvin TNMP 138kV | Brazoria | COASTAL | 2026-03-01 | BA | 207 | 2023-05-15 | 2023-08-11 | 2023-05-04 |  | No | 2024-04-18
ERCOT | 25INR0422 | Waterloo Solar 1 | SS Completed, FIS Started, No IA | Waterloo Solar, LLC | AUSTROP TO GARFIELD 345kV LINE [Bus # 7040 - 7048] | Bastrop | SOUTH | 2027-12-01 | PV | 200.64 | 2023-04-19 | 2023-07-12 | 2023-03-30
ERCOT | 25INR0423 | Brackens Solar | SS Completed, FIS Started, No IA | Brackens Solar | 3558 Ranchland 138 kV | Freestone | NORTH | 2026-08-07 | PV | 177.24 | 2023-05-15 | 2023-08-11 | 2023-05-01
ERCOT | 25INR0424 | Brackens BESS | SS Completed, FIS Started, No IA | Brackens BESS | 3558 Ranchland 138 kV | Freestone | NORTH | 2026-08-07 | BA | 103.58 | 2023-05-03 | 2023-07-28 | 2023-04-19
ERCOT | 25INR0425 | Aldrin 345 BESS | SS Completed, FIS Started, IA | Aldrin Energy Storage LLC | (Bus: 43030) Meadow 345kV substation | Brazoria | COASTAL | 2027-12-01 | BA | 362 | 2023-05-15 | 2023-08-11 | 2023-05-05 |  | No | 2024-06-15
ERCOT | 25INR0430 | Hackberry Creek Solar | SS Completed, FIS Started, No IA | Hackberry Creek Solar LLC | tap 345kV 10053 Cattleman Switch - 1058 Longshore Switch | Mitchell | WEST | 2028-07-01 | PV | 175.51 | 2023-07-31 | 2023-10-27 | 2023-07-19
ERCOT | 25INR0431 | Millennium Energy Storage | SS Completed, FIS Completed, No IA | Rocky Mountain Energy Development, LLC | Tap 138kV 23837 Buffalo - 23839 Triangle | Martin | WEST | 2027-04-30 | BA | 102.59 | 2023-05-03 | 2023-07-31 |  | 2024-12-16
ERCOT | 25INR0432 | Brotherton Storage | SS Completed, FIS Completed, IA | BT Brotherton Storage, LLC | 6937 Tucker Sub 138kV | Anderson | NORTH | 2026-12-31 | BA | 176.13 | 2023-04-19 | 2023-07-13 | 2023-04-12 | 2023-12-08 | No | 2024-08-06
ERCOT | 25INR0434 | Bluegill BESS | SS Completed, FIS Started, No IA | Bluegill BESS, LLC | Tap 138 kV 40130 Atascocita - 40690 East Gate | Harris | HOUSTON | 2026-10-01 | BA | 251 | 2023-06-28 | 2023-09-21 | 2023-05-18 |  | No
ERCOT | 25INR0436 | Hess King Solar Farm | SS Completed, FIS Started, No IA | Facility Innovations Group | 8212 DILLEYSW4A 138kV | Frio | SOUTH | 2025-12-31 | PV | 130 | 2023-04-19 | 2023-07-13
ERCOT | 25INR0439 | Stephens Ranch Wind Repower | SS Completed, FIS Started, No IA | Stephens Ranch Wind Energy, LLC | 59900 Long Draw 345 kV | Borden | WEST | 2026-10-01 | WT | 12.4 | 2023-06-28 | 2023-09-20 | 2023-05-15
ERCOT | 25INR0440 | Bronc Rodeo Solar Project | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 16 LLC | Tap 138 kV Line from Temple Pecan Creek (#3420) to the Cow Bayou Switch (#3385) | Falls | NORTH | 2027-04-12 | PV | 121.63 | 2023-05-03 | 2023-07-28
ERCOT | 25INR0441 | Dios BESS | SS Completed, FIS Started, No IA | Dios BESS, LLC | 8117 GANADO138kV | Jackson | SOUTH | 2025-12-31 | BA | 201.08 | 2023-05-15 | 2023-08-11 | 2023-05-08
ERCOT | 25INR0442 | Happy Dog Storage | SS Completed, FIS Started, IA | Rosula Solar LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2026-09-14 | BA | 60.16 | 2023-06-07 | 2023-09-01 | 2023-06-02 |  |  | 2024-12-16
ERCOT | 25INR0444 | Peridot Storage | SS Completed, FIS Started, No IA | BT Castro Storage, LLC | 5836 North Batesville 69kV | Zavala | SOUTH | 2025-12-31 | BA | 50.48 | 2023-05-26 | 2023-08-22 | 2023-05-22
ERCOT | 25INR0447 | Waterloo BESS 1 | SS Completed, FIS Started, No IA | Waterloo Solar, LLC | Tap 345kV 7040 AUSTROP - 7048 GARFIELD | Bastrop | SOUTH | 2027-12-01 | BA | 105.64 | 2023-05-15 | 2023-08-11 | 2023-05-03
ERCOT | 25INR0451 | Tres Rios Ranch BESS | SS Completed, FIS Started, No IA | LectricWind LLC | 76008 Twelvemile 345kV | Upton | WEST | 2027-12-31 | BA | 290 | 2023-05-26 | 2023-08-22 | 2023-05-23
ERCOT | 25INR0452 | Spaniel Farm Solar Project | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 18 LLC | Tap 138 kV 2241 Ennis West Switch - 12320 Templeton | Ellis | NORTH | 2027-04-12 | PV | 100.52 | 2023-05-03 | 2023-07-28
ERCOT | 25INR0455 | John Bull BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 13, LLC | 8482 WEIL TRC4A 138kV | Nueces | COASTAL | 2025-09-01 | BA | 147.42 | 2023-07-31 | 2023-10-27 | 2023-07-27
ERCOT | 25INR0457 | Mountain Creek BESS Expansion | SS Completed, FIS Started, No IA | Mountain Creek Power, LLC | 2412 Mountain Creek East 138kV | Dallas | NORTH | 2028-06-01 | BA | 408.69 | 2023-09-25 | 2023-12-21
ERCOT | 25INR0458 | Surfside Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Holdings, LLC | Tap 138kV 42110 Angleton – 43150 Riwood ckt 82 | Brazoria | COASTAL | 2026-12-31 | BA | 50.34 | 2023-07-19 | 2023-10-10
ERCOT | 25INR0459 | Old Sorrell Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Holdings, LLC | Tap 69kV 6372 Eden - 6376 Colorado River Municipal Water #1 | Concho | WEST | 2028-01-10 | BA | 43.1 | 2023-06-28 | 2023-09-21
ERCOT | 25INR0460 | Acker BESS | SS Completed, FIS Started, No IA | Ogallala BESS LLC | 23912 Ogallala 345 kV | Castro | PANHANDLE | 2027-09-14 | BA | 301.04 | 2023-06-07 | 2023-09-01 | 2023-05-09
ERCOT | 25INR0466 | Yooperlite Storage | SS Completed, FIS Started, No IA | BT Yooperlite Storage, LLC | Tap 138 kV 580 Westbrook Switch - 588 Willow | Wise | NORTH | 2026-05-29 | BA | 175.65 | 2023-06-28 | 2023-09-20 | 2023-06-06
ERCOT | 25INR0467 | Bocanova Power | SS Completed, FIS Completed, IA | Bocanova Power LLC | 39030 TNALVIN 138kV | Brazoria | COASTAL | 2025-07-19 | BA | 150.46 | 2023-06-07 | 2023-09-01 | 2023-05-26 | 2024-07-24 | No | 2024-02-26
ERCOT | 25INR0471 | Tyler BESS | SS Completed, FIS Started, No IA | SMT Tyler LLC | 3104 Shamburger Switch 138kV | Smith | NORTH | 2027-06-30 | BA | 305.3 | 2023-07-10 | 2023-10-03 | 2023-07-03 | [5 empty] | COD
ERCOT | 25INR0473 | Crowded Star I BESS | SS Completed, FIS Started, No IA | Jones City Solar II, LLC | 68014 Open Sky | Jones | WEST | 2026-06-25 | BA | 202.69 | 2023-08-21 | 2023-11-02 | 2023-08-09 | [5 empty] | COD
ERCOT | 25INR0474 | Solheim Solar | SS Completed, FIS Started, No IA | Solheim Solar, LLC | Meridian (Bus# 315) - Glen Rose (Bus #319) 69 kV | Bosque | NORTH | 2027-03-01 | PV | 108.68 | 2023-08-14 | 2023-11-10
ERCOT | 25INR0475 | Castle Corral BESS | SS Completed, FIS Started, No IA | Castle Corral BESS, LLC | 345 kV Russell Gap Switching Station Bus #3348 | Mills | NORTH | 2027-08-23 | BA | 201.1 | 2023-07-31 | 2023-10-27 | 2023-07-26
ERCOT | 25INR0480 | Bell Creek BESS | SS Completed, FIS Completed, IA | BELL CREEK BESS, LLC | Tap 138kV 39500 West Colombia - 39703 FM524 | Brazoria | COASTAL | 2026-05-15 | BA | 200.9 | 2023-06-28 | 2023-09-21 |  | 2024-05-16 |  | 2024-11-14
ERCOT | 25INR0482 | Vault Solar | SS Completed, FIS Completed, No IA | PPM THR Solar | Tap #331 Rwmiller - #320 Jaybird 138kV | Palo Pinto | NORTH | 2026-12-31 | PV | 108.5 | 2023-06-28 | 2023-09-20 | 2023-06-16 | 2024-12-02 | No
ERCOT | 25INR0487 | Marick Rose BESS | SS Completed, FIS Completed, No IA | Marick BESS | Tap 138kV 44521 Marick - 44615 Rosenberg Ckt 60 | Fort Bend | HOUSTON | 2026-05-01 | BA | 50.18 | 2023-07-10 | 2023-10-05 | 2023-06-23 | 2024-04-19
ERCOT | 25INR0489 | Ranchero BESS | SS Completed, FIS Started, No IA | Ranchero Battery Facility, LLC | 7053 Noelke 345 kV | Crockett | WEST | 2026-10-30 | BA | 150 | 2023-06-28 | 2023-09-22
ERCOT | 25INR0491 | Tarim BESS | SS Started, FIS Started, No IA | BRP Tarim BESS LLC | 5727 Pawnee Switching Substation 138kV | Karnes | SOUTH | 2027-12-01 | BA | 201 | 2024-11-19 |  | 2024-10-10
ERCOT | 25INR0492 | Blue Summit Energy Storage | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | 61001 JIM TREECE 345kV | Wilbarger | WEST | 2026-07-01 | BA | 100 | 2023-10-20 | 2024-01-16 | 2023-10-18 |  | No | 2012-02-22
ERCOT | 25INR0493 | PHOTON SOLAR 1 2 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2025-12-31 | PV | 235.66 | 2024-09-02 | 2021-02-02 | 2024-08-28 | 2022-11-28 |  | 2021-10-01 | 2024-10-31
ERCOT | 25INR0494 | Willow Beach Wind | SS Completed, FIS Completed, No IA | ACE DevCo NC LLC | Tap 138 kV Bus# 42100 HUD_8 – Bus# 42960 MUSTNG_S04_8 138kV CKT# 4 | Brazoria | COASTAL | 2027-10-01 | WT | 202.33 | 2023-10-13 | 2024-01-10 | 2023-09-20 | 2024-11-18
ERCOT | 25INR0495 | Dolomite Storage | SS Completed, FIS Started, No IA | BT Wilson Storage, LLC | 218 Rockett 69kV | Ellis | NORTH | 2026-12-01 | BA | 125.7 | 2023-09-08 | 2023-12-04 | 2023-08-22
ERCOT | 25INR0497 | Stegall Solar | SS Completed, FIS Started, No IA | BT Martin Solar, LLC | Elliott (Bus #53) to Franklin (Bus #57) 69kV Transmission Line | Robertson | NORTH | 2026-12-31 | PV | 81.57 | 2023-08-21 | 2023-11-06 | 2023-08-02
ERCOT | 25INR0498 | Stegall Storage | SS Completed, FIS Started, No IA | BT Martin Solar, LLC | Tap connection to a new switching station on the Elliott (Bus #53) - Franklin (Bus #57) 69 kV Transmission Line | Robertson | NORTH | 2026-12-31 | BA | 50.47 | 2023-08-21 | 2023-11-06 | 2023-08-15
ERCOT | 25INR0501 | Longday Solar SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-03-15 | PV | 200.8 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  | No
ERCOT | 25INR0502 | Longday BESS SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap 138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-03-15 | BA | 0 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  | No
ERCOT | 25INR0503 | Uhland Maxwell Expansion | SS Completed, FIS Not Started, IA | Lower Colorado River Authority | 7041 John Dumas 345kV | Caldwell | SOUTH | 2026-04-07 | IC | 188.4 | 2023-09-22 | 2023-12-14 |  |  | No | 2023-12-28
ERCOT | 25INR0504 | Lazy Frog Solar SLF | SS Completed, FIS Started, No IA | Lazy Frog Solar, LLC | 11688 Thorn Tree Switch 345kV | Franklin | NORTH | 2028-04-10 | PV | 105.8 | 2023-09-22 | 2023-12-14
ERCOT | 25INR0505 | Mud Cat Solar SLF | SS Completed, FIS Started, No IA | Mud Cat Solar, LLC | Tap 138KV 11768 Hawk Hollow – 1768 Deport | Lamar | NORTH | 2027-09-13 | PV | 100.5 | 2023-10-20 | 2024-01-16 | 2024-05-14
ERCOT | 25INR0506 | Lazy Frog Storage SLF | SS Completed, FIS Started, No IA | Lazy Frog Solar, LLC | 11688 Thorn Tree Switch 345kV | Franklin | NORTH | 2028-04-10 | BA | 0 | 2023-09-22 | 2023-12-14
ERCOT | 25INR0507 | Mud Cat Storage SLF | SS Completed, FIS Started, No IA | Mud Cat Solar, LLC | 11768 Hawk Hollow – 1768 Deport 138kV | Lamar | NORTH | 2027-09-13 | BA | 0 | 2023-10-20 | 2024-01-16 | 2024-05-14
ERCOT | 25INR0510 | Deer BESS | SS Completed, FIS Started, No IA | GRS BESS Texas Two | 1687 BLOOSOM_T8 138kV | Lamar | NORTH | 2025-10-31 | BA | 102.31 | 2023-09-08 | 2023-12-01 | 2023-08-21
ERCOT | 25INR0511 | Pearl Moon | SS Completed, FIS Started, No IA | Pearl Moon Solar, LLC | Tap 345kV 9073 Holman - 44200 Hillje | Colorado | SOUTH | 2028-03-31 | PV | 208 | 2023-09-07 | 2023-12-06 | 2023-08-23
ERCOT | 25INR0512 | Monument Hill Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 7055 Fayette - 9074 Lytton Springs | Fayette | SOUTH | 2027-06-01 | PV | 200 | 2023-10-13 | 2024-01-10 | 2023-08-23
ERCOT | 25INR0513 | Kahla Storage | SS Completed, FIS Started, No IA | BT Kahla Storage, LLC | Tap 345kV 46020 Limestone 967 Gibbons Creek Circuit 50 | Leon | NORTH | 2028-12-29 | BA | 200.9 | 2023-08-21 | 2023-11-17 | 2023-08-15
ERCOT | 25INR0515 | Fagus Storage SLF | SS Completed, FIS Started, No IA | Greenalia Energy Storage MISAE II LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2026-09-01 | BA | 0 | 2023-10-25 | 2024-01-22 | 2023-09-22
ERCOT | 25INR0519 | Silver Birch Solar | SS Completed, FIS Started, No IA | Silver Birch Solar, LLC | Tap 345kV 3400 Twin Oak - 967 Gibbons Creek | Brazos | NORTH | 2026-12-31 | PV | 201 | 2024-02-02 | 2024-04-29
ERCOT | 25INR0520 | Silver Birch BESS | SS Completed, FIS Started, No IA | Silver Birch BESS, LLC | Tap 345 kV 3400 Twin Oak - 967 Gibbons Creek | Brazos | NORTH | 2026-12-31 | BA | 208.8 | 2024-02-02 | 2024-04-29
ERCOT | 25INR0528 | Indigo Storage 2 | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | BA | 60 | 2023-09-22 | 2023-12-20
ERCOT | 25INR0529 | Indigo Storage 3 | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | BA | 60 | 2023-11-14 | 2024-02-09
ERCOT | 25INR0530 | Indigo Storage 4 | SS Completed, FIS Started, No IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2026-08-17 | BA | 60 | 2023-10-25 | 2024-01-22
ERCOT | 25INR0531 | CPS Energy AvR1CT2 Rotor Replacement | SS Completed, FIS Completed, No IA | CPS Energy | 5475 Braunig 345kV | Bexar | SOUTH | 2025-03-03 | CC | 23.2 | 2023-10-13 | 2024-01-10 |  | 2024-04-25 |  |  | 2024-11-22
ERCOT | 25INR0541 | Port City Energy Storage | SS Completed, FIS Started, No IA | Port City Energy Storage, LLC | Tap 138kV 80258 Mayo4A - 80260 Gila4A | San Patricio | COASTAL | 2026-06-15 | BA | 101.2 | 2023-10-25 | 2024-01-22 | 2023-10-17 |  | No
ERCOT | 25INR0542 | Hynes Bay Energy Storage | SS Completed, FIS Started, No IA | Hynes Bay Energy Storage, LLC | Tap 138kV 5546 DANEVANG SW - 8121 BLESSING | Wharton | SOUTH | 2026-04-15 | BA | 101.2 | 2023-10-25 | 2024-01-22 | 2023-10-16
ERCOT | 25INR0544 | Palacios Bay Energy Storage | SS Completed, FIS Started, No IA | Palacios Bay Energy Storage, LLC | Tap 138kV #8115 WADSWORT4A - #8139 CELNEBC4B | Matagorda | COASTAL | 2026-06-15 | BA | 101.2 | 2023-10-19 | 2024-01-16 | 2023-10-10
ERCOT | 25INR0545 | Blue Creek Energy Storage | SS Completed, FIS Started, No IA | Blue Creek Energy Storage, LLC | Tap 138kV 42985 DYANN_POI8 - 43190 S_LANE_B138 Ckt 60 | Wharton | SOUTH | 2026-06-15 | BA | 101.2 | 2023-10-13 | 2024-01-10 | 2023-10-11 |  | No
ERCOT | 25INR0546 | VISOL 1 SOLAR | SS Completed, FIS Started, No IA | VISOL 1 SOLAR, LLC | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2027-09-01 | PV | 94.78 | 2023-10-25 | 2024-01-22
ERCOT | 25INR0547 | Indigo solar 2 | SS Completed, FIS Started, No IA | Indigo Solar 2 | Tap 345KV 68001 Clayton 345KV -68000 WShack Ckt 2 | Fisher | WEST | 2027-07-15 | PV | 180 | 2023-10-04 | 2023-12-22 | 2024-08-13
ERCOT | 25INR0550 | Carolina Storage Friendswood | SS Completed, FIS Started, No IA | CSE Storage, LLC | TAP 138kV 39010 HASTINGS - 38980 FRIENDSWOOD | Brazoria | COASTAL | 2025-12-14 | BA | 105.08 | 2024-02-02 | 2024-04-29 | 2024-01-17
ERCOT | 25INR0552 | HarryoungBESS | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | 8319 Rio Hondo sub 138kV | Cameron | COASTAL | 2027-05-15 | BA | 190.01 | 2023-10-04 | 2023-12-19 | 2023-09-19
ERCOT | 25INR0554 | Dan Kearney BESS | SS Completed, FIS Completed, IA | Dan Kearney BESS LLC | 39703 TNFM524 138kV | Brazoria | COASTAL | 2025-06-01 | BA | 200.78 | 2024-01-11 | 2024-04-08 | 2024-01-03 | 2024-10-02 |  | 2024-10-18
ERCOT | 25INR0555 | Stargazer Solar | SS Completed, FIS Started, No IA | Stargazer Solar LLC | 44010 WA Parish - 42980 Nash 138 kV Ckt 02 | Brazoria | COASTAL | 2027-02-01 | PV | 157.7 | 2023-10-30 | 2024-01-26 | 2023-10-23
ERCOT | 25INR0556 | Stargazer BESS | SS Completed, FIS Started, No IA | Stargazer Solar LLC | 44010 WA Parish - 42980 Nash 138 kV | Brazoria | COASTAL | 2027-02-01 | BA | 104.5 | 2023-10-30 | 2024-01-26 | 2023-10-23
ERCOT | 25INR0557 | McCamey's Castle Battery | SS Completed, FIS Started, No IA | Castle Storage, LLC | 76597 Robbins Switch 138 kV | Upton | WEST | 2025-12-15 | BA | 409.6 | 2023-10-13 | 2024-01-10 | 2023-10-09
ERCOT | 25INR0558 | Ayass BESS | SS Completed, FIS Started, No IA | Harvick BESS, LLC | 6206 Bush Knob 69kV | Throckmorton | WEST | 2026-10-15 | BA | 51.28 | 2023-12-04 | 2024-03-01 | 2023-11-15
ERCOT | 25INR0566 | Copano Bay Energy Storage | SS Completed, FIS Started, No IA | Copano Bay Energy Storage, LLC | Tap 138kV 42980 Nash - 44010 WA Parish Ckt 2 | Brazoria | COASTAL | 2026-06-15 | BA | 201.04 | 2023-10-25 | 2024-01-22 | 2023-10-17
ERCOT | 25INR0578 | Forest Creek Wind Repower | SS Completed, FIS Completed, No IA | RWE Clean Energy Development, LLC | Mcdonald 138 kV (Bus #: 1333) | Glasscock | WEST | 2025-12-15 | WT | 126.9 | 2024-01-11 | 2024-04-05 | 2023-12-08 | 2024-12-10
ERCOT | 25INR0579 | Albatross BESS 2 | SS Completed, FIS Started, No IA | Albatross Solar, LLC | Tap 138kV 165 Windsor Switch - 161 McGregor | McLennan | NORTH | 2028-02-22 | BA | 159.6 | 2024-02-27 | 2024-05-22 | 2024-01-03 | [5 empty] | COD
ERCOT | 25INR0582 | Maleza Storage II | SS Completed, FIS Started, No IA | Brush Storage, LLC | 44220 Julia 345kV | Wharton | SOUTH | 2025-11-01 | BA | 256.1 | 2024-02-27 | 2024-05-24 | 2024-02-20
ERCOT | 25INR0583 | Shannon Wind Repower | SS Completed, FIS Started, No IA | Shannon Wind, LLC | 1458 Cobb Switching Station 345 kV | Archer | WEST | 2025-12-15 | WT | 18.7 | 2024-02-27 | 2024-05-31 | 2024-01-29
ERCOT | 25INR0586 | Zeus Armstrong Solar | SS Completed, FIS Started, No IA | Armstrong Solar, LLC | Tap 345KV 23900 AlLIBATES -23914 TULECNYN | Armstrong | PANHANDLE | 2028-04-17 | PV | 509.6 | 2024-05-20 | 2024-06-19
ERCOT | 25INR0587 | Zeus Armstrong BESS | SS Completed, FIS Started, No IA | Armstrong BESS, LLC | Tap 345KV 23900 ALIBATES - 23914 TULECNYN | Armstrong | PANHANDLE | 2028-04-17 | BA | 421.5 | 2024-03-22 | 2024-06-19
ERCOT | 25INR0606 | Proteus Thornton Ranch Solar SLF | SS Completed, FIS Started, No IA | Thornton Ranch Solar, LLC | 37990 TNSTAGHORN1 138kV | Ward | WEST | 2026-09-30 | PV | 180 | 2024-02-26 | 2024-05-20 | 2024-02-12
ERCOT | 25INR0607 | Proteus Thornton Ranch Storage SLF | SS Completed, FIS Started, No IA | Thornton Ranch Solar, LLC | 37990 TNSTAGHORN1 138kV | Ward | WEST | 2026-09-30 | BA | 0 | 2024-03-22 | 2024-06-19 | 2024-03-11
ERCOT | 25INR0608 | Proteus London-Leigh Solar SLF | SS Completed, FIS Started, No IA | London Leigh Solar, LLC | 345kV Bernoulli (bus # 59907) | Glasscock | WEST | 2027-12-31 | PV | 600 | 2024-03-22 | 2024-06-19 | 2024-02-19
ERCOT | 25INR0609 | Proteus London-Leigh Storage SLF | SS Completed, FIS Started, No IA | London Leigh Solar, LLC | Bernoulli (bus # 59907) | Glasscock | WEST | 2027-12-31 | BA | 0 | 2024-02-27 | 2024-04-19 | 2023-12-22
ERCOT | 25INR0610 | Adam Bryant BESS | SS Completed, FIS Started, No IA | Adam Bryant BESS LLC | Tap 138kV 5225 HONDO – 5819 HONDO CREEK | Medina | SOUTH | 2027-12-01 | BA | 99.9 | 2024-02-26 | 2024-05-24
ERCOT | 25INR0611 | Carolina Storage Odessa | SS Completed, FIS Started, No IA | CSE STORAGE, LLC | 1058 LONGSHORE 345kV | Howard | WEST | 2027-04-20 | BA | 202.05 | 2024-02-02 | 2024-04-29 | 2024-01-17
ERCOT | 25INR0616 | Bobcat Bluff Storage SLF | SS Completed, FIS Started, No IA | Cub Storage LLC | 1475 Windthorst 138 kV | Archer | WEST | 2027-04-15 | BA | 0 | 2024-02-27 | 2024-05-25
ERCOT | 25INR0622 | Turkey Creek Solar | SS Completed, FIS Started, No IA | Greenray Solar Corporation | 7425 ODLASW 138kV | Kinney | SOUTH | 2026-09-29 | PV | 211.2 | 2024-02-26 | 2024-05-24
ERCOT | 25INR0623 | Turkey Creek Battery Energy Storage System | SS Completed, FIS Started, No IA | Greenray Solar Corporation | 7425 ODLASW 138 kV | Kinney | SOUTH | 2026-09-29 | BA | 40 | 2024-03-29 | 2024-05-24
ERCOT | 25INR0628 | Carolina Storage Wichita Falls | SS Completed, FIS Started, No IA | CSE Storage, LLC | Tap 345kV 1422 Bowman - 1458 Cobb Switch | Wichita | WEST | 2027-09-22 | BA | 202 | 2024-02-26 | 2024-05-25 | 2024-02-14
ERCOT | 25INR0629 | Carolina Storage Midland | SS Completed, FIS Started, No IA | CSE Storage, LLC | Tap 345kV 10057 Prong Moss Switch - 10062 Rockhound Switch CKT 1 | Howard | WEST | 2028-03-15 | BA | 203.6 | 2024-07-01 | 2024-09-26 | 2024-03-26
ERCOT | 25INR0632 | Jenna Eco-Electric Solar | SS Completed, FIS Started, No IA | Clean Energy Holdings, LLC | Tap 345 kV 1048 Tonkawa Switch - 1430 Graham SES | Fisher | WEST | 2027-06-05 | PV | 576.3 | 2024-05-20 | 2024-08-13 | 2024-05-17
ERCOT | 25INR0637 | South Loop Energy Center | SS Completed, FIS Started, No IA | Concurrent Holdco LLC | Tap 345 KV 5400 SPRUCE - 5231 HOWARD | Bexar | SOUTH | 2028-05-01 | BA | 161.3 | 2024-05-09 | 2024-08-05 | 2024-04-24
ERCOT | 25INR0653 | Southfork Energy Storage | SS Completed, FIS Started, No IA | Southfork Energy Storage, LLC | tap 345kV 60709 Oersted - 91919 Edison CKT 1 | Kimble | SOUTH | 2028-11-30 | BA | 306.4 | 2024-07-22 | 2024-10-08 | 2024-06-13
ERCOT | 25INR0656 | Gilleys Energy Storage | SS Completed, FIS Started, No IA | Gilleys Energy Storage, LLC | Tap 345 kV 1730 West Krum - 6111 Riley CKT 2 | Wise | NORTH | 2028-04-21 | BA | 306.4 | 2024-06-03 | 2024-08-27 | 2024-05-06
ERCOT | 25INR0657 | O'Bannion Energy Storage | SS Completed, FIS Started, No IA | O'Bannion Energy Storage, LLC | 1506 Long Hollow Switch 345 kV | Jack | NORTH | 2027-09-25 | BA | 306.4 | 2024-05-09 | 2024-08-05 | 2024-05-01
ERCOT | 25INR0660 | Wooderson Energy Storage | SS Completed, FIS Started, No IA | Wooderson Energy Storage, LLC | Tap 345 kV 11418 TECUMSEH- 1421 Willow Creek | Jack | NORTH | 2028-04-30 | BA | 306.4 | 2024-05-09 | 2024-08-05 | 2024-04-18
ERCOT | 25INR0661 | McCrae Energy Storage | SS Completed, FIS Started, No IA | McCrae Energy Storage, LLC | Tap 345 kV 1900 COMCHPKW_5 - 1440 COMCHESS1_5 | Erath | NORTH | 2028-04-21 | BA | 306.35 | 2024-05-20 | 2024-08-13 | 2024-05-01
ERCOT | 25INR0666 | GIBSON BRANCH BESS | SS Completed, FIS Started, No IA | Gibson Branch BESS LLC | 7064 Lampasas Substation 138kV | Lampasas | NORTH | 2028-01-15 | BA | 142.9 | 2024-05-20 | 2024-08-14 | 2024-04-24
ERCOT | 25INR0672 | Fagus Solar Park 2 SLF | SS Completed, FIS Completed, IA | Excel Advantage Services, LLC dba Misae Solar Park II | 60501 Tesla 345 kV | Childress | PANHANDLE | 2025-12-01 | PV | 166.57 | 2024-06-03 | 2018-07-06 | 2024-05-30 | 2024-02-27 | No | 2019-02-21
ERCOT | 25INR0673 | PHOTON SOLAR 4 SLF | SS Completed, FIS Completed, No IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2024-12-30 | PV | 105.98 | 2024-09-04 | 2021-02-02 | 2024-08-21 | 2022-11-28 |  |  | 2024-11-04
ERCOT | 25INR0688 | Giga Texas Data Center | SS Completed, FIS Started, No IA | Giga Texas Energy, LLC | HORNSBY Substation POIB# 7047 Site will be connected behind the meter at Medium Voltage 24.9 kV with non export controls GSU TRANSFORMER 80/106/133MVA 345kV DELTA PRIMARY 24.9kV WYE-G SECONDARY Z=XX%, 65DEG C RISE | Travis | SOUTH | 2025-08-30 | BA | 133 | 2024-08-27 | 2024-11-25 | 2024-07-30
ERCOT | 25INR0691 | PHOTON BESS2 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2025-11-28 | BA | 152.74 | 2022-06-02 | 2022-08-29 | 2024-08-28 | 2023-04-10 |  | 2023-03-23 | 2024-11-26
ERCOT | 25INR0693 | Leon BESS | SS Started, FIS Started, No IA | Leon BESS | Tab 138kv 3355 Grapeland_Magnolia - 3357 Pleasant_Springs. | Houston | NORTH | 2027-01-16 | BA | 153.7 | 2024-11-26 |  | 2024-11-18
ERCOT | 25INR0706 | Bocanova Power II | SS Started, FIS Started, No IA | Bocanova Power II LLC | 39030 TNMP Alvin 138kV | Brazoria | COASTAL | 2025-09-30 | BA | 150.46 | 2024-10-10 |  | 2024-10-01
ERCOT | 26INR0001 | Turin TxHSR TPSS HN-6 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2028-07-15 | OT | 50 | 2019-09-27 | 2021-04-28 | 2019-09-27
ERCOT | 26INR0004 | GRIMES SOLAR | SS Completed, FIS Started, No IA | CG Grimes County LLC | 40600 Roans Prairie 345kV | Grimes | NORTH | 2026-02-15 | PV | 153.45 | 2022-03-14 | 2022-06-03 | 2022-03-07
ERCOT | 26INR0008 | Puerto Del Sol 1 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2026-12-31 | PV | 213.8 | 2022-05-16 | 2022-08-13
ERCOT | 26INR0014 | Greenwolfe Solar Alt POI | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | Tap 345 kV line from Farmersville Switch (#1685) to Cyclone Switch (#11689) | Hunt | NORTH | 2026-09-24 | PV | 274.14 | 2022-11-15 | 2023-02-10 | 2022-11-07
ERCOT | 26INR0018 | Galactic Storage SLF | SS Completed, FIS Started, No IA | UKA North America, LLC | Tap 138kV 1744 Gordonville - 11704 Sherman West | Grayson | NORTH | 2026-11-15 | BA | 0 | 2022-09-02 | 2022-11-30 | 2022-08-10
ERCOT | 26INR0019 | HyFuels Green Lake Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | 8189 Tungsten 138kV | Victoria | SOUTH | 2027-12-01 | PV | 346 | 2022-09-27 | 2022-12-22 | [6 empty] | COD
ERCOT | 26INR0021 | HyFuels Western Farmland Wind | SS Completed, FIS Not Started, IA | HyFuels Green Lake Wind LLC | 8721 BEECHER4A 138kV | Victoria | SOUTH | 2027-06-30 | WT | 253.29 | 2022-09-27 | 2022-12-22 |  |  |  | 2024-07-24 |  |  | COD
ERCOT | 26INR0022 | Bowhead Storage 2 | SS Completed, FIS Started, No IA | Baffin Bay Solar, LLC | Tap 138kV 8519 Kleberg-8518 Kingsville | Kleberg | COASTAL | 2026-01-15 | BA | 0 | 2022-09-21 | 2022-12-16 | 2022-09-19
ERCOT | 26INR0023 | Leon Solar Park | SS Completed, FIS Started, IA | Misae Solar IV LLC | Tap 138kV Grapeland Magnolia Tap (bus #3355) to Pleasant Springs POI (bus# 3357) section of the Jewett -Crockett 138kV Line | Leon | NORTH | 2026-07-01 | PV | 210.1 | 2022-09-15 | 2022-12-13 | 2022-08-27 |  | Yes | 2024-05-21 |  |  | MW Size
ERCOT | 26INR0024 | Becerra Creek Storage 1 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2026-12-01 | BA | 125.62 | 2022-09-21 | 2022-12-19 | 2022-09-07
ERCOT | 26INR0028 | HyFuels Calhoun Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | Tap 345kV 8715 RADIANT7A - 8728 COBRA7A | Victoria | SOUTH | 2026-10-01 | PV | 301.82 | 2022-10-18 | 2023-01-15 |  |  | Yes
ERCOT | 26INR0030 | Perry Creek Solar SLF | SS Completed, FIS Started, No IA | Perry Creek Solar, LLC | 345kV Navarro (#68091) to Limestone (# 46020) | Freestone | NORTH | 2027-03-24 | PV | 102.04 | 2022-12-07 | 2023-03-04 | 2022-11-08
ERCOT | 26INR0031 | Perry Creek Storage SLF | SS Completed, FIS Started, No IA | Perry Creek Solar, LLC | 345kV Navarro (#68091) to Limestone (# 46020) | Freestone | NORTH | 2027-03-24 | BA | 0 | 2022-12-07 | 2023-03-04 | 2022-11-08
ERCOT | 26INR0033 | Fairway Storage | SS Completed, FIS Started, No IA | Fairway Storage LLC | Tap 138kV 3503 FAIRWPOD_8 - 196 FAIRFIELD | Freestone | NORTH | 2027-09-24 | BA | 121.03 | 2022-11-07 | 2023-02-04
ERCOT | 26INR0034 | Bracero Pecan Storage | SS Completed, FIS Not Started, IA | Bracero Pecan Storage LLC | 60716 SARAGOSA 138kV | Reeves | WEST | 2026-06-01 | BA | 232 | 2022-11-07 | 2023-02-04 |  |  |  | 2024-06-27
ERCOT | 26INR0042 | Valhalla Solar | SS Completed, FIS Completed, IA | Industrial Papa Project LLC | Tap 138 kV 42215 Copper to 42195 Booster | Brazoria | COASTAL | 2026-05-31 | PV | 306.8 | 2023-03-09 | 2023-06-05 | 2023-03-08 | 2024-03-19 | No | 2023-12-06
ERCOT | 26INR0045 | LUND STORAGE CENTER 1 | SS Completed, FIS Started, No IA | Lund Storage Center 1, LLC | TAP 138 KV LINE AND CREATE NEW BUS BETWEEN KIMBRO (7337) AND ELGIN SWITCH (3650) | Bastrop | SOUTH | 2026-12-31 | BA | 407.55 | 2023-01-17 | 2023-04-14
ERCOT | 26INR0046 | Paluxy Solar | SS Completed, FIS Completed, No IA | S&S Renewables LLC | Double tapping: 345kV 5915 STP - 5133 Elm Creek ckt#1 and 345kV 5068 Cachena – 5323 Old Hickory ckt#2 | Victoria | SOUTH | 2027-06-30 | PV | 1029.06 | 2023-01-03 | 2023-03-30 | 2022-12-27 | 2024-05-31 | Yes
ERCOT | 26INR0047 | Paluxy Storage | SS Completed, FIS Completed, No IA | S&S Renewables LLC | Double tapping: 345kV 5915 STP - 5133 Elm Creek ckt#1 and 345kV 5068 Cachena – 5323 Old Hickory ckt#2 | Victoria | SOUTH | 2027-06-30 | BA | 511.68 | 2023-01-03 | 2023-03-30 | 2022-12-12 | 2024-07-23
ERCOT | 26INR0049 | Calpine Freestone Peaker 1 | SS Completed, FIS Completed, IA | Freestone Power Generation, LLC | 3134 RICHLAND CHAMBERS 345kV (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2026-05-01 | GT | 228 | 2023-04-19 | 2023-07-13 | 2023-04-11 | 2024-04-23 |  | 2024-05-30
ERCOT | 26INR0068 | Charro Creek Solar 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | PV | 203 | 2023-01-30 | 2023-04-28 | 2023-02-10
ERCOT | 26INR0069 | Charro Creek Storage 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | BA | 0 | 2023-03-08 | 2023-04-28 | 2023-02-15
ERCOT | 26INR0070 | Charro Creek Solar 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | PV | 203 | 2023-03-08 | 2023-06-01 | 2023-02-15
ERCOT | 26INR0071 | Charro Creek Storage 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | BA | 0 | 2023-03-08 | 2023-06-01 | 2023-02-15
ERCOT | 26INR0072 | Charro Creek Solar 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap on PAWNEESW5 (#5725) - COLETO7A (#8164) Line | Karnes | SOUTH | 2026-07-01 | PV | 203 | 2023-03-08 | 2023-06-01 | 2023-02-15
ERCOT | 26INR0073 | Charro Creek Storage 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2026-07-01 | BA | 0 | 2023-01-30 | 2023-04-28 | 2023-02-10
ERCOT | 26INR0074 | Anila Solar | SS Completed, FIS Completed, No IA | Alina Energy LLC | Tap 345kV 5133 Elm Creek - 5901 San Miguel Gen Ckt 1 | Wilson | SOUTH | 2026-07-02 | PV | 200.8 | 2023-01-30 | 2023-04-28 | 2023-01-20 | 2024-07-10
ERCOT | 26INR0076 | Matias Solar | SS Completed, FIS Started, No IA | Industrial Bravo Project II LLC | 8114 Conoco 138kV | Matagorda | COASTAL | 2027-03-31 | PV | 152.3 | 2023-03-13 | 2023-06-09 | 2023-03-08 |  | No
ERCOT | 26INR0077 | Anila BESS | SS Completed, FIS Completed, No IA | Alina Energy LLC | Tap of 345 kV Elm Creek (Bus# 5133) - San Miguel Gen (Bus# 5901) Transmission Line Ckt 1 | Wilson | SOUTH | 2026-07-02 | BA | 209 | 2023-02-20 | 2023-05-20 |  | 2024-07-10
ERCOT | 26INR0082 | Amerada Solar | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2027-08-23 | PV | 301.57 | 2023-05-15 | 2023-08-11 | 2023-04-28
ERCOT | 26INR0083 | Zeppelin Energy Storage | SS Completed, FIS Started, No IA | ZEPPELIN ENERGY STORAGE LLC | 6464 San Angelo North | Tom Green | WEST | 2026-02-16 | BA | 163.93 | 2023-01-30 | 2023-04-28
ERCOT | 26INR0084 | Amerada Storage | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2027-08-23 | BA | 150.78 | 2023-05-15 | 2023-08-11 | 2023-04-28
ERCOT | 26INR0085 | Mountain Creek Thermal Expansion | SS Completed, FIS Started, No IA | Mountain Creek Power, LLC | 2412 Mountain Creek East 138kV | Dallas | NORTH | 2028-06-01 | GT | 736.98 | 2023-10-30 | 2024-01-26
ERCOT | 26INR0088 | La Salle Solar | SS Completed, FIS Started, No IA | OCI La Salle Solar LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) | La Salle | SOUTH | 2027-07-01 | PV | 503.9 | 2023-04-19 | 2023-07-14 | 2023-04-03 |  | No
ERCOT | 26INR0089 | La Salle ESS | SS Completed, FIS Started, No IA | OCI La Salle ESS LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) CKT#2 | La Salle | SOUTH | 2027-07-01 | BA | 503.9 | 2023-04-07 | 2023-07-03 | 2023-03-15 |  | Yes
ERCOT | 26INR0098 | Douie Solar | SS Completed, FIS Started, No IA | Buffalo Spring Solar LLC | Tap 138 kV 3501 Sea way Teague - 3394 Jewett | Freestone | NORTH | 2027-09-30 | PV | 221.2 | 2023-05-15 | 2023-08-11 | 2023-05-12
ERCOT | 26INR0106 | Upstream BESS | SS Completed, FIS Started, No IA | Upstream Storage LLC | 1902 Johnson Switch | Johnson | NORTH | 2026-05-29 | BA | 461.6 | 2023-03-27 | 2023-06-24 | 2023-03-14
ERCOT | 26INR0107 | Freedom Falcon BESS | SS Completed, FIS Started, No IA | Falcon BESS, LLC | Tap 345kV 80307 Delsol - 80225 Cenizo CKT#2 | Zapata | SOUTH | 2026-05-31 | BA | 501.9 | 2023-06-28 | 2023-09-22 | 2023-06-14
ERCOT | 26INR0109 | Calpine Freestone Peaker 2 | SS Completed, FIS Completed, IA | FPEC, LLC | 3134 RICHLAND CHAMBERS (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2026-05-01 | GT | 228 | 2023-04-19 | 2023-07-13 | 2023-04-11 | 2024-04-23 | No | 2024-05-30
ERCOT | 26INR0110 | Western Flats Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain Solar Facility 1 LLC | Tap 138 kV 76615 Crane -76635 King Mountain; POI is 7.85 miles from Crane. | Crane | WEST | 2026-12-31 | PV | 410.2 | 2023-04-07 | 2023-07-05
ERCOT | 26INR0111 | Graphic Packaging Gas | SS Completed, FIS Started, No IA | Graphic Packaging International | Tap 138kV 3446 Peppervine Switch - 3544 Castleman Substation | McLennan | NORTH | 2026-01-01 | GT | 43.36 | 2024-01-11 | 2024-03-19 | 2024-01-05
ERCOT | 26INR0112 | Lemma Solar | SS Completed, FIS Started, No IA | Greening USA Corp. | 6088 Benjamin AEP 138kV | Knox | WEST | 2028-07-01 | PV | 100.61 | 2023-04-07 | 2023-07-05
ERCOT | 26INR0113 | Meitner Wind | SS Completed, FIS Started, IA | IP Meitner, LLC | 79000 Gray Substation 345kV | Gray | PANHANDLE | 2027-12-20 | WT | 836.5 | 2023-07-18 | 2023-10-15 | 2023-06-29 |  |  | 2024-04-19
ERCOT | 26INR0114 | Ochoa Energy Storage | SS Completed, FIS Started, No IA | Ochoa Energy Storage LLC | Tap 138kV Katy (44420) - Franz (44260) Ckt 09 | Waller | HOUSTON | 2027-06-03 | BA | 260.8 | 2023-04-19 | 2023-07-14 | 2023-04-11 |  | No
ERCOT | 26INR0116 | Falcon Zapata Storage 138 | SS Completed, FIS Started, No IA | Falcon BESS, LLC | Tap 138kV 8299 Zapata - 8957 Lopeno | Zapata | SOUTH | 2026-05-31 | BA | 200.79 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  | No
ERCOT | 26INR0117 | Oyster Creek Solar I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2026-06-23 | PV | 0 | 2023-06-28 | 2023-09-22 | 2023-06-15 |  | No
ERCOT | 26INR0118 | Oyster Creek Storage I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2026-06-23 | BA | 0 | 2023-06-28 | 2023-09-22 | 2023-06-20 |  | No
ERCOT | 26INR0120 | Bramble Energy Center | SS Completed, FIS Started, No IA | Bramble Energy Center LLC | 8236 Batesville 138kV | Zavala | SOUTH | 2026-10-03 | BA | 225.1 | 2023-09-08 | 2023-12-04 | 2023-08-15
ERCOT | 26INR0121 | Pioneer Hutt Solar (Alternative POI) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 345kV 11028 Odessa Ehv - 59901 Grelton (West C) | Midland | WEST | 2026-12-30 | PV | 116 | 2023-06-28 | 2023-09-22 | 2023-06-12
ERCOT | 26INR0128 | SunWave Solar | SS Completed, FIS Started, No IA | Buckeye Nueces Bay Solar LLC | 8459 Bunsen 138kV | Nueces | COASTAL | 2027-05-29 | PV | 159.89 | 2023-05-26 | 2023-08-22
ERCOT | 26INR0130 | Elm Flats Solar SLF | SS Completed, FIS Started, No IA | Elm Flats Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2026-12-01 | PV | 125.58 | 2024-07-30 | 2023-09-01 | 2023-06-13
ERCOT | 26INR0131 | Elm Flats Storage SLF | SS Completed, FIS Started, No IA | Elm Flats Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2026-12-01 | BA | 0 | 2023-06-07 | 2023-09-01 | 2023-05-22
ERCOT | 26INR0134 | Myers Solar | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8629 Baez 69 kV | Bee | SOUTH | 2028-07-01 | PV | 100.94 | 2023-06-28 | 2023-09-20 | 2023-06-01 | [5 empty] | COD
ERCOT | 26INR0135 | Myers Storage | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8629 Baez 69 kV | Bee | SOUTH | 2028-07-01 | BA | 75.7 | 2023-06-28 | 2023-09-20 | 2023-06-01 | [5 empty] | COD
ERCOT | 26INR0138 | Weathervane Solar SLF | SS Completed, FIS Started, No IA | Mallard Place LLC | Tap 138 kV 620 Bowie - 741 Dye Mound | Montague | NORTH | 2026-12-31 | PV | 160.49 | 2023-08-14 | 2023-11-02 | 2023-07-20
ERCOT | 26INR0139 | Weathervane Storage SLF | SS Completed, FIS Started, No IA | Mallard Place LLC | Tap 138 kV 620 Bowie - 741 Dye Mound | Montague | NORTH | 2026-12-31 | BA | 32.47 | 2023-08-14 | 2023-11-02 | 2023-07-20
ERCOT | 26INR0143 | Santa Garcias Solar | SS Completed, FIS Started, No IA | Oxy Renewable Energy LLC | Tap 138kV 8515 Alazan - 8458 Barney Davis | Kleberg | COASTAL | 2029-02-01 | PV | 265 | 2023-06-28 | 2023-09-22 | 2023-06-07 |  | No |  |  |  | COD
ERCOT | 26INR0144 | Wittig Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Wittig LLC | 138 kV Gulftie (#43340) – San Bernard (#43110) | Wharton | SOUTH | 2027-09-30 | PV | 106.9 | 2024-02-27 | 2024-05-24 | 2024-01-18 |  | No
ERCOT | 26INR0146 | DMF Sagerton Solar SLF | SS Completed, FIS Started, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2026-12-31 | PV | 125.5 | 2023-07-31 | 2023-10-27 | 2023-07-24
ERCOT | 26INR0147 | Seven Springs Solar | SS Completed, FIS Started, No IA | Hancock Springs, LLC | Tap 7061 COPPERAS COVE 7260 Kempner 138kV | Coryell | NORTH | 2026-05-15 | PV | 145.57 | 2023-09-22 | 2023-12-14 | 2023-09-05
ERCOT | 26INR0148 | DMF Sagerton Storage SLF | SS Completed, FIS Started, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2026-12-31 | BA | 0 | 2023-07-31 | 2023-10-27 | 2023-07-20
ERCOT | 26INR0150 | Proving Ground Solar | SS Completed, FIS Started, No IA | Lantana Solar LLC | Tap 138 kV Live Oak (6500) - Santiago (6490) | Schleicher | WEST | 2026-03-01 | PV | 82.1 | 2023-07-10 | 2023-10-05
ERCOT | 26INR0153 | Apis Solar | SS Completed, FIS Started, No IA | S&S Renewables LLC | Tap 345kV 8606 Goddard – 8689 Tango | Bee | SOUTH | 2026-09-30 | PV | 533.72 | 2023-07-18 | 2023-09-22 | 2023-06-29 |  | Yes
ERCOT | 26INR0154 | Apis Storage | SS Completed, FIS Started, No IA | S&S Renewables LLC | to the 345kV Goddard (#8606) – Tango (#8689) line; AEP | Bee | SOUTH | 2026-09-30 | BA | 268.43 | 2023-06-13 | 2023-09-22 | 2023-05-25 |  | Yes
ERCOT | 26INR0155 | Ross Solar | SS Completed, FIS Started, IA | S&S Renewables, LLC | tap 345kV 8249 Angstrom – 8676 Static | Refugio | COASTAL | 2027-07-31 | PV | 1025.57 | 2023-07-31 | 2023-10-27 | 2023-07-18 |  | Yes | 2024-06-27
ERCOT | 26INR0156 | Ross Storage | SS Completed, FIS Started, IA | S&S Renewables, LLC | tap the 345 kV Angstrom (#8249) – Static (#8676) line; AEP | Refugio | COASTAL | 2027-07-31 | BA | 510.99 | 2023-08-14 | 2023-11-03 | 2023-07-27 |  | Yes | 2024-06-27
ERCOT | 26INR0159 | Proving Ground BESS | SS Completed, FIS Started, No IA | Lantana Solar LLC | Tap 138kV 6500 Live Oak - 6490 Santiago | Schleicher | WEST | 2026-03-01 | BA | 42.9 | 2023-07-10 | 2023-10-05
ERCOT | 26INR0161 | Timberline Solar | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2026-09-22 | PV | 201 | 2023-08-14 | 2023-11-10 | 2023-08-02
ERCOT | 26INR0162 | Timberline Storage | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2026-09-22 | BA | 100.5 | 2023-08-14 | 2023-11-10 | 2023-08-04
ERCOT | 26INR0168 | Nightfall BESS SLF | SS Completed, FIS Started, No IA | BDPU Solar Nightfall, LLC | Tap 138KV 8707 Dryfrio - 8234 Uvalde | Uvalde | SOUTH | 2026-06-30 | BA | 11 | 2024-05-09 | 2024-08-05 | 2024-05-08
ERCOT | 26INR0169 | AQUAMARINE BESS | SS Completed, FIS Started, No IA | ME USA Project I LLC | tap 138kV 720 Salt Creek Reactor – 6150 Spur | Dickens | PANHANDLE | 2026-05-23 | BA | 213.81 | 2023-06-28 | 2023-09-20
ERCOT | 26INR0171 | Lazy U Solar 1 | SS Completed, FIS Started, No IA | Lazy U Solar 1 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A ckt2 | Hardeman | WEST | 2027-07-01 | PV | 252 | 2023-08-21 | 2023-11-02 | 2023-08-09
ERCOT | 26INR0172 | Lazy U Solar 2 | SS Completed, FIS Started, No IA | Lazy U Solar 2 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A CKT2 | Hardeman | WEST | 2027-07-01 | PV | 252 | 2023-08-21 | 2023-11-02 | 2023-08-15
ERCOT | 26INR0173 | Lazy U ESS 1 | SS Completed, FIS Started, No IA | Lazy U ESS 1 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] 345kV ckt2 | Hardeman | WEST | 2027-07-01 | BA | 251.5 | 2023-09-08 | 2023-12-04 | 2023-08-16
ERCOT | 26INR0174 | Lazy U ESS 2 | SS Completed, FIS Started, No IA | Lazy U ESS 2 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] ckt2 | Hardeman | WEST | 2027-07-01 | BA | 251.5 | 2023-08-21 | 2023-11-02 | 2023-08-16
ERCOT | 26INR0176 | Dionysus Solar | SS Completed, FIS Started, No IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2026-12-31 | PV | 153.26 | 2023-06-28 | 2023-09-22 | 2023-06-05
ERCOT | 26INR0177 | Dionysus Storage | SS Completed, FIS Started, No IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2026-12-31 | BA | 77.28 | 2023-06-28 | 2023-09-22 | 2023-06-05
ERCOT | 26INR0178 | Alliance Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 68091 Navarro - 1907 Venus Switch | Navarro | NORTH | 2028-07-01 | PV | 175 | 2023-07-10 | 2023-10-05 | 2023-06-29
ERCOT | 26INR0179 | SunShiner ESS | SS Completed, FIS Started, No IA | SunShiner ESS LLC | 8672 LaPryor2A 138 kV | Zavala | SOUTH | 2027-07-01 | BA | 200 | 2023-09-25 | 2023-12-21 | 2023-09-20 |  | No
ERCOT | 26INR0180 | Cape Rich BESS | SS Completed, FIS Completed, No IA | Cape Rich BESS | 3387 Revolution Switch 138kV | Navarro | NORTH | 2027-06-01 | BA | 150.52 | 2023-07-10 | 2023-10-06 | 2023-07-03 | 2024-06-26 | No |  |  |  | COD
ERCOT | 26INR0181 | Solar Star Frontier BESS | SS Completed, FIS Started, No IA | Solar Star Frontier BESS, LLC | 8656 Luna 138kV | Cameron | COASTAL | 2025-12-31 | BA | 100.26 | 2023-06-28 | 2023-09-22 |  |  | No
ERCOT | 26INR0183 | TRIFECTA Gas | SS Completed, FIS Started, No IA | NET Power | Tap 345kV 1185 Midland County Northwest – 1022 Midland East CKT 01 | Midland | WEST | 2027-12-31 | GT | 453 | 2023-06-28 | 2023-09-20
ERCOT | 26INR0184 | Arc Energy Storage | SS Completed, FIS Started, No IA | Paris Energy Storage, LLC | Tap 138kV 1693 Paris Switch - 11806 ENLOE T8 | Lamar | NORTH | 2027-04-15 | BA | 204.5 | 2023-07-31 | 2023-10-27 | 2023-07-25
ERCOT | 26INR0185 | Beitel Energy Storage | SS Completed, FIS Started, No IA | Brazos Energy Storage, LLC | 579 Jack County 138kV | Jack | NORTH | 2027-12-31 | BA | 200.6 | 2023-08-14 | 2023-11-10 | 2023-08-02
ERCOT | 26INR0189 | Skipjack Energy Storage | SS Completed, FIS Started, IA | Skipper Energy Storage LLC | Tap 138 42980 Nash - 44010 W A Parish ckt #2 | Brazoria | COASTAL | 2027-04-05 | BA | 150.6 | 2023-07-31 | 2023-10-27 | 2023-07-29 |  |  | 2024-08-13
ERCOT | 26INR0194 | Motif BESS II | SS Started, FIS Started, No IA | Motif Storage, LLC | 7440 Tarpley 69kV | Bandera | SOUTH | 2026-04-21 | BA | 201.13 | 2024-11-19 |  | 2024-10-29
ERCOT | 26INR0195 | Realitos Storage SLF | SS Completed, FIS Started, No IA | Mesquite Creek LLC | Bruni (#8297) – Crestonio (#8695) 138 kV line; AEP | Duval | SOUTH | 2026-12-31 | BA | 0 | 2023-09-07 | 2023-12-05 | 2023-08-02 |  | No
ERCOT | 26INR0196 | Realitos Solar SLF | SS Completed, FIS Started, No IA | Mesquite Creek LLC | Bruni (#8297) – Crestonio (#8695) 138 kV line; AEP | Duval | SOUTH | 2026-12-31 | PV | 150.49 | 2023-09-07 | 2023-12-05 | 2023-07-20 |  | No
ERCOT | 26INR0200 | Vaughn Energy Storage | SS Completed, FIS Started, No IA | Vaughn Battery Storage, LLC | 13 Keith 138kV | Grimes | NORTH | 2027-12-31 | BA | 200.6 | 2023-08-21 | 2023-11-17 | 2023-08-20
ERCOT | 26INR0201 | Rock Rose Energy BESS | SS Completed, FIS Completed, IA | Rock Rose Energy Storage LLC | 44070 Whaley 345 kV | Fort Bend | HOUSTON | 2026-07-02 | BA | 211.5 | 2023-09-22 | 2023-12-14 | 2023-09-08 | 2024-05-07 |  | 2024-06-15
ERCOT | 26INR0211 | Titus Low Carbon Ventures Solar 1 | SS Completed, FIS Started, No IA | Vaquero Solar, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2028-06-01 | PV | 286.84 | 2023-10-13 | 2024-01-10 | 2023-09-21
ERCOT | 26INR0215 | JackGard BESS | SS Completed, FIS Completed, No IA | Jackgard BESS | 1429 Jacksboro 345kV | Jack | NORTH | 2027-09-15 | BA | 200.59 | 2023-08-14 | 2023-11-02 | 2023-07-31 | 2024-11-15 | No |  |  |  | COD
ERCOT | 26INR0218 | Fort Chadbourne Cattle BESS | SS Completed, FIS Started, No IA | Fort Chadbourne BESS | AEP Fort Chadbourne 138 kv substation (#6324) | Coke | WEST | 2026-04-01 | BA | 50.23 | 2023-08-21 | 2023-11-06 | 2023-07-31
ERCOT | 26INR0219 | Mountain Springs BESS | SS Completed, FIS Started, No IA | Mountain Springs BESS | 704 Mountain Springs 138 kV | Cooke | NORTH | 2026-04-01 | BA | 150.52 | 2023-10-04 | 2023-12-30 | 2023-09-21
ERCOT | 26INR0220 | NEZUKO BESS | SS Completed, FIS Started, No IA | AEU BATTERY PROJECT I LLC | Tap 69 kV 6202 ALBNY_FD2A - 60426 HULLTOWN2A | Shackelford | WEST | 2028-01-24 | BA | 63.14 | 2023-07-31 | 2023-10-27
ERCOT | 26INR0222 | GOTHAM BESS | SS Completed, FIS Started, No IA | AEU BATTERY PROJECT IV LLC | 5640 DRISCOLLSUB9 69kV | Nueces | COASTAL | 2026-01-23 | BA | 151.2 | 2023-07-31 | 2023-10-27
ERCOT | 26INR0228 | Santa Monica Solar | SS Completed, FIS Started, No IA | Karol Solar IV | Tap 345 KV 68091 NAVARRO - 3381 BIGBRNW_5 Ckt 2 | Navarro | NORTH | 2028-09-20 | PV | 105.85 | 2023-09-07 | 2023-12-04
ERCOT | 26INR0229 | Pamplona Solar | SS Completed, FIS Started, No IA | Karol Solar III | Tap 138 kV 44740 WALLIS_S65_8 - 44700 GEBHRT_X65B8 Ckt#65 | Austin | SOUTH | 2028-10-17 | PV | 42.38 | 2023-08-14 | 2023-11-03 | [6 empty] | COD
ERCOT | 26INR0230 | Titus Sienta Solar | SS Completed, FIS Started, No IA | Sol Sienta Solar, LLC | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | Pecos | WEST | 2028-06-01 | PV | 501.93 | 2023-10-13 | 2024-01-09 | 2023-10-09
ERCOT | 26INR0231 | Energy City BESS | SS Completed, FIS Started, No IA | Energy City BESS LLC | Tap 138kV 1179 Texaco Mabee Tap - 1200 Mariensfield | Midland | WEST | 2027-03-15 | BA | 204.9 | 2023-10-04 | 2023-12-30 | 2023-09-25
ERCOT | 26INR0235 | Noor Solar | SS Completed, FIS Completed, No IA | Industrial Kilo Project LLC | Tap 138kV 40390 Crosby - 40680 Placid Ckt 86 | Chambers | HOUSTON | 2028-03-01 | PV | 188.2 | 2023-10-13 | 2024-01-09 | 2023-10-04 | 2024-05-20 | Yes
ERCOT | 26INR0238 | Clapton Solar | SS Completed, FIS Started, No IA | Clapton Solar | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | Mills | NORTH | 2028-03-08 | PV | 178.87 | 2024-03-22 | 2024-06-19 | 2024-02-13
ERCOT | 26INR0241 | Sol Marina Energy Center | SS Completed, FIS Started, No IA | Adapture Solar Development, LLC | Tap 345kV 2427 Watermill - 2466 Big Onion | Ellis | NORTH | 2027-04-17 | PV | 175.3 | 2023-10-25 | 2024-01-22 | 2023-09-07
ERCOT | 26INR0242 | Sol Marina Energy Center BESS | SS Completed, FIS Started, No IA | Adapture Solar Development, LLC | Tap 345kV 2427 Watermill - 2466 Big Onion | Ellis | NORTH | 2027-04-17 | BA | 57.15 | 2023-10-25 | 2024-01-22 | 2023-09-07
ERCOT | 26INR0243 | Caladium BESS | SS Started, FIS Started, No IA | Caladium Storage, LLC | 57664 Sunnyside 69kV | Waller | HOUSTON | 2026-05-11 | BA | 201.13 | 2024-11-19 |  | 2024-10-29
ERCOT | 26INR0245 | Cairos Storage | SS Completed, FIS Started, No IA | Cairos Solar, LLC | 7425 ODLAW SWITCH 138kV | Kinney | SOUTH | 2026-12-31 | BA | 77.28 | 2023-10-25 | 2023-12-30 | 2023-10-03
ERCOT | 26INR0246 | Cairos Solar | SS Completed, FIS Started, No IA | Cairos Solar, LLC | ODLAW SWITCH (#7425) | Kinney | SOUTH | 2026-12-31 | PV | 153.26 | 2023-10-04 | 2023-12-30 | 2023-09-22
ERCOT | 26INR0247 | Jane Storage Energy Center | SS Completed, FIS Started, No IA | NMRE Holdings, LLC | 59901 Grelton 345 kV | Martin | WEST | 2026-06-01 | BA | 240.6 | 2023-09-08 | 2023-12-01 | 2023-08-28
ERCOT | 26INR0248 | Sengun BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 12, LLC | WEST_OSO4A (8484) 138 KV | Nueces | COASTAL | 2026-01-06 | BA | 200.89 | 2024-01-03 | 2024-03-29 | 2023-12-18
ERCOT | 26INR0250 | Duffy BESS | SS Completed, FIS Started, No IA | Duffy Energy Storage LLC | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | Matagorda | COASTAL | 2026-09-15 | BA | 235.9 | 2023-08-21 | 2023-11-17 | 2023-08-08
ERCOT | 26INR0252 | Neutron Storage | SS Completed, FIS Started, No IA | Neutron Storage | Tap 345kV 13405 Trading House - 68090 Sam Switch | McLennan | NORTH | 2026-10-07 | BA | 104.36 | 2023-09-08 | 2023-12-01 | 2023-08-21
ERCOT | 26INR0253 | Goldfinch Solar | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap Connection Bus 2485 Poetry Switch – 3223 Shamburger Switch | Van Zandt | NORTH | 2027-09-23 | PV | 150.54 | 2023-09-22 | 2023-12-14 | 2023-09-15 | [5 empty] | Status Change INA-to-PLN
ERCOT | 26INR0254 | Goldfinch Storage | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap Connection Bus 2485 Poetry Switch – 3223 Shamburger Switch | Van Zandt | NORTH | 2027-09-23 | BA | 100.44 | 2023-10-04 | 2023-12-14 | 2023-09-20 | [5 empty] | Status Change INA-to-PLN
ERCOT | 26INR0255 | Operation Sunshine | SS Completed, FIS Started, No IA | Duck Creek Solar, LLC | 7077 Amos Creek 345kV | Concho | WEST | 2026-07-01 | PV | 602.1 | 2023-11-14 | 2024-02-09 | 2023-09-27
ERCOT | 26INR0256 | Camino Ranch Solar 2 SLF | SS Completed, FIS Started, No IA | Camino Ranch Solar Project LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | PV | 237.21 | 2024-02-27 | 2024-05-24 | 2024-01-10
ERCOT | 26INR0257 | Camino Ranch Storage 2 SLF | SS Completed, FIS Started, No IA | Camino Ranch Solar LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2027-10-30 | BA | 238.45 | 2024-02-02 | 2024-04-29 | 2023-10-12
ERCOT | 26INR0258 | Running Iron Solar | SS Completed, FIS Started, No IA | Running Iron Solar, LLC | Tap 138kV Conoco 8138 - Black Cat 80124 | Matagorda | COASTAL | 2028-06-01 | PV | 204.74 | 2023-10-25 | 2024-01-22 | 2023-10-19
ERCOT | 26INR0259 | Cottontail Energy Center | SS Completed, FIS Started, No IA | Mission Clean Energy LLC | 7258 Glidden Substation 138kV | Colorado | SOUTH | 2027-10-19 | BA | 200.85 | 2023-10-25 | 2024-01-22 | 2023-10-17
ERCOT | 26INR0260 | Evans Creek Energy Storage | SS Completed, FIS Started, No IA | Evans Creek Energy Storage LLC | Comstock 138kV Substation (PSSE Bus #8683) | Val Verde | WEST | 2028-04-01 | BA | 102.96 | 2023-10-25 | 2024-01-22 | 2023-10-19
ERCOT | 26INR0261 | Bastrop Peaking Generators | SS Completed, FIS Started, No IA | MPH Bastrop Peakers, LLC | 7048 L_GARFIE5_1Y 345kV | Bastrop | SOUTH | 2026-05-31 | GT | 1104 | 2024-02-02 | 2024-05-01
ERCOT | 26INR0269 | Moccasin Solar | SS Completed, FIS Started, IA | Swenson Solar LLC | Tapping the 345 kV Line from Kirchhoff (Bus# 60707) to Clear Crossing (Bus# 60515) | Stonewall | WEST | 2027-07-06 | PV | 806.8 | 2023-09-07 | 2023-12-06 | 2023-09-01 |  | Yes | 2024-09-04
ERCOT | 26INR0272 | Momentum Stout BESS | SS Completed, FIS Started, No IA | Momentum STOUT, LLC | 70111 Flat Rock 138kV | Burnet | SOUTH | 2026-04-04 | BA | 125.5 | 2023-11-14 | 2024-02-09
ERCOT | 26INR0274 | Malala Storage | SS Completed, FIS Started, No IA | Malala Storage, LLC | 2434 Seagoville SW 138kV | Dallas | NORTH | 2027-04-03 | BA | 205.5 | 2023-10-25 | 2024-01-22 | 2023-10-09
ERCOT | 26INR0277 | Salt-Lick Solar | SS Completed, FIS Started, No IA | Salt-Lick Solar, LLC | Elcor_8 bus # 11198 | Culberson | WEST | 2028-06-01 | PV | 510 | 2023-10-13 | 2024-01-10 | 2023-10-02
ERCOT | 26INR0279 | Firebird Solar | SS Completed, FIS Started, No IA | TX Firebird SB 6, LLC | 138 kV 1099 SOUTHWESTERN PORTLAND TAP - 11281 OLSIN SWITCH | Ector | WEST | 2026-12-31 | PV | 100.42 | 2023-11-14 | 2024-02-09 | 2023-10-31
ERCOT | 26INR0280 | Pethrus BESS | SS Completed, FIS Started, No IA | Pethrus BESS, LLC | Tap Wichita Falls Switch (#1464) – North Star (#1467) 138 kV Line | Wichita | WEST | 2027-04-03 | BA | 174.08 | 2023-09-23 | 2023-12-20 | 2023-08-30
ERCOT | 26INR0281 | SHAWNEE BOTTOM SOLAR | SS Completed, FIS Started, No IA | Shawnee Bottom Solar, LLC | tap 138kV 3319 REDLAND_8 - 3120 NACOGDSE_8 | Nacogdoches | NORTH | 2026-06-01 | PV | 153 | 2023-09-22 | 2023-12-19
ERCOT | 26INR0283 | Bonaparte BESS | SS Completed, FIS Started, No IA | Bonaparte BESS, LLC | 7568 Lincoln 138 kV | Lee | SOUTH | 2026-08-01 | BA | 153.67 | 2023-11-14 | 2024-02-09 | 2023-09-06
ERCOT | 26INR0285 | Hill Valley BESS | SS Completed, FIS Completed, No IA | Hill Valley BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2026-12-01 | BA | 245.8 | 2023-12-04 | 2024-03-01 | 2023-11-10 | 2024-12-03
ERCOT | 26INR0287 | Firebird BESS | SS Completed, FIS Started, No IA | TX BESS 6, LLC | 138 kV 1099 SOUTHWESTERN PORTLAND TAP - 11281 OLSIN SWITCH | Ector | WEST | 2026-12-31 | BA | 100.42 | 2023-11-14 | 2024-02-09 | 2023-10-31
ERCOT | 26INR0289 | Wadsworth Storage Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy Real Estate, LLC | 8115 Wadsworth Substation 138 kV | Matagorda | COASTAL | 2026-06-01 | BA | 200.8 | 2023-10-25 | 2024-01-22 | 2023-10-10
ERCOT | 26INR0290 | Cold Creek Solar 2 | SS Completed, FIS Started, No IA | Cold Creek Solar LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2026-12-31 | PV | 445.41 | 2023-12-18 | 2024-03-01 | 2023-11-07
ERCOT | 26INR0291 | Cold Creek Storage 2 | SS Completed, FIS Started, No IA | Cold Creek Solar LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2026-12-31 | BA | 174.24 | 2023-12-04 | 2024-03-01 | 2023-11-02
ERCOT | 26INR0293 | Firefly Power | SS Completed, FIS Started, No IA | Firefly Power LLC | 1880 Rocky Creek 345kV | Tarrant | NORTH | 2027-04-15 | BA | 401.18 | 2024-02-27 | 2024-05-24 | 2024-01-23
ERCOT | 26INR0294 | Longleaf Power Station | SS Completed, FIS Completed, No IA | WattBridge Texas Holding, LLC | Redland Substation (# 3321) | Angelina | NORTH | 2026-06-01 | GT | 612 | 2023-10-13 | 2024-01-09 | 2023-10-04 | 2024-10-22 | No
ERCOT | 26INR0295 | Trinity Hills BESS SLF | SS Completed, FIS Started, No IA | Phoenix Battery Storage, LLC | To the 345 kV Garvey Road Switch (#17002) | Archer | WEST | 2026-04-14 | BA | 27 | 2023-11-30 | 2024-02-26 | 2023-11-03
ERCOT | 26INR0296 | Sherbino II BESS SLF | SS Completed, FIS Started, IA | Phoenix Battery Storage, LLC | 38430 TNMP White baker Switching Station 138kV | Pecos | WEST | 2025-11-08 | BA | 77.37 | 2023-11-30 | 2024-02-27 | 2023-11-16 |  |  | 2024-08-01
ERCOT | 26INR0297 | Buzzi Maryneal Wind Project | SS Completed, FIS Started, No IA | Buzzi Unicem USA | 1413 SWEETCRK-9 | Nolan | WEST | 2026-01-02 | WT | 18 | 2023-10-25 | 2024-01-22 | 2023-10-16
ERCOT | 26INR0300 | Whitewright Solar 2 | SS Completed, FIS Started, No IA | SunWR, LLC | Tap 345kV 1729 Valley South – Anna Switch 2373 | Grayson | NORTH | 2028-05-02 | PV | 301.69 | 2023-12-18 | 2024-03-15 | 2023-11-07
ERCOT | 26INR0301 | Bhalu Storage | SS Completed, FIS Started, No IA | Bhalu Storage, LLC | Tap 138kV Bulldog (#23833) – Elbow (#23834) | Howard | WEST | 2027-03-03 | BA | 205.5 | 2023-10-30 | 2024-01-26 | 2023-10-23
ERCOT | 26INR0302 | Carolina Storage Young County | SS Completed, FIS Started, No IA | CSE STORAGE, LLC | TAP 138 KV BUS AND CREAT NEW BUS BETWEEN MURRAY (792) AND GRAHAM SES (1431) COUNTY : YOUNG | Young | WEST | 2027-09-22 | BA | 104.4 | 2024-02-27 | 2024-05-20 | 2024-02-12
ERCOT | 26INR0304 | JUNIPERUSSS | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE XXI LLC | TAP CASHSW_T5 (2464) -SULSP_SS1_5 (1697) | Hopkins | NORTH | 2027-04-23 | PV | 80.33 | 2024-01-11 | 2024-04-08 | 2024-01-04
ERCOT | 26INR0306 | Nautilus Heavy Storage | SS Completed, FIS Started, No IA | Nautilus Heavy Storage, LLC | 8422 Dupont 138kV | San Patricio | COASTAL | 2027-12-31 | BA | 256.24 | 2023-12-20 | 2024-03-15 | 2023-12-01 | [5 empty] | COD
ERCOT | 26INR0309 | Solace Storage | SS Completed, FIS Started, No IA | IP Quantum BESS, LLC | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2026-07-23 | BA | 321.02 | 2024-03-22 | 2024-06-19 | 2024-02-22
ERCOT | 26INR0310 | Quantum Storage | SS Completed, FIS Started, IA | IP Quantum II BESS, LLC | 60089 Kilby Switching Station 345kV | Haskell | WEST | 2026-06-30 | BA | 321.06 | 2024-03-22 | 2024-06-19 | 2024-02-22 |  |  | 2023-10-26 |  |  | COD
ERCOT | 26INR0311 | Senator Aggreko Solar | SS Completed, FIS Started, No IA | Senator Aggreko Solar LLC | 138 kV Rosita Creek Substation (#78015) | Maverick | SOUTH | 2026-10-31 | PV | 251 | 2024-02-02 | 2024-01-08 | 2023-10-18
ERCOT | 26INR0312 | Senator Aggreko Storage | SS Completed, FIS Started, No IA | Senator Aggreko Storage LLC | 138 kV Rosita Creek Substation (#78015) | Maverick | SOUTH | 2026-10-31 | BA | 153.1 | 2023-11-14 | 2024-01-08 | 2023-10-25
ERCOT | 26INR0313 | Edens Solar | SS Completed, FIS Started, No IA | Hill PV, LLC | Tap 69kV 3532 Itasca - 3523 Hillsboro | Hill | NORTH | 2027-04-12 | PV | 70.37 | 2023-10-25 | 2024-01-22 | 2023-10-20
ERCOT | 26INR0314 | Brazos River BESS | SS Completed, FIS Completed, No IA | Brazos River BESS LLC | Tap 138kV 39530 West Colombia LOCAL TNP - 39560 ANGLETON TNP | Brazoria | COASTAL | 2026-12-31 | BA | 180.36 | 2023-10-04 | 2024-01-01 |  | 2024-11-04
ERCOT | 26INR0317 | Pinnacle Point Energy Storage | SS Completed, FIS Started, No IA | GCI Pinnacle Point, LLC | Tap Highlands (Bus # 40812) - HANEY ( BUS # 40790) 138 kV | Harris | HOUSTON | 2027-06-01 | BA | 101.3 | 2023-11-14 | 2024-01-08 | 2023-11-08
ERCOT | 26INR0318 | Sandford Solar | SS Completed, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | Wise | NORTH | 2028-08-15 | PV | 126.18 | 2024-01-03 | 2024-03-29 | 2023-12-12
ERCOT | 26INR0319 | Sandford Storage | SS Completed, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | Wise | NORTH | 2028-08-15 | BA | 100.93 | 2024-01-03 | 2024-03-29 | 2023-12-12
ERCOT | 26INR0320 | Augite Storage | SS Completed, FIS Started, No IA | BT Augite Storage, LLC | tap 138kV 8798 La Grulla - 8355 Goodwin | Starr | SOUTH | 2027-12-30 | BA | 151.41 | 2024-02-02 | 2024-05-01 | 2024-01-15
ERCOT | 26INR0321 | Windmill Ridge Storage | SS Completed, FIS Completed, No IA | BT WMR Storage, LLC | Angleton (Bus #42110) - West Columbia Local (Bus #43381) 138 kV Substation | Brazoria | COASTAL | 2026-12-31 | BA | 151.4 | 2023-11-14 | 2024-01-08 | 2023-11-03 | 2024-07-29
ERCOT | 26INR0322 | Kobernat Solar | SS Completed, FIS Started, No IA | BT Kobernat Solar, LLC | A DIRECT CONNECTION TO A NEW SWITCHING STATION ON THE AEP TEXAS CENTRAL OWNED GARZA (BUS #8399) - LISTON (BUS #8394) 138 KV LINE | Starr | SOUTH | 2026-12-30 | PV | 100.54 | 2024-02-02 | 2024-04-29 | 2024-01-11
ERCOT | 26INR0323 | Kobernat Storage | SS Completed, FIS Started, No IA | BT Kobernat Solar, LLC | A DIRECT CONNECTION TO A NEW SWITCHING STATION ON THE AEP TEXAS CENTRAL OWNED GARZA (BUS #8399) - LISTON - (BUS #8394) 138 KV LINE | Starr | SOUTH | 2026-12-30 | BA | 51.46 | 2024-02-02 | 2024-04-29 | 2024-01-16
ERCOT | 26INR0324 | Misty Hollow BESS | SS Completed, FIS Started, No IA | Clear Fork BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2026-12-01 | BA | 245.8 | 2023-12-20 | 2024-03-15 | 2023-12-06
ERCOT | 26INR0326 | Leaning Tree BESS | SS Completed, FIS Started, No IA | RamZ BESS, LLC | To Tap 345 kV Thomas Price Switch (Bus# 11523) to Clear Crossing (Bus# 60515) Line | Throckmorton | WEST | 2027-02-13 | BA | 256.1 | 2023-11-30 | 2024-02-27 | 2023-11-15
ERCOT | 26INR0327 | Sleepy Hollow BESS | SS Completed, FIS Started, No IA | Sleepy Hollow BESS, LLC | Tap 138 kV 792 Murray - 6169 Paint Creek | Throckmorton | WEST | 2027-02-13 | BA | 123.1 | 2023-11-30 | 2024-02-27 | 2023-11-15
ERCOT | 26INR0328 | Yorktown BESS | SS Completed, FIS Started, No IA | Navitas Energy LLC | (#78575) LCRA Yorktown 138 kV | DeWitt | SOUTH | 2026-12-16 | BA | 150.49 | 2023-10-25 | 2024-01-22 | 2023-10-10
ERCOT | 26INR0329 | Pianissimo BESS II | SS Started, FIS Started, No IA | Pianissimo Storage, LLC | LEO Substation (#685) | Wise | NORTH | 2026-09-14 | BA | 201.08 | 2024-11-19 |  | 2024-10-29
ERCOT | 26INR0330 | Alamo City BESS | SS Completed, FIS Started, No IA | ALAMO CITY ESS LLC | Tap 138kV 5294 Martinez - 5110 JT Deely | Bexar | SOUTH | 2027-07-01 | BA | 128.12 | 2024-02-27 | 2024-05-24
ERCOT | 26INR0331 | RUSH ESS | SS Completed, FIS Started, No IA | OCI Solar Power LLC | Tap 345 kV 5231 HOWARD_5 – 5400 SPRUCE | Bexar | SOUTH | 2027-07-01 | BA | 202.7 | 2023-11-30 | 2024-01-16
ERCOT | 26INR0333 | VERTUS ENERGY STORAGE | SS Completed, FIS Completed, IA | VERTUS ENERGY STORAGE LLC | Bus Name: TnMainland1, Bus Number: 38830, | Galveston | HOUSTON | 2026-02-01 | BA | 401.4 | 2023-10-13 | 2024-01-10 | 2023-10-10 | 2024-09-09 |  | 2024-03-27
ERCOT | 26INR0334 | TOCE TX BESS 2 | SS Completed, FIS Started, No IA | TOCE TX BESS 2, LLC | Tap 44200 Hillje - 44000 WA Parrish 345 kV | Wharton | SOUTH | 2027-08-01 | BA | 523.38 | 2024-02-02 | 2024-04-29 | 2024-01-23
ERCOT | 26INR0340 | SOUTHERN SELECT ENERGY STORAGE | SS Completed, FIS Completed, No IA | SOUTHERN SELECT ENERGY STORAGE LLC | Bus Name: TNHEIGHTS_1 Bus Number: 38740 | Galveston | HOUSTON | 2026-02-01 | BA | 404.3 | 2023-10-25 | 2024-01-22 | 2023-10-12 | 2024-10-22
ERCOT | 26INR0341 | Megamouth Energy Storage | SS Completed, FIS Started, No IA | GCI Megamouth, LLC | 42750 Mykawa 138 kV | Harris | HOUSTON | 2026-09-01 | BA | 101.3 | 2024-03-22 | 2024-06-19 | 2024-03-11
ERCOT | 26INR0343 | Stinger Energy Storage | SS Completed, FIS Started, No IA | Stinger Energy Storage LLC | Tap Atascocita 138kV Substation (Bus # 40130) - Lake Houston (Bus #40820) | Harris | HOUSTON | 2028-03-01 | BA | 200.8 | 2023-11-14 | 2024-01-08 | 2023-11-02
ERCOT | 26INR0344 | Kendall BESS | SS Completed, FIS Started, No IA | Kendall Energy Storage LLC | #7046 Kendall 345kV | Kendall | SOUTH | 2027-07-01 | BA | 0 | 2023-11-14 | 2024-01-16
ERCOT | 26INR0345 | NET Power Demonstration plant | SS Completed, FIS Started, No IA | NET Power LLC | 42360 Mirage POI 8 138kV | Harris | HOUSTON | 2027-03-15 | GT | 25.5 | 2023-12-20 | 2024-03-08 | 2024-09-03
ERCOT | 26INR0347 | Midfield PV Project SLF | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 138kV 8121 Blessing - 8125 Lolita | Matagorda | COASTAL | 2027-12-01 | PV | 150 | 2023-12-04 | 2024-02-27 | 2023-11-28
ERCOT | 26INR0349 | ARTIO ENERGY STORAGE | SS Completed, FIS Started, No IA | Artio Energy Storage LLC | Farmersville 345kV Substation (PSSE BUS # 1685) | Collin | NORTH | 2028-10-01 | BA | 205.94 | 2023-11-14 | 2024-02-08 | 2023-10-30
ERCOT | 26INR0350 | Jack County III – 138 kV | SS Completed, FIS Started, No IA | Jack County Power Development, LLC | 579 JACK COUNTY 138kV | Jack | NORTH | 2026-05-01 | GT | 660 | 2023-11-14 | 2024-02-08
ERCOT | 26INR0351 | Jack County III – 345 kV | SS Completed, FIS Started, No IA | Jack County Power Development, LLC | Substation Name: JACK COUNTY 2 PLANT STATION CODE: JCKCNTY2 BUS NUMBER: 575 | Jack | NORTH | 2027-07-01 | GT | 660 | 2023-11-14 | 2024-02-08
ERCOT | 26INR0355 | Pleiades Storage | SS Completed, FIS Started, No IA | Pleiades Storage, LLC | Tap 138kV Einstein 23852 - 10043 St. Lawrence | Glasscock | WEST | 2027-09-29 | BA | 205.5 | 2024-03-22 | 2024-06-19 | 2024-02-23
ERCOT | 26INR0356 | Saluga Ranch Storage | SS Completed, FIS Started, No IA | Saluga Ranch Energy, LLC | Asherton 8283 - Big wells 8613 -138 kV | Dimmit | SOUTH | 2026-07-31 | BA | 105.98 | 2024-02-02 | 2024-04-29 | 2024-01-08
ERCOT | 26INR0357 | Operation Sunshine Storage | SS Completed, FIS Started, No IA | Duck Creek Storage, LLC | 7077 Amos Creek 345kV | Concho | WEST | 2026-07-01 | BA | 409.5 | 2024-02-02 | 2024-02-09 | 2024-01-18
ERCOT | 26INR0359 | Uva Creek Solar | SS Completed, FIS Started, IA | Grape Creek Solar, LLC | Tap 345 kV 59905 Faraday - 59900 Long Draw | Borden | WEST | 2028-08-25 | PV | 302.16 | 2024-02-27 | 2024-05-20 | 2024-02-06 |  |  | 2024-10-30
ERCOT | 26INR0362 | Midfield BESS Project SLF | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 138kV 8121 Blessing - 8125 Lolita | Matagorda | COASTAL | 2027-12-01 | BA | 0 | 2024-05-20 | 2024-07-22 | 2024-05-07
ERCOT | 26INR0364 | Pollo Pinto Solar | SS Completed, FIS Started, No IA | TX Palo Pinto SB 6, LLC | Tap 138kV 331 RWMILLER - 320 JAYBIRD | Palo Pinto | NORTH | 2027-08-15 | PV | 150.8 | 2024-02-27 | 2024-05-20 | 2024-02-26
ERCOT | 26INR0365 | BLACK BEAR SOLAR | SS Completed, FIS Started, No IA | ESCONDIDO DRAW RESOURCES, LLC | #6564 ILLN4A 138 KV | Crockett | WEST | 2028-06-01 | PV | 102.9 | 2023-12-04 | 2024-03-04
ERCOT | 26INR0366 | BLACK BEAR BESS | SS Completed, FIS Started, No IA | ESCONDIDO DRAW RESOURCES, LLC | #6564 ILLN4A 138kV | Crockett | WEST | 2028-06-01 | BA | 51.2 | 2023-12-04 | 2024-03-04
ERCOT | 26INR0367 | Austin Bayou Solar II | SS Completed, FIS Started, No IA | Austin Bayou Solar, LLC | Tap 345 kV Savannah 43180 - Seabreeze 43020 ckt #27 | Brazoria | COASTAL | 2027-06-01 | PV | 401.8 | 2024-03-29 | 2024-06-25 | 2024-03-15
ERCOT | 26INR0372 | Centennial Solar | SS Completed, FIS Started, No IA | Centennial AD 8 LLC | Tap 138kV 6364 YELLOW JACKET - 76390 FORT MASON | Menard | WEST | 2027-11-30 | PV | 61.36 | 2024-01-03 | 2024-03-22 | 2023-12-22
ERCOT | 26INR0374 | Cobra Clean Energy Center | SS Completed, FIS Started, No IA | Cobra Clean Energy Center LLC | looped on circuit 04 between Mustang Bayou (#42960) and Hudson (#42100) | Brazoria | COASTAL | 2027-10-08 | BA | 100.4 | 2024-02-02 | 2024-05-01
ERCOT | 26INR0375 | Avalon BESS | SS Completed, FIS Completed, No IA | Avalon BESS, LLC | Tapping the 345 kV Line from Smithers (Bus# 44650) to Bellaire (Bus# 47000). | Fort Bend | HOUSTON | 2026-12-01 | BA | 522.12 | 2023-12-20 | 2024-03-08 | 2023-11-30 | 2024-05-20 | Yes
ERCOT | 26INR0376 | Blackcat Storage | SS Completed, FIS Started, No IA | Matagorda ESS, LLC | 138kV Blackcat Substation (#80124) | Matagorda | COASTAL | 2026-04-06 | BA | 200.59 | 2024-01-11 | 2024-04-08 | 2023-11-30
ERCOT | 26INR0377 | Ridley Solar SLF | SS Completed, FIS Started, No IA | Ridley Solar Project, LLC | Tap 138kV 8912 Medio Creek - 8920 HAISLEY | Refugio | COASTAL | 2029-03-23 | PV | 200.81 | 2024-07-01 | 2024-09-27 | 2024-06-12
ERCOT | 26INR0378 | Larimar Solar | SS Completed, FIS Started, No IA | BT S7 Solar, LLC | Tap 138 kV 8186 KENEDYSW4A ‐ 8590 TULETA4A | Bee | SOUTH | 2026-12-18 | PV | 150.91 | 2024-01-11 | 2024-04-05 | 2024-01-05
ERCOT | 26INR0380 | Pepper Solar Farm | SS Completed, FIS Started, No IA | Pepper Solar Farm LLC | Tap 345kV 3405 THOUSE__5 - 3406 ELM_MOTT_5 | McLennan | NORTH | 2027-07-01 | PV | 120.69 | 2024-02-27 | 2024-05-20 | 2024-02-22
ERCOT | 26INR0383 | Larimar Storage | SS Completed, FIS Started, No IA | BT S7 Solar, LLC | A DIRECT CONNECTION TO A NEW SWITCHING STATION ON THE KENEDYSW4A (BUS #8186) ‐ TULETA4A (BUS #8590) 138 KV LINE | Bee | SOUTH | 2026-12-18 | BA | 100.91 | 2024-01-11 | 2024-03-19 | 2024-01-05
ERCOT | 26INR0384 | Olsovksy Storage | SS Completed, FIS Started, No IA | BT Sky Storage, LLC | Tap 345kV 68035 Helix - 68091 Navarro | Hill | NORTH | 2026-12-18 | BA | 151.42 | 2024-01-11 | 2024-04-08 | 2024-01-09
ERCOT | 26INR0388 | Aggie Solar Project SLF | SS Completed, FIS Started, No IA | reNRG TX 8 LLC | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER : 38113 COUNTY : REEVES POI LOCATION: 31.396675, -103.6252777 | Reeves | WEST | 2026-12-31 | PV | 103.7 | 2024-02-02 | 2024-04-29 | 2023-12-08
ERCOT | 26INR0389 | AGGIE STORAGE PROJECT SLF | SS Completed, FIS Started, No IA | reNRG TX 8 LLC | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER: 38113 POI LOCATION: 31.396675, -103.6252777 COUNTY: REEVES | Reeves | WEST | 2026-12-31 | BA | 0 | 2024-02-02 | 2024-04-29 | 2023-12-08
ERCOT | 26INR0391 | Jumping Cactus Storage | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | 138 kV Zenaida Bus# 80043 | Duval | SOUTH | 2027-09-30 | BA | 125.37 | 2024-01-11 | 2024-03-19 | 2023-12-19
ERCOT | 26INR0393 | Dove Wing Storage | SS Completed, FIS Started, No IA | Dove Run Solar Project, LLC | Tap 138kV 8510 Falfurriass - 8695 Crestonio | Duval | SOUTH | 2028-07-31 | BA | 122.41 | 2024-02-07 | 2024-04-29 | 2024-01-05
ERCOT | 26INR0394 | Timber Cove Storage SLF | SS Completed, FIS Started, No IA | Freestone Solar, LLC | Tap 138 kV 212 Winkler - 3510 Pin Oak | Freestone | NORTH | 2027-04-01 | BA | 0 | 2024-01-11 | 2024-04-08 | 2023-12-18
ERCOT | 26INR0396 | Kodiak AGR1 | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | 38113 TNCOYOTSPG1 | Reeves | WEST | 2027-06-15 | OT | 132 | 2024-02-27 | 2024-05-28
ERCOT | 26INR0405 | Buffalo Creek BESS | SS Completed, FIS Started, IA | Old 300 Storage Center, LLC | 44090 Cedar Creek 345kV | Fort Bend | HOUSTON | 2026-06-01 | BA | 251.4 | 2024-03-22 | 2024-06-19 | 2024-03-07 |  |  | 2024-10-02
ERCOT | 26INR0407 | Rock Creek BESS | SS Completed, FIS Started, No IA | Flat Rock Energy Center, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2026-12-01 | BA | 251.05 | 2024-02-27 | 2024-05-24 | 2024-02-27
ERCOT | 26INR0408 | Liatris Flexible Gas | SS Completed, FIS Started, No IA | Stone Creek Peaker LLC | Tap 138 kV (42980) Nash - (44010) WA Parish CKT02 | Brazoria | COASTAL | 2026-12-31 | GT | 204.71 | 2024-03-22 | 2024-06-19 | 2024-03-06
ERCOT | 26INR0409 | Lucky 7 Solar | SS Completed, FIS Started, No IA | OCI SOLAR POWER LLC | Tap 345kV 1697 SULPHUR SPRINGS SWITCH - 2464 CASH SWITCH | Hopkins | NORTH | 2027-09-04 | PV | 100.8 | 2024-03-22 | 2024-06-19 | 2024-02-29
ERCOT | 26INR0410 | Prost ESS | SS Completed, FIS Started, No IA | Prost ESS LLC | Tap 138kV L_PISEK_8_1Y (#7296) - L_WELCOM8_1Y(#7577) | Austin | SOUTH | 2027-07-01 | BA | 202.7 | 2024-02-27 | 2024-05-20 | 2024-02-12
ERCOT | 26INR0411 | Tex-Bar ESS | SS Completed, FIS Completed, No IA | Tex-Bar ESS LLC | Tap 345kV JEWETT_S5 (#3390) -- SINGLETON (#44645) | Madison | NORTH | 2027-07-01 | BA | 201.5 | 2024-03-22 | 2024-06-19 | 2024-02-26 | 2024-09-26 | Yes
ERCOT | 26INR0412 | BumbleBee Solar | SS Completed, FIS Started, No IA | BumbleBee Solar Farm LLC | Tap 345kV 5725 PawneeSW5 - 8689 Tango | Bee | SOUTH | 2027-07-01 | PV | 211.6 | 2024-02-27 | 2024-05-24 | 2024-02-26
ERCOT | 26INR0417 | GAMAY ENERGY STORAGE | SS Completed, FIS Completed, No IA | GAMAY ENERGY STORAGE LLC | Tap 138 kV Line from TNFM524 (39703) to West Columbia Main (39500), in Brazoria County. | Brazoria | COASTAL | 2026-05-15 | BA | 418.6 | 2024-02-07 | 2024-04-30 | 2024-01-26 | 2024-10-17
ERCOT | 26INR0418 | TE Smith Storage 2 | SS Completed, FIS Started, No IA | Smith II Battery Storage, LLC | 2483 Royse 345kV | Rockwall | NORTH | 2026-07-15 | BA | 125.36 | 2024-04-15 | 2024-07-12 | [6 empty] | FIS Request
ERCOT | 26INR0422 | PowerVault BESS | SS Completed, FIS Started, No IA | SMT Elm Mott BESS | Tap 345kV 3406 Elm Mott - 3405 Tradinghouse Ses | McLennan | NORTH | 2027-07-01 | BA | 254.8 | 2024-03-22 | 2024-06-19
ERCOT | 26INR0425 | Twinwood Solar 1 | SS Completed, FIS Started, No IA | Twinwood PV1, LLC | Tap 138kV 44750 FULSHR_S25_8 - 44860 TWINWD_S25_8 | Waller | HOUSTON | 2027-10-27 | PV | 358.06 | 2024-03-22 | 2024-06-19
ERCOT | 26INR0426 | Maderagemela BESS1 | SS Completed, FIS Started, No IA | Twinwood ES1, LLC | Tap 138kV 44750 FULSHR_S25_8 to 44860 TWINWD_S25_8 | Waller | HOUSTON | 2027-10-27 | BA | 153.96 | 2024-02-27 | 2024-05-24
ERCOT | 26INR0427 | BremRaek BESS | SS Completed, FIS Started, No IA | BremRaek BESS | 7271 LCRA New Bremen 138 kV | Austin | SOUTH | 2026-07-01 | BA | 200.6 | 2024-03-22 | 2024-06-19 | 2024-02-28
ERCOT | 26INR0428 | Diamond Cowboy Storage | SS Completed, FIS Started, No IA | Diamond B Storage, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2028-06-01 | BA | 103.5 | 2024-04-15 | 2024-07-12 | 2024-04-16
ERCOT | 26INR0429 | Post Trail Energy | SS Completed, FIS Started, No IA | Post Trail Energy, LLC | Tap 138kV Conoco 8138 - Black Cat 80124 | Matagorda | COASTAL | 2028-06-01 | BA | 103.5 | 2024-09-10 | 2024-12-08 | 2024-08-26
ERCOT | 26INR0430 | Clapton Storage | SS Completed, FIS Started, No IA | Clapton BESS | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | Mills | NORTH | 2027-08-04 | BA | 208.91 | 2024-03-22 | 2024-06-19 | 2024-02-13
ERCOT | 26INR0431 | Big Rooter West Solar SLF | SS Completed, FIS Completed, No IA | Big Rooter West, LLC | 39950# TNTNP_ONE_3 345 KV | Robertson | NORTH | 2026-12-31 | PV | 403.42 | 2024-03-22 | 2024-06-19 | 2024-03-22 | 2024-12-05
ERCOT | 26INR0432 | Big Rooter West Storage SLF | SS Completed, FIS Completed, No IA | Big Rooter West, LLC | 39950# TNTNP_ONE_3 345 KV | Robertson | NORTH | 2026-12-31 | BA | 0 | 2024-03-22 | 2024-06-19 | 2024-03-22 | 2024-12-05
ERCOT | 26INR0440 | Hamby Solar | SS Completed, FIS Started, No IA | Abilene GCE LLC | 6245 ABILENE ROBERTSON PRISON 69 KV | Jones | WEST | 2028-06-27 | PV | 71.4 | 2024-03-22 | 2024-06-19 | [6 empty] | COD
ERCOT | 26INR0442 | Donna BESS | SS Completed, FIS Started, No IA | Donna Solar LLC | Tap 345 kV 80137 Stewart Road - 8383 North Edinburg | Hidalgo | SOUTH | 2027-12-31 | BA | 54.08 | 2024-03-22 | 2024-06-19
ERCOT | 26INR0443 | Sullivan Solar | SS Completed, FIS Started, No IA | Sullivan Solar LLC | Tap La Grulla (Bus# 8798) to Goodwin (Bus# 8355) 138 kV L | Hidalgo | SOUTH | 2029-02-25 | PV | 171.4 | 2024-03-22 | 2024-06-19 | [6 empty] | COD
ERCOT | 26INR0444 | Sullivan BESS | SS Completed, FIS Started, No IA | Sullivan Solar LLC | Tap 138 kV La Grulla (Bus# 8798) - Goodwin (Bus# 8355) | Hidalgo | SOUTH | 2029-02-25 | BA | 72.51 | 2024-03-22 | 2024-06-19 | [6 empty] | COD
ERCOT | 26INR0445 | Sword Solar | SS Completed, FIS Started, No IA | Hidalgo Solar LLC | Tap 138 kV 8394 Liston - 8392 Bates | Starr | SOUTH | 2027-12-31 | PV | 137.56 | 2024-03-22 | 2024-06-19
ERCOT | 26INR0446 | Sword BESS | SS Completed, FIS Started, No IA | Hidalgo Solar LLC | Tap 138 kV 8394 Liston - 8392 Bates | Starr | SOUTH | 2027-12-31 | BA | 44.39 | 2024-03-22 | 2024-06-19
ERCOT | 26INR0447 | Honey Mesquite Wind Farm | SS Completed, FIS Started, IA | Honey Mesquite Wind Farm , LLC | 59902 Sand Bluff 345kV | Glasscock | WEST | 2026-12-31 | WT | 155.1 | 2024-03-22 | 2024-06-19 | 2024-03-11 |  |  | 2024-09-16
ERCOT | 26INR0448 | Cairos Storage 2 | SS Completed, FIS Started, No IA | Cairos Solar, LLC | 7425 ODLAW SWITCH 138kV | Kinney | SOUTH | 2026-12-31 | BA | 184 | 2024-07-01 | 2024-09-27 | 2024-06-20
ERCOT | 26INR0452 | Cannibal Draw Solar | SS Completed, FIS Started, No IA | Cannibal Draw Solar, LLC | Sand_Bluff 345 kV (59902) | Glasscock | WEST | 2028-04-10 | PV | 149.5 | 2024-07-01 | 2024-09-27 | 2024-06-10
ERCOT | 26INR0453 | Cannibal Draw Storage | SS Completed, FIS Started, No IA | Cannibal Draw Solar, LLC | Sand_Bluff 345 kV (59902) | Glasscock | WEST | 2028-04-10 | BA | 98.6 | 2024-07-01 | 2024-09-27 | 2024-06-10
ERCOT | 26INR0454 | Dove Creek Solar | SS Completed, FIS Started, No IA | Dove Creek Solar, LLC | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | Tom Green | WEST | 2028-07-01 | PV | 163.6 | 2024-07-22 | 2024-10-08 | 2024-06-25
ERCOT | 26INR0455 | Dove Creek Storage | SS Completed, FIS Started, No IA | Dove Creek Solar, LLC | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | Tom Green | WEST | 2028-07-01 | BA | 162.5 | 2024-07-22 | 2024-10-08 | 2024-06-25
ERCOT | 26INR0456 | Ridley Storage SLF | SS Completed, FIS Started, No IA | Ridley Solar Project, LLC | Medio Creek (Bus# 8912) to HAISLEY (Bus# 8920) | Refugio | COASTAL | 2029-03-23 | BA | 0 | 2024-07-01 | 2024-09-27 | 2024-06-12
ERCOT | 26INR0460 | Lightning Ridge Energy Storage | SS Completed, FIS Started, No IA | Lightning Ridge Storage LLC | Tap #1429 Jacksboro Substation 345kV | Jack | NORTH | 2027-09-15 | BA | 204.7 | 2024-03-29 | 2024-06-25 | 2024-03-27
ERCOT | 26INR0461 | Rio Hondo BESS | SS Completed, FIS Started, No IA | SBESS TX25 LLC | 138 kV 8319 Rio Hondo Substation | Cameron | COASTAL | 2027-03-01 | BA | 200.78 | 2024-05-09 | 2024-08-05 | 2024-04-18
ERCOT | 26INR0464 | Ceres BESS | SS Started, FIS Started, No IA | Ceres BESS, LLC | Tap 138 kV 6883 QUINLAN NORTH SS - 6860 UNION VALLEY SS | Hunt | NORTH | 2027-11-30 | BA | 202.7 | 2024-10-29 |  | 2024-10-24 | [5 empty] | COD
ERCOT | 26INR0465 | Lavita BESS | SS Started, FIS Started, No IA | Lavita BESS, LLC | #3414 Temple Pecan Creek 345kV | Bell | NORTH | 2026-12-31 | BA | 606 | 2024-12-19 |  | 2024-12-16 | [5 empty] | FIS Request
ERCOT | 26INR0467 | Basketflower Storage | SS Started, FIS Started, No IA | Basketflower Solar, LLC | Tap 138kV Risingstar (285) - Nimrod (289) | Eastland | NORTH | 2027-12-31 | BA | 92 | 2024-10-29 |  | 2024-10-25 | [5 empty] | MW Size COD
ERCOT | 26INR0468 | Basketflower Solar | SS Started, FIS Started, No IA | Basketflower Solar, LLC | Tap 138kV Risingstar (285) - Nimrod (289) | Eastland | NORTH | 2027-12-31 | PV | 183 | 2024-10-29 |  | 2024-10-24 | [5 empty] | MW Size COD
ERCOT | 26INR0469 | Roxton Storage | SS Started, FIS Started, No IA | Roxton Solar, LLC | Tap 138 KV Bois Pump (1835) - Brookston (1833) | Lamar | NORTH | 2026-12-31 | BA | 102 | 2024-11-26 |  | 2024-11-05
ERCOT | 26INR0470 | Roxton Solar | SS Started, FIS Started, No IA | Roxton Solar, LLC | Tap 138 KV Bois Pump (1835) - Brookston (1833) | Lamar | NORTH | 2026-12-31 | PV | 116.8 | 2024-11-26 |  | 2024-11-05
ERCOT | 26INR0472 | Bologna BESS | SS Completed, FIS Started, No IA | MALONEY BESS LLC | Tap 138kV #1450 Pleasant Valley Switch - #1492 Wichita Falls Riverbend | Wichita | WEST | 2027-09-13 | BA | 202.56 | 2024-03-29 | 2024-06-25 | 2024-03-20
ERCOT | 26INR0474 | Sorghum BESS | SS Completed, FIS Completed, No IA | Blue Creek BESS, LLC | #44060 Blue Substation 345kV | Wharton | SOUTH | 2026-12-01 | BA | 208.9 | 2024-04-15 | 2024-07-05 | 2024-04-18 | 2024-11-13 | No
ERCOT | 26INR0485 | Prospector Energy Storage | SS Completed, FIS Started, No IA | Prospector Storage LLC | Natural Dam 138kV Substation (23836) | Howard | WEST | 2026-09-30 | BA | 204.6 | 2024-08-16 | 2024-11-01 | 2024-06-27
ERCOT | 26INR0487 | Anglin BESS | SS Completed, FIS Started, No IA | Fort Worth BESS LLC | 1883 EVRSW 138kV | Tarrant | NORTH | 2026-10-31 | BA | 206 | 2024-05-09 | 2024-08-06
ERCOT | 26INR0489 | Seven Springs Storage | SS Completed, FIS Started, No IA | Hancock Reservoir, LLC | Tap 7061 Copperas Cove to 7260 Kempner 138 kV | Lampasas | NORTH | 2028-04-15 | BA | 170.51 | 2024-04-09 | 2024-07-03 | 2024-04-08
ERCOT | 26INR0496 | Hardeman BESS | SS Completed, FIS Started, No IA | Quanah BESS LLC | 6050 PAUL 138kV | Hardeman | WEST | 2026-10-31 | BA | 104 | 2024-05-09 | 2024-08-05 | [6 empty] | FIS Request
ERCOT | 26INR0498 | Buckaroo BESS | SS Completed, FIS Started, No IA | Weatherford BESS LLC | #487 Brock 138kV | Parker | NORTH | 2026-10-31 | BA | 104 | 2024-05-09 | 2024-08-05 | [6 empty] | FIS Request
ERCOT | 26INR0499 | Mineral Springs BESS | SS Completed, FIS Started, No IA | Burnet County LLC | 7065 DOBVI 138kV | Burnet | SOUTH | 2026-10-31 | BA | 104 | 2024-06-03 | 2024-08-30 | [6 empty] | FIS Request
ERCOT | 26INR0501 | Rolling Plains BESS | SS Completed, FIS Started, No IA | Haskell County BESS LLC | 6104 SMOKY HILL 345kV | Haskell | WEST | 2026-10-31 | BA | 104 | 2024-08-16 | 2024-09-13 | [6 empty] | FIS Request
ERCOT | 26INR0502 | Fudge Ranch BESS | SS Completed, FIS Started, No IA | Crandall BESS LLC | 6902<6902><TALTY_RC><138kV> | Kaufman | NORTH | 2026-10-31 | BA | 104 | 2024-04-15 | 2024-07-11 | [6 empty] | FIS Request
ERCOT | 26INR0503 | Rex Storage | SS Completed, FIS Started, No IA | Rex BESS, LLC | 48284 Pilgrim 138kV | Harris | HOUSTON | 2027-09-15 | BA | 256.4 | 2024-06-13 | 2024-08-07 | 2024-06-04
ERCOT | 26INR0505 | Goldhill Energy Storage | SS Completed, FIS Started, No IA | Goldhill Energy Storage LLC | Tap 138kV 8154 VISTRON4B – 8189 TUNGSTEN4A | Victoria | SOUTH | 2026-09-30 | BA | 200.58 | 2024-04-15 | 2024-07-05 | 2024-04-15
ERCOT | 26INR0506 | Momentum Bock | SS Completed, FIS Started, No IA | Momentum Bock, LLC | 1771 LAMAR BLOSSOM 138kV | Lamar | NORTH | 2026-08-29 | BA | 125.38 | 2024-09-04 | 2024-12-03 | 2024-08-04
ERCOT | 26INR0507 | Los Vientos IB Repower | SS Completed, FIS Started, No IA | Los Vientos Windpower IB, LLC | #8319 RIOHONDO 138 kV | Willacy | COASTAL | 2027-03-01 | WT | 184.8 | 2024-07-22 | 2024-10-07 | 2024-07-12
ERCOT | 26INR0511 | Little Star Solar | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | #9043 CISTERN 345kV | Bastrop | SOUTH | 2026-12-31 | PV | 61.6 | 2024-07-01 | 2024-09-23 | 2024-06-12
ERCOT | 26INR0514 | Techne BESS | SS Completed, FIS Started, No IA | Techne BESS, LLC | 7560 RED ROCK 138kV | Bastrop | SOUTH | 2026-12-31 | BA | 202.7 | 2024-09-10 | 2024-12-08 | 2024-09-05
ERCOT | 26INR0516 | Jade Flash Storage | SS Completed, FIS Started, No IA | IP Lumina BESS, LLC | 59911 MHOS 345kV | Scurry | WEST | 2026-07-01 | BA | 320 | 2024-07-22 | 2024-10-08 | 2024-07-17
ERCOT | 26INR0517 | Andromeda Storage II | SS Completed, FIS Started, No IA | IP Lumina II BESS, LLC | 60011 Nebulast 345kV | Scurry | WEST | 2026-07-01 | BA | 320 | 2024-08-16 | 2024-11-12 | 2024-07-15
ERCOT | 26INR0518 | Radian Storage II | SS Completed, FIS Started, No IA | IP Radian BESS, LLC | Tap 1444 Brown Switch 345KV | Brown | NORTH | 2027-04-02 | BA | 320 | 2024-07-30 | 2024-10-25 | 2024-07-15
ERCOT | 26INR0519 | Sky Global West Houston | SS Completed, FIS Started, No IA | Sky Global Power Two, LLC | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | Austin | SOUTH | 2027-06-01 | IC | 324.58 | 2024-07-01 | 2024-10-04 | 2024-06-04 |  | Yes
ERCOT | 26INR0523 | Demeter Storage 2 | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 Lockhart | Caldwell | SOUTH | 2026-12-31 | BA | 138 | 2024-10-01 | 2024-12-30 | 2024-09-19 | [5 empty] | COD
ERCOT | 26INR0524 | Fagus Solar Park 3 SLF | SS Completed, FIS Completed, IA | Greenalia Solar Power Misae III, LLC | 60501 Tesla 345 kV | Childress | PANHANDLE | 2026-04-01 | PV | 186.83 | 2024-06-03 | 2018-07-06 | 2024-05-30 | 2024-02-27 | No | 2019-02-21
ERCOT | 26INR0525 | Bypass BESS II | SS Started, FIS Started, No IA | Bypass BESS II LLC | 44000 Wa Parish 345 kV | Fort Bend | HOUSTON | 2026-05-01 | BA | 415.97 | 2024-11-19 |  | 2024-10-23
ERCOT | 26INR0527 | Mandolin Solar SLF | SS Completed, FIS Started, No IA | Mission Clean Energy Devco LLC | Del Sol (SERIES CAP LINE SIDE) BUS#80307 to Cenizo (CAP LINE SIDE) BUS#80225 Transmission Line | Starr | SOUTH | 2029-04-30 | PV | 300 | 2024-07-22 | 2024-10-17 | 2024-06-24
ERCOT | 26INR0528 | Mandolin Storage SLF | SS Completed, FIS Started, No IA | Mission Clean Energy Devco LLC | Del Sol (SERIES CAP LINE SIDE) BUS#80307 to Cenizo (CAP LINE SIDE) BUS#80225 Transmission Line | Starr | SOUTH | 2029-04-30 | BA | 0 | 2024-07-22 | 2024-10-17 | 2024-06-24
ERCOT | 26INR0529 | Electric E - West Texas Generation | SS Started, FIS Started, No IA | Electric E Power Marketing | #11166 ENPOD 138kV | Loving | WEST | 2026-11-17 | GT | 44.4 | 2024-10-18 |  | 2024-10-10
ERCOT | 26INR0531 | West Munday Wind | SS Started, FIS Started, No IA | West Munday Wind, LLC | Tap 345 kV 60701 Gauss7B - 6104 SMOKY HILL | Knox | WEST | 2026-10-31 | WT | 351.91 | 2024-11-19 |  | 2024-11-05
ERCOT | 26INR0537 | Comanche Creek generating station | SS Completed, FIS Started, No IA | Longfellow Power LLC | TNCENTRY1_1 [138 kV] ( 38431) | Pecos | WEST | 2026-03-31 | IC | 107 | 2024-07-01 | 2024-09-23 | 2024-06-18
ERCOT | 26INR0539 | Jade Thunder Storage | SS Completed, FIS Started, No IA | IP Lumina BESS, LLC | 59911 MHOS 345kV | Scurry | WEST | 2028-07-01 | BA | 320 | 2024-07-22 | 2024-10-08 | 2024-07-17
ERCOT | 26INR0540 | Andromeda Storage IIB | SS Completed, FIS Started, No IA | IP Lumina II BESS, LLC | 60011 Nebulast 345kV | Scurry | WEST | 2028-07-01 | BA | 320 | 2024-07-22 | 2024-10-08 | 2024-06-21
ERCOT | 26INR0541 | Radian Storage IIB | SS Completed, FIS Started, No IA | IP Radian BESS, LLC | 1444 Brown Switch 345 kV | Brown | NORTH | 2028-07-01 | BA | 320 | 2024-07-30 | 2024-10-25 | 2024-06-21
ERCOT | 26INR0543 | Three Canes Solar SLF | SS Completed, FIS Started, IA | Three Canes Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro CKT#02 | Navarro | NORTH | 2026-12-31 | PV | 333 | 2024-07-22 | 2024-10-17 | 2024-07-10 |  |  | 2024-11-27 |  |  | SFS/NtP
ERCOT | 26INR0544 | Signal Hill BESS I | SS Completed, FIS Started, No IA | Signal Hill Generating LLC | 1498 WFCOGEN_8 138 - Wichita Falls Cogen 138 kV Substation | Wichita | WEST | 2027-08-18 | BA | 122.78 | 2024-09-04 | 2024-12-03 | 2024-08-06
ERCOT | 26INR0545 | Knight Airport BESS I | SS Completed, FIS Started, No IA | Airport Storage I LLC | Tap 138kV 48126 Gulfgate - 48199 Knight 06 and 42680 Garden Villas - 42770 Ashville 06 | Harris | HOUSTON | 2027-10-15 | BA | 522.46 | 2024-08-16 | 2024-11-13 | 2024-08-08
ERCOT | 26INR0546 | Hobby BESS I | SS Completed, FIS Started, No IA | Airport Storage II LLC | Double Tap 138kV 42680 Garden Villas – 48250 Hall & 42680 Garden Villas – 48013 Chocolate Bayou | Harris | HOUSTON | 2027-10-15 | BA | 602.88 | 2024-09-04 | 2024-12-03 | 2024-08-15
ERCOT | 26INR0548 | Burnet Bay Storage | SS Completed, FIS Started, No IA | TOCE TX BESS 4, LLC | tap 138kV 40390 Crosby - 40790 Haney | Harris | HOUSTON | 2027-06-01 | BA | 207.83 | 2024-09-10 | 2024-12-08 | 2024-08-29
ERCOT | 26INR0550 | Grand Mesa BESS | SS Completed, FIS Started, No IA | PERRY GREEN POWER LLC | 76582 MESA VIEW SWITCH 138kV | Pecos | WEST | 2026-09-30 | BA | 255.6 | 2024-08-16 | 2024-11-13 | 2024-08-01 | [5 empty] | MW Size
ERCOT | 26INR0551 | Hastings Park BESS | SS Completed, FIS Started, No IA | Brazos Roots BESS, LLC | 39010 138kV HASTINGS | Brazoria | COASTAL | 2026-12-31 | BA | 256.34 | 2024-08-16 | 2024-11-01 | 2024-08-09
ERCOT | 26INR0552 | Coastal Bayou Storage | SS Completed, FIS Started, No IA | TOCE TX BESS 5, LLC | tap 138kV 41690 Hopson - 41700 Warvue | Harris | HOUSTON | 2027-06-01 | BA | 174.59 | 2024-09-04 | 2024-12-03 | 2024-08-30
ERCOT | 26INR0555 | Desert Palm BESS | SS Completed, FIS Started, No IA | Desert Palm BESS LLC | 78280 Bevo Substation 138 kV | Dimmit | SOUTH | 2027-07-01 | BA | 201.3 | 2024-08-16 | 2024-11-13 | 2024-08-08
ERCOT | 26INR0556 | Wintergarden BESS | SS Completed, FIS Started, No IA | Wintergarden BESS LLC | 8970 Catarina 138 kV | Dimmit | SOUTH | 2028-09-30 | BA | 201.2 | 2024-08-16 | 2024-10-08 | 2024-08-07
ERCOT | 26INR0559 | Georgia-Lynn BESS | SS Completed, FIS Started, No IA | Concurrent Holdco LLC | 80064 CHOCBAYU4A 138 kV | Victoria | SOUTH | 2026-12-01 | BA | 108.7 | 2024-07-30 | 2024-10-28 | 2024-07-25
ERCOT | 26INR0566 | ELTEX Power Station | SS Completed, FIS Started, No IA | ELTEX Power Station LLC | 46220 Peters Substation 138 kV | Austin | SOUTH | 2027-06-01 | GT | 487.72 | 2024-09-04 | 2024-12-03 | 2024-08-26
ERCOT | 26INR0568 | Texas Cotton Solar | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | Tap 345kV 975 Jack_Creek - 967 Gibbons Creek | Brazos | NORTH | 2026-12-31 | PV | 201.6 | 2024-10-01 | 2024-12-30 | 2024-09-19
ERCOT | 26INR0573 | Cummins BESS | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 1333 MCDONALD 138kV | Glasscock | WEST | 2028-06-30 | BA | 201.6 | 2024-10-01 | 2024-11-12 | 2024-09-16
ERCOT | 26INR0577 | Pine Forest BESS 2 | SS Started, FIS Started, No IA | Pine Forest Hybrid II, LLC | new SCRSW substation 12464 (Tap 345kV 1696 Monticello SES - 2514 Allen Switch) | Hopkins | NORTH | 2026-10-29 | BA | 201.4 | 2024-12-16 |  | 2024-11-22 | [5 empty] | FIS Request
ERCOT | 26INR0590 | Callisto ID Energy Center | SS Completed, FIS Started, No IA | Tempus Power management LLC | 47150 (H_O_C__B138) 138kV | Harris | HOUSTON | 2026-06-01 | BA | 100 | 2024-10-01 | 2024-11-13 | 2024-09-10
ERCOT | 26INR0597 | Electric E - West Texas Generation 2 | SS Started, FIS Started, No IA | Electric E Power Marketing | #18664 SHAWPD 138kV | Midland | WEST | 2026-12-17 | GT | 0 | 2024-12-19 |  | 2024-11-06 | [5 empty] | FIS Request
ERCOT | 26INR0609 | Scorpius Solar | SS Started, FIS Started, No IA | Ben Milam Solar 4 | 3377 LTPSW 345KV | Milam | SOUTH | 2026-10-23 | PV | 500 | 2024-12-16 |  | 2024-11-20
ERCOT | 26INR0610 | Mica BESS | SS Started, FIS Started, No IA | Mica BESS LLC | 42240 CARDIFF 138kV | Harris | HOUSTON | 2026-01-31 | BA | 80.39 | 2024-11-19 |  | 2024-11-12
ERCOT | 26INR0612 | Clay County Yang Storage | SS Started, FIS Started, No IA | DM-CCY, LLC | To 345 kV Cobb Switching Station (Bus# 1458) | Archer | WEST | 2026-10-01 | BA | 307.51 | 2024-12-26 |  | 2024-12-20 | [5 empty] | FIS Request
ERCOT | 26INR0613 | Wichita County Mawson Storage | SS Started, FIS Started, No IA | DM-WCM, LLC | #1425 Fisher Road Switch 345 kV | Wichita | WEST | 2026-10-01 | BA | 153.8 | 2024-12-19 |  | 2024-12-13 | [5 empty] | FIS Request
ERCOT | 26INR0614 | Bell County Leifester Storage | SS Started, FIS Started, No IA | DM-BCRCML, LLC | 3428 Killen South Substation 138kV | Bell | NORTH | 2026-10-01 | BA | 205 | 2024-11-19 |  | 2024-11-14
ERCOT | 26INR0615 | Bell County Morgan Storage | SS Started, FIS Started, No IA | DM-BCTRM, LLC | To Tap 138 kV Trimmier Substation (Bus# 136) | Bell | NORTH | 2028-04-01 | BA | 256.4 | 2024-11-19 |  | 2024-11-14 | [5 empty] | COD
ERCOT | 26INR0616 | Blanco County Behrends Storage | SS Started, FIS Started, No IA | DM-BCB, LLC | #70482 Blanco Substation 138 kV - currently being upgraded | Blanco | SOUTH | 2026-10-01 | BA | 153.8 | 2024-12-19 |  | 2024-12-13 | [5 empty] | FIS Request
ERCOT | 26INR0617 | Knox County Moore Storage | SS Started, FIS Started, No IA | DM-KCM, LLC | #6110 Munday East Substation 138kV | Knox | WEST | 2026-10-01 | BA | 77 | 2024-12-19 |  | 2024-12-13 | [5 empty] | FIS Request
ERCOT | 26INR0618 | Taylor County Paul Storage | SS Started, FIS Started, No IA | DM-TCP, LLC | 6260 Abilene South Substation 138kV | Taylor | WEST | 2026-10-01 | BA | 205 | 2024-12-19 |  | 2024-12-05 | [5 empty] | FIS Request
ERCOT | 26INR0625 | Buffalo Gap 2 Wind Repower | SS Started, FIS Started, No IA | Buffalo Gap Wind Farm 2, LLC | 6216 Bluff Creek 138 kV | Nolan | WEST | 2026-12-01 | WT | 231.81 | 2024-12-19 |  | 2024-11-26 | [5 empty] | FIS Request
ERCOT | 26INR0626 | Buffalo Gap 3 Wind Repower | SS Started, FIS Started, No IA | Buffalo Gap Wind Farm 3, LLC | 6216 Bluff_Creek 138kV | Taylor | WEST | 2026-12-01 | WT | 168.63 | 2024-12-03 |  | 2024-11-20
ERCOT | 27INR0002 | Puerto Del Sol 2 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2027-12-31 | PV | 213.8 | 2022-05-16 | 2022-08-13
ERCOT | 27INR0003 | Becerra Creek Storage 2 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2026-12-01 | BA | 125.62 | 2022-09-21 | 2022-12-19 | 2022-09-07
ERCOT | 27INR0004 | Dundee North Wind | SS Completed, FIS Started, No IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | WT | 307.72 | 2023-01-03 | 2023-03-30 | 2022-12-28 |  | No
ERCOT | 27INR0005 | Dundee South A Wind | SS Completed, FIS Started, No IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-07-31 | WT | 307.23 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No
ERCOT | 27INR0007 | Felix East Solar | SS Completed, FIS Started, No IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | PV | 301.44 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No
ERCOT | 27INR0009 | Felix Storage | SS Completed, FIS Started, No IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | BA | 100.54 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No
ERCOT | 27INR0011 | Dundee South B Wind | SS Completed, FIS Started, No IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-07-31 | WT | 300.27 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | No
ERCOT | 27INR0012 | Felix West Solar | SS Completed, FIS Started, No IA | Felix 1, LLC | 6101 Riley 345 kV | Wilbarger | WEST | 2027-07-31 | PV | 200.95 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | No
ERCOT | 27INR0014 | Kit Fox Storage | SS Completed, FIS Started, No IA | Kit Fox Storage, LLC | Walton Switch (6899) 138KV | Henderson | NORTH | 2027-07-01 | BA | 153.6 | 2023-03-13 | 2023-06-09 | 2023-03-10
ERCOT | 27INR0015 | Cumbia Energy Center | SS Completed, FIS Started, No IA | Cumbia Energy Center LLC | 8485 Westside Bulk 138kV substation, owned by AEP Texas Central Co., bus number # | Nueces | COASTAL | 2027-09-07 | BA | 200 | 2023-03-27 | 2023-06-19 | 2023-03-21
ERCOT | 27INR0020 | SCOTT CROSSING PV1 | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 60514 Clear Crossing - 60507 | Haskell | WEST | 2027-09-01 | PV | 364.14 | 2023-03-27 | 2023-06-19 | 2023-03-13
ERCOT | 27INR0021 | Live Oak Bayou Solar SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV Refuge (42400) - Hawkinsville (42440) ckt 27 | Matagorda | COASTAL | 2027-12-01 | PV | 156.06 | 2023-05-15 | 2023-08-11 | 2023-05-09
ERCOT | 27INR0022 | Panhandle Flagship Solar 1 | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2027-12-01 | PV | 439.4 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes
ERCOT | 27INR0023 | Panhandle Flagship Solar 2 | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005). Station 2 (27INR0023) connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 (27INR0022 & 27INR0025) connects to POIB via 22.5 mile tie-line | Hutchinson | PANHANDLE | 2027-12-01 | PV | 304.4 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes
ERCOT | 27INR0024 | Panhandle Flagship Solar 3 | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005).Station 3 (27INR0024) connects to Station 2 (27INR0023) via a 4.4 mile internal tie line. Station 2 connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 connects to POI | Hutchinson | PANHANDLE | 2027-12-01 | PV | 260.3 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes
ERCOT | 27INR0025 | Panhandle Flagship Storage | SS Completed, FIS Started, No IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2027-12-01 | BA | 371.7 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes
ERCOT | 27INR0029 | Short Creek BESS | SS Completed, FIS Started, No IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch | Wichita | WEST | 2027-12-01 | BA | 150.51 | 2023-04-19 | 2023-07-14 | 2023-04-12 |  | No
ERCOT | 27INR0038 | SCOTT CROSSING STORAGE SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 60514 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2027-09-01 | BA | 0 | 2023-04-19 | 2023-07-13 | 2023-04-07
ERCOT | 27INR0039 | Live Oak Bayou Storage SLF | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 345kV 42530 Jones Creek – 42440 Hawkinsville ckt 27 | Matagorda | COASTAL | 2027-12-01 | BA | 0 | 2023-05-03 | 2023-07-28 | 2023-04-20
ERCOT | 27INR0040 | Solar Star Rhome Storage | SS Completed, FIS Started, No IA | Solar Star Rhome Storage | 576 RHOME 138kV | Wise | NORTH | 2027-03-31 | BA | 220.7 | 2023-04-19 | 2023-07-12
ERCOT | 27INR0047 | Sunscape Renewable Energy Solar SLF | SS Completed, FIS Started, IA | Sunscape Renewable Energy LLC | Bus# 8455 Lon C Hill to Bus# 80078 Reforzar 345 kV Line | Nueces | COASTAL | 2028-10-28 | PV | 522.75 | 2023-06-28 | 2023-09-20 | 2023-05-30 |  | Yes | 2024-07-18
ERCOT | 27INR0048 | Sunscape Renewable Energy Storage SLF | SS Completed, FIS Started, IA | Sunscape Renewable Energy LLC | Tap 345kV 8455 Lon C Hill -- 80078 Reforzar | Nueces | COASTAL | 2028-10-28 | BA | 0 | 2023-06-28 | 2023-09-20 | 2023-06-06 |  | Yes | 2024-07-18
ERCOT | 27INR0049 | Darkwood Solar | SS Completed, FIS Started, No IA | Mustang Creek Solar, LLC | Tap 345KV 1900 Comanche Peak to 1440 Comanche SS | Comanche | NORTH | 2027-01-30 | PV | 150.76 | 2023-06-28 | 2023-09-01 | 2023-11-09
ERCOT | 27INR0050 | Darkwood BESS | SS Completed, FIS Started, No IA | Mustang Creek Solar, LLC | Tap 345KV 1900 Comanche Peak - 1440 Comanche Switch | Comanche | NORTH | 2027-01-30 | BA | 150.5 | 2023-06-07 | 2023-09-01
ERCOT | 27INR0056 | Laurel Wind Energy Center | SS Completed, FIS Started, No IA | Laurel Energy Center, LLC | Solstice to Bakersfield (Bus# 60404 -76002) 345kV Ckt 2 line tap | Pecos | WEST | 2027-01-31 | WT | 501.76 | 2023-06-28 | 2023-09-22 | 2023-06-08
ERCOT | 27INR0061 | Hecate Energy Orem Wind | SS Completed, FIS Started, No IA | Hecate Energy LLC | 42530 Jones Creek 345kV | Brazoria | COASTAL | 2030-06-01 | WT | 1542 | 2023-06-28 | 2023-09-22
ERCOT | 27INR0063 | Supra Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap #6101 Riley 7A to #60505 Edithcla 7B 345kV | Hardeman | WEST | 2027-12-23 | WT | 205.86 | 2023-07-10 | 2023-10-05 | 2023-06-29
ERCOT | 27INR0068 | Jerboa BESS | SS Completed, FIS Started, No IA | Jerboa Storage, LLC | Tap 138kV 8906 North Alamo - 8354 Weslaco Switching Station | Hidalgo | SOUTH | 2027-02-28 | BA | 201.08 | 2023-08-14 | 2023-11-02 | 2023-07-18
ERCOT | 27INR0076 | Lili Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap Sand Bluff <59902> Divide <76090>, 345kV | Sterling | WEST | 2028-07-01 | WT | 240 | 2024-01-11 | 2024-04-08 | 2024-01-09
ERCOT | 27INR0077 | Cuchillas BESS | SS Completed, FIS Started, No IA | Gransolar Texas Two | 80219 Lobo 345kV | Webb | SOUTH | 2026-12-27 | BA | 306.94 | 2023-09-26 | 2023-12-20 | 2023-08-17
ERCOT | 27INR0080 | Laurel Storage Energy Center | SS Completed, FIS Started, No IA | Laurel Energy Center, LLC | Tap 345kV 60404 Solstice - 76002 Bakersfield Ckt 2 | Pecos | WEST | 2027-01-31 | BA | 200.8 | 2023-09-07 | 2023-12-01 | 2023-08-21
ERCOT | 27INR0082 | Orbit Energy Storage | SS Completed, FIS Started, No IA | GCI Orbit Energy Storage, LLC | Tap 345 kV Calaveras Power Station (BUS #5400) to HOWARD_5 (BUS #5231). | Bexar | SOUTH | 2027-06-01 | BA | 501.94 | 2023-11-30 | 2024-02-29 | 2023-09-27
ERCOT | 27INR0083 | Spinner Energy Storage | SS Completed, FIS Started, No IA | GCI Wolf Energy Storage, LLC | 8196 Poesta Substation 138kV | Bee | SOUTH | 2027-06-01 | BA | 125.63 | 2023-10-13 | 2024-01-09 | 2023-09-27
ERCOT | 27INR0084 | Aegle Power | SS Completed, FIS Started, No IA | Aegle Power LLC | (#79501) Kingfisher 345 kV | Cameron | COASTAL | 2027-07-30 | CC | 1536.4 | 2024-07-22 | 2024-10-17 | 2024-07-03
ERCOT | 27INR0085 | Eagle Claw Energy Center | SS Completed, FIS Completed, No IA | Cypress Energy Center, LLC | 30.615932, -95.962023 - Singleton (Bus #44645) - Zenith (Bus #44900) Circuit #98 345 kV Line | Grimes | NORTH | 2027-03-15 | BA | 200.84 | 2023-10-13 | 2024-01-10 | 2023-10-06 | 2024-10-30 | Yes
ERCOT | 27INR0086 | Tumbleweed Solar | SS Completed, FIS Started, No IA | Hecate Energy Tumbleweed Solar LLC | 59905 Faraday 345 kV | Borden | WEST | 2027-12-01 | PV | 613.89 | 2023-09-22 | 2023-12-20
ERCOT | 27INR0087 | Tumbleweed Storage | SS Completed, FIS Started, No IA | Hecate Energy Tumbleweed Storage LLC | 59905 Faraday 345 kV | Borden | WEST | 2027-12-01 | BA | 507.2 | 2023-10-04 | 2023-12-20
ERCOT | 27INR0090 | Antonio Road BESS | SS Completed, FIS Started, No IA | Tempus Power management LLC | Paige 138kV, bus number 7308, connecting to the existing substation via adding a breaker | Bastrop | SOUTH | 2027-06-01 | BA | 155.52 | 2023-10-13 | 2024-01-09 | [6 empty] | COD
ERCOT | 27INR0091 | Oak Tree Energy Storage | SS Completed, FIS Started, No IA | Live Oak Energy Storage, LLC | Tap Shaula (#5380) – South Texas (#5915) | Lavaca | SOUTH | 2027-11-04 | BA | 310.2 | 2023-12-04 | 2024-02-21 | 2023-11-21
ERCOT | 27INR0092 | Pecan BESS | SS Completed, FIS Started, No IA | Gransolar Texas Three LLC | (PSSE BUS# 47) HILTOPLKS8 138kV | Leon | NORTH | 2027-07-15 | BA | 157.12 | 2023-10-25 | 2024-01-22 | 2023-10-12
ERCOT | 27INR0093 | Guadalupe Battery Storage Project | SS Completed, FIS Started, No IA | Guadalupe Power Partners, LP | # 7044 Marion 345kV | Guadalupe | SOUTH | 2027-05-01 | BA | 210.5 | 2023-11-14 | 2024-02-08 | [6 empty] | FIS Request
ERCOT | 27INR0095 | Bulldog Power | SS Completed, FIS Started, No IA | Bulldog Power LLC | 39703 TNMP FM524 Substation 138kV | Brazoria | COASTAL | 2026-04-30 | GT | 300.75 | 2023-11-14 | 2024-02-08 | 2023-11-08 |  | No
ERCOT | 27INR0096 | Rubicon Power BESS | SS Completed, FIS Completed, No IA | Rubicon Power LLC | 39703 TNMP FM524 138kV | Brazoria | COASTAL | 2025-11-15 | BA | 301.38 | 2023-11-14 | 2024-02-08 | 2023-11-08 | 2024-08-23 | No
ERCOT | 27INR0097 | JUNIPERUS BESS | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE XXI LLC | TAP CASHSW_T5 (2464) -SULSP_SS1_5 (1697) | Hopkins | NORTH | 2028-04-03 | BA | 226.39 | 2023-10-30 | 2024-01-26
ERCOT | 27INR0099 | Silver Spur Energy Center | SS Completed, FIS Started, No IA | Silver Spur Energy Center, LLC | TAP BRYN_WBRN (BUS #32895) - MILL_SW138 (BUS #32856) 138 KV LINE | Brazos | NORTH | 2027-02-01 | BA | 200.83 | 2023-12-04 | 2024-03-01 | 2023-10-16
ERCOT | 27INR0102 | Cottonseed Energy Storage | SS Completed, FIS Completed, No IA | Cottonseed Energy Storage LLC | South Lane City and PSEE # is 43190 | Wharton | SOUTH | 2027-04-20 | BA | 207.6 | 2023-11-14 | 2024-01-08 | 2023-11-02 | 2024-08-23
ERCOT | 27INR0105 | Starlight Solar | SS Completed, FIS Started, No IA | Mills Tx Solar LLC | tap the 138 kV Goldthwaite (#7070) – San Saba Switch (#77074) | Mills | NORTH | 2027-03-15 | PV | 130.72 | 2024-02-27 | 2024-05-22 | 2024-02-08
ERCOT | 27INR0106 | Bluewind Energy Center | SS Completed, FIS Started, No IA | Bluewind Energy Center, LLC | 5713 Oaks Substation 138kV | Atascosa | SOUTH | 2026-07-02 | BA | 102.56 | 2024-02-27 | 2024-05-20 | 2024-01-15
ERCOT | 27INR0107 | Starlight Storage | SS Completed, FIS Started, No IA | Mills Tx Solar LLC | Tap 138kV 7070 Goldthwaite – 77074 San Saba Switch | Mills | NORTH | 2027-03-15 | BA | 104.66 | 2024-02-27 | 2024-05-22 | 2024-02-08
ERCOT | 27INR0108 | Menarcho | SS Completed, FIS Started, No IA | Orsted Onshore Development North America, LLC | Tap 345-kV Double Circuit Amos Creek (7077) – Brown (1444)/Amos Creek (7077) – Bow Wood (76006) | Concho | WEST | 2028-03-29 | WT | 405.4 | 2024-01-03 | 2024-03-29 | 2023-12-11
ERCOT | 27INR0109 | Two Barbaras BESS | SS Completed, FIS Started, No IA | Two Barbaras BESS | Tap 138 kV Pinehurst (#46240) – Mill Creek (#44850) Line | Montgomery | HOUSTON | 2028-03-02 | BA | 217.16 | 2024-03-22 | 2024-06-19 | 2024-03-14
ERCOT | 27INR0111 | Malachite Solar | SS Completed, FIS Started, No IA | Malachite Solar LLC | The 345 kV Hillje (#44200) – Holman (#9073) Line; AEN. | Wharton | SOUTH | 2028-07-31 | PV | 184.55 | 2024-02-27 | 2024-05-22 | 2024-01-25
ERCOT | 27INR0112 | Malachite BESS | SS Completed, FIS Started, No IA | Malachite Storage LLC | Tap 345 kV 44200 Hillje – 9073 Homan | Wharton | SOUTH | 2028-07-31 | BA | 191.12 | 2024-05-20 | 2024-07-22 | 2024-05-15
ERCOT | 27INR0118 | Grapefruit Solar | SS Completed, FIS Started, No IA | Grapefruit Solar LLC | North Edinburg (Bus #8905) - Reforzar (Bus # 80078) 345kV | Hidalgo | SOUTH | 2027-12-30 | PV | 301.2 | 2024-02-27 | 2024-05-22 | 2024-01-26 |  | No
ERCOT | 27INR0122 | Paddlewheel Solar SLF | SS Completed, FIS Started, No IA | Paddlewheel Solar, LLC | 138 kV Pavlov Station (#8608); AEP | Matagorda | COASTAL | 2027-09-30 | PV | 150 | 2024-06-03 | 2024-08-27 | 2024-06-03
ERCOT | 27INR0124 | RedSun Solar | SS Completed, FIS Started, No IA | Gransolar Texas Twenty Two | Tap 138kV 7100 Burnet - 7529 Bertram | Burnet | SOUTH | 2027-06-15 | PV | 82.55 | 2023-12-04 | 2024-03-01 | 2023-11-28
ERCOT | 27INR0125 | RedSun BESS | SS Completed, FIS Started, No IA | Gransolar Texas Twenty Two | Existing Line from Substation Name: Burnet (PSSE#7100) to Substation Name: Bertram (PSSE#7520) | Burnet | SOUTH | 2027-06-15 | BA | 84.04 | 2023-12-04 | 2024-03-01 | 2023-11-21
ERCOT | 27INR0126 | Corvus Solar, LLC | SS Completed, FIS Started, No IA | Corvus Solar, LLC | Tap 345kV Cenzio (#80219) - Lobo (#80220) | Webb | SOUTH | 2027-07-13 | PV | 200.9 | 2024-02-07 | 2024-04-30 | 2024-01-16 |  | No
ERCOT | 27INR0127 | Bigway Solar I | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 59904 Cottonwood - 60500 Edith Clarke Ckt #2 | King | WEST | 2028-12-31 | PV | 200 | 2024-01-11 | 2024-03-15
ERCOT | 27INR0128 | Bigway Solar II | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345KV #59904 Cottonwood - #60500 Edith Clarke Ckt #2 | King | WEST | 2028-12-31 | PV | 200 | 2023-12-20 | 2024-03-15 |  |  | No
ERCOT | 27INR0132 | Palo Verde Wind | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | Tap 345kV 8624 Grissom – 8455 Lon C Hill | San Patricio | COASTAL | 2027-09-02 | WT | 301.5 | 2024-04-09 | 2024-07-05 | 2024-04-01
ERCOT | 27INR0137 | Moonlit Bayou Storage | SS Completed, FIS Started, No IA | Moonlit Bayou Energy Center, LLC | Tap 138kV 7252 Schulenburg - 7254 Weimar | Fayette | SOUTH | 2028-07-31 | BA | 209.23 | 2024-02-26 | 2024-05-24 | 2024-02-08
ERCOT | 27INR0139 | Gatsby Energy Storage | SS Completed, FIS Started, No IA | Gatsby Energy Storage LLC | Fort Lancaster 138 kV Substation (PSSE Bus #76579) | Pecos | WEST | 2027-03-31 | BA | 103.36 | 2024-02-07 | 2024-04-29 | 2023-12-07
ERCOT | 27INR0141 | Bluefox Solar 1 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2029-05-31 | PV | 402.6 | 2024-03-22 | 2024-06-19 | 2024-02-21
ERCOT | 27INR0142 | UNICORN BESS | SS Completed, FIS Started, No IA | Unicorn Energies | Tap 138 kV Wa Parish (#44015) - Crabb River Road Line (#44170) Line; CNP | Fort Bend | HOUSTON | 2027-09-01 | BA | 278.98 | 2024-01-11 | 2024-04-05 | 2024-01-05
ERCOT | 27INR0143 | Ogalalla Storage | SS Completed, FIS Started, No IA | Hecate Energy Ogalalla Solar LLC | 23912 OGALLALA_5 345kV | Castro | PANHANDLE | 2028-04-15 | BA | 251.6 | 2024-01-03 | 2024-03-25
ERCOT | 27INR0144 | Angel City Solar | SS Completed, FIS Started, No IA | Angel City Energy Center, LLC | Coleto Creek (# 8164) AEP – Pawnee (#5725) STEC, 25.9 miles from Coleto Creek, 28.2 miles from Pawnee Sub. POI co-ordinates: 28.755, -97.583 | Goliad | SOUTH | 2029-09-30 | PV | 221.02 | 2024-02-07 | 2024-04-30 | 2024-01-23
ERCOT | 27INR0145 | Steelhead Energy Storage | SS Completed, FIS Started, No IA | GRS BESS TEXAS SEVEN, LLC | Tap 1593 BONHAM_P8 to Allens Creek 1835 138kV | Fannin | NORTH | 2027-09-30 | BA | 192.1 | 2024-02-07 | 2024-04-29 | 2024-01-04
ERCOT | 27INR0146 | Larrea Solar | SS Completed, FIS Started, No IA | Greasewood IV LLC | Tap 345kV 76002 Bakerfield - 60404 Solstice CKT#1 | Pecos | WEST | 2027-09-18 | PV | 231.6 | 2024-01-03 | 2024-03-29
ERCOT | 27INR0147 | Paloma Energy Center | SS Completed, FIS Started, No IA | Harrison Street Development, LLC | Tap138 kV 57640 Rock Island - 57639 Sheridan | Colorado | SOUTH | 2027-06-01 | PV | 193.8 | 2024-02-07 | 2024-05-01 | 2024-01-09
ERCOT | 27INR0148 | Paloma Energy Center BESS | SS Completed, FIS Started, No IA | Harrison Street Development, LLC | 138 kV Tap 57640 Rock Island and 57639 Sheridan | Colorado | SOUTH | 2027-06-01 | BA | 53.6 | 2024-02-07 | 2024-05-01 | 2024-01-22
ERCOT | 27INR0149 | Diablo Campo Storage | SS Completed, FIS Started, No IA | Diablo Campo Energy Center, LLC | The Coleto Greek (#8164) to Pawnee Switching Station (#5725) ; LCRA | Goliad | SOUTH | 2029-09-30 | BA | 313.54 | 2024-02-07 | 2024-04-29 | 2024-01-23
ERCOT | 27INR0151 | Coyote Den Storage | SS Completed, FIS Started, No IA | Coyote Den Energy Center, LLC | The Kenedy Switching Station #2 (#8186) to Rosata POD (#8153) Line ; AEP | Karnes | SOUTH | 2028-09-30 | BA | 156.61 | 2024-02-07 | 2024-04-29 | 2024-01-09
ERCOT | 27INR0152 | New Shepherd Solar | SS Completed, FIS Started, No IA | New Shepherd Energy Center, LLC | the Kenedy Switching Station #2 (#8186) – Rosata POD (#8153) line, AEP. | Karnes | SOUTH | 2028-09-30 | PV | 150.81 | 2024-01-11 | 2024-04-05 | 2023-12-19
ERCOT | 27INR0154 | Jim Wells BESS | SS Completed, FIS Started, No IA | Jim Wells ESS | 69kV PREMONT (#8894) | Jim Wells | SOUTH | 2027-04-01 | BA | 100.32 | 2024-02-07 | 2024-05-01 | 2024-01-15
ERCOT | 27INR0169 | Marcos Solar | SS Completed, FIS Started, No IA | GRS BESS Texas Eight | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | Victoria | SOUTH | 2027-08-15 | PV | 115.88 | 2024-01-11 | 2024-04-08 | 2023-12-28
ERCOT | 27INR0170 | Marcos BESS | SS Completed, FIS Started, No IA | GRS BESS Texas Eight LLC | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | Victoria | SOUTH | 2027-08-15 | BA | 115.88 | 2024-02-07 | 2024-04-30 | 2024-01-16
ERCOT | 27INR0173 | Trenno BESS | SS Completed, FIS Started, No IA | JSB1, LLC | Tap 138kV 2281 Godley - 2888 Carmichael | Johnson | NORTH | 2027-09-13 | BA | 202.56 | 2024-02-07 | 2024-04-30
ERCOT | 27INR0180 | Otter BESS | SS Completed, FIS Started, No IA | GRS BESS TEXAS TEN, LLC | 5378 SHEPHERD RD 138kV | Bexar | SOUTH | 2027-04-15 | BA | 157.12 | 2024-02-27 | 2024-05-20 | 2024-02-05
ERCOT | 27INR0181 | Elk Unit 4 | SS Completed, FIS Started, No IA | Golden Spread Electric Cooperative, Inc. | 141607 AEEC_5 | Hale | PANHANDLE | 2027-02-28 | GT | 210 | 2024-04-09 | 2024-07-05 | 2024-03-19
ERCOT | 27INR0186 | Silver Dollar Solar | SS Completed, FIS Started, No IA | Silver Dollar Solar Project, LLC | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | Freestone | NORTH | 2028-04-28 | PV | 301.9 | 2024-06-03 | 2024-08-29 | 2024-05-13
ERCOT | 27INR0187 | Silver Dollar Storage | SS Completed, FIS Started, No IA | Silver Dollar Solar Project, LLC | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | Freestone | NORTH | 2028-04-28 | BA | 153.1 | 2024-06-03 | 2024-08-29 | 2024-05-13
ERCOT | 27INR0190 | Millsing BESS | SS Completed, FIS Completed, No IA | Millsing BESS | 44645 CNP Singleton 345kV | Grimes | NORTH | 2027-07-01 | BA | 501.6 | 2024-02-27 | 2024-05-24 | 2024-02-05 | 2024-10-08
ERCOT | 27INR0192 | Cedar Draw Solar | SS Completed, FIS Started, No IA | Cedar Draw Solar LLC | 60011 Nebula7A 345kV | Scurry | WEST | 2027-12-31 | PV | 451.4 | 2024-03-22 | 2024-06-19 | 2024-03-01
ERCOT | 27INR0193 | Cedar Draw BESS | SS Completed, FIS Started, No IA | Cedar Draw Solar LLC | 60011 Nebula7A 345kV | Scurry | WEST | 2027-12-31 | BA | 225.7 | 2024-03-22 | 2024-06-19 | 2024-02-20
ERCOT | 27INR0195 | CORRUSCANT BESS | SS Completed, FIS Started, No IA | AEU Battery Project III LLC | Tap 345kV 59904 COTTONWOOD - 60500 EDITHCLA7A | Dickens | PANHANDLE | 2027-04-18 | BA | 337.35 | 2024-02-27 | 2024-05-20 | 2024-02-06
ERCOT | 27INR0196 | Houston County BESS | SS Completed, FIS Started, No IA | Houston ESS, LLC | Tap ETEC 138kV #6733 Mustang Prairie to #6732 Latexo Sub | Houston | NORTH | 2027-04-12 | BA | 125.4 | 2024-02-27 | 2024-05-20 | 2024-01-31
ERCOT | 27INR0202 | Shallow Valley Storage | SS Completed, FIS Started, No IA | Shallow Valley Storage, LLC | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | Ward | WEST | 2028-06-01 | BA | 103.39 | 2024-07-22 | 2024-10-17 | 2024-07-19
ERCOT | 27INR0203 | Dunlay Solar | SS Completed, FIS Started, No IA | Medina PV, LLC | Tap 138kV 5813 PearsonSW - 5225 Hondo | Medina | SOUTH | 2028-06-01 | PV | 150.5 | 2024-03-22 | 2024-06-19 | 2024-03-12
ERCOT | 27INR0205 | Donna Solar | SS Completed, FIS Started, No IA | Donna Solar LLC | Tap 345 kV (80137) Stewart Road - (8383) North Edinburg CKT ID#01 | Hidalgo | SOUTH | 2027-12-31 | PV | 168.97 | 2024-03-22 | 2024-06-19
ERCOT | 27INR0206 | Chacon Creek | SS Completed, FIS Started, No IA | Cattlemen BESS LLC | (#8962) LYTLE4A 138KV | Medina | SOUTH | 2027-10-31 | BA | 181.9 | 2024-03-22 | 2024-06-19 | 2024-03-14
ERCOT | 27INR0207 | Wander Waters BESS | SS Completed, FIS Started, No IA | Wander Waters BESS LLC | 61001 JIMTREEC7A 345kV | Wilbarger | WEST | 2027-10-31 | BA | 303.5 | 2024-03-22 | 2024-06-19 | 2024-03-12
ERCOT | 27INR0208 | Sugarloaf BESS | SS Completed, FIS Started, No IA | Sugarloaf Clean Energy LLC | (#80481) PILONCIL4 138KV | Dimmit | SOUTH | 2026-10-31 | BA | 100.6 | 2024-03-22 | 2024-06-19 | 2024-03-11
ERCOT | 27INR0209 | Goby Energy Center | SS Completed, FIS Started, No IA | Goby Energy Center | Tap 138kV line 44390 Karsten - 44721 Thompsons | Brazoria | COASTAL | 2027-06-30 | BA | 200.65 | 2024-05-20 | 2024-08-15 | 2024-05-07
ERCOT | 27INR0216 | Champs Elysees BESS | SS Completed, FIS Started, No IA | Champs Elysees Renewables, LLC | Tap 345 kV 3377 Little Pond Switch - 3704 Hog Creek Switch | Milam | SOUTH | 2027-12-15 | BA | 256.1 | 2024-08-16 | 2024-10-08 | 2024-07-26
ERCOT | 27INR0217 | Journey Solar | SS Completed, FIS Started, No IA | Journey Solar, LLC | Tap 138kV Paint Creek 6161 - Aspermont 6158 | Haskell | WEST | 2027-09-14 | PV | 124.7 | 2024-03-29 | 2024-06-19 | 2024-03-14
ERCOT | 27INR0218 | Themisto Solar | SS Completed, FIS Started, No IA | Themisto Solar, LLC | Tap 345kV Champion Creek #1414 – Sweetwater East #11420 | Nolan | WEST | 2027-07-28 | PV | 301.2 | 2024-02-26 | 2024-05-24 | 2024-02-13
ERCOT | 27INR0219 | Rigel Solar | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Tap 345kV 2427 Watermill - 3159 Elrod | Ellis | NORTH | 2028-10-30 | PV | 151.43 | 2024-03-22 | 2024-06-19 | [6 empty] | MW Size COD
ERCOT | 27INR0220 | Rigel Storage | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Tap 345kV 2427 Watermill - 3159 Elrod | Ellis | NORTH | 2028-10-30 | BA | 151.57 | 2024-03-22 | 2024-06-19 | [6 empty] | MW Size COD
ERCOT | 27INR0221 | Fierce River Solar | SS Completed, FIS Started, No IA | Rio Grande Solar LLC | Tap 345 kV 80355 Del Sol - 80119 Frontera Ckt 1 | Starr | SOUTH | 2028-12-06 | PV | 895.67 | 2024-03-22 | 2024-06-19
ERCOT | 27INR0222 | Fierce River BESS | SS Completed, FIS Started, No IA | Rio Grande Solar LLC | Tapping the 345 kV Line from Del Sol (Bus# 80355) to Frontera (Bus# 80119) ckt 1 | Starr | SOUTH | 2028-12-06 | BA | 284.49 | 2024-03-22 | 2024-06-19
ERCOT | 27INR0223 | Benitoite Storage | SS Completed, FIS Started, No IA | BT Van Storage, LLC | Tap 138kV 3183 VAN_8 - 3197 TYLERSW_8 | Van Zandt | NORTH | 2027-08-25 | BA | 125.65 | 2024-03-22 | 2024-06-19 | 2024-03-10
ERCOT | 27INR0224 | Leopard BESS | SS Completed, FIS Started, No IA | Bobcat Energy Center, LLC | 8721 Beecher 138 kV | Victoria | SOUTH | 2027-07-02 | BA | 264.24 | 2024-05-09 | 2024-08-05 | 2024-04-05
ERCOT | 27INR0226 | Sunlit Pines Solar SLF | SS Completed, FIS Started, No IA | Sunlit Pines Energy Center LLC | Tap 138 kV 3342 Bayou Loco - 3341 Central Angelina County | Nacogdoches | NORTH | 2027-10-03 | PV | 206.71 | 2024-03-29 | 2024-06-24 | 2024-03-29
ERCOT | 27INR0227 | PALO VERDE BESS | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | Tap 345kV 8624 Grissom – 8455 Lon C Hill | San Patricio | COASTAL | 2027-09-02 | BA | 150 | 2024-04-15 | 2024-07-05 | 2024-04-01
ERCOT | 27INR0228 | Sunlit Pines BESS SLF | SS Completed, FIS Started, No IA | Sunlit Pines BESS LLC | Tap 138 kV 3342 Bayou Loco - 3341 Central Angelina County | Nacogdoches | NORTH | 2027-10-03 | BA | 208.12 | 2024-04-09 | 2024-06-24 | 2024-03-29
ERCOT | 27INR0231 | Easy Battery Energy Storage Center | SS Completed, FIS Started, No IA | Easy Wind Energy Center, LLC | Tap 345 kV 76003 Big Hill to 76005 Schneeman Draw | Schleicher | WEST | 2027-12-01 | BA | 200 | 2024-03-29 | 2024-06-19 | 2024-03-20
ERCOT | 27INR0232 | Anawa La Solar | SS Completed, FIS Started, No IA | EIA Properties, Ltd. | TAP 138 KV 8394 LISTON - 8392 BATES | Hidalgo | SOUTH | 2027-08-31 | PV | 93.3 | 2024-03-29 | 2024-06-19
ERCOT | 27INR0233 | Anawa La BESS | SS Completed, FIS Started, No IA | EIA Properties, Ltd. | Tap 138KV 8394 Liston- 8392 Bates | Hidalgo | SOUTH | 2027-08-31 | BA | 103.7 | 2024-03-22 | 2024-06-19
ERCOT | 27INR0234 | Maddox Solar | SS Completed, FIS Started, No IA | Industrial Lima Project LLC | Tap 138 kV Haggerty Switch (12677) to Van Al (1754) 138kV | Grayson | NORTH | 2027-09-17 | PV | 101.3 | 2024-05-09 | 2024-08-05 | 2024-04-17
ERCOT | 27INR0235 | Ochoa Energy Storage II | SS Completed, FIS Started, No IA | Ochoa Energy Storage II LLC | Tap 138kV 44420 Katy - 44230 Flewellen | Waller | HOUSTON | 2027-06-03 | BA | 501.72 | 2024-04-15 | 2024-07-12 | 2024-04-11
ERCOT | 27INR0236 | Atticus Energy Storage | SS Completed, FIS Started, No IA | Atticus Energy Storage | 6570 Bond Road Substation 69KV | Sutton | WEST | 2027-03-01 | BA | 102.98 | 2024-03-29 | 2024-06-25 | 2024-03-29
ERCOT | 27INR0241 | Callan Solar | SS Completed, FIS Started, No IA | Menard PV, LLC | Tap 69kV 60386 Heartland to 6363 Yellow Jacket | Menard | WEST | 2028-09-01 | PV | 90.97 | 2024-06-13 | 2024-08-07 | 2024-06-04
ERCOT | 27INR0242 | Stonewall Solar | SS Completed, FIS Started, No IA | Stonewall PV, LLC | #755 BEPC ASPERMONT 69KV | Stonewall | WEST | 2029-01-15 | PV | 60.2 | 2024-05-09 | 2024-08-05 | 2024-05-01
ERCOT | 27INR0243 | Brookview Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Green Field | Channelview 1 ( 40280) 138kV Substation | Harris | HOUSTON | 2027-05-31 | BA | 203.2 | 2024-04-09 | 2024-07-05 | 2024-04-02
ERCOT | 27INR0245 | Pez Rojo BESS | SS Completed, FIS Started, No IA | Pez Rojo BESS, LLC | Tap 138 kV #40260 Chamon - #40912 King | Harris | HOUSTON | 2028-03-01 | BA | 217.23 | 2024-07-01 | 2024-09-23 | 2024-06-14
ERCOT | 27INR0246 | Easy Wind Energy Center | SS Completed, FIS Started, No IA | Easy Wind Energy Center, LLC | Tap 345kV #76003 Big Hill - #76005 Schneeman Draw circuit #1 | Schleicher | WEST | 2027-12-01 | WT | 241.13 | 2024-05-20 | 2024-08-16 | 2024-05-02
ERCOT | 27INR0247 | Sun Angel ESS | SS Completed, FIS Started, No IA | Sun Angel ESS LLC | Tap 138kV LUFKINE_8 (#3326)-HERTYTAP_8 (#3318) | Angelina | NORTH | 2028-07-01 | BA | 201.54 | 2024-06-13 | 2024-08-07 | 2024-06-11
ERCOT | 27INR0248 | Double A Solar | SS Completed, FIS Started, No IA | Double A Solar, LLC | Tap 69kV 5678 Schroeder - 5675 Big Oak | Goliad | SOUTH | 2027-05-31 | PV | 132.6 | 2024-06-13 | 2024-08-07 | 2024-05-30
ERCOT | 27INR0249 | Raghorn Solar | SS Completed, FIS Started, No IA | Raghorn Solar LLC | Tap 69kV #5654 San Diego - #5658 Orange Grove | Jim Wells | SOUTH | 2027-05-31 | PV | 91.9 | 2024-05-20 | 2024-08-16 | 2024-05-16
ERCOT | 27INR0251 | Sayle Solar | SS Completed, FIS Started, No IA | Sayle Solar LLC | Tap 69kV #5522 Edna - #5518 El Toro SW | Jackson | SOUTH | 2027-05-31 | PV | 122.4 | 2024-06-03 | 2024-08-30 | 2024-05-22
ERCOT | 27INR0252 | Parula Energy Center | SS Completed, FIS Started, No IA | Parula Energy Center | 7287 Bellville North 138kV | Austin | SOUTH | 2027-06-30 | BA | 250.95 | 2024-05-20 | 2024-08-15 | 2024-05-09
ERCOT | 27INR0253 | Old Victory Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 8692 MAVERICK4A 138kV | Maverick | SOUTH | 2027-05-01 | BA | 208.8 | 2024-05-09 | 2024-08-05 | 2024-04-25
ERCOT | 27INR0254 | REVOLUTION BESS | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 8619 Encinal Substation 138KV | La Salle | SOUTH | 2027-05-01 | BA | 208.8 | 2024-05-09 | 2024-08-05 | 2024-04-22
ERCOT | 27INR0255 | New Minglewood Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | #11098 Sand Lake Switch Station (SANDLAKE_5) 345kV | Ward | WEST | 2027-09-30 | BA | 208.3 | 2024-05-09 | 2024-08-05 | 2024-04-29
ERCOT | 27INR0256 | Paddlewheel BESS SLF | SS Completed, FIS Started, No IA | Paddlewheel Solar, LLC | 138 kV Pavlov Station (#8608); AEP | Matagorda | COASTAL | 2027-09-30 | BA | 50 | 2024-06-03 | 2024-08-27 | 2024-06-03
ERCOT | 27INR0257 | Double A Storage | SS Completed, FIS Started, No IA | Double A Storage, LLC | Tap 69kV 5678 Schroeder - 5675 Big Oak | Goliad | SOUTH | 2027-05-31 | BA | 132.4 | 2024-06-13 | 2024-08-07 | 2024-05-30
ERCOT | 27INR0259 | Raghorn Storage | SS Completed, FIS Started, No IA | Raghorn Storage LLC | Tap 69kV #5654 San Diego - #5658 Orange Grove | Jim Wells | SOUTH | 2027-05-31 | BA | 91.7 | 2024-05-20 | 2024-08-16 | 2024-05-16
ERCOT | 27INR0260 | Sayle Storage | SS Completed, FIS Started, No IA | Sayle Storage LLC | Tap 69kV #5522 Edna - #5518 El Toro SW | Jackson | SOUTH | 2027-05-31 | BA | 122.3 | 2024-06-03 | 2024-08-30 | 2024-05-22
ERCOT | 27INR0261 | Tipperary Solar | SS Completed, FIS Started, No IA | Tippsol | 6498 Live Oak AEP 69kV | Schleicher | WEST | 2027-09-30 | PV | 60.16 | 2024-06-13 | 2024-09-10 | 2024-05-17
ERCOT | 27INR0272 | EMPower Odessa | SS Completed, FIS Started, No IA | EMPOWER TXMX | Tap 138 kV 1110 EDWARDS TAP - 1102 JUDKINS | Ector | WEST | 2027-07-06 | IC | 123.4 | 2024-07-22 | 2024-10-17 | 2024-07-03
ERCOT | 27INR0274 | XE Flying Kite Bess | SS Completed, FIS Started, No IA | Flying Kite BESS, LLC | tap 69kV 8672 La Pryor - 8231 Uvalde | Zavala | SOUTH | 2027-05-21 | BA | 104.73 | 2024-07-30 | 2024-10-28 | 2024-07-22
ERCOT | 27INR0279 | Red Hollow Renewable Energy BESS SLF | SS Completed, FIS Started, No IA | Red Hollow Renewable Energy LLC | Tap 345kV 1422 Bowman - 17002 Garvey Road | Archer | WEST | 2028-04-10 | BA | 308.6 | 2024-06-13 | 2024-09-10 | 2024-06-04
ERCOT | 27INR0280 | Goose Foot Energy Storage | SS Started, FIS Started, No IA | Goose Foot Energy Storage Project, LLC | New station tapping 345 kV Scurry County Switch (11318) – Tonkawa (11048) Circuit – I (approximately 8.9 miles from the Scurry County Switch) | Scurry | WEST | 2028-10-31 | BA | 305.9 | 2024-12-19 |  | 2024-12-05 | [5 empty] | FIS Request
ERCOT | 27INR0291 | Nouveau BESS | SS Completed, FIS Started, No IA | RamZ BESS, LLC | 1444 Brown Switch - 3348 Russell Gap 345 kV Line | Brown | NORTH | 2027-12-15 | BA | 256.1 | 2024-08-16 | 2024-01-08 | 2024-07-31
ERCOT | 27INR0294 | Bernice Energy Storage | SS Completed, FIS Started, No IA | Bernice Energy Storage LLC | 5135 ELMENDORF 138kV | Bexar | SOUTH | 2027-02-15 | BA | 402.8 | 2024-09-04 | 2024-12-02 | 2024-08-12
ERCOT | 27INR0296 | Sugar Land Power Plant | SS Completed, FIS Started, No IA | Imperial Power Plant, LLC | tap 138kV 44015 W A Parish - 44671 Stafford CKT 9 | Fort Bend | HOUSTON | 2027-10-01 | IC | 147.6 | 2024-08-16 | 2024-11-12 | 2024-08-05
ERCOT | 27INR0297 | Tolivar Power Plant | SS Completed, FIS Started, IA | Pecos Power Plant, LLC | Tap 138 KV 38045 IH20-38043 COWPEN | Reeves | WEST | 2027-04-15 | IC | 225.6 | 2024-07-01 | 2024-09-25 | 2024-06-14 |  |  | 2024-11-12
ERCOT | 27INR0298 | Symank Solar | SS Started, FIS Started, No IA | BT Symank Solar, LLC | Tap 69 kV 37470 TNOLSEN_0 - 37520 TNSYCAMORE0 | Bosque | NORTH | 2027-12-15 | PV | 66.55 | 2024-11-19 |  | 2024-11-11
ERCOT | 27INR0299 | Mills Prairie Solar | SS Started, FIS Started, No IA | Mills Solar, LLC | Tap 69kV #194 Purdon - #199 Brushie | Navarro | NORTH | 2027-08-31 | PV | 33 | 2024-11-19 |  | 2024-11-04
ERCOT | 27INR0300 | Mills Prairie Storage | SS Started, FIS Started, No IA | Mills Storage, LLC | Tap 69kV #194 Purdon - #199 Brushie | Navarro | NORTH | 2027-08-31 | BA | 33 | 2024-11-19 |  | 2024-11-04
ERCOT | 27INR0301 | Hondo Arroyo Solar | SS Completed, FIS Started, No IA | Hondo Creek Solar, LLC | Tap 138 kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2027-07-01 | PV | 60.4 | 2024-06-13 | 2024-09-10 | 2024-06-06
ERCOT | 27INR0303 | Rocky Point BESS | SS Completed, FIS Started, No IA | Nicole BESS | 6351 Nicole Substation 138kV | Coke | WEST | 2027-11-01 | BA | 150.96 | 2024-07-30 | 2024-10-25 | 2024-07-18
ERCOT | 27INR0304 | Fletcher BESS | SS Completed, FIS Started, No IA | Archer Energy Center, LLC | Tap 138 kV 44630 Garth – 48156 Highlands | Harris | HOUSTON | 2027-07-02 | BA | 309.92 | 2024-07-22 | 2024-10-17 | 2024-06-28
ERCOT | 27INR0305 | Kurtz Solar SLF | SS Completed, FIS Started, No IA | Kurtz Solar, LLC | Tap 69kV #8206 Charlotte - #8607 Jourdanton | Atascosa | SOUTH | 2027-07-31 | PV | 101.9 | 2024-09-04 | 2024-12-02 | 2024-08-05
ERCOT | 27INR0306 | Kurtz Storage SLF | SS Completed, FIS Started, No IA | Kurtz Storage, LLC | Tap 69kV #8206 Charlotte - #8607 Jourdanton | Atascosa | SOUTH | 2027-07-31 | BA | 0 | 2024-09-04 | 2024-12-02 | 2024-08-26
ERCOT | 27INR0307 | Beaverhead Solar SLF | SS Completed, FIS Started, No IA | Pronghorn Solar, LLC | Direct to Sub 69kv #5653 Ben Bolt. | Jim Wells | SOUTH | 2027-07-31 | PV | 61.5 | 2024-08-16 | 2024-10-07 | 2024-08-05
ERCOT | 27INR0308 | Beaverhead Storage SLF | SS Completed, FIS Started, No IA | Pronghorn Storage, LLC | Direct to Sub 69kv #5653 Ben Bolt. | Jim Wells | SOUTH | 2027-07-31 | BA | 61.5 | 2024-08-16 | 2024-10-07 | 2024-08-05
ERCOT | 27INR0313 | Spindletop Solar | SS Completed, FIS Started, No IA | Banita Creek Solar LLC | Tap Stryker [3109] - Lufkin [3117] 345 kV line | Nacogdoches | NORTH | 2027-06-30 | PV | 286.04 | 2024-07-30 | 2024-10-25 | 2024-07-26
ERCOT | 27INR0314 | Spindletop Storage | SS Completed, FIS Started, No IA | Banita Creek Solar LLC | Tap 345 kV Stryker [3109] - Lufkin [3117] | Nacogdoches | NORTH | 2027-06-30 | BA | 142.57 | 2024-07-30 | 2024-10-25 | 2024-07-26
ERCOT | 27INR0315 | Old Roman Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 23868 STILES 138 KV | Reagan | WEST | 2027-08-31 | BA | 207.34 | 2024-10-01 | 2024-11-13 | 2024-08-30
ERCOT | 27INR0316 | Avant Prairie BESS | SS Completed, FIS Started, No IA | Avant Prairie ESS LLC | Tap 345kV BIGBRNE (#3380) - JEWETT (#3390) | Freestone | NORTH | 2027-07-01 | BA | 201.72 | 2024-09-04 | 2024-12-02 | 2024-09-02
ERCOT | 27INR0317 | Edgewood BESS 1 | SS Started, FIS Started, No IA | Tempus Power management LLC | Edgewood (bus number-3181); Line break on Sulphur springs(1698) to Canton(3174) line | Van Zandt | NORTH | 2027-06-01 | BA | 100.3 | 2024-11-21 |  | 2024-11-05
ERCOT | 27INR0320 | Perseus Gas | SS Completed, FIS Started, No IA | Engie Flexible Generation NA LLC | Tap 345kV 84550 BLULACY 7A – 8455 Lon Hill 7A Ckt 2 | Nueces | COASTAL | 2028-12-31 | GT | 1056.8 | 2024-08-16 | 2024-11-13 | [6 empty] | FIS Request
ERCOT | 27INR0321 | Rock Island Generating | SS Completed, FIS Started, No IA | Kerrville Public Utility Board Public Facility Corporation | 57640 Rock Island 138 kV | Colorado | SOUTH | 2027-06-01 | IC | 121.8 | 2024-07-22 | 2024-10-08 | 2024-07-11 | [5 empty] | SFS/NtP
ERCOT | 27INR0323 | Prairie Blossom Storage | SS Started, FIS Started, No IA | Prairie Blossom Storage, LLC | 1322 Big Spring 138kV | Howard | WEST | 2027-07-01 | BA | 120 | 2024-12-19 |  | 2024-10-07 | [5 empty] | FIS Request
ERCOT | 27INR0324 | LIP GAS POWER PROJECT | SS Completed, FIS Started, No IA | LONE STAR INDUSTRIAL PARK, LLC | 1795 Monticello SES 138kV | Morris | NORTH | 2027-06-01 | IC | 186.74 | 2024-09-04 | 2024-12-02 | 2024-08-28
ERCOT | 27INR0326 | Thunderbird Valley Storage | SS Started, FIS Started, No IA | Thunderbird Valley Storage | (787) Olney Substation 138 kV | Young | WEST | 2028-07-01 | BA | 150.39 | 2024-11-19 |  | 2024-10-22
ERCOT | 27INR0330 | Wild Horse Desert Solar | SS Started, FIS Started, No IA | Wild Horse Desert Solar, LLC | Tap #8613 Big Well - #8212 Dilley Switch | Dimmit | SOUTH | 2027-07-01 | PV | 120 | 2024-12-19 |  | 2024-12-06 | [5 empty] | FIS Request
ERCOT | 27INR0331 | Wild Horse Desert Storage | SS Started, FIS Started, No IA | Wild Horse Desert Solar, LLC | Tap #8613 Big Well - #8212 Dilley Switch | Dimmit | SOUTH | 2027-07-01 | BA | 90.3 | 2024-12-19 |  | 2024-12-06 | [5 empty] | FIS Request
ERCOT | 27INR0339 | Sentinel Solar | SS Completed, FIS Started, No IA | Alamo Ranch Solar Project, LLC | tap 345kV 80219 Lobo - 5709 Fowlerton CKT2 | La Salle | SOUTH | 2029-01-24 | PV | 271.3 | 2024-10-01 | 2024-12-03 | 2024-09-18 | [5 empty] | COD
ERCOT | 27INR0341 | Tomahawk Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | Tap 138 kV 1019 Moss - 1113 Odessa Southwest | Ector | WEST | 2028-03-01 | BA | 257.25 | 2024-08-16 | 2024-11-12 | 2024-08-09
ERCOT | 27INR0343 | Plant Road BESS | SS Started, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | 1027 ODEHV 138kV | Ector | WEST | 2028-03-01 | BA | 251.32 | 2024-10-10 |  | 2024-10-02
ERCOT | 27INR0348 | Johnson Grass Solar | SS Completed, FIS Started, No IA | Johnson Grass Solar ,LLC | Tap 138kV (#11395) Navigation - (#10054) Cattlemen | Mitchell | WEST | 2028-04-19 | PV | 195.8 | 2024-10-01 | 2024-12-09 | 2024-09-30
ERCOT | 27INR0350 | Saddle Horn Station BESS SLF | SS Completed, FIS Started, No IA | Saddle Horn Station BESS LLC | tap 138kV 1650 COMANCHE_T8 - 290SHILOHC | Comanche | NORTH | 2028-04-10 | BA | 177.41 | 2024-09-04 | 2024-11-13 | 2024-08-28 | [5 empty] | COD
ERCOT | 27INR0351 | Saddle Horn Station Solar SLF | SS Completed, FIS Started, No IA | Saddle Horn Station LLC | 1650 COMANCHE_T8 - 290 SHILOHC 138 kV Line | Comanche | NORTH | 2028-04-10 | PV | 174.64 | 2024-09-04 | 2024-11-13 | 2024-09-03 | [5 empty] | COD
ERCOT | 27INR0354 | Cebocell BESS | SS Completed, FIS Started, No IA | Cebocell, LLC | 3137 BlackFork 138 KV | Smith | NORTH | 2028-06-06 | BA | 200.85 | 2024-09-04 | 2024-11-13 | 2024-08-13
ERCOT | 27INR0355 | Gardner Draw Solar | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | 59902 Sand Bluff 345kV | Glasscock | WEST | 2027-12-31 | PV | 200 | 2024-10-01 | 2024-12-30 | 2024-09-25
ERCOT | 27INR0362 | Hamlet Solar | SS Started, FIS Started, No IA | Hamlet Solar, LLC | Tap 138kV #5895 PEARSALL - #5827 MOORE | Frio | SOUTH | 2028-09-05 | PV | 204 | 2024-11-19 |  | 2024-11-04 | [5 empty] | COD
ERCOT | 27INR0363 | Hamlet Storage | SS Started, FIS Started, No IA | Hamlet Solar, LLC | Tap 138kV #5895 PEARSALL -#5827 MOORE | Frio | SOUTH | 2028-09-05 | BA | 204 | 2024-11-19 |  | 2024-11-04 | [5 empty] | COD
ERCOT | 27INR0364 | Cashel BESS | SS Started, FIS Started, No IA | TIPPSOL LLC | 6500 Live Oak AEP 138kV | Schleicher | WEST | 2027-09-30 | BA | 150.44 | 2024-10-29 |  | 2024-10-22
ERCOT | 27INR0365 | Comanche BESS | SS Started, FIS Started, No IA | ENERGOS BESS | #1440 Comanche Switching Station 345kV | Comanche | NORTH | 2027-01-16 | BA | 614.4 | 2024-12-06 |  | 2024-11-05 | [5 empty] | FIS Request
ERCOT | 27INR0366 | Gold Coin Storage | SS Started, FIS Started, No IA | Grenergy USA | Tap 138kV 1470 Newport - 616 Carter | Montague | NORTH | 2027-07-01 | BA | 72.95 | 2024-11-19 |  | 2024-10-25
ERCOT | 27INR0371 | Feather Dalea BESS | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | 59902 Sand_Bluff 345kV | Glasscock | WEST | 2027-07-02 | BA | 200 | 2024-10-01 | 2024-12-09 | 2024-09-24
ERCOT | 27INR0372 | Abeja Solar Farm | SS Started, FIS Started, No IA | Abeja Solar | Tap 345kV GODDARD7A (#8606) - TANGO7A (#8689) | Bee | SOUTH | 2027-07-01 | PV | 200.84 | 2024-12-19 |  | 2024-12-09 | [5 empty] | FIS Request
ERCOT | 27INR0373 | Velado Solar | SS Started, FIS Started, No IA | Velado Solar, LLC | Tap 138kV 78281 Dimmit - 8274 Conoco Chittam | Dimmit | SOUTH | 2028-09-14 | PV | 96 | 2024-11-19 |  | 2024-11-07 | [5 empty] | COD
ERCOT | 27INR0374 | Velado Storage | SS Started, FIS Started, No IA | Velado Storage, LLC | Tap 138kv 78281 Dimmit - 8274 Conoco Chittam. | Dimmit | SOUTH | 2028-09-14 | BA | 96 | 2024-11-19 |  | 2024-11-05 | [5 empty] | COD
ERCOT | 27INR0375 | Buck Ranch Solar | SS Started, FIS Started, No IA | Buck Ranch Solar, LLC | 5690 WEST GEORGE WEST SUB 69kV | Live Oak | SOUTH | 2028-08-02 | PV | 45 | 2024-12-19 |  | 2024-12-16 | [5 empty] | FIS Request
ERCOT | 27INR0377 | Vista Bluff Wind 1 | SS Completed, FIS Started, No IA | Terra-Gen Development Company, LLC | Double Tap 345kV Bearkat 59903 - 76000 McCamey Ckt 1 & 2 | Upton | WEST | 2027-12-31 | WT | 290.4 | 2024-09-04 | 2024-11-13 | [6 empty] | FIS Request
ERCOT | 27INR0378 | Vista Bluff Wind 2 | SS Completed, FIS Started, No IA | Terra-Gen Development Company, LLC | Double Tap 345kV Bearkat 59903 - 76000 McCamey Ckt 1 & 2 | Upton | WEST | 2027-12-31 | WT | 290.4 | 2024-09-04 | 2024-11-13 | [6 empty] | FIS Request
ERCOT | 27INR0380 | La Mancha Solar | SS Started, FIS Started, No IA | La Mancha Solar, LLC | Tap 69kV 5836 NBatesville - 5822 Leona | Zavala | SOUTH | 2028-10-10 | PV | 40.9 | 2024-11-19 |  | 2024-11-07 | [5 empty] | COD
ERCOT | 27INR0381 | La Mancha Storage | SS Started, FIS Started, No IA | La Mancha Storage, LLC | Tap 69kV 5836 NBatesville - 5822 Leona | Zavala | SOUTH | 2028-10-10 | BA | 40.9 | 2024-11-19 |  | 2024-11-07 | [5 empty] | COD
ERCOT | 27INR0383 | Windjammer Windpower | SS Completed, FIS Started, No IA | Windjammer Windpower, LLC | tap 345kV 59902 Sand Bluff Wind Farm - 59907 Bernoulli | Glasscock | WEST | 2027-12-31 | WT | 292.58 | 2024-09-10 | 2024-12-06 | [6 empty] | FIS Request
ERCOT | 27INR0384 | Straight Spur Wind | SS Started, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345 kV 23876 Clear Fork -11157 Gardenale Switch | Ector | WEST | 2027-12-01 | WT | 247.3 | 2024-12-19 |  | 2024-12-06 | [5 empty] | FIS Request
ERCOT | 27INR0385 | Straight Spur Solar | SS Started, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345 kV ClearFork (Bus #23876) to Gardenale Switch (Bus #11157) | Ector | WEST | 2027-12-01 | PV | 251.7 | 2024-11-21 |  | 2024-11-08
ERCOT | 27INR0386 | Straight Spur Storage | SS Started, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345kV ClearFork( Bus # 23876) to Gardenale Switch (Bus # 11157) | Ector | WEST | 2027-12-01 | BA | 306.2 | 2024-11-19 |  | 2024-11-08
ERCOT | 27INR0389 | Sugaree Solar | SS Completed, FIS Started, No IA | Sugaree Solar LLC | 138kV Escondido (8260) to Brackettville (8252) | Maverick | SOUTH | 2027-12-15 | PV | 251.4 | 2024-10-10 | 2024-12-09 | 2024-10-08
ERCOT | 27INR0393 | Ferdinand Grid BESS II | SS Started, FIS Started, No IA | Ambar Power Holdco LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2027-06-08 | BA | 208.12 | 2024-12-19 |  | 2024-12-03 | [5 empty] | FIS Request
ERCOT | 27INR0394 | Mariette Solar | SS Started, FIS Started, No IA | Mariette Solar LLC | Tap 345kV #1422 Bowman - #1425 Fisher Road | Wichita | WEST | 2028-12-15 | PV | 301.4 | 2024-10-29 |  | 2024-10-22
ERCOT | 27INR0397 | Zodiac Storage | SS Started, FIS Started, No IA | Grenergy USA | Tap 138 kV 8680 RGEC Rough Canyon (ROUGHCAN4A) - 8683 Comstock (COMSTOCK4A) Line | Val Verde | WEST | 2027-08-01 | BA | 125.58 | 2024-11-19 |  | 2024-11-13
ERCOT | 27INR0398 | Bravo BESS | SS Started, FIS Started, No IA | Bravo BESS LLC | Tap 345kV 80220 CENIZO7A - 80224 TIEMPO7A | Webb | SOUTH | 2027-12-08 | BA | 207.38 | 2024-11-26 |  | 2024-11-21
ERCOT | 27INR0399 | Resaca Oasis Storage | SS Started, FIS Started, No IA | Resaca Oasis Storage, LLC | # 79601 Stillman Substation 138 kV | Cameron | COASTAL | 2027-09-20 | BA | 200.7 | 2024-12-12 |  | 2024-11-22 | [5 empty] | FIS Request
ERCOT | 27INR0400 | Reforzar BESS 1 | SS Started, FIS Started, No IA | Tempus Power management LLC | POIB is AEP's new Reforzar 345kV switching station, PSSE bus number 80078 | Brooks | SOUTH | 2027-06-30 | BA | 200.6 | 2024-12-19 |  | 2024-11-05 | [5 empty] | FIS Request
ERCOT | 27INR0401 | Reforzar Bess 2 | SS Started, FIS Started, No IA | Tempus Power management LLC | 345 kV 80078 Reforzar | Brooks | SOUTH | 2027-06-30 | BA | 200.3 | 2024-12-19 |  | 2024-10-10
ERCOT | 27INR0417 | Bluebonnet Trail Solar | SS Started, FIS Started, No IA | Bluebonnet trail solar LLC | Tap 345 kV (#2427) WATMLL_W5 - (#2466) BIGONION_5 | Ellis | NORTH | 2027-12-18 | PV | 150.7 | 2024-12-19 |  | 2024-12-13 | [5 empty] | FIS Request
ERCOT | 27INR0421 | M-Bar Solar I | SS Started, FIS Started, No IA | M-Bar Energy I, LLC | 1141 Holt Switch Substation 138kV | Ector | WEST | 2027-09-01 | PV | 30.21 | 2024-12-19 |  | 2024-12-13 | [5 empty] | FIS Request
ERCOT | 27INR0422 | M-Bar BESS I | SS Started, FIS Started, No IA | M-Bar Energy I, LLC | 1141 Holt Switch Substation 138 kV | Ector | WEST | 2027-09-01 | BA | 82.1 | 2024-12-19 |  | 2024-12-13 | [5 empty] | FIS Request
ERCOT | 27INR0437 | Hondo Arroyo Storage | SS Started, FIS Started, No IA | Hondo Creek Solar, LLC | Tap 138 kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2027-07-01 | BA | 100.7 | 2024-12-19 |  | 2024-12-06 | [5 empty] | FIS Request
ERCOT | 28INR0005 | Tetris Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 345kV 80307 Del Sol 7C - 80225 Cenizo 7C | Zapata | SOUTH | 2029-07-01 | PV | 350 | 2023-07-28 | 2023-10-23 | 2023-07-21
ERCOT | 28INR0007 | Tetris Solar (Alternative POI) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 138kV 8985 San Ygnacio - 8299 Zapata | Zapata | SOUTH | 2028-07-01 | PV | 350 | 2023-07-10 | 2023-10-03 | 2023-06-30
ERCOT | 28INR0008 | Oriole Solar | SS Completed, FIS Started, No IA | Rolling Plain Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | PV | 503.91 | 2023-05-15 | 2023-08-11 | 2023-05-09
ERCOT | 28INR0009 | Oriole BES | SS Completed, FIS Started, No IA | Rolling Plains Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | BA | 150.39 | 2023-05-15 | 2023-08-11 | 2023-05-09
ERCOT | 28INR0013 | Varadero Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #68092 Liberty Station 345kV | Limestone | NORTH | 2028-04-11 | PV | 304.74 | 2023-07-10 | 2023-10-03 | 2023-07-05
ERCOT | 28INR0017 | Sitges Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 59904 Cottonwood to 23922 White River Ckt 2 | Motley | PANHANDLE | 2029-01-30 | WT | 300 | 2024-03-22 | 2024-06-19 | 2024-02-29
ERCOT | 28INR0018 | Channing Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 23906 AJ Swope Station 345kV | Oldham | PANHANDLE | 2028-12-31 | WT | 352.38 | 2023-12-20 | 2024-03-08 | 2023-11-29
ERCOT | 28INR0020 | Caracara Energy Storage Center | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 5234 Hunt Lane 138kV | Bexar | SOUTH | 2028-08-01 | BA | 203 | 2024-05-09 | 2024-08-05
ERCOT | 28INR0023 | Silverton Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 23914 Tule Canyon - 79001 Cross_W1 | Briscoe | PANHANDLE | 2029-07-01 | PV | 401.2 | 2023-12-04 | 2024-03-01
ERCOT | 28INR0024 | Padua Grid BESS Unit 3 | SS Completed, FIS Started, No IA | Padua Grid, LLC | Tap #5395 O.W Sommer 138kV | Bexar | SOUTH | 2026-03-15 | BA | 201.35 | 2024-03-22 | 2024-06-19 | 2024-03-01
ERCOT | 28INR0030 | Brela BESS LLC | SS Completed, FIS Started, No IA | Brela BESS LLC | 44040 Bailey SW 345 kV | Wharton | SOUTH | 2028-05-29 | BA | 251.3 | 2024-01-11 | 2024-04-08
ERCOT | 28INR0033 | Corvette Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #79005 Railhead Station 345kV | Carson | PANHANDLE | 2029-04-01 | WT | 1200 | 2024-02-27 | 2024-05-24
ERCOT | 28INR0037 | Bullring Wind 1 | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-07-04 | WT | 303.5 | 2024-05-09 | 2024-08-05 | 2024-04-30
ERCOT | 28INR0038 | Bullring Wind 2 | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WT | 303.8 | 2024-05-09 | 2024-08-05 | 2024-04-30
ERCOT | 28INR0039 | Bullring Wind 3 | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WT | 190.4 | 2024-05-09 | 2024-08-05 | 2024-04-29
ERCOT | 28INR0040 | Black Hawk Solar | SS Completed, FIS Started, No IA | ACE DevCo NC, LLC | San Miguel (5901) - Cruce (80079) double circuit transmission line. Requesting interconnection to both lines on the double circuit. This is a planned double circuit with ISD of 2027. | Duval | SOUTH | 2028-05-15 | PV | 251.34 | 2024-02-27 | 2024-05-24
ERCOT | 28INR0048 | Findley BESS | SS Completed, FIS Started, No IA | Gransolar Texas Sixteen, LLC | #107 Prairie Hill 69 kV | Limestone | NORTH | 2028-01-01 | BA | 51.74 | 2024-02-07 | 2024-04-30 | 2024-01-16
ERCOT | 28INR0057 | Windecker | SS Completed, FIS Started, No IA | Windecker Energy LLC | 10058 Catclaw Switch 138kV | Upton | WEST | 2027-09-15 | WT | 419.7 | 2024-03-29 | 2024-06-19 | 2024-03-14
ERCOT | 28INR0059 | Verily Solar (FKA Cuello De Cuero Solar) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 80078 Reforzar Switch Station 345kV | Brooks | SOUTH | 2028-07-01 | PV | 250 | 2024-03-22 | 2024-06-19 | 2024-03-06
ERCOT | 28INR0061 | Sunrose Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Sunrose Renewable Energy LLC | Tap 138kV #44740 WALLIS - #44700 GEBHRT | Austin | SOUTH | 2027-12-31 | PV | 300.88 | 2024-04-09 | 2024-07-05 | 2024-03-29
ERCOT | 28INR0063 | Bluefox Solar 2 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2030-01-17 | PV | 401.8 | 2024-03-22 | 2024-06-19 | 2024-02-21
ERCOT | 28INR0064 | Bluefox Solar 3 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2030-04-18 | PV | 201.8 | 2024-03-22 | 2024-06-19 | 2024-02-21
ERCOT | 28INR0066 | Sunrose Renewable Energy Storage SLF | SS Completed, FIS Started, No IA | Sunrose Renewable Energy LLC | Tap 138kV 44740 WALLIS - 44700 GEBHRT | Austin | SOUTH | 2027-12-31 | BA | 0 | 2024-04-15 | 2024-07-05 | 2024-04-12
ERCOT | 28INR0068 | Alpujarra Solar | SS Completed, FIS Started, No IA | Greening USA Corp. | 5521 GALOW 138 KV | Wharton | SOUTH | 2028-05-01 | PV | 112.5 | 2024-09-04 | 2024-11-27 | 2024-08-12
ERCOT | 28INR0072 | Mirando Valley Wind | SS Completed, FIS Started, No IA | ACE DevCo NC LLC | Tap 345kV 80220 Cenizo - 80079 Cruce Ckt-1 | Jim Hogg | SOUTH | 2028-07-06 | WT | 351 | 2024-08-16 | 2024-11-12 | 2024-06-05
ERCOT | 28INR0073 | Daystar Solar | SS Completed, FIS Started, No IA | Choate Solar, LLC | 5728 Choate 138kV | Karnes | SOUTH | 2028-03-15 | PV | 150 | 2024-04-15 | 2024-07-05 | 2024-04-09
ERCOT | 28INR0074 | Massey Storage | SS Completed, FIS Started, No IA | Massey Storage, LLC | Tap 138 kV 41690 Hopson - 40012 Cedar Bayou | Harris | HOUSTON | 2028-01-03 | BA | 102.86 | 2024-07-30 | 2024-10-25 | 2024-07-23
ERCOT | 28INR0075 | Wild Paw Storage | SS Completed, FIS Started, No IA | Wild Paw Energy Center, LLC | Tap 345kV 3124 Trinidad - 3130 Forest Grove | Henderson | NORTH | 2028-09-30 | BA | 313.2 | 2024-05-09 | 2024-08-05 | 2024-05-07
ERCOT | 28INR0080 | Turtle Rock Storage | SS Completed, FIS Started, No IA | Turtle Rock Energy Center, LLC | Tap 138 kV 13501 Clayhill to 13681 Reed | Freestone | NORTH | 2028-07-02 | BA | 135.59 | 2024-05-09 | 2024-08-05 | 2024-05-08
ERCOT | 28INR0081 | Villarreal Solar SLF | SS Completed, FIS Started, No IA | Orion US Land Holding Co LLC | 80439 LAQUINTA4A 138kV | Webb | SOUTH | 2028-08-30 | PV | 152.5 | 2024-05-20 | 2024-08-14 | 2024-05-02
ERCOT | 28INR0083 | Villarreal BESS SLF | SS Completed, FIS Started, No IA | Orion US Land Holding Co LLC | LAQUINTA4A (Bus # 80439) | Webb | SOUTH | 2028-08-30 | BA | 0 | 2024-05-09 | 2024-08-05 | 2024-05-02
ERCOT | 28INR0088 | Red Hollow Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Red Hollow Renewable Energy LLC | Tap 345kV (Bus# 1422) Bowman - (Bus# 17002) Garvey Road | Archer | WEST | 2028-04-10 | PV | 308.6 | 2024-07-01 | 2024-10-04 | 2024-06-04
ERCOT | 28INR0089 | EmberYork | SS Completed, FIS Started, No IA | EmberYork Energy Center | TAP 138kV WALLIS 44740 - GERBHRT 44700 | Austin | SOUTH | 2028-01-01 | GT | 900 |  | 2024-08-29 | [6 empty] | FIS Request
ERCOT | 28INR0094 | Pham BESS | SS Completed, FIS Started, No IA | ASB1, LLC | Tap 138kV 3281 TENNCLNY_8 - 3284 BETO_8 | Anderson | NORTH | 2028-04-17 | BA | 130.29 | 2024-06-13 | 2024-09-10
ERCOT | 28INR0095 | Starlit Pasture Storage | SS Completed, FIS Started, No IA | Starlit Pasture Energy Center, LLC | 7574 Chappell Hill 138 KV | Washington | SOUTH | 2029-09-30 | BA | 208.8 | 2024-08-16 | 2024-11-12 | 2024-06-24
ERCOT | 28INR0097 | Catamount Storage | SS Completed, FIS Started, No IA | TOCE TX BESS 3, LLC | Tap 345kV 46100 North Belt - 40850 Jordan CKT 99 | Harris | HOUSTON | 2028-06-01 | BA | 515.44 | 2024-09-04 | 2024-11-27 | 2024-08-21
ERCOT | 28INR0101 | Vazlon Solar SLF | SS Completed, FIS Started, No IA | Vazlon Energy LLC | 8619 Encinal - 8627 Lemay Box Bay 138kV line | La Salle | SOUTH | 2028-06-30 | PV | 211.41 | 2024-10-01 | 2024-12-16 | 2024-09-06
ERCOT | 28INR0104 | Vazlon BESS SLF | SS Completed, FIS Started, No IA | Vazlon Energy LLC | 8619 Encinal - 8627 Lemay Box Bay 138kV line | La Salle | SOUTH | 2028-06-30 | BA | 0 | 2024-10-01 | 2024-12-16 | 2024-09-06
ERCOT | 28INR0105 | Vast Sands Power I | SS Completed, FIS Started, No IA | Permian Power I LLC | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | Ward | WEST | 2028-06-01 | GT | 440 | 2024-07-22 | 2024-10-08
ERCOT | 28INR0109 | Vast Sands Power II | SS Completed, FIS Started, No IA | Permian Power II LLC | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | Ward | WEST | 2028-08-01 | GT | 440 | 2024-07-22 | 2024-10-08 | 2024-07-03
ERCOT | 28INR0113 | Axis Ridge Wind | SS Started, FIS Started, No IA | Axis Ridge Wind, LLC | Tap 345kV 60709 Oersted - 60616 Edison | Sutton | WEST | 2029-01-31 | WT | 750.05 | 2024-11-19 |  | 2024-11-07 | [5 empty] | COD
ERCOT | 28INR0116 | Salazar BESS | SS Completed, FIS Started, No IA | Salazar Energy Storage LLC | 2068 Rosen Heights 138kV | Tarrant | NORTH | 2028-07-11 | BA | 127.82 | 2024-10-01 | 2024-12-09 | 2024-08-27
ERCOT | 28INR0117 | North Leona Solar | SS Completed, FIS Started, No IA | Orion US Land Holding Co LLC | Tap 138 KV 8212 Dilly - 5866 Palo Duro | Frio | SOUTH | 2028-08-01 | PV | 204.9 | 2024-07-30 | 2024-10-27 | 2024-07-26
ERCOT | 28INR0118 | Copperleaf Energy Storage | SS Started, FIS Started, No IA | Copperleaf Energy Storage, LLC | 1426 FISHER ROAD SWITCH 138 kV | Wichita | WEST | 2028-12-01 | BA | 167.2 | 2024-11-19 |  | 2024-10-16
ERCOT | 28INR0119 | Rabbit Hollow Energy Storage | SS Started, FIS Started, No IA | Diamondback Energy Storage, LLC | 1190 Barber Lake Switch 138kV | Mitchell | WEST | 2028-12-01 | BA | 341.8 | 2024-12-19 |  | 2024-12-01 | [5 empty] | FIS Request
ERCOT | 28INR0120 | North Leona BESS | SS Completed, FIS Started, No IA | Orion US Land Holding Co LLC | Tap 138 KV 8212 Dilly - 5866 Palo Duro | Frio | SOUTH | 2028-08-01 | BA | 102.2 | 2024-08-16 | 2024-10-27 | 2024-08-01
ERCOT | 28INR0124 | Silverbell Storage | SS Completed, FIS Started, No IA | Silverbell Energy Center, LLC | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | Red River | NORTH | 2028-09-30 | BA | 130.57 | 2024-08-16 | 2024-10-07 | 2024-07-31
ERCOT | 28INR0125 | Silverbell Solar | SS Completed, FIS Started, No IA | Silverbell Energy Center, LLC | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | Red River | NORTH | 2028-09-30 | PV | 125.63 | 2024-08-16 | 2024-10-07 | 2024-07-31
ERCOT | 28INR0127 | Half Moon Solar | SS Started, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #80231 Pronto 345kV | Starr | SOUTH | 2029-07-01 | PV | 512.5 |  |  | 2024-12-23 | [5 empty] | FIS Request
ERCOT | 28INR0132 | River Boat Solar | SS Completed, FIS Started, No IA | Champion Creek Solar, LLC | Tap 345 kV Bus # 10053 Cattlemen 5 - Bus #76030 Gasconades Creek | Mitchell | WEST | 2028-09-25 | PV | 502.2 | 2024-09-04 | 2024-12-02 | 2024-08-22 | [5 empty] | MW Size
ERCOT | 28INR0133 | River Boat Storage | SS Completed, FIS Started, No IA | Champion Creek Storage, LLC | Tap 345 kV Bus # 10053 Cattlemen 5 - Bus #76030 Gasconades Creek | Mitchell | WEST | 2028-09-25 | BA | 207.02 | 2024-10-01 | 2024-12-02 | 2024-09-24 | [5 empty] | MW Size
ERCOT | 28INR0134 | Salt-Lick Storage | SS Completed, FIS Started, No IA | Salt-Lick Storage, LLC | 11198 Elcor_8 138 KV | Culberson | WEST | 2028-06-01 | BA | 155.3 | 2024-10-10 | 2024-12-09 | 2024-10-07
ERCOT | 28INR0147 | Fallstone Solar | SS Started, FIS Started, No IA | Fallstone Solar, LLC | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | Falls | NORTH | 2028-06-14 | PV | 60.35 | 2024-12-19 |  | 2024-12-04 | [5 empty] | FIS Request
ERCOT | 28INR0148 | Sonora High Noon BESS | SS Completed, FIS Started, No IA | Sonora High Noon, LLC | 60412 CARVER 138kV | Sutton | WEST | 2028-07-01 | BA | 204.08 | 2024-09-04 | 2024-11-27 | 2024-09-03
ERCOT | 28INR0149 | Fallstone Storage | SS Started, FIS Started, No IA | Fallstone Solar, LLC | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | Falls | NORTH | 2028-06-14 | BA | 1.71 | 2024-12-19 |  | 2024-12-04 | [5 empty] | FIS Request
ERCOT | 28INR0154 | Callisto 1C Energy Center | SS Completed, FIS Started, No IA | Tempus Power management LLC | #47150 HOC 138kV | Harris | HOUSTON | 2026-06-01 | BA | 103.8 | 2024-09-10 | 2024-12-03 | 2024-09-09 | [5 empty] | MW Size
ERCOT | 28INR0155 | Coke BESS | SS Completed, FIS Started, No IA | Coke ESS, LLC | 76090 Divide Switchyard 345kV | Coke | WEST | 2028-04-10 | BA | 220.3 | 2024-10-01 | 2024-12-09 | 2024-09-27
ERCOT | 28INR0164 | Savanna Prairie Solar | SS Started, FIS Started, No IA | Savanna Prairie Solar, LLC | Tap 345 kV Bus # 60404 Solstice7A - Bus # 76002 L_Bakers5_1Y | Pecos | WEST | 2028-06-01 | PV | 354.8 | 2024-10-29 |  | 2024-10-04
ERCOT | 28INR0165 | Savanna Prairie Storage | SS Started, FIS Started, No IA | Savanna Prairie Storage, LLC | Tap 345 kV Bus # 60404 Solstice7A - Bus # 76002 L_Bakers5_1Y | Pecos | WEST | 2028-06-01 | BA | 114.43 | 2024-10-29 |  | 2024-10-04
ERCOT | 28INR0168 | Guajillo Wind | SS Started, FIS Started, No IA | Guajillo Wind LLC | Tap 345 kV 80079 Cruce - 5901 San Miguel | Duval | SOUTH | 2028-09-01 | WT | 204 | 2024-12-19 |  | 2024-12-10 | [5 empty] | FIS Request
ERCOT | 28INR0170 | Kiskadee Trail Solar | SS Completed, FIS Started, No IA | Kiskadee Trail Solar, LLC | Tap 138kV 8005 Carrizo Springs - 8006 Crystal City | Dimmit | SOUTH | 2028-03-01 | PV | 406 | 2024-10-08 | 2024-12-18 | 2024-10-08
ERCOT | 28INR0171 | Kiskadee Trail Storage | SS Completed, FIS Started, No IA | Kiskadee Trail Storage, LLC | Tap 138kV 8005 Carrizo Springs - 8006 Crystal City | Dimmit | SOUTH | 2028-03-01 | BA | 406 | 2024-10-01 | 2024-12-18 | 2024-09-20
ERCOT | 28INR0176 | Gail Mountain Solar | SS Started, FIS Started, No IA | Gail Mountain Solar, LLC | Tap 345kV 59905 Faraday - 59900 Long Draw | Borden | WEST | 2028-08-25 | PV | 244.4 | 2024-10-29 |  | 2024-10-11
ERCOT | 28INR0177 | Sisters Solar II | SS Started, FIS Started, No IA | Oberon Solar III, LLC | tap 345kV 11010 Wolf Switching Station - 10012 Meteor | Ector | WEST | 2028-12-15 | PV | 205.54 | 2024-10-21 |  | 2024-10-18 | [5 empty] | MW Size
ERCOT | 28INR0178 | Shoe Bar Solar | SS Started, FIS Started, No IA | Oberon Solar V, LLC | Tap 138kV 11128 Shin Oak POD - 18663 Raceway Switch | Winkler | WEST | 2028-12-15 | PV | 205.53 | 2024-10-29 |  | 2024-10-21 | [5 empty] | MW Size
ERCOT | 28INR0179 | Sunburst Solar | SS Started, FIS Started, No IA | Indigo Solar, LLC | Tap LONHILL (Bus#8455) to KATOEN (Bus#8579). | San Patricio | COASTAL | 2028-06-30 | PV | 301.6 | 2024-10-10 |  | 2024-10-23
ERCOT | 28INR0181 | Sunburst BESS | SS Started, FIS Started, No IA | Indigo Solar, LLC | Tap 345kV 8455 LONHILL - 8579 KATOEN | San Patricio | COASTAL | 2028-06-30 | BA | 256.3 | 2024-10-10 |  | 2024-10-23
ERCOT | 28INR0186 | Saddlehorn Energy Storage | SS Started, FIS Started, No IA | Saddlehorn, LLC | 7287 Bellville North 138kV | Austin | SOUTH | 2028-11-01 | BA | 256.8 | 2024-11-26 |  | 2024-12-03 | [5 empty] | FIS Request
ERCOT | 28INR0194 | Tapaderos Solar | SS Started, FIS Started, No IA | Tapaderos Solar, LLC | TAP 345kV #1435 Long Creek - #1430 Graham SES | Young | WEST | 2028-06-01 | PV | 303.4 | 2024-11-19 |  | 2024-10-16
ERCOT | 28INR0196 | Tapaderos Storage | SS Started, FIS Started, No IA | Tapaderos Storage, LLC | TAP 345kV #1430 GRAHAM SES - #1435 LONG CREEK | Young | WEST | 2028-06-01 | BA | 207.09 | 2024-11-19 |  | 2024-10-16
ERCOT | 28INR0198 | Winters Glow Solar | SS Started, FIS Started, No IA | Winters Glow Solar, LLC | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | Runnels | WEST | 2028-06-01 | PV | 252.94 | 2024-10-29 |  | 2024-10-16
ERCOT | 28INR0199 | Winters Glow Storage | SS Started, FIS Started, No IA | Winters Glow Storage, LLC | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | Runnels | WEST | 2028-06-01 | BA | 155.29 | 2024-10-29 |  | 2024-10-21
ERCOT | 28INR0202 | Fluvanna Max BESS | SS Started, FIS Started, No IA | Fluvanna Max Solar LLC | 11305-DERMOTT-345 kV A 345kV gen-tie line, approximately 5.5 miles long, will connect the Fluvanna Max BESS (Co-located with 29INR0077) project to the Dermott Substation (Scurry County), terminating at an assigned bay within the Dermott Substation. | Scurry | WEST | 2028-09-28 | BA | 50 | 2024-12-19 |  | 2024-11-11 | [5 empty] | FIS Request
ERCOT | 28INR0206 | Wagon Timber Solar | SS Started, FIS Started, No IA | Wagon Timber Solar, LLC | 6110 Munday East 138kV | Knox | WEST | 2028-06-01 | PV | 172.1 | 2024-12-19 |  | 2024-11-15 | [5 empty] | FIS Request
ERCOT | 28INR0239 | Tierra Alta Storage SLF | SS Started, FIS Started, No IA | ET Fuels US Inc. | Tap 138 kV 6490 Santiago – 6015 Maddux | Schleicher | WEST | 2028-10-01 | BA | 204.82 | 2024-12-19 |  | 2024-11-25 | [5 empty] | FIS Request
ERCOT | 28INR0245 | Hittson Creek Solar | SS Started, FIS Started, No IA | 174 Power Global Properties | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | Callahan | WEST | 2028-12-15 | PV | 404 | 2024-12-19 |  | 2024-12-18 | [5 empty] | FIS Request
ERCOT | 28INR0246 | Hittson Creek BESS | SS Started, FIS Started, No IA | 174 Power Global Properties | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | Callahan | WEST | 2028-12-15 | BA | 206 | 2024-12-19 |  | 2024-12-18 | [5 empty] | FIS Request
ERCOT | 29INR0003 | Aurelius Solar | SS Completed, FIS Started, No IA | IP Roman, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-03-31 | PV | 1124.24 | 2023-07-18 | 2023-10-15 | 2023-07-13
ERCOT | 29INR0004 | Aurelius Wind | SS Completed, FIS Started, No IA | IP Roman, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-03-31 | WT | 623 | 2023-08-14 | 2023-11-06 | 2023-08-07
ERCOT | 29INR0009 | Aurelius 2 Solar | SS Completed, FIS Started, No IA | IP Roman II, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2028-09-30 | PV | 445.4 | 2023-12-04 | 2024-03-01 | 2023-11-30
ERCOT | 29INR0010 | Aurelius 2 Wind | SS Completed, FIS Started, No IA | IP Roman II, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2028-09-30 | WT | 623 | 2023-12-04 | 2024-03-01 | 2023-11-30
ERCOT | 29INR0011 | Aurelius 3 Solar | SS Completed, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2029-03-31 | PV | 445.4 | 2023-12-04 | 2024-03-01 | 2023-11-30
ERCOT | 29INR0012 | Aurelius 3 Wind | SS Completed, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2029-03-31 | WT | 623 | 2023-12-04 | 2024-03-01 | 2023-11-30
ERCOT | 29INR0013 | Queen Mesa Solar II | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 76000 North McCamey 345kV | Crane | WEST | 2029-07-01 | PV | 300 | 2024-06-13 | 2024-09-10 | 2024-06-13
ERCOT | 29INR0015 | Funston Solar (Alternative POI Lone Star) | SS Completed, FIS Not Started, IA | Funston Solar LLC | tap 345 kV 68000 West Shackelford – 68004 Phantom Hill Circuit 2 | Jones | WEST | 2027-07-01 | PV | 351.4 | 2024-02-27 | 2024-05-26 |  |  | Yes | 2024-10-23
ERCOT | 29INR0017 | Big Rooter East Solar SLF | SS Completed, FIS Started, No IA | Big Rooter East, LLC | 39950 TNP One Plant 345 kV | Robertson | NORTH | 2029-01-01 | PV | 554.94 | 2024-03-22 | 2024-06-19 | 2024-03-22
ERCOT | 29INR0018 | Big Rooter East Storage SLF | SS Completed, FIS Started, No IA | Big Rooter East, LLC | 39950 TNP One Plant 345 kV | Robertson | NORTH | 2029-01-01 | BA | 0 | 2024-03-22 | 2024-06-19 | 2024-03-22
ERCOT | 29INR0019 | Infinium Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | #1058 Longshore_5 345kV | Howard | WEST | 2029-07-01 | PV | 401.6 | 2024-08-16 | 2024-10-07 | 2024-07-18
ERCOT | 29INR0025 | Skyrider Wind | SS Started, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 138kV #38365 TNPINION | Pecos | WEST | 2028-07-01 | WT | 365 | 2024-11-19 |  | 2024-10-29
ERCOT | 29INR0026 | Skeeter Solar | SS Completed, FIS Started, No IA | Mesquite Solar, LLC | 345 kV SWEETWATER EAST (11420) - LONG CREEK (1435) | Jones | WEST | 2028-12-02 | PV | 251 | 2024-06-03 | 2024-08-29 | 2024-05-30
ERCOT | 29INR0040 | Gusty Windpower | SS Completed, FIS Started, No IA | Ballenger Windpower, LLC | Tap 345kV 59903 Bearkat - 1058 Longshore_5 | Glasscock | WEST | 2027-12-31 | WT | 208.5 | 2024-07-30 | 2024-10-27
ERCOT | 29INR0041 | Homestead Power | SS Completed, FIS Started, No IA | Homestead Power LLC | 138 kV New Bremen #7271 | Austin | SOUTH | 2029-12-15 | GT | 260.3 | 2024-07-30 | 2024-10-27 | 2024-07-29
ERCOT | 29INR0045 | Veco Ranch Solar SLF | SS Completed, FIS Started, No IA | Orion US Land Holding Co LLC | 8283 ASHERTON4A 138kV | Webb | SOUTH | 2029-08-30 | PV | 152.5 | 2024-07-30 | 2024-10-27 | 2024-07-26
ERCOT | 29INR0046 | Veco Ranch BESS SLF | SS Completed, FIS Started, No IA | Orion US Land Holding Co LLC | 8283 ASHERTON4A 138kV | Webb | SOUTH | 2029-08-30 | BA | 0 | 2024-07-30 | 2024-10-27 | 2024-07-26
ERCOT | 29INR0048 | Rippling Curve Peaking Power | SS Completed, FIS Started, No IA | OxyVinyls LP | 41580 TIDAL__X06B8 138kV | Harris | HOUSTON | 2029-01-01 | GT | 208 | 2024-09-04 | 2024-11-27 | 2024-08-20
ERCOT | 29INR0050 | Amphion Solar | SS Started, FIS Started, No IA | Blue Heron Solar, LLC | TAP 345KV (#5709) FLOWERTON - (#5901) SAN MIGUEL LINE Ckt FOWRTN_SMIGL2 | Atascosa | SOUTH | 2028-11-01 | PV | 507.57 | 2024-10-10 |  | 2024-10-10
ERCOT | 29INR0077 | Fluvanna Max Solar | SS Started, FIS Started, No IA | Fluvanna Max Solar LLC | 11305 DERMOTT SUBSTATION 345 kV A 345kV gen-tie line, approximately 5.5 miles in length, will connect the Fluvanna Max Solar project to the Dermott Substation (Scurry County), terminating at an assigned bay within the Dermott Substation. | Scurry | WEST | 2028-09-28 | PV | 150 | 2024-12-19 |  | 2024-11-11 | [5 empty] | FIS Request
ERCOT | 29INR0083 | Denver City - Mustang - Gas | SS Started, FIS Started, No IA | Golden Spread Electric Cooperative, Inc. | 23876 CLEARFRK_5 345kV | Yoakum | WEST | 2029-05-31 | GT | 504 | 2024-12-19 |  | 2024-12-17 | [5 empty] | FIS Request
ERCOT | 30INR0002 | Southeast Oklahoma Pumped Storage | SS Completed, FIS Started, No IA | Apex Energy Solutions, LLC | 1692 Paris Switch 345kV | Lamar | NORTH | 2030-01-01 | EN | 1232 | 2022-08-05 | 2022-11-01
ERCOT | 30INR0004 | Hecate Energy Arkansas Wind | SS Completed, FIS Started, No IA | Hecate Energy Gulf Wind LLC | 8659 Naismith 345kV | San Patricio | COASTAL | 2030-06-01 | WT | 1029.39 | 2023-06-28 | 2023-09-22
ERCOT | 30INR0005 | Woodland Energy Storage | SS Completed, FIS Started, No IA | Woodland Energy Storage, LLC | 68040 Kopperl Substation 345kV | Bosque | NORTH | 2030-10-01 | BA | 207.6 | 2023-12-18 | 2024-03-15 | 2023-10-23
ERCOT | 12INR0059b | HOVEY (Barilla Solar 1B) |  | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2024-12-31 | PV | 7.4 | [5 empty] | 2013-12-26 | 2015-09-14
ERCOT | 22INR0590 | Muenster BESS |  | Regis Development I, LLC | Station Name (TDSP Station Code): Muenster Load/Load Transformer Name: Muenster1 PTI BUS number: 695 Voltage in kV (Transmission Level): 138kV | Cooke | NORTH | 2025-03-04 | BA | 9.9 | [5 empty] | 2023-07-12 | 2024-11-07
ERCOT | 22INR0596 | Grizzly Ridge BESS SLF |  | Grizzly Ridge Solar LLC | Pottsville Switching Substation (Bus# 178) | Hamilton | NORTH | 2023-05-31 | BA | 0 | [5 empty] | 2021-10-18
ERCOT | 23INR0483 | Rio Nogales CT1 Rotor Replacement |  | CPS Energy | Rio Nogales Substation 5362 RIONOG 345kV | Guadalupe | SOUTH | 2023-06-08 | CC | 3.1 | [5 empty] | 2023-01-20 | 2023-04-27
ERCOT | 23INR0499 | Laureles BESS |  | Regis Laureles LLC | Station Name (TDSP Station Code) LAURELES; Load/Load Transformer Name LD01; PTI BUS number 5756; Voltage in kV (Transmission Level) 138kV | Cameron | COASTAL | 2025-06-21 | BA | 9.8 | [5 empty] | 2023-02-16
ERCOT | 23INR0500 | Fort Mason BESS |  | Regis Mason LLC | Station Name (TDSP Station Code): FORTMA; Load/Load Transformer Name: T1-FM140; PTI BUS number: 76390; Voltage in kV (Transmission Level): 138kV Transformer: 3x 4000kVA 800VAC Δ - 12.47kVA Υ | Mason | SOUTH | 2025-03-04 | BA | 9.8 | [5 empty] | 2023-01-10 | 2024-11-07
ERCOT | 23INR0523 | Damon BESS |  | Baccharis Storage LLC | Station Name: DA Load/Load Transformer Name: TR1 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV | Brazoria | COASTAL | 2025-02-03 | BA | 4.98 | [5 empty] | 2022-10-18 | 2024-11-04 |  | COD
ERCOT | 23INR0529 | Torrecillas BESS |  | Torrecillas Interconnect, LLC | 161257 Torrecillas 345kV Station code: TORR | Webb | SOUTH | 2025-04-21 | BA | 9.9 | [5 empty] | 2015-01-30 |  |  | COD
ERCOT | 23INR0552 | Milton BESS |  | Regis Milton LLC | Station Name (TSP Station Code): MILTON; Load/Load Transformer Name: LD_1; PTI Bus Number: 78583; Voltage in kV (Transmission Level): 138 kV | Karnes | SOUTH | 2025-04-15 | BA | 9.9 | [5 empty] | 2023-09-07
ERCOT | 23INR0556 | IEP Orchard BESS |  | IEP Tejas Verde LLC | Station Name (TDSP Station Code): OR Load/Load Transformer Name :TR1 PTI BUS number: 44541 Voltage in kV (Transmission Level): 138 kV Project Size: 9.99 MW battery energy storage (BESS) system; 50 MWh connecting on CNP 34.5kV Distribution System. | Fort Bend | HOUSTON | 2025-02-28 | BA | 9.99 | [5 empty] | 2023-08-09 | 2024-12-06
ERCOT | 23INR0603 | Damon BESS 2 |  | IEP Tejas Verde LLC | 9.99 MW 50 MWh battery energy storage project connecting at 12.47kV Damon (DA) substation. Station Name (TDSP Station Code): DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV | Brazoria | COASTAL | 2025-08-12 | BA | 9.99 | [5 empty] | 2023-10-06
ERCOT | 23INR0617 | Hidden Lakes BESS |  | SBESS TX 6 LLC | Station Name: HDNLAKES PTI Bus#: 38900 Load XFMR Name: HDLAKE_2 Transmission Level Voltage: 138 kV | Galveston | HOUSTON | 2025-06-06 | BA | 9.9 | [5 empty] | 2024-02-07
ERCOT | 23INR0618 | Farmersville West BESS 2 |  | SBESS TX 7 LLC | Station Name: Farmersville West TNP Substation Station Code: FRMRSVLW PTI Bus#: 37291 Load Transformer Name: FRMVW_3 Transmission Level Voltage: 138 kV | Collin | NORTH | 2024-11-30 | BA | 9.9 | [5 empty] | 2024-04-05 | 2024-10-30
ERCOT | 23INR0619 | Junction North BESS |  | SBESS TX 5 LLC | Station Name: New Junction Station Code: P_NEWJUNC_1_ PTI Bus#: 70600 Load XFMR Name: PEC Load ID: 1 << The planning cases do not have "Load Names" only a two character Load ID Transmission Level Voltage: 69 kV | Kimble | SOUTH | 2024-11-30 | BA | 9.9 | [5 empty] | 2023-09-05 | 2024-10-30
ERCOT | 23INR0688 | Midway BESS |  | Midway BESS Station LLC | Station Code: MIDWY Station name: Midway Load/Load Transformer Name: LDXFMR1 PTI Bus number: 1253 Transmission level kV: 138kV | Ector | WEST | 2025-03-07 | BA | 9.95 | [5 empty] | 2022-06-13 | 2023-12-15
ERCOT | 23INR0807 | Mayberry II BESS |  | SMT Mission II LLC | Bus Name: Mayberry, Load name: 1, Bus number: 8109, Voltage: 138kV | Hidalgo | SOUTH | 2025-01-20 | BA | 9.95 | [5 empty] | 2023-05-17 | 2024-11-14 |  | COD
ERCOT | 24INR0499 | Medina Lake BESS |  | Regis Medina Lake LLC | Station Name (TDSP Station Code) MEDILA; Load/Load Transformer Name T2; PTI BUS number 7432; Voltage in kV (Transmission Level) 138kV | Bandera | SOUTH | 2024-12-31 | BA | 9.8 | [5 empty] | 2023-01-18
ERCOT | 24INR0545 | Spencer BESS |  | Harris Spencer BESS, LLC | Station Name: TSP STATION CODE = SP Load Transformer name = TR1 Bus#: PTI Bus number = 43271 Voltage: Transmission level kV = 138 KV | Harris | HOUSTON | 2025-05-01 | BA | 9.9 | [5 empty] | 2023-10-31
ERCOT | 24INR0546 | Crosby BESS |  | Harris Centerpoint BESS LLC | Station Name: TSP STATION CODE = CS Load Transformer name = TR3 Bus#: PTI Bus number = 40390 Voltage: Transmission level kV = 138 KV | Harris | HOUSTON | 2025-02-17 | BA | 9.9 | [5 empty] | 2023-10-31 |  |  | COD
ERCOT | 24INR0547 | Angleton BESS |  | Brazoria Winmill BESS, LLC | STATION NAME (TSP STATION CODE): Angleton (AE) LOAD/LOAD TRANSFORMER NAME: TR1 PTI BUS NUMBER: 42111 VOLTAGE (TRANSMISSION LEVEL): 138KV | Brazoria | COASTAL | 2025-02-13 | BA | 9.9 | [5 empty] | 2023-10-31
ERCOT | 24INR0560 | Pearsall BESS |  | Sunset Ridge Energy Center, LLC | Station Name: PEARSALL Load Transformer name: PRSAL_LD1 Bus#: PTI Bus number: 5895 Transmission Voltage: 138kV | Frio | SOUTH | 2024-12-30 | BA | 9.95 | [5 empty] | 2024-07-30 | 2024-12-31
ERCOT | 24INR0580 | Texas Bluebonnet Solar |  | Texas Bluebonnet Solar Partners, LLC | 3370 McGuffey POD 138 kV | McLennan | NORTH | 2025-01-11 | PV | 9.72 | [5 empty] | 2023-08-28 | 2024-09-06 |  | COD
ERCOT | 24INR0591 | Citrus City BESS |  | SBESS TX10 LLC | Citrus City Substation Transformer # 2 Station Code - CITRUSCY Load Name - LD02 PTI Bus Number - 80123 Transmission Voltage - 138 | Hidalgo | SOUTH | 2025-06-17 | BA | 9.9 | [5 empty] | 2024-02-02
ERCOT | 24INR0592 | Rio Grande City BESS 2 |  | SBESS TX12 LLC | Station Code - RIO_GRAN Load Name - 69_12_2 PTI Bus Number - 8797 Transformer Voltage - 69 | Starr | SOUTH | 2025-06-17 | BA | 9.9 | [5 empty] | 2024-02-02
ERCOT | 24INR0593 | Falfur BESS |  | Regis Falfurrias, LLC | Connected to AEP 12.47kV Station Name (TDSP Station Code): FALFUR Load/Load Transformer Name: R1 PTI Bus Number: #8510 Voltage in kV (Transmission Level): 138kV | Brooks | SOUTH | 2025-05-29 | BA | 9.8 | [5 empty] | 2024-06-21 |  |  | COD
ERCOT | 24INR0594 | Hidden Valley BESS |  | Regis Hidden Valley, LLC | Station Name (TSP Station Code): Hidden Valley (HV) Load/Load Transformer Name: TR4 PTI Bus Number: 45861 Voltage in kV (Transmission Level): 138 kV | Harris | HOUSTON | 2025-04-15 | BA | 9.9 | [5 empty] | 2023-09-20 |  |  | COD
ERCOT | 24INR0595 | Gears BESS |  | Regis Gears-Harris LLC | Station Name (TSP Station Code): Gears (GZ) Load/Load Transformer Name: TR1 PTI Bus Number: 45781 Voltage in kV (Transmission Level): 138 kV | Harris | HOUSTON | 2025-02-15 | BA | 9.9 | [5 empty] | 2023-09-20
ERCOT | 24INR0596 | Hearn Road BESS |  | Regis Hearn Road, LLC | Station Name (TSP Station Code): Hearn Road(5021) Load/Load Transformer Name: R2 PTI Bus Number: 8860 Voltage in kV (Transmission Level): 69kV | Nueces | COASTAL | 2025-03-15 | BA | 9.9 | [8 empty] | COD
ERCOT | 24INR0597 | Pirate BESS |  | Regis Sinton-Pirate, LLC | Station Name (TSP Station Code): Pirate (5218) Load/Load Transformer Name: R1 PTI Bus Number: 8652 Voltage in kV (Transmission Level): 69 kV | San Patricio | COASTAL | 2025-05-29 | BA | 9.8 | [8 empty] | COD
ERCOT | 24INR0599 | Mustang Bayou BESS |  | Maverick Clean Energy Center | STATION NAME (TSP STATION CODE) = MU LOAD/LOAD TRANSFORMER NAME = TR2 PTI BUS NUMBER = 42960 VOLTAGE (TRANSMISSION LEVEL) = 138KV | Brazoria | COASTAL | 2025-03-04 | BA | 9.99 | [5 empty] | 2023-10-31 |  |  | COD
ERCOT | 24INR0602 | CPS Rio Nogales CT301 Rotor Replacement |  | CPS Energy | 5362 RIONOG 345kV | Guadalupe | SOUTH | 2025-02-01 | CC | 3.1 | [5 empty] | 2023-11-10 | 2024-04-03
ERCOT | 24INR0628 | Palmview BESS |  | SBESS TX14 LLC | Palmview XFMR 2 CKT 6790 Substation transmission - 138kv ERCOT station code - PALMVIEW PTI Bus # 8387 ERCOT Load Name - LD02 | Hidalgo | SOUTH | 2025-03-01 | BA | 9.9 | [5 empty] | 2024-04-15
ERCOT | 24INR0638 | Cotulla BESS 2 |  | SBESS TX19 LLC | Cotulla Substation XFMR 2 #460 CKT Sub max transmission - 138kv Substation name - COTULLA Bus # 8610 Load - LOAD02 | La Salle | SOUTH | 2025-03-01 | BA | 9.9 | [5 empty] | 2024-04-15
ERCOT | 24INR0642 | SE Edinburg BESS |  | SBESS TX16 LLC | Southeast Edinburg, XFMR 2, #6580 CKT, SOUTHEAST EDINBURG, SE_EDINB, Ercot Bus # 8374, Ercot Load name - 138_12_2 | Hidalgo | SOUTH | 2025-03-01 | BA | 9.9 | [5 empty] | 2024-04-26
ERCOT | 24INR0645 | COYOTE SPRINGS AGR1 |  | HEN INFRASTRUCTURE, LLC 1 | Station Name: COYOTSPR Load Name: COYOTE_1 Bus#: 38113 Voltage: 138 kV DAC: COYOTSPR_LD8 COYOTSPR/COYOTE_1/38113/COYOTSPR_LD8 | Reeves | WEST | 2025-01-08 | OT | 9.95 | [5 empty] | 2023-10-16
ERCOT | 24INR0646 | SADDLEBACK AGR1 |  | HEN INFRASTRUCTURE, LLC 1 | SADLBACK/SADLBK_1/38058/SADLBACK_LD8 | Reeves | WEST | 2025-01-08 | OT | 9.95 | [5 empty] | 2023-10-16
ERCOT | 24INR0647 | OLNEY AGR1 |  | HEN INFRASTRUCTURE, LLC 1 | OLNEYTN/OLNEY_2/37830/OLNEYTN_LD2 | Young | WEST | 2025-01-31 | OT | 9.95 | [5 empty] | 2023-10-16
ERCOT | 24INR0659 | Empire Central BESS |  | SMT Dallas III LLC | Station name: EMPCT, Load name: LDLXFMR2, XFMR Number: 2, Bus Number:2799, Voltage: 138kV | Dallas | NORTH | 2025-06-01 | BA | 9.95
ERCOT | 24INR0662 | Prairie Creek BESS |  | SMT Dallas LLC | Station Name: PRCK Load Name: LDLXFMR4 XFMR Number: 4 Bus number: 2762 Voltage: 138 kV | Dallas | NORTH | 2025-06-01 | BA | 9.95
ERCOT | 24INR0759 | Tynan BESS1 |  | HEN INFRASTRUCTURE, LLC 1 | STATION: TYNAN/LOAD: LOAD1/NODE: LD01 | Bee | SOUTH | 2024-11-27 | BA | 9.9 | [5 empty] | 2024-03-09
ERCOT | 25INR0592 | Carrizo Springs BESS |  | Regis Carrizo Springs LLC | Station Name: CARRIZO SPRINGS Station Code: CARIZZO Load/Load XFMR Name: LOAD1 PTI Bus Number: #8244 Voltage in kV (Transmission): 69 kV Distribution Voltage: 12.47 kV | Dimmit | SOUTH | 2025-05-30 | BA | 9.99 | [5 empty] | 2023-11-29
ERCOT | 25INR0593 | Escondido BESS |  | Regis Escondido LLC | Station Name: ESCONDIDO TSP Station Code: ESCONDID Load Transformer Name: LOAD2 Bus #: 8260 Voltage in kV (Transmission Level): 138 kV | Maverick | SOUTH | 2025-05-30 | BA | 9.99 | [5 empty] | 2023-11-29
ERCOT | 25INR0594 | Goodwin BESS |  | Regis Goodwin LLC | Station Name: GOODWIN TSP Station Code: GOODWIN Load Transformer Name: 138_12_1 Bus #: 8355 Voltage in kV (Transmission Level): 138 kV | Hidalgo | SOUTH | 2025-05-31 | BA | 9.99 | [5 empty] | 2023-11-29
ERCOT | 25INR0701 | Abilene Elmcreek BESS |  | DGSP2 LLC | Station Name: Abilene Elm Creek TSP Station Code: ELMCRK Load Transformer name: LOAD1 Bus#: 6255 Voltage in kV (Transmission Level): 138kV | Taylor | WEST | 2025-04-21 | BA | 9.9 | [5 empty] | 2024-08-15
ERCOT | 25INR0702 | Abilene Industrial Park BESS |  | Distributed Generation Solutions LLC | Station Name: Abilene Industrial Park TSP Station Code: ABINDUST Load Transformer name: LOAD1 Bus#: 60772 Voltage in kV (Transmission Level): 138kV | Taylor | WEST | 2025-04-21 | BA | 9.9 | [5 empty] | 2024-08-15
ERCOT | 25INR0715 | Poteet BESS |  | HEN INFRASTRUCTURE, LLC 1 | TSP Station Name: POTEET SUB TSP Station Code: POTEETS Load Name: POTEE_1 Bus#: 5710 kV: 69 | Atascosa | SOUTH | 2025-04-01 | BA | 9.95