## Sheet1
ISO | Project ID | POI Name | Project Name | State | County | Project Status | Transmission Owner | MW Energy | Capacity (MW) | Capacity Status | Service Type | Technology | Feasibility Study Status | System Impact Study Status | Facilities Study Status | Interconnection Agreement Status | Queue Date | Withdrawal Date | Comment | Projected COD | Actual In Service Date
PJM | A01 | South Lebanon 230 KV | Ironwood | PA | Lebanon | In Service | ME | 720 | 673 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/1997 |  |  | 4/1/2002 | 4/1/2002
PJM | A02 | Oak Hall 138 kV (Oil CT) | Chesapeake | VA | Unknown | In Service | DPL | 315 | 315 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 4/1/1997 |  |  | 8/22/2001 | 8/22/2001
PJM | A03 | Linden 230 kV or 138 kV | Linden 5 & 6 | NJ | Union | In Service | PSEG | 120 | 120 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/1/1997 |  |  | 6/1/2000 | 6/1/2000
PJM | A04 | Linden 230 kV or 138 kV | Linden 1, 2 & 3 | NJ | Union | In Service | PPL | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/1997 |  |  | 5/1/2006 | 5/1/2006
PJM | A05 | Bergen | Bergen | NJ | Bergen | In Service | PSEG | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/1997 |  |  | 6/1/2002 | 6/1/2002
PJM | A06 | Kearny |  | NJ | Gloucester | Withdrawn | PSEG | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/1/1997 | 8/28/2000
PJM | A07 | Dickerson 120 MW |  | MD | Montgomery | Withdrawn | PEPCO | 25 | 120 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 5/1/1997 | 7/22/2002 | Customer Initiated Withdrawal
PJM | A08 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 15 | 15 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 6/1/1997 |  |  | 7/1/2002 | 7/1/2002
PJM | A09 | Susquehanna 230 kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 35 | 35 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 6/1/1997 |  |  | 5/1/2003 | 5/1/2003
PJM | A10 | Glory 115 kV | Colver Power | PA | Cambria | In Service | PENELEC | 6 | 6 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required |  | 6/2/1997 |  |  | 1/8/2000 | 1/8/2000
PJM | A11 | Harwood 230 kV | Hazelton | PA | Luzerne | In Service | PPL | 201 | 201 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/30/1997 |  |  | 4/1/2002 | 4/1/2002
PJM | A12 | Martins Creek 230 kV | Lower Mt Bethel | PA | Northampton | In Service | PPL | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/20/1997 |  |  | 5/14/2004 | 5/14/2004
PJM | A13 | Mickleton 230 kV | Mantua Creek Generating Station | NJ | Gloucester | Withdrawn | AEC | 803 | 803 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/26/1997 |  |  | 6/1/2004
PJM | A14 | Sewaren |  | NJ | Middlesex | Withdrawn | PSEG | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/1/1998 | 6/18/2002
PJM | A15 | Sayreville 230 kV | Red Oak CC1, CT1 - CT4 | NJ | Middlesex | In Service | JCPL | 765 | 765 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/20/1998 |  |  | 2/1/2002 | 2/1/2002
PJM | A16 | Eagle Point 230 kV |  | NJ | Gloucester | Withdrawn | PECO | 800 | 800 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/3/1998 | 4/19/2000
PJM | A17 | Linden 230 kV |  | NJ | Union | Withdrawn | PSEG | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 5/8/1998 | 10/10/2003 |  | 5/1/2006
PJM | A18 | North Temple 230 kV |  | PA | Berks | In Service | ME | 557 | 557 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Interim Study | Document Posted | Document Posted | 5/11/1998 |  |  | 12/1/2002 | 12/1/2002
PJM | A19 | Eddystone 230 kV | Liberty (Eddy) | PA | Delaware | In Service | PECO | 521 | 521 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 5/15/1998 |  |  | 1/1/2002 | 1/1/2002
PJM | A20 | Juniata 500 kV |  | PA | Dauphin | Withdrawn | PPL | 12 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 7/9/1998 | 7/18/1999 | Customer Milestone Not Met
PJM | A21 | Chichester 230 kV | Phillips Island | PA | Philadelphia | In Service | PECO | 725 | 725 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/17/1998 |  |  | 12/31/2004 | 12/31/2004
PJM | A22 | Hudson 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/20/1998 | 8/28/2000
PJM | A23 | New Castle 138 kV |  | DE | New Castle | Withdrawn | DPL | 257 | 257 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/13/1998 | 7/23/1999
PJM | A24 | South River 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 725 | 725 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/28/1998 | 6/26/1999
PJM | A25 | Hosensack 500 kV |  | PA | Northampton | Withdrawn | PPL | 1000 | 1000 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 10/30/1998 | 1/24/2002
PJM | A26 | Linden | Tosco #6 | NJ | Union | In Service | PSEG | 180 |  | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/2/1998 |  |  | 1/25/2002 | 1/25/2002
PJM | A27 | Passyunk 230 kV |  | PA | Philadelphia | Withdrawn | PECO | 615 | 515 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/4/1998 | 4/30/2002
PJM | A28 | Dover | Kent | DE | Kent | In Service | DPL | 100 | 98 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/4/1998 |  |  | 6/14/2001 | 6/14/2001
PJM | A29 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/18/1998 |  |  | 6/13/2003 | 6/13/2003
PJM | A30 | Colora Tap | Rock Springs | MD | Cecil | In Service | DPL | 465 | 465 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 12/3/1998 |  |  | 12/1/2005 | 12/1/2005
PJM | A31 | Peckville/Varden 69 kV | Archbald | PA | Lackawanna | In Service | PPL | 44 | 44 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 12/22/1998 |  |  | 10/27/2001 | 10/27/2001
PJM | A32 | Montour #1 | Montour #1 | PA | Montour | In Service | PPL | 14 | 14 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/12/1999 |  |  | 6/19/2001 | 6/19/2001
PJM | A33 | Montour #2 | Montour #2 | PA | Montour | In Service | PPL | 14 | 14 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/12/1999 |  |  | 11/1/2000 | 11/1/2000
PJM | A34 | Brunner 230 kV |  | PA | York | In Service | PPL | 14 | 14 | Capacity | Generation Interconnection | Coal | Document Posted | Interim Study | Document Posted | Document Posted | 1/12/1999 |  |  | 4/27/2002 | 4/27/2002
PJM | A35 | North Bangor 34.5 kV | Grand Central Sanitary LF | PA | Northampton | In Service | ME | 10 | 10 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Document Posted | 1/13/1999 |  |  | 4/18/2001 | 4/18/2001
PJM | A36 | Hunterstown 500 kV | Hunterstown | PA | Adams | In Service | ME | 830 | 830 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/27/1999 |  |  | 7/31/2003 | 7/31/2003
PJM | A37 | Sayreville 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 749 | 749 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/27/1999 | 9/8/1999
PJM | A38 | Erie West 345 kV |  | PA | Crawford | Withdrawn | PENELEC | 765 | 765 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/27/1999 | 8/6/2001
PJM | A39 | Pequest River 115 kV |  | NJ | Warren | Withdrawn | JCPL | 73 | 73 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/27/1999 | 8/6/2001
PJM | A40 | TMI 500 kV |  | PA | Dauphin | Withdrawn | ME | 1271 | 1271 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/27/1999 | 10/12/1999
PJM | A41 | TMI 500 kV |  | PA | Dauphin | Withdrawn | ME | 765 | 765 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/27/1999
PJM | A42 | Atlantic 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 449 | 449 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/27/1999 | 8/6/2001
PJM | A43 | Portland 230 kV |  | PA | Northampton | Withdrawn | ME | 472 | 472 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted |  | 1/27/1999 | 7/20/2003
PJM | A44 | Shelocta 230 kV |  | PA | Indiana | Withdrawn | PENELEC | 402 | 402 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/27/1999 | 10/22/1999
PJM | A45 | Oyster Creek 230 kV |  | NJ | Ocean | Withdrawn | JCPL | 752 | 752 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/27/1999 | 12/6/1999
PJM | A46 | Gilbert 115 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/27/1999 | 8/30/1999
PJM | A47 | Perryman 230kV or 115kV |  | MD | Harford | Withdrawn | BGE | 740 | 740 | Capacity | Generation Interconnection | Natural Gas | Withdrawn | Withdrawn |  |  | 4/30/1999 | 8/30/1999
PJM | A48 | East Towanda 230kV |  | NJ | Union | Withdrawn | PENELEC | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/3/1999 | 10/3/2001
PJM | A49 | West Hempfield 230kV |  | NJ | Bergen | Withdrawn | PPL | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/3/1999 | 9/10/1999
PJM | A50 | Bayonne |  | NJ | Hudson | Withdrawn | PSEG | 60 |  | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/3/1999 |  | Customer Initiated Withdrawal | 12/1/2005
PJM | A51 | Camden |  | NJ | Camden | Withdrawn | PSEG | 258 | 258 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/3/1999 | 11/26/2001
PJM | A52 | Linden |  | NJ | Union | Withdrawn | PSEG | 180 |  | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/3/1999 | 3/17/2004 |  | 6/1/2005
PJM | A53 | Titusville |  | PA | Crawford | Withdrawn | PENELEC | 25 | 25 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted |  | 2/3/1999 | 1/15/2002
PJM | A54 | TMI 230 kV |  | PA | Dauphin | Withdrawn | ME | 45 | 45 | Capacity | Generation Interconnection | Nuclear | Document Posted | Interim Study | Not Required | Withdrawn | 2/9/1999 |  | Customer Milestone Not Met | 6/1/2002
PJM | A55 | Lakewood 230kV | Lakewood NUG | NJ | Ocean | In Service | JCPL | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/22/1999 |  |  | 12/31/2005 | 12/31/2005
PJM | A56 | Pedricktown 230kV |  | NJ | Salem | Withdrawn | AEC | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 3/8/1999 | 8/17/1999
PJM | A57 | Edgemoor | Unit 1 | PA | Dauphin | Withdrawn | AEC | 30 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/8/1999 | 7/27/2000 |  | 10/31/2001
PJM | A58 | Hawkins Gate / Oak Grove 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 450 | 450 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/29/1999 | 8/28/1999
PJM | A59 | Emilie | Ford Mill | PA | Bucks | In Service | PECO | 540 | 540 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/1999 |  |  | 5/27/2004 | 5/27/2004
PJM | A59_W00 | Springdale 138 kV | Springdale 1 & 2 | PA | Allegheny | In Service | APS | 96 | 88 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required |  | 1/1/1999 |  |  | 12/1/2000 | 12/1/2000
PJM | A60 | Hunterstown 500 kV |  | PA | Adams | Withdrawn | ME | 679 | 679 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 4/8/1999
PJM | A61 | Hawkins Gate / Oak Grove 230kV |  | DE | New Castle | Withdrawn | PEPCO | 450 | 450 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 3/30/1999
PJM | B01 | Dickerson |  | MD | Montgomery | Withdrawn | PEPCO | 398 | 398 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 4/29/1999 | 7/22/2002
PJM | B02 | Morgantown | Morgantown Units 1 & 2 | MD | Charles | In Service | PEPCO | 80 | 80 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/30/1999 |  |  | 3/17/2001 | 3/17/2001
PJM | B03 | Hosensack 500kV | Bethlehem | PA | Northampton | In Service | PPL | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/1999 |  |  | 1/28/2003 | 1/28/2003
PJM | B04 | Oyster Creek |  | NJ | Ocean | Withdrawn | JCPL | 800 | 800 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/1999
PJM | B05 | Wayne-Homer City 345kV |  | PA | Indiana | In Service | PENELEC | 265 | 250 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Interim Study | Not Required | Document Posted | 4/30/1999 |  |  | 1/1/2002 | 1/1/2002
PJM | B06 | Wayne-Homer City 345kV |  | PA | Indiana | Withdrawn | PENELEC | 525 | 525 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/10/1999
PJM | B07 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/10/1999
PJM | B08 | Friedensburg 69kV |  | PA | Berks | Withdrawn | ME | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 6/9/1999
PJM | B09A | Burlington 138kV | Burlington | NJ | Burlington | In Service | PSEG | 168 | 168 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 6/10/1999 |  |  | 7/22/2000 | 7/22/2000
PJM | B09b | Burlington 138kV |  | NJ | Burlington | Withdrawn | PSEG | 336 | 336 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 6/10/1999
PJM | B10 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 6/10/1999
PJM | B12 | Limerick 230kV |  | PA | Montgomery | Withdrawn | PECO | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 6/14/1999 | 6/13/2002
PJM | B12_W01 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required |  | 1/1/1999 |  |  | 3/1/2002 | 3/1/2002
PJM | B12_W02 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required |  | 1/1/1999 |  |  | 10/1/2002 | 10/1/2002
PJM | B13 | Lakewood 230kV |  | NJ | Ocean | Withdrawn | JCPL | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/2/1999
PJM | B14 | Arnold 115kV | Arnold (Green Mountain) WF | PA | Somerset | Deactivated | PENELEC | 10.4 | 2.08 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/6/1999 |  |  | 1/1/1999 | 8/13/2004
PJM | B15 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/12/1999 | 10/2/2002 |  | 6/1/2003
PJM | B16 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/12/1999 | 10/2/2002 |  | 6/1/2004
PJM | B17 | Jerseyville 34.5kV | Statoil | NJ | Monmouth | Withdrawn | JCPL | 2.1 |  | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/17/1999 | 1/26/2021 |  | 1/1/1999
PJM | B18 | Limerick-Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/23/1999
PJM | B18_W03 | Springdale 138 kV | Springdale CT3, CT4, ST5 | PA | Allegheny | In Service | APS | 525 | 525 | Capacity | Generation Interconnection | Natural Gas | Not Required | Document Posted | Not Required | Document Posted | 1/1/1999 |  |  | 8/1/2003 | 8/1/2003
PJM | B19 | Melrose 34.5kV | Middlesex Sewer | NJ | Middlesex | In Service | JCPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/30/1999 |  |  | 4/6/2001 | 4/6/2001
PJM | B20 | Elm St. 115kV |  | PA | Warren | Withdrawn | PENELEC | 70 | 70 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/7/1999 | 10/23/2000
PJM | B21 | South Reading 500kV |  | PA | Berks | Withdrawn | ME | 925 | 925 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/9/1999 | 9/15/2000
PJM | B22 | Gould St. 34.5 kV |  | MD | Baltimore City | Withdrawn | BGE | 9.9 | 9.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/11/1999
PJM | B23 | Siegfried/Allentown 138kV | Northampton | PA | Northampton | In Service | PPL | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 8/21/1999 |  |  | 6/10/2001 | 6/10/2001
PJM | B23_W04 | Gans 138 kV | Gans 8 & 9 | PA | Fayette | In Service | APS | 88 | 88 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required |  | 8/26/1999 |  |  | 12/1/2001 | 12/1/2001
PJM | B24 | Oak Grove 13.8kV |  | MD | Prince George's | Withdrawn | PEPCO | 6.8 | 6.8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/7/1999
PJM | B25 | Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 870 | 870 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 9/20/1999 | 5/3/2002
PJM | B26 | Hunlock Creek 66kV | Hunlock Creek 66kV | PA | Luzerne | In Service | UGI | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/20/1999 |  |  | 5/26/2002 | 5/26/2002
PJM | B27 | Portland 230kV |  | PA | Northampton | Withdrawn | ME | 362 | 362 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/3/1999 | 11/6/2000
PJM | B28 | Muddy Run 230kV | Muddy Run | PA | York | In Service | PECO | 160 | 160 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 11/12/1999 |  |  | 8/27/2003 | 8/27/2003
PJM | B28_W07 | Backbone Mountain 138 kV | Backbone WF | WV | Tucker | In Service | APS | 90 | 18 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 11/12/1999 |  |  | 5/1/2003 | 5/1/2003
PJM | B28_W08 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS | 15 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 11/12/1999 |  |  | 4/1/2002 | 4/1/2002
PJM | B29 | Perryman 230kV/115kV |  | MD | Harford | Withdrawn | BGE | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/15/1999 | 4/17/2001
PJM | B30 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 605 | 605 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/22/1999 |  |  | 6/29/2004 | 6/29/2004
PJM | B31 | Brunner-West Hempfield 230kV |  | PA | Lancaster | Withdrawn | PPL | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/22/1999 | 10/9/2000
PJM | B32 | TMI 230kV |  | PA | Dauphin | Withdrawn | ME | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/23/1999 | 12/5/2000
PJM | B33 | Steelton 230kV |  | PA | Dauphin | Withdrawn | PPL | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/23/1999 | 12/3/2002 |  | 5/1/2005
PJM | B34 | Seward 230kV | Seward 1 (Hay Road 5,6,7,8) | PA | Westmoreland | In Service | PENELEC | 525 | 304 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Document Posted | Document Posted | 11/23/1999 |  |  | 6/9/2006 | 6/9/2006
PJM | B35 | South Akron 230kV | West Earl | PA | Lancaster | Withdrawn | PPL | 313 | 313 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/24/1999 | 3/10/2003
PJM | B36 | South Akron 230kV | West Earl | PA | Lancaster | Withdrawn | PPL | 78 | 78 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/24/1999 | 3/10/2003 |  | 6/30/2004
PJM | B37 | East Greenville 69kV |  | PA | Montgomery | Withdrawn | PPL | 90 | 90 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn | Withdrawn | 11/24/1999 | 4/9/2002
PJM | B38 | Elroy 138kV |  | PA | Montgomery | Withdrawn | PPL | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted |  | 11/24/1999 | 1/7/2002
PJM | B39 | Quarryville 69kV |  | PA | Lancaster | Withdrawn | PPL | 90 | 90 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/24/1999 | 1/7/2002
PJM | B40 | West Hempfield 69kV |  | PA | Lancaster | Withdrawn | PPL | 100 | 90 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  | Document Posted | Withdrawn | 11/24/1999 | 1/7/2002
PJM | B41 | West Hempfield 138kV |  | PA | Lancaster | Withdrawn | PPL | 90 | 90 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/24/1999 | 1/7/2002
PJM | B42 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/29/1999 | 11/8/2000
PJM | B43 | Homer City-Wayne 345kV |  | PA | Venango | Withdrawn | PENELEC | 284 | 284 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/29/1999 | 11/8/2000
PJM | B44 | Elko-Forrest 230kV |  | PA | Elk | Withdrawn | PENELEC | 240 | 240 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/29/1999
PJM | B45 | Lackawanna 230kV |  | PA | Lackawanna | Withdrawn | PPL | 555 | 555 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/29/1999 | 7/23/2002 |  | 6/1/2004
PJM | B46 | Conowingo 230kV | Conowingo | MD | Harford | In Service | PECO | 36 | 36 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 11/29/1999 |  |  | 11/21/2003 | 11/21/2003
PJM | B47 | Red Lion 500kV | Hay Road 5, 6, 7 | DE | New Castle | In Service | DPL |  | 545 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/29/1999 |  |  | 7/22/2002 | 7/22/2002
PJM | B48 | Graceton 230kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/30/1999 | 10/17/2003 |  | 6/1/2005
PJM | B49 | Erie South-Warren 230kV |  | PA | Warren | Withdrawn | PENELEC | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/30/1999 | 7/31/2001
PJM | B50 | Morgantown 69kV |  | PA | Erie | Withdrawn | PPL | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/1999
PJM | B51 | Wayne 345 |  | PA | Indiana | Withdrawn | PENELEC | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/1999 | 11/19/2001
PJM | B52 | Woodbridge 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/1999 | 12/5/2000
PJM | C01 | Linden 138kV | Linden 1, 2 & 3 | NJ | Union | In Service | PSEG | 436 | 436 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 12/17/1999 |  |  | 5/1/2006 | 5/1/2006
PJM | C02 | South Lebanon 230kV | Ironwood | PA | Lebanon | Withdrawn | ME | 47 | 47 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 1/6/2000 |  |  | 1/1/2007
PJM | C03 | Morgantown/Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 1/11/2000 | 9/16/2002 |  | 12/1/2003
PJM | C04 | Burches Hill 230kV |  | MD | Charles | Withdrawn | PEPCO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/11/2000 | 1/25/2002
PJM | C05 | Somerset 34.5kV |  | NJ | Somerset | Withdrawn | JCPL | 3.75 | 3.75 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted |  |  | 1/24/2000
PJM | C06 | Susquehanna 230kV** |  | PA | Luzerne | Withdrawn | PPL | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/26/2000 | 7/6/2001
PJM | C07 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 26 | 26 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2000 |  |  | 7/19/2001 | 7/19/2001
PJM | C08 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 69 | 69 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2000 |  |  | 8/1/2001 | 8/1/2001
PJM | C09 | Fairlawn 26.4kV |  | NJ | Bergen | Withdrawn | PSEG | 37 | 37 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/4/2000 | 1/25/2001
PJM | C10 | Erie East 230kV | Northeast Cogen | PA | Erie | Withdrawn | PENELEC | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/8/2000 | 6/23/2005 | Customer Milestone Not Met | 6/1/2006
PJM | C11 | Mifflintown 69kV |  | PA | Juniata | Withdrawn | PPL | 9.9 | 9.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/25/2000 | 7/6/2001
PJM | C11_W11 | Hunker 138 kV |  | PA | Westmoreland | Withdrawn | APS | 88 | 88 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/25/2000
PJM | C12 | Conastone - Peach Bottom 500kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 3/15/2000 | 6/22/2004 |  | 12/1/2004
PJM | C13 | Conastone - Peach Bottom 500kV |  | MD | Harford | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 3/15/2000 | 6/22/2004 |  | 12/1/2004
PJM | C14 | Keystone - Conemaugh 550 |  | PA | Indiana | Withdrawn | PENELEC | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/27/2000 | 3/1/2002
PJM | C15 | Friedensburg 69kV |  | PA | Berks | Withdrawn | ME | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn | Withdrawn | Withdrawn | 3/28/2000 |  |  | 12/1/2002
PJM | C16 | Westover South 34.5kV |  | PA | Clearfield | Withdrawn | PENELEC | 13.15 | 13.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/28/2000
PJM | C17 | Somerset 23kV |  | PA | Somerset | Withdrawn | PENELEC | 4.5 | 4.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/28/2000
PJM | D01 | Engleside 69kV | Sight and Sound Theater | PA | Lancaster | In Service | PPL | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/6/2000 |  |  | 5/31/2000 | 5/31/2000
PJM | D02 | Edgemoor | Hay Road 1-4 | DE | New Castle | In Service | DPL | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/7/2000 |  |  | 4/12/2000 | 4/12/2000
PJM | D03 | Harwood 69kV | Haxelton Units 2-4 | PA | Luzerne | In Service | PPL | 99 | 99 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/17/2000 |  |  | 6/1/2002 | 6/1/2002
PJM | D03_W15 | Horse Shoe Run 69 kV |  | WV | Preston | Withdrawn | APS | 12 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/24/2000 |  |  | 6/1/2003
PJM | D04 | Peckville 69kV | Archbald | PA | Wayne | In Service | PPL | 1 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/26/2000 |  |  | 6/9/2000 | 6/9/2000
PJM | D05 | East Carbondale 69kV | Waymart WF | PA | Wayne | In Service | PPL | 70 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/15/2000 |  |  | 12/1/2003 | 12/1/2003
PJM | D05_W17 | Friendsville 500 kV |  | MD | Garrett | Withdrawn | APS | 432 | 432 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 6/15/2000 | 9/20/2002 |  | 6/1/2004
PJM | D06 | Eclipse 115kV | Scrubgrass NUG | PA | Unknown | In Service | PENELEC | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/19/2000 |  |  | 7/15/2000 | 7/15/2000
PJM | D07 | Blueball 69kV | Sunoil Gen Unit | PA | Delaware | Deactivated | PECO | 8 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/23/2000 |  |  | 7/25/2000 | 7/25/2000
PJM | D08 | Kearny 230kV | Kearny #12 | NJ | Hudson | In Service | PSEG | 168 | 168 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Interim Study | Document Posted | 7/3/2000 |  |  | 8/4/2001 | 8/4/2001
PJM | D08_W18 | Terra Alta 138 kV |  | WV | Preston | Withdrawn | APS | 88 | 88 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 7/3/2000
PJM | D08_W19 | Bald Eagle 46 kV |  | PA | Centre | Withdrawn | APS | 88 | 88 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 7/3/2000
PJM | D09 | 9th St (sub 117) 13kV | Central Heating & Refrigeriation Facility 1 & 2 | DC |  | In Service | PEPCO | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/24/2000 |  |  | 6/1/2004 | 6/1/2004
PJM | D10 | NIH 13kV | NIH Unit 1 | MD | Montgomery | In Service | PEPCO | 25 |  | Energy | Generation Interconnection | Oil | Document Posted | Document Posted | Document Posted | Document Posted | 7/26/2000 |  |  | 6/1/2004 | 6/1/2004
PJM | D11 | Clayton 138kV | DEMEC/Smyrna 1 &2 | DE | Kent | In Service | DPL | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/26/2000 |  |  | 5/1/2002 | 5/1/2002
PJM | D13 | Deep Run 34.5kV |  | NJ | Middlesex | Withdrawn | JCPL | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/27/2000 | 3/21/2002
PJM | D14 | Red Lion 500kV |  | DE | New Castle | Withdrawn | DPL | 190 | 190 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/28/2000 | 3/1/2002
PJM | D15 | Red Lion 500kV |  | DE | New Castle | Withdrawn | DPL | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/28/2000
PJM | D16 | Hummelstown 230kV |  | PA | Dauphin | Withdrawn | PPL | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/28/2000 | 1/15/2002
PJM | D17 | Hummelstown 230kV |  | PA | Dauphin | Withdrawn | PPL | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/28/2000 | 1/15/2002
PJM | D18 | Hosensack 230kV | Conectiv Bethlem CT 6, ST2 | PA | Northampton | In Service | PPL | 350 | 350 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/28/2000 |  |  | 5/1/2004 | 5/1/2004
PJM | D19 | Brunner-West Hempfield 230kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/28/2000 | 4/28/2003 |  | 12/1/2004
PJM | D20 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn | Withdrawn | 7/28/2000 | 4/28/2003 |  | 5/1/2005
PJM | D21 | Hunterstown-Conemaugh 500kV |  | PA | Cambria | Withdrawn | PENELEC | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/28/2000 | 4/28/2003 |  | 12/1/2005
PJM | D22 | Hunterstown-Conemaugh 500kV |  | PA | Cambria | Withdrawn | PENELEC | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/28/2000 | 4/28/2003 |  | 12/1/2005
PJM | D23 | Keystone 500kV |  | PA | Indiana | Withdrawn | PENELEC | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2000 | 3/27/2002
PJM | D24 | Mansfield 115kV |  | PA | Tioga | Withdrawn | PENELEC | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2000 | 3/27/2002
PJM | D25 | Hay Road 69kV & 138kV |  | DE | New Castle | Withdrawn | DPL | 39 | 39 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Interim Study | Not Required | Document Posted | 7/31/2000 | 9/17/2003
PJM | D26 | Mercer 230kV |  | NJ | Mercer | Withdrawn | PSEG | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2000
PJM | D27 | Salem - East Windsor 500kV |  | NJ | Burlington | Withdrawn | PSEG | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/31/2000 | 12/3/2002 |  | 12/1/2004
PJM | D28 | Passyunk 230kV |  | PA | Philadelphia | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 7/30/2000 | 11/12/2002
PJM | D29 | Derwood 13kV |  | MD | Montgomery | In Service | PEPCO | 3 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2000 |  |  | 6/29/2001 | 6/29/2001
PJM | E01 | Kearny 230kV |  | NJ | Hudson | Withdrawn | PSEG | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/15/2000 | 11/1/2001
PJM | E02 | N. Lebanon 69kV |  | PA | Lebanon | In Service | ME | 1.2 | 1.2 | Capacity | Generation Interconnection | Methane | Document Posted | Interim Study | Not Required | Document Posted | 8/15/2000 |  |  | 11/17/2000 | 11/17/2000
PJM | E03 | Somerville 13.8kV |  | NJ | Middlesex | Withdrawn | PSEG | 5 | 5 | Capacity | Generation Interconnection | Methane | Document Posted | Interim Study |  |  | 8/17/2000 | 10/25/2002 |  | 1/31/2001
PJM | E04 | Atlantic 230kV |  | NJ | Monmouth | Withdrawn | JCPL | 24 | 24 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/6/2000
PJM | E04_W20 | Guilford 138 kV |  | PA | Franklin | In Service | APS | 88 | 88 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Not Required | Not Required | Not Required | 9/6/2000 |  |  | 12/1/2002 | 12/1/2002
PJM | E05 | Bethlehem Steel 33kV | Sparrow Point | MD | Baltimore County | In Service | BGE | 2.5 | 2.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/14/2000 |  |  | 1/1/2001 | 1/1/2001
PJM | E05_W25 | Doubs 500 kV or 230 kV |  | MD | Frederick | Withdrawn | APS | 620 | 620 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/4/2000 | 11/26/2002 |  | 5/1/2004
PJM | E06 | Bear Creek 69kV (Wind) | Bear Creek | PA | Luzerne | Withdrawn | PPL | 15.6 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/5/2000 | 10/25/2002 |  | 12/1/2002
PJM | E07 | Montour 230kV | Montour #2 | PA | Montour | In Service | PPL | 7 | 7 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 10/6/2000 |  |  | 1/1/1999 | 5/6/2002
PJM | E08 | Hunlock Creek |  | PA | Luzerne | Withdrawn | UGI | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/17/2000
PJM | E09 | Kiamensi 34kV |  | DE | New Castle | Withdrawn | DPL | 8.4 | 8.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/19/2000
PJM | E10 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 162 | 162 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/23/2000
PJM | E11 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/23/2000
PJM | E12 | Larrabee 230kV |  | NJ | Monmouth | Withdrawn | JCPL | 661 | 661 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/25/2000
PJM | E13 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC | 10 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/3/2000 |  |  | 1/1/1999 | 8/13/2004
PJM | E14 | Elm St. 115 kV |  | PA | Erie | Withdrawn | PENELEC | 70 | 70 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/7/2000
PJM | E15 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 16.9 | 16.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/7/2000
PJM | E16 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 70 | 70 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/8/2000
PJM | E17 | Limerick |  | PA | Montgomery | Withdrawn | PECO | 75 | 75 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  | Withdrawn | 11/9/2000 | 6/25/2002 |  | 12/1/2003
PJM | E17_W26 | Taylorstown 500 kV |  | PA | Unknown | Withdrawn | APS | 1595 | 1595 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/14/2000 |  |  | 7/1/2005
PJM | E17_W27 | Ronco | Ronco CT1, CT2, STG | PA | Fayette | In Service | APS | 620 | 620 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/15/2000 |  |  | 6/1/2003 | 6/1/2003
PJM | E17_W29 | Yukon 500 kV |  | PA | Westmoreland | Withdrawn | APS | 640 | 640 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/15/2000 | 6/2/2004 |  | 12/31/2005
PJM | E18 | Essex / Foundry St 138kV |  | NJ | Essex | Withdrawn | PSEG | 275 | 275 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/28/2000
PJM | E19 | Delco Tap 230kV |  | PA | Delaware | Withdrawn | PECO | 330 | 330 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/28/2000
PJM | E20 | Croydon 230kV | Croydon #11,12,21,22,31,32,41,42 | PA | Bucks | In Service | PECO | 6.5 | 6.5 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 11/28/2000 |  |  | 12/20/2002 | 12/20/2002
PJM | E21 | Camden-Richmond 230kV |  | NJ | Camden | Withdrawn | PSEG | 727 | 727 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/28/2000 | 11/11/2004 | Customer Initiated Withdrawal | 12/1/2004
PJM | E22 | Burches Hill 500kV |  | VA | Prince William | Withdrawn | PEPCO | 960 | 960 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/29/2000 | 8/8/2002 |  | 1/1/2005
PJM | E23 | Lakehurst 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/30/2000 | 9/17/2002 |  | 12/1/2003
PJM | E24 | Parlin 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/2000 | 5/22/2002
PJM | E27 | Hosensack 500kV |  | PA | Northampton | Withdrawn | PPL | 350 | 350 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/2000
PJM | E28 | Motiva | Delaware City/Motiva Unit G6 | DE | New Castle | In Service | DPL | 60 | 60 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/30/2000 |  |  | 10/1/2003 | 10/1/2003
PJM | F01 | TMI |  | PA | Dauphin | Withdrawn | ME | 551 | 551 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/4/2000 | 4/2/2002 |  | 12/1/2004
PJM | F02 | Hudson |  | NJ | Hudson | Withdrawn | PSEG | 650 | 650 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/7/2000 | 12/1/2001
PJM | F03 | Martins Creek 230kV | Martins Creek #3 | PA | Northampton | In Service | PPL | 30 | 30 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 12/13/2000 |  |  | 4/1/2001 | 4/1/2001
PJM | F04 | Somerset 115kV | Keystone | PA | Somerset | Withdrawn | PENELEC | 30 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 1/18/2001 | 4/14/2005 | Customer Milestone Not Met | 12/31/2005
PJM | F05 | Keystone-Conemaugh 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 646 | 646 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/25/2001
PJM | F05_W38 | White Oak 500 kV |  | PA | Unknown | Withdrawn | APS | 1200 | 1200 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 1/29/2001 |  |  | 3/1/2004
PJM | F06 | Birdsboro 13.2kV |  | PA | Berks | Withdrawn | ME | 6.5 | 6.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/31/2001
PJM | F07 | Dickerson 230kV | Dickerson | MD | Montgomery | In Service | PEPCO | 16 | 16 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2001 |  |  | 3/17/2001 | 3/17/2001
PJM | F08 | Chalk Point 230kV | Chalk Point | MD | Prince George's | In Service | PEPCO | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2001 |  |  | 3/17/2001 | 3/17/2001
PJM | F09 | Central City West 23kV |  | PA | Somerset | Withdrawn | PENELEC | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/31/2001 | 10/15/2002 |  | 12/1/2003
PJM | G00_W39 | Doubs 500 kV or 230 kV |  | MD | Frederick | Withdrawn | APS | 668 | 668 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/5/2001 | 10/25/2002 |  | 4/1/2004
PJM | G00_W40 | Warren 138 kV |  | VA | Warren | Withdrawn | APS | 264 | 264 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 2/5/2001 | 11/4/2002 |  | 5/1/2005
PJM | G02 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 234 | 234 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/14/2001 | 10/23/2003 |  | 5/1/2006
PJM | G02_W43 | Tallmansville 138 kV |  | WV | Upshur | Withdrawn | APS | 450 | 450 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/16/2001 | 1/31/2003 |  | 7/1/2005
PJM | G03 | Todd 69kV |  | MD | Dorchester | Withdrawn | DPL | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 2/22/2001 | 4/22/2002 |  | 12/1/2002
PJM | G04 | Brunner Island #2 | Brunner Island #2 | PA | York | Withdrawn | PPL | 14 | 14 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required |  | 2/23/2001 |  |  | 1/1/2002
PJM | G05 | Brunner Island #1 | Brunner Island #1 | PA | York | Withdrawn | PPL | 14 | 14 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required |  | 2/23/2001 |  |  | 1/1/2002
PJM | G06 | Martins Creek #4 | Martins Creek #4 | PA | Northampton | In Service | PPL | 30 | 30 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/23/2001 |  |  | 3/1/2012 | 3/1/2012
PJM | G06_W44 | Fort Martin 500 kV |  | WV | Monongalia | Withdrawn | APS | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 2/28/2001 |  |  | 6/1/2005
PJM | G06_W45 | Harrison 500 kV |  | WV | Harrison | Withdrawn | APS | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 2/28/2001 |  |  | 6/1/2005
PJM | G06_W47 | Black Oak 500 kV |  | PA | Allegheny | Withdrawn | APS | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 2/28/2001 |  |  | 6/1/2005
PJM | G07 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/7/2001 | 12/4/2001
PJM | G08 | Kearny | Kearny #12 | NJ | Hudson | In Service | PSEG | 7 | 7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Interim Study | Document Posted | 3/13/2001 |  |  | 6/30/2001 | 6/30/2001
PJM | G09 | Homer City |  | PA | Indiana | Withdrawn | PENELEC | 547 | 547.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/13/2001 |  |  | 12/1/2004
PJM | G10 | Bergen | Bergen #2 | NJ | Bergen | In Service | PSEG | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/20/2001 |  |  | 6/1/2002 | 6/1/2002
PJM | G11 | Burlington 138kV |  | NJ | Burlington | Withdrawn | PSEG | 622 | 622 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/20/2001 | 1/8/2002
PJM | G12 | Burlington 230kV |  | NJ | Burlington | Withdrawn | PSEG | 316 | 316 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/20/2001 | 1/4/2002
PJM | G13 | Woodbourne |  | PA | Bucks | Withdrawn | PECO | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/22/2001 | 6/3/2003 |  | 12/1/2005
PJM | G14 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 610 | 610 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/26/2001 |  |  | 12/1/2004
PJM | G15 | Sewaren |  | NJ | Middlesex | Withdrawn | PSEG | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/27/2001 |  |  | 6/1/2004
PJM | G16 | Bayview 26kV (Wind) |  | VA | Northampton | Withdrawn | DPL | 8 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 4/2/2001 |  |  | 12/1/2002
PJM | G17 | Burlington | Burlington #10 | NJ | Burlington | In Service | PSEG | 16 | 16 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/5/2001 |  |  | 7/19/2002 | 7/19/2002
PJM | G18 | Linden | Linden 5 & 6 | NJ | Union | In Service | PSEG | 12 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/5/2001 |  |  | 5/4/2004 | 5/4/2004
PJM | G19 | Linden | Linden 7 & 8 | NJ | Union | In Service | PSEG | 12 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/5/2001 |  |  | 5/4/2004 | 5/4/2004
PJM | G20 | Essex | Essex 9 | NJ | Essex | In Service | PSEG | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/5/2001 |  |  | 6/1/2003 | 6/1/2003
PJM | G21 | Meyersdale North 115 kV | Meyersdale WF | PA | Somerset | In Service | PENELEC | 30 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 4/6/2001 |  |  | 12/3/2003 | 12/3/2003
PJM | G22 | North Wales 34.5 kV | Merck | PA | Montgomery | In Service | PECO | 38 | 38 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/6/2001 |  |  | 9/30/2002 | 9/30/2002
PJM | G24 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 1.9 | 1.9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 5/1/2001 |  |  | 6/8/2002 | 6/8/2002
PJM | G25 | Marion 26.4kV | Baler LF | NJ | Bergen | In Service | PSEG | 3.8 | 3.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 5/1/2001 |  |  | 5/1/2003 | 5/1/2003
PJM | G26 | England 138kV |  | NJ | Cape May | Withdrawn | AEC | 350 | 350 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/3/2001 | 1/10/2002
PJM | G27 | Churchtown 230kV |  | NJ | Salem | Withdrawn | AEC | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/3/2001 | 1/10/2002
PJM | G28 | Vienna 230kV |  | MD | Dorchester | Withdrawn | DPL | 390 | 390 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/3/2001 |  |  | 12/1/2004
PJM | G29 | Indian River 138kV |  | DE | Sussex | Withdrawn | DPL | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/3/2001 | 1/10/2002
PJM | G30 | Perryman 115kV | Perryman 51 | MD | Harford | In Service | BGE | 10 | 10 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 5/7/2001 |  |  | 6/1/2001 | 6/1/2001
PJM | G30_W51 | Fort Martin 500 kV | Longview ST1 | WV | Monongalia | In Service | APS | 600 | 600 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 5/21/2001 |  |  | 4/22/2011 | 6/1/2008
PJM | G30_W52 | Oak Grove 138 kV | Oak Grove CT1 & CT2 | WV | Pleasants | In Service | APS | 54 | 54 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/23/2001 |  |  | 6/1/2003 | 6/1/2003
PJM | G30_W53 | South Bend 500 kV | South Bend CT1 - CT4 | PA | Armstrong | In Service | APS | 104 | 104 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/23/2001 |  |  | 6/1/2003 | 6/1/2003
PJM | G30_W55 | Kempton 500 kV |  | MD | Unknown | Withdrawn | APS | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 5/29/2001 | 11/19/2002 |  | 1/1/2006
PJM | G31 | Johnstown 230kV |  | PA | Indiana | Withdrawn | PENELEC | 610 | 610 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/30/2001 | 4/11/2003 |  | 12/1/2005
PJM | G32 | TMI - Juniata 500kV |  | PA | York | Withdrawn | ME | 675 | 675 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 5/31/2001 |  |  | 6/1/2005
PJM | G33 | Brunner Island 230kV |  | PA | York | Withdrawn | PPL | 1200 | 1200 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/31/2001
PJM | G34 | Frackville 69kV |  | PA | Schuylkill | Withdrawn | PPL | 51.6 | 51.6 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 7/2/2001
PJM | G35 | Chalk Point |  | MD | St. Mary's | Withdrawn | PEPCO | 340 | 340 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/11/2001 | 9/25/2003 |  | 12/1/2004
PJM | G36 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 107 | 107 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 7/16/2001 |  |  | 4/1/2002 | 4/1/2002
PJM | G36_W58 | Horse Shoe Run 69 kV |  | WV | Preston | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 7/19/2001
PJM | G37 | Atlantic |  | NJ | Monmouth | Withdrawn | JCPL | 471 | 471 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/19/2001 | 4/10/2002
PJM | G38 | Portland |  | PA | Northampton | Withdrawn | ME | 86 | 86 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/19/2001 | 4/10/2002 |  | 12/1/2004
PJM | G39 | Joppatowne 13kV |  | MD | Baltimore County | Withdrawn | BGE | 4.2 | 4.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 7/19/2001 | 6/13/2002 |  | 6/1/2002
PJM | G40 | Warren 230kV |  | PA | Warren | Withdrawn | PENELEC | 260 | 260 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/20/2001 | 3/15/2002
PJM | G41 | Croydon |  | PA | Bucks | Withdrawn | PECO | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/26/2001 | 3/18/2002
PJM | G42 | Keystone/Conemaugh 500kV |  | PA | Indiana | Withdrawn | PENELEC | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/26/2001 | 4/10/2002 |  | 12/1/2004
PJM | G43 | Homer City |  | PA | Indiana | Withdrawn | PENELEC | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/30/2001 | 4/9/2002
PJM | G44 | Dupont Seaford 69kV | DuPont Seaford | DE | Sussex | Deactivated | DPL | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2001 |  |  | 6/1/2002 | 6/1/2002
PJM | G45 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 575 | 575 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/30/2001 | 6/18/2003 |  | 12/1/2005
PJM | G46 | Peach Bottom 500kV | Peach Bottom 2 & 3 | PA | York | In Service | PECO | 70 | 70 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2001 |  |  | 12/31/2001 | 12/31/2001
PJM | G47 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 32 | 32 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2001 | 4/10/2002
PJM | G48 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/31/2001 | 6/11/2003 |  | 12/1/2003
PJM | G49 | Clinton 69kV |  | PA | Lycoming | Withdrawn | PPL | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/31/2001 | 3/13/2002
PJM | G50 | Dickerson 230kV |  | MD | Frederick | Withdrawn | PEPCO | 910 | 910 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2001 | 5/25/2002 |  | 12/1/2005
PJM | G51 | Keystone 500kV |  | PA | Armstrong | Withdrawn | PENELEC | 75 | 75 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2001 | 3/25/2002
PJM | G51_W60 | Hatfield Ferry 500 kV | Greene Energy Resource Recovery Project | PA | Greene | Withdrawn | APS | 525 | 525 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2001 | 3/19/2013 | Customer Initiated Withdrawal | 8/1/2015
PJM | G51_W61 | Gates Hill 138 kV |  | PA | Fayette | Withdrawn | APS | 525 | 525 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2001 | 7/1/2002 |  | 1/1/2006
PJM | G51_W62 | Eastalco 230 kV | Catoctin CC | MD | Frederick | Withdrawn | APS | 640 | 640 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2001 | 4/21/2010 | Customer Milestone Not Met | 3/1/2013
PJM | G51_W63 | Upton 34.5 kV | Upton | PA | Franklin | In Service | APS | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2001 |  |  | 4/1/2003 | 4/1/2003
PJM | H01 | Susquehanna 500kV |  | PA | Columbia | Withdrawn | PPL | 2 | 2 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 7/26/2001 |  |  | 12/1/2003
PJM | H02 | Susquehanna 230kV | Susquehanna #1 | PA | Columbia | In Service | PPL | 9 | 9 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 8/20/2001 |  |  | 6/1/2007 | 6/1/2007
PJM | H03 | Susquehanna 500kV | Susquehanna #2 | PA | Columbia | In Service | PPL | 9 | 9 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 8/21/2001 |  |  | 12/1/2003 | 12/1/2003
PJM | H04 | Wright 69kV (Wind) |  | PA | Luzerne | Withdrawn | PPL | 16.9 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 9/7/2001 |  |  | 12/1/2002
PJM | H04_W64 | Henry 138 kV |  | WV | Grant | Withdrawn | APS | 150 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 9/17/2001 | 6/29/2004 |  | 12/31/2005
PJM | H05 | Riverside 230/115kV |  | MD | Baltimore County | Withdrawn | BGE | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/18/2001 | 8/6/2002 |  | 12/1/2007
PJM | H05_W65 | Tallmansville 138 kV |  | WV | Upshur | Withdrawn | APS | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/15/2001 |  |  | 7/1/2005
PJM | H06 | Chichester 230kV | Phillips Island | PA | Philadelphia | In Service | PECO | 25 | 25 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/22/2001 |  |  | 12/31/2004 | 12/31/2004
PJM | H07 | Salem - East Windsor 500kV |  | NJ | Burlington | Withdrawn | AEC | 200 | 200 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/25/2001 | 6/11/2002 |  | 6/1/2004
PJM | H08 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 560 | 560 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/7/2001 | 6/18/2002 |  | 12/1/2005
PJM | H08_W66 | Windsor 138 kV |  | WV | Unknown | Withdrawn | APS | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/14/2001 |  |  | 6/1/2005
PJM | H09 | Hooversville & Johns-Alt 230kV |  | PA | Somerset | Withdrawn | PENELEC | 635 | 635 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/15/2001 | 11/4/2002 |  | 12/1/2006
PJM | H10 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 560 | 560 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/20/2001 |  |  | 12/1/2005
PJM | H11 | New Freedom - Cardiff 230kV |  | NJ | Gloucester | Withdrawn | AEC | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/20/2001 | 7/22/2002 |  | 12/1/2005
PJM | H12 | Edgemoor 230kV | Hay Road 4 | DE | New Castle | In Service | DPL | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/20/2001 |  |  | 12/1/2005 | 12/1/2005
PJM | H13 | Dolfield | Owings Mills | MD | Baltimore County | In Service | BGE | 9 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/27/2001 |  |  | 6/1/2004 | 6/1/2004
PJM | H14 | TMI-Peach Bottom 500kV |  | PA | York | Withdrawn | ME | 1060 | 1060 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/2001 | 10/29/2002 |  | 12/1/2005
PJM | H14_W67 | Enon 138 kV |  | PA | Unknown | Withdrawn | APS | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/10/2001 | 7/8/2002 |  | 1/1/2007
PJM | H15 | Chapman-Moshannon 230kV |  | PA | Clearfield | Withdrawn | PENELEC | 520 | 520 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/20/2001 | 11/4/2002 |  | 12/1/2006
PJM | H16 | Edgemoor |  | DE | New Castle | Withdrawn | DPL | 565 | 565 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/21/2001 | 9/25/2002 |  | 12/1/2005
PJM | H17 | Salem 500kV | Salem 1 & 2 | NJ | Salem | In Service | PSEG | 115 | 115 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 1/11/2002 |  |  | 6/18/2008 | 6/1/2008
PJM | H18 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 78 | 78 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 1/11/2002 |  |  | 8/26/2008 | 12/1/2007
PJM | H19 | Hope Creek 500kV | Hope Creek 1 | NJ | Salem | In Service | PSEG | 43 | 43 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 1/11/2002 |  |  | 8/26/2008 | 12/1/2007
PJM | H20 | Oak Grove 13.8kV |  | MD | Prince George's | In Service | PEPCO | 3.5 | 3.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/21/2002 |  |  | 12/31/2003 | 5/31/2003
PJM | H20_CE12 |  |  | IL | Adams | Withdrawn | ComEd |  |  | Energy | Generation Interconnection | Coal |  |  | Withdrawn |  | 1/21/2002 |  |  | 6/6/2001
PJM | H21 | Ironwood 230kV |  | PA | Lebanon | Withdrawn | ME | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/24/2002 |  |  | 12/1/2005
PJM | H21_W68 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS | 300 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/29/2002 |  |  | 9/25/2007 | 9/30/2007
PJM | H22 | Erie South |  | PA | Erie | Withdrawn | PENELEC | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/30/2002 | 3/17/2003 |  | 6/1/2006
PJM | H23 | Bear Creek |  | PA | Luzerne | Withdrawn | PPL | 10 |  | Energy | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/30/2002 | 10/25/2002 |  | 12/1/2002
PJM | H23_W69 | Bluestone Dam 46 kV |  | WV | Summers | Withdrawn | APS | 41 | 41 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 1/29/2002 |  |  | 6/1/2006
PJM | H23_W70 | Kelso Gap 138 kV | Kelso Gap WF | MD | Garrett | In Service | APS | 100 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/30/2002 |  |  | 10/26/2010 | 11/6/2006
PJM | H24 | Forest 230kV |  | PA | Elk | Withdrawn | PENELEC | 575 | 575 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/31/2002 | 11/13/2002 |  | 6/1/2006
PJM | H25 | Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 500 | 500 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/31/2002 |  |  | 6/1/2007
PJM | H26 | Eagle Point 230kV |  | NJ | Gloucester | Withdrawn | PSEG | 25 | 25 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required |  | 1/31/2002 | 7/3/2003 |  | 12/1/2003
PJM | H27 | Marion 26.4kV | BCUA LF | NJ | Bergen | In Service | PSEG | 1 | 1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2002 |  |  | 12/1/2002 | 12/1/2002
PJM | H27_W71 | McConnellsburg-Guilford 138 kV |  | PA | Fulton | Withdrawn | APS | 252 | 252 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/31/2002 | 4/10/2003 |  | 5/1/2004
PJM | H27_W72 | McConnellsburg-Cherry Run 138 kV |  | PA | Fulton | Withdrawn | APS | 350 | 350 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/31/2002 |  |  | 5/1/2004
PJM | I01 | Ontario 23kV | Jersey Atlantic WF | NJ | Atlantic | In Service | AEC | 7.5 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 2/13/2002 |  |  | 12/30/2005 | 12/30/2005
PJM | I02 | Erie West-Ashtabula 345kV |  | OH | Ashtabula | Withdrawn | PENELEC | 35 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/15/2002 | 5/7/2003 |  | 12/1/2007
PJM | I02_W73 | Harrison 500 kV | Harrison 1, 2, 3 | WV | Harrison | In Service | APS | 35 | 35 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 3/7/2002 |  |  | 9/22/2004 | 9/22/2004
PJM | I03 | TMI-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PPL | 70 | 70 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/20/2002 | 4/28/2003 | Customer Milestone Not Met | 6/1/2005
PJM | I03_W74 | Savage 138kV | Savage Mtn WF | PA | Allegheny | Withdrawn | APS | 40 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/27/2002 | 11/18/2009 | Customer Initiated Withdrawal | 9/30/2011
PJM | I04 | Somerset-Allegheny 115kV | Stonycreek | PA | Somerset | Withdrawn | PENELEC | 45 | 9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 3/29/2002 | 4/14/2005 |  | 12/31/2005
PJM | I05 | Whiteoak (sub153) 13kV |  | MD | Calvert | Withdrawn | PEPCO | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/2/2002 | 5/21/2003 |  | 12/1/2003
PJM | I06 | Greenwich Pumphousse 2.4kV | Repauno Unit 1 | NJ | Unknown | In Service | AEC | 1.7 |  | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/8/2002 |  |  | 5/1/2003 | 5/1/2003
PJM | I07 | W. H. Sammis 345kV |  | OH | Jefferson | Withdrawn | PENELEC | 1860 | 1860 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 4/11/2002 | 12/10/2002 |  | 5/1/2005
PJM | I08 | Cromby 230kV |  | PA | Chester | Withdrawn | PECO | 870 | 870 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/19/2002 |  |  | 5/1/2005
PJM | I09 | Bath County 500kV |  | VA | Bath | Withdrawn | APS | 252 | 252 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn |  | 5/10/2002 | 1/15/2004 |  | 6/1/2009
PJM | I10 | Bethesda (Sub 6) |  | MD | Montgomery | In Service | PEPCO | 2 |  | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/11/2002 |  |  | 10/1/2004 | 10/1/2004
PJM | I11 | Cardiff 230kV |  | NJ | Atlantic | Withdrawn | AEC | 450 | 450 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/19/2002 | 2/23/2004 |  | 5/1/2006
PJM | I12 | Grand Point 69kV | Orchard Park Generating Station | PA | Franklin | In Service | APS | 23.3 | 23.3 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Document Posted | 7/29/2002 |  |  | 1/1/2004 | 1/1/2004
PJM | I13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 29.4 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/30/2002 |  |  | 3/6/2008 | 3/6/2008
PJM | I14 | Upton 34.5kV | Upton | PA | Franklin | In Service | APS | 4.1 | 4.1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2002 |  |  | 6/1/2004 | 6/1/2004
PJM | I15 | Scalp Level 115kV |  | PA | Somerset | Withdrawn | PENELEC | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/31/2002 | 1/7/2003 |  | 5/1/2003
PJM | I16 | Atwell 25kV |  | PA | Butler | Withdrawn | APS | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/31/2002 | 2/7/2003 |  | 5/1/2003
PJM | I17 | Pine Grove 69kV |  | PA | Berks | Withdrawn | PPL | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/31/2002 | 2/7/2003 |  | 5/1/2003
PJM | I18 | South Park 25kV |  | PA | Allegheny | Withdrawn | APS | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/31/2002 |  |  | 5/1/2003
PJM | I19 | Level Green 25kV |  | PA | Westmoreland | Withdrawn | APS | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/31/2002 | 2/7/2003 |  | 5/1/2003
PJM | I20 | Wycoff 25kV |  | PA | Allegheny | Withdrawn | APS | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/31/2002 | 2/7/2003 |  | 5/1/2003
PJM | I22 | Hinton 46kV |  | WV | Summers | Withdrawn | APS | 41 | 41 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn |  | 7/31/2002 | 11/4/2003 |  | 9/1/2004
PJM | J01 | Monterey 69kV |  | VA | Highland | Withdrawn | APS | 41 |  | Energy | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/28/2002 | 1/20/2004 |  | 12/31/2004
PJM | J02 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/9/2002 |  |  | 12/1/2005
PJM | J03 | Edgemoor |  | DE | New Castle | Withdrawn | DPL | 565 | 565 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/26/2002 | 2/12/2004 |  | 12/1/2005
PJM | J03_CE14 | Sublette Wind Farm |  | IL | Lee | Withdrawn | ComEd | 4 | 4 | Capacity | Generation Interconnection | Wind | Not Required | Document Posted | Not Required | Withdrawn | 10/15/2002 | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006
PJM | J04 | Bustleton 138kV |  | NJ | Burlington | Withdrawn | PSEG | 7 | 7 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 10/18/2002 | 8/4/2004 |  | 11/1/2004
PJM | J04_CE15 | West Brooklyn Wind Farm |  | IL | Lasalle | Withdrawn | ComEd | 25 | 5 | Capacity | Generation Interconnection | Wind | Not Required | Document Posted | Not Required | Withdrawn | 10/20/2002 | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006
PJM | J05 | Huron 69kV | Borgata D1 / D2 | NJ | Atlantic | In Service | AEC | 8 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/25/2002 |  |  | 7/30/2003 | 7/30/2003
PJM | J06 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 34 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/25/2002 | 5/14/2003 |  | 12/1/2003
PJM | J06_CE16 |  |  | IL | Adams | Withdrawn | ComEd |  |  | Energy | Generation Interconnection | Hydro |  | Withdrawn |  |  | 10/31/2002 |  |  | 8/1/2005
PJM | J07 | North Franklin 138kV | Liberty Gap WF | WV | Pendleton | Withdrawn | APS | 155 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2002 | 6/28/2010 | Customer Initiated Withdrawal | 11/30/2011
PJM | J08 | Whiteoak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 8 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/12/2002 |  |  | 8/15/2004 | 8/15/2004
PJM | J09 | Harrisburg Authority | Harrisburg Municipal Solid Waste Authority | PA | Dauphin | In Service | PPL | 26 | 26 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2003 |  |  | 4/24/2006 | 4/24/2006
PJM | K01 | Salem 69kV | Mannington Mills Units 1,2,3 | NJ | Salem | Deactivated | AEC | 8 | 8 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Document Posted | 2/10/2003 |  |  | 7/1/2004 | 7/1/2004
PJM | K02 | East Towanda-Moshannon 230kV | Laurel Hill | PA | Lycoming | In Service | PENELEC | 70 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/25/2003 |  |  | 10/29/2012 | 9/25/2012
PJM | K02_CE18 | Baileyville Wind Farm | Baileyville Wind Farm | IL | Stephenson | Withdrawn | ComEd | 80 | 16 | Capacity | Generation Interconnection | Wind | Not Required | Document Posted | Not Required | Document Posted | 2/26/2003 | 8/26/2013 | Customer Milestone Not Met | 12/31/2011
PJM | K03 | Wright 69kV |  | PA | Luzerne | Withdrawn | PPL | 39.6 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/3/2003 | 6/5/2003
PJM | K04 | Camden 26kV | Pennsauken Sanitary Landfill / Aluminum Shapes | NJ | Camden | In Service | PSEG | 5.1 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 4/15/2003 |  |  | 6/30/2005 | 6/30/2005
PJM | K04_CE17 | Lena Wind Farm |  | IL | Stephenson | Withdrawn | ComEd | 80 | 16 | Capacity | Generation Interconnection | Wind | Not Required | Document Posted | Not Required | Withdrawn | 4/15/2003 | 2/11/2005 | Customer Initiated Withdrawal | 6/1/2006
PJM | K04_CE19 | Freeport Wind Farm | Freeport Wind Farm | IL | Stephenson | Withdrawn | ComEd | 80 | 16 | Capacity | Generation Interconnection | Wind | Not Required | Document Posted | Not Required | Document Posted | 4/15/2003 | 9/26/2011 | Customer Milestone Not Met | 10/15/2011
PJM | K05 | Cedar 69kV |  | NJ | Ocean | Withdrawn | AEC | 0.12 |  | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/23/2003 |  |  | 6/1/2003
PJM | K06 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/6/2003 |  |  | 11/1/2004 | 11/1/2004
PJM | K07 | Easton 69kV | Easton Utilities Substation 2 | MD | Talbot | In Service | DPL | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/7/2003 |  |  | 11/1/2004 | 11/1/2004
PJM | K07_CE20 | Benson Wind Farm | Benson Wind Farm | IL | Woodford | Withdrawn | ComEd | 158 | 31.6 | Capacity | Generation Interconnection | Wind | Not Required | Document Posted | Not Required | Document Posted | 5/16/2003 | 9/18/2009 | Customer Initiated Withdrawal | 12/31/2010
PJM | K08 | Morgantown / Oak Grove |  | MD | Charles | Withdrawn | PEPCO |  | 1800 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 5/21/2003 | 8/13/2003
PJM | K09 | Bear Creek |  | PA | Luzerne | Withdrawn | PPL | 34 | 6.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/5/2003 | 1/9/2004 |  | 6/1/2004
PJM | K10 | Somerset 115kV |  | PA | Somerset | Withdrawn | PENELEC |  | 6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 7/16/2003 | 4/14/2005 | Customer Milestone Not Met | 12/31/2005
PJM | K11 | Greenland Gap 500kV | Greenland Gap WF | WV | Grant | In Service | APS |  | 60 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/25/2003 |  |  | 10/1/2007 | 9/30/2007
PJM | K12 | Somerset-Allegheny 115kV |  | PA | Somerset | Withdrawn | PENELEC | 13.6 | 2.72 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/28/2003 | 4/14/2005 | Customer Milestone Not Met | 12/31/2005
PJM | K13 | Hooversville 115kV | Forward WF | PA | Somerset | In Service | PENELEC | 0 | 5.88 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/28/2003 |  |  | 3/6/2008 | 9/1/2007
PJM | K14 | Monterey 69kV |  | VA | Highland | Withdrawn | APS |  | 7 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 7/28/2003 | 1/20/2004
PJM | K15 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL |  | 6.8 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 7/28/2003 | 1/9/2004
PJM | K16 | Birdsboro 69kV |  | PA | Berks | Withdrawn | ME |  | 9.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/28/2003 | 2/19/2004 |  | 8/1/2004
PJM | K17 | Emerald 6 25kV |  | PA | Greene | Withdrawn | APS |  | 5 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/28/2003 | 2/12/2004 |  | 6/1/2004
PJM | K18 | Arnold (Green Mountain) 115kV | Green Mountain | PA | Somerset | Deactivated | PENELEC |  | 2.08 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2003 |  |  | 8/13/2004 | 8/13/2004
PJM | K19 | Backbone Mountain 138kV | Backbone WF | WV | Tucker | In Service | APS | 0 | 18 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2003 |  |  | 6/1/2001 | 11/12/2006
PJM | K20 | Mill Run 25 kV | Mill Run WF | PA | Fayette | In Service | APS |  | 3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2003 |  |  | 4/1/2002 | 7/28/2005
PJM | K21 | East Carbondale 69kV | Waymart | PA | Wayne | In Service | PPL |  | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2003 |  |  | 7/1/2004 | 7/1/2004
PJM | K22 | Somerset 22.86kV | Somerset WF | PA | Somerset | In Service | PENELEC |  | 1.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2003 |  |  | 1/1/1999 | 8/13/2004
PJM | K23 | Meyersdale North 115 kV | Meyersdale WF | PA | Somerset | In Service | PENELEC | 0 | 5.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2003 |  |  | 7/1/2004 | 7/1/2004
PJM | K24 | Henry 138kV |  | WV | Grant | Withdrawn | APS |  | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required |  | 7/30/2003 | 7/21/2004 |  | 12/1/2005
PJM | K25 | Savage 138kV | Savage Mtn WF | PA | Allegheny | Withdrawn | APS |  | 8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/30/2003 | 11/12/2009 | Customer Initiated Withdrawal | 9/30/2011
PJM | K26 | North Franklin 138kV | Liberty Gap WF | WV | Pendleton | Withdrawn | APS |  | 31 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/30/2003 | 6/28/2010 | Customer Initiated Withdrawal | 11/30/2011
PJM | K27 | Calvert Cliffs 500kV |  | MD | Calvert | Withdrawn | BGE |  | 35 | Capacity | Generation Interconnection | Nuclear | Document Posted | Interim Study | Not Required | Document Posted | 7/30/2003 | 8/20/2005 |  | 6/1/2004
PJM | K28 | Kelso Gap 138kV | Kelso Gap WF | MD | Garrett | In Service | APS |  | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2003 |  |  | 10/26/2010 | 11/6/2006
PJM | K29 | Ontario |  | NJ | Atlantic | Withdrawn | AEC |  | 1.5 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 7/31/2003 | 9/28/2004
PJM | L01 | Morgantown / Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 | 1800 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 8/1/2003 | 4/8/2004 |  | 1/6/2008
PJM | L01_AEP137 | Bellefonte-N. Proctorville 138kV |  | OH | Lawrence | Withdrawn | AEP | 165 | 165 | Capacity | Generation Interconnection | Biomass | Not Required | Not Required | Document Posted | Document Posted | 8/27/2003 | 3/21/2012 | Customer Milestone Not Met | 12/31/2012
PJM | L01_CE21 | Pearl City Wind Farm |  | IL | Stephenson | Withdrawn | ComEd | 15 | 3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 8/5/2003 | 11/1/2005 | Customer Milestone Not Met | 12/31/2005
PJM | L02 | Pleasantville 12 kV | Pleasantville / AC LF Unit 1 | NJ | Atlantic | In Service | AEC | 1.5 | 1.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/10/2003 |  |  | 1/30/2005 | 1/30/2005
PJM | L03 | Morgantown | Morgantown LF | PA | Berks | Withdrawn | PPL | 0.8 |  | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/10/2003 | 6/3/2008 | Customer Initiated Withdrawal | 5/31/2009
PJM | L04 | Chestnut Ridge 138 kV |  | PA | Westmoreland | Withdrawn | APS | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 10/8/2003 | 7/7/2004 |  | 12/31/2005
PJM | L05 | Bear Creek 69kV |  | PA | Luzerne | Withdrawn | PPL | 25 | 25 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 10/10/2003 | 4/30/2004 |  | 6/30/2005
PJM | L05_CE22 | Camp Grove | Camp Grove Wind Farm | IL | Stark | In Service | ComEd | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/15/2003 |  |  | 12/14/2007 | 9/1/2006
PJM | L06 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/20/2003 | 6/22/2004 |  | 6/1/2006
PJM | L07 | Jenkins-Harwood #2 69kV | Mountain Top | PA | Luzerne | Withdrawn | PPL | 42.9 | 8.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 10/23/2003 | 5/18/2005 |  | 12/31/2005
PJM | L08 | Holtwood 69kV | Holtwood | PA | Lancaster | In Service | PPL | 2 | 2 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 11/7/2003 |  |  | 10/1/2003 | 8/16/2004
PJM | L09 | Montour #1 230kV | Montour #1 | PA | Montour | In Service | PPL | 2 | 2 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 11/7/2003 |  |  | 10/1/2003 | 8/16/2004
PJM | L10 | Hatfield 500 kV |  | PA | Greene | Withdrawn | APS | 520 | 520 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 11/12/2003 | 7/12/2004 |  | 12/1/2006
PJM | L11 | Rockwood 25 kV |  | PA | Somerset | Withdrawn | APS | 9.9 | 2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 12/2/2003 | 4/15/2005 | Customer Initiated Withdrawal | 12/1/2005
PJM | L12 | Essex |  | NJ | Essex | Withdrawn | PSEG | 6.2 | 6.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 12/4/2003 | 8/31/2004 |  | 9/30/2004
PJM | L12_CE23 | West Brooklyn II | West Brooklyn WF | IL | Lee | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 12/8/2003 | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007
PJM | L12_CE24 | Willow Creek Wind Farm |  | IL | Lee | Withdrawn | ComEd | 79 | 15.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 12/10/2003 | 2/11/2005 | Customer Initiated Withdrawal | 12/1/2005
PJM | L13 | Rockwood | Casselman WF1 | PA | Somerset | In Service | PENELEC | 40 | 8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/19/2003 |  |  | 1/11/2008 | 12/31/2007
PJM | L13_CE25 | Geneva | City of Geneva Units 1-5 | IL | Kane | In Service | ComEd | 29 | 29 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/26/2003 |  |  | 6/1/2005 | 6/1/2005
PJM | L13_CE26 | Heartland Grand Ridge |  | IL | Lasalle | Withdrawn | ComEd | 175 | 35 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 1/18/2004 | 8/9/2006 | Customer Initiated Withdrawal | 10/30/2006
PJM | L13_CE27 | Heartland Wind Livingston |  | IL | Livingston | Withdrawn | ComEd | 225 | 45 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 1/18/2004 | 10/3/2005 | Customer Initiated Withdrawal | 10/30/2006
PJM | L14 | Berlin 69kV Tap 5 MW |  | MD | Worcester | Withdrawn | AEC | 5 | 5 | Capacity | Generation Interconnection | Diesel | Document Posted | Withdrawn |  |  | 1/20/2004 | 8/19/2004 | Customer Milestone Not Met | 7/1/2005
PJM | L16 | Monterey 69KV |  | VA | Highland | Withdrawn | APS | 35 | 35 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/22/2004 | 9/20/2004 |  | 12/1/2005
PJM | L17 | Rolling Hills | Rolling Hills | PA | Berks | Deactivated | ME | 6 |  | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/22/2004 |  |  | 4/1/2005 | 4/1/2005
PJM | L18 | Bear Creek | Bear Creek WF | PA | Luzerne | In Service | PPL | 26 | 5.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/28/2004 |  |  | 2/26/2006 | 2/26/2006
PJM | L19 | Karthaus 230kV | Karthaus | PA | Clearfield | Withdrawn | APS | 290 | 290 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 1/28/2004 | 3/24/2010 | Customer Initiated Withdrawal | 12/31/2012
PJM | L20 | Birdsboro 13.2kV |  | PA | Berks | Withdrawn | ME | 9.9 | 9.9 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 1/30/2004 | 8/4/2004 |  | 3/31/2005
PJM | L21 | Hudson #2 |  | NJ | Hudson | Withdrawn | PSEG |  | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/30/2004 | 9/2/2004 |  | 1/1/2006
PJM | M01 | Morgantown-Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 1800 | 1800 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/1/2004 | 3/18/2005 | Customer Milestone Not Met | 1/1/2008
PJM | M02 | Jenkins-Harwood #2 | Mountain Top | PA | Luzerne | Withdrawn | PPL | 8.1 | 8.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 2/23/2004 | 5/18/2005 |  | 12/31/2005
PJM | M03 | Cardiff |  | NJ | Atlantic | Withdrawn | AEC | 150 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/23/2004 | 4/5/2005 | Customer Milestone Not Met | 6/1/2005
PJM | M04 | Calvert Cliffs | Clavert Cliffs 1 and 2 | MD | Calvert | In Service | BGE | 63 |  | Energy | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 2/25/2004 |  |  | 6/30/2005 | 6/30/2005
PJM | M06 | Grand Point |  | PA | Franklin | Withdrawn | APS | 30.5 | 30.5 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Withdrawn |  | 3/11/2004 | 10/20/2005 |  | 6/1/2006
PJM | M07 | Peckville (Archbald) | Archbald | PA | Lackawanna | In Service | PPL | 6.3 | 6.3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/12/2004 |  |  | 3/15/2004 | 3/15/2004
PJM | M08 | Somerset-Allegheny | Stonycreek | PA | Somerset | Withdrawn | PENELEC | 65 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 3/29/2004 | 4/14/2005 | Customer Milestone Not Met | 12/31/2005
PJM | M09_CE28 | Wempletown 345kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 4/14/2004 | 2/11/2005 | Customer Initiated Withdrawal | 11/30/2006
PJM | M11 | Susquehanna #1 | Susquehanna #1 | PA | Luzerne | In Service | PPL | 111 | 111 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 5/19/2004 |  |  | 7/24/2010 | 7/24/2010
PJM | M12 | Susquehanna #2 | Susquehanna #2 | PA | Luzerne | In Service | PPL | 107 | 107 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 5/19/2004 |  |  | 8/18/2011 | 8/18/2011
PJM | M13 | Amboy |  | IL | Lee | Withdrawn | ComEd | 3.3 | 3.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 5/27/2004 | 1/4/2005 | Customer Initiated Withdrawal | 6/1/2005
PJM | M14 | Churchtown-Cumberland 230kV |  | NJ | Atlantic | Withdrawn | AEC | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/9/2004 | 12/13/2004 | Customer Initiated Withdrawal | 6/15/2006
PJM | M15 | Union City 230kV |  | PA | Erie | Withdrawn | PENELEC | 302 | 301.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 6/9/2004 | 10/17/2005 | Customer Initiated Withdrawal | 6/1/2007
PJM | M17 | Mount Zion 13.8 kV |  | MD | Montgomery | Withdrawn | PEPCO | 4 | 4 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 6/15/2004 | 9/30/2004 |  | 5/1/2005
PJM | M18 | Dixon-Mendota 34kV |  | IL | Lee | Withdrawn | ComEd | 1.65 |  | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 6/17/2004 | 1/3/2006 |  | 12/31/2005
PJM | M19 | Otter Point | Otter Point LF-1 | MD | Baltimore County | In Service | BGE | 4.5 |  | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 6/25/2004 |  |  | 9/1/2006 | 9/1/2006
PJM | M20 | Chestnut Valley 25kV |  | PA | Fayette | Withdrawn | APS | 5 | 5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Withdrawn |  | 7/13/2004 | 7/7/2006 | Customer Initiated Withdrawal | 5/30/2006
PJM | M21 | Rochelle | City of Rochelle, IL | IL | Ogle | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Document Posted | 7/23/2004 |  |  | 12/31/2006 | 11/11/2005
PJM | M22 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 125 | 125 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 7/23/2004 | 10/23/2006 | Customer Milestone Not Met | 2/1/2008
PJM | M23 | Henry 138kV | Mt Storm WF | WV | Grant | Withdrawn | APS | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/26/2004 | 2/4/2016 | Customer Milestone Not Met | 12/31/2015
PJM | M24 | Grassy Falls | Beech Ridge / Field Mtn WF | WV | Greenbrier | In Service | APS | 186 | 37.2 | Capacity | Generation Interconnection | Wind; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 7/27/2004 |  |  | 12/1/2014 | 11/1/2007
PJM | M25 | South Reading (United Corrstack) 69kV | United Corrstack | PA | Berks | Withdrawn | ME | 11 | 2 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2004 | 11/18/2005 | Customer Milestone Not Met | 12/1/2006
PJM | M26 | Champion | Beech Hollow | PA | Washington | Withdrawn | APS | 150 | 150 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/29/2004 | 7/8/2013 | Customer Initiated Withdrawal | 6/1/2015
PJM | M27 | Eddystone 138kV | Eddystone | PA | Delaware | In Service | PECO | 7 | 7 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2004 |  |  | 6/17/2004 | 12/1/2006
PJM | M28 | Elwood-Dresden 345kV | Indeck-Elwood Energy Center | IL | Will | Withdrawn | ComEd | 600 | 600 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2004 | 11/30/2006 | Customer Milestone Not Met | 12/31/2011
PJM | N01 | Graceton-Nottingham 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/2/2004 | 8/30/2005 | Customer Milestone Not Met | 6/1/2008
PJM | N02 | Peach Bottom |  | PA | York | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/2/2004 | 8/30/2005 | Customer Milestone Not Met | 6/1/2008
PJM | N02_AEP139 | McClung 138kV |  | WV | Greenbrier | Withdrawn | AEP | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/4/2004 | 6/23/2005 | Customer Milestone Not Met | 9/1/2006
PJM | N03 | Edgemoor 69kV | Hay Road 2 | DE | New Castle | In Service | DPL | 7 | 7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/25/2004 |  |  | 8/9/2004 | 6/1/2006
PJM | N04 | Edgemoor 230kV |  | DE | New Castle | Withdrawn | DPL | 8 | 8 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 8/25/2004 | 10/12/2004 |  | 8/9/2004
PJM | N05 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/25/2004 |  |  | 8/9/2004 | 6/1/2006
PJM | N06 | Hamilton 12kV | Pine Hurst Acres | PA | Northumberland | In Service | PPL | 0.047 |  | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/16/2004 |  |  | 3/1/2005 | 3/1/2005
PJM | N07 | Monterey 69kV | Highland New Wind | VA | Highland | Withdrawn | APS | 39 | 7.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 9/28/2004 | 3/10/2020 |  | 4/29/2021
PJM | N08 | Dans Mountain |  | PA | Allegheny | Withdrawn | APS | 125 | 25 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/28/2004 | 9/1/2005 | Customer Initiated Withdrawal | 12/31/2005
PJM | N09 | Grassy Falls 138kV | West Greenbrier | WV | Greenbrier | Withdrawn | APS | 90 | 90 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Withdrawn | 10/4/2004 | 8/26/2008 |  | 3/31/2009
PJM | N10 | Grangston 138 kV | Big Sandy Peaker Plant | WV | Wayne | In Service | AEP | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/11/2004 |  |  | 6/1/2005 | 6/1/2005
PJM | N11 | Wolf Hills 138 kV | Wolf Hills Energy Plant | VA | Washington | In Service | AEP | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/11/2004 |  |  | 6/1/2005 | 6/1/2005
PJM | N12 | North Haverhill 69 kV | North Haverhill | OH | Scioto | In Service | AEP | 75 | 75 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 10/13/2004 |  |  | 6/1/2009 | 6/1/2009
PJM | N13 | Beaver Valley |  | PA | Beaver | In Service | DL | 1630 | 1630 | Capacity | Generation Interconnection | Nuclear | Not Required | Not Required | Not Required | Document Posted | 11/1/2004 |  |  | 1/1/2005 | 1/1/2005
PJM | N14 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 24 | 5.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/22/2004 |  |  | 6/1/2006 | 6/1/2006
PJM | N15 | LaSalle 138 kV | Grand Ridge Energy LLC | IL | Lasalle | In Service | ComEd | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/2/2004 |  |  | 11/1/2009 | 11/1/2009
PJM | N16 | Kent-Harrington 69kV | Central Landfill Units 1-4 | DE | New Castle | In Service | DPL | 4 |  | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 12/9/2004 |  |  | 12/7/2006 | 12/7/2006
PJM | N17 | Laurel-Sussex 69kV | Southern Landfill Units 1-4 | DE | New Castle | In Service | DPL | 3 |  | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 12/9/2004 |  |  | 10/24/2006 | 10/24/2006
PJM | N18 | Clinton-Collier 345kV |  | PA | Allegheny | Withdrawn | DL | 19.2 | 19.2 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 12/22/2004 | 2/16/2005 | Customer Initiated Withdrawal | 12/31/2005
PJM | N19 | Paw Paw 12 kV |  | IL | Lee | Withdrawn | ComEd | 1.65 | 1.65 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 12/28/2004 | 9/6/2005 | Customer Milestone Not Met | 3/31/2006
PJM | N20 | Poplar Grove 34kV |  | IL | Boone | Withdrawn | ComEd | 9.9 | 9.9 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 1/6/2005 | 2/17/2005 | Customer Initiated Withdrawal | 12/29/2005
PJM | N21 | Sublette Wind II | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 2.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 1/18/2005 | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007
PJM | N22 | Sublette Wind 3 | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 30 | 2.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 1/18/2005 | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007
PJM | N23 | West Brooklyn Wind 3 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 53 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 1/18/2005 | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007
PJM | N24 | West Brooklyn 4 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 53 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 1/18/2005 | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007
PJM | N25 | West Brooklyn 5 | West Brooklyn II | IL | Lee | Withdrawn | ComEd | 11 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 1/18/2005 | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007
PJM | N26 | Daleville | SECCRA LF | PA | Chester | In Service | PECO | 1.74 | 1.7 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/20/2005 |  |  | 12/31/2009 | 12/31/2009
PJM | N27 | Pequest River 34.5 kV | Warren County LF | NJ | Warren | In Service | JCPL | 3.6 | 3.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/27/2005 |  |  | 6/1/2007 | 6/1/2007
PJM | N28 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 40 | 40 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 1/27/2005 | 6/24/2005 | Customer Milestone Not Met | 2/1/2007
PJM | N29 | Roth Rock 138kV |  | MD | Garrett | Withdrawn | APS | 40 | 8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 1/28/2005 | 9/5/2007 | Customer Milestone Not Met | 12/31/2008
PJM | N30 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 5 |  | Energy | Generation Interconnection | Methane | Document Posted | Not Required | Withdrawn |  | 1/28/2005 | 4/3/2007 | Customer Initiated Withdrawal | 12/31/2007
PJM | N31 | Freemansburg 69kV | Bethlehem LF | PA | Northampton | Deactivated | PPL | 5 |  | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/28/2005 |  |  | 5/1/2008 | 5/1/2008
PJM | N32 | Gans 138kV | South Chestnut WF | PA | Fayette | In Service | APS | 50.4 | 10.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/28/2005 |  |  | 12/31/2011 | 12/24/2011
PJM | N33 | Afton 138kV | North Briery WF | WV | Preston | Withdrawn | APS | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/28/2005 | 2/16/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | N34 | Motiva | Delaware City | DE | New Castle | In Service | DPL | 250 | 142 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 1/28/2005 |  |  | 12/31/2005 | 12/31/2005
PJM | N35 | South Reading-Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9 | 9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 1/28/2005 | 12/14/2005 | Customer Initiated Withdrawal | 12/31/2005
PJM | N36 | Gold-Sabinsville 115kV | Gold Sabinsville | PA | Potter | Withdrawn | PENELEC | 50 | 10 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/28/2005 | 1/15/2014 | Customer Initiated Withdrawal | 12/15/2014
PJM | N37 | Windsor 138kV |  | PA | Washington | Withdrawn | APS | 50 | 10 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/28/2005 | 11/1/2005 | Customer Initiated Withdrawal | 11/1/2006
PJM | N38 | W. Newton-Lynn 138kV |  | OH | Hardin | Withdrawn | AEP | 120 | 24 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/28/2005 | 8/2/2005 | Customer Initiated Withdrawal | 11/1/2006
PJM | N39 | Johnstown-Altoona 230kV | Allegheny Ridge WF1 | PA | Cambria | In Service | PENELEC | 80 | 16 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/28/2005 |  |  | 3/15/2007 | 11/1/2006
PJM | N40 | Champion 345kV |  | PA | Washington | Withdrawn | DL | 300 | 300 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 1/28/2005 | 9/6/2005 | Customer Initiated Withdrawal | 5/31/2009
PJM | N41 | Mountaineer 765kV |  | WV | Mason | Withdrawn | AEP | 1200 | 1200 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 1/31/2005 | 10/21/2008 | Customer Initiated Withdrawal | 5/1/2010
PJM | N42 | Mountaineer-Belmont 765kV |  | OH | Meigs | Withdrawn | AEP | 1200 | 600 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 1/31/2005 | 12/1/2011 | Customer Initiated Withdrawal | 5/1/2010
PJM | N43 | Hanging Rock-Jefferson 765kV |  | KY | Lewis | Withdrawn | AEP | 1200 | 1200 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 1/31/2005 | 3/28/2006 | Customer Initiated Withdrawal | 5/1/2010
PJM | N44 | Dover |  | DE | Kent | Withdrawn | DPL | 1 | 1 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2005 | 10/11/2005 | Customer Milestone Not Met | 12/31/2005
PJM | N45 | Ft. Martin 500kV |  | WV | Monongalia | Withdrawn | APS | 600 | 600 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 1/31/2005 | 12/14/2005 | Customer Initiated Withdrawal | 1/31/2010
PJM | N46 | Cook 345kV |  | MI | Berrien | Withdrawn | AEP | 1120 | 1120 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 1/31/2005 | 10/18/2005 | Customer Initiated Withdrawal | 6/1/2009
PJM | N47 | Beryl 138kV | Pinnacle WF | WV | Mineral | In Service | APS | 85 | 17 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2005 |  |  | 12/31/2011 | 11/16/2011
PJM | N48 | Lancaster-Maryland 138kV |  | IL | Ogle | Withdrawn | ComEd | 84 | 84 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 1/31/2005 | 3/11/2005 | Customer Initiated Withdrawal | 12/31/2005
PJM | N49 | Salix-Claysburg 115kV |  | PA | Cambria | Withdrawn | PENELEC | 90 | 90 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 1/31/2005 | 4/14/2005 | Customer Milestone Not Met | 11/1/2006
PJM | N50 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 90 | 18 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/31/2005 | 3/7/2006 | Customer Milestone Not Met | 11/1/2006
PJM | N51 | Harwood 230kV |  | PA | Carbon | Withdrawn | PPL | 100.5 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/31/2005 | 3/7/2006 | Customer Milestone Not Met | 11/1/2006
PJM | O01 | Letort 12kV | Frey Farms LF | PA | Lancaster | Withdrawn | PPL | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 2/8/2005 | 5/26/2011 | Customer Initiated Withdrawal | 1/12/2006 | 1/12/2006
PJM | O02 | Glendon 34.5kV |  | PA | Northampton | Withdrawn | PPL | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 2/8/2005 | 8/16/2006 | Customer Milestone Not Met | 12/31/2006
PJM | O03 | Sublette | Sublette Wind Farm | IL | Lee | Withdrawn | ComEd | 11 | 2.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 2/11/2005 | 8/16/2012 | Customer Initiated Withdrawal | 4/15/2007
PJM | O04 | Camden-Richmond |  | NJ | Camden | Withdrawn | PSEG | 640 | 640 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/11/2005 | 2/1/2006 | Customer Initiated Withdrawal | 6/1/2008
PJM | O05 | Rochelle | City of Rochelle | IL | Ogle | In Service | ComEd | 22 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Document Posted | 2/22/2005 |  |  | 12/31/2006 | 6/30/2005
PJM | O06_DP01 | Altavista 115kV | Pittsylvania | VA | Pittsylvania | In Service | Dominion | 4 | 4 | Capacity | Generation Interconnection | Wood | Document Posted | Document Posted | Not Required | Document Posted | 2/24/2005 |  |  | 6/1/2006 | 6/1/2006
PJM | O07 | Poplar Grove 34.5kV | Boone Heritage WF | IL | Boone | Withdrawn | ComEd | 25 | 5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 3/1/2005 | 3/22/2007 | Customer Initiated Withdrawal | 6/30/2007
PJM | O09 | Normandy | Walnut Ridge Wind, LLC | IL | Lee | In Service | ComEd | 212 | 42.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/7/2005 |  |  | 10/15/2018 | 10/31/2018
PJM | O10 | Edgemoor 138kV | Hay Road 1-3 | DE | New Castle | In Service | DPL | 7 | 7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/14/2005 |  |  | 6/1/2005 | 6/1/2005
PJM | O11 | Bustelton 13kV | Burlington Co LF | NJ | Burlington | Deactivated | PSEG | 7 | 7 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 3/21/2005 |  |  | 8/28/2007 | 6/1/2007
PJM | O12 | Chicago Heights 138kV | Geneva Energy LLC | IL | Adams | Deactivated | ComEd | 20 | 20 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Document Posted | 3/28/2005 |  |  | 12/31/2006 | 12/1/2005
PJM | O17 | Somerset-Allegheny 115kV | Stoney Creek WF | PA | Somerset | Withdrawn | PENELEC | 65 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 4/14/2005 | 1/6/2009 | Customer Milestone Not Met | 12/1/2009
PJM | O18 | Salix-Claysburg (Krayn) 115kV | Highland WF | PA | Somerset | In Service | PENELEC | 65 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 4/21/2005 |  |  | 12/18/2008 | 12/18/2008
PJM | O19 | Somerset 115kV | Somerset (Kimberly Run) WF | PA | Somerset | Withdrawn | PENELEC | 33 | 6.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/4/2005 | 6/4/2012 | Customer Initiated Withdrawal | 5/31/2013
PJM | O20 | Lakehurst 34.5kV | Ocean Energy LF | NJ | Ocean | In Service | JCPL | 9.4 | 9.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/4/2005 |  |  | 6/1/2007 | 6/1/2007
PJM | O21 | Liberty 69kV |  | OH | Logan | Withdrawn | Dayton | 48 | 9.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/6/2005 | 10/6/2009 | Customer Initiated Withdrawal | 12/31/2008
PJM | O22 | Powerton-Goodings Grove 345kV | Top Crop WF 1 & 2 | IL | Livingston | In Service | ComEd | 300 | 60 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/11/2005 |  |  | 10/25/2010 | 10/25/2010
PJM | O23 | Powerton-Dresden 345kV | Top Crop Wind Farm | IL | Livingston | Withdrawn | ComEd | 300 | 60 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/11/2005 | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2013
PJM | O24 | Pontiac Midpoint-Dresden 345kV | Bright Stalk WF | IL | Livingston | Withdrawn | ComEd | 300 | 60 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/11/2005 | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2013
PJM | O25 | N. Salisbury 25kV | Newland Park LF | MD | Wicomico | In Service | DPL | 6 | 6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 5/12/2005 |  |  | 6/1/2007 | 6/1/2007
PJM | O26 | Pine Grove 69kV | Guilford Mills LF | PA | Schuylkill | In Service | PPL | 8 | 8 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Document Posted | 5/12/2005 |  |  | 6/30/2008 | 6/30/2008
PJM | O27 | Powerton-Goodings Grove 345kV |  | IL | Livingston | Withdrawn | ComEd | 300 | 60 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 5/13/2005 | 5/15/2012 | Customer Initiated Withdrawal | 5/31/2015
PJM | O28 | Jenkins-Harwood #2 69kV | Penobscot Mountain WF | PA | Luzerne | Withdrawn | PPL | 51 | 10.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/13/2005 | 4/15/2010 | Customer Initiated Withdrawal | 11/30/2011
PJM | O29 | Normandy 138kV | Green River Wind Farm Phase 2 | IL | Lee | In Service | ComEd | 225 | 45 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/16/2005 |  |  | 10/30/2019 | 11/25/2019
PJM | O30 | Nora |  | IL | JoDaviess | Withdrawn | ComEd | 9 |  | Energy | Generation Interconnection | Wind | Withdrawn |  |  |  | 5/16/2005 | 7/25/2005 | Customer Initiated Withdrawal | 10/1/2006
PJM | O31 | Fries 12kV | Fries Hydorelectric Plant | VA | Grayson | In Service | AEP | 5.21 | 5.21 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 5/18/2005 |  |  | 12/31/2006 | 12/31/2006
PJM | O32 | Mountaineer 765kV | Mountaineer #1 | WV | Mason | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 5/31/2005 |  |  | 5/31/2005 | 5/31/2005
PJM | O33 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 6/2/2005 |  |  | 12/31/2012 | 5/1/2012
PJM | O34 | Frederick 12kV |  | MD | Frederick | Withdrawn | APS | 3 | 3 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 6/3/2005 | 10/6/2005 | Customer Initiated Withdrawal | 5/1/2006
PJM | O35 | Providence Heights #1 138kV | Providence Heights WF | IL | Bureau | In Service | ComEd | 74 | 14.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 6/6/2005 |  |  | 6/26/2008 | 6/30/2007
PJM | O36 | Honey Brook 12kV | Honeybrook | PA | Chester | In Service | PPL | 1.6 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/6/2005 |  |  | 6/1/2011 | 6/1/2011
PJM | O37 | Belle 46kV |  | WV | Kanawha | Withdrawn | AEP | 14 | 14 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 6/23/2005 | 4/12/2006 | Customer Initiated Withdrawal | 6/1/2006
PJM | O38 | Johnstown-Altoona 230kV | North Alleghney WF | PA | Cambria | In Service | PENELEC | 50 | 10 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 6/27/2005 |  |  | 9/1/2009 | 12/15/2007
PJM | O39 | Sunbury - Dauphin 69kV | Mahantango WF | PA | Dauphin | Withdrawn | PPL | 56 | 11.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/27/2005 | 5/18/2010 | Customer Initiated Withdrawal | 6/1/2010
PJM | O40 | Pine Grove - Frailey 69kV | Pine Grove WF | PA | Schuylkill | Withdrawn | PPL | 28 | 5.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/27/2005 | 4/1/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | O42 | Cook 345 kV | Cook #1 | MI | Berrien | In Service | AEP | 84 | 84 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/6/2005 |  |  | 1/19/2007 | 12/31/2006
PJM | O43 | University Park | University Park North Energy Center | IL | Will | In Service | ComEd | 54 | 54 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/7/2005 |  |  | 6/1/2007 | 12/19/2011
PJM | O44 | West Lima 138kV |  | OH | Allen | Withdrawn | AEP | 540 | 540 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 7/19/2005 | 1/23/2006 |  | 6/1/2007
PJM | O46 | Frackville-Hauto #3 69kV | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 2 | 0.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/22/2005 |  |  | 12/1/2007 | 12/1/2007
PJM | O47 | Nora |  | IL | JoDaviess | Withdrawn | ComEd | 10 | 2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 7/25/2005 | 6/6/2014 | Customer Milestone Not Met | 12/31/2007
PJM | O48 | Hays Mill - Lookout 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 36 | 7.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/26/2005 |  |  | 6/1/2008 | 6/1/2008
PJM | O49 | Wempletown-Byron 345kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 7/26/2005 | 8/2/2012 | Customer Milestone Not Met | 12/31/2012
PJM | O50 | Powerton-Dresden 345kV | Minonk Wind Farm | IL | Woodford | In Service | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/26/2005 |  |  | 12/31/2012 | 10/31/2012
PJM | O51 | Pontiac Midpoint-Wilton Center 345kV | Cayuga Ridge South WF | IL | Livingston | In Service | ComEd | 300 | 60 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/27/2005 |  |  | 5/6/2010 | 12/31/2007
PJM | O52 | Gold-Potter Co 115kV | Potter WF | PA | Potter | Withdrawn | PENELEC | 50 | 10 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/27/2005 | 5/8/2013 | Customer Initiated Withdrawal | 12/25/2014
PJM | O53 | Beaver Valley #1 | Beaver Valley 1 | PA | Beaver | In Service | DL | 81 | 81 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/27/2005 |  |  | 6/1/2007 | 9/15/2006
PJM | O54 | Beaver Valley #2 | Beaver Valley 2 | PA | Beaver | In Service | DL | 77 | 77 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/27/2005 |  |  | 7/1/2008 | 10/23/2006
PJM | O55 | Peckville 69kV |  | PA | Lackawanna | Withdrawn | PPL | 9 | 9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 7/27/2005 | 7/17/2006 | Customer Milestone Not Met | 1/1/2007
PJM | O56 | Osterburg East 115kV | Dunning Mountain WF | PA | Bedford | Withdrawn | PENELEC | 76 | 15.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/28/2005 | 6/4/2012 | Customer Initiated Withdrawal | 3/1/2013
PJM | O57 | Kanawha 138kV |  | WV | Fayette | Withdrawn | AEP | 142 |  | Energy | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 7/28/2005 | 4/18/2006 | Customer Milestone Not Met | 6/1/2006
PJM | O58 | Tenn Eastman 138kV |  | TN | Sullivan | Withdrawn | AEP | 75 | 75 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Withdrawn | 7/28/2005 | 8/14/2008 | Customer Milestone Not Met | 6/1/2007
PJM | O59 | Gold 115kV | Gold | PA | Potter | Withdrawn | PENELEC | 99 | 19.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn | Withdrawn | 7/29/2005 | 12/21/2009 | Customer Initiated Withdrawal | 12/1/2009
PJM | O60 | Berlin 23 kV | AMP Berlin WF | PA | Somerset | Withdrawn | PENELEC | 5.4 | 1.08 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/29/2005 | 4/9/2014 | Customer Initiated Withdrawal | 1/31/2012
PJM | O61 | Lawrenceville 34.5kV |  | VA | Brunswick | Withdrawn | Dominion | 8 | 8 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/29/2005 | 3/9/2007 | Customer Initiated Withdrawal | 1/31/2007
PJM | O62 | Shackleford 34.5kV |  | VA | King and Queen | Withdrawn | Dominion | 8 | 8 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 7/29/2005 | 4/27/2006 | Customer Milestone Not Met | 10/31/2006
PJM | O63 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 525 | 525 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/29/2005 | 3/7/2006 | Customer Milestone Not Met | 6/1/2009
PJM | O64 | Grays Ferry - Island Road |  | PA | Philadelphia | Withdrawn | PECO | 201 | 201 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/29/2005 | 2/11/2006 | Customer Milestone Not Met | 6/1/2008
PJM | O65 | Olive-Dumont 345kV |  | IN | St. Joseph | Withdrawn | AEP | 650 | 650 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 7/29/2005 | 10/17/2005 | Customer Initiated Withdrawal | 7/1/2010
PJM | O68 | Dixon-Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/31/2005 | 11/15/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | O69 | Beaver Creek-Hazard 138kV |  | KY | Perry | Withdrawn | AEP | 535 | 535 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 7/31/2005 | 6/30/2006 | Customer Milestone Not Met | 7/1/2009
PJM | O70 | Susquehanna - Harwood 230kV | Nescopeck WF | PA | Luzerne | Withdrawn | PPL | 124 | 24.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2005 | 5/9/2011 | Customer Initiated Withdrawal | 12/1/2011
PJM | O71 | Hooversville 115kV |  | PA | Somerset | Withdrawn | PENELEC | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 7/31/2005 | 4/12/2006 | Customer Initiated Withdrawal | 11/30/2007
PJM | O72 | Hooversville-Central City | Shaffer Mountain WF | PA | Somerset | Withdrawn | PENELEC | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2005 | 6/12/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | O73 | Benson 345kV |  | IL | Woodford | Withdrawn | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/31/2005 | 11/15/2011 | Customer Initiated Withdrawal | 12/31/2010
PJM | P01 | Westover-Madera 115kV | Rock Run Wind Park | PA | Cambria | Withdrawn | PENELEC | 65 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/23/2005 | 1/4/2013 | Customer Initiated Withdrawal | 12/31/2011
PJM | P02 | Ohio Central 138kV |  | OH | Muskingum | Withdrawn | AEP | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/25/2005 | 8/14/2006 | Customer Initiated Withdrawal | 6/1/2007
PJM | P03 | Frackville-Hauto #3 | Locust Ridge WF | PA | Schuylkill | In Service | PPL | 1.3 | 1.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/29/2005 |  |  | 12/31/2007 | 12/31/2007
PJM | P04 | Peach Bottom 500kV | Delta | PA | York | In Service | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/8/2005 |  |  | 3/1/2011 | 3/1/2011
PJM | P05 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/8/2005 | 6/12/2006 | Customer Milestone Not Met | 6/1/2008
PJM | P06 | Cumberland 230 kV | Cumberland 2 | NJ | Cumberland | In Service | AEC | 225 | 225 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/9/2005 |  |  | 6/1/2016 | 12/31/2008
PJM | P07 | Middle 138kV |  | NJ | Cape May | Withdrawn | AEC | 122 | 122 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/9/2005 | 6/16/2006 | Customer Milestone Not Met | 12/31/2008
PJM | P08 | Possum Point |  | VA | Prince William | Withdrawn | Dominion | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 9/14/2005 | 4/24/2009 | Customer Milestone Not Met | 6/1/2014
PJM | P09 | Kerr Dam 115kV | John H. Kerr Dam Hydro Units 1(15MW), 2-7(42MW) | VA | Mecklenburg | In Service | Dominion | 27 | 27 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 9/14/2005 |  |  | 1/19/2011 | 1/19/2011
PJM | P10 | LaSalle 138kV | Grand Ridge WF | IL | Lasalle | In Service | ComEd | 190.5 | 37.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2005 |  |  | 12/1/2013 | 6/1/2010
PJM | P11 | Kewanee 138kV | Bishop Hill WF | IL | Mercer | In Service | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2005 |  |  | 10/1/2011 | 2/24/2012
PJM | P13 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/5/2005 | 6/27/2006 | Customer Milestone Not Met | 12/31/2009
PJM | P14 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 80 | 16 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/12/2005 |  |  | 12/31/2012 | 5/1/2012
PJM | P15 | McGirr - Mendota 138kV |  | IL | Lee | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 10/12/2005 | 2/2/2006 | Customer Initiated Withdrawal | 12/1/2006
PJM | P16 | Bath County | Bath County | VA | Bath | In Service | Dominion | 340 | 340 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 10/19/2005 |  |  | 12/1/2009 | 12/1/2009
PJM | P17 | Dixon-Mendota 34kV |  | IL | Lee | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 10/20/2005 | 2/2/2006 | Customer Initiated Withdrawal | 9/30/2006
PJM | P18 | Dixon-Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 2.5 | 0.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 10/20/2005 | 6/6/2014 | Customer Milestone Not Met | 12/31/2007
PJM | P19 | McGirr Road - Mendota 138kV |  | IL | Lee | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 10/20/2005 | 2/2/2006 | Customer Initiated Withdrawal | 12/31/2006
PJM | P20 | Nelson-Electric Junction 345kV | Walnut Ridge Wind Farm | IL | Bureau | Withdrawn | ComEd | 210 | 42 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/26/2005 | 12/14/2016 |  | 12/31/2017
PJM | P21 | McGirr Road - Dixon 138kV |  | IL | Bureau | Withdrawn | ComEd | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 10/26/2005 | 10/24/2006 | Customer Milestone Not Met | 9/15/2007
PJM | P22 | Johnstown Altoona 230kV | North Allegheny WF | PA | Cambria | In Service | PENELEC | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 10/28/2005 |  |  | 9/1/2009 | 9/1/2009
PJM | P23 | Bayonne 138kV |  | NJ | Hudson | Withdrawn | PSEG | 46 | 45.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 10/28/2005 | 2/18/2009 | Customer Milestone Not Met | 1/1/2009
PJM | P24 | Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 11/7/2005 | 6/6/2014 | Customer Milestone Not Met | 12/1/2008
PJM | P25 | Mendota 34.5kV |  | IL | Lee | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 11/7/2005 | 6/6/2014 | Customer Milestone Not Met | 12/1/2008
PJM | P26 | McGirr-Mendota | Shady Oaks Wind Power Project | IL | Lee | In Service | ComEd | 9.5 | 1.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 11/7/2005 |  |  | 12/31/2012 | 5/1/2012
PJM | P27 | Winchester 34.5 kV | Bethel LF | VA | Unknown | In Service | Dominion | 13 | 13 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/18/2005 |  |  | 1/25/2008 | 1/25/2008
PJM | P28 | Mehoopany 115kV | Mehoopany WF | PA | Wyoming | In Service | PENELEC | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/22/2005 |  |  | 1/21/2013 | 1/9/2013
PJM | P30 | Bellefonte - N. Proctorville 138kV | South Point | OH | Lawrence | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 11/30/2005 | 3/21/2012 | Customer Milestone Not Met | 12/31/2012
PJM | P32 | White Oak | GSA Federal Research Center (FDA) | MD | Montgomery | In Service | PEPCO | 19.5 |  | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/7/2005 |  |  | 12/31/2007 | 12/31/2007
PJM | P33 | Laurel - Sussex 69kV | Southern Landfill Units 1-4 | DE | Sussex | In Service | DPL | 1 |  | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 12/8/2005 |  |  | 10/24/2006 | 10/24/2006
PJM | P34 | Washington Landfill |  | PA | Washington | In Service | APS | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane | Document Posted | Not Required | Not Required | Wholesale Market Participation Agreement | 12/20/2005 |  |  | 3/17/2009 | 12/31/2006
PJM | P35 | Pleasantville | Pleasantville /AC LF Unit 2 | NJ | Atlantic | In Service | AEC | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/20/2005 |  |  | 7/31/2006 | 7/31/2006
PJM | P36 | Nelson - Lee Co. EC 345kV | Big Sky | IL | Bureau | In Service | ComEd | 240 | 48 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 12/22/2005 |  |  | 8/31/2010 | 8/31/2010
PJM | P37 | Normandy 138kV |  | IL | Bureau | Withdrawn | ComEd | 140 | 28 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 12/22/2005 | 7/17/2013 | Customer Initiated Withdrawal | 5/31/2013
PJM | P38 | Bremo 230kV | Bremo | VA | Buckingham | In Service | Dominion | 675 | 625 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 12/22/2005 |  |  | 3/30/2011 | 3/30/2011
PJM | P39 | Kewanee-Powerton 138kV |  | IL | Stark | Withdrawn | ComEd | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 12/28/2005 | 3/2/2011 | Customer Milestone Not Met | 12/1/2008
PJM | P40 | Crescent Ridge 138kV | Providence Heights WF | IL | Bureau | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 12/28/2005 | 2/21/2013 | Customer Initiated Withdrawal | 11/12/2010
PJM | P41 | South Reading - Birdsboro 69kV |  | PA | Berks | Withdrawn | ME | 9 | 9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 1/3/2006 | 6/28/2006 | Customer Milestone Not Met | 9/30/2006
PJM | P42 | West Kingsport 138kV | West Kingsport | TN | Sullivan | Deactivated | AEP | 50 | 45 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 1/12/2006 |  |  | 1/8/2007 | 1/8/2007
PJM | P43 | Weyerhaeuser 115kV | Domtar Paper Company Generating Units 7-10 | NC | Martin | In Service | Dominion | 62.5 | 50 | Capacity | Generation Interconnection | Wood | Document Posted | Document Posted | Document Posted | Document Posted | 1/13/2006 |  |  | 10/1/2021 | 1/1/2010
PJM | P44 | City of Columbus | Columbus Floodwall | OH | Franklin | In Service | AEP | 7.47 | 7 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Document Posted | 1/16/2006 |  |  | 12/31/2006 | 12/31/2006
PJM | P45A | Thompson 115kV |  | PA | Wayne | Withdrawn | PPL | 120 | 24 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 1/17/2006 | 9/1/2009 | Customer Initiated Withdrawal | 12/1/2009
PJM | P46 | Lena 138kV | EcoGrove WF (67 WT) | IL | JoDaviess | In Service | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 1/23/2006 |  |  | 3/11/2009 | 10/1/2007
PJM | P47 | Mansfield-S. Troy 115kV | Armenia Mountain WF | PA | Bradford | In Service | PENELEC | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/25/2006 |  |  | 12/16/2009 | 12/16/2009
PJM | P48 | Bedford North - Allegheny 115kV |  | PA | Somerset | Withdrawn | PENELEC | 80 | 16 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/27/2006 | 2/12/2007 | Customer Initiated Withdrawal | 12/15/2007
PJM | P49 | Adkins 345kV | Darby Generating Station | OH | Pickaway | In Service | Dayton | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/27/2006 |  |  | 6/1/2006 | 6/1/2006
PJM | P50 | Greenville 69kV | Greenville Electric Generating Station | OH | Darke | In Service | Dayton | 14 | 14 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/27/2006 |  |  | 6/1/2006 | 6/1/2006
PJM | P51 | Stuart 345kV | Stuart Electric Generating Station | OH | Adams | In Service | Dayton | 7 | 7 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/27/2006 |  |  | 6/1/2006 | 6/1/2006
PJM | P52 | Albright 138kV |  | WV | Preston | Withdrawn | APS | 80 | 16 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/30/2006 | 12/30/2010 | Customer Initiated Withdrawal | 12/31/2012
PJM | P53 | Bent Mtn. 138kV |  | VA | Roanoke | Withdrawn | AEP | 81 | 16.2 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/30/2006 | 8/21/2006 | Customer Initiated Withdrawal | 12/31/2008
PJM | P54 | Sporn - Waterford 345kV | Racine | OH | Meigs | Withdrawn | AEP | 1035 | 1035 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 1/30/2006 | 1/26/2010 | Customer Milestone Not Met | 8/30/2014
PJM | P55 | West Lima 138kV |  | OH | Allen | Withdrawn | AEP | 600 | 600 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 1/31/2006 | 3/20/2009 | Customer Milestone Not Met | 10/1/2010
PJM | P58 | Canaan - Seneca 138kV |  | WV | Randolph | Withdrawn | APS | 80 | 16 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/31/2006 | 2/17/2010 | Customer Initiated Withdrawal | 12/31/2014
PJM | P59 | Belington 138kV | Laurel Mountain WF | WV | Barbour | In Service | APS | 97.6 | 19.52 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2006 |  |  | 6/15/2011 | 12/31/2008
PJM | P60 | New Baltimore 115kV (Stony Creek) | Stony Creek WF | PA | Somerset | In Service | PENELEC | 52.5 | 10.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2006 |  |  | 3/1/2010 | 3/1/2010
PJM | P61 | Gavin #1 765kV | Gavin 1 | OH | Adams | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2006 |  |  | 1/1/2010 | 5/1/2007
PJM | P62 | Gavin #2 765kV | Gavin 2 | OH | Adams | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2006 |  |  | 5/1/2009 | 5/1/2009
PJM | Q01 | Olive-Dequine 345kv | Fowler Ridge WF | IN | Benton | In Service | AEP | 500 | 100 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 2/7/2006 |  |  | 7/1/2009 | 12/1/2008
PJM | Q02 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 80 | 16 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 2/10/2006 | 7/17/2006 | Customer Initiated Withdrawal | 12/31/2008
PJM | Q03 | Olive-Dequine 345kV | Fowler Ridge 4 WF | IN | Benton | In Service | AEP | 250 | 50 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 2/13/2006 |  |  | 12/31/2014 | 12/3/2015
PJM | Q04 | Snake Spring 115kV |  | PA | Bedford | Withdrawn | PENELEC | 140 | 28 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/15/2006 | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008
PJM | Q05 | Emmaville Mountain |  | PA | Fulton | Withdrawn | APS | 18 | 5 | Capacity | Generation Interconnection | Wind | Document Posted | Not Required | Not Required |  | 2/15/2006 | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008
PJM | Q06 | Breezewood |  | PA | Fulton | Withdrawn | APS | 18 | 5 | Capacity | Generation Interconnection | Wind | Document Posted | Not Required | Not Required |  | 2/15/2006 | 10/27/2006 | Customer Initiated Withdrawal | 9/30/2008
PJM | Q07 | DuVall South |  | PA | Fulton | Withdrawn | PENELEC | 18 | 5 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 2/15/2006 | 6/14/2006 | Customer Initiated Withdrawal | 9/30/2008
PJM | Q08 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 2/21/2006 | 8/18/2009 | Customer Initiated Withdrawal | 6/1/2011
PJM | Q09 | Emporia | Emporia Hydro | VA | Greensville | In Service | Dominion | 2.5 | 2.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/21/2006 |  |  | 4/1/2007 | 4/1/2007
PJM | Q10 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 27 | 27 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/23/2006 |  |  | 12/31/2008 | 12/31/2008
PJM | Q11 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 2/23/2006 | 3/31/2010 | Customer Milestone Not Met | 12/1/2011
PJM | Q12 | Fox River Heights 12kV |  | IL | Kane | Withdrawn | ComEd | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/8/2006 | 8/10/2010 | Customer Milestone Not Met | 6/1/2007
PJM | Q13 | Kankakee 12kV |  | IL | Kankakee | Withdrawn | ComEd | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/8/2006 | 8/10/2010 | Customer Milestone Not Met | 6/1/2007
PJM | Q14 | Hegewisch 12kV |  | IL | Cook | Withdrawn | ComEd | 6.6 | 6.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/8/2006 | 8/10/2010 | Customer Milestone Not Met | 6/1/2007
PJM | Q15 | Woodridge 12kV |  | IL | Du Page | Withdrawn | ComEd | 6.6 | 6.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/8/2006 | 8/10/2010 | Customer Milestone Not Met | 6/1/2007
PJM | Q16 | Western Ave 12kV |  | IL | Kane | Withdrawn | ComEd | 6.6 | 6.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/8/2006 | 8/23/2010 | Customer Milestone Not Met | 9/1/2007
PJM | Q17 | Northbrook 12kV |  | IL | Cook | Withdrawn | ComEd | 6.6 | 6.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/8/2006 | 8/23/2010 | Customer Milestone Not Met | 6/1/2007
PJM | Q18 | Moser 34.5kV | Pottstown LF Units 1 & 2 | PA | Montgomery | In Service | PECO | 5 | 5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 3/8/2006 |  |  | 11/6/2007 | 11/6/2007
PJM | Q19 | Atlantic 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 1 | 1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/13/2006 | 12/6/2006 | Customer Milestone Not Met | 11/1/2006
PJM | Q20 | Holtwood | Holtwood | PA | Lancaster | In Service | PPL | 140 | 140 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 3/17/2006 |  |  | 12/31/2013 | 10/30/2010
PJM | Q22 | Columbia 34.5kV | Great Bear Hydro | NJ | Warren | In Service | JCPL | 0.5 | 0.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/20/2006 |  |  | 5/5/2009 | 12/26/2006
PJM | Q23 | Bayard |  | WV | Grant | Withdrawn | APS | 19 | 7 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 3/20/2006 | 11/27/2006 | Customer Milestone Not Met | 3/31/2007
PJM | Q24 | Gold-Sabinsville 115kV |  | PA | Potter | Withdrawn | PENELEC | 101 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/23/2006 | 2/2/2009 | Customer Milestone Not Met | 12/30/2010
PJM | Q25 | Donegal-Iron City 138kV | Harmony WF | PA | Fayette | Withdrawn | APS | 80 | 16 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 3/24/2006 | 6/4/2012 | Customer Initiated Withdrawal | 3/1/2014
PJM | Q26 | Churchtown 230kV |  | NJ | Salem | Withdrawn | AEC | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/29/2006 | 10/12/2006 | Customer Milestone Not Met | 12/31/2008
PJM | Q27 | Frackville-Shennandoah 69kV | Locust Ridge II WF | PA | Schuylkill | In Service | PPL | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 4/7/2006 |  |  | 4/29/2009 | 4/29/2009
PJM | Q28 | Eldred-Frackville 230kV | Rausch Creek WF (68 WT) | PA | Schuylkill | Withdrawn | PPL | 170 | 34 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 4/7/2006 | 8/2/2013 | Customer Initiated Withdrawal | 12/31/2014
PJM | Q29 | Zion 12kV |  | IL | Lake | Withdrawn | ComEd | 5.4 | 5.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required |  | 4/11/2006 | 10/29/2013 | Customer Initiated Withdrawal | 6/1/2007
PJM | Q30 | City of Columbus |  | OH | Franklin | Withdrawn | AEP | 3 | 0 | Energy | Generation Interconnection | Methane | Withdrawn | Not Required | Not Required | Withdrawn | 4/11/2006 | 9/20/2006 | Customer Initiated Withdrawal | 12/31/2006
PJM | Q31 | Wagner 34kV | Hawkins Point | MD | Baltimore City | In Service | BGE | 10 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/11/2006 |  |  | 4/24/2007 | 6/1/2006
PJM | Q32 | Gosport 115kV | Gosport | VA | City of Portsmouth | Withdrawn | Dominion | 30 | 30 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted |  |  | 4/21/2006 | 8/22/2007 | Customer Initiated Withdrawal | 7/1/2007
PJM | Q33 | Homer-Watercure 345kV |  | PA | Tioga | Withdrawn | PENELEC | 150 | 30 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 4/24/2006 | 6/6/2006 | Customer Initiated Withdrawal | 12/15/2008
PJM | Q34 | Garrett 115kV |  | PA | Somerset | Withdrawn | PENELEC | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 4/24/2006 | 7/24/2013 | Customer Initiated Withdrawal | 4/1/2011
PJM | Q35 | N. Coshocton 69kV |  | OH | Coshocton | Withdrawn | AEP | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/26/2006 | 11/28/2006 | Customer Milestone Not Met | 6/1/2007
PJM | Q36 | Philipsburg - Tyrone North 115kV | Sandy Ridge WF | PA | Centre | In Service | PENELEC | 50 | 10 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 4/28/2006 |  |  | 12/31/2011 | 4/17/2012
PJM | Q37 | Loganton 12kV | Schrack Farms | PA | Clinton | Withdrawn | PPL | 0.02 | 0 | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/2/2006 | 1/12/2007 | Customer Initiated Withdrawal | 6/16/2006
PJM | Q39 | Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 105 | 21 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 5/8/2006 | 10/22/2015 | Customer Initiated Withdrawal | 12/31/2016
PJM | Q40 | Renovo Lock Haven |  | PA | Clinton | Withdrawn | PPL | 40 | 8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 5/15/2006 | 8/29/2008 | Customer Initiated Withdrawal | 6/1/2009
PJM | Q41 | Mt. Hope Mine 34.5kV | Mt Hope Waterpower Project | NJ | Morris | Withdrawn | JCPL | 30 |  | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/5/2006 | 11/11/2013 | Customer Milestone Not Met | 12/31/2013
PJM | Q42 | Indian River |  | DE | Sussex | Withdrawn | DPL | 630 | 630 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 6/5/2006 | 7/30/2008 | Customer Initiated Withdrawal | 6/1/2011
PJM | Q43 | Clinch River 138kV | Virginia City Hybrid Energy Center - 1 Unit | VA | Wise | In Service | AEP | 534 | 534 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 6/7/2006 |  |  | 3/1/2012 | 3/22/2012
PJM | Q44 | Elizabethtown | Elizabethtown | PA | Lancaster | In Service | PPL | 0.3 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/9/2006 |  |  | 7/1/2006 | 7/1/2006
PJM | Q45 | North Lebanon 13.2kV | GLRA LF | PA | Lebanon | In Service | ME | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 6/14/2006 |  |  | 9/25/2007 | 9/25/2007
PJM | Q46 | Curwensville 34.5 kV | Sunnyside Ethonol | PA | Clearfield | Withdrawn | PENELEC | 10 | 10 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/16/2006 | 3/14/2013 | Customer Milestone Not Met | 3/1/2009
PJM | Q47 | Peach Bottom | Peach Bottom - Units 2 & 3 | PA | York | In Service | PECO | 140 | 140 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 6/20/2006 |  |  | 4/1/2013 | 11/12/2012
PJM | Q48 | Calvert Cliffs | Calvert Cliffs Nuclear Power Plant Unit 3 | MD | Calvert | Withdrawn | BGE | 1640 | 1640 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 6/20/2006 | 11/16/2009 | Customer Initiated Withdrawal | 1/1/2016
PJM | Q49 | Dresden 345kV | Dresden Nuclear Generating Station U2 | IL | Grundy | In Service | ComEd | 70 | 70 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 6/20/2006 |  |  | 1/31/2012 | 11/14/2011
PJM | Q50 | Dresden 345kV | Dresden Nuclear Station Unit 3 | IL | Grundy | In Service | ComEd | 70 | 70 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 6/20/2006 |  |  | 1/31/2012 | 12/12/2012
PJM | Q51 | Quad City 345kV | Quad Cities - Units 1 & 2 | IL | Rock Island | In Service | ComEd | 140 | 140 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 6/20/2006 |  |  | 10/1/2011 | 9/25/2011
PJM | Q52 | Hunlock Creek |  | PA | Luzerne | Withdrawn | UGI | 300 | 300 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 6/21/2006 | 12/11/2007 | Customer Initiated Withdrawal | 6/15/2011
PJM | Q53 | Summit-West Fall 115kV | Chestnut Flats WF | PA | Blair | In Service | PENELEC | 38 | 7.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/23/2006 |  |  | 5/20/2011 | 5/20/2011
PJM | Q54 | Haviland-Tillman 138kV |  | IN | Allen | Withdrawn | AEP | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/28/2006 | 10/27/2006 | Customer Milestone Not Met | 12/15/2009
PJM | Q55 | Snowy Creek |  | WV | Preston | Withdrawn | APS | 62.5 | 12.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 6/28/2006 | 7/31/2012 | Customer Initiated Withdrawal | 12/31/2009
PJM | Q56 | Claysburg 115kV |  | PA | Blair | Withdrawn | PENELEC | 180 | 36 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 7/5/2006 | 11/17/2006 | Customer Milestone Not Met | 6/30/2008
PJM | Q57 | Steward-Waterman 138kV | Lee - DeKalb Wind Energy Center | IL | Lee | In Service | ComEd | 240 | 48 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/6/2006 |  |  | 6/1/2010 | 11/14/2014
PJM | Q58 | Sunbury-Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 7/6/2006 | 8/18/2008 | Customer Initiated Withdrawal | 12/31/2009
PJM | Q59 | S. Reading-Birdsboro 64kV | Pioneer Crossing LF | PA | Berks | In Service | ME | 6.4 | 6.4 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 7/7/2006 |  |  | 5/30/2008 | 5/30/2008
PJM | Q60 | Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 201 | 40.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 7/7/2006 | 4/5/2012 | Customer Initiated Withdrawal | 3/1/2009
PJM | Q61 | Grassy Falls 138kV |  | WV | Greenbrier | Withdrawn | APS | 10 | 10 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 7/10/2006 | 8/26/2008 |  | 1/1/2010
PJM | Q62 | Sayton -Snake Spring 115kV |  | PA | Bedford | Withdrawn | PENELEC | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/11/2006 | 3/27/2009 | Customer Initiated Withdrawal | 12/1/2009
PJM | Q63 | Seneca 230kV | Seneca Pumped Storage Generating Station Unit 1 | PA | Warren | In Service | PENELEC | 16 | 16 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 7/11/2006 |  |  | 8/11/2010 | 8/11/2010
PJM | Q64 | Gosport 115kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Biomass | Document Posted | Withdrawn |  |  | 7/12/2006 | 5/31/2007 | Customer Milestone Not Met | 12/31/2007
PJM | Q65 | North Anna 500kV | North Anna Power Station Unit 3 | VA | Louisa | Withdrawn | Dominion | 1594 | 1570 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 7/14/2006 | 4/28/2016 | Customer Initiated Withdrawal | 1/1/2024
PJM | Q66 | Beecher Energy - Distribution Cener #36 |  | IL | Will | Withdrawn | ComEd | 2.1 | 2.1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required |  | 7/14/2006 | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007
PJM | Q67 | LaGrange Park - West Chester Sexton Energy |  | IL | Cook | Withdrawn | ComEd | 3.5 | 3.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required |  | 7/14/2006 | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007
PJM | Q67B | Mt. Prospect - Des Plaines Sexton Energy |  | IL | Cook | Withdrawn | ComEd | 3.5 | 3.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required |  | 7/14/2006 | 10/10/2013 | Customer Initiated Withdrawal | 6/1/2007
PJM | Q68 | Kincaid 345kV |  | IL | Christian | Withdrawn | ComEd | 726 | 641 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 7/21/2006 | 6/5/2012 | Customer Initiated Withdrawal | 9/30/2015
PJM | Q69 | Shackleford 34.5kV | King - Queen | VA | Brunswick | In Service | Dominion | 10 | 10 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 7/25/2006 |  |  | 2/7/2008 | 2/7/2008
PJM | Q70 | Lawrenceville 34.5kV | Brunswick | VA | King and Queen | In Service | Dominion | 11 | 11 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 7/25/2006 |  |  | 11/1/2007 | 11/1/2007
PJM | Q71 | Cranes Corner 13.2kV | Strafford Regional LF | VA | Stafford | In Service | Dominion | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 7/26/2006 |  |  | 6/1/2008 | 6/1/2008
PJM | Q72 | Mansfield - S. Troy 115kV |  | PA | Bradford | Withdrawn | PENELEC | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/27/2006 | 12/23/2009 | Customer Initiated Withdrawal | 12/1/2010
PJM | Q73 | South Reading 69kV | Evergreen Community Power | PA | Berks | Deactivated | ME | 30 | 16 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 7/27/2006 |  |  | 4/6/2010 | 4/6/2010
PJM | Q74 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 600 | 600 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Withdrawn |  | 7/31/2006 | 10/22/2008 | Customer Initiated Withdrawal | 6/1/2013
PJM | Q76 | Quinton 12kV | Salem County LF Generating Unit I | NJ | Salem | Deactivated | AEC | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2006 |  |  | 12/19/2008 | 12/19/2008
PJM | Q77 | Calvert Cliffs |  | MD | Calvert | Withdrawn | PEPCO | 1640 | 1640 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 7/31/2006 | 3/21/2007 | Customer Initiated Withdrawal | 12/30/2016
PJM | Q78 | Trail Fork 34.5kV |  | WV | McDowell | Withdrawn | AEP | 5 | 5 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 7/31/2006 | 1/24/2007 | Customer Milestone Not Met | 4/1/2007
PJM | Q79 | Ft. Martin - Kammer 500kV | Longview ST1 | WV | Monongalia | In Service | APS | 100 | 100 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2006 |  |  | 4/22/2011 | 9/1/2010
PJM | Q80 | Ft. Martin - Kammer 500kV |  | WV | Monongalia | Withdrawn | APS | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/31/2006 | 6/2/2009 | Customer Initiated Withdrawal | 8/1/2012
PJM | Q81 | AMOS 765kV |  | WV | Putnam | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 7/31/2006 | 10/24/2006 | Customer Milestone Not Met | 12/30/2007
PJM | Q85 | Minonk 34.5kV |  | IL | Marshall | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 7/31/2006 | 12/15/2008 | Customer Initiated Withdrawal | 12/31/2008
PJM | Q86 | Hudson - Essex 230kV |  | NJ | Hudson | Withdrawn | PSEG | 455.1 | 455.1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/31/2006 | 4/2/2009 | Customer Milestone Not Met | 5/31/2010
PJM | Q89 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 750 | 750 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 7/31/2006 | 3/30/2007 | Customer Initiated Withdrawal | 8/1/2012
PJM | Q90 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 650 | 650 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2006 |  |  | 6/1/2016 | 8/11/2014
PJM | R01 | Susquehanna |  | PA | Montour | Withdrawn | PPL | 800 | 800 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Withdrawn | 8/25/2006 | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2018
PJM | R02 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 800 | 800 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Withdrawn | 8/25/2006 | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2018
PJM | R03 | Adams - Allen 138kV |  | IN | Adams | Withdrawn | AEP | 130 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/25/2006 | 2/5/2013 | Customer Initiated Withdrawal | 12/31/2013
PJM | R04 | Sunbury 500kV |  | PA | Snyder | Withdrawn | PPL | 817 | 817 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 9/6/2006 | 10/13/2008 | Customer Initiated Withdrawal | 12/15/2011
PJM | R05 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 50 | 10 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/8/2006 | 8/5/2009 | Customer Initiated Withdrawal | 12/1/2009
PJM | R06 | Weissport 69kV |  | PA | Carbon | Withdrawn | PPL | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/8/2006 | 4/3/2007 | Customer Milestone Not Met | 12/31/2008
PJM | R07 | Pleasantville | AC Landfill Energy Units 1-3 | NJ | Atlantic | Deactivated | AEC | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/12/2006 |  |  | 10/1/2007 | 10/1/2007
PJM | R08 | Central City 115kV, Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 300 | 300 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 9/14/2006 | 2/18/2009 | Customer Initiated Withdrawal | 12/10/2012
PJM | R09 | Johnstown-Altoona 230 kV |  | PA | Cambria | Withdrawn | PENELEC | 48 | 9.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/15/2006 | 9/3/2009 | Customer Milestone Not Met | 12/15/2009
PJM | R11 | South River 230 kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 440 | 440 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/20/2006 | 11/27/2019 |  | 5/16/2020
PJM | R13 | Tidd - Canton Central 345kV |  | OH | Columbiana | Withdrawn | AEP | 350 | 350 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 9/28/2006 | 6/18/2008 | Customer Initiated Withdrawal | 9/30/2011
PJM | R14 | Tait 69kV | Tait Generating Units 4-7 | OH | Montgomery | In Service | Dayton | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/29/2006 |  |  | 5/1/2007 | 5/1/2007
PJM | R15 | Adkins 345kV | Darby Generation Station Units 1-6 | OH | Pickaway | In Service | Dayton | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/29/2006 |  |  | 5/1/2007 | 5/1/2007
PJM | R16 | Lena 138kV |  | IL | Stephenson | Withdrawn | ComEd | 126 | 25.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/2/2006 | 11/24/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | R17 | Morgantown - Oak Grove 230kV | CPV St. Charles | MD | Charles | Withdrawn | PEPCO | 645 | 645 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 10/2/2006 | 4/1/2010 | Customer Milestone Not Met | 6/1/2013
PJM | R18 | Blackhawk | Winnebago Energy Center | IL | Boone | In Service | ComEd | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/2/2006 |  |  | 1/3/2008 | 1/3/2008
PJM | R19 | Ladysmith 230kV | Ladysmith CT Units 3 & 4 | VA | Caroline | In Service | Dominion | 340 | 340 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/3/2006 |  |  | 6/1/2008 | 6/1/2008
PJM | R20 | Rock Springs | Rock Springs Units 3 & 4 | MD | Cecil | In Service | ODEC | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/4/2006 |  |  | 7/1/2010 | 1/1/2007
PJM | R21 | Short Mountain |  | WV | Hardy | Withdrawn | APS | 14 | 14 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 10/12/2006 | 5/18/2007 | Customer Initiated Withdrawal | 11/30/2010
PJM | R22 | Elk Garden - Junction 138kV |  | WV | Mineral | Withdrawn | APS | 90 | 18 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 10/12/2006 | 1/9/2009 | Customer Initiated Withdrawal | 11/30/2009
PJM | R23 | Lakewood 230kV | Ocean Peaking Power (Lakewood CT1, CT2) | NJ | Ocean | In Service | JCPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/16/2006 |  |  | 1/1/2007 | 1/1/2007
PJM | R24 | Susquehanna - Alburtis 500kV |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted |  |  | 10/17/2006 | 7/16/2008 | Customer Initiated Withdrawal | 4/1/2011
PJM | R26 | Sunbury - Susquehanna 500kV |  | PA | Northumberland | Withdrawn | PPL | 940 | 940 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 10/23/2006 | 6/13/2007 | Customer Milestone Not Met | 7/1/2011
PJM | R27 | Frackville |  | PA | Schuylkill | Withdrawn | PPL | 52 | 52 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 10/24/2006 | 1/20/2009 | Customer Milestone Not Met | 6/1/2010
PJM | R28 | Susquehanna - Alburtis 500kV |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 10/24/2006 | 7/19/2007 | Customer Initiated Withdrawal | 7/1/2011
PJM | R29 | Kawanee 138kV |  | IL | Knox | Withdrawn | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/24/2006 | 1/20/2010 | Customer Milestone Not Met | 12/1/2008
PJM | R30 | Pontiac Mid-Point 345kV | Pleasant Ridge Wind Farm | IL | Livingston | Withdrawn | ComEd | 500 | 100 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/24/2006 | 8/19/2019 |  | 12/31/2020
PJM | R31 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 18 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/30/2006 | 4/27/2010 | Customer Initiated Withdrawal | 10/1/2010
PJM | R32 | Salix - Claysburg 115kV | Highland North | PA | Cambria | In Service | PENELEC | 75 | 15 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2006 |  |  | 3/31/2012 | 3/23/2012
PJM | R33 | Nelson 345 kV | Nelson Energy Center | IL | Unknown | In Service | ComEd | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2006 |  |  | 6/1/2014 | 5/8/2015
PJM | R35 | Robbins 138kV | Robbins Community Power | IL | Cook | Withdrawn | ComEd | 50 | 50 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Withdrawn | 11/3/2006 | 1/25/2013 | Customer Milestone Not Met | 9/30/2011
PJM | R36 | Bethany 138kV | Bluewater Wind - Bethany | DE | Unknown | Withdrawn | DPL | 450 | 90 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/8/2006 | 8/6/2012 | Customer Initiated Withdrawal | 6/1/2018
PJM | R37 | Rehoboth 138kV |  | DE | Sussex | Withdrawn | DPL | 450 | 90 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 11/8/2006 | 1/12/2009 | Customer Initiated Withdrawal | 6/1/2014
PJM | R38 | Milford 230kV |  | DE | Sussex | Withdrawn | DPL | 547 | 110 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 11/8/2006 | 9/7/2007 | Customer Milestone Not Met | 6/1/2010
PJM | R39 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/10/2006 | 12/2/2008 |  | 8/1/2009
PJM | R40 | Rockwood - Meyersdale 115kV | Lookout WF | PA | Somerset | In Service | PENELEC | 1.8 | 0.36 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 11/15/2006 |  |  | 6/30/2008 | 6/30/2008
PJM | R41 | Roxbury - Blain 23kV |  | PA | Cumberland | Withdrawn | PENELEC | 6 | 0 | Energy | Generation Interconnection | Methane | Withdrawn |  |  |  | 11/15/2006 | 11/27/2007 | Customer Initiated Withdrawal | 12/31/2008
PJM | R42 | Moselem 69kV | Evansville Biomass | PA | Berks | Withdrawn | ME | 6 | 6 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 11/21/2006 | 8/6/2009 | Customer Initiated Withdrawal | 3/1/2009
PJM | R43 | Frackville - Hauto #3 | GCC Realty | PA | Schuylkill | Withdrawn | PPL | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 11/27/2006 | 6/15/2015 | Customer Initiated Withdrawal | 6/1/2015
PJM | R44 | Rockport 765kV |  | KY | Henderson | Withdrawn | AEP | 485 | 485 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 11/27/2006 | 5/21/2010 | Customer Initiated Withdrawal | 3/31/2011
PJM | R45 | Mansfield - Tower Hill 115kV |  | PA | Tioga | Withdrawn | PENELEC | 70 | 14 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 12/4/2006 | 2/2/2009 |  | 4/30/2009
PJM | R46 | Providence Heights #1A 138kV |  | IL | Bureau | Withdrawn | ComEd | 9 | 1.8 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 12/4/2006 | 10/1/2007 | Customer Initiated Withdrawal | 12/31/2008
PJM | R48 | Antwerp - Payne 69kV | Paulding aka Project R48 | OH | Paulding | Withdrawn | AEP | 48.3 | 9.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 12/6/2006 | 1/4/2018 |  | 11/30/2020
PJM | R49 | Haviland - Milan 138kV | Timber Road II WF | OH | Paulding | In Service | AEP | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 12/6/2006 |  |  | 12/31/2012 | 7/15/2011
PJM | R50 | Liberty - Blue Jacket 69kV |  | OH | Logan | Withdrawn | Dayton | 48 | 9.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 12/6/2006 | 9/6/2007 | Customer Milestone Not Met | 2/15/2009
PJM | R51 | Kings Creek - Woodstock 69kV |  | OH | Champaign | Withdrawn | Dayton | 48 | 9.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 12/6/2006 | 9/6/2007 | Customer Milestone Not Met | 12/15/2010
PJM | R52 | Mechanicsburg - Darby | Buckeye Wind Farm - Phase 1 | OH | Champaign | Withdrawn | Dayton | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/6/2006 | 2/21/2018 |  | 12/31/2019
PJM | R52A | Kings Creek 69kV | Buckeye Wind Farm - Phase 2 | OH | Champaign | Withdrawn | Dayton | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/6/2006 | 9/12/2019 |  | 12/31/2019
PJM | R53 | Stanton-Brookside 69kV |  | PA | Lackawanna | Withdrawn | PPL | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 12/8/2006 | 2/19/2009 | Customer Milestone Not Met | 11/11/2009
PJM | R54 | Dixon - Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 12/11/2006 | 6/10/2011 | Customer Initiated Withdrawal | 12/1/2013
PJM | R55 | Dixon - Maryland 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 12/11/2006 | 6/10/2011 | Customer Initiated Withdrawal | 12/1/2014
PJM | R56 | Quemahoning - Hooversville 230kV |  | PA | Somerset | Withdrawn | PENELEC | 124 | 24.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 12/11/2006 | 12/31/2009 | Customer Milestone Not Met | 11/30/2009
PJM | R57 | South Reading 69kV | Evergreen Community Power | PA | Berks | Deactivated | ME | 30 | 9 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 12/20/2006 |  |  | 4/6/2010 | 4/6/2010
PJM | R58 | Gloucester 230kV | Camden Cogen Tech | NJ | Camden | Withdrawn | PSEG | 55 | 55 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/21/2006 | 12/3/2009 | Customer Initiated Withdrawal | 6/1/2013
PJM | R59 | Nelson-Lee County Energy Ctr 345kV |  | IL | Bureau | Withdrawn | ComEd | 160 | 32 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/3/2007 | 1/25/2010 | Customer Initiated Withdrawal | 12/31/2008
PJM | R60 | Convoy-East Lima 345kV | Blue Creek WF | OH | Van Wert | In Service | AEP | 350 | 70 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 1/8/2007 |  |  | 4/1/2012 | 4/1/2012
PJM | R61 | Collingwood-Hiple 345kV |  | IN | LeGrange | Withdrawn | AEP | 350 | 70 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/8/2007 | 4/13/2009 | Customer Initiated Withdrawal | 6/30/2010
PJM | R62 | Big Sandy 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/8/2007 |  |  | 6/1/2009 | 5/31/2016
PJM | R63 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 19 | 19 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/11/2007 |  |  | 6/1/2011 | 6/1/2011
PJM | R64 | Lancaster 138kV |  | IL | Stephenson | Withdrawn | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/12/2007 | 1/28/2010 | Customer Initiated Withdrawal | 7/1/2009
PJM | R65 | Dixon-Cherry Valley 138kV |  | IL | Ogle | Withdrawn | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/12/2007 | 1/28/2010 | Customer Initiated Withdrawal | 2/25/2010
PJM | R66 | Fairlawn 138kV | Marcal Paper | NJ | Bergen | In Service | PSEG | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/12/2007 |  |  | 5/1/2009 | 3/1/2007
PJM | R67 | Beaver Valley 345kV |  | PA | Beaver | Withdrawn | DL | 2510 | 2510 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 1/16/2007 | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980
PJM | R68 | Sammis 345kV |  | OH | Jefferson | Withdrawn | AEP | 1940 | 1940 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 1/16/2007 | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980
PJM | R69 | Clifty Creek 345kV |  | IN | Jefferson | Withdrawn | AEP | 251 | 251 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 1/16/2007 | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980
PJM | R70 | Kygov Creek |  | OH | Gallia | Withdrawn | AEP | 210 | 210 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 1/16/2007 | 2/20/2007 | Customer Initiated Withdrawal | 12/31/1980
PJM | R72 | Indian River 230kV | Indian River Units 3-4 | DE | Sussex | In Service | DPL | 18 | 18 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/18/2007 |  |  | 12/10/2008 | 12/10/2008
PJM | R73 | Indian River 138kV | Indian River Units #3 & #4 | DE | Sussex | In Service | DPL | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/18/2007 |  |  | 12/10/2008 | 12/10/2008
PJM | R74 | Carlls Corner | Shoreham Energy Units 1-3 | NJ | Atlantic | In Service | AEC | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/19/2007 |  |  | 11/14/2008 | 11/14/2008
PJM | R76 | Kanawha 138kV | Hawks Nest Hydro | WV | Fayette | In Service | AEP | 6.16 | 5.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 1/23/2007 |  |  | 1/23/2017 | 3/1/2009
PJM | R77 | Morrisville 500kV |  | VA | Warren | Withdrawn | APS | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 1/23/2007 | 7/20/2009 | Customer Initiated Withdrawal | 5/1/2012
PJM | R78 | Dresden-Pontiac 345kV |  | IL | Livingston | Withdrawn | ComEd | 300.3 | 60.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/26/2007 | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | R79 | Tazewell-Kendall 345kV |  | IL | Livingston | Withdrawn | ComEd | 300.3 | 60.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/26/2007 | 5/5/2014 | Customer Initiated Withdrawal | 12/31/2012
PJM | R80 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 0 | 60 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/26/2007 |  |  | 1/26/2017 | 4/30/2015
PJM | R81 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 101 | 101 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/26/2007 |  |  | 2/8/2010 | 2/8/2010
PJM | R82 | Kanawha #1 | Kanawna River #1 | WV | Kanawha | In Service | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/29/2007 |  |  | 4/1/2007 | 4/1/2007
PJM | R83 | Kanawha #2 | Kanawna River #2 | WV | Kanawha | In Service | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/29/2007 |  |  | 4/1/2007 | 4/1/2007
PJM | R84 | Picway #5 | Pickway #5 | OH | Pickaway | In Service | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/29/2007 |  |  | 4/1/2007 | 4/1/2007
PJM | R85 | Tanners Creek #1 | Tanners Creek #1 | IN | Dearborn | In Service | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/29/2007 |  |  | 4/1/2007 | 4/1/2007
PJM | R86 | Tanners Creek #2 | Tanners Creek #2 | IN | Dearborn | In Service | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/29/2007 |  |  | 4/1/2007 | 4/1/2007
PJM | R87 | Muskingum River #5 | Muskingum River #5 | OH | Washington | In Service | AEP | 10 | 10 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/29/2007 |  |  | 4/1/2007 | 4/1/2007
PJM | R88 | Providence Heights #2 138kV |  | IL | Bureau | Withdrawn | ComEd | 75 | 15 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/30/2007 | 7/8/2008 | Customer Initiated Withdrawal | 12/31/2008
PJM | R89 | Conowingo | Conowingo Hydro Station | MD | Harford | In Service | PECO | 24 | 24 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 1/30/2007 |  |  | 12/1/2010 | 12/1/2010
PJM | R91 | Columbus-NJ |  | NJ | Burlington | In Service | PSEG | 0.37 | 0 | Energy | Generation Interconnection | Methane | Not Required | Not Required | Not Required | Document Posted | 1/30/2007 |  |  | 10/15/2008 | 6/1/2007
PJM | R92 | DuBois 115kV |  | PA | Clearfield | Withdrawn | PENELEC | 70 | 14 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 1/31/2007 | 12/19/2013 | Customer Initiated Withdrawal | 6/30/2009
PJM | R93 | Kelford 115kV |  | NC | Bertie | Withdrawn | Dominion | 12 | 12 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 1/31/2007 | 5/31/2007 | Customer Milestone Not Met | 3/1/2008
PJM | R94 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 1/31/2007 | 7/23/2007 | Customer Initiated Withdrawal | 7/1/2011
PJM | R95 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 940 | 940 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 1/31/2007 | 7/23/2007 | Customer Initiated Withdrawal | 10/1/2011
PJM | R96 | Lancaster-Maryland 138kV |  | IL | Stephenson | Withdrawn | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/31/2007 | 8/29/2012 | Customer Initiated Withdrawal | 5/31/2010
PJM | R97 | Rockport 765kV | Rockport Unit 1 | IN | Spencer | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2007 |  |  | 11/1/2011 | 11/1/2011
PJM | R98 | Northeast 34.5kV |  | VA | Henrico | Withdrawn | Dominion | 14 | 14 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2007 | 2/27/2008 | Customer Milestone Not Met | 6/30/2008
PJM | S01 | Derwood 13kV | Gude LF | MD | Montgomery | Deactivated | PEPCO | 1 | 1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 2/5/2007 |  |  | 7/1/2009 | 7/1/2008
PJM | S02 | Mt. Zion 13kV | Oaks LF | MD | Montgomery | Deactivated | PEPCO | 4 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 2/5/2007 |  |  | 7/1/2009 | 7/1/2008
PJM | S03 | Edgemoor 230kV | Edgemoor #5 | DE | New Castle | In Service | DPL | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/13/2007 |  |  | 12/31/2007 | 12/31/2007
PJM | S04 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 633 | 633 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/13/2007 | 11/1/2007 | Customer Milestone Not Met | 7/1/2010
PJM | S05 | Seneca #2 230kV | Seneca Pumped Generating Station Unit 2 | PA | Warren | In Service | PENELEC | 16 | 16 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 2/27/2007 |  |  | 8/11/2010 | 8/11/2010
PJM | S06 | Olive-DeQuine 345kV | Meadow Lake | IN | White | In Service | AEP | 202 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 2/27/2007 |  |  | 10/6/2009 | 12/1/2009
PJM | S100 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 80 | 80 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2007 |  |  | 3/1/2012 | 3/22/2012
PJM | S101 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 580 | 580 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 10/22/2011 | 10/22/2011
PJM | S102 | Ladysmith 230kV | Ladysmith Combustion Turbine Unit 5 | VA | Caroline | In Service | Dominion | 170 | 170 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 3/31/2009 | 3/31/2009
PJM | S103 | Warren 115kV | Warren Generating Station | PA | Warren | In Service | PENELEC | 57 | 57 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2007 |  |  | 4/5/2011 | 4/5/2011
PJM | S105 | Croydon-Emilie |  | PA | Bucks | Withdrawn | PECO | 1200 | 1200 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2007 | 3/3/2008 | Customer Milestone Not Met | 6/1/2011
PJM | S107 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 520 | 520 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 7/31/2007 | 7/16/2013 | Customer Initiated Withdrawal | 6/1/2015
PJM | S108 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/18/2010 | 5/18/2010
PJM | S109 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/2/2010 | 5/2/2010
PJM | S11 | Seward-Tower 51 115kV |  | PA | Cambria | Withdrawn | PENELEC | 70 | 14 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 3/5/2007 | 6/26/2009 | Customer Initiated Withdrawal | 2/1/2009
PJM | S110 | North Anna 500kV | North Anna Unit 1 | VA | Louisa | In Service | Dominion | 65 | 65 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/2/2010 | 5/2/2010
PJM | S111 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 15 | 15 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2011 | 6/1/2011
PJM | S112 | North Anna 500kV | North Anna Unit 2 | VA | Louisa | In Service | Dominion | 65 | 65 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/18/2010 | 5/18/2010
PJM | S113 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 15 | 15 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2011 | 6/1/2011
PJM | S114 | Surry 230kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 75 | 75 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 9/1/2012 | 6/13/2012
PJM | S115 | Surry 500kV | Surry Power Station - Units 1 & 2 | VA | Surry | In Service | Dominion | 75 | 75 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 7/1/2011 | 7/1/2011
PJM | S116 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 912 | 912 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2007 | 2/24/2009 | Customer Initiated Withdrawal | 6/1/2011
PJM | S117 | Haviland 138kV |  | OH | Paulding | Withdrawn | AEP | 150 | 30 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 7/31/2007 | 9/17/2007 | Customer Initiated Withdrawal | 10/1/2008
PJM | S118 | North Delphos 138kV |  | OH | Paulding | Withdrawn | AEP | 150 | 30 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 7/31/2007 | 9/17/2007 | Customer Initiated Withdrawal | 10/1/2008
PJM | S12 | Killen 345kV |  | OH | Adams | Withdrawn | Dayton | 1300 | 1300 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 3/14/2007 | 3/12/2008 |  | 1/1/2014
PJM | S121 | Vineland 69kV | Howard M. Down Power Plant Unit 11 | NJ | Cumberland | In Service | AEC | 63 | 63 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2012 | 4/18/2012
PJM | S122 | Churchtown-Cumberland 230kV |  | NJ | Cumberland | Withdrawn | AEC | 478 | 478 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2007 | 7/28/2008 |  | 6/1/2010
PJM | S123 | Tiltonsville 138kV | Pike Island | OH | Jefferson | Withdrawn | AEP | 50 | 39 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn | Interim Study | 7/31/2007 | 6/2/2009 | Customer Initiated Withdrawal | 3/1/2012
PJM | S124 | Aroyo-Wilie Ridge 138kV |  | WV | Hancock | Withdrawn | APS | 45 | 45 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn |  | 7/31/2007 | 3/27/2009 | Customer Initiated Withdrawal | 9/1/2010
PJM | S13 | Keystone 345kV | Montpelier | IN | Wells | In Service | AEP | 19 | 19 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/19/2007 |  |  | 12/31/2008 | 12/31/2008
PJM | S14 | Dans Mountain | Dans Mountain | PA | Allegheny | Under Construction | APS | 54.9 | 14 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/20/2007 |  |  | 3/1/2025
PJM | S17 | Talbert 230kV |  | MD | Charles | Withdrawn | PEPCO | 225 | 225 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/19/2007 | 12/18/2013 | Customer Milestone Not Met | 12/31/2017
PJM | S18 | Talbert 230kV |  | MD | Charles | Withdrawn | PEPCO | 1250 | 1250 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/19/2007 | 2/21/2008 | Customer Milestone Not Met | 12/31/2011
PJM | S19 | Pine Grove-Frailey 69kV |  | PA | Schuylkill | Withdrawn | PPL | 28 | 5.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 3/19/2007 | 11/1/2007 | Customer Initiated Withdrawal | 10/1/2009
PJM | S20 | Pine Grove-Fishbach 69kV | Pine Grove WF | PA | Schuylkill | Withdrawn | PPL | 50 | 10 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 3/19/2007 | 5/12/2011 | Customer Initiated Withdrawal | 5/1/2013
PJM | S22 | Peach Bottom 500kV |  | PA | York | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/28/2007 | 11/13/2007 | Customer Milestone Not Met | 6/1/2011
PJM | S23 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/28/2007 | 9/9/2009 | Customer Initiated Withdrawal | 6/1/2011
PJM | S25 | Parlin 230kV | Calpine Parlin Energy Center | NJ | Middlesex | In Service | JCPL | 114 | 114 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/9/2007 |  |  | 5/13/2008 | 5/13/2008
PJM | S26 | Bluff Point-Jay 138kV |  | IN | Jay | Withdrawn | AEP | 75 | 15 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 4/9/2007 | 5/29/2008 | Customer Initiated Withdrawal | 1/1/2009
PJM | S27 | Blue Mound I | Twin Groves I WF | IL | McLean | In Service | ComEd | 0 | 39.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 4/17/2007 |  |  | 6/24/2010 | 6/24/2010
PJM | S28 | Blue Mound II | Twin Groves II WF | IL | McLean | In Service | ComEd | 0 | 39.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 4/17/2007 |  |  | 6/24/2010 | 6/24/2010
PJM | S29 | Morgantown-Oak Grove |  | MD | Charles | Withdrawn | PEPCO | 900 | 900 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/24/2007 | 2/23/2008 | Customer Milestone Not Met | 12/31/2007
PJM | S29B | Somerset 23kV | SCI Laurel Highlands | PA | Somerset | Deactivated | PENELEC | 6.75 | 5.7 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2007 |  |  | 9/1/2011 | 9/29/2011
PJM | S30 | Gould | Sun Paper | MD | Baltimore City | In Service | BGE | 4 | 0 | Energy | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2007 |  |  | 8/8/2008 | 12/31/2007
PJM | S31 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 450 | 90 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 5/3/2007 | 4/9/2008 | Customer Milestone Not Met | 12/9/2009
PJM | S32 | Perryman | Perryman 6 Units 1-4 | MD | Harford | In Service | BGE | 130 | 130 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/3/2007 |  |  | 12/31/2015 | 5/9/2015
PJM | S33 | Riverside |  | MD | Baltimore County | Withdrawn | BGE | 120 | 85 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 5/3/2007 | 7/2/2009 | Customer Initiated Withdrawal | 5/1/2010
PJM | S34 | Handsome Lake Energy 345kV | Handsome Lake | PA | Venango | In Service | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/7/2007 |  |  | 6/1/2007 | 6/1/2007
PJM | S35 | Beverly 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 5/7/2007 |  |  | 6/27/2007 | 6/1/2008
PJM | S36 | Kankakee 138 kV | Kankakee Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 35 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/7/2007 |  |  | 6/30/2015 | 7/28/2015
PJM | S37 | Kankakee 138kV | Kelly Creek Wind Farm | IL | Kankakee | In Service | ComEd | 175 | 35 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/7/2007 |  |  | 12/1/2016 | 11/9/2016
PJM | S38 | Westvaco 138kV | Luke Paper | PA | Allegheny | Deactivated | APS | 8 | 0 | Energy | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 5/7/2007 |  |  | 1/26/2009 | 4/1/2009
PJM | S40 | Hegins | Commonwealth LF | PA | Schuylkill | In Service | PPL | 10.5 | 10.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Document Posted | 5/10/2007 |  |  | 1/21/2009 | 1/21/2009
PJM | S41 | Eldred-Reed 69kV | IntelliWatt | PA | Northumberland | Withdrawn | PPL | 12.5 | 12.5 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 5/10/2007 | 2/16/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | S42 | Eldred-Fairview | Penn Wind | PA | Northumberland | Withdrawn | PPL | 18 | 3.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 5/15/2007 | 1/8/2014 | Customer Initiated Withdrawal | 5/1/2013
PJM | S43 | Vineland | Vineland Unit #9 | NJ | Cumberland | In Service | AEC | 17 | 17 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 5/15/2007 |  |  | 11/12/2007 | 11/12/2007
PJM | S44 | Mifflin County |  | PA | Mifflin | Withdrawn | PENELEC | 110 | 22 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 5/18/2007 | 10/28/2008 | Customer Initiated Withdrawal | 12/1/2009
PJM | S45 | Mechanicsburg North |  | OH | Champaign | Withdrawn | Dayton | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/18/2007 | 3/12/2012 | Customer Initiated Withdrawal | 12/31/2009
PJM | S46 | Mechanicsburg South |  | OH | Champaign | Withdrawn | Dayton | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/18/2007 | 5/15/2009 | Customer Initiated Withdrawal | 12/31/2009
PJM | S49 | Bedford 115kV |  | PA | Bedford | Withdrawn | PENELEC | 90 | 18 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/24/2007 | 9/22/2010 | Customer Initiated Withdrawal | 10/31/2013
PJM | S50 | Occoquan 230kV | Ogden Martin | VA | Fairfax | In Service | Dominion | 18 | 18 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 5/24/2007 |  |  | 6/30/2007 | 6/30/2007
PJM | S51 | E. Liberty-Blue Jacket 69kV |  | OH | Logan | Withdrawn | Dayton | 99 | 19.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/29/2007 | 4/7/2010 | Customer Initiated Withdrawal | 6/1/2009
PJM | S52 | Morrisville 500kV |  | VA | Warren | Withdrawn | Dominion | 50 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 5/29/2007 | 7/2/2009 | Customer Milestone Not Met | 5/1/2012
PJM | S53 | Lee County E.C. 345kV |  | IL | Bureau | Withdrawn | ComEd | 20 | 4 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 5/29/2007 | 8/15/2008 | Customer Milestone Not Met | 9/1/2008
PJM | S54 | Tazewell 138kV |  | VA | Tazewell | Withdrawn | AEP | 130 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 6/5/2007 | 6/25/2009 | Customer Milestone Not Met | 12/31/2009
PJM | S55 | Zion 345kV | Zion Energy Center | IL | Lake | In Service | ComEd | 585 | 495 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/6/2007 |  |  | 2/25/2011 | 12/19/2011
PJM | S56 | Beaver Creek-Hazard 138kV |  | KY | Knott | Withdrawn | AEP | 535 | 535 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 6/8/2007 | 4/28/2008 | Customer Milestone Not Met | 1/1/2011
PJM | S59 | Sharpsburg 12kV | Wenning Poultry | OH | Mercer | In Service | Dayton | 1.89 | 0 | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/25/2007 |  |  | 11/1/2007 | 10/30/2008
PJM | S60 | Essex 26kV | Newark Boxboard | NJ | Essex | Withdrawn | PSEG | 63 | 63 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn | Withdrawn | 6/27/2007 | 5/8/2012 | Customer Milestone Not Met | 6/1/2008
PJM | S61 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/27/2007 |  |  | 10/11/2011 | 10/11/2011
PJM | S62 | LaSalle-Braidwood 345kV |  | IL | Lasalle | Withdrawn | ComEd | 500 | 100 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/3/2007 | 8/11/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | S63 | Tait 69kV | Tait Generating Station | OH | Montgomery | In Service | Dayton | 13 | 13 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/5/2007 |  |  | 6/29/2007 | 10/5/2007
PJM | S64 | York Inc. 115kV |  | PA | York | Withdrawn | ME | 18 | 18 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Document Posted | Withdrawn | 7/6/2007 | 5/31/2013 | Customer Initiated Withdrawal | 1/1/2011
PJM | S65 | Cambria |  | PA | Cambria | Withdrawn | PENELEC | 85 | 17 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 7/19/2007 | 12/30/2008 | Customer Initiated Withdrawal | 12/31/2010
PJM | S66 | Downing Avenue 115kV |  | PA | Erie | Withdrawn | PENELEC | 96 | 96 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Withdrawn |  | 7/20/2007 | 8/28/2008 | Customer Milestone Not Met | 4/1/2009
PJM | S67 | Gould St. | Gould Street | MD | Baltimore City | Deactivated | BGE | 101 | 101 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/26/2007 |  |  | 5/30/2008 | 6/1/2008
PJM | S70 | Eureka 138kV | Willow Island Hydro Generation Project | WV | Wetzel | In Service | APS | 36.4 | 36.4 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 7/27/2007 |  |  | 7/31/2015 | 11/15/2015
PJM | S71 | Bluff Point 138kV | Bluff Point | IN | Jay | In Service | AEP | 120 | 24 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/30/2007 |  |  | 12/31/2017 | 9/15/2017
PJM | S72 | Convoy-East Lima 345kV | Dog Creek Wind Farm | IN | Allen | Withdrawn | AEP | 240 | 48 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/30/2007 | 12/7/2015 | Customer Initiated Withdrawal | 12/31/2016
PJM | S73 | Lincoln-North Delphos |  | IN | Allen | Withdrawn | AEP | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2007 | 1/7/2014 | Customer Milestone Not Met | 12/31/2013
PJM | S74 | Mount Storm 500kV | Mount Storm Unit 2 | WV | Grant | In Service | Dominion | 38 | 25 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2011 | 6/1/2011
PJM | S75 | Mount Storm 500kV | Mount Storm Unit 3 | WV | Grant | Withdrawn | Dominion | 29 | 29 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 | 7/12/2012 | Queue Not Required | 6/1/2012
PJM | S76 | Mount Storm 500kV | Mount Storm Unit 1 | WV | Grant | In Service | Dominion | 38 | 25 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2013 | 6/6/2013
PJM | S77 | Clover 230kV |  | VA | Halifax | Withdrawn | Dominion | 16 | 16 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 7/31/2007 | 12/4/2008 | Customer Initiated Withdrawal | 11/1/2011
PJM | S78 | Clover 230kV |  | VA | Halifax | Withdrawn | Dominion | 19 | 19 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 7/31/2007 | 12/4/2008 | Customer Initiated Withdrawal | 4/1/2012
PJM | S79 | Chesterfield 230kV | Chesterfield Unit #6 | VA | Chesterfield | In Service | Dominion | 27 | 27 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 12/1/2010 | 12/1/2010
PJM | S80 | Chesterfield 230kV | Chesterfield Unit #5 | VA | Chesterfield | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2011 | 6/1/2011
PJM | S81 | Basin 230kV | Bellemeade | VA | City of Richmond | Deactivated | Dominion | 22 | 22 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 4/27/2010 | 4/27/2010
PJM | S82 | Surry 230kV | Gravel Neck Gas Turbine #3 | VA | Surry | In Service | Dominion | 19 | 19 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/6/2010 | 5/6/2010
PJM | S83 | Surry 230kV | Gravel Neck Gas Turbine #4 | VA | Surry | In Service | Dominion | 19 | 19 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/6/2010 | 5/6/2010
PJM | S84 | Surry 230kV | Gravel Neck Gas Turbine #5 | VA | Surry | In Service | Dominion | 19 | 19 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/6/2010 | 5/6/2010
PJM | S85 | Surry 230kV | Gravel Neck Gas Turbine #6 | VA | Surry | In Service | Dominion | 19 | 19 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 5/6/2010 | 5/6/2010
PJM | S86 | Darbytown 230kV | Darbytown GT1 | VA | Henrico | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S87 | Darbytown 230kV | Darbytown GT2 | VA | Henrico | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S88 | Darbytown 230kV | Darbytown GT3 | VA | Henrico | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S89 | Darbytown 230kV | Darbytown GT4 | VA | Henrico | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S90 | Elizabeth River 230kV | Elizabeth River GT1 | VA | City of Chesapeake | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S91 | Elizabeth River 230kV | Elizabeth River GT2 | VA | City of Chesapeake | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S92 | Elizabeth River 230kV | Elizabeth River GT3 | VA | City of Chesapeake | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S93 | Remington 230kV | Remington GT1 | VA | Fauquier | In Service | Dominion | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S94 | Remington 230kV | Remington GT2 | VA | Fauquier | In Service | Dominion | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S95 | Remington 230kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S96 | Remington 230kV | Remington GT4 | VA | Fauquier | In Service | Dominion | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | S97 | South Anna 230kV | South Anna Unit 1 | VA | Orange | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 | 7/12/2012 | Queue Not Required | 6/1/2013
PJM | S98 | South Anna 230kV | South Anna Unit 2 | VA | Orange | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2007 | 7/12/2012 | Queue Not Required | 6/1/2013
PJM | S99 | Possum Point 230kV |  | VA | Prince William | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Withdrawn | 7/31/2007 | 4/3/2009 | Customer Initiated Withdrawal | 5/1/2013
PJM | T06 | Yorktown 230kV | Yorktown 3 | VA | York | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 8/3/2007 | 7/12/2012 | Queue Not Required | 5/1/2014
PJM | T10 | Cranes Corner 34.5KV | Stafford Regional LF | VA | Stafford | In Service | Dominion | 3 | 3 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 8/15/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | T100 | Grover-East Towanda 230 kV |  | PA | Bradford | Withdrawn | PENELEC | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/12/2007 | 10/15/2008 | Customer Initiated Withdrawal | 9/30/2009
PJM | T101 | Glassrock 69kV |  | OH | Perry | Withdrawn | AEP | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Withdrawn |  | 11/12/2007 | 5/21/2008 |  | 11/1/2008
PJM | T102 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 10 | 10 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 11/13/2007 |  |  | 10/30/2007 | 9/2/2008
PJM | T103 | Sunbury 69kV | Sunbury #1 | PA | Snyder | In Service | PPL | 10 | 10 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 11/13/2007 |  |  | 10/30/2007 | 9/2/2008
PJM | T104 | Gosport 115kV | SPSA Navy Power Plant | VA | City of Portsmouth | In Service | Dominion | 20 |  | Energy | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Document Posted | 11/15/2007 |  |  | 4/1/2008 | 4/1/2008
PJM | T105 | Pontiac Midpoint-Wilton Center 350 MW |  | IL | Livingston | Withdrawn | ComEd | 350 | 70 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 11/20/2007 | 12/20/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | T106 | Lee County |  | IL | Bureau | Withdrawn | ComEd | 140 | 28 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/21/2007 | 4/27/2010 | Customer Milestone Not Met | 12/31/2008
PJM | T107 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 625 | 625 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/21/2007 |  |  | 3/31/2016 | 6/29/2015
PJM | T108 | Archbald 69kV | Archbald Generating Station | PA | Lackawanna | In Service | PPL | 9.2 | 9.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 11/29/2007 |  |  | 1/25/2010 | 1/25/2010
PJM | T109 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 12/3/2007 |  |  | 8/23/2010 | 8/23/2010
PJM | T11 | Laurel-Sussex 69kV | Southern LF Units 1-5 | DE | Sussex | In Service | DPL | 5 | 5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 8/15/2007 |  |  | 5/21/2010 | 5/21/2010
PJM | T110 | Keystone 500kV | Keystone Generating Station | PA | Indiana | In Service | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 12/3/2007 |  |  | 8/23/2010 | 8/23/2010
PJM | T111 | Buchanan Hydro-Niles 69kV | Southeast Berrien LF | MI | Berrien | In Service | AEP | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 12/12/2007 |  |  | 5/29/2009 | 5/29/2009
PJM | T113 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 16 | 16 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Withdrawn | 12/14/2007 | 11/10/2008 | Customer Initiated Withdrawal | 5/31/2010
PJM | T114 | Croydon 230kV |  | PA | Bucks | Withdrawn | PECO | 32.5 | 32.5 | Capacity | Generation Interconnection | Oil | Document Posted | Withdrawn |  |  | 12/14/2007 | 2/20/2008 | Customer Milestone Not Met | 5/31/2010
PJM | T115 | Croydon 230kV |  | PA | Bucks | Withdrawn | PECO | 32.5 | 32.5 | Capacity | Generation Interconnection | Oil | Document Posted | Withdrawn |  |  | 12/14/2007 | 2/20/2008 | Customer Milestone Not Met | 5/31/2010
PJM | T116 | LaSalle 1 |  | IL | Lasalle | Withdrawn | ComEd | 18 | 18 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 12/17/2007 | 3/19/2010 | Customer Milestone Not Met | 3/1/2008
PJM | T117 | Hunlock Creek 69kV | Hunlock Creek | PA | Luzerne | In Service | UGI | 126 | 126 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/17/2007 |  |  | 6/30/2011 | 1/31/2011
PJM | T118 | Linwood 230kV | Phillips Island CT1, CT2, CT3, CT4 | PA | Delaware | In Service | PECO | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/19/2007 |  |  | 9/30/2009 | 9/30/2009
PJM | T119 | Metuchen 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 12/20/2007 | 12/21/2009 | Customer Milestone Not Met | 1/1/2011
PJM | T12 | Kent-Harrington 69kV | Central LF Units 1-4 | DE | Kent | In Service | DPL | 4 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 8/15/2007 |  |  | 8/14/2007 | 10/1/2007
PJM | T120 | Kankakee #3 138kV |  | IL | Iroquois | Withdrawn | ComEd | 250 | 50 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 12/28/2007 | 6/30/2010 | Customer Initiated Withdrawal | 12/31/2012
PJM | T121 | Potter-Gold 115kV | Potter Wind Farm | PA | Potter | Withdrawn | PENELEC | 75 | 15 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/28/2007 | 2/22/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | T122 | Ocean Bay 138kV |  | MD | Worcester | Withdrawn | DPL | 600 | 120 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 12/28/2007 | 7/30/2009 | Customer Initiated Withdrawal | 6/1/2015
PJM | T123 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 440 | 440 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/2/2008 | 5/29/2009 | Customer Initiated Withdrawal | 6/1/2012
PJM | T124 | Latham-Pontiac I 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/2/2008 | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | T125 | Latham-Pontiac II 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/2/2008 | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | T126 | Olive-Dequine 345kV | Meadow Lake WF II, Meadow Lake WF III | IN | Benton | In Service | AEP | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 1/2/2008 |  |  | 10/28/2010 | 10/28/2010
PJM | T127 | Olive-Dequine 345kV | Meadow Lake WF 4 - 5 | IN | White | In Service | AEP | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 1/2/2008 |  |  | 12/31/2017 | 10/30/2010
PJM | T128 | Masontown 500kV |  | PA | Fayette | Withdrawn | APS | 700 | 700 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 1/7/2008 | 6/2/2008 | Customer Milestone Not Met | 1/1/2012
PJM | T129 | Printz 230kV | Liberty | PA | Delaware | In Service | PECO | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/8/2008 |  |  | 12/1/2008 | 12/1/2008
PJM | T130 | Maddox Creek-RP Mone 345 kV |  | OH | Paulding | Withdrawn | AEP | 300 | 60 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 1/9/2008 | 1/26/2015 | Customer Initiated Withdrawal | 12/31/2016
PJM | T131 | Lincoln-Sterling 138kV | Timber Road III | OH | Paulding | In Service | AEP | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/9/2008 |  |  | 12/31/2017 | 11/23/2016
PJM | T133 | Chalk Point-Bowie 230kV | Powell Generation Facility | MD | Prince George's | Withdrawn | PEPCO | 225 | 225 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/10/2008 | 9/25/2014 | Customer Initiated Withdrawal | 7/31/2018
PJM | T134 | Chalk Point-Bowie 230kV | Powell Generation Facility | MD | Prince George's | Withdrawn | PEPCO | 325 | 325 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/10/2008 | 9/25/2014 | Customer Initiated Withdrawal | 7/31/2018
PJM | T135 | Chambers 230kV |  | NJ | Salem | Withdrawn | AEC | 15 | 15 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Not Required | 1/10/2008 | 4/28/2009 | Queue Not Required | 1/7/2008
PJM | T142 | Southwest Lima-Marysville 345kV | Van Wert II | OH | Hardin | Withdrawn | AEP | 300 | 60 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/15/2008 | 9/18/2018 |  | 12/31/2019
PJM | T143 | Hennepin |  | IL | Putnam | Withdrawn | ComEd | 250 | 50 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/16/2008 | 11/16/2015 | Customer Initiated Withdrawal | 12/31/2016
PJM | T144 | Pocomoke |  | MD | Somerset | Withdrawn | DPL | 19.8 | 10 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Document Posted | Withdrawn | 1/17/2008 | 7/30/2014 | Customer Initiated Withdrawal | 1/1/2010
PJM | T146 | England |  | NJ | Cape May | Withdrawn | AEC | 346 | 69.2 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 1/22/2008 | 1/28/2014 | Customer Initiated Withdrawal | 12/31/2020
PJM | T147 | Perryman | Perryman Generating Unit 51 | MD | Harford | In Service | BGE | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/24/2008 |  |  | 6/1/2008 | 6/1/2008
PJM | T148 | Wempletown-Belvidere 138kV |  | IL | Boone | Withdrawn | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/25/2008 | 9/19/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | T149 | Birchwood 230kV |  | VA | King George | Withdrawn | Dominion | 580 | 580 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/28/2008 | 5/29/2008 | Customer Milestone Not Met | 1/1/2012
PJM | T152 | North Haverhill 69kV |  | OH | Scioto | Withdrawn | AEP | 140 | 140 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 1/28/2008 | 9/28/2009 | Customer Milestone Not Met | 1/1/2011
PJM | T153 | Milford 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1.12 | 1.12 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted |  |  | 1/28/2008 | 12/11/2008 | Customer Initiated Withdrawal | 6/1/2008
PJM | T154 | Bellefontaine 69kV | Cherokee Run LF | OH | Logan | Deactivated | Dayton | 10 | 10 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/28/2008 |  |  | 2/27/2009 | 2/27/2009
PJM | T155 | Belknap 25kV | Mahoning Creek Dam Hydro Project | PA | Armstrong | In Service | APS | 6 | 6 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2008 |  |  | 3/1/2014 | 12/26/2013
PJM | T156 | Champion |  | PA | Washington | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required |  | 1/30/2008 | 5/28/2013 | Customer Initiated Withdrawal | 2/28/2011
PJM | T157 | New Creek Mountain 500kV | New Creek Mountain Wind Farm | WV | Mineral | In Service | Dominion | 102.5 | 20.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/30/2008 |  |  | 12/18/2016 | 12/26/2016
PJM | T158 | Elk Garden-Junction 138kV |  | WV | Mineral | Withdrawn | APS | 70 | 14 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/30/2008 | 7/24/2008 |  | 11/30/2010
PJM | T159 | Bergen 230kV |  | NJ | Hudson | Withdrawn | PSEG | 230 | 230 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/30/2008 | 5/7/2008 |  | 6/1/2011
PJM | T16 | Kelso Gap 138kV | Fair Wind Project | MD | Garrett | In Service | APS | 30 | 6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 8/20/2007 |  |  | 10/31/2015 | 11/15/2015
PJM | T162 | Lock Haven |  | PA | Clinton | Withdrawn | PPL | 90 | 63 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Withdrawn |  | 1/30/2008 | 7/16/2009 | Customer Initiated Withdrawal | 9/30/2011
PJM | T163 | Carter Fabrics 115kV |  | VA | Halifax | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Wood | Document Posted | Withdrawn |  |  | 1/30/2008 | 5/29/2008 | Customer Milestone Not Met | 4/1/2012
PJM | T164 | Muskingum River | Muskingum River #5 | OH | Washington | In Service | AEP | 15 | 15 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2008 |  |  | 2/1/2008 | 2/1/2008
PJM | T165 | Conesville #5 | Conesville #5 | OH | Coshocton | Deactivated | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2008 |  |  | 2/1/2008 | 2/1/2008
PJM | T166 | Conesville #6 | Conesville #6 | OH | Coshocton | Deactivated | AEP | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2008 |  |  | 2/1/2008 | 2/1/2008
PJM | T167 | Four Rivers 230kV | Four Rivers NUG CC | VA | Hanover | Withdrawn | Dominion | 190 | 120 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2008 | 1/10/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | T168 | Four Rivers 500kV |  | VA | Hanover | Withdrawn | Dominion | 1010 | 1010 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/31/2008 | 7/21/2009 | Customer Milestone Not Met | 6/1/2013
PJM | T169 | Corson |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 1/31/2008 | 6/3/2008 | Customer Milestone Not Met | 1/1/2009
PJM | T170 | Graceton |  | MD | Harford | Withdrawn | BGE | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/31/2008 | 2/29/2008 | Customer Initiated Withdrawal | 1/1/2009
PJM | T171 | Morgantown 69kV | Newburg High Efficiency Flywheel | MD | Charles | Withdrawn | PEPCO | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2008 | 7/23/2010 | Customer Initiated Withdrawal | 1/1/2009
PJM | T172 | Northwest |  | MD | Baltimore County | Withdrawn | BGE | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/31/2008 | 2/29/2008 | Customer Initiated Withdrawal | 1/1/2009
PJM | T174 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 930 | 900 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2008 |  |  | 3/1/2019 | 11/18/2018
PJM | T175 | Tiltonsville 69kV |  | OH | Jefferson | Withdrawn | AEP | 11 | 11 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 1/31/2008 | 6/2/2009 | Customer Initiated Withdrawal | 3/1/2012
PJM | T179 | Steel City |  | PA | Northampton | Withdrawn | PPL | 873 | 873 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 1/31/2008 | 9/19/2008 | Customer Milestone Not Met | 6/1/2012
PJM | T180 | Gainesville 230kV |  | VA | Prince William | Withdrawn | Dominion | 690 | 650 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 1/31/2008 | 3/10/2010 | Customer Milestone Not Met | 6/1/2012
PJM | T182 | TMI 230kV | Three Mile Island 1 | PA | Dauphin | Deactivated | ME | 14 | 16.8 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2008 |  |  | 4/10/2015 | 10/22/2015
PJM | T183 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/31/2008 | 1/3/2013 | Customer Initiated Withdrawal | 10/30/2010
PJM | T184 | Olive-Dequine 345kV |  | IN | White | Withdrawn | AEP | 200 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/31/2008 | 1/3/2013 | Customer Initiated Withdrawal | 10/30/2010
PJM | T185 | Lewis |  | NJ | Cape May | Withdrawn | AEC | 20 | 4 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 1/31/2008 | 6/19/2008 | Customer Milestone Not Met | 4/1/2011
PJM | T186 | England |  | NJ | Cape May | Withdrawn | AEC | 20 | 4 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 1/31/2008 | 6/19/2008 | Customer Milestone Not Met | 4/1/2011
PJM | T187 | Reybold |  | DE | New Castle | Withdrawn | DPL | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2008 | 8/24/2009 | Customer Milestone Not Met | 1/1/2009
PJM | T192 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 1.8 | 0 | Energy | Generation Interconnection | Hydro | Withdrawn |  |  |  | 1/31/2008 | 4/30/2008 | Customer Initiated Withdrawal | 9/30/2008
PJM | T20 | Falls | Exelon Epuron Solar Energy Center | PA | Bucks | In Service | PECO | 3.3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/30/2007 |  |  | 12/23/2008 | 4/28/2008
PJM | T27 | Hyndman 34kV |  | PA | Somerset | Withdrawn | APS | 60 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/7/2007 | 1/9/2009 | Customer Initiated Withdrawal | 1/1/2010
PJM | T32 | Collins |  | SD | McPherson | Withdrawn | ComEd | 2500 | 925 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/12/2007 | 12/6/2012 | Customer Initiated Withdrawal | 9/12/2014
PJM | T33 | Collins II |  | SD | McPherson | Withdrawn | ComEd | 1000 | 370 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/12/2007 | 3/2/2012 | Customer Initiated Withdrawal | 9/12/2014
PJM | T34 | Collins III |  | SD | McPherson | Withdrawn | ComEd | 1500 | 555 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/12/2007 | 3/2/2012 | Customer Initiated Withdrawal | 9/12/2014
PJM | T35 | Byron Wind IV |  | ND | LaMoure | Withdrawn | ComEd | 1500 | 300 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/12/2007 | 4/22/2010 | Customer Initiated Withdrawal | 9/12/2014
PJM | T37 | Hegins |  | PA | Schuylkill | Withdrawn | PPL | 150 | 30 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/14/2007 | 12/17/2008 | Customer Initiated Withdrawal | 12/1/2010
PJM | T38 | Delco Tap 230kV |  | PA | Delaware | Withdrawn | PECO | 900 | 900 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/14/2007 | 9/8/2008 | Customer Initiated Withdrawal | 6/1/2012
PJM | T39 | Coudersport 46kV |  | PA | Potter | Withdrawn | APS | 18 | 3.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/14/2007 | 12/6/2010 | Customer Initiated Withdrawal | 3/31/2011
PJM | T40 | South Harrington |  | DE | Kent | Withdrawn | DPL | 225 | 225 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 9/14/2007 | 7/21/2009 | Customer Initiated Withdrawal | 6/1/2012
PJM | T41 | Kearny 138kV | Kearny #13 | NJ | Hudson | In Service | PSEG | 178 | 178 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/19/2007 |  |  | 8/31/2012 | 5/7/2012
PJM | T42 | Kearny 138kV | Kearny #14 | NJ | Hudson | In Service | PSEG | 89 | 89 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/19/2007 |  |  | 8/31/2012 | 5/7/2012
PJM | T43 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 178 | 178 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 9/19/2007 | 5/30/2012 | Customer Initiated Withdrawal | 6/1/2012
PJM | T44 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 205 | 205 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 9/19/2007 | 7/28/2009 | Customer Milestone Not Met | 9/19/2014
PJM | T45 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 205 | 205 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 9/19/2007 | 4/10/2012 | Customer Initiated Withdrawal | 6/1/2011
PJM | T48 | Coldwater-Rossburg 69kV |  | OH | Mercer | Withdrawn | Dayton | 40 | 8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/21/2007 | 5/9/2012 | Customer Initiated Withdrawal | 11/30/2013
PJM | T49 | Steel City | Bethlehem Gen Facility Units 1 - 8 | PA | Northampton | In Service | PPL | 42 | 42 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 5/6/2009 | 5/6/2009
PJM | T51 | Hay Road | Hay Road Units 1, 2, 3, 4 | DE | New Castle | In Service | DPL | 13 | 13 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 5/26/2010 | 5/26/2010
PJM | T52 | Red Lion 500kV | Hay Road Units 5, 6, 7, 8 | DE | New Castle | In Service | DPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 5/1/2008 | 5/1/2008
PJM | T53 | Delaware City | Delaware City Unit #10 | DE | New Castle | In Service | DPL | 7.3 | 7.3 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | T54 | Cumberland 138kV | Cumberland Unit 1 | NJ | Cumberland | In Service | AEC | 9.4 | 9.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 8/12/2010 | 8/12/2010
PJM | T55 | Sherman Ave | Sherman Avenue Unit 1 | NJ | Cumberland | In Service | AEC | 12.4 | 12.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 5/3/2010 | 5/3/2010
PJM | T56 | Christiana | Christiana Units #11 & 14 | DE | New Castle | In Service | DPL | 8.4 | 8.4 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 5/31/2009 | 5/31/2009
PJM | T57 | Middle |  | NJ | Cape May | Withdrawn | AEC | 22.2 | 22.2 | Capacity | Generation Interconnection | Oil | Document Posted | Withdrawn |  |  | 9/21/2007 | 2/7/2008 | Customer Milestone Not Met | 4/1/2009
PJM | T59 | Mickleton |  | NJ | Gloucester | In Service | AEC | 14.4 | 14.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 7/7/2011 | 7/7/2011
PJM | T60 | Missouri Ave |  | NJ | Atlantic | Withdrawn | AEC | 10.5 | 10.5 | Capacity | Generation Interconnection | Oil | Document Posted | Withdrawn |  |  | 9/21/2007 | 2/7/2008 | Customer Milestone Not Met | 4/1/2009
PJM | T61 | Cedar |  | NJ | Ocean | Withdrawn | AEC | 8.3 | 8.3 | Capacity | Generation Interconnection | Oil | Document Posted | Withdrawn |  |  | 9/21/2007 | 2/7/2008 | Customer Milestone Not Met | 4/1/2009
PJM | T63 | Carlls Corner |  | NJ | Cumberland | Withdrawn | AEC | 27.2 | 27.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/21/2007 | 2/7/2008 | Customer Milestone Not Met | 4/1/2009
PJM | T66 | Tasley | Tasley | VA | Accomack | In Service | DPL | 6.7 | 6.7 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 3/26/2009 | 3/26/2009
PJM | T67 | West | West #1 | DE | New Castle | In Service | DPL | 5.3 | 5.3 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 4/1/2009 | 4/1/2009
PJM | T68 | Edgemoor | Edgemoor #10 | DE | New Castle | In Service | DPL | 5.2 | 5.2 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2007 |  |  | 4/1/2009 | 4/1/2009
PJM | T73 | Hanging Rock 765kV | Hanging Rock CC2 | OH | Lawrence | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2007 |  |  | 6/1/2008 | 6/1/2008
PJM | T74 | Elgin | Elgin Energy Center | IL | Kane | In Service | ComEd | 16 | 16 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/26/2007 |  |  | 9/1/2007 | 1/8/2013
PJM | T75 | South River 230kV | South River | NJ | Middlesex | In Service | JCPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2007 |  |  | 4/16/2009 | 11/15/2012
PJM | T76 | South River 230 kV | South River | NJ | Middlesex | In Service | JCPL | 27 | 27 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2007 |  |  | 6/15/2009 | 11/15/2012
PJM | T77 | Linden 230kV | Linden 1 & 2 | NJ | Union | In Service | PSEG | 44 | 44 | Capacity | Generation Interconnection | Natural Gas | Not Required | Document Posted | Not Required | Document Posted | 10/5/2007 |  |  | 5/31/2013 | 6/1/2008
PJM | T78 | Arnolds Corner 34.5kV | King George Renewable Energy Facility | VA | King George | In Service | Dominion | 9.8 | 8.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 10/5/2007 |  |  | 5/4/2010 | 5/4/2010
PJM | T79 | Shacklefords 34.5kv | Middle Pennisula Gas to Energy Power Plant | VA | Gloucester | In Service | Dominion | 6.2 | 6.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 10/5/2007 |  |  | 10/1/2009 | 10/1/2009
PJM | T81 | Cedar 230kV |  | NJ | Ocean | Withdrawn | AEC | 350 | 70 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 10/15/2007 | 7/18/2008 | Customer Initiated Withdrawal | 12/31/2012
PJM | T82 | Cardiff 230kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 70 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 10/15/2007 | 7/20/2009 | Customer Milestone Not Met | 12/31/2012
PJM | T83 | Merion 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 70 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 10/15/2007 | 7/9/2008 | Customer Milestone Not Met | 12/31/2012
PJM | T84 | Corson 138kV |  | NJ | Cape May | Withdrawn | AEC | 350 | 70 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 10/15/2007 | 10/15/2012 | Customer Initiated Withdrawal | 6/1/2015
PJM | T85 | Roxbury-Blain 23kV | Cumberland County LF | PA | Cumberland | In Service | PENELEC | 6.4 | 6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 10/16/2007 |  |  | 12/31/2008 | 12/31/2008
PJM | T86 | Bradford 34.5kV | North Tier LF | PA | Bradford | In Service | PENELEC | 1.6 | 1.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 10/16/2007 |  |  | 7/1/2008 | 7/1/2008
PJM | T92 | Paddtown I Wind 1500 MW |  | IA | Pocahontas | Withdrawn | ComEd | 1500 | 300 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 10/23/2007 | 9/16/2009 | Customer Initiated Withdrawal | 8/1/2010
PJM | T93 | Paddtown II Wind 1500 MW |  | IA | Pocahontas | Withdrawn | ComEd | 1500 | 300 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 10/23/2007 | 9/16/2009 | Customer Initiated Withdrawal | 8/1/2010
PJM | T94 | Cook-Palesades 345kV |  | MI | Van Buren | In Service | ITCI | 1035 | 1035 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/24/2007 |  |  | 6/30/2016 | 6/1/2016
PJM | T98 | South Mahwah 69kV |  | NJ | Bergen | Withdrawn | RECO | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/29/2007 | 6/2/2009 | Customer Initiated Withdrawal | 10/29/2007
PJM | T99 | Wempletown-Belvidere 138kV |  | IL | Boone | Withdrawn | ComEd | 100 | 20 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/29/2007 | 9/19/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | U1-010 | Peach Bottom | Delta | PA | York | In Service | PECO | 18 | 18 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/7/2008 |  |  | 3/1/2011 | 3/1/2011
PJM | U1-011 | Minonk II 34.5kV |  | IL | Woodford | Withdrawn | ComEd | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 2/7/2008 | 12/15/2008 | Customer Initiated Withdrawal | 12/1/2009
PJM | U1-012 | Richmond |  | PA | Philadelphia | Withdrawn | PECO | 630 | 630 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/7/2008 | 9/3/2009 | Customer Initiated Withdrawal | 1/1/2013
PJM | U1-013 | Eddystone |  | PA | Delaware | Withdrawn | PECO | 630 | 630 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/7/2008 | 10/14/2009 | Customer Initiated Withdrawal | 1/1/2013
PJM | U1-014 | Cromby |  | PA | Montgomery | Withdrawn | PECO | 700 | 700 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/7/2008 | 8/15/2008 | Customer Initiated Withdrawal | 1/1/2013
PJM | U1-015 | Barbados |  | PA | Montgomery | Withdrawn | PECO | 700 | 700 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/7/2008 | 6/18/2008 | Customer Initiated Withdrawal | 1/1/2013
PJM | U1-016 | Muddy Run |  | PA | Lancaster | Withdrawn | PECO | 700 | 700 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/7/2008 | 6/18/2008 | Customer Initiated Withdrawal | 1/1/2013
PJM | U1-024 | Dequine-Eugene 345kV |  | IN | Warren | Withdrawn | AEP | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/12/2008 | 9/8/2008 | Customer Milestone Not Met | 12/1/2010
PJM | U1-029 | Sherman Ave 138kV |  | NJ | Cumberland | Withdrawn | AEC | 110 | 110 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Withdrawn |  | 2/19/2008 | 7/21/2009 | Customer Initiated Withdrawal | 5/1/2012
PJM | U1-030 | Missouri Ave |  | NJ | Atlantic | Withdrawn | AEC | 110 | 110 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Withdrawn |  | 2/19/2008 | 7/21/2009 | Customer Initiated Withdrawal | 5/1/2013
PJM | U1-031 | Earleys 230kV |  | NC | Hertford | Withdrawn | Dominion | 80 | 80 | Capacity | Generation Interconnection | Wood | Document Posted | Document Posted | Document Posted | Withdrawn | 2/19/2008 | 12/3/2010 | Customer Initiated Withdrawal | 6/30/2012
PJM | U1-032 | Hopewell 230kV |  | VA | City of Hopewell | Deactivated | Dominion | 20 | 0 | Energy | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/20/2008 |  |  | 9/28/2009 | 9/28/2009
PJM | U1-033 | Miami Fort 345kV |  | OH | Hamilton | Withdrawn | Dayton | 4 | 4 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 2/21/2008 | 7/18/2008 | Customer Initiated Withdrawal | 2/6/2008
PJM | U1-034 | Miami Fort 345kV |  | OH | Hamilton | Withdrawn | Dayton | 4 | 4 | Capacity | Generation Interconnection | Coal | Withdrawn |  |  |  | 2/21/2008 | 7/18/2008 | Customer Initiated Withdrawal | 2/6/2008
PJM | U1-036 | Steel Side 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 220 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/25/2008 | 10/29/2009 | Customer Milestone Not Met | 6/1/2011
PJM | U1-037 | LaSalle-Plano 345kV |  | IL | Lasalle | Withdrawn | ComEd | 250 | 32.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/29/2008 | 7/12/2010 | Customer Initiated Withdrawal | 9/1/2010
PJM | U1-038 | Millheim |  | PA | Centre | Withdrawn | APS | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/29/2008 | 1/27/2010 |  | 12/1/2010
PJM | U1-044 | Frederick County VA Regional Landfill | Fredrick County Regional LF | VA | Frederick | In Service | APS | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/18/2008 |  |  | 11/4/2010 | 1/1/2009
PJM | U1-048 | Reichs Ford Landfill | Reichs LF | MD | Frederick | Deactivated | APS | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/24/2008 |  |  | 5/3/2010 | 2/1/2009
PJM | U1-049 | Kankakee #4 138kV |  | IL | Kankakee | Withdrawn | ComEd | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/24/2008 | 12/6/2013 | Customer Initiated Withdrawal | 9/1/2010
PJM | U1-050 | Clearfield |  | PA | Clearfield | Withdrawn | PENELEC | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 3/25/2008 | 5/12/2009 | Customer Initiated Withdrawal | 12/1/2011
PJM | U1-051 | Clearfield |  | PA | Clearfield | Withdrawn | PENELEC | 130 | 16.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/25/2008 | 1/9/2012 | Customer Initiated Withdrawal | 12/1/2011
PJM | U1-054 | Calumet | River Energy Center | IL | Cook | In Service | ComEd | 27 | 27 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/26/2008 |  |  | 3/28/2008 | 1/25/2013
PJM | U1-056 | Lewis 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 45.5 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 3/28/2008 | 7/14/2014 | Customer Initiated Withdrawal | 4/1/2014
PJM | U1-057 | North Lebanon |  | PA | Lebanon | Withdrawn | ME | 950 | 900 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/31/2008 | 1/28/2010 | Customer Initiated Withdrawal | 6/1/2011
PJM | U1-058 | Olive-Dumont 345kV |  | IN | St. Joseph | Withdrawn | AEP | 586 | 586 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/2/2008 | 1/8/2009 | Customer Initiated Withdrawal | 6/1/2013
PJM | U1-059 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 48.3 | 9.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 4/2/2008 |  |  | 12/31/2017 | 11/15/2017
PJM | U1-060 | East Lima-South Kenton 138kV |  | OH | Hardin | Withdrawn | AEP | 151.8 | 19.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 4/2/2008 | 1/23/2013 | Customer Initiated Withdrawal | 4/1/2011
PJM | U1-065 | Middle 69kV |  | NJ | Cape May | Withdrawn | AEC | 20 | 20 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Withdrawn |  | 4/7/2008 | 7/28/2009 | Customer Initiated Withdrawal | 5/1/2009
PJM | U1-066 | Carlls Corner 69kV | Carll's Corner Units 1 & 2 | NJ | Cumberland | In Service | AEC | 18 | 18 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 4/7/2008 |  |  | 6/24/2011 | 6/24/2011
PJM | U1-067 | Honey Brook | Granger of Honeybrook | PA | Lancaster | In Service | PPL | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 4/9/2008 |  |  | 6/1/2011 | 6/1/2011
PJM | U1-068 | York 115kV | York | PA | Lancaster | Deactivated | ME | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/14/2008 |  |  | 2/28/2011 | 2/28/2011
PJM | U1-069 | Emsworth Locks & Dam |  | PA | Allegheny | Withdrawn | DL | 30 | 30 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Withdrawn | 4/14/2008 | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-070 | Dashields Lock & Dam |  | PA | Allegheny | Withdrawn | DL | 14 | 14 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 4/14/2008 | 9/11/2008 | Customer Milestone Not Met | 1/1/2015
PJM | U1-071 | CW Bill Young Lock & Dam |  | PA | Allegheny | Withdrawn | APS | 15 | 15 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Not Required | 4/14/2008 | 10/23/2009 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-072 | Braddock Lock & Dam |  | PA | Allegheny | Withdrawn | DL | 10 | 10 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn |  | 4/14/2008 | 8/6/2009 | Customer Milestone Not Met | 1/1/2015
PJM | U1-073 | Allegheny Lock & Dam #7 |  | PA | Allegheny | Withdrawn | APS | 16 | 16 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Not Required | 4/14/2008 | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-074 | Point Marion Lock & Dam |  | PA | Fayette | Withdrawn | APS | 10 | 10 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Not Required | 4/14/2008 | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-075 | Sutton Dam |  | WV | Braxton | Withdrawn | APS | 12 | 12 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Withdrawn | 4/14/2008 | 7/10/2013 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-076 | Allegheny Lock & Dam #2 |  | PA | Allegheny | Withdrawn | DL | 12 | 12 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Withdrawn | 4/14/2008 | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-077 | Allegheny Lock & Dam #4 |  | PA | Allegheny | Withdrawn | APS | 16 | 16 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn |  | 4/14/2008 | 7/24/2009 | Customer Milestone Not Met | 1/1/2015
PJM | U1-078 | Tionesta Dam |  | PA | Forest | Withdrawn | PENELEC | 8 | 8 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 4/14/2008 | 11/10/2008 | Customer Milestone Not Met | 1/1/2015
PJM | U1-079 | Opekiska Lock & Dam |  | WV | Monongalia | Withdrawn | APS | 10 | 10 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Not Required | 4/14/2008 | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-080 | Montgomery Lock & Dam |  | PA | Beaver | Withdrawn | DL | 35 | 35 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Withdrawn | 4/14/2008 | 1/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-081 | Monongahela Lock & Dam #4 |  | PA | Westmoreland | Withdrawn | APS | 10 | 10 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Not Required | 4/14/2008 | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-082 | Maxwell Lock & Dam |  | PA | Fayette | Withdrawn | APS | 10 | 10 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Not Required | 4/14/2008 | 2/25/2010 | Customer Initiated Withdrawal | 1/1/2015
PJM | U1-083 | Hildebrand Lock & Dam |  | WV | Monongalia | Withdrawn | APS | 10 | 10 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn |  | 4/14/2008 | 7/24/2009 | Customer Milestone Not Met | 1/1/2015
PJM | U1-086 | Eldred 230kV |  | PA | Schuylkill | Withdrawn | PPL | 150 | 150 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Withdrawn |  | 4/17/2008 | 12/19/2009 | Customer Milestone Not Met | 6/1/2010
PJM | U1-087 | Dequine 345kV |  | IN | Benton | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 4/18/2008 | 1/2/2013 | Customer Milestone Not Met | 12/31/2010
PJM | U1-088 | Dequine 345kV |  | IN | Benton | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 4/18/2008 | 1/2/2013 | Customer Milestone Not Met | 12/31/2010
PJM | U1-089 | Paper Tap 69kV | Kimberly Clark | PA | Delaware | Deactivated | PECO | 0 | 20 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Document Posted | 4/18/2008 |  |  | 10/15/2008 | 10/15/2008
PJM | U1-090 | Killen 345kV | Killen Electric Generating Station | OH | Adams | Deactivated | Dayton | 12 | 12 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 4/22/2008 |  |  | 5/31/2008
PJM | U1-093 | Ladysmith 230kV | Ladysmith Unit 3 | VA | Caroline | In Service | Dominion | 20 | 0 | Energy | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2008 |  |  | 4/8/2008 | 10/1/2009
PJM | U1-094 | Ladysmith 230kV | Ladysmith Unit 4 | VA | Caroline | In Service | Dominion | 20 | 0 | Energy | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2008 |  |  | 4/8/2008 | 10/1/2009
PJM | U1-095 | Ladysmith 230kV | Ladysmith Unit 5 | VA | Caroline | In Service | Dominion | 20 | 0 | Energy | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2008 |  |  | 3/31/2009 | 3/31/2009
PJM | U1-096 | Reybold |  | DE | New Castle | Withdrawn | DPL | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 4/29/2008 | 8/26/2008 | Customer Milestone Not Met | 1/1/2009
PJM | U1-097 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/2008 | 12/9/2008 | Customer Milestone Not Met | 6/1/2011
PJM | U1-099 | Joliet 4 MW |  | IL | Will | Withdrawn | ComEd | 4 | 4 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 4/30/2008 | 4/21/2010 | Customer Initiated Withdrawal | 3/31/2011
PJM | U2-003 | Wempletown |  | IL | Stephenson | Withdrawn | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 5/13/2008 | 4/29/2009 | Customer Initiated Withdrawal | 9/1/2010
PJM | U2-005 | Branchburg-Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1010 | 1010 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/14/2008 | 12/1/2008 | Customer Initiated Withdrawal | 6/1/2014
PJM | U2-006 | Branchburg-Deans 500kV |  | NJ | Middlesex | Withdrawn | PSEG | 1010 | 1010 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/14/2008 | 12/1/2008 | Customer Initiated Withdrawal | 6/1/2015
PJM | U2-013 | Northeast 34.5kV | Richmond Energy Facility | VA | Henrico | In Service | Dominion | 8 | 8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 5/16/2008 |  |  | 10/1/2011 | 12/29/2011
PJM | U2-015 | Harwood-E. Palmerton 230kV | Buck Mountain Wind Farm | PA | Columbia | Withdrawn | PPL | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/22/2008 | 11/15/2019 |  | 10/1/2019
PJM | U2-016 | East Towanda-Grover 230kV |  | PA | Bradford | Withdrawn | PENELEC | 85 | 11.05 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/23/2008 | 1/13/2012 | Customer Initiated Withdrawal | 10/1/2011
PJM | U2-017 | Tazewell-Baileysville 138kV |  | VA | Tazewell | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 5/23/2008 | 10/30/2008 | Customer Initiated Withdrawal | 7/1/2011
PJM | U2-024 | Tazewell-Baileyville 138kV |  | WV | McDowell | Withdrawn | AEP | 900 | 825 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/23/2008 | 1/6/2009 | Customer Milestone Not Met | 5/1/2012
PJM | U2-025 | Brooke County Landfill |  | WV | Brooke | Withdrawn | APS | 4 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 5/29/2008 | 2/23/2009 | Customer Milestone Not Met | 7/31/2009
PJM | U2-026 | Antwerp 69kV |  | OH | Paulding | Withdrawn | AEP | 30 | 3.9 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 5/29/2008 | 12/9/2008 | Customer Milestone Not Met | 12/1/2010
PJM | U2-027 | Mehoopany 115kV |  | PA | Bradford | Withdrawn | PENELEC | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 5/29/2008 | 12/8/2008 | Customer Milestone Not Met | 12/1/2010
PJM | U2-028A_AT1 | Ironville | FDS Coke Plant | OH | Lucas | Withdrawn | ATSI | 135 | 135 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Document Posted | Document Posted | 5/29/2008 | 2/5/2015 | Customer Milestone Not Met | 7/1/2017
PJM | U2-029 | Passyunk |  | PA | Philadelphia | Withdrawn | PECO | 1.3 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 6/5/2008 | 3/7/2012 | Customer Initiated Withdrawal | 11/1/2015
PJM | U2-030 | Four Mile Ridge Wind 138kV | Four Mile Ridge WF - 24 WT | MD | Garrett | In Service | APS | 60 | 7.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/5/2008 |  |  | 12/23/2017 | 11/21/2014
PJM | U2-031 | Kings Fork 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion | 30 | 24.75 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Document Posted | 6/9/2008 | 8/24/2010 | Customer Milestone Not Met | 6/1/2011
PJM | U2-032 | Elbow Mountain |  | MD | Garrett | Withdrawn | APS | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/9/2008 | 12/4/2008 | Customer Milestone Not Met | 10/1/2010
PJM | U2-040 | Bridgewater-Middlesex 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 650 | 650 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/12/2008 | 8/17/2009 | Customer Initiated Withdrawal | 5/1/2012
PJM | U2-041 | East Lima-Marysville 345kV | Hardin Wind Farm | OH | Hardin | Withdrawn | AEP | 166.4 | 21.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/13/2008 | 12/5/2019 |  | 12/31/2019
PJM | U2-042 | East Lima-South Kenton 138kV |  | OH | Hardin | Withdrawn | AEP | 201 | 26.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 6/13/2008 | 7/27/2010 | Customer Milestone Not Met | 12/1/2011
PJM | U2-044 | Lewis 138kV |  | NJ | Cape May | Withdrawn | AEC | 20 | 2.6 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 6/20/2008 | 11/21/2008 |  | 3/1/2011
PJM | U2-045 | Huron 69kV | Fishermen's Atlantic City Windfarm (FACW) | NJ | Cape May | Withdrawn | AEC | 20 | 2.6 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/20/2008 | 3/12/2019 |  | 1/27/2019
PJM | U2-048 | Cox's Corner-Croydon 230kV |  | NJ | Burlington | Withdrawn | PSEG | 640 | 640 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/24/2008 | 12/1/2008 | Customer Initiated Withdrawal | 5/15/2012
PJM | U2-049 | Monmouth |  | NJ | Monmouth | Withdrawn | JCPL | 640 | 640 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/24/2008 | 2/9/2011 | Customer Initiated Withdrawal | 5/15/2012
PJM | U2-050 | Lonesome Pine 138kV |  | VA | Tazewell | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 6/24/2008 | 1/5/2011 | Customer Milestone Not Met | 12/1/2010
PJM | U2-051 | Glen Lyn-Wythe 138kV |  | VA | Giles | Withdrawn | AEP | 60 | 10.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 6/24/2008 | 1/5/2011 | Customer Milestone Not Met | 12/1/2010
PJM | U2-052 | S. Bluefield-Wythe 69kV |  | VA | Bland | Withdrawn | AEP | 80 | 10.4 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/24/2008 | 3/18/2009 | Customer Initiated Withdrawal | 12/1/2011
PJM | U2-053 | Martins Creek |  | PA | Northampton | Withdrawn | PPL | 800 | 800 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/24/2008 | 6/2/2009 | Customer Milestone Not Met | 5/1/2012
PJM | U2-054 | Weissport | Beltzville Hydro Dam | PA | Carbon | Withdrawn | PPL | 2.6 | 2.6 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/25/2008 | 2/26/2014 |  | 6/1/2014
PJM | U2-055 | Karthaus-Milesburg 230kV |  | PA | Centre | Withdrawn | APS | 89.1 | 11.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 6/27/2008 | 8/7/2013 | Customer Milestone Not Met | 7/1/2012
PJM | U2-056 | West Point |  | VA | Unknown | Withdrawn | Dominion | 88.7 | 88.7 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Withdrawn | 6/30/2008 | 10/12/2010 | Customer Milestone Not Met | 12/1/2010
PJM | U2-057 | Hopewell 34.5kV |  | VA | City of Hopewell | Withdrawn | Dominion | 47.6 | 47.6 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Withdrawn | 6/30/2008 | 10/12/2010 | Customer Milestone Not Met | 12/1/2010
PJM | U2-058 | Kincaid Wind |  | IL | Christian | Withdrawn | ComEd | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/30/2008 | 7/20/2010 | Customer Initiated Withdrawal | 12/1/2011
PJM | U2-059 | Foul Rift 13kV | Belvidere SP | NJ | Warren | In Service | JCPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/7/2008 |  |  | 6/1/2011 | 12/12/2011
PJM | U2-060 | Camden | Pennsauk LF | NJ | Camden | Withdrawn | PSEG | 5 | 5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 7/7/2008 | 4/15/2009 | Customer Initiated Withdrawal | 12/15/2004
PJM | U2-061 | Garrett County | Roth Rock WF | MD | Garrett | In Service | APS | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/7/2008 |  |  | 1/5/2011 | 12/1/2009
PJM | U2-062 | Randolph 138kV |  | OH | Darke | Withdrawn | AEP | 187.5 | 24.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 7/9/2008 | 7/8/2013 | Customer Initiated Withdrawal | 9/30/2012
PJM | U2-063 | Croydon 230kV | Croydon Generating Station | PA | Bucks | In Service | PECO | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/10/2008 |  |  | 7/1/2008 | 1/2/2014
PJM | U2-064 | Branchburg-Ramapo 500kV |  | NJ | Sussex | Withdrawn | PSEG | 1000 | 1000 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 7/10/2008 | 8/17/2009 | Customer Initiated Withdrawal | 6/1/2014
PJM | U2-065 | Kankakee 138kV |  | IL | Iroquois | Withdrawn | ComEd | 250 | 32.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 7/14/2008 | 7/28/2010 | Customer Initiated Withdrawal | 9/1/2012
PJM | U2-066 | Marysville-SW Lima 345kV |  | OH | Hardin | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/14/2008 | 12/19/2011 | Customer Initiated Withdrawal | 9/1/2012
PJM | U2-067 | Eldred-Pine Grove 69kV | Westwood Generation | PA | Bucks | In Service | PPL | 2.5 | 2.5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/15/2008 |  |  | 7/1/2008 | 12/29/2008
PJM | U2-068 | Mount Storm-Valley 500kV | Lost River WF | VA | Rockingham | Withdrawn | Dominion | 130 | 16.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/21/2008 | 1/10/2014 |  | 6/1/2018
PJM | U2-069 | Frackville | Broad Mountain WF | PA | Schuylkill | Withdrawn | PPL | 56 | 7.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/21/2008 | 12/13/2010 | Customer Initiated Withdrawal | 6/1/2014
PJM | U2-070 | Somerset |  | PA | Somerset | Withdrawn | PENELEC | 7.5 | 0.98 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 7/21/2008 | 7/2/2009 | Customer Milestone Not Met | 12/1/2010
PJM | U2-071 | Tazewell-Saltville 138kV |  | VA | Tazewell | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 7/23/2008 | 2/27/2009 | Customer Initiated Withdrawal | 7/1/2011
PJM | U2-072 | East Lima-Marysville 345kV | Scioto Ridge Wind Farm | OH | Hardin | In Service | AEP | 250 | 32.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/23/2008 |  |  | 5/31/2021 | 12/17/2020
PJM | U2-073 | Frostburg 138kV II | Twin Ridges Wind Farm | PA | Somerset | In Service | APS | 139.4 | 18.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/23/2008 |  |  | 12/31/2020 | 12/21/2012
PJM | U2-074 | Peach Bottom-Rock Springs 500kV |  | PA | Lancaster | Withdrawn | PECO | 650 | 650 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/24/2008 | 8/3/2012 | Customer Initiated Withdrawal | 10/1/2012
PJM | U2-075 | Susquehanna-Roseland 500kV |  | PA | Lackawanna | Withdrawn | PPL | 636 | 636 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/24/2008 | 4/13/2009 | Customer Initiated Withdrawal | 6/1/2012
PJM | U2-076 | Falls | Grows North LF | PA | Bucks | Withdrawn | PECO | 10 | 10 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 7/25/2008 | 1/7/2014 | Customer Milestone Not Met | 3/1/2011
PJM | U2-080 | South Portsmouth 138kV |  | KY | Greenup | Withdrawn | AEP | 134 | 134 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2008 | 7/13/2012 | Customer Initiated Withdrawal | 7/1/2011
PJM | U2-081 | Chalk Point 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/30/2008 | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012
PJM | U2-082 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 400 | 400 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/30/2008 | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012
PJM | U2-083 | Chalk Point 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 400 | 400 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/30/2008 | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012
PJM | U2-084 | Dickerson |  | MD | Montgomery | Withdrawn | PEPCO | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/30/2008 | 12/1/2008 | Customer Initiated Withdrawal | 12/31/2012
PJM | U2-085 | Sakron-Prince #3 138kV |  | PA | Lancaster | Withdrawn | PPL | 11.4 | 11.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 7/30/2008 | 4/15/2009 | Customer Milestone Not Met | 12/1/2009
PJM | U2-090 | Desoto-Tanners Creek 345kV | HeadwatersWF | IN | Randolph | In Service | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 7/31/2008 |  |  | 10/31/2014 | 10/27/2014
PJM | U2-091 | Delaware-Richmond 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/31/2008 | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | U2-092 | Delaware-Centerville 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/31/2008 | 4/5/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | U2-094 | Foul Rift 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 19 | 7.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/31/2008 | 9/2/2009 | Customer Initiated Withdrawal | 12/31/2010
PJM | U2-095 | Nelson 345kV |  | IL | Lee | Withdrawn | ComEd | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2008 | 2/18/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U2-096 | Lock Haven-Lycoming #1 69kV |  | PA | Lycoming | Withdrawn | PPL | 1.5 | 1.5 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 7/31/2008 | 11/10/2008 | Customer Initiated Withdrawal | 3/31/2009
PJM | U2-098 | South Amboy |  | NJ | Middlesex | Withdrawn | JCPL | 1320 | 1320 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2008 | 8/27/2009 | Customer Milestone Not Met | 6/1/2013
PJM | U2-099 | Martins Creek 230kV |  | PA | Northampton | Withdrawn | PPL | 700 | 700 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 7/31/2008 | 11/30/2009 | Customer Initiated Withdrawal | 5/1/2014
PJM | U2-101 | Nelson Bio |  | IL | Lee | Withdrawn | ComEd | 20 | 20 | Capacity | Generation Interconnection | Biomass | Document Posted | Withdrawn |  |  | 7/31/2008 | 9/5/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | U3-001 | Barbadoes 34kV | AES Energy Storage Unit | PA | Montgomery | Withdrawn | PECO | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/11/2008 | 9/26/2018 |  | 8/31/2008 | 8/31/2008
PJM | U3-002 | Deer Creek-Fisher Body-Mullin 138kV | Wildcat Wind Farm I | IN | Madison | In Service | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 8/13/2008 |  |  | 12/31/2012 | 12/26/2012
PJM | U3-003 | Mt. Olive 69kV | Worcester County Renewable Energy | MD | Worcester | Deactivated | DPL | 2 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 8/14/2008 |  |  | 6/1/2012 | 3/1/2012
PJM | U3-004 | Cecil | Cecil County Landfill | MD | Cecil | Withdrawn | DPL | 1.6 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/14/2008 | 10/4/2013 | Customer Milestone Not Met | 12/31/2013
PJM | U3-008 | Mt. Bethel 230kV |  | PA | Northampton | Withdrawn | ME | 200 | 200 | Capacity | Generation Interconnection | Oil | Withdrawn |  |  |  | 8/18/2008 | 4/20/2010 | Customer Initiated Withdrawal | 1/1/2012
PJM | U3-009 | Mt. Bethel 230kV |  | PA | Northampton | Withdrawn | ME | 595 | 595 | Capacity | Generation Interconnection | Oil | Withdrawn |  |  |  | 8/18/2008 | 4/20/2010 | Customer Initiated Withdrawal | 1/1/2014
PJM | U3-010 | Towanda |  | PA | Bradford | Withdrawn | PENELEC | 120 | 15.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/22/2008 | 3/9/2009 | Customer Milestone Not Met | 10/15/2011
PJM | U3-012 | Bradford 115kV |  | PA | McKean | Withdrawn | PENELEC | 85 | 11 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/28/2008 | 3/9/2009 | Customer Milestone Not Met | 10/15/2011
PJM | U3-013 | Clermont 115kV |  | PA | McKean | Withdrawn | PENELEC | 125 | 16.3 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/28/2008 | 3/9/2009 | Customer Milestone Not Met | 10/15/2011
PJM | U3-016 | Midlothian 230kV |  | VA | Goochland | Withdrawn | Dominion | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/4/2008 | 2/23/2009 | Customer Initiated Withdrawal | 5/1/2012
PJM | U3-017 | Westvaco 138kV |  | PA | Allegheny | Withdrawn | APS | 4 | 0 | Energy | Generation Interconnection | Coal | Document Posted | Document Posted |  |  | 9/22/2008 | 10/22/2010 | Customer Initiated Withdrawal | 8/22/2008
PJM | U3-018 | Knieriem |  | PA | Somerset | Withdrawn | PENELEC | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/17/2008 | 3/3/2009 | Customer Initiated Withdrawal | 12/1/2010
PJM | U3-021 | Silver Lake-Cherry Valley | Garden Prairie Energy Facility | IL | Boone | Withdrawn | ComEd | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2008 | 5/4/2022 |  | 4/30/2024
PJM | U3-022 | Sherman-Cumberland 138kV |  | NJ | Cumberland | Withdrawn | AEC | 14 | 5.32 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2008 | 2/20/2009 | Customer Initiated Withdrawal | 9/15/2009
PJM | U3-023 | Printz 230kV |  | PA | Delaware | Withdrawn | PECO | 720 | 720 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/1/2008 | 2/23/2009 | Customer Initiated Withdrawal | 6/1/2012
PJM | U3-025 | Elk Garden-Parr Run 138kV |  | WV | Mineral | Withdrawn | APS | 80 | 10.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/2/2008 | 2/28/2012 | Customer Milestone Not Met | 12/31/2011
PJM | U3-029 | Beaver Valley #1 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 48 | 37 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 10/29/2008 |  |  | 10/31/2013 | 11/15/2013
PJM | U3-030 | Beaver Valley #2 | Beaver Valley Power Station | PA | Beaver | In Service | DL | 43 | 38 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 10/29/2008 |  |  | 11/1/2012 | 11/7/2012
PJM | U3-031 | Lincoln Generating Facility | Lincoln Generating Facility | IL | Will | In Service | ComEd | 40 | 40 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2008 |  |  | 10/31/2009 | 1/24/2013
PJM | U3-032 | Traynor 34.5kV | Britton Road Solar Facility | NJ | Morris | Withdrawn | JCPL | 20 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2008 | 8/20/2018 |  | 6/1/2012
PJM | U4-001 | Howard 138kV | Black Fork Wind | OH | Richland | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/3/2008 | 1/23/2019 |  | 11/3/2019
PJM | U4-002 | Pickens-Monterville 138kV |  | WV | Randolph | Withdrawn | APS | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required |  | 11/3/2008 | 12/17/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | U4-003 | Olive-Dequine 345kV |  | IN | Jasper | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/29/2008 | 1/3/2013 | Customer Initiated Withdrawal | 6/1/2012
PJM | U4-004 | York 115kV |  | PA | York | Withdrawn | ME | 120 | 120 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/5/2008 | 10/16/2009 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-005 | Susquehanna |  | PA | Luzerne | Withdrawn | PPL | 700 | 640 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/5/2008 | 11/25/2009 | Customer Initiated Withdrawal | 6/1/2013
PJM | U4-006 | Mendota 138kV |  | IL | Lasalle | Withdrawn | ComEd | 20 | 20 | Capacity | Generation Interconnection | Biomass | Document Posted | Withdrawn |  |  | 11/5/2008 | 9/5/2012 | Customer Initiated Withdrawal | 3/31/2012
PJM | U4-007 | Jennings Randolph Dam |  | MD | Garrett | Withdrawn | APS | 14 | 13.4 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Withdrawn | 11/11/2008 | 7/16/2013 | Customer Initiated Withdrawal | 7/2/2013
PJM | U4-008 | South Central Power | Suburban LF | OH | Perry | In Service | AEP | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/13/2008 |  |  | 1/7/2011 | 1/7/2011
PJM | U4-009 | Louisa 230kV | Louisa Gas Turbines Units 1 through 5 | VA | Orange | In Service | Dominion | 3 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/17/2008 |  |  | 5/26/2009 | 5/26/2009
PJM | U4-010 | Pontiac-Latham 345kV |  | IL | Ford | Withdrawn | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 11/20/2008 | 11/27/2012 | Customer Initiated Withdrawal | 1/1/2012
PJM | U4-011 | Pontiac Midpoint I 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 11/20/2008 | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | U4-012 | Pontiac Midpoint II 345kV |  | IL | McLean | Withdrawn | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 11/20/2008 | 11/27/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | U4-013 | North Lebanon 230kV |  | PA | Lebanon | Withdrawn | ME | 950 | 900 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 11/21/2008 | 6/8/2009 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-014 | Siegfried-Hauto 69kV | PA SP | PA | Carbon | In Service | PPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/24/2008 |  |  | 12/31/2012 | 11/6/2012
PJM | U4-015 | Rock Springs 500kV | Rocks Springs 1 & 2 | MD | Cecil | In Service | ODEC | 8.7 | 8.7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/25/2008 |  |  | 5/7/2009 | 5/31/2009
PJM | U4-016 | Harwood |  | PA | Luzerne | Withdrawn | PPL | 48 | 48 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/26/2008 | 6/1/2009 | Customer Milestone Not Met | 6/1/2010
PJM | U4-017 | Corder Crossing 138kV |  | WV | Barbour | Withdrawn | APS | 165 | 21.45 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/28/2008 | 6/16/2009 | Customer Milestone Not Met | 12/1/2012
PJM | U4-026 | Lowmoor-Lexington 230kV | Rocky Ford WF | VA | Botetourt | Withdrawn | Dominion | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/19/2008 | 8/23/2013 | Customer Initiated Withdrawal | 12/31/2016
PJM | U4-027 | Normandy-Kewanee 138kV |  | IL | Henry | Withdrawn | ComEd | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 12/22/2008 | 5/29/2019 |  | 12/31/2018
PJM | U4-028 | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/26/2008 | 11/5/2021 |  | 12/31/2020
PJM | U4-029 | Fostoria Central-Greenlawn-Howard 138kV | Seneca Wind | OH | Seneca | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/26/2008 | 11/5/2021 |  | 12/31/2020
PJM | U4-030 | Sabrooke 138kV | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/26/2008 |  |  | 6/23/2010 | 6/23/2010
PJM | U4-032 | South Bend 500kV |  | PA | Armstrong | Withdrawn | APS | 400 | 400 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/31/2008 | 5/28/2009 | Customer Milestone Not Met | 4/1/2013
PJM | U4-033 | University Park North |  | IL | Will | In Service | ComEd | 36 | 36 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/31/2008 |  |  | 6/1/2009 | 1/21/2014
PJM | U4-034 | Conesville #5 | Conesville #5 | OH | Coshocton | Deactivated | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/20/2009 |  |  | 2/1/2008 | 1/1/2010
PJM | U4-035 | Conesville #6 | Conesville #6 | OH | Coshocton | Deactivated | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 1/20/2009 |  |  | 2/1/2008 | 1/1/2010
PJM | U4-036 | Gloucester 26.4kV | Paradise SP | NJ | Gloucester | In Service | PSEG | 5.1 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 1/28/2009 |  |  | 1/4/2011 | 12/31/2009
PJM | U4-037 | Brokaw-Lanesville 345kV |  | IL | DeWitt | Withdrawn | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/29/2009 | 12/12/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | U4-038 | Mullin-Greentown Tap 138kV |  | IN | Madison | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 1/30/2009 | 5/7/2013 | Customer Initiated Withdrawal | 9/1/2013
PJM | U4-039 | Greentown 138kV |  | IN | Madison | Withdrawn | AEP | 710 | 92.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn | Withdrawn | 1/30/2009 | 7/20/2015 | Customer Initiated Withdrawal | 9/30/2015
PJM | U4-040 | Lincoln 13.2kV |  | PA | Adams | Withdrawn | ME | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-041 | Valley 13.2kV |  | PA | Adams | Withdrawn | ME | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-042 | Hanover 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-043 | Tolna 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-044 | Stoverstown 13.2kV |  | PA | York | Withdrawn | ME | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-045 | Oil Creek 34.kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-046 | Teepleville 34.5kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-047 | Mill Village 34.5kV |  | PA | Erie | Withdrawn | PENELEC | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | U4-048 | Saegertown 34.5kV |  | PA | Crawford | Withdrawn | PENELEC | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/30/2009 | 2/11/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | V1-009 | Gilbert 46kV |  | WV | Unknown | Withdrawn | AEP | 12 | 11 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 2/17/2009 | 8/18/2009 | Customer Milestone Not Met | 4/1/2012
PJM | V1-010 | Howard-Fostoria Central 138kV |  | OH | Crawford | Withdrawn | AEP | 260 | 33.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/25/2009 | 4/19/2012 | Customer Initiated Withdrawal | 12/1/2013
PJM | V1-011 | Haviland 138kV | Trishe Wind Ohio, LLC | OH | Paulding | In Service | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2009 |  |  | 12/31/2018 | 9/10/2018
PJM | V1-012 | Haviland 138kV | Trishe Wind Ohio, LLC | OH | Paulding | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2009 | 5/8/2018 |  | 12/31/2015
PJM | V1-013 | Springdale 138kV |  | PA | Allegheny | Withdrawn | APS | 580 | 580 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 2/27/2009 | 9/11/2009 | Customer Initiated Withdrawal | 1/1/2012
PJM | V1-015 | New Liberty 138kV |  | OH | Hancock | Withdrawn | AEP | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 3/10/2009 | 9/3/2009 | Customer Milestone Not Met | 2/1/2010
PJM | V1-021 | Cape May County 12kV | Cape May County Municipal Utiltities Authority (CM | NJ | Cape May | In Service | AEC | 1.9 | 1.7 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/23/2009 |  |  | 6/1/2013 | 10/22/2013
PJM | V1-022 | Plano 345kV |  | IL | Kendall | Withdrawn | ComEd | 380 | 380 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/31/2009 | 12/17/2013 | Customer Milestone Not Met | 6/1/2015
PJM | V1-023 | Bridge 12kV | Charlston LF | WV | Kanawha | In Service | AEP | 2 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/6/2009 |  |  | 12/7/2010 | 12/7/2010
PJM | V1-024 | LaSalle 1 | LaSalle Nuclear Station Unit 1 | IL | Lasalle | In Service | ComEd | 20 | 11.9 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 4/9/2009 |  |  | 11/1/2010 | 5/21/2015
PJM | V1-025 | LaSalle 2 | LaSalle Nuclear Station Unit 2 | IL | Lasalle | In Service | ComEd | 20 | 10.9 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 4/9/2009 |  |  | 3/1/2011 | 5/21/2015
PJM | V1-026 | Limerick |  | PA | Montgomery | Withdrawn | PECO | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Interim Study | 4/9/2009 | 7/7/2020 |  | 4/4/2011 | 4/4/2011
PJM | V1-027 | Limerick |  | PA | Montgomery | Withdrawn | PECO | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Interim Study | 4/9/2009 | 7/7/2020 |  | 4/1/2011 | 6/12/2013
PJM | V1-028 | North Wales | Morris Road | PA | Montgomery | In Service | PECO | 2 | 2 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Document Posted | 4/16/2009 |  |  | 5/31/2009 | 5/2/2012
PJM | V1-029 | Frackville-Fishbach 69kV |  | PA | Schuylkill | Withdrawn | PPL | 6 | 0.78 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 4/23/2009 | 9/14/2009 | Customer Milestone Not Met | 7/1/2013
PJM | V1-030 | PSE&G Area |  | NJ | Various | In Service | PSEG | 52 | 19.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/27/2009 |  |  | 6/22/2010 | 12/27/2011
PJM | V1-031 | Possum Point 230kV |  | VA | Prince William | Withdrawn | Dominion | 950 | 875 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 4/28/2009 | 1/30/2012 | Customer Initiated Withdrawal | 4/1/2016
PJM | V1-032 | Highland 69kV |  | OH | Highland | Withdrawn | AEP | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2009 | 4/14/2011 | Customer Milestone Not Met | 8/1/2010
PJM | V1-033 | Pumphrey 115kV | Fairfield Renewable Energy Facility | MD | Baltimore City | Withdrawn | BGE | 132 | 132 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2009 | 5/11/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | V1-035 | Kanawha 138kV | ST | WV | Fayette | Withdrawn | AEP | 53 | 53 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Withdrawn |  | 4/30/2009 | 1/14/2013 | Customer Milestone Not Met | 5/1/2011
PJM | V2-001 | Bucyrus Center 138kV | 54 1.8 WT | OH | Crawford | Withdrawn | AEP | 91.8 | 11.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/6/2009 | 3/18/2013 | Customer Initiated Withdrawal | 12/31/2016
PJM | V2-002 | Martinsburg |  | PA | Blair | Withdrawn | PENELEC | 2.65 | 2.65 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 5/6/2009 | 2/8/2010 | Customer Milestone Not Met | 6/30/2010
PJM | V2-003 | Beasley 23kV |  | NJ | Atlantic | Withdrawn | AEC | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 5/7/2009 | 1/6/2014 | Customer Initiated Withdrawal | 12/31/2009
PJM | V2-004 | Harwood-E. Hazleton #1 |  | PA | Schuylkill | Withdrawn | PPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 5/11/2009 | 12/4/2009 | Customer Initiated Withdrawal | 12/31/2010
PJM | V2-005 | Pleasantville 12kV |  | NJ | Atlantic | Withdrawn | AEC | 1.91 | 1.91 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Withdrawn |  | 5/15/2009 | 2/17/2010 | Customer Milestone Not Met | 12/31/2010
PJM | V2-006 | East Leipsic 138kV | Leipsic Wind Project | OH | Putnam | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/28/2009 | 2/21/2020 |  | 12/31/2021
PJM | V2-008 | Kincaid 345kV |  | IL | Christian | Withdrawn | ComEd | 600 | 600 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 5/29/2009 | 1/2/2013 | Customer Initiated Withdrawal | 10/1/2014
PJM | V2-009 | Plainsboro & Devils Brook 13kV | Cranbury SP | NJ | Middlesex | Withdrawn | PSEG | 16.11 | 6.12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/29/2009 | 2/1/2024 |  | 6/1/2024
PJM | V2-010 | Stewartsville 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/5/2009 | 3/15/2013 | Customer Milestone Not Met | 6/30/2011
PJM | V2-011 | Sunbury-Milton 69kV |  | PA | Northumberland | Withdrawn | PPL | 5.63 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/8/2009 | 8/18/2009 | Customer Initiated Withdrawal | 2/1/2010
PJM | V2-012 | Essex 26.4kV | Essex SP | NJ | Essex | Withdrawn | PSEG | 2.8 | 2.8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 6/9/2009 | 12/21/2009 | Customer Milestone Not Met | 3/5/2010
PJM | V2-013 | Farmingdale 12.47kV | Farmingdale Solar | NJ | Monmouth | Withdrawn | JCPL | 0.5 | 0.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/11/2009 | 1/11/2013 | Customer Milestone Not Met | 4/1/2011
PJM | V2-014 | Waretown 12.47kV |  | NJ | Ocean | Withdrawn | AEC | 5.065 | 1.92 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/15/2009 | 2/17/2010 | Customer Milestone Not Met | 12/31/2009
PJM | V2-015 | Lumberton 13.2kV |  | NJ | Burlington | Withdrawn | PSEG | 3.3 | 1.25 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/15/2009 | 12/21/2009 | Customer Milestone Not Met | 12/31/2009
PJM | V2-018 | Tuckahoe |  | NJ | Cape May | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/17/2009 | 12/20/2010 | Customer Initiated Withdrawal | 11/1/2010
PJM | V2-019 | Mansfield-S. Troy 115kV | AES Armenia Mountain Wind, LLC | PA | Bradford | In Service | PENELEC | 0.5 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 6/18/2009 |  |  | 8/19/2010 | 8/19/2010
PJM | V2-020 | Howard-West End Fostoria 138kV |  | OH | Crawford | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/26/2009 | 3/10/2010 | Customer Milestone Not Met | 7/31/2012
PJM | V2-021 | Clayville |  | NJ | Cumberland | Withdrawn | AEC | 64 | 64 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Withdrawn |  | 6/26/2009 | 5/4/2010 | Customer Milestone Not Met | 6/1/2014
PJM | V2-022 | Galion-Leesburg 138kV |  | OH | Morrow | Withdrawn | AEP | 201 | 26.1 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 6/30/2009 | 8/17/2009 | Customer Initiated Withdrawal | 12/31/2012
PJM | V2-023 | Galion-Muskingham River 345kV |  | OH | Morrow | Withdrawn | AEP | 250.5 | 37.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/30/2009 | 4/7/2010 | Customer Milestone Not Met | 12/31/2012
PJM | V2-025 | Turnpike 13.8kV | Kearny SP | NJ | Hudson | In Service | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/30/2009 |  |  | 1/31/2012 | 3/1/2012
PJM | V2-026 | Denver 138kV |  | WV | Barbour | Withdrawn | APS | 164 | 21.32 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/30/2009 | 12/11/2009 | Customer Initiated Withdrawal | 12/31/2012
PJM | V2-027 | South Milton |  | PA | Northumberland | Withdrawn | PPL | 1.62 | 1.62 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/8/2009 | 2/21/2013 | Customer Initiated Withdrawal | 9/1/2013
PJM | V2-028 | Vienna | Vienna Solar Facility | MD | Dorchester | Withdrawn | DPL | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/8/2009 | 2/9/2018 |  | 11/30/2018
PJM | V2-030 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 950 | 875 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/14/2009 |  |  | 9/30/2015 | 10/30/2014
PJM | V2-035 | Pittsgrove | Pittsgrove Solar, LLC | NJ | Salem | In Service | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/20/2009 |  |  | 4/14/2014 | 4/19/2014
PJM | V2-037 | White Oak | White Oak | MD | Montgomery | In Service | PEPCO | 4.5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/24/2009 |  |  | 5/3/2010 | 3/31/2010
PJM | V2-040 | Mountain Road 34.5kV | Henrico County Landfill | VA | Henrico | In Service | Dominion | 4 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 7/28/2009 |  |  | 9/23/2010 | 9/23/2010
PJM | V2-041 | Clayville 12kV | Vineland-Mays Landing | NJ | Cumberland | In Service | AEC | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2009 |  |  | 9/30/2011 | 9/30/2011
PJM | V2-042 | Calvert Cliffs 500kV |  | MD | Calvert | Withdrawn | BGE | 1640 | 1640 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Withdrawn |  | 7/29/2009 | 9/6/2012 | Customer Initiated Withdrawal | 6/1/2017
PJM | V2-042A_AT2 | Galion 138kV |  | OH | Morrow | Withdrawn | ATSI | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/27/2009 | 4/14/2014 | Customer Initiated Withdrawal | 12/31/2012
PJM | V2-043 | Upper Deerfield Township I |  | NJ | Cumberland | Withdrawn | AEC | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/31/2009 | 3/30/2010 | Customer Initiated Withdrawal | 6/30/2010
PJM | V2-044 | Upper Deerfield Township II |  | NJ | Cumberland | Withdrawn | AEC | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/31/2009 | 3/30/2010 | Customer Initiated Withdrawal | 6/30/2010
PJM | V2-045 | Bayview |  | VA | Northampton | Withdrawn | ODEC | 20 | 12.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required |  | 7/31/2009 | 9/12/2011 | Customer Initiated Withdrawal | 10/1/2011
PJM | V2-046 | Pilesgrove Township 12kV | Pilesgrove SP | NJ | Salem | In Service | AEC | 19.9 | 7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2009 |  |  | 7/31/2011 | 7/31/2011
PJM | V2-047 | Maurice River Township |  | NJ | Cumberland | Withdrawn | AEC | 1.35 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/31/2009 | 1/31/2013 | Customer Initiated Withdrawal | 12/31/2009
PJM | V3-001 | Burches Hill 500kV |  | MD | Prince George's | Withdrawn | PEPCO | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/3/2009 | 3/2/2010 | Customer Milestone Not Met | 5/1/2015
PJM | V3-002 | Ellicott City |  | MD | Howard | Withdrawn | BGE | 1.2 | 0.456 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/4/2009 | 3/10/2010 | Customer Milestone Not Met | 6/30/2010
PJM | V3-003 | Greentown-Jefferson 765kV |  | IN | Clinton | Withdrawn | AEP | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/5/2009 | 2/10/2011 | Customer Initiated Withdrawal | 12/31/2010
PJM | V3-004 | Siegfried |  | PA | Carbon | Withdrawn | PPL | 83 | 83 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 8/6/2009 | 4/7/2010 | Customer Milestone Not Met | 10/1/2012
PJM | V3-005 | Morris 34.5kV |  | NJ | Morris | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/10/2009 | 11/7/2013 | Customer Initiated Withdrawal | 12/31/2013
PJM | V3-006 | Linglestown |  | PA | Dauphin | Withdrawn | PPL | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/10/2009 | 4/14/2011 | Customer Initiated Withdrawal | 12/31/2009
PJM | V3-007 | Desoto-Tanners Creek #1 345kV | Headwaters II | IN | Randolph | In Service | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/10/2009 |  |  | 9/1/2021 | 1/26/2021
PJM | V3-008 | Desoto-Tanners Creek #1 345kV |  | IN | Randolph | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 8/10/2009 | 6/3/2016 | Customer Milestone Not Met | 5/18/2018
PJM | V3-009 | Desoto-Tanners Creek #2 345kV |  | IN | Randolph | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 8/10/2009 | 6/3/2016 | Customer Milestone Not Met | 5/19/2019
PJM | V3-010 | Delaware-Modoc 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/10/2009 | 6/4/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | V3-011 | Sussex 12.47kV | Sussex County Land Fill | NJ | Sussex | Deactivated | JCPL | 3.4 | 3.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/11/2009 |  |  | 6/3/2011 | 6/3/2011
PJM | V3-013 | Wilmington 69kV |  | OH | Clinton | Withdrawn | Dayton | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 8/18/2009 | 10/27/2011 | Customer Initiated Withdrawal | 12/31/2015
PJM | V3-014 | Lee County |  | IL | Lee | Withdrawn | ComEd | 160.2 | 20.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/20/2009 | 2/23/2012 | Customer Milestone Not Met | 11/20/2011
PJM | V3-015 | Keystone 345kV | Wells County Wind Farm | IN | Wells | Withdrawn | AEP | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 8/24/2009 | 4/19/2018 |  | 12/31/2014
PJM | V3-016 | Greenville-West Milton 138kV |  | OH | Darke | Withdrawn | Dayton | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 8/24/2009 | 4/9/2012 | Customer Initiated Withdrawal | 8/1/2012
PJM | V3-017 | Morgantown-Oak Grove | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 725 | 725 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/24/2009 |  |  | 11/1/2016 | 11/25/2016
PJM | V3-018 | Towanda 115kV |  | PA | Bradford | Withdrawn | PENELEC | 75 | 9.75 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/24/2009 | 9/1/2010 | Customer Initiated Withdrawal | 12/31/2012
PJM | V3-019 | Edinboro 13.8kV |  | PA | Erie | Withdrawn | PENELEC | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 8/27/2009 | 3/24/2010 | Customer Initiated Withdrawal | 1/1/2011
PJM | V3-024 | Devils Brook 13.2kV | RE Cranbury Solar I, LLC | NJ | Middlesex | In Service | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2009 |  |  | 9/27/2011 | 9/27/2011
PJM | V3-025 | Cranbury 13.8kV | English SP | NJ | Middlesex | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 8/31/2009 | 6/9/2010 | Customer Milestone Not Met | 5/31/2010
PJM | V3-027 | Pickens 138kV |  | WV | Webster | Withdrawn | APS | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/31/2009 | 2/25/2010 | Customer Initiated Withdrawal | 12/1/2013
PJM | V3-028 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | In Service | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/31/2009 |  |  | 6/1/2021 | 9/29/2020
PJM | V3-029 | Chatfield 138kV |  | OH | Crawford | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/31/2009 | 7/27/2010 | Customer Milestone Not Met | 12/1/2013
PJM | V3-030 | St. Benedict-Patton 46kV | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 30.6 | 3.98 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 8/31/2009 |  |  | 6/30/2013 | 12/24/2012
PJM | V3-031 | Germantown |  | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2009 | 4/9/2010 | Customer Initiated Withdrawal | 12/31/2010
PJM | V3-032 | Darwin-Eugene 345kV |  | IL | Vermilion | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/1/2009 | 7/26/2012 | Customer Initiated Withdrawal | 9/1/2011
PJM | V3-034 | Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 9/8/2009 | 7/21/2010 | Customer Initiated Withdrawal | 6/30/2011
PJM | V3-036 | Ontario 23kV | Midtown Thermal Control Center | NJ | Atlantic | In Service | AEC | 5.5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/14/2009 |  |  | 12/1/2011 | 12/1/2011
PJM | V3-037 | Naval Academy Junction 13kV | Millersville Landfill & Resource Recovery Facility | MD | Anne Arundel | In Service | BGE | 4 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/14/2009 |  |  | 5/31/2013 | 6/13/2012
PJM | V3-038 | Turnpike 13kV | Turnpike SP | NJ | Hudson | Withdrawn | PSEG | 0.6 | 0.23 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/16/2009 | 1/10/2013 |  | 12/31/2010
PJM | V3-039 | Harrison 4kV | Harrison SP | NJ | Hudson | Withdrawn | PSEG | 1.2 | 0.45 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/16/2009 | 1/10/2013 |  | 12/31/2010
PJM | V3-040 | Siegfried-Hauto 69kV | PA SP | PA | Carbon | Withdrawn | PPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/17/2009 | 9/19/2016 | Customer Initiated Withdrawal | 6/30/2016
PJM | V3-041 | Daleville | SECCRA Units 1, 2 & 3 | PA | Chester | In Service | PECO | 2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/21/2009 |  |  | 11/1/2011 | 12/15/2010
PJM | V3-042 | Thompson 115kV |  | PA | Wayne | Withdrawn | PENELEC | 84 | 10.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 9/2/2009 | 8/8/2014 | Customer Initiated Withdrawal | 9/30/2016
PJM | V3-044 | Glendon 34.5kV | Chrin LF | PA | Northampton | Deactivated | ME | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2009 |  |  | 6/14/2011 | 6/14/2011
PJM | V3-045 | Zimmer-Spurlock 345kV | Meldahl Hydroelectric Plant | OH | Butler | In Service | DEOK | 112 | 112 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2009 |  |  | 12/31/2015 | 11/1/2015
PJM | V3-047 | Sutton Dam 69kV |  | WV | Braxton | Withdrawn | APS | 9.9 | 9.9 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Withdrawn |  | 9/30/2009 | 3/1/2010 | Customer Milestone Not Met | 12/21/2010
PJM | V3-050 | Penns Neck 13kV |  | NJ | Middlesex | Withdrawn | PSEG | 4.6 | 4.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/12/2009 | 8/5/2011 | Customer Milestone Not Met | 9/1/2011
PJM | V3-051 | Letort | Turkey Hill Dairy WF | PA | Lancaster | In Service | PPL | 3.2 | 0.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 10/16/2009 |  |  | 1/17/2011 | 1/17/2011
PJM | V3-053 | Desoto 138kV |  | IN | Delaware | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 10/22/2009 | 10/14/2013 | Customer Milestone Not Met | 12/31/2013
PJM | V3-055 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Withdrawn | 10/23/2009 | 8/30/2010 | Customer Initiated Withdrawal | 1/1/2013
PJM | V3-056 | Metropolitan Court 34.5kV |  | MD | Frederick | Withdrawn | APS | 50 | 50 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 10/30/2009 | 8/3/2010 | Customer Milestone Not Met | 10/1/2013
PJM | V3-057 | Ironwood 230kV |  | PA | Lebanon | Withdrawn | ME | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/30/2009 | 5/20/2011 | Customer Milestone Not Met | 3/31/2011
PJM | V3-058 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2009 |  |  | 10/1/2010 | 10/24/2011
PJM | V3-059 | Brunswick 26.4kV | Edgeboro | NJ | Middlesex | In Service | PSEG | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2009 |  |  | 10/1/2010 | 10/24/2011
PJM | V3-060 | Antioch |  | IL | Lake | Withdrawn | ComEd | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 10/30/2009 | 7/26/2010 | Customer Initiated Withdrawal | 9/30/2011
PJM | V3-061 | Bayview |  | VA | Northampton | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required |  | 10/30/2009 | 11/27/2012 | Customer Initiated Withdrawal | 10/1/2011
PJM | V3-062 | McConnellsburg-Guilford 138kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required |  | 10/30/2009 | 11/27/2012 | Customer Initiated Withdrawal | 10/1/2011
PJM | V3-063 | Dupont 69kV |  | VA | City of Martinsville | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Biomass | Document Posted | Withdrawn |  |  | 10/30/2009 | 2/25/2010 | Customer Initiated Withdrawal | 3/31/2012
PJM | V3-064 | Rivesville-Pruntytown 138kV |  | WV | Marion | Withdrawn | APS | 28 | 28 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 10/30/2009 | 12/17/2011 | Customer Initiated Withdrawal | 12/1/2012
PJM | V3-065 | Clay St. 4kV (Barringer) | Clay ST SP | NJ | Essex | In Service | PSEG | 0.549 | 0.21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2009 |  |  | 10/1/2010 | 10/1/2010
PJM | V3-066 | Cook Road 13.8kV (Park) | Cook Rd SP | NJ | Essex | In Service | PSEG | 0.432 | 0.16 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2009 |  |  | 12/31/2010 | 11/17/2010
PJM | V3-067 | Norfolk St. 4kV (Central) | Newark I SP | NJ | Essex | In Service | PSEG | 0.773 | 0.29 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2009 |  |  | 3/16/2011 | 2/16/2011
PJM | V3-068 | Norfolk St. 4kV (New Central HS) | Newark II SP | NJ | Essex | In Service | PSEG | 0.425 | 0.16 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2009 |  |  | 12/20/2010 | 12/31/2010
PJM | V3-069 | Woodbridge 13kV (Matrix Bldg) | Woodbridge SP | NJ | Middlesex | In Service | PSEG | 2.308 | 0.877 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2009 |  |  | 10/31/2010 | 1/26/2011
PJM | V3-070 | J. Rinco 34.5kV | Lilac Site | NJ | Hunterdon | In Service | JCPL | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2009 |  |  | 6/1/2013 | 1/2/2012
PJM | V3-071 | Frenchtown 12.47kV | Frenchtown SP | NJ | Hunterdon | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/30/2009 | 6/21/2012 | Customer Initiated Withdrawal | 10/1/2010
PJM | V4-001 | Lebanon 34.5kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/2/2009 |  |  | 12/31/2011 | 1/2/2012
PJM | V4-002 | Graceton 230kV |  | PA | York | Withdrawn | PECO | 575 | 575 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/5/2009 | 5/21/2010 | Customer Initiated Withdrawal | 9/1/2014
PJM | V4-003 | Churchmans |  | DE | New Castle | Withdrawn | DPL | 14 | 5 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 11/9/2009 | 5/17/2010 | Customer Milestone Not Met | 3/31/2010
PJM | V4-004 | Roxbury 12.5kV |  | NJ | Morris | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 11/11/2009 | 5/7/2010 | Customer Initiated Withdrawal | 7/1/2010
PJM | V4-005 | Southampton 13.8kV | Lumberton SP | NJ | Burlington | In Service | PSEG | 2.9 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/11/2009 |  |  | 11/10/2011 | 8/1/2010
PJM | V4-009 | Upper Deerfield | Deerfield Project | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 11/12/2009 | 11/25/2013 | Customer Milestone Not Met | 6/1/2014
PJM | V4-010 | Tiffin Center 138kV | Republic Wind LLC | OH | Seneca | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/12/2009 | 11/18/2021 |  | 12/31/2022
PJM | V4-011 | Granger Electric | Granger Electric of Hancock County | OH | Hancock | In Service | AEP | 3 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/13/2009 |  |  | 3/31/2015 | 3/31/2015
PJM | V4-012 | Morgantown |  | PA | Berks | Withdrawn | PPL | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/13/2009 | 11/8/2011 | Customer Initiated Withdrawal | 3/1/2012
PJM | V4-013 | Gloucester 26kV |  | NJ | Gloucester | Withdrawn | PSEG | 5.2 | 1.99 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 11/18/2009 | 6/9/2010 | Customer Milestone Not Met | 9/30/2010
PJM | V4-014 | Greenridge Landfill |  | PA | Westmoreland | Withdrawn | APS | 6.5 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Withdrawn |  | 11/20/2009 | 11/12/2010 | Customer Milestone Not Met | 12/31/2010
PJM | V4-015 | Fostoria Central 138kV |  | OH | Hancock | Withdrawn | AEP | 66.6 | 8.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 11/23/2009 | 9/15/2014 | Customer Milestone Not Met | 12/31/2015
PJM | V4-016 | Valley 138kV |  | MI | Cass | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 11/25/2009 | 3/27/2015 | Customer Initiated Withdrawal | 11/30/2014
PJM | V4-017 | Woodruffs Gap 345kV |  | NJ | Sussex | Withdrawn | JCPL | 3.5 | 1.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 11/25/2009 | 2/15/2012 | Customer Milestone Not Met | 9/30/2010
PJM | V4-018 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 475 | 415 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/25/2009 |  |  | 9/30/2015 | 10/30/2014
PJM | V4-019 | Bergen 230kV | Bergen Generating Station | NJ | Bergen | In Service | PSEG | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/25/2009 |  |  | 6/1/2013 | 5/31/2013
PJM | V4-020 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 650 | 650 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/25/2009 | 2/12/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | V4-021 | Keystone 345kV |  | IN | Wells | Withdrawn | Dayton | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 11/30/2009 | 2/23/2012 | Customer Milestone Not Met | 12/15/2014
PJM | V4-022 | Tasley | Tasley Solar | VA | Accomack | Withdrawn | ODEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/30/2009 | 3/13/2019 |  | 11/30/2019
PJM | V4-023 | Upper Pittsgrove 1 | Upper Pittsgrove Project | NJ | Salem | Withdrawn | AEC | 18 | 6.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 11/30/2009 | 9/30/2014 | Customer Initiated Withdrawal | 10/1/2015
PJM | V4-024 | Upper Pittsgrove 2 | Quinton Project | NJ | Salem | Withdrawn | AEC | 18 | 6.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 11/30/2009 | 2/12/2015 | Customer Initiated Withdrawal | 11/30/2016
PJM | V4-025 | Upper Pittsgrove 3 | Beckett ProjectWoodstown Project | NJ | Salem | Withdrawn | AEC | 20 | 7.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 11/30/2009 | 8/12/2015 | Customer Initiated Withdrawal | 10/1/2015
PJM | V4-027 | Quarryville | Keystone Solar | PA | Lancaster | In Service | PPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 12/7/2009 |  |  | 12/30/2012 | 9/17/2012
PJM | V4-028 | Kuller Road 13.2kV | Kuller Road SP | NJ | Passaic | Withdrawn | PSEG | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 12/7/2009 | 1/10/2010 | Customer Milestone Not Met | 7/1/2010
PJM | V4-029 | Mannington Township |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 12/7/2009 | 9/17/2013 | Customer Initiated Withdrawal | 5/31/2011
PJM | V4-033 | Desoto-Tanners Creek 345kV |  | IN | Randolph | Withdrawn | AEP | 299.2 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 12/11/2009 | 9/8/2016 | Customer Milestone Not Met | 12/31/2018
PJM | V4-035 | Yankee 12.5kV |  | OH | Montgomery | Withdrawn | Dayton | 1.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/14/2009 | 1/22/2010 | Customer Initiated Withdrawal | 4/30/2010
PJM | V4-036 | Newport-South Millville 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 12/14/2009 | 3/20/2012 | Customer Initiated Withdrawal | 9/30/2012
PJM | V4-037 | Pilesgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/14/2009 | 1/18/2013 | Customer Initiated Withdrawal | 5/31/2011
PJM | V4-038 | Friendship Manor 34.5kV | Alpha Ridge Landfill | MD | Carroll | In Service | BGE | 1 | 1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Document Posted | 12/16/2009 |  |  | 2/28/2013 | 7/31/2012
PJM | V4-039 | Church |  | MD | Queen Anne's | Withdrawn | DPL | 9 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/18/2009 | 5/20/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | V4-039A_AT3 | MOABs A16, A17, A18 |  | OH | Sandusky | Withdrawn | ATSI | 22 | 22 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required |  | 12/21/2009 | 7/27/2012 | Queue Not Required | 5/1/2010
PJM | V4-040 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/22/2009 | 5/28/2010 | Customer Milestone Not Met | 6/1/2011
PJM | V4-041 | Upper Pittsgrove 4 | Upper Pittsgrove Township - Site 4 | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 12/24/2009 | 9/25/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | V4-042 | Upper Pittsgrove 5 | Upper Pittsgrove Township - Site 5 | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 12/24/2009 | 9/25/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | V4-043 | Shirley 12kV | Stewartstown Generating Facility | NJ | Salem | Withdrawn | AEC | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/24/2009 | 10/27/2010 | Customer Initiated Withdrawal | 12/1/2010
PJM | V4-044 | Mannington Township 2 |  | NJ | Salem | Withdrawn | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/24/2009 | 6/1/2010 | Customer Milestone Not Met | 12/31/2010
PJM | V4-045 | Peach Bottom | Peach Bottom Units 2 & 3 | PA | York | In Service | PECO | 133.8 | 206 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 12/24/2009 |  |  | 10/3/2015 | 1/6/2016
PJM | V4-046 | Byron 1 | Byron Nuclear Generating Station, Unit 1 | IL | Ogle | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 12/24/2009 |  |  | 1/1/2012 | 2/6/2014
PJM | V4-047 | Byron 2 | Byron Nuclear Generating Station, Unit 2 | IL | Ogle | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 12/24/2009 |  |  | 1/1/2012 | 2/6/2014
PJM | V4-048 | Braidwood 1 | Braidwood Nuclear Generating Station, Unit 1 | IL | Will | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 12/24/2009 |  |  | 1/1/2012 | 2/6/2014
PJM | V4-049 | Braidwood 2 | Braidwood Nuclear Generating Station, Unit 2 | IL | Will | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Document Posted | Document Posted | 12/24/2009 |  |  | 1/1/2012 | 2/6/2014
PJM | V4-052 | West Reading | The Reading Hospital and Medical Center | PA | Berks | In Service | ME | 10 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/28/2009 |  |  | 7/12/2011 | 7/12/2011
PJM | V4-053 | Double Toll Gate 138kV |  | VA | Clarke | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/30/2009 | 11/28/2012 | Customer Initiated Withdrawal | 11/1/2011
PJM | V4-054 | Fairfield Township 12kV | NJ Oak Solar | NJ | Cumberland | In Service | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/31/2009 |  |  | 12/20/2011 | 12/20/2011
PJM | V4-055 | Meigs-Ravenswood 69kV |  | OH | Meigs | Withdrawn | AEP | 11 | 4.18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/6/2010 | 11/16/2010 | Customer Milestone Not Met | 12/31/2011
PJM | V4-059 | Pine Creek 46kV |  | WV | Mingo | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 1/11/2010 | 11/18/2010 | Customer Milestone Not Met | 12/31/2011
PJM | V4-062 | Upper Pittsgrove 6 |  | NJ | Salem | Withdrawn | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/22/2010 | 7/18/2013 | Customer Initiated Withdrawal | 12/1/2010
PJM | V4-063 | Upper Pittsgrove 7 |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/22/2010 | 11/3/2010 | Customer Initiated Withdrawal | 5/31/2011
PJM | V4-064 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/26/2010 | 12/11/2013 | Customer Initiated Withdrawal | 9/30/2012
PJM | V4-065 | Meadow Road 13kV | Edison Project | NJ | Middlesex | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/27/2010 | 2/8/2011 | Customer Milestone Not Met | 8/30/2011
PJM | V4-066 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 3.6 | 1.36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/28/2010 | 2/12/2010 | Customer Initiated Withdrawal | 12/1/2010
PJM | V4-067 | Cates Road Egg Harbor Township 12kV | McKee City Solar | NJ | Atlantic | In Service | AEC | 2.6 | 0.98 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 1/28/2010 |  |  | 6/1/2014 | 12/22/2011
PJM | V4-068 | Murphy's 34.5kV |  | NC | Hertford | In Service | Dominion | 5 | 3.23 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 1/29/2010 |  |  | 12/31/2011 | 12/29/2011
PJM | V4-069 | Frenchtown 34.5kV | Frenchtown 1 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2010 |  |  | 3/1/2011 | 12/31/2011
PJM | V4-070 | Frenchtown 12.5kV | Frenchtown 2 Solar | NJ | Hunterdon | In Service | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2010 |  |  | 12/31/2011 | 1/2/2012
PJM | V4-071 | Bixby 13.8kV |  | OH | Franklin | Withdrawn | AEP | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 1/29/2010 | 7/30/2010 | Customer Milestone Not Met | 6/1/2010
PJM | V4-072 | Blue Ridge Landfill |  | PA | Franklin | Withdrawn | APS | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2010 | 5/7/2012 | Customer Initiated Withdrawal | 5/1/2012
PJM | V4-073 | Yankee 12.5kV |  | OH | Montgomery | In Service | Dayton | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2010 |  |  | 5/28/2010 | 5/28/2010
PJM | V4-074 | Quad Cities Wind |  | IL | Hancock | Withdrawn | ComEd | 1000 | 130 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 1/29/2010 | 1/27/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | V4-075 | Warwick 12kV |  | PA | Lancaster | Withdrawn | PPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2010 | 8/11/2014 | Customer Initiated Withdrawal | 3/1/2015
PJM | V4-076 | Carlisle Pike 23kV |  | PA | Cumberland | Withdrawn | PENELEC | 5.3 | 2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2010 | 8/25/2014 | Customer Initiated Withdrawal | 12/31/2014
PJM | V4-077 | Montgomery Avenue 12.47kV |  | PA | Mifflin | Withdrawn | PENELEC | 13 | 4.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2010 | 8/25/2014 | Customer Initiated Withdrawal | 12/31/2014
PJM | V4-078 | Hawks Bridge Road |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/29/2010 | 3/15/2010 | Customer Initiated Withdrawal | 2/15/2011
PJM | W1-003 | Oak Hall | Oak Hall Project A | VA | Unknown | In Service | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/4/2010 |  |  | 10/15/2016 | 12/8/2016
PJM | W1-004 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/4/2010 |  |  | 12/30/2016 | 12/8/2016
PJM | W1-005 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/4/2010 |  |  | 12/30/2017 | 12/8/2016
PJM | W1-006 | Oak Hall | Oak Hall Project D | VA | Unknown | In Service | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/4/2010 |  |  | 12/30/2017 | 12/8/2016
PJM | W1-007 | Oak Hall |  | VA | Accomack | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/4/2010 | 8/23/2010 | Customer Initiated Withdrawal | 12/1/2011
PJM | W1-008 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/4/2010 | 8/29/2014 | Customer Initiated Withdrawal | 9/30/2016
PJM | W1-009 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/4/2010 | 8/23/2010 | Customer Initiated Withdrawal | 12/1/2011
PJM | W1-010 | Cooper |  | PA | York | Withdrawn | PECO | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/4/2010 | 3/7/2012 | Customer Milestone Not Met | 12/1/2011
PJM | W1-011 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 70 | 26.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/4/2010 | 5/19/2011 | Customer Initiated Withdrawal | 9/30/2011
PJM | W1-012 | Millheim-Brush Jct 46kV |  | PA | Centre | Withdrawn | APS | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 2/12/2010 | 5/8/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | W1-013 | Saint Thomas 34kV I |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/17/2010 | 10/17/2011 | Customer Milestone Not Met | 12/15/2011
PJM | W1-014 | Saint Thomas 34kV II |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/18/2010 | 10/17/2011 | Customer Milestone Not Met | 12/15/2011
PJM | W1-015 | Shade Gap 115kV |  | PA | Unknown | Withdrawn | PENELEC | 60.8 | 7.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/19/2010 | 5/14/2012 | Customer Initiated Withdrawal | 12/1/2013
PJM | W1-021 | Fairton 69kV I |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/22/2010 | 10/16/2013 | Customer Initiated Withdrawal | 7/1/2011
PJM | W1-022 | Fairton 69kV II |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/24/2010 | 7/30/2013 | Customer Initiated Withdrawal | 7/1/2011
PJM | W1-023 | Fairton 69kV III |  | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/24/2010 | 2/18/2014 | Customer Initiated Withdrawal | 7/1/2011
PJM | W1-024 | Manalapan 12.5kV | Village at Manalapan Solar Farm | NJ | Monmouth | In Service | JCPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 2/24/2010 |  |  | 6/30/2012 | 12/14/2011
PJM | W1-029 | Winfall 230kV | Desert Wind Farm | NC | Pasquotank | In Service | Dominion | 208 | 27 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/25/2010 |  |  | 12/31/2020 | 3/2/2017
PJM | W1-030 | Pontiac Midpoint-Reynolds 345kV |  | IL | Ford | Withdrawn | ComEd | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/25/2010 | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2014
PJM | W1-031 | Pontiac Midpoint-Reynolds 345kV |  | IL | Ford | Withdrawn | ComEd | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/25/2010 | 8/25/2010 | Customer Initiated Withdrawal | 12/31/2014
PJM | W1-032 | Millhurst 12.5kV | Millhurst Solar Farm | NJ | Monmouth | In Service | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 2/25/2010 |  |  | 12/31/2015 | 2/2/2016
PJM | W1-033 | Pumphrey 115kV | Fairfield Renewable Energy Facility | MD | Baltimore City | Withdrawn | BGE | 25 | 25 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Document Posted | Document Posted | 2/25/2010 | 5/11/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | W1-034 | Burches Hill |  | MD | Prince George's | Withdrawn | PEPCO | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/26/2010 | 8/24/2010 | Customer Initiated Withdrawal | 5/1/2015
PJM | W1-035 | Baker 345kV |  | KY | Lawrence | Withdrawn | AEP | 750 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/26/2010 | 11/22/2010 | Customer Milestone Not Met | 6/1/2012
PJM | W1-036 | Matt Funk-Tech Drive 138kV | Central Solar Park | VA | Roanoke | Withdrawn | AEP | 45 | 5.85 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/26/2010 | 3/21/2012 | Customer Milestone Not Met | 10/1/2012
PJM | W1-037 | East Lima-South Kenton 138kV |  | VA | Unknown | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/26/2010 | 1/3/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W1-038 | Fairlawn 138kV |  | NJ | Bergen | Withdrawn | PSEG | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/26/2010 | 8/31/2010 | Customer Milestone Not Met | 1/1/2011
PJM | W1-039 | Pedricktown 230kV | PCLP Facility | NJ | Salem | Deactivated | AEC | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/26/2010 |  |  | 6/1/2011 | 3/7/2012
PJM | W1-040 | LaSalle |  | IL | Lasalle | Withdrawn | ComEd | 350 | 350 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 2/26/2010 | 2/13/2012 | Customer Milestone Not Met | 4/10/2016
PJM | W1-041 | W. Milton-Greenville |  | OH | Darke | Withdrawn | Dayton | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/26/2010 | 1/20/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | W1-042 | Hubar Road 1 |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/4/2010 | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011
PJM | W1-043 | Hubar Road 2 |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/4/2010 | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011
PJM | W1-044 | Mont Alto |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/4/2010 | 4/3/2011 | Customer Initiated Withdrawal | 12/15/2011
PJM | W1-045 | Roxbury 23 kV | Roxbury Solar Project | PA | Franklin | In Service | PENELEC | 13.5 | 5.13 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/4/2010 |  |  | 12/31/2019 | 12/31/2019
PJM | W1-046 | Face Rock 69kV |  | PA | Lancaster | Withdrawn | PPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/4/2010 | 11/30/2013 | Customer Initiated Withdrawal | 6/1/2015
PJM | W1-048 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/9/2010 | 7/18/2013 | Customer Initiated Withdrawal | 3/15/2011
PJM | W1-050 | Keller & Valley Camp Roads I |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/12/2010 | 10/17/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W1-051 | St. Thomas 34kV III |  | PA | Franklin | Withdrawn | APS | 130 | 49.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/12/2010 | 10/14/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | W1-052 | Keller & Valley Camp Roads II |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/12/2010 | 4/3/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W1-054 | South Akron-Prince | Dart Container | PA | Lancaster | In Service | PPL | 11.4 | 11.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 3/16/2010 |  |  | 12/31/2011 | 10/6/2012
PJM | W1-055 | Broadway 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/18/2010 | 9/28/2011 | Customer Initiated Withdrawal | 5/31/2011
PJM | W1-056 | Ada-Dunkirk 69kV | Hog Creek Wind Farm | OH | Hardin | In Service | AEP | 18.4 | 2.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 3/18/2010 |  |  | 12/31/2017 | 11/15/2017
PJM | W1-057 | Earleys 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/23/2010 | 12/14/2011 | Customer Milestone Not Met | 5/31/2011
PJM | W1-058A_DK1 | AK Steel Middletown-AK Steel 1C 138kV |  | OH | Butler | Withdrawn | Duke | 134.5 | 134.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/23/2010 | 7/2/2012 | Customer Initiated Withdrawal | 9/30/2012
PJM | W1-059 | Denville |  | NJ | Morris | Withdrawn | JCPL | 2 | 0.78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/24/2010 | 4/19/2012 | Customer Milestone Not Met | 6/1/2011
PJM | W1-060 | Carneys Point Township |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/25/2010 | 1/11/2011 | Customer Milestone Not Met | 5/31/2011
PJM | W1-062 | Clayton 138kV | Smyrna Units 1 & 2 | DE | Kent | In Service | DPL | 53 | 53 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/29/2010 |  |  | 5/31/2012 | 6/15/2012
PJM | W1-064 | Grand Point 12kV |  | PA | Franklin | Withdrawn | APS | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 3/31/2010 | 7/1/2014 | Customer Initiated Withdrawal | 1/31/2011
PJM | W1-065 | Millstone |  | NJ | Monmouth | Withdrawn | JCPL | 1.99 | 0.756 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 3/31/2010 | 11/17/2011 | Customer Milestone Not Met | 3/31/2011
PJM | W1-066 | New Brooklyn Road 12kV |  | NJ | Camden | Withdrawn | AEC | 9 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2010 | 2/27/2012 | Customer Initiated Withdrawal | 9/1/2010
PJM | W1-068 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/16/2010 | 2/20/2014 | Customer Initiated Withdrawal | 4/1/2011
PJM | W1-070 | Laurel 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/20/2010 | 1/6/2014 | Customer Initiated Withdrawal | 5/31/2011
PJM | W1-070A_AT4 | Ashtabula 138kV |  | OH | Ashtabula | Withdrawn | ATSI | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 4/20/2010 | 4/16/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | W1-071 | Elk Road 12kV |  | NJ | Salem | Withdrawn | AEC | 1.04 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/22/2010 | 1/13/2011 | Customer Milestone Not Met | 10/31/2010
PJM | W1-072A_AT5 | Lemoyne | Troy Energy | OH | Wood | In Service | ATSI | 40 | 40 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/26/2010 |  |  | 6/1/2011 | 4/11/2014
PJM | W1-073 | Ladysmith CT 230kV |  | VA | Caroline | Withdrawn | Dominion | 612 | 498 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/27/2010 | 8/30/2010 | Customer Initiated Withdrawal | 6/1/2014
PJM | W1-074 | Remington CT 230kV |  | VA | Fauquier | Withdrawn | Dominion | 610 | 498 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/27/2010 | 8/30/2010 | Customer Initiated Withdrawal | 6/1/2014
PJM | W1-075 | Hunterstown 115kV |  | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/28/2010 | 9/12/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | W1-076 | Kingwood | Keller Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/28/2010 | 5/16/2014 |  | 6/30/2012
PJM | W1-077 | Shacklefords 34.5kV | King and Queen | VA | King and Queen | In Service | Dominion | 4 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 4/28/2010 |  |  | 12/31/2011 | 9/1/2011
PJM | W1-080 | Sutton Dam |  | WV | Braxton | Withdrawn | APS | 9.9 | 9.9 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2010 | 4/12/2011 | Customer Milestone Not Met | 12/31/2012
PJM | W1-081 | Mickleton 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 10/5/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | W1-082 | Milford | Milford Solar | NJ | Hunterdon | Withdrawn | JCPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2010 | 3/7/2018 |  | 2/17/2018
PJM | W1-083 | Deptford 13kV | West Deptford Solar | NJ | Gloucester | Withdrawn | PSEG | 4.6 | 1.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2010 | 1/10/2013 | Customer Milestone Not Met | 6/30/2012
PJM | W1-084 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/13/2011 | Customer Milestone Not Met | 6/1/2011
PJM | W1-085 | Millville 1 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011
PJM | W1-086 | Millville 2 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011
PJM | W1-087 | Millville 3 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011
PJM | W1-088 | Millville 4 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/24/2014 | Customer Initiated Withdrawal | 10/11/2011
PJM | W1-089 | Newport 69kV |  | NJ | Cumberland | Withdrawn | AEC | 18 | 6.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/24/2014 | Customer Initiated Withdrawal | 1/7/2011
PJM | W1-090 | Berlin 69kV |  | NJ | Camden | Withdrawn | AEC | 18 | 6.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/24/2014 | Customer Initiated Withdrawal | 4/25/2011
PJM | W1-091 | Berlin 12kV |  | NJ | Camden | Withdrawn | AEC | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2010 | 8/25/2010 | Customer Initiated Withdrawal | 4/25/2011
PJM | W1-092 | Mays Landing 12kV |  | NJ | Cumberland | Withdrawn | AEC | 8.7 | 3.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/13/2011 | Customer Milestone Not Met | 7/21/2011
PJM | W1-093 | Cape May 12kV |  | NJ | Cape May | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/13/2011 | Customer Milestone Not Met | 7/21/2011
PJM | W1-094 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/13/2011 | Customer Milestone Not Met | 7/21/2011
PJM | W1-095 | Buena 12kV |  | NJ | Atlantic | Withdrawn | AEC | 18 | 7.02 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/13/2011 | Customer Milestone Not Met | 7/21/2011
PJM | W1-096 | Woodbine 12kV |  | NJ | Cape May | Withdrawn | AEC | 7 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2010 | 1/13/2011 | Customer Milestone Not Met | 7/21/2011
PJM | W1-097 | Fairfield Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/30/2010 | 1/13/2011 | Customer Milestone Not Met | 12/30/2010
PJM | W1-098 | Levittown 13kV | Levittown SP | NJ | Burlington | Withdrawn | PSEG | 0.965 | 0.367 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011
PJM | W1-099 | Levittown 13kV | Levittown 2 SP | NJ | Burlington | Withdrawn | PSEG | 1.282 | 0.487 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011
PJM | W1-100 | Minue Street 12kV | Rathway SP | NJ | Middlesex | Withdrawn | PSEG | 1.741 | 0.662 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 3/11/2011 | Customer Initiated Withdrawal | 1/1/2011
PJM | W1-101 | Bayonne 13kV | Bayonne SP | NJ | Hudson | In Service | PSEG | 1.4 | 0.532 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 |  |  | 3/14/2011 | 3/14/2011
PJM | W1-102 | Southampton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 1.9 | 0.722 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2010 | 6/1/2010 | Customer Milestone Not Met | 2/1/2011
PJM | W1-103 | Millville 12kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2010 | 8/27/2010 | Customer Initiated Withdrawal | 6/15/2011
PJM | W1-104 | Bellefonte 12kV |  | PA | Centre | Withdrawn | APS | 0.65 | 0.25 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/30/2010 | 9/4/2012 | Customer Initiated Withdrawal | 10/1/2011
PJM | W1-105 | Reamstown | Heatherwoods Solar Farm | PA | Lancaster | Withdrawn | PPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 8/11/2014 | Customer Initiated Withdrawal | 6/30/2017
PJM | W1-106 | West Carlisle | Shover Solar Farm | PA | Cumberland | Withdrawn | PPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 8/11/2014 | Customer Initiated Withdrawal | 6/30/2017
PJM | W1-107 | Grove City Road 12kV | Grove City Road 12kV | PA | Butler | Withdrawn | APS | 2 | 0.74 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 10/12/2015 | Customer Milestone Not Met | 8/31/2015
PJM | W1-108 | Grays Ferry 230kV | Grays Ferry Cogeneration Partnership | PA | Philadelphia | In Service | PECO | 13 | 13 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2010 |  |  | 6/1/2011 | 7/29/2013
PJM | W1-109 | Bloom 138kV |  | IL | Cook | Withdrawn | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 4/30/2010 | 11/4/2011 | Customer Initiated Withdrawal | 1/20/2014
PJM | W1-110 | Galloway Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 3.21 | 1.19 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2010 | 8/31/2010 | Customer Initiated Withdrawal | 9/3/2012
PJM | W1-111 | Harwood-Berwick 69kV | Beacon Power Flywheel Station | PA | Luzerne | In Service | PPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2010 |  |  | 6/1/2014 | 7/24/2014
PJM | W1-112 | Holmdel | Holmdel SP | NJ | Monmouth | In Service | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 |  |  | 3/1/2013 | 3/1/2013
PJM | W1-113 | Millstone 2 | Northpark Solar Farm #1 | NJ | Monmouth | In Service | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2010 |  |  | 12/31/2015 | 3/22/2016
PJM | W1-114 | Port Carbon | East Norwegian Township Solar I | PA | Schuylkill | Withdrawn | PPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 12/19/2016 |  | 12/31/2013
PJM | W1-115 | Tamanend | Ryan Township Solar I | PA | Schuylkill | Withdrawn | PPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 12/19/2017 |  | 6/30/2014
PJM | W1-116 | Emmitsburg 34kV | Mount St. Mary's PV Park | MD | Frederick | In Service | APS | 14 | 5.32 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2010 |  |  | 4/30/2012 | 7/5/2012
PJM | W1-117 | Silica Spur 1 |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/30/2010 | 1/29/2014 | Customer Initiated Withdrawal | 6/30/2011
PJM | W1-118 | Silica Spur 2 |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/30/2010 | 1/29/2014 | Customer Initiated Withdrawal | 12/31/2011
PJM | W1-119 | Pemberton Township 1 34.5 kV | Greenburg Solar | NJ | Burlington | In Service | JCPL | 8.8 | 3.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 |  |  | 10/31/2017 | 6/16/2017
PJM | W1-120 | Pemberton Township 2 34.5 kV | Perez Solar | NJ | Burlington | In Service | JCPL | 8.8 | 3.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 |  |  | 10/31/2017 | 6/15/2017
PJM | W1-121 | Crosswicks 13kV | Property #6 | NJ | Mercer | In Service | PSEG | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 |  |  | 1/1/2012 | 12/14/2011
PJM | W1-122 | Wantage 12.47kV | Lower Unionville Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 5.13 | 1.93 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 | 3/7/2014 |  | 12/31/2014
PJM | W1-123 | Mannington Township 1 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2010 | 9/1/2010 | Customer Initiated Withdrawal | 6/1/2011
PJM | W1-124 | Tinton Falls 34.5kV | Tinton Falls Solar | NJ | Monmouth | In Service | JCPL | 16.9 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2010 |  |  | 8/1/2014 | 12/6/2012
PJM | W1-125 | Mannington Township 2 12kV |  | NJ | Salem | Withdrawn | AEC | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2010 | 8/26/2010 | Customer Milestone Not Met | 7/1/2011
PJM | W1-126 | White | White Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2010 | 11/21/2012 | Customer Initiated Withdrawal | 12/30/2013
PJM | W1-127 | Phillipsburg 12.47kV | Harmony Solar Farm | NJ | Warren | In Service | JCPL | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2010 |  |  | 9/30/2015 | 6/30/2015
PJM | W1-128 | Red School Lane 69kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/30/2010 | 2/9/2011 | Customer Milestone Not Met | 11/30/2011
PJM | W1-129 | Cookstown 34.5kV | Jacobstown Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2010 |  |  | 5/29/2014 | 9/20/2014
PJM | W1-130 | Vine Road 12kV | Cedar Branch Solar Farm | NJ | Cumberland | In Service | AEC | 9.2 | 3.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/30/2010 |  |  | 12/31/2016 | 10/27/2016
PJM | W1-131 | Kenney |  | MD | Worcester | Withdrawn | DPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/30/2010 | 2/3/2011 | Customer Milestone Not Met | 4/30/2011
PJM | W1-132 | Pittstown | Paunch Solar | NJ | Hunterdon | In Service | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2010 |  |  | 6/30/2014 | 12/6/2013
PJM | W2-001 | Fostoria Central 138/kV |  | OH | Hancock | Withdrawn | AEP | 66.6 | 8.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 5/6/2010 | 9/15/2014 | Customer Milestone Not Met | 12/31/2015
PJM | W2-002 | Kennedyville 1 69kV |  | MD | Kent | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/10/2010 | 12/13/2010 | Customer Initiated Withdrawal | 12/1/2011
PJM | W2-003 | Kennedyville 2 69kV |  | MD | Kent | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/10/2010 | 12/13/2010 | Customer Initiated Withdrawal | 12/1/2011
PJM | W2-004 | Foundry St. 138kV |  | NJ | Essex | Withdrawn | PSEG | 45 | 45 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required |  | 5/12/2010 | 5/23/2012 | Customer Milestone Not Met | 9/1/2012
PJM | W2-005 | Pruntytown 138kV |  | WV | Taylor | Withdrawn | APS | 30 | 30 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 5/12/2010 | 12/16/2010 | Customer Milestone Not Met | 10/30/2013
PJM | W2-006 | Newburgh 12kV |  | NJ | Morris | Withdrawn | JCPL | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/12/2010 | 11/19/2010 | Customer Milestone Not Met | 11/30/2010
PJM | W2-007 | East Leipsic 138kV |  | OH | Putnam | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/14/2010 | 1/29/2013 | Customer Initiated Withdrawal | 12/31/2013
PJM | W2-009 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 18 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 5/19/2010 | 12/22/2010 | Customer Initiated Withdrawal | 5/31/2011
PJM | W2-010 | Conemaugh Unit 1 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 5/20/2010 |  |  | 6/30/2013 | 7/9/2012
PJM | W2-011 | Conemaugh Unit 2 | Conemaugh Generating Station | PA | Indiana | In Service | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 5/20/2010 |  |  | 6/30/2013 | 7/9/2012
PJM | W2-014 | Richmond |  | PA | Philadelphia | In Service | PECO | 2 | 2 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 5/25/2010 |  |  | 11/25/2010 | 6/24/2014
PJM | W2-015 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/25/2010 | 12/1/2010 | Customer Milestone Not Met | 12/31/2011
PJM | W2-016 | Frenchtown 34.5kV | Barbertown-Point Breeze Solar Farm | NJ | Hunterdon | In Service | JCPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/25/2010 |  |  | 6/30/2014 | 12/31/2013
PJM | W2-017 | Pennsville Township |  | NJ | Salem | Withdrawn | AEC | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/28/2010 | 6/16/2010 |  | 6/1/2012
PJM | W2-018 | Cumberland County Landfill | Cumberland County Landfill | PA | Cumberland | In Service | PENELEC | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 5/28/2010 |  |  | 12/31/2012 | 4/22/2012
PJM | W2-019 | Wrightstown 34.5kV | Shemesh Solar Farm | NJ | Burlington | In Service | JCPL | 6 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 5/28/2010 |  |  | 9/30/2016 | 10/24/2016
PJM | W2-020 | Deptford 13kV |  | NJ | Camden | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/28/2010 | 8/28/2012 | Customer Milestone Not Met | 8/30/2011
PJM | W2-021 | Deptford 13kV |  | NJ | Camden | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/28/2010 | 8/28/2012 | Customer Milestone Not Met | 8/30/2011
PJM | W2-022 | Pantego 115kV | Pantego Wind Farm | NC | Hyde | Withdrawn | Dominion | 73.6 | 9.57 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/28/2010 | 11/22/2016 | Customer Initiated Withdrawal | 10/15/2018
PJM | W2-023 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 625 | 625 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 5/28/2010 | 2/24/2015 | Customer Initiated Withdrawal | 5/31/2017
PJM | W2-024 | Kearny 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 625 | 625 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/28/2010 | 11/29/2011 | Customer Milestone Not Met | 5/31/2014
PJM | W2-025 | Oldmans Township |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/28/2010 | 11/23/2010 | Customer Initiated Withdrawal | 9/30/2011
PJM | W2-026 | Glassboro Road | Suncatcher Clean Energy | NJ | Gloucester | Withdrawn | AEC | 1.5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 5/28/2010 | 5/14/2013 | Customer Milestone Not Met | 4/30/2013
PJM | W2-027 | Terrace 12kV |  | NJ | Gloucester | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 5/28/2010 | 1/5/2011 | Customer Milestone Not Met | 9/30/2011
PJM | W2-028 | Limerick #1 |  | PA | Montgomery | Withdrawn | PECO | 5 | 5 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required |  | 6/1/2010 | 7/7/2020 |  | 12/31/2014
PJM | W2-029 | Limerick #2 |  | PA | Montgomery | Withdrawn | PECO | 5 | 5 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required |  | 6/1/2010 | 7/7/2020 |  | 12/31/2014
PJM | W2-030 | Egg Harbor Township | 1307 Doughty Road | NJ | Atlantic | In Service | AEC | 9.6 | 3.65 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 6/3/2010 |  |  | 9/30/2016 | 10/4/2016
PJM | W2-031 | Gloucester 26kV |  | NJ | Gloucester | Withdrawn | PSEG | 8.5 | 3.23 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 6/10/2010 | 9/13/2011 | Customer Initiated Withdrawal | 12/31/2012
PJM | W2-032 | Stow Creek Township |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/10/2010 | 11/30/2010 | Customer Initiated Withdrawal | 12/31/2011
PJM | W2-034 | Cohansey Road |  | NJ | Salem | Withdrawn | AEC | 20 | 7.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/16/2010 | 2/2/2011 | Customer Initiated Withdrawal | 9/1/2011
PJM | W2-035 | Cohansey Road |  | NJ | Salem | Withdrawn | AEC | 16 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/16/2010 | 2/3/2014 | Customer Initiated Withdrawal | 9/1/2011
PJM | W2-036 | Polhemus Lane 13kV | Central SP | NJ | Somerset | In Service | PSEG | 0.749 | 0.284 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/18/2010 |  |  | 3/21/2010 | 3/21/2011
PJM | W2-037 | Cookstown 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 7 | 2.66 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/22/2010 | 12/1/2010 | Customer Milestone Not Met | 11/30/2011
PJM | W2-039 | Clayville 69kV | Clayville Unit #1 | NJ | Cumberland | In Service | AEC | 63 | 63 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 6/28/2010 |  |  | 6/1/2015 | 11/1/2015
PJM | W2-040 | Camden 69kV | Preble Solar Energy | OH | Preble | Withdrawn | Dayton | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 6/29/2010 | 1/23/2020 |  | 6/1/2018
PJM | W2-041 | Egg Harbor Township |  | NJ | Atlantic | Withdrawn | AEC | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/29/2010 | 8/2/2010 | Customer Initiated Withdrawal | 3/1/2011
PJM | W2-042 | Dennis Township |  | NJ | Cape May | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/29/2010 | 12/1/2010 | Customer Milestone Not Met | 6/30/2011
PJM | W2-044 | Columbia 138kV |  | IN | Whitley | Withdrawn | AEP | 100.5 | 13.06 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/30/2010 | 1/5/2011 | Customer Initiated Withdrawal | 9/1/2011
PJM | W2-046 | Powerton-Goodings Grove 345kV |  | IL | Livingston | Withdrawn | ComEd | 450 | 58.5 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 6/30/2010 | 12/7/2011 | Customer Initiated Withdrawal | 12/31/2013
PJM | W2-047 | Oldmans Township |  | NJ | Salem | Withdrawn | AEC | 7.5 | 2.85 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 6/30/2010 | 5/15/2014 | Customer Initiated Withdrawal | 8/31/2011
PJM | W2-048 | Brokaw-Lanesville | Hilltopper Wind, LLC | IL | Logan | In Service | ComEd | 62.5 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/30/2010 |  |  | 5/31/2019 | 11/1/2018
PJM | W2-049 | Reedy Creek 115kV | South Boston Energy Facility | VA | Halifax | In Service | Dominion | 47.4 | 47.4 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Document Posted | Document Posted | 6/30/2010 |  |  | 5/30/2013 | 9/24/2013
PJM | W2-050 | Flemington | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/13/2010 |  |  | 4/1/2016 | 3/22/2016
PJM | W2-051 | Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 2 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/13/2010 | 11/30/2010 | Customer Initiated Withdrawal | 12/31/2011
PJM | W2-052 | Pierson Avenue 13kV |  | NJ | Middlesex | In Service | PSEG | 0.592 | 0.225 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/19/2010 |  |  | 3/14/2011 | 3/14/2011
PJM | W2-053 | West Waynesboro 34.5kV I |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/21/2010 | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | W2-054 | West Waynesboro II 34.5kV II |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/21/2010 | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | W2-056 | Lumberton 13kV | Reeves Station Road Solar | NJ | Burlington | In Service | PSEG | 11 | 4.18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/23/2010 |  |  | 9/1/2012 | 10/16/2012
PJM | W2-057 | Laurel Mountain | Laurel Mountain BT | WV | Barbour | In Service | APS | 27.4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 7/28/2010 |  |  | 7/30/2011 | 9/21/2011
PJM | W2-058 | Southampton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2010 | 1/5/2011 | Customer Milestone Not Met | 2/28/2012
PJM | W2-059 | Strasburg 12kV | Sight & Sound Theaters | PA | Lancaster | Withdrawn | PPL | 2.4 | 1 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2010 | 8/27/2012 | CIW | 12/31/2012
PJM | W2-060 | Burlington 26kV | Florence solar | NJ | Burlington | Withdrawn | PSEG | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2010 | 5/30/2013 | Customer Initiated Withdrawal | 2/28/2014
PJM | W2-061 | Ringoes 12kV | Everitt Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2010 |  |  | 1/18/2017 | 6/1/2016
PJM | W2-062 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 12.1 | 12.1 | Capacity | Generation Interconnection | Biomass | Withdrawn |  |  |  | 7/29/2010 | 8/30/2010 | Customer Initiated Withdrawal | 12/31/2012
PJM | W2-063 | Millbrook Park 138kV |  | KY | Greenup | Withdrawn | AEP | 70 | 70 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Withdrawn | 7/30/2010 | 9/11/2013 | Customer Initiated Withdrawal | 3/31/2014
PJM | W2-064 | Ringoes 34.5kV | Ringoes Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 1/24/2012 | Customer Initiated Withdrawal | 6/30/2014
PJM | W2-065 | Woodstown Road 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/30/2010 | 12/1/2010 | Customer Milestone Not Met | 8/1/2011
PJM | W2-067 | Amsterdam 138kV |  | OH | Darke | Withdrawn | Dayton | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 7/30/2010 | 8/24/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | W2-068 | Bluff Point 138kV |  | OH | Mercer | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/30/2010 | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | W2-069 | Fishburn/Tanney 46kV |  | PA | Centre | Withdrawn | APS | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/30/2010 | 5/4/2011 | Customer Initiated Withdrawal | 12/1/2012
PJM | W2-070 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/30/2010 | 12/2/2010 | Customer Initiated Withdrawal | 10/1/2011
PJM | W2-071 | Mt. Laurel 13kV |  | NJ | Burlington | In Service | PSEG | 2.8 | 1.06 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 |  |  | 10/31/2011 | 12/15/2011
PJM | W2-072 | Pilesgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/30/2010 | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W2-073 | New Canton 12kV | Ward's Nursery Solar Farm | NJ | Middlesex | Withdrawn | JCPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 3/17/2017 | Customer Initiated Withdrawal | 9/30/2017
PJM | W2-074 | Bennett 12kV | Hurley Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 1 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 3/7/2014 |  | 6/30/2014
PJM | W2-075 | Tolna Unit 2 | Tolna Unit 2 | PA | York | In Service | ME | 0.9 | 0.9 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2010 |  |  | 8/31/2010 | 7/28/2011
PJM | W2-076 | Rocktown 4.8kV | West Amwell Mason Supply Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2 | 0.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 11/15/2016 |  | 5/30/2017
PJM | W2-077 | Wrightstown 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 2.06 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/30/2010 | 9/8/2010 | Customer Milestone Not Met | 4/1/2011
PJM | W2-078 | Applegarth 12.5kV | Northpark Solar Farm #2 | NJ | Monmouth | In Service | JCPL | 9 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2010 |  |  | 12/31/2015 | 3/22/2016
PJM | W2-079 | Stillman Valley |  | IL | Winnebago | Withdrawn | ComEd | 19.4 | 7.37 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/30/2010 | 12/30/2013 | Customer Milestone Not Met | 3/31/2011
PJM | W2-080 | Stanton 12kV | Fisher Solar Farm | NJ | Hunterdon | In Service | JCPL | 2 | 0.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 |  |  | 6/25/2017 | 5/30/2017
PJM | W2-081 | Port Carbon 12kV |  | PA | Schuylkill | Withdrawn | PPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/30/2010 | 11/2/2011 | Customer Milestone Not Met | 2/22/2011
PJM | W2-082 | Fort Dix-McGuire 34.5kV | North Hanover Solar Farm | NJ | Burlington | In Service | JCPL | 17 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 |  |  | 1/17/2017 | 3/17/2017
PJM | W2-083 | Frenchtown-Rosemont 34.5kV | Perotti Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 12/7/2015 | Customer Initiated Withdrawal | 6/30/2014
PJM | W2-084 | Branchville-Holiday Lakes 34.5kV | Roberts Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 2/19/2013 | Customer Milestone Not Met | 6/30/2014
PJM | W2-085 | Baptistown-Frenchtown 34.5kV | Gombasi Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 2/19/2013 | Customer Milestone Not Met | 6/30/2014
PJM | W2-086 | Baptistown-East Flemington 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/30/2010 | 6/1/2011 | Customer Milestone Not Met | 1/10/2011
PJM | W2-087 | Mt. Holly 26kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/30/2010 | 6/16/2011 | Customer Milestone Not Met | 6/1/2012
PJM | W2-088 | Gravel Hill-Smithburg 34.5kV | Freehold Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 17 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 12/7/2015 | Customer Initiated Withdrawal | 6/30/2014
PJM | W2-089 | Cookstown-Fort Dix 34.5kV |  | NJ | Burlington | Withdrawn | JCPL | 17 | 6.46 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/30/2010 | 6/8/2011 | Customer Milestone Not Met | 1/6/2012
PJM | W2-090 | Lumberton 230kV | Stacy Haines Road | NJ | Burlington | Withdrawn | PSEG | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 | 1/19/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | W2-091 | Broadway-Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 |  |  | 6/13/2016 | 5/31/2016
PJM | W2-092 | Hunterstown 115kV II |  | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2010 | 9/12/2012 | Customer Initiated Withdrawal | 6/1/2013
PJM | W2-093 | Hunterstown 115kV III |  | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2010 | 9/12/2012 | Customer Initiated Withdrawal | 6/1/2013
PJM | W2-094 | Lincoln 13.2kV | Lincoln Solar Farm | PA | Adams | Withdrawn | ME | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2010 |  |  | 12/31/2016
PJM | W2-095 | Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/30/2010 | 5/23/2011 | Customer Milestone Not Met | 6/30/2012
PJM | W2-096 | West Carlisle-Newville 1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2010 | 3/7/2012 | Customer Initiated Withdrawal | 6/1/2012
PJM | W2-097 | West Carlisle-Newville 2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 7/30/2010 | 3/7/2012 | Customer Initiated Withdrawal | 6/1/2012
PJM | W2-098 | Hunterstown 115kV IV |  | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2010 | 9/13/2012 | Customer Initiated Withdrawal | 6/1/2013
PJM | W2-099 | Kenney 69kV |  | MD | Worcester | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/30/2010 | 5/4/2011 | Customer Milestone Not Met | 6/1/2012
PJM | W2-100 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/30/2010 | 11/19/2010 | Customer Initiated Withdrawal | 6/1/2012
PJM | W2-101 | Quinton Township |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2010 | 10/16/2014 | Customer Initiated Withdrawal | 12/31/2017
PJM | W2-102 | Mt. Holly 26.4kV | West Pemberton Solar | NJ | Burlington | In Service | PSEG | 7 | 2.66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2010 |  |  | 6/30/2014 | 7/3/2014
PJM | W3-001 | Gilbert-Morris Park 34.5kV | Alpha Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/28/2010 | 9/28/2012 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-002 | Occoquan 34.5kV | I-95 Landfill Phase 2 | VA | Fairfax | In Service | Dominion | 3.2 | 2.9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 8/2/2010 | 11/7/2019 |  | 4/1/2011 | 4/1/2011
PJM | W3-003 | East Flemington-Frenchtown 34.5kV | Quakertown Solar Farm #1 | NJ | Hunterdon | In Service | JCPL | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/3/2010 |  |  | 10/31/2018 | 10/30/2018
PJM | W3-004 | Ridgefield 13kV |  | NJ | Bergen | Withdrawn | PSEG | 1.261 | 0.479 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 8/3/2010 | 3/11/2011 | Customer Initiated Withdrawal | 1/15/2011
PJM | W3-005 | Fostoria Central-Galion (FE) 345kV |  | OH | Huron | Withdrawn | AEP | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn | Withdrawn | 8/3/2010 | 6/18/2014 | Customer Initiated Withdrawal | 11/30/2013
PJM | W3-006 | Newburgh 12kV |  | NJ | Morris | Withdrawn | JCPL | 5 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/5/2010 | 3/7/2011 | Customer Milestone Not Met | 6/1/2011
PJM | W3-007 | Reed 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/6/2010 | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-008 | Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/6/2010 | 9/12/2013 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-009 | Fairton |  | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/6/2010 | 7/24/2013 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-010 | Hans Meadow 12.47KV |  | VA | Montgomery | Withdrawn | AEP | 0.34 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 8/10/2010 | 6/16/2011 | Customer Milestone Not Met | 8/1/2010
PJM | W3-011 | East Lima-Fostoria Central 345kV |  | OH | Hancock | Withdrawn | AEP | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/10/2010 | 9/2/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | W3-012 | East Lima-Fostoria Central 345kV |  | OH | Hancock | Withdrawn | AEP | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/10/2010 | 3/2/2012 | Customer Initiated Withdrawal | 12/31/2014
PJM | W3-013 | Miami |  | OH | Miami | Withdrawn | Dayton | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/10/2010 | 3/16/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | W3-014 | Galion-Fostoria Central 345kV |  | OH | Crawford | Withdrawn | AEP | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/10/2010 | 4/19/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | W3-015 | Egg Harbor Township |  | NJ | Atlantic | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/10/2010 | 2/18/2011 | Customer Initiated Withdrawal | 3/1/2011
PJM | W3-016 | Pilesgrove |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/12/2010 | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-017 | Pilesgrove |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/12/2010 | 2/18/2011 | Customer Initiated Withdrawal | 12/21/2011
PJM | W3-018 | Deepwater-Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 60 | 22.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/12/2010 | 8/23/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-019 | Fentress-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/20/2010 | 7/29/2011 | Customer Initiated Withdrawal | 12/31/2013
PJM | W3-021 | Jacksons Ferry-Peak Creek 138kV |  | VA | Pulaski | Withdrawn | AEP | 70 | 9.1 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/24/2010 | 3/2/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | W3-021A | Corry East 115kV |  | PA | Crawford | Withdrawn | PENELEC | 70 | 9.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/23/2010 | 10/1/2012 | Customer Initiated Withdrawal | 12/31/2014
PJM | W3-022 | Frackville-Eldred #1 230kV |  | PA | Schuylkill | Withdrawn | PPL | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/25/2010 | 3/25/2015 | Customer Initiated Withdrawal | 12/31/2016
PJM | W3-023 | Frackville-Eldred #2 230kV |  | PA | Schuylkill | Withdrawn | PPL | 120 | 15.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/25/2010 | 10/3/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | W3-024 | Columbia 138kV |  | IN | Whitley | Withdrawn | AEP | 149.4 | 19.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/26/2010 | 4/25/2013 | Customer Milestone Not Met | 10/1/2013
PJM | W3-025 | Wrightstown 34.5kV | Saylors Pond Solar Farm | NJ | Burlington | Withdrawn | JCPL | 2.06 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/27/2010 | 6/22/2016 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-026 | Burlington 13kV | 1900 River Road | NJ | Burlington | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/27/2010 | 7/23/2013 | Customer Milestone Not Met | 3/1/2013
PJM | W3-028 | Cedar 230kV | New Jersey Offshore Wind Project | NJ | Atlantic | Withdrawn | AEC | 348 | 45 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/27/2010 | 5/12/2016 | Customer Initiated Withdrawal | 1/1/2019
PJM | W3-029 | Buckeye-Ringoes 34.5kV | Ringoes Solar Farm | NJ | Hunterdon | In Service | JCPL | 8.4 | 3.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/30/2010 |  |  | 5/31/2018 | 6/4/2018
PJM | W3-030 | Southampton 13kV | 1626 Route 70 | NJ | Burlington | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/30/2010 | 3/7/2012 | Customer Initiated Withdrawal | 4/30/2012
PJM | W3-031 | Medford 69kV |  | NJ | Burlington | Withdrawn | PSEG | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/30/2010 | 10/27/2010 | Customer Initiated Withdrawal | 2/6/2012
PJM | W3-032 | Stewartsville-West Portal 34.5kV | New Village Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/30/2010 | 12/24/2013 | Customer Milestone Not Met | 9/1/2014
PJM | W3-032A | Cartanza 230kV | Garrison Energy Center | DE | New Castle | In Service | DPL | 309.2 | 309.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2010 |  |  | 6/1/2015 | 5/21/2015
PJM | W3-033 | Egg Harbor Township 1 |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 7.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Withdrawn | 8/31/2010 | 10/1/2014 | Customer Initiated Withdrawal | 3/31/2018
PJM | W3-034 | Egg Harbor Township 2 |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 7.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Withdrawn |  | 8/31/2010 | 8/10/2011 | Customer Milestone Not Met | 3/1/2012
PJM | W3-035 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 7 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2010 | 2/23/2011 | Customer Initiated Withdrawal | 3/1/2012
PJM | W3-036 | Pemberton 12kV |  | MD | Wicomico | Withdrawn | DPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2010 | 3/2/2011 | Customer Milestone Not Met | 3/1/2012
PJM | W3-037 | Delmar 12kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2010 | 3/8/2011 | Customer Milestone Not Met | 3/1/2012
PJM | W3-038 | Lumberton 13kV | Trotter Property | NJ | Burlington | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2010 | 5/9/2012 | Customer Initiated Withdrawal | 6/30/2013
PJM | W3-039 | Bayonne 26kV |  | NJ | Hudson | Withdrawn | PSEG | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Withdrawn | 8/31/2010 | 6/3/2013 | Customer Initiated Withdrawal | 10/10/2012
PJM | W3-040 | Martinsburg |  | PA | Blair | Withdrawn | PENELEC | 3.8 | 3.8 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 8/31/2010 | 4/22/2011 | Customer Milestone Not Met | 1/30/2012
PJM | W3-041 | Burlington 26kV | Springfield Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2010 | 1/2/2013 | Customer Milestone Not Met | 7/1/2012
PJM | W3-042 | Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 16 | 6.08 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2010 | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012
PJM | W3-043 | Pendleton 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 500 | 65 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 8/31/2010 | 8/16/2011 | Customer Milestone Not Met | 11/30/2017
PJM | W3-044 | Washington 34.5kV | McCullough Road Solar Farm | NJ | Warren | In Service | JCPL | 8.8 | 3.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 8/31/2010 |  |  | 6/30/2019 | 6/27/2019
PJM | W3-045 | Fairfield 12kV | Fairfield at Howell Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2010 | 10/28/2016 |  | 9/1/2014
PJM | W3-046 | Powerton 345kV |  | IL | Mason | Withdrawn | ComEd | 207.5 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/31/2010 | 5/17/2018 |  | 12/31/2015
PJM | W3-047 | Front Royal 500kV | Warren County | VA | Warren | In Service | Dominion | 39 | 60 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2010 |  |  | 9/30/2015 | 10/30/2014
PJM | W3-048 | Hope Creek 500kV | Hope Creek Generating Station | NJ | Salem | In Service | PSEG | 50 | 50 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 8/31/2010 |  |  | 6/1/2012 | 1/23/2013
PJM | W3-049 | Carneys Point 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2010 | 2/23/2011 | Customer Initiated Withdrawal | 5/31/2012
PJM | W3-050 | Kelford 34.5kV |  | NC | Bertie | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 8/31/2010 | 12/14/2011 | Customer Milestone Not Met | 12/31/2012
PJM | W3-051 | Dorton 138kV |  | KY | Pike | Withdrawn | AEP | 60 | 7.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/31/2010 | 1/5/2012 | Customer Milestone Not Met | 9/30/2013
PJM | W3-052 | Tazewell-Kendall 345kV |  | IL | Woodford | Withdrawn | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/31/2010 | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | W3-053 | Trowbridge 230kV |  | NC | Washington | Withdrawn | Dominion | 260 | 33.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/31/2010 | 2/25/2011 | Customer Initiated Withdrawal | 9/30/2013
PJM | W3-054 | Mackeys-Riders Creek 115kV |  | NC | Tyrell | Withdrawn | Dominion | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 8/31/2010 | 5/28/2012 | Customer Initiated Withdrawal | 9/30/2013
PJM | W3-054A | Oak Hall 138kV |  | VA | Accomack | Withdrawn | ODEC | 95 | 12.35 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/31/2010 | 1/22/2013 | Customer Initiated Withdrawal | 6/1/2013
PJM | W3-055 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 9/1/2010 | 9/7/2011 | Customer Initiated Withdrawal | 11/30/2011
PJM | W3-056 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 9/1/2010 | 9/7/2011 | Customer Milestone Not Met | 3/1/2013
PJM | W3-057 | Lumberton 69kV | Warfield II | NJ | Burlington | Withdrawn | PSEG | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/1/2010 | 1/5/2016 | Customer Initiated Withdrawal | 10/1/2015
PJM | W3-058 | Rio Grande 12kV |  | NJ | Cape May | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/10/2010 | 7/24/2013 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-059 | Quinton 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/10/2010 | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2012
PJM | W3-059A_AT6 | Avery-Greenfield 138kV |  | OH | Erie | Withdrawn | ATSI | 99 | 12.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 9/10/2010 | 11/7/2014 | Customer Initiated Withdrawal | 9/9/2017
PJM | W3-059B_AT7 | Allen Junction-Lyons 138kV |  | OH | Fulton | Withdrawn | ATSI | 97.6 | 12.69 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/10/2010 | 2/2/2012 | Customer Initiated Withdrawal | 12/31/2010
PJM | W3-059C_AT8 | Allen Junction 138kV |  | OH | Fulton | Withdrawn | ATSI | 99 | 12.9 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/10/2010 | 6/15/2011 | Customer Initiated Withdrawal | 12/31/2010
PJM | W3-060 | Kendallville 138kV |  | IN | Noble | Withdrawn | AEP | 120 | 15.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn | Withdrawn |  | 9/13/2010 | 11/14/2011 | Customer Milestone Not Met | 11/1/2012
PJM | W3-061 | Church 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/14/2010 | 2/28/2011 | Customer Initiated Withdrawal | 5/31/2011
PJM | W3-063 | South Fultonham 4kV | Zanesville Energy | OH | Muskingum | Deactivated | AEP | 0.85 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/17/2010 | 9/8/2018 |  | 5/31/2011 | 5/31/2011
PJM | W3-064 | Hunterstown 115kV V |  | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/22/2010 | 4/3/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-066 | Shawboro 230kV | Hales Lake Energy Center | NC | Camden | Withdrawn | Dominion | 300 | 40 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/24/2010 | 8/1/2016 | Customer Initiated Withdrawal | 6/1/2016
PJM | W3-067 | Gardners-Hunterstown 115kV |  | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/27/2010 | 4/3/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-068 | Cumberland-W. Shore 3 #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/28/2010 | 5/23/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-069 | Cumberland-W. Shore 3 #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/28/2010 | 5/23/2011 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-070 | Metropolitan Court 34.5kV |  | MD | Frederick | Withdrawn | APS | 52 | 50 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 9/29/2010 | 3/25/2013 | Customer Initiated Withdrawal | 10/31/2013
PJM | W3-071 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 12.54 | 4.77 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2010 | 3/21/2012 | Customer Initiated Withdrawal | 6/1/2012
PJM | W3-072 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2010 | 9/12/2013 | Customer Initiated Withdrawal | 7/1/2012
PJM | W3-073 | West Cape May 12kV |  | NJ | Cape May | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2010 | 8/12/2011 | Customer Milestone Not Met | 3/1/2011
PJM | W3-075 | Orchard 230kV |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2010 | 8/12/2011 | Customer Milestone Not Met | 6/1/2012
PJM | W3-076 | Morris Park-Stewartsville 34.5kV | South Main Street Solar Farm | NJ | Warren | Withdrawn | JCPL | 17 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2010 | 12/7/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | W3-077 | Broadway-Stewartsville 34.5kV | Franklin Township Solar Farm | NJ | Warren | In Service | JCPL | 8.8 | 3.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2010 |  |  | 1/31/2020 | 1/10/2020
PJM | W3-078 | Twin Rivers-Windsor 34.5kV | East Windsor Solar Farm | NJ | Mercer | Withdrawn | JCPL | 13 | 4.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2010 | 10/21/2014 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-079 | Allenwood-Larabee 34.5kV | Lakewood-Farmingdale Road Solar Farm | NJ | Monmouth | In Service | JCPL | 7 | 2.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2010 |  |  | 10/6/2016 | 4/19/2016
PJM | W3-080 | Burlington 26kV | Cedar Lane | NJ | Burlington | In Service | PSEG | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2010 |  |  | 11/15/2016 | 12/29/2016
PJM | W3-081 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 11 | 4.18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2010 | 7/26/2011 | Customer Milestone Not Met | 2/15/2012
PJM | W3-082 | Woodbine Township |  | NJ | Cape May | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2010 | 2/18/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-084 | Clinton-Round Valley 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 16.6 | 6.31 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/15/2010 | 12/3/2010 | Customer Initiated Withdrawal | 12/1/2011
PJM | W3-085 | Chatfield-South Tiffin 138kV |  | OH | Crawford | Withdrawn | AEP | 185 | 24 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/15/2010 | 5/7/2013 | Customer Initiated Withdrawal | 12/31/2012
PJM | W3-086 | Townsend 138kV |  | DE | New Castle | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/18/2010 | 8/16/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W3-087 | Cartanza 230kV |  | DE | Kent | Withdrawn | DPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/18/2010 | 3/15/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-088 | South West Lima 345kV | Long Prairie Wind I, LLC | OH | Van Wert | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/21/2010 | 10/28/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | W3-089 | Carneys Point 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/21/2010 | 8/15/2011 | Customer Milestone Not Met | 12/31/2012
PJM | W3-090 | Carneys Point 12kV 1 |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/21/2010 | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-092 | Carneys Point 12kV 2 |  | NJ | Salem | Withdrawn | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/21/2010 | 2/24/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-093 | Lyon Station |  | PA | Berks | Withdrawn | ME | 3 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/25/2010 | 3/5/2012 | Customer Initiated Withdrawal | 10/1/2011
PJM | W3-095 | Broadway-Stewartsville#2 34.5kV | Stewartsville Solar Farm | NJ | Warren | Withdrawn | JCPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/26/2010 | 9/18/2014 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-096 | Perkiomen |  | PA | Montgomery | Withdrawn | PECO | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/26/2010 | 11/2/2011 | Customer Milestone Not Met | 4/1/2011
PJM | W3-097 | Russelville OH |  | OH | Brown | Withdrawn | AEP | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/26/2010 | 10/10/2011 | Customer Initiated Withdrawal | 9/30/2012
PJM | W3-098 | Hillsboro-Kenton (KU) 138kV |  | OH | Brown | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 10/26/2010 | 10/24/2011 | Customer Initiated Withdrawal | 6/30/2013
PJM | W3-099 | Erie East-Erie South 230 kV | Greenfield Wind Farm | PA | Erie | Withdrawn | PENELEC | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/27/2010 | 9/10/2018 |  | 12/31/2019
PJM | W3-100 | Daretown Road 12kV |  | NJ | Salem | Withdrawn | AEC | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/28/2010 | 3/3/2011 | Customer Initiated Withdrawal | 6/30/2012
PJM | W3-101 | East Elmer Road 12kV | Elmer Road | NJ | Cumberland | Withdrawn | AEC | 3.2 | 1.21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/28/2010 | 12/18/2012 | Customer Initiated Withdrawal | 9/15/2012
PJM | W3-102 | East Carbondale-Lackawanna 69kV |  | PA | Wayne | Withdrawn | PPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/28/2010 | 5/19/2011 | Customer Initiated Withdrawal | 5/30/2011
PJM | W3-103 | Upper Deerfield Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 8/16/2011 | Customer Milestone Not Met | 12/1/2011
PJM | W3-104 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 8/15/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W3-105 | Dickerson 230kV | Dickerson CT1 (D-CT1) | MD | Montgomery | Deactivated | PEPCO | 5 | 5 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 10/29/2010 |  |  | 12/31/2011 | 8/23/2011
PJM | W3-106 | Sussex-Wykertown 34.5kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 9.9 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/29/2010 |  |  | 9/30/2015 | 1/22/2016
PJM | W3-107 | Ringoes-Texas Eastern 34.5kV | Garboski I Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 1/27/2012 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-108 | Ringoes #2 34.5kV | Garboski I Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 11/21/2011 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-109 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 0.625 | 0.24 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/3/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W3-110 | Sussex | Wantage Solar Farm | NJ | Sussex | In Service | JCPL | 7.5 | 2.85 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 |  |  | 12/31/2014 | 11/15/2013
PJM | W3-111 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/29/2010 | 7/25/2018 |  | 4/16/2017
PJM | W3-112 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/29/2010 | 7/25/2018 |  | 4/16/2018
PJM | W3-113 | S. Cumberland 69kV | Turning Point Solar | OH | Noble | Withdrawn | AEP | 14.9 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/29/2010 | 7/25/2018 |  | 4/16/2019
PJM | W3-114 | Venango I |  | PA | Venango | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/16/2011 | Customer Milestone Not Met | 8/1/2011
PJM | W3-115 | Venango II |  | PA | Venango | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/16/2011 | Customer Milestone Not Met | 8/1/2011
PJM | W3-116 | Venango III |  | PA | Venango | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/29/2010 | 11/17/2010 | Customer Milestone Not Met | 8/1/2011
PJM | W3-117 | Clarion |  | PA | Clarion | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/29/2010 | 11/17/2010 | Customer Milestone Not Met | 8/1/2011
PJM | W3-118 | Venango IV |  | PA | Venango | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/29/2010 | 11/17/2010 | Customer Milestone Not Met | 8/1/2011
PJM | W3-119 | Venango V |  | PA | Venango | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/29/2010 | 11/17/2010 | Customer Milestone Not Met | 8/1/2011
PJM | W3-120 | Cookstown-Great Adventure 34.5kV | Polizzi Solar Farm | NJ | Ocean | Withdrawn | JCPL | 17 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 5/16/2014 |  | 12/31/2014
PJM | W3-121 | Queen Anne County 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn | Not Required | Withdrawn | 10/29/2010 | 3/8/2011 | Customer Milestone Not Met | 6/1/2013
PJM | W3-124 | Devils Brook 13kV | Matrix-Stults Road | NJ | Middlesex | In Service | PSEG | 2.85 | 1.08 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 |  |  | 6/30/2011 | 6/17/2011
PJM | W3-125 | Eagle Point 230kV |  | NJ | Gloucester | Withdrawn | PSEG | 27.9 | 27.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/8/2011 | Customer Milestone Not Met | 6/1/2011
PJM | W3-126 | Branchville-Holiday Lakes 34.5kV | Syncarpha Ty Solar Farm | NJ | Sussex | Withdrawn | JCPL | 17 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 1/3/2014 | Customer Milestone Not Met | 9/1/2014
PJM | W3-127 | City of Columbus 14.4kV |  | OH | Franklin | Withdrawn | AEP | 1 | 0 | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2010 | 10/3/2012 | Customer Initiated Withdrawal | 12/1/2010
PJM | W3-128 | Sporn-Waterford 345kV |  | OH | Meigs | Withdrawn | AEP | 652 | 652 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 5/22/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | W3-129 | Beaver Brook 13kV | Blackwood Solar | NJ | Camden | Withdrawn | PSEG | 7.3 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 9/27/2012 | Customer Milestone Not Met | 6/30/2012
PJM | W3-130 | Crosswicks 13kV | Mansfield Solar | NJ | Burlington | Withdrawn | PSEG | 8.3 | 3.23 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 9/27/2012 | Customer Milestone Not Met | 6/30/2012
PJM | W3-131 | Alpha #2 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 7.6 | 2.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/29/2010 | 12/21/2010 | Customer Initiated Withdrawal | 11/1/2011
PJM | W3-132 | Stillman Valley |  | IL | Winnebago | Withdrawn | ComEd | 19.4 | 7.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 12/30/2013 | Customer Milestone Not Met | 12/31/2011
PJM | W3-133 | Kewanee |  | IL | Stark | Withdrawn | ComEd | 19.5 | 2.5 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 10/29/2010 | 9/15/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-134 | South Joliet 34.5kV | Brandon Road Lock & Dam | IL | Will | Withdrawn | ComEd | 10.6 | 10.6 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 4/20/2021 |  | 1/31/2022
PJM | W3-135 | Goose Lake 34.5kV | Dresden Island Lock & Dam | IL | Grundy | Withdrawn | ComEd | 12.1 | 12.1 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 2/21/2022 |  | 1/31/2022
PJM | W3-136 | Andover-Kittatinny #2 34.5kV | Hibler Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-137 | Furnace Brook 12kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/25/2011 | Customer Milestone Not Met | 10/1/2011
PJM | W3-138 | Blairstown-Kittatinny 34.5kV | Stillwater Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2012
PJM | W3-139 | Broadway-Stewartsville #3 34.5kV | Broadway Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 1/17/2018 | Customer Initiated Withdrawal | 5/31/2017
PJM | W3-140 | Sussex #2 | Roy Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 3/17/2015 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-141 | Knowlton #1 12kV |  | NJ | Warren | Withdrawn | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 8/18/2011 | Customer Initiated Withdrawal | 3/31/2012
PJM | W3-142 | Lopatcong |  | NJ | Warren | Withdrawn | JCPL | 18 | 6.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 7/25/2011 | Customer Initiated Withdrawal | 3/31/2012
PJM | W3-143 | Knowlton #2 |  | NJ | Warren | Withdrawn | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 2/3/2012 | Customer Milestone Not Met | 3/1/2012
PJM | W3-144 | Pequest-Washington 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2010 | 4/11/2012 | Customer Initiated Withdrawal | 3/1/2012
PJM | W3-145 | Branchville-Newton 34.5kV | Hampton Township Solar Farm | NJ | Sussex | Withdrawn | JCPL | 17 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 3/17/2015 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-146 | Andover-Kittatinny 34.5kV | Kerrs Corner Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 10/15/2014 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-147 | Baptistown-Frenchtown #2 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2010 | 8/30/2011 | Customer Milestone Not Met | 3/1/2012
PJM | W3-148 | Baptistown 12kV |  | NJ | Hunterdon | Withdrawn | JCPL | 6 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 5/25/2011 | Customer Milestone Not Met | 11/15/2011
PJM | W3-149 | Frenchtown-Rosemont 34.5kV | Route 519 Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 5/7/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | W3-150 | Flemington 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn | Not Required |  | 10/29/2010 | 3/16/2011 | Customer Milestone Not Met | 3/15/2012
PJM | W3-151 | Phillipsburg 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 16 | 6.1 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/16/2011 | Customer Milestone Not Met | 3/15/2012
PJM | W3-152 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 12/21/2011 | Customer Milestone Not Met | 4/1/2011
PJM | W3-153 | Heaton 34kV |  | PA | Montgomery | Withdrawn | PECO | 2.6 | 1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 11/2/2011 | Customer Milestone Not Met | 6/4/2011
PJM | W3-154 | Broadway 12kV | Schanzlin Solar Farm | NJ | Warren | Withdrawn | JCPL | 1.6 | 0.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 12/1/2014 | Customer Milestone Not Met | 9/1/2014
PJM | W3-155 | Alabama 13.8kV |  | DC |  | Withdrawn | PEPCO | 20 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2010 | 8/15/2013 | Customer Milestone Not Met | 2/28/2014
PJM | W3-156 | Englishtown-Texas Road 34.5kV | Swayles Solar Farm | NJ | Middlesex | Withdrawn | JCPL | 17 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 2/15/2012 | Customer Initiated Withdrawal | 9/1/2014
PJM | W3-157 | Stow Creek Township 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.7 | 0.65 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 7/18/2013 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-158 | Great Adventure-Great Adventure Tap 34kV | Millstone Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 7/26/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | W3-159 | Hornerstown-Windsor 34kV | Monmouth West Solar I | NJ | Monmouth | Withdrawn | JCPL | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 5/5/2016 | Customer Initiated Withdrawal | 6/30/2015
PJM | W3-160 | Worcester 25kV | Worcester Solar Facility | MD | Worcester | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/29/2010 | 9/24/2015 | Customer Initiated Withdrawal | 10/31/2017
PJM | W3-161 | Kanawha River 138kV |  | WV | Fayette | Withdrawn | AEP | 13 | 13 | Capacity | Generation Interconnection | Other | Document Posted | Withdrawn |  |  | 10/29/2010 | 2/16/2012 | Customer Milestone Not Met | 6/1/2013
PJM | W3-162 | Baker 345kV | Riverside Generating Stations | KY | Lawrence | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/29/2010 |  |  | 2/8/2010 | 9/9/2011
PJM | W3-163 | Upper Pittsgrove 138kV 1 |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 8/15/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W3-164 | Upper Pittsgrove 138kV 2 |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 8/15/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W3-165 | Upper Pittsgrove 138kV 3 |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 8/15/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W3-166 | Nottingham I |  | PA | Chester | Withdrawn | PECO | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/22/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W3-167 | Nottingham II |  | PA | Chester | Withdrawn | PPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2010 | 7/26/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | W3-168 | Germantown 13.2 kV |  | PA | Adams | Withdrawn | ME | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012
PJM | W3-169 | North Hanover 12.5kV |  | PA | Adams | Withdrawn | ME | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/29/2010 | 10/6/2011 | Customer Initiated Withdrawal | 6/1/2012
PJM | W3-170 | Buckskin 69kV |  | OH | Putnam | Withdrawn | AEP | 12 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/29/2010 | 11/12/2014 | Customer Milestone Not Met | 9/30/2015
PJM | W3-171 | Levittown 13kV | Rancocas Road Solar Project | NJ | Burlington | Withdrawn | PSEG | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/29/2010 | 4/10/2012 | Customer Initiated Withdrawal | 4/30/2012
PJM | W3-172 | Hay Road 230kV 1 |  | DE | New Castle | Withdrawn | DPL | 402 | 402 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/2/2011 | Customer Initiated Withdrawal | 6/1/2013
PJM | W3-173 | Hay Road 230kV 2 |  | DE | New Castle | Withdrawn | DPL | 218 | 218 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/29/2010 | 3/2/2011 | Customer Initiated Withdrawal | 6/1/2015
PJM | W3-174 | Churchtown 230kV 1 |  | NJ | Salem | Withdrawn | AEC | 193.5 | 193.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/29/2010 | 4/15/2013 | Customer Initiated Withdrawal | 6/1/2015
PJM | W3-175 | Churchtown 230kV 2 | Deepwater | NJ | Salem | Withdrawn | AEC | 371 | 371 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/29/2010 | 2/7/2019 |  | 12/1/2021
PJM | W4-001 | Clover |  | VA | Halifax | Withdrawn | Dominion | 7 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/2/2010 | 1/20/2011 | Customer Initiated Withdrawal | 12/31/2012
PJM | W4-001A_AT9 | Lowellville 69kV | Carbon Limestone Landfil Gas to Electricity Facility | OH | Mahoning | Deactivated | ATSI | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 11/2/2010 |  |  | 12/31/2012 | 9/19/2012
PJM | W4-004 | Madison-Tanners Creek 138kV | Flat Rock-WF-1 | IN | Henry | Withdrawn | AEP | 90 | 11.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/10/2010 | 10/22/2018 |  | 7/1/2021
PJM | W4-004A_AT10 | Oberlin Road 69kV | Lorain | OH | Lorain | In Service | ATSI | 19.2 | 19.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/12/2010 |  |  | 9/1/2012 | 5/31/2012
PJM | W4-004B_AT11 | Perry 345kV | Perry Nuclear Power Plant | OH | Lake | In Service | ATSI | 16 | 16 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 11/15/2010 |  |  |  | 4/26/2013
PJM | W4-005 | Blue Mound-Latham | Radford's Run Wind Farm | IL | Macon | In Service | ComEd | 306 | 39.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/17/2010 |  |  | 6/1/2019 | 12/14/2017
PJM | W4-006 | S. Hicksville-Lockwood Road 138kV |  | OH | Defiance | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 11/19/2010 | 4/19/2012 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-007 | Afton 138kV |  | WV | Preston | Withdrawn | APS | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/19/2010 | 5/31/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-008 | Madison-Tanners Creek 138kV | Flat Rock - WF-1 | IN | Henry | Withdrawn | AEP | 90 | 11.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/22/2010 | 10/22/2018 |  | 7/1/2021
PJM | W4-009 | Raritan River 230kV | Woodbridge Energy Center | NJ | Middlesex | In Service | JCPL | 725 | 725 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/22/2010 |  |  | 6/1/2017 | 12/4/2015
PJM | W4-010 | White Oak |  | MD | Montgomery | In Service | PEPCO | 29.1 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/22/2010 |  |  | 12/31/2015 | 5/8/2014
PJM | W4-011 | Larabee 34.5kV | Solar Wind Energy Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/24/2010 | 2/22/2016 | Customer Milestone Not Met | 12/31/2014
PJM | W4-012 | Whetstone 115kV |  | PA | Elk | Withdrawn | PENELEC | 120 | 15.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/24/2010 | 5/31/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-013 | Frack-Orwigsburg 69kV |  | PA | Schuylkill | Withdrawn | PPL | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 11/24/2010 | 11/13/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-014 | Stewartsville-Captive Plastics 34.5kV | Stewartsville II Solar Farm | NJ | Warren | Withdrawn | JCPL | 17 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/29/2010 | 1/21/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-015 | Mickleton 230kV 1 | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 210 | 136 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/29/2010 |  |  | 6/1/2015 | 1/16/2015
PJM | W4-016 | Mickleton 230kV 2 | West Deptford Energy Station | NJ | Gloucester | Withdrawn | AEC | 235 | 235 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/29/2010 | 11/20/2018 |  | 6/1/2019
PJM | W4-017 | Kings Creek-Crisfield 69kV |  | MD | Somerset | Withdrawn | DPL | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 11/29/2010 | 11/27/2012 | Customer Initiated Withdrawal | 12/1/2013
PJM | W4-018 | Monroeville 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 11/30/2010 | 3/15/2013 | Customer Initiated Withdrawal | 7/1/2012
PJM | W4-019 | Mendota |  | IL | Bureau | Withdrawn | ComEd | 40 | 9.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/30/2010 | 1/30/2012 | Customer Initiated Withdrawal | 10/1/2012
PJM | W4-020 | Mt. Zion 13.8kV |  | MD | Montgomery | Withdrawn | PEPCO | 10.08 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 11/30/2010 | 9/18/2012 | Customer Milestone Not Met | 8/1/2011
PJM | W4-021 | Atlantic-South River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 738.4 | 738.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/30/2010 | 9/11/2013 | Customer Milestone Not Met | 6/1/2015
PJM | W4-021A | Richland & Crawford |  | OH | Richland | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/30/2010 | 9/18/2012 | Customer Initiated Withdrawal | 9/1/2012
PJM | W4-022 | Hunterstown 230kV |  | PA | Adams | Withdrawn | ME | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/1/2010 | 7/29/2011 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-023 | Kearny 138kV |  | NJ | Hudson | Withdrawn | PSEG | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/1/2010 | 5/21/2012 |  | 5/31/2014
PJM | W4-024 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 12/1/2010 | 6/5/2012 | Customer Initiated Withdrawal | 6/1/2014
PJM | W4-025 | Cookstown-Fort Dix 34.5kV | North Run Solar | NJ | Burlington | In Service | JCPL | 7 | 2.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 12/6/2010 |  |  | 5/29/2014 | 2/4/2015
PJM | W4-026 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 5.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/14/2010 | 11/28/2011 | Customer Initiated Withdrawal | 5/31/2012
PJM | W4-027 | Minotola 12kV | Minotola 2 Solar Facility | NJ | Atlantic | Withdrawn | AEC | 7.9 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 12/15/2010 | 5/20/2016 | Customer Initiated Withdrawal | 6/1/2018
PJM | W4-028 | Quinton 69kV |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/15/2010 | 6/1/2011 | Customer Milestone Not Met | 6/30/2011
PJM | W4-029 | Medford 13kV | Reeve's Station North | NJ | Burlington | Withdrawn | PSEG | 2.4 | 0.91 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/17/2010 | 10/31/2018 |  | 12/31/2014
PJM | W4-030 | Jessup |  | MD | Howard | Withdrawn | BGE | 0.008 | 0 | Energy | Generation Interconnection | Solar | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 12/20/2010 | 7/20/2012 | Customer Initiated Withdrawal | 3/1/2012
PJM | W4-031 | Perryville 12.5kV | Pattenburg Quarry Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2.6 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/22/2010 | 11/23/2015 |  | 12/31/2014
PJM | W4-032 | West Portal 4.8kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1.5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 12/28/2010 | 4/4/2012 | Customer Initiated Withdrawal | 12/22/2011
PJM | W4-033 | Wilmington | Lincoln Solar | IL | Will | Withdrawn | ComEd | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/28/2010 | 12/8/2015 | Customer Initiated Withdrawal | 12/31/2016
PJM | W4-034 | Essex 26.4kV |  | NJ | Essex | Withdrawn | PSEG | 3 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 12/28/2010 | 9/1/2011 | Customer Milestone Not Met | 3/1/2011
PJM | W4-035 | Martinsville |  | OH | Clinton | Withdrawn | Dayton | 20 | 11.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/28/2010 | 12/12/2011 | Customer Initiated Withdrawal | 5/31/2012
PJM | W4-036 | Buckskin 12kV | Ohio Solar I | OH | Ross | Withdrawn | AEP | 12 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 12/28/2010 | 1/2/2018 |  | 1/31/2019
PJM | W4-037 | Bismark 500kV | New Creek Mountain Energy Storage | WV | Grant | Withdrawn | Dominion | 32 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 12/30/2010 | 11/5/2018 |  | 12/31/2018 | 12/26/2016
PJM | W4-038 | Hudson 230kV | Hudson Generating Station | NJ | Hudson | Deactivated | PSEG | 24 | 24 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 12/30/2010 |  |  | 8/31/2018 | 11/1/2012
PJM | W4-039 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.5 | 62.5 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 12/30/2010 | 6/22/2012 | Customer Milestone Not Met | 12/31/2013
PJM | W4-040 | Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 9.7 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/30/2010 | 6/2/2014 | Customer Initiated Withdrawal | 5/13/2012
PJM | W4-041 | Carlls Corner 69kV |  | NJ | Cumberland | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/30/2010 | 1/31/2012 | Customer Milestone Not Met | 9/1/2012
PJM | W4-042 | McConnellsburg 34.5kV | Cove Creek Solar Project | PA | Fulton | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/30/2010 | 7/23/2013 | Customer Initiated Withdrawal | 12/15/2014
PJM | W4-043 | Roberts 34.5kV |  | OH | Marion | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/31/2010 | 1/18/2011 |  | 9/1/2012
PJM | W4-044 | Kelson Ridge 230kV |  | MD | Charles | Withdrawn | PEPCO | 725 | 725 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 1/5/2011 | 7/31/2013 | Customer Milestone Not Met | 6/1/2015
PJM | W4-045 | Great Adventure-Great Adventure Tap 34.5kV | Red Valley Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 9 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/11/2011 | 7/26/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | W4-046 | Washington-Mobile Chemical 34.5kV | Hengst Solar Farm | NJ | Warren | In Service | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/11/2011 |  |  | 11/28/2016 | 7/13/2016
PJM | W4-048 | Doremus Place 13kV |  | NJ | Essex | Withdrawn | PSEG | 1.05 | 0.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/18/2011 | 6/27/2011 | Customer Initiated Withdrawal | 6/30/2011
PJM | W4-051 | Packer 13kV |  | PA | Philadelphia | Withdrawn | PECO | 12 | 10.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 1/24/2011 | 11/3/2011 | Customer Milestone Not Met | 9/1/2011
PJM | W4-053 | Rocktown 4.8kV | Green Power West Amwell Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/24/2011 | 10/20/2015 |  | 12/31/2014
PJM | W4-054 | Williamstown 12kV |  | NJ | Gloucester | Withdrawn | AEC | 12 | 4.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/26/2011 | 5/24/2011 | Customer Milestone Not Met | 5/1/2012
PJM | W4-055 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/28/2011 | 12/13/2011 | Customer Milestone Not Met | 10/1/2012
PJM | W4-056 | Pittsgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/28/2011 | 6/1/2011 | Customer Milestone Not Met | 4/15/2012
PJM | W4-057 | Pittsgrove 2 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/28/2011 | 6/1/2011 | Customer Milestone Not Met | 4/15/2012
PJM | W4-058 | Lawrence 13kV | Rider University | NJ | Mercer | In Service | PSEG | 0.702 | 0.267 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 |  |  | 12/31/2011 | 12/16/2011
PJM | W4-059 | Kuller Road 13kV | Metro Division Headquarters | NJ | Passaic | In Service | PSEG | 0.6 | 0.228 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 |  |  | 6/30/2012 | 7/5/2012
PJM | W4-060 | Midland-Werner 34.5kV | Old Bridge Solar Farm | NJ | Middlesex | In Service | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 |  |  | 3/31/2018 | 8/4/2018
PJM | W4-061 | Lawrence 26kV |  | NJ | Mercer | Withdrawn | PSEG | 9 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2011 | 1/27/2012 | Customer Initiated Withdrawal | 6/1/2012
PJM | W4-062 | Tabernacle 69kV |  | NJ | Burlington | Withdrawn | AEC | 18 | 6.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2011 | 11/29/2011 | Customer Milestone Not Met | 12/31/2012
PJM | W4-063 | Huron 69kV | Fishermen's Atlantic City Windfarm (FACW) | NJ | Cape May | Withdrawn | AEC | 5 | 0.65 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2011 | 3/12/2019 |  | 1/27/2019
PJM | W4-064 | N. Newton 12kV | Augusta Solar Farm | NJ | Sussex | In Service | JCPL | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 |  |  | 6/12/2016 | 5/31/2016
PJM | W4-065 | Sussex 12kV | Layton Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 | 5/3/2016 | Customer Milestone Not Met | 12/31/2014
PJM | W4-066 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 11/4/2011 | Customer Initiated Withdrawal | 12/31/2012
PJM | W4-067 | Vernon 12kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 8/23/2011 | Customer Milestone Not Met | 12/31/2012
PJM | W4-068 | Hazen-Pequest River 34.5kV | White Township Solar Farm | NJ | Warren | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-069 | Lycoming |  | PA | Lycoming | Withdrawn | PPL | 3 | 3 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 1/31/2011 | 4/29/2011 | Customer Initiated Withdrawal | 4/1/2012
PJM | W4-070 | Morgantown |  | PA | Berks | Withdrawn | PPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2011 | 6/27/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | W4-071 | Garrett |  | PA | Somerset | Withdrawn | PENELEC | 2.25 | 0.29 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 1/31/2011 | 2/17/2011 | Customer Milestone Not Met | 3/30/2012
PJM | W4-072 | Englishtown-Rt. 33 Sw Point 34.5kV | Big Hill Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 16 | 6.08 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 | 10/23/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-073 | Phillipsburg 34.5kV | Hamptons at Pohatcong Solar Farm | NJ | Warren | In Service | JCPL | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 |  |  | 12/31/2019 | 1/10/2020
PJM | W4-074 | Cox’s Corner 13kV | CleanLight Medford Solar Project | NJ | Burlington | Withdrawn | PSEG | 5 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 | 1/31/2012 | Customer Initiated Withdrawal | 4/30/2012
PJM | W4-075 | Trenton 26kV | CleanLight Mansfield Solar Project | NJ | Burlington | Withdrawn | PSEG | 9 | 3.42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 | 6/7/2012 |  | 6/30/2012
PJM | W4-076 | Ritchie |  | MD | Prince George's | Withdrawn | PEPCO | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 6/7/2011 | Customer Milestone Not Met | 11/1/2011
PJM | W4-078 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 6/1/2011 | Customer Milestone Not Met | 6/1/2013
PJM | W4-079 | Lebanon |  | NJ | Hunterdon | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2011 | 1/30/2012 | Customer Milestone Not Met | 10/31/2011
PJM | W4-080 | Metuchen 26.4kV | IRL Landfill Solar Project | NJ | Middlesex | Withdrawn | PSEG | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 | 2/4/2016 |  | 11/30/2012
PJM | W4-081 | Manchester |  | NJ | Ocean | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 6/2/2011 | Customer Milestone Not Met | 10/31/2011
PJM | W4-082 | Libertyville 12kV | Countryside Landfill | IL | Lake | Deactivated | ComEd | 7.99 | 7.99 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2011 |  |  | 4/1/2001 | 7/16/2012
PJM | W4-083 | Quinton 69kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2011 | 11/29/2011 | Customer Milestone Not Met | 5/1/2012
PJM | W4-084 | Dixon 12kV | Dixon/Lee Landfill | IL | Lee | Deactivated | ComEd | 3.95 | 3.95 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2011 |  |  | 3/1/2001 | 4/16/2013
PJM | W4-085 | Grays Ferry |  | PA | Philadelphia | Withdrawn | PECO | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 1/31/2011 | 6/17/2014 | Customer Initiated Withdrawal | 5/15/2011
PJM | W4-086 | Goose Lake 34.5kV | Morris Landfill | IL | Grundy | Deactivated | ComEd | 2.1 | 2.1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2011 |  |  | 3/1/2001 | 5/16/2013
PJM | W4-087 | South Holland |  | IL | Cook | Withdrawn | ComEd | 3.07 | 3.07 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 1/31/2011 | 12/13/2012 | Customer Initiated Withdrawal | 4/1/1998
PJM | W4-088 | Salem-Woodstown 69kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 6/1/2011 | Customer Milestone Not Met | 5/1/2012
PJM | W4-089 | Vineland #1 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.6 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/31/2011 | 6/19/2014 | Customer Initiated Withdrawal | 6/1/2011
PJM | W4-090 | Vineland #2 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.34 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/31/2011 | 6/19/2014 | Customer Initiated Withdrawal | 6/1/2011
PJM | W4-091 | Andover-Kittatinny 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 6/1/2011 | Customer Milestone Not Met | 8/1/2012
PJM | W4-092 | Englishtown 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 6/3/2011 | Customer Milestone Not Met | 8/1/2012
PJM | W4-093 | Frenchtown 34.5kV | Dotoli Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 7 | 2.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 | 5/7/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | W4-094 | Millhurst-Raceway Mall 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 6 | 2.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2011 | 1/11/2012 | Customer Initiated Withdrawal | 3/15/2012
PJM | W4-095 | Beckett 12kV |  | NJ | Gloucester | Withdrawn | AEC | 5.2 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2011 | 11/29/2011 | Customer Milestone Not Met | 3/31/2013
PJM | W4-096 | Piney Grove 25kV |  | MD | Wicomico | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/31/2011 | 2/18/2011 | Customer Initiated Withdrawal | 3/31/2013
PJM | W4-097 | Hawks 12.5kV | Wetteland Solar Farm | NJ | Hunterdon | In Service | JCPL | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 |  |  | 7/31/2016 | 1/6/2016
PJM | W4-098 | U.S. Silica #1 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2011 | 11/18/2011 | Customer Milestone Not Met | 12/31/2011
PJM | W4-099 | U.S. Silica #2 69kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/31/2011 | 2/22/2011 | Customer Initiated Withdrawal | 12/31/2011
PJM | W4-100 | Exxon-NewYork Life 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 7/8/2011 | Customer Initiated Withdrawal | 12/31/2012
PJM | W4-101 | Limecrest-Newton 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2011 | 7/6/2011 | Customer Initiated Withdrawal | 12/31/2012
PJM | W4-102 | Lappans 34.5kV | Lappans 34.5kV Project | MD | Washington | In Service | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2011 |  |  | 12/31/2012 | 11/29/2012
PJM | W4-103 | Burlington 26kV | North American Solar | NJ | Burlington | In Service | PSEG | 7 | 2.66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2011 |  |  | 8/15/2016 | 3/3/2016
PJM | X1-001 | South Millville 69kV |  | NJ | Cumberland | Withdrawn | AEC | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn | Withdrawn |  | 2/1/2011 | 10/4/2011 | Customer Milestone Not Met | 12/31/2011
PJM | X1-003 | Belvidere |  | NJ | Warren | Withdrawn | JCPL | 1.9 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/11/2011 | 4/27/2012 | Customer Milestone Not Met | 3/30/2012
PJM | X1-004 | Asbury |  | NJ | Hunterdon | Withdrawn | JCPL | 9.7 | 3.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/11/2011 | 1/11/2012 | Customer Milestone Not Met | 12/31/2011
PJM | X1-005 | Port Murray | Meadows at Mansfield Solar Farm | NJ | Warren | Withdrawn | JCPL | 9.7 | 3.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/11/2011 | 11/21/2013 | Customer Milestone Not Met | 12/31/2014
PJM | X1-006 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 4.8 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/11/2011 | 3/7/2012 | Customer Milestone Not Met | 1/31/2012
PJM | X1-007 | Hackettstown |  | NJ | Burlington | Withdrawn | JCPL | 5.8 | 2.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/11/2011 | 3/7/2012 | Customer Milestone Not Met | 10/1/2011
PJM | X1-008 | Mansfield |  | NJ | Warren | Withdrawn | JCPL | 7.8 | 2.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/11/2011 | 1/31/2012 | Customer Milestone Not Met | 10/1/2011
PJM | X1-009 | Sterling 69kV |  | OH | Allen | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/11/2011 | 9/19/2011 | Customer Initiated Withdrawal | 12/1/2012
PJM | X1-012 | Branchville-Sussex 34.5kV | Frankford Solar Farm | NJ | Sussex | In Service | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/22/2011 |  |  | 6/1/2016 | 3/3/2016
PJM | X1-013 | N. Lebanon 230kV |  | PA | Lebanon | Withdrawn | ME | 1018 | 951 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required |  | 2/24/2011 | 12/2/2013 | Customer Initiated Withdrawal | 6/1/2015
PJM | X1-014 | Peters Mountain 13kV |  | WV | Monroe | Withdrawn | AEP | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/25/2011 | 9/19/2011 | Customer Milestone Not Met | 3/15/2013
PJM | X1-016 | Upper Pittsgrove 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/28/2011 | 9/16/2011 | Customer Milestone Not Met | 1/1/2013
PJM | X1-017 | Cedar 230kV |  | NJ | Atlantic | Withdrawn | AEC | 720 | 93 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 2/28/2011 | 2/7/2012 | Customer Initiated Withdrawal | 9/30/2016
PJM | X1-018 | Lewistown 230kV |  | PA | Mifflin | Withdrawn | PENELEC | 75 | 9.75 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/28/2011 | 1/10/2012 | Customer Milestone Not Met | 8/15/2013
PJM | X1-019 | Sunbury-Dauphin 69kV |  | PA | Dauphin | Withdrawn | PPL | 60 | 7.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/28/2011 | 8/29/2011 | Customer Milestone Not Met | 8/15/2013
PJM | X1-020 | Dumont-Greentown 765kV |  | IN | Cass | Withdrawn | AEP | 1500 | 195 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 2/28/2011 | 7/25/2018 |  | 8/31/2018
PJM | X1-021 | Deptford 13kV | Deptford Solar | NJ | Burlington | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/28/2011 | 10/27/2017 |  | 9/1/2017
PJM | X1-022 | Park Hall |  | MD | St. Mary's | Withdrawn | PEPCO | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2011 | 4/8/2011 | Queue Not Required | 4/30/2012
PJM | X1-023 | Mechanicsville |  | MD | St. Mary's | Withdrawn | PEPCO | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2011 | 4/8/2011 | Queue Not Required | 4/30/2012
PJM | X1-024 | Pedricktown 12kV |  | NJ | Salem | Withdrawn | AEC | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/28/2011 | 9/21/2011 | Customer Milestone Not Met | 4/30/2012
PJM | X1-025 | Leonardtowne |  | MD | St. Mary's | Withdrawn | PEPCO | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2011 | 4/8/2011 | Queue Not Required | 4/30/2012
PJM | X1-026 | Brick |  | NJ | Ocean | Withdrawn | JCPL | 6.25 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/2/2011 | 9/7/2011 | Customer Milestone Not Met | 12/31/2011
PJM | X1-027 | Hanging Rock 138kV |  | OH | Scioto | Withdrawn | AEP | 200 | 200 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 3/2/2011 | 3/9/2012 | Customer Initiated Withdrawal | 6/30/2014
PJM | X1-027A_AT12 | Davis Besse-Beaver 345kV | Emerson Creek Wind Farm | OH | Huron | Withdrawn | ATSI | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/3/2011 | 7/18/2018 |  | 4/1/2018
PJM | X1-028 | Upton 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/4/2011 | 11/29/2011 | Customer Initiated Withdrawal | 11/30/2012
PJM | X1-029 | Dorchester County |  | MD | Dorchester | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/4/2011 | 9/30/2011 | Customer Milestone Not Met | 12/31/2012
PJM | X1-032 | Costen 25kV | Somerset Solar Project | MD | Worcester | In Service | DPL | 4 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/16/2011 |  |  | 12/31/2012 | 1/9/2013
PJM | X1-033 | NCEC Sycamore 69/12.47kV |  | OH | Wyandot | Withdrawn | AEP | 12 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/17/2011 | 11/27/2012 | Customer Milestone Not Met | 3/31/2012
PJM | X1-034 | Stoney Brook 12kV | Renaissance at Hanover Solar Farm | NJ | Morris | Withdrawn | JCPL | 1.25 | 0.475 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/22/2011 | 4/9/2013 |  | 12/21/2014
PJM | X1-035 | Piney 34.5kV I |  | PA | Venango | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 3/24/2011 | 5/22/2012 | Customer Milestone Not Met | 12/31/2011
PJM | X1-036 | Piney 34.5kV II |  | PA | Venango | Withdrawn | PENELEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 3/24/2011 | 5/22/2012 | Customer Milestone Not Met | 12/31/2011
PJM | X1-037 | Howell | Howell Solar Farm | NJ | Middlesex | In Service | JCPL | 17 | 6.46 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/28/2011 |  |  | 12/31/2014 | 11/20/2014
PJM | X1-038 | Union Camp 115kV | Franklin Mill Power Facility | VA | City of Franklin | In Service | Dominion | 35 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/29/2011 |  |  | 12/31/2012 | 6/6/2012
PJM | X1-039 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 22.9 | 22.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/29/2011 |  |  | 9/6/2012 | 9/6/2012
PJM | X1-040 | Collingwood-Hiple 345kV |  | IN | DeKalb | Withdrawn | AEP | 360 | 46.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/29/2011 | 3/5/2013 | Customer Initiated Withdrawal | 12/31/2013
PJM | X1-041 | Dumont-Sorensen 345kV |  | IN | Marshall | Withdrawn | AEP | 262 | 32.7 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 3/29/2011 | 5/14/2012 | Customer Milestone Not Met | 12/31/2013
PJM | X1-042 | Watervliet | Orchard Hills | MI | Berrien | In Service | AEP | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/29/2011 |  |  | 11/30/2012 | 3/4/2013
PJM | X1-043 | Cox's Corner 13kV | All American Self Storage | NJ | Burlington | Withdrawn | PSEG | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/30/2011 | 1/10/2013 | Customer Milestone Not Met | 3/31/2012
PJM | X1-044 | Minotola 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/30/2011 | 9/23/2011 | Customer Milestone Not Met | 4/6/2012
PJM | X1-045 | Dresden | Dresden Nuclear Generation Station, Units 2 & 3 | IL | Grundy | In Service | ComEd | 3 | 3 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2011 |  |  | 12/1/2012 | 8/13/2013
PJM | X1-046 | Branchville-N Newton #1 34kV | Morris Solar Farm | NJ | Sussex | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2011 | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | X1-047 | Delaware City 69kV |  | DE | New Castle | Withdrawn | DPL | 40 | 40 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/31/2011 | 12/16/2011 | Customer Initiated Withdrawal | 6/1/2011
PJM | X1-048 | Kenvil 12.5kV |  | NJ | Morris | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/31/2011 | 9/19/2011 |  | 12/31/2012
PJM | X1-049 | Englishtown 12.5kV | Monroe Sun Club | NJ | Middlesex | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2011 | 3/13/2017 | Customer Initiated Withdrawal | 12/31/2014
PJM | X1-050 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/31/2011 | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | X1-051 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/31/2011 | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | X1-052 | Lumberton 69kV |  | NJ | Burlington | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/31/2011 | 9/24/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | X1-053 | Suffolk 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/31/2011 | 9/19/2011 | Customer Milestone Not Met | 12/1/2011
PJM | X1-054 | Burlington 26kV | Mansfield Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2011 | 3/5/2013 | Customer Initiated Withdrawal | 3/31/2013
PJM | X1-055 | Robbinsville |  | NJ | Mercer | Withdrawn | JCPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/31/2011 | 9/8/2011 | Customer Milestone Not Met | 10/1/2011
PJM | X1-058A_DK2 | Todhunter 69kV |  | OH | Butler | Withdrawn | Duke | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/5/2011 | 2/22/2012 | Customer Initiated Withdrawal | 9/1/2012
PJM | X1-064A_AT13 | Barberton-Star 138kV |  | OH | Summit | Withdrawn | ATSI | 268 | 268 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/11/2011 | 1/16/2013 | Customer Initiated Withdrawal | 1/10/2014
PJM | X1-066 | Galloway Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/18/2011 | 7/11/2013 | Customer Initiated Withdrawal | 9/1/2011
PJM | X1-067 | Plymouth |  | NC | Washington | Withdrawn | Dominion | 20 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/19/2011 | 11/21/2012 | Customer Milestone Not Met | 9/30/2013
PJM | X1-068 | Red Oak 230kV | Red Oak | NJ | Middlesex | In Service | JCPL | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/20/2011 |  |  | 4/19/2011 | 12/3/2012
PJM | X1-069 | Frenchtown |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/22/2011 | 10/20/2011 | Customer Milestone Not Met | 6/1/2013
PJM | X1-070 | Levittown 138kV | Mill Creek | NJ | Burlington | In Service | PSEG | 3.5 | 1.33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/25/2011 |  |  | 1/9/2012 | 9/15/2011
PJM | X1-071 | Cinnaminson 138kV | Southern Division Headquarters | NJ | Burlington | In Service | PSEG | 0.93 | 0.35 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/25/2011 |  |  | 10/31/2013 | 10/7/2013
PJM | X1-072 | Hackensack 4kV | Hackensack Solar Farm | NJ | Bergen | In Service | PSEG | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/26/2011 |  |  | 3/31/2013 | 1/11/2013
PJM | X1-073 | Alpha-Gilbert 34kV | Pohatcong II Solar Farm | NJ | Warren | Withdrawn | JCPL | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/27/2011 | 5/3/2016 | Customer Milestone Not Met | 6/30/2015
PJM | X1-074 | Hay Road 230kV | Edge Moor Units EM6, EM7; Hay Road Units 5,6,7,8 | DE | New Castle | Withdrawn | DPL | 291 | 291 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2011 | 11/14/2017 | Customer Initiated Withdrawal | 6/18/2018
PJM | X1-075 | Sussex 12kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/27/2011 | 9/7/2011 | Customer Milestone Not Met | 12/30/2011
PJM | X1-076 | East Greenwich Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 18 | 6.84 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/28/2011 | 10/6/2011 | Customer Milestone Not Met | 12/31/2012
PJM | X1-077 | Wrightstown 34.5kV | Saylos Pond Solar Farm | NJ | Burlington | Withdrawn | JCPL | 0 | 0.78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/28/2011 | 6/22/2016 | Customer Initiated Withdrawal | 9/1/2014
PJM | X1-079 | Baptistown-Frenchtown #2 34kV |  | NJ | Hunterdon | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/28/2011 | 3/5/2012 | Customer Milestone Not Met | 12/31/2012
PJM | X1-080 | Poe-Suffolk 115kV |  | VA | Prince George | Withdrawn | Dominion | 135 | 135 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 4/28/2011 | 6/25/2014 | Customer Milestone Not Met | 6/1/2015
PJM | X1-081 | Andover 12kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/28/2011 | 9/8/2011 | Customer Milestone Not Met | 12/31/2012
PJM | X1-082 | Hazen Switch Point-Warren 34kV | Quarry Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/28/2011 | 4/29/2016 | Customer Milestone Not Met | 12/31/2014
PJM | X1-083 | Salem 12kV |  | NJ | Salem | Withdrawn | AEC | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/28/2011 | 1/17/2012 | Customer Milestone Not Met | 5/1/2012
PJM | X1-084 | Altavista 115kV | Altavista Power Station | VA | Campbell | In Service | Dominion | 60 | 60 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 4/28/2011 |  |  | 12/31/2013 | 5/7/2013
PJM | X1-085 | Hornerstown-Windsor 34kV | Upper Freehold Solar | NJ | Monmouth | In Service | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 |  |  | 2/29/2016 | 5/18/2016
PJM | X1-086 | Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 9.7 | 3.69 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 1/10/2012 | Customer Milestone Not Met | 3/31/2012
PJM | X1-087 | Stillman Valley | Orchard Hills Renewable Energy Station | IL | Ogle | Deactivated | ComEd | 15.3 | 15.3 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/29/2011 |  |  | 10/15/2016 | 11/17/2016
PJM | X1-088 | Franklin #2 | Flemington Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 17 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 | 8/13/2013 | Customer Initiated Withdrawal | 12/31/2012
PJM | X1-089 | Franklin #3 |  | NJ | Warren | Withdrawn | JCPL | 17 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 9/1/2011 | Customer Initiated Withdrawal | 12/31/2012
PJM | X1-090 | Yardville 138kV | BKB Properties | NJ | Mercer | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 | 6/18/2012 | Customer Initiated Withdrawal | 3/31/2012
PJM | X1-091 | Bridgeton 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.91 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 10/6/2011 | Customer Milestone Not Met | 8/31/2012
PJM | X1-092 | Newport 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.91 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 10/6/2011 | Customer Milestone Not Met | 8/31/2012
PJM | X1-093 | Pequest 12kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 9/9/2011 | Customer Milestone Not Met | 1/31/2012
PJM | X1-094 | Flanders-Saxton Fall 34kV | Mount Olive Solar Farm | NJ | Morris | Withdrawn | JCPL | 17 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/29/2011 | 9/18/2015 | Customer Initiated Withdrawal | 12/31/2015
PJM | X1-095 | Bernardsville 12kV | Bernards Township Solar Farm | NJ | Somerset | In Service | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 |  |  | 9/20/2017 | 10/3/2016
PJM | X1-096 | Loretto-Kings Creek 138kV | Great Bay Wind Farm | MD | Somerset | Withdrawn | DPL | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2011 | 6/26/2015 |  | 12/31/2018
PJM | X1-097 | Red Lion 138kV | Red Lion Energy Center | DE | New Castle | In Service | DPL | 24.9 | 23.3 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2011 |  |  | 3/15/2013 | 12/12/2012
PJM | X1-098 | Cook Road 13kV | Montgomery Recycling | NJ | Essex | Withdrawn | PSEG | 0.5 | 0.5 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2011 | 4/2/2014 | Customer Initiated Withdrawal | 3/31/2012
PJM | X1-099 | Woodhill 12kV |  | IL | Will | Withdrawn | ComEd | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2011 | 11/22/2013 | Customer Initiated Withdrawal | 7/1/2012
PJM | X1-100 | Branchville 12kV | Mattison Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 | 3/7/2014 | Customer Initiated Withdrawal | 12/31/2014
PJM | X1-101 | Clinton-Round Valley 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 9/9/2011 | Customer Milestone Not Met | 3/1/2012
PJM | X1-102 | Stewartsville-Captive Plastics 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 9.5 | 3.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 8/29/2011 | Customer Initiated Withdrawal | 3/1/2012
PJM | X1-103 | Branchville-Sussex 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 9/9/2011 | Customer Milestone Not Met | 2/28/2012
PJM | X1-104 | Baptistown-Frenchtown 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2.45 | 0.93 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 9/6/2011 | Customer Milestone Not Met | 2/28/2012
PJM | X1-105 | Branchville-Holiday Lakes 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 11.2 | 4.26 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2011 | 4/25/2012 | Customer Milestone Not Met | 2/28/2012
PJM | X1-106 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 16.8 | 6.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2011 | 4/11/2012 | Customer Milestone Not Met | 1/31/2012
PJM | X1-107 | Hopatcong |  | NJ | Sussex | Withdrawn | JCPL | 2.8 | 1.06 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 9/6/2011 | Customer Initiated Withdrawal | 2/28/2012
PJM | X1-108 | Martins Creek 230kV | Lower Mount Bethel | PA | Northampton | In Service | PPL | 33 | 33 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2011 |  |  | 1/31/2013 | 12/15/2012
PJM | X1-109 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 850 | 765 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2011 |  |  | 2/29/2016 | 3/28/2016
PJM | X1-110 | Lower Township 12kV | Lower Township, NJ | NJ | Cape May | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/29/2011 | 11/23/2015 | Customer Milestone Not Met | 12/1/2014
PJM | X1-111 | Jackson |  | NJ | Ocean | Withdrawn | JCPL | 1.6 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 9/14/2011 | Customer Milestone Not Met | 7/1/2011
PJM | X1-112 | Pennsville 12kV |  | NJ | Salem | Withdrawn | AEC | 20 | 4.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 4/29/2011 | 1/31/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | X1-113 | Lawrence 26kV | Bristol-Myers | NJ | Mercer | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 | 8/25/2012 | Customer Initiated Withdrawal | 12/1/2013
PJM | X1-114 | Holiday Lakes 12kV | Sandyston Solar Farm | NJ | Sussex | Withdrawn | JCPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 | 5/3/2016 | Customer Milestone Not Met | 12/31/2014
PJM | X1-115 | Andover |  | NJ | Sussex | Withdrawn | JCPL | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2011 | 8/18/2011 | Customer Initiated Withdrawal | 3/31/2013
PJM | X1-116 | Branchville-N Newton #2 34kV | Frankford Solar Farm | NJ | Sussex | Withdrawn | JCPL | 7 | 2.66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2011 | 3/17/2015 | Customer Initiated Withdrawal | 12/31/2014
PJM | X1-117 | Hampton |  | NJ | Sussex | Withdrawn | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2011 | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013
PJM | X1-118 | Hampton #2 |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2011 | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013
PJM | X1-119 | Andover #2 |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2011 | 6/7/2011 | Customer Initiated Withdrawal | 3/31/2013
PJM | X2-001 | Howell |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/4/2011 | 2/14/2012 | Customer Milestone Not Met | 5/13/2012
PJM | X2-002 | Somerville 13kV |  | NJ | Somerset | Withdrawn | PSEG | 11.2 | 4.26 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/4/2011 | 11/4/2011 | Customer Initiated Withdrawal | 2/28/2012
PJM | X2-003 | East Rutherford 13kV |  | NJ | Bergen | Withdrawn | PSEG | 2.1 | 0.79 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/4/2011 | 9/14/2011 | Customer Initiated Withdrawal | 2/28/2012
PJM | X2-004 | Cumberland-W. Shore #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/5/2011 | 11/14/2011 | Customer Milestone Not Met | 12/15/2012
PJM | X2-005 | Cumberland-W. Shore #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/5/2011 | 11/14/2011 | Customer Milestone Not Met | 12/15/2012
PJM | X2-006 | Baker 345kV | Riverside Generating Station | KY | Lawrence | In Service | AEP | 0 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 5/6/2011 |  |  | 6/1/2021
PJM | X2-007 | Peckville-Varden 69kV |  | PA | Wayne | Withdrawn | PPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 5/12/2011 | 8/3/2012 | Customer Initiated Withdrawal | 6/30/2012
PJM | X2-008 | Pruntytown 138kV |  | WV | Taylor | Withdrawn | APS | 30 | 30 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 5/16/2011 | 5/17/2012 |  | 12/31/2013
PJM | X2-011 | Fairlawn 138kV | Elmwood | NJ | Bergen | Deactivated | PSEG | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/19/2011 |  |  | 9/30/2012 | 9/28/2012
PJM | X2-012 | Clinton 230kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 850 | 765 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 5/19/2011 |  |  | 7/30/2016 | 7/13/2016
PJM | X2-013 | Thorofare 13kV | Mantua Creek Frequency Regularor | NJ | Gloucester | In Service | PSEG | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 5/19/2011 |  |  | 12/31/2012 | 1/17/2013
PJM | X2-014 | Trenton 26kV | Hedding Road Solar | NJ | Burlington | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/23/2011 | 8/9/2012 | Customer Initiated Withdrawal | 6/30/2013
PJM | X2-015 | Mt. Holly 26kV |  | NJ | Burlington | Withdrawn | PSEG | 2.25 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 5/23/2011 | 1/5/2012 | Customer Milestone Not Met | 10/15/2011
PJM | X2-016 | Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 5/24/2011 | 5/8/2012 | Customer Milestone Not Met | 5/17/2013
PJM | X2-017 | Elk Township 12kV #1 |  | NJ | Gloucester | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 5/24/2011 | 5/8/2012 | Customer Milestone Not Met | 2/28/2013
PJM | X2-018 | Elk Township 12kV #2 |  | NJ | Gloucester | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 5/24/2011 | 5/8/2012 | Customer Milestone Not Met | 2/28/2013
PJM | X2-019 | Silver Lake 345kV |  | IL | Lake | Withdrawn | ComEd | 225 | 180 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/25/2011 | 7/8/2013 | Customer Initiated Withdrawal | 5/31/2015
PJM | X2-020 | Erie East 230 kV |  | PA | Erie | Withdrawn | PENELEC | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 5/26/2011 | 5/25/2012 | Customer Initiated Withdrawal | 10/31/2014
PJM | X2-021 | Erie East 230kV |  | PA | Erie | Withdrawn | PENELEC | 153.75 | 19.98 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/27/2011 | 1/18/2013 | Customer Milestone Not Met | 10/1/2013
PJM | X2-022 | Brokaw-Lanesville | Hilltopper Wind Farm | IL | Logan | In Service | ComEd | 187.5 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/31/2011 |  |  | 5/31/2019 | 11/1/2018
PJM | X2-023 | North Mashoppen-Mehoopany 115kV |  | PA | Sullivan | Withdrawn | PENELEC | 51 | 6.63 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/31/2011 | 1/22/2013 | Customer Milestone Not Met | 10/15/2013
PJM | X2-024 | Lower Alloways Creek 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 5/31/2011 | 1/11/2012 | Customer Milestone Not Met | 11/1/2011
PJM | X2-025 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 416 | 416 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 5/31/2011 |  |  | 3/18/2018 | 3/18/2018
PJM | X2-026 | Leola |  | PA | Lancaster | Withdrawn | PPL | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 5/31/2011 | 7/12/2011 | Customer Initiated Withdrawal | 9/1/2012
PJM | X2-027 | Quinton 12kV | Quinton-Alloway | NJ | Salem | Withdrawn | AEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 5/31/2011 | 12/15/2017 |  | 11/1/2016
PJM | X2-028 | Quinton Township 12kV |  | NJ | Salem | Withdrawn | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 5/31/2011 | 2/20/2014 | Customer Initiated Withdrawal | 3/15/2012
PJM | X2-030 | Morgantown-Oak Grove 230kV |  | MD | Charles | Withdrawn | PEPCO | 830 | 830 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/31/2011 | 2/1/2012 | Customer Milestone Not Met | 1/1/2016
PJM | X2-031 | Krayn 115kV | Highland III Wind Farm | PA | Cambria | Withdrawn | PENELEC | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/31/2011 | 11/29/2016 |  | 12/31/2015
PJM | X2-032 |  |  | NJ | Atlantic | Withdrawn | JCPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/2/2011 | 9/26/2013 | Customer Milestone Not Met
PJM | X2-033 | Trenton 26kV | Ward Avenue Solar | NJ | Burlington | Withdrawn | PSEG | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/3/2011 | 1/4/2013 | Customer Initiated Withdrawal | 6/30/2013
PJM | X2-034 | Laplume |  | PA | Lackawanna | Withdrawn | PPL | 0.032 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 6/3/2011 | 1/18/2012 | Customer Initiated Withdrawal
PJM | X2-035 | Sunnymeade Road 13kV) | Valley Road Solar | NJ | Somerset | Withdrawn | PSEG | 8 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/6/2011 | 10/1/2013 | Customer Milestone Not Met | 7/31/2013
PJM | X2-036 | Whitehouse |  | NJ | Hunterdon | Withdrawn | JCPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/6/2011 | 1/5/2012 | Customer Milestone Not Met | 12/31/2011
PJM | X2-037 | Lewis 138kV |  | NJ | Atlantic | Withdrawn | AEC | 350 | 45.5 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 6/8/2011 | 2/15/2012 | Customer Initiated Withdrawal
PJM | X2-038 | Halfway 12.5kV | Washington County Renewable Energy Project | MD | Washington | Withdrawn | APS | 2 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/10/2011 | 1/14/2016 | Customer Initiated Withdrawal | 10/31/2013
PJM | X2-039 | Brookside-Cloverdale 138kV |  | OH | Ashland | Withdrawn | ATSI | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 6/15/2011 | 12/9/2011 | Customer Milestone Not Met | 12/31/2013
PJM | X2-040 | Wurno 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 6 | 6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Not Required | 6/22/2011 | 3/15/2012 | Customer Milestone Not Met | 6/1/2012
PJM | X2-044 | Winslow 12kV |  | NJ | Camden | Withdrawn | AEC | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/24/2011 | 1/3/2012 | Customer Milestone Not Met | 9/1/2012
PJM | X2-045 | Kenney-Mt. Olive 69kV |  | MD | Worcester | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/27/2011 | 5/21/2012 |  | 6/30/2013
PJM | X2-046 | Sussex County |  | DE | Sussex | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/27/2011 | 5/8/2012 | Customer Milestone Not Met | 1/1/2013
PJM | X2-047 | Oldmans Township 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/28/2011 | 5/10/2012 | Customer Milestone Not Met | 11/30/2011
PJM | X2-048 | South Harrison Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/28/2011 | 5/10/2012 | Customer Milestone Not Met | 11/30/2011
PJM | X2-049 | S. Reading-Birdsboro 64kV |  | PA | Berks | Withdrawn | ME | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted |  |  | 6/28/2011 | 1/3/2012 | Customer Initiated Withdrawal | 3/1/2012
PJM | X2-050 | Essex 230kV |  | NJ | Essex | Withdrawn | PSEG | 705 | 660 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 6/28/2011 | 11/20/2013 | Customer Initiated Withdrawal | 5/31/2016
PJM | X2-051 |  |  | OH | Unknown | Withdrawn | AEP | 6 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/28/2011 | 9/22/2013 | Customer Milestone Not Met
PJM | X2-052 | Dumont-Olive 345kV | St. Joseph Energy Center, LLC | IN | St. Joseph | In Service | AEP | 675 | 675 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 6/29/2011 |  |  | 4/29/2018 | 4/1/2018
PJM | X2-053 | Amsterdam 69kV |  | OH | Jefferson | Withdrawn | AEP | 6.4 | 6.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 6/29/2011 | 5/15/2012 | Customer Milestone Not Met | 1/31/2013
PJM | X2-054 | Franklin | Quakertown Solar Farm #2 | NJ | Hunterdon | Withdrawn | JCPL | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/30/2011 | 7/15/2016 | Customer Initiated Withdrawal | 4/13/2016
PJM | X2-056 | Greenwich 12kV |  | NJ | Cumberland | Withdrawn | AEC | 1.94 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/30/2011 | 1/11/2012 | Customer Milestone Not Met | 12/31/2012
PJM | X2-057 | White |  | NJ | Warren | Withdrawn | JCPL | 4.1 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/30/2011 | 11/21/2011 | Customer Milestone Not Met | 12/31/2012
PJM | X2-058 | Buckley Road 138kV |  | OH | Hancock | Withdrawn | AEP | 149.5 | 19.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 6/30/2011 | 7/10/2013 | Customer Milestone Not Met | 11/15/2012
PJM | X2-059 | Freehold | Cloverleaf Solar Farm | NJ | Monmouth | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/30/2011 | 7/15/2015 | Customer Milestone Not Met | 12/31/2014
PJM | X2-060 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | City of Covington | In Service | Dominion | 30 | 0 | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Document Posted | Document Posted | 6/30/2011 |  |  | 6/1/2014 | 10/15/2013
PJM | X2-061 | Lawrenceville 34.5kV |  | VA | Brunswick | Withdrawn | Dominion | 4 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 6/30/2011 | 12/14/2011 | Customer Initiated Withdrawal | 6/1/2012
PJM | X2-062 | North Hanover |  | NJ | Burlington | Withdrawn | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/30/2011 | 11/18/2011 | Customer Milestone Not Met | 10/30/2012
PJM | X2-066 | S. Harrington-N. Seaford 138kV |  | DE | Sussex | Withdrawn | DPL | 312 | 309 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 7/18/2011 | 1/15/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | X2-067 | Cartanza 230kV |  | DE | Kent | Withdrawn | DPL | 309 | 309 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 7/18/2011 | 2/26/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | X2-068 | Lopatcong |  | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/19/2011 | 11/30/2011 | Customer Milestone Not Met | 5/31/2013
PJM | X2-069 | Swedesboro |  | NJ | Gloucester | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/19/2011 | 1/3/2012 | Customer Milestone Not Met | 5/31/2013
PJM | X2-070 | Hightstown |  | NJ | Mercer | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/19/2011 | 8/15/2011 | Customer Initiated Withdrawal | 5/31/2013
PJM | X2-071 | Beckett |  | NJ | Salem | Withdrawn | AEC | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/19/2011 | 1/3/2012 |  | 5/31/2013
PJM | X2-072 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/19/2011 | 9/22/2013 | Customer Milestone Not Met
PJM | X2-074 | Gibbsboro 12kV |  | NJ | Camden | Withdrawn | AEC | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/25/2011 | 5/8/2012 | Customer Initiated Withdrawal | 9/1/2012
PJM | X2-075 | Flemington | Junction Road Solar Farm | NJ | Hunterdon | In Service | JCPL | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/26/2011 |  |  | 6/12/2017 | 5/19/2016
PJM | X2-076 | Carson-Wake 500kV | Brunswick Combined Cycle Power Station | VA | Brunswick | In Service | Dominion | 1525.5 | 1376 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 7/28/2011 |  |  | 5/1/2016 | 3/7/2016
PJM | X2-077 | Hursch Road 69kV |  | OH | Darke | Withdrawn | Dayton | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/28/2011 | 2/14/2012 | Customer Initiated Withdrawal | 3/31/2013
PJM | X2-078 | Ringoes |  | NJ | Hunterdon | Withdrawn | JCPL | 0.38 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2011 | 5/11/2012 | Customer Milestone Not Met | 12/31/2012
PJM | X2-079 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/28/2011 | 9/27/2013 | Customer Milestone Not Met
PJM | X2-080 |  |  | NJ | Cumberland | Withdrawn | AEC |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/28/2011 | 9/27/2013 | Customer Milestone Not Met
PJM | X2-081 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 1.5 | 0.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/28/2011 | 8/23/2011 | Customer Milestone Not Met | 2/1/2012
PJM | X2-082 | Chesterfield 230kV |  | VA | Chesterfield | Withdrawn | Dominion | 1575 | 1420 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn | Interim Study | 7/28/2011 | 12/5/2012 | Customer Initiated Withdrawal | 12/1/2015
PJM | X2-083 | Newark 12kV | Brookside Energy Center | DE | New Castle | In Service | DPL | 3 | 3 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 7/29/2011 |  |  | 8/15/2012 | 6/21/2012
PJM | X2-084 | East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 19.6 | 7.45 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/29/2011 | 5/10/2012 | Customer Milestone Not Met | 10/1/2012
PJM | X2-085 | Barberton–Seiberling 23kV | Barberton Solar | OH | Summit | Withdrawn | ATSI | 14 | 5.32 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2011 | 6/12/2014 | Customer Initiated Withdrawal | 6/30/2014
PJM | X2-086 | Mt. Storm 115kV |  | WV | Grant | Withdrawn | Dominion | 77 | 74 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2011 | 1/9/2012 | Customer Milestone Not Met | 12/1/2014
PJM | X2-087 | Doremus 13kV | Food Bank Solar | NJ | Union | In Service | PSEG | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2011 |  |  | 9/30/2012 | 8/18/2012
PJM | X2-088 | Devils Brook 13kV | Black Rock Solar | NJ | Middlesex | In Service | PSEG | 2.356 | 0.895 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2011 |  |  | 9/30/2012 | 3/26/2012
PJM | X2-089 | Pierson Avenue 13kV | Summit Associates Solar | NJ | Middlesex | In Service | PSEG | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2011 |  |  | 9/30/2012 | 12/31/2011
PJM | X2-090 | Dewey-Inez 69kV |  | KY | Martin | Withdrawn | AEP | 19 | 11.4 | Capacity | Generation Interconnection | Biomass | Document Posted | Withdrawn |  |  | 7/29/2011 | 1/12/2012 | Customer Milestone Not Met | 8/31/2012
PJM | X2-091 | Hegewisch 34kV |  | IL | Cook | Withdrawn | ComEd | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2011 | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013
PJM | X2-092 | Cornell 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2011 | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013
PJM | X2-093 | Pontiac-Midpoint 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2011 | 7/2/2012 | Customer Initiated Withdrawal | 7/31/2013
PJM | X2-094 | Green Brook 13kV |  | NJ | Middlesex | Withdrawn | PSEG | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/29/2011 | 1/12/2012 | Customer Milestone Not Met | 1/31/2013
PJM | X2-095 | Cape May Court House 12kV |  | NJ | Cape May | Withdrawn | AEC | 1.82 | 0.69 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/29/2011 | 8/23/2011 | Customer Milestone Not Met | 6/1/2012
PJM | X2-096 | Wantage |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/29/2011 | 8/23/2011 | Customer Milestone Not Met | 7/31/2013
PJM | X2-097 | Andover |  | NJ | Sussex | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/29/2011 | 8/23/2011 | Customer Milestone Not Met | 7/31/2013
PJM | X2-098 | Lopatcong #2 |  | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/29/2011 | 8/23/2011 | Customer Milestone Not Met | 7/31/2013
PJM | X2-099 | Sparta-Woodruff's Gap 34kV | Sparta Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/29/2011 | 3/14/2013 | Customer Initiated Withdrawal | 12/31/2014
PJM | X2-100 | Woodstown-Laurel 69kV |  | NJ | Salem | Withdrawn | AEC | 14.4 | 1.87 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/29/2011 | 1/18/2012 | Customer Milestone Not Met | 9/1/2012
PJM | X2-101 | Upper Pittsgrove 138kV |  | NJ | Salem | Withdrawn | AEC | 18 | 2.34 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 7/29/2011 | 1/18/2012 | Customer Milestone Not Met | 9/1/2012
PJM | X3-001 | West Melrose 34.5kV | Edgewood | OH | Hancock | Withdrawn | AEP | 1.82 | 0.69 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/1/2011 | 11/10/2016 | Customer Initiated Withdrawal | 7/15/2014
PJM | X3-002 | Greenville 12kV | Greenville Solar | OH | Darke | Withdrawn | Dayton | 3.38 | 1.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/1/2011 | 9/17/2018 |  | 12/31/2017
PJM | X3-003 | Mehoopany II 115 kV | Mehoopany Plant | PA | Wyoming | In Service | PENELEC | 20 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/3/2011 |  |  | 10/17/2013 | 11/15/2013
PJM | X3-004 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 35 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/8/2011 |  |  | 3/31/2016 | 6/29/2015
PJM | X3-005 | Wildwood 12kV | City Solar | IL | Cook | In Service | ComEd | 9 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/8/2011 |  |  | 6/1/2013 | 9/26/2013
PJM | X3-006 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 150 | 110 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/8/2011 | 2/13/2014 | Customer Milestone Not Met | 6/1/2014
PJM | X3-007 | Bustleton 13kV | LB Solar | NJ | Burlington | Withdrawn | PSEG | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/8/2011 | 1/28/2015 | Customer Milestone Not Met | 9/30/2014
PJM | X3-008 | Todd 69kV | Dorchester County Solar 1 Project | MD | Anne Arundel | In Service | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 8/12/2011 |  |  | 7/31/2021 | 4/8/2021
PJM | X3-009 | New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/12/2011 | 8/24/2012 | Customer Initiated Withdrawal | 6/1/2017
PJM | X3-010 | Franklin #1 |  | NJ | Warren | Withdrawn | JCPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/15/2011 | 3/9/2012 | Customer Initiated Withdrawal | 8/30/2013
PJM | X3-011 | Franklin #2 | Beidelman Solar Farm | NJ | Warren | Withdrawn | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/15/2011 | 7/21/2015 | Customer Initiated Withdrawal | 6/30/2015
PJM | X3-013 | Wildwood Crest 12kV |  | NJ | Cape May | Withdrawn | AEC | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/15/2011 | 3/12/2012 | Customer Initiated Withdrawal | 11/1/2012
PJM | X3-014 | South Harrington-North Seaford 138kV |  | DE | Sussex | Withdrawn | DPL | 300 | 300 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/16/2011 | 4/27/2012 | Customer Milestone Not Met | 6/1/2016
PJM | X3-015 | West Cambridge-Vienna 69kV | Linkwood Solar | MD | Dorchester | Withdrawn | DPL | 19.5 | 7.41 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/22/2011 | 10/10/2017 |  | 9/1/2017
PJM | X3-016 | Carneys Point Township 12kV |  | NJ | Salem | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/23/2011 | 3/13/2012 | Customer Initiated Withdrawal | 12/31/2011
PJM | X3-017 | Elsinboro Township 12kV |  | NJ | Salem | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/29/2011 | 3/14/2012 | Customer Initiated Withdrawal | 11/1/2011
PJM | X3-018 | Vineland 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/29/2011 | 10/11/2011 | Customer Initiated Withdrawal | 11/1/2011
PJM | X3-022 | Hunterstown-Jackson 138kV |  | PA | Adams | Withdrawn | ME | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/29/2011 | 3/22/2012 | Customer Milestone Not Met | 12/31/2014
PJM | X3-023 | S. Greenwich-Willard 69kV | 6011 Greenwich Windpark, LLC | OH | Huron | Withdrawn | AEP | 60 | 7.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 8/29/2011 | 8/5/2016 | Customer Milestone Not Met | 12/31/2017
PJM | X3-024 | Cape May Court House |  | NJ | Cape May | Withdrawn | AEC | 1.82 | 0.69 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/29/2011 | 3/14/2012 | Customer Milestone Not Met | 6/1/2012
PJM | X3-025 | Morris Park 12kV |  | NJ | Warren | Withdrawn | JCPL | 1.82 | 0.69 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/29/2011 | 3/14/2012 | Customer Milestone Not Met | 6/1/2012
PJM | X3-026 | Buena Vista Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/29/2011 | 3/12/2012 | Customer Milestone Not Met | 12/31/2012
PJM | X3-027 | Ocean |  | NJ | Ocean | Withdrawn | AEC | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/29/2011 | 5/2/2012 | Customer Milestone Not Met | 12/31/2012
PJM | X3-029 | Belvidere | CHP Belvidere Generation Facility | NJ | Warren | In Service | JCPL | 11.15 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/30/2011 |  |  | 12/31/2013 | 12/17/2013
PJM | X3-030 | Shelby-S.W. Lima 345kV |  | OH | Marion | Withdrawn | Dayton | 245 | 31.85 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/30/2011 | 5/30/2013 | Customer Initiated Withdrawal | 12/31/2015
PJM | X3-031 | Southwest Lima-West Moulton 138kV |  | OH | Allen | Withdrawn | AEP | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/30/2011 | 5/31/2013 | Customer Initiated Withdrawal | 9/30/2015
PJM | X3-032 | Poe-Suffolk 115kV |  | VA | Prince George | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 8/31/2011 | 6/25/2014 | Customer Milestone Not Met | 6/1/2015
PJM | X3-033 | Green |  | NJ | Sussex | Withdrawn | JCPL | 16 | 6.08 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2011 | 2/7/2012 | Customer Initiated Withdrawal | 5/1/2013
PJM | X3-034 | Hunterstown-Jackson 130kV |  | PA | Washington | Withdrawn | APS | 20 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/31/2011 | 9/27/2012 | Customer Milestone Not Met | 8/1/2012
PJM | X3-035 | Mansfield |  | NJ | Warren | Withdrawn | JCPL | 5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2011 | 3/23/2012 | Customer Milestone Not Met | 7/4/2012
PJM | X3-036 | William 138kV |  | WV | Grant | Withdrawn | APS | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/31/2011 | 3/22/2012 | Customer Milestone Not Met | 12/31/2012
PJM | X3-038 | Manchester |  | NJ | Ocean | Withdrawn | JCPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2011 | 2/10/2012 | Customer Milestone Not Met | 9/30/2013
PJM | X3-039 | Geneva 115kV |  | PA | Crawford | Withdrawn | PENELEC | 96 | 96 | Capacity | Generation Interconnection | Other | Document Posted | Document Posted | Withdrawn |  | 8/31/2011 | 6/19/2013 | Customer Initiated Withdrawal | 7/7/2014
PJM | X3-040 | Weirwood-Eastville 69kV |  | VA | Northampton | Withdrawn | ODEC | 18 | 0 | Energy | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/31/2011 | 8/13/2014 | Customer Initiated Withdrawal | 6/30/2016
PJM | X3-041 | Milton | Milton | DE | Sussex | Withdrawn | DPL | 14.9 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2011 | 12/19/2014 | Customer Initiated Withdrawal | 9/2/2018
PJM | X3-042 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/2/2011 | 9/29/2011
PJM | X3-043 | Lumberton 69kV | Warfield I | NJ | Burlington | Withdrawn | AEC | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/12/2011 | 1/5/2015 | Customer Initiated Withdrawal | 10/15/2015
PJM | X3-044 | Three Mile Island |  | PA | Dauphin | Withdrawn | ME | 15 | 15 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Withdrawn | 9/14/2011 | 7/16/2014 | Customer Initiated Withdrawal | 6/30/2013
PJM | X3-045 | Dresden |  | IL | Grundy | Withdrawn | ComEd | 32 | 32 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 9/14/2011 | 3/4/2013 | Customer Initiated Withdrawal | 6/1/2014
PJM | X3-046 | Quad Cities |  | IL | Rock Island | Withdrawn | ComEd | 32 | 32 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 9/14/2011 | 3/4/2013 | Customer Initiated Withdrawal | 6/1/2014
PJM | X3-047 | Bayview 25kV |  | VA | Northampton | Withdrawn | ODEC | 5 | 0.65 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Withdrawn |  |  | 9/26/2011 | 4/12/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | X3-051 | Flatlick 765kV |  | OH | Unknown | Withdrawn | AEP | 610 | 610 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 9/27/2011 | 5/23/2016 | Customer Milestone Not Met | 3/1/2017
PJM | X3-052 | Essex 26.4kV | Essex County Correctional Facility | NJ | Essex | In Service | PSEG | 3 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/28/2011 |  |  | 5/31/2013 | 9/10/2014
PJM | X3-053 | Homer-Seville 69kV |  | OH | Medina | Withdrawn | ATSI | 17.68 | 6.72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/29/2011 | 8/2/2012 | Customer Milestone Not Met | 7/1/2013
PJM | X3-054 | Sussex | Hough Solar Farm | NJ | Sussex | Withdrawn | JCPL | 4.9 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/29/2011 | 11/13/2013 | Customer Milestone Not Met | 6/30/2015
PJM | X3-055 | Occoquan 34.5kV |  | VA | Fairfax | Withdrawn | Dominion | 10 | 0 | Energy | Generation Interconnection | Diesel | Withdrawn |  |  |  | 9/29/2011 | 11/14/2011 | Queue Not Required | 2/28/2013
PJM | X3-056 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 50 | 0 | Energy | Generation Interconnection | Nuclear | Document Posted | Document Posted | Withdrawn |  | 9/30/2011 | 9/13/2013 | Customer Initiated Withdrawal | 10/31/2011
PJM | X3-057 | Susquehanna 230kV |  | PA | Luzerne | Withdrawn | PPL | 50 | 0 | Energy | Generation Interconnection | Nuclear | Document Posted | Document Posted | Withdrawn |  | 9/30/2011 | 9/13/2013 | Customer Initiated Withdrawal | 10/31/2011
PJM | X3-059 | Roberts 34.5kV |  | OH | Marion | Withdrawn | ATSI | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/10/2011 | 10/16/2012 | Customer Initiated Withdrawal | 9/1/2012
PJM | X3-060 | Fairfield Twp 1 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/10/2011 | 11/2/2011 | Customer Initiated Withdrawal | 9/30/2012
PJM | X3-061 | Fairfield Twp 2 12kV |  | NJ | Cumberland | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/10/2011 | 11/2/2011 | Customer Initiated Withdrawal | 9/30/2012
PJM | X3-062 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/11/2011 | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012
PJM | X3-066 | Church Hill 69kV | Church Hill Solar Farm | MD | Queen Anne's | In Service | DPL | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/13/2011 |  |  | 9/1/2015 | 5/19/2016
PJM | X3-067 | Church Hill 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/13/2011 | 2/29/2012 | Customer Initiated Withdrawal | 9/30/2012
PJM | X3-068 | Graceton 230kV |  | PA | York | Withdrawn | BGE | 678 | 678 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/14/2011 | 6/4/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | X3-069 | Hamilton |  | NJ | Atlantic | Withdrawn | JCPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/19/2011 | 11/4/2011
PJM | X3-070 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/28/2011 |  |  | 6/1/2014 | 12/12/2013
PJM | X3-071 | Sussex County 12kV | Burbage Property | DE | Sussex | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/28/2011 | 11/12/2013 | Customer Milestone Not Met | 10/31/2018
PJM | X3-072 | Lafayette |  | NJ | Sussex | Withdrawn | JCPL | 10.5 | 3.99 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/28/2011 | 3/7/2012 | Customer Milestone Not Met | 3/1/2013
PJM | X3-073 | Massey 69kV |  | MD | Kent | Withdrawn | DPL | 9.8 | 3.72 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/28/2011 | 3/12/2012 | Customer Milestone Not Met | 3/31/2013
PJM | X3-074 | Chestertown 69kV |  | MD | Kent | Withdrawn | DPL | 11.9 | 4.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/28/2011 | 8/15/2012 | Customer Initiated Withdrawal | 3/31/2013
PJM | X3-075 | Runnemede 13kV | Owens Corning Solar | NJ | Camden | In Service | PSEG | 3 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/28/2011 |  |  | 2/16/2017 | 5/11/2017
PJM | X3-076 | Loudoun-Meadowbrook 500kV |  | VA | Fauquier | Withdrawn | Dominion | 510 | 412 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/28/2011 | 6/7/2013 | Customer Initiated Withdrawal | 5/1/2015
PJM | X3-077 | Sussex County 12kV | Baxter Property | DE | Sussex | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2011 | 11/12/2013 | Customer Milestone Not Met | 10/31/2018
PJM | X3-078 | Harrisburg 12kV |  | PA | Dauphin | Withdrawn | PPL | 4 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2011 | 4/11/2012 | Customer Initiated Withdrawal | 8/15/2014
PJM | X3-079 | Oyster Creek-Waretown 34kV | Volunteer Way Solar Farm | NJ | Ocean | Withdrawn | JCPL | 16 | 6.08 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2011 | 12/21/2012 |  | 6/30/2015
PJM | X3-080 | Fairton Township |  | NJ | Cumberland | Withdrawn | AEC | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/31/2011 | 3/13/2012 | Customer Initiated Withdrawal | 12/31/2012
PJM | X3-081 | Upper Darby 13kV | Astra Foods | PA | Delaware | Withdrawn | PECO | 0.5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2011 | 8/27/2018 |  | 12/30/2012
PJM | X3-082 | Marble Hill-Morris Park 34kV | Lopatcong Solar Farm | NJ | Warren | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2011 | 4/29/2016 | Customer Milestone Not Met | 6/30/2015
PJM | X3-083 | Andover-Kittatinny 34kV | Andover Solar Farm | NJ | Sussex | Withdrawn | JCPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2011 | 4/29/2016 | Customer Milestone Not Met | 12/31/2015
PJM | X3-084 | Wantage |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2011 | 3/9/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | X3-085 | Sussex 34kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2011 | 2/27/2013 | Customer Milestone Not Met | 12/31/2013
PJM | X3-086 | Lafayette |  | NJ | Sussex | Withdrawn | JCPL | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2011 | 11/17/2011 | Customer Initiated Withdrawal | 12/31/2013
PJM | X3-087 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Withdrawn | PEPCO | 894 | 744 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2011 | 12/23/2020 |  | 3/1/2022
PJM | X3-088 | Dickerson 230kV |  | MD | Montgomery | Withdrawn | PEPCO | 440 | 440 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/31/2011 | 6/21/2012 | Customer Milestone Not Met | 12/31/2016
PJM | X3-089 | Sayreville 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 744 | 744 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/31/2011 | 5/3/2012 | Customer Milestone Not Met | 12/31/2016
PJM | X3-102 | Burches Hill-Possum Point 500kV |  | MD | Charles | Withdrawn | PEPCO | 971.2 | 937 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/31/2011 | 6/20/2012 | Customer Milestone Not Met | 6/1/2016
PJM | X3-103 | Oakgrove-Morgantown 230kV |  | MD | Charles | Withdrawn | PEPCO | 971.2 | 971.2 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/31/2011 | 11/18/2011 | Queue Not Required | 6/1/2016
PJM | X4-001 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 11/2/2011 | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012
PJM | X4-002 | St. Thomas-Guilford 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 11/2/2011 | 8/16/2013 | Customer Initiated Withdrawal | 12/31/2012
PJM | X4-003 | Mill Creek-Riverview 138kV |  | OH | Washington | Withdrawn | AEP | 56 | 56 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/2/2011 | 11/26/2012 | Customer Initiated Withdrawal | 3/31/2015
PJM | X4-004 | Woodbury 26.4kV | Johnson Matthey | NJ | Gloucester | Withdrawn | PSEG | 5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/2/2011 | 6/7/2016 | Customer Initiated Withdrawal | 12/31/2012
PJM | X4-005 | Raritan River 230kV |  | NJ | Middlesex | In Service | JCPL | 60 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Not Required | Document Posted | Document Posted | 11/3/2011 |  |  | 6/1/2017 | 12/4/2015
PJM | X4-006 | Kelson Ridge 230kV | St. Charles Combined Cycle Facility | MD | Charles | In Service | PEPCO | 60 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/3/2011 |  |  | 11/1/2016 | 1/28/2017
PJM | X4-007 | Kelson Ridge 230kV |  | MD | Charles | Withdrawn | PEPCO | 60 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/3/2011 | 7/31/2013 | Customer Milestone Not Met | 6/1/2015
PJM | X4-009 | Cumberland - W. Shore #1 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 11/17/2011 | 7/1/2013 | Customer Initiated Withdrawal | 7/1/2014
PJM | X4-010 | Cumberland - W. Shore #2 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 11/17/2011 | 5/29/2012 | Customer Initiated Withdrawal | 12/15/2012
PJM | X4-011 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 11/17/2011 | 8/16/2013 | Customer Initiated Withdrawal | 12/15/2012
PJM | X4-012 | Branchville-Sussex 34kV | Plains Road Solar Farm | NJ | Sussex | Withdrawn | JCPL | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/21/2011 | 3/17/2015 | Customer Initiated Withdrawal | 9/30/2015
PJM | X4-014 | Kellam - Bayview 69kV |  | VA | Northampton | Withdrawn | ODEC | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 11/28/2011 | 7/3/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | X4-015 | Cookstown-Fort Dix 34kV | Jacobstown III Solar Farm | NJ | Burlington | In Service | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/28/2011 |  |  | 9/30/2015 | 9/28/2015
PJM | X4-016 | Bayonne 138kV | Bayonne Cogen | NJ | Hudson | Deactivated | PSEG | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/29/2011 |  |  | 9/30/2013 | 9/30/2013
PJM | X4-017 | Fruitland 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 11/30/2011 | 7/24/2013 | Customer Initiated Withdrawal | 6/1/2017
PJM | X4-018 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 110 | 110 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/2011 | 6/5/2012 | Customer Initiated Withdrawal | 5/31/2015
PJM | X4-019 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 227 | 227 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/30/2011 |  |  | 3/18/2018 | 3/18/2018
PJM | X4-020 | Peach Bottom-TMI #1 500kV I |  | PA | York | Withdrawn | PPL | 800 | 760 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/30/2011 | 5/12/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | X4-021 | Peach Bottom-TMI #2 500kV II |  | PA | York | Withdrawn | PPL | 320 | 304 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 11/30/2011 | 5/12/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | X4-025 | Millbrook Park 138kV |  | KY | Greenup | Withdrawn | AEP | 80 | 80 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Document Posted | Document Posted | 11/30/2011 | 9/18/2017 |  | 12/31/2018
PJM | X4-026 | Aquasco 230kV |  | MD | Prince George's | Withdrawn | PEPCO | 792 | 650 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/30/2011 | 8/2/2012 | Customer Initiated Withdrawal | 6/1/2015
PJM | X4-027 | Linwood 230kV | Phillips Island CT1, CT2,CT3 & ST4 | PA | Delaware | In Service | PECO | 12 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/8/2011 |  |  | 5/31/2018 | 6/1/2018
PJM | X4-028 | Northerly Island |  | IL | Cook | Withdrawn | ComEd | 0.103 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Withdrawn | 12/13/2011 | 8/30/2012 | Customer Milestone Not Met | 12/12/2011
PJM | X4-029 | Upper Deerfield 12kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/23/2011 | 6/8/2012 | Customer Initiated Withdrawal | 1/2/2013
PJM | X4-030 | Freemont 69kV |  | OH | Sandusky | Withdrawn | AEP | 13.75 | 5.23 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/30/2011 | 8/27/2012 | Customer Milestone Not Met | 4/1/2013
PJM | X4-031 | Bennett-Farmingdale 34kV | Skudera Solar Farm | NJ | Monmouth | In Service | JCPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/30/2011 |  |  | 9/30/2015 | 6/17/2015
PJM | X4-032 | Zach |  | PA | Montgomery | Withdrawn | PECO | 4 | 4 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Withdrawn |  | 12/30/2011 | 12/31/2012 | Customer Milestone Not Met | 5/1/2012
PJM | X4-034 | Dravosburg–Rankin 23kV |  | PA | Allegheny | Withdrawn | DL | 5 | 0 | Energy | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Withdrawn | 1/19/2012 | 11/16/2012 |  | 8/31/2013
PJM | X4-035 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | In Service | PEPCO | 735.5 | 735.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/20/2012 |  |  | 6/15/2018 | 5/21/2018
PJM | X4-039 | Pleasant View-Brambleton 230kV | Stonewall Energy Park | VA | Loudoun | In Service | Dominion | 800 | 750 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/30/2012 |  |  | 10/1/2017 | 4/28/2017
PJM | X4-040 | Sussex County 12kV |  | DE | Sussex | Withdrawn | DPL | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/30/2012 | 12/8/2014 | Customer Initiated Withdrawal | 9/30/2015
PJM | X4-042 | Footedale 12kV |  | PA | Fayette | Withdrawn | APS | 3 | 3 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 1/31/2012 | 7/17/2013 | Customer Milestone Not Met | 5/31/2013
PJM | X4-043 | Clinton | Allerton Road Solar Farm | NJ | Hunterdon | Withdrawn | JCPL | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2012 | 9/19/2012 | Customer Initiated Withdrawal | 6/30/2015
PJM | X4-044 | Aldene 230kV | EF Kenilworth LLC | NJ | Union | In Service | PSEG | 17.9 | 9.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/31/2012 |  |  | 5/1/2015 | 6/11/2015
PJM | X4-045 | Southwark 13kV |  | PA | Philadelphia | Withdrawn | PECO | 0.5 | 0.07 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/31/2012 | 4/29/2013 | Customer Initiated Withdrawal | 5/1/2012
PJM | X4-046 | E Street (Sub 18) 13kV |  | DC |  | In Service | PEPCO | 19.5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2012 |  |  | 9/1/2015 | 2/4/2019
PJM | X4-047 | Phillipsburg |  | NJ | Warren | Withdrawn | JCPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/31/2012 | 5/30/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | X4-048 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 1000 | 1000 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2012 |  |  | 12/31/2018 | 3/8/2018
PJM | Y1-001 | BL England 138kV | B.L. England Station | NJ | Cape May | Withdrawn | AEC | 452 | 447 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/3/2012 | 12/18/2019 |  | 6/1/2021
PJM | Y1-003 | Deep Creek-Penn Mar 115kV | Winding Ridge Wind Farm | MD | Garrett | Withdrawn | APS | 60 | 7.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/7/2012 | 1/25/2017 |  | 10/31/2017
PJM | Y1-005 | LaSalle |  | IL | Lasalle | Withdrawn | ComEd | 350 | 350 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 2/13/2012 | 10/1/2013 | Customer Milestone Not Met | 4/10/2016
PJM | Y1-006 | Jubal Early-Austinville 138kV | Poplar Camp | VA | Carroll | Withdrawn | AEP | 72 | 9.36 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/14/2012 | 10/17/2021 |  | 3/1/2023
PJM | Y1-008 | Tasley-Kellam 69kV |  | VA | Accomack | Withdrawn | ODEC | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/17/2012 | 3/26/2013 | Customer Initiated Withdrawal | 12/31/2014
PJM | Y1-009 | Yardville 13kV |  | NJ | Mercer | Withdrawn | PSEG | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/21/2012 | 9/26/2012 | Customer Milestone Not Met | 11/30/2012
PJM | Y1-010 | Quinton 12kV |  | NJ | Salem | Withdrawn | AEC | 1.9 | 1.9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Withdrawn |  | 2/21/2012 | 9/12/2012 | Customer Milestone Not Met | 5/17/2012
PJM | Y1-011 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 520 | 520 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/23/2012 | 9/11/2012 | Customer Initiated Withdrawal | 6/1/2016
PJM | Y1-012 | Geneva | Geneva Renewable Energy Facility | OH | Ashtabula | In Service | ATSI | 6.48 | 6.48 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/23/2012 |  |  | 8/1/2013 | 7/22/2013
PJM | Y1-013 | McAlpin 12kV |  | WV | Harrison | Withdrawn | APS | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 2/23/2012 | 3/28/2012 | Customer Initiated Withdrawal | 9/9/2013
PJM | Y1-014 | Worton 12kV |  | MD | Kent | Withdrawn | DPL | 1.6 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/24/2012 | 8/17/2012 | Customer Initiated Withdrawal | 6/15/2012
PJM | Y1-015 | Shenango-Hoytdale 345kV |  | PA | Lawrence | Withdrawn | ATSI | 1000 | 870 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 2/24/2012 | 7/29/2014 | Customer Initiated Withdrawal | 6/1/2015
PJM | Y1-016 | Baker-Hardy 138kV |  | WV | Hardy | Withdrawn | APS | 50 | 6.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/28/2012 | 4/4/2013 | Customer Milestone Not Met | 12/31/2015
PJM | Y1-017 | Tabernacle |  | NJ | Burlington | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/28/2012 | 8/27/2012 | Customer Initiated Withdrawal | 12/31/2013
PJM | Y1-018 | Conesville #5 | Conesville #5 | OH | Muskingum | Deactivated | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2012 |  |  | 6/1/2013 | 6/1/2013
PJM | Y1-019 | Conesville #6 | Conesville #6 | OH | Muskingum | Deactivated | AEP | 5 | 5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2012 |  |  | 6/1/2013 | 6/1/2013
PJM | Y1-020 | Sussex 34kV | Beaver Run Solar Farm | NJ | Sussex | In Service | JCPL | 0 | 3.72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/28/2012 |  |  | 9/30/2015 | 1/22/2016
PJM | Y1-022 | Cooper |  | PA | York | Withdrawn | PECO | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/28/2012 | 6/21/2013 | Customer Initiated Withdrawal | 10/21/2013
PJM | Y1-023 | Felicity 69kV |  | OH | Unknown | Withdrawn | Duke | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/28/2012 | 10/17/2012 | Customer Initiated Withdrawal | 10/22/2013
PJM | Y1-024 | Felicity 12.5kV |  | OH | Unknown | Withdrawn | Duke | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/28/2012 | 10/17/2012 | Customer Initiated Withdrawal | 10/22/2013
PJM | Y1-025 | Raritan River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 785 | 725 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/29/2012 | 6/4/2013 | Customer Initiated Withdrawal | 5/15/2015
PJM | Y1-026 | Tosco 230kV | Tosco #6 | NJ | Union | In Service | PSEG | 0 | 160 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/29/2012 |  |  | 3/1/2012 | 6/1/2018
PJM | Y1-027 | Belmon 12.5kV | Westmoreland Landfill Gas Plant | PA | Fayette | Withdrawn | APS | 4 | 1.52 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/29/2012 | 7/11/2016 |  | 12/31/2016
PJM | Y1-028 | Lewis Run 115kV |  | PA | McKean | Withdrawn | PENELEC | 125 | 16.25 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/29/2012 | 10/19/2012 | Customer Milestone Not Met | 12/1/2014
PJM | Y1-029 | Waynesboro-Dooms 115kV |  | VA | Accomack | Withdrawn | Dominion | 99 | 12.9 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/29/2012 | 8/29/2012 | Customer Initiated Withdrawal | 9/15/2014
PJM | Y1-030 | Forest 69kV |  | OH | Wyandot | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 2/29/2012 | 2/18/2015 | Customer Initiated Withdrawal | 12/31/2015
PJM | Y1-031 | Erie East 230kV |  | PA | Clarion | Withdrawn | PENELEC | 101.47 | 13.19 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/29/2012 | 3/13/2013 | Customer Initiated Withdrawal | 6/1/2013
PJM | Y1-032 | Potter-Gold 115kV |  | PA | Potter | Withdrawn | PENELEC | 99 | 12.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/29/2012 | 5/8/2013 | Customer Milestone Not Met | 12/31/2016
PJM | Y1-033 | Penn Mar-Rock Wood 115kV |  | PA | Somerset | In Service | PENELEC | 38.3 | 4.98 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/29/2012 |  |  | 3/27/2017 | 12/14/2016
PJM | Y1-034 | Everson 23kV | Purdys Run Plant | WV | Harrison | Withdrawn | APS | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/29/2012 | 6/7/2016 | Customer Initiated Withdrawal | 1/1/2015
PJM | Y1-035 | Eastlake 138kV |  | OH | Lake | Withdrawn | ATSI | 462 | 462 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 3/8/2012 | 7/23/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | Y1-036 | Eastlake 345kV |  | OH | Lake | Withdrawn | ATSI | 462 | 462 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 3/8/2012 | 7/23/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | Y1-037 |  |  | NJ | Unknown | Withdrawn | JCPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/15/2012 | 4/4/2012 | Customer Milestone Not Met
PJM | Y1-038 | Sparta |  | NJ | Sussex | Withdrawn | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/19/2012 | 8/28/2012 | Customer Milestone Not Met | 8/31/2013
PJM | Y1-039 | Kings Creek 69kV |  | MD | Somerset | Withdrawn | DPL | 5.2 | 0 | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 3/23/2012 | 9/12/2012 | Customer Milestone Not Met | 10/1/2013
PJM | Y1-039A_EKPC1 | JK Smith 138 KV |  | KY | Clark | Withdrawn | EKPC | 170 | 170 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/23/2012 | 7/16/2013 | Customer Initiated Withdrawal | 6/1/2016
PJM | Y1-042 | Vineland 12kV |  | NJ | Cumberland | Withdrawn | AEC | 3.5 | 1.33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/30/2012 | 8/28/2012 | Customer Initiated Withdrawal | 9/1/2014
PJM | Y1-043 | Mackeys-Creswell 115kV |  | NC | Washington | Withdrawn | Dominion | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/30/2012 | 3/26/2013 | Customer Initiated Withdrawal | 5/31/2015
PJM | Y1-044 | Belmont 138kV | Willow Island Hydro Generation Project | WV | Pleasants | In Service | APS | 6.8 | 6.8 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 3/30/2012 |  |  | 7/31/2015 | 11/15/2015
PJM | Y1-045 | Friendship Manor |  | MD | Howard | Withdrawn | BGE | 2 | 0 | Energy | Generation Interconnection | Solar | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 3/30/2012 | 8/16/2018 |  | 9/1/2017
PJM | Y1-046 | New Prospect Road 12kV |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 3.04 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2012 | 6/18/2012 | Customer Initiated Withdrawal | 3/13/2013
PJM | Y1-047 | North Meshoppen 34.5kV | Roundtop Energy Project | PA | Wyoming | In Service | PENELEC | 15.4 | 15.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2012 |  |  | 4/1/2015 | 10/15/2015
PJM | Y1-048 | Four Rivers 115kV | Four Rivers NUG CC-1 | VA | Hanover | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/2/2012 | 1/10/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Y1-049 | Wurno 34.5kV | New River Resource Authority Waste Management Facility IRD LEG-E | VA | Pulaski | In Service | AEP | 6 | 6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 4/6/2012 |  |  | 3/31/2013 | 12/1/2014
PJM | Y1-054 | Rochelle 138kV | Rochelle Plant | OH | Hamilton | In Service | DEOK | 20 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/16/2012 |  |  | 5/1/2013 | 5/30/2013
PJM | Y1-055 | Brick-Lanes Mill 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/16/2012 | 8/10/2012 | Customer Milestone Not Met | 6/30/2015
PJM | Y1-056 | TMI |  | PA | York | Withdrawn | ME | 19 | 19 | Capacity | Generation Interconnection | Nuclear | Document Posted | Withdrawn |  |  | 4/16/2012 | 6/10/2013 | Customer Initiated Withdrawal | 6/30/2013
PJM | Y1-057 | Barbadoes 34kV | Barbadoes Energy Storage Unit | PA | Montgomery | Deactivated | PECO | 1 | 0.1 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/25/2012 |  |  | 12/1/2013 | 9/30/2013
PJM | Y1-060 | Aulander 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 15 | 7.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/25/2012 | 1/18/2013 | Customer Milestone Not Met | 12/31/2013
PJM | Y1-063 | Trenton 34.5kV |  | OH | Delaware | In Service | AEP | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/27/2012 |  |  | 3/31/2014 | 3/31/2014
PJM | Y1-064 | Berkshire 34.5kV | Berkshire 3.4kV | OH | Delaware | Withdrawn | AEP | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/27/2012 | 10/31/2013 | Customer Initiated Withdrawal | 3/31/2015
PJM | Y1-065 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 834.1 | 805 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2012 |  |  | 9/21/2017 | 7/26/2017
PJM | Y1-066 | Four Rivers 115kV | Four Rivers NUG CC-1 | VA | Hanover | In Service | Dominion | 0 | 13.3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2012 |  |  | 6/1/2016 | 9/1/2013
PJM | Y1-067 | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 64.6 | 8.4 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 4/27/2012 | 11/30/2012 | Customer Milestone Not Met | 11/1/2013
PJM | Y1-068 | East Mill 138kV | MeadWestvaco Covington Mill Site | VA | Unknown | In Service | Dominion | 20 | 0 | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2012 |  |  | 6/1/2014 | 10/15/2013
PJM | Y1-069 | Bay Shore-Fostoria Central 345kV & Bayshore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 799 | 799 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2012 |  |  | 5/15/2017 | 6/23/2017
PJM | Y1-070 | Shenango-Hoytdale 345kV |  | PA | Lawrence | Withdrawn | ATSI | 825 | 825 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/30/2012 | 4/24/2013 | Customer Initiated Withdrawal | 6/1/2017
PJM | Y1-071 | Burma 25kV | Kelly Generation Facility | PA | Lawrence | Withdrawn | APS | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2012 | 3/10/2017 | Customer Initiated Withdrawal | 6/1/2015
PJM | Y1-072 | Glen Gardner 12kV | Lebanon Solar | NJ | Hunterdon | In Service | JCPL | 0 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2012 |  |  | 12/23/2011 | 5/30/2013
PJM | Y1-073 | Riders Creek |  | NC | Tyrell | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2012 | 9/4/2012 | Customer Milestone Not Met | 12/31/2016
PJM | Y1-074 | Martin 12kV |  | OH | Summit | Withdrawn | ATSI | 7.8 | 2.96 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2012 | 2/25/2013 | Customer Initiated Withdrawal | 11/1/2013
PJM | Y1-075 | Medford 13kV | Reeve's Station South | NJ | Burlington | In Service | PSEG | 1 | 0.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2012 |  |  | 12/31/2013 | 12/19/2013
PJM | Y1-076 | BL England 138kV |  | NJ | Cape May | Withdrawn | AEC | 18.1 | 18.1 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/30/2012 | 5/29/2012 |  | 6/1/2015
PJM | Y1-077 | BL England 138kV | Cape May Energy Center (CMEC) | NJ | Cape May | Withdrawn | AEC | 34 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2012 | 12/18/2019 |  | 6/1/2021
PJM | Y1-078 | Crawford 138kV |  | IL | Cook | Withdrawn | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 4/30/2012 | 2/7/2014 | Customer Initiated Withdrawal | 12/31/2012
PJM | Y1-079 | Wye Mills 69kV | Wye Mills Solar Site | MD | Talbot | In Service | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/30/2012 |  |  | 7/29/2016 | 8/24/2016
PJM | Y1-080 | Dorchester 12kV | Constellation Solar Maryland II, LLC Solar Facility | MD | Dorchester | In Service | DPL | 3.38 | 1.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2012 |  |  | 4/30/2015 | 4/30/2015
PJM | Y1-081 | Wye Mills 12kV |  | MD | Talbot | Withdrawn | DPL | 3.38 | 1.28 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2012 | 9/10/2012 | Customer Initiated Withdrawal | 11/1/2013
PJM | Y1-084 | East Newton–Blairstown 34.5kV | Fredon Solar Farm | NJ | Sussex | Withdrawn | JCPL | 1.99 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2012 | 5/16/2017 |  | 5/30/2015
PJM | Y1-085 | Kings Creek 25kV |  | MD | Somerset | Withdrawn | DPL | 4.4 | 0 | Energy | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 4/30/2012 | 10/4/2012 | Customer Milestone Not Met | 12/31/2013
PJM | Y1-086 | Morgans Corner | Morgan's Corner Solar | NC | Pasquotank | In Service | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2012 |  |  | 1/30/2016 | 12/26/2015
PJM | Y1-087 | New Hope |  | MD | Wicomico | Withdrawn | DPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2012 | 9/6/2012 | Customer Initiated Withdrawal | 12/31/2016
PJM | Y2-001 | Gosport | SPSA Navy Power Plant | VA | City of Portsmouth | In Service | Dominion | 3.8 | 40 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 5/2/2012 |  |  | 6/1/2014 | 5/22/2014
PJM | Y2-002 |  |  | PA | Adams | Withdrawn | PPL |  |  | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 5/8/2012 | 5/24/2012 | Customer Milestone Not Met
PJM | Y2-003 | Chicago Battery |  | IL | Unknown | Withdrawn | ComEd | 0.6 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 5/16/2012 | 3/28/2016 | Customer Milestone Not Met | 8/31/2014
PJM | Y2-010 | Olive-Meadow Lake 345kV |  | IN | White | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 5/23/2012 | 2/6/2014 | Customer Initiated Withdrawal | 12/31/2015
PJM | Y2-011 | Brunot Island I 138kV |  | PA | Allegheny | Withdrawn | DL | 20 | 15 | Capacity | Generation Interconnection | Oil | Withdrawn | Not Required | Not Required | Not Required | 5/24/2012 | 5/12/2014 | Customer Initiated Withdrawal | 11/1/2015
PJM | Y2-012 | Brunot Island II 138kV |  | PA | Allegheny | Withdrawn | DL | 20 | 15 | Capacity | Generation Interconnection | Oil | Withdrawn | Not Required | Not Required | Not Required | 5/24/2012 | 5/12/2014 | Customer Initiated Withdrawal | 11/1/2015
PJM | Y2-013 | Linden VFT-Tosco 230kV |  | NJ | Union | Withdrawn | PSEG | 800 | 800 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/30/2012 | 5/20/2013 | Customer Initiated Withdrawal | 5/1/2017
PJM | Y2-015 | Eldred-Frackville #1 230kV |  | PA | Schuylkill | Withdrawn | PPL | 344 | 337 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 5/31/2012 | 10/2/2017 |  | 12/31/2018
PJM | Y2-016 |  |  | PA | Adams | Withdrawn | PENELEC |  |  | Energy | Generation Interconnection | Wind | Withdrawn |  |  |  | 6/6/2012 | 6/12/2012 | Customer Initiated Withdrawal
PJM | Y2-018 | Pequest River 34.5kV | Warren County Landfill | NJ | Warren | In Service | JCPL | 3.8 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 6/20/2012 |  |  | 5/31/2016 | 5/12/2014
PJM | Y2-019 | Essex 230kV | Newark Energy Center | NJ | Essex | In Service | PSEG | 45 | 45 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/21/2012 |  |  | 3/31/2016 | 6/29/2015
PJM | Y2-029 | Ringoes 12kV |  | NJ | Atlantic | Withdrawn | JCPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/29/2012 | 8/16/2012
PJM | Y2-037 | Tuscarora 12kV #1 | Blythe Township Solar Farm #1 | PA | Schuylkill | Withdrawn | PPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/11/2012 | 9/10/2013 | Customer Milestone Not Met | 6/1/2016
PJM | Y2-038 | Tuscarora 12kV #2 |  | PA | Schuylkill | Withdrawn | PPL | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/11/2012 | 8/23/2012 | Customer Milestone Not Met | 12/31/2012
PJM | Y2-042 | Oxbow 34.5 kV | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 18.3 | 18.3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/23/2012 |  |  | 10/30/2019 | 11/16/2019
PJM | Y2-043 | Kickapoo | Grand Ridge Battery Storage | IL | Lasalle | In Service | ComEd | 4.5 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 7/30/2012 |  |  | 12/31/2012 | 12/21/2012
PJM | Y2-045 | Baker 345kV | Riverside Generating Station | KY | Lawrence | In Service | AEP | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/2/2012 |  |  | 7/8/2015 | 1/8/2016
PJM | Y2-048 | Haumesser Road |  | IL | DeKalb | Withdrawn | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/8/2012 | 11/5/2013 | Customer Initiated Withdrawal | 3/29/2013
PJM | Y2-050 | Tidd–Canton Central | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 742 | 672 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/15/2012 |  |  | 11/1/2017 | 9/25/2017
PJM | Y2-051 | Brick-Lane Mill 34.5kV | French's Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/15/2012 |  |  | 6/1/2016 | 10/22/2014
PJM | Y2-052 | South Bend 500kV |  | PA | Armstrong | Withdrawn | APS | 0 | 34.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/15/2012 | 7/17/2013 | Customer Milestone Not Met | 6/1/2016
PJM | Y2-053 | Lemoyne 138kV |  | OH | Wood | Withdrawn | ATSI | 35 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 8/15/2012 | 1/6/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | Y2-054 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 13.7 | 13.7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/15/2012 |  |  | 6/1/2016 | 10/10/2014
PJM | Y2-055 | Elm Street 34.5kV | United Refining Company Oil Refinery | PA | Warren | Withdrawn | PENELEC | 29 | 29 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 8/16/2012 | 2/15/2019 |  | 1/1/2018
PJM | Y2-057 | Wyandot 13kV |  | OH | Wyandot | Withdrawn | AEP | 3 | 3 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 8/23/2012 | 9/14/2012 | Customer Milestone Not Met | 10/1/2013
PJM | Y2-058 | Broadford-Jackson's Ferry 765kV |  | VA | Unknown | Withdrawn | AEP | 762 | 668 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/27/2012 | 6/2/2015 | Customer Initiated Withdrawal | 5/15/2017
PJM | Y2-059 | Kingston-Westover 69kV |  | MD | Somerset | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/30/2012 | 3/11/2013 | Customer Initiated Withdrawal | 9/1/2015
PJM | Y2-060 | North Meshoppen 34.5kv II | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 3.5 | 3.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2012 |  |  | 4/1/2015 | 10/15/2015
PJM | Y2-061 | Cumberland-West Shore 69kV |  | PA | Cumberland | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2012 | 3/19/2013 | Customer Initiated Withdrawal | 7/1/2014
PJM | Y2-062 | East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2012 | 1/14/2013 | Customer Initiated Withdrawal | 12/1/2014
PJM | Y2-063 | Eldred-Frackville #2 230kV |  | PA | Schuylkill | Withdrawn | PPL | 344 | 337 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 9/20/2012 | 4/14/2015 | Customer Initiated Withdrawal | 12/31/2015
PJM | Y2-064 | Printz | Liberty Electric | PA | Delaware | In Service | PECO | 65.5 | 19 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/24/2012 |  |  | 9/30/2014 | 10/5/2015
PJM | Y2-065 | Valley-Raccoon 138kV |  | PA | Beaver | Withdrawn | DL | 205 | 97 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/28/2012 | 3/26/2013 | Customer Milestone Not Met | 6/1/2017
PJM | Y2-066 | Suffolk 34.5kV | Suffolk Landfill Units 1-10 | VA | City of Suffolk | Withdrawn | Dominion | 9 | 9 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/28/2012 | 6/5/2015 | Customer Initiated Withdrawal | 6/1/2015
PJM | Y2-067 | Clinch River 138kV | Virginia City Hybrid Energy Center | VA | Wise | In Service | AEP | 12 | 12 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 9/28/2012 |  |  | 11/1/2012 | 3/28/2014
PJM | Y2-074 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 8 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/19/2012 |  |  | 6/1/2013 | 6/1/2013
PJM | Y2-075 | Solar City |  | MD | Frederick | Withdrawn | APS | 0.5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/19/2012 | 5/13/2013 | Customer Milestone Not Met | 4/5/2013
PJM | Y2-076 | Clover 230kV | Clover Power Station Unit 1 | VA | Halifax | In Service | Dominion | 4 | 13.7 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 10/22/2012 |  |  | 6/1/2014 | 6/1/2014
PJM | Y2-077 | Hopewell 230kV | Hopewell Cogeneration Facility (HCF) | VA | City of Hopewell | In Service | Dominion | 30 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/23/2012 |  |  | 6/1/2016 | 12/20/2017
PJM | Y2-078 | Lakewood #1 230kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/25/2012 |  |  | 6/1/2016 | 6/1/2015
PJM | Y2-079 | Lakewood #2 230kV | Ocean Peaking Power | NJ | Ocean | In Service | JCPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/25/2012 |  |  | 6/1/2015 | 6/1/2015
PJM | Y2-080 | Rhodes Lane 500kV |  | PA | Westmoreland | Withdrawn | APS | 1065 | 1065 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/29/2012 | 11/23/2015 | Customer Initiated Withdrawal | 6/1/2017
PJM | Y2-081 | Deptford 13kV | Deptford (Kinsley Solar)13kV | NJ | Gloucester | In Service | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2012 |  |  | 11/1/2014 | 1/14/2015
PJM | Y2-083 | Essex 138kV |  | NJ | Essex | Withdrawn | PSEG | 218 | 198 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/30/2012 | 5/29/2013 | Customer Initiated Withdrawal | 5/31/2016
PJM | Y2-084 | Dequine 345kV |  | IN | Tippecance | Withdrawn | AEP | 64 | 3.33 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/30/2012 | 3/14/2014 | Customer Initiated Withdrawal | 2/28/2014
PJM | Y2-085 | Sammis–Star 345kV |  | OH | Carroll | Withdrawn | ATSI | 1050 | 1050 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/30/2012 | 7/3/2013 | Customer Initiated Withdrawal | 1/1/2017
PJM | Y2-086 | Engle 69kV |  | KY | Perry | Withdrawn | AEP | 62.5 | 62.5 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 10/30/2012 | 11/10/2014 | Customer Initiated Withdrawal | 1/1/2015
PJM | Y2-087 | Raystown-Lewistown 230kV |  | PA | Mifflin | Withdrawn | PENELEC | 150.4 | 19.55 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/31/2012 | 8/28/2014 | Customer Initiated Withdrawal | 10/31/2016
PJM | Y2-088 | Garards Fort 25kV | Bayles-Garards Fort 25kV | PA | Greene | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn | Wholesale Market Participation Agreement | 10/31/2012 | 1/20/2017 | Customer Initiated Withdrawal | 6/30/2015
PJM | Y2-089 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 370 | 370 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2012 |  |  | 4/1/2019 | 10/2/2018
PJM | Y2-091 | Toledo Solar |  | OH | Lucas | Withdrawn | ATSI | 0.332 | 0 | Energy | Generation Interconnection | Solar | Not Required | Not Required | Not Required | Withdrawn | 10/31/2012 | 1/13/2014 | Customer Initiated Withdrawal
PJM | Y2-092 | Walbridge Solar |  | OH | Wood | Withdrawn | ATSI | 0.3 | 0 | Energy | Generation Interconnection | Solar | Not Required | Not Required | Not Required | Withdrawn | 10/31/2012 | 1/13/2014 | Customer Initiated Withdrawal
PJM | Y2-095 | Sullivan 765 kV |  | IL | Randolph | Withdrawn | AEP | 1211 | 1211 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 10/31/2012 | 9/10/2013 | Customer Initiated Withdrawal | 10/24/2013
PJM | Y2-096 | Balenger Sewage-Thomas Bakery 34.5kV |  | MD | Frederick | Withdrawn | APS | 47.2 | 47.2 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 10/31/2012 | 12/2/2014 | Customer Initiated Withdrawal | 8/18/2016
PJM | Y2-097 | Brunswick 500kV |  | VA | Brunswick | Withdrawn | Dominion | 1551 | 1376 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/31/2012 | 11/18/2013 | Customer Initiated Withdrawal | 12/1/2018
PJM | Y2-098 | Freemansburg #1 12kV | Bethlehem Landfill | PA | Northampton | Deactivated | PPL | 5 | 5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2012 |  |  | 11/1/2012 | 8/10/2016
PJM | Y2-099 | Warrenton 34.5kV | Fauquier County Landfill Units 1 & 2 | VA | Fauquier | Withdrawn | Dominion | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2012 | 3/11/2016 | Customer Initiated Withdrawal | 6/1/2016
PJM | Y2-100 | Otter Point 34.5kV | Eastern Landfill Gas | MD | Baltimore County | In Service | BGE | 4 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2012 |  |  | 4/30/2013 | 11/18/2016
PJM | Y2-101 | Freemansburg #2 12kV |  | PA | Northampton | Withdrawn | PPL | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Withdrawn |  |  | 10/31/2012 | 4/4/2013 | Customer Milestone Not Met | 12/31/2013
PJM | Y2-102 | Deepwater 138kV |  | NJ | Salem | Withdrawn | AEC | 193 | 193 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/1/2012 | 7/10/2013 | Customer Initiated Withdrawal | 6/1/2016
PJM | Y2-103 | Zion Energy Center |  | IL | Lake | Withdrawn | ComEd | 360 | 360 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 11/1/2012 | 12/24/2019 |  | 6/1/2016
PJM | Y2-104 | Russell Hill-N. Meshoppen 34.5kV |  | PA | Wyoming | Withdrawn | PENELEC | 6.6 | 6.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/1/2012 | 7/25/2013 | Customer Initiated Withdrawal | 3/1/2014
PJM | Y2-105 | Eagle Point 230kV | Eagle Point | NJ | Gloucester | In Service | PSEG | 63 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2012 |  |  | 6/1/2016 | 3/25/2015
PJM | Y2-107 | Robison Park-Argenta 345 kV |  | IN | LeGrange | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/2/2012 | 8/19/2013 | Customer Milestone Not Met | 11/30/2015
PJM | Y2-108 | Crisfield 25kV |  | MD | Somerset | Withdrawn | DPL | 2 | 2 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Withdrawn | 11/2/2012 | 12/11/2014 | Customer Initiated Withdrawal | 3/31/2015
PJM | Y2-109 | Bayview 25kV | Bayview | VA | Northampton | In Service | ODEC | 0.5 | 0.5 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 11/2/2012 |  |  | 7/19/2013 | 7/19/2013
PJM | Y2-110 | BL England 138kV |  | NJ | Cape May | Withdrawn | AEC | 40 | 40 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 11/2/2012 | 3/7/2016 | Customer Initiated Withdrawal | 1/1/2016
PJM | Y2-111 | Tait 69kV | AES Tait Energy Storage | OH | Montgomery | Deactivated | Dayton | 12 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 11/2/2012 |  |  | 3/27/2014 | 8/27/2013
PJM | Y2-112 | Keystone 345kV |  | IN | Wells | Withdrawn | AEP | 12 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 11/2/2012 | 8/21/2013 | Customer Milestone Not Met | 3/1/2013
PJM | Y2-113 | Morris 138kV | Morris Cogen | IL | Grundy | In Service | ComEd | 12.6 | 12.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 11/2/2012 |  |  | 10/31/2012 | 3/14/2014
PJM | Y2-116 | Sullivan 765 kV |  | IL | Randolph | Withdrawn | AEP | 600 | 600 | Capacity | Generation Interconnection | Coal | Document Posted | Withdrawn |  |  | 11/2/2012 | 9/10/2013 | Customer Initiated Withdrawal | 10/24/2013
PJM | Y2-117 | Perryman Solar | Perryman Solar Farm | MD | Harford | Withdrawn | BGE | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/2/2012 | 8/2/2018 |  | 12/31/2017
PJM | Y3-001 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 705 | 660 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 11/5/2012 | 1/21/2014 | Customer Milestone Not Met | 5/31/2017
PJM | Y3-010 | Brush Junction-Millheim 46kV |  | PA | Centre | Withdrawn | APS | 70 | 9.1 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 12/14/2012 | 9/23/2013 | Customer Initiated Withdrawal | 12/31/2016
PJM | Y3-012 | Huron 69kV | Marina Thermal Facility | NJ | Atlantic | In Service | AEC | 7.5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/21/2012 |  |  | 12/31/2013 | 1/31/2014
PJM | Y3-013 | Zion Energy Center | Zion Energy Center | IL | Lake | In Service | ComEd | 0 | 90 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/27/2012 |  |  | 9/1/2021 | 1/12/2021
PJM | Y3-023 | Country Side 12kV | Wabash Valley Power Association, Inc. | IN | Elkhart | In Service | AEP | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/18/2013 |  |  | 6/1/2015 | 1/1/2015
PJM | Y3-024 | Bluff Point 12kV | Wabash Valley Power Association, Inc. | IN | Jay | In Service | AEP | 3.2 | 3.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/18/2013 |  |  | 6/1/2015 | 1/1/2015
PJM | Y3-025 | Bridge-South Park 12kV | Charleston Clean Energy | WV | Kanawha | In Service | AEP | 3.18 | 3.18 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 1/22/2013 |  |  | 5/29/2015 | 5/29/2019
PJM | Y3-026 | Burlington 26kV | Burlington (L&D Solar) 26kV | NJ | Burlington | In Service | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 1/25/2013 |  |  | 9/24/2015 | 1/26/2016
PJM | Y3-027 | Camden 26kV | Camden (Cinnaminson Solar) 26kV | NJ | Burlington | Withdrawn | PSEG | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/25/2013 | 2/18/2015 | Customer Initiated Withdrawal | 5/28/2015
PJM | Y3-029 | Damascus-Mt. Airy 34.5kV | Hickory Plains Hydroponics | MD | Frederick | Withdrawn | APS | 4.375 | 4.375 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/1/2013 | 4/4/2018 |  | 12/31/2017
PJM | Y3-031 | Riders Creek 115kV |  | NC | Tyrell | Withdrawn | Dominion | 130.9 | 17 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/6/2013 | 9/16/2013 | Customer Initiated Withdrawal | 10/31/2016
PJM | Y3-031A_EKPC2 | Flemingsburg 138 KV |  | KY | Unknown | Withdrawn | EKPC | 150.28 | 19.53 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/11/2013 | 5/1/2014 | Customer Initiated Withdrawal | 12/31/2015
PJM | Y3-033 | Chestertown-Millington 69kV | Mills Branch Wind Farm | MD | Kent | Withdrawn | DPL | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 2/19/2013 | 1/20/2017 | Customer Initiated Withdrawal | 4/30/2018
PJM | Y3-034 | Eldred-Pine Grove 690kV | Stonegate Renewable Energy | PA | Schuylkill | In Service | PPL | 0 | 1.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 2/20/2013 |  |  | 12/31/2013 | 12/26/2013
PJM | Y3-035 | Mole Creek 345kV |  | IL | Marshall | Withdrawn | ComEd | 97.5 | 12.675 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 2/21/2013 | 10/1/2013 | Customer Milestone Not Met | 6/1/2015
PJM | Y3-036 | Gavin Unit 2 | Gavin Unit #2 | OH | Gallia | In Service | AEP | 36 | 36 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2013 |  |  | 12/31/2014 | 1/14/2015
PJM | Y3-037 | Amos Unit 3 | John Amos Generating Plant Unit No. 3 | WV | Putnam | In Service | AEP | 36 | 36 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2013 |  |  | 12/31/2014 | 4/1/2015
PJM | Y3-038 | Rockport Unit 1 | Rockport Unit #1 | IN | Spencer | In Service | AEP | 36 | 36 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2013 |  |  | 6/30/2017 | 6/30/2017
PJM | Y3-039 | Clinch River Unit 1 | Clinch River Power Plant | VA | Russell | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2013 |  |  | 4/15/2016 | 5/27/2016
PJM | Y3-040 | Clinch River Unit 2 | Clinch River Power Plant | VA | Russell | In Service | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2013 |  |  | 6/6/2016 | 5/23/2016
PJM | Y3-041 | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 62 | 8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 2/28/2013 | 1/29/2015 | Customer Milestone Not Met | 12/31/2017
PJM | Y3-042 | Elrama 69kV |  | PA | Washington | Withdrawn | DL | 460 | 460 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/28/2013 | 10/22/2013 | Customer Initiated Withdrawal | 6/1/2015
PJM | Y3-043 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 760 | 760 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2013 |  |  | 12/31/2018 | 12/11/2018
PJM | Y3-044 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 |  |  | 3/31/2015 | 10/21/2015
PJM | Y3-045 | Bergen | Bergen Genertating Station | NJ | Bergen | In Service | PSEG | 0 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 |  |  | 3/31/2015 | 10/29/2015
PJM | Y3-046 | Linden | Linden Generating Station | NJ | Union | Withdrawn | PSEG | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 | 6/30/2017 |  | 3/31/2015 | 2/13/2015
PJM | Y3-047 | Essex |  | NJ | Essex | Withdrawn | PSEG | 10 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn | Interim Study | 2/28/2013 | 7/22/2014 | Customer Initiated Withdrawal | 5/31/2013
PJM | Y3-048 | Burlington | Burlington Generating Station | NJ | Burlington | In Service | PSEG | 2 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 |  |  | 3/31/2015 | 10/21/2015
PJM | Y3-049 | Edison |  | NJ | Middlesex | Withdrawn | PSEG | 0 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  | Not Required | Interim Study | 2/28/2013 | 7/22/2014 | Customer Initiated Withdrawal | 5/31/2013
PJM | Y3-050 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 24 | 21 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 |  |  | 3/31/2015 | 10/21/2015
PJM | Y3-051 | Linden | Linden Generating Station | NJ | Union | In Service | PSEG | 47 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 |  |  | 3/31/2015 | 8/29/2016
PJM | Y3-052 | Bergen |  | NJ | Bergen | In Service | PSEG | 50 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 |  |  | 3/31/2015 | 10/29/2015
PJM | Y3-053 | Kearny | Kearny Generating Station | NJ | Hudson | In Service | PSEG | 40 | 13 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2013 |  |  | 6/1/2016 | 10/21/2015
PJM | Y3-054 | Milford 138kV | Milford Solar | DE | Kent | Withdrawn | DPL | 12 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/5/2013 | 5/16/2016 |  | 12/31/2014
PJM | Y3-056 | Pioneer Crossing 69kV | Pioneer Crossing | PA | Berks | In Service | ME | 1.6 | 1.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 3/12/2013 |  |  | 10/31/2013 | 9/1/2013
PJM | Y3-057 | Forest Park |  | MD | Charles | Withdrawn | PEPCO | 12 | 4.56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/13/2013 | 4/12/2013 | Customer Initiated Withdrawal | 9/1/2014
PJM | Y3-058 | Rockawalkin 69kV | Rockfish Solar Power Plant | MD | Wicomico | In Service | DPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/13/2013 |  |  | 12/31/2016 | 2/22/2016
PJM | Y3-062 | Erie East 34.5kV | North East Wind Farm | PA | Erie | Withdrawn | PENELEC | 18.7 | 2.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/18/2013 | 12/17/2014 | Customer Milestone Not Met | 12/31/2016
PJM | Y3-063 | State Line 138kV |  | IN | Lake | Withdrawn | ComEd | 1161 | 1161 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/20/2013 | 9/9/2013 | Customer Initiated Withdrawal | 6/1/2018
PJM | Y3-068 | George Washington 138kV | Moundsville Power, LLC | WV | Marshall | Withdrawn | AEP | 525 | 525 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2013 | 4/27/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | Y3-073 | W.H. Zimmer Station |  | OH | Clermont | Withdrawn | DEOK | 50 | 50 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Withdrawn | 4/10/2013 | 2/24/2016 | Customer Initiated Withdrawal | 6/1/2013
PJM | Y3-074 | Ashton 480V |  | MD | Montgomery | In Service | BGE | 0.372 | 0 | Energy | Generation Interconnection | Hydro | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 4/12/2013 |  |  | 7/1/2014 | 10/1/2014
PJM | Y3-080 | Tait 69kV | AES Tait Energy Storage | OH | Montgomery | Deactivated | Dayton | 8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/19/2013 |  |  | 3/27/2014 | 9/24/2013
PJM | Y3-081 |  |  | OH | Adams | Withdrawn | ATSI |  |  | Energy | Generation Interconnection | Methane | Withdrawn |  |  |  | 4/19/2013 | 4/25/2013
PJM | Y3-087 | Beaverbrook 13kV | Beaverbrook (Kinsley Solar) | NJ | Gloucester | In Service | PSEG | 3.8 | 1.44 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/26/2013 |  |  | 6/30/2015 | 1/14/2015
PJM | Y3-088 | Kendall I | Kendall Energy Center | IL | Grundy | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/26/2013 |  |  | 12/1/2015 | 5/23/2017
PJM | Y3-089 | Kendall II | Kendall Energy Center | IL | Grundy | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/26/2013 |  |  | 12/1/2015 | 5/23/2017
PJM | Y3-090 | Kendall III | Kendall Energy Center | IL | Grundy | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/26/2013 |  |  | 12/1/2015 | 5/23/2017
PJM | Y3-091 | Kendall IV | Kendall Energy Center | IL | Grundy | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/26/2013 |  |  | 12/1/2015 | 5/23/2017
PJM | Y3-095 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2013 | 5/24/2013 | Customer Initiated Withdrawal | 9/25/2013
PJM | Y3-096 | Hanging Rock 765kV |  | OH | Lawrence | Withdrawn | AEP | 10 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 4/29/2013 | 4/23/2015 | Customer Initiated Withdrawal | 3/31/2015
PJM | Y3-097 | Trent (Jug St.) 34.5kV |  | OH | Delaware | Withdrawn | AEP | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2013 | 9/29/2014 | Customer Initiated Withdrawal | 9/30/2015
PJM | Y3-098 | Printz |  | PA | Delaware | Withdrawn | PECO | 735 | 735 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/29/2013 | 9/26/2013 | Customer Initiated Withdrawal | 10/1/2017
PJM | Y3-099 | Beckjord 2 MW-1 | Beckjord Battery #1 | OH | Clermont | In Service | DEOK | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2013 |  |  | 5/1/2015 | 1/21/2015
PJM | Y3-100 | Beckjord 2 MW-2 | Beckjord Battery #2 | OH | Clermont | Deactivated | DEOK | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2013 |  |  | 10/1/2015 | 11/1/2015
PJM | Y3-101 | Cedar 12kV |  | NJ | Ocean | Withdrawn | AEC | 5.7 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/29/2013 | 9/30/2013 | Customer Initiated Withdrawal | 12/31/2014
PJM | Y3-102 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 166 | 135 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2013 |  |  | 8/21/2017 | 7/27/2017
PJM | Y3-103 | Valley-Raccoon 138kV | Pennsylvania Chemicals Generating Facility | PA | Beaver | In Service | DL | 205 | 97 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2013 |  |  | 11/30/2021 | 6/22/2021
PJM | Y3-104 | Sullivan Trail-Stanton 69kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 4/30/2013 | 1/22/2015 | Customer Milestone Not Met | 1/1/2015
PJM | Y3-105 | Belvidere-Gilbert-115kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 4/30/2013 | 10/1/2013 | Customer Milestone Not Met | 1/1/2015
PJM | Y3-106 | Belleville-Rutland 138kV | Belleville Hydroelectric Plant | WV | Wood | In Service | AEP | 7 | 7 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2013 |  |  | 12/31/2014 | 12/31/2014
PJM | Y3-107 | Bergen 230kV |  | NJ | Bergen | In Service | PSEG | 35 | 45 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2013 |  |  | 4/1/2015 | 10/29/2015
PJM | Y3-108 | Linden 230kV |  | NJ | Union | Withdrawn | PSEG | 110 | 107 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/2013 | 11/20/2013 | Customer Initiated Withdrawal | 3/1/2014
PJM | Y3-109 | Nyswaner 25kV | Red Glen Generator | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2013 | 1/25/2018 |  | 12/31/2016
PJM | Y3-110 | North Salisbury-Worcester 69kV |  | MD | Wicomico | Withdrawn | DPL | 15.7 | 15.7 | Capacity | Generation Interconnection | Biomass | Document Posted | Withdrawn |  |  | 4/30/2013 | 10/9/2013 | Customer Initiated Withdrawal | 12/31/2016
PJM | Y3-111 | Harborcreek Township 34kV |  | PA | Erie | Withdrawn | PENELEC | 18.7 | 2.4 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 4/30/2013 | 9/22/2013 | Customer Milestone Not Met | 4/1/2014
PJM | Y3-113 | Russell Hill-W. Meshoppen |  | PA | Wyoming | Withdrawn | PENELEC | 3.4 | 3.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/2013 | 7/25/2013 | Customer Initiated Withdrawal | 9/1/2014
PJM | Y3-114 |  |  | PA | Adams | Withdrawn | PENELEC |  |  | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/30/2013 | 4/30/2013 | Customer Initiated Withdrawal
PJM | Y3-119 | E. Lynchburg-Peaks View 34.5kV |  | VA | City of Lynchburg | Withdrawn | AEP | 19 | 7 | Capacity | Generation Interconnection | Wood | Document Posted | Document Posted | Not Required | Withdrawn | 4/30/2013 | 11/12/2014 | Customer Milestone Not Met | 9/30/2015
PJM | Y3-120 | Conowingo 230kV |  | MD | Harford | Withdrawn | PECO | 45 | 45 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 4/30/2013 | 9/27/2013 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-015 | Springdale 3, 4, 5 | Springdale | PA | Allegheny | In Service | APS | 0 | 26 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/20/2013 |  |  | 6/1/2015 | 1/21/2015
PJM | Z1-018 | Richland III 138kV |  | OH | Defiance | Withdrawn | ATSI | 591 | 591 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 5/29/2013 | 4/1/2014 | Customer Initiated Withdrawal | 5/15/2016
PJM | Z1-020 | Richland I 138kV |  | OH | Defiance | Withdrawn | ATSI | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/4/2013 | 4/22/2014 | Customer Milestone Not Met | 4/30/2014
PJM | Z1-021 | Richland II 138kV |  | OH | Defiance | Withdrawn | ATSI | 36 | 36 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/4/2013 | 4/22/2014 | Customer Milestone Not Met | 4/30/2014
PJM | Z1-022 | Stryker 138kV |  | OH | Defiance | Withdrawn | ATSI | 5 | 5 | Capacity | Generation Interconnection | Oil | Document Posted | Withdrawn |  |  | 6/4/2013 | 4/1/2014 | Customer Initiated Withdrawal | 4/30/2014
PJM | Z1-030 | Bay Shore 138kV |  | OH | Lucas | Withdrawn | ATSI | 464 | 464 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/24/2013 | 4/1/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | Z1-034 | Niles 138kV |  | OH | Trumbull | Withdrawn | ATSI | 217 | 217 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 7/3/2013 | 7/31/2013 | Customer Initiated Withdrawal | 6/1/2017
PJM | Z1-035 | Lake Road 11.5 kV |  | OH | Unknown | Withdrawn | ATSI | 18 | 2.34 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Not Required | Withdrawn | 7/5/2013 | 2/7/2022 |  | 9/30/2017
PJM | Z1-036 | WinFall-Chowan 230kV | Timbermill Wind Farm | NC | Perquimans | In Service | Dominion | 189 | 24.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 7/23/2013 |  |  | 3/31/2025 | 12/13/2024
PJM | Z1-038 | Florey Knob 34.5kV | Florey Knob Generating Station | PA | Wyoming | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/1/2013 | 2/21/2019 |  | 3/31/2017
PJM | Z1-041 | Rock Springs 500kV | Rock Springs Units #1 & #2 | MD | Cecil | In Service | Essential Power | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/14/2013 |  |  | 6/1/2017 | 5/28/2015
PJM | Z1-042 | Belleville/New Holland-Logan 46kV |  | PA | Mifflin | Withdrawn | PENELEC | 46 | 9.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/16/2013 | 11/3/2014 | Customer Initiated Withdrawal | 12/31/2015
PJM | Z1-047 | Albright |  | PA | Mifflin | Withdrawn | PENELEC | 464 | 464 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/28/2013 | 4/23/2014 | Customer Milestone Not Met | 6/1/2017
PJM | Z1-048 | Rivesville |  | WV | Marion | Withdrawn | APS | 464 | 464 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/28/2013 | 4/28/2014 | Customer Initiated Withdrawal | 6/1/2017
PJM | Z1-049 | Willow Island |  | WV | Pleasants | Withdrawn | APS | 464 | 464 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/28/2013 | 4/23/2014 | Customer Milestone Not Met | 6/1/2017
PJM | Z1-050 | Kittatinny 230kV | Yards Creek Pumped Storage Hydro-electric Generating Station | NJ | Warren | In Service | JCPL | 20 | 20 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 8/29/2013 |  |  | 3/1/2014 | 5/1/2014
PJM | Z1-051 | D.C. Cook Unit 2 | D.C. Cook Generating Plant Unit No. 2 | MI | Berrien | In Service | AEP | 102 | 83 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 8/29/2013 |  |  | 11/18/2016 | 1/14/2017
PJM | Z1-052 | Burches Hill-Chalk Point 500kV | Keys Energy Center | MD | Prince George's | In Service | PEPCO | 64.5 | 44.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/29/2013 |  |  | 8/15/2018 | 7/23/2018
PJM | Z1-053 | Monocacy 12.47 KV - Worman Mill Feeder |  | MD | Frederick | Withdrawn | APS | 0.3 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/5/2013 | 9/25/2013 | Customer Initiated Withdrawal | 4/15/2014
PJM | Z1-055 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/11/2013 |  |  | 6/1/2016 | 1/31/2017
PJM | Z1-056 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/11/2013 |  |  | 6/1/2016 | 1/31/2017
PJM | Z1-057 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 0 | 15.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/26/2013 |  |  | 10/1/2013 | 5/6/2014
PJM | Z1-058 | Linden 1 - 138kV | Linden Generating Station | NJ | Union | In Service | PSEG | 23 | 36 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2013 |  |  | 9/30/2015 | 8/29/2016
PJM | Z1-059 | Linden 2 - 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 23 | 18 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2013 |  |  | 6/1/2017 | 8/29/2016
PJM | Z1-063 | Kirk 34.5kV |  | OH | Licking | Withdrawn | AEP | 6 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 9/30/2013 | 10/5/2016 | Customer Milestone Not Met | 12/31/2016
PJM | Z1-064 | Shannon 13.2kV |  | OH | Franklin | Withdrawn | AEP | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 9/30/2013 | 10/5/2016 | Customer Milestone Not Met | 12/31/2016
PJM | Z1-065 | Wiley 34.5kV | Willey Energy Storage Project | OH | Hamilton | In Service | DEOK | 6 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2013 |  |  | 11/30/2015 | 12/1/2015
PJM | Z1-066 | Arnold 115kV | Green Mountain Battery | PA | Somerset | In Service | PENELEC | 10.4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2013 |  |  | 3/1/2016 | 12/30/2015
PJM | Z1-068 | Birdneck 34.5kV |  | VA | City of Virginia Beach | In Service | Dominion | 12 | 1.5 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Not Required | Not Required | Wholesale Market Participation Agreement | 10/10/2013 |  |  | 12/31/2020 | 9/26/2020
PJM | Z1-069 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 70 | 13.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/24/2013 |  |  | 10/31/2019 | 11/20/2019
PJM | Z1-072 | Crescent Ridge | Crescent Ridge Wind Farm | IL | Bureau | In Service | ComEd | 0 | 9.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/28/2013 |  |  | 12/31/2014 | 6/1/2016
PJM | Z1-073 | Mendota Hills |  | IL | Lee | In Service | ComEd | 0 | 5.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/28/2013 |  |  | 12/31/2014 | 8/5/2015
PJM | Z1-074 | Garrett-Jenning 34.5kV |  | MD | Garrett | Withdrawn | APS | 20 | 2.6 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 10/28/2013 | 4/23/2014 | Customer Milestone Not Met | 12/18/2015
PJM | Z1-076 | Stockton 1 69kV |  | MD | Worcester | Withdrawn | DPL | 14 | 5.32 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/30/2013 | 7/25/2017 | Customer Initiated Withdrawal | 6/30/2018
PJM | Z1-077 | Stockton 2 69kV |  | MD | Worcester | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/30/2013 | 7/25/2017 | Customer Initiated Withdrawal | 6/30/2018
PJM | Z1-078 | Broadford-Jackson Ferry Phase II 765kV |  | VA | Unknown | Withdrawn | AEP | 777 | 777 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/30/2013 | 11/10/2014 | Customer Initiated Withdrawal | 6/15/2018
PJM | Z1-079 | Todhunter-Foster 345kV | Middletown Energy Center | OH | Butler | In Service | DEOK | 513 | 513 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2013 |  |  | 6/1/2018 | 2/6/2018
PJM | Z1-080 | Clinton County 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 6 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2013 |  |  | 10/31/2016 | 8/29/2016
PJM | Z1-081 | Church 25kV | Sunfish Solar Project | MD | Queen Anne's | Withdrawn | DPL | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/30/2013 | 3/3/2017 | Customer Initiated Withdrawal | 7/15/2017
PJM | Z1-082 | Lawnside 13kV | Lawnside Battery | NJ | Camden | In Service | PSEG | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2013 |  |  | 8/1/2014 | 1/13/2015
PJM | Z1-086 | Heritage-Carson | Greensville Generating Facility | VA | Greensville | In Service | Dominion | 1681 | 1630 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2013 |  |  | 6/1/2019 | 12/8/2018
PJM | Z1-087 | Glade 230kV | Seneca Pumped Storage Generating Station | PA | Warren | In Service | PENELEC | 17 | 17 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2013 |  |  | 12/31/2017 | 4/21/2017
PJM | Z1-088 | Allegheny Dam 5 | Allegheny River Lock & Dam # 5 | PA | Armstrong | In Service | APS | 0 | 5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2013 |  |  | 10/31/2013 | 3/25/2015
PJM | Z1-089 | Allegheny Dam 6 138kV | Allegheny River Lock & Dam #6 | PA | Armstrong | In Service | APS | 0 | 5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2013 |  |  | 10/31/2013 | 3/25/2015
PJM | Z1-090 | Sunbury 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 381 | 381 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2013 |  |  | 3/18/2018 | 3/24/2018
PJM | Z1-091 | Lenox 34kV | Hop Bottom Generating Station | PA | Lackawanna | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/31/2013 | 12/15/2018 |  | 3/31/2017
PJM | Z1-092 | Milan 34kV | Milan Energy | PA | Lackawanna | In Service | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2013 |  |  | 2/2/2017 | 2/20/2017
PJM | Z1-093 | Woodville Battery 34.5kV |  | OH | Sandusky | Withdrawn | ATSI | 6 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 10/31/2013 | 10/31/2014 | Customer Initiated Withdrawal | 12/30/2014
PJM | Z1-094 | Jugg 34.5kV |  | OH | Licking | Withdrawn | AEP | 6 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2013 | 10/5/2016 | Customer Milestone Not Met | 5/18/2018
PJM | Z1-095 | North Woodcock 34.5kV |  | OH | Allen | Withdrawn | AEP | 6 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/27/2015 | Customer Initiated Withdrawal | 12/30/2014
PJM | Z1-096 | Trenton 26kV | Parkland Solar | NJ | Burlington | In Service | PSEG | 7.84 | 2.98 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2013 |  |  | 12/15/2014 | 1/14/2015
PJM | Z1-097 | Adkins 345kV | Darby Generating Station Unites, 1,2,3,4,5,6 | OH | Madison | In Service | AEP | 0 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2013 |  |  | 6/30/2017 | 12/15/2014
PJM | Z1-098 | Peckville-Jackson 69kV | Valley View Flywheel Station | PA | Lackawanna | Withdrawn | PPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2013 | 11/6/2015 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z1-099 | North Street 69kV | City of Dover Generating Facilities | DE | Kent | In Service | DPL | 7 | 7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2013 |  |  | 10/31/2015 | 9/22/2016
PJM | Z1-100 | Oak Hall | Oak Hal lProject A | VA | Unknown | In Service | DPL | 0 | 4.162 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2013 |  |  | 10/15/2016 | 12/8/2016
PJM | Z1-101 | Oak Hall | Oak Hall Project B | VA | Unknown | In Service | DPL | 0 | 4.162 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2013 |  |  | 12/30/2016 | 12/8/2016
PJM | Z1-102 | Oak Hall | Oak Hall Project C | VA | Unknown | In Service | DPL | 0 | 4.162 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2013 |  |  | 12/30/2017 | 12/8/2016
PJM | Z1-103 | Oak Hall |  | VA | Unknown | In Service | DPL | 0 | 4.162 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2013 |  |  | 12/30/2017 | 12/8/2016
PJM | Z1-104 | Somerset County 25kV |  | MD | Somerset | Withdrawn | DPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/19/2014 | Customer Initiated Withdrawal | 4/30/2013
PJM | Z1-105 | Emlenton 34.5kV |  | PA | Clarion | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2013 | 2/27/2015 | Customer Initiated Withdrawal | 7/1/2015
PJM | Z1-106 | West Chicago 34kV | West Chicago Energy Storage | IL | Du Page | Deactivated | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2013 |  |  | 12/31/2015 | 9/22/2015
PJM | Z1-107 | Joliet 34kV |  | IL | Will | Deactivated | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  | Not Required | Wholesale Market Participation Agreement | 10/31/2013 |  |  | 12/31/2015 | 8/26/2015
PJM | Z1-108 | McHenry 34kV | McHenry Energy Storage | IL | McHenry | In Service | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2013 |  |  | 12/31/2015 | 12/17/2015
PJM | Z1-109 | Tosco-VFT 230kV |  | NJ | Union | Withdrawn | PSEG | 208 | 208 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2013 | 3/16/2016 | Customer Initiated Withdrawal | 6/30/2016
PJM | Z1-110 | Grover 34kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2013 |  |  | 12/31/2016 | 6/7/2016
PJM | Z1-113 | West Winchester 13kV | HP Hood Generation Facility | VA | Rockingham | In Service | APS | 12 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2013 |  |  | 3/30/2015 | 5/11/2015
PJM | Z1-114 | Oxford 13kV |  | PA | York | Withdrawn | ME | 6 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2013 | 9/29/2014 | Customer Initiated Withdrawal | 6/30/2015
PJM | Z1-115 | Crescentville 13kV |  | PA | Philadelphia | Withdrawn | PECO | 2 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2013 | 5/13/2014 | Customer Milestone Not Met | 12/31/2014
PJM | Z1-116 | Metuchen 230kV | CPV Keasbey Energy Center | NJ | Middlesex | Withdrawn | PSEG | 675 | 671 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2013 | 10/2/2023 |  | 1/1/2027
PJM | Z1-117 | Pocomoke 1 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-118 | Pocomoke 2 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-119 | Pocomoke 3 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-120 | Loretto 1 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-121 | Loretto 2 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-122 | Loretto 3 138kV |  | MD | Somerset | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 5/19/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-123 | Piney Grove 1 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-124 | Piney Grove 2 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-125 | Piney Grove 3 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-126 | Piney Grove 4 138kV |  | MD | Worcester | Withdrawn | DPL | 10 | 5.88 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2013 | 4/2/2014 | Customer Initiated Withdrawal | 6/1/2016
PJM | Z1-127 | University Park |  | IL | Will | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2013 |  |  | 10/31/2013 | 2/10/2014
PJM | Z2-001 | Burlington 26 kV | Recovery Road Solar Farm | NJ | Burlington | Withdrawn | PSEG | 7.1 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/1/2013 | 3/29/2018 |  | 6/30/2018
PJM | Z2-002 | Linden 230kV | Linden Generating Station | NJ | Union | In Service | PSEG | 61 | 54 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2013 |  |  | 6/1/2017 | 5/16/2018
PJM | Z2-004 | Mantua Township 12kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 10 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 11/8/2013 | 9/24/2014 | Customer Initiated Withdrawal | 8/4/2014
PJM | Z2-007 | East Palmerton-Harwood 230kV |  | PA | Carbon | Withdrawn | PPL | 212.5 | 27 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 11/22/2013 | 10/1/2014 | Customer Milestone Not Met | 6/1/2015
PJM | Z2-008 | East Palmerton-Wagner 69kV |  | PA | Carbon | Withdrawn | PPL | 99 | 12.9 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 12/9/2013 | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2017
PJM | Z2-009 | East Hazelton-Harwood 69kV |  | PA | Luzerne | Withdrawn | PPL | 52 | 6.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 12/23/2013 | 1/14/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z2-011 | Canton 34.5kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 12/30/2013 |  |  | 6/30/2017 | 2/27/2017
PJM | Z2-012 | Weirwood-Eastville 69kV | Hecate Energy Cherrydale | VA | Northampton | In Service | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 12/31/2013 |  |  | 4/1/2017 | 9/7/2017
PJM | Z2-013 | Frostburg 138kV | Twin Ridges Wind Farm | PA | Somerset | In Service | APS | 0 | 4.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 1/9/2014 |  |  | 12/31/2014 | 12/15/2014
PJM | Z2-014 | St. Benedict-Patton | Patton Wind Farm | PA | Cambria | In Service | PENELEC | 0 | 1.35 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 1/9/2014 |  |  | 12/31/2015 | 2/13/2015
PJM | Z2-015 | Dans Mountain 138kV |  | PA | Allegheny | Withdrawn | APS | 19.8 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/15/2014 | 2/12/2014 | Customer Initiated Withdrawal | 6/1/2014
PJM | Z2-019 | Fairborn 12.47kV | Dovetail Biogas Facility | OH | Greene | Withdrawn | ATSI | 0.85 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/7/2014 | 7/7/2015 | Customer Initiated Withdrawal | 6/30/2015
PJM | Z2-020 | New Franklin 12.47kV |  | OH | Summit | Withdrawn | ATSI | 0.85 | 0 | Energy | Generation Interconnection | Methane | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 2/7/2014 | 11/10/2017 |  | 6/30/2015
PJM | Z2-026 | North Temple 230kV |  | PA | Berks | Withdrawn | ME | 800 | 800 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/14/2014 | 4/8/2016 | Customer Initiated Withdrawal | 6/1/2018
PJM | Z2-027 | Pasquotank 34.5kV | Elizabeth City Solar Park | NC | Pasquotank | In Service | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/20/2014 |  |  | 2/15/2015 | 12/31/2014
PJM | Z2-028 | Highland-Sammis 345kV & Highland-Mansfield 345kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 800 | 800 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/21/2014 |  |  | 12/28/2018 | 8/15/2018
PJM | Z2-029 | Stuart 4 | Stuart Electric Generating Station | OH | Brown | Deactivated | Dayton | 20.5 | 20.5 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 2/25/2014 |  |  | 12/31/2015 | 10/1/2015
PJM | Z2-030 | Double Toll Gate 34.5kV | Double Tollgate Solar Project | VA | Clarke | In Service | APS | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/26/2014 |  |  | 12/31/2016 | 7/12/2017
PJM | Z2-032 | Clean River Power MR-1 (Devola) |  | OH | Washington | Withdrawn | AEP | 5.21 | 5.21 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 2/27/2014 | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z2-033 | Clean River Power MR-2 (Lowell) |  | OH | Washington | Withdrawn | AEP | 5.21 | 5.21 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 2/27/2014 | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z2-034 | Clean River Power MR-3 (Beverly) |  | OH | Washington | Withdrawn | AEP | 3.95 | 3.95 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 2/27/2014 | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z2-035 | Clean River Power MR-5 (Malta) |  | OH | Morgan | Withdrawn | AEP | 3.95 | 3.95 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 2/27/2014 | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z2-036 | Clean River Power MR-6 (Rokeby) |  | OH | Morgan | Withdrawn | AEP | 3.95 | 3.95 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 2/27/2014 | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z2-037 | Clean River Power MR-7 (Philo) |  | OH | Muskingum | Withdrawn | AEP | 3.95 | 3.95 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 2/27/2014 | 9/29/2014 | Customer Initiated Withdrawal | 12/31/2016
PJM | Z2-038 | Ridgeley-Frostburg 138kV | Dan's Mountain Solar Project | MD | Allegany | Withdrawn | APS | 19.9 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/27/2014 | 12/22/2017 |  | 3/31/2018
PJM | Z2-039 | PF Hydro | Warren Hydro Station; Newport Hydro Station; Luray Hydro Station; Shenandoah Hydro Station | VA | Warren | In Service | APS | 0 | 2.82 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2014 |  |  | 5/31/2015 | 5/13/2015
PJM | Z2-040 | PF Hydro | Dam 4 Hydro Generation Facility; Dam 5 Hydro Generation Facility; Millville Hydroelectric Facility | WV | Jefferson | In Service | APS | 0 | 3.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 2/27/2014 |  |  | 3/31/2014 | 4/17/2015
PJM | Z2-041 | Silver Lake |  | IL | McHenry | Withdrawn | ComEd | 455 | 435 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/27/2014 | 10/2/2014 | Customer Initiated Withdrawal | 5/1/2018
PJM | Z2-042 | Wurno-Clayor 138kV |  | VA | Pulaski | Withdrawn | AEP | 180 | 23.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 2/28/2014 | 10/25/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | Z2-043 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/5/2014 |  |  | 12/31/2015 | 12/31/2015
PJM | Z2-044 | Whitakers 34.5kV | Whitakers Solar Park | NC | Nash | In Service | Dominion | 12 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/5/2014 |  |  | 12/31/2015 | 12/31/2015
PJM | Z2-046 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 1050 | 900 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/14/2014 |  |  | 12/31/2018 | 2/20/2018
PJM | Z2-048 | George Washington 138kV | Moundsville Power, LLC | WV | Marshall | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/26/2014 | 4/27/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | Z2-056 | Crossmans-Werner 34.5kV |  | NJ | Middlesex | In Service | JCPL | 0.5 | 0 | Energy | Generation Interconnection | Solar | Not Required | Not Required | Not Required | Document Posted | 3/31/2014 |  |  | 12/31/2015 | 8/4/2016
PJM | Z2-060 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Withdrawn | PEPCO | 33 | 116 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2014 | 12/23/2020 |  | 3/1/2022
PJM | Z2-062 | Gloucester 26kV | Camden County Energy Recovery Associates | NJ | Camden | In Service | PSEG | 0 | 3 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 4/2/2014 |  |  | 5/1/2015 | 11/19/2014
PJM | Z2-064 | Smith-N. Fayette 138kV |  | PA | Washington | Withdrawn | APS | 651 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/10/2014 | 6/25/2015 | Customer Initiated Withdrawal | 6/1/2018
PJM | Z2-073 | Chestertown West 25kV |  | MD | Kent | Withdrawn | DPL | 5 | 3.36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/22/2014 | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016
PJM | Z2-074 | Chestertown East 25kV |  | MD | Kent | Withdrawn | DPL | 6 | 4.03 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/22/2014 | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016
PJM | Z2-075 | Lynch East 25kV |  | MD | Kent | Withdrawn | DPL | 5.5 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/22/2014 | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016
PJM | Z2-076 | Worcester South 25kV | Worcester South | MD | Worcester | In Service | DPL | 2.64 | 1.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/22/2014 |  |  | 12/31/2018 | 5/29/2019
PJM | Z2-077 | Worcester North 25kV | Worcester North | MD | Worcester | In Service | DPL | 5 | 3.33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/22/2014 |  |  | 12/31/2018 | 3/15/2019
PJM | Z2-081 | Streator 34.5kV | Livingston Landfill Gas to Energy Facility | IL | Livingston | In Service | ComEd | 13.3 | 13.3 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted |  | Document Posted | 4/28/2014 |  |  | 12/1/2014 | 4/4/2017
PJM | Z2-082 | Cape May County 12kV | Cape May County Municipal Utilities Authority Landfill | NJ | Cape May | In Service | AEC | 0 | 0.3 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2014 |  |  | 6/1/2015 | 6/1/2015
PJM | Z2-083 | Mickleton 230kV | West Deptford Energy Station | NJ | Gloucester | In Service | AEC | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2014 |  |  | 12/31/2018 | 12/31/2018
PJM | Z2-084 | JK Smith 345kV |  | KY | Nelson | Withdrawn | EKPC | 207.8 | 207.8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/29/2014 | 10/7/2014 | Customer Milestone Not Met | 12/1/2016
PJM | Z2-085 | Mahoning Valley Hydro 25kV | Mahoning Creek Hydroelectric Plant | PA | Clarion | In Service | APS | 1.5 | 1.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2014 |  |  | 11/1/2014 | 10/10/2014
PJM | Z2-086 |  |  | IL | Adams | Withdrawn | ComEd |  |  | Energy | Generation Interconnection | Wind | Withdrawn |  |  |  | 4/29/2014 | 5/21/2014 | Customer Milestone Not Met
PJM | Z2-087 | Pontiac MidPoint-Brokaw 345kV | Bright Stalk Wind Farm | IL | Livingston | In Service | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2014 |  |  | 12/30/2019 | 12/16/2019
PJM | Z2-088 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 80 | 30.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2014 |  |  | 11/30/2015 | 12/21/2015
PJM | Z2-089 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 568 | 541 | Capacity | Generation Interconnection | Natural Gas; Oil | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2014 |  |  | 6/1/2018 | 5/2/2018
PJM | Z2-090 | Blackhawk 12.5kV |  | IL | Winnebago | Withdrawn | ComEd | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 | 6/13/2016 | Customer Initiated Withdrawal | 10/1/2014
PJM | Z2-091 | Woodsdale Road |  | OH | Butler | Withdrawn | DEOK | 36 | 36 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/30/2014 | 5/19/2014 | Customer Initiated Withdrawal | 12/31/2014
PJM | Z2-092 | Bennett-Farmingdale 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 4/30/2014 | 10/1/2014 | Customer Milestone Not Met | 12/31/2015
PJM | Z2-093 | Hawks 12kV |  | NJ | Hunterdon | Withdrawn | JCPL | 3.5 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/30/2014 | 5/29/2014 | Customer Initiated Withdrawal | 12/31/2014
PJM | Z2-094 | Washington-Mobile Chemical 34kV |  | NJ | Warren | Withdrawn | JCPL | 10 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/30/2014 | 7/15/2014 | Customer Initiated Withdrawal | 12/31/2014
PJM | Z2-095 | Branchville-Sussex 34kV |  | NJ | Sussex | Withdrawn | JCPL | 10 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 4/30/2014 | 10/1/2014 | Customer Milestone Not Met | 12/31/2015
PJM | Z2-096 | Lynch West 25kV |  | MD | Kent | Withdrawn | DPL | 10 | 7.07 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/30/2014 | 4/22/2015 | Customer Initiated Withdrawal | 5/1/2016
PJM | Z2-097 | Church 25kV | Church | MD | Kent | Withdrawn | DPL | 5 | 3.54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/30/2014 | 3/5/2019 |  | 9/28/2019
PJM | Z2-099 | Boykins 34.5kV | Boykins Solar | VA | Southampton | Withdrawn | Dominion | 8.5 | 5.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 | 1/25/2018 |  | 5/31/2019
PJM | Z2-100 | Boykin 115kV |  | VA | Unknown | Withdrawn | Dominion |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2014 | 5/9/2014 | Customer Initiated Withdrawal
PJM | Z2-101 | Frackville-Fishbach 69kV |  | PA | Schuylkill | Withdrawn | PPL | 67.5 | 8.78 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 4/30/2014 | 5/15/2015 | Customer Milestone Not Met | 12/31/2016
PJM | Z2-102 | Argonne-New Lisbon 34.5kV | Dix Solar Farm | NJ | Burlington | In Service | JCPL | 13 | 4.94 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 |  |  | 8/24/2017 | 7/13/2017
PJM | Z2-103 | North Meshoppen 34.5kV III | Roundtop Energy Project | PA | Susquehanna | In Service | PENELEC | 1 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2014 |  |  | 12/1/2016 | 1/28/2016
PJM | Z2-104 | Oxbow 34.5 kV II | Oxbow Creek Generation Plant | PA | Wyoming | In Service | PENELEC | 1.6 | 1.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 |  |  | 10/30/2019 | 11/16/2019
PJM | Z2-105 | Bell-Mariana 25kV | Ten Mile Generation Facility | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 | 2/25/2015 | Customer Initiated Withdrawal | 7/1/2016
PJM | Z2-106 | Washington-Bell 25kV | Amity Generation Facility | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 | 1/29/2019 |  | 6/30/2017
PJM | Z2-107 | East Carbondale-Lackawanna 69kV | Waymart Battery Energy Storage System | PA | Wayne | Withdrawn | PPL | 10 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2014 | 12/22/2022 |  | 12/15/2020
PJM | Z2-108 | Meyersdale North 115kV | Meyersdale Wind Farm & Battery Energy Storage System | PA | Somerset | In Service | PENELEC | 18 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2014 |  |  | 12/31/2015 | 12/17/2015
PJM | Z2-109 | South River 230kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2014 | 3/21/2019 |  | 5/16/2019
PJM | Z2-112 | Waterford 345kV |  | OH | Washington | In Service | AEP | 97 | 64.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2014 |  |  | 6/1/2015 | 6/15/2015
PJM | Z2-113 | Watervliet 12.47kV | Watervliet Solar Facility | MI | Berrien | In Service | AEP | 4.6 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 |  |  | 12/15/2016 | 11/8/2016
PJM | Z2-114 | Olive 12.47kV | Olive Solar Facility | IN | St. Joseph | In Service | AEP | 5 | 2.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 |  |  | 12/15/2016 | 8/26/2016
PJM | Z2-115 | Deer Creek 12.47kV | Deer Creek Solar Facility | IN | Grant | In Service | AEP | 2.5 | 1.25 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 |  |  | 3/1/2016 | 1/6/2016
PJM | Z2-116 | Twin Branch 12.47kV | Twin Branch Solar Facility | IN | St. Joseph | In Service | AEP | 2.6 | 1.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/30/2014 |  |  | 7/31/2016 | 8/18/2016
PJM | AA1-006 | Erie County Landfill | Erie County Landfill | OH | Erie | In Service | ATSI | 0.8 | 0.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/2/2014 |  |  | 9/30/2015 | 12/31/2015
PJM | AA1-007 | Smith Gap Regional Landfill |  | VA | Roanoke | Withdrawn | AEP | 6 | 6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 6/19/2014 | 1/7/2016 | Customer Milestone Not Met | 6/1/2016
PJM | AA1-013 | Hanging Rock 765kV | Cornu | OH | Lawrence | In Service | AEP | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/23/2014 |  |  | 10/1/2015 | 11/1/2015
PJM | AA1-014 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/23/2014 |  |  | 10/1/2015 | 11/1/2015
PJM | AA1-015 | Fayette II | Fayette Energy Facility | PA | Fayette | In Service | APS | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/23/2014 |  |  | 1/1/2016 | 12/14/2015
PJM | AA1-016 | Portland 1 |  | PA | Monroe | Withdrawn | ME | 158 | 158 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Withdrawn | 6/25/2014 | 11/18/2015 | Customer Milestone Not Met | 6/1/2017
PJM | AA1-017 | Portland 2 |  | PA | Monroe | Withdrawn | ME | 243 | 243 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Withdrawn | 6/25/2014 | 11/18/2015 | Customer Milestone Not Met | 6/1/2017
PJM | AA1-018 | Powerton-Goodings Grove | Otter Creek Wind Farm | IL | Livingston | In Service | ComEd | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 6/25/2014 |  |  | 1/17/2020 | 1/9/2020
PJM | AA1-019 | Beaverbrook 13kV | Gloucester Solar Farm | NJ | Camden | Withdrawn | PSEG | 7.3 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/9/2014 | 7/27/2017 | Customer Initiated Withdrawal | 9/30/2015
PJM | AA1-020 | Andersontown Road #2 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/10/2014 | 8/18/2014 | Customer Initiated Withdrawal
PJM | AA1-021 | Andersontown Rd #2 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/10/2014 | 8/18/2014 | Customer Initiated Withdrawal
PJM | AA1-022 | Andersontown Rd #3 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/10/2014 | 8/18/2014 | Customer Initiated Withdrawal
PJM | AA1-023 | Andersontown Rd #4 |  | MD | Caroline | Withdrawn | DPL | 1.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/10/2014 | 11/25/2014 | Customer Initiated Withdrawal | 6/30/2015
PJM | AA1-025 | Oak Hall A |  | VA | Unknown | In Service | DPL | 0 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/11/2014 |  |  | 10/15/2016 | 12/8/2016
PJM | AA1-026 | Oak Hall B |  | VA | Unknown | In Service | DPL | 0 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/11/2014 |  |  | 12/30/2016 | 12/8/2016
PJM | AA1-027 | Oak Hall C |  | VA | Unknown | In Service | DPL | 0 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/11/2014 |  |  | 12/30/2017 | 12/8/2016
PJM | AA1-028 | Oak Hall D |  | VA | Unknown | In Service | DPL | 0 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/11/2014 |  |  | 12/30/2017 | 12/8/2016
PJM | AA1-032 | Kingsport Mill | Kingsport Mill | TN | Sullivan | Deactivated | AEP | 0 | 45 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Not Required | Document Posted | 7/21/2014 |  |  | 6/1/2015 | 5/24/2017
PJM | AA1-033 | Hay Road 230kV |  | DE | New Castle | Withdrawn | DPL | 80 | 80 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 7/23/2014 | 10/21/2015 | Customer Initiated Withdrawal | 6/18/2018
PJM | AA1-034 | Peach Bottom 500kV | Delta York | PA | York | In Service | PECO | 120 | 70 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/24/2014 |  |  | 12/31/2018 | 12/11/2018
PJM | AA1-036 | Mountain 230kV |  | PA | Luzerne | Withdrawn | UGI | 180 | 180 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 8/11/2014 | 4/6/2016 | Customer Initiated Withdrawal | 6/1/2017
PJM | AA1-037 | Piney Hydro 34.5kV | Piney Station (Piney 1-3) | PA | Clarion | In Service | PENELEC | 5.26 | 5.26 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 8/13/2014 |  |  | 6/1/2015 | 6/19/2015
PJM | AA1-038 | Lexington-Low Moor 230kV | Rocky Forge Wind | VA | Botetourt | Suspended | Dominion | 78.2 | 10.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/19/2014 |  |  | 12/31/2025
PJM | AA1-040 | Morris | Morris Cogen | IL | Grundy | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/27/2014 |  |  | 6/1/2015 | 1/28/2016
PJM | AA1-041 | Tioga 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/27/2014 | 4/2/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | AA1-042 | Ontelaunee |  | PA | Bradford | Withdrawn | ME | 0 | 52.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/27/2014 | 11/18/2015 | Customer Initiated Withdrawal | 11/4/2016
PJM | AA1-043 | Ontelaunee 230kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 34.1 | 19.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/27/2014 |  |  | 9/30/2017 | 9/30/2017
PJM | AA1-044 | Shenango-Hoytdale 345kV | Hickory Run Energy Station | PA | Lawrence | In Service | ATSI | 1000 | 870 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/27/2014 |  |  | 3/30/2020 | 10/31/2019
PJM | AA1-045 | McConnellsburg-Guilford 138kV |  | PA | Venango | Withdrawn | APS | 308 | 308 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/29/2014 | 11/3/2015 | Customer Milestone Not Met | 12/18/2015
PJM | AA1-046 | Somerset-Allegheny 115kV | Kimberly Run Wind Farm | PA | Somerset | Withdrawn | PENELEC | 80 | 10.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/29/2014 | 6/21/2018 |  | 12/29/2018
PJM | AA1-047 | Hazelton-Jennings 138kV | Garrett County Wind Facility | MD | Garrett | Withdrawn | APS | 69.1 | 9.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/29/2014 | 1/12/2020 |  | 12/1/2018
PJM | AA1-048 | Kendall |  | IL | Grundy | Withdrawn | ComEd | 800 | 780 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 8/29/2014 | 4/13/2015 | Customer Milestone Not Met | 12/1/2018
PJM | AA1-049 | Shawboro-Sligo 230kV | Shawboro East Ridge Solar Park | NC | Currituck | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2014 | 6/5/2017 | Customer Milestone Not Met | 11/30/2019
PJM | AA1-050 | Tarboro-Everetts 230kV | Conetoe II Solar Park | NC | Edgecombe | In Service | Dominion | 0 | 25.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2014 |  |  | 11/30/2015 | 12/21/2015
PJM | AA1-056 | Bay Shore-Fostoria 345kV & Bay Shore-Monroe 345kV | Oregon Energy Center | OH | Lucas | In Service | ATSI | 161 | 46 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/10/2014 |  |  | 5/15/2017 | 6/23/2017
PJM | AA1-057 | Sunbury-Milton 69kV | Northumberland Wood Fired Power Plant | PA | Northumberland | Withdrawn | PPL | 16 | 16 | Capacity | Generation Interconnection | Wood | Document Posted | Document Posted | Not Required | Document Posted | 9/10/2014 | 9/30/2019 |  | 9/30/2019
PJM | AA1-059 | Crisfield 25kV | Ibis | MD | Somerset | Withdrawn | DPL | 6 | 4.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 9/16/2014 | 5/23/2018 |  | 6/30/2020
PJM | AA1-060 | Great Adventure 34.5kV | Plumsted Energy Storage Facility | NJ | Monmouth | In Service | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 9/22/2014 |  |  | 10/31/2018 | 12/11/2018
PJM | AA1-061 | Jacktown-East New Market 69kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 13.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/23/2014 | 4/24/2018 |  | 12/31/2016
PJM | AA1-062 | Williams 138kV | Mt. Storm Wind Force | WV | Grant | Withdrawn | APS | 150 | 22.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2014 | 9/25/2020 |  | 12/31/2018
PJM | AA1-063 | Huntsville (Cabin Creek) 69kV |  | IN | Randolph | Withdrawn | AEP | 3.6 | 3.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Withdrawn | 9/26/2014 | 4/6/2016 | Customer Initiated Withdrawal | 3/31/2016
PJM | AA1-063A | Carolina–Seaboard 115kV | Spuds Lane Solar Park | NC | Northhampton | In Service | Dominion | 74.9 | 50.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2014 |  |  | 8/17/2018 | 11/8/2018
PJM | AA1-064 | Carson-Wake 500kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2014 | 2/1/2017 | Customer Initiated Withdrawal | 12/31/2015
PJM | AA1-065 | Earleys 230kV | Aulander Holloman Solar Park | NC | Hertford | In Service | Dominion | 80 | 53.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2014 |  |  | 12/31/2018 | 1/9/2019
PJM | AA1-066 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 0 | 80 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2014 |  |  | 12/31/2018 | 8/31/2018
PJM | AA1-067 | Everetts 34.5kV | Williamston Speight Solar | NC | Martin | In Service | Dominion | 15 | 10.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2014 |  |  | 12/31/2016 | 1/24/2017
PJM | AA1-068 | Wilson 34.5kV |  | MD | Washington | Withdrawn | Unknown | 3.5 | 2.33 | Capacity | Generation Interconnection | Solar | Document Posted | Not Required | Not Required | Withdrawn | 10/1/2014 | 6/17/2015 | Customer Initiated Withdrawal | 5/1/2016
PJM | AA1-070 | Hatfield 500kV | Hatfield Ferry, Units 1, 2, and 3 | PA | Greene | Withdrawn | APS | 1710 | 1590 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 10/6/2014 | 11/23/2016 | Customer Initiated Withdrawal | 6/1/2019
PJM | AA1-072 | Kelford 34.5kV | Kelford Solar Park | NC | Bertie | In Service | Dominion | 3.1 | 2.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/13/2014 |  |  | 12/31/2015 | 12/31/2015
PJM | AA1-073 | Metuchen 26kV | Middlesex Plant | NJ | Middlesex | Withdrawn | PSEG | 5.6 | 3.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/14/2014 | 4/27/2017 | Customer Initiated Withdrawal | 12/16/2016
PJM | AA1-075 | Huron 23kV |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 7.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/21/2014 | 5/29/2015 | Customer Initiated Withdrawal | 11/1/2015
PJM | AA1-076 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 1050 | 1000 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/22/2014 |  |  | 3/1/2021 | 9/22/2019
PJM | AA1-077 | Lackawanna 230kV | Lackawanna Thermal Generating Station | PA | Lackawanna | In Service | PPL | 113 | 34 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/23/2014 |  |  | 4/1/2019 | 1/21/2019
PJM | AA1-078 | University Park North | University Park North Energy Center | IL | Will | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/23/2014 |  |  | 10/14/2015 | 6/1/2016
PJM | AA1-079 | Emilie 230kV | Ford Mill | PA | Bucks | In Service | PECO | 74 | 74 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/24/2014 |  |  | 6/1/2015 | 9/13/2016
PJM | AA1-080 | Wilson 34.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Not Required | Not Required | Wholesale Market Participation Agreement | 10/24/2014 | 3/3/2019 |  | 10/31/2016
PJM | AA1-081 | Cooksville 13kV |  | MD | Howard | Withdrawn | BGE | 3 | 2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/24/2014 | 5/1/2015 | Customer Milestone Not Met | 5/1/2016
PJM | AA1-082 | E. Towanda 230kV | Liberty/Asylum Township Plant | PA | Bradford | In Service | PENELEC | 57.5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/24/2014 |  |  | 1/29/2016 | 8/25/2016
PJM | AA1-083 | Four Rivers 230kV | Doswell Facility | VA | Hanover | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/27/2014 |  |  | 6/1/2017 | 8/31/2015
PJM | AA1-084 | Reybold 138kV | PBF Delaware City Refinery Units G3, G6 & G7 | DE | New Castle | In Service | DPL | 0 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/27/2014 |  |  | 6/1/2018 | 6/19/2015
PJM | AA1-085 | Moshannon-Milesburg 230kV | Centre County Wind Facility | PA | Centre | Withdrawn | APS | 82 | 10.66 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/29/2014 | 12/11/2018 |  | 6/1/2019
PJM | AA1-086 | Blue Mound-Latham |  | IL | Macon | Withdrawn | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 10/29/2014 | 2/23/2016 | Customer Milestone Not Met | 10/1/2017
PJM | AA1-091 | Dover 12kV |  | DE | Kent | Withdrawn | DPL | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2014 | 3/6/2015 | Customer Initiated Withdrawal | 11/1/2015
PJM | AA1-092 | Halfway 34.5kV | Perennial Solar Project | MD | Washington | Withdrawn | APS | 12 | 8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2014 | 5/20/2024 |  | 12/31/2024
PJM | AA1-093 | Clear Spring 12.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Not Required | Not Required | Wholesale Market Participation Agreement | 10/30/2014 | 10/18/2019 |  | 10/31/2016
PJM | AA1-094 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 6 | 4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/30/2014 | 3/19/2015 | Customer Milestone Not Met | 5/1/2016
PJM | AA1-095 | Halfway-Marlowe 34.5kV | Pinesburg Solar Project | MD | Washington | In Service | APS | 4.25 | 2.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2014 |  |  | 1/16/2020 | 5/27/2020
PJM | AA1-096 | Wilson 12.5kV |  | MD | Washington | Withdrawn | APS | 3.5 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Not Required | Not Required | Wholesale Market Participation Agreement | 10/30/2014 | 3/7/2019 |  | 10/31/2016
PJM | AA1-097 | Oyster Creek 230kV |  | NJ | Ocean | Withdrawn | JCPL | 100 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/30/2014 | 4/14/2015 | Customer Milestone Not Met | 6/1/2018
PJM | AA1-098 | Raritan River-Red Oak 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 560 | 560 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/30/2014 | 11/2/2016 | Customer Initiated Withdrawal | 5/30/2018
PJM | AA1-099 | Clinton Co. 34.5kV | Clinton County Energy Storage Project | OH | Clinton | In Service | DEOK | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2014 |  |  | 10/31/2016 | 8/29/2016
PJM | AA1-100 | Warrior Run 138kV | AES Warrior Run Energy Storage | PA | Allegheny | In Service | APS | 11 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2014 |  |  | 10/31/2015 | 10/15/2015
PJM | AA1-101 | Tait 69kV |  | OH | Montgomery | Withdrawn | Dayton | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2014 | 12/13/2017 |  | 5/1/2018
PJM | AA1-102 | Kings Creek-Loretto 138kV | Perry Road Solar | MD | Somerset | Partially in Service - Under Construction | DPL | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2014 |  |  | 12/31/2023 | 12/28/2017
PJM | AA1-103 | Harwood-Siegfried 230kV |  | PA | Carbon | Withdrawn | PPL | 208.5 | 27 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 10/30/2014 | 9/15/2016 | Customer Milestone Not Met | 6/1/2016
PJM | AA1-104 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 10/30/2014 | 11/20/2018 |  | 6/30/2017
PJM | AA1-105 | Thorofare 13kV |  | NJ | Gloucester | Withdrawn | PSEG | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/30/2014 | 3/19/2015 | Customer Initiated Withdrawal | 11/1/2015
PJM | AA1-106 | Grover II 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2014 | 2/2/2019 |  | 12/31/2016
PJM | AA1-107 | Kings Creek-Pocomoke 138kV |  | MD | Somerset | Withdrawn | DPL | 19.9 | 15.9 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 10/30/2014 | 3/31/2015 | Customer Initiated Withdrawal | 12/1/2016
PJM | AA1-108 | Churchtown 230kV | Deepwater | NJ | Salem | Withdrawn | AEC | 158 | 158 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2014 | 2/7/2019 |  | 12/1/2021
PJM | AA1-109 | Cotoctin-Troutville Junction 34.5kV | Frederick Road Solar | MD | Frederick | In Service | APS | 9 | 4.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2014 |  |  | 10/31/2017 | 10/23/2017
PJM | AA1-110 | Massey 25kV | Blue Star Solar Project | MD | Kent | Withdrawn | DPL | 6 | 4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/31/2014 | 8/17/2017 |  | 10/17/2019
PJM | AA1-111 | Moshannon-East Towanda 230kV | Renovo Energy Center | PA | Clinton | Withdrawn | PENELEC | 463 | 463 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2014 | 4/20/2023 |  | 6/30/2025
PJM | AA1-112 | Westmoreland 25kV | Westmoreland Landfill Project | PA | Westmoreland | Withdrawn | APS | 7.2 | 4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2014 | 2/21/2017 | Customer Initiated Withdrawal | 8/16/2017
PJM | AA1-113 | Frackville-Hauto 69kV |  | PA | Schuylkill | Withdrawn | PPL | 68 | 8.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 10/31/2014 | 4/7/2015 | Customer Milestone Not Met | 12/30/2017
PJM | AA1-114 | Harwood-East Hazelton #2 69kV |  | PA | Carbon | Withdrawn | PPL | 60 | 7.72 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2014 | 9/20/2016 | Customer Initiated Withdrawal | 12/30/2017
PJM | AA1-115 | Thirty First Street 115kV |  | PA | Blair | Withdrawn | PENELEC | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2014 | 11/17/2016 | Customer Initiated Withdrawal | 6/1/2016
PJM | AA1-116 | Kensington/Kankakee |  | IL | Kankakee | Withdrawn | ComEd | 18.4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn | Interim Study | 10/31/2014 | 10/11/2018 |  | 6/1/2016
PJM | AA1-117 | Kensington/Kankakee |  | IL | Kankakee | Withdrawn | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn | Interim Study | 10/31/2014 | 10/11/2018 |  | 9/1/2016
PJM | AA1-118 | Picway 69kV |  | OH | Pickaway | Withdrawn | AEP | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/31/2014 | 5/15/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | AA1-121 | South Granville 12kV | Denison University | OH | Licking | Withdrawn | AEP | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2014 | 4/18/2017 | Customer Initiated Withdrawal | 1/31/2018
PJM | AA1-122 | Antietam 34.5kV |  | MD | Washington | Withdrawn | APS | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2014 | 11/3/2015 | Customer Milestone Not Met | 9/2/2016
PJM | AA1-123 | Highland-Sammis 345kV | South Field Energy Power Plant | OH | Columbiana | In Service | ATSI | 1152 | 1105 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2014 |  |  | 7/29/2021 | 6/14/2021
PJM | AA1-124 | Englishtown-Monroe 34kV |  | NJ | Middlesex | Withdrawn | JCPL | 1.5 | 0.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2014 | 10/13/2015 | Customer Initiated Withdrawal | 8/1/2016
PJM | AA1-125 | Seaman 138kV |  | OH | Brown | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2014 | 7/7/2015 | Customer Initiated Withdrawal | 10/1/2016
PJM | AA1-126 | Hillcrest 138kV |  | OH | Brown | Withdrawn | DEOK | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2014 | 6/5/2015 | Customer Milestone Not Met | 10/1/2016
PJM | AA1-127 | Andersontown Road 25kV |  | MD | Caroline | Withdrawn | DPL | 6 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2014 | 4/24/2015 | Customer Initiated Withdrawal | 8/1/2016
PJM | AA1-128 | Glen Lyn |  | VA | Giles | Withdrawn | AEP | 10 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 10/31/2014 | 7/24/2015 | Customer Initiated Withdrawal | 10/1/2016
PJM | AA1-129 | Northbrook-Skokie |  | IL | Cook | Withdrawn | ComEd | 27 | 27 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2014 | 7/1/2016 | Customer Milestone Not Met | 6/1/2018
PJM | AA1-130 | St. Claire 13kV |  | OH | Franklin | Withdrawn | AEP | 5 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn | Not Required | Withdrawn | 10/31/2014 | 3/31/2016 | Customer Milestone Not Met | 11/1/2015
PJM | AA1-131 | N. Towanda 34.5kV | Bradford Natural Gas Facility | PA | Bradford | Withdrawn | PENELEC | 8 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2014 | 12/3/2015 | Customer Initiated Withdrawal | 12/1/2016
PJM | AA1-132 | Shawboro-Sligo 230kV | Shawboro East Ridge Solar Park | NC | Currituck | Withdrawn | Dominion | 60 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2014 | 6/5/2017 | Customer Milestone Not Met | 10/31/2015
PJM | AA1-133 | Hickory-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2014 | 2/1/2017 | Customer Initiated Withdrawal | 10/31/2015
PJM | AA1-134 | Sunbury-WinFall 230kV |  | NC | Gates | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Interim Study | 10/31/2014 | 2/15/2017 | Customer Initiated Withdrawal | 10/31/2015
PJM | AA1-135 | Earleys-Everetts 230kV | Aulander Earleys Solar | NC | Bertie | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2014 | 5/11/2017 | Customer Milestone Not Met | 11/15/2019
PJM | AA1-136 | Cashie-E. Trowbridge 230kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2014 | 12/1/2014 | Customer Milestone Not Met | 10/31/2015
PJM | AA1-137 | Earleys-Northampton 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2014 | 12/1/2014 | Customer Milestone Not Met | 10/31/2015
PJM | AA1-138 | Earleys-Suffolk 230kV | Haslett Solar Park | NC | Gates | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2014 | 6/7/2017 | Customer Milestone Not Met | 11/15/2019
PJM | AA1-139 | Hickory-Shawboro 230kV | Summit Farms Solar and Ranchland Solar | NC | Currituck | In Service | Dominion | 120 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2014 |  |  | 2/28/2018 | 3/6/2018
PJM | AA1-140 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2014 | 10/27/2017 |  | 6/30/2018
PJM | AA1-141 | Kenney 25kV |  | MD | Worcester | Withdrawn | DPL | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2014 | 10/27/2017 |  | 10/31/2016
PJM | AA1-142 | Vienna-Laurel 69kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2014 | 10/29/2015 | Customer Initiated Withdrawal | 10/31/2016
PJM | AA1-143 | Easton-Wye Mills 69kV |  | MD | Talbot | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2014 | 10/29/2015 | Customer Initiated Withdrawal | 10/31/2016
PJM | AA1-144 | East Towanda-Grover 230kV | Gateway Bradford Plant | PA | Bradford | Withdrawn | PENELEC | 163 | 163 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2014 | 10/12/2021 | Customer Milestone Not Met | 11/30/2021
PJM | AA1-145 | Four Rivers 230kV | Doswell SC Units 2 & 3 | VA | Hanover | In Service | Dominion | 340 | 340 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2014 |  |  | 7/1/2018 | 5/30/2018
PJM | AA1-146 | Nelson | Invenergy Nelson Expansion LLC | IL | Lee | In Service | ComEd | 190 | 157 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2014 |  |  | 5/31/2023 | 5/20/2023
PJM | AA2-001 | Reusens 34.5kV |  | VA | Campbell | Withdrawn | AEP | 12.5 | 2 | Capacity | Generation Interconnection | Hydro | Withdrawn |  |  |  | 11/3/2014 | 9/10/2015 | Customer Milestone Not Met | 12/8/2014
PJM | AA2-008 | Saegers 230 kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 57 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 11/6/2014 |  |  | 9/1/2016 | 9/1/2016
PJM | AA2-011 | Winslow Township |  | NJ | Camden | Withdrawn | AEC | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 11/24/2014 | 9/9/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | AA2-017 | East Palmerton-Acahela 69kV | Penn Forest Wind Project | PA | Carbon | Withdrawn | PPL | 98 | 12.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 11/26/2014 | 10/13/2021 |  | 12/31/2020
PJM | AA2-020 | Albright-Cross School 138kV |  | MD | Garrett | Withdrawn | APS | 15 | 15 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 12/5/2014 | 10/29/2015 | Customer Milestone Not Met | 5/30/2017
PJM | AA2-021 | Steele 25kV |  | MD | Caroline | Withdrawn | DPL | 7 | 2.67 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/5/2014 | 10/6/2015 | Customer Milestone Not Met | 12/31/2015
PJM | AA2-029 | Everetts 34.5kV |  | NC | Martin | Withdrawn | Dominion | 8 | 5.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 12/18/2014 | 10/2/2015 | Customer Initiated Withdrawal | 12/15/2015
PJM | AA2-030 | Nelson | Invenergy Nelson Expansion LLC | IL | Lee | In Service | ComEd | 190 | 157 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 12/24/2014 |  |  | 5/31/2023 | 5/20/2023
PJM | AA2-035 | Collins |  | IL | Grundy | Withdrawn | ComEd | 1019.3 | 1019.3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 12/30/2014 | 10/15/2018 |  | 6/30/2019
PJM | AA2-036 | West Cambridge 12kV |  | MD | Dorchester | Withdrawn | DPL | 14 | 5.3 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/9/2015 | 10/6/2015 | Customer Milestone Not Met | 12/31/2015
PJM | AA2-037 | Preston 12kV |  | MD | Caroline | Withdrawn | DPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 1/9/2015 | 10/6/2015 | Customer Milestone Not Met | 12/31/2015
PJM | AA2-039 | Kewanee 138 kV |  | IL | Henry | Withdrawn | ComEd | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 1/23/2015 | 4/16/2020 |  | 12/1/2016
PJM | AA2-040 | Kings Fork 34.5kV |  | VA | City of Suffolk | Withdrawn | Dominion |  |  | Energy | Generation Interconnection | Biomass | Withdrawn |  |  |  | 1/30/2015 | 2/24/2015 | Customer Milestone Not Met | 8/31/2015
PJM | AA2-043 | Smith-N. Fayette 138kV |  | PA | Washington | Withdrawn | APS | 67 | 99 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/2/2015 | 6/25/2015 | Customer Initiated Withdrawal | 6/1/2018
PJM | AA2-044 | Sherman Avenue 69kV |  | NJ | Cumberland | Withdrawn | AEC | 13.5 | 7.3 | Capacity | Generation Interconnection | Solar; Biomass | Document Posted | Document Posted | Document Posted | Withdrawn | 2/6/2015 | 8/30/2017 | Customer Milestone Not Met | 12/1/2016
PJM | AA2-048 | Allenwood-Larrabee 34kV | Lakewood-Farmingdale Road Solar Farm & Storage Facility | NJ | Monmouth | In Service | JCPL | 7 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 2/19/2015 |  |  | 8/31/2022 | 3/17/2023
PJM | AA2-049 | Atlantic-Oceanview 34kV | Tinton Falls Solar & Storage Facility | NJ | Monmouth | Withdrawn | JCPL | 3 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 2/18/2015 | 1/6/2020 |  | 6/30/2017
PJM | AA2-050 | Penrose #1 230klV |  | PA | Philadelphia | Withdrawn | PECO | 210 | 210 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/18/2015 | 3/10/2015 | Customer Milestone Not Met | 5/1/2018
PJM | AA2-051 | Penrose #2 230kV |  | PA | Philadelphia | Withdrawn | PECO | 130 | 130 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/19/2015 | 3/10/2015 | Customer Milestone Not Met | 5/1/2018
PJM | AA2-052 | Essex 26kV |  | NJ | Essex | In Service | PSEG | 0 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/20/2015 |  |  | 2/12/2015 | 9/11/2015
PJM | AA2-053 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 74.9 | 52.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/23/2015 |  |  | 6/19/2019 | 7/10/2019
PJM | AA2-055 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2015 | 5/4/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | AA2-056 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2015 | 5/4/2015 | Customer Initiated Withdrawal | 6/1/2016
PJM | AA2-057 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 66 | 44.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2015 |  |  | 12/1/2019 | 11/26/2019
PJM | AA2-058 | Mount Rose 13kV | Hopewell Valley Solar | NJ | Mercer | In Service | PSEG | 1 | 0.3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/28/2015 |  |  | 5/1/2016 | 12/30/2015
PJM | AA2-059 | Edenton 15kV | Edenton Solar | NC | Chowan | Withdrawn | Dominion | 10 | 6.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2015 | 4/5/2018 |  | 12/31/2018
PJM | AA2-060 | Branchville-Sussex #1 34kV | Roy Road Battery Storage Facility | NJ | Sussex | In Service | JCPL | 6 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Document Posted | 2/28/2015 |  |  | 7/31/2023 | 8/14/2023
PJM | AA2-061 | Branchville-Sussex #2 34.5kV | Roy Road Battery Storage Facility | NJ | Sussex | In Service | JCPL | 8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 2/27/2015 |  |  | 7/31/2023 | 8/14/2023
PJM | AA2-062 | Branchville-N. Newton #1 34.kV |  | NJ | Sussex | Withdrawn | JCPL | 7 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 2/27/2015 | 5/6/2016 | Customer Milestone Not Met | 12/1/2015
PJM | AA2-063 | Branchville-N. Newton #2 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 2/27/2015 | 5/6/2016 | Customer Milestone Not Met | 12/1/2015
PJM | AA2-064 | Branchville-N. Newton #3 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 17 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 2/27/2015 | 4/3/2017 | Customer Milestone Not Met | 12/1/2015
PJM | AA2-065 | Hazen Switch Point-Washington 34.5kV |  | NJ | Warren | Withdrawn | JCPL | 8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 2/27/2015 | 9/2/2016 | Customer Milestone Not Met | 12/1/2015
PJM | AA2-066 | Penns Neck 13kV | Princeton Hospital NRG Energy Center | NJ | Mercer | In Service | PSEG | 2 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2015 |  |  | 6/1/2016 | 8/16/2017
PJM | AA2-067 | Belvidere |  | IL | Boone | Withdrawn | ComEd | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 2/27/2015 | 11/29/2016 | Customer Initiated Withdrawal | 6/1/2017
PJM | AA2-068 | South Justice 115kV | N301 Solar | NC | Halifax | Withdrawn | Dominion | 20 | 13.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 2/27/2015 | 4/3/2018 |  | 8/31/2018
PJM | AA2-069 | Cartanza 230kV | Garrison Energy Center | DE | New Castle | Withdrawn | DPL | 451 | 451 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/27/2015 | 6/5/2023 |  | 6/1/2024
PJM | AA2-069A | Peckville-Jackson 69kV |  | PA | Wayne | Withdrawn | PPL | 64.6 | 8 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 2/27/2015 | 3/26/2015
PJM | AA2-070 | Smith Mountain 138kV | Smith Mountain Hydro | VA | Henry | In Service | AEP | 34 | 34 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted |  | Document Posted | 2/28/2015 |  |  | 12/31/2018 | 12/31/2018
PJM | AA2-072 | Kingsville 13kV | Kingsville Solar | MD | Harford | In Service | BGE | 1.1 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/9/2015 |  |  | 5/1/2016 | 6/14/2016
PJM | AA2-075 | Southwest Lima 345kV |  | OH | Van Wert | Withdrawn | AEP | 250 | 33 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 3/16/2015 | 1/27/2017 | Customer Initiated Withdrawal | 3/14/2022
PJM | AA2-076 | Linwood 230kV | Phillips Island CT1, CT2, CT3 & ST4 | PA | Delaware | In Service | PECO | 0 | 18 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/27/2015 |  |  | 4/27/2021
PJM | AA2-077 | Penrose #1 230kV |  | PA | Philadelphia | Withdrawn | PECO | 220 | 220 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 3/27/2015 | 5/31/2018 |  | 5/1/2018
PJM | AA2-078 | Penrose #2 230kV |  | PA | Philadelphia | Withdrawn | PECO | 130 | 130 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/27/2015 | 11/12/2015 | Customer Milestone Not Met | 5/1/2018
PJM | AA2-079 | Possum Point 230kV | Possum Point Unit 6 | VA | Prince William | In Service | Dominion | 28 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/30/2015 |  |  | 10/31/2016 | 7/27/2016
PJM | AA2-080 | Ellsworth-Eppler Junction 25kV |  | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 3/31/2015 | 12/2/2015 | Customer Initiated Withdrawal | 6/1/2017
PJM | AA2-081 | Niles Valley 34.5kV | Niles Valley 34.5kV | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2015 | 3/15/2018 |  | 8/28/2018
PJM | AA2-082 | Alpha 34.5kV | Alpha Battery Storage Facility | NJ | Warren | In Service | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Document Posted | 3/31/2015 |  |  | 10/20/2018 | 1/28/2019
PJM | AA2-083 | South Troy 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/31/2015 | 5/5/2016 | Customer Milestone Not Met | 6/1/2017
PJM | AA2-084 | Lappans Road 12.5kV |  | MD | Washington | Withdrawn | APS | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 3/31/2015 | 9/20/2016 | Customer Initiated Withdrawal | 11/2/2016
PJM | AA2-085 | General Office 12.5kV |  | MD | Washington | Withdrawn | APS | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2015 | 9/6/2019 |  | 9/5/2016
PJM | AA2-086 | Boykins 34.5kV | Boykins Solar | VA | Southampton | Withdrawn | Dominion | 4.5 | 3.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2015 | 1/25/2018 |  | 10/31/2017
PJM | AA2-087 | Boykins 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/31/2015 | 10/5/2015 | Customer Milestone Not Met | 9/5/2016
PJM | AA2-088 | Boykins-Handsome 115kV | Newsoms Solar | VA | Southampton | In Service | Dominion | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2015 |  |  | 12/1/2017 | 12/15/2017
PJM | AA2-098 | George Washington (Moundsville) |  | WV | Marshall | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/20/2015 | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018
PJM | AA2-099 | Sewaren 230kV | Sewaren 7 | NJ | Middlesex | In Service | PSEG | 0 | 32 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/21/2015 |  |  | 6/1/2018 | 6/5/2018
PJM | AA2-100 | Brown 34.5kV | Bio Energy Landfill Facility | OH | Brown | In Service | DEOK | 4.8 | 4.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 4/22/2015 |  |  | 10/31/2018 | 5/10/2017
PJM | AA2-103 | Backbone Mountain 138kV | Backbone Mountain Energy Storage | WV | Tucker | Withdrawn | APS | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 4/24/2015 | 10/31/2022 |  | 7/31/2022
PJM | AA2-104 | Bigby 115kV |  | PA | Somerset | Withdrawn | PENELEC | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/24/2015 | 7/27/2016 | Customer Milestone Not Met | 12/30/2016
PJM | AA2-105 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 13.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  | Interim Study | 4/24/2015 | 9/28/2016 | Customer Initiated Withdrawal | 3/31/2017
PJM | AA2-106 | Bluff Point 69kV |  | IN | Jay | Withdrawn | AEP | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/24/2015 | 3/13/2018 |  | 12/31/2018
PJM | AA2-107 | Waterman 34kV |  | IL | DeKalb | Withdrawn | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/24/2015 | 10/22/2018 |  | 12/1/2016
PJM | AA2-109 | Rock Springs-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PECO | 1100 | 1100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/27/2015 | 2/4/2016 |  | 6/1/2019
PJM | AA2-110 | Eddystone 230kV |  | PA | Delaware | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/27/2015 | 2/4/2016 |  | 6/1/2019
PJM | AA2-111 | Cochranville-Peach Bottom 230kV |  | PA | Lancaster | Withdrawn | PECO | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/27/2015 | 2/4/2016 |  | 6/1/2019
PJM | AA2-112 | Tiffany 34.5kV |  | PA | Susquehanna | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 4/27/2015 | 11/14/2017 | Customer Initiated Withdrawal | 6/1/2017
PJM | AA2-113 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 16 | 10.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/28/2015 | 9/28/2016 | Customer Initiated Withdrawal | 3/31/2017
PJM | AA2-114 | Furnace Brook-Hazen Switch Point 34kV |  | NJ | Union | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/28/2015 | 5/2/2016 | Customer Initiated Withdrawal | 4/1/2016
PJM | AA2-115 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 450 | 450 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/28/2015 |  |  | 6/1/2019 | 2/7/2019
PJM | AA2-116 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | In Service | AEP | 994 | 994 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/28/2015 |  |  | 3/15/2022 | 12/27/2021
PJM | AA2-117 | Sussex |  | NJ | Sussex | Withdrawn | JCPL | 16 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/28/2015 | 6/2/2016 | Customer Milestone Not Met | 5/2/2016
PJM | AA2-118 | Murphy-Tunis 115kV |  | NC | Hertford | Withdrawn | Dominion | 35.2 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2015 | 5/6/2015 | Customer Initiated Withdrawal | 6/30/2017
PJM | AA2-119 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 |  |  | 3/31/2028
PJM | AA2-120 | Tower Hill 115kV |  | PA | Tioga | Withdrawn | PENELEC | 250 | 250 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/29/2015 | 5/25/2016 | Customer Milestone Not Met | 6/1/2020
PJM | AA2-121 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I | WV | Brooke | Withdrawn | APS | 685 | 685 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2015 | 10/10/2020 |  | 8/3/2021
PJM | AA2-122 | Parlin 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/29/2015 | 5/24/2016 | Customer Milestone Not Met | 5/1/2016
PJM | AA2-123 | Marengo 34kV | Marengo Battery Storage | IL | McHenry | In Service | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2015 |  |  | 9/30/2018 | 11/19/2018
PJM | AA2-124 | Sewaren 230kV |  | NJ | Middlesex | Withdrawn | PSEG | 576 | 553 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/29/2015 | 9/10/2015 | Customer Initiated Withdrawal | 5/31/2019
PJM | AA2-125 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 580.08 | 504 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2015 | 9/9/2015 | Customer Initiated Withdrawal | 5/31/2017
PJM | AA2-126 | Thorofare 13kV |  | NJ | Gloucester | Withdrawn | PSEG | 5 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/30/2015 | 6/5/2015 | Customer Initiated Withdrawal | 4/1/2016
PJM | AA2-127 | Bear Garden 230kV | Bear Garden Facility | VA | Buckingham | In Service | Dominion | 7 | 32.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 9/30/2017 | 5/1/2016
PJM | AA2-128 | Raritan River-Werner 115kV |  | NJ | Middlesex | Withdrawn | JCPL | 175 | 70 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/30/2015 | 8/24/2017 | Customer Initiated Withdrawal | 6/27/2017
PJM | AA2-129 | New Church 138kV |  | VA | Accomack | Withdrawn | DPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 4/30/2015 | 6/8/2018 |  | 12/31/2016
PJM | AA2-130 | Kings Creek-Crisfield 69kV | CleanBay Biomass Generator | MD | Somerset | Withdrawn | DPL | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/30/2015 | 5/8/2019 |  | 9/25/2018
PJM | AA2-131 | Oak Grove 138kV | Oak Grove 138kV | WV | Pleasants | In Service | APS | 0 | 18 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 3/30/2018 | 5/25/2018
PJM | AA2-132 | Thompson 34.5kV | Thompson 34.5kV | PA | Susquehanna | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 | 12/7/2020 |  | 9/28/2018
PJM | AA2-133 | Wyalusing 34.5kV | Wyalusing 34.5kV | PA | Bradford | In Service | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 |  |  | 5/31/2019 | 2/21/2019
PJM | AA2-134 | Andrew Shaft-84 Junction 25kV |  | PA | Washington | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/2015 | 10/29/2015 | Customer Milestone Not Met | 6/1/2017
PJM | AA2-135 | East Towanda 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/30/2015 | 5/17/2016 | Customer Milestone Not Met | 6/1/2017
PJM | AA2-136 | Kendall |  | IL | Kendall | Withdrawn | ComEd | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/2015 | 10/2/2015 | Customer Milestone Not Met | 5/1/2016
PJM | AA2-137 | Hanging Rock 765kV - Power Block 1 | Cornu | OH | Lawrence | In Service | AEP | 45 | 45 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 5/1/2019 | 12/2/2016
PJM | AA2-138 | Hanging Rock 765kV - Power Block 2 | Cornu | OH | Lawrence | In Service | AEP | 45 | 45 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 5/1/2019 | 12/2/2016
PJM | AA2-139 | Ronco 500kV | Fayette Energy Facility | PA | Fayette | In Service | APS | 45 | 45 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 10/1/2017 | 4/21/2017
PJM | AA2-140 | Printz 230kV | Liberty Electric | PA | Delaware | In Service | PECO | 35 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 5/1/2016 | 6/30/2017
PJM | AA2-141 | Washington 345kV | Washington Energy Facility | OH | Washington | In Service | AEP | 45 | 45 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 8/31/2016 | 12/2/2016
PJM | AA2-142 | Branchburg-Deans 500kV |  | NJ | Somerset | Withdrawn | PSEG | 1377 | 1278 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/2015 | 2/2/2016 | Customer Initiated Withdrawal | 6/1/2021
PJM | AA2-143 | Catoctin 12.5kV |  | MD | Frederick | Withdrawn | APS | 4 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/30/2015 | 10/26/2016 | Customer Initiated Withdrawal | 9/15/2016
PJM | AA2-144 | East New Market 12kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 6.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/30/2015 | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016
PJM | AA2-145 | Catoctin 34.5kV | Hessong Birdge Solar Facility | MD | Frederick | Withdrawn | APS | 20 | 10.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2015 | 7/22/2019 |  | 9/15/2017
PJM | AA2-146 | Catoctin 34.5kV |  | MD | Frederick | Withdrawn | APS | 20 | 10.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/30/2015 | 7/13/2016 | Customer Milestone Not Met | 9/15/2016
PJM | AA2-147 | Todd 12kV |  | MD | Dorchester | Withdrawn | DPL | 4 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/30/2015 | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016
PJM | AA2-148 | Madison-Tanners Creek 138kV |  | IN | Fayette | Withdrawn | AEP | 174.2 | 22.75 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 4/30/2015 | 4/20/2021 |  | 12/31/2017
PJM | AA2-149 | Carolina-Seaboard 115kV |  | NC | Northhampton | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2015 | 10/6/2015 | Customer Milestone Not Met | 12/15/2015
PJM | AA2-150 | Trappe 12kV |  | MD | Talbot | Withdrawn | DPL | 10 | 6.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/30/2015 | 4/29/2016 | Customer Initiated Withdrawal | 9/15/2016
PJM | AA2-151 | Delano-Scioto Trail 138kV |  | OH | Ross | Withdrawn | AEP | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/18/2015 |  | 6/30/2016
PJM | AA2-152 | Keeney-Steel 230kV |  | MD | Caroline | Withdrawn | DPL | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/20/2015 | Customer Milestone Not Met | 6/30/2016
PJM | AA2-153 | Yellow Springs 34.5kV |  | MD | Frederick | Withdrawn | APS | 4 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/30/2015 | 8/22/2016 | Customer Initiated Withdrawal | 9/15/2016
PJM | AA2-154 | Watkins Corner 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/30/2015 | 10/2/2015 | Customer Initiated Withdrawal | 11/30/2015
PJM | AA2-155 | Mt. Lena 12.5kV |  | MD | Washington | Withdrawn | APS | 4 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/30/2015 | 9/19/2016 | Customer Initiated Withdrawal | 9/15/2016
PJM | AA2-156 | Aydlett-Shawboro 230kV |  | NC | Currituck | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/22/2015 | Customer Milestone Not Met | 6/30/2016
PJM | AA2-157 | Cashie-Trowbridge 230kV |  | NC | Martin | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/22/2015 | Customer Milestone Not Met | 6/30/2016
PJM | AA2-158 | Louisa 34.5kV |  | VA | Louisa | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/21/2015 | Customer Milestone Not Met | 11/30/2015
PJM | AA2-159 | Downsville 34.5kV | Route 632 Washington Solar Facility | MD | Washington | Withdrawn | APS | 16 | 8.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2015 | 7/21/2020 |  | 9/15/2017
PJM | AA2-160 | Bridgeville 12kV |  | DE | Sussex | Withdrawn | DPL | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/18/2015 |  | 11/30/2015
PJM | AA2-161 | Yukon-Robbins 138kV | Allegheny Energy Center LLC | PA | Allegheny | Withdrawn | APS | 541 | 513 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 5/1/2015 | 10/17/2023 |  | 9/1/2027
PJM | AA2-162 | Elizabeth City-Shawboro 230kV |  | NC | Camden | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/22/2015 | Customer Milestone Not Met
PJM | AA2-163 | Wakefield 12.5kV |  | VA | Sussex | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/21/2015 | Customer Milestone Not Met | 11/30/2015
PJM | AA2-164 | Murphy 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/21/2015 | Customer Milestone Not Met | 11/30/2015
PJM | AA2-165 | Hornertown-Whitakers 115kV | Chestnut Solar | NC | Halifax | In Service | Dominion | 8.9 | 5.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 |  |  | 12/1/2019 | 11/26/2019
PJM | AA2-166 | Shenango-Bedford 69kV |  | PA | Lawrence | Withdrawn | ATSI | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/30/2015 | 7/8/2016 | Customer Milestone Not Met | 6/1/2017
PJM | AA2-167 | East Sayre 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/30/2015 | 7/8/2016 | Customer Milestone Not Met | 6/1/2017
PJM | AA2-168 | Prince George's County |  | MD | Prince George's | Withdrawn | PEPCO | 4 | 1.52 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 8/27/2015 | Customer Milestone Not Met | 12/31/2016
PJM | AA2-169 | Five Forks 115kV | Five Forks Solar | NC | Warren | Withdrawn | Dominion | 20 | 13.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/30/2015 | 4/3/2018 |  | 8/31/2018
PJM | AA2-170 | Burches Hill-Brandywine 230kV | Mattawoman Energy | MD | Prince George's | Withdrawn | PEPCO | 111.1 | 92 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 | 12/23/2020 |  | 3/1/2022
PJM | AA2-171 | Sunbury #1 500kV | Sunbury Generation Facility | PA | Snyder | In Service | PPL | 97 | 60 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 3/15/2018 | 6/1/2018
PJM | AA2-173 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 515 | 515 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 |  |  | 5/9/2021 | 4/1/2021
PJM | AA2-174 | Carolina-Jackson 115kV | Gutenberg Solar | NC | Northhampton | In Service | Dominion | 5 | 2.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 |  |  | 4/22/2019 | 7/10/2019
PJM | AA2-175 | Suffolk-Sunbury 230kV |  | NC | Gates | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/22/2015 | Customer Milestone Not Met | 6/30/2016
PJM | AA2-176 | Indian River-Piney Grove 230kV |  | DE | Sussex | Withdrawn | DPL | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/21/2015 | Customer Milestone Not Met | 6/30/2016
PJM | AA2-177 | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 | 10/13/2017 |  | 11/15/2021
PJM | AA2-178 | Mackeys 230kV | Ablemarle Beach Solar | NC | Washington | In Service | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 |  |  | 4/20/2021 | 12/23/2020
PJM | AA2-179 | Creswell-Mackeys 115kV |  | NC | Washington | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/22/2015 | Customer Milestone Not Met | 6/30/2015
PJM | AA2-180 | Hickory 34.5kV | Chesapeake Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2015 | 9/29/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AA2-181 | Earleys-Northampton 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/30/2015 | 5/22/2015 | Customer Milestone Not Met | 6/30/2016
PJM | AA2-182 | Sunbury #2 500kV |  | PA | Snyder | Withdrawn | PPL | 1030 | 977 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 4/30/2015 | 5/4/2020 |  | 9/2/2019
PJM | AA2-183 | Tosco-VFT 230kV |  | NJ | Union | Withdrawn | PSEG | 234 | 230 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/30/2015 | 2/11/2016 |  | 6/1/2019
PJM | AA2-184 | Atlantic-Red Bank 34kV | Atlantic-RedBank 34.5kV Solar | NJ | Monmouth | In Service | JCPL | 20 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 4/30/2015 |  |  | 12/5/2019 | 12/31/2019
PJM | AA2-185 | Independent Hill 115kV |  | VA | Prince William | Withdrawn | Dominion | 1.6 | 0 | Energy | Generation Interconnection | Methane | Withdrawn |  |  |  | 4/30/2015 | 9/15/2015 | Customer Initiated Withdrawal | 1/31/2016
PJM | AA2-186 | Forest 69kV |  | OH | Hardin | Withdrawn | AEP | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/30/2015 | 5/11/2017 | Customer Initiated Withdrawal | 12/1/2016
PJM | AB1-001 | Absecon 12 kV | Oak Street Landfill Solar Project | NJ | Atlantic | In Service | AEC | 2.3 | 0.87 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 5/1/2015 |  |  | 3/30/2020 | 9/30/2020
PJM | AB1-002 | Atlantic-South River 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 909 | 765 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 5/1/2015 | 4/25/2016 | Customer Milestone Not Met | 6/1/2019
PJM | AB1-003 | Keystone-Conemaugh 500kV |  | PA | Indiana | Withdrawn | PENELEC | 1474 | 1474 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 5/4/2015 | 4/18/2016 | Customer Initiated Withdrawal | 12/31/2019
PJM | AB1-004 | Solar Holler |  |  |  | Withdrawn | AEP | 0.4 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/4/2015 | 5/19/2015 |  | 10/1/2015
PJM | AB1-005 | Harrisonville 13kV |  | MD | Baltimore County | Withdrawn | BGE | 1.3 | 0 | Energy | Generation Interconnection | Natural Gas | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 5/18/2015 | 7/2/2021 |  | 12/1/2021
PJM | AB1-006 | Meadow Lake 345kV | Meadow Lake Wind Farm VI | IN | White | In Service | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/22/2015 |  |  | 12/31/2018 | 12/21/2018
PJM | AB1-010 | Quakertown |  | NJ | Hunterdon | Withdrawn | JCPL | 0.5 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 5/27/2015 | 6/18/2015 | Customer Milestone Not Met | 4/1/2015
PJM | AB1-011 | Bear Branch 13kV |  | MD | Prince George's | Withdrawn | BGE | 0.5 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 5/27/2015 | 6/18/2015 |  | 5/15/2015
PJM | AB1-012 | Hackettstown |  | NJ | Warren | Withdrawn | JCPL | 0.5 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 5/27/2015 | 6/18/2015 | Customer Milestone Not Met | 4/1/2015
PJM | AB1-013 | Riders Creek 115kV | Little Alligator Windfarm | NC | Tyrell | Withdrawn | Dominion | 130 | 16.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/29/2015 | 5/22/2018 |  | 12/31/2020
PJM | AB1-014 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | In Service | DEOK | 125 | 47.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/8/2015 |  |  | 12/31/2020 | 12/18/2020
PJM | AB1-015 | Evergreen 138kV | Warren Natural Gas Generation Faciility | OH | Trumbull | In Service | ATSI | 16.5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/16/2015 |  |  | 10/1/2017 | 10/10/2016
PJM | AB1-017 | Highland-Sammis 345 kV & Highland-Mansfield 345 kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 140 | 64 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 6/18/2015 |  |  | 12/31/2018 | 8/11/2018
PJM | AB1-020 | Cold Spring 240v |  | MD | Baltimore City | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 6/29/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-021 | West Caldwell 13kV | West Caldwell Solar | NJ | Essex | In Service | PSEG | 2 | 0.3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/29/2015 |  |  | 12/1/2016 | 6/1/2018
PJM | AB1-022 | Columbia 115kV |  | VA | Louisa | Withdrawn | Dominion | 2 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 7/6/2015 | 4/6/2020 |  | 3/31/2017
PJM | AB1-025 | Lumberton 13kV | Lumberton Solar | NJ | Burlington | In Service | PSEG | 6.8 | 2.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/21/2015 |  |  | 12/1/2016 | 8/22/2016
PJM | AB1-026 | Westmoreland 34.5kV | Montross Solar | VA | Westmoreland | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/22/2015 | 5/25/2017 | Customer Milestone Not Met | 11/15/2020
PJM | AB1-027 | Old Church 34.5 KV | Mechanicsville Solar | VA | Hanover | In Service | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/22/2015 |  |  | 12/1/2020 | 9/23/2020
PJM | AB1-028 | Boykins 34.5kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/27/2015 | 8/14/2015 |  | 8/31/2016
PJM | AB1-030 | Huron 69kV |  | NJ | Atlantic | Withdrawn | AEC | 7.5 | 3.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 7/28/2015 | 6/28/2016 | Customer Milestone Not Met | 12/1/2016
PJM | AB1-031 | North Wales 34kV |  | PA | Montgomery | Withdrawn | PECO | 9 | 0 | Energy | Generation Interconnection | Diesel | Withdrawn |  |  |  | 7/29/2015 | 7/29/2015
PJM | AB1-032 | Lee Station Southwest 12kV |  | OH | Athens | Withdrawn | AEP | 3.3 | 1.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/31/2015 | 8/1/2017 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB1-033 | North Wales 34.5kV | Morris Road | PA | Montgomery | In Service | PECO | 4 | 4.1 | Capacity | Generation Interconnection | Diesel | Document Posted | Document Posted | Document Posted | Document Posted | 8/12/2015 |  |  | 6/1/2020 | 9/3/2020
PJM | AB1-034 | Maintou 34.5kV |  | NJ | Ocean | Withdrawn | JCPL | 0.6 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 8/12/2015 | 4/8/2016 | Customer Milestone Not Met | 9/1/2015
PJM | AB1-035 | Mill Creek 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-036 | Howard 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-037 | Ridgeview 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-038 | Shadyside 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-039 | Lipins Corner 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-040 | Glendale 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-041 | Hunt Club 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-042 | Wall Cove 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-043 | Riva Road 240v |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-044 | Highland 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-045 | East Towson 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-046 | Sudbrook Park 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 8/15/2015
PJM | AB1-047 | Highland 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-048 | Texas 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-049 | Friendship Manor 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-050 | High Ridge 240v |  | MD | Howard | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/14/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-051 | Lutherville 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/24/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-052 | Bengies 240v |  | MD | Baltimore County | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 8/24/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-053 | Hornertown 34.5kV |  | NC | Halifax | Withdrawn | Dominion | 10 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/24/2015 | 1/13/2017 | Customer Initiated Withdrawal | 11/15/2017
PJM | AB1-054 | Boykins 115kV |  | VA | Southampton | Withdrawn | Dominion | 60 | 40.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 8/24/2015 | 12/13/2016 | Customer Initiated Withdrawal | 12/31/2018
PJM | AB1-055 | Balls Gap 34.5kV | Balls Gap Battery Facility | WV | Cabell | Deactivated | AEP | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2015 |  |  | 12/1/2016 | 3/1/2017
PJM | AB1-056 | Indian River 230kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Engineering and Procurement | DPL | 247.8 | 64.4 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2015 |  |  | 12/31/2027
PJM | AB1-057 | Indian River 230kV II |  | DE | Sussex | Withdrawn | DPL | 251.8 | 65.4 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 8/31/2015 | 8/16/2018 |  | 3/1/2020
PJM | AB1-058 | Gavin Unit #1 765kV | Gavin #1 | OH | Gallia | In Service | AEP | 11 | 11 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted |  | Document Posted | 8/31/2015 |  |  | 12/31/2017 | 12/31/2017
PJM | AB1-059 | Old Church 34.5kV |  | VA | Hanover | Withdrawn | Dominion | 5 | 3.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 8/31/2015 | 3/31/2016 | Customer Initiated Withdrawal | 1/1/2017
PJM | AB1-063 | Locust St. 13kV | Cooper Solar | NJ | Camden | In Service | PSEG; PSEG | 0.4 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/1/2015 |  |  | 12/1/2016 | 2/15/2017
PJM | AB1-064 | Monessen 25kV | Westmoreland Landfill Project | PA | Westmoreland | Withdrawn | APS | 4 | 2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2015 | 2/21/2017 | Customer Initiated Withdrawal | 8/16/2017
PJM | AB1-065 | Jennings-Hoyes 34.5kV | CleanLight Power Solar Facility | MD | Garrett | Withdrawn | APS | 10.9 | 4.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2015 | 11/20/2020 |  | 10/31/2019
PJM | AB1-066 | Lime Kiln-Aqueduct 34.5kV |  | MD | Frederick | Withdrawn | APS | 19.8 | 7.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2015 | 3/2/2016 | Customer Initiated Withdrawal | 12/15/2016
PJM | AB1-067 | Unionville 12.5kV |  | VA | Orange | Withdrawn | Dominion | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted |  |  |  | 8/31/2015 | 4/4/2016 | Customer Milestone Not Met | 9/26/2016
PJM | AB1-068 | Eldred-Frackville 230kV |  | PA | Schuylkill | Withdrawn | PPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/8/2015 | 10/2/2017 |  | 5/1/2019
PJM | AB1-069 | Wylie Ridge 500kV | Beech Hollow Energy Center | PA | Washington | Withdrawn | APS | 1025 | 950 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/9/2015 | 3/25/2021 |  | 2/28/2023
PJM | AB1-070 | Emporia-Trego 115kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2015 | 9/28/2015 | Customer Initiated Withdrawal | 12/15/2017
PJM | AB1-071 | Greenbury Point 240V |  | MD | Anne Arundel | Withdrawn | BGE | 0.005 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 9/11/2015 | 9/27/2019 |  | 12/31/2015
PJM | AB1-072 | Hancock-Marlowe 34.5kV |  | MD | Washington | Withdrawn | APS | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 9/14/2015 | 7/13/2016 | Customer Milestone Not Met | 7/1/2016
PJM | AB1-073 | Eddystone 138kV |  | PA | Delaware | Withdrawn | PECO | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/17/2015 | 12/15/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB1-074 | Richmond 230kV |  | PA | Philadelphia | Withdrawn | PECO | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/17/2015 | 12/15/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB1-075 | Riverside 115kV |  | MD | Baltimore County | Withdrawn | BGE | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/17/2015 | 12/16/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB1-076 | Fourmile Ridge 138kV |  | MD | Garrett | Withdrawn | APS | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/17/2015 | 11/9/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB1-077 | Suffolk-WinFall 230kV |  | NC | Perquimans | Withdrawn | Dominion | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 9/21/2015 | 11/21/2016 | Customer Initiated Withdrawal | 12/31/2019
PJM | AB1-078 | Wilson 34.5kV |  | PA | Washington | Withdrawn | APS | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 9/22/2015 | 5/18/2016 | Customer Initiated Withdrawal | 12/1/2016
PJM | AB1-079 | Zion 12kV |  | IL | Lake | Withdrawn | ComEd | 6.5 | 6.5 | Capacity | Generation Interconnection | Methane | Document Posted |  |  |  | 9/25/2015 | 8/5/2016 | Customer Milestone Not Met | 12/29/2016
PJM | AB1-080 | Dumont-Olive 345kV | St. Joseph's Energy Center, LLC | IN | St. Joseph | In Service | AEP | 40 | 40 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2015 |  |  | 4/29/2018 | 4/1/2018
PJM | AB1-081 | Anaconda-Mayo Dunbar 115kV | Harts Mill Solar | NC | Edgecombe | In Service | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2015 |  |  | 12/7/2020 | 12/21/2020
PJM | AB1-082 | Potter 46kV | IMG Generation Potter Facility | PA | Potter | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2015 | 9/18/2020 |  | 9/30/2019
PJM | AB1-083 | McDowell-Sharon 69kV |  | PA | Susquehanna | Withdrawn | ATSI | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 9/30/2015 | 5/5/2016 | Customer Milestone Not Met | 12/1/2017
PJM | AB1-084 | Greenfield-Elk Mountain 69kV |  | PA | Susquehanna | Withdrawn | PPL | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2015 | 6/14/2018 |  | 12/1/2017
PJM | AB1-085 | North Aurora |  | IL | Kane | Withdrawn | ComEd | 20 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/30/2015 | 11/29/2016 | Customer Initiated Withdrawal | 9/1/2016
PJM | AB1-086 | Pontiac Midpoint 345kV |  | IL | McLean | Withdrawn | ComEd | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/30/2015 | 4/27/2017 | Customer Initiated Withdrawal | 6/1/2019
PJM | AB1-087 | Sullivan 345kV #1 | Sullivan Generating Station 1 | IN | Sullivan | Engineering and Procurement | AEP | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2015 |  |  | 6/1/2025
PJM | AB1-088 | Sullivan 345kV #2 | Sullivan Generating Station 2 | IN | Sullivan | Engineering and Procurement | AEP | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2015 |  |  | 6/1/2025
PJM | AB1-089 | Byron-Wayne 345kV #1 | Byron to Wayne Thermal #1 Project | IL | Lee | Suspended | ComEd | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2015 |  |  | 6/1/2026
PJM | AB1-090 | Byron-Wayne 345kV #2 |  | IL | Lee | Withdrawn | ComEd | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 9/30/2015 | 10/18/2018 |  | 6/1/2019
PJM | AB1-091 | Davis Creek 345kV |  | IL | Kankakee | Withdrawn | ComEd | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2015 | 4/11/2022 |  | 6/1/2019
PJM | AB1-092 | Moshannon-East Towanda 230kV | Renovo Energy Center | PA | Clinton | Withdrawn | PENELEC | 41 | 17 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2015 | 4/20/2023 |  | 6/30/2025
PJM | AB1-093 | Oakland |  | NJ | Bergen | Withdrawn | RE | 0.85 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/5/2015 | 10/12/2015 |  | 12/1/2015
PJM | AB1-094 | Rio Grande 12kV |  | NJ | Cape May | Withdrawn | AEC | 0.85 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/5/2015 | 10/12/2015 |  | 12/1/2015
PJM | AB1-095 | Rona 12kV | Dovetail Biogas Facility | OH | Greene | In Service | ATSI | 0.85 | 0 | Energy | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/6/2015 |  |  | 12/31/2016 | 9/30/2016
PJM | AB1-096 | Carroll-Mt. Airy 34.5kV | Union Bridge Solar Facility | MD | Carroll | In Service | APS | 8.166 | 3.134 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/7/2015 |  |  | 2/28/2022 | 4/21/2022
PJM | AB1-097 | Harrisonburg-Stauton 115kV |  | VA | Rockingham | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/7/2015 | 4/26/2016 | Customer Initiated Withdrawal | 11/10/2017
PJM | AB1-098 | Walkersville 12kV | Walkersville Solar Facility | MD | Frederick | Withdrawn | APS | 8.16 | 5.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/8/2015 | 6/23/2017 | Customer Initiated Withdrawal | 1/1/2019
PJM | AB1-099 | Sunnymeade Road 13kV |  | NJ | Somerset | Withdrawn | PSEG | 2 | 0 | Energy | Generation Interconnection | Storage | Not Required | Not Required | Not Required | Wholesale Market Participation Agreement | 10/13/2015 | 6/16/2017 | Customer Initiated Withdrawal | 9/1/2016
PJM | AB1-104 | Camden 26kV |  | NJ | Camden | Withdrawn | PSEG | 9.9 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/21/2015 | 2/22/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB1-105 | Highland-Hanna 345kV | Trumbull Energy Center | OH | Trumbull | Under Construction | ATSI | 940 | 850 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/22/2015 |  |  | 8/12/2025
PJM | AB1-106 | Yukon-Hatfield 500kV | Smithton Generating Station | PA | Westmoreland | In Service | APS | 10 | 40 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/22/2015 |  |  | 3/1/2019 | 11/18/2018
PJM | AB1-107 | Bayshore-GM Powertrain 138 kV & Lallendorf 345kV | Cedar Point Energy Center | OH | Lucas | Withdrawn | ATSI | 955 | 860 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/22/2015 | 9/12/2023 |  | 11/30/2024
PJM | AB1-108 | Lackawanna 500 kV |  | PA | Lackawanna | Withdrawn | PPL | 485 | 485 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/23/2015 | 5/15/2019 |  | 6/19/2019
PJM | AB1-109 | Mountaineer | Mountaineer #1 | WV | Unknown | Partially in Service - Under Construction | AEP | 36 | 36 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted |  | Document Posted | 10/26/2015 |  |  | 6/1/2021 | 12/31/2018
PJM | AB1-110 | Cochranville-Peach Bottom 230kV |  | PA | Lancaster | Withdrawn | PECO | 70 | 70 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/27/2015 | 2/4/2016 |  | 6/1/2019
PJM | AB1-111 | Rock Springs-Peach Bottom 500kV |  | PA | Lancaster | Withdrawn | PECO | 135 | 135 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/27/2015 | 2/4/2016 |  | 6/1/2019
PJM | AB1-112 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/27/2015 |  |  | 5/9/2021 | 4/1/2021
PJM | AB1-113 | East New Market 12kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/27/2015 | 3/24/2016 | Customer Initiated Withdrawal | 12/1/2016
PJM | AB1-114 | Masury-Maysvile 69kV |  | PA | Mercer | Withdrawn | ATSI | 12.5 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/28/2015 | 3/2/2017 | Customer Milestone Not Met | 1/27/2017
PJM | AB1-115 | Painesville 13kV | Lake County Generating Station | OH | Lake | Withdrawn | ATSI | 3.1 | 2.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/28/2015 | 2/8/2017 | Customer Initiated Withdrawal | 12/31/2017
PJM | AB1-116 | Egg Harbor Road 12kV |  | NJ | Atlantic | In Service | AEC | 0.787 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/28/2015 |  |  | 12/1/2016 | 2/1/2018
PJM | AB1-117 | Cunningham 500kV |  | VA | Fluvanna | Withdrawn | Dominion | 17.3 | 17.3 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/28/2015 | 11/4/2015 | Customer Initiated Withdrawal | 4/24/2016
PJM | AB1-118 | Trenton 13kV |  | NJ | Mercer | Withdrawn | PSEG | 0.735 | 0.735 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/28/2015 | 11/2/2015 | Customer Initiated Withdrawal | 1/31/2016
PJM | AB1-119 | Tansboro Road 12kV | Tansboro Road | NJ | Camden | In Service | AEC | 0.735 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/28/2015 |  |  | 7/1/2017 | 2/1/2018
PJM | AB1-120 | King of Prussia |  | PA | Montgomery | Withdrawn | PECO | 0.8 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/28/2015 | 4/22/2016 | Customer Initiated Withdrawal | 3/14/2016
PJM | AB1-122 | Kendall-Tazewell & Dresden-Mole Creek | Three Rivers Energy Center | IL | Grundy | In Service | ComEd | 1160 | 1150 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2015 |  |  | 6/20/2023 | 6/16/2023
PJM | AB1-123 | Showalter 34.5kV | Mason Dixon Solar Center Facility | MD | Washington | Withdrawn | APS | 18.4 | 7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/29/2015 | 5/4/2021 |  | 9/30/2018
PJM | AB1-124 | Carroll-Monocacy 34.5kV | Legore Bridge Solar Center Facility | MD | Frederick | Engineering and Procurement | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/29/2015 |  |  | 9/1/2025
PJM | AB1-125 | Carroll-Monocacy 34.5kV | Biggs Ford Solar Facility | MD | Frederick | Engineering and Procurement | APS | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 10/30/2015 |  |  | 9/1/2025
PJM | AB1-126 | McConnellsburg-Mercersburg 34.5kV |  | PA | Franklin | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2015 | 7/12/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB1-127 | St. Thomas-Guilford 34.5kV | St. Thomas Township Solar Facility | PA | Franklin | In Service | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/29/2015 |  |  | 8/31/2020 | 8/21/2020
PJM | AB1-128 | St. Thomas-Mercersburg 34.5kV | St. Thomas Township Solar Facility II | PA | Franklin | In Service | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/29/2015 |  |  | 8/31/2020 | 9/8/2020
PJM | AB1-129 | Mercersburg-Milnor 34.5kV |  | PA | Franklin | Withdrawn | APS | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/29/2015 | 7/12/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB1-130 | Loretto 69kV |  | MD | Somerset | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/29/2015 | 11/17/2015 | Customer Initiated Withdrawal | 6/1/2017
PJM | AB1-131 | South Joliet |  | IL | Will | Withdrawn | ComEd | 6 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/30/2015 | 2/3/2016 |  | 6/1/2016
PJM | AB1-132 | Thelma 230kV | Gaston Green Acres Solar | NC | Northhampton | In Service | Dominion | 120 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/2/2015 |  |  | 12/25/2023 | 8/22/2024
PJM | AB1-133 | Chestertown 69kV |  | MD | Somerset | Withdrawn | DPL | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/30/2015 | 11/16/2015 | Customer Milestone Not Met | 11/1/2016
PJM | AB1-134 | Wye Mills-Centreville 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 60 | 42 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/30/2015 | 11/16/2015 | Customer Milestone Not Met | 11/1/2016
PJM | AB1-135 | Chickahominy 34.5kV | Charles City Solar | VA | Unknown | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2015 | 6/7/2017 | Customer Milestone Not Met | 11/15/2019
PJM | AB1-136 | Picway Solar 138kV |  | OH | Franklin | Withdrawn | AEP | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/30/2015 | 11/17/2015 | Customer Milestone Not Met | 11/1/2016
PJM | AB1-137 | Frankford 25kV | Millsboro Solar | DE | Sussex | Withdrawn | DPL | 6 | 4.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/30/2015 | 12/7/2020 |  | 3/26/2021
PJM | AB1-138 | Navy 34.5kV | Lakehurst Solar Farm | NJ | Ocean | In Service | JCPL | 9.6 | 3.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 10/30/2015 |  |  | 8/18/2020 | 3/24/2020
PJM | AB1-139 | Metuchen 26kV | Nixon Lane Solar | NJ | Middlesex | In Service | PSEG | 6.6 | 2.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2015 |  |  | 12/1/2016 | 5/26/2017
PJM | AB1-140 | George Washington 138kV I |  | WV | Marshall | Withdrawn | AEP | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/30/2015 | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018
PJM | AB1-141 | Church-Wye Mills 138 kV I | Pondtown Solar 1 | MD | Queen Anne's | In Service | DPL | 19.8 | 13.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2015 |  |  | 12/31/2023 | 10/18/2022
PJM | AB1-142 | Church-Wye Mills 138 kV II | Pondtown Solar 1 | MD | Queen Anne's | In Service | DPL | 19.8 | 13.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2015 |  |  | 12/31/2023 | 10/18/2022
PJM | AB1-143 | George Washington 138kV II |  | WV | Marshall | Withdrawn | AEP | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/30/2015 | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018
PJM | AB1-144 | Shawville 230kV | Shawville Generating Station | PA | Clearfield | In Service | PENELEC | 590 | 590 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2015 |  |  | 12/21/2017 | 10/24/2016
PJM | AB1-145 | Winslow 12kV |  | NJ | Camden | Withdrawn | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/30/2015 | 12/11/2017 |  | 12/23/2016
PJM | AB1-146 | Sabrooke 12kV |  | IL | Winnebago | Withdrawn | ComEd | 2 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/30/2015 | 2/21/2017 | Customer Initiated Withdrawal | 6/1/2016
PJM | AB1-147 | Hoytdale 138kV |  | PA | Beaver | Withdrawn | ATSI | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 10/30/2015 | 3/25/2016 | Customer Initiated Withdrawal | 11/1/2016
PJM | AB1-148 | Branchburg-Deans 500kV |  | NJ | Somerset | Withdrawn | PSEG | 368 | 235 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/30/2015 | 2/2/2016 | Customer Initiated Withdrawal | 6/1/2021
PJM | AB1-149 | Baker 138kV |  | WV | Hardy | Withdrawn | APS | 121.6 | 15.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/30/2015 | 11/28/2016 | Customer Initiated Withdrawal | 12/31/2018
PJM | AB1-150 | Grassy Falls 138kV | Beech Ridge Wind Farm | WV | Greenbrier | In Service | APS | 50.6 | 6.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  | Document Posted | 10/30/2015 |  |  | 4/30/2020 | 3/14/2020
PJM | AB1-151 | Paupack 230kV |  | PA | Wayne | Withdrawn | PPL | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 10/30/2015 | 3/29/2016 | Customer Initiated Withdrawal | 6/1/2020
PJM | AB1-152 | Culpeper 34.5kV | Stevensburg Solar | VA | Unknown | Withdrawn | Dominion | 15 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2015 | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2019
PJM | AB1-153 | Hunterstown 500kV |  | PA | Adams | Withdrawn | ME | 1061.5 | 985.1 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 10/30/2015 | 5/10/2016 | Customer Initiated Withdrawal | 6/1/2020
PJM | AB1-154 | Gilbert 230kV |  | NJ | Hunterdon | Withdrawn | JCPL | 1092.2 | 1028 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 10/30/2015 | 8/16/2018 |  | 6/1/2020
PJM | AB1-155 | Wakefield 34.5kV |  | VA | Surry | Withdrawn | Dominion | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/30/2015 | 11/16/2015 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB1-156 | Sligo 34.5kV |  | NC | Camden | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/30/2015 | 4/7/2016 | Customer Milestone Not Met | 10/31/2017
PJM | AB1-157 | George Washington 138kV III |  | WV | Marshall | Withdrawn | AEP | 10 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/30/2015 | 5/16/2017 | Customer Initiated Withdrawal | 6/1/2018
PJM | AB1-158 | Thornville 34.5kV |  | OH | Perry | Withdrawn | AEP | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/30/2015 | 11/12/2015 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB1-159 | Wakefield 34.5kV |  | VA | Surry | Withdrawn | Dominion | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/30/2015 | 5/3/2016 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB1-160 | Gold-Sabinsville 115kV | Big Level Wind Farm | PA | Potter | In Service | PENELEC | 20 | 3.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2015 |  |  | 10/31/2019 | 11/20/2019
PJM | AB1-161 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 1.34 | 0 | Energy | Generation Interconnection | Solar | Document Posted |  |  |  | 10/30/2015 | 3/21/2016 | Customer Initiated Withdrawal | 8/31/2016
PJM | AB1-162 | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 16.7 | 6.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/30/2015 | 7/1/2019 |  | 7/1/2017
PJM | AB1-163 | Glidden-Van Hiseville 34.5 kV | Legler Landfill Solar Farm | NJ | Ocean | In Service | JCPL | 2.88 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 10/30/2015 |  |  | 10/30/2021 | 11/6/2021
PJM | AB1-164 | Whiteley 25kV | Whitely - Greene Battery Storage Facility | PA | Greene | Withdrawn | APS | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2015 | 4/14/2017 | Customer Initiated Withdrawal | 7/31/2019
PJM | AB1-165 | Tabernacle 12kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/30/2015 | 12/11/2017 |  | 12/24/2016
PJM | AB1-166 | Wilson 23kV | Wilson Battery Storage | PA | Allegheny | Withdrawn | DL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2015 | 5/30/2019 |  | 8/31/2019
PJM | AB1-167 | South Cumberland 69kV |  | OH | Noble | Withdrawn | AEP | 50 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/30/2015 | 11/30/2017 |  | 8/31/2017
PJM | AB1-168 | Berlin 12kV |  | NJ | Camden | Withdrawn | AEC | 4.5 | 1.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/30/2015 | 12/11/2017 |  | 3/31/2017
PJM | AB1-169 | Stuart 345kV | Mason Energy Center | KY | Mason | Withdrawn | Dayton | 1150 | 1100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2015 | 2/9/2022 |  | 6/30/2023
PJM | AB1-169A | Minotola 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 575 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/30/2015 | 7/20/2020 |  | 6/1/2020
PJM | AB1-170 | LaSalle-Braidwood |  | IL | Grundy | Withdrawn | ComEd | 250 | 32.5 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 10/30/2015 | 8/4/2016 | Customer Initiated Withdrawal | 12/1/2017
PJM | AB1-171 | Franklin 25kV | Franklin Generation Facility | PA | Greene | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2015 | 10/22/2018 |  | 10/31/2019
PJM | AB1-172 | Joliet-Wilmington |  | IL | Will | Withdrawn | ComEd | 6.2 | 6.2 | Capacity | Generation Interconnection | Methane | Document Posted |  |  |  | 10/30/2015 | 6/29/2018 |  | 9/1/2017
PJM | AB1-173 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 19.8 | 13.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2015 |  |  | 4/1/2022 | 9/29/2022
PJM | AB1-173A | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 19.8 | 13.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2015 |  |  | 4/1/2022 | 9/29/2022
PJM | AB1-174 | Thornville12kV | Thornville 12kV | OH | Perry | Withdrawn | AEP | 10 | 6.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2015 | 2/7/2018 |  | 12/31/2018
PJM | AB1-175 | Homer City-Mainesburg 345kV |  | PA | Clearfield | Withdrawn | PENELEC | 989 | 960 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/30/2015 | 11/19/2015 | Customer Initiated Withdrawal | 1/1/2020
PJM | AB1-176 | Price 25kV II | Cedar Lane Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 10/30/2015 |  |  | 4/1/2026
PJM | AB1-177 | Ontario 23kV |  | NJ | Atlantic | Withdrawn | AEC | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 10/30/2015 | 4/4/2016 | Customer Initiated Withdrawal | 4/30/2016
PJM | AB1-178 | Pidgeon 69kV |  | OH | Columbiana | Withdrawn | ATSI | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 10/30/2015 | 11/9/2016 | Customer Milestone Not Met | 12/1/2017
PJM | AB1-179 | Sabinsville-Wellsboro 34kV |  | PA | Tioga | Withdrawn | PENELEC | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 10/30/2015 | 11/9/2016 | Customer Milestone Not Met | 12/1/2017
PJM | AB1-180 | Pine View 12kV | Seven Islands Environmental Solutions, LLC | WV | Unknown | In Service | AEP | 3.2 | 2.4 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/30/2015 |  |  | 12/31/2016 | 3/7/2017
PJM | AB1-181 | Cunningham 500kV |  | VA | Fluvanna | In Service | Dominion | 28 | 37.3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/30/2015 |  |  | 2/28/2017 | 3/7/2017
PJM | AB1-182 | Bear Creek | Bear Creek Energy Storage Facility | PA | Luzerne | Withdrawn | PPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 10/30/2015 | 7/25/2024 |  | 12/1/2022
PJM | AB1-183 | Kennedyville-Massey 69kV |  | MD | Kent | Withdrawn | DPL | 0 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 10/30/2015 | 1/20/2017 | Customer Initiated Withdrawal | 10/28/2016
PJM | AB1-184 | Centreville 12kV II |  | MD | Queen Anne's | Withdrawn | DPL | 1.96 | 0 | Energy | Generation Interconnection | Solar | Document Posted |  |  |  | 10/30/2015 | 3/21/2016 | Customer Initiated Withdrawal | 11/11/2016
PJM | AB2-001 | Ringoes-US Bronze 34kV | Flemington Solar Farm | NJ | Hunterdon | In Service | JCPL | 0 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 11/2/2015 |  |  | 12/31/2016 | 12/31/2016
PJM | AB2-003 | Halfway-N=Milnor 34.5kV | Thornton Solar Facility | MD | Washington | Withdrawn | APS | 4.4 | 1.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 11/9/2015 | 12/19/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | AB2-004 | Halfway-Milnor 34.5kV | Hagerstown Solar Facility | MD | Washington | Withdrawn | APS | 5.4 | 2.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 11/13/2015 | 10/23/2017 |  | 3/31/2018
PJM | AB2-008 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 105 | 96 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 11/30/2015 | 10/10/2016 | Customer Initiated Withdrawal | 5/31/2020
PJM | AB2-009 | Edison 138kV |  | NJ | Middlesex | Withdrawn | PSEG | 116 | 105 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 11/30/2015 | 10/10/2016 | Customer Initiated Withdrawal | 5/31/2020
PJM | AB2-010 | Saltville-Holston 34.5kV - Phase I | Saltville-Holston 34.5kV Solar Facility | VA | Smyth | Withdrawn | AEP | 5 | 2.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/1/2015 | 2/5/2019 |  | 12/1/2017
PJM | AB2-011 | Saltville-Holstone 34.5kV - Phase II | Saltville-Holston 34.5kV Solar Facility | VA | Smyth | Withdrawn | AEP | 5 | 2.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/1/2015 | 2/5/2019 |  | 12/1/2017
PJM | AB2-012 | Blooming Grove to West Damascus 69 kV |  | PA | Wayne | Withdrawn | PPL | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 12/9/2015 | 8/3/2018 |  | 6/1/2018
PJM | AB2-014 | Lakewood 230kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 0 | 8.1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/15/2015 |  |  | 9/30/2017 | 11/16/2016
PJM | AB2-015 | Franklin 115kV | Tidewater Solar Projects | VA | Southampton | Withdrawn | Dominion | 91 | 50 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/21/2015 | 1/3/2022 |  | 12/31/2022
PJM | AB2-016 | Maddox Creek 345kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 12/28/2015 | 3/9/2018 |  | 12/31/2019
PJM | AB2-017 |  |  | NJ | Atlantic | Withdrawn | JCPL | 1 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/4/2016 | 1/27/2016 | Customer Milestone Not Met
PJM | AB2-018 | Bethel-Carolina 12.kkV |  | NC | Unknown | Withdrawn | Dominion | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/20/2016 | 2/9/2016 |  | 12/31/2016
PJM | AB2-022 | Elizabeth City 34.5kV | Elizabeth City Solar | NC | Camden | In Service | Dominion | 20 | 13 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 2/4/2016 |  |  | 6/30/2021 | 10/18/2021
PJM | AB2-023 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 15 | 9.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/4/2016 | 3/30/2016 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB2-024 | Correctional 34.5kV |  | VA | New Kent | In Service | Dominion | 20 | 13.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  | Wholesale Market Participation Agreement | 2/8/2016 |  |  | 12/31/2017 | 11/27/2017
PJM | AB2-025 | Sapony 34.5kV |  | VA | Sussex | In Service | Dominion | 20 | 13.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  | Wholesale Market Participation Agreement | 2/8/2016 |  |  | 12/31/2017 | 11/30/2017
PJM | AB2-026 | Powhatan 34.5kV |  | VA | Powhatan | In Service | Dominion | 20 | 13.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  | Wholesale Market Participation Agreement | 2/8/2016 |  |  | 12/31/2017 | 11/30/2017
PJM | AB2-027 | Maple Ave-Mount Lena 34.5kV | Funkstonw Solar Facility | MD | Washington | Withdrawn | APS | 8.8 | 3.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/10/2016 | 10/26/2020 |  | 11/30/2017
PJM | AB2-028 | Fall Creek-Desoto 345kV |  | IN | Henry | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/10/2016 | 6/17/2021 |  | 10/31/2018
PJM | AB2-029 | Remington 34.5kV |  | VA | Fauquier | In Service | Dominion | 19.8 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  | Wholesale Market Participation Agreement | 2/11/2016 |  |  | 12/31/2017 | 10/1/2017
PJM | AB2-030 | Tasley 25kV |  | VA | Accomack | Withdrawn | DPL | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 2/11/2016 | 10/16/2017 |  | 12/1/2016
PJM | AB2-031 | Brink-Trego 115kV | Meherrin Solar | VA | Greensville | In Service | Dominion | 20 | 13.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/13/2016 |  |  | 4/1/2022 | 9/29/2022
PJM | AB2-032 | Church-Wye Mills 138 kV | Pondtown Solar 2 | MD | Queen Anne's | In Service | DPL | 20 | 13.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/11/2016 |  |  | 12/31/2023 | 10/18/2022
PJM | AB2-033 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 10 | 7.16 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/22/2016 | 3/20/2018 |  | 5/1/2017
PJM | AB2-035 | Bethel-Carolina 12.5kV |  | NC | Pitt | Withdrawn | Dominion | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/23/2016 | 11/30/2018 |  | 12/31/2016
PJM | AB2-036 | Church - Oil City 138kV | Waypost Solar Project | MD | Caroline | Engineering and Procurement | DPL | 92 | 34.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2016 |  |  | 12/30/2025
PJM | AB2-037 | Keeney-Steele 230kV | Cherrywood Solar I | MD | Caroline | Engineering and Procurement | DPL | 202 | 76.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2016 |  |  | 12/30/2025
PJM | AB2-038 | Frostburg 138kV |  | MD | Allegany | In Service | APS | 0 | 2.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 3/1/2016 |  |  | 12/31/2020 | 9/13/2017
PJM | AB2-039 | Bakers Pond-Ivor 115kV |  | VA | Southampton | Withdrawn | Dominion | 85 | 47 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/29/2016 | 7/7/2017 | Customer Milestone Not Met | 12/31/2018
PJM | AB2-040 | Brink 115kV | Brink Solar Project | VA | Greensville | In Service | Dominion | 80 | 44 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/2/2016 |  |  | 10/1/2024 | 12/27/2024
PJM | AB2-041 | Frostburg 138kV | Mason Dixon Wind Farm | PA | Somerset | Withdrawn | APS | 19.4 | 3.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 2/29/2016 | 10/26/2020 |  | 12/15/2020
PJM | AB2-042 | Smithfield-Surry 230kV |  | VA | Isle of Wight | Withdrawn | Dominion | 160 | 89 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/29/2016 | 10/11/2016 | Customer Milestone Not Met | 9/30/2018
PJM | AB2-043 | Chase City 115kV | Bluestone Farm Solar | VA | Mecklenburg | In Service | Dominion | 49.9 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/29/2016 |  |  | 4/8/2021 | 4/3/2021
PJM | AB2-044 |  |  | NJ | Middlesex | Withdrawn | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/29/2016 | 3/17/2016 |  | 7/1/2017
PJM | AB2-045 | Buckingham 34.5kV |  | VA | Buckingham | In Service | Dominion | 19.8 | 13.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  | Wholesale Market Participation Agreement | 2/29/2016 |  |  | 12/31/2017 | 11/30/2017
PJM | AB2-046 | Charleroi 12kV |  | PA | Washington | Withdrawn | APS | 0.5 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/29/2016 | 6/27/2016 | Customer Initiated Withdrawal | 12/1/2016
PJM | AB2-047 | Brokaw-Pontiac Midpoint | Blooming Grove WF | IL | McLean | In Service | ComEd | 250 | 32.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 2/29/2016 |  |  | 12/30/2020 | 10/30/2020
PJM | AB2-048 | Grandin 12kV | Clinton Energy Storage System | NJ | Hunterdon | Withdrawn | JCPL | 0.5 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/3/2016 | 7/31/2018 |  | 6/30/2019
PJM | AB2-049 | Gloucester Township 12kV | GEMS Landfill Solar | NJ | Camden | In Service | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 3/4/2016 |  |  | 6/30/2022 | 4/14/2022
PJM | AB2-050 | Four Rivers 230kV | Doswell Complex 5 & 6 | VA | Hanover | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/4/2016 |  |  | 3/1/2020 | 2/28/2018
PJM | AB2-051 | Chesapeake 230kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 840 | 765.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 3/14/2016 | 10/3/2018 |  | 1/1/2021
PJM | AB2-052 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 13 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/16/2016 | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB2-053 | Culpeper 34.5kV |  | VA | Culpeper | Withdrawn | Dominion | 5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/17/2016 | 3/27/2017 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB2-054 | JK Smith 345kV |  | KY | Clark | Withdrawn | EKPC | 614 | 504 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/17/2016 | 5/8/2017 | Customer Initiated Withdrawal | 3/1/2023
PJM | AB2-055 | Bayonne 345kV |  | NJ | Hudson | Withdrawn | PSEG | 1041.4 | 1041.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/17/2016 | 9/20/2019 |  | 6/1/2021
PJM | AB2-056 | Colora 34.5kV |  | MD | Cecil | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/21/2016 | 5/24/2017 | Customer Initiated Withdrawal | 10/1/2018
PJM | AB2-057 | Brunswick 26kV | New Road Solar | NJ | Middlesex | In Service | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/24/2016 |  |  | 3/30/2018 | 6/22/2018
PJM | AB2-058 | Stewartsville 34.5kV | Stewartsville Solar Farm | NJ | Warren | In Service | JCPL | 0 | 3.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/25/2016 |  |  | 12/31/2016 | 12/6/2016
PJM | AB2-059 | Benson-Dunbar 115kV | Moccasin Creek Solar | NC | Edgecombe | In Service | Dominion | 100 | 66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/25/2016 |  |  | 6/15/2020 | 10/12/2020
PJM | AB2-060 | Chase City-Lunenburg 115kV | Chase City Solar | VA | Mecklenburg | In Service | Dominion | 80 | 54.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/25/2016 |  |  | 5/15/2020 | 7/21/2020
PJM | AB2-061 | Meadow Road 13kV | Meadow Road Solar | NJ | Middlesex | Withdrawn | PSEG | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/29/2016 | 5/12/2017 | Customer Initiated Withdrawal | 6/30/2018
PJM | AB2-062 | Unionville 115kV |  | VA | Orange | Withdrawn | Dominion | 20 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/30/2016 | 8/24/2018 |  | 2/1/2018
PJM | AB2-063 | Price 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/30/2016 | 7/1/2019 |  | 12/31/2018
PJM | AB2-064 | Southwest Lima 345kV |  | OH | Van Wert | Withdrawn | AEP | 40 | 15.2 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2016 | 9/22/2016 |  | 12/31/2018
PJM | AB2-065 | Madison-Tanners Creek 138kV |  | IN | Rush | Withdrawn | AEP | 124.2 | 16 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 3/30/2016 | 2/27/2018 |  | 12/31/2019
PJM | AB2-066 | Crawfords Corner 23kV |  | NJ | Monmouth | Withdrawn | JCPL | 0.1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 3/31/2016 | 11/18/2016 | Customer Milestone Not Met | 7/31/2016
PJM | AB2-067 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 1100 | 1100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2016 |  |  | 12/31/2022 | 4/7/2023
PJM | AB2-068 | Chickahominy 500kV | C4GT | VA | Charles City | Withdrawn | Dominion | 1060 | 1060 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2016 | 1/11/2021 |  | 12/31/2023
PJM | AB2-069 | Chase City-Kerr Dam 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 49 | 19 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2016 | 10/11/2016 | Customer Milestone Not Met | 12/31/2018
PJM | AB2-070 | Mt. Pulaski-Brokaw | Alta Farms II | IL | DeWitt | In Service | ComEd | 197 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2016 |  |  | 5/31/2023 | 5/20/2023
PJM | AB2-071 | Hunterstown-Lincoln 115kV |  | PA | Adams | Withdrawn | ME | 100 | 68 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/31/2016 | 5/31/2017 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB2-072 | Arnold's Corner 34.5kV |  | VA | King George | Withdrawn | Dominion | 18 | 12.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 3/31/2016 | 1/29/2019 |  | 9/15/2017
PJM | AB2-073 | Earleys 230kV |  | NC | Hertford | Withdrawn | Dominion | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/1/2016 | 5/27/2016 | Customer Milestone Not Met | 10/31/2016
PJM | AB2-074 | Sunbury #2 500kV |  | PA | Snyder | Withdrawn | PPL | 113 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 4/1/2016 | 5/4/2020 |  | 9/2/2019
PJM | AB2-077 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/14/2016 |  |  | 5/31/2024 | 6/18/2024
PJM | AB2-078 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/14/2016 |  |  | 5/31/2024 | 6/18/2024
PJM | AB2-079 | Buggs Island-Chase City 115kV | Spanish Grove Solar | VA | Mecklenburg | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/14/2016 |  |  | 5/31/2024 | 6/18/2024
PJM | AB2-080 | Marysville-Flatlick 765kV |  | OH | Pickaway | Withdrawn | AEP | 1200 | 1200 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 4/12/2016 | 10/4/2016 | Customer Milestone Not Met | 6/1/2021
PJM | AB2-081 | Sligo 34.5kV |  | NC | Camden | Withdrawn | Dominion | 20 | 13 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/13/2016 | 5/3/2016 |  | 10/31/2017
PJM | AB2-082 | Metuchen 230kv |  | NJ | Middlesex | Withdrawn | PSEG | 675 | 671 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/14/2016 | 4/30/2019 |  | 6/1/2019
PJM | AB2-083 | Delano 138kV |  | OH | Ross | Withdrawn | AEP | 40 | 27.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/14/2016 | 3/4/2021 |  | 10/31/2017
PJM | AB2-084 | Costen 25kV | Costen Solar Energy Center | MD | Somerset | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/15/2016 | 2/1/2019 |  | 10/20/2019
PJM | AB2-085 | Adams 138kV | Stone Branch Solar | OH | Adams | Suspended | AEP | 49.9 | 33.93 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/18/2016 |  |  | 12/31/2023
PJM | AB2-086 | Grassfield 13.2kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 13 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/18/2016 | 5/5/2016 | Customer Milestone Not Met | 10/31/2017
PJM | AB2-087 | Earleys 34.5kV |  | NC | Hertford | Withdrawn | Dominion | 5 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/21/2016 | 11/27/2017 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB2-088 | Tarboro 12.5kV |  | NC | Edgecombe | Withdrawn | Dominion | 4 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/22/2016 | 11/30/2018 |  | 12/31/2016
PJM | AB2-089 | Beechwood DP-Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Interim Study | 4/25/2016 | 7/24/2019 |  | 6/1/2017
PJM | AB2-090 | Chase City 34.5kV |  | VA | Mecklenburg | Withdrawn | Dominion | 36 | 23.8 | Capacity | Generation Interconnection | Solar | Document Posted | Interim Study | Document Posted | Withdrawn | 4/25/2016 | 8/31/2018 |  | 6/12/2018
PJM | AB2-091 | Hudson 230kV |  | NJ | Hudson | Withdrawn | PSEG | 105 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/26/2016 | 4/21/2017 | Customer Initiated Withdrawal | 5/31/2020
PJM | AB2-092 | Bergen 138kV | Bergen Generating Station | NJ | Bergen | Partially in Service - Under Construction | PSEG | 51.1 | 51.1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/26/2016 |  |  | 12/5/2019 | 12/5/2019
PJM | AB2-093 | Ormet 138kV | Hannibal Port Power Project | OH | Monroe | In Service | AEP | 485 | 485 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/26/2016 |  |  | 9/13/2021 | 6/1/2021
PJM | AB2-094 | Warren Glen Switch Point 34kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Withdrawn | 4/26/2016 | 11/23/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | AB2-095 | Ocean Pines-Walston Switch 69kV |  | MD | Wicomico | Withdrawn | DPL | 30 | 11.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/26/2016 | 10/12/2016 | Customer Initiated Withdrawal | 10/31/2018
PJM | AB2-096 | Silver Lake-Cherry Valley | Garden Prairie Energy Facility | IL | Boone | Withdrawn | ComEd | 350 | 350 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2016 | 5/5/2022 |  | 4/30/2024
PJM | AB2-097 | Antietam 34.5kV | Hagerstown Plant | MD | Washington | In Service | APS | 10 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/27/2016 |  |  | 2/28/2020 | 10/15/2020
PJM | AB2-098 | Everetts 34.5kV |  | NC | Martin | Withdrawn | Dominion | 5 | 3.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/27/2016 | 9/18/2019 |  | 12/30/2016
PJM | AB2-099 | Ahoskie 34.5kV | Colice Hall Solar | NC | Hertford | In Service | Dominion | 5 | 3.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 4/28/2016 |  |  | 7/23/2023 | 7/6/2023
PJM | AB2-100 | Clubhouse-Lakeview 230kV | Sadler Solar | VA | Greensville | In Service | Dominion | 100 | 67 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/27/2016 |  |  | 12/1/2021 | 1/22/2021
PJM | AB2-101 | George Washington 138kV |  | WV | Marshall | Withdrawn | AEP | 31 | 31 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/27/2016 | 5/16/2017 | Customer Initiated Withdrawal | 4/1/2019
PJM | AB2-102 | Cumberland 230kV | Cumberland | NJ | Cumberland | Withdrawn | AEC | 230 | 225 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 4/28/2016 | 4/26/2024 |  | 12/1/2023
PJM | AB2-103 | Seaman 138kV |  | OH | Adams | Withdrawn | AEP | 40 | 27.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/28/2016 | 3/26/2018 |  | 10/31/2017
PJM | AB2-104 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I, LLC | WV | Brooke | Withdrawn | APS | 65 | 65 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/28/2016 | 10/10/2020 |  | 8/3/2021
PJM | AB2-105 | Mantua 12kV |  | NJ | Gloucester | Withdrawn | AEC | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/28/2016 | 10/12/2016 | Customer Milestone Not Met | 12/31/2016
PJM | AB2-106 | Pierson Avenue 480V |  | NJ | Middlesex | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/28/2016 | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB2-107 | Burlington 480V |  | NJ | Burlington | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Not Required | Not Required | Not Required | Withdrawn | 4/28/2016 | 9/30/2016 | Customer Milestone Not Met | 12/31/2016
PJM | AB2-108 | Egg Harbor Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/28/2016 | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB2-109 | Reusens 34.5kV | Reusens Hydro Electric Generating Plant | VA | City of Lynchburg | In Service | AEP | 12.5 | 4 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 4/28/2016 |  |  | 3/31/2018 | 11/29/2017
PJM | AB2-110 | Englishtown-Millhurst 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 11.1 | 4.2 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/28/2016 | 3/27/2017 | Customer Initiated Withdrawal | 4/19/2017
PJM | AB2-111 | Millhurst-Rt 33 Switch Point 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 11.1 | 4.2 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/28/2016 | 3/27/2017 | Customer Initiated Withdrawal | 4/20/2017
PJM | AB2-112 | S. Reading-Boyertown 230kV | Birdsboro Power LLC Generation Facility | PA | Berks | In Service | ME | 35 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 4/28/2016 |  |  | 6/1/2019 | 2/7/2019
PJM | AB2-113 | Cecil County 1 |  | MD | Cecil | Withdrawn | DPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/28/2016 | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017
PJM | AB2-114 | Cecil County 2 |  | MD | Cecil | Withdrawn | DPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/28/2016 | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017
PJM | AB2-115 | Cecil County 3 |  | MD | Cecil | Withdrawn | DPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/28/2016 | 9/21/2016 | Customer Initiated Withdrawal | 11/15/2017
PJM | AB2-116 | Cecil County 4 |  | MD | Cecil | Withdrawn | DPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/28/2016 | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017
PJM | AB2-117 | Cecil County 5 |  | MD | Cecil | Withdrawn | DPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/28/2016 | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017
PJM | AB2-118 | Cecil County 6 |  | MD | Cecil | Withdrawn | DPL | 2 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/28/2016 | 9/22/2016 | Customer Initiated Withdrawal | 11/15/2017
PJM | AB2-119 | Middle Township 12kV |  | NJ | Cape May | Withdrawn | AEC | 1.5 | 0.57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/28/2016 | 5/24/2017 | Customer Initiated Withdrawal | 12/1/2017
PJM | AB2-120 | Piney Grove-New Church 138kV |  | MD | Worcester | Withdrawn | DPL | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/28/2016 | 2/23/2021 |  | 12/14/2018
PJM | AB2-121 | Burlington 26kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/28/2016 | 2/14/2017 | Customer Milestone Not Met | 12/1/2017
PJM | AB2-122 | Egg Harbor 12kV | Winzinger Egg Harbor Solar Project | NJ | Atlantic | Withdrawn | AEC | 1.9 | 0.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/28/2016 | 5/5/2020 |  | 9/4/2021
PJM | AB2-123 | Whiterock 34kV |  | MD | Howard | Withdrawn | BGE | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/28/2016 | 8/1/2017 | Customer Milestone Not Met | 12/31/2017
PJM | AB2-124 | Whiterock 34kV |  | MD | Howard | Withdrawn | BGE | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/28/2016 | 8/1/2017 | Customer Milestone Not Met | 12/31/2017
PJM | AB2-125 | Marriott Hill 34kV |  | MD | Anne Arundel | Withdrawn | BGE | 3.3 | 1.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/28/2016 | 8/1/2017 | Customer Milestone Not Met | 12/31/2017
PJM | AB2-126 | Finksburg 34kV |  | MD | Baltimore County | Withdrawn | BGE | 3.8 | 1.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/28/2016 | 8/1/2017 | Customer Milestone Not Met | 12/31/2017
PJM | AB2-127 | Gilbert 34.5kV |  | NJ | Hunterdon | Withdrawn | JCPL | 16 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 4/28/2016 | 12/2/2016 | Customer Initiated Withdrawal | 6/29/2018
PJM | AB2-128 | Clubhouse-Lakeview 230kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 57.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 7/17/2017 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB2-129 | Doubs 230kV | Potomac Solar, LLC | MD | Frederick | Withdrawn | APS | 80 | 30.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 | 7/30/2021 |  | 4/30/2020 | 5/30/2021
PJM | AB2-130 | Laurel 69kV |  | DE | Sussex | Withdrawn | DPL | 85 | 32.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/29/2016 | 2/19/2021 |  | 6/1/2019
PJM | AB2-131 | Galion-Roberts South 138kV |  | OH | Marion | Withdrawn | ATSI | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/29/2016 | 8/29/2020 |  | 6/1/2019
PJM | AB2-132 | Haumesser Road | Lee-DeKalb Wind Energy Center | IL | Lee | In Service | ComEd | 0 | 2.2 | Capacity | Generation Interconnection | Wind; Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/30/2016 |  |  | 9/1/2023 | 9/1/2023
PJM | AB2-133 | Chestertown-Church 69kV | Morgnec Road Solar | MD | Kent | Engineering and Procurement | DPL | 55.8 | 24.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 8/16/2025
PJM | AB2-134 | Hopewell-Surry 230kV | Colonial Trail West Solar | VA | Surry | In Service | Dominion | 142.4 | 71.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 12/1/2019 | 11/7/2019
PJM | AB2-135 | Church-Kent 69kV | Jones Farm Lane Solar | MD | Queen Anne's | Under Construction | DPL | 64 | 29.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2016 |  |  | 4/30/2025
PJM | AB2-136 | Cambridge-West Cambridge 69kV | Egypt Road Solar | MD | Dorchester | Under Construction | DPL | 51.1 | 24.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2016 |  |  | 9/15/2025
PJM | AB2-137 | St. Clair 13.2kV |  | OH | Franklin | Withdrawn | AEP | 4 | 1 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/29/2016 | 9/30/2016 | Customer Initiated Withdrawal | 11/1/2017
PJM | AB2-138 | Clybourn 12.5kV |  | IL | Cook | Withdrawn | ComEd | 0.1 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/28/2016 | 5/20/2016 | Customer Milestone Not Met
PJM | AB2-139 | Raceway Mall 34.5kV | Freemall Fuel Cell Facility | NJ | Monmouth | In Service | JCPL | 0.42 | 0 | Energy | Generation Interconnection | Other | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2016 |  |  | 6/30/2017 | 2/1/2018
PJM | AB2-140 | Rock Ridge 13kV |  | MD | Harford | Withdrawn | BGE | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2016 | 7/27/2017 | Customer Initiated Withdrawal | 10/31/2017
PJM | AB2-141 | George Washington 138kV |  | WV | Marshall | Withdrawn | AEP | 394 | 388.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 4/29/2016 | 2/27/2019 |  | 4/1/2019
PJM | AB2-142 | Steele 25kV |  | MD | Caroline | Withdrawn | DPL | 13.4 | 5.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 5/24/2017 | Customer Milestone Not Met | 12/31/2018
PJM | AB2-143 | Lynch 25kV |  | MD | Kent | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/29/2016 | 10/14/2016 | Customer Milestone Not Met | 12/31/2018
PJM | AB2-144 | Emmitsburg–Taneytown 2 34.5 kV |  | MD | Frederick | Withdrawn | APS | 13.8 | 5.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Withdrawn | 4/29/2016 | 11/9/2016 | Customer Milestone Not Met | 3/1/2017
PJM | AB2-145 | Axton 138kV |  | VA | Henry | Withdrawn | AEP | 572 | 572 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/29/2016 | 2/23/2018 |  | 1/1/2021
PJM | AB2-146 | Axton 138kV |  | VA | Henry | Withdrawn | AEP | 382 | 382 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 4/29/2016 | 10/3/2016 | Customer Initiated Withdrawal | 1/1/2021
PJM | AB2-147 | Clubhouse-Freeman 115kV |  | VA | Greensville | Withdrawn | Dominion | 40 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 7/11/2017 | Customer Initiated Withdrawal | 10/30/2017
PJM | AB2-148 | Mapleton-Murphy 115kV |  | NC | Hertford | Withdrawn | Dominion | 19.9 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 5/18/2016 | Customer Milestone Not Met | 10/30/2017
PJM | AB2-149 | Myrtle-Windsor 115kV |  | VA | Isle of Wight | Withdrawn | Dominion | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 7/21/2017 | Customer Initiated Withdrawal | 10/30/2017
PJM | AB2-150 | Clubhouse-Freeman 115kV |  | VA | Greensville | Withdrawn | Dominion | 40 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 7/11/2017 | Customer Initiated Withdrawal | 10/30/2017
PJM | AB2-151 | Mapleton-Murphy 115kV |  | NC | Hertford | Withdrawn | Dominion | 19.9 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 5/18/2016 | Customer Milestone Not Met | 10/30/2017
PJM | AB2-152 | Hopewell 230kV |  | VA | City of Hopewell | Withdrawn | Dominion | 54 | 54 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 4/29/2016 | 2/1/2017 | Customer Initiated Withdrawal | 6/30/2019
PJM | AB2-153 | Church-Wye Mills 138 kV | Pondtown Solar 2 | MD | Queen Anne's | In Service | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 12/31/2023 | 10/18/2022
PJM | AB2-154 | Kendall 345kV |  | IL | Kendall | Withdrawn | ComEd | 65 | 65 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 4/29/2016 | 9/27/2016 | Customer Initiated Withdrawal | 5/1/2017
PJM | AB2-155 | Richland-Stryker |  | OH | Defiance | Withdrawn | ATSI | 25 | 25 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 4/29/2016 | 11/4/2016 | Customer Milestone Not Met | 6/1/2017
PJM | AB2-156 | W.H. Zimmer 345kV |  | OH | Clermont | Withdrawn | DEOK | 50 | 50 | Capacity | Generation Interconnection | Coal | Document Posted |  |  |  | 4/29/2016 | 9/26/2016 | Customer Initiated Withdrawal | 6/1/2016
PJM | AB2-157 | Prince George's County 12kV | Rollins Avenue Phoenix | MD | Prince George's | In Service | PEPCO | 2.5 | 0.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/29/2016 |  |  | 7/12/2019 | 12/23/2019
PJM | AB2-158 | Louisa-South Anna 230kV | Belcher Solar | VA | Louisa | In Service | Dominion | 88.2 | 61 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 12/1/2020 | 6/30/2021
PJM | AB2-159 | Lumberton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 1.3 | 0 | Energy | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 4/29/2016 | 12/11/2017 |  | 10/3/2016
PJM | AB2-160 | Reams 115kV | Reams Solar | VA | Dinwiddie | Withdrawn | Dominion | 80 | 30.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2016 | 7/18/2024 |  | 12/31/2022
PJM | AB2-161 | Waverly #2 DP 115kV | Waverly Solar | VA | Sussex | In Service | Dominion | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 5/2/2016 |  |  | 12/29/2023 | 3/14/2024
PJM | AB2-162 | Camden 480V |  | NJ | Camden | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Not Required | Not Required | Not Required | Withdrawn | 4/29/2016 | 9/30/2016 | Customer Milestone Not Met | 12/31/2016
PJM | AB2-163 | Sicklerville 12kV |  | NJ | Camden | Withdrawn | AEC | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/29/2016 | 6/28/2016 | Customer Initiated Withdrawal | 12/31/2016
PJM | AB2-164 | Wattsville-Wallops Island 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/29/2016 | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018
PJM | AB2-165 | Tasley-Oak Hall 69kV I |  | VA | Accomack | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/29/2016 | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018
PJM | AB2-166 | Edgewood 12kV | Aydelotte Solar Project | MD | Wicomico | Withdrawn | DPL | 5.5 | 2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2016 | 1/10/2019 |  | 3/31/2019
PJM | AB2-167 | Stockton 69kV |  | MD | Worcester | Withdrawn | DPL | 14 | 5.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 8/11/2017 | Customer Initiated Withdrawal | 11/1/2017
PJM | AB2-168 | Perch 34.5kV | Crouse Solar Project | MD | Cecil | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/29/2016 | 3/9/2020 |  | 9/6/2022
PJM | AB2-169 | Pantago-Five Points 115kV | Wilkinson Solar Energy Center | NC | Hyde | In Service | Dominion | 74 | 39 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 6/30/2021 | 11/20/2019
PJM | AB2-170 | East Lima-Marysville 345kV | Hardin Energy Center | OH | Hardin | In Service | AEP | 130 | 49.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 6/1/2021 | 10/13/2020
PJM | AB2-171 | Handsome 115kV |  | VA | Southampton | Withdrawn | Dominion | 75 | 28.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 7/18/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AB2-172 | Todd 69kV | Richfield Solar and Storage | MD | Dorchester | In Service | DPL | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/30/2016 |  |  | 1/10/2024 | 2/9/2024
PJM | AB2-173 | Nelson 345kV |  | IL | Lee | Withdrawn | ComEd | 16 | 28 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 4/29/2016 | 12/24/2019 |  | 6/1/2018
PJM | AB2-174 | Emporia-Trego 115kV | Greensville County Solar Project | VA | Greensville | In Service | Dominion | 80 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 12/31/2020 | 12/1/2020
PJM | AB2-175 | Peach Bottom 500kV | Peach Bottom Units #2 & #3 | PA | York | Partially in Service - Under Construction | PECO | 44 | 44 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted |  | Document Posted | 4/29/2016 |  |  | 12/31/2018 | 3/26/2019
PJM | AB2-176 | Chase City 34.5kV |  | VA | Mecklenburg | Withdrawn | Dominion | 14 | 9.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/29/2016 | 7/23/2018 |  | 6/1/2017
PJM | AB2-177 | Kenney 25kV |  | MD | Worcester | Withdrawn | DPL | 6.6 | 2.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/29/2016 | 6/9/2017 | Customer Initiated Withdrawal | 6/1/2018
PJM | AB2-178 | Beckjord 138kV | 138kV Bus 5 Beckjord Battery | OH | Clermont | Withdrawn | DEOK | 19.8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/29/2016 | 12/10/2019 |  | 11/30/2018
PJM | AB2-179 | Townsend 138kV | New Castle Solar | DE | New Castle | In Service | DPL | 50 | 37.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  |  | 12/16/2022 | 12/30/2022
PJM | AB2-180 | Rockawalkin 69kV | Hebron Solar | MD | Wicomico | Withdrawn | DPL | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/29/2016 | 10/6/2022 |  | 2/29/2024
PJM | AB2-181 | Catoctin 138kV |  | MD | Frederick | Withdrawn | APS | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 6/2/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB2-182 | Townsend 25kV |  | MD | Cecil | Withdrawn | DPL | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 5/20/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB2-183 | Massey 25kV |  | MD | Kent | Withdrawn | DPL | 20 | 14 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 5/20/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB2-184 | Monkton |  | MD | Baltimore County | Withdrawn | BGE | 5 | 3.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 5/19/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB2-185 | Wye Mills 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 8 | 5.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/29/2016 | 4/14/2021 |  | 6/30/2017
PJM | AB2-186 | South Hertford 34.5kV |  | NC | Perquimans | Withdrawn | Dominion | 5 | 3.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2016 | 1/28/2019 |  | 6/30/2017
PJM | AB2-187 | Indian River-Nelson 138kV |  | DE | Sussex | Withdrawn | DPL | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 5/20/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB2-188 | Creswell 34.5kV |  | NC | Washington | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 4/29/2016 | 2/20/2019 |  | 6/30/2017
PJM | AB2-189 | Mackeys 230kV |  | NC | Washington | Withdrawn | Dominion | 120 | 84 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2016 | 5/20/2016 | Customer Milestone Not Met | 6/30/2017
PJM | AB2-190 | Hopewell-Surry 230kV | Fort Powhatan Solar | VA | Prince George | In Service | Dominion | 150 | 105 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/29/2016 |  | Customer Milestone Not Met | 12/1/2021 | 1/19/2022
PJM | AB2-191 | Mendota Hills | Mendota Hills Wind Farm | IL | Lee | In Service | ComEd | 20 | 8.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  | Document Posted | 4/29/2016 |  |  | 3/1/2019 | 2/11/2019
PJM | AB2-192 | Tasley-Oak Hall 69kV II |  | VA | Accomack | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/29/2016 | 9/26/2016 | Customer Initiated Withdrawal | 1/1/2018
PJM | AC1-001 | Delano 138kV | Salt City Solar | OH | Ross | Partially in Service - Under Construction | AEP | 49.9 | 33.93 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 5/6/2016 |  |  | 8/31/2023 | 8/8/2023
PJM | AC1-003 | Tidd-Wylie Ridge 345kV | ESC Brooke County Power I | WV | Brooke | Withdrawn | APS | 80 | 80 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 5/9/2016 | 10/10/2020 |  | 8/3/2021
PJM | AC1-006 | Aydlett 34.5kV |  | NC | Currituck | Withdrawn | Dominion | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/31/2016 | 9/21/2016 | Customer Initiated Withdrawal | 12/1/2017
PJM | AC1-007 | Crittenden 34.5kV |  | VA | Isle of Wight | Withdrawn | Dominion | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 5/31/2016 | 4/11/2017 | Customer Initiated Withdrawal | 12/1/2017
PJM | AC1-008 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 15 | 19.2 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 6/9/2016 |  |  | 1/13/2023
PJM | AC1-009 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 6/15/2016 | 3/29/2018 |  | 3/31/2019
PJM | AC1-010 | Gloucester 26kV | National Park NJ | NJ | Gloucester | Under Construction | PSEG | 6 | 2.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 6/22/2016 |  |  | 12/31/2025
PJM | AC1-011 | Emlenton 34.5kV |  | PA | Clarion | Withdrawn | PENELEC | 18 | 18 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 6/22/2016 | 4/21/2017 | Customer Milestone Not Met | 1/5/2018
PJM | AC1-012 | Rupert 34.5kV | Tri-State Solar | WV | Greenbrier | Withdrawn | AEP | 5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/23/2016 | 7/30/2018 |  | 10/31/2017
PJM | AC1-013 | Clybourn 12.5kV | Western Avenue Battery | IL | Cook | Withdrawn | ComEd | 0.1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/28/2016 | 5/7/2018 |  | 12/29/2017
PJM | AC1-014 | Farmingdale-Bennett I 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 4 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/8/2016 | 7/10/2017 | Customer Milestone Not Met | 5/30/2018
PJM | AC1-015 | Farmingdale-Bennett II 34.5kV |  | NJ | Monmouth | Withdrawn | JCPL | 0.4 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/8/2016 | 7/10/2017 | Customer Milestone Not Met | 9/1/2017
PJM | AC1-016 | Burlington 26 kV | Burlington 26 kV Solar | NJ | Burlington | Withdrawn | PSEG | 8.8 | 3.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/13/2016 |  |  | 3/31/2021
PJM | AC1-017 | Levittown 13 kV | Levittown 13 kV Solar | NJ | Burlington | In Service | PSEG | 3.7 | 1.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/13/2016 |  |  | 3/31/2020 | 5/28/2020
PJM | AC1-018 | Morris Park 12.47kV | Strykers Road Solar Farm | NJ | Warren | Withdrawn | JCPL | 1.4 | 0.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 7/13/2016 | 8/4/2020 |  | 7/1/2019
PJM | AC1-019 | Lake Nelson 13 kV | Lake Nelson 13 kV Solar | NJ | Middlesex | Withdrawn | PSEG | 0.9 | 0.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/13/2016 | 1/22/2018 |  | 11/30/2018
PJM | AC1-020 | Kittatinny-Newton 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 12.2 | 4.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/13/2016 | 5/31/2017 | Customer Milestone Not Met | 9/1/2016
PJM | AC1-021 | Yukon Hatfield 500kV | Smithton Generation Station | PA | Westmoreland | In Service | APS | 110 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 7/14/2016 |  |  | 3/1/2019 | 11/18/2018
PJM | AC1-022 | N. Vienna 138kV |  | OH | Brown | Withdrawn | DEOK | 60 | 42 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/14/2016 | 8/3/2016 | Customer Milestone Not Met | 12/31/2017
PJM | AC1-023 | Southwest Lima-East Lima 345kV |  | OH | Allen | Withdrawn | AEP | 120 | 84 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/14/2016 | 8/2/2016 | Customer Milestone Not Met | 12/31/2017
PJM | AC1-024 | Frazeysburg 138kV |  | OH | Muskingum | Withdrawn | AEP | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/14/2016 | 4/21/2017 | Customer Milestone Not Met | 12/1/2018
PJM | AC1-025 | Dale Summit | State College Pumping Station Battery | PA | Centre | In Service | APS | 1.5 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/18/2016 |  |  | 10/31/2018 | 2/14/2019
PJM | AC1-026 | Sayreville |  | NJ | Atlantic | Withdrawn | JCPL | 1.3 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/18/2016 | 8/9/2016
PJM | AC1-027 | Pendleton 34.5kV | Oceana Solar Facility | VA | City of Virginia Beach | In Service | Dominion | 17.6 | 11.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/26/2016 |  |  | 1/1/2018 | 12/1/2017
PJM | AC1-028 | North Salisbury 25kV |  | MD | Wicomico | Withdrawn | DPL | 3.8 | 3.8 | Capacity | Generation Interconnection | Biomass | Document Posted |  |  |  | 7/27/2016 | 4/5/2017 | Customer Initiated Withdrawal | 6/30/2017
PJM | AC1-029 | South River 230kV | Gateway Energy Center | NJ | Middlesex | Withdrawn | JCPL | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/29/2016 | 11/27/2019 |  | 5/16/2019
PJM | AC1-030 | Cinnaminson 13kV | Pennsauken Solar 3 | NJ | Camden | In Service | PSEG | 2.5 | 0.95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/1/2016 |  |  | 12/29/2017 | 12/13/2017
PJM | AC1-031 | Hampstead 13 kV |  | MD | Carroll | Withdrawn | BGE | 2 | 0.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 8/1/2016 | 8/1/2017 | Customer Milestone Not Met | 6/30/2017
PJM | AC1-032 | Wilmington |  | IL | Will | Withdrawn | ComEd | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/9/2016 | 8/30/2017 | Customer Initiated Withdrawal | 6/30/2017
PJM | AC1-033 | Kewanee 138 kV | Midland Wind Farm | IL | Henry | In Service | ComEd | 100.8 | 13.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/14/2016 |  |  | 4/15/2024 | 1/31/2024
PJM | AC1-034 | Heartsease DP - Mayo Dunbar 115kV | Edgecome Solar Energy Center | NC | Edgecombe | Suspended | Dominion | 75 | 42.75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/11/2016 |  |  | 12/31/2025
PJM | AC1-035 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | In Service | ME | 30 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 8/18/2016 |  |  | 5/31/2018 | 3/30/2018
PJM | AC1-036 | Twittys Creek 34.5kV | Twittys Creek Solar | VA | Charlotte | In Service | Dominion | 13.75 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 8/22/2016 |  |  | 12/31/2020 | 12/8/2020
PJM | AC1-037 | Doremus 13kV | Hillside Battery | NJ | Union | Withdrawn | PSEG | 0.5 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/22/2016 | 8/30/2017 | Customer Initiated Withdrawal | 12/29/2017
PJM | AC1-038 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 13 | 13 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 8/30/2016 |  |  | 10/1/2018 | 5/30/2016
PJM | AC1-039 | Catoctin 34kV | Catoctin Furnace Solar Facility | MD | Frederick | Withdrawn | APS | 20 | 10.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/31/2016 | 2/25/2021 |  | 10/31/2018
PJM | AC1-040 | Rockport-Duff-Coleman 345 kV |  | IN | Spencer | Withdrawn | AEP | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/31/2016 | 11/7/2018 |  | 12/31/2020
PJM | AC1-041 | Mt. Olive 12kV |  | MD | Worcester | Withdrawn | DPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 8/31/2016 | 6/5/2018 |  | 5/1/2018
PJM | AC1-042 | Altavista-Mt. Airy 69kV | Sycamore Solar I | VA | Pittsylvania | In Service | Dominion | 42 | 15.96 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/1/2016 |  |  | 12/1/2022 | 2/14/2023
PJM | AC1-043 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2016 |  |  | 12/15/2025
PJM | AC1-044 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 550 | 550 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2016 |  |  | 12/31/2022 | 12/7/2022
PJM | AC1-045 | King's Fork 34.5kV | TWE Myrtle Solar | VA | City of Suffolk | Withdrawn | Dominion | 15 | 9.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2016 | 6/22/2018 |  | 11/15/2018
PJM | AC1-046 | Fentress 34.5kV | Centerville Pike Solar | VA | City of Chesapeake | Withdrawn | Dominion | 15 | 9.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2016 | 10/20/2017 |  | 11/15/2018
PJM | AC1-047 | Hickory 34.5kV | TWE Chesapeake Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 12.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2016 | 10/20/2017 |  | 11/15/2018
PJM | AC1-048 | Germantown 115kV | Brookview Solar I | PA | Adams | Withdrawn | ME | 35 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2016 | 12/11/2023 |  | 12/31/2023
PJM | AC1-049 | Worcester 25kV |  | MD | Worcester | Withdrawn | DPL | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/31/2016 | 12/6/2018 |  | 5/1/2018
PJM | AC1-050 | Mardela 12kV | Mardela Springs | MD | Wicomico | Withdrawn | DPL | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2016 | 8/27/2018 |  | 5/1/2018
PJM | AC1-051 | Willard-S. Greenwich 69kV |  | OH | Huron | Withdrawn | AEP | 60 | 7.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn | Interim Study | 8/31/2016 | 1/12/2021 |  | 12/31/2017
PJM | AC1-052 | Tasley 69kV |  | VA | Accomack | Withdrawn | ODEC | 9 | 6.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2016 | 3/20/2018 |  | 5/1/2017
PJM | AC1-053 | Lanesville-Brokaw | Top Hat Wind Energy Center | IL | Logan | Under Construction | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/1/2016 |  |  | 12/15/2025
PJM | AC1-054 | Kerr Dam–Eatons Ferry 115 kV | Hawtree Creek | NC | Warren | In Service | Dominion | 65 | 44.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2016 |  |  | 6/1/2021 | 10/1/2021
PJM | AC1-055 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 30 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 9/10/2016 |  |  | 3/31/2028
PJM | AC1-059 | Desoto-Tanners Creek 345kV |  | IN | Fayette | Withdrawn | AEP | 300 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 9/13/2016 | 6/5/2018 |  | 12/15/2018
PJM | AC1-060 | Providence Forge 34.5kV | Charles City 1 | VA | Charles City | In Service | Dominion | 0 | 2.5 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/20/2016 |  |  | 6/1/2017 | 6/9/2017
PJM | AC1-061 | Locks 34.5kV | Dinwiddie 2 | VA | Dinwiddie | In Service | Dominion | 0 | 0.2 | Capacity | Generation Interconnection | Diesel; Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/20/2016 |  |  | 6/1/2017 | 6/1/2017
PJM | AC1-062 | Jetersville 34.5kV | Amelia 1 | VA | Amelia | In Service | Dominion | 0 | 1.9 | Capacity | Generation Interconnection | Diesel; Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/20/2016 |  |  | 6/1/2017 | 8/24/2018
PJM | AC1-063 | Shackleford 34.5kV | King & Queen Landfill Facility | VA | King and Queen | In Service | Dominion | 0 | 2.2 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/20/2016 |  |  | 6/1/2019 | 5/9/2019
PJM | AC1-064 | Route 16 34.5kV | Route 16 (Mountain View) 345kV (Upton 114) | PA | Franklin | In Service | APS | 1.1 | 1.1 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 9/20/2016 |  |  | 9/30/2017 | 6/22/2017
PJM | AC1-065 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/22/2016 |  |  | 12/31/2023
PJM | AC1-066 | Linden 26 kV |  | NJ | Union | Withdrawn | PSEG | 5 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 9/21/2016 | 12/11/2017 |  | 9/1/2017
PJM | AC1-067 | Davis Creek-Burnham |  | IL | Cook | Withdrawn | ComEd | 1254 | 1092 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/21/2016 | 3/27/2019 |  | 12/1/2021
PJM | AC1-068 | Atlanta 69kV I | Pickaway County Solar | OH | Pickaway | In Service | Dayton | 49.9 | 34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2016 |  |  | 1/7/2025 | 1/17/2025
PJM | AC1-069 | Atlanta 69kV II | Pickaway County II Solar | OH | Pickaway | In Service | Dayton | 49.9 | 34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2016 |  |  | 1/7/2025 | 1/17/2025
PJM | AC1-070 | Stuarts Draft 23kV |  | VA | Augusta | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/26/2016 | 12/15/2017 |  | 10/1/2018
PJM | AC1-071 | Paupack-Lackawanna 230kV | Waymart Wind II | PA | Wayne | Withdrawn | PPL | 67.25 | 8.74 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2016 | 9/8/2022 |  | 10/15/2021
PJM | AC1-072 | Segreto (Covert) 345kV | Covert Generating Facility | MI | Van Buren | In Service | ITCI | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 9/28/2016 |  |  | 6/18/2018 | 5/9/2018
PJM | AC1-073 | Laurel Mountain 138 kV | Laurel Mountain Wind Farm & Energy Storage Facility | WV | Barbour | Canceled | APS | 16.3 | 5.8 | Capacity | Generation Interconnection | Wind; Storage | Document Posted | Document Posted |  | Document Posted | 9/28/2016 |  |  | 12/31/2019
PJM | AC1-074 | Jacksonville-Renaker 138kV I | Bluebird Solar | KY | Harrison | Under Construction | EKPC | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2016 |  |  | 1/30/2025
PJM | AC1-075 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | In Service | Dominion | 60 | 38.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2016 |  |  | 12/31/2021 | 4/1/2021
PJM | AC1-076 | Locust Grove-Paytes 115kV | Pine Glade Solar | VA | Orange | In Service | Dominion | 62.5 | 23.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/2/2016 |  |  | 7/15/2024 | 9/13/2024
PJM | AC1-077 | Sayreville Storage |  | NJ | Middlesex | Withdrawn | JCPL | 0.38 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/30/2016 | 10/27/2016
PJM | AC1-078 | Beatty-London 138kV | Big Plain | OH | Madison | In Service | ATSI | 176 | 66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2016 |  |  | 8/31/2023 | 7/25/2023
PJM | AC1-079 | Broadwell Solar |  | KY | Harrison | Withdrawn | EKPC | 80 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2016 | 10/21/2016 |  | 6/1/2019
PJM | AC1-080 | Perth-Hickory Grove 115kV | Stagecoach Solar | VA | Halifax | In Service | Dominion | 20 | 12.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2016 |  |  | 12/31/2021 | 4/1/2021
PJM | AC1-081 | Susquehanna-Lackawanna 500kV |  | PA | Luzerne | Withdrawn | PPL | 180 | 180 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 9/30/2016 | 4/7/2017 | Customer Initiated Withdrawal | 9/28/2020
PJM | AC1-082 | Ravenswood-Hemlock 69kV | Great Bend | OH | Meigs | Engineering and Procurement | AEP | 48 | 29 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2016 |  |  | 10/31/2025
PJM | AC1-083 | Smith Mountain-Bearskin 138kV | Maplewood Solar | VA | Pittsylvania | In Service | AEP | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2016 |  |  | 5/20/2022 | 9/2/2022
PJM | AC1-084 | Mt. Arlington Solar |  | NJ | Morris | Withdrawn | JCPL | 1.6 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2016 | 10/17/2016 |  | 3/31/2018
PJM | AC1-085 | Stuart-Clinton 345kV | Highland County Solar | OH | Highland | In Service | Dayton | 400 | 152 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/2/2016 |  |  | 12/31/2023 | 8/21/2024
PJM | AC1-086 | Thelma 230kV | Cherry Solar | NC | Northhampton | Suspended | Dominion | 180 | 123.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/11/2016 |  |  | 8/31/2025
PJM | AC1-087 | Siegfried-Hauto 69kV | PA Solar Park | PA | Carbon | In Service | PPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/11/2016 |  |  | 12/1/2021 | 1/17/2020
PJM | AC1-088 | Strawton 138kV |  | IN | Madison | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 10/12/2016 | 5/8/2018 |  | 12/31/2017
PJM | AC1-089 | Hillsboro-Wildcat 138kV | Willowbrook Solar | OH | Highland | In Service | AEP | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/15/2016 |  |  | 1/19/2024 | 9/27/2024
PJM | AC1-090 | Hamilton Township 12kV |  | NJ | Atlantic | Withdrawn | AEC | 4 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/17/2016 | 7/17/2017 | Customer Milestone Not Met | 10/1/2017
PJM | AC1-091 | Cedar Creek 138kV I | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 19.8 | 7.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/19/2016 |  |  | 6/15/2025
PJM | AC1-092 | Cedar Creek 138kV II | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 19.8 | 7.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/20/2016 |  |  | 6/15/2025
PJM | AC1-093 | Cedar Creek 138kV III | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 18.8 | 7.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/20/2016 |  |  | 6/15/2025
PJM | AC1-094 | Cedar Creek 138kV IV | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 15.9 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/20/2016 |  |  | 6/15/2025
PJM | AC1-095 | Cedar Creek 25kV |  | DE | New Castle | Withdrawn | DPL | 9.9 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/19/2016 | 3/9/2020 |  | 6/30/2018
PJM | AC1-096 | Marysville-Flatlick 765kV |  | OH | Pickaway | Withdrawn | AEP | 1277 | 1277 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/20/2016 | 2/23/2017 | Customer Initiated Withdrawal | 6/1/2021
PJM | AC1-097 | Hatfield 500kV | Renaissance Energy Center | PA | Greene | Withdrawn | APS | 1140 | 1040 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/21/2016 | 11/11/2019 |  | 6/1/2021
PJM | AC1-098 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Under Construction | Dominion | 60 | 37.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/22/2016 |  |  | 6/30/2025
PJM | AC1-099 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Under Construction | Dominion | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/22/2016 |  |  | 6/30/2025
PJM | AC1-100 | Ohio Central 138kV | Dresden | OH | Muskingum | In Service | AEP | 98 | 43.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/24/2016 |  |  | 6/1/2020 | 11/10/2017
PJM | AC1-101 | Johns Creek-Excel 138kV I | Pike County Solar | KY | Pike | Suspended | AEP | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/26/2016 |  |  | 12/1/2028
PJM | AC1-102 | Johns Creek-Excel 138kV II | Pike County Solar | KY | Pike | Suspended | AEP | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/25/2016 |  |  | 12/1/2028
PJM | AC1-103 | Nottingham 138kV | Harrison Power Plant | OH | Harrison | Withdrawn | AEP | 1050 | 1026 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/25/2016 | 7/21/2022 |  | 6/11/2024
PJM | AC1-104 | Deepwater-Penns Grove 69kV |  | NJ | Salem | Withdrawn | AEC | 19.8 | 7.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/25/2016 | 11/6/2017 |  | 6/30/2018
PJM | AC1-105 | Halifax-Mt. Laurel 115kV | Sunnybrook Farm Solar | VA | Halifax | In Service | Dominion | 51 | 34.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/26/2016 |  |  | 2/9/2023 | 12/28/2022
PJM | AC1-106 | Chase City 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 0 | 15.7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/26/2016 | 4/10/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AC1-107 | Chickahominy 500kV | Chickahominy Power | VA | Charles City | Withdrawn | Dominion | 1600 | 1600 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/26/2016 | 2/13/2022 |  | 3/1/2024
PJM | AC1-108 | Hunterstown-Conemaugh 500kV | CPV Fairview Energy Center | PA | Cambria | In Service | PENELEC | 50 | 100 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/26/2016 |  |  | 3/1/2021 | 9/22/2019
PJM | AC1-109 | Aurora 345kV | Aurora Generation | IL | Du Page | In Service | ComEd | 30 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/26/2016 |  |  | 12/31/2020 | 8/27/2020
PJM | AC1-110 | Aurora 138kV | Aurora Generation | IL | Du Page | In Service | ComEd | 30 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/26/2016 |  |  | 8/28/2023 | 4/30/2023
PJM | AC1-111 | Aurora 138kV | Aurora Generation | IL | Du Page | In Service | ComEd | 36 | 36 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/26/2016 |  |  | 12/31/2020 | 8/27/2020
PJM | AC1-112 | Old Church 34.5kV | Hollyfield Solar Facility | VA | King William | In Service | Dominion | 17 | 10.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/27/2016 |  |  | 2/15/2019 | 8/8/2018
PJM | AC1-113 | Rockford | Rockford I Energy Center | IL | Winnebago | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/27/2016 |  |  | 12/31/2021 | 6/5/2021
PJM | AC1-114 | Rockford II | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/27/2016 |  |  | 12/31/2021 | 8/25/2021
PJM | AC1-115 | St. Johns 115kV |  | VA | Caroline | Withdrawn | Dominion | 14.9 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/27/2016 | 12/29/2017 |  | 4/30/2018
PJM | AC1-116 | Mount Eagle 34.5kV | Rivanna Solar | VA | Albemarle | Withdrawn | Dominion | 12.5 | 4.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/27/2016 | 6/5/2023 |  | 4/17/2023
PJM | AC1-117 | Stockton 34.5kV | Leatherwood | VA | Henry | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/27/2016 |  |  | 12/31/2021
PJM | AC1-118 | Westmoreland 34.5kV | Montross Solar Facility | VA | Westmoreland | In Service | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/27/2016 |  |  | 2/15/2019 | 12/12/2018
PJM | AC1-119 | Deep Run |  | NJ | Middlesex | Withdrawn | JCPL | 1.5 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/27/2016 | 11/16/2016 |  | 4/30/2017
PJM | AC1-120 | Mitchell-Mountain Run 115kV | Cricket Solar | VA | Culpeper | Engineering and Procurement | Dominion | 60 | 39.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/29/2016 |  |  | 6/28/2026
PJM | AC1-121 | Mitchell-Mountain Run 115kV | Cricket Solar | VA | Culpeper | Suspended | Dominion | 20 | 13.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/27/2016 |  |  | 6/30/2024
PJM | AC1-122 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | In Service | AEP | 60 | 40.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/27/2016 |  |  | 6/1/2021 | 10/21/2020
PJM | AC1-123 | Smith Mountain-Candler's Mountain 138kV | Altavista Solar | VA | Campbell | In Service | AEP | 20 | 13.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/27/2016 |  |  | 6/1/2021 | 10/21/2020
PJM | AC1-124 | Harryette 12kV |  | OH | Guernsey | Withdrawn | AEP | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/27/2016 | 7/20/2017 | Customer Initiated Withdrawal | 10/1/2017
PJM | AC1-125 | Harryette 12kV |  | OH | Guernsey | Withdrawn | AEP | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/27/2016 | 7/20/2017 | Customer Initiated Withdrawal | 10/1/2017
PJM | AC1-134 | Four Rivers 230kV | Doswell Facility (Doswell Complex 5 & 6) | VA | Hanover | In Service | Dominion | 0 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/28/2016 |  |  | 9/30/2019 | 2/28/2018
PJM | AC1-135 | Mickleton 230kV |  | NJ | Gloucester | Withdrawn | AEC | 0 | 62 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/28/2016 | 11/16/2016 | Customer Initiated Withdrawal | 6/1/2018
PJM | AC1-136 | Keriton 12kV |  | KY | Keaton | Withdrawn | DEOK | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/28/2016 | 11/4/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | AC1-137 | Erlanger 12kV |  | KY | Boone | Withdrawn | DEOK | 1.9 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/28/2016 | 11/4/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | AC1-138 | Bend Station 12kV |  | KY | Boone | Withdrawn | DEOK | 2.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/28/2016 | 11/28/2016 | Customer Initiated Withdrawal | 12/31/2017
PJM | AC1-139 | Doubs 230kV |  | MD | Frederick | Withdrawn | APS | 102 | 38.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/28/2016 | 10/31/2017 |  | 6/1/2019
PJM | AC1-140 | North Longview 500 kV | Longview Power | WV | Monongalia | In Service | APS | 10 | 10 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted |  | Document Posted | 10/28/2016 |  |  | 6/30/2018 | 5/14/2018
PJM | AC1-141 | Cook-East Elkhart 345kV | Indeck Niles Energy Center | MI | Cass | In Service | AEP | 91 | 91 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/28/2016 |  |  | 3/15/2022 | 12/27/2021
PJM | AC1-142 | Garner-Lancaster 115kV |  | VA | Lancaster | Withdrawn | Dominion | 100 | 57 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/28/2016 | 6/12/2017 | Customer Initiated Withdrawal | 12/31/2019
PJM | AC1-142A | Joliet | Joliet Units 7 and 8 | IL | Will | In Service | ComEd | 64 | 64 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/28/2016 |  |  | 12/31/2020 | 12/8/2020
PJM | AC1-143 | Brandy-Remington 115kV | Elkwood Solar | VA | Culpeper | Suspended | Dominion | 60 | 41.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 12/16/2023
PJM | AC1-144 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 85 | 57.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/31/2016 | 6/18/2018 |  | 10/1/2019
PJM | AC1-145 | Gretna DP 69 kV | Whitethorn Solar | VA | Pittsylvania | In Service | Dominion | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 9/1/2021 | 10/13/2021
PJM | AC1-146 | Chatham 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/31/2016 | 5/8/2017 | Customer Initiated Withdrawal | 9/1/2018
PJM | AC1-147 | Grassfield 34.5kV |  | VA | City of Chesapeake | In Service | Dominion | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  | Wholesale Market Participation Agreement | 10/31/2016 |  |  | 12/31/2021 | 3/25/2022
PJM | AC1-148 | Granger-Twin Branch 138kV |  | IN | St. Joseph | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2016 | 3/16/2018 |  | 11/1/2018
PJM | AC1-149 | Buckskin 69kV |  | OH | Ross | Withdrawn | AEP | 85 | 32.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2016 | 11/22/2016 | Customer Milestone Not Met | 6/1/2019
PJM | AC1-150 | Beaver 138kV |  | OH | Pike | Withdrawn | AEP | 200 | 76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2016 | 11/22/2016 | Customer Milestone Not Met | 6/1/2019
PJM | AC1-151 | Harwood-Berwick 69kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2016 | 9/23/2019 |  | 2/28/2019
PJM | AC1-152 | Lawrenceburg 345kV PB I | Lawrenceburg Generating Plant | IN | Dearborn | In Service | AEP | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/31/2016 |  |  | 6/1/2020 | 11/13/2019
PJM | AC1-153 | Kendall-Tazewell-Dresden-Mole Creek |  | IL | Grundy | Withdrawn | ComEd | 1300 | 1250 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 10/31/2016 | 8/10/2018 |  | 6/1/2021
PJM | AC1-154 | I.B. Corners 12kV | Harris Project | MD | Queen Anne's | Withdrawn | DPL | 3.2 | 1.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 7/25/2018 |  | 11/8/2018
PJM | AC1-155 | Mt. Airy 34.5kV |  | VA | Wythe | Withdrawn | AEP | 50 | 19 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2016 | 11/22/2016 | Customer Milestone Not Met | 6/1/2019
PJM | AC1-156 | Morgan's Cut 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 60 | 22.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2016 | 11/22/2016 | Customer Milestone Not Met | 6/1/2019
PJM | AC1-157 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2016 | 11/18/2016 | Customer Initiated Withdrawal | 10/1/2019
PJM | AC1-158 | Spotsylvania 500kV | Spotsylvania Energy Center | VA | Spotsylvania | In Service | Dominion | 485 | 337 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 12/31/2022 | 9/2/2020
PJM | AC1-159 | Chesapeake 230kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 250.1 | 369.1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 10/3/2018 |  | 1/1/2021
PJM | AC1-160 | Buckskin 69kV |  | OH | Ross | Withdrawn | Dayton | 100 | 100 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2016 | 11/18/2016 | Customer Initiated Withdrawal | 10/1/2019
PJM | AC1-161 | Septa 500kV | Cavalier | VA | Isle of Wight | In Service | Dominion | 240 | 168.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/2/2016 |  |  | 1/1/2023 | 12/10/2024
PJM | AC1-162 | Briery-Clover 230kV |  | VA | Prince Edward | Withdrawn | Dominion | 240 | 168.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 2/26/2019 |  | 10/1/2019
PJM | AC1-163 | Ahoskie 34.5KV |  | NC | Hertford | Withdrawn | Dominion | 16.94 | 11.54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 6/1/2018 |  | 10/1/2019
PJM | AC1-164 | Chickahominy 230kV | Chickahominy Solar 1 and 2 | VA | Charles City | Suspended | Dominion | 320 | 220.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 12/31/2024
PJM | AC1-165 | Atlanta 69kV III | Buckeye Plains II Solar | OH | Pickaway | In Service | Dayton | 49.9 | 33.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/2/2016 |  |  | 1/7/2025 | 1/17/2025
PJM | AC1-166 | Atlanta 69kV IV | Buckeye Plains Solar | OH | Pickaway | In Service | Dayton | 49.9 | 33.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/2/2016 |  |  | 1/7/2025 | 1/17/2025
PJM | AC1-167 | Mark Center 69kV | Mark Center Solar Project | OH | Defiance | Engineering and Procurement | AEP | 49.9 | 33.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2016 |  |  | 11/30/2024
PJM | AC1-168 | Kewanee-Streator | Hickory Wind | IL | Putnam | Suspended | ComEd | 78.65 | 10.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 10/31/2025
PJM | AC1-169 | Chicago Heights |  | IL | Will | Withdrawn | ComEd | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 10/31/2016 | 5/4/2018 |  | 9/30/2017
PJM | AC1-170 | New Canton 12.47V |  | NJ | Mercer | Withdrawn | JCPL | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2016 | 4/28/2017 | Customer Initiated Withdrawal | 10/1/2017
PJM | AC1-171 | Powerton | ZEP Valley Wind Farm | IL | Tazewell | Withdrawn | ComEd | 79.1 | 10.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 | 10/18/2022 |  | 12/15/2025
PJM | AC1-172 | Lawrenceburg 345kV PB II | Lawrenceburg Generating Plant | IN | Dearborn | In Service | AEP | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 10/31/2016 |  |  | 6/1/2020 | 11/13/2019
PJM | AC1-173 | Logtown 138kV | Timber Road IV Wind Farm (Southern Phase) | OH | Paulding | In Service | AEP | 75.9 | 9.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2016 |  |  | 3/31/2020 | 3/27/2020
PJM | AC1-174 | Losantville 345kV | Riverstart Solar Park | IN | Randolph | In Service | AEP | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 6/1/2022 | 9/24/2021
PJM | AC1-175 | Losantville 345kV | Riverstart Solar Park | IN | Randolph | In Service | AEP | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 6/1/2022 | 9/24/2021
PJM | AC1-176 | Timber Switch 138kV |  | OH | Paulding | Withdrawn | AEP | 58.7 | 7.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 7/9/2020 |  | 10/31/2019
PJM | AC1-177 | Kings Creek 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 4 | 4 | Capacity | Generation Interconnection | Biomass | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 5/28/2019 |  | 1/1/2019
PJM | AC1-178 | Millsboro 25kV |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | Capacity | Generation Interconnection | Biomass | Withdrawn |  |  |  | 10/31/2016 | 12/5/2016 |  | 1/1/2019
PJM | AC1-179 | Millsboro 25kV II |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | Capacity | Generation Interconnection | Biomass | Withdrawn |  |  |  | 10/31/2016 | 12/5/2016 |  | 1/1/2019
PJM | AC1-180 | Kings Creek 25kV |  | MD | Somerset | Withdrawn | DPL | 6 | 6 | Capacity | Generation Interconnection | Biomass | Document Posted |  |  |  | 10/31/2016 | 3/20/2017 | Customer Initiated Withdrawal | 1/1/2019
PJM | AC1-181 | Richland 138kV | Richland Power Plant | OH | Defiance | In Service | ATSI | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2016 |  |  | 6/1/2019 | 8/8/2018
PJM | AC1-182 | W.H. Zimmer Station 345kV | Zimmer Station | OH | Clermont | Deactivated | DEOK | 20 | 20 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted |  | Document Posted | 10/31/2016 |  |  | 12/31/2018 | 1/13/2019
PJM | AC1-183 | Ontelaunee 230kV |  | PA | Berks | Withdrawn | ME | 12 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 10/31/2016 | 5/15/2017 | Customer Initiated Withdrawal | 6/1/2019
PJM | AC1-184 | Printz |  | PA | Delaware | Withdrawn | PECO | 35 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 10/31/2016 | 7/25/2017 | Customer Initiated Withdrawal | 6/1/2019
PJM | AC1-185 | Lee County | Lee Energy Facility | IL | Lee | In Service | ComEd | 48 | 48 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 6/1/2019 | 12/14/2018
PJM | AC1-186 | Central City 115kV |  | PA | Somerset | Withdrawn | PENELEC | 138 | 17.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 10/31/2016 | 7/11/2018 |  | 12/31/2019
PJM | AC1-187 | Potter-Gold 115kV |  | PA | Potter | Withdrawn | APS | 117 | 15 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 10/31/2016 | 6/20/2018 |  | 12/31/2019
PJM | AC1-188 | Rio-Lick 138kV | Dixon Solar | OH | Jackson | Engineering and Procurement | AEP | 70 | 46.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2016 |  |  | 2/26/2027
PJM | AC1-189 | Chinquapin-Everetts 230kV | Pitt Solar | NC | Pitt | Engineering and Procurement | Dominion | 80 | 53.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 11/17/2026
PJM | AC1-190 | East New Market 69kV | New Market Solar | MD | Dorchester | Engineering and Procurement | DPL | 50 | 35 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 7/1/2028
PJM | AC1-191 | Elmont 115kV | Springfield Solar | VA | Hanover | Suspended | Dominion | 80 | 53.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 3/31/2024
PJM | AC1-193 | Handsome DP-Southampton 115kV |  | VA | Southampton | Withdrawn | Dominion | 55 | 20.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 10/31/2016 | 7/18/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AC1-194 | Elk 138kV | Vinton Solar | OH | Vinton | Suspended | AEP | 125 | 47.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 12/31/2025
PJM | AC1-195 | Dunkirk-Ada 69kV |  | OH | Hardin | Withdrawn | AEP | 75 | 9 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 10/31/2016 | 5/30/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AC1-196 | Mantua 12kV |  | NJ | Gloucester | Withdrawn | AEC | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 10/31/2016 | 11/22/2016 | Customer Initiated Withdrawal | 6/30/2017
PJM | AC1-197 | Somerset 480v | Somerset 480v | NJ | Somerset | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 12/3/2018 |  | 12/29/2017
PJM | AC1-198 | Union 480v | Union 480v | NJ | Union | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 12/3/2018 |  | 12/29/2017
PJM | AC1-199 | Mercer 480v I | Mercer 480v I | NJ | Mercer | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 12/3/2018 |  | 1/31/2018
PJM | AC1-200 | Mercer 480v II | Mercer 480v II | NJ | Mercer | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 12/3/2018 |  | 2/28/2018
PJM | AC1-201 | Camden 480v II | Camden 480v II | NJ | Camden | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 12/3/2018 |  | 12/29/2017
PJM | AC1-202 | Cedar 12kV | The Home Depot Store #0951 | NJ | Ocean | Withdrawn | AEC | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 11/12/2018 |  | 12/31/2018
PJM | AC1-203 | Camden 480v III | Camden 480v III | NJ | Camden | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 12/3/2018 |  | 12/29/2017
PJM | AC1-204 | Elwood | Jackson Generation | IL | Will | In Service | ComEd | 1200.9 | 1115.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 4/1/2022 | 5/3/2022
PJM | AC1-205 | Madison Park |  | NJ | Middlesex | Withdrawn | JCPL | 10.3 | 3.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2016 | 11/17/2016 |  | 12/29/2017
PJM | AC1-206 | Clubhouse 230kV |  | VA | Greensville | Withdrawn | Dominion | 85 | 57.72 | Capacity | Generation Interconnection | Storage; Solar | Document Posted | Document Posted |  |  | 10/31/2016 | 1/18/2018 |  | 10/1/2019
PJM | AC1-207 | Monroe 34.5kV | Hoffman Station Road Solar | NJ | Middlesex | In Service | JCPL | 13.1 | 4.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 10/31/2016 |  |  | 5/26/2020 | 6/25/2020
PJM | AC1-208 | Cox-Whitakers 115kV | Halifax County Solar | NC | Halifax | Engineering and Procurement | Dominion | 80 | 55.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2016 |  |  | 12/15/2023
PJM | AC1-209 | Pine Grove Solar | Pine Grove Solar | PA | York | Withdrawn | PECO | 18 | 12.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 10/4/2019 |  | 9/30/2021
PJM | AC1-210 | Madison 69kV |  | OH | Madison | Withdrawn | AEP | 45 | 31 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/31/2016 | 7/17/2018 |  | 6/30/2018
PJM | AC1-211 | McConnellsburg 138kV |  | PA | Fulton | Withdrawn | APS | 70 | 48.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/31/2016 | 11/6/2017 |  | 6/30/2018
PJM | AC1-212 | Minster 69kV | Minster III ESS | OH | Auglaize | Withdrawn | Dayton | 19.9 | 1.9 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/31/2016 | 12/16/2020 |  | 12/31/2020
PJM | AC1-213 | North Salisbury 25kV |  | MD | Somerset | Withdrawn | DPL | 5.3 | 3.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 5/24/2021 |  | 9/30/2017
PJM | AC1-214 | Crescent Ridge | Lone Tree Wind | IL | Bureau | In Service | ComEd | 79.4 | 19 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 12/30/2020 | 11/20/2020
PJM | AC1-215 | Chase-City-Twittys Creek 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 100 | 68.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/31/2016 | 6/21/2017 | Customer Initiated Withdrawal | 6/30/2018
PJM | AC1-216 | Hopewell-Surry 230kV | Spring Grove I Solar | VA | Surry | In Service | Dominion | 97.9 | 54.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/31/2016 |  |  | 12/1/2020 | 10/1/2020
PJM | AC1-217 | McConnellsburg-Texas Eastern 6 138kV |  | PA | Franklin | Withdrawn | APS | 55 | 37.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/31/2016 | 11/29/2017 |  | 6/30/2018
PJM | AC1-218 |  |  | NJ | Morris | Withdrawn | JCPL | 0.25 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/31/2016 | 11/7/2016 |  | 1/31/2017
PJM | AC1-219 |  |  | NJ | Morris | Withdrawn | JCPL | 0.2 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/31/2016 | 11/7/2016 |  | 1/31/2017
PJM | AC1-220 | Price 25kV |  | MD | Queen Anne's | Withdrawn | DPL | 26.5 | 15.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 5/8/2018 |  | 9/30/2018
PJM | AC1-221 | Halifax-Person 230kV | Alton Post Office Solar | VA | Halifax | In Service | Dominion | 29.2 | 14.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/2/2016 |  |  | 12/31/2024 | 1/9/2025
PJM | AC1-222 | Crystal Hill-Halifax 115kV | Halifax County Solar | VA | Halifax | In Service | Dominion | 44.7 | 22.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/3/2016 |  |  | 12/29/2023 | 2/15/2024
PJM | AC1-224 | Wye Mills 25kV |  | MD | Talbot | Withdrawn | DPL | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 10/31/2016 | 4/4/2018 |  | 2/1/2017
PJM | AC1-225 | Sorenson-Marysville 765kV |  | OH | Van Wert | Withdrawn | AEP | 300.2 | 39 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 10/31/2016 | 7/16/2018 |  | 12/31/2019
PJM | AC1-226 | Wurno-Claytor 138kV |  | VA | Pulaski | Withdrawn | AEP | 200.1 | 26 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 10/31/2016 | 4/3/2017 | Customer Initiated Withdrawal | 12/31/2019
PJM | AC1-227 | Low Moor-Lexington 230kV |  | VA | Botetourt | Withdrawn | Dominion | 96.6 | 12 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 7/13/2018 |  | 12/31/2019
PJM | AC1-228 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/31/2016 | 2/23/2018 |  | 3/31/2018
PJM | AC1-229 | Omar 12kV |  | DE | Sussex | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 10/31/2016 | 12/6/2018 |  | 3/31/2018
PJM | AC2-001 |  |  | OH | Van Wert | Withdrawn | AEP | 300.2 | 39 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 11/1/2016 | 12/6/2016 | Queue Not Required | 12/31/2019
PJM | AC2-002 |  |  | VA | Pulaski | Withdrawn | AEP | 179.4 | 23 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 11/1/2016 | 12/6/2016 | Queue Not Required | 12/31/2019
PJM | AC2-003 |  |  | VA | Botetourt | Withdrawn | Dominion | 78 | 10 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 11/1/2016 | 12/6/2016 | Queue Not Required | 10/12/2023
PJM | AC2-004 | Meyersdale 115kV |  | PA | Somerset | Withdrawn | PENELEC | 50.75 | 6.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 11/1/2016 | 7/12/2018 |  | 12/13/2019
PJM | AC2-005 | Todd 25kV |  | MD | Dorchester | Withdrawn | DPL | 3 | 1.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/1/2016 | 1/23/2017 |  | 3/31/2018
PJM | AC2-006 | Oman 12kV |  | DE | Sussex | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/1/2016 | 1/23/2017 |  | 3/31/2018
PJM | AC2-007 | Belvidere |  | IL | Boone | Withdrawn | ComEd | 20 | 7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 11/1/2016 | 7/5/2018 |  | 12/31/2017
PJM | AC2-008 | Wildcat 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/3/2016 | 6/5/2017 | Customer Initiated Withdrawal | 6/3/2019
PJM | AC2-009 | Pennington 13 kV | Pennington 13 kV Solar | NJ | Mercer | In Service | PSEG | 0.59 | 0.1 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/1/2016 |  |  | 3/2/2018 | 10/19/2017
PJM | AC2-010 | Millsboro 25kV |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | Capacity | Generation Interconnection | Biomass | Withdrawn |  |  |  | 12/5/2016 | 3/24/2017 | Customer Milestone Not Met | 4/30/2018
PJM | AC2-011 | Millsboro 25kV II |  | DE | Sussex | Withdrawn | DPL | 6 | 6 | Capacity | Generation Interconnection | Biomass | Withdrawn |  |  |  | 12/5/2016 | 3/24/2017 | Customer Milestone Not Met | 7/31/2018
PJM | AC2-012 | Grassfield-Great Bridge 115kV | Shillelagh Solar | VA | City of Chesapeake | In Service | Dominion | 118 | 44.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/20/2016 |  |  | 12/31/2023 | 12/20/2023
PJM | AC2-013 | Ripley 69kV |  | MD | Charles | Withdrawn | PEPCO | 27.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/28/2016 | 1/24/2017 | Customer Milestone Not Met | 11/30/2018
PJM | AC2-014 | Ripley-Nanjemoy 69kV |  | MD | Charles | Withdrawn | PEPCO | 32.5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/28/2016 | 1/24/2017 | Customer Milestone Not Met | 11/30/2018
PJM | AC2-015 | Chatfield-Howard 138kV | Sycamore Creek Solar | OH | Crawford | Engineering and Procurement | AEP | 117 | 53.55 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/29/2016 |  |  | 9/1/2025
PJM | AC2-016 | Stemple 345kV | Carroll County Energy LLC | OH | Carroll | In Service | AEP | 6 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 1/3/2017 |  |  | 9/1/2019 | 2/14/2020
PJM | AC2-017 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 11.1 | 11.1 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 1/4/2017 |  |  | 1/13/2023
PJM | AC2-018 | Rock Springs 500kV | Rock Springs Units #3 & #4 | MD | Cecil | In Service | Essential Power | 60 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 1/19/2017 |  |  | 6/1/2017 | 10/1/2017
PJM | AC2-019 | Highland 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/19/2017 | 7/13/2017 | Customer Initiated Withdrawal | 12/31/2019
PJM | AC2-020 | Greenfield-Buckskin 69kV |  | OH | Ross | Withdrawn | Dayton | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/19/2017 | 8/3/2018 |  | 12/31/2019
PJM | AC2-021 | Albright-Cross School 138 kV |  | MD | Garrett | Withdrawn | APS | 15 | 15 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Withdrawn | 1/25/2017 | 9/9/2020 |  | 1/15/2019
PJM | AC2-022 | Gordonsville-Remington 230kV |  | VA | Culpeper | Withdrawn | Dominion | 100 | 70.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 1/25/2017 | 11/1/2017 |  | 9/30/2019
PJM | AC2-023 | Hebron 69kV | Porter Mill Solar | MD | Wicomico | Engineering and Procurement | DPL | 45.8 | 26.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/25/2017 |  |  | 5/1/2026
PJM | AC2-024 | Edison 4kV |  | NJ | Middlesex | Withdrawn | PSEG | 1.2 | 0.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 1/25/2017 | 1/29/2018 |  | 12/31/2017
PJM | AC2-025 | Hatfield 500kV |  | PA | Greene | Withdrawn | APS | 1140 | 1140 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 1/25/2017 | 3/28/2017 | Customer Initiated Withdrawal | 6/1/2022
PJM | AC2-026 | Wakefield 138kV |  | OH | Scioto | Withdrawn | AEP | 50 | 27.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 1/30/2017 | 9/6/2017 | Customer Milestone Not Met | 6/30/2019
PJM | AC2-027 | Highland 12kV |  | OH | Highland | Withdrawn | AEP | 10 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/30/2017 | 7/19/2017 | Customer Initiated Withdrawal | 11/30/2018
PJM | AC2-028 | Highland 13.2kV |  | OH | Highland | Withdrawn | AEP | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/31/2017 | 4/12/2017 | Customer Initiated Withdrawal | 10/31/2018
PJM | AC2-029 | Circleville 138kV | Circleville Solar Energy | OH | Pickaway | Suspended | AEP | 70 | 26.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/2/2017 |  |  | 12/31/2027
PJM | AC2-030 | East Beaver 69kV |  | OH | Pike | Withdrawn | AEP | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/3/2017 | 12/6/2017 |  | 12/31/2018
PJM | AC2-031 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 67 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/3/2017 | 10/4/2017 |  | 10/1/2019
PJM | AC2-035 | Lick-Firebrick 69kV |  | OH | Jackson | Withdrawn | AEP | 49 | 29.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/3/2017 | 2/25/2019 |  | 6/1/2019
PJM | AC2-036 | Ravenswood-East Bashan Switch 69kV |  | OH | Meigs | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/3/2017 | 3/12/2019 |  | 6/1/2020
PJM | AC2-037 | Lick 69kV |  | OH | Jackson | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/3/2017 | 5/5/2017 | Customer Initiated Withdrawal | 6/1/2019
PJM | AC2-038 | Lee 69kV |  | OH | Athens | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/3/2017 | 9/27/2019 |  | 6/1/2019
PJM | AC2-039 | Poston-Dexter 69kV |  | OH | Athens | Withdrawn | AEP | 43 | 29.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/3/2017 | 5/5/2017 | Customer Initiated Withdrawal | 6/1/2019
PJM | AC2-040 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 49 | 29.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/3/2017 | 10/18/2017 |  | 6/1/2019
PJM | AC2-041 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/3/2017 | 10/18/2017 |  | 6/1/2019
PJM | AC2-042 | Hillsboro 138kV |  | OH | Highland | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/3/2017 | 10/18/2017 |  | 6/1/2019
PJM | AC2-043 | W. Millersport-S. Baltimore 138kV |  | OH | Fairfield | Withdrawn | AEP | 50 | 20 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/6/2017 | 9/14/2018 |  | 12/15/2018
PJM | AC2-044 | Maddox Creek 345kV | Blue Creek Wind Farm | OH | Van Wert | Suspended | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/7/2017 |  |  | 11/30/2024
PJM | AC2-045 | Clark 12kV | Solar Power and Light, LLC | OH | Athens | Withdrawn | AEP | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/7/2017 | 6/29/2020 |  | 12/31/2019
PJM | AC2-046 | EAst Beaver 138kV |  | OH | Jackson | Withdrawn | AEP | 63 | 39.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/8/2017 | 9/26/2017 |  | 12/31/2018
PJM | AC2-047 | Ashley-Millbrook Park 69 kV |  | OH | Scioto | Withdrawn | AEP | 18.3 | 7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/8/2017 | 10/23/2017 |  | 10/31/2018
PJM | AC2-048 | Sporn 138kV |  | OH | Meigs | Withdrawn | AEP | 60 | 22.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/10/2017 | 1/9/2023 |  | 12/31/2018
PJM | AC2-049 | Hillsboro-Millbrook 138kV |  | OH | Highland | Withdrawn | AEP | 49 | 29.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/10/2017 | 10/13/2017 |  | 6/1/2019
PJM | AC2-050 | Tabernacle 12kV | Seneca Energy | NJ | Burlington | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 2/10/2017 | 6/27/2022 |  | 11/30/2025
PJM | AC2-051 | Pickaway Solar |  | OH | Pickaway | Withdrawn | AEP | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/13/2017 | 3/24/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AC2-053 | Germantown 115kV | Brookview Solar I | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/15/2017 | 12/11/2023 |  | 12/31/2023
PJM | AC2-054 | South Rultonham 69kV |  | OH | Muskingum | Withdrawn | AEP | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/14/2017 | 5/1/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AC2-055 | Buckskin 69kV |  | OH | Highland | Withdrawn | AEP | 47.5 | 18.05 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/14/2017 | 4/22/2021 |  | 7/1/2019
PJM | AC2-056 | Killen 345kV |  | OH | Adams | Withdrawn | Dayton | 20 | 13.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/15/2017 | 5/5/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AC2-057 | Ridgeway-Dan River 69kV |  | VA | Pittsylvania | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/16/2017 | 10/4/2017 |  | 12/31/2018
PJM | AC2-058 | Newcomerstown-N. Philly 69kV |  | OH | Tuscarawas | Withdrawn | AEP | 16.37 | 16.37 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/16/2017 | 7/12/2017 | Customer Initiated Withdrawal | 12/31/2018
PJM | AC2-059 | Biers Run-Circleville 138kV | Yellowbud Solar | OH | Ross | In Service | AEP | 127 | 62.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/16/2017 |  |  | 12/15/2022 | 12/21/2022
PJM | AC2-060 | Buckskin 69kV | Ross County Solar | OH | Ross | Partially in Service - Under Construction | AEP | 100 | 64 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/18/2017 |  |  | 6/1/2024
PJM | AC2-061 | Hillsboro-Clinton 138kV | Dodson Creek Solar | OH | Ross | Under Construction | AEP | 117 | 58.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/17/2017 |  |  | 7/30/2024
PJM | AC2-062 | Emerald-Kenton 138kV |  | OH | Brown | Withdrawn | AEP | 55 | 55 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/22/2017 | 10/4/2017 |  | 12/31/2019
PJM | AC2-063 | Earleys 230kV |  | NC | Bertie | Withdrawn | Dominion | 100 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/22/2017 | 3/17/2017 | Customer Milestone Not Met | 10/31/2019
PJM | AC2-064 | Hillsboro-Millbrook 138kV |  | OH | Highland | Withdrawn | AEP | 115 | 69 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/22/2017 | 12/9/2019 |  | 6/1/2019
PJM | AC2-066 | Hillcrest 138kV | Hillcrest Solar Facility | OH | Brown | In Service | DEOK | 75 | 28.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 2/24/2017 |  |  | 12/31/2020 | 12/18/2020
PJM | AC2-067 | Camden-Crystal I 69kV | Eaton OH Solar | OH | Preble | Suspended | Dayton | 49.9 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/27/2017 |  |  | 12/31/2024
PJM | AC2-068 | Camden-Crystal II 69kV | Eaton OH Solar | OH | Preble | Suspended | Dayton | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/27/2017 |  |  | 12/31/2024
PJM | AC2-069 | Jacsonville-Renaker 138kV III |  | KY | Harrison | Withdrawn | EKPC | 60 | 40.2 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/27/2017 | 9/11/2017 | Customer Initiated Withdrawal | 6/1/2019
PJM | AC2-070 | Old Church 34.5kV | Hollyfield II | VA | King William | Withdrawn | Dominion | 13 | 9.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2017 | 1/22/2021 |  | 12/31/2021
PJM | AC2-071 | Buckingham 35kV | Buckingham IIK | VA | Buckingham | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2017 | 1/22/2021 |  | 12/31/2021
PJM | AC2-072 | Nokesville 35kV | Nokesville | VA | Prince William | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2017 | 1/22/2021 |  | 12/31/2021
PJM | AC2-073 | Harmony Village 35kV | Church View | VA | Middlesex | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2017 | 9/24/2019 |  | 12/31/2021
PJM | AC2-074 | Mt. Jackson 35kV | Mt. Jackson I | VA | Shenandoah | Withdrawn | Dominion | 15.65 | 10.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/27/2017 | 1/22/2021 |  | 12/31/2021
PJM | AC2-075 | Jacksonville-Renaker 138 kV | Bluebird Solar | KY | Harrison | Under Construction | EKPC | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2017 |  |  | 5/28/2025
PJM | AC2-076 | Kiski Valley–Vandergrift 25 kV | Kiski Valley | PA | Westmoreland | Withdrawn | APS | 19.9 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/28/2017 | 10/22/2018 |  | 4/30/2020
PJM | AC2-077 | Sabinsville 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 2/28/2017 | 8/1/2019 |  | 5/31/2018
PJM | AC2-078 | Disputanta-Waverly 115kV | Warwick PVI | VA | Prince George | Withdrawn | Dominion | 60 | 22.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2017 | 2/9/2021 |  | 12/1/2022
PJM | AC2-079 | Ivor-Oak Ridge 115kV | Windsor PVI | VA | Isle of Wight | Suspended | Dominion | 85 | 32.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/3/2017 |  |  | 6/1/2023
PJM | AC2-080 | Olive-Reynolds 345kV |  | IN | Jasper | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/28/2017 | 4/21/2021 |  | 12/31/2019
PJM | AC2-081 | Battle Town 115kV |  | VA | Clarke | Withdrawn | APS | 100 | 38 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2017 | 3/24/2017 | Customer Milestone Not Met | 12/31/2019
PJM | AC2-082 | Remington-Gainesville 230kV |  | VA | Fauquier | Withdrawn | Dominion | 85 | 32.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/28/2017 | 6/5/2018 |  | 12/31/2019
PJM | AC2-083 | Dawson-South Justice 115kV |  | NC | Halifax | Withdrawn | Dominion | 20 | 13.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/28/2017 | 10/3/2020 |  | 6/1/2019
PJM | AC2-084 | Dawson-South Justice 115kV | American Beech Solar | NC | Halifax | Under Construction | Dominion | 60 | 40.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/2/2017 |  |  | 6/30/2025
PJM | AC2-085 | Eastwood 34kV |  | OH | Clermont | Withdrawn | DEOK | 20 | 10.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/28/2017 | 7/2/2018 |  | 5/31/2019
PJM | AC2-086 | Eastwood 34.5kV |  | OH | Clermont | Withdrawn | DEOK | 20 | 10.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2017 | 4/10/2017 | Customer Initiated Withdrawal | 5/30/2019
PJM | AC2-087 | Buckskin 69kV |  | OH | Ross | Withdrawn | AEP | 85 | 47.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/28/2017 | 1/15/2020 |  | 5/31/2019
PJM | AC2-088 | S. Bethel-Brown 69kV | Nestlewood Solar | OH | Clermont | In Service | DEOK | 70 | 38.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/1/2017 |  |  | 3/31/2024 | 12/27/2023
PJM | AC2-089 | Klockner 34.5 kV | Silverside Solar | VA | Wythe | Withdrawn | AEP | 18.2 | 8.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/28/2017 | 3/22/2019 |  | 12/31/2019
PJM | AC2-090 | Losantville 345kV | Riverstart Solar Park III | IN | Randolph | In Service | AEP | 100 | 38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/7/2017 |  | Customer Milestone Not Met | 12/31/2024 | 12/18/2024
PJM | AC2-091 | Modoc (Riverstart Solar IV) 138kV |  | IN | Randolph | Withdrawn | AEP | 100 | 38 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2017 | 3/31/2017 | Customer Milestone Not Met | 11/30/2019
PJM | AC2-092 | Susquehanna-Lackawanna 500kV | Freedom Generation Plant | PA | Luzerne | In Service | PPL | 55 | 65 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/1/2017 |  |  | 6/1/2022 | 1/26/2023
PJM | AC2-093 | Brunswick-Wake 500 kV |  | NC | Northhampton | Withdrawn | Dominion | 675 | 429.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/2/2017 | 7/6/2018 |  | 12/1/2021
PJM | AC2-094 | Louisa-North Anna 230kV |  | VA | Louisa | Withdrawn | Dominion | 99.9 | 63.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/6/2017 | 10/30/2017 |  | 10/1/2019
PJM | AC2-095 | Eastwood 138kV |  | OH | Clermont | Withdrawn | DEOK | 10 | 5.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/8/2017 | 4/11/2017 | Customer Initiated Withdrawal | 5/30/2019
PJM | AC2-096 | Wurno I 34.5KV |  | VA | Pulaski | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 3/9/2017 | 1/10/2018 |  | 6/1/2018
PJM | AC2-097 | Wurno II 34.5kV |  | VA | Pulaski | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 3/9/2017 | 1/10/2018 |  | 6/1/2018
PJM | AC2-098 | Buckhorn-Lonesome Pine 138kV |  | VA | Tazewell | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/9/2017 | 8/30/2017 | Customer Initiated Withdrawal | 6/1/2018
PJM | AC2-099 | Nursery 36kV |  | OH | Lake | Withdrawn | ATSI | 3 | 3 | Capacity | Generation Interconnection | Methane | Document Posted |  |  |  | 3/9/2017 | 9/8/2017 | Customer Initiated Withdrawal | 6/30/2018
PJM | AC2-100 | Halifax-Person 230kV | Powells Creek Solar | VA | Halifax | In Service | Dominion | 50 | 33.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/12/2017 |  |  | 11/1/2023 | 8/23/2023
PJM | AC2-101 | Ripley-Nanjemoy 69kV | Shugart Solar | MD | Charles | Withdrawn | SMECO | 32.5 | 12.35 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 3/10/2017 | 12/3/2020 |  | 3/15/2021
PJM | AC2-102 | Mitchell DP 115kV |  | VA | Culpeper | Withdrawn | Dominion | 80 | 30.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/10/2017 | 4/15/2020 |  | 6/30/2019
PJM | AC2-103 | Beaver-Davis Besse 345 kV I | Firelands Wind | OH | Erie | Suspended | ATSI | 297.66 | 38.69 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/10/2017 |  |  | 12/31/2023
PJM | AC2-104 | Marysville-Sorenson 765kv |  | OH | Van Wert | Withdrawn | AEP | 500.25 | 65.03 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 3/10/2017 | 11/7/2019 |  | 12/31/2020
PJM | AC2-105 | Saddler 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 73.51 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/13/2017 | 3/29/2017 | Customer Initiated Withdrawal | 10/1/2019
PJM | AC2-106 | Biers Run 138kV |  | OH | Ross | Withdrawn | AEP | 100 | 68.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/13/2017 | 12/13/2017 |  | 10/1/2019
PJM | AC2-107 | Perth 115kV |  | VA | Halifax | Withdrawn | Dominion | 100 | 68.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/13/2017 | 3/27/2019 |  | 10/1/2019
PJM | AC2-108 | Wharton 115kV |  | NC | Beaufort | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/13/2017 | 3/31/2017 | Customer Milestone Not Met | 9/30/2019
PJM | AC2-110 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/14/2017 |  |  | 12/31/2023
PJM | AC2-111 | College Corner 138kV | Angelina Solar I | OH | Preble | Suspended | AEP | 80 | 30.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/16/2017 |  |  | 7/1/2024
PJM | AC2-112 | Stuarts Draft-Waynesboro 115kV | Augusta Solar | VA | Augusta | Withdrawn | Dominion | 150 | 103.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/17/2017 | 9/27/2024 |  | 12/15/2023
PJM | AC2-113 | Culpeper 35kV | Culpeper North | VA | Culpeper | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/17/2017 | 10/8/2018 |  | 12/31/2021
PJM | AC2-114 | Magnolia-Summersville 69kV |  | KY | Campbell | Withdrawn | EKPC | 49.9 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/20/2017 | 9/13/2017 | Customer Initiated Withdrawal | 7/1/2019
PJM | AC2-115 | Rockford | Rockford I Energy Center | IL | Winnebago | In Service | ComEd | 40 | 40 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/21/2017 |  |  | 12/31/2021 | 8/27/2021
PJM | AC2-116 | Rockford II | Rockford II Energy Center | IL | Winnebago | In Service | ComEd | 7 | 7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/21/2017 |  |  | 6/1/2021 | 8/25/2021
PJM | AC2-117 | University Park North | University Park North Energy Center | IL | Will | In Service | ComEd | 46 | 46 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/21/2017 |  |  | 5/31/2021 | 11/6/2023
PJM | AC2-118 | Cabot-Keystone 500kV |  | PA | Armstrong | Withdrawn | APS | 1200 | 1100 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 3/21/2017 | 8/22/2017 | Customer Initiated Withdrawal | 6/1/2021
PJM | AC2-119 | Grandview 138kV |  | WV | Raliegh | Withdrawn | AEP | 25 | 17.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/22/2017 | 9/6/2017 | Customer Milestone Not Met | 12/31/2018
PJM | AC2-120 | Ripley 69kV | Ripley Solar | MD | Charles | In Service | SMECO | 27.5 | 10.45 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 3/24/2017 |  |  | 7/13/2022 | 6/23/2023
PJM | AC2-121 | Gordonsville-Remington 230kV |  | VA | Culpeper | Withdrawn | Dominion | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/23/2017 | 11/2/2017 |  | 9/15/2019
PJM | AC2-122 | Lick Run 115kV |  | PA | Somerset | Withdrawn | PENELEC | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/23/2017 | 12/10/2018 |  | 12/15/2019
PJM | AC2-123 | Jacksons Ferry 138kV | Wythe County Solar Project | VA | Wythe | Under Construction | AEP | 75 | 44.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/25/2017 |  |  | 10/15/2024
PJM | AC2-124 | Gunn Road 345kV |  | OH | Hardin | Withdrawn | AEP | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/24/2017 | 11/19/2018 |  | 12/15/2019
PJM | AC2-125 | Ladysmith 230 kV I | Ladysmith Combustion Turbines Unit 1 | VA | Caroline | In Service | Dominion | 19 | 14.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/24/2017 |  |  | 6/1/2020 | 5/17/2019
PJM | AC2-126 | Ladysmith 230 kV II | Ladysmith Combustion Turbines Unit 2 | VA | Caroline | In Service | Dominion | 19 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/24/2017 |  |  | 6/1/2020 | 5/17/2019
PJM | AC2-127 | Ladysmith CT Unit 3 |  | VA | Caroline | Withdrawn | Dominion | 19 | 8.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/24/2017 | 4/12/2019 |  | 6/1/2017
PJM | AC2-128 | Ladysmith CT Unit 4 |  | VA | Caroline | Withdrawn | Dominion | 19 | 7.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/24/2017 | 4/12/2019 |  | 6/1/2017
PJM | AC2-129 | Ladysmith CT Unit 5 |  | VA | Caroline | Withdrawn | Dominion | 19 | 7.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/24/2017 | 4/12/2019 |  | 6/1/2017
PJM | AC2-130 | Chesterfield 230kV 5 | Chesterfield Unit 5 | VA | Chesterfield | In Service | Dominion | 14 | 13.2 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted |  | Document Posted | 3/24/2017 |  |  | 12/31/2018 | 12/31/2018
PJM | AC2-131 | Chesterfield 230kV 7 |  | VA | Chesterfield | Withdrawn | Dominion | 14 | 14.3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/24/2017 | 12/17/2018 |  | 6/1/2017
PJM | AC2-132 | Chesterfield 230kV 8 |  | VA | Chesterfield | Withdrawn | Dominion | 11 | 8.8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/24/2017 | 12/17/2018 |  | 6/1/2017
PJM | AC2-133 | Warren County 500kV | Warren County Power Station | VA | Warren | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/24/2017 |  |  | 9/30/2018 | 9/4/2018
PJM | AC2-134 | Hamburg 34.5kV |  | NJ | Sussex | Withdrawn | JCPL | 9 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/27/2017 | 10/24/2017 |  | 12/31/2018
PJM | AC2-135 | Double Toll Gate 34.5kV |  | VA | Clarke | Withdrawn | APS | 20 | 9.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/27/2017 | 6/20/2017 | Customer Initiated Withdrawal | 6/30/2018
PJM | AC2-136 | East Hagerstown 12kV | East Hagerstown Solar | MD | Washington | Under Construction | APS | 11.8 | 5.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/29/2017 |  |  | 9/30/2024
PJM | AC2-137 | Elko 34.5kV | Briel Farm Solar | VA | Henrico | In Service | Dominion | 18.8 | 11.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2017 |  |  | 12/30/2020 | 12/21/2020
PJM | AC2-138 | Northern Neck 34.5kV | Gardy's Mill Solar | VA | Westmoreland | In Service | Dominion | 10.8 | 4.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2017 |  |  | 12/30/2020 | 12/21/2020
PJM | AC2-139 | Mantua 12kV | The Home Depot Store # 0974 | NJ | Gloucester | Withdrawn | AEC | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2017 | 11/12/2018 |  | 12/30/2018
PJM | AC2-140 | DC Cook Unit 2 | DC Cook Generating Plant Unit No. 2 | MI | Berrien | In Service | AEP | 28 | 38 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 3/27/2017 |  |  | 6/1/2020 | 1/14/2017
PJM | AC2-141 | Septa 500kV | Sycamore Cross Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 240 | 168.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/30/2017 |  |  | 4/1/2026
PJM | AC2-142 | Hatfield 500kV | Hilltop Energy Center Facility | PA | Greene | In Service | APS | 129.7 | 129.7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/28/2017 |  |  | 5/9/2021 | 4/1/2021
PJM | AC2-143 | Cranbury 34.5kV |  | NJ | Middlesex | Withdrawn | JCPL | 3 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 3/28/2017 | 11/13/2017 | Customer Initiated Withdrawal | 3/31/2019
PJM | AC2-144 | Newburgh 12.47kV | 59 Newburgh | NJ | Warren | Withdrawn | JCPL | 0.25 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/28/2017 | 3/17/2021 |  | 6/1/2018
PJM | AC2-145 | Beach Glen 4.8kV | 94-98 Ford | NJ | Morris | Withdrawn | JCPL | 0.2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/28/2017 | 3/17/2021 |  | 6/1/2018
PJM | AC2-146 | Modoc 138kV |  | IN | Randolph | Withdrawn | AEP | 50 | 19 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/28/2017 | 3/31/2017 | Customer Milestone Not Met | 11/30/2019
PJM | AC2-147 | Maryland |  | IL | Ogle | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/28/2017 | 2/18/2020 |  | 5/1/2019
PJM | AC2-148 | South Dixon |  | IL | Lee | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 3/28/2017 | 2/6/2018 |  | 5/1/2019
PJM | AC2-149 | Glidden |  | IL | DeKalb | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/28/2017 | 7/5/2018 |  | 5/1/2019
PJM | AC2-150 | Dixon |  | IL | Lee | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 3/28/2017 | 2/6/2018 |  | 5/1/2019
PJM | AC2-151 | Mazon |  | IL | Grundy | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/28/2017 | 5/30/2018 |  | 5/1/2019
PJM | AC2-152 | Pontiac Midpoint |  | IL | Livingston | Withdrawn | ComEd | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 3/28/2017 | 4/10/2018 |  | 5/1/2019
PJM | AC2-153 | Steward |  | IL | DeKalb | Withdrawn | ComEd | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 3/28/2017 | 4/10/2018 |  | 5/1/2019
PJM | AC2-154 | Davis Creek 138kV | Staley Solar | IL | Kankakee | Suspended | ComEd | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2017 |  |  | 6/28/2024
PJM | AC2-155 | North Franklin 138kV |  | WV | Pendleton | Withdrawn | APS | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/29/2017 | 8/16/2017 | Customer Initiated Withdrawal | 12/31/2019
PJM | AC2-156 | Sandwich 34.5kV |  | IL | DeKalb | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/29/2017 | 5/5/2021 |  | 3/31/2019
PJM | AC2-157 | Sullivan 345 kV | Trade Post Solar Energy Center | IN | Sullivan | Engineering and Procurement | AEP | 200 | 76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2017 |  |  | 6/30/2026
PJM | AC2-158 | Cashie-Earleys 230kV |  | NC | Bertie | Withdrawn | Dominion | 65 | 32.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/29/2017 | 11/2/2017 |  | 5/1/2019
PJM | AC2-159 | Jackson-Woodland 115kV |  | NC | Northhampton | Withdrawn | Dominion | 80 | 40 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/29/2017 | 11/2/2017 |  | 5/1/2019
PJM | AC2-160 | Centreville 12kV |  | MD | Queen Anne's | Withdrawn | DPL | 1.9 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/29/2017 | 9/8/2017 | Customer Initiated Withdrawal | 12/1/2017
PJM | AC2-161 | Smithfield 34.5kV | Solidago | VA | Isle of Wight | Withdrawn | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/29/2017 | 9/5/2018 |  | 12/31/2020
PJM | AC2-162 | Old Church 34.5kV | Sweetspire | VA | Hanover | Withdrawn | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/29/2017 | 9/10/2018 |  | 12/31/2020
PJM | AC2-163 | Harmony Village-Dunnsville 34.5kV |  | VA | Middlesex | Withdrawn | Dominion | 17.5 | 12.79 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2017 | 3/30/2017 | Customer Initiated Withdrawal | 6/3/2019
PJM | AC2-164 | Darby-Urbana 138kV |  | OH | Champaign | Withdrawn | Dayton | 0 | 14.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/29/2017 | 2/22/2018 |  | 12/15/2019
PJM | AC2-165 | Bremo-Powhatan 230kV | Cartersville Solar | VA | Powhatan | Engineering and Procurement | Dominion | 99.9 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2017 |  |  | 5/17/2026
PJM | AC2-166 | Waterman 34 kV |  | IL | DeKalb | Withdrawn | ComEd | 40 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/30/2017 | 9/25/2018 |  | 12/1/2019
PJM | AC2-167 | Boykins-Murphy 115kV |  | VA | Southampton | Withdrawn | Dominion | 50 | 19 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2017 | 6/20/2017 | Customer Initiated Withdrawal | 6/30/2019
PJM | AC2-168 | Clinton 23kV | Gaucho Solar | PA | Washington | In Service | DL | 11.7 | 4.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/30/2017 |  |  | 6/1/2023 | 6/29/2023
PJM | AC2-169 | Nortonville 12kV |  | NJ | Gloucester | Withdrawn | AEC | 4.14 | 2.07 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2017 | 5/1/2017 | Customer Initiated Withdrawal | 12/31/2017
PJM | AC2-170 | Quarryville | Keystone Solar | PA | Lancaster | Withdrawn | PPL | 0 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/30/2017 | 10/2/2023 |  | 11/1/2021
PJM | AC2-171 | Jeffersonville 69kV |  | OH | Ross | Withdrawn | Dayton | 29 | 11 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2017 | 8/23/2017 | Customer Initiated Withdrawal | 5/31/2019
PJM | AC2-172 | Big Sandy 1 138kV | Big Sandy #1 | KY | Lawrence | In Service | AEP | 17 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/30/2017 |  |  | 10/1/2018 | 5/30/2016
PJM | AC2-173 | Wempleton-Belvidere |  | IL | Winnebago | Withdrawn | ComEd | 90 | 60.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2017 | 10/13/2017 |  | 11/1/2018
PJM | AC2-174 | Double Tollgate 34.5kV | Double Tollgate Solar Project | VA | Clarke | Withdrawn | APS | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/1/2017 | 2/28/2024 |  | 3/31/2023
PJM | AC2-175 | Berkshire Solar 12 kV | Berkshire Solar | NJ | Morris | In Service | JCPL | 1.6 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2017 |  |  | 9/30/2021 | 11/6/2021
PJM | AC2-176 | Jay 138 kV | Bitter Ridge Wind Farm | IN | Jay | In Service | AEP | 130 | 16.9 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2017 |  |  | 10/31/2020 | 9/5/2020
PJM | AC2-177 | Desoto-Tanners Creek 345kV |  | IN | Henry | Withdrawn | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/31/2017 | 6/17/2021 |  | 12/31/2019
PJM | AC2-178 | Ortanna 138kV |  | MD | Frederick | Withdrawn | APS | 100 | 38 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2017 | 3/31/2017 | Customer Milestone Not Met | 5/31/2019
PJM | AC2-179 | Natrium 138kV |  | WV | Marshall | Withdrawn | AEP | 57 | 48.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 3/31/2017 | 7/12/2017 | Customer Initiated Withdrawal | 6/1/2019
PJM | AC2-180 | Babcock & Wilcox 69kV |  | VA | Campbell | Withdrawn | AEP | 12 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 3/31/2017 | 11/20/2019 |  | 10/1/2018
PJM | AC2-181 | Payne 69kV |  | IN | Randolph | Withdrawn | AEP | 49.9 | 18.96 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2017 | 3/31/2017 | Customer Milestone Not Met | 11/30/2019
PJM | AC2-182 | McConnelsburg-Texas Eastern |  | PA | Franklin | Withdrawn | PENELEC | 80 | 57.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2017 | 3/31/2017 | Customer Milestone Not Met | 6/30/2018
PJM | AC2-183 | Pepper 69kV |  | DE | Sussex | Withdrawn | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2017 | 5/1/2017 | Customer Initiated Withdrawal | 12/15/2018
PJM | AC2-184 | Cedar Creek 138kV I | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/1/2017 |  |  | 6/15/2025
PJM | AC2-185 | Cedar Creek 138kV II | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/1/2017 |  |  | 6/15/2025
PJM | AC2-186 | Harrington 25kV | Raceway Solar | DE | Kent | Under Construction | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2017 |  |  | 3/1/2025
PJM | AC2-187 | Harrington 69kV | Raceway Solar | DE | Kent | Under Construction | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2017 |  |  | 3/1/2025
PJM | AC2-188 | Harrington 69 kV | Raceway Solar | DE | Kent | Under Construction | DPL | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2017 |  |  | 3/1/2025
PJM | AC2-189 | Crisfield-Kings Creek 69kV |  | MD | Somerset | Withdrawn | DPL | 11.6 | 10.3 | Capacity | Generation Interconnection | Methane; Solar | Document Posted | Document Posted |  |  | 3/31/2017 | 4/17/2018 |  | 12/31/2018
PJM | AC2-190 | Sussex-Harbeson 69kV |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | Capacity | Generation Interconnection | Methane | Document Posted |  |  |  | 3/31/2017 | 9/15/2017 |  | 12/31/2018
PJM | AC2-191 | Sussex-Harbeson 69kV II |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | Capacity | Generation Interconnection | Methane | Document Posted |  |  |  | 3/31/2017 | 9/15/2017 |  | 9/28/2018
PJM | AC2-192 | Greene-Clark 138kV |  | OH | Fayette | Withdrawn | ATSI | 56 | 21 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2017 | 8/29/2017 | Customer Initiated Withdrawal | 5/31/2019
PJM | AC2-193 | Camden 26kV |  | NJ | Camden | Withdrawn | PSEG | 10 | 10 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2017 | 3/31/2017 | Customer Milestone Not Met | 12/31/2017
PJM | AC2-194 | WinFall 34.5kV |  | NC | Perquimans | Withdrawn | Dominion | 16.2 | 6.2 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2017 | 11/8/2017 |  | 12/22/2017
PJM | AC2-195 | Galion-Roberts South 138 kV | Marion County Solar Project | OH | Marion | Engineering and Procurement | ATSI | 99.96 | 62.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2017 |  |  | 12/31/2025
PJM | AC2-196 | Fentress 34.5kV | Centerville Pike Solar | VA | City of Chesapeake | Withdrawn | Dominion | 16.7 | 10 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2017 | 2/8/2021 |  | 12/15/2021
PJM | AD1-001 | Kilmer 480 v | Kilmer 480V | NJ | Union | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-002 | North Bergen I 480 v | North Bergen I 480V | NJ | Hudson | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-003 | North Bergen II 480 v | North Bergen II 480V | NJ | Bergen | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/1/2020
PJM | AD1-004 | Paramus 480 v | Paramus 480V | NJ | Bergen | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-005 | Jackson Rd 480 v | Jackson Road 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-006 | Secaucus 480 v |  | NJ | Hudson | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/3/2017 | 10/26/2017 |  | 12/31/2017
PJM | AD1-007 | Bergenfield 480 v | Bergenfield 480V | NJ | Bergen | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-008 | Sand Hills 480 v | Sand Hills 480V | NJ | Middlesex | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/21/2020
PJM | AD1-009 | Saddle Brook 480 v | Saddle Brook 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-010 | McLean 480 v | McLean 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-011 | Athenia 480 v | Atheina 480V | NJ | Passaic | Withdrawn | PSEG | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Withdrawn | 4/3/2017 | 6/6/2018 |  | 1/31/2020
PJM | AD1-012 | Cheesequake 12.5 kV |  | NJ | Middlesex | Withdrawn | JCPL | 0.21 | 0 | Energy | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 4/3/2017 | 6/1/2017 | Customer Milestone Not Met | 3/31/2018
PJM | AD1-013 | Twombly Road 138kV | Rochelle Solar | IL | Ogle | Engineering and Procurement | ComEd | 40 | 15.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/6/2017 |  |  | 4/1/2026
PJM | AD1-015 | Frazeysburg 138 kV | Muskingum Solar | OH | Muskingum | Withdrawn | AEP | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/21/2017 | 2/14/2022 |  | 12/31/2023
PJM | AD1-016 | Marengo | Marengo Solar, LLC | IL | McHenry | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/29/2017 | 8/26/2024 |  | 8/31/2026
PJM | AD1-017 | Smith Mountain-Bearskin 138 kV | Maplewood Solar | VA | Pittsylvania | In Service | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 5/11/2017 |  |  | 12/1/2022 | 9/2/2022
PJM | AD1-018 | Carlos Jct - Plaza 34 kV | Pigtoe Bobcat Solar | MD | Allegany | Withdrawn | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 5/12/2017 | 10/6/2022 |  | 1/1/2021
PJM | AD1-019 | Ontario 23 kV |  | NJ | Atlantic | Withdrawn | AEC | 7.6 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 5/24/2017 | 3/8/2022 |  | 6/3/2019
PJM | AD1-020 | Hunterstown-Lincoln 115 kV | Adams Solar LLC | PA | Adams | In Service | ME | 80 | 53.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/9/2017 |  |  | 2/25/2024 | 3/21/2024
PJM | AD1-022 | Cashie-Trowbridge 230 kV | Sumac Solar | NC | Bertie | Engineering and Procurement | Dominion | 80 | 51.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/19/2017 |  |  | 12/31/2026
PJM | AD1-023 | Cashie-Trowbridge 230 kV |  | NC | Bertie | Withdrawn | Dominion | 40 | 25.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/19/2017 | 4/21/2022 |  | 6/1/2019
PJM | AD1-024 | Davis Creek-Wilmington |  | IL | Kankakee | Withdrawn | ComEd | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 6/19/2017 | 3/1/2018 |  | 5/1/2019
PJM | AD1-025 | Hopewell-Surry 230 kV | Spring Grove Solar II | VA | Surry | Under Construction | Dominion | 150 | 94.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/28/2017 |  |  | 6/30/2025
PJM | AD1-026 | Shenango-Hoytdale 345 kV | Hickory Run Energy Station | PA | Lawrence | In Service | ATSI | 0 | 130 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 6/28/2017 |  |  | 3/30/2020 | 4/28/2020
PJM | AD1-027 | Camden 26 kV |  | NJ | Camden | Withdrawn | PSEG | 10 | 4.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/3/2017 | 8/9/2017 | Customer Milestone Not Met | 12/31/2017
PJM | AD1-028 | Home DepotNJ #957 - Old Bridge | Old Bridge Fuel Cell | NJ | Middlesex | Withdrawn | JCPL | 0.2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/11/2017 | 12/18/2018 |  | 3/31/2020
PJM | AD1-029 | Scotland Neck-South Justice 115 kV |  | NC | Halifax | Withdrawn | Dominion | 110 | 66.3 | Capacity | Generation Interconnection | Storage; Solar | Document Posted |  |  |  | 7/20/2017 | 3/6/2018 |  | 12/1/2019
PJM | AD1-030 | Camden 26 kV II |  | NJ | Burlington | Withdrawn | PSEG | 7 | 2.94 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/20/2017 | 8/9/2017 | Customer Milestone Not Met | 5/31/2018
PJM | AD1-031 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Suspended | ComEd | 70 | 26.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/24/2017 |  |  | 6/15/2027
PJM | AD1-033 | Fentress-Landstown 230 kV | Bedford Solar Center | VA | City of Chesapeake | In Service | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/26/2017 |  |  | 12/1/2021 | 11/23/2021
PJM | AD1-034 | Sapony 230 kV |  | VA | Sussex | Withdrawn | Dominion | 74.9 | 44.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/26/2017 | 3/16/2018 |  | 12/31/2020
PJM | AD1-035 | Darby-East Liberty 69 kV |  | OH | Union | Withdrawn | Dayton | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/27/2017 | 2/20/2018 |  | 10/1/2019
PJM | AD1-036 | Chatfield 138 kV |  | OH | Crawford | Withdrawn | AEP | 35 | 13.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/27/2017 | 9/15/2017 |  | 12/31/2020
PJM | AD1-037 | Martins Creek 230 kV | Lower Mount Bethel | PA | Northampton | In Service | PPL | 51.6 | 86.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 7/28/2017 |  |  | 9/29/2019 | 7/10/2019
PJM | AD1-038 | Oliver Solar |  | NJ | Burlington | Withdrawn | PSEG | 0.3 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/28/2017 | 8/25/2017 | Customer Milestone Not Met | 10/31/2019
PJM | AD1-039 | Kendall-Tazewell & Dresden-Mole Creek | Three Rivers Energy Center | IL | Grundy | Partially in Service - Under Construction | ComEd | 102.7 | 93 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 7/29/2017 |  |  | 2/28/2025 | 6/16/2023
PJM | AD1-040 | Mount Eagle 34.5 kV |  | VA | Albemarle | Withdrawn | Dominion | 11 | 4.18 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/31/2017 | 8/10/2017 | Customer Initiated Withdrawal | 4/30/2018
PJM | AD1-041 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | In Service | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/3/2017 |  |  | 6/28/2024 | 8/22/2024
PJM | AD1-042 | Stuarts Draft-Waynesboro 115 kV |  | VA | Augusta | Withdrawn | Dominion | 0 | 12.5 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 7/31/2017 | 4/10/2018 |  | 10/31/2018
PJM | AD1-043 | Makahoy 138 kV | Lone Oak Solar | IN | Madison | Suspended | AEP | 120 | 45.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/1/2017 |  |  | 7/1/2028
PJM | AD1-044 | Oak Grove 34.5 kV I | Oak Grove I | VA | Westmoreland | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2017 | 8/14/2020 |  | 6/30/2021
PJM | AD1-045 | Oak Grove 34.5 kV II | Oak Grove II | VA | Westmoreland | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2017 | 8/14/2020 |  | 6/30/2021
PJM | AD1-046 | Oak Grove 34.5 kV III | Oak Grove III | VA | Westmoreland | Withdrawn | Dominion | 11.2 | 6.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2017 | 8/14/2020 |  | 6/30/2021
PJM | AD1-047 | Brink 115 kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 7/31/2017 | 1/30/2020 |  | 12/1/2018
PJM | AD1-048 | Turner 34.5 kV | Turner I Solar | VA | Henrico | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/3/2017 | 9/5/2019 |  | 12/31/2022
PJM | AD1-049 | Culpeper 34.5 kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 6.3 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/3/2017 | 9/11/2018 |  | 12/1/2019
PJM | AD1-050 | Beechwood DP-Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 45 | 29.1 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 8/7/2017 | 10/15/2019 |  | 12/1/2019
PJM | AD1-051 | Sporn South 138 kV |  | WV | Mason | Withdrawn | AEP | 30 | 18.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 8/7/2017 | 6/4/2018 |  | 12/31/2018
PJM | AD1-052 | Freemont Energy Center | Freemont Energy Center | OH | Sandusky | In Service | ATSI | 38 | 26.3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/10/2017 |  |  | 10/1/2020 | 2/24/2021
PJM | AD1-053 | Plainsboro 13 kV | Plainsboro 13kV | NJ | Middlesex | Withdrawn | PSEG | 3 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/11/2017 | 3/6/2019 |  | 12/31/2018
PJM | AD1-054 | Bergen 13 kV | Bergen 13kV | NJ | Bergen | In Service | PSEG | 1.5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/11/2017 |  |  | 10/15/2019 | 12/31/2019
PJM | AD1-055 | Crystal Hill-Halifax 115 kV | Halifax County Solar | VA | Halifax | In Service | Dominion | 20 | 15.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/16/2017 |  |  | 12/29/2023 | 2/15/2024
PJM | AD1-056 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 60 | 38.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/14/2017 |  |  | 12/31/2026
PJM | AD1-057 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 33 | 21.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/14/2017 |  |  | 12/31/2026
PJM | AD1-058 | Halifax-Person 230 kV | Alton Post Office Solar | VA | Halifax | In Service | Dominion | 45.9 | 36.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/16/2017 |  |  | 12/31/2024 | 1/9/2025
PJM | AD1-059 | Lakewood 230 kV | Lakewood Cogeneration Plant | NJ | Ocean | In Service | JCPL | 0 | 14.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 8/17/2017 |  |  | 9/30/2019 | 5/7/2018
PJM | AD1-060 | Mercersburg-Milnor 34.5 kV | Upton Solar | PA | Franklin | In Service | APS | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/18/2017 |  |  | 9/1/2021 | 12/17/2020
PJM | AD1-061 | McConnelsburg-Mercersburg 34 kV |  | PA | Franklin | In Service | APS | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/18/2017 |  |  | 3/31/2022 | 5/6/2022
PJM | AD1-062 | Itasca 12.5 kV | 0 | IL | Du Page | Withdrawn | ComEd | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/18/2017 |  |  | 12/1/2018 | 9/5/2018
PJM | AD1-063 | Harmony Village 34.5 kV | Puller Solar | VA | Middlesex | In Service | Dominion | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/22/2017 |  |  | 12/1/2018 | 10/8/2018
PJM | AD1-064 | White Rock-Wayne 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/25/2017 | 9/19/2019 |  | 12/15/2019
PJM | AD1-065 | Eldred-Frackville 230kV |  | PA | Schuylkill | Withdrawn | PPL | 175.8 | 25.84 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 8/31/2017 | 10/15/2018 |  | 12/31/2020
PJM | AD1-066 | Crescent Ridge |  | IL | Bureau | Withdrawn | ComEd | 0 | 9.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 8/31/2017 | 7/1/2018 |  | 10/31/2019
PJM | AD1-067 | Mendota Hills | Mendota Hills Wind Farm | IL | Lee | In Service | ComEd | 5.725 | 1.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 8/31/2017 |  |  | 11/30/2018 | 10/19/2020
PJM | AD1-068 | Albright-Garrett 138 kV |  | WV | Preston | Withdrawn | APS | 80 | 11.76 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/31/2017 | 7/19/2021 |  | 12/15/2020
PJM | AD1-069 | Iron Bridge-Donegal 138 kV |  | PA | Fayette | Withdrawn | APS | 80 | 11.76 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 8/31/2017 | 4/14/2020 |  | 12/15/2020
PJM | AD1-070 | Fostoria Central 138 kV | South Branch Solar | OH | Hancock | Suspended | AEP | 205 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2017 |  |  | 12/31/2025
PJM | AD1-071 | Levittown 13kV | Levittown 13kV | NJ | Burlington | Withdrawn | PSEG | 2.6 | 0.99 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2017 | 11/8/2018 |  | 3/31/2019
PJM | AD1-072 | Biers Run-Circleville 138 kV | Yellowbud Solar | OH | Ross | In Service | AEP | 20 | 13.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2017 |  |  | 12/15/2022 | 12/21/2022
PJM | AD1-073 | Buckskin 69 kV | Ross County Solar | OH | Ross | Partially in Service - Under Construction | AEP | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/2/2017 |  |  | 6/1/2024
PJM | AD1-074 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 300 | 198.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/1/2017 |  |  | 3/31/2028
PJM | AD1-075 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 75 | 49.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2017 |  |  | 3/31/2028
PJM | AD1-076 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 109 | 72.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2017 |  |  | 3/31/2028
PJM | AD1-077 | Standardsville-Pratts 34.5 kV |  | VA | Greene | Withdrawn | APS | 17 | 10.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/1/2017 | 4/25/2018 |  | 1/31/2019
PJM | AD1-078 | Paytes 115 kV |  | VA | Orange | Withdrawn | Dominion | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/1/2017 | 6/14/2019 |  | 1/31/2019
PJM | AD1-080 | Endless Caverns 34.5 kV |  | VA | Rockingham | Withdrawn | Dominion | 20 | 12.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/1/2017 | 4/24/2018 |  | 1/31/2019
PJM | AD1-081 | Beatty-London 138 kV | Big Plain 2 | OH | Madison | In Service | ATSI | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/6/2017 |  |  | 8/31/2023 | 7/25/2023
PJM | AD1-082 | Bakers Pond-Ivor 115kV | Waverly Solar | VA | Sussex | In Service | Dominion | 68 | 43.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/8/2017 |  |  | 2/16/2024 | 3/14/2024
PJM | AD1-083 | Page-Bethel 138 kV | Cape Solar | VA | Page | Withdrawn | APS | 100 | 60.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/11/2017 | 7/21/2023 |  | 12/31/2023
PJM | AD1-084 | Cushaw 115 kV | Cushaw Hydropower Station | VA | Bedford | In Service | Dominion | 5.5 | 5.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 9/12/2017 |  |  | 1/15/2019 | 11/12/2018
PJM | AD1-085 | North Shenandoah-Stanley 34.5 kV | North Shenandoah-Stanley 34.5kV | VA | Page | Withdrawn | APS | 20 | 12.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 9/15/2017 | 8/5/2024 |  | 9/8/2026
PJM | AD1-087 | Clover-Sedge Hill 230 kV | Foxhound Solar | VA | Halifax | In Service | Dominion | 64.2 | 43.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/16/2017 |  |  | 5/31/2024 | 4/24/2024
PJM | AD1-088 | Briery-Clover 230 kV | Seven Bridges Solar | VA | Mecklenburg | Suspended | Dominion | 80 | 54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/15/2017 |  |  | 12/31/2026
PJM | AD1-089 | Birdneck 34.5 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 4 | 1.3 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 9/15/2017 | 11/1/2017 |  | 12/1/2020
PJM | AD1-090 | Muskingum River 345 kV Phase I |  | OH | Washington | Withdrawn | AEP | 1260 | 1180 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/18/2017 | 8/30/2019 |  | 1/1/2022
PJM | AD1-091 | Muskingum River 345 kV Phase II |  | OH | Washington | Withdrawn | AEP | 630 | 590 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 9/18/2017 | 11/7/2017 |  | 1/1/2022
PJM | AD1-095 | North Salisbury 25 kV |  | MD | Wicomico | Withdrawn | DPL | 2 | 2 | Capacity | Generation Interconnection | Methane | Document Posted |  |  |  | 9/19/2017 | 2/6/2018 |  | 6/1/2019
PJM | AD1-096 | Stillman Valley 34 kV |  | IL | Ogle | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/19/2017 | 7/22/2020 |  | 12/15/2018
PJM | AD1-097 | Linwood 230 kV II | Phillips Island CT1, CT2, CT3, and ST4 | PA | Delaware | In Service | PECO | 67 | 34.8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/20/2017 |  |  | 7/30/2021 | 6/9/2020
PJM | AD1-098 | Dixon - McGirr 138 kV |  | IL | Lee | Withdrawn | ComEd | 100 | 57.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/21/2017 | 3/20/2023 |  | 12/1/2020
PJM | AD1-099 | South Bend 500 kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 0 | 70 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 9/21/2017 |  |  | 9/1/2019 | 9/20/2018
PJM | AD1-100 | Loretto-Wilton 345 kV & Braidwood-Davis Creek 345 kV |  | IL | Ford | Under Construction | ComEd | 850 | 150 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/22/2017 |  |  | 11/30/2026
PJM | AD1-101 | Continental 69 kV | Blue Harvest Solar Park | OH | Putnam | In Service | AEP | 49.9 | 18.96 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/21/2017 |  |  | 6/30/2023 | 11/22/2023
PJM | AD1-102 | Wurno-Claytor Lake 138 KV |  | VA | Pulaski | Withdrawn | AEP | 180.01 | 23.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 9/21/2017 | 5/17/2023 |  | 12/18/2020
PJM | AD1-103 | Beaver-Davis Besse 345 kV II |  | OH | Huron | Withdrawn | ATSI | 500.4 | 65.052 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/22/2017 | 7/13/2022 |  | 12/18/2020
PJM | AD1-104 | Marysville-Sorenson 765 kV II |  | OH | Van Wert | Withdrawn | AEP | 403.2 | 52.42 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 9/22/2017 | 3/27/2020 |  | 12/17/2021
PJM | AD1-105 | Kings Dominion DP 115 kV | Sweet Sue Solar | VA | King William | Under Construction | Dominion | 74 | 44.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/23/2017 |  |  | 12/31/2026
PJM | AD1-106 | North Waldo-Wild Creek 138 kV | Chestnut Solar | OH | Marion | Suspended | AEP | 60 | 22.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/23/2017 |  |  | 12/31/2026
PJM | AD1-107 | McGuire Battery Storage |  | NJ | Burlington | Withdrawn | JCPL | 1.25 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/22/2017 | 10/2/2017 |  | 8/1/2018
PJM | AD1-108 | Grover 34 kV | Beaver Dam Generating Station | PA | Bradford | In Service | PENELEC | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2017 |  |  | 9/17/2018 | 7/16/2018
PJM | AD1-109 | Canton 34.5 kV | Glory Barn Road Generating Facility Alpaca | PA | Bradford | In Service | PENELEC | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2017 |  |  | 7/9/2018 | 5/10/2018
PJM | AD1-110 | North Meshoppen 34.5 kV | Roundtop Energy Projects | PA | Susquehanna | In Service | PENELEC | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2017 |  |  | 8/9/2018 | 6/22/2018
PJM | AD1-111 | Woolrich 12.47 kV |  | PA | Clinton | Withdrawn | PPL | 4.125 | 4.125 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 9/25/2017 | 1/3/2018 |  | 12/31/2018
PJM | AD1-112 | Davis Creek 138 kV |  | IL | Kankakee | Withdrawn | ComEd | 200 | 34 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 9/25/2017 | 10/2/2017 |  | 9/30/2020
PJM | AD1-113 | Raritan River 230 kV | Woodbridge Energy Center | NJ | Middlesex | Withdrawn | JCPL | 35 | 75 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2017 | 2/16/2022 |  | 6/1/2021
PJM | AD1-114 | Kelson Ridge 230kV | CPV Maryland | MD | Charles | In Service | PEPCO | 75 | 75 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 9/26/2017 |  |  | 5/31/2021 | 3/28/2019
PJM | AD1-115 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 50 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/27/2017 |  |  | 12/15/2025
PJM | AD1-116 | Nevada 345 kV |  | IL | Lasalle | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 9/26/2017 | 9/21/2022 |  | 12/31/2020
PJM | AD1-117 | Maryland 138 kV |  | IL | Ogle | Withdrawn | ComEd | 78 | 46.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/26/2017 | 12/11/2018 |  | 7/1/2020
PJM | AD1-118 | Lemoyne | Troy Energy | OH | Wood | In Service | ATSI | 60 | 60 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/27/2017 |  |  | 8/1/2022 | 8/17/2022
PJM | AD1-119 | Payne 69 kV | Timber Road Solar Park | OH | Paulding | In Service | AEP | 49.9 | 18.96 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2017 |  |  | 11/30/2023 | 9/12/2024
PJM | AD1-123 | Welco 34.5 kV |  | VA | Halifax | Withdrawn | Dominion | 10 | 6.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/28/2017 | 6/6/2018 |  | 12/31/2018
PJM | AD1-124 | Lynbrook 12 kV |  | VA | Campbell | Withdrawn | AEP | 15 | 5.7 | Capacity | Generation Interconnection | Solar | Withdrawn | Withdrawn |  |  | 9/28/2017 | 9/10/2019 |  | 12/31/2019
PJM | AD1-125 | Baker 138 kV | Short Mountain Wind Energy | WV | Hardy | Suspended | APS | 80 | 11.76 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2017 |  |  | 12/31/2024
PJM | AD1-126 | W. DeKalb-Waterman |  | IL | DeKalb | Withdrawn | ComEd | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2017 | 7/5/2018 |  | 12/31/2020
PJM | AD1-127 | Cambria Slope 115 kV |  | PA | Cambria | Withdrawn | PENELEC | 235 | 235 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 9/28/2017 | 5/8/2018 |  | 9/1/2020
PJM | AD1-128 | Modoc-Delaware 138 kV | Riverstart Solar Park IV | IN | Randolph | Engineering and Procurement | AEP | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2017 |  |  | 12/31/2025
PJM | AD1-129 | Belvidere 34 kV | Cherry Valley Solar Project, LLC | IL | Boone | Withdrawn | ComEd | 12.5 | 7.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2017 | 8/26/2024 |  | 9/30/2026
PJM | AD1-130 | Hardin Switch 345 kV | Hardin Energy Center – Phase 2 | OH | Hardin | In Service | AEP | 150 | 101.47 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/2/2017 |  |  | 12/31/2024 | 12/3/2024
PJM | AD1-131 | Sedge Hill-Person 230 kV | Powells Creek Solar | VA | Halifax | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2017 |  |  | 11/1/2023 | 8/23/2023
PJM | AD1-132 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 150 | 57 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/29/2017 | 10/2/2017 |  | 12/15/2019
PJM | AD1-133 | Pontiac MidPoint-Dresden |  | IL | Grundy | Withdrawn | ComEd | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2017 | 5/31/2023 |  | 12/31/2019
PJM | AD1-134 | JK Smith 138 kV |  | KY | Unknown | Withdrawn | EKPC | 73 | 72.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 9/29/2017 | 4/22/2019 |  | 7/1/2020
PJM | AD1-135 | Clinton 23 kV II | Gaucho Solar | PA | Washington | In Service | DL | 8.3 | 3.15 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/29/2017 |  |  | 6/1/2023 | 6/29/2023
PJM | AD1-136 | South Bethel-Brown 69 kV | Nestlewood Solar | OH | Clermont | In Service | DEOK | 10 | 5.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2017 |  |  | 3/31/2024 | 12/27/2023
PJM | AD1-137 | Dequine 345 kV |  | IN | Benton | Withdrawn | AEP | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 9/29/2017 | 1/16/2020 |  | 12/18/2020
PJM | AD1-138 | Valley 138 kV |  | MI | Van Buren | Withdrawn | AEP | 100 | 65.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/29/2017 | 10/2/2017 |  | 12/1/2020
PJM | AD1-139 | Mullin-Grant Tap 138 kV |  | IN | Madison | Withdrawn | AEP | 99.9968 | 68.9978 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/29/2017 | 10/2/2017 |  | 12/1/2020
PJM | AD1-140 | Greene-Clark 138 kV | Kingwood Solar | OH | Greene | Suspended | ATSI | 175 | 95.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2017 |  |  | 9/30/2024
PJM | AD1-141 | S. Lucasville-Wakefield 138 kV |  | OH | Scioto | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/29/2017 | 3/27/2020 |  | 12/1/2019
PJM | AD1-142 | Milan 34.5 kV | Milan Energy | PA | Bradford | In Service | PENELEC | 1.1 | 1.1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/29/2017 |  |  | 7/9/2018 | 4/24/2018
PJM | AD1-143 | Hauto-Siegfried 69 kV | Broad Mountain | PA | Carbon | Withdrawn | PPL | 90 | 11.84 | Capacity | Generation Interconnection | Wind; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2017 | 3/31/2023 |  | 6/30/2021
PJM | AD1-144 | Kings Fork 34.5 kV | TWE Myrtle Solar Project | VA | City of Suffolk | In Service | Dominion | 15 | 9.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2017 |  |  | 6/1/2020 | 6/29/2020
PJM | AD1-145 | Laurel-Dupont Seaford 69 kV |  | DE | Sussex | Withdrawn | DPL | 9.6 | 9.6 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted |  |  | 9/30/2017 | 11/14/2018 |  | 7/31/2019
PJM | AD1-146 | Millsboro 25 kV |  | DE | Sussex | Withdrawn | DPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2017 | 10/16/2018 |  | 6/30/2019
PJM | AD1-147 | Martinsville-Wilmington 69 kV |  | OH | Clinton | Withdrawn | Dayton | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2017 | 10/3/2017 |  | 9/1/2020
PJM | AD1-148 | Brokaw-Lanesville | HillTopper Wind Farm | IL | Logan | In Service | ComEd | 0 | 36.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 10/1/2017 |  |  | 9/1/2022 | 9/1/2022
PJM | AD1-149 | Carbondale 69 kV |  | WV | Kanawha | Withdrawn | AEP | 19.9 | 8.33 | Capacity | Generation Interconnection | Storage; Solar | Document Posted |  |  |  | 9/30/2017 | 6/18/2018 |  | 6/30/2019
PJM | AD1-150 | Kankakee 34.5 kV |  | IL | Kankakee | Withdrawn | ComEd | 19.9 | 3.98 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/30/2017 | 10/5/2017 |  | 7/31/2019
PJM | AD1-151 | Hopewell-Surry 230 kV | Wild Indigo Solar | VA | Surry | Suspended | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2017 |  |  | 9/1/2026
PJM | AD1-152 | Clover-Sedge Hill 230 kV | Piney Creek Solar | VA | Halifax | In Service | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2017 |  |  | 12/1/2023 | 8/15/2023
PJM | AD1-153 | Walker Mill 12 kV |  | MD | Prince George's | Withdrawn | PEPCO | 2.76 | 1.0488 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2017 | 12/24/2018 |  | 9/1/2018
PJM | AD1-154 | Timblin 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 9/30/2017 | 2/4/2021 |  | 6/1/2020
PJM | AD1-155 | Meadow Brook-Strasburg 138 kV | Foxglove Solar | VA | Frederick | In Service | APS | 75 | 37.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/2/2017 |  |  | 6/30/2024 | 10/19/2024
PJM | AD1-156 | Poe 34.5 kV | Rives Road Solar | VA | Prince George | Withdrawn | Dominion | 19.7 | 11.82 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2017 | 1/14/2020 |  | 12/31/2020
PJM | AD1-157 | South Creek 34.5 kV | Spout Springs Solar | VA | Appomattox | Withdrawn | Dominion | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2017 | 1/26/2021 |  | 12/15/2021
PJM | AD1-158 | Old Chapel-Millville 138kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2017 | 10/6/2017 |  | 6/30/2019
PJM | AD1-159 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2017 | 10/6/2017 |  | 6/30/2019
PJM | AD1-160 | Pamplin 34.5 kV | Pamplin Solar | VA | Appomattox | Withdrawn | Dominion | 15.7 | 6.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2017 | 1/14/2020 |  | 12/31/2020
PJM | AD1-161 | Stonewall-Long Mountain 69 kV |  | VA | Appomattox | Withdrawn | AEP | 55 | 30.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2017 | 5/31/2023 |  | 12/31/2020
PJM | AD2-001 | Grangston 138 kV | Big Sandy Peaker Plant | WV | Wayne | In Service | AEP | 18 | 18 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/2/2017 |  |  | 12/31/2020 | 10/2/2020
PJM | AD2-002 | Franklin-Emerald 25 kV | Evergreene Energy | PA | Greene | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/17/2017 | 12/30/2020 |  | 12/31/2022
PJM | AD2-004 | Steel-Vienna 230 kV |  | MD | Caroline | Withdrawn | DPL | 600 | 600 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 10/26/2017 | 9/19/2018 |  | 12/1/2022
PJM | AD2-005 | Nottingham 138kV | Harrison Power Plant | OH | Harrison | Withdrawn | AEP | 35 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/24/2017 | 7/21/2022 |  | 6/11/2024
PJM | AD2-006 | Gilbert-Morris Park 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 7.5 | 3.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/2/2017 | 11/29/2017 |  | 11/30/2018
PJM | AD2-007 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 7.6 | 4.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 11/4/2017 | 4/26/2023 |  | 11/1/2019
PJM | AD2-008 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 52.1 | 16.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 11/4/2017 | 4/26/2023 |  | 9/30/2019
PJM | AD2-009 | McConnellsburg 138 kV | Great Cover Solar LLC | PA | Fulton | In Service | APS | 70 | 48.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/7/2017 |  |  | 3/31/2024 | 4/16/2024
PJM | AD2-010 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 11/7/2017 | 11/9/2018 |  | 6/1/2019
PJM | AD2-011 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 11/7/2017 | 11/9/2018 |  | 6/1/2019
PJM | AD2-012 | Hillsboro 138 kV |  | OH | Highland | Withdrawn | AEP | 49 | 29.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 11/7/2017 | 11/9/2018 |  | 6/1/2019
PJM | AD2-013 | Earleys 115 kV |  | NC | Hertford | Withdrawn | Dominion | 74.9 | 52.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/3/2017 | 11/30/2017 |  | 12/31/2020
PJM | AD2-014 | Steubenville 69 kV | Steubenville Solar | OH | Jefferson | Suspended | AEP | 49.5 | 20.79 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/10/2017 |  |  | 12/31/2027
PJM | AD2-015 | Dequine 345 kV |  | IN | Benton | Withdrawn | AEP | 500 | 65 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 11/13/2017 | 1/16/2018 |  | 12/18/2020
PJM | AD2-016 | Biers Run-Circleville 138 kV | Yellowbud Solar | OH | Ross | In Service | AEP | 127 | 62.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/16/2017 |  |  | 12/15/2022 | 12/21/2022
PJM | AD2-017 | Buckskin 69 kV |  | OH | Ross | Withdrawn | AEP | 100 | 65.59 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/15/2017 | 1/18/2018 |  | 12/31/2020
PJM | AD2-020 | Valley 138 kV | Southwest Michigan Energy Center | MI | Van Buren | Suspended | AEP | 100 | 61.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/1/2017 |  |  | 4/30/2026
PJM | AD2-021 | Elko 34.5 kV | Briel Farm Solar | VA | Henrico | In Service | Dominion | 1.2 | 1.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 11/29/2017 |  |  | 12/30/2020 | 12/21/2020
PJM | AD2-022 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Suspended | AEP | 96 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/2/2017 |  |  | 2/28/2025
PJM | AD2-023 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Suspended | AEP | 54 | 95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/2/2017 |  |  | 2/28/2025
PJM | AD2-024 | Marengo 34 kV |  | IL | McHenry | Withdrawn | ComEd | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 12/1/2017 | 9/17/2018 |  | 6/1/2019
PJM | AD2-025 | Hillsborough 13 kV | Hillsborough Storage | NJ | Somerset | Withdrawn | PSEG | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 12/5/2017 | 12/19/2023 |  | 12/31/2023
PJM | AD2-026 | East Flemington-Frenchtown 34.5 kV II | Quakertown Solar Farm | NJ | Hunterdon | In Service | JCPL | 0 | 4.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 12/6/2017 |  |  | 12/31/2020 | 5/3/2019
PJM | AD2-027 | Camden Switch 26 kV | Taylors Lane Solar | NJ | Burlington | In Service | PSEG | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 12/7/2017 |  |  | 2/15/2019 | 3/22/2019
PJM | AD2-028 | McConnellsburg-Texas Eastern |  | PA | Franklin | Withdrawn | APS | 150 | 76.3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 12/12/2017 | 8/20/2018 |  | 6/30/2019
PJM | AD2-029 | Dorchester County 12kV |  | MD | Dorchester | Withdrawn | DPL | 19.5 | 7.95 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 12/13/2017 | 9/20/2018 |  | 12/31/2019
PJM | AD2-030 | Wan 34.5 kV | Gloucester Solar | VA | Gloucester | In Service | Dominion | 19.8 | 13.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 12/13/2017 |  |  | 5/21/2019 | 3/22/2019
PJM | AD2-031 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | Under Construction | Dayton | 49.9 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/16/2017 |  |  | 12/31/2024
PJM | AD2-032 | Morrisville 230 kV |  | VA | Accomack | Withdrawn | Dominion | 150 | 83.8495 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/15/2017 | 1/5/2018 |  | 12/31/2020
PJM | AD2-033 | Chase City-Lunenburg 115 kV | Red Brick Solar | VA | Lunenburg | Suspended | Dominion | 130 | 78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/23/2017 |  |  | 2/28/2025
PJM | AD2-035 | Ontelaunee 230 kV | Ontelaunee Power Generating Plant | PA | Berks | In Service | ME | 38.9 | 14 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 1/12/2018 |  |  | 12/1/2019 | 12/1/2019
PJM | AD2-036 | Jacksonville-Renaker 138kV IV |  | KY | Harrison | Withdrawn | EKPC | 60 | 40 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/16/2018 | 8/19/2019 |  | 6/1/2020
PJM | AD2-037 | Gilbert-Morris Park 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 7.5 | 3.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/18/2018 |  |  | 6/30/2019
PJM | AD2-038 | Powerton-Nevada 345 kV | Osagrove Flats Wind | IL | Lasalle | Under Construction | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/22/2018 |  |  | 10/30/2026
PJM | AD2-039 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/20/2018 |  |  | 12/31/2023
PJM | AD2-040 | Showalter 34.5 kV |  | MD | Washington | Withdrawn | APS | 0 | 4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 1/23/2018 | 8/20/2018 |  | 12/31/2018
PJM | AD2-041 | Normandy |  | IL | Whiteside | Withdrawn | ComEd | 17 | 11.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/24/2018 | 2/20/2018 |  | 12/31/2019
PJM | AD2-042 | Camden Switch 26 kV II | Pennsauken Solar II | NJ | Camden | In Service | PSEG | 13.2 | 5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 1/29/2018 |  |  | 9/10/2019 | 10/4/2019
PJM | AD2-043 | Crystal Hill 115 kV |  | VA | Halifax | Withdrawn | Dominion | 65.5 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/29/2018 | 12/20/2019 |  | 1/31/2019
PJM | AD2-044 | Northern Neck 34.5 kV | Gardy's Mill Solar | VA | Westmoreland | In Service | Dominion | 3.2 | 1.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 1/29/2018 |  |  | 12/30/2020 | 12/21/2020
PJM | AD2-045 | Price Solar |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 12.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/29/2018 | 3/29/2019 |  | 10/1/2019
PJM | AD2-046 | Boydton DP-Kerr Dam 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 80 | 54.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 1/31/2018 | 3/15/2023 |  | 6/1/2021
PJM | AD2-047 | Davis Creek 138 kV | Lower Crossing Wind | IL | Kankakee | Suspended | ComEd | 200 | 34 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2018 |  |  | 11/30/2026
PJM | AD2-048 | Cynthia-Headquarters 69 kV | Blue Moon Solar | KY | Harrison | Under Construction | EKPC | 70 | 46.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/1/2018 |  |  | 6/30/2026
PJM | AD2-049 | Newport News 23kV | Newport News Battery Storage | VA | City of Newport News | Withdrawn | Dominion | 10 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2018 | 10/21/2019 |  | 4/30/2021
PJM | AD2-050 | Buxmont 69kV |  | PA | Bucks | Withdrawn | PPL | 200 | 200 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/31/2018 | 3/2/2018 |  | 12/31/2019
PJM | AD2-051 | Earleys – Northampton 230kV |  | NC | Hertford | Withdrawn | Dominion | 74.9 | 52.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2018 | 8/30/2022 |  | 12/31/2020
PJM | AD2-052 | Laurel Lake Solar |  | NJ | Salem | Withdrawn | AEC | 10 | 6.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2018 | 5/1/2019 |  | 6/30/2019
PJM | AD2-055 | Moshannon-East Towanda 230 kV | Renovo Energy Center | PA | Clinton | Withdrawn | PENELEC | 44 | 35 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 2/9/2018 | 4/20/2023 |  | 6/30/2025
PJM | AD2-056 | Charles City |  | VA | Henrico | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/13/2018 | 3/7/2018 |  | 12/31/2020
PJM | AD2-057 | Highland-Hanna 345kV |  | OH | Trumbull | Withdrawn | ATSI | 940 | 850 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 2/20/2018 | 9/26/2018 |  | 10/16/2020
PJM | AD2-058 | St. Barnabas 13 kV | Spectrum Solar | MD | Prince George's | In Service | PEPCO | 5.6 | 2.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 2/21/2018 |  |  | 6/3/2022 | 1/2/2024
PJM | AD2-059 | Chapel Street 138 kV | UD Motor Pool | DE | New Castle | Withdrawn | DPL | 0.77 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 2/21/2018 | 9/22/2023 |  | 11/1/2022
PJM | AD2-060 | Davis Creek 138kV | Staley Solar | IL | Kankakee | Suspended | ComEd | 20 | 20 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/21/2018 |  |  | 6/28/2024
PJM | AD2-061 | Spring Run 23 kV |  | PA | Adams | Withdrawn | PENELEC | 7.4 | 4.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/23/2018 | 4/25/2018 |  | 6/1/2020
PJM | AD2-062 | Roxbury-Greene 138 kV | Beaver Creek Solar | PA | Franklin | Suspended | PENELEC | 80.3 | 53.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/24/2018 |  |  | 12/3/2024
PJM | AD2-063 | Central-Chase City 115kV |  | VA | Charlotte | Withdrawn | Dominion | 149.5 | 89.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/26/2018 | 5/24/2023 |  | 3/31/2021
PJM | AD2-064 | Tansboro 12kV |  | NJ | Camden | Withdrawn | AEC | 1.26 | 0.53 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/27/2018 | 6/16/2020 |  | 12/1/2019
PJM | AD2-065 | Atco 12 kV | Kettle Run | NJ | Burlington | In Service | AEC | 2.57 | 1.08 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 2/27/2018 |  |  | 5/20/2022 | 3/24/2023
PJM | AD2-066 | Mazon-Crescent Ridge 138 kV |  | IL | Grundy | Engineering and Procurement | ComEd | 116 | 69.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/1/2018 |  |  | 5/31/2026
PJM | AD2-067 | Centerburg 138kV | Harvey Solar I | OH | Licking | Suspended | AEP | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/2/2018 |  |  | 4/1/2029
PJM | AD2-068 | Everetts-Greenville 230kV |  | NC | Pitt | Withdrawn | Dominion | 50 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/28/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-069 | Cox's Corner 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 3 | 2.01 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/28/2018 | 6/21/2019 |  | 9/30/2019
PJM | AD2-070 | Gilbert-Morris Park 34.5kV | Milford Solar Farm | NJ | Hunterdon | In Service | JCPL | 7.5 | 3.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 3/12/2018 |  |  | 6/1/2020 | 9/18/2019
PJM | AD2-071 | Strawton-Deer Creek 138 kV | Madison County Solar | IN | Madison | Suspended | AEP | 100 | 67 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/15/2018 |  |  | 9/30/2025
PJM | AD2-072 | Van Arsdell-Mercer Industrial 69kV | Mercer County Solar Project | KY | Mercer | Withdrawn | EKPC | 95 | 63.75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/14/2018 | 11/18/2024 |  | 6/30/2023
PJM | AD2-073 | Sanders DP 230 kV | Woodbine Road Solar | VA | Westmoreland | In Service | Dominion | 19.92 | 13.32 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 3/14/2018 |  |  | 12/1/2021 | 9/2/2021
PJM | AD2-074 | Garner DP-Lancaster 115 kV | Waller Solar I | VA | Lancaster | Suspended | Dominion | 86 | 32.68 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/15/2018 |  |  | 5/31/2024
PJM | AD2-075 | Segreto 345kV | Covert Generating Facility | MI | Van Buren | Withdrawn | AEP | 285 | 145 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn | Document Posted | 3/15/2018 |  |  | 8/31/2023
PJM | AD2-076 | Carville 138 kV | Concho Solar I | MD | Queen Anne's | Suspended | DPL | 49 | 18.62 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/15/2018 |  |  | 6/3/2027
PJM | AD2-077 | Buxmont 69 kV | Energy Mountain | PA | Bucks | Suspended | PPL | 150 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/16/2018 |  |  | 7/31/2029
PJM | AD2-078 | N. Haverhill 69kV |  | OH | Scioto | Withdrawn | AEP | 20 | 40 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted |  |  | 3/15/2018 | 10/15/2020 |  | 9/1/2020
PJM | AD2-079 | Capitol Ave 34.5kV | St. Joseph County, Indiana | IN | St. Joseph | In Service | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/19/2018 |  |  | 3/31/2021 | 3/16/2021
PJM | AD2-081 | Banister 34.5kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 13.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/20/2018 | 9/13/2018 |  | 9/30/2019
PJM | AD2-082 | Pamplin 34.5kV |  | VA | Prince Edward | Withdrawn | Dominion | 15 | 10.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/20/2018 | 4/5/2019 |  | 9/30/2019
PJM | AD2-085 | Myrtle-Windsor DP 115kV | Knoxville Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 51 | 19.38 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2018 |  |  | 12/1/2027
PJM | AD2-086 | Hardin Switch 345 kV | Hardin Energy Center – Phase 3 | OH | Hardin | Partially in Service - Under Construction | AEP | 230 | 138 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2018 |  |  | 12/31/2025
PJM | AD2-087 | Randolf 138kV |  | OH | Darke | Withdrawn | AEP | 200 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 3/20/2018 | 12/9/2019 |  | 12/31/2020
PJM | AD2-088 | Laurel 69kV |  | DE | Sussex | Withdrawn | DPL | 30 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/20/2018 | 2/6/2020 |  | 12/31/2020
PJM | AD2-089 | Anaconda-Tar River 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/20/2018 | 12/9/2019 |  | 12/31/2020
PJM | AD2-090 | Handsom - Southampton 115kV |  | VA | Southampton | Withdrawn | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/20/2018 | 1/30/2020 |  | 12/31/2020
PJM | AD2-091 | Hardin Tap 345kV | Hardin Energy Center – Storage I | OH | Hardin | Suspended | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/20/2018 |  |  | 12/31/2025
PJM | AD2-092 | Marysville 345kV | Cadence Solar II Energy Center | OH | Union | Under Construction | AEP | 120 | 72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2018 |  |  | 3/20/2026
PJM | AD2-093 | Marysville 345kV | Cadence Solar Energy Center | OH | Union | Under Construction | AEP | 120 | 72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2018 |  |  | 3/20/2026
PJM | AD2-094 | Pantego-Five Points 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 16 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/20/2018 | 4/2/2018 |  | 12/31/2020
PJM | AD2-095 | Todd 69 kV |  | MD | Dorchester | Withdrawn | DPL | 20 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/20/2018 | 4/2/2018 |  | 12/31/2021
PJM | AD2-096 | Marysville 345kV | Cadence Energy Storage | OH | Union | Suspended | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2018 |  |  | 3/20/2026
PJM | AD2-097 | Spruance NUG 230kV | Spruance Operating Services LLC | VA | Henrico | In Service | Dominion | 66 | 11 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/21/2018 |  |  | 5/1/2019 | 10/1/2019
PJM | AD2-100 | Kincaid-Pana 345 kV | Broomstick Solar Energy Centergy Center | IL | Christian | Engineering and Procurement | ComEd | 210 | 126 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/23/2018 |  |  | 12/7/2028
PJM | AD2-101 | Bloom-Davis Creek |  | IL | Will | Withdrawn | ComEd | 200 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/22/2018 | 5/1/2019 |  | 12/31/2021
PJM | AD2-102 | Wempletown 345 kV |  | IL | Winnebago | Withdrawn | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/22/2018 | 4/5/2023 |  | 12/31/2021
PJM | AD2-103 | Crane CT 1 115kV |  | MD | Baltimore County | Withdrawn | BGE | 14 | 14 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Document Posted | Withdrawn | 3/22/2018 | 10/27/2021 |  | 10/31/2019
PJM | AD2-104 | Crane CT 2-3-4 115kV |  | MD | Baltimore County | Withdrawn | BGE | 144.6 | 144.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Withdrawn | 3/22/2018 | 10/27/2021 |  | 10/31/2019
PJM | AD2-105 | Leslie-Stinnett 161KV |  | KY | Leslie | Withdrawn | AEP | 100 | 40.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/22/2018 | 1/30/2020 |  | 12/31/2021
PJM | AD2-106 | Bulan 69kV |  | KY | Perry | Withdrawn | AEP | 80 | 33.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/22/2018 | 1/30/2020 |  | 12/31/2021
PJM | AD2-107 | Chavies-Bonnyman 69kV |  | KY | Perry | Withdrawn | AEP | 55 | 23.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/22/2018 | 4/16/2020 |  | 12/31/2021
PJM | AD2-108 | Springdale CT II 138kV | Springdale | PA | Allegheny | In Service | APS | 0 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/22/2018 |  |  | 6/1/2022 | 7/10/2019
PJM | AD2-109 | Gans 138kV |  | PA | Fayette | Withdrawn | APS | 4 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/22/2018 | 7/12/2019 |  | 5/31/2022
PJM | AD2-110 | Guilford 138kV | Chambersburg Energy, LLC | PA | Franklin | In Service | APS | 12 | 12 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/22/2018 |  |  | 9/30/2022 | 9/14/2020
PJM | AD2-111 | Hunlock 69 kV |  | PA | Luzerne | Withdrawn | AEP | 6 | 8 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 3/22/2018 | 3/28/2018 |  | 5/31/2022
PJM | AD2-112 | Springdale CC II 138kV | Springdale | PA | Allegheny | In Service | APS | 20 | 50.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/22/2018 |  |  | 6/1/2022 | 11/21/2023
PJM | AD2-113 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | In Service | APS | 70 | 60.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/22/2018 |  |  | 6/1/2023 | 4/27/2022
PJM | AD2-114 | South Bend 500kV | South Bend Generating Station | PA | Armstrong | Withdrawn | APS | 410 | 400 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/22/2018 | 10/20/2021 |  | 6/1/2023
PJM | AD2-115 | Lyons-Moselem 69kV | Lyons Solar | PA | Berks | In Service | ME | 20 | 13 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/24/2018 |  |  | 8/31/2023 | 12/1/2023
PJM | AD2-116 | Hokes-Grantley 69 kV | Cottontail Solar 2 | PA | York | In Service | ME | 20 | 13 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/24/2018 |  |  | 12/31/2023 | 3/1/2024
PJM | AD2-117 | Bernville 69kV |  | PA | Berks | Withdrawn | ME | 15 | 7.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/22/2018 | 5/8/2019 |  | 4/1/2020
PJM | AD2-118 | Laurel 12 kV |  | DE | Sussex | Withdrawn | DPL | 5 | 3.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2018 | 3/28/2018 |  | 4/1/2020
PJM | AD2-119 | Milesburg-Dale Summit 230kV |  | PA | Centre | Withdrawn | APS | 75 | 31.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/22/2018 | 9/11/2018 |  | 12/15/2021
PJM | AD2-120 | Shenango-McDowell 138kV |  | PA | Mercer | Withdrawn | ATSI | 120 | 50.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/22/2018 | 6/19/2019 |  | 12/15/2020
PJM | AD2-123 | East Danville-Roxborough 230 kV |  | NC | Person | Withdrawn | AEP | 94 | 68.15 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2018 | 4/16/2018 |  | 6/1/2021
PJM | AD2-124 | East Danville-Roxborough 230 kV |  | NC | Person | Withdrawn | AEP | 20 | 14.54 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2018 | 4/16/2018 |  | 6/1/2021
PJM | AD2-125 | Myersdale Storage |  | PA | Somerset | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2018 | 4/3/2018 |  | 12/31/2020
PJM | AD2-126 | Backbone Mountain 138 kV |  | WV | Tucker | Withdrawn | APS | 90 | 18 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2018 | 3/27/2018 |  | 12/31/2020
PJM | AD2-127 | East Carbondale-Lackawanna 69 kV |  | PA | Wayne | Withdrawn | PPL | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2018 | 4/3/2018 |  | 12/31/2020
PJM | AD2-128 | Mill Run 25 kV |  | PA | Fayette | Withdrawn | APS | 15 | 3 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2018 | 3/27/2018 |  | 12/31/2020
PJM | AD2-129 | Somerset Storage |  | PA | Somerset | Withdrawn | PENELEC | 9 | 9 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2018 | 4/3/2018 |  | 12/31/2020
PJM | AD2-130 | ESS-J338 |  | IL | Will | Withdrawn | ComEd | 0 | 4.3 | Capacity | Generation Interconnection | Hydro | Document Posted | Withdrawn |  |  | 3/23/2018 | 12/14/2018 |  | 9/14/2018
PJM | AD2-131 | Kincaid-Pana 345kV | Broomstick Solar Energy Centergy Center | IL | Christian | Engineering and Procurement | ComEd | 50 | 8.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/24/2018 |  |  | 12/7/2028
PJM | AD2-132 | Olive-Reynolds 345kV |  | IN | Pulaski | Withdrawn | AEP | 200 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 1/10/2019 |  | 12/31/2020
PJM | AD2-133 | Eagle Valley 115kV | Sandy Ridge | PA | Centre | In Service | PENELEC | 85.4 | 15.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/25/2018 |  |  | 7/31/2023 | 9/16/2023
PJM | AD2-134 | Shady Oaks | Shady Oaks Wind Power Project | IL | Lee | Partially in Service - Under Construction | ComEd | 105.9 | 21.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/25/2018 |  |  | 12/7/2027
PJM | AD2-135 | Williamstown 12kV | Monroe-Sicklerville Road LF Solar | NJ | Gloucester | Under Construction | AEC | 1.62 | 0.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 3/23/2018 |  |  | 3/1/2025
PJM | AD2-136 | Melmore Tap 138kV |  | OH | Seneca | Withdrawn | AEP | 360 | 46.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 3/23/2018 | 11/22/2022 |  | 10/31/2021
PJM | AD2-137 | Loretto-Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-138 | Olive-Reynolds #1 345kV |  | IN | Warren | Withdrawn | AEP | 200 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/23/2018 | 4/20/2021 |  | 12/31/2020
PJM | AD2-139 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 200 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/23/2018 | 3/31/2018 |  | 12/31/2020
PJM | AD2-140 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-141 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 150 | 26.25 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-142 | Wilton Center |  | IL | Will | Withdrawn | ComEd | 300 | 52.8 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-143 | Richland Jct-East Leipsic 138kV |  | IN | Randolph | Withdrawn | AEP | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 1/7/2019 |  | 12/31/2020
PJM | AD2-144 | Marysville 345kV |  | IN | Randolph | Withdrawn | AEP | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 1/7/2019 |  | 12/31/2020
PJM | AD2-145 | Star 345kV |  | IN | Randolph | Withdrawn | ATSI | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 9/4/2018 |  | 12/31/2020
PJM | AD2-146 | Wiley 138 kV |  | OH | Butler | Withdrawn | DEOK | 100 | 42 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/23/2018 | 3/31/2018 |  | 12/31/2020
PJM | AD2-147 | South Charleston 345kV |  | OH | Butler | Withdrawn | Dayton | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/23/2018 | 9/24/2019 |  | 12/31/2020
PJM | AD2-148 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-149 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-150 | Davis Creek 345kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/28/2019 |  | 12/31/2020
PJM | AD2-151 | Hillcrest 345kV |  | OH | Muskingum | Withdrawn | DEOK | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/23/2018 | 7/26/2019 |  | 12/31/2020
PJM | AD2-152 | Pocono 230 kV |  | PA | Wayne | Withdrawn | PPL | 150 | 17.6 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/23/2018 | 4/5/2018 |  | 12/31/2020
PJM | AD2-153 | Brokaw-Pontiac Midpoint |  | IL | McLean | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/19/2019 |  | 12/31/2020
PJM | AD2-154 | Brokaw-Pontiac Midpoint |  | IL | McLean | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/17/2019 |  | 12/31/2020
PJM | AD2-155 | Brokaw-Pontiac Midpoint |  | IL | Kankakee | Withdrawn | ComEd | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/23/2018 | 6/17/2019 |  | 12/31/2020
PJM | AD2-156 | Avery 138 kV |  | OH | Erie | Withdrawn | ATSI | 100 | 42 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/23/2018 | 4/2/2018 |  | 12/31/2020
PJM | AD2-157 | Hampshire-Gore 138kV |  | WV | Hampshire | Withdrawn | APS | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/23/2018 | 10/10/2022 |  | 12/21/2021
PJM | AD2-158 | Old Chapel-Millville 138kV | Wild Hill Solar | WV | Jefferson | Withdrawn | APS | 77.5 | 46.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/24/2018 | 10/16/2024 |  | 9/1/2024
PJM | AD2-159 | Chestnut 345kV |  | IL | Macon | Withdrawn | ComEd | 187.5 | 33 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/26/2018 | 3/4/2022
PJM | AD2-160 | Hickory-Moyock 230kV | Oak Trail Solar | NC | Currituck | In Service | Dominion | 50 | 32.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2018 |  |  | 7/1/2023 | 7/5/2023
PJM | AD2-161 | Hunlock 69kV |  | PA | Luzerne | Withdrawn | PPL | 10 | 10 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/26/2018 | 3/28/2018 |  | 5/22/2022
PJM | AD2-162 | Biers Run-Circleville 138kV | Scioto Farms Solar Project | OH | Pickaway | Withdrawn | AEP | 110 | 73.81 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/27/2018 | 6/21/2023 |  | 5/31/2025
PJM | AD2-163 | Broadview-Tangy 138 kV | Madison Fields Solar Project | OH | Madison | In Service | ATSI | 180 | 120.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/27/2018 |  |  | 12/31/2023 | 1/23/2024
PJM | AD2-164 | Peninsula 34.5kV | Langley AFB Generation | VA | City of Hampton | Withdrawn | Dominion | 26.7 | 26.7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/26/2018 | 6/30/2020 |  | 6/1/2022
PJM | AD2-165 | South River II 230kV |  | NJ | Middlesex | Withdrawn | JCPL | 105 | 40 | Capacity | Generation Interconnection | Natural Gas; Storage | Document Posted | Document Posted | Withdrawn |  | 3/26/2018 | 2/10/2020 |  | 5/1/2021
PJM | AD2-166 | Ironwood 230kV | Helix Ironwood Facility | PA | Lebanon | In Service | ME | 75 | 89.8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/27/2018 |  |  | 4/30/2022 | 4/28/2022
PJM | AD2-167 | Rock Springs 500kV | Wildcat Point | MD | Cecil | In Service | Essential Power | 90 | 52 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/27/2018 |  |  | 12/31/2019 | 7/27/2017
PJM | AD2-168 | Wempletown 138 kV |  | IL | Winnebago | Withdrawn | ComEd | 150 | 57 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/28/2018 | 4/3/2018 |  | 9/15/2020
PJM | AD2-169 | Pleasant Hill-Trego 115kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Not Required | Document Posted |  |  | 3/28/2018 | 1/28/2020 |  | 9/30/2020
PJM | AD2-170 | Carll's Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 0 | 0 | Energy | Generation Interconnection | Solar | Document Posted |  |  |  | 3/28/2018 | 9/20/2018 |  | 1/1/2019
PJM | AD2-171 | Branchburg-Alburtis 500kV |  | NJ | Hunterdon | Withdrawn | PSEG | 700 | 700 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/28/2018 | 11/25/2020 |  | 6/1/2023
PJM | AD2-172 | Lena 138kV | High Point Solar | IL | Stephenson | In Service | ComEd | 50 | 21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2018 |  |  | 2/28/2024 | 11/30/2023
PJM | AD2-173 | Bremo-Kidds Store 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 75 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/28/2018 | 4/2/2018 |  | 5/1/2020
PJM | AD2-174 | Oakville-St. Andrews 69kV |  | MD | St. Mary's | Withdrawn | SMECO | 52.5 | 31.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/28/2018 | 1/24/2019 |  | 9/30/2020
PJM | AD2-175 | Davis Creek 345 kV |  | IL | Kankakee | Withdrawn | ComEd | 205 | 123 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/28/2018 | 12/10/2019 |  | 12/31/2021
PJM | AD2-176 | Marengo 138kV |  | IL | McHenry | Withdrawn | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/28/2018 | 6/27/2019 |  | 12/31/2021
PJM | AD2-177 | Pontiac MidPoint 345 kV |  | IL | Livingston | Withdrawn | ComEd | 205 | 123 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/28/2018 | 3/23/2018 |  | 12/31/2021
PJM | AD2-178 | Wurno 138kV | Blackbird Solar | VA | Pulaski | Withdrawn | AEP | 120 | 72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/28/2018 | 4/5/2023 |  | 6/1/2021
PJM | AD2-179 | Morgans Cut-Glen Lyn 138kV | Blue Jay Solar | VA | Pulaski | Suspended | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2018 |  |  | 12/31/2025
PJM | AD2-180 | Elk Garden-Parr Run 138kV | Black Rock Wind | WV | Mineral | In Service | APS | 110 | 15.08 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2018 |  |  | 12/15/2021 | 10/25/2021
PJM | AD2-181 | Shawboro-Sligo 230 kV |  | NC | Currituck | Withdrawn | Dominion | 150 | 105 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2018 | 4/3/2018 |  | 12/31/2018
PJM | AD2-182 | George Washington 138 kV |  | WV | Marshall | Withdrawn | AEP | 481.5 | 380 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 3/29/2018 | 4/6/2018 |  | 4/1/2022
PJM | AD2-183 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 31.2 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/29/2018 | 4/3/2018 |  | 9/15/2020
PJM | AD2-184 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 31.2 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/29/2018 | 4/3/2018 |  | 9/15/2020
PJM | AD2-185 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 31.2 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/29/2018 | 4/3/2018 |  | 9/15/2021
PJM | AD2-186 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 14.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2018 | 4/6/2018 |  | 9/30/2019
PJM | AD2-187 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 8.64 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2018 | 4/6/2018 |  | 9/30/2019
PJM | AD2-188 | Nelson-Electric Junc |  | IL | Lee | Withdrawn | ComEd | 125 | 75 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2018 | 4/6/2018 |  | 6/30/2021
PJM | AD2-189 | Kammer-Vassell 765kV | Guernsey Power Station | OH | Guernsey | In Service | AEP | 225 | 186 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/30/2018 |  |  | 12/31/2022 | 2/27/2023
PJM | AD2-190 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 111.7933 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/6/2018 |  | 11/1/2020
PJM | AD2-191 | Melmore 138kV |  | OH | Seneca | Withdrawn | AEP | 170 | 22.1 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 3/30/2018 | 6/3/2020 |  | 11/2/2020
PJM | AD2-192 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 45 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2018 |  |  | 3/31/2028
PJM | AD2-193 | Spotsylvania 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 208.5 | 208.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/6/2018 |  | 11/1/2020
PJM | AD2-194 | Elwood 345 kV | Jackson Generation | IL | Will | Partially in Service - Under Construction | ComEd | 60 | 120 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2018 |  |  | 1/1/2027
PJM | AD2-195 | Trowbridge-Pantero 115 kV |  | NC | Washington | Withdrawn | Dominion | 80 | 55.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2018 | 9/25/2018 |  | 6/1/2021
PJM | AD2-196 | Acahela 230 kV |  | PA | Luzerne | Withdrawn | PPL | 150 | 26.4 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/30/2018 | 4/5/2018 |  | 12/31/2020
PJM | AD2-197 | Carson-Rodgers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 500 | 300 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  | Withdrawn | 3/30/2018 | 4/9/2018 |  | 5/3/2021
PJM | AD2-198 | Ellwood |  | IL | Will | Withdrawn | ComEd | 135 | 135 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 3/30/2018 | 4/6/2018 |  | 3/1/2020
PJM | AD2-199 | St. Barnabas 13kV II | Spectrum Solar II | MD | Prince George's | Withdrawn | PEPCO | 3 | 1.26 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 3/30/2018 | 4/27/2024 |  | 6/3/2022
PJM | AD2-200 | Briery-Clover 230 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 14 | 9.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2018 | 10/16/2018 |  | 9/2/2019
PJM | AD2-201 | South Creek 115 kV |  | VA | Appomattox | Withdrawn | Dominion | 62 | 40.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/6/2018 |  | 3/31/2020
PJM | AD2-201A | Hickman-Riverbend 69kV |  | VA | Pulaski | Withdrawn | AEP | 50 | 31 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2018 | 1/22/2019 |  | 5/3/2021
PJM | AD2-202 | Clover-Sedge Hill 230kV | Foxhound Solar | VA | Halifax | In Service | Dominion | 18.8 | 12.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2018 |  |  | 5/31/2024 | 4/24/2024
PJM | AD2-203 | Clubhouse-Lakeville 230 kV |  | VA | Greensville | Withdrawn | Dominion | 72.3 | 49.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/6/2018 |  | 9/4/2020
PJM | AD2-204 | Burlington 26 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/2/2018 |  | 5/31/2019
PJM | AD2-205 | Byllesby 69 kV | Buck & Byllesby Hydro Project | VA | Carroll | In Service | AEP | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 4/13/2018 |  |  | 12/31/2018 | 1/31/2019
PJM | AD2-206 | Clubhouse-Freeman DP 115 kV |  | VA | Greensville | Withdrawn | Dominion | 250 | 150.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/4/2018 |  | 6/1/2020
PJM | AD2-207 | Suffolk-Poe 115 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/4/2018 |  | 6/1/2020
PJM | AD2-208 | Boykins 115 kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/5/2018
PJM | AD2-209 | Cherryville 12.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 3/30/2018 | 10/9/2018 |  | 11/30/2018
PJM | AD2-210 | Cedar Knolls 12.5 kV | South Jefferson Road Storage | NJ | Morris | Withdrawn | JCPL | 2 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 3/30/2018 | 11/1/2023 |  | 12/31/2020
PJM | AD2-211 | Great Adventure 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/30/2018 | 3/31/2018 |  | 10/1/2018
PJM | AD2-212 | Ocean Bay 128 kV |  | MD | Worcester | Withdrawn | DPL | 160 | 70 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 3/30/2018 | 4/10/2018 |  | 6/1/2022
PJM | AD2-213 | East Flemington-Lebanon 34.5 kV | Justin Court Energy Storage | NJ | Hunterdon | In Service | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2018 |  |  | 7/14/2023 | 2/15/2024
PJM | AD2-214 | Rock Falls-Garden Plains |  | IL | Whiteside | Withdrawn | ComEd | 68 | 40.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/30/2018 | 5/2/2023 |  | 5/3/2021
PJM | AD2-215 | Kings Fork 34.5 kV | Godwin Blvd Solar | VA | City of Suffolk | Withdrawn | Dominion | 15 | 9.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/30/2018 | 1/14/2021 |  | 12/1/2021
PJM | AD2-216 | Axton 138 kV |  | VA | Henry | Withdrawn | AEP | 68 | 43.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2018 | 4/3/2018 |  | 3/31/2020
PJM | AD2-217 | Crossland 13 kV |  | PA | Mercer | Withdrawn | ATSI | 8.8 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/30/2018 | 4/4/2018 |  | 3/1/2019
PJM | AE1-001 | Calvert Cliffs 500kV | Calvert Cliffs Units 1 and 2 (f/k/a PJM Queue M04) | MD | Calvert | In Service | BGE | 28.1 | 7.1 | Capacity | Generation Interconnection | Nuclear | Document Posted | Document Posted | Not Required | Document Posted | 4/2/2018 |  |  | 1/13/2023
PJM | AE1-002 | Wilton Center-Loretto |  | IN | Benton | Withdrawn | ComEd | 100 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 4/4/2018 | 7/29/2019 |  | 12/31/2020
PJM | AE1-003 | Williams 138 kV |  | WV | Grant | Withdrawn | APS | 59 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 4/4/2018 | 9/25/2020 |  | 12/31/2020
PJM | AE1-004 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/7/2018 |  |  | 12/31/2023
PJM | AE1-005 | Pantego-Five Points 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 16 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/20/2018 |  |  | 12/31/2020
PJM | AE1-006 | Germantown 115 kV | Brookview Solar I | PA | Adams | Withdrawn | ME | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/23/2018 | 12/11/2023 |  | 12/15/2025
PJM | AE1-007 | Camden-Crystal III 69 kV |  | OH | Preble | Withdrawn | Dayton | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/23/2018 | 8/16/2021 |  | 7/1/2019
PJM | AE1-008 | College Corner 138 kV |  | OH | Preble | Withdrawn | AEP | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/23/2018 | 8/1/2019 |  | 7/1/2019
PJM | AE1-009 | Bremo-Cunningham DP 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 20 | 13.1 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/25/2018 | 3/11/2019 |  | 3/31/2020
PJM | AE1-010 | Locust Grove-Paytes 115 kV |  | VA | Orange | Withdrawn | Dominion | 33 | 33 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 4/27/2018 | 3/11/2019 |  | 9/30/2021
PJM | AE1-011 | Livingston Road 13 kV |  | MD |  | Withdrawn | PEPCO | 1.48 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/2/2018 | 9/24/2018 |  | 3/31/2019
PJM | AE1-012 | 64th St. 13 kV | 1724 64th Street | MD | Prince George's | Withdrawn | PEPCO | 0.54 | 0.22 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/2/2018 | 11/11/2022 |  | 12/30/2022
PJM | AE1-013 | Suitland Road 13 kV | 4179 Suitland Road | MD | Prince George's | Withdrawn | PEPCO | 0.9 | 0.378 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/3/2018 | 4/27/2024 |  | 12/31/2022
PJM | AE1-014 | Canada Street 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 0.54 | 0.23 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/2/2018 | 9/24/2018 |  | 9/30/2019
PJM | AE1-015 | St. Barnabas Road 13 kV | 5203 Saint Barnabas Road | MD | Prince George's | Withdrawn | PEPCO | 1.4 | 0.567 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/2/2018 | 11/11/2022 |  | 12/31/2022
PJM | AE1-016 | Livingston Road 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 1.08 | 0.4536 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 5/3/2018 | 12/16/2019 |  | 9/30/2019
PJM | AE1-017 | Peak Creek-Draper 34.5 kV |  | VA | Pulaski | Withdrawn | AEP | 20 | 11 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 5/14/2018 | 7/15/2020 |  | 6/1/2020
PJM | AE1-018 | Peak Creek-Memoria Drive 12 kV | Pulaski Community Solar | VA | Pulaski | Withdrawn | AEP | 5 | 2.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required |  | 5/14/2018 | 2/21/2020 |  | 6/1/2020
PJM | AE1-019 | Earleys-Scotland Neck 115 kV |  | NC | Hertford | Withdrawn | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/15/2018 | 10/31/2018 |  | 6/30/2021
PJM | AE1-020 | Oyster Creek 230 kV | Ocean Wind | NJ | Ocean | Suspended | JCPL | 816 | 229.3 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 5/23/2018 |  |  | 2/28/2026
PJM | AE1-021 | Gavin #2 765 kV | Gavin Unit No. 2 | OH | Gallia | In Service | AEP | 11 | 11 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 5/24/2018 |  |  | 6/1/2021 | 6/19/2021
PJM | AE1-022 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 111.7933 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/25/2018 | 6/21/2018 |  | 11/2/2020
PJM | AE1-023 | Wempletown |  | IL | Winnebago | Withdrawn | ComEd | 150 | 57 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 5/25/2018 | 6/25/2018 |  | 12/15/2021
PJM | AE1-024 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 63.8 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 5/25/2018 | 10/3/2020 |  | 12/15/2021
PJM | AE1-025 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 63.8 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 5/25/2018 | 10/3/2020 |  | 12/15/2021
PJM | AE1-026 | Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 80 | 63.8 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 5/25/2018 | 10/3/2020 |  | 12/15/2022
PJM | AE1-027 | Hickory 34.5 kV | Hickory Solar | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 13.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/29/2018 | 1/14/2020 |  | 12/31/2020
PJM | AE1-028 | Hickory 34.5 kV | Hickory Solar | VA | City of Chesapeake | Withdrawn | Dominion | 12 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/29/2018 | 1/14/2020 |  | 12/31/2020
PJM | AE1-029 | Wheatland 12 kV |  | PA | Mercer | Withdrawn | ATSI | 8.8 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 5/30/2018 | 6/19/2019 |  | 3/1/2019
PJM | AE1-030 | Stuart-Clinton 345 kV II |  | OH | Montgomery | Withdrawn | Dayton | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/4/2018 | 6/29/2018 |  | 6/1/2021
PJM | AE1-031 | Stuart-Clinton 345 kV III |  | OH | Montgomery | Withdrawn | Dayton | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/4/2018 | 6/29/2018 |  | 6/1/2020
PJM | AE1-034 | Larrabee 230 kV |  | NJ | Atlantic | Withdrawn | JCPL | 1104 | 310.224 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 6/7/2018 | 4/19/2019 |  | 6/1/2024
PJM | AE1-035 | Earleys 230 kV | Aulander Holloman Solar Park | NC | Hertford | In Service | Dominion | 19.9 | 13.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 6/8/2018 |  |  | 6/1/2020 | 2/24/2020
PJM | AE1-036 | Red Oak 230 kV | Red Oak | NJ | Middlesex | In Service | JCPL | 0 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 6/13/2018 |  |  | 7/1/2018 | 2/8/2019
PJM | AE1-038 | Cartanza 69 kV |  | DE | Kent | Withdrawn | DPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 6/22/2018 | 9/30/2019 |  | 10/31/2020
PJM | AE1-039 | West Street (Orchard Hills) 12.47 kV | Orchard Hills Sanitary Landfill | MI | Berrien | In Service | AEP | 0.8 | 0.8 | Capacity | Generation Interconnection | Methane | Document Posted | Document Posted | Not Required | Document Posted | 6/22/2018 |  |  | 9/30/2020 | 10/1/2019
PJM | AE1-040 | Greenfield 69 kV | Fayette Solar | OH | Fayette | In Service | Dayton | 48 | 31.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/26/2018 |  |  | 5/31/2024 | 1/2/2025
PJM | AE1-041 | Edison 4kV | Highland Park | NJ | Middlesex | In Service | PSEG | 1.1 | 0.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/25/2018 |  |  | 1/31/2020 | 12/30/2019
PJM | AE1-043 | Clayton-Woodstown 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 1 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/3/2018 | 7/25/2018 |  | 11/1/2018
PJM | AE1-044 | Morrisville 230 kV | Fitch Solar | VA | Fauquier | Withdrawn | Dominion | 200 | 111.7933 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/6/2018 | 1/8/2025 |  | 12/30/2025
PJM | AE1-045 | Minotola 12 kV I |  | NJ | Atlantic | Withdrawn | AEC | 3 | 2.01 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/11/2018 | 3/4/2019 |  | 12/31/2019
PJM | AE1-046 | Minotola 12 kV II |  | NJ | Atlantic | Withdrawn | AEC | 3 | 2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 7/11/2018 | 9/20/2019 |  | 12/31/2019
PJM | AE1-047 | Spotsylvania 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 300 | 208.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/11/2018 | 10/12/2018 |  | 11/1/2021
PJM | AE1-048 | Wye Mills 25 kV |  | MD | Queen Anne's | Withdrawn | DPL | 1 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/17/2018 | 8/9/2018
PJM | AE1-050 | Gavin Unit 1 765 kV | Gavin Unit No. 1 | OH | Gallia | Partially in Service - Under Construction | AEP | 18 | 18 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/20/2018 |  |  | 6/9/2024
PJM | AE1-051 | East Carbondale-Lackawanna 69kV |  | PA | Wayne | Withdrawn | PPL | 0 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/20/2018 | 1/25/2023 |  | 9/1/2020
PJM | AE1-052 | William 138 kV | Backbone Mountain Windpower | WV | Tucker | Withdrawn | APS | 0 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  | Document Posted | 7/21/2018 | 11/28/2022 |  | 9/1/2024
PJM | AE1-053 | Meyersdale North |  | PA | Somerset | Withdrawn | PENELEC | 0 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/20/2018 | 12/1/2022 |  | 9/1/2020
PJM | AE1-054 | Mill Run 25kV |  | PA | Fayette | Withdrawn | APS | 0 | 7.5 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/23/2018 | 3/19/2021 |  | 9/1/2020
PJM | AE1-055 | Mason 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 134 | 134 | Capacity | Generation Interconnection | Natural Gas; Other; Storage; Solar | Withdrawn |  |  |  | 7/24/2018 | 8/14/2018 |  | 12/31/2021
PJM | AE1-056 | Red House-South Creek 115 kV | Caden Energix Spout Spring | VA | Appomattox | Suspended | Dominion | 60 | 38.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/25/2018 |  |  | 1/31/2025
PJM | AE1-057 | Brandy DP 115 kV |  | VA | Culpeper | Withdrawn | Dominion | 5 | 3.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/26/2018 | 11/7/2018 |  | 12/1/2019
PJM | AE1-058 | Frackville-Siegfried 230 kV |  | PA | Schuylkill | Withdrawn | PPL | 500 | 250 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Withdrawn | 7/26/2018 | 10/13/2023 |  | 12/15/2022
PJM | AE1-059 | Stanton-Summit 230 kV | AREW Old Forge | PA | Luzerne | Withdrawn | PPL | 200 | 200 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Document Posted | Document Posted | 7/27/2018 | 3/7/2024 |  | 9/30/2027
PJM | AE1-060 | Kittatinny-Newton 34.5 kV | VESI – Andover Energy Storage | NJ | Sussex | In Service | JCPL | 19.8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 7/26/2018 |  |  | 9/30/2022 | 6/17/2023
PJM | AE1-061 | Minotola 12 kV | Panther Branch Storage | NJ | Atlantic | Withdrawn | AEC | 5.5 | 2.75 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2018 | 4/28/2023 |  | 4/1/2025
PJM | AE1-062 | Silver Lake 69 kV |  | NJ | Camden | Withdrawn | AEC | 20 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2018 | 3/22/2022 |  | 10/30/2020
PJM | AE1-063 | Buckeye-Ringoes 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 3 | 1.26 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/30/2018 | 3/27/2019 |  | 11/29/2019
PJM | AE1-064 | Whitehouse-Lone Gum 138 kV |  | VA | Bedford | Withdrawn | AEP | 102.1 | 67.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/31/2018 | 4/12/2024 |  | 5/3/2021
PJM | AE1-065 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 158.9 | Capacity | Generation Interconnection | Offshore Wind | Document Posted |  |  |  | 7/31/2018 | 3/5/2019 |  | 12/31/2025
PJM | AE1-066 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 163.3 | Capacity | Generation Interconnection | Offshore Wind | Document Posted |  |  |  | 7/31/2018 | 3/5/2019 |  | 12/31/2027
PJM | AE1-067 | Virginia Beach 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 148.5 | Capacity | Generation Interconnection | Offshore Wind | Document Posted |  |  |  | 7/31/2018 | 3/5/2019 |  | 12/31/2029
PJM | AE1-068 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Withdrawn | Dominion | 500 | 322.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/31/2018 | 9/8/2023 |  | 12/1/2021
PJM | AE1-069 | Carson-Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 400 | 254.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/31/2018 | 9/8/2023 |  | 12/1/2021
PJM | AE1-070 - moved to TC1 | Elwood 345 kV |  | IL | Will | Active | ComEd | 0 | 135 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | In Progress |  | 7/31/2018 |  |  | 12/31/2020
PJM | AE1-071 | Shade Gap-Roxbury 115 kV | Aspen Road Solar | PA | Franklin | Under Construction | PENELEC | 100.1 | 62.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2018 |  |  | 3/8/2025
PJM | AE1-072 | Shawboro-Sligo 230 kV | Shawboro Solar | NC | Currituck | Engineering and Procurement | Dominion | 150 | 98.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2018 |  |  | 12/1/2027
PJM | AE1-073 | Bremo-Kidds Store 115 kV |  | VA | Accomack | Withdrawn | Dominion | 75 | 48 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/31/2018 | 3/13/2019 |  | 12/1/2021
PJM | AE1-074 | Winterpock 34.5 kV | Winterpock I | VA | Chesterfield | Suspended | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/1/2018 |  |  | 12/1/2023
PJM | AE1-075 | Powhatan 34.5 kV | Powhatan Solar I, LLC | VA | Powhatan | Partially in Service - Under Construction | Dominion | 18 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/2/2018 |  |  | 10/31/2024
PJM | AE1-076 | Twombley Road 138 kV |  | IL | Ogle | Withdrawn | ComEd | 20 | 20 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/7/2018 | 9/10/2018 |  | 12/31/2019
PJM | AE1-079 | Maysville-Sharon 69 kV | Welcome Solar, LLC | PA | Mercer | Engineering and Procurement | ATSI | 19.9 | 13.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 8/11/2018 |  |  | 6/5/2024
PJM | AE1-080 | Wylie Ridge 500 kV |  | PA | Washington | Withdrawn | APS | 50 | 80 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/21/2018 | 3/26/2021 |  | 2/1/2022
PJM | AE1-081 | Landing 12.47 kV | Durban Ave Solar | NJ | Sussex | In Service | JCPL | 1.25 | 0.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/27/2018 |  |  | 6/30/2021 | 9/25/2020
PJM | AE1-082 | Charles County 13 kV |  | MD | Charles | Withdrawn | SMECO | 1.25 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/28/2018 | 9/13/2018 |  | 11/30/2018
PJM | AE1-083 | Busselton 13kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 2.1 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 8/28/2018 | 6/19/2019 |  | 5/31/2019
PJM | AE1-084 | Barterbrook-Stuarts Draft 115 kV | Round Hill Solar | VA | Augusta | Withdrawn | Dominion | 83 | 49.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2018 | 7/11/2024 |  | 10/31/2023
PJM | AE1-085 | Bakers Pond-Bell Ave 115 kV |  | VA | Sussex | Withdrawn | Dominion | 75 | 50 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/30/2018 | 8/31/2022 |  | 6/1/2022
PJM | AE1-086 | Grassy Falls 138 kV | Beech Ridge Wind Farm | WV | Greenbrier | In Service | APS | 5 | 0.6 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 8/31/2018 |  |  | 5/31/2020 | 3/14/2020
PJM | AE1-087 | Todd 69 kV | Richfield Solar and Storage | MD | Dorchester | Withdrawn | DPL | 20 | 16 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2018 | 4/27/2024 |  | 4/1/2024
PJM | AE1-088 | Five Points-Pantego 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 8/31/2018 | 4/17/2020 |  | 12/31/2020
PJM | AE1-089 | Elderberry-Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 310 | 130.65 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 8/31/2018 | 1/30/2020 |  | 12/31/2021
PJM | AE1-090 | Hardin Switch 345 kV | Hardin Energy Center - Phase 3 | OH | Hardin | Partially in Service - Under Construction | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/1/2018 |  |  | 12/31/2025
PJM | AE1-091 | West Newton-Lynn 138 kV | Strawhat Solar Energy Center | OH | Hardin | Suspended | AEP | 110 | 46.93 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2018 |  |  | 1/14/2026
PJM | AE1-092 - moved to TC1 | Blue Jacket-Kirby 138 kV |  | OH | Union | Active | Dayton | 229.5 | 96.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 8/31/2018 |  |  | 12/31/2021
PJM | AE1-093 | Elk 138 kV | Vinton Energy Storage | OH | Vinton | Engineering and Procurement | AEP | 42 | 42 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2018 |  |  | 12/31/2026
PJM | AE1-098 | Endless Caverns 34.5 kV | Endless Caverns Solar | VA | Rockingham | Withdrawn | Dominion | 15.7 | 10.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 8/31/2018 | 3/6/2023 |  | 6/26/2023
PJM | AE1-099 | Endless Caverns 34.kV | Endless Caverns Solar | VA | Rockingham | Withdrawn | Dominion | 15.7 | 10.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/31/2018 | 3/6/2023 |  | 6/26/2023
PJM | AE1-100 | Axton 138 kV | Caden Energix Axton | VA | Henry | In Service | AEP | 66 | 41.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/3/2018 |  |  | 12/31/2023 | 2/22/2024
PJM | AE1-101 | McConnellsburg-Texas Eastern 138 kV | Great Cove Solar II | PA | Franklin | In Service | APS | 150 | 100.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/2/2018 |  |  | 3/31/2024 | 6/6/2024
PJM | AE1-102 | Maddox Creek 345 kV | Blue Creek Wind Farm | OH | Van Wert | Suspended | AEP | 26 | 15.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/1/2018 |  |  | 11/30/2024
PJM | AE1-103 | Holland-Union Camp 115 kV | Ho-Fel Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 40 | 16.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/1/2018 |  |  | 10/19/2026
PJM | AE1-104 | BL England 138 kV | Ocean Wind LLC | NJ | Cape May | Suspended | AEC | 432 | 121.4 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/6/2018 |  |  | 2/28/2026
PJM | AE1-105 | North Longview 500 kV | Maidsville CCGT | WV | Preston | Suspended | APS | 1270 | 1235 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/6/2018 |  |  | 7/1/2026
PJM | AE1-106 | Lake Lynn-Hazelton 138 kV | Brandonville Solar | WV | Preston | Engineering and Procurement | APS | 99.6 | 59 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/11/2018 |  |  | 12/31/2026
PJM | AE1-107 | Mt. Pleasant-Lums Pond 138 kV |  | DE | New Castle | Withdrawn | DPL | 53.1 | 31 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/10/2018 | 4/5/2023 |  | 9/30/2021
PJM | AE1-108 | Bremo-Scottsville 138 kV | Riverstone Solar | VA | Buckingham | Engineering and Procurement | AEP | 149.5 | 89.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/13/2018 |  |  | 3/31/2026
PJM | AE1-109 | Frenchs Mill 34 kV | Capon Bridge Solar | WV | Hampshire | In Service | APS | 20 | 8.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/15/2018 |  |  | 7/31/2024 | 7/25/2024
PJM | AE1-109A | Baker Pont-Ivor 115 kV |  | VA | Southampton | Withdrawn | Dominion | 85 | 51 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/12/2018 | 3/6/2019 |  | 12/1/2022
PJM | AE1-113 | Mole Creek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 300 | 66 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/14/2018 |  |  | 1/18/2027
PJM | AE1-114 - moved to TC1 | Maryland-Lancaster 138 kV |  | IL | Ogle | Active | ComEd | 150 | 34 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 9/13/2018 |  |  | 12/31/2021
PJM | AE1-115 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 20 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 9/14/2018 | 4/29/2022 |  | 6/1/2021
PJM | AE1-116 | Somerset 22.86kV |  | PA | Somerset | Withdrawn | PENELEC | 0 | 4.5 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 9/14/2018 | 3/19/2021 |  | 10/1/2020
PJM | AE1-117 | Bethany 138 kV |  | DE | Sussex | Withdrawn | DPL | 152 | 41.5 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 9/14/2018 | 7/15/2022 |  | 6/1/2022
PJM | AE1-118 | Bethany-138th Street 138 kV |  | DE | Sussex | Withdrawn | DPL | 152 | 41.5 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 9/14/2018 | 7/10/2020 |  | 6/1/2022
PJM | AE1-119 | Lemoyne 345 kV |  | OH | Wood | Withdrawn | ATSI | 550 | 550 | Capacity | Generation Interconnection | Natural Gas; Other | Document Posted | Document Posted | Withdrawn |  | 9/17/2018 | 10/27/2021 |  | 6/1/2022
PJM | AE1-120 | Hillcrest 138 kV | Hillcrest Solar I | OH | Brown | In Service | DEOK | 0 | 44 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/17/2018 |  |  | 12/31/2020 | 12/18/2020
PJM | AE1-121 | Axton 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 529.5 | 483 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 9/18/2018 | 1/8/2021 |  | 6/1/2022
PJM | AE1-122 | Axton 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 529.5 | 483 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 9/18/2018 | 7/18/2019 |  | 6/1/2023
PJM | AE1-123 | Emlenton 34.5 kV | Clarion Boards | PA | Clarion | In Service | PENELEC | 18 | 18 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/20/2018 |  |  | 11/10/2023 | 11/3/2023
PJM | AE1-124 | Oak Grove 34.5 kV | VSF Solar I | VA | Westmoreland | Withdrawn | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/19/2018 | 4/30/2021 |  | 3/27/2024
PJM | AE1-125 | Mt. Jackson 34.5 kV |  | VA | Shenandoah | Withdrawn | Dominion | 18.9 | 13 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/19/2018 | 3/11/2019 |  | 11/20/2020
PJM | AE1-126 | Kingsland 26 kV |  | NJ | Bergen | Withdrawn | PSEG | 19.8 | 8.316 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/19/2018 | 10/1/2018 |  | 11/29/2019
PJM | AE1-127 | Eldred-Sunbury 69 kV |  | PA | Northumberland | Withdrawn | PPL | 50 | 32.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/19/2018 | 10/18/2019 |  | 6/7/2021
PJM | AE1-128 | Bedford North-Wills Mounain 115 kV |  | PA | Bedford | Withdrawn | PENELEC | 120 | 72 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Withdrawn | 9/19/2018 | 2/8/2023 |  | 12/31/2021
PJM | AE1-129 | Zion View - Middletown 115 kV | Strinestown Solar Project | PA | York | Suspended | ME | 79.6 | 47 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/7/2018 |  |  | 12/31/2024
PJM | AE1-130 | Meads Store 138 kV |  | VA | Bedford | Withdrawn | AEP | 83 | 55.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/11/2018 | 8/6/2021 |  | 11/30/2020
PJM | AE1-131 | Gardners-Hunterstown 115 kV |  | PA | Adams | Withdrawn | ME | 65 | 39 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/20/2018 | 6/11/2021 |  | 12/31/2021
PJM | AE1-132 | McConnellsburg 138 kV |  | PA | Fulton | Withdrawn | APS | 85 | 51 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/20/2018 | 2/23/2022 |  | 12/31/2021
PJM | AE1-133 | Elizabeth City-Tanglewood 230 kV |  | NC | Alamance | Withdrawn | Dominion | 300 | 201 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/24/2018 | 3/11/2019 |  | 9/1/2022
PJM | AE1-134 | Nelson 345 kV | Nelson Energy Center | IL | Lee | In Service | ComEd | 9 | 24.4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/24/2018 |  |  | 6/30/2023 | 5/12/2023
PJM | AE1-135 | Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 200 | 120 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 9/24/2018 | 3/19/2019 |  | 6/30/2019
PJM | AE1-136 | McConnellsburg-Guilford 138 kV |  | PA | Franklin | Withdrawn | APS | 53.32 | 32 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/24/2018 | 3/26/2019 |  | 12/31/2021
PJM | AE1-137 | Bluff Point-Randolph |  | IN | Randolph | Withdrawn | AEP | 100 | 38 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/24/2018 | 10/3/2018 |  | 10/31/2021
PJM | AE1-138 | Hamilton 115 kV |  | PA | Adams | Withdrawn | ME | 22 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/24/2018 | 3/30/2022
PJM | AE1-139 | Hunterstown 115 kV |  | PA | Adams | Withdrawn | ME | 65 | 39 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/24/2018 | 3/29/2022 |  | 12/15/2022
PJM | AE1-140 | Fayetteville-West Waynesboro 138 kV |  | PA | Franklin | Withdrawn | APS | 22 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/24/2018 | 4/30/2019 |  | 12/31/2021
PJM | AE1-141 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 55 | 33 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/24/2018 | 10/1/2018 |  | 12/31/2021
PJM | AE1-142 | Manitou-Pleasant Plains 34.5 kV | Toms River Solar | NJ | Ocean | In Service | JCPL | 20 | 8.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/24/2018 |  |  | 2/28/2021 | 3/12/2021
PJM | AE1-143 | Marion County 161 kV | Northern Bobwhite Solar | KY | Marion | Engineering and Procurement | EKPC | 96 | 64.163 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/25/2018 |  |  | 3/15/2027
PJM | AE1-144 - moved to TC1 | Goddard-Plumville 138 kV |  | KY | Fleming | Withdrawn | EKPC | 100 | 66.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/24/2018 | 8/2/2024 |  | 6/1/2022
PJM | AE1-145 | Wallops Island 69 kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/24/2018 | 4/20/2022 |  | 12/1/2020
PJM | AE1-146 | Ebersole #2-Fostoria Central 138 kV | Border Basin | OH | Hancock | Engineering and Procurement | AEP | 120 | 81.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/25/2018 |  |  | 12/31/2025
PJM | AE1-147 | Bellefonte 46 kV | Nittany Solar | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/24/2018 | 3/12/2022 |  | 12/15/2022
PJM | AE1-148 - moved to TC1 | Kerr Dam-Ridge Rd 115 kV |  | VA | Mecklenburg | Active | Dominion | 90 | 54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/24/2018 |  |  | 12/1/2021
PJM | AE1-149 | Disputanta-Poe 115 kV | Bakers Pond Solar | VA | Prince George | Suspended | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/24/2018 |  |  | 7/1/2026
PJM | AE1-150 | Curdsville-Willis Mountain 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/24/2018 | 3/15/2019 |  | 12/1/2021
PJM | AE1-151 | PACA Street 13.8kV |  | MD | Baltimore City | Withdrawn | BGE | 9 | 9 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 9/24/2018 | 10/8/2019 |  | 3/2/2020
PJM | AE1-152 | Gosport 34.5 kV |  | VA | City of Portsmouth | Withdrawn | Dominion | 21.5 | 20.2 | Capacity | Generation Interconnection | Natural Gas; Diesel; Other; Storage | Withdrawn |  |  |  | 9/24/2018 | 10/16/2018 |  | 10/16/2020
PJM | AE1-153 | Remington-Gordonsville 230 kV | Maroon Solar | VA | Culpeper | Suspended | Dominion | 149 | 89.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/25/2018 |  |  | 5/30/2027
PJM | AE1-154 | Louisa-South Anna 230 kV | Belcher Solar | VA | Louisa | Withdrawn | Dominion | 17 | 10 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/24/2018 | 7/5/2023 |  | 12/1/2021
PJM | AE1-155 | Garner-Northern Neck 115 kV | Bookers Mill Solar | VA | City of Richmond | In Service | Dominion | 127 | 76.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2018 |  |  | 5/14/2024 | 12/18/2024
PJM | AE1-156 | Quakertown Solar II 34.5 kV | Quakertown Solar Farm | NJ | Hunterdon | Under Construction | JCPL | 7.6 | 4.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2018 |  |  | 12/31/2025
PJM | AE1-157 | Ladysmith CT-St. Johns 230 kV | CC Solar I | VA | Caroline | Suspended | Dominion | 120 | 77.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/24/2018 |  |  | 6/30/2025
PJM | AE1-158 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 120 | 79.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/24/2018 | 7/28/2023 |  | 12/1/2021
PJM | AE1-159 | Fredericksburg-Pinewood 115 kV |  | VA | Caroline | Withdrawn | Dominion | 120 | 75.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/24/2018 | 12/20/2019 |  | 12/1/2021
PJM | AE1-160 | Venango 34.5 kV | Titusville Solar | PA | Venango | Withdrawn | PENELEC | 20 | 12.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/25/2018 | 4/2/2024 |  | 12/31/2024
PJM | AE1-161 | Landis 138 kV |  | NJ | Cumberland | Withdrawn | AEC | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 9/24/2018 | 8/7/2023 |  | 10/1/2021
PJM | AE1-162 | Smithfield 34.5 kV | Solidago Solar | VA | Isle of Wight | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 9/24/2018 |  |  | 12/31/2023 | 8/1/2023
PJM | AE1-163 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 350 | 49 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/24/2018 |  |  | 2/1/2027
PJM | AE1-164 | Old Chapel 138 kV |  | VA | Accomack | Withdrawn | APS | 40 | 24 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/24/2018 | 2/19/2019 |  | 12/30/2021
PJM | AE1-165 | Cambria Slope 115kV |  | PA | Cambria | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/24/2018 | 4/8/2019 |  | 12/30/2021
PJM | AE1-166 | Loretto-Wilton & Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 150 | 78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/24/2018 |  |  | 9/30/2020
PJM | AE1-167 | Wattsville 12 kV |  | VA | Accomack | Withdrawn | DPL | 11.09 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/25/2018 | 4/22/2020 |  | 6/25/2021
PJM | AE1-168 | Victoria-Martin 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/25/2018 | 1/8/2020 |  | 9/1/2021
PJM | AE1-169 | Titusville 115 kV |  | PA | Venango | Withdrawn | PENELEC | 85 | 51 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/25/2018 | 1/23/2020 |  | 7/1/2021
PJM | AE1-170 | Kenzie Creek-Colby 138 kV | Wingstem Solar Energy Farm | MI | Cass | Suspended | AEP | 150 | 63 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/25/2018 |  |  | 12/31/2025
PJM | AE1-171 | Reynolds-Olive 345 kV |  | IN | White | Withdrawn | AEP | 280 | 118 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/25/2018 | 10/1/2018 |  | 12/31/2022
PJM | AE1-172 - moved to TC1 | Loretto-Wilton Center |  | IL | Livingston | Active | ComEd | 255 | 44.88 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 9/25/2018 |  |  | 10/1/2021
PJM | AE1-173 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 800 | 480 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/25/2018 |  |  | 12/31/2021
PJM | AE1-174 | Light Foot 34.5 kV |  | VA | James City | Withdrawn | Dominion | 5 | 5 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 9/25/2018 | 6/16/2020 |  | 10/23/2020
PJM | AE1-175 | Light Foot 34.5 kV | Lightfoot 34.5 kV II | VA | James City | In Service | Dominion | 19.9 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/25/2018 |  |  | 11/15/2021 | 5/10/2022
PJM | AE1-176 | Roanoke-Vinton 12 kV (Niagara Hydro) | Niagara Power Plant Dam | VA | Roanoke | In Service | AEP | 2.4 | 2.4 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2018 |  |  | 6/1/2020 | 5/23/2020
PJM | AE1-177 | Louisa-South Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 19 | 19 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/25/2018 | 10/1/2018 |  | 10/31/2020
PJM | AE1-178 | Wolf Hills 138 kV | Wolf Hills Energy Plant | VA | Washington | In Service | AEP | 19 | 19 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2018 |  |  | 12/21/2021 | 5/25/2021
PJM | AE1-179 | South Millville-Newport 69 kV | Buckshutem Solar I | NJ | Cumberland | Engineering and Procurement | AEC | 59.7 | 35 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/25/2018 |  |  | 1/31/2027
PJM | AE1-180 | Mountain Run 115 kV |  | VA | Culpeper | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/25/2018 | 8/7/2019 |  | 9/30/2020
PJM | AE1-181 | St. Johns-Freeland 69 kV |  | PA | Luzerne | Withdrawn | PPL | 45 | 27 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/25/2018 | 11/1/2022 |  | 10/27/2020
PJM | AE1-182 | Newville-West Carlise 69 kV |  | PA | Cumberland | Withdrawn | PPL | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Withdrawn | 9/25/2018 | 8/14/2020
PJM | AE1-183 | Maysville-McDowell 69 kV | Jackson Center Solar Facility | PA | Mercer | Engineering and Procurement | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2018 |  |  | 10/18/2025
PJM | AE1-185 | Hokes-Jackson 69 kV | Cottontail Solar 1 | PA | York | In Service | ME | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2018 |  |  | 7/31/2024 | 8/12/2024
PJM | AE1-186 | Moselem-Lyons 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/26/2018 | 3/25/2019 |  | 4/1/2021
PJM | AE1-187 | North Lebanon- Cleona 69 kV |  | PA | Adams | Withdrawn | ME | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/26/2018 | 11/26/2019 |  | 4/1/2021
PJM | AE1-188 | Fayetteville 34.5 kV | Fayetteville Solar | PA | Franklin | Withdrawn | APS | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/26/2018 | 10/10/2023 |  | 3/1/2022
PJM | AE1-189 | Penville-Adams 138 kV |  | IN | Jay | Withdrawn | AEP | 245 | 103 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/26/2018 | 10/1/2018 |  | 12/31/2022
PJM | AE1-190 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Under Construction | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/28/2018 |  |  | 11/30/2025
PJM | AE1-191 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Under Construction | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/28/2018 |  |  | 11/30/2025
PJM | AE1-192 | Belle Haven-Tasley 69 kV |  | VA | Accomack | Withdrawn | ODEC | 70 | 47 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/26/2018 | 9/29/2020 |  | 11/30/2021
PJM | AE1-193 | Crete 345 kV |  | IL | Henry | Withdrawn | ComEd | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/26/2018 | 9/7/2023 |  | 9/1/2021
PJM | AE1-194 | Crete 345 kV |  | IL | Will | Withdrawn | ComEd | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/26/2018 | 9/7/2023 |  | 9/1/2021
PJM | AE1-195 | Crete 345 kV |  | IL | Will | Withdrawn | ComEd | 500 | 65 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/26/2018 | 9/7/2023 |  | 9/1/2021
PJM | AE1-196 | Hokes-Jackson 69 kV II | Cottontail Solar 8 | PA | York | In Service | ME | 20 | 12.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2018 |  |  | 12/31/2023 | 4/24/2024
PJM | AE1-197 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 65 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 9/26/2018 | 10/1/2018 |  | 9/1/2021
PJM | AE1-198 | Crete 345 kV |  | IL | McHenry | Withdrawn | ComEd | 357 | 193 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/26/2018 | 9/14/2022 |  | 9/1/2021
PJM | AE1-199 | Twombly Road 138 kV |  | IL | Ogle | Withdrawn | ComEd | 20 | 20 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/26/2018 | 8/14/2019 |  | 12/31/2019
PJM | AE1-200 | College Corner-Randolph 138 kV |  | IN | Randolph | Withdrawn | AEP | 235 | 99 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/26/2018 | 10/1/2018 |  | 12/31/2022
PJM | AE1-201 | Marengo 34 kV |  | IL | McHenry | Withdrawn | ComEd | 20 | 16.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/26/2018 | 8/14/2019 |  | 9/15/2019
PJM | AE1-202 | Effort Mountain 12.47 kV |  | PA | Monroe | Withdrawn | PPL | 19.8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Withdrawn | 9/26/2018 | 11/4/2019 |  | 9/30/2020
PJM | AE1-203 | Iliff 12.47 kV |  | NJ | Sussex | Withdrawn | JCPL | 4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/26/2018 | 9/30/2019 |  | 9/30/2019
PJM | AE1-204 | Waukegan 13 kV |  | IL | Lake | Withdrawn | ComEd | 4.4 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/26/2018 | 11/18/2019 |  | 9/30/2020
PJM | AE1-205 | McLean 345 kV | Blooming Grove Solar Energy Center | IL | Livingston | Active | ComEd | 200 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/26/2018 |  |  | 12/29/2028
PJM | AE1-206 | Four Rivers-Hanover 230 kV |  | VA | Hanover | Withdrawn | Dominion | 285 | 171 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/26/2018 | 9/12/2023 |  | 12/31/2022
PJM | AE1-207 | Mississinewa-Gaston 138 kV | Golden Aster Solar Energy Center | IN | Grant | Suspended | AEP | 160 | 67.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2018 |  |  | 5/31/2026
PJM | AE1-208 | Delaware-Van Buren 138 kV | Meadow Forge Solar Energy Center | IN | Delaware | Suspended | AEP | 130 | 55 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2018 |  |  | 11/30/2026
PJM | AE1-209 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Engineering and Procurement | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2018 |  |  | 5/31/2026
PJM | AE1-210 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Engineering and Procurement | AEP | 100 | 13 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2018 |  |  | 5/31/2026
PJM | AE1-211 | Reynolds 345 kV |  | IN | Jasper | Withdrawn | AEP | 302.4 | 40 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 9/27/2018 | 10/1/2018 |  | 10/31/2020
PJM | AE1-212 | Grandview-Clifftop 138 kV | Raleigh Solar Project | WV | Raliegh | Under Construction | AEP | 90 | 53.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/10/2018 |  |  | 6/25/2025
PJM | AE1-213 | Highland-Lordstown 1 & 2 345 kV |  | OH | Trumbull | Withdrawn | ATSI | 1170 | 1025 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 9/26/2018 | 10/1/2018 |  | 11/1/2023
PJM | AE1-214 | Rockport 765 kV |  | IN | Spencer | Withdrawn | AEP | 800 | 625 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/27/2018 | 10/2/2018 |  | 12/1/2023
PJM | AE1-215 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 395 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/27/2018 | 10/1/2018 |  | 12/1/2023
PJM | AE1-216 | Reynolds 345 kV |  | IN | White | Withdrawn | AEP | 500 | 395 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/27/2018 | 10/2/2018 |  | 12/1/2023
PJM | AE1-217 | Gaston 138kV |  | IN | Delaware | Withdrawn | AEP | 200 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/27/2018 | 1/30/2020 |  | 12/31/2022
PJM | AE1-218 | Glassboro 12 kV | Glassboro LF Solar | NJ | Gloucester | Under Construction | AEC | 2 | 0.82 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2018 |  |  | 7/31/2024
PJM | AE1-219 | Glassboro 12 kV II | Glassboro RE Solar | NJ | Gloucester | Withdrawn | AEC | 4.4 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/27/2018 | 8/17/2020 |  | 7/17/2022
PJM | AE1-220 | Coleen-Clifford 138 kV |  | VA | Nelson | Withdrawn | AEP | 100 | 66.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/24/2018 | 6/17/2019 |  | 6/1/2022
PJM | AE1-221 | North Wales 34.5 kV | West Point Cogeneration Facility | PA | Montgomery | In Service | PECO | 0 | 14 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/28/2018 |  |  | 6/1/2022 | 4/21/2020
PJM | AE1-222 | Dresden Tazewell Mole Creek |  | IL | Grundy | Withdrawn | ComEd | 2562.7 | 1270 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 9/28/2018 | 8/7/2019 |  | 6/1/2022
PJM | AE1-223 | Allentown Booster 138 kV |  | NJ | Burlington | Withdrawn | PSEG | 1.86 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/28/2018 | 6/3/2019 |  | 11/16/2018
PJM | AE1-224 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/24/2018 | 9/30/2018 |  | 9/30/2020
PJM | AE1-225 | Columbia-Sunbury 69 kV | Sunbury Solar | PA | Snyder | Suspended | PPL | 19.8 | 9.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2018 |  |  | 6/30/2027
PJM | AE1-226 | Face Rock-Kinzer #13 69 kV | Holtwood Solar | PA | Lancaster | Suspended | PPL | 19.8 | 9.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2018 |  |  | 4/1/2026
PJM | AE1-227 | South Cumberland 69 kV | Recreation Solar | OH | Guernsey | Suspended | AEP | 49.5 | 30.69 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2018 |  |  | 12/15/2025
PJM | AE1-228 | Steward 138 kV |  | IL | Lee | Withdrawn | ComEd | 140 | 84 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2018 | 8/12/2019 |  | 6/1/2021
PJM | AE1-229 | Deepwater-Upper Pittsgrove 138 kV | Pilesgrove Solar Project | NJ | Salem | Engineering and Procurement | AEC | 149.3 | 89 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/18/2018 |  |  | 12/31/2026
PJM | AE1-230 | Shockoe 69 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 7.2 | Capacity | Generation Interconnection | Storage; Solar | Document Posted | Document Posted | Withdrawn |  | 9/28/2018 | 9/1/2021 |  | 7/31/2020
PJM | AE1-231 | Hughesville 69 kV |  | MD | Charles | Withdrawn | SMECO | 20 | 9.4 | Capacity | Generation Interconnection | Storage; Solar | Document Posted | Document Posted | Withdrawn |  | 9/28/2018 | 9/3/2021 |  | 7/31/2020
PJM | AE1-232 | Harrowgate-Locks 115 kV |  | VA | Chesterfield | Withdrawn | Dominion | 120 | 72 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/28/2018 | 10/1/2018 |  | 12/31/2021
PJM | AE1-233 | West Dekalb 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 97.5 | 24.3 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 9/28/2018 | 1/3/2019 |  | 12/31/2021
PJM | AE1-235 | Carson-Clover 500 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 180 | 76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/28/2018 | 10/1/2018 |  | 12/31/2022
PJM | AE1-236 | Corson-Septa 500 kV |  | NC | Edgecombe | Withdrawn | Dominion | 290 | 122 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/28/2018 | 10/1/2018 |  | 12/31/2022
PJM | AE1-237 | Andover (Maysville) 69kV I | Welcome Solar II | PA | Crawford | Engineering and Procurement | ATSI | 19.9 | 13.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2018 |  |  | 6/5/2024
PJM | AE1-238 | Oceanview Wind 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 816 | 225 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 9/28/2018 | 8/28/2023 |  | 6/1/2024
PJM | AE1-239 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 38.2 | 22.92 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2018 | 3/28/2019 |  | 12/31/2021
PJM | AE1-240 | Carlls Corner-Sherman Avenue 69 kV | Nabb Solar Project | NJ | Cumberland | Suspended | AEC | 49.7 | 29 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2018 |  |  | 10/15/2024
PJM | AE1-241 | Wilmington-Davis Creek |  | IL | Will | Withdrawn | ComEd | 250 | 150 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/28/2018 | 10/1/2018 |  | 5/31/2021
PJM | AE1-242 | Kincaid-Pana |  | IL | Christian | Withdrawn | ComEd | 150 | 63 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/28/2018 | 10/5/2018 |  | 12/31/2022
PJM | AE1-243 | Warren Glen Storage 34.5 kV | Warren Glen Storage | NJ | Warren | Under Construction | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2018 |  |  | 12/31/2024
PJM | AE1-244 | Gilbert Storage 34.5 kV |  | NJ | Atlantic | Withdrawn | JCPL | 19.8 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/28/2018 | 12/19/2019 |  | 9/30/2020
PJM | AE1-245 | Haviland 138 kV | Grover Hill Wind Project | OH | Paulding | Engineering and Procurement | AEP | 140.3 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/18/2018 |  |  | 2/5/2026
PJM | AE1-246 | Barren County-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 85 | 57.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/24/2018 | 1/21/2025 |  | 6/1/2022
PJM | AE1-247 | Barren County-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 205 | 137.1 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/24/2018 | 2/11/2020 |  | 6/1/2022
PJM | AE1-248 | Bell Avenue 115 kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 8/31/2018 | 4/22/2021 |  | 9/30/2021
PJM | AE1-249 | Reams 115 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 70 | 40.1 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/25/2018 | 1/10/2020 |  | 12/31/2021
PJM | AE1-250 | Smith Mountain-E. Danville 138 kV | Blue Ridge Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2018 |  |  | 1/21/2028
PJM | AE1-251 | Penn-Lees Lick 69 kV |  | KY | Scott | Withdrawn | EKPC | 120 | 72 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/14/2018 | 3/27/2019 |  | 9/30/2021
PJM | AE1-252 | Loretto-Wilton Center |  | IL | Livingston | Withdrawn | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/18/2018 | 9/12/2023 |  | 10/1/2021
PJM | AE2-001 | Nittany-Zion 46 kV | Confer Solar I | PA | Centre | Suspended | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/2/2018 |  |  | 5/30/2026
PJM | AE2-002 | 64th Street 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 3.6 | 3.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/3/2018 | 9/6/2019 |  | 12/31/2019
PJM | AE2-003 | Walker Mill Road 13 kV |  | MD | Prince George's | Withdrawn | DPL | 3 | 1.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/3/2018 | 9/6/2019 |  | 10/1/2019
PJM | AE2-004 | Poolesville 230 kV |  | VA | Surry | Withdrawn | Dominion | 60 | 40.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/4/2018 | 11/28/2018 |  | 6/30/2021
PJM | AE2-005 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 10/5/2018 |  |  | 12/31/2023
PJM | AE2-006 | Twittys Creek 34.5 kV | Twittys Creek Solar | VA | Charlotte | In Service | Dominion | 0 | 2.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/8/2018 |  |  | 12/31/2020 | 12/8/2020
PJM | AE2-007 | Chesapeake 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 967.6 | 967.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 10/10/2018 | 12/11/2020 |  | 6/1/2022
PJM | AE2-008 | Elderberry-Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 80 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/15/2018 | 1/30/2020 |  | 12/31/2022
PJM | AE2-010 | Paper Tap 69 kV | Jericho | PA | Delaware | In Service | PECO | 29 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 10/30/2018 |  |  | 12/31/2020 | 8/12/2020
PJM | AE2-011 | Tansboro 12 kV |  | NJ | Camden | Withdrawn | AEC | 3.1 | 1.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 11/7/2018 | 8/12/2019 |  | 11/30/2020
PJM | AE2-012 | Red Oak-South River 230 kV |  | NJ | Middlesex | Withdrawn | JCPL | 570 | 540 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 11/9/2018 | 3/29/2019 |  | 6/1/2023
PJM | AE2-013 | Highland-Lordstown 345 kV |  | OH | Trumbull | Withdrawn | ATSI | 1170 | 1025 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 11/12/2018 | 8/27/2019 |  | 11/1/2023
PJM | AE2-015 | Cookstown-New Lisbon 34.5 kV |  | NJ | Burlington | Withdrawn | JCPL | 5 | 3.35 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 11/26/2018 | 8/15/2019 |  | 6/30/2020
PJM | AE2-016 | Bustleton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.5 | 2.35 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/26/2018 | 5/15/2019 |  | 6/30/2020
PJM | AE2-017 | Lexington Park 69 kV | Whitetail VI | MD | St. Mary's | Withdrawn | SMECO | 20 | 10.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 11/28/2018 | 3/16/2021 |  | 3/31/2023
PJM | AE2-018 | Laurence 13.2 kV |  | NJ | Mercer | Withdrawn | PSEG | 3.5 | 2.3333 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 12/10/2018 | 8/15/2019 |  | 6/30/2020
PJM | AE2-019 | New Road 230 kV | New Road Storage | VA | Loudoun | Engineering and Procurement | Dominion | 120 | 120 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 12/12/2018 |  |  | 12/31/2026
PJM | AE2-020 | Cardiff 230 kV I | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 604.8 | 106.44 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/16/2018 |  |  | 8/31/2029
PJM | AE2-021 | Cardiff 230 kV II | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 604.8 | 106.44 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/15/2018 |  |  | 8/31/2029
PJM | AE2-022 | Cardiff 230 kV III | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 300 | 52.8 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 12/15/2018 |  |  | 8/31/2029
PJM | AE2-023 | BL England 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 445.2 | 78.36 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted |  |  | 12/14/2018 | 4/15/2020 |  | 12/1/2024
PJM | AE2-024 | Larrabee 230 kV I |  | NJ | Ocean | Withdrawn | JCPL | 882 | 155.23 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Withdrawn | 12/14/2018 | 9/1/2023 |  | 12/1/2025
PJM | AE2-025 | Larrabee 230 kV II |  | NJ | Ocean | Withdrawn | JCPL | 445.2 | 78.36 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 12/14/2018 | 9/12/2023 |  | 12/1/2026
PJM | AE2-026 | Louisa-South Anna 230kV |  | VA | Louisa | Withdrawn | Dominion | 44.8 | 19 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 12/19/2018 | 8/14/2019 |  | 10/30/2020
PJM | AE2-027 | Harrowgate-Locks 115kV | Chester Solar | VA | Chesterfield | Suspended | Dominion | 120 | 72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/20/2018 |  |  | 6/30/2025
PJM | AE2-028 | Broadway 12.47 kV | State Route 57 Solar | NJ | Warren | Withdrawn | JCPL | 0.75 | 0.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/24/2018 | 6/7/2023 |  | 6/15/2021
PJM | AE2-029 | Grottoes-Merck 115kV | Stonewall Solar | VA | Rockingham | Engineering and Procurement | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 12/29/2018 |  |  | 3/14/2026
PJM | AE2-030 | Frostburg 138kV |  | MD | Allegany | Withdrawn | APS | 18 | 7.56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 12/31/2018 | 3/7/2023 |  | 8/24/2020
PJM | AE2-031 | Carson-Rawlings 500 kV |  | VA | Sussex | Withdrawn | Dominion | 290 | 174 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/7/2019 | 5/23/2022 |  | 12/31/2021
PJM | AE2-033 | Clubhouse-Sapony 230 kV | Enclave Solar Energy Center | VA | Sussex | Suspended | Dominion | 149 | 89 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/8/2019 |  |  | 2/4/2027
PJM | AE2-034 | Mackeys 230 kV | Albemarle Beach Solar | NC | Washington | Partially in Service - Under Construction | Dominion | 60 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 1/16/2019 |  |  | 12/31/2026
PJM | AE2-035 | Lena 138 kV | High Point II Solar | IL | Stephenson | In Service | ComEd | 50 | 21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/16/2019 |  |  | 2/28/2024 | 11/30/2023
PJM | AE2-036 | Masury-Maysville 138 kV |  | PA | Mercer | Withdrawn | ATSI | 19.9 | 13.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 1/17/2019 | 8/12/2019 |  | 6/1/2019
PJM | AE2-037 | Earleys-Everetts 230 kV |  | NC | Bertie | Withdrawn | Dominion | 71.5 | 48.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/18/2019 | 4/13/2020 |  | 9/17/2021
PJM | AE2-038 - moved to TC1 | Goddard-Plumsville 138 kV II |  | KY | Fleming | Withdrawn | EKPC | 80 | 53.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/23/2019 | 8/2/2024 |  | 6/1/2022
PJM | AE2-039 | Clayton-Williamstown 69 kV |  | NJ | Gloucester | Withdrawn | AEC | 44 | 28.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/22/2019 | 2/20/2019 |  | 6/30/2022
PJM | AE2-040 | Sapony 34.5 kV | Shands Energy Center | VA | Sussex | Suspended | Dominion | 15.7 | 15.7 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/23/2019 |  |  | 12/31/2024
PJM | AE2-041 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Suspended | Dominion | 40 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 1/24/2019 |  |  | 3/1/2026
PJM | AE2-042 | Milton 69 kV | Northumberland Solar | PA | Northumberland | Suspended | PPL | 65 | 43.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/25/2019 |  |  | 11/4/2026
PJM | AE2-043 | Franklinville 138 kV |  | NJ | Gloucester | Withdrawn | AEC | 4 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/23/2019 | 4/1/2019 |  | 5/1/2020
PJM | AE2-044 | Anaconda-Dunbar 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 40 | 28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/29/2019 | 4/23/2024 |  | 12/31/2019
PJM | AE2-045 | Olive-Reynolds 345 kV | Bottlebrush Solar | IN | Lake | Engineering and Procurement | AEP | 200 | 84.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/29/2019 |  |  | 3/31/2028
PJM | AE2-046 | Harwood-East Hazelton 69 kV | McAdoo Solar | PA | Schuylkill | Withdrawn | PPL | 50 | 24 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 2/2/2019 | 10/21/2024 |  | 3/16/2025
PJM | AE2-047 | Ridgeway-Solite 69 kV | Henry County Solar Facility | VA | Henry | Engineering and Procurement | AEP | 50 | 32.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2019 |  |  | 12/31/2026
PJM | AE2-048 | Muskingum-W. Millersport 345 kV | Eastern Cottontail Solar | OH | Fairfield | Engineering and Procurement | AEP | 220 | 147.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2019 |  |  | 12/31/2028
PJM | AE2-049 | Wilmington-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 115 | 46 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 1/31/2019 | 2/7/2020 |  | 5/31/2021
PJM | AE2-050 | Braidwood-E. Frankfort |  | IL | Will | Withdrawn | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 1/31/2019 | 2/7/2020 |  | 5/31/2021
PJM | AE2-051 | Carson-Septa 500 kV | Big Pine Solar | VA | Sussex | Engineering and Procurement | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/1/2019 |  |  | 8/1/2031
PJM | AE2-052 | Disputanta-Poe 115 kV |  | VA | Prince George | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 1/31/2019 | 5/31/2024 |  | 9/15/2021
PJM | AE2-053 - moved to TC1 | Kerr Dam-Ridge Road 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 2/1/2019 | 6/24/2024 |  | 9/15/2021
PJM | AE2-054 | Warfordsburg 34 kV | Blairs Valley | PA | Franklin | Partially in Service - Under Construction | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/2/2019 |  |  | 11/30/2024
PJM | AE2-055 | Shingletown-Boalsburg 46 kV | Windmill Road | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2019 | 8/27/2024 |  | 12/31/2023
PJM | AE2-056 | Howell 12.47 kV Solar I | Willow Brook Road Solar I | NJ | Monmouth | Withdrawn | JCPL | 3 | 1.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2019 | 8/8/2022 |  | 5/1/2022
PJM | AE2-057 | Jerseyville 12.47 kV Solar | Willow Brook Road Solar II | NJ | Monmouth | Withdrawn | JCPL | 1 | 0.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2019 | 3/11/2021 |  | 5/1/2022
PJM | AE2-058 | Cherokee-Milton 69 kV |  | PA | Northumberland | Withdrawn | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/1/2019 | 9/4/2019 |  | 3/5/2021
PJM | AE2-059 | Derry Tap-Derry Bus 69 kV | Cottontail Solar 4 aka East Chilli Solar | PA | Northumberland | In Service | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/7/2019 |  |  | 5/31/2024 | 8/20/2024
PJM | AE2-060 | Mifflintown Bus-Mifflintown Tap 69 kV | Cottontail Solar 5 aka Walker Solar | PA | Juniata | In Service | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/7/2019 |  |  | 12/1/2023 | 12/12/2023
PJM | AE2-061 | Rock Springs 500 kV | Rock Springs Unit #1 and Unit #2 | MD | Cecil | In Service | Essential Power | 0 | 7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 2/4/2019 |  |  | 8/23/2019 | 8/12/2019
PJM | AE2-062 | Romeoville 12 kV | Magid Glove & Safety Mfg. Co | IL | Will | In Service | ComEd | 0.98 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/5/2019 |  |  | 3/31/2021 | 4/8/2021
PJM | AE2-063 | Normantown |  | IL | Will | Withdrawn | ComEd | 0.98 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 2/5/2019 | 1/14/2020 |  | 9/2/2019
PJM | AE2-064 | Beaverbrook 13 kV | Kinsley 2 Beaverbrook Solar | NJ | Gloucester | Partially in Service - Under Construction | PSEG | 2 | 0.85 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 2/7/2019 |  |  | 8/31/2020
PJM | AE2-065 | Romeoville 12 kV | Kinsley 2 Deptford Solar | NJ | Gloucester | In Service | PSEG | 1.8 | 0.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 2/6/2019 |  |  | 8/31/2020 | 9/19/2020
PJM | AE2-066 | Gloucester 13 kV |  | NJ | Gloucester | Withdrawn | PSEG | 4.5 | 1.89 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/6/2019 | 5/15/2019 |  | 12/10/2019
PJM | AE2-067 | N. Meshoppen 34 kV |  | PA | Wyoming | Withdrawn | PENELEC | 20 | 19.9 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 2/12/2019 | 9/4/2019 |  | 1/1/2021
PJM | AE2-068 | Second Street12 kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/12/2019 | 4/30/2019 |  | 6/1/2020
PJM | AE2-069 | Burlington 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 5 | 1.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/12/2019 | 4/10/2019 |  | 6/1/2020
PJM | AE2-070 | White Rock 34 kV |  | MD | Howard | Withdrawn | BGE | 4 | 1.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required |  | 2/13/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-071 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | In Service | EKPC | 35 | 21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/19/2019 |  |  | 4/30/2024 | 6/7/2024
PJM | AE2-072 | East Leipsic-Richland 138 kV | Powell Creek Solar | OH | Putnam | Under Construction | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/15/2019 |  |  | 6/2/2025
PJM | AE2-073 | Centerburg 138kV |  | OH | Licking | Withdrawn | AEP | 50 | 21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/15/2019 | 10/2/2024 |  | 11/1/2021
PJM | AE2-074 | Potter 46 kV | Potter Solar | PA | Potter | Engineering and Procurement | APS | 35 | 15.11 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/20/2019 |  |  | 7/31/2026
PJM | AE2-075 | Second Street 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.4 | 2.64 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/19/2019 | 4/30/2019 |  | 6/1/2020
PJM | AE2-076 | Southampton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2 | 0.84 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/19/2019 | 4/10/2019 |  | 6/1/2020
PJM | AE2-077 | Pierpoint-Freeport |  | IL | Winnebago | Withdrawn | ComEd | 70 | 26.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/21/2019 | 9/3/2019 |  | 12/31/2021
PJM | AE2-078 | Poolesville 34.5 kV | Mantura | VA | Surry | Withdrawn | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/21/2019 | 6/6/2022 |  | 6/1/2022
PJM | AE2-079 | Poolesville 34.5 kV | Mantura II | VA | Surry | Withdrawn | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/21/2019 | 4/22/2022 |  | 6/1/2022
PJM | AE2-080 | Poolesville 34.5 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/21/2019 | 4/28/2020 |  | 6/18/2021
PJM | AE2-081 | Howell 12.47 kV Solar II | Casino Drive Solar | NJ | Monmouth | Withdrawn | JCPL | 3.2 | 1.57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/31/2019 | 8/8/2022 |  | 5/1/2022
PJM | AE2-082 | Englishtown-Wyckoff 34.5 kV Solar |  | NJ | Monmouth | Withdrawn | JCPL | 7 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Withdrawn | 1/31/2019 | 7/13/2021 |  | 9/30/2019
PJM | AE2-083 | Forrester Solar 34.5 kV |  | NJ | Mercer | Withdrawn | JCPL | 1.625 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/22/2019 | 3/5/2019 |  | 3/2/2020
PJM | AE2-084 | Derry Tap-Derry Bus 69 kV | Cottontail Solar 3 | PA | Montour | Suspended | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/3/2019 |  |  | 4/1/2026
PJM | AE2-085 | Southampton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 5.04 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 2/22/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-086 | Reeder Road Solar 12.47 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/22/2019 | 4/3/2019 |  | 3/2/2020
PJM | AE2-087 | Carlls Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.54 | 1.47 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 2/22/2019 | 8/22/2019 |  | 3/2/2020
PJM | AE2-088 | Clayton 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 2.53 | 0.735 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 2/22/2019 | 8/22/2019 |  | 3/2/2020
PJM | AE2-089 | Pennville-Adams 138 kV | Skycrest Solar Energy Center | IN | Jay | Engineering and Procurement | AEP | 155 | 93 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/22/2019 |  |  | 12/31/2026
PJM | AE2-090 | Randolph-Hodgin 138 kV |  | IN | Randolph | Withdrawn | AEP | 144 | 86.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/22/2019 | 10/15/2020 |  | 12/31/2022
PJM | AE2-091 | Newport 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 35 | 23 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/24/2019 | 3/31/2020 |  | 6/30/2022
PJM | AE2-092 | Kidds Store-Sherwood 115 kV | Woodridge Solar | VA | Albemarle | Engineering and Procurement | Dominion | 138 | 82.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2019 |  |  | 6/30/2027
PJM | AE2-093 | Easton-Steele 138 kV | Crockett Solar Project | MD | Talbot | Suspended | DPL | 44 | 16.72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2019 |  |  | 3/31/2026
PJM | AE2-094 | Carson-Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 300 | 207.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 2/26/2019 |  |  | 8/1/2031
PJM | AE2-095 | Hopewell 26 kV |  | NJ | Mercer | Withdrawn | PSEG | 2.145 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 2/28/2019 | 4/4/2019 |  | 3/2/2020
PJM | AE2-096 | East Flemington-Frenchtown Solar 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 2.75 | 1.16 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/28/2019 | 9/4/2019 |  | 3/2/2020
PJM | AE2-097 | Levittown 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/28/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-098 | Belvidere Solar 12 kV |  | NJ | Warren | Withdrawn | JCPL | 1.875 | 0.79 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2019 | 4/3/2019 |  | 3/2/2020
PJM | AE2-099 | Burlington 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 2.77 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 2/28/2019 | 4/4/2019 |  | 3/2/2020
PJM | AE2-100 | Carlstadt 13.2 kV |  | NJ | Bergen | Withdrawn | PSEG | 2.3 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/28/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-101 | Nortonville 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/28/2019 | 8/21/2019 |  | 3/2/2020
PJM | AE2-102 | Columbus 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 5.04 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 2/28/2019 | 4/4/2019 |  | 3/2/2020
PJM | AE2-103 | Cookstown-Van Hiseville Solar 34.5 kV |  | NJ | Ocean | Withdrawn | JCPL | 3 | 1.26 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2019 | 5/23/2019 |  | 3/2/2020
PJM | AE2-104 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Suspended | Dominion | 49 | 18.92 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/2/2019 |  |  | 10/31/2025
PJM | AE2-105 | Kittatinny-Newton Solar 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 3.5 | 1.47 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/28/2019 | 9/6/2019 |  | 3/2/2020
PJM | AE2-106 | Carlls Corner 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 4.915 | 1.63 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 2/28/2019 | 8/22/2019 |  | 3/2/2020
PJM | AE2-107 - moved to TC1 | Haumesser Road 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 90 | 54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/28/2019 | 6/21/2024 |  | 12/31/2022
PJM | AE2-108 | Kings Dominion DP 115 kV |  | VA | Hanover | Withdrawn | Dominion | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/28/2019 | 4/8/2020 |  | 3/31/2020
PJM | AE2-109 | Kings Dominion DP 115 kV |  | VA | Hanover | Withdrawn | Dominion | 7 | 2.94 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 2/28/2019 | 4/8/2020 |  | 3/31/2021
PJM | AE2-110 | Columbia-West Bloomsburg 69 kV | Montour 1 | PA | Columbia | Suspended | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/3/2019 |  |  | 2/28/2025
PJM | AE2-111 | Beavertown Tap-Beavertown Weaving Tap 69kV | Thomas Ridge Solar | PA | Snyder | Withdrawn | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/1/2019 | 1/18/2023 |  | 12/31/2024
PJM | AE2-112 | Carville 138 kV II | Concho Solar I | MD | Queen Anne's | Suspended | DPL | 17 | 6.46 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2019 |  |  | 6/3/2027
PJM | AE2-113 | Farmers Valley-Ridgeway 115 kV | Ridgeway Solar | PA | McKean | Engineering and Procurement | PENELEC | 120 | 61.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/1/2019 |  |  | 6/30/2025
PJM | AE2-114 | Midland 23 kV I | BE-PINE 1 Cain Road | PA | Beaver | In Service | DL | 17.1 | 10.26 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/1/2019 |  |  | 12/31/2023 | 11/20/2023
PJM | AE2-115 | Midland 23 kV II | BE-PINE 2 Dam Road | PA | Beaver | In Service | DL | 17.1 | 10.26 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/1/2019 |  |  | 12/31/2023 | 11/5/2023
PJM | AE2-116 | Midland 23 kV III |  | PA | Adams | Withdrawn | DL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/28/2019 | 12/3/2019 |  | 9/1/2021
PJM | AE2-117 | ABW Tap-Alexandria 46 kV | HU-Pauls | PA | Huntingdon | Under Construction | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/1/2019 |  |  | 3/1/2027
PJM | AE2-118 | ABW Tap-Williamsburg 46 kV | HU-Logging | PA | Huntingdon | Suspended | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/28/2019 |  |  | 8/31/2024
PJM | AE2-119 | Shawville-Phillipsburg 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 2/28/2019 | 12/16/2019 |  | 9/1/2021
PJM | AE2-120 | Graymont-Zion 46 kV | CE-Shady Farm LLC | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/1/2019 | 6/7/2023 |  | 12/30/2025
PJM | AE2-121 | Milesburg-Tanney Junction 46 kV | CE-JACKSONVILLE | PA | Centre | Withdrawn | APS | 10.64 | 6.384 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/1/2019 | 7/22/2024 |  | 12/31/2023
PJM | AE2-122 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 800.1 | 158.9 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | In Progress |  | 2/28/2019 |  |  | 12/31/2025
PJM | AE2-123 - moved to TC1 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 163.3 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 2/28/2019 | 6/24/2024 |  | 12/31/2027
PJM | AE2-124 - moved to TC1 | Landstown 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 800.1 | 148.5 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 2/28/2019 | 6/24/2024 |  | 12/31/2029
PJM | AE2-125 | Stahlstown-Ligonier 25 kV | Stahlstown-Ligonier 25 kV | PA | Westmoreland | In Service | APS | 13.8 | 8.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/2/2019 |  |  | 11/15/2024 | 12/4/2024
PJM | AE2-126 | Dubois-Curwensville 34.5 kV | CL-Viaduct | PA | Clearfield | In Service | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/1/2019 |  |  | 5/31/2023 | 3/23/2023
PJM | AE2-127 | Milesburg-Moshannon 230 kV |  | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2019 | 4/12/2019 |  | 11/1/2021
PJM | AE2-128 | Milesburg-Moshannon 230 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2019 | 4/12/2019 |  | 10/1/2021
PJM | AE2-129 | Philipsburg-Clarence 34.5 kV | Philipsburg-Clarence 34.5 kV | PA | Clearfield | In Service | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/1/2019 |  |  | 11/1/2022 | 1/28/2023
PJM | AE2-130 - moved to TC1 | Rockport 765 kV |  | IN | Spencer | Withdrawn | AEP | 800 | 480 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 2/28/2019 | 6/21/2024 |  | 12/1/2022
PJM | AE2-131 | Philipsburg-Karthaus 34.5 | UN-Kylertown | PA | Westmoreland | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 2/28/2019 |  |  | 10/16/2025
PJM | AE2-132 | Remington CT 230 kV | Remington GT3 | VA | Fauquier | In Service | Dominion | 0 | 17.7 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/1/2019 |  |  | 5/31/2020 | 10/17/2019
PJM | AE2-133 | Penns Tap-Richfield Tie 69 kV | Penn Solar (Cottontail 6) | PA | Snyder | In Service | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/6/2019 |  |  | 12/1/2023 | 5/8/2024
PJM | AE2-134 | Locust Grove-Paytes 115 kV | Pine Glade Solar | VA | Orange | In Service | Dominion | 0 | 16.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/6/2019 |  |  | 7/15/2024 | 9/13/2024
PJM | AE2-135 | Frackville-Siegfried 230 kV |  | PA | Schuylkill | Withdrawn | PPL | 500 | 250 | Capacity | Generation Interconnection | Hydro | Withdrawn |  |  |  | 3/5/2019 | 4/5/2019 |  | 12/15/2022
PJM | AE2-136 | Muskingum River-W. Millersport 345 kV | Appalachian Cottontail Solar | OH | Fairfield | Engineering and Procurement | AEP | 114 | 83.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/6/2019 |  |  | 12/31/2028
PJM | AE2-137 | Yukon-Robbins 138 kV II | Allegheny Energy Center LLC | PA | Westmoreland | Withdrawn | APS | 84 | 87 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/7/2019 | 10/17/2023 |  | 9/1/2027
PJM | AE2-138 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 260 | 20.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/8/2019 |  |  | 6/1/2022
PJM | AE2-139 | East Towanda-Grover 230 kV | Bradford Solar | PA | McKean | Engineering and Procurement | PENELEC | 100.5 | 60.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/9/2019 |  |  | 12/15/2026
PJM | AE2-140 | Axton-Danville 138 kV | Axton Solar | VA | Henry | Suspended | AEP | 201.1 | 120.66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/11/2019 |  |  | 12/31/2025
PJM | AE2-141 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/11/2019 | 9/4/2019 |  | 6/1/2021
PJM | AE2-142 | Glen Gardner-Washington Solar 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/11/2019 | 9/6/2019 |  | 3/2/2020
PJM | AE2-143 | Yardville 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.905 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 3/11/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-144 | Deptford 13.2 kV |  | NJ | Gloucester | Withdrawn | PSEG | 4.03 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 3/11/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-145 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 2.52 | 0.84 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/11/2019 | 4/3/2019 |  | 3/2/2020
PJM | AE2-146 | Gold 115 kV |  | PA | Potter | Withdrawn | PENELEC | 183 | 75.95 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/11/2019 | 9/4/2019 |  | 3/5/2021
PJM | AE2-147 - moved to TC1 | Swamp 230 kV |  | NC | Perquimans | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/13/2019 |  |  | 12/1/2022
PJM | AE2-148 | Beatty-Greene 345 kV | Fox Squirrel Solar | OH | Madison | In Service | AEP | 577 | 397.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/22/2019 |  |  | 11/1/2023 | 11/1/2024
PJM | AE2-149 | Biers Run-Bixby 345 kV |  | OH | Pickaway | Withdrawn | AEP | 400 | 291.4 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 3/14/2019 | 2/14/2023 |  | 6/1/2022
PJM | AE2-150 | Bakers Pond-Bell Ave 115 kV |  | VA | Sussex | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage; Solar | Document Posted | Document Posted | Withdrawn |  | 3/14/2019 | 8/31/2022 |  | 6/1/2022
PJM | AE2-151 | Earleys 34.5kV | Kruger Energy Hertford | NC | Hertford | Withdrawn | Dominion | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/14/2019 | 1/8/2021 |  | 12/8/2020
PJM | AE2-152 | Loretto-Wilton & Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/4/2019 |  |  | 9/30/2020
PJM | AE2-153 | Braidwood-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 200 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/14/2019 | 9/12/2023 |  | 3/31/2021
PJM | AE2-154 | Meadow Lake 345 kV (MLV VIII) |  | IN | White | Withdrawn | AEP | 250 | 32.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/14/2019 | 6/29/2023 |  | 10/31/2021
PJM | AE2-155 | Old Church 34.5 kV | Hanover Solar | VA | Hanover | In Service | Dominion | 5 | 3.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/15/2019 |  |  | 12/1/2020 | 9/23/2020
PJM | AE2-156 - moved to TC1 | Yadkin 115 kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/15/2019 |  |  | 12/1/2021
PJM | AE2-157 | Wakefield–Waverly 115 kV |  | VA | Sussex | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/15/2019 | 3/9/2020 |  | 12/31/2021
PJM | AE2-159 | Kanawha River 138 kV |  | WV | Fayette | Withdrawn | AEP | 48 | 0 | Energy | Generation Interconnection | Hydro | Document Posted |  |  |  | 3/15/2019 | 11/21/2019 |  | 10/1/2021
PJM | AE2-160 | Kanawha River 138 kV |  | WV | Fayette | Active | AEP | 51 | 30 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | In Progress |  | 3/15/2019 |  |  | 10/1/2021
PJM | AE2-161 | Morris Park-Washington 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/15/2019 | 4/2/2019 |  | 3/2/2020
PJM | AE2-162 | Lumberton 13.2 kV |  | NJ | Burlington | Withdrawn | PSEG | 3.78 | 1.26 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/15/2019 | 5/6/2019 |  | 3/2/2020
PJM | AE2-163 | West Caldwell 13.2 kV |  | NJ | Essex | Withdrawn | PSEG | 1 | 0.42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/15/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-164 | Saddle Brook 13.2 kV |  | NJ | Bergen | Withdrawn | PSEG | 1.4 | 0.588 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/15/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-165 | Cedar Grove 13.2 kV |  | NJ | Passaic | Withdrawn | PSEG | 2.6 | 1.092 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/15/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-166 | Stockton 138 kV | Rocky Ford Solar Energy Center | VA | Henry | Engineering and Procurement | AEP | 90 | 54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/16/2019 |  |  | 12/31/2026
PJM | AE2-167 | Belmont-Harrison 500 kV |  | WV | Doddridge | Withdrawn | APS | 1335 | 1315 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 3/15/2019 | 9/6/2019 |  | 7/1/2023
PJM | AE2-168 | Belmont-Harrison 500 kV II |  | WV | Doddridge | Withdrawn | APS | 665 | 660 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 3/15/2019 | 9/6/2019 |  | 7/1/2023
PJM | AE2-169 | Delaware-Van Buren 138 kV | Meadow Forge Solar Energy Center | IN | Delaware | Suspended | AEP | 33 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/16/2019 |  |  | 11/30/2026
PJM | AE2-170 | Gaston-Desoto 138 kV |  | IN | Delaware | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 3/15/2019 | 1/30/2020 |  | 12/31/2022
PJM | AE2-171 | Makahoy 138 kV |  | IN | Madison | Withdrawn | AEP | 30 | 30 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 3/15/2019 | 3/24/2021 |  | 12/31/2022
PJM | AE2-172 | Mississinewa-Gaston 138 kV | Golden Aster Solar Energy Center | IN | Grant | Suspended | AEP | 40 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/16/2019 |  |  | 5/31/2026
PJM | AE2-173 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/18/2019 |  |  | 12/31/2022
PJM | AE2-174 | Fremont Center-Tiffin Center 138 kV circuit #1 |  | OH | Seneca | Withdrawn | AEP | 198 | 34.85 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/19/2019 | 2/13/2023 |  | 10/31/2021
PJM | AE2-175 | Jackson-Long Pond 69 kV | Swiftwater Solar | PA | Monroe | Under Construction | PPL | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/19/2019 |  |  | 6/30/2025
PJM | AE2-176 | Groton 138 kV Solar | Wheatsborough Solar | OH | Erie | Under Construction | ATSI | 125 | 75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/19/2019 |  |  | 4/30/2025
PJM | AE2-177 | Squabb SVC 230 kV |  | PA | Elk | Withdrawn | APS | 165 | 99 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2019 | 4/8/2019 |  | 10/31/2021
PJM | AE2-178 | Wayne 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 62 | 37.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2019 | 4/8/2019 |  | 10/31/2021
PJM | AE2-179 | Lick-Waverly 115kV |  | OH | Pike | Withdrawn | OVEC | 78 | 46.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2019 | 4/1/2019 |  | 10/31/2021
PJM | AE2-180 | Beatty-London 138 kV III |  | OH | Madison | Withdrawn | ATSI | 79 | 47.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/18/2019 | 9/3/2019 |  | 10/31/2021
PJM | AE2-181 | Snyder 69kV | Montpelier Solar | OH | Williams | Engineering and Procurement | ATSI | 49 | 29.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/18/2019 |  |  | 12/31/2025
PJM | AE2-182 | Briery-Clover 230 kV | Seven Bridges Solar | VA | Mecklenburg | Withdrawn | Dominion | 17 | 11.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/18/2019 | 6/24/2024 |  | 12/31/2025
PJM | AE2-183 | Rogers Road 500 kV | Greensville Power Station | VA | Greensville | In Service | Dominion | 75 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/18/2019 |  |  | 8/15/2023 | 8/30/2023
PJM | AE2-184 | Warren County 500 kV | Warren County Power Station | VA | Warren | In Service | Dominion | 15 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/18/2019 |  |  | 4/30/2021 | 8/11/2020
PJM | AE2-185 - moved to TC1 | Gladys DP-Stonemill Switching Station 69 kV | Gladys II Solar Farm | VA | Campbell | Active | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/18/2019 |  |  | 9/1/2020
PJM | AE2-186 | Brandy DP-Remington 115 kV |  | VA | Fauquier | Withdrawn | Dominion | 60 | 39 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2019 | 4/29/2019 |  | 9/1/2020
PJM | AE2-187 - moved to TC1 | Shockoe DP-Chatham 69 kV |  | VA | Pittsylvania | Active | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/18/2019 |  |  | 9/1/2020
PJM | AE2-188 | Mitchell DP-Mountain Run 115 kV |  | VA | Culpeper | Withdrawn | Dominion | 40 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 3/18/2019 | 3/27/2020 |  | 12/31/2020
PJM | AE2-189 | Housenville 138 kV |  | PA | Butler | Withdrawn | APS | 42 | 17.64 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/18/2019 | 8/12/2019 |  | 12/31/2022
PJM | AE2-190 | Elk Run D.P.-Gainesville 230 kV | Alameda Solar | VA | Fauquier | Suspended | Dominion | 70 | 27.02 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/18/2019 |  |  | 1/31/2026
PJM | AE2-191 | Saxonburg 138 kV |  | PA | Butler | Withdrawn | APS | 52 | 21.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/18/2019 | 3/2/2022 |  | 12/31/2022
PJM | AE2-192 | Orrtanna 115 kV |  | PA | Adams | Withdrawn | ME | 65 | 39 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/18/2019 | 1/28/2022 |  | 12/31/2022
PJM | AE2-193 | Shenango 138 kV |  | PA | Mercer | Withdrawn | ATSI | 120 | 50.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/18/2019 | 3/29/2022 |  | 12/31/2022
PJM | AE2-194 | Congress-Toronto 138 kV | Kensington Solar | OH | Columbiana | Suspended | ATSI | 145 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/18/2019 |  |  | 1/2/2026
PJM | AE2-195 | East Canton-Robertsville 69 kV | Robertsville PV I | OH | Stark | Withdrawn | AEP | 19.7 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/18/2019 | 11/14/2024 |  | 1/14/2026
PJM | AE2-196 | Mt. Airy-Wythe 138 kV |  | VA | Wythe | Withdrawn | AEP | 94.6 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/19/2019 | 3/27/2020 |  | 12/31/2022
PJM | AE2-197 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2019 | 4/1/2019 |  | 10/1/2020
PJM | AE2-198 |  |  | NJ | Mercer | Withdrawn | PSEG | 2.75 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2019 | 4/1/2019
PJM | AE2-199 |  |  | NJ | Camden | Withdrawn | AEC | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2019 | 4/1/2019
PJM | AE2-200 |  |  | NJ | Salem | Withdrawn | AEC | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2019 | 4/1/2019
PJM | AE2-201 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2019 | 3/31/2019
PJM | AE2-202 |  |  | NJ | Hunterdon | Withdrawn | JCPL | 3.88 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2019 | 3/31/2019
PJM | AE2-203 |  |  | NJ | Warren | Withdrawn | JCPL | 4.38 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2019 | 3/31/2019
PJM | AE2-204 | Bolivar 34.5 kV | Bolivar Solar | OH | Stark | Engineering and Procurement | AEP | 19.3 | 9.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 3/19/2019 |  |  | 12/31/2026
PJM | AE2-205 | Cumberland 230 kV |  | NJ | Cumberland | Withdrawn | AEC | 78 | 46.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/19/2019 | 3/31/2020 |  | 6/30/2022
PJM | AE2-206 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | Partially in Service - Under Construction | Dayton | 99 | 41.58 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/20/2019 |  |  | 1/31/2025
PJM | AE2-207 | Heartsease DP-Mayo Dunbar 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 18 | 18 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 3/20/2019 | 8/21/2019 |  | 12/31/2020
PJM | AE2-208 | Chavies-Bonnyman 69 kV |  | KY | Perry | Withdrawn | AEP | 25 | 25 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 3/20/2019 | 3/27/2020 |  | 12/31/2021
PJM | AE2-209 | Airey 69 kV |  | MD | Dorchester | Withdrawn | DPL | 56 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/20/2019 | 3/31/2020 |  | 12/31/2021
PJM | AE2-210 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 90 | 7.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/20/2019 |  |  | 6/1/2022
PJM | AE2-211 | Jackson-Three Mile Island 230 kV | Dover Solar | PA | York | Suspended | ME | 55 | 23.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/20/2019 |  |  | 11/1/2024
PJM | AE2-212 | Harrowgate 34 kV | Harrowgate 1 | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/20/2019 |  |  | 3/30/2025
PJM | AE2-213 | Thorofare 13.2 kV |  | NJ | Gloucester | Withdrawn | PSEG | 3.145 | 1.1025 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 3/20/2019 | 8/14/2019 |  | 3/2/2020
PJM | AE2-214 | Cole 345 kV | Pleasant Prairie Solar | OH | Franklin | Engineering and Procurement | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/23/2019 |  |  | 12/31/2026
PJM | AE2-215 | Blain 115 kV |  | PA | Perry | Withdrawn | PENELEC | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/21/2019 | 3/27/2020 |  | 12/31/2021
PJM | AE2-216 | Hardin Switch 345 kV | Hardin Energy Center – Storage II | OH | Hardin | Engineering and Procurement | AEP | 55 | 55 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2019 |  |  | 12/31/2026
PJM | AE2-217 | East Springfield-London 138 kV | Sloopy Solar Energy Center | OH | Clark | Suspended | ATSI | 180 | 108 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2019 |  |  | 9/30/2028
PJM | AE2-218 | Eldean 138 kV | Eldean Solar | OH | Miami | Suspended | Dayton | 178 | 106 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2019 |  |  | 12/31/2024
PJM | AE2-219 | Bluff Point-Randolph 138 kV | Riverstart Solar Park V | IN | Randolph | Engineering and Procurement | AEP | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2019 |  |  | 5/31/2026
PJM | AE2-220 | Losantville 345 kV | Riverstart Solar Park II | IN | Randolph | Active | AEP | 125 | 52.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/21/2019 |  |  | 11/15/2027
PJM | AE2-221 | Clinton-Stuart 345 kV | Yellow Wood Solar Energy Center | OH | Clinton | Engineering and Procurement | Dayton | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/21/2019 |  |  | 12/31/2025
PJM | AE2-222 | Higbee 69 kV |  | NJ | Atlantic | Withdrawn | AEC | 300 | 84.3 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 3/22/2019 | 11/9/2022 |  | 6/1/2023
PJM | AE2-223 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 19.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 3/22/2019 |  |  | 10/31/2022
PJM | AE2-224 | Bearrock-Johnstown 230 kV | CPV Maple Hill Solar | PA | Cambria | In Service | PENELEC | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/23/2019 |  |  | 11/17/2023 | 11/28/2023
PJM | AE2-225 | Suffolk 34 kV | Hosier Road Solar | VA | City of Suffolk | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/22/2019 | 4/23/2021 |  | 11/30/2022
PJM | AE2-226 | Millville-Old Chapel 138 kV | Rippon | WV | Jefferson | Engineering and Procurement | APS | 99 | 59.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2019 |  |  | 12/31/2026
PJM | AE2-227 | Iron Bridge 34 kV | Bradley Ridge Solar | VA | Chesterfield | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/22/2019 |  |  | 3/30/2025
PJM | AE2-228 | Tyler 34 kv | Bradley BridgeSolar | VA | Chesterfield | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/22/2019 |  |  | 3/30/2025
PJM | AE2-229 | Suffolk 34 kV | Hosier Road Solar II | VA | City of Suffolk | Withdrawn | Dominion | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/22/2019 | 4/23/2021 |  | 11/30/2022
PJM | AE2-230 | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/24/2019 |  |  | 7/1/2024 | 12/27/2024
PJM | AE2-231 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 44 | 26.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/22/2019 |  |  | 12/1/2022
PJM | AE2-232 | Oyster Creek 230 kV II |  | NJ | Atlantic | Withdrawn | JCPL | 400 | 112.4 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted |  |  | 3/22/2019 | 3/26/2020 |  | 6/1/2023
PJM | AE2-233 | Carson-Rogers Rd 500 kV |  | VA | Accomack | Withdrawn | Dominion | 94 | 67.7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/22/2019 | 10/2/2019 |  | 6/1/2022
PJM | AE2-234 | Liberty Center-Buckeye Tap 69 kV | Maple Solar | IN | Huntington | Engineering and Procurement | AEP | 35 | 24.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2019 |  |  | 12/31/2027
PJM | AE2-235 | Murphysville-Plumville 69 kV |  | KY | Mason | Withdrawn | EKPC | 60 | 41.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/22/2019 | 8/13/2019 |  | 7/31/2021
PJM | AE2-236 | Columbia-Northeast 138 kV | Dover Solar Facility | IN | Whitley | Suspended | AEP | 55 | 38.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2019 |  |  | 7/29/2026
PJM | AE2-237 | Vernon-Sugar Loaf #2 115 kV |  | NJ | Sussex | Withdrawn | JCPL | 107 | 21.4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/22/2019 | 7/27/2022 |  | 3/1/2022
PJM | AE2-238 | Reybold 12 kV |  | DE | New Castle | Withdrawn | DPL | 8 | 3.36 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/21/2019 | 9/17/2019 |  | 5/14/2021
PJM | AE2-241 | Bloomsburg-Columbia 69 kV | Mountain Holly | PA | Columbia | Suspended | PPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/23/2019 |  |  | 6/1/2027
PJM | AE2-242 | Bowmanns Mill-Scott 69 kV |  | PA | Columbia | Withdrawn | PPL | 85 | 35.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/22/2019 | 9/24/2019 |  | 3/5/2021
PJM | AE2-243 | East Carbondale 12.47 kV I |  | PA | Wayne | Withdrawn | PPL | 16.5 | 2.3 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/22/2019 | 9/6/2019 |  | 3/31/2021
PJM | AE2-244 | East Carbondale 12.47 kV II |  | PA | Wayne | Withdrawn | PPL | 16.5 | 2.3 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/22/2019 | 9/6/2019 |  | 3/31/2021
PJM | AE2-245 | Stockton 34.5 kV |  | VA | Henry | Withdrawn | AEP | 0 | 5.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/25/2019 | 10/23/2020 |  | 12/30/2020
PJM | AE2-246 | Gretna DP 69 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 0 | 13.95 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/25/2019 | 9/10/2019 |  | 12/15/2020
PJM | AE2-247 | Myrtle-Windsor 115 kV | Knoxville Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/25/2019 |  |  | 12/1/2027
PJM | AE2-248 | Fillmore-Thompson Farm 46 kV | CE-FILMORE | PA | Centre | Suspended | APS | 16 | 9.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/25/2019 |  |  | 12/31/2027
PJM | AE2-249 | Bedford North-Pennsylvania Hollow 23 kV | BE-ASTOR | PA | Bedford | Withdrawn | PENELEC | 16.6 | 9.96 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/25/2019 |  |  | 7/1/2021
PJM | AE2-250 - moved to TC1 | Purdy Sw.-Reams 115 kV |  | VA | Greensville | Active | Dominion | 82.5 | 54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/26/2019 |  |  | 9/30/2021
PJM | AE2-251 | Cardiff 230 kV |  | NJ | Monmouth | Withdrawn | AEC | 1200 | 337.2 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 3/26/2019 | 9/12/2023 |  | 6/1/2024
PJM | AE2-252 | Gardners-Mountain 115 kV |  | PA | Cumberland | Withdrawn | ME | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/26/2019 | 3/25/2020 |  | 11/9/2021
PJM | AE2-253 | Hickory-Moyock 230 kV | Oak Trail Solar | NC | Currituck | In Service | Dominion | 50 | 34.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/25/2019 |  |  | 7/15/2023 | 7/5/2023
PJM | AE2-254 | Garrard County-Tommy-Gooch 69 kV | Turkey Creek Solar | KY | Garrard | In Service | EKPC | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2019 |  |  | 12/31/2022 | 10/28/2022
PJM | AE2-255 | Molecreek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 100 | 25 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2019 |  |  | 1/18/2027
PJM | AE2-256 | Copperstone-North Lebanon 230 kV | Lebanon Solar | PA | Lebanon | Suspended | ME | 70 | 29.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/28/2019 |  |  | 8/1/2026
PJM | AE2-257 | Cedar Neck 69 kV |  | DE | Sussex | Withdrawn | DPL | 120 | 33 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 3/27/2019 | 8/1/2022 |  | 6/1/2022
PJM | AE2-258 | Chase City 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 0 | 14.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/27/2019 | 9/12/2023 |  | 6/1/2020
PJM | AE2-259 | Curdsville-Willis Mtn 115 kV | Blue Rock Solar | VA | Buckingham | Engineering and Procurement | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/28/2019 |  |  | 12/31/2026
PJM | AE2-260 | Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 200 | 82.7 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 3/28/2019 | 9/12/2023 |  | 6/30/2020
PJM | AE2-261 - moved to TC1 | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 299 | 179.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/28/2019 |  |  | 6/1/2022
PJM | AE2-262 | Moshannon-Milesburg 230 kV | MPG Solar | PA | Centre | Engineering and Procurement | APS | 83.6 | 50 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2019 |  |  | 12/31/2026
PJM | AE2-263 | Moshannon-Milesburg 230 kV II | MPG Solar | PA | Centre | Engineering and Procurement | APS | 78.38 | 47 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2019 |  |  | 12/31/2026
PJM | AE2-264 | Altoona-Raystown 230 kV |  | PA | Blair | Withdrawn | PENELEC | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/28/2019 | 6/6/2023 |  | 6/30/2022
PJM | AE2-265 | Corey 138 kV |  | MI | St. Joseph | Withdrawn | AEP | 150 | 47.78 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/28/2019 | 4/1/2019 |  | 9/1/2021
PJM | AE2-266 | Corey 138kV |  | MI | St. Joseph | Withdrawn | AEP | 198.9 | 64.19 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/28/2019 | 4/1/2019 |  | 9/1/2021
PJM | AE2-267 | Woodsdale 345 kV | Woodsdale Renewable Energy Center | OH | Butler | Engineering and Procurement | DEOK | 49 | 28.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2019 |  |  | 6/1/2026
PJM | AE2-268 | Harmony Village 34 kV |  | VA | Middlesex | Withdrawn | Dominion | 15 | 9.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 3/28/2019 | 9/12/2019 |  | 12/31/2021
PJM | AE2-269 | Fayetteville 138 kV |  | PA | Franklin | Withdrawn | APS | 22 | 9.24 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/28/2019 | 8/12/2019 |  | 12/31/2021
PJM | AE2-270 - moved to TC1 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 3/28/2019 | 6/24/2024 |  | 9/29/2021
PJM | AE2-271 | Montour 230 kV | Montour Solar One | PA | Montour | Suspended | PPL | 101.6 | 61 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/14/2019 |  |  | 9/26/2026
PJM | AE2-272 | Woodstown 12 kV | Pilesgrove Solar | NJ | Salem | In Service | AEC |  | 0.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/28/2019 |  |  | 12/31/2019 | 9/17/2019
PJM | AE2-273 | Siegfried-Hauto 69KV | PA Solar Park | PA | Carbon | In Service | PPL | 0 | 0.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/28/2019 |  |  | 12/1/2021 | 1/17/2020
PJM | AE2-274 | Siegfried-Hauto 69 kV | PA Solar Park | PA | Carbon | In Service | PPL | 0 | 0.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/28/2019 |  |  | 12/1/2021 | 1/17/2020
PJM | AE2-275 - moved to TC1 | J.K. Smith-Fawkes 138 kV |  | KY | Madison | Active | EKPC | 90 | 7.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/28/2019 |  |  | 6/1/2022
PJM | AE2-276 | Sullivan 345kV | Trade Post Energy Storage | IN | Sullivan | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 3/28/2019 |  |  | 12/31/2020
PJM | AE2-277 | McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 38.2 | 16 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/28/2019 | 3/30/2022
PJM | AE2-278 | Urbana 138 kV | Urbana Solar | OH | Champaign | Withdrawn | Dayton | 150.7 | 90.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2019 | 1/20/2022 |  | 6/30/2023
PJM | AE2-279 | Oxford 115 kV |  | PA | Adams | Withdrawn | ME | 44 | 26.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/13/2019 | 9/6/2019 |  | 10/1/2021
PJM | AE2-280 | Claytor Lake-Edgemont 138 kV |  | VA | Montgomery | Withdrawn | AEP | 126.65 | 75.99 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/29/2019 | 3/15/2024 |  | 12/31/2022
PJM | AE2-281 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 50 | 7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2019 |  |  | 2/1/2027
PJM | AE2-282 | East Fayette 138 kV | Arche Energy Project | OH | Fulton | In Service | ATSI | 67 | 43.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2019 |  |  | 12/31/2023 | 1/17/2024
PJM | AE2-283 - moved to TC1 | Gladys-Stone Mill 69 kV |  | VA | Campbell | Active | Dominion | 53 | 28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/29/2019 |  |  | 9/30/2021
PJM | AE2-284 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Withdrawn | AEP | 75 | 75 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 3/29/2019 | 1/30/2020 |  | 12/31/2022
PJM | AE2-285 | Maysville 69 kV | MC Solar I | PA | Mercer | Engineering and Procurement | ATSI | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2019 |  |  | 8/29/2025
PJM | AE2-286 | Airey 12 kV |  | MD | Dorchester | Withdrawn | DPL | 19.5 | 7.95 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/29/2019 | 8/1/2019 |  | 12/31/2019
PJM | AE2-287 | Brunswick 115 kV |  | VA | Brunswick | Withdrawn | Dominion | 130 | 78 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/29/2019 | 8/22/2019 |  | 6/30/2022
PJM | AE2-288 | Sunbury 500 kV |  | PA | Snyder | Withdrawn | PPL | 90 | 206 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 3/29/2019 | 4/7/2020 |  | 5/1/2023
PJM | AE2-289 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 80 | 11.76 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted |  | 3/29/2019 |  |  | 12/31/2021
PJM | AE2-290 | Nottingham 138 kV | Nottingham Solar | OH | Harrison | Suspended | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2019 |  |  | 12/15/2023
PJM | AE2-291 - moved to TC1 | Grit DP-Perth 115 kV |  | VA | Pittsylvania | Active | Dominion | 102 | 61.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/29/2019 |  |  | 4/1/2021
PJM | AE2-292 - moved to TC1 | Grit DP-Perth 115 kV |  | VA | Campbell | Withdrawn | Dominion | 127 | 76.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/29/2019 | 6/24/2024 |  | 4/1/2021
PJM | AE2-293 | Dauphin-Pine Grove 69kV |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2019 | 4/4/2019 |  | 6/1/2020
PJM | AE2-294 | Dauphin-Pine Grove 69 kV |  | PA | Dauphin | Withdrawn | PPL | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/29/2019 | 4/4/2019 |  | 3/31/2020
PJM | AE2-295 | Eldred 230 kV |  | PA | Schuylkill | Withdrawn | PPL | 174.8 | 25.7 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 3/29/2019 | 7/7/2022 |  | 5/31/2022
PJM | AE2-296 | Hutchings West 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 104 | 104 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 3/29/2019 | 8/20/2019 |  | 5/1/2020
PJM | AE2-297 | Madison-Tanners Creek 138 kV | Bellflower Solar 1 | IN | Henry | In Service | AEP | 152.5 | 91.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2019 |  |  | 12/31/2024 | 12/6/2022
PJM | AE2-298 | Cavett Switch - West Van Wert 69 kV | White Trillium | OH | Van Wert | Engineering and Procurement | AEP | 49.9 | 29.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2019 |  |  | 12/30/2026
PJM | AE2-299 | Erie East 230 kV | Erie East Energy | PA | Erie | Suspended | PENELEC | 160 | 32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2019 |  |  | 6/1/2026
PJM | AE2-300 |  |  | OH | Licking | Withdrawn | AEP | 200 | 200 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/29/2019 | 4/1/2019 |  | 9/22/2022
PJM | AE2-301 | Crisfield 25 kV |  | MD | Somerset | Withdrawn | DPL | 5.5 | 2.2 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 3/29/2019 | 3/26/2020 |  | 9/22/2021
PJM | AE2-302 | East Beaver-Lick 138 kV |  | OH | Jackson | Withdrawn | AEP | 49.9 | 29.94 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/29/2019 | 10/2/2023 |  | 7/1/2022
PJM | AE2-303 | Honda Marysville Tap | Cardinal Solar | OH | Union | Withdrawn | Dayton | 49.9 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2019 | 3/7/2024 |  | 12/1/2023
PJM | AE2-304 | South Hertford 34 kV | South Hertford Solar | NC | Perquimans | Withdrawn | Dominion | 5 | 3.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/29/2019 | 10/26/2020 |  | 6/1/2022
PJM | AE2-305 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 78 | 46.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/29/2019 |  |  | 8/1/2021
PJM | AE2-306 | Gunn Road 345 kV | Scioto Solar | OH | Hardin | Engineering and Procurement | AEP | 30 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2019 |  |  | 12/31/2028
PJM | AE2-307 | Braidwood-East Frankfort |  | IL | Will | Withdrawn | ComEd | 225 | 165 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 3/29/2019 | 2/7/2020 |  | 5/31/2021
PJM | AE2-308 - moved to TC1 | Three Forks-Dale 138 kV | Madison Solar 1 | KY | Madison | Active | EKPC | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress | Interim Study | 3/29/2019 |  |  | 5/31/2021
PJM | AE2-309 | Carlos Junction-Lonaconing 34.5 kV | Jade Meadow | MD | Allegany | In Service | APS | 19.84 | 11.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/1/2019 |  |  | 3/22/2024 | 3/26/2024
PJM | AE2-310 | Wilmington-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 85 | 67 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 3/29/2019 | 2/7/2020 |  | 5/31/2021
PJM | AE2-311 | Carson-Septa 500 kV |  | VA | Sussex | Withdrawn | Dominion | 400 | 240 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2019 | 6/19/2019 |  | 12/31/2021
PJM | AE2-312 | Rocky Road |  | IL | Kane | Withdrawn | ComEd | 7 | 7 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 3/29/2019 | 4/4/2019 |  | 6/1/2019
PJM | AE2-313 - moved to TC1 | Carson-Rawlings 500 kV |  | VA | Dinwiddie | Active | Dominion | 314 | 188.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/29/2019 |  |  | 9/15/2022
PJM | AE2-314 | Cardiff 230 kV |  | NJ | Atlantic | Withdrawn | AEC | 72 | 43.2 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/29/2019 | 12/16/2019 |  | 6/30/2022
PJM | AE2-315 | Yankee Tap 69 kV | Yankee 1-7 | OH | Montgomery | In Service | Dayton | 23.5 | 23.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 3/29/2019 |  |  | 11/30/2022 | 4/19/2022
PJM | AE2-316 | Brookville-Squab Hollow 138 kV | Squab Solar | PA | Jefferson | Suspended | PENELEC | 90 | 41.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2019 |  |  | 7/10/2026
PJM | AE2-317 | Pequest River 115 kV |  | NJ | Atlantic | Withdrawn | JCPL | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/30/2019 | 4/7/2020 |  | 6/30/2022
PJM | AE2-318 | Ford-Cedarville 138 kV | Clermont County Solar Project | OH | Clermont | Suspended | DEOK | 100 | 67.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2019 |  |  | 12/31/2025
PJM | AE2-319 | Atlanta 69kV I | Mustang County Solar Project | OH | Pickaway | Withdrawn | Dayton | 100 | 66.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2019 | 2/9/2024 |  | 10/1/2028
PJM | AE2-320 | Atlanta 69 kV II |  | OH | Pickaway | Withdrawn | Dayton | 50 | 46 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2019 | 2/9/2024 |  | 12/1/2022
PJM | AE2-321 - moved to TC1 | Belvidere-Marengo 138 kV |  | IL | McHenry | Active | ComEd | 100 | 67 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/30/2019 |  |  | 12/1/2021
PJM | AE2-322 | Mark Center 69 kV | Mark Center Solar Project | OH | Defiance | Engineering and Procurement | AEP | 60 | 40.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2019 |  |  | 12/31/2025
PJM | AE2-323 | Twin Branch-Guardian 138 kV | Elkhart County Solar Project | IN | Elkhart | Engineering and Procurement | AEP | 100 | 67.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2019 |  |  | 5/1/2026
PJM | AE2-324 | Galion-Roberts South II 138 kV |  | OH | Marion | Withdrawn | ATSI | 20.3 | 20.3 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/30/2019 | 6/24/2022 |  | 12/1/2022
PJM | AE2-325 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 52.2 | 31.32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/30/2019 |  |  | 12/1/2022
PJM | AE2-326 | Jacksons Ferry 138 kV | Wythe County Solar Project | VA | Wythe | Active | AEP | 52.2 | 31.32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 3/30/2019 |  |  | 12/1/2022
PJM | AE2-327 | Biers Run-Circleville 138 kV |  | OH | Pickaway | Withdrawn | AEP | 52.2 | 31.32 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 3/30/2019 | 3/6/2020 |  | 12/1/2021
PJM | AE2-328 | Briery DP-Clover 230 kV |  | VA | Accomack | Withdrawn | Dominion | 100 | 68.1 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2019 | 9/23/2019 |  | 4/1/2022
PJM | AE2-329 | Cedarville-Ford 138 kV |  | OH | Clermont | Withdrawn | DEOK | 52.2 | 208.8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/30/2019 | 4/29/2019 |  | 12/1/2022
PJM | AE2-330 | Belvidere-Marengo |  | IL | McHenry | Withdrawn | ComEd | 52.2 | 208.8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/30/2019 | 4/29/2019 |  | 12/1/2021
PJM | AE2-331 | Mark Center 69 kV |  | OH | Defiance | Withdrawn | AEP | 34.8 | 139.2 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2019 | 4/29/2019 |  | 12/1/2021
PJM | AE2-332 | Twin Branch-Guardian 138 kV |  | IN | Elkhart | Withdrawn | AEP | 52.2 | 208.8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2019 | 4/29/2019 |  | 12/1/2021
PJM | AE2-333 | Bedington 138 kV | Bedington Energy Facility | MD | Frederick | Suspended | APS | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2019 |  |  | 10/31/2025
PJM | AE2-334 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Engineering and Procurement | AEC | 44 | 26.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2019 |  |  | 12/31/2026
PJM | AE2-335 | Gloucester Solar II |  | NJ | Gloucester | Withdrawn | AEC | 60 | 41.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/31/2019 | 3/31/2020 |  | 6/30/2022
PJM | AE2-336 | St. Barnabas 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 4.6 | 1.932 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2019 | 9/6/2019 |  | 12/31/2020
PJM | AE2-337 | St. Barnabas 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 2.4 | 1.008 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2019 | 9/6/2019 |  | 12/31/2020
PJM | AE2-338 | Avon 138 kV |  | KY | Fayette | Withdrawn | EKPC | 20.3 | 81.2 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2019 | 4/22/2019 |  | 12/1/2022
PJM | AE2-339 | Avon 138 kV | Grassy Plains | KY | Fayette | Engineering and Procurement | EKPC | 40 | 26.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2019 |  |  | 6/30/2027
PJM | AE2-340 | Sandwich-Plano |  | IL | Kendall | Withdrawn | ComEd | 52.2 | 208.8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2019 | 4/29/2019 |  | 12/1/2022
PJM | AE2-341 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 150 | 100.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2019 |  |  | 12/1/2022
PJM | AE2-342 | Woodstock 69 kV | Woodstock Solar | OH | Champaign | Engineering and Procurement | Dayton | 40 | 26.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2019 |  |  | 9/30/2025
PJM | AE2-343 | Andover (Maysville) 69 kV II | Welcome Solar III, LLC | PA | Crawford | Engineering and Procurement | ATSI | 17.9 | 12.3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2019 |  |  | 6/5/2024
PJM | AE2-344 | Edinboro South-Venango Junction 115 kV | Shorebird Solar | PA | Crawford | Suspended | PENELEC | 116.5 | 69.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/14/2019 |  |  | 12/31/2025
PJM | AE2-345 | Hunterstown-Texas Eastern Tap 115 kV | Granite Hill Solar | PA | Adams | Suspended | ME | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/13/2019 |  |  | 2/1/2026
PJM | AE2-346 | Ahoskie 34.5 kV | Colice Hall Solar | NC | Hertford | In Service | Dominion | 12 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/29/2019 |  |  | 9/15/2023 | 7/6/2023
PJM | AF1-001 | Thayerville 34.5 kV | Sand Flat Road Solar Project | MD | Garrett | Withdrawn | APS | 13.75 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/1/2019 | 8/6/2024 |  | 2/28/2023
PJM | AF1-002 | Berwick 12.47 kV |  | PA | Luzerne | Withdrawn | PPL | 5 | 2.1 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/1/2019 | 3/4/2020 |  | 3/31/2020
PJM | AF1-003 | Hawkins Gate-Billingsley Rd 69 kV | Charles County Solar II | MD | Charles | Suspended | SMECO | 20 | 9.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/2/2019 |  |  | 9/30/2027
PJM | AF1-004 | Hwy 228-Bennsville 69 kV |  | MD | Charles | Withdrawn | SMECO | 16.82 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/1/2019 | 10/8/2020 |  | 4/30/2021
PJM | AF1-005 | Grayton-Ripley 69 kV | Charles County Solar I | MD | Charles | Suspended | SMECO | 20 | 9.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Wholesale Market Participation Agreement | 4/1/2019 |  |  | 9/30/2028
PJM | AF1-006 | Fairview East 34.5 kV | Erie Solar | PA | Erie | Partially in Service - Under Construction | PENELEC | 20 | 12.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/2/2019 |  |  | 12/31/2024
PJM | AF1-007 | Indian River 230 kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Engineering and Procurement | DPL | 7.3 | 1.9 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2019 |  |  | 12/31/2027
PJM | AF1-008 | CPV NJ Solar |  | NJ | Morris | Withdrawn | JCPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/2/2019 | 5/6/2019 |  | 12/31/2019
PJM | AF1-009 | Dixon-McGirr |  | IL | Lee | Withdrawn | ComEd | 25 | 5 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/2/2019 | 10/8/2020 |  | 12/31/2021
PJM | AF1-010 | Schauff Road |  | IL | Lee | Withdrawn | ComEd | 30 | 30 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 4/2/2019 | 3/9/2020 |  | 12/31/2021
PJM | AF1-011 | Schauff Road |  | IL | Lee | Withdrawn | ComEd | 30 | 30 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 4/2/2019 | 9/29/2020 |  | 9/30/2021
PJM | AF1-012 | Electric Junc-Nelson |  | IL | Lee | Withdrawn | ComEd | 175 | 105 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 4/2/2019 | 10/13/2023 |  | 9/30/2022
PJM | AF1-013 | Dixon-McGirr |  | IL | Lee | Withdrawn | ComEd | 25 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 4/2/2019 | 3/9/2020 |  | 12/1/2020
PJM | AF1-014 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 19.9 | 7.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/4/2019 |  |  | 3/31/2025
PJM | AF1-015 | Easton-Steele 138 kV II | Crockett Solar Project | MD | Talbot | Suspended | DPL | 15 | 6.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/3/2019 |  |  | 3/31/2026
PJM | AF1-016 | Suffolk 115 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 20 | 7.72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 4/3/2019 | 2/20/2020 |  | 11/30/2021
PJM | AF1-017 | Myrtle-Windsor 115 kV | Knoxville Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/3/2019 |  |  | 12/1/2027
PJM | AF1-018 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Suspended | Dominion | 40 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 4/3/2019 |  |  | 3/1/2026
PJM | AF1-019 | Branchville-Holiday Lakes 34.5 kV | Viridity Energy Solutions Montague Storage | NJ | Sussex | In Service | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 4/6/2019 |  |  | 1/31/2025 | 12/20/2024
PJM | AF1-021 | Bethelboro-Connellsville #1 25 kV | Pechin Solar | PA | Fayette | In Service | APS | 14 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/17/2019 |  |  | 11/29/2024 | 10/18/2024
PJM | AF1-022 | Lake Lynn-Uniontown 25 kV | Gans Solar Farm | PA | Fayette | In Service | APS | 14 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/17/2019 |  |  | 11/29/2024 | 12/3/2024
PJM | AF1-023 | Atlantic-Red Bank 34 kV II | Hamilton Road Solar | NJ | Monmouth | In Service | JCPL | 0 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 4/18/2019 |  |  | 9/1/2023 | 8/6/2020
PJM | AF1-024 | Freeland Municipal Authority |  | PA | Adams | Withdrawn | PPL | 19.9 | 9.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/1/2019 | 5/21/2019 |  | 12/31/2021
PJM | AF1-026 | Edge Road Battery Storage (CIRs) | Alpha Battery Storage Facility | NJ | Warren | In Service | JCPL | 0 | 2 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 5/6/2019 |  |  | 9/1/2023 | 9/21/2020
PJM | AF1-027 | Plumsted 537 Energy Storage (CIRs) | Plumsted Energy Storage Facility | NJ | Ocean | In Service | JCPL | 0 | 2 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 5/6/2019 |  |  | 9/1/2023 | 9/21/2020
PJM | AF1-028 | Endless Caverns 115 kV | Prospect Power | VA | Rockingham | Engineering and Procurement | Dominion | 200 | 200 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 5/13/2019 |  |  | 2/1/2026
PJM | AF1-029 | Cavett Switch - West Van Wert 69 kV |  | OH | Van Wert | Withdrawn | AEP | 25 | 15 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 5/14/2019 | 8/21/2023 |  | 12/31/2021
PJM | AF1-030 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 100 | 66.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 5/17/2019 |  |  | 12/1/2022
PJM | AF1-031 | Kings Dominion DP 115 kV |  | VA | Caroline | Withdrawn | Dominion | 93.5 | 60.69 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 5/17/2019 | 5/26/2022 |  | 12/31/2022
PJM | AF1-032 | Suffolk 34.5 kV | Stratford Solar Center | VA | City of Suffolk | In Service | Dominion | 15 | 9.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/18/2019 |  |  | 2/28/2023 | 1/4/2023
PJM | AF1-033 | Poolesville 34 kV | Surry Solar Center | VA | Surry | Withdrawn | Dominion | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 5/17/2019 | 8/17/2023 |  | 2/28/2023
PJM | AF1-034 | Clinton-Stuart 345 kV |  | OH | Highland | Withdrawn | Dayton | 300 | 180 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/22/2019 | 6/12/2019 |  | 11/1/2021
PJM | AF1-035 | Clinton-Stuart 345 kV |  | OH | Highland | Withdrawn | Dayton | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  | Withdrawn | 5/22/2019 | 6/12/2019 |  | 11/1/2021
PJM | AF1-036 | Carville 138 kV III | Concho Solar I | MD | Queen Anne's | Suspended | DPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 5/24/2019 |  |  | 6/3/2024
PJM | AF1-037 | C.P. Crane 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 200 | 200 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 5/31/2019 | 3/9/2020 |  | 6/1/2021
PJM | AF1-038 | Sewellton Jct-Webbs Crossroads 69 kV | Mt Olive Creek Solar | KY | Russell | Engineering and Procurement | EKPC | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/8/2019 |  |  | 9/30/2026
PJM | AF1-039 | Listonburg-Highpoint 24.9 kV | Listonburg Solar | PA | Somerset | In Service | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/7/2019 |  |  | 10/31/2024
PJM | AF1-040 | Gratz Tap 69 kV | Momentum Gratz | PA | Dauphin | Suspended | PPL | 20 | 1 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 6/15/2019 |  |  | 9/6/2024
PJM | AF1-041 | Absecon 12.47 kV | Pear Street Solar | NJ | Atlantic | In Service | AEC | 2.4 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/18/2019 |  |  | 3/3/2022 | 5/8/2020
PJM | AF1-042 | Garner DP-Lancaster 115 kV | Waller Solar I | VA | Lancaster | Suspended | Dominion | 45 | 17.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/24/2019 |  |  | 5/31/2024
PJM | AF1-043 | Moshannon-East Towanda 230 kV |  | PA | Clinton | Withdrawn | PENELEC | 92 | 105 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Withdrawn |  |  | 6/28/2019 | 4/20/2023 |  | 1/1/2023
PJM | AF1-044 | Wye Mills-Longwood 69 kV |  | MD | Allegany | Withdrawn | DPL | 45 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 6/28/2019 | 2/7/2020 |  | 11/30/2021
PJM | AF1-045 | Cedarville-Ford 138 kV | Clermont County Solar Project | OH | Clermont | Suspended | DEOK | 52.2 | 31.3 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 6/29/2019 |  |  | 12/31/2025
PJM | AF1-046 | Twin Branch-Guardian 138 kV |  | IN | Elkhart | Withdrawn | AEP | 52.2 | 31.32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 6/28/2019 | 9/14/2023 |  | 12/1/2023
PJM | AF1-047 | Mark Center 69 kV |  | OH | Defiance | Withdrawn | AEP | 34.8 | 20.88 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 6/28/2019 | 9/14/2023 |  | 12/1/2023
PJM | AF1-048 - moved to TC1 | Belvidere-Marengo |  | IL | McHenry | Active | ComEd | 52.2 | 31.32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 6/28/2019 |  |  | 12/1/2023
PJM | AF1-049 | Berry Hill 138 kV | Berry Hill | VA | Pittsylvania | Engineering and Procurement | AEP | 125 | 75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/12/2019 |  |  | 3/30/2027
PJM | AF1-050 | Summer Shade - Green County 161 kV | Horseshoe Bend Solar | KY | Green | Engineering and Procurement | EKPC | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/14/2019 |  |  | 11/30/2026
PJM | AF1-051 | Gavin 765 kV | Gavin Unit No. 1 | OH | Gallia | Under Construction | AEP | 11 | 11 | Capacity | Generation Interconnection | Coal | Document Posted | Document Posted | Not Required | Document Posted | 7/13/2019 |  |  | 5/31/2025
PJM | AF1-052 | Mason 230 kV |  | NJ | Hudson | Withdrawn | PSEG | 131.5 | 114.2 | Capacity | Generation Interconnection | Natural Gas; Other; Storage; Solar | Document Posted | Document Posted | Withdrawn |  | 7/26/2019 | 2/11/2021 |  | 12/31/2024
PJM | AF1-053 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 40 | 16 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 7/31/2019 |  |  | 12/1/2021
PJM | AF1-054 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 38.5 | 23.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 7/31/2019 |  |  | 12/1/2021
PJM | AF1-055 | Wayne 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 69.5 | 41.7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/31/2019 | 2/19/2020 |  | 10/31/2021
PJM | AF1-056 | Maysville/Masury 138 kV |  | PA | Mercer | Withdrawn | ATSI | 100 | 68.1 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 7/31/2019 | 8/27/2019 |  | 10/1/2023
PJM | AF1-057 | Jackson-Three Mile Island 230 kV II | Dover Solar | PA | York | Suspended | ME | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2019 |  |  | 11/1/2024
PJM | AF1-058 | Welco 34.5 kV | Watlington Solar | VA | Halifax | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/1/2019 |  |  | 11/30/2022 | 3/8/2023
PJM | AF1-059 | Brodnax-South Hill 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 99.2 | 99.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 7/31/2019 | 9/12/2023 |  | 10/31/2021
PJM | AF1-060 | Lena 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 10.34 | 10.34 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/31/2019 | 6/23/2023 |  | 12/31/2020
PJM | AF1-061 | Fayetteville 12.47 kV |  | PA | Franklin | Withdrawn | APS | 4 | 1.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 7/31/2019 | 8/6/2020 |  | 12/10/2021
PJM | AF1-062 | Jug Street 138 kV | Flint Grid | OH | Licking | Engineering and Procurement | AEP | 200 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2019 |  |  | 11/1/2026
PJM | AF1-063 | Lockwood Road 138 kV |  | OH | Defiance | Withdrawn | AEP | 30 | 19.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn | Interim Study | 7/31/2019 | 10/29/2024 |  | 3/31/2022
PJM | AF1-064 | Weston 69 kV | Juliet Energy | OH | Wood | Engineering and Procurement | ATSI | 50 | 33.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2019 |  |  | 11/30/2025
PJM | AF1-065 | Tidd-Wylie Ridge 345 kV III |  | WV | Brooke | Withdrawn | APS | 100 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  |  | 7/24/2019 | 10/14/2020 |  | 6/1/2022
PJM | AF1-066 | New Road 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 8/2/2019 | 8/8/2023 |  | 11/30/2021
PJM | AF1-067 | Kings Dominion DP 115 kV |  | VA | Caroline | Withdrawn | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 8/8/2019 | 6/29/2023 |  | 12/16/2022
PJM | AF1-068 | Boalsburg-Centre Hall 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 12.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 8/8/2019 | 12/15/2020 |  | 1/10/2022
PJM | AF1-069 | Carson-Rogers Rd 500 kV |  | VA | Sussex | Active | Dominion | 94 | 67.7 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress | Document Posted | 8/9/2019 |  |  | 8/1/2031
PJM | AF1-070 | North Clark 345 kV |  | KY | Clark | Withdrawn | EKPC | 350 | 255.3 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 8/13/2019 | 10/1/2019 |  | 6/1/2022
PJM | AF1-071 | College Corner 138 kV |  | OH | Preble | Active | AEP | 18 | 6.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 8/13/2019 |  |  | 7/1/2019
PJM | AF1-072 | Rocky Road |  | IL | Kane | Withdrawn | ComEd | 17.2 | 17.2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/14/2019 | 9/11/2023 |  | 8/1/2019
PJM | AF1-073 | Trowbridge 230 kV |  | NC | Washington | Withdrawn | Dominion | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/31/2019 | 2/11/2020 |  | 10/31/2021
PJM | AF1-074 | Waverly-Wakefield 115 kV |  | VA | Sussex | Withdrawn | Dominion | 68 | 40.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/26/2019 | 2/20/2020 |  | 6/30/2022
PJM | AF1-075 | Harrisburg-Endless Caverns 230 kV | Skyline Solar | VA | Rockingham | Suspended | Dominion | 73 | 45.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/21/2019 |  |  | 12/31/2024
PJM | AF1-076 | Southwest Lima 138 kV |  | OH | Allen | Withdrawn | AEP | 100 | 61.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/22/2019 | 9/14/2023 |  | 12/31/2021
PJM | AF1-077 | Southwest Lima 138 kV |  | OH | Allen | Withdrawn | AEP | 100 | 61.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/22/2019 | 9/14/2023 |  | 12/31/2021
PJM | AF1-078 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | Partially in Service - Under Construction | Dayton | 45 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/27/2019 |  |  | 1/31/2025
PJM | AF1-079 | Louisa-South Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 44.8 | 19 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/28/2019 | 12/6/2022 |  | 11/1/2021
PJM | AF1-080 | Deer Creek-Fisher Body-Mullin 138 kV |  | IN | Madison | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 8/28/2019 | 9/29/2020 |  | 9/15/2021
PJM | AF1-081 | Cumberland 230 kV |  | NJ | Atlantic | Withdrawn | AEC | 160 | 96 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 8/28/2019 | 2/27/2020 |  | 6/30/2022
PJM | AF1-082 | Heartsease-Mayo Dunbar DP |  | NC | Edgecombe | Withdrawn | Dominion | 18 | 18 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 8/29/2019 | 4/8/2024 |  | 12/31/2020
PJM | AF1-083 | Green County-Saloma 161 kV | Flat Run Solar | KY | Barren | Engineering and Procurement | EKPC | 55 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2019 |  |  | 12/15/2026
PJM | AF1-084 | Hartford-Almena 69 kV | Murch Solar | MI | Van Buren | Engineering and Procurement | AEP | 85 | 54.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2019 |  |  | 1/15/2027
PJM | AF1-085 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 77 | 32.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/30/2019 | 4/26/2024 |  | 11/30/2022
PJM | AF1-086 | Madera-Westover South 115 kV | Rogue's Wind | PA | Clearfield | Under Construction | PENELEC | 109.9 | 20.54 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2019 |  |  | 9/1/2026
PJM | AF1-087 | Bakers Pond-Bell Ave 115 kV II |  | VA | Accomack | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted |  |  |  | 8/30/2019 | 2/18/2020 |  | 6/1/2022
PJM | AF1-089 | New Castle 69 kV |  | KY | Henry | Withdrawn | EKPC | 70 | 53.6 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 8/30/2019 | 2/12/2020 |  | 6/1/2022
PJM | AF1-090 | Kincaid-Pana | Rolling Farms Wind Project | IL | Christian | Engineering and Procurement | ComEd | 200 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2019 |  |  | 12/31/2029
PJM | AF1-091 | Varner - Sowers 138 kV | Sculpin Solar | IN | DeKalb | Engineering and Procurement | AEP | 180 | 138.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2019 |  |  | 11/30/2027
PJM | AF1-092 | Huntington Jct. 138 kV |  | IN | Huntington | Engineering and Procurement | AEP | 150 | 115 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2019 |  |  | 12/31/2026
PJM | AF1-093 | Henderson-Stoneboro 69 kV | Jackson Center Solar II | PA | Mercer | Engineering and Procurement | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/31/2019 |  |  | 1/6/2026
PJM | AF1-094 | Union City-Cambridge Springs 34.5 kV | Franklin Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/30/2019 |  |  | 9/20/2026
PJM | AF1-095 | Hertlein Road-Winburne 34 kV |  | PA | Clearfield | Withdrawn | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/30/2019 | 10/2/2019 |  | 1/1/2023
PJM | AF1-096 | Titusville-Oil Creek 34.5 kV | Big Bell Solar | PA | Crawford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 8/30/2019 | 2/21/2023 |  | 1/1/2023
PJM | AF1-097 | Zion-E College Ave 34 kV |  | PA | Centre | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/30/2019 | 9/19/2019 |  | 1/1/2023
PJM | AF1-098 | Four Mile Jct-Corry East 115 kV | Wilson Solar | PA | Erie | Engineering and Procurement | PENELEC | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/30/2019 |  |  | 9/1/2026
PJM | AF1-099 - moved to TC1 | Moshannon-Milesburg 230 kV III |  | PA | Clearfield | Active | APS | 126.5 | 75.9 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 9/4/2019 |  |  | 4/1/2022
PJM | AF1-100 - moved to TC1 | Shawville-Moshannon 230 kV |  | PA | Clearfield | Withdrawn | PENELEC | 250 | 150 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/4/2019 | 6/21/2024 |  | 4/1/2022
PJM | AF1-101 | Oyster Creek 230 kV III |  | NJ | Ocean | Withdrawn | JCPL | 800 | 224.8 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/6/2019 | 7/15/2021 |  | 11/23/2022
PJM | AF1-102 | Gans 138 kV II | Gans CT | PA | Fayette | In Service | APS | 0 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/6/2019 |  |  | 9/1/2023 | 3/11/2021
PJM | AF1-103 | Warren 34.5 kV |  | PA | Warren | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/10/2019 | 9/12/2023 |  | 6/1/2023
PJM | AF1-104 | Erie West 34.5 kV | Elder West | PA | Erie | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/10/2019 | 11/15/2024 |  | 10/15/2026
PJM | AF1-105 | Glen Gardner 34.5 kV | Holly Glen | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/10/2019 | 4/17/2023 |  | 12/31/2024
PJM | AF1-106 | East Sayre 34.5 kV | Ellistown Solar & BESS | PA | Bradford | Engineering and Procurement | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Storage; Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 9/10/2019 |  |  | 6/1/2023
PJM | AF1-107 | Pohatcong 230 kV |  | NJ | Warren | Withdrawn | JCPL | 60 | 60 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 9/10/2019 | 4/13/2020 |  | 6/1/2023
PJM | AF1-108 | East Flemington 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 20 | Capacity | Generation Interconnection | Storage; Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/10/2019 | 11/22/2022 |  | 6/1/2023
PJM | AF1-109 | Pleasant Valley 230 kV |  | NJ | Mercer | Withdrawn | PSEG | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/10/2019 | 9/11/2023 |  | 6/1/2023
PJM | AF1-110 | Kingsland 26 kV |  | NJ |  | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2019 | 9/23/2019
PJM | AF1-111 | Kingsland 26 kV |  | NJ |  | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2019 | 9/23/2019
PJM | AF1-112 | Centre Hall-Boalsburg 46 kV | Centre Hall | PA | Centre | Withdrawn | APS | 15 | 8.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/11/2019 | 7/29/2024 |  | 10/31/2026
PJM | AF1-113 | Gristmill 345 kV |  | OH | Auglaize | Withdrawn | AEP | 180 | 137.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/11/2019 | 9/14/2023 |  | 6/1/2022
PJM | AF1-114 | Oak Grove-Dahlgren 230 kV | Gibson Solar I | VA | King George | Suspended | Dominion | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/12/2019 |  |  | 5/1/2027
PJM | AF1-115 | Poolesville 230 kV |  | VA | Surry | Withdrawn | Dominion | 60 | 40.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/12/2019 | 10/9/2020 |  | 12/1/2021
PJM | AF1-116 - moved to TC1 | Marion County 161 kV |  | KY | Washington | Active | EKPC | 120 | 72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/12/2019 |  |  | 12/29/2023
PJM | AF1-117 | Atlanta-Stuart 345 kV |  | OH | Ross | Withdrawn | AEP | 200 | 152.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/13/2019 | 9/14/2023 |  | 6/1/2023
PJM | AF1-118 | Sorenson-Desoto 345 kV |  | IN | Wells | Active | AEP | 350 | 268.9 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/13/2019 |  |  | 6/1/2022
PJM | AF1-119 | Keystone-Desoto 345 kV | Lake Trout Solar | IN | Blackford | Active | AEP | 200 | 140 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/13/2019 |  |  | 1/31/2028
PJM | AF1-120 | East Fayette 2 138 kV | Arche Energy Project | OH | Fulton | In Service | ATSI | 40 | 26.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/31/2019 |  |  | 12/31/2023 | 1/17/2024
PJM | AF1-121 | Crain Highway 13 kV |  | MD | Prince George's | Withdrawn | PEPCO | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/17/2019 | 3/5/2020 |  | 11/30/2021
PJM | AF1-122 | Cardington-Liberty 69 kV | Morrow County Solar II | OH | Morrow | Suspended | ATSI | 64 | 26.88 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/17/2019 |  |  | 3/31/2029
PJM | AF1-123 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 833 | 253.2 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | In Progress | Interim Study | 9/17/2019 |  |  | 12/31/2025
PJM | AF1-124 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 836 | 254.1 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | In Progress | Interim Study | 9/17/2019 |  |  | 12/31/2026
PJM | AF1-125 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 820 | 249.3 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | In Progress | Interim Study | 9/17/2019 |  |  | 12/31/2024
PJM | AF1-126 | Cookstown 230 kV |  | NJ | Burlington | Withdrawn | JCPL | 250 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/17/2019 | 10/1/2020 |  | 10/22/2022
PJM | AF1-127 | Avon 345 kV |  | KY | Fayette | Withdrawn | EKPC | 80 | 53.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/17/2019 | 9/13/2023 |  | 12/1/2023
PJM | AF1-128 - moved to TC1 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 569 | 569 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | In Progress | Interim Study | 9/18/2019 |  |  | 6/1/2023
PJM | AF1-129 | Chesterfield 230 kV | Chesterfield CT Units 3&4 | VA | Chesterfield | Engineering and Procurement | Dominion | 569 | 569 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/18/2019 |  |  | 12/31/2029
PJM | AF1-130 | Inez 138 kV | Martin County Solar Project | KY | Martin | Partially in Service - Under Construction | AEP | 177 | 133.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/20/2019 |  |  | 12/15/2025
PJM | AF1-131 | Clearville-Clearville Junction 34.5 kV |  | PA | Bedford | Withdrawn | APS | 16.15 | 9.69 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/18/2019 | 9/28/2020 |  | 6/1/2021
PJM | AF1-132 | Shingletown-Boalsburg 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/18/2019 | 12/15/2020 |  | 4/1/2021
PJM | AF1-133 | Pequest River-Richmond 34.5 kV | NH Gravel Hill at Martins Creek | PA | Northampton | Withdrawn | ME | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/18/2019 | 6/9/2023 |  | 2/28/2023
PJM | AF1-134 | Philipsburg-Madera 34.5 kV | CL-Green Acres | PA | Clearfield | Suspended | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/19/2019 |  |  | 6/30/2026
PJM | AF1-135 | Madera 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/18/2019 | 3/19/2020 |  | 4/1/2022
PJM | AF1-136 | Warfordsburg-Purcell Junction 34.5 kV | FU-Hanks Solar | PA | Fulton | Engineering and Procurement | APS | 15.72 | 9.43 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/19/2019 |  |  | 11/17/2026
PJM | AF1-137 | Newlinville 34.5 kV | Ch-Valley Solar | PA | Chester | Withdrawn | PECO | 9.8 | 5.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/18/2019 | 4/27/2024 |  | 4/10/2023
PJM | AF1-138 | Huntingdon-Warrier Ridge 46 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/18/2019 | 3/19/2020 |  | 4/1/2022
PJM | AF1-139 | Thompson 34.5 kV |  | PA | Wayne | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/18/2019 | 3/19/2020 |  | 6/1/2022
PJM | AF1-140 | Claysburg 23 kV | BL-Diamond Bear Rocks | PA | Adams | Engineering and Procurement | PENELEC | 16.3 | 9.78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/19/2019 |  |  | 12/31/2025
PJM | AF1-141 | Varner 138 kV | Thalassa Energy Project | IN | DeKalb | Withdrawn | AEP | 96 | 62.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 8/30/2019 | 10/16/2024 |  | 5/31/2022
PJM | AF1-142 - moved to TC1 | Moshannon-Milesburg 230 kV IV |  | PA | Clearfield | Active | APS | 202.4 | 121.44 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/4/2019 |  |  | 4/1/2022
PJM | AF1-143 | Lick Run 115 kV | Rockdale Solar | PA | Somerset | Engineering and Procurement | PENELEC | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/18/2019 |  |  | 12/31/2027
PJM | AF1-144 | Hayden 345 kV | Hayden Run | OH | Franklin | Withdrawn | AEP | 100 | 66.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/18/2019 | 6/6/2024 |  | 12/1/2023
PJM | AF1-145 | Flanders-Netcong 34.5 kV |  | NJ | Morris | Withdrawn | JCPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/18/2019 | 10/7/2019 |  | 10/1/2021
PJM | AF1-146 | Hoytdale -McClelland 345 kV | Firefly Solar | PA | Lawrence | Withdrawn | ATSI | 201.95 | 121.17 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/18/2019 | 12/2/2024 |  | 9/1/2026
PJM | AF1-147 | Poland Rd-Runway DP 230kV | Dulles Solar | VA | Loudoun | Engineering and Procurement | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/20/2019 |  |  | 12/31/2023
PJM | AF1-148 | Sorenson-Desoto 345 kV |  | IN | Wells | Withdrawn | AEP | 159 | 95.4 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/19/2019 | 11/8/2024 |  | 4/30/2023
PJM | AF1-149 | Graymont-Zion 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/19/2019 | 10/1/2020 |  | 3/1/2021
PJM | AF1-150 | Midfield 22.9 kV | Pittsburgh International Airport | PA | Allegheny | In Service | DL | 14.4 | 4.28 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/19/2019 |  |  | 9/1/2021 | 10/28/2021
PJM | AF1-151 | Fayetteville 34.5 kV |  | PA | Franklin | Withdrawn | APS | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/19/2019 | 3/6/2020 |  | 12/31/2022
PJM | AF1-152 - moved to TC1 | Swamp 230 kV |  | NC | Pasquotank | Active | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/19/2019 |  |  | 10/2/2023
PJM | AF1-153 | Motion-Ridgeway 46 kV | Jakes Hollow Solar | PA | Elk | Suspended | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/19/2019 |  |  | 9/1/2026
PJM | AF1-154 | Dauphin |  | PA | Dauphin | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/19/2019 | 10/8/2019 |  | 5/1/2022
PJM | AF1-155 | Paper City-Wilcox 46 kV | EL-Mefferts Run | PA | Elk | Engineering and Procurement | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/19/2019 |  |  | 2/28/2026
PJM | AF1-156 | Braidwood-Davis Creek |  | IL | Kankakee | Withdrawn | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/19/2019 | 9/11/2023 |  | 9/30/2021
PJM | AF1-157 | Laurel-Sussex 69 kV |  | DE | Sussex | Withdrawn | DPL | 25 | 15 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/20/2019 | 10/12/2020 |  | 12/31/2022
PJM | AF1-158 | Edison-Gravel Pit 138 kV | Honeysuckle Solar Project | IN | St. Joseph | Partially in Service - Under Construction | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/24/2019 |  |  | 1/31/2025
PJM | AF1-159 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | Under Construction | Dayton | 0 | 10.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/21/2019 |  |  | 12/31/2024
PJM | AF1-160 | Silver Lake 69 kV |  | NJ | Camden | Withdrawn | AEC | 20 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Withdrawn | 9/20/2019 | 3/22/2022 |  | 11/1/2021
PJM | AF1-161 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 50 | 25 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/20/2019 |  |  | 3/1/2022
PJM | AF1-162 | Inez 138 kV |  | KY | Martin | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Interim Study | 9/20/2019 |  |  | 12/1/2023
PJM | AF1-163 | Barren-Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 120 | 80.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/20/2019 | 12/11/2019 |  | 6/1/2022
PJM | AF1-164 | Southwest Lima 345 kV | Birch Solar | OH | Allen | Withdrawn | AEP | 300 | 195 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/20/2019 | 1/9/2025 |  | 12/31/2027
PJM | AF1-165 | Campbelltown-Millars Quarry 69 kV | East Ridge Solar | PA | Lebanon | Withdrawn | ME | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/23/2019 | 12/5/2024 |  | 1/31/2027
PJM | AF1-166 | Target-Chambers No.5 34.5 kV | FR-BOYER MILL 1 | PA | Franklin | Withdrawn | APS | 16 | 9.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/23/2019 | 11/22/2023 |  | 2/28/2023
PJM | AF1-167 | West Freedom-C&K Coal 25 kV | CL-Route 58 B | PA | Clarion | Suspended | APS | 13.515 | 8.109 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/24/2019 |  |  | 1/31/2026
PJM | AF1-168 | Kingsland 26.4 kV I |  | NJ | Bergen | Withdrawn | PSEG | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2019 | 10/8/2019 |  | 9/30/2020
PJM | AF1-169 | Kingsland 26.4 kV II |  | NJ | Bergen | Withdrawn | PSEG | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2019 | 10/8/2019 |  | 9/30/2020
PJM | AF1-170 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 77.5 | 46.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/23/2019 | 12/3/2024 |  | 2/15/2023
PJM | AF1-171 | Jamestown-Hartstown 69 kV |  | PA | Crawford | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/23/2019 | 12/15/2020 |  | 2/15/2023
PJM | AF1-172 | Moshannon-Chapman 230 kV |  | PA | Clinton | Withdrawn | PENELEC | 250 | 150 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/24/2019 | 3/2/2020 |  | 10/31/2022
PJM | AF1-173 | Gretna DP-Shockoe DP 69 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 0 | 13.95 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/23/2019 | 9/12/2023 |  | 12/15/2020
PJM | AF1-174 | Newlinville 34.5 kv II | Ch-Goosetown Solar | PA | Chester | Withdrawn | PECO | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/25/2019 | 4/27/2024 |  | 6/1/2022
PJM | AF1-175 | Donald C Cook-Jackson Road 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 152 | 91.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 9/24/2019 | 4/16/2020 |  | 4/30/2023
PJM | AF1-176 - moved to TC1 | Corey 138 kV |  | MI | St. Joseph | Active | AEP | 300 | 155.684 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 9/25/2019 |  |  | 10/31/2022
PJM | AF1-177 | Warren 115 kV | Warren Generating Station | PA | Warren | In Service | PENELEC | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/1/2023 | 7/1/2020
PJM | AF1-178 | Tolna 2 115 kV | Tolna Unit 2 | PA | York | In Service | ME | 1.5 | 1.5 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-179 | Tolna 1 115 kV | Tolna Unit 1 | PA | York | In Service | ME | 1 | 1 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-180 | Titus 4 & 5 69 kV | Titus Generating Station (Titus CT 4 and Titus CT 5) | PA | Berks | In Service | ME | 2 | 2 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-181 | Shawville 3 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 3 | 3 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-182 | Shawville 4 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 4 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-183 | Shawville 1 230 kV | Shawville Generating Station | PA | Adams | In Service | PENELEC | 1 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-184 | Shawnee 1 34.5 kv | Shawnee Generating Station (CT 1) | PA | Monroe | In Service | ME | 1 | 1 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-185 | Sayreville 1-2-3 230 kV | Sayreville Facility (Raritan River) | NJ | Middlesex | In Service | JCPL | 0 | 5.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 3/10/2020 | 3/10/2020
PJM | AF1-186 | Portland 5 230 kV | Portland Station Unit 5 | PA | Northampton | In Service | ME | 6.5 | 6.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-187 | Portland 3 & 4 115 kV | Portland Station Unit 3 and Unit 4 | PA | Northampton | In Service | ME | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-188 | Orrtanna 115 kV | Orrtanna Station Unit C1 | PA | Adams | In Service | ME | 1 | 1 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-189 | Niles CT A 23 kV | Niles A CT | OH | Trumbull | In Service | ATSI | 1.5 | 1.5 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-190 | New Castle 4 69 kV | New Castle Generating Station | PA | Lawrence | In Service | ATSI | 1 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-191 | New Castle 5 138 kV | New Castle Generating Station | PA | Lawrence | In Service | ATSI | 4 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-192 | Mountain 2 115 kV | Mountain Station Unit C2 | PA | Cumberland | In Service | ME | 1 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-193 | Hunterstown 115 kV | Hunterstown CT Facility | PA | Adams | In Service | ME | 4 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-194 | Hamilton CT1 115 kV | Hamilton Station | PA | York | In Service | ME | 1 | 1 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-195 | Gilbert CT9 230 kV | Gilbert Station Unit 9 | NJ | Hunterdon | In Service | JCPL | 0 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 3/10/2020 | 3/10/2020
PJM | AF1-196 | Gilbert CT 5-6-7 230 kV | Gilbert Station 4x1 Combined Cycle (Unit 4, Unit 5, Unit 6, Unit 7, and Unit 8) | NJ | Hunterdon | In Service | JCPL | 0 | 14.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 3/10/2020 | 3/10/2020
PJM | AF1-197 | Brunot Island 138 kV |  | PA | Allegheny | Withdrawn | DL | 15 | 15 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 9/25/2019 | 3/5/2020 |  | 10/1/2019
PJM | AF1-198 | Blossburg #1 CT 34.5 kV | Blossburg Station Unit 1 | PA | Tioga | In Service | PENELEC | 2.5 | 2.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/26/2019 |  |  | 9/30/2023 | 7/1/2020
PJM | AF1-199 | Avon Lake 10 138 kV | Avon Lake Plant | OH | Lorain | Deactivated | ATSI | 4 | 4 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Not Required | Document Posted | 9/25/2019 |  |  | 9/1/2023 | 7/1/2020
PJM | AF1-201 - moved to TC1 | Hayes-White Marsh 115 kV |  | VA | Gloucester | Withdrawn | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/24/2019 | 6/24/2024 |  | 12/31/2021
PJM | AF1-202 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 34 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress | Interim Study | 9/25/2019 |  |  | 12/31/2022
PJM | AF1-203 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | In Service | EKPC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 4/30/2024 | 6/7/2024
PJM | AF1-204 - moved to TC1 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 255 | 63.75 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 9/25/2019 |  |  | 12/31/2022
PJM | AF1-205 | Napoleon Muni 138 kV | Henry County Solar | OH | Henry | Suspended | AMPT | 40 | 24 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2019 |  |  | 8/1/2026
PJM | AF1-206 | East Fayette 138 kV | CG Fulton County | OH | Fulton | Engineering and Procurement | ATSI | 199 | 119.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2019 |  |  | 5/31/2028
PJM | AF1-207 | Reynolds-Olive #1 345 kV | Hoosier Line Solar | IN | White | Active | AEP | 180 | 34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/27/2019 |  |  | 12/31/2022
PJM | AF1-208 | Laurel-Roadstown 69 kV | Horse Run Solar I | NJ | Salem | Engineering and Procurement | AEC | 45 | 27 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/26/2019 |  |  | 12/31/2028
PJM | AF1-209 | Guilford 34.5 kV | FR Boyer Mill 2 | PA | Franklin | Withdrawn | APS | 15.9 | 9.54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/26/2019 | 11/22/2023 |  | 9/30/2022
PJM | AF1-210 | Burma 23 kV | CL-Route 58 S | PA | Clarion | Withdrawn | APS | 15.9 | 9.54 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/26/2019 | 9/19/2024 |  | 6/1/2022
PJM | AF1-211 | Campbelltown-Millars Quarry 69 kV | Palmyra Solar | PA | Lebanon | Withdrawn | ME | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/26/2019 | 12/5/2024 |  | 1/31/2027
PJM | AF1-212 | Campbelltown-Millars Quarry 69 kV | Bellegrove Solar | PA | Lebanon | Withdrawn | ME | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/26/2019 | 12/5/2024 |  | 1/31/2027
PJM | AF1-213 | Bionol-Madera 115 kV |  | PA | Clearfield | Withdrawn | PENELEC | 151.8 | 91.08 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/26/2019 | 4/13/2020 |  | 6/1/2023
PJM | AF1-214 | Nittany-Zion 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/26/2019 | 12/3/2020 |  | 5/1/2022
PJM | AF1-215 | Olive-Reynolds 345 kV | Mammoth North Solar Project | IN | Starke | In Service | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2019 |  |  | 7/31/2024 | 11/8/2024
PJM | AF1-216 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Withdrawn | PPL | 143.11 | 85.87 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/26/2019 | 8/30/2023 |  | 5/31/2021
PJM | AF1-217 | Edinboro -Cambridge Springs 34.5 kV | Crawford Solar II | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2019 |  |  | 3/29/2024
PJM | AF1-218 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 15 | 6.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/27/2019 | 10/17/2019 |  | 12/31/2020
PJM | AF1-219 | Hunt Farm 69 kV |  | KY | Boyle | Withdrawn | EKPC | 30 | 20.4 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/27/2019 | 9/9/2020 |  | 6/1/2022
PJM | AF1-220 | Ridgway-Whetstone 115 kV |  | PA | Elk | Withdrawn | PENELEC | 151.7 | 91 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/27/2019 | 8/4/2020 |  | 3/1/2022
PJM | AF1-221 - moved to TC1 | College Corner-Drewersburg 138 kV |  | IN | Franklin | Withdrawn | AEP | 180 | 25.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/27/2019 | 1/17/2025 |  | 6/1/2022
PJM | AF1-222 | Oceanview Wind 2 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 510 | 140.25 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 9/27/2019 | 8/28/2023 |  | 12/30/2025
PJM | AF1-223 | Keystone-Desoto 345 kV |  | IN | Jay | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/27/2019 |  |  | 12/31/2022
PJM | AF1-224 | Fayetteville 34.5 kV | Fayetteville Solar | PA | Franklin | Withdrawn | APS | 11.9 | 7.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/27/2019 | 10/10/2023 |  | 3/31/2022
PJM | AF1-225 | Milnor 34.5 kV |  | PA | Franklin | Withdrawn | APS | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 9/27/2019 | 9/7/2023 |  | 12/30/2021
PJM | AF1-226 | Bowmans Mill-Scott 69 kV | Cottontail Solar 7 | PA | Columbia | Suspended | PPL | 35 | 14.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2019 |  |  | 11/30/2028
PJM | AF1-227 | Marysville – Gunn Road 345 kV | Union Solar | OH | Union | In Service | AEP | 325 | 195 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 12/31/2024 | 11/15/2024
PJM | AF1-228 | Beatty-Greene 345 kV | Springwater Solar | OH | Madison | Engineering and Procurement | AEP | 155 | 93 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2019 |  |  | 8/31/2026
PJM | AF1-229 | Galion-South Berwick 345 kV | Tymochtee Solar | OH | Wyandot | Engineering and Procurement | AEP | 120 | 72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2019 |  |  | 8/31/2026
PJM | AF1-230 | Chatfield 138 kV |  | OH | Crawford | Withdrawn | AEP | 49 | 29.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/27/2019 | 2/5/2020 |  | 10/31/2022
PJM | AF1-231 | New Church 138 kV |  | VA | Accomack | Withdrawn | DPL | 19 | 7.6 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 9/27/2019 | 9/10/2024 |  | 12/31/2022
PJM | AF1-232 | Allegheny-Somerset 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 160 | 104 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/27/2019 | 1/19/2021 |  | 5/31/2022
PJM | AF1-233 - moved to TC1 | Flemingsburg – Spurlock 138kV | AEUG Fleming Solar | KY | Fleming | Active | EKPC | 188.5 | 113.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress | Interim Study | 9/27/2019 |  |  | 5/31/2022
PJM | AF1-234 | Baldy-Wesnberg 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/27/2019 | 11/11/2019 |  | 12/15/2022
PJM | AF1-235 | Sunbury 500 kV |  | PA | Snyder | Withdrawn | PPL | 617 | 617 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 9/27/2019 | 3/2/2020 |  | 5/1/2023
PJM | AF1-236 | Mackeys 230 kV |  | NC | Tyrell | Withdrawn | Dominion | 1210 | 459.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/27/2019 | 8/19/2022 |  | 9/30/2024
PJM | AF1-237 | Mercer 230 kV | Lamberton Road Battery | NJ | Mercer | Engineering and Procurement | Unknown | 170 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2019 |  |  | 8/11/2027
PJM | AF1-238 - moved to TC1 | Sherman Ave - West Vineland 69 kV |  | NJ | Cumberland | Active | AEC | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/28/2019 |  |  | 5/31/2023
PJM | AF1-239 | Sherman Ave - West Vineland 69 kV | South Orchard | NJ | Cumberland | Engineering and Procurement | AEC | 30 | 12 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2019 |  |  | 6/1/2028
PJM | AF1-240 - moved to TC1 | Timblin 34.5 kV |  | PA | Armstrong | Active | PENELEC | 17.5 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2019 |  |  | 7/1/2022
PJM | AF1-241 | Watson 12.47 kV |  | PA | Adams | Withdrawn | PPL | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 2/24/2020 |  | 7/1/2022
PJM | AF1-242 | Wilcox-Paper City 46 kV |  | PA | Adams | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 3/19/2020 |  | 8/1/2022
PJM | AF1-243 | Tasley 25 kV |  | VA | Accomack | Withdrawn | ODEC | 5 | 5 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/30/2019 | 10/9/2020 |  | 6/30/2020
PJM | AF1-244 | Kingston 12 kV |  | MD | Somerset | Withdrawn | DPL | 8 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 6/7/2021 |  | 6/30/2020
PJM | AF1-245 | Hudson 230 kV | Hudson Energy Storage Facility | NJ | Hudson | Engineering and Procurement | PSEG | 200 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 12/1/2028
PJM | AF1-246 | Clover-Rawlings 500 kV |  | VA | Charlotte | Withdrawn | Dominion | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 4/23/2024 |  | 7/1/2022
PJM | AF1-247 | Woodsdale 345 kV |  | OH | Butler | Withdrawn | DEOK | 50 | 30.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2019 | 1/27/2020 |  | 10/20/2021
PJM | AF1-248 | Northern Neck 34.5 kV | Gardy’s Mill Solar | VA | Westmoreland | In Service | Dominion | 0 | 2.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 12/30/2020 | 6/1/2023
PJM | AF1-249 | Nickel 12.47 kV | Nickel Solar | OH | Warren | In Service | DEOK | 19.92 | 14 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/2/2019 |  |  | 10/18/2024 | 12/5/2024
PJM | AF1-250 | Maysville 69 kV II |  | PA | Mercer | Withdrawn | ATSI | 18 | 10.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 9/24/2021 |  | 6/30/2022
PJM | AF1-251 | Avon-North Clark 345 kV |  | KY | Clark | Withdrawn | EKPC | 220 | 132 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 9/13/2023 |  | 5/15/2023
PJM | AF1-252 - moved to TC1 | Kincaid-Pana |  | IL | Christian | Withdrawn | ComEd | 62.4 | 62.4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 6/24/2024 |  | 9/1/2022
PJM | AF1-253 - moved to TC1 | Kincaid-Pana |  | IL | Christian | Withdrawn | ComEd | 43.2 | 43.2 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 6/24/2024 |  | 9/1/2022
PJM | AF1-254 | Milnor-Huyetts 34.5 kV | FR-Williamsport | PA | Franklin | Engineering and Procurement | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 12/31/2025
PJM | AF1-255 | Osterburg-Claysburg 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 13.5 | 5.67 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 2/18/2020 |  | 12/31/2019
PJM | AF1-256 - moved to TC1 | Flemingsburg-Spurlock 138 kV |  | KY | Fleming | Withdrawn | EKPC | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 8/2/2024 |  | 6/1/2023
PJM | AF1-257 | Hawks 2 12 kV |  | NJ | Hunterdon | In Service | JCPL | 0 | 0.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 |  |  | 9/1/2023 | 5/10/2021
PJM | AF1-258 | Rockawalkin 69 kV | Hebron Solar | MD | Wicomico | In Service | DPL | 0 | 3.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 9/1/2023 | 11/5/2020
PJM | AF1-259 | Price 25 kV | Church Hill Solar | MD | Queen Anne's | In Service | DPL | 0 | 0.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 |  |  | 9/1/2023 | 9/10/2020
PJM | AF1-260 | Allenwood-Larrabee 2 34.5 kV | Lakewood-Farmingdale Road Solar Farm | NJ | Monmouth | In Service | JCPL | 0 | 1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 |  |  | 9/1/2023 | 9/8/2020
PJM | AF1-261 | Burlington 26 kV | North American Solar | NJ | Burlington | In Service | PSEG | 0 | 0.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 |  |  | 9/30/2023 | 6/1/2021
PJM | AF1-262 | Upper Pittsgrove 12 kV | Pittsgrove Solar | NJ | Salem | In Service | AEC | 0 | 0.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 |  |  | 9/1/2023 | 9/15/2022
PJM | AF1-263 | Bennett-Farmingdale 2 34.5 kV |  | NJ | Salem | Withdrawn | JCPL | 0 | 0.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 3/2/2020 |  | 10/1/2019
PJM | AF1-264 | Runnemede 13 kV | Owens Corning Solar | NJ | Gloucester | In Service | PSEG | 0 | 1.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 |  |  | 9/30/2023 | 6/1/2021
PJM | AF1-265 | Four Rivers-Hanover 230 kV |  | VA | Hanover | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 9/12/2023 |  | 12/31/2022
PJM | AF1-266 - moved to TC1 | Clubhouse-Sapony 230 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 74.5 | 74.5 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 6/24/2024 |  | 12/31/2022
PJM | AF1-267 | Union City Tap 138 kV |  | KY | Madison | Withdrawn | EKPC | 54 | 37 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 11/10/2020 |  | 1/31/2022
PJM | AF1-268 | Desoto-Jay 138 kV | Hawthorn Solar | IN | Delaware | Engineering and Procurement | AEP | 83 | 57.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 12/31/2027
PJM | AF1-269 | Airey-Golden Hill 69 kV |  | MD | Dorchester | Withdrawn | DPL | 11 | 11 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2019 | 5/12/2020 |  | 12/31/2022
PJM | AF1-270 - moved to TC1 | Blue Jacket-Kirby 138 kV |  | OH | Logan | Withdrawn | Dayton | 50 | 50 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 6/21/2024 |  | 12/31/2022
PJM | AF1-271 | Keisters-Krendale 138 kV |  | PA | Butler | Withdrawn | APS | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 10/11/2021 |  | 12/31/2023
PJM | AF1-271A | Gratz 69 kV | G Morris Solar | PA | Dauphin | Suspended | PPL | 17 | 10.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2019 |  |  | 4/15/2026
PJM | AF1-272 | Lucerne 115 kV | Hoodlebug Solar Energy Center | PA | Indiana | Engineering and Procurement | PENELEC | 110 | 66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2019 |  |  | 8/31/2027
PJM | AF1-273 | Allegheny 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 85 | 51 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 10/14/2020 |  | 12/31/2023
PJM | AF1-274 | Harvey Run 115 kV |  | PA | Clearfield | Withdrawn | PENELEC | 85 | 51 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2019 | 4/8/2020 |  | 12/31/2023
PJM | AF1-275 | Cole 345 kV |  | OH | Franklin | Active | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2019 |  |  | 12/31/2022
PJM | AF1-276 - moved to TC1 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Withdrawn | PENELEC | 100 | 67 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2019 | 6/24/2024 |  | 6/29/2024
PJM | AF1-277 - moved to TC1 | Lewis Run-Pierce Brook 2 230 kV |  | PA | McKean | Withdrawn | PENELEC | 100 | 67 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2019 | 6/21/2024 |  | 6/29/2024
PJM | AF1-278 - moved to TC1 | Lewis Run-Pierce Brook 3 230 kV |  | PA | Mc Kean | Withdrawn | PENELEC | 80 | 53.44 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2019 | 6/21/2024 |  | 6/29/2024
PJM | AF1-279 | Carlisle 138 kV |  | OH | Lorain | Withdrawn | ATSI | 150 | 90 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 9/20/2019 | 3/6/2023 |  | 12/15/2022
PJM | AF1-280 - moved to TC1 | Nelson-Lee County |  | IL | Lee | Active | ComEd | 200 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/10/2019 |  |  | 12/1/2022
PJM | AF1-281 - moved to TC1 | Nelson-Lee County |  | IL | Lee | Withdrawn | ComEd | 20 | 3 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/10/2019 | 6/24/2024 |  | 12/1/2022
PJM | AF1-282 | Stuart-Clinton 345 kV | Nuthatch Solar 5 | OH | Highland | Engineering and Procurement | Dayton | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 5/1/2030
PJM | AF1-283 | Stuart-Clinton 345 kV |  | OH | Highland | Active | Dayton | 130 | 78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2019 |  |  | 8/1/2022
PJM | AF1-284 | Penn Mar-Garrett 138 kV |  | MD | Garrett | Withdrawn | APS | 20 | 12.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 2/20/2020 |  | 12/31/2021
PJM | AF1-285 | Gunn Road 345 kV | Scioto Solar | OH | Hardin | Under Construction | AEP | 100 | 56 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 10/2/2019 |  |  | 12/31/2028
PJM | AF1-286 | East Sayre 34.5 kV II |  | PA | Bradford | Withdrawn | PENELEC | 13.6 | 5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn | Not Required | Wholesale Market Participation Agreement | 9/30/2019 | 9/26/2023 |  | 2/28/2026
PJM | AF1-287 | Edinboro South 34.5 kV II | Crawford Solar III | PA | Crawford | Suspended | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2019 |  |  | 1/31/2025
PJM | AF1-288 | Curryville-Claysburg 115 kV I |  | PA | Bedford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/27/2019 | 3/18/2020 |  | 3/1/2021
PJM | AF1-289 | Curryville-Claysburg 115 kV II |  | PA | Bedford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/27/2019 | 3/18/2020 |  | 3/1/2021
PJM | AF1-290 | Feagans Mill-Millville 138 kV | Blake Solar | WV | Jefferson | In Service | APS | 80 | 40.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/5/2019 |  |  | 4/15/2024 | 3/6/2024
PJM | AF1-291 | Tyler 34.5 kV | Chester Solar Technology Park | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 10/31/2022
PJM | AF1-291A | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2019 |  |  | 7/1/2024 | 12/27/2024
PJM | AF1-292 | Fields 34.5kV | Jarratt Solar | VA | Greensville | Engineering and Procurement | Dominion | 14.9 | 8.94 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 8/29/2027
PJM | AF1-293 - moved to TC1 | Kidds Store-Fort Union 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 127.86 | 108.37 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 6/24/2024 |  | 6/30/2022
PJM | AF1-294 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 41 | 24.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2019 |  |  | 12/1/2022
PJM | AF1-295 | Blain 115 kV II |  | PA | Perry | Withdrawn | PENELEC | 12 | 12 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 9/30/2019 | 3/25/2020 |  | 12/31/2022
PJM | AF1-296 - moved to TC1 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 212.1 | 37.3296 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 9/30/2019 |  |  | 9/15/2022
PJM | AF1-297 | North Longview 500 kV |  | PA | Greene | Withdrawn | APS | 52.8 | 31.68 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 10/28/2020 |  | 4/1/2022
PJM | AF1-298 | Desoto 345 kV |  | IN | Delaware | Withdrawn | AEP | 200 | 84 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 3/6/2020 |  | 10/31/2023
PJM | AF1-299 | Otter Point 34.5 kV I | Fairview Farms II | MD | Harford | Under Construction | BGE | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 12/30/2024
PJM | AF1-300 | Otter Point 34.5 kV II | Fairview Farms I | MD | Harford | Under Construction | BGE | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 12/30/2024
PJM | AF1-301 - moved to TC1 | Louisa-South Anna 230 kV |  | VA | Louisa | Withdrawn | Dominion | 117 | 70 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 6/24/2024 |  | 12/31/2022
PJM | AF1-302 | Brookville-Squab Hollow 138 kV |  | PA | Jefferson | Engineering and Procurement | PENELEC | 42 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 12/31/2026
PJM | AF1-303 | Vernon 115 kV |  | NJ | Atlantic | Withdrawn | JCPL | 107 | 21.4 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 9/30/2019 | 2/18/2020 |  | 5/31/2022
PJM | AF1-304 | Titusville-Grandview 115 kV |  | PA | Venango | Withdrawn | PENELEC | 100 | 60 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 9/12/2023 |  | 12/31/2023
PJM | AF1-305 | Maysville-Masury 138 kV |  | PA | Mercer | Withdrawn | ATSI | 35 | 21 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2019 | 10/16/2020 |  | 12/31/2023
PJM | AF1-306 - moved to TC1 | Squab Hollow 230 kV |  | PA | Elk | Withdrawn | APS | 197.2 | 49.3 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2019 | 6/21/2024 |  | 5/31/2023
PJM | AF1-307 | Seward-Jackson Rd 115 kV |  | PA | Indiana | Withdrawn | PENELEC | 66.5 | 39.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 10/28/2020 |  | 12/31/2023
PJM | AF1-308 | Waverly 138 kV |  | OH | Pike | Withdrawn | AEP | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 3/6/2020 |  | 12/31/2023
PJM | AF1-309 | North Hanover 115 kV |  | PA | Adams | Withdrawn | ME | 32 | 19.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 9/24/2020 |  | 12/31/2023
PJM | AF1-310 | Clover 230 kV |  | VA | Halifax | Withdrawn | Dominion | 300 | 114 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2019 | 11/5/2019 |  | 9/30/2022
PJM | AF1-311 | Montour 230 kV |  | PA | Montour | Withdrawn | PPL | 150 | 57 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 10/16/2023 |  | 9/30/2022
PJM | AF1-312 | Dan River-Ridgeway 138 kV |  | NC | Rockingham | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/30/2019 | 10/28/2019 |  | 12/31/2023
PJM | AF1-313 | Wes Del-Royerton 138 kV |  | IN | Delaware | Withdrawn | AEP | 40 | 24 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 10/9/2020 |  | 12/31/2022
PJM | AF1-314 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 212 | 37.2 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 9/30/2019 |  |  | 9/15/2022
PJM | AF1-315 | Cedarville-Ford 138 kV |  | OH | Clermont | Withdrawn | DEOK | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 10/9/2020 |  | 12/31/2023
PJM | AF1-316 | Katydid Road 345 kV |  | IL | Grundy | Withdrawn | ComEd | 132 | 52.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 3/13/2020 |  | 6/1/2022
PJM | AF1-317 | Electric Junction-Nelson 354 kV |  | IL | Lee | Withdrawn | ComEd | 0 | 20 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2019 | 10/23/2020 |  | 12/31/2023
PJM | AF1-318 - moved to TC1 | Crescent Ridge-Corbin |  | IL | Putnam | Withdrawn | ComEd | 299.97 | 52.7947 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 9/30/2019 | 6/21/2024 |  | 9/15/2022
PJM | AF1-319 | Honda Marysville Tap 69 kV |  | OH | Union | Withdrawn | Dayton | 58 | 38.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2019 | 11/8/2024 |  | 3/31/2022
PJM | AF1-320 | Merrill Creek 115 kV | Harmony Plains Solar and Storage Facility | NJ | Warren | Engineering and Procurement | JCPL | 70 | 42 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2019 |  |  | 3/31/2026
PJM | AF1-321 | Hooversville 115 kV I | SunEast Hooversville Solar | PA | Somerset | Suspended | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 8/1/2026
PJM | AF1-322 | Meadow Lake 345 kV | Black Prairie Solar Park | IN | White | Engineering and Procurement | AEP | 200 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/23/2019 |  |  | 7/1/2027
PJM | AF1-323 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 55 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2019 |  |  | 12/12/2022
PJM | AF1-324 | Greystone-West Denville 34.5 kV | Denville Storage Facility | NJ | Morris | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 | 12/3/2020 |  | 10/1/2021
PJM | AF1-325 | Sparta-Woodruff's Gap 34.5 kV | Houses Corner Storage | NJ | Sussex | Engineering and Procurement | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 1/1/2026
PJM | AF1-326 | Pohatcong-Newburgh 34.5 kV | Mansfield #1 | NJ | Warren | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 | 12/3/2020 |  | 10/1/2021
PJM | AF1-327 | Pohatcong-Newburgh 34.5 kV | Mansfield #2 | NJ | Warren | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2019 | 12/3/2020 |  | 10/1/2021
PJM | AF1-328 | Hackettstown-Pohatcong 34.5 kV | Mansfield #3 | NJ | Warren | Engineering and Procurement | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2019 |  |  | 3/1/2025
PJM | AF1-329 | Chickahominy 230 kV |  | VA | Charles City | Withdrawn | Dominion | 250 | 172.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/19/2019 | 10/10/2019 |  | 9/1/2021
PJM | AF1-330 | Marengo 34.5 kV |  | IL | McHenry | Active | ComEd | 20 | 16.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2019 |  |  | 9/15/2021
PJM | AF1-331 | Twombley Road |  | IL | Ogle | Active | ComEd | 20 | 20 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2019 |  |  | 9/15/2021
PJM | AF1-332 | Electric Jct-Nelson |  | IL | Lee | Withdrawn | ComEd | 50 | 20 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2019 | 3/9/2020 |  | 12/31/2023
PJM | AF1-333 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2019 |  |  | 9/30/2027
PJM | AF1-334 | Northkill 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/27/2019 | 8/4/2022 |  | 3/1/2021
PJM | AF1-335 | Northkill 230 kV |  | PA | Berks | Withdrawn | ME | 101.2 | 60.72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/27/2019 | 1/15/2021 |  | 3/1/2021
PJM | AF1-336 | Northkill 69 kV |  | PA | Berks | Withdrawn | ME | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/27/2019 | 8/4/2022 |  | 3/1/2021
PJM | AF1-337 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2019 |  |  | 9/30/2027
PJM | AF1-338 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/27/2019 |  |  | 9/30/2027
PJM | AF1-339 | Laurelton-Mifflinburg 69 kV | Limestone Solar | PA | Union | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2019 |  |  | 9/30/2027
PJM | AF2-001 | Hooversville 115 kV II | SunEast Hooversville Solar | PA | Somerset | Suspended | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2019 |  |  | 8/1/2026
PJM | AF2-002 | Hooversville 115 kV III | SunEast Hooversville Solar | PA | Somerset | Suspended | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2019 |  |  | 8/1/2026
PJM | AF2-003 | Powerton-Mole Creek |  | IL | Marshall | Withdrawn | ComEd | 303 | 53.328 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 10/1/2019 |  |  | 10/1/2023
PJM | AF2-004 | Beaver 345 kV |  | OH | Lorain | Active | ATSI | 33 | 33 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted |  | 10/1/2019 |  |  | 11/1/2020
PJM | AF2-005 | Beaver 138 kV | West Lorain 138 kV Power Plant | OH | Lorain | Engineering and Procurement | ATSI | 8 | 8 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2019 |  |  | 12/31/2028
PJM | AF2-006 | Jermyn Tap-Brownell 69 kV |  | PA | Lackawanna | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 10/1/2019 | 4/13/2021 |  | 9/16/2021
PJM | AF2-007 | Tinker Tap–East Carbondale 69 kV |  | PA | Lackawanna | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 10/1/2019 | 10/8/2020 |  | 9/15/2021
PJM | AF2-009 | Queen Street 34.5 kV |  | PA | York | Withdrawn | ME | 20 | 8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/10/2019 | 1/10/2020 |  | 10/1/2021
PJM | AF2-010 - moved to TC1 | Union City-Titusville 115 kV |  | PA | Erie | Active | PENELEC | 77 | 46 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 10/11/2019 |  |  | 12/15/2022
PJM | AF2-011 | Tait 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 0 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 10/11/2019 | 9/3/2020 |  | 5/31/2020
PJM | AF2-012 | Tait 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 104 | 104 | Capacity | Generation Interconnection | Natural Gas | Document Posted |  |  |  | 10/11/2019 | 9/1/2020 |  | 5/28/2021
PJM | AF2-013 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 10/15/2019 |  |  | 10/1/2023
PJM | AF2-014 | Maddox Creek 345 kV | Wild Grains Solar | OH | Van Wert | Engineering and Procurement | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/18/2019 |  |  | 12/31/2027
PJM | AF2-016 - moved to TC1 | Lewis 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 240 | 96 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 10/1/2019 | 6/21/2024 |  | 5/31/2023
PJM | AF2-017 | John's Creek 34 kV |  | KY | Pike | Withdrawn | AEP | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/31/2019 | 3/6/2020 |  | 12/31/2021
PJM | AF2-018 | Inez 138 kV | Lynn Bark Energy Center | KY | Martin | Engineering and Procurement | AEP | 200 | 133.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 11/1/2019 |  |  | 3/30/2028
PJM | AF2-019 | Middle 69 kV | Middle Battery Storage | NJ | Cape May | Engineering and Procurement | AEC | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 11/15/2019 |  |  | 4/30/2028
PJM | AF2-020 | Carll's Corner 69 kV | Carll's Corner Battery Storage | NJ | Cumberland | Active | AEC | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 11/15/2019 |  |  | 6/1/2021
PJM | AF2-021 - moved to TC1 | Cedar 69 kV |  | NJ | Ocean | Withdrawn | AEC | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 11/15/2019 | 5/31/2024 |  | 6/1/2021
PJM | AF2-022 | Cumberland 138 kV |  | NJ | Cumberland | Withdrawn | AEC | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 11/15/2019 | 9/1/2020 | 2 | 6/1/2021
PJM | AF2-023 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 42.5 | 17 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 11/15/2019 | 10/9/2023 |  | 6/1/2021
PJM | AF2-024 | Mickleton 69 kV | Mickleton Battery Storage | NJ | Gloucester | Engineering and Procurement | AEC | 24 | 9.6 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 11/15/2019 |  |  | 5/31/2028
PJM | AF2-025 - moved to TC1 | Ontario 69 kV |  | NJ | Atlantic | Active | AEC | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 11/15/2019 |  |  | 6/1/2021
PJM | AF2-026 | Sherman Ave 138 kV |  | NJ | Cumberland | Withdrawn | AEC | 30 | 12 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 11/15/2019 | 9/1/2020 |  | 6/1/2021
PJM | AF2-027 | Zion Energy Center 345 kV | Zion Energy Center - BESS | IL | Lake | Engineering and Procurement | ComEd | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 11/15/2019 |  |  | 8/25/2027
PJM | AF2-029 | Ronco 500 kV | Fayette Energy Facility | PA | Fayette | Engineering and Procurement | APS | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 10/28/2019 |  |  | 10/31/2027
PJM | AF2-030 | Ontelaunee 230 kV | Ontelaunee Power Generating Plant | PA | Berks | Engineering and Procurement | ME | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 10/28/2019 |  |  | 2/29/2028
PJM | AF2-031 | Calumet | Calumet BESS | IL | Cook | Engineering and Procurement | ComEd | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 10/28/2019 |  |  | 12/31/2027 | 12/31/2027
PJM | AF2-032 | Kincaid 345 kV |  | IL | Christian | Engineering and Procurement | ComEd | 20 | 13.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/28/2019 |  |  | 6/1/2021
PJM | AF2-033 | Miami Fort GT 138 kV |  | OH | Hamilton | Withdrawn | DEOK | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 10/28/2019 | 6/7/2021 |  | 6/1/2021
PJM | AF2-034 - moved to TC1 | Kendall 345kV |  | IL | Kendall | Active | ComEd | 20 | 10.8 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 10/28/2019 |  |  | 6/1/2021
PJM | AF2-035 - moved to TC1 | St. Johns 115 kV |  | VA | Hanover | Active | Dominion | 72 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 11/27/2019 |  |  | 10/27/2023
PJM | AF2-036 | Garner-Northern Neck 115 kV |  | VA | Richmond | Withdrawn | Dominion | 62 | 37.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/27/2019 | 1/23/2020 |  | 10/27/2023
PJM | AF2-037 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 94 | 56.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 11/29/2019 |  |  | 7/1/2021
PJM | AF2-038 | Printz 230 kV |  | PA | Delaware | Withdrawn | PECO | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 10/28/2019 | 4/20/2021 |  | 6/1/2021
PJM | AF2-039 | Shawville-Clearfield 34.5 kV |  | PA | Clearfield | Engineering and Procurement | PENELEC | 13.5 | 8.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/29/2019 |  |  | 9/1/2026
PJM | AF2-040 | Elk Run-Gainesville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 75 | 75 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 12/4/2019 | 6/23/2023 |  | 10/1/2023
PJM | AF2-041 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 12/9/2019 |  |  | 11/1/2023
PJM | AF2-042 - moved to TC1 | Clover-Rawlings 500 kV |  | VA | Halifax | Active | Dominion | 500 | 300 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 12/9/2019 |  |  | 12/31/2022
PJM | AF2-043 | Suffolk 34.5 kV | Pleasant Hill Solar | VA | City of Suffolk | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 12/11/2019 |  |  | 12/31/2022 | 6/20/2023
PJM | AF2-044 | Highland-Sammis and Highland-Mansfield 345 kV | Lordstown Energy Center | OH | Trumbull | In Service | ATSI | 0 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 12/10/2019 |  |  | 9/1/2023 | 10/20/2020
PJM | AF2-045 | Cambria Nug 115 kV | Cambria Energy | PA | Cambria | Withdrawn | PENELEC | 20 | 2 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 12/13/2019 | 10/8/2021 |  | 9/30/2022
PJM | AF2-046 - moved to TC1 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 140 | 93 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 12/19/2019 |  |  | 6/1/2022
PJM | AF2-047 - moved to TC1 | Creswell-Riders Creek 115 kV |  | NC | Washington | Withdrawn | Dominion | 150 | 99.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/19/2019 | 6/24/2024 |  | 6/1/2022
PJM | AF2-048 | Rio-Lick 138 kV | Dixon Solar | OH | Jackson | Engineering and Procurement | AEP | 70 | 46.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 12/19/2019 |  |  | 2/28/2028
PJM | AF2-049 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 60 | 34.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 12/20/2019 | 9/12/2023 |  | 12/1/2021
PJM | AF2-050 - moved to TC1 | Bearrock-Johnstown 230 kV |  | PA | Cambria | Active | PENELEC | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 12/23/2019 |  |  | 9/1/2021
PJM | AF2-051 | Geneva 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 50 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/6/2020 | 4/27/2021 |  | 6/1/2023
PJM | AF2-052 | Farmers Valley-Ridgeway 115 kV |  | PA | McKean | Withdrawn | PENELEC | 55 | 37 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 1/6/2020 | 8/28/2020 |  | 6/1/2023
PJM | AF2-053 | Chickahominy 500kV |  | VA | Charles City | Withdrawn | Dominion | 200 | 200 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 12/26/2019 | 1/21/2020 |  | 6/1/2024
PJM | AF2-054 | Wan 34.5 kV | Camellia Solar | VA | Gloucester | Engineering and Procurement | Dominion | 19.9 | 11.94 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/11/2020 |  |  | 8/29/2027
PJM | AF2-055 | Plaintation Creek 69 kV |  | VA | Northampton | Withdrawn | ODEC | 45 | 27 | Capacity | Generation Interconnection | Storage; Solar | Document Posted | Document Posted | Withdrawn |  | 1/16/2020 | 6/4/2024 |  | 6/1/2025
PJM | AF2-056 - moved to TC1 | Shenandoah Tap 1– Mahanoy Tap 2 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 50 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 1/16/2020 |  |  | 6/1/2023
PJM | AF2-057 | Grassfield 34.5 kV | Cedar Energy Center | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/22/2020 | 11/17/2023 |  | 12/1/2024
PJM | AF2-058 | Fairton 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 2.5 | 0 | Energy | Generation Interconnection | Solar | Document Posted |  |  |  | 1/24/2020 | 9/1/2020 |  | 3/31/2021
PJM | AF2-059 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/24/2020 | 4/26/2024 |  | 11/30/2022
PJM | AF2-060 | Wattsville 12 kV | Scout Storage I | VA | Accomack | Engineering and Procurement | DPL | 9 | 9 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/25/2020 |  |  | 4/1/2026
PJM | AF2-061 | Wattsville 69kV | Scout Energy Storage | VA | Accomack | Withdrawn | DPL | 40 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 1/24/2020 | 11/5/2024 |  | 6/30/2021
PJM | AF2-062 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Withdrawn | PENELEC | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 1/24/2020 | 9/3/2020 |  | 5/31/2023
PJM | AF2-063 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 1/29/2020 |  |  | 2/1/2023
PJM | AF2-064 | Flanders 115 kV |  | NJ | Warren | Withdrawn | JCPL | 15 | 15 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/29/2020 | 2/20/2020 |  | 12/18/2020
PJM | AF2-065 - moved to TC1 | Surry-Hopewell 230 kV |  | VA | Surry | Withdrawn | Dominion | 150 | 76.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/30/2020 | 6/24/2024 |  | 10/21/2021
PJM | AF2-066 | West Manchester-Crown 69kV |  | OH | Preble | Withdrawn | Dayton | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/30/2020 | 9/11/2024 |  | 10/3/2022
PJM | AF2-067 | West Manchester 69 kV |  | OH | Preble | Withdrawn | Dayton | 40 | 24 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 1/30/2020 | 9/11/2024 |  | 10/3/2022
PJM | AF2-068 - moved to TC1 | Jay 138 kV |  | IN | Blackford | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 1/30/2020 |  |  | 10/3/2022
PJM | AF2-069 - moved to TC1 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 9.3 | 2.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 1/31/2020 |  |  | 10/4/2021
PJM | AF2-070 - moved to TC1 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 18.15 | 3.1 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 1/31/2020 |  |  | 10/4/2021
PJM | AF2-071 | Windsor 230 kV |  | NJ | Mercer | Withdrawn | JCPL | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 1/31/2020 | 10/9/2023 |  | 3/1/2023
PJM | AF2-072 | Larrabee 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 50 | 25 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 1/31/2020 | 2/21/2023 |  | 3/1/2023
PJM | AF2-073 | Nucor Steel-Suffolk 230 kV |  | NC | Gates | Withdrawn | Dominion | 90 | 54.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/31/2020 | 7/2/2020 |  | 3/1/2024
PJM | AF2-074 | Nucor Steel-Suffolk 230 kV |  | NC | Gates | Withdrawn | Dominion | 40 | 24.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/31/2020 | 7/2/2020 |  | 3/1/2024
PJM | AF2-075 | Bartonsville-Meadow Brook 138 kV III | Bartonsville Energy Facility | VA | Frederick | In Service | APS | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/1/2020 |  |  | 7/1/2024 | 12/27/2024
PJM | AF2-076 | Suffolk-Nucor Steel 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2020 | 7/23/2021 |  | 12/1/2023
PJM | AF2-077 | White Marsh 34.5 kV | Winterberry Solar | VA | Gloucester | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/1/2020 |  |  | 8/14/2024 | 6/4/2024
PJM | AF2-078 | Reynolds-Olive #1 345 kV | Honey Creek Solar | IN | White | Active | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 2/1/2020 |  |  | 10/31/2022
PJM | AF2-079 | Greenville-West Milton 138 kV |  | OH | Darke | Withdrawn | Dayton | 165 | 99 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2020 | 9/19/2023 |  | 10/31/2023
PJM | AF2-080 - moved to TC1 | Chinquapin-Everetts 230 kV |  | NC | Pitt | Active | Dominion | 70 | 48.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 1/31/2020 |  |  | 6/30/2022
PJM | AF2-081 - moved to TC1 | Moyock 230 kV |  | NC | Currituck | Active | Dominion | 80 | 56 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 1/31/2020 |  |  | 12/1/2023
PJM | AF2-082 | Dauphin PG Tie–Dauphin Juniata Tie 69 k | Upper Paxton Solar | PA | Dauphin | Engineering and Procurement | PPL | 55 | 33 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 1/31/2020 |  |  | 8/31/2027
PJM | AF2-083 | Kenzie Creek-Stone Lake 69 kV |  | MI | Cass | Active | AEP | 150 | 100 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Interim Study | 1/31/2020 |  |  | 10/21/2022
PJM | AF2-084 | Honda-Marysville Tap 69 kV |  | OH | Union | Withdrawn | Dayton | 42 | 28.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 1/31/2020 | 11/8/2024 |  | 12/30/2022
PJM | AF2-085 | Midlothian 34.5 kV | Dry Bridge Energy Center | VA | Chesterfield | In Service | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/4/2020 |  |  | 12/31/2023 | 11/21/2023
PJM | AF2-086 | Scott Tap-Bowmans Mill Tap 69 kV | Stoneybrook Solar | PA | Columbia | Engineering and Procurement | PPL | 19.6 | 11.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/3/2020 |  |  | 12/31/2027
PJM | AF2-087 | East Altoona-Pinecroft 12.47 kV | Antis Solar Facility | PA | Blair | Withdrawn | PENELEC | 7.25 | 3.05 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/3/2020 | 11/9/2023 |  | 9/30/2022
PJM | AF2-088 | Shawville-Clearfield 34.5 kV II |  | PA | Clearfield | Engineering and Procurement | PENELEC | 6.5 | 3.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 2/5/2020 |  |  | 9/1/2026
PJM | AF2-089 | Titusville 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 5 | 3.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/6/2020 | 8/27/2020 |  | 12/31/2021
PJM | AF2-090 | Central Hardin 138 kV |  | KY | Hardin | Withdrawn | EKPC | 110 | 73.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/6/2020 | 12/16/2024 |  | 10/1/2022
PJM | AF2-091 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 34 | 14.28 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required |  | 2/7/2020 |  |  | 11/30/2021
PJM | AF2-092 | Snake Spring-Bedford Area 23 kV | Magenta Solar | PA | Bedford | Suspended | PENELEC | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/11/2020 |  |  | 8/11/2026
PJM | AF2-093 | Derry 12.47 kV |  | PA | Montour | Withdrawn | PPL | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 1/21/2020 | 8/25/2020 |  | 12/31/2021
PJM | AF2-094 | Huntington Jct. 138 kV |  | IN | Huntington | Withdrawn | AEP | 40 | 26.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/12/2020 | 1/17/2025 |  | 2/1/2022
PJM | AF2-095 - moved to TC1 | Davis Creek 138 kV |  | IL | Kankakee | Active | ComEd | 160 | 96 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 2/13/2020 |  |  | 5/31/2021
PJM | AF2-096 - moved to TC1 | Braidwood-East Frankfort 345 kV |  | IL | Will | Active | ComEd | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 2/12/2020 |  |  | 5/31/2022
PJM | AF2-097 | Fairview East 34.5 kV II |  | PA | Erie | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 2/13/2020 | 9/21/2020 |  | 12/31/2021
PJM | AF2-098 | Crittenden 12 kV |  | KY | Grant | Withdrawn | DEOK | 3.45 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/14/2020 | 4/30/2020 |  | 12/31/2020
PJM | AF2-099 | Taxville 2 13.2 kV | PA York Garber 2 | PA | York | Withdrawn | ME | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/28/2020 | 4/8/2024 |  | 9/30/2022
PJM | AF2-100 | Taxville 1 13.2 kV | PA York Garber 1 | PA | York | Withdrawn | ME | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/28/2020 | 4/8/2024 |  | 9/30/2022
PJM | AF2-101 | Allen 13.2 kV | PA Cumberland Diehl | PA | Cumberland | Withdrawn | ME | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/28/2020 | 4/8/2024 |  | 9/30/2022
PJM | AF2-102 | Germantown 13.2 kV | PA Adams Ramsburg | PA | Adams | Withdrawn | ME | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 1/29/2020 | 2/23/2024 |  | 2/1/2025
PJM | AF2-103 | Haviland 138 kV | Northwest Ohio Wind | OH | Paulding | Under Construction | AEP | 3.15 | 1.32 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Document Posted | 3/17/2020 |  |  | 2/1/2021 | 6/1/2021
PJM | AF2-104 | Somerset 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 4 | 2.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 2/21/2020 | 12/8/2020 |  | 6/1/2020
PJM | AF2-105 | Morgans Cut-Glen Lyn #2 138 kV | Bella Terra | VA | Pulaski | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 1/31/2020 | 8/19/2024 |  | 12/31/2026
PJM | AF2-106 | Hazel Hollow-Glen Lyn #1 138 kV |  | VA | Pulaski | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 1/31/2020 |  |  | 3/28/2022
PJM | AF2-107 | Clifford 138 kV |  | VA | Amherst | Active | AEP | 50 | 32.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 2/24/2020 |  |  | 2/1/2022
PJM | AF2-108 | Locks 34.5 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 10 | 10 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 2/25/2020 | 8/2/2022 |  | 10/31/2022
PJM | AF2-109 | Church 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 20 | 10 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 2/25/2020 | 8/21/2020 |  | 10/31/2022
PJM | AF2-110 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Suspended | Dominion | 20 | 7.72 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 2/27/2020 |  |  | 10/31/2025
PJM | AF2-111 - moved to TC1 | North Clark-Spurlock 345 kV |  | KY | Mason | Active | EKPC | 250 | 150 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 2/28/2020 |  |  | 12/31/2023
PJM | AF2-112 | Oakland-Gorman 69 kV | Webb Solar | MD | Garrett | Withdrawn | APS | 10 | 6.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/28/2020 | 9/5/2023 |  | 6/1/2022
PJM | AF2-113 | Clinton-Stuart 345 kV |  | OH | Clinton | Withdrawn | Dayton | 75 | 75 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/28/2020 | 3/26/2020 |  | 12/31/2022
PJM | AF2-114 | Old Chapel-Millville 138 kV II |  | WV | Jefferson | Withdrawn | APS | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 2/28/2020 | 10/17/2024 |  | 9/30/2022
PJM | AF2-115 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 25 | 15 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 2/28/2020 |  |  | 12/1/2022
PJM | AF2-116 | McConnellsburg 138 kV | Great Cove Solar | PA | Fulton | Withdrawn | APS | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/28/2020 | 11/20/2024 |  | 9/30/2027
PJM | AF2-117 | Warfordsburg-McConnellsburg 138 kV | Spring Run Solar | PA | Fulton | Withdrawn | APS | 70 | 46.67 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/28/2020 | 12/18/2024 |  | 12/31/2030
PJM | AF2-118 | Gilbert-Morris Park (A-27) 34.5 kV II |  | NJ | Warren | Withdrawn | JCPL | 19.99 | 3.999 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 2/28/2020 | 9/15/2020 |  | 3/31/2021
PJM | AF2-119 | Bristers-Sowego 115 kV |  | VA | Fauquier | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/28/2020 | 6/7/2024 |  | 12/12/2022
PJM | AF2-120 - moved to TC1 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 62 | 37.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress | Interim Study | 2/28/2020 |  |  | 12/1/2023
PJM | AF2-121 - moved to TC1 | Philipsburg-Shawville 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/29/2020 | 7/18/2024 |  | 6/1/2021
PJM | AF2-122 | Kirk 138 kV | Union Ridge Solar | OH | Licking | Engineering and Procurement | AEP | 107.7 | 64.62 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 2/29/2020 |  |  | 12/31/2025
PJM | AF2-123 | National-Tangy 138 kV |  | OH | Madison | Withdrawn | ATSI | 49 | 20.58 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/28/2020 | 8/14/2023 |  | 12/31/2023
PJM | AF2-124 | Kyger Creek-Pierce 345 kV |  | OH | Highland | Withdrawn | OVEC | 120 | 50.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 2/28/2020 | 12/13/2024 |  | 12/31/2023
PJM | AF2-125 | Varner 138 kV |  | IN | DeKalb | Withdrawn | AEP | 54 | 35.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 2/28/2020 | 10/16/2024 |  | 4/3/2023
PJM | AF2-126 - moved to TC1 | Weston 69 kV II |  | OH | Wood | Active | ATSI | 12 | 8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 2/28/2020 |  |  | 12/31/2021
PJM | AF2-127 | Lockwood Road 138 kV |  | OH | Defiance | Withdrawn | AEP | 38 | 24.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn | Interim Study | 2/28/2020 | 10/29/2024 |  | 3/31/2022
PJM | AF2-128 - moved to TC1 | Crescent Ridge-Corbin 138 kV |  | IL | Lasalle | Withdrawn | ComEd | 79.5 | 13.992 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 2/28/2020 | 6/25/2024 |  | 8/26/2024
PJM | AF2-129 | Sharon-Mercer 69 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/3/2020 | 6/9/2023 |  | 6/30/2023
PJM | AF2-130 | Cobalt Corners 34.5 kV | Cobalt Solar | PA | Clarion | Under Construction | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/4/2020 |  |  | 3/12/2025
PJM | AF2-131 | Cooper 34.5 kV |  | PA | York | Withdrawn | PECO | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/4/2020 | 8/25/2020 |  | 6/1/2022
PJM | AF2-132 | Reynolds-Olive #1 345 kV |  | IN | Pulaski | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/4/2020 |  |  | 5/31/2021
PJM | AF2-133 | Reynolds-Olive #2 345 kV |  | IN | Pulaski | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/4/2020 |  |  | 5/31/2021
PJM | AF2-134 | Olive-Reynolds #2 345 kV | Mammoth North Solar Project | IN | Starke | In Service | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/7/2020 |  |  | 6/30/2024 | 10/21/2024
PJM | AF2-135 | Rockwood-Confluence 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/5/2020 | 9/11/2020 |  | 6/1/2022
PJM | AF2-136 | Swamp 230 kV |  | NC | Perquimans | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/6/2020 | 9/12/2023 |  | 11/1/2022
PJM | AF2-137 | Marysville-Sorenson 765 kV | Grange Solar | OH | Logan | Active | AEP | 500 | 210 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/6/2020 |  |  | 12/31/2023
PJM | AF2-138 | Flanders-West Wharton 34.5 kV | Mount Olive Solar Farm | NJ | Morris | In Service | JCPL | 19.8 | 8.32 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/10/2020 |  |  | 5/31/2023 | 3/15/2023
PJM | AF2-139 | Gilbert-Warren Glen 34.5 kV | Holland Solar Farm | NJ | Hunterdon | In Service | JCPL | 8.8 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Document Posted | 3/10/2020 |  |  | 8/31/2022 | 7/28/2022
PJM | AF2-140 | Saegers 230 kV | Patriot Generating Station | PA | Lycoming | In Service | PPL | 0 | 30 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/12/2020 |  |  | 9/1/2024
PJM | AF2-141 | Lick Run 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 0 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 3/11/2020 | 7/11/2024 |  | 7/1/2023
PJM | AF2-142 - moved to TC1 | Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/12/2020 |  |  | 12/31/2023
PJM | AF2-143 - moved to TC1 | Powerton-Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/12/2020 |  |  | 12/31/2023
PJM | AF2-144 | Powhatan 34.5 kV | Scott 1 BESS | VA | Powhatan | In Service | Dominion | 17 | 10.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/12/2020 |  |  | 6/1/2023 | 6/1/2023
PJM | AF2-145 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Withdrawn | PPL | 51 | 30.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/12/2020 | 8/30/2023 |  | 12/31/2021
PJM | AF2-146 | Hill Valley-Valley REC 46 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/12/2020 | 4/16/2021 |  | 9/1/2023
PJM | AF2-147 | McVeytown-Strodes Mill 46 kV |  | PA | Mifflin | Withdrawn | PENELEC | 13.1 | 7.86 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/12/2020 | 8/23/2020 |  | 9/1/2023
PJM | AF2-148 | Shade Gap-Three Springs KTS 23 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 13.5 | 8.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/12/2020 | 4/16/2021 |  | 9/1/2023
PJM | AF2-149 | Sharp Road 69 kV | Frasier Solar | OH | Knox | Engineering and Procurement | AEP | 80 | 32 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/12/2020 |  |  | 1/31/2028
PJM | AF2-150 | Galion 138 kV | Blossom Solar | OH | Morrow | Engineering and Procurement | ATSI | 88 | 36.96 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/13/2020 |  |  | 4/30/2026
PJM | AF2-151 | Dillsburg 13.2 kV | PA York Hess | PA | York | Withdrawn | ME | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/16/2020 | 10/15/2024 |  | 9/30/2022
PJM | AF2-152 | Morgantown CT5 230 kV |  | MD | Charles | Withdrawn | PEPCO | 2 | 2 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Withdrawn |  | 3/16/2020 | 12/13/2022 |  | 2/28/2021
PJM | AF2-153 | Morgantown CT4 230 kV |  | MD | Charles | Withdrawn | PEPCO | 2 | 2 | Capacity | Generation Interconnection | Oil | Document Posted | Document Posted | Withdrawn |  | 3/16/2020 | 12/13/2022 |  | 2/28/2021
PJM | AF2-154 | Dickerson H2 CT 230 kV | Dickerson HCT1, HCT2, DCT1 | MD | Montgomery | In Service | PEPCO | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/16/2020 |  |  | 4/1/2023 | 5/31/2023
PJM | AF2-155 | Chalk Point CT3-CT6 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 13 | 13 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/16/2020 | 12/13/2022 |  | 2/28/2021
PJM | AF2-156 | Chalk Point CT2 69 kV | Chalk Point CT 2 | MD | Prince George's | In Service | PEPCO | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/16/2020 |  |  | 6/22/2023 | 5/31/2023
PJM | AF2-157 | Chalk Point CT1 69 kV |  | MD | Prince George's | Withdrawn | PEPCO | 0 | 1 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/16/2020 | 12/13/2022 |  | 2/28/2021
PJM | AF2-158 | Chalk Point Unit 4 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 4 | 4 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/16/2020 | 12/13/2022 |  | 2/28/2021
PJM | AF2-159 | Chalk Point ST3 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 2 | 2 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 3/16/2020 | 12/13/2022 |  | 2/28/2021
PJM | AF2-160 | Brunot Island 138 kV |  | PA | Allegheny | Withdrawn | DL | 3.5 | 3.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Withdrawn | 3/16/2020 | 12/13/2022 |  | 4/1/2020
PJM | AF2-161 | Mount Rock 12.47 kV | Ritner Solar | PA | Cumberland | Withdrawn | PPL | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/16/2020 | 10/15/2024 |  | 4/17/2023
PJM | AF2-162 | Keystone-Desoto 345 kV | Lake Trout Solar | IN | Blackford | Active | AEP | 45 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/16/2020 |  |  | 1/31/2028
PJM | AF2-163 | Lick Run 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 0 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/13/2020 | 9/12/2023 |  | 10/3/2022
PJM | AF2-164 - moved to TC1 | Handsome Lake 345 kV |  | PA | Venango | Withdrawn | PENELEC | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/17/2020 | 6/21/2024 |  | 9/15/2023
PJM | AF2-165 | Clark Summit-Emlenton 34.5 kV | Cardinal Solar | PA | Venango | Under Construction | PENELEC | 18.9 | 11.34 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/19/2020 |  |  | 5/16/2025
PJM | AF2-166 | Emlenton 34.5 kV | Long Bridge | PA | Venango | Suspended | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/18/2020 |  |  | 8/1/2026
PJM | AF2-167 | Eaton Crest-Red Bank 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 8 | 3.36 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/18/2020 | 9/4/2020 |  | 9/30/2021
PJM | AF2-168 | Princeton University 69 kV | Princeton University Generating Facility | NJ | Mercer | In Service | PSEG | 5 | 0 | Energy | Generation Interconnection | Natural Gas; Solar; Other | Document Posted | Document Posted | Not Required | Document Posted | 3/18/2020 |  |  | 4/27/2023 | 3/2/2022
PJM | AF2-169 | BL England 138 kV |  | NJ | Atlantic | Withdrawn | AEC | 552 | 155 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/19/2020 | 6/9/2020 |  | 6/1/2023
PJM | AF2-170 | Erie West-Springboro 34.5 kV |  | PA | Erie | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/19/2020 | 9/4/2020 |  | 9/15/2022
PJM | AF2-171 - moved to TC1 | Madisonville 115 kV |  | VA | Prince Edward | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/19/2020 |  |  | 3/31/2022
PJM | AF2-172 | Newport 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 10 | 3.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/19/2020 | 1/14/2021 |  | 6/1/2022
PJM | AF2-173 - moved to TC1 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 140 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/19/2020 |  |  | 10/31/2023
PJM | AF2-174 | Tabernacle 12 kV |  | NJ | Burlington | Withdrawn | AEC | 11 | 4.62 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/19/2020 | 4/26/2021 |  | 9/30/2021
PJM | AF2-175 | Straban 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn | Not Required | Wholesale Market Participation Agreement | 3/19/2020 | 9/19/2023 |  | 2/1/2025
PJM | AF2-176 - moved to TC1 | Masury-Maysville 138 kV |  | PA | Mercer | Withdrawn | ATSI | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/19/2020 | 6/21/2024 |  | 9/15/2022
PJM | AF2-177 - moved to TC1 | Sorenson-DeSoto #2 345 kV |  | IN | Blackford | Active | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 3/20/2020 |  |  | 10/31/2023
PJM | AF2-178 | Roxbury 23 kV II | Whitetail Solar 1 | PA | Franklin | In Service | PENELEC | 0 | 3.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/20/2020 |  |  | 9/1/2022 | 1/12/2021
PJM | AF2-179 | St. Thomas-Mercersburg 34.5 kV II | Whitetail Solar 2 | PA | Franklin | In Service | APS | 0 | 5.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/20/2020 |  |  | 9/1/2022 | 1/12/2021
PJM | AF2-180 | St. Thomas-Guilford 34.5 kV II | St Thomas Township Solar Facility | PA | Franklin | In Service | APS | 0 | 5.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/20/2020 |  |  | 9/1/2023 | 1/12/2021
PJM | AF2-181 | Lexington Park 69 kV |  | MD | St. Mary's | Withdrawn | SMECO | 0 | 3.1 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/20/2020 | 9/14/2020 |  | 9/1/2021
PJM | AF2-182 - moved to TC1 | Nelson-Lee County 345 kV II |  | IL | Lee | Active | ComEd | 300 | 0 | Energy | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 3/21/2020 |  |  | 12/1/2022
PJM | AF2-183 - moved to TC1 | Nelson-Lee County 345 kV |  | IL | Lee | Withdrawn | ComEd | 80 | 32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/20/2020 | 6/24/2024 |  | 12/1/2022
PJM | AF2-184 | McConnelsburg-Mercersburg 34 kV II |  | PA | Franklin | In Service | APS | 0 | 5.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/20/2020 |  |  | 10/7/2020 | 5/1/2023
PJM | AF2-185 | Mercersburg-Milnor 34.5 kV II | Elk Hill Solar 2 | PA | Franklin | In Service | APS | 0 | 4.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/20/2020 |  |  | 9/1/2022 | 1/4/2021
PJM | AF2-186 | South Cecil 69 kV |  | OH | Paulding | Withdrawn | AEP | 45 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/20/2020 | 7/18/2023 |  | 12/31/2023
PJM | AF2-187 | Brookside-Cloverdale 138 kV | Canal Road | OH | Wayne | Engineering and Procurement | ATSI | 120 | 78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/22/2020 |  |  | 11/30/2027
PJM | AF2-188 | Reynolds-Meadow Lake #1 345 kV |  | IN | White | Withdrawn | AEP | 112 | 67.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/22/2020 | 9/14/2023 |  | 6/30/2023
PJM | AF2-189 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/22/2020 | 9/17/2021 |  | 6/30/2023
PJM | AF2-190 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Withdrawn | AEP | 260 | 156 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/22/2020 | 9/10/2020 |  | 6/30/2023
PJM | AF2-191 | New Carlisle 138 kV |  | IN | St. Joseph | Withdrawn | AEP | 110 | 66 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/22/2020 | 10/16/2024 |  | 6/30/2023
PJM | AF2-192 | Frenchtown Solar-West Flemington 34.5 kV | Barbertown Solar | NJ | Hunterdon | Engineering and Procurement | JCPL | 7 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/23/2020 |  |  | 6/30/2026
PJM | AF2-193 - moved to TC1 | Indian River 230 kV I |  | DE | Sussex | Withdrawn | DPL | 440 | 119 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 3/23/2020 | 6/21/2024 |  | 10/31/2026
PJM | AF2-194 - moved to TC1 | Indian River 230 kV II |  | DE | Sussex | Withdrawn | DPL | 440 | 119 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 3/23/2020 | 6/21/2024 |  | 10/31/2026
PJM | AF2-195 | Queen Street 115 kV |  | PA | York | Withdrawn | ME | 171.7 | 68.68 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 3/23/2020 | 9/11/2020 |  | 12/31/2022
PJM | AF2-196 | Cedar Neck 69 kV II |  | DE | Sussex | Withdrawn | DPL | 30 | 9 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 3/23/2020 | 8/1/2022 |  | 6/1/2022
PJM | AF2-197 | East Towanda 115 kV |  | PA | Bradford | Withdrawn | PENELEC | 100.8 | 40.32 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 3/23/2020 | 9/8/2023 |  | 10/1/2022
PJM | AF2-198 | Heath 69 kV |  | OH | Licking | Withdrawn | AEP | 22.4 | 8.96 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/23/2020 | 9/8/2023 |  | 10/15/2022
PJM | AF2-199 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/24/2020 |  |  | 11/1/2023
PJM | AF2-200 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/24/2020 |  |  | 11/1/2023
PJM | AF2-201 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 199 | 51.4 | Capacity | Generation Interconnection | Wind; Solar | Document Posted | In Progress |  |  | 3/24/2020 |  |  | 5/31/2023
PJM | AF2-202 | Landis 12 V |  | NJ | Salem | Withdrawn | AEC | 2.7 | 1.14 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/24/2020 | 9/9/2020 |  | 6/30/2021
PJM | AF2-203 | Rohrsburg 12.5 kV |  | PA | Columbia | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/25/2020 | 4/12/2021 |  | 5/31/2022
PJM | AF2-204 | Van Buren-Delaware 138 kV |  | IN | Grant | Withdrawn | AEP | 110 | 72 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 3/24/2020 | 1/17/2025 |  | 6/1/2023
PJM | AF2-205 | Olive-Reynolds #2 345 kV | Moss Creek Solar | IN | Pulaski | Active | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Interim Study | 3/25/2020 |  |  | 3/30/2027
PJM | AF2-206 | Larrabee-Point Pleasant 34.5 kV |  | NJ | Monmouth | Withdrawn | JCPL | 15.4 | 6.47 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/24/2020 | 9/11/2020 |  | 12/31/2021
PJM | AF2-207 | Nelson 69 kV |  | DE | Sussex | Withdrawn | DPL | 50.4 | 20.16 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/24/2020 | 9/12/2023 |  | 10/15/2022
PJM | AF2-208 | Colora 230 kV |  | MD | Cecil | Withdrawn | DPL | 100.8 | 40.32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/24/2020 | 9/1/2023 |  | 10/15/2022
PJM | AF2-209 - moved to TC1 | South Hicksville-Sowers 138 kV |  | OH | Defiance | Active | AEP | 140 | 19.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/25/2020 |  |  | 6/2/2023
PJM | AF2-210 | Foster-Garver Road 345 kV |  | OH | Pickaway | Withdrawn | DEOK | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/25/2020 | 3/8/2021 |  | 12/31/2023
PJM | AF2-211 | College Corner 138 kV |  | IN | Henry | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/25/2020 | 4/15/2021 |  | 12/31/2023
PJM | AF2-212 | Shelby 138 kV |  | IN | Jay | Withdrawn | Dayton | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/25/2020 | 4/15/2021 |  | 12/31/2023
PJM | AF2-213 | Zions View-Smith Street 115 kV |  | PA | York | Withdrawn | ME | 81.2 | 32.48 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/25/2020 | 8/14/2023 |  | 10/15/2022
PJM | AF2-214 | Heartsease DP-Anaconda 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 151.2 | 60.5 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 3/25/2020 | 8/24/2020 |  | 12/2/2022
PJM | AF2-215 | Saint Thomas-LeMasters Junction 34.5 kV | Mercersburg Road Solar | PA | Franklin | Withdrawn | APS | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/25/2020 | 3/1/2024 |  | 4/12/2024
PJM | AF2-216 | Blue Jacket-Kirby 138 kV |  | OH | Union | Withdrawn | ATSI | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/25/2020 | 9/3/2020 |  | 8/30/2024
PJM | AF2-217 | Hyatt-Marysville 345 kV |  | OH | Union | Withdrawn | AEP | 220 | 132 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/25/2020 | 9/3/2020 |  | 8/30/2024
PJM | AF2-218 | Gettysburg 69 kV |  | OH | Darke | Withdrawn | Dayton | 49.99 | 29.99 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/25/2020 | 8/28/2020 |  | 8/30/2024
PJM | AF2-219 |  |  | NC | Halifax | Withdrawn | Dominion | 58 | 38.67 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/25/2020 | 4/22/2020 |  | 12/31/2023
PJM | AF2-220 | Hickman-River Bend 69 kV |  | VA | Pulaski | Withdrawn | AEP | 37 | 22.2 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/25/2020 | 8/27/2020 |  | 6/30/2023
PJM | AF2-221 | Scalp Level 22.9 kV | Stony Creek Solar | PA | Somerset | Engineering and Procurement | PENELEC | 15 | 6.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 3/25/2020 |  |  | 10/1/2025
PJM | AF2-222 - moved to TC1 | Madisonville DP-Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 167 | 100 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress | Interim Study | 3/25/2020 |  |  | 5/31/2023
PJM | AF2-223 | Marysville 345 kV |  | OH | Union | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/25/2020 | 9/14/2023 |  | 10/1/2023
PJM | AF2-224 | Allen 345 kV | Flatrock Creek Solar I | IN | Allen | Engineering and Procurement | AEP | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2020 |  |  | 12/31/2028
PJM | AF2-225 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 63 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/26/2020 |  |  | 10/31/2022
PJM | AF2-226 - moved to TC1 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/26/2020 |  |  | 10/31/2023
PJM | AF2-227 | Martins Creek–Cherry Hill 69 kV |  | PA | Northampton | Withdrawn | PPL | 63.75 | 38.25 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/26/2020 | 9/13/2023 |  | 6/30/2023
PJM | AF2-228 | Brunner Island 13.8 kV |  | PA | York | Withdrawn | PPL | 61 | 36.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/26/2020 | 8/8/2023 |  | 6/30/2023
PJM | AF2-229 | Roxbury 23 kV | Gobbler Knob | PA | Cumberland | Engineering and Procurement | PENELEC | 20 | 10.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2020 |  |  | 11/30/2027
PJM | AF2-230 | Lock 34 kV |  | PA | Montgomery | Withdrawn | PECO | 4 | 2.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/26/2020 | 8/25/2020 |  | 6/1/2020
PJM | AF2-231 | Belleville 12.47 kV |  | PA | Mifflin | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/26/2020 | 10/19/2020 |  | 6/1/2020
PJM | AF2-232 | Bowmanns Mill Tap-Scott 69 kV |  | PA | Columbia | Withdrawn | PPL | 40 | 24 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 3/26/2020 | 9/13/2023 |  | 12/15/2021
PJM | AF2-233 | Penns-Richfield Tie #1 69 kV | Washington East Solar | PA | Snyder | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2020 |  |  | 12/30/2026
PJM | AF2-234 | Sunbury Yard #1-Richfield Tie #2 69 kV | Washington West Solar | PA | Snyder | Engineering and Procurement | PPL | 40 | 24 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2020 |  |  | 12/30/2026
PJM | AF2-235 | Titusville-Oil Creek 34.5 kV | Big Bell Solar | PA | Crawford | Engineering and Procurement | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/27/2020 |  |  | 7/31/2027
PJM | AF2-236 | Jamestown-Hartstown 69 kV |  | PA | Crawford | Withdrawn | ATSI | 8 | 4.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/26/2020 | 9/14/2020 |  | 2/15/2023
PJM | AF2-237 | Union City-Cambridge Springs 34.5 kV |  | PA | Crawford | Withdrawn | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/26/2020 | 9/14/2020 |  | 1/1/2023
PJM | AF2-238 | Mansfield-South Troy 34.5 kV | Farmers Valley Solar | PA | Bradford | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/26/2020 |  |  | 7/31/2027
PJM | AF2-239 | Wyalusing-Hollenback WRC 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 20 | 11.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/26/2020 | 3/25/2021 |  | 11/30/2021
PJM | AF2-240 | North Orwell 12.47 kV |  | PA | Bradford | Withdrawn | PENELEC | 7 | 3.78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/26/2020 | 3/19/2021 |  | 11/30/2021
PJM | AF2-241 | Athens-Milan 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 20 | 11.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/26/2020 | 3/29/2021 |  | 11/30/2021
PJM | AF2-242 | Wharton 115 kV |  | NC | Beaufort | Withdrawn | Dominion | 80 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/27/2020 | 3/25/2021 |  | 9/30/2023
PJM | AF2-243 | Clark Summit 34.5 kV | Pearl Solar | PA | Venango | Engineering and Procurement | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 |  |  | 9/2/2026
PJM | AF2-244 | Powhatan 34.5 kV |  | VA | Powhatan | Withdrawn | Dominion | 15 | 9.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/27/2020 | 1/6/2021 |  | 3/31/2023
PJM | AF2-245 | Spurlock-Flemingsburg 138 kV |  | KY | Mason | Withdrawn | EKPC | 132 | 79.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 3/27/2020 | 8/31/2020 |  | 6/1/2023
PJM | AF2-246 | Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 58 | 38.67 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/27/2020 | 4/16/2020 |  | 12/29/2023
PJM | AF2-247 | Bustleton 13.2 kV | FLR Florence Landfill | NJ | Burlington | In Service | PSEG | 5 | 2.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/27/2020 |  |  | 6/30/2022 | 3/2/2022
PJM | AF2-248 | Edgewood 12 kV I |  | MD | Wicomico | Withdrawn | DPL | 7.2 | 3.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/27/2020 | 4/21/2021 |  | 6/1/2020
PJM | AF2-249 | Edgewood 12 kV II | Citron Storage | MD | Wicomico | Withdrawn | DPL | 3 | 0.6 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 7/11/2024 |  | 11/30/2023
PJM | AF2-250 | Edgewood 12 kV III | Kumquat Solar | MD | Wicomico | In Service | DPL | 1.95 | 1.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 |  |  | 7/31/2022 | 10/19/2022
PJM | AF2-251 | Susquehanna unit 1 230 kV |  | PA | Luzerne | Withdrawn | PPL | 50 | 0 | Energy | Generation Interconnection | Nuclear | Document Posted | Document Posted | Withdrawn |  | 3/27/2020 | 11/30/2022 |  | 8/1/2020
PJM | AF2-252 | Blue Mound 345 kV | Twin Groves Storage I | IL | McLean | Engineering and Procurement | ComEd | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 3/27/2020 |  |  | 1/28/2028
PJM | AF2-253 | McClelland-Shenango 345 kV |  | PA | Lawrence | Withdrawn | ATSI | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/27/2020 | 9/14/2020 |  | 6/1/2022
PJM | AF2-254 | Cookstown-New Lisbon 34.5 kV | NJ Land Phase II | NJ | Burlington | Suspended | JCPL | 10 | 4.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/27/2020 |  |  | 6/1/2025
PJM | AF2-255 | Iron Bridge 34.5 kV | Bradley Ridge Solar | VA | Chesterfield | Withdrawn | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 5/19/2022 |  | 11/30/2023
PJM | AF2-256 | Tyler 34.5 kV | Bradley Bridge Solar | VA | Chesterfield | Withdrawn | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 5/19/2022 |  | 11/30/2023
PJM | AF2-257 | Tyler 34.5 kV |  | VA | Chesterfield | Withdrawn | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Withdrawn | 3/27/2020 | 5/24/2022 |  | 12/12/2022
PJM | AF2-258 | Harrowgate 34.5 kV |  | VA | Chesterfield | Withdrawn | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/27/2020 | 5/24/2022 |  | 12/12/2022
PJM | AF2-259 | Locks 34.5 kV |  | VA | Chesterfield | Withdrawn | Dominion | 25 | 15 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/27/2020 | 9/8/2023 |  | 12/12/2022
PJM | AF2-260 | Stephensburg-Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 85 | 53 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/27/2020 |  |  | 12/31/2023
PJM | AF2-261 | Harwood-Susquehanna #1 230 kV |  | PA | Luzerne | Withdrawn | PPL | 75 | 31.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/27/2020 | 8/28/2020 |  | 11/30/2023
PJM | AF2-262 | Freeland #1 Tap-Jeddo-Highland 69 kV |  | PA | Luzerne | Withdrawn | PPL | 45 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/27/2020 | 8/28/2020 |  | 12/31/2023
PJM | AF2-263 - moved to TC1 | Shelby 138 kV |  | OH | Shelby | Withdrawn | Dayton | 98 | 58.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/27/2020 | 6/21/2024 |  | 7/1/2022
PJM | AF2-264 | Tunis 34.5 kV |  | NC | Hertford | Withdrawn | Dominion | 20 | 13.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/27/2020 | 8/24/2020 |  | 3/30/2023
PJM | AF2-265 | South Troy-Athens 34.5 kV | Big Pond Solar Power Plant | PA | Bradford | Withdrawn | PENELEC | 15 | 8.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/27/2020 | 8/29/2023 |  | 9/1/2022
PJM | AF2-266 | Clover 230 kV |  | VA | Charlotte | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 3/27/2020 | 3/29/2021 |  | 7/1/2022
PJM | AF2-267 | Lancaster 138 kV |  | IL | Stephenson | Withdrawn | ComEd | 210.9 | 37.1184 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 3/27/2020 | 9/15/2020 |  | 3/31/2022
PJM | AF2-268 | Orrtanna 13.2 kV | AD-Chambersburg | PA | Adams | Withdrawn | ME | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 4/5/2024 |  | 9/30/2022
PJM | AF2-269 | Adams Y Solar II |  | PA |  | Withdrawn | ME | 3.72 |  | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/27/2020 | 4/27/2020 |  | 7/1/2021
PJM | AF2-270 | Bedford South RCB-Bedford Area 23 kV | BE-Chalybeate | PA | Bedford | Withdrawn | PENELEC | 3.72 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 10/6/2023 |  | 9/30/2022
PJM | AF2-271 | Pemberton-Sinking Valley 12.47 kV | BL-Kettle | PA | Blair | Withdrawn | PENELEC | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 3/11/2024 |  | 9/30/2022
PJM | AF2-272 | Bernville 13.2 kV | BR-Swissdale | PA | Blair | Withdrawn | ME | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 3/11/2024 |  | 9/30/2022
PJM | AF2-273 | Sligo 25 kV | CL-Route 58 R | PA | Clarion | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 8/19/2022 |  | 9/30/2022
PJM | AF2-274 | Lardin 12.47 kV | FA-Rockwell | PA | Fayette | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/28/2020 | 12/18/2023 |  | 9/30/2024
PJM | AF2-275 | Guilford 12.47 kV | FR-Social Island | PA | Franklin | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 4/5/2024 |  | 4/9/2026
PJM | AF2-276 | Guilford 12.47 kV | FR-Statler | PA | Franklin | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 4/5/2024 |  | 4/9/2026
PJM | AF2-277 | Richland 12.47 kV | BU-Union | PA | Bucks | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-278 | Halifax 12.47 kV | DA-Matamoras | PA | Dauphin | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Storage; Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-279 | Letort 12.47 kV | LA-Blue Rock | PA | Lancaster | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-280 | Buck 12.47 kV | LA-Buck | PA | Lancaster | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-281 | Lynnville 13.2 kV | LH-Decatur | PA | Lehigh | Withdrawn | ME | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 4/25/2024 |  | 4/9/2026
PJM | AF2-282 | Edelle 12.47 kV | LK-Justus | PA | Lackawanna | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 6/28/2022 |  | 2/1/2023
PJM | AF2-283 | Greenfield 12.47 kV | LK-Route 106 | PA | Lackawanna | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 9/29/2023
PJM | AF2-284 | Watson 12.47 kV | NO-Oakes | PA | Northumberland | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/2/2023
PJM | AF2-285 | W. Damascus 12.47 kV | WA-Cohechton 1 | PA | Wayne | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-286 | Shermansdale 12.47 kV | PE-Windy Hill | PA | Perry | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 6/28/2022 |  | 2/1/2023
PJM | AF2-287 | Green Park 12.47 kV | PE-Green Park | PA | Perry | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-288 | Benvenue 12.47 kV | PE-Dellville | PA | Perry | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 9/1/2024
PJM | AF2-289 | Watson 12.47 kV | NO-Vincent | PA | Northumberland | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 9/1/2024
PJM | AF2-290 | Derry 12.47 kV | NO-Mexico | PA | Montour | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/27/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-291 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/28/2020 |  |  | 5/1/2022
PJM | AF2-292 | South Union 12.47 kV | FA-Morgantown | PA | Fayette | Withdrawn | APS | 1.17 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/28/2020 | 1/2/2024 |  | 4/9/2026
PJM | AF2-293 | Beech Creek 12.47 kV | CT-Industrial Park | PA | Clinton | Withdrawn | APS | 1.17 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/28/2020 | 3/11/2024 |  | 4/9/2026
PJM | AF2-294 | Thompson 34.5 kV |  | PA | Wayne | Suspended | PENELEC | 17 | 10.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/29/2020 |  |  | 3/31/2025
PJM | AF2-295 | Wilcox-Paper City 46 kV | Evergreen Solar | PA | Elk | Engineering and Procurement | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress | Wholesale Market Participation Agreement | 3/28/2020 |  |  | 7/30/2027
PJM | AF2-296 - moved to TC1 | Madera 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/28/2020 |  |  | 10/1/2021
PJM | AF2-297 - moved to TC1 | Sedge Hill 115 kV |  | VA | Halifax | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/28/2020 |  |  | 3/12/2022
PJM | AF2-298 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 49.9 | 29.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 5/1/2022
PJM | AF2-299 - moved to TC1 | Fields 34.5 kV | Jarratt Energy Facility 2 | VA | Greensville | Active | Dominion | 19.5 | 11.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/30/2020 |  |  | 12/12/2022
PJM | AF2-300 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required |  | 3/30/2020 |  |  | 12/12/2022
PJM | AF2-301 | Poolesville-Winchester 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 25 | 15 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2020 | 8/27/2020 |  | 12/12/2023
PJM | AF2-302 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/30/2020 |  |  | 12/12/2022
PJM | AF2-303 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 8/3/2023
PJM | AF2-304 | Surry-Hopewell 230 kV |  | VA | Surry | Active | Dominion | 89 | 89 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 8/3/2023
PJM | AF2-305 | Brokaw-Lanesville 345 kV | Alta Farms II | IL | DeWitt | In Service | ComEd | 0 | 9.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 3/30/2020 |  |  | 9/2/2024 | 5/20/2023
PJM | AF2-306 | Hope-Blevins Valley Tap 69 kV | Flat Top Solar | KY | Barren | Engineering and Procurement | EKPC | 26 | 26 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2020 |  |  | 10/31/2027
PJM | AF2-307 - moved to TC1 | Hope-Belvins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 66 | 39.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/30/2020 |  |  | 9/1/2023
PJM | AF2-308 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 28 | 28 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/30/2020 | 10/14/2024 |  | 9/1/2023
PJM | AF2-309 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/30/2020 | 10/14/2024 |  | 9/1/2023
PJM | AF2-310 | Jennings-Hoyes Road 34.5 kV |  | MD | Garrett | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 3/30/2020 | 5/18/2021 |  | 11/30/2022
PJM | AF2-311 | Gilboa-Jones Branch 138 kV | Nicholas Solar | WV | Nicholas | Active | APS | 100 | 55 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 2/28/2029
PJM | AF2-312 | Carrolltown-Patton 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 18 | 10.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2020 | 9/4/2020 |  | 9/1/2022
PJM | AF2-313 | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 19.9 | 12.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/30/2020 | 9/12/2023 |  | 8/15/2021
PJM | AF2-314 | Vandergrift-Guffy Junction 25 kV | Ponytail Solar | PA | Armstrong | Withdrawn | APS | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/30/2020 | 7/31/2024 |  | 9/30/2023
PJM | AF2-315 | Susquehanna Unit 2 500 kV |  | PA | Luzerne | Withdrawn | PPL | 50 | 0 | Energy | Generation Interconnection | Nuclear | Document Posted | Document Posted | Withdrawn |  | 3/30/2020 | 11/30/2022 |  | 8/1/2020
PJM | AF2-316 | Gilboa-Jones Branch 138 kV II | Deep Lake Solar | WV | Nicholas | Active | APS | 150 | 82.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 2/28/2029
PJM | AF2-317 | Hill Topper 345 kV | Whitney Hill Wind Farm | IL | Logan | In Service | ComEd | 0 | 15.68 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2020 |  |  | 9/1/2022 | 9/1/2022
PJM | AF2-318 | East Towanda-New Albany 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/30/2020 | 4/14/2021 |  | 4/1/2022
PJM | AF2-319 - moved to TC1 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/30/2020 |  |  | 10/31/2023
PJM | AF2-321 - moved to TC1 | Stryker-Ridgeville 138 kV |  | OH | Williams | Active | ATSI | 148 | 88.8 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 3/30/2020 |  |  | 12/31/2023
PJM | AF2-322 | Hoytdale-McClelland 345 kV | Firefly Solar | PA | Lawrence | Withdrawn | ATSI | 199.67 | 119.802 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/30/2020 | 12/2/2024 |  | 9/1/2026
PJM | AF2-323 | Geneva-Franklin Tap 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 44 | 26.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2020 | 9/25/2020 |  | 4/1/2022
PJM | AF2-324 - moved to TC1 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 3/30/2020 |  |  | 11/30/2022
PJM | AF2-325 | Jacktown 12 kV | SBC Solar | MD | Dorchester | Engineering and Procurement | DPL | 10 | 4.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/30/2020 |  |  | 12/31/2027
PJM | AF2-326 | Battleboro 34.5kV |  | NC | Edgecombe | Withdrawn | Dominion | 20 | 16 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 3/30/2020 | 7/22/2020 |  | 8/3/2023
PJM | AF2-327 | Wakefield 13 kV |  | VA | Sussex | Withdrawn | Dominion | 20 | 16 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 3/30/2020 | 7/22/2020 |  | 8/3/2023
PJM | AF2-328 | Inez-Johns Creek 138 kV |  | KY | Pike | Withdrawn | AEP | 75 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/30/2020 | 3/1/2024 |  | 12/1/2023
PJM | AF2-329 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 42.2 | 42.2 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/30/2020 |  |  | 12/1/2023
PJM | AF2-330 | Claysburg-Summit 115 kV |  | PA | Cambria | Withdrawn | PENELEC | 70 | 48.7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/30/2020 | 9/11/2020 |  | 12/31/2022
PJM | AF2-331 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 12/31/2023
PJM | AF2-332 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 12/31/2023
PJM | AF2-333 | Montour 230 kV |  | PA | Montour | Active | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 12/31/2023
PJM | AF2-334 | Montour 230 kV |  | PA | Montour | Active | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/30/2020 |  |  | 12/31/2023
PJM | AF2-335 - moved to TC1 | Delaware-Royerton 138 kV |  | IN | Delaware | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/31/2023
PJM | AF2-336 | Snake Spring 115 kV I | Snake Spring Solar I & II | PA | Bedford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/31/2020 | 8/14/2024 |  | 2/1/2028
PJM | AF2-337 | Snake Spring 115 kV II |  | PA | Bedford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/31/2020 | 8/14/2024 |  | 12/31/2023
PJM | AF2-338 | Snake Spring 115 kV III |  | PA | Bedford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 9/12/2023 |  | 12/31/2023
PJM | AF2-339 | Snake Spring 115 kV IV |  | PA | Bedford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 9/12/2023 |  | 12/31/2023
PJM | AF2-340 |  |  | PA | Adams | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2020 | 4/10/2020 |  | 12/31/2023
PJM | AF2-341 | Maysville138 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 7/23/2021 |  | 12/31/2023
PJM | AF2-342 | Maysville138 kV II |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 7/23/2021 |  | 12/31/2023
PJM | AF2-343 | Maysville 138 kV III |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 7/23/2021 |  | 12/31/2023
PJM | AF2-344 | Maysville 138 kV IV |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 7/23/2021 |  | 12/31/2023
PJM | AF2-345 | Maysville 138 kV V |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 7/23/2021 |  | 12/31/2023
PJM | AF2-346 | Electric Junction-Nelson 345 kV |  | IL | Lee | Withdrawn | ComEd | 75 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 10/13/2023 |  | 12/31/2023
PJM | AF2-348 - moved to TC1 | North Clark-Spurlock 345 kV |  | KY | Madison | Active | EKPC | 250 | 150 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 7/1/2022
PJM | AF2-349 - moved to TC1 | SILVER LAKE- CHERRY VALLEY 345 KV |  | IL | McHenry | Active | ComEd | 300 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/1/2023
PJM | AF2-350 - moved to TC1 | Kensington 138 kV |  | IL | Kankakee | Active | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/1/2023
PJM | AF2-351 - moved to TC1 | Kensington 138 kV |  | IL | Kankakee | Withdrawn | ComEd | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 6/24/2024 |  | 12/1/2023
PJM | AF2-352 | Blue Mound 345 kV | Twin Groves Storage II | IL | McLean | Engineering and Procurement | ComEd | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2020 |  |  | 1/28/2028
PJM | AF2-353 | Rockport 765 kV |  | IN | Spencer | Withdrawn | AEP | 800 | 560 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 3/31/2020 | 9/14/2020 |  | 9/1/2023
PJM | AF2-354 | Washington 34.5 kV II | Washington Solar PH II | NJ | Warren | Engineering and Procurement | JCPL | 11 | 4.62 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2020 |  |  | 8/29/2025
PJM | AF2-355 - moved to TC1 | West Gerrard-J.K. Smith 345 kV |  | KY | Madison | Active | EKPC | 225 | 135 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 7/1/2022
PJM | AF2-356 | Albright-Mt. Zion 138 kV | CPV Backbone Solar | MD | Garrett | Under Construction | APS | 175 | 105 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 8/31/2025
PJM | AF2-357 | Nipetown-Reid 138 kV |  | MD | Washington | Withdrawn | APS | 24 | 14.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/31/2020 | 3/29/2021 |  | 12/31/2023
PJM | AF2-358 - moved to TC1 | Airey-Vienna 69 kV |  | MD | Dorchester | Active | DPL | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/15/2023
PJM | AF2-359 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 125 | 75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 12/15/2023
PJM | AF2-360 | Keeney-Steele 230 kV |  | MD | Allegany | Withdrawn | DPL | 125 | 75 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2020 | 5/1/2020 |  | 12/15/2023
PJM | AF2-361 | Mifflintown Tap 69 kV | Walker Solar Two | PA | Juniata | Engineering and Procurement | PPL | 80 | 35 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 9/19/2026
PJM | AF2-362 |  |  | VA | Lancaster | Withdrawn | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2020 | 4/22/2020 |  | 12/12/2023
PJM | AF2-363 | Cherry Valley-Glidden 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 81.4 | 48.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 3/31/2020 | 12/2/2024 |  | 12/31/2020
PJM | AF2-364 | Wayne Red 138 kV |  | IL |  | Withdrawn | ComEd | 81.4 | 48.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/31/2020 | 4/1/2021 |  | 12/31/2022
PJM | AF2-365 - moved to TC1 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/31/2022
PJM | AF2-366 | Crego Rd 138 kV | Red Maple Solar | IL | Adams | Engineering and Procurement | ComEd | 94.9 | 56.94 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 2/7/2028
PJM | AF2-367 | Neville 23 kV | Emsworth Back Channel Dam Hydroelectric Project | PA | Allegheny | Under Construction | DL | 12 | 12 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 |  |  | 12/31/2024
PJM | AF2-368 | Pine Creek 23 kV | Allegheny Lock and Dam No. 2 Hydroelectric Project | PA | Allegheny | Engineering and Procurement | DL | 9.5 | 9.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 |  |  | 12/31/2029
PJM | AF2-369 | Kirby 138 kV |  | OH | Union | Withdrawn | ATSI | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 9/11/2020 |  | 12/31/2022
PJM | AF2-370 - moved to TC1 | Delaware-Royerton 138 kV |  | IN | Delaware | Active | AEP | 0 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/31/2023
PJM | AF2-371 | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 84 | 50.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 12/31/2023
PJM | AF2-372 | Black Branch 34.5 kV |  | VA | Lunenburg | Withdrawn | Dominion | 19.95 | 7.58 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 8/20/2020 |  | 11/26/2021
PJM | AF2-373 | Mount Laurel 115 kV |  | VA | Halifax | Withdrawn | Dominion | 14.25 | 5.7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 8/26/2020 |  | 5/30/2022
PJM | AF2-374 | Woodland 34.5 kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 7.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 9/3/2020 |  | 10/29/2021
PJM | AF2-375 | Ebersole-Fostoria 138 kV | South Branch Solar | OH | Hancock | Active | AEP | 129.6 | 77.76 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 12/31/2022
PJM | AF2-376 - moved to TC1 | Timber Switch 138 kV |  | OH | Paulding | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 10/31/2023
PJM | AF2-377 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 10/31/2023
PJM | AF2-378 | Cambridge 12 kV | GGC Solar | MD | Dorchester | Engineering and Procurement | DPL | 2.65 | 1.11 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 |  |  | 3/31/2024
PJM | AF2-379 | Princess Anne 25 kV | RHC Solar | MD | Somerset | Under Construction | DPL | 3.9 | 1.638 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/1/2020 |  |  | 12/1/2024
PJM | AF2-380 | Karns City-Bear Creek 25 kV | Richardson Solar | PA | Clarion | Engineering and Procurement | APS | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 |  |  | 7/30/2027
PJM | AF2-381 - moved to TC1 | Bedford North-Central City West 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 60 | 40.2 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 4/1/2020 | 6/21/2024 |  | 6/30/2023
PJM | AF2-382 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 12/1/2023
PJM | AF2-383 | Tolna 115 kV | Tolna Energy Center | PA | York | Engineering and Procurement | ME | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 1/31/2028
PJM | AF2-384 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 12/1/2023
PJM | AF2-385 | Nelson 69 kV |  | DE | Sussex | Withdrawn | DPL | 75 | 47.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 10/14/2021 |  | 10/31/2022
PJM | AF2-386 | Bryan 69 kV |  | OH | Williams | Withdrawn | ATSI | 15 | 6.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 10/16/2020 |  | 12/31/2022
PJM | AF2-387 | Hillsboro-Steele 138 kV |  | MD | Queen Anne's | Withdrawn | DPL | 100 | 66.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/31/2020 | 4/1/2021 |  | 12/1/2023
PJM | AF2-388 - moved to TC1 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/15/2023
PJM | AF2-389 | Kenzie Creek-Stone Lake 69 kV |  | MI | Cass | Active | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 10/31/2023
PJM | AF2-390 | Kenzie Creek138 kV |  | MI | Cass | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2020 | 4/30/2020 |  | 10/31/2023
PJM | AF2-391 - moved to TC1 | Central Hardin 69 kV |  | KY | Hardin | Withdrawn | EKPC | 120 | 72 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 1/14/2025 |  | 6/15/2023
PJM | AF2-392 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Lee | Active | ComEd | 199 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 3/31/2020 |  |  | 9/1/2024
PJM | AF2-393 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Active | ComEd | 60 | 55 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 9/1/2024
PJM | AF2-394 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Active | ComEd | 40 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 9/1/2024
PJM | AF2-395 | Flatlick 765 kV | Rolling Hills Generating | OH | Vinton | In Service | AEP | 51.1 | 89.6 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2020 |  |  | 4/1/2023 | 2/7/2023
PJM | AF2-396 - moved to TC1 | Stinger 138 kV |  | MI | Cass | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/31/2023
PJM | AF2-397 - moved to TC1 | Fork Union-Mt. Eagle 230 kV |  | VA | Fluvanna | Withdrawn | Dominion | 130 | 78 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 4/1/2020 | 6/24/2024 |  | 12/15/2023
PJM | AF2-398 | Necessity-Dinnerbell 12.47 kV | Fike Solar | PA | Fayette | Withdrawn | APS | 3 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 10/8/2024 |  | 9/30/2023
PJM | AF2-399 | Crewe 12.5 kV |  | VA | Nottoway | Withdrawn | Dominion | 5.225 | 1.938 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 9/8/2020 |  | 10/29/2021
PJM | AF2-400 | Franklin 13.2 kV | Delaware Road Solar | VA | Southampton | Withdrawn | Dominion | 7.125 | 2.7075 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/1/2020 | 9/6/2023 |  | 5/31/2022
PJM | AF2-401 | Culpeper 34.5 kV | Stevensburg Road Solar | VA | Culpeper | Withdrawn | Dominion | 9.272 | 3.523 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 5/11/2021 |  | 10/31/2022
PJM | AF2-402 | Ivor-Oak Ridge 115 kV |  | VA | Southampton | Withdrawn | Dominion | 16.625 | 6.3175 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 9/3/2020 |  | 6/30/2022
PJM | AF2-403 - moved to TC1 | Shockoe DP-Chatham 69 kV | Shockoe Storage / Shockoe DP-Chatham 69 kV | VA | Fluvanna | Active | Dominion | 0 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/15/2022
PJM | AF2-404 - moved to TC1 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 12/15/2022
PJM | AF2-405 | East Sayre 34.5 kV III | Elm Line Energy Storage | PA | Bradford | Withdrawn | PENELEC | 10 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn | Withdrawn | 3/31/2020 | 12/24/2024 |  | 6/1/2021
PJM | AF2-406 - moved to TC1 | Sayre 115 kV |  | PA | Bradford | Withdrawn | PENELEC | 75 | 75 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 3/31/2020 | 6/21/2024 |  | 6/1/2022
PJM | AF2-407 - moved to TC1 | Fall Creek 345 kV |  | IN | Madison | Active | AEP | 300 | 300 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 3/31/2020 |  |  | 6/1/2022
PJM | AF2-408 | Fall Creek 138 kV | Fall Creek Energy Storage | IN | Madison | Engineering and Procurement | AEP | 80 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 1/15/2028
PJM | AF2-409 | Vienna 138 kV |  | MD | Dorchester | Withdrawn | DPL | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 3/31/2020 | 7/6/2021 |  | 6/1/2022
PJM | AF2-410 | Vienna 18 kV |  | MD | Dorchester | Withdrawn | DPL | 10 | 10 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2020 | 4/24/2020 |  | 6/1/2021
PJM | AF2-411 | Mainesburg 345 kV |  | PA | Clinton | Withdrawn | PENELEC | 300 | 300 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 3/31/2020 | 12/8/2020 |  | 6/1/2023
PJM | AF2-412 - moved to TC1 | Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 3/31/2020 |  |  | 6/1/2022
PJM | AF2-413 | Raritan River 230 kV | Woods Landing Energy Storage | NJ | Atlantic | Active | JCPL | 250 | 250 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 1/31/2030
PJM | AF2-414 | Bergen 345 kV |  | NJ | Hudson | Withdrawn | PSEG | 300 | 300 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 9/11/2023 |  | 6/1/2023
PJM | AF2-415 | Bergen 138 kV | Two Rivers Storage | NJ | Hudson | Engineering and Procurement | PSEG | 150 | 150 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 5/30/2028
PJM | AF2-416 | Bergen 26 kV | Railroad Avenue Energy Storage | NJ | Hudson | Suspended | PSEG | 10 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 4/1/2020 |  |  | 6/1/2026
PJM | AF2-417 | West Damascus Tap-West Damascus 69 kV | WA-Cochecton 2 | PA | Adams | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 12/31/2027
PJM | AF2-418 | Millville Tap 69 kV |  | PA | Columbia | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 9/13/2023 |  | 10/1/2021
PJM | AF2-419 | Hunt Farm-Ballard 69 kV |  | KY | Boyle | Withdrawn | EKPC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 3/31/2020 | 9/14/2020 |  | 11/1/2021
PJM | AF2-420 | Hunt Farm-Ballard 69 kV |  | KY | Boyle | Withdrawn | EKPC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 9/14/2020 |  | 10/1/2021
PJM | AF2-421 | East Hazelton-Weatherly Tap 69 | Club Ford Energy Center | PA | Adams | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2020 |  |  | 3/1/2027
PJM | AF2-422 | East Hazelton 12.47 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 8/27/2020 |  | 3/1/2022
PJM | AF2-423 | East Hazelton 12.47 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 9/16/2020 |  | 3/1/2022
PJM | AF2-424 | Reed-Reed Tap #1 69 kV | Shamrock Energy Center | PA | Northumberland | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 2/1/2027
PJM | AF2-425 | Reed-Reed Tap#1 69 kV | Shamrock Energy Center | PA | Adams | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 2/1/2027
PJM | AF2-426 | Bethelboro 12.47 kV | FA-Auto Auction | PA | Fayette | Withdrawn | APS | 1.17 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 1/2/2024 |  | 4/9/2026
PJM | AF2-427 | Watson 12.47 kV | Glidepath Ventures | PA | Northumberland | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-428 | West Boyertown 13.2 kV | BR-Water | PA | Berks | Withdrawn | ME | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 4/24/2024 |  | 9/30/2022
PJM | AF2-429 | South Hamburg 34.5 kV | BR-Mountain View | PA | Berks | Withdrawn | ME | 3.72 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 1/2/2024 |  | 9/30/2022
PJM | AF2-430 | Moselem 13.2 kV | BR-Allentown | PA | Berks | Withdrawn | ME | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 1/2/2024 |  | 9/30/2022
PJM | AF2-431 | Baldy 13.2 kV | BR-Kutztown | PA | Berks | Withdrawn | ME | 1.17 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 1/2/2024 |  | 9/30/2022
PJM | AF2-432 | University 12.47 kV |  | PA | Columbia | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2020 | 11/22/2023 |  | 2/1/2023
PJM | AF2-433 | Columbia-Geisinger Tap #1 69 kV | Frosty Valley Energy Center | PA | Columbia | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 1/15/2027
PJM | AF2-434 | Columbia-Geisinger Tap #1 69 kV | Frosty Valley Energy Center | MD | Anne Arundel | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 3/31/2020 |  |  | 1/15/2027
PJM | AF2-435 | Waugh Chapel 115 kV |  | MD | Anne Arundel | Withdrawn | BGE | 55 | 33 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 3/31/2020 | 9/2/2020 |  | 9/1/2023
PJM | AF2-436 | Wyalusing 34.5 kV II | Wyalusing 34.5 kV | PA | Bradford | In Service | PENELEC | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted |  | Document Posted | 3/31/2020 |  |  | 9/30/2023 | 3/18/2021
PJM | AF2-437 | Oxbow 34.5 kV III | Oxbow Creek Energy | PA | Wyoming | In Service | PENELEC | 1.5 | 1.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 3/31/2020 |  |  | 9/30/2023 | 1/11/2021
PJM | AF2-438 | Heidleberg-Lavino 69 kV |  | PA | Mercer | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 3/31/2020 | 9/13/2023 |  | 12/31/2023
PJM | AF2-439 | Roxbury-Carlisle 115 kV |  | PA | Adams | Withdrawn | PENELEC | 50 | 26 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 3/31/2020 | 4/23/2021 |  | 12/31/2023
PJM | AF2-440 | Hillsboro-Middleboro 138 kV |  | OH | Highland | Active | AEP | 50 | 25 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/31/2020 |  |  | 12/31/2023
PJM | AF2-441 - moved to TC1 | Burnham 138kV |  | IL | Cook | Active | ComEd | 200 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 3/31/2020 |  |  | 5/31/2024
PJM | AF2-444 | Reed-Reed Tap #2 69 kV |  | PA | Northumberland | Withdrawn | PPL | 19.8 | 11.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 3/31/2020 | 12/18/2024 |  | 6/1/2021
PJM | AF2-445A | Fishbach-Port Carbon 69 kV | Norwegian Solar | PA | Northumberland | Suspended | PPL | 19.8 | 11.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 4/1/2020 |  |  | 9/24/2024
PJM | AG1-001 | US Silica-Unimin 69 kV | Santos Solar | NJ | Cumberland | Withdrawn | AEC | 31 | 11.78 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 4/3/2020 | 1/10/2025 |  | 3/1/2023
PJM | AG1-002 | Kennywood 23 kV |  | PA | Allegheny | Withdrawn | DL | 5.25 | 5.25 | Capacity | Generation Interconnection | Hydro | Withdrawn |  |  |  | 4/16/2020 | 5/22/2020 |  | 12/31/2022
PJM | AG1-003 | Marysville-Sorenson 765 kV | Grange Solar | OH | Logan | Active | AEP | 400 | 226 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 4/20/2020 |  |  | 12/31/2023
PJM | AG1-004 | Marysville-Sorenson 765 kV | Grange Solar | OH | Logan | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 4/20/2020 |  |  | 12/31/2023
PJM | AG1-005 - moved to TC1 | Corbin-Crescent Ridge 138 kV |  | IL | Stephenson | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 4/29/2020 |  |  | 10/1/2023
PJM | AG1-006 | Jay 138 kV |  | IN | Jay | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/29/2020 | 6/15/2020 |  | 10/1/2023
PJM | AG1-007 | Tar River 12.5 kV |  | NC | Edgecombe | Active | Dominion | 9.4 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 5/1/2020 |  |  | 12/15/2021
PJM | AG1-008 - moved to TC1 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 140 | 93 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 5/1/2020 |  |  | 12/15/2024
PJM | AG1-009 | Hopewell-Surry 230kV |  | VA | Surry | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 5/4/2020 | 9/12/2023 |  | 6/30/2022
PJM | AG1-010 | Ladysmith-CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 5/5/2020 | 9/12/2023 |  | 6/30/2022
PJM | AG1-011 - moved to TC1 | Colonial Trail 230 kV |  | VA | Surry | Withdrawn | Dominion | 160 | 160 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 5/8/2020 | 6/24/2024 |  | 6/30/2022
PJM | AG1-012 | Meadow Brook-Strasburg 138 kV II | Foxglove Solar Storage Uprate | VA | Frederick | Withdrawn | APS | 0 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 5/8/2020 | 9/12/2023 |  | 6/30/2022
PJM | AG1-013 | Ladysmith CT-St. Johns 230 kV |  | VA | Caroline | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 5/8/2020 | 7/28/2023 |  | 6/30/2022
PJM | AG1-014 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 5/8/2020 | 9/8/2023 |  | 12/1/2021
PJM | AG1-015 | Carson-Rogers Rd 500 kV |  | VA | Greensville | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 5/8/2020 | 9/8/2023 |  | 12/1/2021
PJM | AG1-016 | Flanders 12.5 kV |  | NJ | Warren | Withdrawn | JCPL | 15 | 6.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/8/2020 | 6/4/2020 |  | 12/18/2020
PJM | AG1-017 | Jay 138 kV |  | IN | Jay | Active | AEP | 12.64 | 2.26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted |  | 5/6/2020 |  |  | 9/30/2020
PJM | AG1-018 | Nipetown-Reid 138 kV |  | MD | Washington | Withdrawn | APS | 8 | 3.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 5/12/2020 | 2/26/2021 |  | 12/31/2023
PJM | AG1-019 - moved to TC1 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 5/20/2020 | 6/24/2024 |  | 10/31/2023
PJM | AG1-020 | New Road 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 5/20/2020 | 6/16/2020 |  | 10/31/2023
PJM | AG1-021 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 5/26/2020 |  |  | 12/12/2023
PJM | AG1-022 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 5/26/2020 |  |  | 12/12/2023
PJM | AG1-023 | North Anna-Louisa 230 kV |  | VA | Louisa | Withdrawn | Dominion | 75 | 15 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 5/26/2020 | 9/12/2023 |  | 10/1/2023
PJM | AG1-024 | Centerburg 138 kV | Harvey Solar I | OH | Licking | Active | AEP | 85 | 35.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 6/1/2020 |  |  | 10/31/2023
PJM | AG1-025 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/2/2020 | 4/26/2024 |  | 10/31/2023
PJM | AG1-027 | Suffolk-Holland 115 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 127.5 | 82.11 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 6/8/2020 | 9/27/2021 |  | 12/31/2024
PJM | AG1-028 | Suffolk-Holland 115 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 6/8/2020 | 9/27/2021 |  | 12/31/2024
PJM | AG1-029 | Weirton Solar 24 kV | Weirton Solar 24 kV | WV | Hancock | Withdrawn | APS | 30 | 13.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/10/2020 | 9/15/2023 |  | 10/1/2024
PJM | AG1-030 - moved to TC1 | Victoria DP-Martin DP 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/9/2020 | 6/24/2024 |  | 1/1/2023
PJM | AG1-031 | Elk Run D.P.-Gainesville 230 kV |  | VA | Fauquier | Active | Dominion | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 6/10/2020 |  |  | 11/30/2021
PJM | AG1-032 | Lightfoot 34.5 kV |  | VA | James City | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/11/2020 | 7/10/2020 |  | 10/1/2022
PJM | AG1-033 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 3.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 6/12/2020 | 9/16/2021 |  | 12/31/2021
PJM | AG1-034 | Centerburg 138 kV | Harvey Solar I | OH | Licking | Active | AEP | 127.5 | 53.55 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 6/12/2020 |  |  | 10/31/2023
PJM | AG1-035 | Ahoskie 34.5 kV |  | NC | Hertford | Withdrawn | Dominion | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/16/2020 | 8/12/2020 |  | 12/31/2021
PJM | AG1-036 | Tunis 34.5 kV |  | NC | Bertie | Withdrawn | Dominion | 13.5 | 8.1 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 6/16/2020 | 3/17/2021 |  | 12/31/2021
PJM | AG1-037 | Ahoskie 34.5 kV | NC3 Ahoskie South Solar Project | NC | Hertford | Engineering and Procurement | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 6/16/2020 |  |  | 8/29/2027
PJM | AG1-038 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 45 | 18.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 6/16/2020 |  |  | 12/31/2022
PJM | AG1-039 | Galion 138 kV II | Blossom Solar | OH | Morrow | Engineering and Procurement | ATSI | 56 | 23.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress | Document Posted | 6/18/2020 |  |  | 7/31/2026
PJM | AG1-040 | Morgan Street-Mount Hope 34.5 kV | Nichols Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/20/2020 |  |  | 12/31/2026
PJM | AG1-041 | Osterburg-Bedford North 23 kV | Salt Solar | PA | Bedford | Suspended | PENELEC | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 6/25/2020 |  |  | 7/25/2026
PJM | AG1-042 | Hayden 345 kV |  | OH | Franklin | Withdrawn | AEP | 100 | 66.9 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 6/26/2020 | 8/19/2021 |  | 12/1/2023
PJM | AG1-043 | Sowego 115 kV |  | VA | Accomack | Withdrawn | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 6/26/2020 | 10/1/2021 |  | 12/12/2023
PJM | AG1-044 | Whiteside County | Rock River ESS | IL | Whiteside | In Service | ComEd | 0.5 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/1/2020 |  |  | 7/30/2021 | 12/27/2021
PJM | AG1-045 | Redbud-Gaylord 34.5 kV | Redbud-Gaylord 34.5 kV | VA | Frederick | Suspended | APS | 30 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/3/2020 |  |  | 12/31/2024
PJM | AG1-047 | Jay 138 kV |  | IN | Jay | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 7/13/2020 |  |  | 10/1/2023
PJM | AG1-048 | Jetersville-Ponton 115 kV |  | VA | Amelia | Withdrawn | Dominion | 106.25 | 52.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 7/17/2020 | 9/12/2023 |  | 12/1/2022
PJM | AG1-049 | College Corner 138 kV |  | OH | Preble | Withdrawn | AEP | 0 | 17.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/17/2020 | 9/14/2023 |  | 12/31/2021
PJM | AG1-050 | Milton 69 kV |  | PA | Northumberland | Withdrawn | PPL | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/17/2020 | 11/15/2024 |  | 6/30/2022
PJM | AG1-051 - moved to TC1 | Maysville 69 kV III |  | PA | Mercer | Withdrawn | ATSI | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/18/2020 | 7/18/2024 |  | 6/30/2022
PJM | AG1-052 | Zionsview-Middletown 115 kV II | Strinestown Solar and BESS | PA | York | Withdrawn | ME | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 7/17/2020 | 12/26/2024 |  | 12/31/2026
PJM | AG1-053 | Jackson-Three Mile Island 230 kV III | Dover Solar and BESS | PA | York | Withdrawn | ME | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 7/17/2020 | 12/2/2024 |  | 6/23/2026
PJM | AG1-054 | Potter-Harlan 69 kV | Green Meadows Solar | PA | Lawrence | Engineering and Procurement | ATSI | 40 | 25.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/21/2020 |  |  | 5/31/2026
PJM | AG1-056 | Stryker-Ridgeville 138 kV |  | OH | Williams | Withdrawn | ATSI | 54 | 32.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 7/22/2020 | 2/26/2021 |  | 12/31/2023
PJM | AG1-057 | Harmony Village 230 kV |  | VA | Middlesex | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/27/2020 | 9/12/2023 |  | 12/31/2023
PJM | AG1-058 |  |  | VA | Greensville | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/27/2020 | 7/31/2020 |  | 4/1/2022
PJM | AG1-059 | Robbins 138 kV |  | PA | Westmoreland | Withdrawn | APS | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/29/2020 | 12/11/2024 |  | 1/1/2023
PJM | AG1-060 - moved to TC1 | Eldred 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 174.8 | 25.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/29/2020 | 6/24/2024 |  | 5/31/2022
PJM | AG1-061 - moved to TC1 | Laurel-Sharptown 69 kV |  | DE | Sussex | Withdrawn | DPL | 109.3 | 65.58 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/29/2020 | 6/25/2024 |  | 12/31/2021
PJM | AG1-062 | Flanders-Pohatcong Mountain 34.5 kV | Independence Solar Farm | NJ | Warren | Withdrawn | JCPL | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 7/30/2020 | 5/10/2024 |  | 6/10/2027
PJM | AG1-063 | Fairhaven 13,8 kV | Fairhaven Battery Energy Storage System | MD | Anne Arundel | In Service | BGE | 2.5 | 0.7 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2020 |  |  | 9/30/2024 | 9/19/2024
PJM | AG1-064 | Plaza 34.5 kV | Bermuda Energy | VA | City of Richmond | Withdrawn | Dominion | 19.1 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2020 | 6/24/2022 |  | 12/1/2023
PJM | AG1-065 | Plaza 34.5 kV | Bermuda Energy | VA | City of Richmond | Withdrawn | Dominion | 19.1 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/30/2020 | 6/24/2022 |  | 12/1/2023
PJM | AG1-066 | Bonnyman 69 kV | Bright Mountain Solar | KY | Perry | Engineering and Procurement | AEP | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/30/2020 |  |  | 1/27/2027
PJM | AG1-067 | Temple Hill 69 kV |  | KY | Barren | Active | EKPC | 38 | 24.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 7/30/2020 |  |  | 6/30/2023
PJM | AG1-068 | London-Tangy 69 kV |  | OH | Adams | Withdrawn | ATSI | 49.9 | 30.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 7/30/2020 | 10/4/2021 |  | 6/30/2023
PJM | AG1-069 |  |  | VA | Warren | Withdrawn | APS | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/30/2020 | 9/23/2020 |  | 1/1/2023
PJM | AG1-070 - moved to TC1 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 45 | 32.7 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 7/30/2020 |  |  | 6/1/2024
PJM | AG1-071 - moved to TC1 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 55 | 37.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 7/30/2020 |  |  | 6/1/2024
PJM | AG1-072 | Hillsboro-Steele 138 kV II |  | MD | Queen Anne's | Withdrawn | DPL | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 7/30/2020 | 9/28/2021 |  | 12/1/2023
PJM | AG1-073 | St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/31/2020 | 9/24/2020 |  | 4/1/2022
PJM | AG1-074 | St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/31/2020 | 9/24/2020 |  | 4/1/2022
PJM | AG1-075 - moved to TC1 | Purdy-Sapony 115 kV |  | VA | Greensville | Active | Dominion | 150 | 93.2 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 7/31/2020 |  |  | 10/15/2024
PJM | AG1-076 | Fostoria Central 138 kV | South Branch Solar | OH | Hancock | Suspended | AEP | 0 | 46 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 7/31/2020 |  |  | 12/31/2025
PJM | AG1-077 | Allegheny Tunnel 23 kV |  | KY | Magoffin | Withdrawn | PENELEC | 3.7 | 0 | Energy | Generation Interconnection | Storage; Solar | Document Posted | Document Posted |  |  | 7/31/2020 | 9/21/2021 |  | 5/31/2022
PJM | AG1-078 |  |  | MD | Garrett | Withdrawn | APS | 60 | 48 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 7/31/2020 | 8/18/2020 |  | 9/30/2023
PJM | AG1-079 | New Meredith 69 kV | TES Blue Hen Solar 23 | DE | Kent | Withdrawn | DPL | 1.5 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2020 | 8/3/2021 |  | 11/1/2021
PJM | AG1-080 | Delair-Locust Street 69 kV | Buckeye Pennsauken Solar Urban Renewal LLC | NJ | Camden | Withdrawn | PSEG | 19.9 | 10.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 8/1/2020 | 9/7/2023 |  | 5/31/2025
PJM | AG1-081 | Poolesville 34.5 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/31/2020 | 1/15/2021 |  | 12/1/2021
PJM | AG1-082 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 7/31/2020 |  |  | 12/31/2021
PJM | AG1-083 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 7/31/2020 |  |  | 12/31/2021
PJM | AG1-084 | Earlys 34.5 kV |  | NC | Hertford | Withdrawn | Dominion | 17.5 | 10.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 7/31/2020 | 10/8/2021 |  | 12/31/2021
PJM | AG1-085 | Earlys 34.5 |  | NC | Hertford | Withdrawn | Dominion | 17.5 | 10.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 7/31/2020 | 10/8/2021 |  | 12/31/2021
PJM | AG1-086 | Findlay 23 kV | Findlay Solar Park | PA | Allegheny | Suspended | DL | 17.5 | 10.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 7/31/2020 |  |  | 12/31/2024
PJM | AG1-087 | Milford-Cartanza 230 kV |  | DE | Sussex | Withdrawn | DPL | 440 | 119 | Capacity | Generation Interconnection | Offshore Wind | Document Posted | Document Posted | Withdrawn |  | 7/31/2020 | 9/12/2023 |  | 10/31/2026
PJM | AG1-088 | Carll's Corner-Sherman Ave 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 7/31/2020 | 9/12/2023 |  | 12/31/2021
PJM | AG1-089 | Grandview-Clifftop 138 kV |  | WV |  | Active | AEP | 30 | 12 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 7/31/2020 |  |  | 12/31/2021
PJM | AG1-090 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 95 | 30 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 8/1/2020 |  |  | 8/1/2023
PJM | AG1-091 | Hickman-River Bend 69 kV |  | VA | Pulaski | Withdrawn | AEP | 50 | 32.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 7/31/2020 | 10/9/2024 |  | 6/30/2023
PJM | AG1-092 | Hickman-River Bend 69 kV |  | VA | Pulaski | Withdrawn | AEP | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 7/31/2020 | 10/4/2021 |  | 6/30/2023
PJM | AG1-093 | Halifax-Chase City 115 kV |  | VA | Halifax | Withdrawn | Dominion | 120 | 92 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 7/31/2020 | 3/4/2021 |  | 12/15/2023
PJM | AG1-094 | Burches Hill 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 35.3 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 8/7/2020 | 9/12/2023 |  | 8/31/2021
PJM | AG1-095 | General Office-Rustoleum 34.5 kV | Downsville Solar | MD | Washington | Withdrawn | APS | 16 | 10.6667 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/14/2020 | 8/14/2023 |  | 9/30/2022
PJM | AG1-096 | Rineyville 69 kV |  | KY | Hardin | Withdrawn | EKPC | 55 | 36.6667 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 8/15/2020 | 9/13/2023 |  | 10/31/2023
PJM | AG1-097 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Withdrawn | APS | 0 | 13 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 8/17/2020 | 10/17/2024 |  | 9/30/2022
PJM | AG1-098 - moved to TC1 | Briery-Clover 230 kV |  | VA | Mecklenburg | Active | Dominion | 107 | 64.2 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 8/18/2020 |  |  | 12/1/2024
PJM | AG1-099 | Westernport 34.5 kV | Jade Meadow III | MD | Garrett | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 8/19/2020 | 7/31/2024 |  | 12/31/2025
PJM | AG1-100 | Venango-Saegertown 34.5 kV | Henry Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 8/18/2020 |  |  | 7/31/2027
PJM | AG1-101 | Oakland-Gorman 69 kV |  | MD | Garrett | Withdrawn | APS | 10 | 6.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 8/20/2020 | 9/5/2023 |  | 6/1/2022
PJM | AG1-102 | White Marsh 34.5 kV |  | VA | Gloucester | Withdrawn | Dominion | 19 | 6.16 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn | Withdrawn | 8/21/2020 | 6/11/2024 |  | 7/1/2022
PJM | AG1-103 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Engineering and Procurement | AEC | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 8/24/2020 |  |  | 12/31/2026
PJM | AG1-104 | Waugh Chapel 230 kV | Chapel Energy Storage Facility | MD | Anne Arundel | Engineering and Procurement | BGE | 300 | 120 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 8/25/2020 |  |  | 6/1/2029
PJM | AG1-105 - moved to TC1 | Mount Laurel-Barnes Junction 115 kV |  | VA | Halifax | Active | Dominion | 90 | 54 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 8/27/2020 |  |  | 12/1/2024
PJM | AG1-106 - moved to TC1 | Thelma 230 kV |  | NC | Northhampton | Active | Dominion | 25.5 | 17.5 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 8/28/2020 |  |  | 6/1/2024
PJM | AG1-107 | Hillsboro-Middleboro 138 kV |  | OH | Highland | Active | AEP | 150 | 85.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 8/31/2020 |  |  | 12/31/2023
PJM | AG1-108 | Larrabee 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 0 | 25 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 8/31/2020 | 2/20/2023 |  | 3/1/2023
PJM | AG1-109 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 0 | 25 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 8/31/2020 |  |  | 3/1/2022
PJM | AG1-110 | Silver Lake 69 kV |  | NJ | Camden | Withdrawn | AEC | 0 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 8/31/2020 | 3/22/2022 |  | 11/1/2022
PJM | AG1-111 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 0 | 10 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 8/31/2020 | 3/16/2021 |  | 11/1/2022
PJM | AG1-112 | William 138 kV |  | WV | Tucker | Withdrawn | APS | 0 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 8/31/2020 | 3/10/2021 |  | 11/1/2022
PJM | AG1-113 | Somerset Windpower 22.86 kV |  | PA | Somerset | Withdrawn | PENELEC | 0 | 3.6 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 8/31/2020 | 2/22/2021 |  | 6/1/2022
PJM | AG1-114 | Meyersdale North 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 0 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 8/31/2020 | 12/1/2022 |  | 11/1/2022
PJM | AG1-115 | Buxmont 69 kV |  | PA | Bucks | Withdrawn | PPL | 0 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 8/31/2020 | 3/28/2023 |  | 11/1/2022
PJM | AG1-116 | Newport-South Millville 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 8/31/2020 | 9/12/2023 |  | 12/3/2021
PJM | AG1-117 | Churchtown-Upper Pittsgrove 138 kV |  | NJ | Salem | Withdrawn | AEC | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn | Withdrawn | 8/31/2020 | 6/28/2024 |  | 12/3/2021
PJM | AG1-118 - moved to TC1 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 8/31/2020 |  |  | 12/29/2023
PJM | AG1-119 - moved to TC1 | Wayne-Byron 345 kV |  | IL | DeKalb | Withdrawn | ComEd | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2020 | 6/24/2024 |  | 12/29/2023
PJM | AG1-120 - moved to TC1 | Glidden-Cherry Valley 138 kV |  | IL | DeKalb | Active | ComEd | 118.6 | 71.16 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 8/31/2020 |  |  | 12/29/2023
PJM | AG1-121 - moved to TC1 | Kewanee-Streator 138 kV |  | IL | Bureau | Withdrawn | ComEd | 294.7 | 51.9 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 8/31/2020 | 6/24/2024 |  | 12/31/2024
PJM | AG1-122 | London-National 138 kV |  | OH | Madison | Withdrawn | ATSI | 70 | 41.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 8/31/2020 | 2/22/2021 |  | 12/1/2024
PJM | AG1-123 - moved to TC1 | Amherst 69 kV |  | VA | Amherst | Withdrawn | AEP | 65 | 38.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 8/31/2020 | 6/21/2024 |  | 12/1/2024
PJM | AG1-124 - moved to TC1 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 90 | 53.01 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 8/31/2020 |  |  | 12/1/2024
PJM | AG1-125 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 234.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 8/31/2020 |  |  | 12/1/2024
PJM | AG1-126 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 234.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 8/31/2020 |  |  | 12/1/2024
PJM | AG1-127 - moved to TC1 | Crego Rd 138 kV |  | IL | DeKalb | Active | ComEd | 95.1 | 57.1 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 8/31/2020 |  |  | 12/29/2023
PJM | AG1-128 | Shady Oaks 138 kV |  | IL | Lee | Withdrawn | ComEd | 294.2 | 51.8 | Capacity | Generation Interconnection | Wind | Document Posted |  |  |  | 8/31/2020 | 3/24/2021 |  | 12/31/2024
PJM | AG1-129 | US Silica - Unimin 69 kV |  | NJ | Atlantic | Withdrawn | AEC | 51 | 30.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 8/31/2020 | 10/1/2021 |  | 6/1/2022
PJM | AG1-130 | Burlington 26 kV | NAES | NJ | Burlington | Suspended | PSEG | 5 | 2 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Document Posted | 9/1/2020 |  |  | 2/28/2026
PJM | AG1-131 | Edinburg 115 kV |  | VA | Shenandoah | Withdrawn | Dominion | 25.6 | 15.36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/2/2020 | 9/12/2023 |  | 8/1/2022
PJM | AG1-132 | Tait 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Withdrawn |  | 9/2/2020 | 10/18/2023 |  | 6/1/2021
PJM | AG1-133 - moved to TC1 | North Anna-Ladysmith 500 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 128 | 76.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/2/2020 | 6/24/2024 |  | 12/1/2024
PJM | AG1-134 - moved to TC1 | Kings Dominion DP 115 kV |  | VA | King William | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/2/2020 | 6/24/2024 |  | 12/1/2024
PJM | AG1-135 - moved to TC1 | Garner-Lancaster 115 kV |  | VA | Richmond | Active | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress | Interim Study | 9/3/2020 |  |  | 12/1/2024
PJM | AG1-136 | Cloverdale-Burlington Height 138 kV | Gateway Grid | VA | Botetourt | Active | AEP | 100 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 9/3/2020 |  |  | 10/22/2023
PJM | AG1-137 | Harrisonburg 230 kV |  | VA | Rockingham | Withdrawn | Dominion | 100 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/3/2020 | 9/13/2021 |  | 10/22/2023
PJM | AG1-138 | Wolfs Corners 34.5 kV |  | PA | Clarion | Withdrawn | PENELEC | 5 | 4.75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/4/2020 | 11/1/2021 |  | 9/15/2022
PJM | AG1-139 | Clark Summit-Emlenton 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 5 | 4.75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/4/2020 | 11/1/2021 |  | 9/15/2022
PJM | AG1-140 | Union City 34.5 kV | Great Lake Growers | PA | Erie | Suspended | PENELEC | 2.62 | 1.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/3/2020 |  |  | 12/31/2024
PJM | AG1-141 | Hempfield 12.47 kV | Hempfield CSG 1 | PA | Westmoreland | Withdrawn | APS | 5 | 2.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/3/2020 | 8/21/2024 |  | 9/30/2022
PJM | AG1-142 | Bethelboro 12.47 kV | North Union CSG 1 | PA | Fayette | Withdrawn | APS | 2.5 | 1.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/4/2020 | 9/25/2024 |  | 9/30/2022
PJM | AG1-143 | Gainesville-Loudoun 230 kV |  | VA | Prince William | Withdrawn | Dominion | 200 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/4/2020 | 8/17/2023 |  | 10/22/2023
PJM | AG1-144 | Phillipsburg 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/4/2020 | 3/2/2021 |  | 6/1/2022
PJM | AG1-145 | Lightfoot 34.5 kV | Norge Solar | VA | James City | In Service | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/10/2020 |  |  | 10/1/2023 | 11/30/2023
PJM | AG1-146 - moved to TC1 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 30 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/9/2020 |  |  | 12/1/2024
PJM | AG1-147 - moved to TC1 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/9/2020 |  |  | 12/1/2024
PJM | AG1-148 | McCarter 26.4 kV | Rutgers Generation | NJ | Essex | In Service | PSEG | 5 | 0 | Energy | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/12/2020 |  |  | 1/12/2024
PJM | AG1-149 | Kingston 12 kV II |  | MD | Somerset | Withdrawn | DPL | 3 | 3 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/9/2020 | 6/7/2021 |  | 12/1/2021
PJM | AG1-150 | Wattsville 69 kV II |  | VA | Accomack | Withdrawn | DPL | 40 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/9/2020 | 9/12/2023 |  | 12/1/2021
PJM | AG1-151 - moved to TC1 | Endless Caverns 115 kV |  | VA | Rockingham | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/10/2020 | 6/24/2024 |  | 10/30/2023
PJM | AG1-152 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/10/2020 |  |  | 12/1/2023
PJM | AG1-153 - moved to TC1 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 75 | 30 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress | Interim Study | 9/10/2020 |  |  | 12/1/2023
PJM | AG1-154 - moved to TC1 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/10/2020 |  |  | 12/1/2023
PJM | AG1-155 | Cloverdale 34.5 kV |  | VA | Botetourt | Withdrawn | AEP | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/10/2020 | 2/17/2021 |  | 10/22/2023
PJM | AG1-156 | Jack Frost-Lake Harmony 69 kV | Mora Solar | PA | Carbon | Engineering and Procurement | PPL | 60 | 39.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/10/2020 |  |  | 12/31/2027
PJM | AG1-157 | Macungie-Emmaus Tie 69 kV |  | PA | Lehigh | Withdrawn | PPL | 7.37 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/11/2020 | 9/13/2023 |  | 6/16/2022
PJM | AG1-158 | Middletown 34.5 kV |  | PA | Delaware | Withdrawn | PECO | 16 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 9/11/2020 | 2/15/2023 |  | 6/16/2022
PJM | AG1-159 | Cox-Whitakers 115 kV |  | NC | Halifax | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/11/2020 | 5/3/2024 |  | 12/15/2022
PJM | AG1-160 - moved to TC1 | Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 75 | 30 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/11/2020 | 6/24/2024 |  | 12/1/2023
PJM | AG1-161 | Conesville 138 kV |  | OH | Coshocton | Withdrawn | AEP | 58.9 | 58.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/14/2020 | 3/5/2021 |  | 12/1/2022
PJM | AG1-162 | Sporn 138 kV |  | WV | Mason | Withdrawn | AEP | 27.4 | 14.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/14/2020 | 9/14/2023 |  | 12/1/2022
PJM | AG1-163 | West Millersport 138 kV | Ripley Solar II | OH | Fairfield | Engineering and Procurement | AEP | 100 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/14/2020 |  |  | 12/31/2027
PJM | AG1-164 | East Hazelton-Weatherly Tap 69 kV | Club Ford Energy Center | PA | Luzerne | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/16/2020 |  |  | 3/1/2027
PJM | AG1-165 | East Hazelton-Weatherly Tap 69 kV | Club Ford Energy Center | PA | Luzerne | Engineering and Procurement | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/17/2020 |  |  | 3/1/2027
PJM | AG1-166 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 20 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-167 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 4.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-168 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 4.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-169 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 4.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-170 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 10 | 3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-171 | Hopewell-Surry 230kV |  | VA | Surry | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-172 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-173 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/16/2020 |  |  | 10/15/2021
PJM | AG1-174 - moved to TC1 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/16/2020 | 6/24/2024 |  | 10/15/2021
PJM | AG1-175 | Hopewell-Surry 230 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/16/2020 | 9/12/2023 |  | 10/15/2021
PJM | AG1-176 | Briery-Clover 230 kV |  | VA | Prince Edward | Withdrawn | Dominion | 149.5 | 89.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/16/2020 | 8/17/2023 |  | 11/1/2023
PJM | AG1-177 | Union City 34.5 kV |  | PA | Crawford | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/17/2020 | 3/10/2021 |  | 3/1/2024
PJM | AG1-178 - moved to TC1 | Carson-Suffolk 500 kV |  | VA | Sussex | Withdrawn | Dominion | 500 | 324.94 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/17/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-179 - moved to TC1 | Brunswick-Gasburg 69 kV |  | VA | Sussex | Withdrawn | Dominion | 50 | 33.66 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/17/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-180 - moved to TC1 | Brunswick-Gasburg 69 kV |  | VA | Sussex | Withdrawn | Dominion | 0 | 16.4 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/17/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-181 - moved to TC1 | Pamplin-Chase City 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 150 | 101.09 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/17/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-182 | Millville-Old Chapel 138 kV | Soapstone Solar and BESS | VA | Clarke | Withdrawn | APS | 100 | 65.21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/17/2020 | 10/9/2024 |  | 6/30/2023
PJM | AG1-183 | St. Johns DP-REC 115 kV |  | VA | King and Queen | Withdrawn | Dominion | 50 | 35.52 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/17/2020 | 9/1/2021 |  | 6/30/2023
PJM | AG1-184 - moved to TC1 | Carson-Suffolk 500 kV |  | VA | Sussex | Withdrawn | Dominion | 0 | 175.06 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/17/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-185 - moved to TC1 | Pamplin-Chase City 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 0 | 48.91 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/17/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-186 | Millville-Old Chapel 138 kV | Soapstone Solar and BESS | VA | Clarke | Withdrawn | APS | 0 | 34.79 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 9/17/2020 | 10/9/2024 |  | 6/30/2023
PJM | AG1-187 | St. Johns DP-REC 115 kV |  | VA | King and Queen | Withdrawn | Dominion | 0 | 14.48 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/17/2020 | 9/1/2021 |  | 6/30/2023
PJM | AG1-188 | Manitou-Oyster Creek 34.5 kV | Lacey Sand Solar | NJ | Ocean | Engineering and Procurement | JCPL | 19.8 | 8.316 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/17/2020 |  |  | 6/30/2027
PJM | AG1-189 | Oyster Creek-Bamber Lake 34.5 | Southern Ocean Waretown Solar | NJ | Ocean | Engineering and Procurement | JCPL | 12 | 5.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/17/2020 |  |  | 12/31/2027
PJM | AG1-190 | Burlington 26 kV |  | NJ | Burlington | Withdrawn | PSEG | 13.2 | 5.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/17/2020 | 3/18/2021 |  | 12/17/2021
PJM | AG1-191 | Chester-Pohatcong Mountain 34.5 kV | South Combe | NJ | Morris | Engineering and Procurement | JCPL | 15.4 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/17/2020 |  |  | 12/31/2025
PJM | AG1-192 | Perry-Stoneboro 69 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/17/2020 | 3/9/2021 |  | 1/15/2023
PJM | AG1-193 | Utica Junction 34.5 kV | Foster Run | PA | Venango | Engineering and Procurement | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/18/2020 |  |  | 8/28/2026
PJM | AG1-194 - moved to TC1 | Nuttall 138 kV |  | WV | Fayette | Active | AEP | 79 | 27 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 9/18/2020 |  |  | 12/1/2023
PJM | AG1-195 - moved to TC1 | Valley 230 kV |  | VA | Augusta | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/18/2020 | 6/24/2024 |  | 12/31/2023
PJM | AG1-196 - moved to TC1 | Grottoes 115 kV |  | VA | Augusta | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/18/2020 | 6/24/2024 |  | 12/31/2023
PJM | AG1-197 | Morgan Street-Cochranton 34.5 kV | Morgan Street-Cochranton 34.5 kV | PA | Crawford | Engineering and Procurement | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/19/2020 |  |  | 5/30/2025
PJM | AG1-198 | Union City 34.5 kV | Union City 34.5 kV | PA | Erie | Engineering and Procurement | PENELEC | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/18/2020 |  |  | 10/31/2025
PJM | AG1-199 - moved to TC1 | Allen Junction 345 kV |  | OH | Lucas | Withdrawn | ATSI | 300 | 300 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/18/2020 | 6/21/2024 |  | 6/1/2023
PJM | AG1-200 | Kingsland 13 kV |  | NJ | Bergen | Withdrawn | PSEG | 3.984 | 1.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/21/2020 | 2/16/2021 |  | 12/1/2021
PJM | AG1-201 | Hadley 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 10 | 6.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/22/2020 | 11/20/2020 |  | 12/31/2022
PJM | AG1-202 | Springboro 12.47 kV |  | PA | Crawford | Withdrawn | PENELEC | 10 | 6.6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/22/2020 | 9/7/2023 |  | 12/31/2022
PJM | AG1-203 | Reels Corner 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/22/2020 | 9/7/2023 |  | 12/31/2022
PJM | AG1-204 | West Berwick 12.47 kV |  | PA | Columbia | Withdrawn | PPL | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/22/2020 | 3/10/2021 |  | 12/31/2022
PJM | AG1-205 | Rockwood 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/22/2020 | 9/7/2023 |  | 12/31/2022
PJM | AG1-206 | Snyder Twp 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/22/2020 | 9/7/2023 |  | 12/31/2022
PJM | AG1-207 | Vandalia 69 kV | Prairie Flyer Energy Storage | OH | Montgomery | Engineering and Procurement | Dayton | 85 | 85 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/22/2020 |  |  | 6/1/2028
PJM | AG1-208 | Sideview-Mt Sterling 69 kV |  | KY | Montgomery | Withdrawn | EKPC | 35 | 21.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/22/2020 | 2/23/2021 |  | 12/31/2022
PJM | AG1-209 | Gretna 12.5 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 7 | 2.8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/22/2020 | 5/24/2023 |  | 12/30/2022
PJM | AG1-210 | Northern Neck 34.5 kV | Haynesville Energy Storage | VA | Richmond | Engineering and Procurement | Dominion | 10 | 4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/23/2020 |  |  | 8/9/2027
PJM | AG1-211 |  |  | VA | Mecklenburg | Withdrawn | Dominion | 15 | 6 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/22/2020 | 10/20/2020 |  | 12/30/2022
PJM | AG1-212 |  |  | VA | King George | Withdrawn | Dominion | 7 | 2.8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/22/2020 | 10/20/2020 |  | 12/30/2022
PJM | AG1-213 | St Johns 13.2 kV | Poplar Energy Storage | VA | Caroline | Withdrawn | Dominion | 10 | 4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 9/23/2020 | 12/17/2024 |  | 6/30/2024
PJM | AG1-214 | Grottoes 12.5 kV |  | VA | Rockingham | Withdrawn | Dominion | 19 | 7.6 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/22/2020 | 5/24/2023 |  | 12/31/2022
PJM | AG1-215 | Fort Pickett 13.2 kV |  | VA | Nottoway | Withdrawn | Dominion | 14 | 5.6 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/22/2020 | 5/12/2023 |  | 12/30/2022
PJM | AG1-218 | Marysville-Tangy 345 kV |  | OH | Union | Withdrawn | AEP | 250 | 150 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/23/2020 | 1/8/2025 |  | 3/31/2024
PJM | AG1-219 - moved to TC1 | Layland 69 kV |  | WV | Fayette | Withdrawn | AEP | 75 | 39.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/23/2020 | 6/21/2024 |  | 12/1/2023
PJM | AG1-220 | West Dekalb 138 kV |  | IL | DeKalb | Withdrawn | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/23/2020 | 3/16/2021 |  | 12/31/2023
PJM | AG1-221 | Poland Rd-Runway DP 230 kV |  | VA | Loudoun | Active | Dominion | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/23/2020 |  |  | 6/1/2023
PJM | AG1-222 | Guardian-Twin Branch 138 kV |  | IN | Elkhart | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 9/23/2020 |  |  | 5/31/2023
PJM | AG1-223 | Larrabee-Allaire 34.5 kV | Monmouth Solar 1 | NJ | Monmouth | Engineering and Procurement | JCPL | 15.4 | 6.47 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/23/2020 |  |  | 12/31/2026
PJM | AG1-224 - moved to TC1 | Pendleton-Tanners Creek 138 kV |  | IN | Fayette | Withdrawn | AEP | 210 | 126 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/24/2020 | 6/21/2024 |  | 12/1/2023
PJM | AG1-225 - moved to TC1 | Adams 138 kV |  | IN | Adams | Withdrawn | AEP | 346 | 207 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/24/2020 | 6/21/2024 |  | 12/1/2023
PJM | AG1-226 - moved to TC1 | Eugene-Dequine 345 kV |  | IN | Fountain | Active | AEP | 450 | 142 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/24/2020 |  |  | 6/1/2024
PJM | AG1-227 | Altamont-Tuscarora 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/24/2020 | 9/13/2023 |  | 6/1/2023
PJM | AG1-228 | Alta Haute-Tuscarora 69 kV |  | PA | Schuylkill | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/24/2020 | 9/13/2023 |  | 6/1/2023
PJM | AG1-231 | Glady Run–Xenia 69 kV |  | OH | Greene | Active | Dayton | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/25/2020 |  |  | 3/31/2023
PJM | AG1-232 | Magley 138 kV | Magley Solar Energy Center | IN | Adams | Active | AEP | 135 | 81 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/25/2020 |  |  | 12/31/2024
PJM | AG1-233 | Hazleton - Lake Lynn 138 kV | Glade Run Solar Energy Center | WV | Preston | Withdrawn | APS | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/25/2020 | 1/8/2025 |  | 6/30/2028
PJM | AG1-234 | Hinton-Ronceverte 115 kV |  | WV | Greenbrier | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/25/2020 | 3/3/2021 |  | 12/31/2024
PJM | AG1-235 | Fentress-Sligo 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 192 | 115.2 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/25/2020 | 9/12/2023 |  | 12/31/2024
PJM | AG1-236 - moved to TC1 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 180 | 23.4 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 9/25/2020 |  |  | 12/31/2024
PJM | AG1-237 | Dequine-Eugene 345 kV | Warren County Wind Energy Center | IN |  | Engineering and Procurement | AEP | 200 | 26 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted | Document Posted | 9/25/2020 |  |  | 12/31/2028
PJM | AG1-238 | Dumont 345 kV |  | IN | St. Joseph | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/25/2020 | 3/17/2021 |  | 8/31/2024
PJM | AG1-239 | Blue Bell-Canton Central 138 kV | Stark Solar | OH | Stark | Engineering and Procurement | ATSI | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/25/2020 |  |  | 12/31/2028
PJM | AG1-240 | Trinity 69 kV |  | VA | Botetourt | Withdrawn | AEP | 90 | 90 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/25/2020 | 12/8/2020 |  | 6/1/2024
PJM | AG1-241 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/25/2020 | 4/28/2021 |  | 12/31/2022
PJM | AG1-242 | Beccaria 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/25/2020 | 9/7/2023 |  | 12/31/2022
PJM | AG1-243 | Guilford-Fayetteville 34.5 kV |  | PA | Franklin | Withdrawn | APS | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/25/2020 | 5/26/2023 |  | 12/31/2022
PJM | AG1-244 | Middleburg 12.47 kV |  | PA | Snyder | Withdrawn | PPL | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/25/2020 | 3/10/2021 |  | 12/31/2022
PJM | AG1-245 | Wakefield 12.47 kV |  | PA | Lancaster | Withdrawn | PPL | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/25/2020 | 3/10/2021 |  | 12/31/2022
PJM | AG1-246 | Gates Hill-Luzerne 25 kV |  | PA | Fayette | Withdrawn | APS | 7.5 | 4.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/25/2020 | 8/23/2023 |  | 9/1/2024
PJM | AG1-247 | North Orwell 12.47 kV |  | PA | Bradford | Withdrawn | PENELEC | 7.5 | 4.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/25/2020 | 4/28/2021 |  | 12/31/2022
PJM | AG1-248 | York Storage 115 kV |  | PA | York | Withdrawn | ME | 119 | 4.8 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/25/2020 | 5/23/2023 |  | 10/31/2022
PJM | AG1-249 | Mechanicsburg-Darby 138 kV |  | OH | Union | Withdrawn | Dayton | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/25/2020 | 3/9/2021 |  | 10/31/2023
PJM | AG1-251 | McDowell 12.47 kV | Springfield CSG 1 | PA | Delaware | Suspended | ATSI | 3.88 | 1.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/25/2020 |  |  | 8/31/2024
PJM | AG1-252 | Henderson 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 3.875 | 2.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Withdrawn | 9/25/2020 | 9/12/2023 |  | 12/31/2021
PJM | AG1-253 | Erie East-Union City 34.5 kV | Greenfield CSG 1 | PA | Erie | Suspended | PENELEC | 4 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/25/2020 |  |  | 5/30/2025
PJM | AG1-254 | Salem-Woodstown 69 kV | Fenwick Creek Solar | NJ | Atlantic | Active | AEC | 38 | 25.3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/25/2020 |  |  | 12/31/2023
PJM | AG1-255 | Churchtown-Quinton 69 kV |  | NJ | Salem | Withdrawn | AEC | 55 | 36.7 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/26/2020 | 9/12/2023 |  | 12/31/2023
PJM | AG1-256 | Northern Neck 230 kV |  | VA | Accomack | Withdrawn | Dominion | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/28/2020 | 10/5/2021 |  | 1/1/2023
PJM | AG1-257 - moved to TC1 | Madisonburg Jct-Millheim 46 kV |  | PA | Centre | Withdrawn | APS | 19.9 | 8.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/29/2020 | 7/18/2024 |  | 8/1/2022
PJM | AG1-258 | Madisonburg Jct-Millheim 46 kV |  | PA | Centre | Withdrawn | APS | 19.9 | 8.3 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2020 | 2/25/2021 |  | 8/1/2023
PJM | AG1-259 | Sunbury-Dalmatia 69 kV | Boyles Run Solar | PA | Northumberland | Engineering and Procurement | PPL | 15.9 | 6.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2020 |  |  | 4/30/2027
PJM | AG1-260 | Sunbury-Dalmatia 69 kV | Boyles Run Solar | PA | Northumberland | Engineering and Procurement | PPL | 15.9 | 6.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/28/2020 |  |  | 4/30/2027
PJM | AG1-262 | Lower Mount Bethel 230 kV |  | PA | Northampton | Withdrawn | PPL | 85 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/28/2020 | 9/13/2023 |  | 10/31/2022
PJM | AG1-263 | Gloucester 230 kV |  | NJ | Camden | Withdrawn | PSEG | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/28/2020 | 9/11/2023 |  | 10/31/2021
PJM | AG1-267 | Martins Creek 69 kV |  | PA | Northampton | Withdrawn | PPL | 20 | 8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/28/2020 | 9/13/2023 |  | 10/31/2021
PJM | AG1-268 | Essex 230 kV |  | NJ | Essex | Withdrawn | PSEG | 80 | 40.8 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/28/2020 | 5/30/2023 |  | 10/31/2022
PJM | AG1-272 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 6 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/29/2020 |  |  | 3/1/2022
PJM | AG1-273 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 6 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/28/2020 |  |  | 6/1/2022
PJM | AG1-274 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 6 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/28/2020 |  |  | 6/1/2022
PJM | AG1-275 | Gladys DP-Stone Mill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2020 | 2/26/2021 |  | 3/1/2022
PJM | AG1-276 | Gladys DP-Stone Mill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2020 | 2/26/2021 |  | 3/1/2022
PJM | AG1-277 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Withdrawn | PPL | 40 | 32 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 9/28/2020 |  |  | 6/1/2022
PJM | AG1-278 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 15.42 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 9/28/2020 |  |  | 6/1/2022
PJM | AG1-279 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 15.42 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 9/28/2020 |  |  | 6/1/2022
PJM | AG1-280 | Claysburg-Puzzletown 46 kV |  | PA | Blair | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn | Not Required | Withdrawn | 9/28/2020 | 9/18/2023 |  | 3/1/2022
PJM | AG1-281 | Claysburg-HCR Tap 46 kV | BL-Hileman Hollow | PA | Blair | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 12/31/2027
PJM | AG1-282 | Dunnsville 34.5 kV | EX-Tidewater LLC | VA | Essex | Engineering and Procurement | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2020 |  |  | 8/29/2027
PJM | AG1-283 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Withdrawn | PPL | 30 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/28/2020 | 8/26/2024 |  | 9/30/2023
PJM | AG1-284 - moved to TC1 | Fork Union 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/28/2020 | 6/24/2024 |  | 9/30/2023
PJM | AG1-285 - moved to TC1 | Chase City-Central 115 kV |  | VA | Charlotte | Active | Dominion | 125 | 75 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/28/2020 |  |  | 12/1/2024
PJM | AG1-286 | Johnson Mountain 138 kV |  | VA | Campbell | Withdrawn | AEP | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2020 | 3/5/2021 |  | 12/1/2022
PJM | AG1-287 | South Boston 12.5 kV |  | VA | Halifax | Withdrawn | Dominion | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/28/2020 | 3/17/2021 |  | 12/1/2022
PJM | AG1-288 - moved to TC1 | Lake of the Woods DP-Wilderness DP 115 kV |  | VA | Orange | Withdrawn | Dominion | 150 | 96.59 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/28/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-289 - moved to TC1 | Lake of the Woods DP-Wilderness DP 115 kV |  | VA | Orange | Withdrawn | Dominion | 0 | 53.41 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/28/2020 | 6/24/2024 |  | 6/30/2023
PJM | AG1-290 | Wagner 115 kV |  | MD | Baltimore County | Withdrawn | BGE | 20 | 4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 9/28/2020 | 8/21/2023 |  | 10/31/2021
PJM | AG1-291 | Neville 23 kV | Emsworth Main Channel Hydroelectric Project 2 | PA | Allegheny | Engineering and Procurement | DL | 16.8 | 13.5 | Capacity | Generation Interconnection | Hydro | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/28/2020 |  |  | 12/15/2025
PJM | AG1-292 | Midland 138 kV |  | PA | Beaver | Withdrawn | DL | 36.6 | 21.5 | Capacity | Generation Interconnection | Hydro | Document Posted |  |  |  | 9/28/2020 | 3/28/2021 |  | 12/31/2023
PJM | AG1-293 | Hartstown 12.47 kV |  | PA | Crawford | Withdrawn | APS | 7.5 | 4.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Withdrawn | 9/28/2020 | 8/17/2023 |  | 12/31/2022
PJM | AG1-294 |  |  | PA | Adams | Withdrawn | ME | 7.5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/29/2020 | 10/21/2020 |  | 12/31/2022
PJM | AG1-295 | Blairsville East 23 kV |  | PA | Indiana | Withdrawn | PENELEC | 7.5 | 4.9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/29/2020 | 4/28/2021 |  | 12/31/2022
PJM | AG1-296 | Snyder Township 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/29/2020 | 9/7/2023 |  | 12/31/2022
PJM | AG1-297 - moved to TC1 | Hanna-Tanners Creek 345 kV |  | IN | Shelby | Active | AEP | 300 | 75 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/29/2020 |  |  | 12/31/2023
PJM | AG1-298 - moved to TC1 | Calumet-Burnham 345 kV |  | IL | Cook | Active | ComEd | 500 | 500 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/29/2020 |  |  | 6/1/2023
PJM | AG1-299 | U.S. Silica 12.47 kV |  | NJ | Atlantic | Withdrawn | AEC | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/29/2020 | 10/1/2021 |  | 12/31/2021
PJM | AG1-300 | U.S Silica II 12.47 kV |  | NJ | Cumberland | Withdrawn | AEC | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/29/2020 | 10/1/2021 |  | 12/31/2021
PJM | AG1-301 | Miller REC-Warrior Ridge 46 kV | Scarecrow Solar | PA | Huntingdon | Engineering and Procurement | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2020 |  |  | 5/1/2027
PJM | AG1-302 | Olive-Reynolds #1 345 kV |  | IN | Pulaski | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/29/2020 |  |  | 12/31/2021
PJM | AG1-303 | Geneva 115 kV | Victory Solar | PA | Crawford | Withdrawn | PENELEC | 44 | 26.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/29/2020 | 12/10/2024 |  | 6/30/2026
PJM | AG1-305 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 63 | 37.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/29/2020 |  |  | 7/1/2022
PJM | AG1-306 - moved to TC1 | Fawkes-Dale 138 kV |  | KY | Madison | Withdrawn | EKPC | 65 | 39 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/29/2020 | 6/21/2024 |  | 10/1/2023
PJM | AG1-307 | Old Chapel-Millville 138 kV | Franklintown Farm Solar and BESS | WV | Jefferson | Engineering and Procurement | APS | 80 | 56 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/29/2020 |  |  | 7/30/2028
PJM | AG1-308 - moved to TC1 | Shawville-Philipsburg 34.5 kV |  | PA | Clearfield | Withdrawn | PENELEC | 19.9 | 8.3 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/29/2020 | 6/21/2024 |  | 8/1/2022
PJM | AG1-310 | Crystal Hill-Perth 115 kV |  | VA | Halifax | Withdrawn | Dominion | 20 | 13.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/29/2020 | 2/23/2021 |  | 10/3/2022
PJM | AG1-311 | Apple Grove 138 kV |  | WV | Mason | Active | AEP | 99 | 69.4 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/29/2020 |  |  | 6/30/2023
PJM | AG1-312 | Earleys-Cashie 230 kV |  | NC | Bertie | Withdrawn | Dominion | 140 | 112 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/29/2020 | 3/4/2021 |  | 12/29/2023
PJM | AG1-313 | Jackson DP-Occoneechee 115 kV |  | NC | Northhampton | Withdrawn | Dominion | 46 | 27.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/29/2020 | 9/12/2023 |  | 10/9/2023
PJM | AG1-314 | Rural Retreat 138 kV |  | VA | Smyth | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/29/2020 | 12/14/2020 |  | 6/1/2024
PJM | AG1-315 | Lardin-Grays Landing 12.47 kV | Woodside Solar | PA | Fayette | Withdrawn | APS | 2 | 0.84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/29/2020 | 8/23/2023 |  | 9/30/2023
PJM | AG1-316 | Sherwill 69 kV |  | VA | Campbell | Withdrawn | AEP | 75 | 54.96 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/29/2020 | 9/14/2023 |  | 6/30/2024
PJM | AG1-317 | Livingston 13.8 kV | National Harbor – Battery Storage | MD | Prince George's | Withdrawn | PEPCO | 1 | 0.3 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 | 4/29/2024 |  | 2/28/2024
PJM | AG1-318 | Ocean Bay 12 kV | Ocean City-Battery Storage | MD | Worcester | Under Construction | DPL | 1 | 0.3 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 12/31/2024
PJM | AG1-319 - moved to TC1 | Napoleon Muni 138 kV |  | OH | Henry | Withdrawn | AMPT | 65 | 39 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 11/1/2022
PJM | AG1-320 - moved to TC1 | Glendale-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 82 | 54.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 |  |  | 10/1/2023
PJM | AG1-321 - moved to TC1 | Dresden-Pontiac Midpoint 345 kV |  | IL | Livingston | Withdrawn | ComEd | 200 | 126.4 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 | 6/21/2024 |  | 10/1/2023
PJM | AG1-322 | Birchwood 230 kV |  | VA | Accomack | Withdrawn | Dominion | 70 | 70 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 | 10/1/2021 |  | 9/1/2023
PJM | AG1-323 - moved to TC1 | Blue Jacket 138 kV |  | OH | Logan | Active | Dayton | 40 | 40 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 9/1/2023
PJM | AG1-324 | Jay-Desoto 138 kV | New Jay PV & BESS | IN | Jay | Active | AEP | 39 | 27.9 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 9/17/2027
PJM | AG1-325 | Barterbrook-Stuarts Draft 115 kV |  | VA | Augusta | Withdrawn | Dominion | 50 | 26 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 9/30/2020 | 3/5/2021 |  | 9/1/2023
PJM | AG1-326 | Circleville-Biers Run 138 kV |  | OH | Ross | Active | AEP | 59 | 35.4 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-327 | Ringgold – East Waynesboro 138 kV |  | PA | Franklin | Withdrawn | APS | 35 | 23.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 | 11/1/2021 |  | 12/31/2023
PJM | AG1-328 | Kirby-Blue Jacket 138 kV |  | OH | Union | Withdrawn | ATSI | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/10/2021 |  | 9/30/2023
PJM | AG1-329 | Conneaut 12.47 kV |  | PA | Crawford | Withdrawn | PENELEC | 5 | 4.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/5/2021 |  | 7/31/2022
PJM | AG1-330 | Beavertown 12.47 kV | ASD Brick Plant PA2 Solar | PA | Beaver | Withdrawn | PPL | 5 | 4.5 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 | 3/23/2022 |  | 3/1/2024
PJM | AG1-331 | Conneaut-Conneaut Tap 69 kV |  | PA | Crawford | Withdrawn | ATSI | 5 | 4.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 8/27/2021 |  | 7/31/2022
PJM | AG1-332 | Oxford 13.2 kV |  | PA | Adams | Withdrawn | ME | 5 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 5/13/2021 |  | 7/31/2022
PJM | AG1-333 | Lake Como-Pine Mills 12.47 kV |  | PA | Wayne | Withdrawn | PENELEC | 5 | 4.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 5/13/2021 |  | 7/31/2022
PJM | AG1-334 | Canal 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 5 | 4.5 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/5/2021 |  | 7/31/2022
PJM | AG1-335 | Wheatland 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 4 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Withdrawn | 9/30/2020 | 3/5/2021 |  | 7/31/2022
PJM | AG1-336 | Hunter 12.47 kV | ASD Hilcrest PA2 Solar | PA | Northumberland | Withdrawn | PPL | 5 | 3.8 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 | 3/23/2022 |  | 3/1/2024
PJM | AG1-337 | Elizabethville 12.47 kV | ASD Market PA2 Solar | PA | Dauphin | Withdrawn | PPL | 5 | 3.7 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 | 3/23/2022 |  | 3/1/2024
PJM | AG1-338 | Curryville-RKB-Yellow Creek 23 kV I |  | PA | Bedford | Withdrawn | PENELEC | 5 | 4.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 | 9/9/2021 |  | 6/30/2023
PJM | AG1-339 | Curryville-RKB-Yellow Creek 23 kV II |  | PA | Bedford | Withdrawn | PENELEC | 5 | 4.6 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 8/4/2021 |  | 6/30/2023
PJM | AG1-340 | Curryville 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 5 | 3.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 8/27/2021 |  | 6/30/2024
PJM | AG1-341 - moved to TC1 | Summer Shade 161 kV |  | KY | Metcalfe | Active | EKPC | 106 | 63.6 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 |  |  | 6/15/2023
PJM | AG1-342 - moved to TC1 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 36 | 21.6 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/1/2023
PJM | AG1-343 - moved to TC1 | Boykins-Murphy 115 kV |  | VA | Southampton | Active | Dominion | 62.5 | 35 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/1/2023
PJM | AG1-344 | Culpeper 34.5 kV |  | VA | Culpeper | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/10/2021 |  | 6/1/2022
PJM | AG1-345 | Crewe 12.5 kV |  | VA | Nottoway | Withdrawn | Dominion | 8 | 4.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 | 10/8/2021 |  | 6/1/2022
PJM | AG1-346 - moved to TC1 | Mount Jackson DP 115 kV |  | VA | Shenandoah | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 12/1/2022
PJM | AG1-347 | Briery DP-Clover 230 kV |  | VA | Lunenburg | Withdrawn | Dominion | 100 | 56 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/12/2023 |  | 12/1/2024
PJM | AG1-348 | Pequest River-Washington 34.5 kV | Foul Rift Solar Farm | NJ | Warren | Under Construction | JCPL | 19.8 | 8.316 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2020 |  |  | 11/15/2025
PJM | AG1-349 | Olive-Reynolds #2 345 kV | Mayapple Solar | IN | Pulaski | Engineering and Procurement | AEP | 260 | 156 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 12/31/2027
PJM | AG1-351 | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 58 | 34.8 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-352 | Hunt Farm Junction 69 kV |  | KY | Boyle | Withdrawn | EKPC | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 | 9/28/2021 |  | 12/31/2023
PJM | AG1-353 - moved to TC1 | Green County-Marion County 161 kV |  | KY | Taylor | Active | EKPC | 98 | 58.8 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-354 - moved to TC1 | Summershade-Green County 161 kV |  | KY | Green | Active | EKPC | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-355 | Scalp Level-Hooversville 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 54 | 32.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 2/26/2021 |  | 12/31/2023
PJM | AG1-356 | Somerset-Allegheny 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 36 | 21.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 2/26/2021 |  | 12/31/2023
PJM | AG1-357 | Clover-Rawlings 500 kV |  | VA | Lunenburg | Withdrawn | Dominion | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/12/2023 |  | 12/1/2024
PJM | AG1-358 | Howard-Melmore 138 kV |  | OH | Crawford | Withdrawn | AEP | 58 | 34.8 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 11/8/2021 |  | 12/31/2023
PJM | AG1-359 - moved to TC1 | Fentress 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 127.5 | 127.5 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/1/2024
PJM | AG1-360 | Costen 25 kV | Costen Solar | MD | Somerset | In Service | DPL | 8.75 | 0 | Energy | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/1/2020 |  |  | 8/30/2024 | 10/7/2024
PJM | AG1-361 | Lexington Park 69 kV |  | MD | St. Mary's | Withdrawn | SMECO | 0 | 2.7 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/16/2021 |  | 3/31/2023
PJM | AG1-362 | Wernersville 12.47 kV | Furnace View Farms | PA | Berks | Suspended | PPL | 5 | 3.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 12/29/2023
PJM | AG1-363 | Black Oak-Hatfield 500 kV | Jade Meadow III Solar Facility | MD | Garrett | Engineering and Procurement | APS | 300 | 220 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 3/31/2028
PJM | AG1-364 - moved to TC1 | Deep Creek 115 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 100 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 11/30/2023
PJM | AG1-365 | Allen 345 kV | Flatrock Creek Solar II | IN | Allen | Engineering and Procurement | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 12/31/2028
PJM | AG1-366 | Allen 345 kV | Flatrock Creek Storage I | IN | Allen | Engineering and Procurement | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 12/31/2028
PJM | AG1-367 - moved to TC1 | DeSoto 345 kV |  | IN | Delaware | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 10/31/2024
PJM | AG1-368 | Tillman 138 kV |  | IN | Allen | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 10/31/2024
PJM | AG1-369 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 49.9 | 29.94 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 10/31/2023
PJM | AG1-371 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 0 | 30 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 | 6/21/2024 |  | 11/1/2024
PJM | AG1-372 | Nelson-Electric Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 0 | 20 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 9/30/2020 | 3/16/2021 |  | 11/1/2024
PJM | AG1-373 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 0 | 10 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/21/2024 |  | 11/1/2024
PJM | AG1-374 - moved to TC1 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/1/2024
PJM | AG1-375 - moved to TC1 | Sorenson-Desoto 345 kV |  | IN | Blackford | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 10/31/2024
PJM | AG1-376 | Sorenson-DeSoto 345 kV |  | IN | Blackford | Withdrawn | AEP | 30 | 12 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 9/30/2020 | 3/9/2021 |  | 10/31/2024
PJM | AG1-377 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 20 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 8/15/2023
PJM | AG1-378 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 20 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 8/15/2023
PJM | AG1-379 - moved to TC1 | Minonk 345 kV |  | IL | Woodford | Withdrawn | ComEd | 200 | 137.2 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 8/31/2023
PJM | AG1-380 | Corwin-Elk 138 kV |  | OH | Jackson | Withdrawn | AEP | 90 | 54 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 9/30/2020 | 3/30/2021 |  | 12/31/2023
PJM | AG1-381 | Hope 69 kV |  | KY | Montgomery | Withdrawn | EKPC | 27 | 17.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/9/2021 |  | 12/31/2023
PJM | AG1-382 | SGC Tap-Reese REC 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 7/25/2024 |  | 3/1/2022
PJM | AG1-383 | Hickory 34.5 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 15.43 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 3/1/2022
PJM | AG1-384 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 6 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2022
PJM | AG1-385 | Motion-Ridgeway 46 kV |  | PA | Washington | Withdrawn | APS | 20 | 15.43 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/24/2021 |  | 3/1/2022
PJM | AG1-386 | Smith-Francis Junction 25 kV | Smith-Francis Junction 25 kV | PA | Washington | Under Construction | APS | 20 | 15.42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 10/2/2020 |  |  | 3/31/2025
PJM | AG1-387 | Beth 33-Lilly 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/4/2021 |  | 3/1/2022
PJM | AG1-388 | Dunnsville 34.5 kV | Ex-Umphlette LLC | VA | Essex | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 9/30/2020 | 3/28/2023 |  | 3/31/2023
PJM | AG1-392 - moved to TC1 | Gold 115 kV I |  | PA | Potter | Active | PENELEC | 30 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2022
PJM | AG1-392A - moved to TC1 | Gold 115 kV II |  | PA | Potter | Active | PENELEC | 30 | 18 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 10/1/2020 |  |  | 6/1/2022
PJM | AG1-392B - moved to TC1 | Gold 115 kV III |  | PA | Potter | Active | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 10/1/2020 |  |  | 6/1/2022
PJM | AG1-392C - moved to TC1 | Gold 115 kV IV |  | PA | Potter | Active | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 10/1/2020 |  |  | 6/1/2022
PJM | AG1-393 - moved to TC1 | Fort Pickett DP 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 3/1/2022
PJM | AG1-394 - moved to TC1 | Boykins 34.5 kV |  | VA | Southampton | Active | Dominion | 14.2 | 5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 3/1/2022
PJM | AG1-395 | Philipsburg-Karthaus 34.5 kV 2 |  | PA | Clearfield | Withdrawn | PENELEC | 20 | 15.42 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 2/26/2021 |  | 3/1/2022
PJM | AG1-396 | Dauphin-Pine Grove 69 kV |  | PA | Dauphin | Withdrawn | PPL | 7.5 | 4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/10/2021 |  | 3/30/2022
PJM | AG1-397 | Walston 12 kV | Walston Solar | MD | Wicomico | Engineering and Procurement | DPL | 9.972 | 4.1882 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 6/30/2025
PJM | AG1-398 | Brokaw-Lanesville 345 kV | Alta Farms II | IL | Fulton | In Service | ComEd | 0 | 7.33 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn | Document Posted | 9/30/2020 |  |  | 9/2/2024 | 5/20/2023
PJM | AG1-399 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 300 | 52.8 | Capacity | Generation Interconnection | Wind | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 9/24/2024
PJM | AG1-400 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 9/24/2024
PJM | AG1-401 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Active | ComEd | 282 | 49.6 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 9/25/2024
PJM | AG1-402 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 150 | 150 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 9/24/2024
PJM | AG1-403 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 188 | 33.1 | Capacity | Generation Interconnection | Wind | Withdrawn | In Progress |  |  | 9/30/2020 | 12/18/2024 |  | 9/24/2024
PJM | AG1-404 - moved to TC1 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Withdrawn | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 9/24/2024
PJM | AG1-405 - moved to TC1 | Walnut Grove-Asahi 69 kV |  | KY | McLean | Active | EKPC | 57 | 34.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 9/25/2024
PJM | AG1-406 | Walnut Grove-Asahi 69 kV |  | KY | McLean | Active | EKPC | 22 | 22 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 9/25/2024
PJM | AG1-408 |  |  | OH | Fulton | Withdrawn | ATSI | 300 | 180 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2020 | 10/20/2020 |  | 9/25/2024
PJM | AG1-410 - moved to TC1 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 9/25/2024
PJM | AG1-411 - moved to TC1 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 9/25/2024
PJM | AG1-412 - moved to TC1 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Active | Dominion | 200 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 12/1/2023
PJM | AG1-413 | South Hill-Bordnax 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 69.5 | 41.7 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/12/2023 |  | 7/1/2024
PJM | AG1-414 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 75 | 45 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 6/30/2023
PJM | AG1-415 | Double Toll Gate-Old Chapel 138 kV | Beckett Solar | VA | Clarke | Engineering and Procurement | APS | 50 | 25 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 12/31/2028
PJM | AG1-416 | Sleepy Hollow 138 kV | Flowing Springs Farm | WV | Jefferson | Engineering and Procurement | APS | 125 | 91 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 8/31/2028
PJM | AG1-417 | Gateway 69 kV |  | IN | Whitley | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/11/2024 |  | 12/29/2023
PJM | AG1-418 | Gateway 69 kV |  | IN | Whitley | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/11/2024 |  | 12/29/2023
PJM | AG1-419 | Lynnville-South Hamburg 69 kV | Mountain Trail Solar | PA | Berks | Withdrawn | ME | 50 | 21 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2020 | 10/28/2024 |  | 1/31/2028
PJM | AG1-420 | Campbell-Kiesters 138 kV |  | PA | Butler | Withdrawn | APS | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2020 | 9/11/2024 |  | 12/29/2023
PJM | AG1-421 - moved to TC1 | Lexington-Dooms 230 kV |  | VA | Augusta | Withdrawn | Dominion | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/24/2024 |  | 12/29/2023
PJM | AG1-422 - moved to TC1 | Lexington-Dooms 230 kV |  | VA | Augusta | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/24/2024 |  | 12/29/2023
PJM | AG1-423 - moved to TC1 | Byron-Wayne 345 kV |  | IL | DeKalb | Withdrawn | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/29/2023
PJM | AG1-424 - moved to TC1 | Sowers 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/24/2024 |  | 12/29/2023
PJM | AG1-425 - moved to TC1 | Groton 138 kV |  | OH | Erie | Withdrawn | ATSI | 0 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/21/2024 |  | 10/31/2023
PJM | AG1-426 - moved to TC1 | Bremo-Scottsville 138 kV |  | VA | Buckingham | Withdrawn | AEP | 0 | 17 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 8/2/2024 |  | 10/31/2023
PJM | AG1-427 - moved to TC1 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Active | Dominion | 118.56 | 71.136 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2024
PJM | AG1-428 - moved to TC1 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Active | Dominion | 46.8 | 28.08 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/28/2024 |  | 12/31/2024
PJM | AG1-429 | Tasley - Oak Hall 69 kV |  | VA | Accomack | Withdrawn | ODEC | 58.7 | 35.2 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 5/26/2022 |  | 12/31/2024
PJM | AG1-431 | Mackeys 230 kV |  | NC | Washington | Withdrawn | Dominion | 0 | 266.2 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 8/19/2022 |  | 12/31/2024
PJM | AG1-431A | Mackeys 230 kV |  | NC | Washington | Withdrawn | Dominion | 0 | 200 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 8/19/2022 |  | 12/31/2024
PJM | AG1-432 - moved to TC1 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 200 | 120 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/31/2024
PJM | AG1-433 - moved to TC1 | Keystone-DeSoto 345 kV |  | IN | Blackford | Active | AEP | 100 | 17.6 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-434 - moved to TC1 | Electric Junction-Nelson 345 kV |  | IL | Lee | Active | ComEd | 175 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-435 - moved to TC1 | Kewanee-Hennepin 138 kV |  | IL | Bureau | Active | ComEd | 150 | 35.2 | Capacity | Generation Interconnection | Wind | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-436 - moved to TC1 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 125 | 75 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-437 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-438 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-439 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Active | Dominion | 250 | 150 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-440 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/31/2023
PJM | AG1-441 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/31/2023
PJM | AG1-442 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 35 | 35 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-443 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 35 | 35 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-444 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Active | Dominion | 80 | 80 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-445 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 26 | 26 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/31/2023
PJM | AG1-446 - moved to TC1 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 26 | 26 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/31/2023
PJM | AG1-447 - moved to TC1 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 55 | 55 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 12/31/2023
PJM | AG1-448 | Olive-University Park 345 kV |  | IN | LaPorte | Withdrawn | AEP | 55 | 55 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted |  |  | 9/30/2020 | 1/27/2022 |  | 12/31/2023
PJM | AG1-449 - moved to TC1 | Rawlings-Carson 500 kV |  | VA | Dinwiddie | Active | Dominion | 122 | 122 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2022
PJM | AG1-450 - moved to TC1 | Airey-Vienna 69 kV II |  | MD | Dorchester | Active | DPL | 25 | 25 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 12/31/2022
PJM | AG1-451 - moved to TC1 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Active | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/31/2022
PJM | AG1-453 - moved to TC1 | Guardian 138 kV |  | IN | Noble | Withdrawn | AEP | 140 | 84 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/21/2024 |  | 12/31/2023
PJM | AG1-454 - moved to TC1 | Guardian 138 kV |  | IN | Noble | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/21/2024 |  | 12/31/2022
PJM | AG1-455 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Withdrawn | PENELEC | 35 | 35 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2020 | 12/3/2024 |  | 12/31/2022
PJM | AG1-456 - moved to TC1 | Wildcat 138 kV |  | OH | Highland | Withdrawn | AEP | 30 | 30 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/21/2024 |  | 12/31/2022
PJM | AG1-457 | Somerset-Rockwood 115 kV |  | PA | Somerset | Withdrawn | PENELEC | 54 | 32.4 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/1/2021 |  | 12/31/2023
PJM | AG1-458 | Marlow-Bedington 138 kV |  | MD | Washington | Withdrawn | APS | 40 | 24 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/1/2021 |  | 12/31/2023
PJM | AG1-459 | Marlow-Bedington 138 kV |  | MD | Washington | Withdrawn | APS | 14 | 5.6 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/2/2021 |  | 12/31/2023
PJM | AG1-460 - moved to TC1 | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 30 | 12 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 6/1/2022
PJM | AG1-461 | Mumford 69 kV |  | DE | Sussex | Withdrawn | DPL | 30 | 19.5 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/20/2021 |  | 12/31/2023
PJM | AG1-462 - moved to TC1 | Cordova 345 kV |  | IL | Whiteside | Active | ComEd | 255 | 153 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 10/1/2020 |  |  | 10/1/2023
PJM | AG1-463 | Maysville 69 kV IV |  | PA | Mercer | Withdrawn | ATSI | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 9/30/2020 | 3/19/2021 |  | 5/21/2024
PJM | AG1-464 | Harrington 69 kV |  | DE | Kent | Withdrawn | DPL | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 9/17/2023
PJM | AG1-465 | North Hanover-Gitts Run 115 kV |  | PA | York | Withdrawn | ME | 100 | 40 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 3/5/2025
PJM | AG1-466 | Orange 34.5 kV |  | VA | Orange | Withdrawn | Dominion | 14 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 12/19/2022
PJM | AG1-467 | Somerset 34.5 kV |  | VA | Orange | Withdrawn | Dominion | 15.6 | 9.36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 12/28/2022
PJM | AG1-468 | Martinsville-Figsboro 34.5 kV |  | VA | Henry | Withdrawn | AEP | 14 | 8.4 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 | 3/31/2021 |  | 10/31/2022
PJM | AG1-469 | Gordonsville 34.5 kV | Turkey Solar | VA | Louisa | Engineering and Procurement | Dominion | 14.04 | 9.36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 8/29/2027
PJM | AG1-470 | Ringgold 138 kV |  | MD | Washington | Withdrawn | APS | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 10/1/2020 | 9/8/2023 |  | 9/6/2024
PJM | AG1-471 - moved to TC1 | Up Church-Wayne County 69 kV |  | KY | Wayne | Active | EKPC | 60 | 36 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 10/2/2023
PJM | AG1-472 | Seymour-Cave City 69 kV |  | KY | Hart | Withdrawn | EKPC | 80 | 48 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/13/2023 |  | 10/9/2023
PJM | AG1-473 - moved to TC1 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Active | PENELEC | 53.9 | 32.34 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2024
PJM | AG1-474 |  |  | PA | Centre | Withdrawn | APS | 70 | 49 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/30/2020 | 10/28/2020 |  | 6/1/2024
PJM | AG1-475 | Mickelton 230 kV |  | NJ | Gloucester | Withdrawn | AEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 4/26/2021 |  | 6/1/2023
PJM | AG1-476 | Mickelton 230 kV II |  | NJ | Gloucester | Withdrawn | AEC | 0 | 33.1 | Capacity | Generation Interconnection | Natural Gas; Other | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 8/21/2023 |  | 6/1/2023
PJM | AG1-477 | Grundy County 34.5 kV |  | IL | Grundy | Withdrawn | ComEd | 18 | 14.8 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/11/2023 |  | 12/29/2023
PJM | AG1-478 | Wilmington 34.5 kV | Wilmington Solar Energy Project | IL | Will | Engineering and Procurement | ComEd | 19.9 | 15.9 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 4/1/2026
PJM | AG1-479 | Grundy County 34.5 kV II |  | IL | Grundy | Withdrawn | ComEd | 19.9 | 15.9 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/30/2020 | 12/3/2020 |  | 12/29/2023
PJM | AG1-480 | Shawnee 34.5 kV | Shawnee Solar and BESS | PA | Monroe | Engineering and Procurement | ME | 18.2 | 18.2 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 12/31/2027
PJM | AG1-481 | Warren 34.5 kV |  | PA | Warren | Withdrawn | PENELEC | 15.53 | 15.53 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 | 11/1/2021 |  | 6/1/2024
PJM | AG1-482 | Hamilton 115 kV | Hamilton Solar and BESS | PA | Adams | Engineering and Procurement | ME | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 2/1/2028
PJM | AG1-483 - moved to TC1 | Dickerson 230 kV | Fourth Quarter | MD | Montgomery | Active | PEPCO | 500 | 500 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 10/1/2020 |  |  | 6/1/2024
PJM | AG1-484 | Mountain 115 kV |  | PA | Cumberland | Withdrawn | ME | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 | 11/1/2021 |  | 6/1/2024
PJM | AG1-485 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 55 | 55 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 6/1/2024
PJM | AG1-486 | Orrtanna 115 kV | Orrtanna | PA | Adams | Engineering and Procurement | ME | 15 | 15 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 12/31/2027
PJM | AG1-487 | Gilbert 230 kV | Gilbert Solar and BESS | NJ | Hunterdon | Engineering and Procurement | JCPL | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 6/1/2027
PJM | AG1-488 - moved to TC1 | Marion Co 161 kV |  | KY | Marion | Withdrawn | EKPC | 70 | 42 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/21/2024 |  | 9/30/2022
PJM | AG1-489 | McClelland-Hoytdale 345 kV |  | PA | Lawrence | Withdrawn | ATSI | 175 | 145 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/30/2020 | 9/27/2024 |  | 6/1/2023
PJM | AG1-490 | Shenango-McDowell 138 kV |  | PA | Mercer | Withdrawn | ATSI | 125 | 105 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 | 9/16/2021 |  | 6/1/2023
PJM | AG1-491 | Central Hardin 69 kV |  | KY | Hardin | Withdrawn | EKPC | 70 | 42 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/13/2023 |  | 6/30/2023
PJM | AG1-494 - moved to TC1 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/1/2023
PJM | AG1-495 | Gilbert-Rocktown 34.5 kV | Ridge Road Solar Farm | NJ | Hunterdon | Engineering and Procurement | JCPL | 19.8 | 8.316 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 10/1/2027
PJM | AG1-496 | East Flemington 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 6.6 | 2.772 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/24/2021 |  | 12/17/2021
PJM | AG1-497 - moved to TC1 | Cartanza 230 kV |  | DE | Kent | Withdrawn | DPL | 120 | 84 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 6/30/2023
PJM | AG1-498 | Mount Bethel 12.47 kV | Martins Creek Solar | PA | Northampton | Withdrawn | PPL | 8.8 | 3.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 | 5/30/2024 |  | 4/1/2025
PJM | AG1-499 | Lambs 12.47 kV | Esky Solar Project | NJ | Gloucester | Under Construction | AEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 9/30/2025
PJM | AG1-500 | Beaver 345 kV |  | OH | Lorain | Active | ATSI | 406.4 | 385.5 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 10/1/2022
PJM | AG1-501 | Beaver 138 kV | West Lorain 138 kV Power Plant | OH | Lorain | Engineering and Procurement | ATSI | 11.3 | 10 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 12/31/2028
PJM | AG1-502 - moved to TC1 | Oak Green 115 kV |  | VA | Orange | Active | Dominion | 80 | 64 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 |  |  | 6/30/2023
PJM | AG1-503 - moved to TC1 | Oak Green 115 kV |  | VA | Orange | Active | Dominion | 20 | 16 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 |  |  | 6/30/2023
PJM | AG1-504 | Glenbrook-Salem 69 kV |  | PA | Luzerne | Withdrawn | PPL | 68 | 41.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 | 10/5/2021 |  | 12/31/2023
PJM | AG1-505 - moved to TC1 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 7/1/2024
PJM | AG1-506 - moved to TC1 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 7/1/2024
PJM | AG1-507 | Calumet 138 kV | Southeast Chicago Energy Project (aka SCEP) | IL | Cook | Withdrawn | ComEd | 296 | 296 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2020 | 1/29/2024 |  | 6/1/2024
PJM | AG1-508 | Point Lookout 69 kV |  | VA | Grayson | Active | AEP | 63.3 | 9.3 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 3/1/2025
PJM | AG1-509 | Point Lookout 69 kV |  | VA | Grayson | Withdrawn | AEP | 105.4 | 15.5 | Capacity | Generation Interconnection | Wind | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 3/29/2022 |  | 3/1/2025
PJM | AG1-510 | Kittatinny-Blairstown 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2020 | 7/15/2024 |  | 6/1/2024
PJM | AG1-511 | Kittatinny 230 kV | Mt Vernon Solar | NJ | Warren | Engineering and Procurement | JCPL | 50 | 30 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 7/31/2028
PJM | AG1-512 | University Park North 345 kV | University Park North Energy Center | IL | Will | Engineering and Procurement | ComEd | 40 | 16 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 1/11/2027
PJM | AG1-513 | Aurora 138 kV | Aurora Battery Storage | IL | Will | Suspended | ComEd | 10 | 4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 10/1/2020 |  |  | 6/1/2028
PJM | AG1-514 | Springdale CT III 138 kV | Springdale | PA | Allegheny | Active | APS | 10 | 4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 6/1/2027
PJM | AG1-515 | Guilford 138 kV | Chambersburg Energy | PA | Franklin | Engineering and Procurement | APS | 10 | 4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 5/31/2027
PJM | AG1-516 | Gans 138 kV | Gans Energy CT and BESS | PA | Fayette | Withdrawn | APS | 10 | 4 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2020 | 11/11/2024 |  | 5/21/2027
PJM | AG1-517 | Osage 138 kV | Beechurt Natural Gas | WV | Monongalia | Engineering and Procurement | APS | 50 | 50 | Capacity | Generation Interconnection | Natural Gas | Document Posted | Document Posted | Document Posted | Document Posted | 9/30/2020 |  |  | 1/31/2028
PJM | AG1-518 | Suffolk 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 9/1/2023
PJM | AG1-519 | Cash's Corner 230 kV |  | VA | Louisa | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted |  |  | 9/30/2020 | 9/16/2021 |  | 10/28/2022
PJM | AG1-520 | Hooversville-Rockingham 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 4 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 1/1/2022
PJM | AG1-521 | Dixon-McGirr Road 138 kV |  | IL | Lee | Withdrawn | ComEd | 100 | 80 | Capacity | Generation Interconnection | Solar | Document Posted |  |  |  | 9/30/2020 | 3/16/2021 |  | 10/30/2023
PJM | AG1-522 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2023
PJM | AG1-523 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2023
PJM | AG1-524 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2023
PJM | AG1-525 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2023
PJM | AG1-526 - moved to TC1 | West Garrard 345 kV |  | KY | Garrard | Active | EKPC | 222 | 133.2 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 6/1/2023
PJM | AG1-527 | Imperial-Joffre 138 kV | Beech Hollow Solar | PA | Allegheny | Withdrawn | APS | 215 | 129 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted | Withdrawn | 9/30/2020 |  |  | 7/31/2028
PJM | AG1-528 | Tenmile - Sundial 138 kV |  | WV |  | Active | AEP | 225 | 135 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 6/1/2023
PJM | AG1-529 - moved to TC1 | Farmview 138 kV |  | DE | Sussex | Withdrawn | DPL | 75 | 48.9 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 8/2/2024 |  | 12/31/2023
PJM | AG1-530 |  |  | OH | Clark | Withdrawn | ATSI | 54 | 35.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2020 | 10/16/2020 |  | 12/31/2023
PJM | AG1-531 - moved to TC1 | Poolesville-Winchester 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 54 | 32.4 | Capacity | Generation Interconnection | Solar | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 12/12/2023
PJM | AG1-532 | Fields 34.5 kV | Fields 2 | VA | Greensville | Engineering and Procurement | Dominion | 13.5 | 8.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 9/29/2027
PJM | AG1-533 | Bartonsville-Meadowbrook 138 kV IV | Bartonsville Energy Facility | VA | Frederick | Withdrawn | APS | 40 | 24 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 10/14/2024 |  | 12/12/2023
PJM | AG1-534 | Evergreen Mills 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 200 | 200 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 9/12/2023 |  | 6/1/2023
PJM | AG1-535 - moved to TC1 | State Line-S. Chicago Properties 138 kV |  | IL | Cook | Withdrawn | ComEd | 85 | 85 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 8/2/2024 |  | 6/1/2023
PJM | AG1-536 - moved to TC1 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 75 | 32 | Capacity | Generation Interconnection | Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 10/1/2024
PJM | AG1-537 - moved to TC1 | Barterbrook-Stuarts Draft 115 kV |  | VA | Augusta | Active | Dominion | 75 | 32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 10/1/2024
PJM | AG1-538 - moved to TC1 | Remington-Gordonsville 230 kV |  | VA | Culpeper | Withdrawn | Dominion | 75 | 32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | Withdrawn |  | 9/30/2020 | 6/24/2024 |  | 10/1/2024
PJM | AG1-539 - moved to TC1 | Grit DP-Perth 115 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 75 | 32 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 10/1/2024
PJM | AG1-540 | Berry Hill 138 kV |  | VA | Pittsylvania | Withdrawn | AEP | 55 | 21.35 | Capacity | Generation Interconnection | Storage | Document Posted |  |  |  | 9/30/2020 | 3/5/2021 |  | 10/1/2024
PJM | AG1-541 | St. Johns 115 kV |  | VA | Hanover | Withdrawn | Dominion | 75 | 32 | Capacity | Generation Interconnection | Storage | Document Posted | Document Posted | In Progress |  | 9/30/2020 | 9/12/2023 |  | 10/1/2024
PJM | AG1-542 |  |  | VA | Greensville | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/30/2020 | 10/16/2020 |  | 10/1/2024
PJM | AG1-543 |  |  | VA | Charles City | Withdrawn | Dominion | 325 | 211.764 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/30/2020 | 11/5/2020 |  | 10/1/2024
PJM | AG1-544 | Bakers Pond DP 115 kV |  | VA | Prince George | Withdrawn | Dominion | 60 | 39.048 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/12/2023 |  | 10/1/2024
PJM | AG1-545 | W. Quaker Rd-Disputanta 34.5 kV |  | VA | Prince George | Withdrawn | Dominion | 20 | 14 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  |  | 9/30/2020 | 9/17/2021 |  | 10/1/2024
PJM | AG1-546 | Ebony-Elams Road 115 kV |  | VA | Brunswick | Withdrawn | Dominion | 150 | 97.62 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 9/30/2020 | 3/17/2021 |  | 10/1/2024
PJM | AG1-547 - moved to TC1 | Mount Airy-Chatham 69 kV |  | VA | Pittsylvania | Withdrawn | Dominion | 50 | 32.54 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 10/1/2024
PJM | AG1-548 - moved to TC1 | Erie South-Union City 115 kV |  | PA | Erie | Active | PENELEC | 150 | 45 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 10/31/2022
PJM | AG1-549 - moved to TC1 | Keystone 230 kV |  | PA | Armstrong | Active | PENELEC | 100 | 85 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 10/31/2022
PJM | AG1-550 | Mount Eagle-Fork Union 230 kV |  | VA | Fluvanna | Withdrawn | Dominion | 35 | 35 | Capacity | Generation Interconnection | Solar; Storage | Document Posted |  |  |  | 9/30/2020 | 3/5/2021 |  | 9/1/2023
PJM | AG1-551 - moved to TC1 | Parmele 12.5 kV |  | NC | Martin | Active | Dominion | 19.99 | 13.1 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | In Progress |  | 9/30/2020 |  |  | 10/15/2023
PJM | AG1-552 - moved to TC1 | Carolina 13.2 kV |  | NC | Northhampton | Active | Dominion | 18 | 12.2 | Capacity | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 10/15/2023
PJM | AG1-553 - moved to TC1 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 284 | 0 | Energy | Generation Interconnection | Solar | Document Posted | In Progress |  |  | 9/30/2020 |  |  | 12/29/2023
PJM | AG1-554 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 49.99 | 32.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 10/31/2023
PJM | AG1-555 | Dequine 345 kV | Rainbow Trout | IN | Tippecance | Active | AEP | 120 | 88.4 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 6/1/2024
PJM | AG1-556 - moved to TC1 | Lexington 115 kV |  | VA | Rockbridge | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 6/24/2024 |  | 6/1/2024
PJM | AG1-557 | Curdsville DP 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/30/2020 | 12/14/2020 |  | 10/21/2022
PJM | AG1-558 | Buckner 34.5 kV | Horsepen Branch Solar | VA | Louisa | Engineering and Procurement | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 10/29/2027
PJM | AG1-559 | Caroline Pines 22 kV |  | VA | Hanover | Engineering and Procurement | Dominion | 20 | 13.3 | Capacity | Generation Interconnection | Solar; Storage | Document Posted | In Progress |  | Wholesale Market Participation Agreement | 9/30/2020 |  |  | 10/27/2027
PJM | AG1-560 | Shade Gap-Roxbury 115 kV II |  | PA | Franklin | Withdrawn | PENELEC | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/12/2023 |  | 6/30/2023
PJM | AG1-561 | Roxbury-Greene 138 kV II |  | PA | Franklin | Withdrawn | PENELEC | 0 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Withdrawn |  |  | 9/30/2020 | 9/12/2023 |  | 6/1/2022
PJM | AG1-562 | Marysville-Gunn Road 345 kV | Taylor Creek | OH | Hardin | Active | AEP | 250 | 150 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Document Posted |  | 9/30/2020 |  |  | 3/31/2028
PJM | AG1-563 | Bennett-Farmingdale 2 34.5 kV | AG1-563 | NJ | Monmouth | In Service | JCPL | 0 | 0.7 | Capacity | Generation Interconnection | Solar | Document Posted | Document Posted | Not Required | Document Posted | 9/30/2020 |  |  | 6/1/2020 | 7/16/2021
PJM | AG2-001 | St. Johns DP 115 kV |  | VA | Essex | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/1/2020 | 12/18/2024 |  | 9/30/2022
PJM | AG2-002 | Galion 138 kV III |  | OH | Morrow | Withdrawn | ATSI | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/2/2020 | 12/18/2024 |  | 12/31/2023
PJM | AG2-003 | West Millersport 138 kV |  | OH | Fairfield | Withdrawn | AEP | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/2/2020 | 12/18/2024 |  | 12/31/2023
PJM | AG2-004 | East Sidney-Quincy 138 kV |  | OH | Champaign | Withdrawn | Dayton | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/2/2020 | 12/18/2024 |  | 11/30/2021
PJM | AG2-005 | Garner-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 20 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/2/2020 |  |  | 12/31/2022
PJM | AG2-006 | Centerburg-Conesville 138 kV |  | OH | Licking | Withdrawn | AEP | 50 | 21 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/2/2020 | 12/18/2024 |  | 10/31/2023
PJM | AG2-007 | Lanexa-Dunnsville 230 kV |  | VA | King William | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/6/2020 | 3/28/2024 |  | 11/15/2023
PJM | AG2-008 | Erie South-Warren 230 kV |  | PA | Erie | Active | PENELEC | 60 | 40.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/8/2020 |  |  | 3/30/2023
PJM | AG2-009 | Erie South-Warren 230 kV II |  | PA | Erie | Active | PENELEC | 20 | 12.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/8/2020 |  |  | 3/30/2023
PJM | AG2-010 | Peninsula-Whealton 115 kV |  | VA | City of Hampton | Active | Dominion | 100 | 75.96 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 10/9/2020 |  |  | 1/1/2023
PJM | AG2-011 | Laurel Mountain 138 kV |  | WV | Barbour | Withdrawn | APS | 56.3 | 34.2 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/13/2020 | 12/18/2024 |  | 4/1/2024
PJM | AG2-012 | Lardin 12 kV |  | PA | Fayette | Withdrawn | APS | 0.165 | 0 | Energy | Generation Interconnection | Solar | Not Required |  |  | Wholesale Market Participation Agreement | 10/15/2020 | 3/8/2023 |  | 12/31/2023
PJM | AG2-013 | Marysville-Sorenson 765 kV |  | OH | Logan | Withdrawn | AEP | 200 | 84 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/16/2020 | 12/18/2024 |  | 12/31/2023
PJM | AG2-014 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 10/19/2020 |  |  | 10/31/2023
PJM | AG2-016 | Oyster Creek-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.8 | 8.316 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/20/2020 |  |  | 12/17/2021
PJM | AG2-017 | New Castle-Clay Village 69 kV |  | KY | Shelby | Withdrawn | EKPC | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/20/2020 | 12/7/2020 |  | 9/30/2022
PJM | AG2-018 |  |  | OH | Morgan | Withdrawn | AEP | 105 | 73.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/20/2020 | 11/18/2020 |  | 4/29/2022
PJM | AG2-019 | Chase City 12.5 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 15 | 6 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 10/23/2020 | 12/18/2024 |  | 12/30/2022
PJM | AG2-020 | Arnolds Corner 34.5 kV |  | VA | King George | Active | Dominion | 7 | 2.8 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 10/23/2020 |  |  | 12/30/2022
PJM | AG2-021 | Crossroads 13.2 kV |  | PA | York | Withdrawn | ME | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 10/15/2024 |  | 12/15/2021
PJM | AG2-022 | Ebenezer 12.47 kV |  | PA | Dauphin | Withdrawn | PPL | 3 | 2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 8/8/2024 |  | 12/15/2021
PJM | AG2-023 | Mechanicsburg 12.47 kV |  | PA | Cumberland | Withdrawn | PPL | 3 | 2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 8/8/2024 |  | 12/15/2021
PJM | AG2-024 | Allen 13.2 kV |  | PA | Cumberland | Withdrawn | ME | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 10/15/2024 |  | 12/15/2021
PJM | AG2-025 | Mountain 13.2 kV |  | PA | Cumberland | Withdrawn | ME | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 10/15/2024 |  | 12/15/2021
PJM | AG2-026 | Leesport 34.5 kV |  | PA | Berks | Withdrawn | ME | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 10/15/2024 |  | 12/15/2021
PJM | AG2-027 | Orrtanna 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 10/15/2024 |  | 12/15/2021
PJM | AG2-028 | Lincoln 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 2.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/23/2020 | 10/15/2024 |  | 12/15/2021
PJM | AG2-029 | Forest G. Hipple-Collingwood 345 kV |  | IN | Noble | Active | AEP | 300 | 221.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/23/2020 |  |  | 6/1/2024
PJM | AG2-031 | East Canton-Robertsville 69 kV |  | OH | Stark | Withdrawn | AEP | 30.2 | 22.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/30/2020 | 11/11/2024 |  | 1/1/2023
PJM | AG2-032 | Mannington 230 kV |  | NJ | Salem | Withdrawn | AEC | 60 | 40 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 10/30/2020 | 12/18/2024 |  | 12/31/2023
PJM | AG2-033 | Southwest Lima-West Moulton 138 kV |  | OH | Auglaize | Withdrawn | AEP | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/4/2020 | 4/26/2024 |  | 10/31/2023
PJM | AG2-034 | Emporia-Pleasant Hill 115 kV |  | VA | Greensville | Withdrawn | Dominion | 150 | 105 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 11/4/2020 | 12/18/2024 |  | 10/1/2024
PJM | AG2-035 | Salem - Woodstown 69 kV |  | NJ | Salem | Active | AEC | 33 | 22 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 11/11/2020 |  |  | 12/31/2021
PJM | AG2-036 | Mantua 12 kV |  | NJ | Gloucester | Withdrawn | AEC | 10 | 5.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/13/2020 | 12/18/2024 |  | 12/31/2021
PJM | AG2-037 | Findlay-Clinton 23 kV |  | PA | Allegheny | Active | DL | 4.7 | 2.82 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/13/2020 |  |  | 12/1/2021
PJM | AG2-038 | Boyers DP 25 kV |  | PA | Venango | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/16/2020 | 12/18/2024 |  | 3/30/2022
PJM | AG2-039 | Erie West-Fairview East 34.5 kV |  | PA | Erie | Withdrawn | PENELEC | 19.8 | 11.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/16/2020 | 12/18/2024 |  | 3/30/2022
PJM | AG2-040 | Garman-Greenwich Mine 34.5 kV |  | PA | Indiana | Withdrawn | PENELEC | 19.8 | 11.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/16/2020 | 12/18/2024 |  | 3/30/2022
PJM | AG2-041 | Jamestown Tap-Maysville 69 kV |  | PA | Mercer | Withdrawn | ATSI | 19.8 | 11.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/16/2020 | 12/18/2024 |  | 3/30/2022
PJM | AG2-042 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/17/2020 | 12/11/2020 |  | 12/31/2021
PJM | AG2-043 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/17/2020 | 12/11/2020 |  | 12/31/2021
PJM | AG2-044 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/17/2020 | 12/11/2020 |  | 12/31/2021
PJM | AG2-045 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/17/2020 | 12/11/2020 |  | 7/31/2022
PJM | AG2-046 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/17/2020 | 12/11/2020 |  | 7/31/2022
PJM | AG2-047 |  |  | NJ | Atlantic | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/17/2020 | 12/11/2020 |  | 12/31/2021
PJM | AG2-048 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/17/2020 | 12/22/2020 |  | 12/31/2021
PJM | AG2-049 | Van Dorn 34.5 kV |  | VA | Arlington | Active | Dominion | 0 | 20 | Capacity | Generation Interconnection | Methane | In Progress |  |  |  | 11/20/2020 |  |  | 12/31/2020
PJM | AG2-050 | Randle Cliff 13.8 kV | CHESAPEAKE BEACH BESS | MD | Calvert | In Service | BGE | 1 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 11/25/2020 |  |  | 5/1/2023 | 5/9/2023
PJM | AG2-051 | St. Johns DP 115 kV |  | VA | Louisa | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/2/2020 | 12/18/2024 |  | 3/31/2023
PJM | AG2-053 | Fulton 138 kV |  | OH | Fulton | Active | ATSI | 300 | 180 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/2/2020 |  |  | 9/25/2024
PJM | AG2-054 | Fulton 138 kV |  | OH | Fulton | Active | ATSI | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/2/2020 |  |  | 9/25/2024
PJM | AG2-055 | Deans 500 kV |  | NJ | Middlesex | Withdrawn | PSEG | 1300 | 370.92 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 12/4/2020 | 12/19/2024 |  | 11/1/2027
PJM | AG2-056 | Gore 138 kV |  | VA | Frederick | Withdrawn | APS | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/4/2020 | 11/7/2024 |  | 5/31/2022
PJM | AG2-057 | Cardington-Liberty 69 kV II |  | OH | Morrow | Active | ATSI | 17 | 7.14 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/7/2020 |  |  | 11/30/2022
PJM | AG2-058 | Harmony Village-White Marsh 115 kV |  | VA | Gloucester | Withdrawn | Dominion | 70 | 46 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/8/2020 | 12/18/2024 |  | 6/3/2024
PJM | AG2-059 | Clubhouse-Lakeview 230 kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 52.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/8/2020 | 12/10/2024 |  | 6/3/2024
PJM | AG2-060 | Hanover-Plymouth 69 kV |  | PA | Luzerne | Withdrawn | UGI | 12.6 | 7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/10/2020 | 12/18/2024 |  | 3/8/2022
PJM | AG2-061 | Powerton-Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/11/2020 |  |  | 12/31/2023
PJM | AG2-062 | Williams 138 kV |  | WV | Grant | Active | APS | 147 | 21.609 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 12/15/2020 |  |  | 8/1/2022
PJM | AG2-063 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 54 | 34.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/16/2020 |  |  | 12/31/2023
PJM | AG2-064 | St Johns DP 115 kV |  | VA | Caroline | Withdrawn | Dominion | 41 | 24.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/17/2020 | 12/18/2024 |  | 10/31/2023
PJM | AG2-065 | River Ridge 34.5 kV |  | VA | Prince William | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 12/28/2020 | 8/23/2022 |  | 12/15/2021
PJM | AG2-066 | Rockcastle 138 kV |  | VA | Bedford | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/28/2020 | 11/7/2024 |  | 5/30/2022
PJM | AG2-067 | Heritage-Wake 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/30/2020 | 12/18/2024 |  | 12/1/2025
PJM | AG2-068 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/30/2020 |  |  | 12/1/2025
PJM | AG2-069 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/30/2020 |  |  | 12/1/2025
PJM | AG2-070 | Chickhominy-Surry 500 kV |  | VA | Charles City | Withdrawn | Dominion | 325 | 228 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 12/30/2020 | 12/18/2024 |  | 10/1/2024
PJM | AG2-071 | Cumberland 12 kV |  | NJ | Cumberland | Withdrawn | AEC | 3 | 1.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/31/2020 | 1/3/2022 |  | 12/31/2021
PJM | AG2-072 | Rockport 765 kV |  | IN | Spencer | Active | AEP | 700 | 700 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 1/6/2021 |  |  | 5/31/2026
PJM | AG2-073 | Crooksville 69 kV |  | KY | Madison | Active | EKPC | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/11/2021 |  |  | 5/1/2024
PJM | AG2-074 | Meckesville Tap 69kV |  | PA | Carbon | Active | PPL | 38 | 26.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/15/2021 |  |  | 12/31/2023
PJM | AG2-075 | Hartland 12.47 kV |  | OH | Fayette | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/19/2021 | 3/22/2021 |  | 9/14/2022
PJM | AG2-077 | Clover-Rawlings 500 kV |  | VA | Charlotte | Active | Dominion | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/19/2021 |  |  | 6/30/2024
PJM | AG2-078 | Lappans 34.5 kV |  | MD | Washington | Withdrawn | APS | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/20/2021 | 12/18/2024 |  | 5/23/2022
PJM | AG2-079 | Clearville-Clearville Junction 34.5 kV |  | PA | Bedford | Withdrawn | APS | 20 | 13.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/20/2021 | 12/18/2024 |  | 4/11/2022
PJM | AG2-080 | Lexington 115 kV |  | VA | Rockbridge | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/21/2021 |  |  | 6/1/2024
PJM | AG2-081 | Mt. Sterling-Fogg Pike 69 kV |  | KY | Montgomery | Active | EKPC | 30 | 18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/21/2021 |  |  | 5/1/2024
PJM | AG2-082 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 200 | 133.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/22/2021 |  |  | 12/1/2024
PJM | AG2-083 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/22/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-084 | Greentown 138 kV |  | IN | Howard | Active | AEP | 100 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/22/2021 |  |  | 12/31/2023
PJM | AG2-085 | West Del-Royerton 138 kV |  | IN | Delaware | Active | AEP | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/22/2021 |  |  | 12/31/2023
PJM | AG2-086 | Mt. Jackson DP-Mt. Jackson 115 kV |  | VA | Shenandoah | Active | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 1/22/2021 |  |  | 12/30/2022
PJM | AG2-087 | Pennsauken 12 kV |  | NJ | Camden | Withdrawn | PSEG | 2.49 | 0.772 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/5/2021 | 4/6/2021 |  | 1/1/2022
PJM | AG2-088 | Midlothian 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/26/2021 |  |  | 4/15/2022
PJM | AG2-089 | Pelikan-Kennaloyal 25 kV |  | PA | Westmoreland | Withdrawn | APS | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/26/2021 | 12/18/2024 |  | 7/1/2022
PJM | AG2-090 | Scalp Level 23 kV IV |  | PA | Somerset | Active | PENELEC | 14 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/26/2021 |  |  | 1/31/2023
PJM | AG2-091 | Scalp Level 23 kV V |  | PA | Somerset | Active | PENELEC | 6 | 3.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/26/2021 |  |  | 1/15/2023
PJM | AG2-092 | Todd 69 kV II |  | MD | Dorchester | Active | DPL | 0 | 11 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/26/2021 |  |  | 12/31/2021
PJM | AG2-093 | Colonial Trail-Hopewell 230 kV |  | VA | Prince George | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 1/26/2021 |  |  | 12/1/2024
PJM | AG2-094 | Summer Shade-Green County 161 kV |  | KY | Metcalfe | Active | EKPC | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/27/2021 |  |  | 4/1/2024
PJM | AG2-095 | Hopewell 34.5 kV (Circuit 313) |  | VA | Prince George | Active | Dominion | 18 | 10.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/28/2021 |  |  | 12/8/2023
PJM | AG2-096 | Dauphin PG Tie-Dauphin Juniata Tie 69 kV |  | PA | Dauphin | Active | PPL | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 1/28/2021 |  |  | 12/1/2022
PJM | AG2-097 | Altoona-Raystown 230 kV II |  | PA | Blair | Withdrawn | PENELEC | 0 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/28/2021 | 8/7/2024 |  | 6/30/2022
PJM | AG2-098 | Copperstone-North Lebanon 230 kV II |  | PA | Lebanon | Active | ME | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 1/28/2021 |  |  | 6/30/2022
PJM | AG2-099 | Moshannon-Milesburg 230 kV V |  | PA | Centre | Active | APS | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 1/28/2021 |  |  | 6/30/2022
PJM | AG2-100 | Moshannon-Milesburg 230 kV VI |  | PA | Centre | Active | APS | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 1/28/2021 |  |  | 6/30/2022
PJM | AG2-101 | Princess Anne–Loretto 69 kV |  | MD | Somerset | Withdrawn | DPL | 58.6 | 35.16 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/28/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-102 | Oak Hall-Perdue 69 kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 1/28/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-103 | Oak Hall-Hallwood 69 kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 1/28/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-104 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 253.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 9/1/2025
PJM | AG2-105 | Marysville-Flatlick 765 kV |  | OH | Madison | Withdrawn | AEP | 400 | 253.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/29/2021 | 12/18/2024 |  | 9/1/2026
PJM | AG2-106 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 0 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/29/2021 |  |  | 12/1/2024
PJM | AG2-107 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 0 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/29/2021 |  |  | 12/1/2024
PJM | AG2-108 | Milford-Cool Springs 230 kV |  | DE | Sussex | Withdrawn | DPL | 460 | 130.6 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 1/29/2021 | 12/18/2024 |  | 10/31/2026
PJM | AG2-109 | Fitchville-New London 69 kV |  | OH | Huron | Active | ATSI | 40 | 28.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 12/31/2023
PJM | AG2-110 | Marysville-Tangy 345 kV |  | OH | Union | Withdrawn | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/29/2021 | 12/17/2024 |  | 6/1/2024
PJM | AG2-111 | Perth 34.5 kV Substation (Circuit 408) |  | VA | Campbell | Active | Dominion | 14.8 | 8.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 2/6/2023
PJM | AG2-112 | Perth 34.5 kV Substation (Circuit 404) |  | VA | Halifax | Active | Dominion | 15.2 | 9.12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 3/24/2023
PJM | AG2-113 | Nokesville-Vint Hill 230 kV |  | VA | Prince William | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/29/2021 | 12/18/2024 |  | 8/10/2022
PJM | AG2-114 | Dresden-Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 3/1/2024
PJM | AG2-115 | Mt. Hermon 25 kV |  | MD | Wicomico | Withdrawn | DPL | 8.466 | 3.5557 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/29/2021 | 12/18/2024 |  | 8/29/2022
PJM | AG2-116 | Olive-Reynolds 345 #1 345 kV |  | IN | White | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 1/29/2021 |  |  | 10/31/2023
PJM | AG2-117 | Olive-Reynolds #2 345 kV |  | IN | White | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 1/29/2021 | 12/18/2024 |  | 10/31/2023
PJM | AG2-118 | Ford-Cedarville 138 kV |  | OH | Clermont | Withdrawn | DEOK | 84 | 56.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/29/2021 | 12/18/2024 |  | 12/1/2024
PJM | AG2-119 | Galion-Roberts South 138 kV II |  | OH | Marion | Active | ATSI | 160 | 106.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 9/1/2024
PJM | AG2-120 | Everetts 34.5 kV |  | NC | Martin | Active | Dominion | 21 | 14 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 12/15/2024
PJM | AG2-121 | Mackeys 230 kV |  | NC | Washington | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 1/29/2021 |  |  | 12/15/2023
PJM | AG2-122 | Crystal Hill - Halifax 115 kV |  | VA | Halifax | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 1/29/2021 | 12/17/2024 |  | 6/30/2022
PJM | AG2-123 | Sedge Hill - Person 230 kV |  | VA | Halifax | Withdrawn | Dominion | 0 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 1/29/2021 | 12/17/2024 |  | 6/30/2022
PJM | AG2-124 | Shackleford-Harmony 115 kV |  | VA | King and Queen | Active | Dominion | 0 | 33.34 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 12/31/2023
PJM | AG2-125 | Camden-Crystal 69 kV |  | OH | Preble | Active | Dayton | 0 | 15.44 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 12/31/2022
PJM | AG2-126 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 1/29/2021 |  |  | 6/30/2023
PJM | AG2-127 | Gladstone 138 kV |  | VA | Nelson | Withdrawn | AEP | 0 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/29/2021 | 12/18/2024 |  | 9/1/2024
PJM | AG2-128 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 0 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/30/2021 | 12/18/2024 |  | 7/1/2024
PJM | AG2-129 | Rawlings-Clover 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 0 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 1/30/2021 | 12/18/2024 |  | 7/1/2024
PJM | AG2-130 | Colby Tap-Valley 138 kV |  | MI | Van Buren | Active | AEP | 55 | 37.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/2/2021 |  |  | 12/31/2026
PJM | AG2-131 | Almena-Valley 69 kV |  | MI | Van Buren | Active | AEP | 40 | 20 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/1/2021 |  |  | 12/31/2026
PJM | AG2-132 | Hartford-South Haven 69 kV |  | MI | Van Buren | Active | AEP | 15 | 7.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/1/2021 |  |  | 12/31/2026
PJM | AG2-133 | South Creek 69 kV |  | VA | Appomattox | Withdrawn | Dominion | 52.44 | 34.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/31/2021 | 1/23/2024 |  | 12/31/2023
PJM | AG2-134 |  |  | PA | Montgomery | Withdrawn | PPL | 5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/3/2021 | 2/25/2021 |  | 8/31/2022
PJM | AG2-135 | Hoffman Estates 12.5 kV | Patel Brothers Energy Storage System | OH | Pickaway | Withdrawn | ComEd | 0.28 | 0 | Energy | Generation Interconnection | Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 2/4/2021 | 1/10/2022 |  | 4/15/2022
PJM | AG2-136 | Lake Lynn-Lardin 138 kV |  | PA | Fayette | Withdrawn | APS | 119.6 | 74.152 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/4/2021 | 4/23/2021 |  | 12/31/2023
PJM | AG2-137 | Surry-Chuckatuck 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 70 | 43.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/8/2021 | 12/18/2024 |  | 6/3/2024
PJM | AG2-139 | Lincoln 771-4 13.2 kV |  | PA | Adams | Withdrawn | ME | 3 | 2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/9/2021 | 8/9/2024 |  | 8/1/2022
PJM | AG2-142 | Bowman's Mill 69 kV |  | PA | Columbia | Withdrawn | PPL | 13 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/12/2021 | 10/6/2023 |  | 11/30/2023
PJM | AG2-143 | Burma-Sligo 25 kV |  | PA | Clarion | Active | APS | 20 | 10 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/16/2021 |  |  | 12/31/2026
PJM | AG2-144 | Carlls Corner 12 kV |  | NJ | Salem | Withdrawn | AEC | 1.5 | 0.63 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/16/2021 | 3/11/2022
PJM | AG2-145 | Page-Bethel 138 kV |  | VA | Pulaski | Withdrawn | APS | 0 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 1/29/2021 | 8/3/2023 |  | 6/30/2022
PJM | AG2-147 | Pontiac Midpoint 34.5kV |  | IL | Livingston | Withdrawn | ComEd | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/22/2021 | 12/18/2024 |  | 3/1/2024
PJM | AG2-148 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 130 | 86 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/22/2021 |  |  | 12/2/2024
PJM | AG2-149 | Galion-South Berwick 345 kV |  | OH | Crawford | Active | AEP | 400 | 267 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/22/2021 |  |  | 12/2/2024
PJM | AG2-150 | River Dock 23 kV |  | PA | Allegheny | Withdrawn | DL | 5.25 | 5.25 | Capacity | Generation Interconnection | Hydro | In Progress |  |  |  | 2/23/2021 |  |  | 12/31/2022
PJM | AG2-151 | Trices Lake - James River Tap 115 kV |  | VA | Cumberland | Active | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2021 |  |  | 2/2/2024
PJM | AG2-152 | Banister-Bear Skin 138 kV |  | VA | Pittsylvania | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2021 |  |  | 2/2/2024
PJM | AG2-153 | Headquarters-Sideview 69 kV |  | KY | Bourbon | Withdrawn | EKPC | 75 | 45 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/24/2021 | 12/18/2024 |  | 12/1/2023
PJM | AG2-154 | Danville 12 kV |  | PA | Northumberland | Withdrawn | PPL | 1 | 0.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/25/2021 | 12/18/2024 |  | 6/30/2022
PJM | AG2-155 | Linden 12 kV |  | PA | Lycoming | Withdrawn | PPL | 2.8 | 1.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/25/2021 | 12/18/2024 |  | 6/30/2022
PJM | AG2-156 | Montgomery 12 kV |  | PA | Lycoming | Withdrawn | PPL | 5.1 | 2.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/25/2021 | 12/18/2024 |  | 6/30/2022
PJM | AG2-157 | Ashfield 12 kV |  | PA | Carbon | Withdrawn | PPL | 1.5 | 0.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/25/2021 | 12/18/2024 |  | 6/30/2022
PJM | AG2-158 |  |  | KY | Russell | Withdrawn | EKPC | 44 | 15 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 2/25/2021 | 2/26/2021 |  | 9/15/2023
PJM | AG2-159 | Williamstown 69 kV |  | KY | Grant | Active | EKPC | 61 | 43 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/25/2021 |  |  | 9/15/2023
PJM | AG2-160 |  |  | KY | Adair | Withdrawn | EKPC | 53 | 20 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 2/25/2021 | 3/16/2021 |  | 9/15/2023
PJM | AG2-161 | Wheelabrator Frackville-Gilberton 69 kV |  | PA | Schuylkill | Active | PPL | 43 | 39.5 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/25/2021 |  |  | 12/1/2023
PJM | AG2-162 | Hanna-Tanners Creek 345 kV |  | IN | Rush | Active | AEP | 115 | 76 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/25/2021 |  |  | 12/2/2024
PJM | AG2-163 | Dequine-Eugene 345 kV |  | IN | Fountain | Active | AEP | 250 | 184 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/25/2021 |  |  | 6/1/2024
PJM | AG2-164 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 270 | 180 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/25/2021 |  |  | 12/2/2024
PJM | AG2-165 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 134 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/25/2021 |  |  | 12/2/2024
PJM | AG2-166 | Newville-Nottingham Tap 1 69 kV |  | PA | Cumberland | Active | PPL | 13.3 | 8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/25/2021 |  |  | 8/18/2023
PJM | AG2-167 | Morgan Street-Cochranton 34.5 kV |  | PA | Crawford | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/25/2021 | 12/18/2024 |  | 1/15/2023
PJM | AG2-168 | Clinch River-Copper Ridge 138 kV |  | VA | Russell | Withdrawn | AEP | 95 | 63.3333 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-169 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 70 | 46.6667 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-170 | Whitewater Valley Power Station 69 kV |  | IN | Wayne | Withdrawn | AEP | 88 | 58.6667 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-171 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/26/2021 |  |  | 7/3/2024
PJM | AG2-172 | Kittatinny 230 kV |  | NJ | Warren | Withdrawn | JCPL | 30 | 30 | Capacity | Generation Interconnection | Hydro | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 6/1/2022
PJM | AG2-173 | Twin Branch-Meridian 345 kV |  | IN | Whitley | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-174 | Jack Frost-Lake Harmony 69 kV |  | PA | Carbon | Withdrawn | PPL | 20 | 13.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/30/2024
PJM | AG2-175 | Van Wert-Delphos 69 kV |  | OH | Van Wert | Withdrawn | AEP | 65 | 49 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/15/2023
PJM | AG2-176 | Geneva 115 kV |  | PA | Crawford | Active | PENELEC | 150 | 90 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/26/2021 |  |  | 1/31/2024
PJM | AG2-177 | Limecrest-Woodruff's Gap 34.5 kV |  | NJ | Sussex | Withdrawn | JCPL | 8 | 3.36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 2/23/2022
PJM | AG2-178 | Remington 34.5 kV |  | VA | Fauquier | Withdrawn | Dominion | 14.125 | 9.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/30/2022
PJM | AG2-179 | Coburg 69 kV |  | KY | Adair | Active | EKPC | 60 | 42.4 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/26/2021 |  |  | 9/15/2023
PJM | AG2-180 | Paulsboro 69 kV |  | NJ | Gloucester | Withdrawn | AEC | 0 | 20 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 2/25/2021
PJM | AG2-181 | Airey - Golden Hill 69 kV |  | MD | Dorchester | Active | DPL | 28 | 16.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/26/2021 |  |  | 6/1/2024
PJM | AG2-182 | Doubs-Bismark 500 kV |  | VA | Frederick | Active | Dominion | 200 | 133.3333 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/26/2021 |  |  | 12/31/2022
PJM | AG2-183 |  |  | KY | Hardin | Withdrawn | EKPC | 45 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 3/19/2021 |  | 12/31/2022
PJM | AG2-184 | Spicewood-Softshell 138 kV |  | KY | Knott | Active | AEP | 210 | 126 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2021 |  |  | 6/1/2024
PJM | AG2-185 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Withdrawn | PPL | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 8/26/2024 |  | 5/1/2024
PJM | AG2-186 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Withdrawn | PPL | 5.2 | 3.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/26/2021 | 8/26/2024 |  | 6/1/2024
PJM | AG2-187 | Amherst-Riverville 138 kV |  | VA | Amherst | Withdrawn | AEP | 40 | 33.2 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/26/2021 | 12/18/2024 |  | 12/1/2024
PJM | AG2-188 | Farmville-Bucking 230 kV |  | VA | Cumberland | Active | Dominion | 140 | 89 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2021 |  |  | 3/1/2024
PJM | AG2-189 | Washington-Pequest River 34.5 kV |  | NJ | Warren | Active | JCPL | 19.8 | 8.316 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2021 |  |  | 2/23/2022
PJM | AG2-190 | Huffman 138 kV |  | VA | Carroll | Withdrawn | AEP | 77.4 | 46.44 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/27/2021 | 3/31/2021 |  | 10/31/2024
PJM | AG2-191 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 30 | 18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2021 |  |  | 11/30/2023
PJM | AG2-192 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/27/2021 |  |  | 12/15/2023
PJM | AG2-193 | Turner 34.5 kV |  | VA | Henrico | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2021 |  |  | 12/31/2023
PJM | AG2-194 | Pierce-Kyger Creek 345 kV |  | OH | Highland | Withdrawn | OVEC | 50 | 21 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/27/2021 | 12/13/2024 |  | 12/31/2024
PJM | AG2-195 | Dowling 138 kV |  | OH | Wood | Withdrawn | ATSI | 53 | 22.26 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/27/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-196 |  |  | MD | Baltimore County | Withdrawn | BGE | 9.3 | 3.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2021 | 3/25/2021 |  | 12/30/2022
PJM | AG2-197 | Nelson- Electrical Junction 345 kV |  | IL | Lee | Withdrawn | ComEd | 295.9 | 52 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 2/28/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-198 | Briery-Clover 230 kV |  | VA | Prince Edward | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2021 |  |  | 2/25/2024
PJM | AG2-199 | Birchwood-NUG 230 kV |  | VA | King George | Withdrawn | Dominion | 55 | 35.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/1/2021 | 12/18/2024 |  | 10/10/2023
PJM | AG2-200 | North Warren–Russell 34.5 kV |  | PA | Warren | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2021 |  |  | 1/15/2023
PJM | AG2-201 | Carwick Junction 25 kV |  | PA | Clarion | Withdrawn | APS | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/2/2021 | 4/26/2021 |  | 1/15/2023
PJM | AG2-202 | Reusens 12.47 kV |  | VA | City of Lynchburg | Active | AEP | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/4/2021 |  |  | 10/31/2022
PJM | AG2-203 | Perkins Park 12.47 kV |  | VA | City of Lynchburg | Withdrawn | AEP | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/4/2021 | 12/18/2024 |  | 10/31/2022
PJM | AG2-204 | Athenia 26 kV |  | NJ | Essex | Withdrawn | PSEG | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/4/2021 | 12/19/2024 |  | 10/31/2022
PJM | AG2-205 | Bonney Forge 23 kV |  | PA | Huntingdon | Withdrawn | PENELEC |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  | Wholesale Market Participation Agreement | 3/6/2021 | 6/2/2023 |  | 3/31/2024
PJM | AG2-206 | Tennessee Gas-East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 48 | 28.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2021 |  |  | 1/15/2023
PJM | AG2-207 | Brandon Shores 230 kV |  | MD | Anne Arundel | Withdrawn | BGE | 275 | 110 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/4/2021 | 12/12/2024 |  | 3/31/2023
PJM | AG2-208 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 79.2 | 44.47 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/5/2021 |  |  | 6/30/2024
PJM | AG2-209 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Withdrawn | Dominion | 0 | 20.76 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/5/2021 | 12/17/2024 |  | 6/30/2024
PJM | AG2-210 |  |  | VA | Orange | Withdrawn | Dominion | 70 | 44.26 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/5/2021 | 3/29/2021 |  | 6/30/2024
PJM | AG2-211 |  |  | VA | Orange | Withdrawn | Dominion | 0 | 20.76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/5/2021 | 3/29/2021 |  | 6/30/2024
PJM | AG2-212 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 134 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/8/2021 |  |  | 12/2/2024
PJM | AG2-213 | Gary D.P Tap - Gary D.P 115 kV |  | VA | Lunenburg | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2021 |  |  | 12/1/2025
PJM | AG2-214 | Red House D.P - Sugar Hill 115 kV |  | VA | Charlotte | Withdrawn | Dominion | 60.17 | 36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/8/2021 | 12/18/2024 |  | 12/1/2025
PJM | AG2-215 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 0 | 36.92 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2021 |  |  | 12/31/2023
PJM | AG2-216 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 0 | 25.92 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2021 |  |  | 12/31/2023
PJM | AG2-217 | Watkins Corner 34.5 kV |  | VA | Southampton | Withdrawn | Dominion | 20.9 | 8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/9/2021 | 9/17/2024 |  | 4/29/2023
PJM | AG2-218 | La Rue 69 kV |  | OH | Marion | Withdrawn | AEP | 49.5 | 32 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2021 | 12/18/2024 |  | 12/2/2024
PJM | AG2-219 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 330 | 220.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2021 |  |  | 12/2/2024
PJM | AG2-220 | East Towanda-South Troy 115 kV |  | PA | Bradford | Active | PENELEC | 31 | 19.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2021 |  |  | 9/30/2025
PJM | AG2-221 | South Troy - North Towanda 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 10 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2021 |  |  | 9/30/2024
PJM | AG2-222 | Tanners Creek-Hanna 345 kV |  | IN | Rush | Withdrawn | AEP | 83 | 55 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2021 | 12/18/2024 |  | 12/2/2024
PJM | AG2-223 | Allen Junction 345 kV |  | OH | Lucas | Withdrawn | ATSI | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/10/2021 | 12/18/2024 |  | 6/1/2023
PJM | AG2-224 | Essex 230 kV |  | NJ | Essex | Withdrawn | PSEG | 90 | 36 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/10/2021 | 5/30/2023 |  | 12/31/2022
PJM | AG2-225 | Wagner 115 kV |  | MD | Anne Arundel | Withdrawn | BGE | 115 | 46 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/10/2021 | 12/12/2024 |  | 12/31/2022
PJM | AG2-226 | Martins Creek 69 kV II |  | PA | Northampton | Withdrawn | PPL | 52 | 20.8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/11/2021 | 10/17/2024 |  | 12/31/2022
PJM | AG2-227 | Harwood 69 kV |  | PA | Luzerne | Withdrawn | PPL | 33 | 13.2 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/11/2021 | 11/28/2023 |  | 10/31/2022
PJM | AG2-228 | Pequest River-Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 11.2 | 4.704 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/12/2021 |  |  | 3/31/2022
PJM | AG2-229 | Floyd 138 kV |  | VA | Floyd | Withdrawn | AEP | 20 | 8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/12/2021 | 12/18/2024 |  | 1/1/2024
PJM | AG2-230 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/12/2021 |  |  | 12/31/2024
PJM | AG2-231 | Arrowhead 12 kV |  | PA | Monroe | Withdrawn | PPL | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/13/2021 | 9/5/2023 |  | 12/1/2023
PJM | AG2-232 | Saint Thomas - CNG 34.5 kV |  | PA | Franklin | Withdrawn | APS | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/12/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-233 | Montgomery Hydroelectric 23 kV |  | PA | Beaver | Withdrawn | DL | 20 | 17.5 | Capacity | Generation Interconnection | Hydro | Withdrawn |  |  |  | 3/15/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-234 | Neville 23 kV |  | PA | Allegheny | Withdrawn | DL | 3.2 | 1.5 | Capacity | Generation Interconnection | Hydro | Withdrawn |  |  |  | 3/15/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-235 | Lincoln-Berrywood 69 kV |  | OH | Delaware | Withdrawn | AEP | 73 | 30.66 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/15/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-236 | Potter-Harlan 69 kV |  | PA | Lawrence | Active | ATSI | 20 | 10.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/15/2021 |  |  | 10/30/2024
PJM | AG2-237 | Thelma 230kV |  | NC | Northhampton | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/16/2021 |  |  | 12/15/2025
PJM | AG2-238 | Earleys 230 kV |  | NC | Hertford | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/16/2021 |  |  | 12/15/2025
PJM | AG2-239 | Hickory-Shawboro 230 kV |  | NC | Currituck | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/16/2021 |  |  | 12/15/2025
PJM | AG2-240 | Old Church 34.5 kV |  | VA | Hanover | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/16/2021 |  |  | 12/15/2025
PJM | AG2-241 | Roadstown 69 kV |  | NJ | Cumberland | Withdrawn | AEC | 47 | 31.3333 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/16/2021 | 12/18/2024 |  | 9/15/2023
PJM | AG2-243 | Rome-Orwell 36 kV |  | OH | Ashtabula | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/16/2021 | 12/18/2024 |  | 1/15/2023
PJM | AG2-244 | Winfield-Presrite Corp 36 kV |  | OH | Ashtabula | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/16/2021 | 12/18/2024 |  | 1/15/2023
PJM | AG2-245 | Olive - Reynolds #1 345 kV |  | IN | Starke | Active | AEP | 210 | 126 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/16/2021 |  |  | 12/1/2023
PJM | AG2-246 | Whitehouse-Lone Gum 138 kV |  | VA | Bedford | Withdrawn | AEP | 0 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 1/29/2021 | 4/12/2024 |  | 6/30/2022
PJM | AG2-247 | Northwestern REC Dixonburg-Vernon 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/17/2021 |  |  | 1/15/2023
PJM | AG2-248 | East Elkhart 345 kV |  | IN | Elkhart | Active | AEP | 150 | 100 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/17/2021 |  |  | 12/2/2024
PJM | AG2-249 | Stoneboro-Perry 69 kV |  | PA | Mercer | Active | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/17/2021 |  |  | 1/15/2023
PJM | AG2-250 | Stoneboro-Perry 69 kV II |  | PA | Mercer | Active | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/17/2021 |  |  | 1/15/2023
PJM | AG2-251 | Dilworth 69 kV |  | OH | Trumbull | Withdrawn | ATSI | 29 | 17.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 12/18/2024 |  | 1/15/2023
PJM | AG2-252 | Dilworth 69 kV II |  | OH | Trumbull | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 12/18/2024 |  | 1/15/2023
PJM | AG2-253 | Dilworth 69 kV III |  | OH | Trumbull | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 12/18/2024 |  | 1/15/2023
PJM | AG2-254 | New Lisbon 12.47 kV |  | NJ | Burlington | Withdrawn | JCPL | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 12/18/2024 |  | 3/30/2022
PJM | AG2-255 | South Hampton 13 kV |  | NJ | Burlington | Withdrawn | PSEG | 4 | 1.68 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 12/19/2024 |  | 3/30/2022
PJM | AG2-256 |  |  | NJ | Somerset | Withdrawn | PSEG | 8 | 8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 4/12/2021 |  | 6/15/2022
PJM | AG2-257 |  |  | NJ | Ocean | Withdrawn | JCPL | 8 | 8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 4/13/2021 |  | 9/15/2022
PJM | AG2-258 | Carson – Rogers Road 500 kV |  | VA | Accomack | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2021 | 12/18/2024 |  | 3/1/2024
PJM | AG2-259 | Sherwood - Kidds Store 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2021 | 12/18/2024 |  | 3/4/2024
PJM | AG2-260 | Crystal Hill - Perth 115 kV |  | VA | Halifax | Active | Dominion | 149 | 89.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/18/2021 |  |  | 12/1/2025
PJM | AG2-261 | Lake View - Clubhouse 230 kV |  | VA | Greensville | Withdrawn | Dominion | 175 | 105 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/18/2021 | 12/18/2024 |  | 12/1/2025
PJM | AG2-262 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 11 | 6.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/18/2021 |  |  | 12/1/2023
PJM | AG2-263 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Withdrawn | Dayton | 40 | 31.14 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/19/2021 | 12/18/2024 |  | 12/15/2023
PJM | AG2-264 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Withdrawn | Dayton | 20 | 14.74 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/19/2021 | 12/18/2024 |  | 12/15/2023
PJM | AG2-265 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Withdrawn | Dayton | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2021 | 12/18/2024 |  | 12/15/2023
PJM | AG2-266 | National-Tangy 138 kV II |  | OH | Madison | Withdrawn | ATSI | 8 | 4.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2021 | 12/1/2023 |  | 12/31/2024
PJM | AG2-267 | Branchton 12.47 kV |  | PA | Butler | Withdrawn | APS | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/20/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-268 | Sedge Hill 230 kV |  | VA | Halifax | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/19/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-269 | Chesterfield 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/19/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-270 | Clover 230 kV |  | VA | Halifax | Active | Dominion | 150 | 105 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/19/2021 |  |  | 12/31/2025
PJM | AG2-271 | Indian River 230 kV |  | DE | Sussex | Withdrawn | DPL | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/19/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-272 | Berry Hill 138 kV |  | VA | Pittsylvania | Active | AEP | 55 | 21.35 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/19/2021 |  |  | 10/1/2024
PJM | AG2-273 | Wurno 138 kV |  | VA | Pulaski | Withdrawn | AEP | 0 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/19/2021 | 4/5/2023 |  | 12/31/2023
PJM | AG2-274 | Hebron 69 kV II |  | MD | Wicomico | Withdrawn | DPL | 0 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/19/2021 | 12/17/2024 |  | 12/31/2022
PJM | AG2-275 | Southwest 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/22/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-276 | Tyler 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/22/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-277 | Robinson 69 kV |  | OH | Fayette | Withdrawn | Dayton | 40 | 34 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/22/2021 | 12/18/2024 |  | 12/15/2023
PJM | AG2-278 | Robinson 69 kV |  | OH | Fayette | Withdrawn | Dayton | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2021 | 12/18/2024 |  | 12/15/2023
PJM | AG2-279 | Hagerstown-Conservit 34.5 kV |  | MD | Washington | Active | APS | 20 | 10 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/22/2021 |  |  | 9/30/2024
PJM | AG2-280 | Walker 34.5 kV |  | PA | Pike | Withdrawn | ME | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/23/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-281 | Church 138 kV |  | MD | Queen Anne's | Active | DPL | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/22/2021 |  |  | 5/1/2024
PJM | AG2-282 | Kuranga Power Generator |  | OH | Butler | Active | DEOK | 10 | 3.102 | Capacity | Generation Interconnection | Solar; Wind | In Progress |  |  |  | 3/22/2021 |  |  | 2/10/2022
PJM | AG2-283 | Yorktown 230 kV |  | VA | York | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/22/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-284 | Catharpin 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/22/2021 |  |  | 12/31/2023
PJM | AG2-285 | Loudoun 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/22/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-286 | Clifton 230 kV |  | VA | Fairfax | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-287 | Beaumeade 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/22/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-288 | Stonewall 138 kV |  | VA | Frederick | Active | APS | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/22/2021 |  |  | 12/31/2023
PJM | AG2-289 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 100 | 66.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/23/2021 |  |  | 12/2/2024
PJM | AG2-290 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 58 | 38.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/22/2021 |  |  | 12/2/2024
PJM | AG2-291 | Williams Central 115 kV |  | PA | Susquehanna | Withdrawn | PENELEC | 16 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2021 | 8/13/2024 |  | 12/31/2023
PJM | AG2-292 | Scotch Hollow 230 kV |  | PA | Bradford | Withdrawn | PENELEC | 16 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2021 | 8/13/2024 |  | 11/30/2023
PJM | AG2-293 | Williams Potter Tap 115 kV |  | PA | Susquehanna | Withdrawn | PENELEC | 18 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2021 | 8/13/2024 |  | 12/31/2023
PJM | AG2-294 | MacNew 115 kV |  | PA | Susquehanna | Withdrawn | PENELEC | 18 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/22/2021 | 8/13/2024 |  | 12/31/2023
PJM | AG2-295 | Price 25 kV |  | MD | Queen Anne's | Withdrawn | DPL | 15.5 | 9.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/23/2021 | 9/3/2021 |  | 10/1/2023
PJM | AG2-296 | South Berwick - Galion 345 kV |  | OH | Crawford | Withdrawn | AEP | 30 | 19.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/23/2021 | 12/18/2024 |  | 12/2/2024
PJM | AG2-297 | Cumberland 230 kV |  | NJ | Cumberland | Active | AEC | 19 | 11.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/23/2021 |  |  | 6/1/2023
PJM | AG2-298 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 40 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/23/2021 |  |  | 9/1/2024
PJM | AG2-299 | Hurley 69 kV |  | VA | Buchanan | Withdrawn | AEP | 0 | 30 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/18/2024 |  | 9/1/2024
PJM | AG2-300 | Meadow Brook 138 kV |  | VA | Frederick | Active | APS | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/23/2021 |  |  | 12/31/2023
PJM | AG2-301 | Morgantown 230 kV |  | MD | Charles | Withdrawn | PEPCO | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-302 | Dickerson 230 kV |  | MD | Montgomery | Withdrawn | PEPCO | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-303 | Birchwood 230 kV |  | VA | King George | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-304 | Liberty 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/23/2021 |  |  | 12/31/2023
PJM | AG2-305 | Bristers 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-306 | Possum Point 230 kV |  | VA | Prince William | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-307 | Roundtable 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-308 | Cumberland 138 kV |  | MD | Allegany | Withdrawn | APS | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2025
PJM | AG2-309 | Lanexa 230 kV |  | VA | New Kent | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/23/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-310 | Matt Funk 138 kV |  | VA | Roanoke | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/23/2021 |  |  | 12/31/2023
PJM | AG2-311 | Smith Mountain 138 kV |  | VA | Bedford | Active | AEP | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/23/2021 |  |  | 12/31/2023
PJM | AG2-312 | Suffolk - Sunbury 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 125 | 75 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/23/2021 | 12/18/2024 |  | 12/1/2025
PJM | AG2-313 | Burches Hill 230 kV |  | MD | Prince George's | Withdrawn | PEPCO | 0 | 35.3 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 3/23/2021 | 9/12/2023 |  | 8/31/2021
PJM | AG2-314 | Gilboa-Jones Branch 138 kV III |  | WV | Nicholas | Withdrawn | APS | 0 | 67 | Capacity | Generation Interconnection | Storage | In Progress | Withdrawn |  |  | 3/25/2021 | 11/27/2024 |  | 5/1/2024
PJM | AG2-315 | Twin Branch - Guardian 138 kV |  | IN | Elkhart | Withdrawn | AEP | 0 | 60 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/18/2024 |  | 12/1/2023
PJM | AG2-316 | Sandwich-Plano 138 KV |  | IL | Kendall | Withdrawn | ComEd | 0 | 49.4 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/18/2024 |  | 12/1/2023
PJM | AG2-317 | Barren - Summer Shade 161 kV |  | KY | Barren | Withdrawn | EKPC | 35 | 23.3 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/24/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-318 | Spotsylvania 115 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 75 | 75 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-319 | Brandon Shores 230 kV |  | MD | Anne Arundel | Withdrawn | BGE | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2025
PJM | AG2-320 | Ladysmith 230 kV |  | VA | Caroline | Active | Dominion | 150 | 105 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/24/2021 |  |  | 12/31/2023
PJM | AG2-321 | Landstown 230 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-322 | Skiffs Creek 230 kV |  | VA | James City | Withdrawn | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-323 | Shelhorn 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-324 | Buttermilk 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-325 | Pacific 230 kV |  | VA | Loudoun | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-326 | Reston 230 kV |  | VA | Fairfax | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/24/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-327 | Tennessee Gas-East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/24/2021 |  |  | 1/15/2023
PJM | AG2-328 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 134 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/25/2021 |  |  | 12/2/2024
PJM | AG2-329 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/25/2021 |  |  | 12/2/2024
PJM | AG2-330 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/25/2021 |  |  | 12/2/2024
PJM | AG2-331 | Jefferson - Greentown 765 kV |  | IN | Decatur | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/25/2021 |  |  | 12/2/2024
PJM | AG2-332 | East Elkhart – Elcona Tap 138 kV |  | IN | Elkhart | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/25/2021 |  |  | 12/2/2024
PJM | AG2-333 | Martinsville - Highland 69 kV |  | OH | Fayette | Withdrawn | Dayton | 49 | 38.05 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/25/2021 | 12/18/2024 |  | 12/15/2023
PJM | AG2-334 | Miller REC - Warrior Ridge 46 kV |  | PA | Huntingdon | Withdrawn | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/25/2021 | 12/18/2024 |  | 1/15/2023
PJM | AG2-335 | Churchtown 69 kV |  | NJ | Salem | Withdrawn | AEC | 0 | 10 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/25/2021 | 4/29/2022 |  | 5/31/2023
PJM | AG2-336 | Midway 138 kV |  | OH | Henry | Active | ATSI | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/25/2021 |  |  | 11/30/2023
PJM | AG2-337 | Midway 138 kV II |  | OH | Henry | Active | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/25/2021 |  |  | 11/30/2023
PJM | AG2-338 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 40 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/25/2021 |  |  | 12/2/2024
PJM | AG2-339 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/25/2021 |  |  | 12/2/2024
PJM | AG2-340 | South Boston 12.5 kV Line |  | VA | Halifax | Withdrawn | Dominion | 11.25 | 6.75 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/25/2021 | 4/16/2021 |  | 12/1/2024
PJM | AG2-341 | Ridge Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/25/2021 |  |  | 12/1/2024
PJM | AG2-342 | Milford - Cool Springs 230 kV II |  | DE | Sussex | Withdrawn | DPL | 440 | 124.9 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 3/26/2021 | 12/18/2024 |  | 10/31/2026
PJM | AG2-343 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/26/2021 |  |  | 12/2/2024
PJM | AG2-344 | Dequine 345 bkV |  | IN |  | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/26/2021 |  |  | 12/2/2024
PJM | AG2-345 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/26/2021 |  |  | 12/2/2024
PJM | AG2-346 | Clubhouse – Freeman 115 kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 65.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/26/2021 | 11/22/2022 |  | 10/15/2024
PJM | AG2-347 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 448.8 | 121.2 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 3/26/2021 |  |  | 8/31/2025
PJM | AG2-348 | Indian River 230 kV II |  | DE | Sussex | Active | DPL | 897.6 | 242.3 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 3/26/2021 |  |  | 8/31/2025
PJM | AG2-349 | Double Toll Gate-Mead Brook 138 kV |  | VA | Frederick | Withdrawn | APS | 47.77 | 28.662 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/27/2021 | 3/31/2021 |  | 10/31/2024
PJM | AG2-350 | Smithfield 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 250 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/26/2021 | 12/22/2022 |  | 4/1/2023
PJM | AG2-351 | Beatty-London 138 kV III |  | OH | Madison | Withdrawn | ATSI | 0 | 38.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/26/2021 | 12/18/2024 |  | 2/28/2023
PJM | AG2-352 | Laurel Lake 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/26/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-353 | Hammett 12.47 kV |  | PA | Erie | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/26/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-354 | Ragland - Grant Branch 138 kV |  | WV | Mingo | Active | AEP | 100 | 72.92 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/26/2021 |  |  | 9/30/2024
PJM | AG2-355 | North Muskingum River - Philo 138 kV |  | OH | Morgan | Active | AEP | 125 | 82.4 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/26/2021 |  |  | 6/1/2024
PJM | AG2-356 | South Troy - Canton 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/26/2021 |  |  | 1/15/2023
PJM | AG2-357 | Wilton 345 kV |  | IL | Will | Active | ComEd | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/26/2021 |  |  | 11/15/2024
PJM | AG2-358 | Midway 345 kV |  | OH | Henry | Withdrawn | ATSI | 300 | 300 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/26/2021 | 12/18/2024 |  | 11/15/2024
PJM | AG2-359 | Hillcrest 345 kV |  | OH | Brown | Withdrawn | DEOK | 125 | 125 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/26/2021 | 12/18/2024 |  | 11/15/2024
PJM | AG2-360 | Broadford 138 kV |  | VA | Smyth | Active | AEP | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/26/2021 |  |  | 11/15/2024
PJM | AG2-361 | Lanexa – Dunnsville 230 kV |  | VA | New Kent | Withdrawn | Dominion | 100 | 63.46 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/26/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-362 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Withdrawn | Dominion | 0 | 36.54 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/26/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-363 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 300 | 180 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/26/2021 |  |  | 5/31/2024
PJM | AG2-364 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/26/2021 |  |  | 5/31/2024
PJM | AG2-365 | Conneaut Lake-Werner 69 kV |  | PA | Mercer | Active | ATSI | 35 | 21 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/26/2021 |  |  | 5/31/2023
PJM | AG2-366 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/26/2021 |  |  | 12/1/2025
PJM | AG2-367 | VEPCO South Creek - Pamplin 115 kV |  | VA | Appomattox | Active | Dominion | 100.28 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/26/2021 |  |  | 12/1/2025
PJM | AG2-368 | Scottsville - CVEC Delivery 69 kV Point |  | VA | Buckingham | Withdrawn | AEP | 45 | 27 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/26/2021 | 12/18/2024 |  | 12/1/2025
PJM | AG2-369 | Vepco Heritage - Wake 500 kV |  | VA | Greensville | Active | Dominion | 86 | 51.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/26/2021 |  |  | 12/1/2025
PJM | AG2-370 | Tillman 138 kV |  | IN | Allen | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/26/2021 |  |  | 10/31/2024
PJM | AG2-371 | Newville 12 kV |  | PA | Cumberland | Withdrawn | PPL | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2021 | 8/7/2024 |  | 6/30/2023
PJM | AG2-372 | Lock 34.5 kV |  | PA | Chester | Withdrawn | PECO | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2021 | 12/18/2024 |  | 6/30/2023
PJM | AG2-373 | Nittany-Zion 46 kV |  | PA | Centre | Withdrawn | APS | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2021 | 8/7/2024 |  | 6/30/2023
PJM | AG2-374 | Warfordsburg 12 kV |  | PA | Tioga | Withdrawn | APS |  |  | Energy | Generation Interconnection | Solar | Not Required |  |  | Wholesale Market Participation Agreement | 3/30/2021 | 10/30/2023 |  | 12/31/2023
PJM | AG2-375 | Fostoria Central 345 kV |  | OH | Hancock | Active | AEP | 500 | 500 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/29/2021 |  |  | 11/15/2024
PJM | AG2-376 | Beatty 345 kV |  | OH | Franklin | Withdrawn | AEP | 400 | 400 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/29/2021 | 12/17/2024 |  | 11/15/2024
PJM | AG2-377 | West Unity – Exit 2/Holiday City Tap 69 kV |  | OH | Williams | Withdrawn | ATSI | 20 | 13.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2021 | 12/18/2024 |  | 7/31/2023
PJM | AG2-378 | North Hampton – Medway 69 kV |  | OH | Clark | Active | ATSI | 20 | 13.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/29/2021 |  |  | 7/31/2023
PJM | AG2-379 | Easton - Steele 138 kV III |  | MD | Talbot | Active | DPL | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/29/2021 |  |  | 9/15/2023
PJM | AG2-380 | Carville 138 kV IV |  | MD | Queen Anne's | Active | DPL | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/29/2021 |  |  | 9/15/2023
PJM | AG2-381 | Church - Oil City 138 kV II |  | MD | Caroline | Withdrawn | DPL | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/29/2021 | 12/18/2024 |  | 9/15/2023
PJM | AG2-382 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/29/2021 |  |  | 9/20/2024
PJM | AG2-383 | Conesville 138 kV |  | OH | Coshocton | Withdrawn | AEP | 58.9 | 29.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2021 | 9/29/2023 |  | 10/27/2023
PJM | AG2-384 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 60 | 24 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/29/2021 |  |  | 12/1/2025
PJM | AG2-385 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 54 | 36.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/29/2021 |  |  | 7/31/2023
PJM | AG2-386 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 30 | 18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/29/2021 |  |  | 4/1/2023
PJM | AG2-387 | Cargill 115 kV (SVEC) |  | VA | Rockingham | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/29/2021 | 6/29/2023 |  | 10/15/2023
PJM | AG2-388 | Pole 249 6094 12.47 kV |  | VA | Campbell | Withdrawn | AEP | 6 | 6 | Capacity | Generation Interconnection | Methane | Withdrawn |  |  |  | 3/29/2021 | 12/18/2024 |  | 9/1/2022
PJM | AG2-389 | Trexlertown 12 kV | LH Church | VA | City of Lynchburg | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 3/31/2021 | 11/22/2023 |  | 4/18/2024
PJM | AG2-390 | Upper Providence 34.5 kV |  | PA | Adams | Withdrawn | PECO | 5 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 4/8/2024 |  | 6/21/2022
PJM | AG2-391 | Route 30-Laurich 12 kV |  | OH | Montgomery | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar | Not Required |  |  | Wholesale Market Participation Agreement | 3/31/2021 | 1/2/2024 |  | 12/31/2023
PJM | AG2-392 | Meason 12 kV |  | OH | Montgomery | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar | Not Required |  |  | Wholesale Market Participation Agreement | 3/31/2021 | 8/11/2023 |  | 12/31/2023
PJM | AG2-393 | Springboro Solar 12 kV |  | VA | Buckingham | Withdrawn | PENELEC | 3 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 5/24/2021 |  | 6/21/2022
PJM | AG2-394 | Rohrsburg 12 kV | CO-Zaners Rohrsburg | VA | City of Lynchburg | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted |  | Wholesale Market Participation Agreement | 3/31/2021 | 12/12/2023 |  | 4/18/2024
PJM | AG2-395 | West Berwick 12 kV | CO-Ridge | VA | City of Lynchburg | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2021 | 12/12/2023 |  | 4/18/2024
PJM | AG2-397 | West Boyertown 13.2 kV |  | PA | Columbia | Withdrawn | ME | 2 | 0 | Energy | Generation Interconnection | Solar | Not Required |  |  | Wholesale Market Participation Agreement | 3/31/2021 | 12/28/2023 |  | 2/28/2025
PJM | AG2-398 | Fairfield 12 kV |  | PA | Lycoming | Withdrawn | PPL | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 8/7/2024 |  | 6/30/2023
PJM | AG2-399 | Harrisville Jct - All Min 25 kV |  | PA | Adams | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar | Not Required |  |  | Wholesale Market Participation Agreement | 3/31/2021 | 8/9/2023 |  | 12/31/2023
PJM | AG2-400 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 10/31/2025
PJM | AG2-401 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 0 | 44 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 12/15/2021
PJM | AG2-402 | Allen 345 kV |  | IN | Allen | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/30/2021 |  |  | 10/31/2025
PJM | AG2-403 | Meadow Brook - Mt. Storm 500 kV |  | WV | Hardy | Active | APS | 125 | 52.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 6/30/2024
PJM | AG2-404 | Meadow Brook - Mt. Storm 500 kV II |  | WV | Hardy | Active | APS | 425 | 172.5 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 6/30/2024
PJM | AG2-405 | Continental 69 kV |  | OH | Putnam | Active | AEP | 0 | 10.98 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 10/31/2022
PJM | AG2-406 | Payne 69 kV |  | OH | Paulding | Active | AEP | 0 | 10.98 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 10/31/2022
PJM | AG2-407 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-408 | Allen 345 kV |  | IN | Allen | Active | AEP | 0 | 18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 9/30/2022
PJM | AG2-410 | Watkins Corner 34.5 kV |  | VA | Southampton | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 11/18/2024 |  | 11/1/2023
PJM | AG2-411 | Statler Hill 115 kV |  | PA | Somerset | Active | PENELEC | 63 | 40.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 7/1/2024
PJM | AG2-412 | Greentown - Hummel Creek 138 kV |  | IN | Grant | Withdrawn | AEP | 100 | 78.4 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 9/12/2022 |  | 10/31/2024
PJM | AG2-413 | Brush Junction - Pleasant Gap 46 kV |  | PA | Centre | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-414 | Axton 138 kV |  | VA | Henry | Withdrawn | AEP | 350 | 210 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-415 | Gold – Tennessee Gas 115 kV |  | PA | Potter | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-416 | Edinboro South - Venango Junction 115 kV II |  | PA | Crawford | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-417 | Clinton 69 kV II |  | PA | Lycoming | Withdrawn | PPL | 100 | 88 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-418 | Blain 115 kV |  | PA | Perry | Active | PENELEC | 40 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 5/31/2023
PJM | AG2-419 | 3 Bridges Rd 34.5 kV |  | MD | Caroline | Withdrawn | DPL | 40 | 20 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 5/31/2023
PJM | AG2-420 | Eclipse #2 34.5 kV |  | PA | Venango | Active | PENELEC | 25 | 14 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 5/31/2023
PJM | AG2-421 | High Street 12.47 kV |  | NJ | Cumberland | Withdrawn | AEC | 1 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-422 | Bustleton 13 kV | Burlington Energy Storage | NJ | Atlantic | Withdrawn | PSEG | 1.2 | 0 | Energy | Generation Interconnection | Solar; Storage | Document Posted | Document Posted | Not Required | Wholesale Market Participation Agreement | 3/31/2021 | 2/22/2022 |  | 12/12/2023
PJM | AG2-423 | Cherry Run–Harmony 138 kV |  | WV | Barbour | Active | APS | 80 | 58 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 6/30/2024
PJM | AG2-424 | Bonnieville - Lebanon 138 kV |  | KY | Larue | Active | EKPC | 63.25 | 34.95 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 5/31/2023
PJM | AG2-425 | Jackson Road - Nanty Glo 46 kV |  | PA | Cambria | Withdrawn | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2023
PJM | AG2-426 | Wakefield - Waverly 115 kV |  | VA | Sussex | Active | Dominion | 59 | 47.66 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 2/29/2024
PJM | AG2-427 | Waverly 115 kV |  | VA | Sussex | Active | Dominion | 85 | 66.3 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 2/29/2024
PJM | AG2-428 | Wakefield 115 kV |  | VA | Sussex | Active | Dominion | 170 | 135.66 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 2/29/2024
PJM | AG2-429 | Burma - Armstrong 138 kV |  | PA | Clarion | Active | APS | 69 | 53.86 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 2/29/2024
PJM | AG2-430 | Sunbury-Dalmatia 69 kV II |  | PA | Northumberland | Active | PPL | 60 | 37.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 12/31/2024
PJM | AG2-431 | Sapony 34.5 kV |  | VA | Sussex | Withdrawn | Dominion | 20 | 12.54 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 11/1/2023
PJM | AG2-432 | Mount Airy - Wythe 138 kV |  | VA | Wythe | Withdrawn | AEP | 45 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-433 | Sabinsville 115 kV |  | PA | Tioga | Withdrawn | PENELEC | 50 | 21 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/10/2024 |  | 9/30/2024
PJM | AG2-434 | Rockwood 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 8/7/2024 |  | 6/30/2023
PJM | AG2-435 | Crossroads 13.2 kV II |  | PA | York | Withdrawn | ME | 4.6 | 2.76 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 8/7/2024 |  | 6/30/2023
PJM | AG2-436 | Carson - Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 400 | 400 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 12/31/2023
PJM | AG2-437 | Monarch I Interconnection 500 kV |  | VA | Greensville | Withdrawn | Dominion | 400 | 400 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/17/2024 |  | 12/31/2023
PJM | AG2-438 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 10 | 6.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 6/15/2023
PJM | AG2-439 | Oxbow 34.5 kV |  | PA | Wyoming | Active | PENELEC | 9.8 | 5.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 6/15/2023
PJM | AG2-440 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 12/31/2024
PJM | AG2-441 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 125 | 75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 12/31/2024
PJM | AG2-442 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 140 | 84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 12/31/2024
PJM | AG2-443 | Benner 12 kV |  | OH | Montgomery | Withdrawn | Dayton | 4 | 1.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/28/2022
PJM | AG2-444 | Bixby - Biers Run 345 kV |  | OH | Pickaway | Active | AEP | 346 | 207.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 12/31/2024
PJM | AG2-445 | Adkins - Atlanta 345 kV |  | OH | Pickaway | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-446 | Cedar Creek 138 kV |  | DE | New Castle | Withdrawn | DPL | 0 | 25.28 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 11/15/2022
PJM | AG2-447 | Cedar Creek 138 kV VII |  | DE | New Castle | Active | DPL | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 2/1/2024
PJM | AG2-448 | Cross School - Westvaco 138 kV |  | WV | Mineral | Active | APS | 150 | 80 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 3/24/2024
PJM | AG2-449 | Tanners Creek - Hanna 345 kV |  | IN | Rush | Active | AEP | 120 | 81.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 12/2/2024
PJM | AG2-450 | Bridgeport 230 kV |  | NJ | Gloucester | Active | AEC | 225 | 115.3 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/30/2021 |  |  | 3/1/2025
PJM | AG2-451 | Chambers 230 kV |  | NJ | Salem | Active | AEC | 240 | 123 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/30/2021 |  |  | 6/1/2024
PJM | AG2-452 | SW Lima - Shelby 345 kV |  | OH | Auglaize | Withdrawn | AEP | 300 | 52.8 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 3/31/2024
PJM | AG2-453 | Lasalle - Plano 345 kV |  | IL | Kendall | Active | ComEd | 280 | 196 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 3/31/2024
PJM | AG2-454 | Dequine - Eugene 345 kV |  | IN | Fountain | Active | AEP | 300 | 210 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 3/31/2024
PJM | AG2-455 | Dequine - Sullivan 345 kV |  | IN | Fountain | Active | AEP | 280 | 196 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 3/31/2024
PJM | AG2-456 | Pierce Brook-Lewis Run 230 kV |  | PA | McKean | Active | PENELEC | 80 | 55.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 3/31/2024
PJM | AG2-457 | Farmers Valley-Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 80 | 55.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/30/2021 |  |  | 3/31/2024
PJM | AG2-458 | Kittatinny-Newton 34.5 kV II |  | NJ | Sussex | Active | JCPL | 0 | 1.89 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/30/2021 |  |  | 5/31/2022
PJM | AG2-459 | Allenwood-Larrabee 34.5 kV II |  | NJ | Monmouth | Active | JCPL | 0 | 0.7 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/30/2021 |  |  | 3/31/2022
PJM | AG2-460 | East Flemington-Lebanon 34.5 kV II |  | NJ | Hunterdon | Active | JCPL | 0 | 2 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/30/2021 |  |  | 8/31/2022
PJM | AG2-461 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Withdrawn | Dominion | 88 | 57.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/15/2024
PJM | AG2-462 | Wythe - Glen Lyn 138 kV |  | VA | Wythe | Active | AEP | 150 | 78 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 10/31/2024
PJM | AG2-463 | Gold – Tennessee Gas 115 kV II |  | PA | Potter | Withdrawn | APS | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-464 | Feagans Mill - Stonewall 138 kV |  | WV | Jefferson | Withdrawn | APS | 80 | 24 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-465 | South Tiffin - West End Fostoria 138 kV |  | OH | Seneca | Withdrawn | AEP | 79 | 29.4 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/30/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-466 | Culloden - Wyoming 765 kV |  | WV |  | Active | AEP | 1000 | 414 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/30/2021 |  |  | 6/30/2024
PJM | AG2-467 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2025
PJM | AG2-468 | Sedge Hill – Person 230 kV |  | VA | Halifax | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 3/14/2024 |  | 12/31/2025
PJM | AG2-469 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2025
PJM | AG2-470 | Fostoria - Lemoyne 345 kV |  | OH | Wood | Withdrawn | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-471 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-472 | Jennings-Hazelton 138kV |  | WV | Preston | Withdrawn | APS | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-473 | Brody 138 kV |  | MI | Cass | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-474 | Mottville 138 kV |  | MI | St. Joseph | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-475 | Chickahominy - Surry 500 kV |  | VA | Charles City | Withdrawn | Dominion | 500 | 200 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/1/2024
PJM | AG2-476 | Hokes-Grantley 69 kV II |  | PA | York | Active | ME | 0 | 0.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 3/31/2022
PJM | AG2-477 | Hokes-Jackson 69 kV III |  | PA | York | Active | ME | 0 | 0.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/30/2022
PJM | AG2-478 | Hokes-Jackson 69 kV IV |  | PA | York | Active | ME | 0 | 0.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 3/31/2022
PJM | AG2-479 | Penns Tap-Richfield Tie 69 kV II |  | PA | Snyder | Active | PPL | 0 | 4.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2022
PJM | AG2-480 | Derry Tap-Derry Bus 69 kV II |  | PA | Montour | Withdrawn | PPL | 0 | 4.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 5/31/2022
PJM | AG2-481 | Derry Tap-Derry Bus 69 kV III |  | PA | Northumberland | Active | PPL | 0 | 4.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 7/31/2022
PJM | AG2-482 | Bowman's Mill-Scott 69 kV II |  | PA | Columbia | Withdrawn | PPL | 0 | 8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 11/15/2022
PJM | AG2-483 | Bowman's Mill Tap-Scott 69 kV III |  | PA | Columbia | Withdrawn | PPL | 0 | 2.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 11/15/2022
PJM | AG2-484 | Mifflintown Bus-Mifflintown Tap 69 kV II |  | PA | Juniata | Active | PPL | 0 | 4.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 8/31/2022
PJM | AG2-485 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Withdrawn | PPL | 0 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 11/30/2022
PJM | AG2-486 | Bloomsburg-Columbia 69 kV II |  | PA | Columbia | Withdrawn | PPL | 0 | 4.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/15/2022
PJM | AG2-487 | Madison - Tanners Creek 138 kV |  | IN | Henry | Active | AEP | 0 | 10.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 5/31/2022
PJM | AG2-488 | Southwest Lima 345 kV |  | OH | Allen | Withdrawn | AEP | 0 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-489 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Withdrawn | AEP | 0 | 3.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-490 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Withdrawn | AEP | 0 | 1.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-491 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 9/1/2024
PJM | AG2-492 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 9/1/2024
PJM | AG2-493 | Phillipsburg Bus II 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 1/3/2024 |  | 6/21/2022
PJM | AG2-494 | Keewaydin 34.5 kV |  | OH | Madison | Withdrawn | PENELEC | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 7/23/2021 |  | 6/21/2022
PJM | AG2-495 | Phillipsburg Bus I 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 2/9/2022
PJM | AG2-496 | Bloom 34.5 kV |  | OH | Madison | Withdrawn | PENELEC | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 7/23/2021 |  | 6/21/2022
PJM | AG2-497 | Tangy 138 kV |  | OH | Delaware | Withdrawn | ATSI | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-498 | Obetz 138 kV |  | OH | Franklin | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2025
PJM | AG2-499 | Bixby 345 kV |  | OH | Franklin | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2025
PJM | AG2-500 | Townsend 138 kV II |  | DE | New Castle | Withdrawn | DPL | 0 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 5/31/2024
PJM | AG2-501 | Sedge Hill - Mount Laurel 115 kV |  | VA | Halifax | Withdrawn | Dominion | 0 | 5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 5/31/2024
PJM | AG2-502 | Sedge Hill - Person 115 kV |  | VA | Halifax | Withdrawn | Dominion | 0 | 7 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 5/31/2024
PJM | AG2-503 | Adams 138 kV |  | OH | Adams | Withdrawn | AEP | 0 | 5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 5/31/2024
PJM | AG2-504 | Delano 138 kV |  | OH | Ross | Withdrawn | AEP | 0 | 5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 5/31/2024
PJM | AG2-505 | Westvaco - Mt Zion 138 kV |  | MD | Garrett | Active | APS | 15 | 15 | Capacity | Generation Interconnection | Hydro | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-506 | Carson 230 kV |  | VA | Dinwiddie | Withdrawn | Dominion | 100 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/2/2024
PJM | AG2-507 | Crewe - Victoria DP 115 kV |  | VA | Nottoway | Withdrawn | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/1/2025
PJM | AG2-508 | Dry Bread 230 kV |  | VA | Greensville | Withdrawn | Dominion | 85 | 51 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/1/2025
PJM | AG2-509 | Robinson 69 kV |  | WV |  | Active | AEP | 55 | 36.3 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-510 | Double Toll Gate 138 kV |  | VA | Clarke | Withdrawn | APS | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 6/28/2023 |  | 12/30/2024
PJM | AG2-511 | Double Toll Gate - Millville 138 kV |  | VA | Clarke | Withdrawn | APS | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 5/18/2021 |  | 12/30/2024
PJM | AG2-512 | Sulphur Creek-Loretto 69 kV |  | KY | Marion | Withdrawn | EKPC | 17.5 | 11 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 7/31/2023
PJM | AG2-513 | Hodgenville-Sulphur Creek 69 kV |  | KY | Larue | Withdrawn | EKPC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 7/31/2023
PJM | AG2-514 | Midway 345 kV II |  | OH | Henry | Withdrawn | ATSI | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/13/2024 |  | 10/31/2023
PJM | AG2-515 | Midway 345 kV III |  | OH | Lucas | Active | ATSI | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2023
PJM | AG2-516 | Pecatonica 138kV |  | IL | Winnebago | Active | ComEd | 120 | 72 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2023
PJM | AG2-517 | Cordova Energy Center 345kV |  | IL | Rock Island | Withdrawn | ComEd | 120 | 72 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 10/31/2023
PJM | AG2-518 | Tech Drive 138 kV |  | VA | Montgomery | Active | AEP | 80 | 32 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 1/1/2024
PJM | AG2-519 | Royerton - Desoto 138 kV |  | IN | Delaware | Active | AEP | 112 | 87.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 2/29/2024
PJM | AG2-520 | Ritchie 69 kV |  | MD | Prince George's | Withdrawn | PEPCO | 17 | 10.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 3/1/2024
PJM | AG2-521 | Fork Union 230 kV |  | VA | Fluvanna | Withdrawn | Dominion | 85 | 51 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/10/2024 |  | 3/1/2024
PJM | AG2-522 | Five Forks 115 kV |  | NC | Warren | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 7/30/2025
PJM | AG2-523 | Bakers Pond 115 kV |  | VA | Prince George | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 3/31/2022
PJM | AG2-524 | LaSalle Station - Mazon 138 kV |  | IL | Grundy | Active | ComEd | 110 | 110 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-525 | Bonney Forge 23 kV II |  | MI | Cass | Withdrawn | PENELEC | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 7/13/2021 |  | 6/1/2023
PJM | AG2-526 | Oak Grove – Saunders DP 230 kV |  | VA | Westmoreland | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-527 | Kewanee-Toulon 138 kV |  | IL | Stark | Active | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2025
PJM | AG2-528 | Bustleburg Tap - Fairfield DP 115 kV |  | VA | Rockbridge | Active | Dominion | 140 | 72.8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2024
PJM | AG2-529 | Harrisonburg - Endless Caverns 230 kV |  | VA | Rockingham | Withdrawn | Dominion | 151.734 | 78 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 10/31/2024
PJM | AG2-530 | Mannington Mills - Woodstown 69 kV |  | NJ | Salem | Withdrawn | AEC | 19.975 | 10 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-531 | Greystone - West Denville 34.5 kV |  | NJ | Morris | Active | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 7/31/2022
PJM | AG2-532 | Newburgh-Newburgh Tap 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 8/31/2022
PJM | AG2-533 | Newburgh-Pohatcong 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 8/31/2021
PJM | AG2-534 | Hackettstown-Pohatcong R722-7 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 8/31/2022
PJM | AG2-535 | Hackettstown-Pohatcong J738-1 34.5 kV II |  | NJ | Warren | Active | JCPL | 20 | 4 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 8/31/2022
PJM | AG2-536 | Buckeye - Ringoes 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 8/31/2022
PJM | AG2-537 | Ringoes-Copper Hill Solar 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 20 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 8/31/2022
PJM | AG2-538 | Ridgeway - Motion Control 46 kV |  | PA | Elk | Active | APS | 20 | 15.42 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 10/15/2022
PJM | AG2-539 | Mechanicsburg - Darby 138 kV |  | OH | Union | Withdrawn | Dayton | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 5/14/2025
PJM | AG2-540 | Clubhouse - Jarratt 115 kV |  | VA | Greensville | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/10/2024 |  | 6/3/2024
PJM | AG2-541 | Perth - Crystal Hill 115 kV |  | VA | Halifax | Active | Dominion | 65 | 39 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/3/2024
PJM | AG2-542 | North Shenandoah – Merck 115 kV |  | VA | Rockingham | Active | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/3/2024
PJM | AG2-543 | Suffolk - Earleys 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 70 | 42 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/3/2024
PJM | AG2-544 | Silver Lake 138 kV |  | IL | McHenry | Active | ComEd | 200 | 80 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 11/6/2024
PJM | AG2-545 | Silver Lake 345 kV |  | IL | McHenry | Active | ComEd | 400 | 160 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 11/6/2024
PJM | AG2-546 | Van Buren - Delaware 138 kV |  | IN | Grant | Withdrawn | AEP | 40 | 26.4 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2023
PJM | AG2-547 | New Liberty - Boutwell 138 kV |  | OH | Hancock | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/13/2024 |  | 9/1/2024
PJM | AG2-548 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 90 | 54 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-549 | Rineyville 69 kV |  | KY | Hardin | Withdrawn | EKPC | 40 | 26.6667 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AG2-550 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2024
PJM | AG2-551 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2024
PJM | AG2-552 | Bullitt County 161 kV |  | KY | Bullitt | Withdrawn | EKPC | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 9/1/2024
PJM | AG2-553 | Bullitt County 161 kV |  | KY | Bullitt | Active | EKPC | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 9/1/2024
PJM | AG2-554 | East End 46 kV |  | PA | Centre | Withdrawn | APS | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-555 | Clarion 12 kV |  | PA | Clarion | Withdrawn | PENELEC | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-556 | Sullivan - Dequine 345 kV |  | IN | Vigo | Withdrawn | AEP | 339.1 | 253.387 | Capacity | Generation Interconnection | Other | Withdrawn |  |  |  | 3/31/2021 | 3/2/2023 |  | 1/1/2024
PJM | AG2-557 | Spring Mills - Millheim 46 kV |  | PA | Centre | Withdrawn | APS | 19.9 | 11.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2023
PJM | AG2-558 | Shawville - Phillipsburg 34.5 kV II |  | PA | Clearfield | Withdrawn | APS | 19.9 | 8.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 1/23/2025 |  | 4/1/2023
PJM | AG2-559 | Shawville - Phillipsburg 34.5 kV III |  | PA | Clearfield | Withdrawn | APS | 19.9 | 8.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 1/23/2025 |  | 4/1/2024
PJM | AG2-560 | Phillipsburg (Karthaus) 34.5 kV |  | PA | Clearfield | Withdrawn | APS | 19.9 | 8.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 1/23/2025 |  | 4/1/2025
PJM | AG2-561 | Glory - Glen Campbell 34.5 kV |  | PA | Indiana | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/15/2023
PJM | AG2-562 | Elderberry 345 kV |  | IN | St. Joseph | Active | AEP | 71 | 35 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2022
PJM | AG2-563 | Gasburg 69 kV |  | VA | Brunswick | Withdrawn | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 9/24/2024
PJM | AG2-564 | Sulphur Springs 138 kV |  | OH | Crawford | Active | AEP | 49.99 | 32.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 7/1/2024
PJM | AG2-565 | Kidds Store - Sherwood 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 30 | 12 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 3/29/2024
PJM | AG2-566 | Briery - Clover 230 kV |  | VA | Prince Edward | Active | Dominion | 30 | 12 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 3/29/2024
PJM | AG2-567 | Stanville - Dewey 138 kV |  | KY |  | Withdrawn | AEP | 200 | 100 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 3/24/2024
PJM | AG2-568 | Stink Run – Sundial 138 kV |  | WV |  | Active | AEP | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 2/25/2024
PJM | AG2-569 | Rogers Road - Carson 500 kV |  | VA | Greensville | Withdrawn | Dominion | 50 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 3/25/2024
PJM | AG2-570 | Brunswick Collector - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 400 | 100 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 3/29/2024
PJM | AG2-571 | Brunswick Collector Bus - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 100 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 3/29/2024
PJM | AG2-572 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 10/9/2023 |  | 3/25/2024
PJM | AG2-573 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Withdrawn | AEP | 30 | 12 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 10/9/2023 |  | 3/29/2024
PJM | AG2-574 | Sowers 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 7/30/2021 |  | 12/29/2023
PJM | AG2-575 | Glidden-Waterman 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 80 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2024
PJM | AG2-576 | Varner 345 kV |  | IN | DeKalb | Withdrawn | AEP | 180 | 108 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-577 | Jay 138 kV |  | IN | Jay | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-578 | Jay 69 kV |  | IN | Jay | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-579 | Fostoria 138 kV |  | OH | Hancock | Withdrawn | AEP | 0 | 41 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/29/2023
PJM | AG2-580 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 10/1/2024
PJM | AG2-581 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/29/2021 |  |  | 10/1/2024
PJM | AG2-582 | Belmont-Flint Run 500 kV |  | WV | Doddridge | Active | APS | 2100 | 2100 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/31/2021 |  |  | 7/1/2026
PJM | AG2-583 | Bremo - Cartersville 230 kV |  | VA | Cumberland | Active | Dominion | 115 | 69 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 6/30/2026
PJM | AG2-584 | Double Toll Gate - Meadowbrook 138 kV |  | VA | Frederick | Withdrawn | APS | 90 | 46.8 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 10/31/2024
PJM | AG2-585 | Kensignton 138kV |  | IL | Kankakee | Active | ComEd | 125 | 75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/1/2024
PJM | AG2-586 | Price 69 kV |  | MD | Queen Anne's | Withdrawn | DPL | 31 | 18.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 11/11/2021 |  | 6/1/2024
PJM | AG2-587 | Graceton 230 kV |  | MD | Harford | Active | BGE | 60 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-588 | Kittatinny - Blairstown 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-589 | Ravenswood Hemlock 69 kV |  | OH | Meigs | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-590 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Active | PENELEC | 38.2 | 22.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-591 | Bluebell-Sancap Tap 69 kV |  | OH | Mahoning | Withdrawn | ATSI | 61 | 36.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-592 | West Cambridge - Vienna 69 kV |  | MD | Dorchester | Withdrawn | DPL | 28 | 16.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-593 | Benton-Scott 69 kV |  | PA | Columbia | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-594 | Benton-Scott 69 kV II |  | PA | Columbia | Active | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-595 | LaRue - North Waldo 138 kV |  | OH | Marion | Active | AEP | 65 | 39 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-596 | Renaker-Avon 138 kV |  | KY | Scott | Withdrawn | EKPC | 65 | 39 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-597 | Broadford 138 kV |  | VA | Smyth | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 10/31/2025
PJM | AG2-598 | Knob Lick-JB Galloway Tap 69 kV |  | KY | Metcalfe | Withdrawn | EKPC | 50 | 40 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 11/11/2024 |  | 11/30/2025
PJM | AG2-599 | Furnace Brook-Warren 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 8.232 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/30/2021
PJM | AG2-600 | American Can-BASF 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 8.232 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/30/2021
PJM | AG2-601 | Milton 69 kV III |  | PA | Northumberland | Withdrawn | PPL | 0 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 9/16/2022
PJM | AG2-602 | Maysville 69 kV V |  | PA | Mercer | Active | ATSI | 0 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 9/15/2022
PJM | AG2-603 | Huffman 138 kV |  | VA | Carroll | Active | AEP | 150 | 78 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2024
PJM | AG2-604 | Edgemont 138 kV |  | VA | Montgomery | Withdrawn | AEP | 94 | 63 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/17/2024 |  | 6/1/2024
PJM | AG2-605 | Skimmer - Abert 69 kV |  | VA | Amherst | Withdrawn | AEP | 37 | 24.8 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 10/29/2024 |  | 6/1/2024
PJM | AG2-606 | Sunbury-Juniata 500 kV |  | PA | Perry | Active | PPL | 89 | 53.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-607 | St. Johns - Dunbrook 34.5 kV |  | VA | King and Queen | Active | Dominion | 20 | 12.74 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 11/1/2023
PJM | AG2-608 | Unionville - Locust 115 kV |  | VA | Orange | Withdrawn | Dominion | 80 | 64 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 11/11/2024 |  | 11/15/2023
PJM | AG2-609 | Unionville - Locust Grove 115 kV |  | VA | Orange | Withdrawn | Dominion | 40 | 32 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 11/11/2024 |  | 11/15/2023
PJM | AG2-610 | Gold 12.5 kV |  | PA | Potter | Withdrawn | PENELEC | 4.998 | 3.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-611 | Hamlin 12 kV |  | PA | Wayne | Withdrawn | PPL | 4.998 | 4.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-612 | Lakeville 12 kV |  | PA | Wayne | Withdrawn | PPL | 4.998 | 4.3 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-613 | Tower Hill 34.5 kV |  | PA | Tioga | Withdrawn | PENELEC | 5 | 4.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 9/7/2021 |  | 12/31/2023
PJM | AG2-614 | Mansfield 12 kV |  | PA | Tioga | Withdrawn | PENELEC | 5 | 4.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-615 | Carlos Junction 138 kV |  | MD | Allegany | Active | APS | 100 | 62.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-616 | Churchtown - Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 50 | 32.35 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-617 | Waugh Chapel 115 kV |  | MD | Anne Arundel | Active | BGE | 55 | 33 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-618 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 110 | 69.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-619 | Carville 138 kV |  | MD | Queen Anne's | Withdrawn | DPL | 150 | 102.45 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 5/17/2021 |  | 12/31/2023
PJM | AG2-620 | Remington 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 6/21/2023 |  | 5/31/2023
PJM | AG2-621 | Hoytdale 138 kV |  | PA | Beaver | Active | ATSI | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 5/31/2023
PJM | AG2-622 | Hanover 230 kV |  | VA | Hanover | Withdrawn | Dominion | 250 | 250 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 11/22/2022 |  | 5/31/2023
PJM | AG2-623 |  |  | DE | New Castle | Withdrawn | DPL |  |  | Energy | Generation Interconnection | Other | Withdrawn |  |  |  | 3/31/2021 | 5/17/2021 |  | 9/1/2021
PJM | AG2-624 | Pequest River-Furnace Brook Tap 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.6 | 8.232 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/30/2021
PJM | AG2-625 | Pequest River-Furnace Brook Tap 34.5 kV II |  | NJ | Warren | Active | JCPL | 19.6 | 8.232 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/30/2021
PJM | AG2-626 | Pequest River-Furnace Brook Tap 34.5 kV III |  | NJ | Warren | Active | JCPL | 12.5 | 5.25 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/30/2021
PJM | AG2-627 | Woodstown-High Street 69 kV |  | NJ | Gloucester | Active | AEC | 60 | 42 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/30/2024
PJM | AG2-628 | Spring Creek - Millcreek 138 kV |  | OH | Miami | Withdrawn | Dayton | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-629 | Tasley - Oak Hall 69 kV II |  | VA | Accomack | Withdrawn | ODEC | 0 | 23.5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 6/20/2024 |  | 4/1/2025
PJM | AG2-630 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 0 | 47.43 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-631 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/1/2025
PJM | AG2-632 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 0 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-633 | Gary DP - Lunenburg 115 kV |  | VA | Lunenburg | Withdrawn | Dominion | 125 | 75 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-634 | Gary DP – Lunenburg 115 kV |  | VA | Lunenburg | Withdrawn | Dominion | 0 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-635 | Heritage 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 270 | 162 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-636 | Heritage 500 kV |  | VA | Brunswick | Withdrawn | Dominion | 0 | 108 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-637 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 4/1/2025
PJM | AG2-638 | Kingsland 69 kV |  | IN | Wells | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-639 | Chickahominy 230 kV |  | VA | Charles City | Active | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 4/1/2025
PJM | AG2-640 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Active | Dominion | 0 | 18.7 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 4/1/2025
PJM | AG2-641 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-642 | Palmer Springs 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 0 | 32 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-643 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Withdrawn | Dominion | 0 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-644 | Morrisville 230 kV |  | VA | Fauquier | Withdrawn | Dominion | 0 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 4/1/2025
PJM | AG2-645 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 0 | 8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/15/2022
PJM | AG2-646 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/10/2024
PJM | AG2-647 | Bolton - Bennsville 69 kV |  | MD | Charles | Withdrawn | SMECO | 9.2 | 4.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 3/31/2023
PJM | AG2-648 | Germantown 13.2 kV |  | PA | Adams | Withdrawn | ME | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-649 | North Hanover 13.2 kV |  | PA | York | Withdrawn | ME | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 9/7/2023 |  | 8/30/2023
PJM | AG2-650 | Newberry 13.2 kV |  | PA | York | Withdrawn | ME | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 9/7/2023 |  | 12/1/2023
PJM | AG2-651 | Central City West 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 6.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 9/7/2023 |  | 8/30/2023
PJM | AG2-652 | Siegfried-Hauto 69 kV IV |  | PA | Carbon | Withdrawn | PPL | 20 | 13.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 3/31/2024
PJM | AG2-653 | Siegfried-Hauto 69 kV V |  | PA | Carbon | Withdrawn | PPL | 20 | 8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 3/31/2024
PJM | AG2-654 | Cowansville Junction – Long Run Tap 25 kV |  | PA | Armstrong | Active | APS | 14.7 | 8.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2022
PJM | AG2-655 | Mt. Storm-Bismark 500 kV |  | WV | Grant | Active | Dominion | 500 | 210 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 6/30/2024
PJM | AG2-656 | Kanawha River - Carbondale 138 kV |  | WV | Kanawha | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2024
PJM | AG2-657 | Carbondale 138 kV |  | WV | Fayette | Active | AEP | 90 | 49.8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/30/2024
PJM | AG2-658 | Cowen 138 kV |  | WV | Webster | Active | APS | 210 | 135.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2024
PJM | AG2-659 | Five Forks - Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 7/30/2025
PJM | AG2-660 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 0 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 11/1/2023
PJM | AG2-661 | Hopewell - Surry 230 kV |  | VA | Surry | Active | Dominion | 0 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 10/31/2024
PJM | AG2-662 | Stephensburg - Central Hardin 69 kV |  | KY | Hardin | Withdrawn | EKPC | 0 | 0 | Energy | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-663 | Pidgeon - Lisbon 69 kV |  | OH | Columbiana | Withdrawn | ATSI | 40 | 31.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 8/16/2022 |  | 7/31/2025
PJM | AG2-664 | TodHunter – Trenton 138 kV |  | OH | Butler | Withdrawn | DEOK | 100 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 8/19/2024 |  | 7/31/2025
PJM | AG2-665 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 90 | 54 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2024
PJM | AG2-666 | Spurlock - Flemingsburg 138 kV |  | KY | Jackson | Withdrawn | EKPC | 90 | 54 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/31/2023
PJM | AG2-667 | Wakesfield - Poolesville 34.5 kV |  | VA | Surry | Withdrawn | Dominion | 20 | 12.53 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 11/18/2024 |  | 11/1/2023
PJM | AG2-668 | Harvey Run 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 12.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 11/1/2023
PJM | AG2-669 | Loudoun - Meadow Brook 500 kV |  | VA | Rappahannock | Withdrawn | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 6/4/2024 |  | 12/31/2025
PJM | AG2-670 | Greensburg 69 kV |  | KY | Green | Active | EKPC | 75 | 45 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/31/2021 |  |  | 12/31/2023
PJM | AG2-671 | Hope - Frenchburg 69 kV |  | KY | Montgomery | Withdrawn | EKPC | 19.9 | 11.94 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 8/8/2024 |  | 12/31/2023
PJM | AG2-672 | Conaway 138 kV |  | DE | Sussex | Withdrawn | DPL | 8 | 4.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 8/15/2022 |  | 9/4/2023
PJM | AG2-673 | Fitzell 33 kV |  | MD | Baltimore County | Withdrawn | BGE | 9.92 | 3.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 12/30/2022
PJM | AG2-674 | Quad Cities - Sterling Steel 345 kV |  | IL | Whiteside | Withdrawn | ComEd | 212.1 | 37.3 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 10/1/2023
PJM | AG2-675 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 80 | 32 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 10/1/2024
PJM | AG2-676 | Russell Co 161 kV |  | KY | Russell | Withdrawn | EKPC | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-677 | Russell Co J - Jamestown T 161 kV |  | KY | Russell | Withdrawn | EKPC | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-678 | Vicco - Beckham 138 kV |  | KY | Knott | Withdrawn | AEP | 120 | 72 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-679 | Daisy - Collier 69 kV |  | KY | Letcher | Withdrawn | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-680 | South Anna - Louisa 230 kV |  | VA | Madison | Withdrawn | Dominion | 202 | 121.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-681 | Soft Shell - Bonny Man 138 kV |  | KY | Perry | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-682 | Stinnett 161 kV |  | KY | Leslie | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-683 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Withdrawn | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-684 | Summer Shade 161 kV |  | KY | Metcalfe | Withdrawn | EKPC | 331 | 198.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-685 | Big Sandy-Inez 138 kV |  | KY | Martin | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-686 | Powell Mountain 138 kV |  | WV | Nicholas | Withdrawn | APS | 215 | 129 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-687 | Garrard 345 kV |  | KY | Garrard | Withdrawn | EKPC | 215 | 129 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-688 | Imperial-Joffre 138 kV |  | PA | Clearfield | Withdrawn | APS | 100 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-689 | Tenmile 138 kV |  | WV |  | Withdrawn | AEP | 125 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/31/2021 | 12/18/2024 |  | 6/1/2024
PJM | AG2-690 | Sullivan - Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 120 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/31/2021 |  |  | 6/1/2024
PJM | AG2-691 | New Lebanon - Ohio Hutchings 69 kV |  | OH | Montgomery | Withdrawn | Dayton | 49.5 | 39.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/31/2021 | 10/17/2024 |  | 7/31/2025
PJM | AH1-001 | Bartonsville-Meadowbrook 138 kV |  | VA | Frederick | Withdrawn | APS | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/1/2021 | 12/18/2024 |  | 12/12/2023
PJM | AH1-002 | Hector 115 kV |  | PA | Potter | Withdrawn | PENELEC | 50 | 7.35 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 4/1/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-003 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Withdrawn | ComEd | 130 | 19.11 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 4/1/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-004 | Avon - Renaker 138 kV |  | KY | Fayette | Active | EKPC | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/7/2021 |  |  | 12/1/2023
PJM | AH1-005 | East Towanda-South Troy 115 kV II |  | PA | Bradford | Active | PENELEC | 23 | 14.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/9/2021 |  |  | 9/30/2025
PJM | AH1-006 | Essex 26 kV |  | NJ | Essex | Withdrawn | PSEG | 3.7 | 2.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/9/2021 | 6/11/2021 |  | 12/1/2022
PJM | AH1-007 | Plymouth 69 kV |  | PA | Luzerne | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/9/2021 | 7/12/2021 |  | 12/1/2022
PJM | AH1-009 |  |  | IL | DeKalb | Withdrawn | ComEd | 86 | 54.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/14/2021 | 4/14/2021 |  | 12/2/2024
PJM | AH1-010 | Stony River - Buffalo Coal 66 kV |  | WV | Grant | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/19/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-011 | Fulton - Tidd 69 kV |  | WV | Brooke | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/19/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-012 | Louisa - North Anna 230 kV |  | VA | Louisa | Active | Dominion | 50 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/19/2021 |  |  | 3/29/2024
PJM | AH1-013 | Hanna - Tanners Creek 345 kV |  | IN | Shelby | Withdrawn | AEP | 0 | 300 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/20/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-014 | Sorenson 345 kV |  | IN | Huntington | Withdrawn | AEP | 111.8 | 67.08 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/19/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-015 | Academia 138 kV |  | OH | Knox | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/22/2021 | 12/18/2024 |  | 12/2/2024
PJM | AH1-016 | Central Hardin 138 kV |  | KY | Hardin | Withdrawn | EKPC | 180 | 108 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/22/2021 | 8/18/2021 |  | 12/2/2024
PJM | AH1-017 | Copperstone-North Lebanon 230 kV III |  | PA | Lebanon | Withdrawn | ME | 30 | 12.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/4/2021 | 12/18/2024 |  | 6/30/2023
PJM | AH1-018 | Cunningham - Elmont 500 kV |  | VA | Fluvanna | Withdrawn | Dominion | 149 | 89 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/13/2021 | 12/18/2024 |  | 6/30/2026
PJM | AH1-019 | Cunningham - Elmont 500 kV II |  | VA | Fluvanna | Withdrawn | Dominion | 149 | 89 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/13/2021 | 12/18/2024 |  | 6/30/2026
PJM | AH1-020 | Kidds Store – Fork Union 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 38 | 22 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/13/2021 | 12/18/2024 |  | 6/30/2026
PJM | AH1-021 | North Temple 781-1 13.2 kV |  | PA | Berks | Withdrawn | ME | 3 | 2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/13/2021 | 8/9/2024 |  | 11/30/2022
PJM | AH1-022 | Allen 13.2 kV |  | PA | Cumberland | Withdrawn | ME | 3 | 2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/12/2021 | 4/14/2023 |  | 11/30/2022
PJM | AH1-023 | Corning Glass-Bush Town Junction 34.5 kV |  | PA | Franklin | Withdrawn | APS | 5 | 3.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/12/2021 | 8/9/2024 |  | 11/30/2022
PJM | AH1-024 | Lickdale 626-2 13.2 kV |  | PA | Lebanon | Withdrawn | ME | 2 | 1.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/12/2021 | 8/9/2024 |  | 11/30/2022
PJM | AH1-025 | Myerstown 751-2 13.2 kV |  | PA | Lebanon | Withdrawn | ME | 4.5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/12/2021 | 8/9/2024 |  | 11/30/2022
PJM | AH1-026 | Newberry 576-4 13.2 kV |  | PA | York | Withdrawn | ME | 4.5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/12/2021 | 8/9/2024 |  | 11/30/2022
PJM | AH1-027 | Cartanza 230 kV |  | DE | Kent | Active | DPL | 25 | 15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 5/20/2021 |  |  | 6/1/2023
PJM | AH1-028 | Freeman1 12.47 kV |  | VA | Brunswick | Withdrawn | Dominion | 8.75 | 3.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/26/2021 | 9/13/2021 |  | 12/20/2023
PJM | AH1-029 | WV-PJM1 12 kV |  | IL | Cook | Withdrawn | AEP |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/3/2021 | 8/3/2021 |  | 5/31/2021
PJM | AH1-030 | WV PJM2 12 kV |  | IL | Cook | Withdrawn | AEP |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/3/2021 | 8/3/2021 |  | 6/30/2022
PJM | AH1-031 | National-Tangy 138 kV III |  | OH | Madison | Withdrawn | ATSI | 20 | 8.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/8/2021 | 12/1/2023 |  | 12/31/2024
PJM | AH1-032 | West Millersport 138 kV |  | OH | Fairfield | Withdrawn | AEP | 18 | 10.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/14/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-033 | Sligo 34.5 kV |  | NC | Currituck | Active | Dominion | 19.5 | 13 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/14/2021 |  |  | 8/15/2024
PJM | AH1-034 | Patton Road Junction - Summer Shade 69 kV |  | KY | Barren | Active | EKPC | 100 | 70 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/14/2021 |  |  | 11/15/2025
PJM | AH1-035 | Plymouth 34.5 kV |  | NC | Washington | Active | Dominion | 20 | 13.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/14/2021 |  |  | 9/15/2024
PJM | AH1-036 | Centerburg 138 kV |  | OH | Licking | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 6/15/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-037 | Chippewa D557 8.320 kV |  |  |  | Withdrawn | ATSI | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/16/2021 | 12/18/2024 |  | 11/1/2023
PJM | AH1-038 | Kramer |  |  |  | Withdrawn | PENELEC | 3.825 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/16/2021 | 1/4/2022 |  | 11/1/2023
PJM | AH1-039 | Mt. Hermon 23 kV |  | MD | Wicomico | Withdrawn | DPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/19/2021 | 1/25/2022 |  | 10/1/2023
PJM | AH1-040 | Mackeys - Creswell 115 kV |  | NC | Washington | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/23/2021 |  |  | 7/1/2025
PJM | AH1-041 | Pennville 138 kV |  | IN | Jay | Active | AEP | 125 | 75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/23/2021 |  |  | 7/1/2025
PJM | AH1-042 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 154 | 99.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/25/2021 |  |  | 9/1/2024
PJM | AH1-043 | Sand Hills - Brunswick 69 kV |  | NJ | Middlesex | Withdrawn | PSEG | 90 | 90 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 6/28/2021 | 12/19/2024 |  | 5/15/2024
PJM | AH1-044 | Nelson - Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/30/2021 |  |  | 12/31/2024
PJM | AH1-045 | Zion Energy Center 345 kV |  | IL | Lake | Active | ComEd | 23 | 13.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/1/2021 |  |  | 6/1/2023
PJM | AH1-046 | Peach Bottom 500 kV |  | PA | York | Active | PECO | 25 | 15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/1/2021 |  |  | 6/1/2023
PJM | AH1-047 | Marengo - Belvidere 138 kV |  | IL | Boone | Active | ComEd | 61.6 | 37 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/6/2021 |  |  | 9/13/2022
PJM | AH1-048 | Riverton 138 |  | VA | Warren | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/7/2021 | 12/18/2024 |  | 5/1/2024
PJM | AH1-049 | Erie East – Union City Ckt 00234-31 34.5 kV |  | PA | Adams | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/7/2021 | 12/18/2024 |  | 7/1/2023
PJM | AH1-050 | Eclipse-Piney 115 kV |  | PA | Venango | Active | PENELEC | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/7/2021 |  |  | 7/1/2023
PJM | AH1-051 | Eclipse-Piney 115 kV II |  | PA | Venango | Active | PENELEC | 30 | 18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/7/2021 |  |  | 7/1/2023
PJM | AH1-052 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/7/2021 | 12/18/2024 |  | 4/1/2025
PJM | AH1-053 | Luthersburg - Curwensville 12.47 kV |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/8/2021 | 6/5/2024 |  | 6/30/2023
PJM | AH1-054 | Upton-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 8.25 | 3.465 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/9/2021 |  |  | 7/8/2022
PJM | AH1-055 | Kyger Creek - Don Marquis 345 kV |  | OH | Jackson | Active | OVEC | 220 | 148.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/14/2021 |  |  | 11/15/2026
PJM | AH1-056 | Red House D.P. 115kV |  | VA | Campbell | Active | Dominion | 100 | 68.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/14/2021 |  |  | 11/15/2026
PJM | AH1-057 | Edgewood 12.47 kV |  | MD | Wicomico | Active | DPL | 7.2 | 3.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/15/2021 |  |  | 1/31/2023
PJM | AH1-058 | Galion 138 kV IV |  | OH | Morrow | Withdrawn | ATSI | 40 | 24 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/16/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-059 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/16/2021 |  |  | 12/31/2024
PJM | AH1-060 | Cardington-Liberty 69 kV III |  | OH | Morrow | Active | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/20/2021 |  |  | 12/31/2024
PJM | AH1-061 | Bernville 13.2kV |  | PA | Berks | Withdrawn | ME | 5 | 2.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/21/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-062 | London-Tangy 69 kV II |  | OH | Madison | Withdrawn | ATSI | 20 | 13.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/22/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-063 | Spring Creek – South Abingdon 138 kV |  | VA | Washington | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/26/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-064 | Hopewell 34.5kV |  | VA | City of Hopewell | Withdrawn | Dominion | 20 | 8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/27/2021 | 12/18/2024 |  | 5/1/2023
PJM | AH1-065 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 20 | 8 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/27/2021 |  |  | 5/1/2023
PJM | AH1-066 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 10 | 4 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/27/2021 |  |  | 5/1/2023
PJM | AH1-067 | Minotola 12.47 kV |  | NJ | Gloucester | Withdrawn | AEC | 8.5 | 4.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/27/2021 | 12/18/2024 |  | 12/10/2023
PJM | AH1-068 | Williamstown 12.47 kV |  | NJ | Gloucester | Withdrawn | AEC | 12 | 5.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/28/2021 | 12/18/2024 |  | 12/10/2023
PJM | AH1-069 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 17 | 10.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/28/2021 |  |  | 11/30/2023
PJM | AH1-070 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 17 | 10.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/28/2021 |  |  | 11/30/2023
PJM | AH1-071 | Midlothian 34.5 kV |  | VA | Powhatan | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/29/2021 |  |  | 7/1/2023
PJM | AH1-072 | Lick Fork 69 kV |  | VA | Dickenson | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/29/2021 |  |  | 3/31/2024
PJM | AH1-073 | Lick Fork 69 kV |  | VA | Dickenson | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/29/2021 |  |  | 3/31/2024
PJM | AH1-074 | Fitchville-New London 69 kV |  | OH | Huron | Withdrawn | ATSI | 20 | 13.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/29/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-075 | North Waldo - Wild Creek 138 kV |  | OH | Marion | Active | AEP | 8 | 24.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/29/2021 |  |  | 12/31/2022
PJM | AH1-076 | Loyalhanna - Reed Junction 25 kV |  | PA | Westmoreland | Active | APS | 18 | 9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/29/2021 |  |  | 12/31/2023
PJM | AH1-077 | TBD 34.5 kV |  | NJ | Burlington | Withdrawn | AEC | 3 | 1.24 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/30/2021 | 12/18/2024 |  | 8/9/2021
PJM | AH1-078 | Paulsboro 69 kV II |  | NJ | Gloucester | Withdrawn | AEC | 0 | 58 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 7/30/2021 | 12/18/2024 |  | 9/1/2022
PJM | AH1-079 | Harmony Village 34.5kV |  | VA | Middlesex | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/30/2021 | 12/18/2024 |  | 12/20/2024
PJM | AH1-080 | Virginia Beach - Pendleton 115 kV |  | VA | City of Virginia Beach | Withdrawn | Dominion | 40 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/30/2021 | 12/18/2024 |  | 1/1/2025
PJM | AH1-081 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 60 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/30/2021 |  |  | 12/20/2024
PJM | AH1-082 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 44 | 26.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/30/2021 |  |  | 12/20/2024
PJM | AH1-083 | Summer Shade - Green County 161 kV |  | KY | Metcalfe | Active | EKPC | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/30/2021 |  |  | 12/20/2024
PJM | AH1-086 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 90 | 90 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/30/2021 |  |  | 7/31/2023
PJM | AH1-087 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/30/2021 |  |  | 7/31/2023
PJM | AH1-088 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/30/2021 |  |  | 7/31/2023
PJM | AH1-089 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/30/2021 |  |  | 7/31/2023
PJM | AH1-090 | Surry - Hopewell 230 kV |  | VA | Surry | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 7/30/2021 | 12/18/2024 |  | 11/15/2024
PJM | AH1-091 | Ahoskie 34.5kV |  | NC | Hertford | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 7/30/2021 |  |  | 11/15/2024
PJM | AH1-092 | SedgeHill - Person 230 kV |  | VA | Halifax | Active | Dominion | 90 | 54 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/30/2021 |  |  | 6/1/2025
PJM | AH1-093 | SedgeHill - Person 230 kV |  | VA | Halifax | Withdrawn | Dominion | 60 | 39 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 7/30/2021 | 12/17/2024 |  | 6/1/2025
PJM | AH1-094 | Wells - Shinrock 69 kV I |  | OH | Huron | Active | ATSI | 49.9 | 32.435 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/30/2021 |  |  | 6/1/2025
PJM | AH1-095 | Wells - Shinrock 69 kV II |  | OH | Huron | Withdrawn | ATSI | 20 | 13 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 7/30/2021 | 12/17/2024 |  | 6/1/2025
PJM | AH1-096 | Wells - Shinrock 69 kv III |  | OH | Huron | Withdrawn | ATSI | 10 | 6.5 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 7/30/2021 | 12/17/2024 |  | 6/1/2025
PJM | AH1-097 | Jubal Early - Pipers Gap 138 kV |  | VA | Carroll | Withdrawn | AEP | 20 | 12.9 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 7/30/2021 | 12/18/2024 |  | 6/1/2025
PJM | AH1-098 | Jubal Early - Pipers Gap 138 kV |  | VA | Carroll | Active | AEP | 40 | 26 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/30/2021 |  |  | 6/1/2025
PJM | AH1-099 | Glady Run–Xenia 69 kV |  | OH | Greene | Withdrawn | Dayton | 0 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/30/2021 | 11/1/2024 |  | 6/1/2025
PJM | AH1-100 | Effort Mountain-Gilbert 138 kV II |  | PA | Monroe | Withdrawn | PPL | 0 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 7/30/2021 | 8/26/2024 |  | 6/1/2025
PJM | AH1-101 | River EC 138 kV |  | IL | Cook | Withdrawn | ComEd | 57.78 | 23.12 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 7/30/2021 | 8/26/2021 |  | 5/31/2024
PJM | AH1-102 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 100 | 63.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/30/2021 |  |  | 12/31/2024
PJM | AH1-103 | Pinewood - St. Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/2/2021 | 1/10/2024 |  | 6/1/2025
PJM | AH1-104 | Hepburna 12.47 kV Grampian ckt |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/2/2021 | 6/5/2024 |  | 7/22/2023
PJM | AH1-105 | TBD 23 kV |  | DE | Kent | Withdrawn | DPL | 4 | 2.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/3/2021 | 11/8/2021 |  | 4/1/2022
PJM | AH1-106 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 15.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/4/2021 |  |  | 10/31/2023
PJM | AH1-107 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 15.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/4/2021 |  |  | 10/31/2023
PJM | AH1-108 | Spruance NUG 230 kV |  | VA | City of Richmond | Active | Dominion | 0 | 9 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 8/4/2021 |  |  | 6/1/2022
PJM | AH1-109 | Krendale - Unionville 12.47 kV |  | OH | Adams | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar | Not Required |  |  | Wholesale Market Participation Agreement | 8/3/2021 | 12/13/2023 |  | 9/20/2024
PJM | AH1-110 | Newville 12 kV II |  | PA | Cumberland | Withdrawn | PPL | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/6/2021 | 8/7/2024 |  | 7/31/2023
PJM | AH1-111 | Walker 12 kV |  | PA | Juniata | Withdrawn | PPL | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/6/2021 | 8/7/2024 |  | 7/31/2023
PJM | AH1-112 | New Meredith 23 kV |  | DE | Kent | Withdrawn | DPL | 4 | 2.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/6/2021 | 11/8/2021 |  | 4/1/2022
PJM | AH1-113 | North Pole - Russelville 34.5 kV |  | OH | Brown | Withdrawn | DEOK | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/9/2021 | 12/18/2024 |  | 7/31/2023
PJM | AH1-114 | North Pole - Russelville 34.5 kV |  | OH | Brown | Withdrawn | DEOK | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/9/2021 | 12/18/2024 |  | 7/31/2023
PJM | AH1-115 |  |  | DE | Kent | Withdrawn | DPL | 4 | 2.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/13/2021 | 9/2/2021 |  | 4/1/2022
PJM | AH1-118 | Windsor 25 kV |  | WV | Brooke | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/13/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-119 | Bismark-Doubs 500 kV |  | VA | Frederick | Withdrawn | Dominion | 100 | 66.6667 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 8/13/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-120 | Felton 23kV |  | DE | Kent | Withdrawn | DPL | 4 | 2.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/17/2021 | 11/8/2021 |  | 4/1/2022
PJM | AH1-121 |  |  | NJ | Atlantic | Withdrawn | AEC |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/18/2021 | 9/9/2021 |  | 8/12/2022
PJM | AH1-122 | Dowling 138 kV II |  | OH | Wood | Withdrawn | ATSI | 22 | 9.24 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/19/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-123 | Locust Grove D.P. 34.5kV |  | VA | Orange | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/24/2021 | 11/17/2021 |  | 2/28/2023
PJM | AH1-124 | Vint Hill 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 8/23/2021 |  |  | 12/23/2022
PJM | AH1-125 | Sycoline 34.5kV |  | VA | Loudoun | Active | Dominion | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 8/23/2021 |  |  | 12/23/2022
PJM | AH1-126 | Bowman 12.5kV |  | VA | Prince William | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/23/2021 | 7/14/2022 |  | 12/23/2022
PJM | AH1-127 | Railroad 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 8/23/2021 |  |  | 12/23/2022
PJM | AH1-128 | Railroad 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 8/23/2021 |  |  | 12/23/2022
PJM | AH1-129 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/24/2021 | 12/18/2024 |  | 2/28/2023
PJM | AH1-130 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/24/2021 | 12/18/2024 |  | 2/28/2023
PJM | AH1-131 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Withdrawn | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/23/2021 | 12/18/2024 |  | 2/28/2023
PJM | AH1-132 | Double Toll Gate - Strasburg 34.5 kV |  | VA | Frederick | Withdrawn | APS | 14.4 | 14.4 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 8/23/2021 | 12/17/2024 |  | 1/1/2022
PJM | AH1-133 | Saltville - Tazewell 138 kV |  | VA | Tazewell | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/23/2021 |  |  | 12/31/2024
PJM | AH1-134 | Northern Neck 230 kV |  | VA | Richmond | Withdrawn | Dominion | 0 | 12 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/25/2021 | 10/5/2021 |  | 1/1/2023
PJM | AH1-136 | Falcon -Middle Creek 46 kV |  | KY |  | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/25/2021 |  |  | 12/31/2024
PJM | AH1-137 |  |  | PA | Adams | Withdrawn | PPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/26/2021 | 8/26/2021 |  | 12/31/2022
PJM | AH1-138 | Penniman 34.5 kV |  | VA | City of Williamsburg | Active | Dominion | 20 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/30/2021 |  |  | 7/15/2022
PJM | AH1-139 | Cooper 34.5kV |  | PA | York | Withdrawn | PECO | 3 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/27/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-140 | Vasco 138 kV |  | PA | Westmoreland | Active | APS | 150 | 115 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/30/2021 |  |  | 12/31/2023
PJM | AH1-141 | Darbytown 230 kV |  | VA | Henrico | Withdrawn | Dominion | 5 | 5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/26/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-142 | Darbytown 230 kV II |  | VA | Henrico | Withdrawn | Dominion | 4 | 4 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/27/2021 |  |  | 12/31/2024
PJM | AH1-143 | Darbytown 230 kV III |  | VA | Henrico | Withdrawn | Dominion | 2 | 2 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/26/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-144 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 120 | 50.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/26/2021 |  |  | 12/31/2024
PJM | AH1-145 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 80 | 80 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/26/2021 |  |  | 12/31/2024
PJM | AH1-146 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/26/2021 |  |  | 12/31/2025
PJM | AH1-147 | Byron-Wayne 345 kV |  | IL | Ogle | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/27/2021 |  |  | 12/31/2025
PJM | AH1-148 | Byron-Wayne 345 kV |  | IL | Ogle | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/26/2021 |  |  | 12/31/2025
PJM | AH1-149 | Moselem-Saint Peters Tap 69 kV |  | PA | Berks | Withdrawn | ME | 8.375 | 4.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/28/2021 | 12/18/2024 |  | 9/19/2022
PJM | AH1-150 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/28/2021 |  |  | 12/31/2025
PJM | AH1-151 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/27/2021 |  |  | 12/31/2025
PJM | AH1-152 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 0 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/27/2021 |  |  | 12/31/2025
PJM | AH1-153 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/27/2021 |  |  | 12/31/2025
PJM | AH1-154 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 0 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/27/2021 |  |  | 12/31/2025
PJM | AH1-154A | Mount Rock12 kV II |  | PA | Snyder | Withdrawn | PPL | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/27/2021 | 2/14/2022 |  | 12/31/2022
PJM | AH1-154B | Hughesville 12 kV |  | PA | Lycoming | Withdrawn | PPL | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/27/2021 | 2/14/2022 |  | 12/31/2022
PJM | AH1-156 | Cane Ridge 69 kV |  | KY | Bourbon | Withdrawn | EKPC | 40 | 25.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/30/2021 | 12/18/2024 |  | 6/30/2026
PJM | AH1-157 | Penniman - Waller 230 kV |  | VA | York | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/31/2021 |  |  | 1/1/2025
PJM | AH1-158 | Eclipse-Piney 115 kV III |  | PA | Venango | Active | PENELEC | 0 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/1/2021 |  |  | 8/31/2023
PJM | AH1-159 | Conneaut-Conneaut Tap 69 kV |  | PA | Crawford | Active | ATSI | 20 | 13.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/30/2021 |  |  | 11/1/2023
PJM | AH1-160 | Tower Hill 34.5 kV |  | PA | Tioga | Active | PENELEC | 20 | 13.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/31/2021 |  |  | 11/1/2023
PJM | AH1-161 | Canal 69 kV |  | PA | Mercer | Withdrawn | ATSI | 20 | 13.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/30/2021 | 12/18/2024 |  | 11/1/2023
PJM | AH1-162 | Curryville-RKB-Yellow Creek 23 kV |  | PA | Bedford | Active | PENELEC | 16 | 11 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/31/2021 |  |  | 11/1/2023
PJM | AH1-163 | Millersburg 69 kV |  | KY |  | Active | EKPC | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/1/2021 |  |  | 7/31/2025
PJM | AH1-164 | Oak Level - Tank Hill 138 kV |  | VA | Franklin | Active | AEP | 65 | 39 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/31/2021 |  |  | 12/20/2024
PJM | AH1-165 | Will County 138 kV |  | IL | Will | Active | ComEd | 80 | 10 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/31/2021 |  |  | 6/1/2025
PJM | AH1-166 | Carson – Suffolk 500 kV |  | VA | Sussex | Withdrawn | Dominion | 0 | 320 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/1/2021 | 10/12/2021 |  | 12/1/2024
PJM | AH1-167 | Pinewood - St Johns 115 kV |  | VA | Caroline | Withdrawn | Dominion | 80 | 51.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/27/2021 | 12/18/2024 |  | 6/1/2026
PJM | AH1-168 | Pinewood - St Johns 115 kV II |  | VA | Caroline | Withdrawn | Dominion | 40 | 25.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/27/2021 | 12/18/2024 |  | 6/1/2026
PJM | AH1-169 | Greenbush 69kV |  | VA | Accomack | Withdrawn | ODEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/27/2021 | 12/18/2024 |  | 12/20/2024
PJM | AH1-170 | Columbia DP 115kV |  | VA | Goochland | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/27/2021 |  |  | 12/20/2024
PJM | AH1-171 | Columbia DP 115kV |  | VA | Goochland | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/27/2021 | 12/18/2024 |  | 12/20/2024
PJM | AH1-172 | Wolf Glade 34.5 kV |  | VA | Carroll | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-173 | Buckhorn 34.5 kV |  | VA | Tazewell | Withdrawn | AEP | 16.65 | 9.99 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 8/18/2023 |  | 12/31/2022
PJM | AH1-174 | Westlake 34.5 kV |  | VA | Franklin | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-175 | Sheffield 34.5 kV |  | VA | Henry | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-176 | Ridgeway 34.5 kV |  | VA | Henry | Withdrawn | AEP | 18.8 | 11.28 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-177 | Willis Gap 34.5 kV |  | VA | Carroll | Withdrawn | AEP | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/1/2021 | 3/2/2023 |  | 12/31/2022
PJM | AH1-178 | Remington - Morrisville 34.5 kV |  | VA | Fauquier | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-179 | Edinburg - Woodstock DP 34.5 kV |  | VA | Shenandoah | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/31/2021 |  |  | 12/31/2022
PJM | AH1-180 | Westlake 34.5 kV |  | VA | Franklin | Withdrawn | AEP | 9 | 5.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-181 | Stuart 34.5 |  | VA | Patrick | Withdrawn | AEP | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 9/5/2024 |  | 12/31/2022
PJM | AH1-182 | Peak Creek 34.5 |  | VA | Pulaski | Withdrawn | AEP | 11.45 | 6.87 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-183 | Remington - Elm 34.5 kV |  | VA | Fauquier | Withdrawn | Dominion | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/1/2021 | 8/15/2023 |  | 12/31/2022
PJM | AH1-184 | Powhatan - Powhatan DP 24.94 kV |  | VA | Powhatan | Withdrawn | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 8/31/2021 | 12/18/2024 |  | 12/31/2022
PJM | AH1-185 | Benn's Church - Smithfield 34.5 kV |  | VA | Isle of Wight | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/31/2021 |  |  | 12/31/2022
PJM | AH1-186 | Maysville-Sharon 69 kV II |  | PA | Mercer | Withdrawn | ATSI | 0 | 6.4 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/1/2021 | 12/18/2024 |  | 10/18/2024
PJM | AH1-187 | Andover (Maysville) 69 kV III |  | PA | Crawford | Withdrawn | ATSI | 0 | 5.6 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/31/2021 | 10/8/2021 |  | 10/18/2024
PJM | AH1-188 | Pigeon Creek 138 kV |  | WV | Mingo | Active | AEP | 185 | 129 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 8/31/2021 |  |  | 6/1/2025
PJM | AH1-189 | Hopkins 138 kV |  | WV |  | Active | AEP | 185 | 129 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 8/31/2021 |  |  | 6/1/2025
PJM | AH1-190 | Waukegan 138 kV |  | IL | Lake | Withdrawn | ComEd | 80 | 10 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/1/2021 | 12/18/2024 |  | 6/1/2025
PJM | AH1-191 | Powerton 138 kV |  | IL | Tazewell | Withdrawn | ComEd | 20.9 | 12.065 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/1/2021 | 12/18/2024 |  | 6/1/2025
PJM | AH1-192 | Sunbury-Columbia 69kV |  | PA | Northumberland | Withdrawn | PPL | 5 | 3.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/1/2021 | 3/14/2022 |  | 9/1/2023
PJM | AH1-193 | Sunbury-Danville 69 kV |  | PA | Northumberland | Withdrawn | PPL | 5 | 2.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/1/2021 | 3/14/2022 |  | 9/1/2023
PJM | AH1-194 | Warfordsburg – Hancock 34.5 kV |  | PA | Fulton | Withdrawn | APS | 5 | 2.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/1/2021 | 3/14/2022 |  | 9/1/2023
PJM | AH1-195 | Mechanicsburg - Darby 138 kV |  | OH | Champaign | Withdrawn | Dayton | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/2/2021 | 8/8/2022 |  | 9/1/2024
PJM | AH1-196 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/2/2021 |  |  | 12/15/2026
PJM | AH1-197 | Occoquan 230kV |  | VA | Fairfax | Active | Dominion | 0 | 7.1 | Capacity | Generation Interconnection | Methane | In Progress |  |  |  | 9/1/2021 |  |  | 8/20/2021
PJM | AH1-198 | Marysville - Sorenson 765 kV |  | OH | Logan | Withdrawn | AEP | 55 | 33 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/1/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-199 | Loretto 345 kV |  | IL | Livingston | Withdrawn | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/3/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-200 | Compressor 605 69kV |  | PA | Wyoming | Withdrawn | PPL | 12 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/4/2021 | 10/6/2023 |  | 12/31/2023
PJM | AH1-201 | New Baltimore 115 kV (Mountain Ridge Solar) |  | PA | Somerset | Active | PENELEC | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/3/2021 |  |  | 8/31/2023
PJM | AH1-202 | New Baltimore 115 kV II (Mountain Ridge Solar) |  | PA | Somerset | Withdrawn | PENELEC | 40 | 24 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/4/2021 | 12/18/2024 |  | 8/31/2023
PJM | AH1-203 | Allegheny-Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 70 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/3/2021 |  |  | 8/31/2023
PJM | AH1-204 | Allegheny-Somerset 115 kV II |  | PA | Somerset | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/4/2021 | 12/18/2024 |  | 8/31/2023
PJM | AH1-205 | New Baltimore 115 kV III |  | PA | Somerset | Active | PENELEC | 0 | 48 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/3/2021 |  |  | 8/31/2023
PJM | AH1-206 | Bethelboro 138 kV |  | PA | Fayette | Active | APS | 60 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/8/2021 |  |  | 12/31/2024
PJM | AH1-207 | Bethelboro 25 kV-1 |  | PA | Fayette | Withdrawn | APS | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-208 | Bethelboro 25 kV-2 |  | PA | Fayette | Withdrawn | APS | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-209 | Bethelboro 25 kV-3 |  | PA | Fayette | Withdrawn | APS | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-210 | Bethelboro 25 kV-4 |  | PA | Fayette | Withdrawn | APS | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-211 | Bethelboro 25 kV-5 |  | PA | Fayette | Withdrawn | APS | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-212 | Bethlehem - Lilly 46 kV |  | PA | Cambria | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/7/2021 |  |  | 12/31/2022
PJM | AH1-213 | James River 115 kV |  | VA | Fluvanna | Withdrawn | Dominion | 52.5 | 31.5 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/9/2021 | 4/1/2024 |  | 2/1/2025
PJM | AH1-214 | Red House DP 115 kV |  | VA | Campbell | Withdrawn | Dominion | 44.1 | 26.4 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/9/2021 | 6/21/2024 |  | 2/1/2025
PJM | AH1-215 | Central VA-Twitty 115 kV |  | VA | Charlotte | Active | Dominion | 31.5 | 18.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2021 |  |  | 2/1/2025
PJM | AH1-216 | Smithfield-Surry 230 kV |  | VA | Isle of Wight | Active | Dominion | 99 | 79.2 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/8/2021 |  |  | 2/1/2025
PJM | AH1-217 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Active | Dominion | 57 | 34.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 2/1/2025
PJM | AH1-218 | Garner DP 115 kV |  | VA | Northumberland | Withdrawn | Dominion | 30 | 18 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 10/18/2023 |  | 2/1/2025
PJM | AH1-219 | Blue Jacket 138 kV |  | OH | Logan | Withdrawn | Dayton | 39.9 | 23.9 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/8/2021 | 4/8/2024 |  | 2/1/2025
PJM | AH1-220 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 0 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/8/2021 |  |  | 12/1/2023
PJM | AH1-221 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 0 | 45 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/8/2021 |  |  | 12/1/2023
PJM | AH1-222 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 0 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/8/2021 |  |  | 12/1/2023
PJM | AH1-223 | Poland Rd-Runway DP 230 kV |  | VA | Loudoun | Active | Dominion | 0 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/8/2021 |  |  | 12/1/2023
PJM | AH1-224 | Willard 69 kV |  | OH | Huron | Withdrawn | AEP | 30 | 18 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 11/18/2022 |  | 8/31/2023
PJM | AH1-225 | Wood Solar 69 kV |  | OH | Wayne | Withdrawn | AEP | 30 | 18 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 8/31/2023
PJM | AH1-226 | Clubhouse - Sapony 230 kV |  | VA | City of Emporia | Active | Dominion | 115 | 69 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/8/2021 |  |  | 12/1/2025
PJM | AH1-227 | Flemming - Fremont 69 kV |  | VA | Wise | Active | AEP | 51.8 | 30.78 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/8/2021 |  |  | 12/1/2025
PJM | AH1-228 | Marsh Run 230kV |  | VA | Fauquier | Withdrawn | Dominion | 18 | 18 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 10/1/2024
PJM | AH1-229 | Louisa 230kV |  | VA | Louisa | Withdrawn | Dominion | 6 | 6 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 4/1/2025
PJM | AH1-230 | Sabinsville 34.5kV |  | PA | Tioga | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 6/1/2025
PJM | AH1-231 | Lanexa 230kV |  | VA | New Kent | Withdrawn | Dominion | 28.8 | 28.8 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/8/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-232 | Wempletown 138 kV |  | IL | Winnebago | Withdrawn | ComEd | 175 | 105 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/31/2025
PJM | AH1-233 | Wempletown 138 kV |  | IL | Winnebago | Withdrawn | ComEd | 0 | 70 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/31/2025
PJM | AH1-234 | Wempletown 345 kV |  | IL | Winnebago | Active | ComEd | 224 | 149.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 11/21/2025
PJM | AH1-235 | Kilgore Compressor Facility 138 kV |  | OH | Harrison | Withdrawn | AEP | 8 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/25/2023
PJM | AH1-236 | Bane 69 kV |  | OH | Carroll | Withdrawn | AEP | 8 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-237 | Ladysmith- Elmont 230kV |  | VA | Caroline | Withdrawn | Dominion | 130 | 78 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-238 | Ladysmith- Elmont 230kV |  | VA | Caroline | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-239 | Upchurch - Zula 69 kV |  | KY | Boone | Active | EKPC | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2024
PJM | AH1-240 | Wayne County 161 kV |  | KY | Boone | Withdrawn | EKPC | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-241 | Cobbs Creek - James River Industrial 115kV |  | VA | Cumberland | Active | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2024
PJM | AH1-242 | New Bethlehem-Armstrong 138kV |  | PA | Clarion | Withdrawn | APS | 30 | 18 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-243 | New Bethlehem – Armstrong 138kV |  | PA | Clarion | Withdrawn | APS | 30 | 18 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-244 | Yukon-Bethelboro 138kV |  | PA | Fayette | Withdrawn | APS | 80 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-245 | Yukon-Bethelboro 138kV |  | PA | Fayette | Withdrawn | APS | 80 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-246 | Osterberg 115kV |  | PA | Bedford | Withdrawn | PENELEC | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-247 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2024
PJM | AH1-248 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 25 | 15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2024
PJM | AH1-249 | Lardin – Lake Lynn 138kV |  | PA | Fayette | Active | APS | 80 | 80 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2024
PJM | AH1-250 | Todds Tavern- Spotsylvania/Goldsdale 115kV |  | VA | Spotsylvania | Withdrawn | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 3/3/2023 |  | 12/31/2024
PJM | AH1-251 | Todds Tavern- Spotsylvania/Goldsdale 115kV |  | VA | Spotsylvania | Active | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2024
PJM | AH1-252 | Wharton - Sundial 138 kV |  | WV | Barbour | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-253 | Price 69kV |  | MD | Queen Anne's | Withdrawn | DPL | 15.5 | 9.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 10/1/2024
PJM | AH1-254 | Greenland Gap 500 kV II |  | WV | Barbour | Active | APS | 207.6 | 36.538 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 9/10/2021 |  |  | 7/31/2025
PJM | AH1-255 | Greenland Gap III |  | WV | Grant | Active | APS | 240 | 240 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 7/31/2025
PJM | AH1-256 | Greeland Gap 500 kV IV |  | WV | Grant | Withdrawn | APS | 240 | 240 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 7/31/2025
PJM | AH1-257 | Broadway - RichLine Hill Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 8.085 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/23/2022
PJM | AH1-258 | Belford - Keansburg 34.5 kV |  | NJ | Monmouth | Active | JCPL | 19.25 | 8.085 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/23/2022
PJM | AH1-259 | Chesterfield- Centralia 115kV |  | VA | Chesterfield | Withdrawn | Dominion | 35 | 35 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-260 | New Freedom 230 kV |  | NJ | Camden | Active | PSEG | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/30/2025
PJM | AH1-261 | East Point - Golden Ring 115kV |  | MD | Baltimore County | Active | BGE | 135 | 135 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/30/2025
PJM | AH1-262 | Deep Creek 115 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 0 | 60 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 11/30/2023
PJM | AH1-263 | Chancellor 115 kV |  | VA | Spotsylvania | Active | Dominion | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 6/30/2025
PJM | AH1-264 | Suffolk- Sunbury 230kV |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-265 | TBD 69kV |  | NJ | Camden | Active | AEC | 29.4 | 12.35 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/23/2022
PJM | AH1-266 | Clubhouse – Lakeview 230 kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-267 | Papermill IND – Harmony Village 230 kV |  | VA | King and Queen | Withdrawn | Dominion | 120 | 72 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-268 | Seward-Glory 115 kV II |  | PA | Indiana | Active | PENELEC | 0 | 36.6 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2024
PJM | AH1-269 | Claytor 138 kV |  | VA | Pulaski | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2025
PJM | AH1-270 | Hayden 345 kV |  | OH | Franklin | Withdrawn | AEP | 85 | 51 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/1/2023
PJM | AH1-271 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 9/20/2024
PJM | AH1-272 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 300 | 180 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 5/1/2025
PJM | AH1-273 | Brown - Eastwood 138 kV |  | OH | Brown | Withdrawn | DEOK | 160 | 96 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/26/2025
PJM | AH1-274 | Monroe – North Central 69kV |  | NJ | Gloucester | Active | AEC | 16.7 | 7.014 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/23/2022
PJM | AH1-275 | Chippewa D557 8.32 kV |  |  |  | Withdrawn | ATSI | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 11/1/2023
PJM | AH1-276 | Leasure 12.47kV |  | VA | Campbell | Withdrawn | PENELEC | 4.99 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 6/15/2022 |  | 11/1/2023
PJM | AH1-277 | Indian River 230kV |  | DE | Sussex | Withdrawn | DPL | 1035 | 279 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/31/2027
PJM | AH1-278 | Milford - Indian River/Cool Springs 230kV |  | DE | Sussex | Withdrawn | DPL | 1035 | 279 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/31/2027
PJM | AH1-279 | Poolesville - Winchester 230 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/12/2023
PJM | AH1-280 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/12/2023
PJM | AH1-281 | Bluegrass Parkway Tap - Woodlawn 69 kV |  | KY | Nelson | Active | EKPC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 6/7/2024
PJM | AH1-282 | Galion - Ohio Central 345 kV |  | OH | Morrow | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 5/1/2025
PJM | AH1-283 | Mount Storm-Pruntytown 500kV |  | MD | Garrett | Active | APS | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 10/31/2024
PJM | AH1-284 | West Willow 12 kV |  | PA | Adams | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-285 | Sandwich 34.5 kV |  | IL | DeKalb | Active | ComEd | 86 | 51.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2025
PJM | AH1-286 | Bradford North 34.5kV |  | WV | Preston | Withdrawn | PENELEC | 3 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 11/1/2023
PJM | AH1-287 | Houseville – Cooperstown 25 kV |  | OH | Madison | Withdrawn | APS | 4.99 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 11/1/2023
PJM | AH1-288 | Chickahominy 230kV |  | VA | Charles City | Withdrawn | Dominion | 43.2 | 43.2 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-289 | Eugene 345 kV |  | IN | Vermillion | Withdrawn | AEP | 300 | 52.8 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 5/1/2028
PJM | AH1-290 | BASF - Washburn Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 8.085 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 9/9/2022
PJM | AH1-291 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 185 | 111 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-292 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 0 | 44 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2023
PJM | AH1-293 | Makahoy 138 kV |  | IN | Madison | Withdrawn | AEP | 0 | 26.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-294 | Mclean 345 kV |  | IL | McLean | Active | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2025
PJM | AH1-295 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Active | ComEd | 200 | 35.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-296 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 60 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-297 | Kewanee - E.D. Edwards 138 kV |  | IL | Stark | Active | ComEd | 200 | 26 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-298 | Twin Branch - Meridian 345 kV |  | IN | Whitley | Active | AEP | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/14/2021 |  |  | 12/31/2025
PJM | AH1-299 | Coventry 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/7/2021 |  | 12/31/2025
PJM | AH1-300 | Hacienda 138 kV |  | IN | Allen | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-301 | Milan 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-302 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-303 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Withdrawn | AEP | 75 | 75 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-304 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 0 | 9.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2023
PJM | AH1-305 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 0 | 35.72 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2023
PJM | AH1-306 | Mississinewa-Gaston 138 kV |  | IN | Grant | Active | AEP | 0 | 28.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2023
PJM | AH1-307 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2025
PJM | AH1-308 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-309 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Active | AEP | 0 | 27 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2023
PJM | AH1-310 | Colby - Valley 138 kV |  | MI | Van Buren | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-311 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 0 | 2.25 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2023
PJM | AH1-312 | Shilo DP – Conetoe DP 115 kV |  | NC | Edgecombe | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-313 | Moshannon-Milesburg 230 kV VII |  | PA | Centre | Active | APS | 100 | 60 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-314 | East Danville 138 kV |  | VA | Pittsylvania | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2025
PJM | AH1-315 | Maroe 69 kV |  | OH | Henry | Withdrawn | ATSI | 96 | 57.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 3/14/2024 |  | 12/31/2025
PJM | AH1-316 | Todd 25kV |  | MD | Dorchester | Active | DPL | 0 | 4.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2025
PJM | AH1-317 | Greene - Beatty 345 kV |  | OH | Madison | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-318 | Cole 345 kV |  | OH | Franklin | Active | AEP | 60 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2025
PJM | AH1-319 | East Springfield-London 138 kV II |  | OH | Clark | Active | ATSI | 54 | 54 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-320 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 69 | 69 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-321 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 54 | 54 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-322 | Fostoria Central - Lemoyne 345 kV |  | OH | Miami | Withdrawn | AEP | 90 | 90 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-323 | Elmont 230 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2025
PJM | AH1-324 | Hopewell – Surry 230 kV |  | VA | Surry | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-325 | Kirk 138 kV |  | OH | Licking | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2021 |  |  | 12/31/2025
PJM | AH1-326 | West Newton - Lynn 138 kV |  | OH | Hardin | Withdrawn | AEP | 0 | 19.07 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-327 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 0 | 8.44 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2023
PJM | AH1-328 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 0 | 21.3 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2023
PJM | AH1-329 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Withdrawn | AEP | 30 | 30 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-330 | Tyner - McKee 69 kV |  | KY |  | Withdrawn | EKPC | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-331 | Edinboro South-Erie South 25kV |  | PA | Erie | Active | PENELEC | 19.9 | 11.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2021 |  |  | 6/1/2023
PJM | AH1-332 | West Hills - Craigsville Junction 25 kV |  | PA | Armstrong | Withdrawn | APS | 19.9 | 7.98 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2021 | 12/18/2024 |  | 6/1/2023
PJM | AH1-333 | Miller - Canal 69kV |  | OH | Butler | Withdrawn | DEOK | 48 | 28.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 4/26/2024
PJM | AH1-334 | Manchester - Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.25 | 8.085 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/9/2022
PJM | AH1-335 | Furnace Brook Tap - Warren County Resource Recovery 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 19.25 | 8.085 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/9/2022
PJM | AH1-336 | Bremo Bluff - Buckingham 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 56 | 33.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-337 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 75 | 75 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/30/2025
PJM | AH1-338 | New Sub S2354 138kV |  | IL | Lee | Active | ComEd | 180 | 120.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 11/21/2025
PJM | AH1-339 | West Crawford 69 kV |  | OH | Wyandot | Active | AEP | 80 | 53.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 11/21/2025
PJM | AH1-340 | Cheat Lake-Ruthbelle 138 kV |  | WV | Preston | Active | APS | 48.89 | 29.33 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 5/31/2024
PJM | AH1-341 | ESS-H445 3B 138kv |  | IL | Ogle | Active | ComEd | 150 | 99 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/7/2025
PJM | AH1-342 | Carlos Junction 138 kV II |  | MD | Allegany | Withdrawn | APS | 75 | 50 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 10/1/2021 |  | 7/16/2025
PJM | AH1-343 | Crystal Hill DP- Perth 115kV |  | VA | Halifax | Active | Dominion | 69 | 41.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/30/2025
PJM | AH1-344 | Sparta Solar 34.5kV |  | NJ | Atlantic | Withdrawn | JCPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 1/4/2022 |  | 9/20/2023
PJM | AH1-345 | Remington 324 34.5 kV |  | VA | Fauquier | Active | Dominion | 14 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/31/2023
PJM | AH1-346 | Harrisonburg 356 34.5 kV |  | VA | Rockingham | Withdrawn | Dominion | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 8/29/2024 |  | 12/31/2023
PJM | AH1-347 | North Pole 492 34.5 kV |  | VA | Goochland | Withdrawn | Dominion | 25 | 15 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 8/5/2024 |  | 3/31/2023
PJM | AH1-348 | Indian Creek 34.5 kV |  | VA | Wise | Active | AEP | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/21/2023
PJM | AH1-349 | Powhatan 406 34.5 kV |  | VA | Powhatan | Withdrawn | Dominion | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 8/5/2024 |  | 12/31/2023
PJM | AH1-350 | Sunnyside – Carrolton 138 kV |  | OH | Stark | Withdrawn | AEP | 92.4 | 55.44 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 11/15/2024 |  | 6/1/2025
PJM | AH1-351 | Hillsboro-Wye Mills 138kV |  | MD | Queen Anne's | Withdrawn | DPL | 50 | 30 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 5/1/2025
PJM | AH1-352 | Red Eye 138 kV |  | VA | Campbell | Active | AEP | 40 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/30/2023
PJM | AH1-353 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-354 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 40 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-355 | Owl Trap Switching Station 115kV |  | VA | Gloucester | Active | Dominion | 40 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-356 | Kings Creek 138kV |  | MD | Somerset | Active | DPL | 30 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/30/2023
PJM | AH1-357 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-358 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-359 | Farmers Valley-Ridgeway 115kV |  | PA | McKean | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-360 | Farmers Valley-Ridgeway 115kV |  | PA | McKean | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-361 | Minonk 345 kV |  | IL | Woodford | Active | ComEd | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2024
PJM | AH1-362 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-363 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-364 | Harmony Village 230kV |  | VA | Middlesex | Withdrawn | Dominion | 68 | 68 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-365 | Iron Bridge 230kV |  | VA | Chesterfield | Withdrawn | Dominion | 50.4 | 50.4 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-366 | Whitely 138 kV |  | PA | Greene | Withdrawn | APS | 30 | 22 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/13/2024 |  | 9/10/2023
PJM | AH1-367 | Franklin 138 kV |  | PA | Greene | Withdrawn | APS | 74 | 54 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/13/2024 |  | 9/10/2023
PJM | AH1-367A | Franklin 138 kV II |  | PA | Greene | Active | APS | 150 | 110 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/10/2023
PJM | AH1-368 | Cloverdale - Joshua Falls 765 kV |  | VA | Bedford | Withdrawn | AEP | 125 | 83.3333 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-369 | Backbone Mountain 138 kV II |  | WV | Tucker | Withdrawn | APS | 20 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 1/23/2023 |  | 12/31/2023
PJM | AH1-370 | Mather - Stoney Point Junction 25 kV |  | PA | Greene | Withdrawn | APS | 8 | 5.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/3/2024
PJM | AH1-371 | Universal 12 kV |  | PA | Allegheny | Withdrawn | DL | 13 | 8.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/15/2021 |  | 6/3/2024
PJM | AH1-372 | Piney - Timblin 115 kV |  | PA | Armstrong | Withdrawn | APS | 16 | 10.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/3/2024
PJM | AH1-373 | Buckeye No. 3 - Cowell Junction 25kV |  | PA | Greene | Withdrawn | APS | 12.8 | 7.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/3/2024
PJM | AH1-374 | Bremo-Cartersville 230 kV II |  | VA | Cumberland | Withdrawn | Dominion | 0 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/9/2024 |  | 6/30/2026
PJM | AH1-375 | Cobbs Creek- James River 115kV |  | VA | Fluvanna | Withdrawn | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 11/18/2024 |  | 6/1/2025
PJM | AH1-376 | Ronceverte - Clenden 46 kV |  | WV | Greenbrier | Active | APS | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-377 | Clover- Farmville 230kV |  | VA | Prince Edward | Active | Dominion | 186 | 111.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-378 | Lunenburg- Butcher Creek 115kV |  | VA | Lunenburg | Active | Dominion | 51 | 30.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-379 | Hickman 69 kV |  | VA | Pulaski | Withdrawn | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/20/2024
PJM | AH1-380 | Mt Olive - Kenny 69kV |  | MD | Worcester | Active | DPL | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/20/2024
PJM | AH1-381 | Lone Gum - Rockcastle 138 kV |  | VA | Bedford | Withdrawn | AEP | 99.5 | 59.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 5/1/2025
PJM | AH1-382 | Van Arsdell 69 kV |  | KY | Mercer | Withdrawn | EKPC | 20 | 17 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/10/2025
PJM | AH1-383 | Celanese 138 kV |  | VA | Giles | Withdrawn | AEP | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-384 | Indian River 230kV |  | DE | Sussex | Withdrawn | DPL | 1410 | 380.7 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/31/2027
PJM | AH1-385 | Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 109 | 65.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-386 | Kerr Dam - Chase City 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 130 | 78 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-387 | Meadowbrook-Mount Storm 500kV |  | WV | Hampshire | Active | APS | 150 | 22.05 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 9/10/2021 |  |  | 1/9/2025
PJM | AH1-388 | Chase City-Herbert 115 kV |  | VA | Mecklenburg | Withdrawn | Dominion | 115 | 63 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/20/2024
PJM | AH1-389 | Utica East Ohio Midstream 138 kV |  | OH | Warren | Withdrawn | ATSI | 19.95 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-390 | TBD 69 kV |  | PA | Northumberland | Active | PPL | 19.9 | 14.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 7/31/2023
PJM | AH1-391 | Michiana Solar |  | IN | St. Joseph | Active | AEP | 100 | 64.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 7/16/2025
PJM | AH1-392 | Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 90 | 57.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 7/16/2025
PJM | AH1-393 | Markus Solar 115 kV |  | PA | Indiana | Withdrawn | PENELEC | 3.75 | 1.425 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/4/2021 |  | 12/31/2023
PJM | AH1-394 | Mainesburg 115 kV |  | PA | Tioga | Withdrawn | PENELEC | 10.5 | 3.99 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 2/2/2022 |  | 12/31/2023
PJM | AH1-395 | Mainesburg 115 kV II |  | PA | Tioga | Withdrawn | PENELEC | 6 | 2.28 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 12/31/2023
PJM | AH1-396 | Gary 24.94 kV |  | VA | Lunenburg | Active | Dominion | 12 | 1.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 10/2/2023
PJM | AH1-397 | Shacklesfords 34.5 kV |  | VA | King and Queen | Active | Dominion | 19.818 | 2.97 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 10/2/2023
PJM | AH1-398 | Oak Grove 22.9 kV |  | VA | Westmoreland | Withdrawn | Dominion | 18 | 11.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/22/2021 | 12/18/2024 |  | 10/2/2023
PJM | AH1-399 | North Doswell 12.5 kV |  | VA | Hanover | Active | Dominion | 12 | 7.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/22/2021 |  |  | 10/2/2023
PJM | AH1-400 | Jones Creek - Aladdin 138 kV |  | IN | Madison | Withdrawn | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/17/2024 |  | 6/1/2025
PJM | AH1-401 | Jones Creek - Aliddin 138 kV |  | IN | Madison | Withdrawn | AEP | 0 | 60 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/17/2024 |  | 6/1/2025
PJM | AH1-402 | Shelocta 115kV |  | PA | Indiana | Withdrawn | PENELEC | 85 | 55.9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 8/21/2024 |  | 12/31/2024
PJM | AH1-403 | Shelocta 115kV |  | PA | Indiana | Withdrawn | PENELEC | 0 | 29.1 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 8/21/2024 |  | 12/31/2024
PJM | AH1-404 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Withdrawn | OVEC | 40 | 24 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/13/2024 |  | 12/31/2024
PJM | AH1-405 | Exchange Tap I 69 kV |  | PA | Northumberland | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/13/2024 |  | 10/18/2024
PJM | AH1-406 | Exchange Tap 69 kV II |  | PA | Northumberland | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/13/2024 |  | 10/18/2024
PJM | AH1-407 | Exchange Tap 69 kV III |  | PA | Northumberland | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/13/2024 |  | 10/18/2024
PJM | AH1-408 | Freeman DP – Lawrenceville 115 kV |  | VA | Brunswick | Active | Dominion | 120 | 75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/1/2024
PJM | AH1-409 | Brodhead - Maretburg 69 kV |  | KY |  | Withdrawn | EKPC | 58 | 34.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2024
PJM | AH1-410 | Union City Tap – JK Smith 138 kV |  | KY | Madison | Withdrawn | EKPC | 68 | 40.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2024
PJM | AH1-411 | Phillipsburg - Ingersol Rand 34.5 kV |  | NJ | Warren | Withdrawn | JCPL | 5.75 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 8/8/2024 |  | 9/8/2022
PJM | AH1-412 | Franklintown 34.5 kV |  | WV | Jefferson | Withdrawn | APS | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 9/19/2024 |  | 10/1/2025
PJM | AH1-413 | Wayne Trace 138 kV |  | IN | Allen | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/11/2021 | 8/7/2024 |  | 10/1/2025
PJM | AH1-414 | Leslie - Pineville 161 kV |  | KY | Leslie | Withdrawn | AEP | 80 | 80 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/11/2021 | 2/29/2024 |  | 10/1/2025
PJM | AH1-415 | Bremo Bluff 34.5kV |  | VA | Fluvanna | Withdrawn | Dominion | 15.975 | 8.6265 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/10/2024 |  | 10/11/2023
PJM | AH1-416 | Bellefontaine 69 kV |  | OH | Logan | Withdrawn | Dayton | 50 | 50 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/11/2021 | 7/16/2024 |  | 10/1/2025
PJM | AH1-417 | Castalia 69 kV |  | OH | Erie | Withdrawn | ATSI | 50 | 50 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 7/24/2024 |  | 10/1/2025
PJM | AH1-418 | Elkhorn City - Second Fork 69 kV |  | KY | Pike | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/13/2024 |  | 10/1/2025
PJM | AH1-419 | Thompson 34.5 kV II |  | PA | Susquehanna | Withdrawn | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/1/2025
PJM | AH1-420 | Fentress 34.5kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 20 | 10.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/26/2023
PJM | AH1-421 | West Mingo 69 kV |  | OH | Champaign | Withdrawn | Dayton | 40 | 40 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-422 | West Mingo 69 kV |  | OH | Champaign | Withdrawn | Dayton | 20 | 18.85 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-423 | West Mingo 69 kV |  | OH | Champaign | Withdrawn | Dayton | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-424 | Sandborn 34.5 kV |  | OH | Ashtabula | Withdrawn | ATSI | 19.2 | 11.52 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-425 | Lemoyne 138kV |  | OH | Ottawa | Withdrawn | ATSI | 32 | 19.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2024
PJM | AH1-426 | Jones Branch 138 kV |  | WV | Kanawha | Active | APS | 64.6 | 64.6 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2023
PJM | AH1-426A | Jones Branch 138 kV |  | WV | Nicholas | Active | APS | 32.3 | 32.3 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2023
PJM | AH1-427 | Tommy Gooch - Garrard County 69 kV |  | KY |  | Active | EKPC | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/1/2026
PJM | AH1-428 | Tommy Gooch - Garrard County 69 kV |  | KY | Boone | Active | EKPC | 0 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/1/2026
PJM | AH1-429 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 90 | 54 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/1/2026
PJM | AH1-430 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Withdrawn | EKPC | 0 | 36 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/1/2026
PJM | AH1-431 | Pennville 138 kV |  | IN | Jay | Withdrawn | AEP | 0 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2025
PJM | AH1-432 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 0 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 4/1/2025
PJM | AH1-433 | Kingsland 69 kV |  | IN | Wells | Withdrawn | AEP | 0 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 4/1/2025
PJM | AH1-434 | Carolina- Earleys 115kV |  | NC | Northhampton | Active | Dominion | 75 | 45 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/1/2026
PJM | AH1-435 | Carolina- Earleys 115kV |  | NC | Northhampton | Withdrawn | Dominion | 0 | 30 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/1/2026
PJM | AH1-436 | Mackeys- Creswell 115kV |  | NC | Washington | Withdrawn | Dominion | 0 | 60 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2025
PJM | AH1-437 | Remington- Gordonsville 230kV |  | VA | Culpeper | Withdrawn | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/1/2026
PJM | AH1-438 | Remington- Gordonsville 230kV |  | VA | Culpeper | Withdrawn | Dominion | 0 | 60 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/1/2026
PJM | AH1-439 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 85 | 51 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/1/2026
PJM | AH1-440 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 0 | 34 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/1/2026
PJM | AH1-441 | Cunningham - Elmont 500 kV III |  | VA | Fluvanna | Withdrawn | Dominion | 0 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/30/2026
PJM | AH1-442 | Cunningham - Elmont 500 kV IV |  | VA | Fluvanna | Withdrawn | Dominion | 0 | 20 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/30/2026
PJM | AH1-443 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Withdrawn | Dominion | 0 | 15 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/30/2026
PJM | AH1-444 | Fentress – Sligo 230 kV |  | VA | City of Chesapeake | Withdrawn | Dominion | 200 | 170 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/18/2021 |  | 9/1/2025
PJM | AH1-445 | Belleville 46 kV |  | PA | Mifflin | Withdrawn | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 8/7/2024 |  | 9/30/2023
PJM | AH1-446 | Sanders DP - Westmoreland 230 kV |  | VA | Westmoreland | Active | Dominion | 65 | 19.5 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/2/2024
PJM | AH1-447 | Axton – Danville #2 138 kV |  | VA | Pittsylvania | Active | AEP | 60 | 36 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/2/2024
PJM | AH1-448 | East Palmerton-Harwood 230 kV |  | PA | Carbon | Withdrawn | PPL | 180 | 180 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 12/1/2024
PJM | AH1-449 | Muskingum River - Sporn 345 kV |  | OH | Washington | Withdrawn | AEP | 150 | 150 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/31/2025
PJM | AH1-450 | Chase City 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2025
PJM | AH1-451 | Hopkins 138 kV |  | WV |  | Withdrawn | AEP | 180 | 108 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 5/1/2025
PJM | AH1-452 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 8.35 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 6/1/2023
PJM | AH1-453 | Eugene 345 kV |  | IN | Vermillion | Withdrawn | AEP | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 5/1/2028
PJM | AH1-454 | Pinewood- St Johns 115kV |  | VA | Caroline | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/1/2025
PJM | AH1-455 | Middle Creek 69 kV |  | KY | Magoffin | Withdrawn | EKPC | 60 | 39.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 11/2/2023 |  | 9/1/2025
PJM | AH1-456 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-457 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-458 | Hampshire - Ridgeley 138 kV 1 |  | WV | Hampshire | Withdrawn | APS | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-459 | Hampshire - Ridgeley 138 kV 2 |  | WV | Hampshire | Withdrawn | APS | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 9/30/2024
PJM | AH1-460 | Hooversville - Scalp Level 115 kV |  | PA | Somerset | Active | PENELEC | 66 | 39.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2024
PJM | AH1-461 | Buckhorn 138 kV |  | VA | Tazewell | Active | AEP | 80 | 80 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2024
PJM | AH1-462 | Rachel Hill 115 kV |  | PA | Cambria | Active | PENELEC | 60 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/11/2021 |  |  | 12/31/2024
PJM | AH1-463 | Owingsville - Preston 69 kV |  | KY | Bath | Active | EKPC | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2024
PJM | AH1-464 | Hinkston 24.9 kV |  | KY | Montgomery | Withdrawn | EKPC | 12 | 7.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 3/2/2023 |  | 12/31/2022
PJM | AH1-465 | Carson – Rogers Road 500 kV |  | VA | Greensville | Withdrawn | Dominion | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-466 | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 600 | 360 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2024
PJM | AH1-467 | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 300 | 120 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2024
PJM | AH1-468 | Hokes-Jackson 69 kV V |  | PA | York | Withdrawn | ME | 15 | 15 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/11/2021 |  | 9/25/2023
PJM | AH1-469 | Derry Tap-Derry Bus 69 kV III |  | PA | Montour | Withdrawn | PPL | 15 | 15 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-470 | Derry Tap- Derry Bus 69 kV IV |  | PA | Northumberland | Withdrawn | PPL | 15 | 15 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-471 | Derry Tap- Derry Bus 69 kV VI |  | PA | Snyder | Withdrawn | PPL | 15 | 15 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-472 | Derry Tap- Derry Bus 69 kV VII |  | PA | Columbia | Withdrawn | PPL | 56 | 56 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-473 | Hokes-Jackson 69 kV VI |  | PA | York | Withdrawn | ME | 15 | 15 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/11/2021 |  | 9/25/2023
PJM | AH1-474 | Edinboro South-Venango Junction 115 kV III |  | PA | Crawford | Withdrawn | PENELEC | 87 | 87 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-475 | Edinboro-Cambridge Springs 34.5 kV II |  | PA | Crawford | Withdrawn | PENELEC | 15 | 15 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-476 | Hunterstown-Texas Eastern Tap 115 kV II |  | PA | Adams | Withdrawn | ME | 73 | 73 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 9/23/2024
PJM | AH1-477 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 112 | 112 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-478 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Withdrawn | PPL | 40 | 40 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-479 | New Carlisle 138 kV |  | IN | St. Joseph | Withdrawn | AEP | 82 | 82 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-480 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Withdrawn | AEP | 57 | 57 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-481 | Reynolds - Meadow Lake #1 345 kV |  | IN | White | Withdrawn | AEP | 84 | 84 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2024
PJM | AH1-482 | Olive - Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 195 | 195 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 9/25/2023
PJM | AH1-483 | Honda Marysville Tap 69 kV |  | OH | Union | Withdrawn | Dayton | 42 | 42 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/23/2024
PJM | AH1-484 | Madison - Tanners Creek 138 kV |  | IN | Henry | Withdrawn | AEP | 115 | 115 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 9/24/2023
PJM | AH1-485 | Brookside-Cloverdale 138 kV II |  | OH | Wayne | Withdrawn | ATSI | 98 | 98 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/11/2021 |  | 9/25/2023
PJM | AH1-486 | Maysville 69 kV 1 |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 7/30/2024
PJM | AH1-487 | Maysville 34.5 kV 2 |  | PA | Mercer | Active | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 7/30/2024
PJM | AH1-488 | Maysville 34.5 kV 3 |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/30/2024
PJM | AH1-489 | Maysville 34.5 kV 4 |  | PA | Mercer | Withdrawn | ATSI | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/30/2024
PJM | AH1-490 | Venango Junction - Cambridge Springs 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 7/30/2024
PJM | AH1-491 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 7/30/2024
PJM | AH1-492 | Bernville 34.5 kV 1 |  | PA | Berks | Active | ME | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 7/30/2024
PJM | AH1-493 | Bernville 34.5 kV 2 |  | PA | Berks | Withdrawn | ME | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 7/30/2024
PJM | AH1-494 | Wakefield 12 kV |  | PA | Lancaster | Withdrawn | PPL | 10 | 6.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/5/2023 |  | 6/30/2024
PJM | AH1-495 | Middleburg 12 kV |  | PA | Snyder | Withdrawn | PPL | 10 | 6.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/5/2023 |  | 6/30/2024
PJM | AH1-496 | West Berwick 12 kV |  | PA | Columbia | Withdrawn | PPL | 10 | 6.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/5/2023 |  | 6/30/2024
PJM | AH1-497 | Hadley 12.47kV |  | PA | Mercer | Withdrawn | ATSI | 5 | 3.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-498 | Jamestown 12.47kV |  | PA | Crawford | Withdrawn | ATSI | 5 | 3.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-499 | Stoneboro 12.47kV |  | PA | Mercer | Withdrawn | ATSI | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-500 | Conesville Junction – Parkview Road Junction 46 kV |  | PA | Potter | Withdrawn | APS | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-501 | Tionesta Junction – Crown 34.5 kV |  | PA | Forest | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-502 | Dequine - Eugene 345 kV |  | IN | Warren | Withdrawn | AEP | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 5/1/2028
PJM | AH1-503 | Kings Fork – Chuckatuck 230 kV |  | VA | City of Suffolk | Withdrawn | Dominion | 150 | 127.5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/30/2025
PJM | AH1-504 | Lickdale 13.2kV |  | PA | Lebanon | Withdrawn | ME | 7.5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-505 | Wheatland 12.47 kV |  | PA | Mercer | Withdrawn | ATSI | 7.5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-506 | Oceanview Wind 3 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 730 | 300 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/30/2028
PJM | AH1-507 | Oceanview Wind 4 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 730 | 300 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/30/2028
PJM | AH1-508 | Bremo-Fork Union Military Academy 34.5 kV |  | VA | Fluvanna | Withdrawn | Dominion | 16 | 9.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/18/2023 |  | 2/1/2025
PJM | AH1-509 | TBD 12 kV |  | PA | Northumberland | Withdrawn | PPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 3/14/2022 |  | 12/31/2023
PJM | AH1-510 | Clarence Solar 12 kV |  |  |  | Withdrawn | PENELEC | 4.95 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/1/2021 |  | 12/31/2023
PJM | AH1-511 | Blacklick Solar 12 kV |  |  |  | Withdrawn | PENELEC | 4.95 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/1/2021 |  | 12/31/2023
PJM | AH1-512 | Brush Creek Solar 12 kV |  |  |  | Withdrawn | PENELEC | 4.95 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/1/2021 |  | 12/31/2023
PJM | AH1-513 | Summit Community Solar 12 kV |  |  |  | Withdrawn | APS | 4.95 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/1/2021 |  | 12/31/2023
PJM | AH1-514 | Philipsburg - Emeigh 12.47 kV-1 |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 3.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/29/2023
PJM | AH1-515 | Philipsburg - Emeigh 12.47 kV-2 |  | PA | Clearfield | Withdrawn | PENELEC | 5 | 2.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/29/2023
PJM | AH1-515A | Springdale - Wycoff 12.8 kV |  | PA | Allegheny | Withdrawn | APS | 5 | 3.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 | 3/14/2022 |  | 12/29/2023
PJM | AH1-516 | Springfield Road - Springfield Road 69 kV |  | OH | Butler | Withdrawn | DEOK | 70 | 44.7 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/1/2025
PJM | AH1-517 |  |  | IL | Adams | Withdrawn | ComEd |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 6/1/2022
PJM | AH1-518 | Pulaski Sub-New Wilmington 69kV |  | PA | Lawrence | Withdrawn | ATSI | 19 | 7.98 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/1/2023
PJM | AH1-519 |  |  | OH | Champaign | Withdrawn | Dayton | 200 | 134.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 10/15/2024
PJM | AH1-520 | Blue Jacket-Kirby 138 kV V |  | OH | Union | Withdrawn | ATSI | 120 | 79.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/15/2024
PJM | AH1-521 | Blue Jacket-Kirby 138 kV VI |  | OH | Union | Withdrawn | ATSI | 100 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/15/2024
PJM | AH1-522 | Timber Switch 138 kV |  | OH | Paulding | Withdrawn | AEP | 47 | 28.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-523 | Heidelberg 69 kV |  | PA | Lebanon | Withdrawn | PPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 7/30/2024
PJM | AH1-524 | University Park - Olive 345 kV |  | IN | LaPorte | Withdrawn | AEP | 117 | 70.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 7/18/2023 |  | 12/31/2025
PJM | AH1-525 | University Park - Olive 345 kV |  | IN | LaPorte | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/11/2021 | 7/18/2023 |  | 12/31/2025
PJM | AH1-526 | South Canton - Sammis 345 kV |  | OH | Carroll | Active | ATSI | 80 | 80 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/11/2021 |  |  | 10/31/2025
PJM | AH1-527 | Chase City- Herbert Plant Substation 115kV |  | VA | Mecklenburg | Withdrawn | Dominion | 149 | 89.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/30/2025
PJM | AH1-528 | Rawlings 500kV |  | VA | Brunswick | Active | Dominion | 300.8 | 180 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/30/2025
PJM | AH1-529 | Renaker - Avon 138 kV |  | KY | Bourbon | Withdrawn | EKPC | 24 | 14.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/1/2025
PJM | AH1-530 | Fairfield – Reily 69 kV |  | OH | Butler | Active | DEOK | 28 | 16.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-531 | Salyers Rd 34.5 kV |  | OH | Pike | Withdrawn | AEP | 21 | 12.6 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/1/2025
PJM | AH1-532 | Marion County - Marion Co. Industrial 161 kV |  | KY | Marion | Withdrawn | EKPC | 37.8 | 22.68 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/1/2025
PJM | AH1-533 | Sunbury-Juniata II |  | PA | Perry | Active | PPL | 96.2 | 57.7 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-534 | Sullivan Gardens - Walters 138 kV |  | TN | Greene | Withdrawn | AEP | 22.7 | 13.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/1/2025
PJM | AH1-535 | Nagel - Cane River 230 kV |  | TN | Hawkins | Active | AEP | 133.6 | 80.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-536 | Church-Oil City 138kV |  | MD | Queen Anne's | Active | DPL | 41.8 | 8.5 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-537 | Pierce - DOE X-530 345 kV |  | OH | Highland | Active | OVEC | 178.5 | 107.1 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/11/2021 |  |  | 3/1/2025
PJM | AH1-538 | East Lima - Haviland 138 kV |  | OH | Van Wert | Active | AEP | 241.5 | 144.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-539 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 129.4 | 77.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-540 | Byron to Wayne 345 kV |  | IL | Ogle | Active | ComEd | 165 | 99 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-541 | Chestnut 345 kV |  | IL | DeWitt | Active | ComEd | 92.4 | 55.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-542 | Crissinger-Delaware Business Park 138kV |  | OH | Marion | Active | ATSI | 132.2 | 79.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-543 | Powerton - Katydid Road 345 kV |  | IL | Livingston | Active | ComEd | 157.4 | 94.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/11/2021 |  |  | 3/1/2025
PJM | AH1-544 | La Salle 345 kV |  | IL | Lasalle | Withdrawn | ComEd | 67.7 | 40.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/1/2025
PJM | AH1-545 | Wylie Ridge-Tidd 345kV |  | PA | Washington | Active | APS | 200 | 200 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 3/1/2025
PJM | AH1-546 | Bremo - Buckingham 230 kV |  | VA | Buckingham | Active | Dominion | 79.8 | 47.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 2/1/2025
PJM | AH1-547 | Reynolds - Olive #1 345 kV |  | IN | White | Withdrawn | AEP | 0 | 74 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/31/2022
PJM | AH1-548 | Sorenson 345 kV |  | IN | Huntington | Withdrawn | AEP | 160 | 96 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-549 | Allen - RP Mone 345 kV |  | IN | Allen | Active | AEP | 180 | 108 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-550 | Hazelton - Kirk 138 kV |  | OH | Licking | Active | AEP | 110 | 66 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/31/2025
PJM | AH1-551 |  |  | OH | Carroll | Withdrawn | AEP | 100 | 42 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 10/31/2025
PJM | AH1-552 | Chalk Point 230kV |  | MD | Prince George's | Active | PEPCO | 809.5 | 670.2 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-553 | Broadview -Tangy 138 kV II |  | OH | Madison | Withdrawn | ATSI | 66 | 39.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 7/17/2024 |  | 10/1/2025
PJM | AH1-554 | Lick 138 kV |  | OH | Jackson | Withdrawn | AEP | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 |  |  | 10/1/2025
PJM | AH1-555 | Maxwell 138 kV |  | OH | Cuyahoga | Withdrawn | ATSI | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/18/2021 |  | 10/1/2025
PJM | AH1-556 | Larrabee 230 kV III |  | NJ | Monmouth | Withdrawn | JCPL | 360 | 63.36 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/31/2029
PJM | AH1-557 | Larrabee Collector Station 230 kV |  | NJ | Monmouth | Active | JCPL | 1300 | 228.8 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 9/10/2021 |  |  | 10/31/2029
PJM | AH1-558 | Four Rivers 230kV |  | VA | Hanover | Active | Dominion | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-559 |  |  | IL | Will | Withdrawn | ComEd | 250 | 250 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 11/1/2021 |  | 6/1/2025
PJM | AH1-560 | University Park 138 kV |  | IL | Will | Active | ComEd | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-561 | Ironwood 230kV |  | PA | Lebanon | Active | ME | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-562 | Springdale 138kV |  | PA | Allegheny | Active | APS | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-563 | Aurora E.C. 138kV |  | IL |  | Active | ComEd | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/11/2021 |  |  | 6/1/2025
PJM | AH1-564 | Rockford II 138 kV |  | IL | Winnebago | Active | ComEd | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-565 | Lemoyne 345kV |  | OH | Wood | Active | ATSI | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-566 | South Bend 500kV |  | PA | Armstrong | Active | APS | 400 | 400 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-567 | University Park 138 kV |  | IL | Will | Active | ComEd | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 9/10/2021 |  |  | 6/1/2025
PJM | AH1-568 | Keen Mountain 138 kV |  | VA | Buchanan | Withdrawn | AEP | 80 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 6/1/2025
PJM | AH1-569 | Broadview - Tangy 138 kV III |  | OH | Union | Active | ATSI | 49.99 | 31.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/1/2024
PJM | AH1-570 | Millersburg 69 kV |  | KY |  | Active | EKPC | 25 | 15.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/1/2024
PJM | AH1-571 | Millersburg 69 kV |  | KY |  | Active | EKPC | 20 | 12.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/1/2024
PJM | AH1-572 | South Morral 69 kV |  | OH | Marion | Active | AEP | 30 | 19.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/1/2024
PJM | AH1-573 | South Morral 69 kV |  | OH | Marion | Active | AEP | 19.99 | 12.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/1/2024
PJM | AH1-574 | Harrington 69kV |  | DE | Kent | Withdrawn | DPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/25/2024
PJM | AH1-575 | Harrington 69kV |  | DE | Kent | Withdrawn | DPL | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/25/2024
PJM | AH1-576 | South Harrington 69kV |  | DE | Kent | Withdrawn | DPL | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/25/2024
PJM | AH1-577 | Tigers 69 kV |  | OH | Wayne | Active | AEP | 70 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 10/15/2028
PJM | AH1-578 | Tigers 69 kV |  | OH | Wayne | Active | AEP | 28 | 28 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 10/15/2028
PJM | AH1-579 | Marysville – Hyatt 345 kV |  | OH | Union | Withdrawn | AEP | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 5/1/2028
PJM | AH1-580 | Nottingham Switch 138 kV |  | OH | Harrison | Active | AEP | 200 | 134 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 5/1/2025
PJM | AH1-581 |  |  | OH | Pickaway | Withdrawn | Dayton | 200 | 134 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 5/1/2025
PJM | AH1-582 | Marysville - Flatlick 765 kV |  | OH | Madison | Withdrawn | AEP | 0 | 146.3 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 5/1/2026
PJM | AH1-583 | Marysville - Flatlick 765 kV |  | OH | Madison | Withdrawn | AEP | 0 | 146.3 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 5/1/2026
PJM | AH1-584 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-585 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-586 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 45 | 45 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-587 | Farmers Valley – Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-588 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 240 | 144 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-589 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 170 | 170 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-590 | Cherry Ridge 66 kV |  | WV | Grant | Active | APS | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-591 | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-592 | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 45 | 45 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2021 |  |  | 12/16/2024
PJM | AH1-593 | Hazelton 138 |  | WV | Preston | Withdrawn | APS | 65 | 39 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/16/2024
PJM | AH1-594 | Hazelton 138kV |  | WV | Preston | Withdrawn | APS | 32 | 32 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/16/2024
PJM | AH1-595 | Fowler Ridge 345 kV |  | IN | Benton | Withdrawn | AEP | 150 | 96.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/3/2025
PJM | AH1-596 | Fowler Ridge 345 kV |  | IN | Benton | Withdrawn | AEP | 125 | 125 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/3/2025
PJM | AH1-597 | LM Troy 138 kV |  | OH | Ashland | Withdrawn | ATSI | 110 | 70.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/3/2025
PJM | AH1-598 | LM Troy 138 kV |  | OH | Ashland | Withdrawn | ATSI | 110 | 110 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 3/3/2025
PJM | AH1-599 |  |  | IL | Lee | Withdrawn | ComEd | 150 | 96 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 3/3/2025
PJM | AH1-600 |  |  | IL | Lee | Withdrawn | ComEd | 110 | 110 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 3/3/2025
PJM | AH1-601 |  |  | IL | Lee | Withdrawn | ComEd | 300 | 192.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 3/3/2025
PJM | AH1-602 |  |  | IL | Lee | Withdrawn | ComEd | 225 | 225 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/13/2021 |  | 3/3/2025
PJM | AH1-603 |  |  | OH | Crawford | Withdrawn | AEP | 200 | 129.1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/14/2021 |  | 3/3/2025
PJM | AH1-604 |  |  | OH | Crawford | Withdrawn | AEP | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/14/2021 |  | 3/3/2025
PJM | AH1-605 |  |  | IN | Union | Withdrawn | AEP | 120 | 77 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/14/2021 |  | 3/3/2025
PJM | AH1-606 |  |  | IN | Union | Withdrawn | AEP | 90 | 90 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 10/14/2021 |  | 3/3/2025
PJM | AH1-607 |  |  | IN | Delaware | Withdrawn | AEP | 119.04 | 71.424 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/19/2021 |  | 4/30/2025
PJM | AH1-608 | Milliron-Brookside 138kV |  | OH | Richland | Withdrawn | ATSI | 49.26 | 29.556 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 10/12/2021 |  | 4/30/2025
PJM | AH1-609 | Milliron-Brookside 138kV |  | OH | Richland | Withdrawn | ATSI | 168.31 | 100.986 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 4/30/2025
PJM | AH1-611 | Perkiomenville 34.5kV |  | PA | Montgomery | Withdrawn | PECO | 7.5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/5/2023 |  | 6/30/2024
PJM | AH1-612 | North Orwell - East Sayre 34.5kV |  | PA | Bradford | Withdrawn | PENELEC | 7.5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 9/7/2023 |  | 6/30/2024
PJM | AH1-613 | Earleys- Suffolk 230kV |  | VA | City of Suffolk | Withdrawn | Dominion | 130 | 130 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 3/22/2024 |  | 10/1/2025
PJM | AH1-614 | Burns 69 kV |  | OH | Clermont | Withdrawn | DEOK | 40 | 40 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/10/2021 | 9/23/2024 |  | 10/1/2025
PJM | AH1-615 | Pine Creek 138 kV |  | PA | Allegheny | Withdrawn | DL | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 10/1/2025
PJM | AH1-616 | Chicago Heights 138 kV |  | IL | Cook | Withdrawn | ComEd | 150 | 150 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 9/19/2024 |  | 10/1/2025
PJM | AH1-617 | Beaver Creek 138 kV |  | KY |  | Active | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2021 |  |  | 9/30/2024
PJM | AH1-618 | Beaver Creek 138 kV |  | KY |  | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/30/2024
PJM | AH1-619 | Beaver Creek 138 kV |  | KY |  | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/30/2024
PJM | AH1-620 | Carville 138kV |  | MD | Queen Anne's | Withdrawn | DPL | 76 | 45.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-621 | Steele-Milford 230kV |  | MD | Allegany | Withdrawn | DPL | 120 | 72 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-622 | Five Fork 115kV |  | PA | York | Withdrawn | PECO | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-623 | South Anna - Desper 230 kV |  | VA | Louisa | Withdrawn | Dominion | 160 | 96 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-624 | Mainesburg-Homer City 345kV |  | PA | Clearfield | Withdrawn | PENELEC | 230 | 138 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-625 | Cowen 138kV |  | WV | Webster | Withdrawn | APS | 250 | 150 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 12/1/2025
PJM | AH1-626 | Ladysmith 230 kV |  | VA | Caroline | Withdrawn | Dominion | 62.5 | 62.5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 1/14/2025 |  | 3/21/2025
PJM | AH1-627 | Ladysmith 230 kV II |  | VA | Caroline | Withdrawn | Dominion | 62.5 | 62.5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 1/14/2025 |  | 3/21/2025
PJM | AH1-629 | Hokes-Grantley 69 kV III |  | PA | York | Withdrawn | ME | 15 | 15 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/11/2021 | 10/18/2021 |  | 9/25/2023
PJM | AH1-630 | Penns Tap-Richfield Tie 69 kV V |  | PA | Snyder | Withdrawn | PPL | 15 | 15 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/11/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-631 | Edinboro South 34.5 kV III |  | PA | Crawford | Withdrawn | PENELEC | 15 | 15 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-632 | Mercersburg-Milnor 34.5 kV III |  | PA | Franklin | Withdrawn | APS | 12 | 12 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2021 | 12/18/2024 |  | 9/25/2023
PJM | AH1-633 | Powerton to Katydid 345 kV |  | IL | Livingston | Withdrawn | ComEd | 288 | 172.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/13/2021 | 12/18/2024 |  | 9/26/2024
PJM | AH1-634 | Indian River 230kV |  | DE | Sussex | Active | DPL | 68 | 17.7 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 9/13/2021 |  |  | 12/31/2024
PJM | AH1-635 |  |  | OH | Champaign | Withdrawn | Dayton | 200 | 134.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/13/2021 | 10/19/2021 |  | 10/15/2024
PJM | AH1-636 |  |  | OH | Champaign | Withdrawn | Dayton | 200 | 134.3 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/13/2021 | 10/19/2021 |  | 10/15/2024
PJM | AH1-637 | Oak Grove 34.5 kV |  | VA | Westmoreland | Active | Dominion | 16 | 9.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/13/2021 |  |  | 12/15/2022
PJM | AH1-638 | Pleasantville 12.47kV |  | NJ | Atlantic | Withdrawn | AEC | 1.625 | 0.6825 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/13/2021 | 8/15/2022 |  | 11/1/2022
PJM | AH1-639 | Lordstown - Mansfield 345 kV |  | OH | Mahoning | Withdrawn | ATSI | 150 | 150 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/13/2021 | 12/18/2024 |  | 10/31/2025
PJM | AH1-640 | Gladys DP - Stonemill 69 kV |  | VA | Campbell | Withdrawn | Dominion | 40 | 40 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/14/2021 | 12/18/2024 |  | 12/3/2025
PJM | AH1-641 | Churchtown - Upper Pittsgrove 138kV |  | NJ | Salem | Active | AEC | 15 | 15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/14/2021 |  |  | 12/31/2023
PJM | AH1-642 | Morgantown - Tompkinsville 69kV |  | MD | Charles | Withdrawn | SMECO | 80 | 80 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/14/2021 | 10/13/2021 |  | 10/31/2023
PJM | AH1-643 | Hewitt Road - Oakville 69kV |  | MD | St. Mary's | Withdrawn | SMECO | 80 | 80 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/14/2021 | 10/14/2021 |  | 10/31/2023
PJM | AH1-644 | Spicewood 138 kV |  | KY |  | Active | AEP | 100 | 65 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/15/2021 |  |  | 1/1/2026
PJM | AH1-645 | Surry - Yadkin 500 kV |  | VA | Isle of Wight | Withdrawn | Dominion | 450 | 450 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/15/2021 | 3/25/2024 |  | 10/1/2025
PJM | AH1-646 | Lake Lynn – Gerards Fort 25 kV |  | PA | Fayette | Withdrawn | APS | 19.9 | 12.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/16/2021 | 8/12/2024 |  | 12/31/2023
PJM | AH1-647 | Greensboro 25 kV |  | PA | Greene | Withdrawn | APS | 19.9 | 12.3 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/17/2021 | 8/12/2024 |  | 12/31/2023
PJM | AH1-648 | Grays Ferry 230kV |  | PA | Philadelphia | Withdrawn | PECO | 5 | 5 | Capacity | Generation Interconnection | Natural Gas | Withdrawn |  |  |  | 9/17/2021 | 8/27/2024 |  | 6/1/2022
PJM | AH1-649 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 60 | 36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 9/18/2024 |  | 12/31/2024
PJM | AH1-650 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 11/21/2024 |  | 12/31/2024
PJM | AH1-651 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/24/2021 | 9/6/2024 |  | 12/31/2024
PJM | AH1-652 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 9/6/2024 |  | 12/31/2024
PJM | AH1-653 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 11/23/2024 |  | 12/31/2025
PJM | AH1-654 | Kincaid 345 kV |  | IL | Christian | Withdrawn | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-655 | SE Canton 138 kV |  | OH | Stark | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/24/2021 | 11/23/2024 |  | 12/31/2025
PJM | AH1-656 | Gary 115kV |  | VA | Lunenburg | Withdrawn | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 6/28/2023 |  | 12/31/2024
PJM | AH1-657 | Nelson 345 kV |  | IL | DeKalb | Withdrawn | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-658 | R. P. Mone 345 kV |  | OH | Van Wert | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 11/23/2024 |  | 12/31/2025
PJM | AH1-659 | Cordova 345 kV |  | IL | Lee | Withdrawn | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/23/2021 | 12/18/2024 |  | 12/31/2024
PJM | AH1-660 | Taylor 69kV |  | DE | Sussex | Withdrawn | DPL | 6.66 | 4.19 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/29/2021 | 2/16/2023 |  | 11/30/2023
PJM | AH1-661 | Philo – Cannelville Switch 138 kV |  | OH | Muskingum | Active | AEP | 15.32 | 15.32 | Capacity | Generation Interconnection | Other | In Progress |  |  |  | 9/29/2021 |  |  | 7/1/2023
PJM | AH1-662 | Wells 69kV |  | DE | Kent | Withdrawn | DPL | 7.66 | 5.3844 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/1/2021 | 2/15/2022 |  | 9/30/2023
PJM | AH1-663 | River EC 138 kV |  | IL | Cook | Withdrawn | ComEd | 57.78 | 57.78 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/30/2021 | 12/18/2024 |  | 5/31/2024
PJM | AH2-001 | Rattlesnake Hill Waste Heat Recovery |  | PA | Susquehanna | Active | PENELEC | 3.6 | 2.9 | Capacity | Generation Interconnection | Other | In Progress |  |  |  | 10/1/2021 |  |  | 12/31/2023
PJM | AH2-002 | Temple Hill - Roseville 69 kV |  | KY | Barren | Active | EKPC | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/2/2021 |  |  | 12/31/2024
PJM | AH2-003 | Hickory Grove 115 kV |  | VA | Halifax | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/2/2021 | 3/26/2024 |  | 5/1/2024
PJM | AH2-004 | Perth – Crystal Hill 115 kV |  | VA | Halifax | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/1/2021 | 12/1/2023 |  | 5/1/2024
PJM | AH2-005 | Pamplin – Willis Tap 115 kV |  | VA | Prince Edward | Withdrawn | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/1/2021 | 2/9/2024 |  | 5/1/2024
PJM | AH2-006 | Harrison - Good Hope 138 kV |  | OH | Pickaway | Active | AEP | 14.234 | 14.234 | Capacity | Generation Interconnection | Other | In Progress |  |  |  | 10/4/2021 |  |  | 6/1/2024
PJM | AH2-007 | Texas Eastern - Jeffersonville 69 kV |  | OH | Fayette | Active | Dayton | 10.12 | 10.12 | Capacity | Generation Interconnection | Other | In Progress |  |  |  | 10/4/2021 |  |  | 6/1/2024
PJM | AH2-008 | Bear Peak East Providence II |  | PA | Bedford | Withdrawn | APS | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/6/2021 | 9/18/2023 |  | 9/15/2023
PJM | AH2-009 | Galion 138 kV V |  | OH | Morrow | Active | ATSI | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/8/2021 |  |  | 12/31/2024
PJM | AH2-010 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/7/2021 |  |  | 12/31/2024
PJM | AH2-011 | National-Tangy 138kV IV |  | OH | Madison | Withdrawn | ATSI | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/9/2021 | 12/1/2023 |  | 12/31/2024
PJM | AH2-012 | Sinai 12.47 kV |  | VA | Halifax | Withdrawn | Dominion | 9.9 | 9.9 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 10/13/2021 | 11/12/2021 |  | 12/31/2022
PJM | AH2-013 | Cartersville 34.5 kV |  | VA | Cumberland | Active | Dominion | 15.996 | 15.996 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 10/12/2021 |  |  | 12/31/2022
PJM | AH2-014 | Crane Solar 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 3.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/15/2021 |  |  | 12/16/2024
PJM | AH2-015 | Nelson 138 kV |  | IL | Lee | Active | ComEd | 110 | 110 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 10/20/2021 |  |  | 3/24/2025
PJM | AH2-016 | Stonycreek 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/21/2021 | 9/18/2023 |  | 5/10/2023
PJM | AH2-017 | Brothersvalley 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/22/2021 | 9/18/2023 |  | 5/15/2023
PJM | AH2-018 | Lawrence 12.47 kV |  | PA | Clearfield | Withdrawn | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/22/2021 | 9/18/2023 |  | 5/15/2023
PJM | AH2-019 |  |  | MD | Allegany | Withdrawn | DPL |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/26/2021 | 12/7/2021 |  | 2/15/2022
PJM | AH2-020 |  |  | PA | Columbia | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/27/2021 | 11/29/2021 |  | 12/29/2023
PJM | AH2-021 | Summer Shade - Barren County 161 kV |  | KY | Barren | Active | EKPC | 150 | 105 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 10/27/2021 |  |  | 11/13/2026
PJM | AH2-022 | Bear Peak West Providence LLC |  | PA | Bedford | Withdrawn | PENELEC | 8.25 | 4.95 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 10/28/2021 | 9/18/2023 |  | 5/15/2023
PJM | AH2-023 | McDowell 12.47 kV |  | PA | Mercer | Active | ATSI | 5 | 3.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/29/2021 |  |  | 12/1/2024
PJM | AH2-024 | Kodiak Solar 13.2 kV |  | PA | Jefferson | Active | PENELEC | 3 | 2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 10/30/2021 |  |  | 12/15/2023
PJM | AH2-025 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 10/29/2021 |  |  | 6/1/2027
PJM | AH2-026 |  |  | VA | City of Richmond | Withdrawn | Dominion | 72 | 72 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 11/2/2021 | 12/1/2021 |  | 9/15/2024
PJM | AH2-028 | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 44 | 44 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 11/2/2021 |  |  | 10/28/2025
PJM | AH2-028A | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/2/2021 |  |  | 10/28/2025
PJM | AH2-029 | Cedarville 12 kV |  | OH | Greene | Withdrawn | Dayton | 18 | 10.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 11/2/2021 | 10/3/2023 |  | 10/30/2025
PJM | AH2-030 | Feagan's Mill 138 kV |  | WV | Jefferson | Active | APS | 90 | 54 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/3/2021 |  |  | 6/1/2025
PJM | AH2-031 | Feagan's Mill 138 kV II |  | WV | Jefferson | Active | APS | 30 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/3/2021 |  |  | 6/1/2025
PJM | AH2-032 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/9/2021 |  |  | 12/31/2026
PJM | AH2-033 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/9/2021 |  |  | 12/31/2027
PJM | AH2-034 | Possum Point 230kV |  | VA | Prince William | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/9/2021 |  |  | 12/31/2028
PJM | AH2-035 | Possum Point 500kV |  | VA | Prince William | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/9/2021 |  |  | 12/31/2028
PJM | AH2-036 | Young 12.47 |  | PA | Bradford | Active | PENELEC | 4.99 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 11/11/2021 |  |  | 11/1/2023
PJM | AH2-037 | Booth 12.47 |  | PA | Fulton | Active | APS | 4.99 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 11/11/2021 |  |  | 11/1/2023
PJM | AH2-038 | Weirton - Arroyo 25 kV |  | WV | Hancock | Active | APS | 10.75 | 5.4395 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/13/2021 |  |  | 12/31/2024
PJM | AH2-039 | Chesapeake - Paw Paw 23 kV |  | WV | Marion | Active | APS | 5.5 | 2.728 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/13/2021 |  |  | 12/31/2024
PJM | AH2-040 | William - Blackwater 69 kV |  | WV | Tucker | Active | APS | 11.5 | 5.7615 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/13/2021 |  |  | 12/31/2024
PJM | AH2-041 | Osage - Collins Ferry 23 kV |  | WV | Monongalia | Active | APS | 18.89 | 9.48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/13/2021 |  |  | 12/31/2023
PJM | AH2-042 | Marlowe - North Martinsburg 34.5 kV |  | WV | Berkeley | Active | APS | 5.75 | 3.6858 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/13/2021 |  |  | 12/31/2024
PJM | AH2-043 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 200 | 140 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 11/19/2021 |  |  | 12/31/2025
PJM | AH2-044 | Clearfield 12.5 kV |  | PA | Clearfield | Active | APS | 5 | 3.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/30/2021 |  |  | 7/1/2024
PJM | AH2-045 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 40 | 40 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 12/16/2021 |  |  | 12/15/2025
PJM | AH2-046 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/16/2021 |  |  | 12/15/2025
PJM | AH2-048 | Bayview 69kV |  | VA | Northampton | Active | ODEC | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/20/2021 |  |  | 6/2/2025
PJM | AH2-049 | Crisfield 69kV |  | MD | Somerset | Active | DPL | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/20/2021 |  |  | 6/2/2025
PJM | AH2-050 | Tasley 69kV |  | VA | Accomack | Active | ODEC | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/19/2021 |  |  | 6/2/2025
PJM | AH2-051 | Edge Moore 230kV |  | DE | New Castle | Active | DPL | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/20/2021 |  |  | 6/2/2025
PJM | AH2-052 | New Hope 12.47 kV |  | MD | Allegany | Active | DPL | 1.98 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 12/21/2021 |  |  | 12/2/2022
PJM | AH2-053 | Mardela Springs 12.47 kV |  | MD | Wicomico | Active | DPL | 1.98 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 12/22/2021 |  |  | 12/2/2022
PJM | AH2-054 | Edgewood 12.47 kV I |  | MD | Wicomico | Active | DPL | 1.98 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 12/21/2021 |  |  | 12/2/2022
PJM | AH2-055 | TBD 69kV |  | MD | Unknown | Active | DPL | 0.99 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 12/22/2021 |  |  | 2/15/2022
PJM | AH2-056 | Chesterfield 230 kV II |  | VA | Chesterfield | Active | Dominion | 0 | 36 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/24/2021 |  |  | 12/1/2025
PJM | AH2-057 | Scottsville - CVEC Delivery Point 46 kV |  | VA | Buckingham | Active | AEP | 29.9 | 17.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/23/2021 |  |  | 12/1/2025
PJM | AH2-058 | Possum Point 115 kV |  | VA | Prince William | Active | Dominion | 30 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/24/2021 |  |  | 12/1/2026
PJM | AH2-059 | Possum Point 115 kV II |  | VA | Prince William | Active | Dominion | 30 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/24/2021 |  |  | 12/1/2027
PJM | AH2-060 | Possum Point 230 kV |  | VA | Prince William | Active | Dominion | 55 | 55 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/24/2021 |  |  | 12/1/2027
PJM | AH2-061 | Possum Point 230 kV II |  | VA | Prince William | Active | Dominion | 55 | 55 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/23/2021 |  |  | 12/1/2028
PJM | AH2-062 | TBD 34kV |  | PA | Chester | Active | PECO | 5 | 3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/31/2021 |  |  | 5/1/2023
PJM | AH2-063 | North Ramsey 23 kV |  | PA | Beaver | Active | DL | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/30/2021 |  |  | 12/31/2023
PJM | AH2-064 | South Ramsey 23 kV |  | PA | Beaver | Active | DL | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/31/2021 |  |  | 12/31/2023
PJM | AH2-065 | TBD 69kV |  | MD | Prince George's | Active | DPL | 1.992 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 12/31/2021 |  |  | 12/1/2022
PJM | AH2-066 | Jefferson 12.5 kV |  | PA | Jefferson | Active | PENELEC | 5 | 3.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/4/2022 |  |  | 12/15/2023
PJM | AH2-067 | Mount Rose 13 kV |  | IL | Cook | Withdrawn | PSEG | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/12/2022 | 3/8/2022 |  | 12/29/2023
PJM | AH2-068 | Pemberville - West End Fostoria 69 kV |  | OH | Wood | Active | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/13/2022 |  |  | 12/31/2027
PJM | AH2-069 | JAckson Ferry - Progress Park 138 kV |  | VA | Wythe | Active | AEP | 250 | 150 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/13/2022 |  |  | 5/30/2025
PJM | AH2-070 | Edgewood 12.47 kV II |  | MD | Wicomico | Active | DPL | 1.98 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 1/19/2022 |  |  | 1/27/2023
PJM | AH2-071 | Edgewood 12.47 kV III |  | MD | Wicomico | Active | DPL | 1.98 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 1/19/2022 |  |  | 1/27/2023
PJM | AH2-072 | Damascus 69 kV |  | VA | Washington | Active | AEP | 62.1 | 62.1 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/21/2022 |  |  | 1/1/2025
PJM | AH2-073 | Ashtabula County PV Project 2 |  | OH | Ashtabula | Active | ATSI | 10 | 2.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/22/2022 |  |  | 9/14/2024
PJM | AH2-074 | Ashtabula County PV Project 1 |  | OH | Ashtabula | Active | ATSI | 10 | 2.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/22/2022 |  |  | 9/14/2024
PJM | AH2-075 | Hampton VA 2 |  | VA | City of Hampton | Active | Dominion | 29.12 | 29.12 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/21/2022 |  |  | 7/1/2024
PJM | AH2-076 | Bonneyman - Softshell 138 kV |  | KY | Perry | Active | AEP | 52.5 | 48.17 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 1/26/2022 |  |  | 12/31/2023
PJM | AH2-077 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/27/2022 |  |  | 6/1/2027
PJM | AH2-078 | Dryburg - Chase City 230 kV |  | VA | Charlotte | Active | Dominion | 99.67 | 59.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/27/2022 |  |  | 1/3/2025
PJM | AH2-079 |  |  | VA | Charlotte | Withdrawn | Dominion | 69 | 69 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 1/28/2022 | 2/28/2022 |  | 1/3/2025
PJM | AH2-080 | Brunswick - Gasburg 69 kV |  | VA | Brunswick | Active | Dominion | 52.65 | 31.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/28/2022 |  |  | 1/3/2025
PJM | AH2-081 | Bentley Farms 69 kV |  | OH | Fayette | Active | Dayton | 35.5 | 21.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/27/2022 |  |  | 9/19/2025
PJM | AH2-082 | New Holland - Washington Courthouse 69 kV |  | OH | Fayette | Active | Dayton | 33.25 | 19.95 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/27/2022 |  |  | 1/3/2025
PJM | AH2-083 | Correctional |  | VA | Caroline | Active | Dominion | 140 | 140 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/27/2022 |  |  | 6/1/2027
PJM | AH2-084 | Sowego |  | VA | Fauquier | Active | Dominion | 125 | 125 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/28/2022 |  |  | 6/1/2027
PJM | AH2-085 | Byron-Wayne 345 kV |  | IL | DeKalb | Active | ComEd | 145.335 | 87.201 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/28/2022 |  |  | 11/11/2026
PJM | AH2-086 | Byron – Wayne 345 kV |  | IL | Ogle | Active | ComEd | 0 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2022 |  |  | 12/31/2025
PJM | AH2-087 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 0 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/31/2022 |  |  | 12/31/2025
PJM | AH2-088 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 0 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2022 |  |  | 12/31/2025
PJM | AH2-089 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 0 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/31/2022 |  |  | 12/31/2027
PJM | AH2-090 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 0 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/31/2022 |  |  | 12/31/2024
PJM | AH2-091 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 0 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/31/2022 |  |  | 12/31/2026
PJM | AH2-092 | Kidds Store-Sherwood 115 kV |  | VA | Albemarle | Withdrawn | Dominion | 0 | 32 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/1/2022 | 3/9/2022 |  | 12/31/2026
PJM | AH2-093 | Jasper 69 kV |  | OH | Greene | Active | Dayton | 32 | 32 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 1/31/2022 |  |  | 12/31/2025
PJM | AH2-094 | Lakeville 12 kV II |  | PA | Wayne | Active | PPL | 4.95 | 2.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/31/2022 |  |  | 5/5/2023
PJM | AH2-095 | Crawford 13.8 kV |  | PA | Crawford | Active | PENELEC | 3.3 | 2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/31/2022 |  |  | 7/13/2022
PJM | AH2-096 | West Cambridge - Airey 69 kV |  | MD | Dorchester | Active | DPL | 19.5 | 8.19 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/1/2022 |  |  | 5/1/2023
PJM | AH2-100 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/31/2022 |  |  | 12/29/2023
PJM | AH2-101 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/31/2022 |  |  | 12/29/2023
PJM | AH2-102 | Blaine - Roanoke 138 kV |  | VA | Franklin | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 1/31/2022 |  |  | 5/4/2026
PJM | AH2-103 | Gans - South Union 138 kV |  | PA | Fayette | Active | APS | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2022 |  |  | 5/4/2026
PJM | AH2-104 | Willis Mts- Farmville 115kV |  | VA | Cumberland | Active | Dominion | 72 | 39.2 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/4/2022 |  |  | 11/1/2024
PJM | AH2-105 | Merck 34.5 kV |  | VA | Rockingham | Active | Dominion | 16 | 9.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/4/2022 |  |  | 1/1/2024
PJM | AH2-106 | Wellsville 345 kV |  | OH | Columbiana | Active | ATSI | 58 | 69 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 2/4/2022 |  |  | 2/28/2022
PJM | AH2-107 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 69 | 69 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/12/2022 |  |  | 12/31/2024
PJM | AH2-108 | Potter-Harlan 69 kV |  | PA | Lawrence | Withdrawn | ATSI | 35 | 21 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/11/2022 | 3/18/2022 |  | 6/1/2026
PJM | AH2-109 | TBD 12.47kV |  | NJ | Unknown | Active | AEC | 1.5 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 2/16/2022 |  |  | 12/1/2022
PJM | AH2-110 | Wells - Harrington 69 kV |  | PA | Fulton | Withdrawn | DPL | 5 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/19/2022 | 3/14/2022 |  | 12/31/2023
PJM | AH2-111 | Hannibal 138 kV |  | OH | Monroe | Active | AEP | 20 | 20 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 2/19/2022 |  |  | 6/30/2022
PJM | AH2-112 | Olive - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 250 | 170 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/22/2022 |  |  | 2/27/2026
PJM | AH2-113 | Dresden – Pontiac Midpoint 345kV |  | IL | Livingston | Active | ComEd | 250 | 170 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/22/2022 |  |  | 2/27/2026
PJM | AH2-115 | Mansfield - Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 85 | 50 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2022 |  |  | 1/1/2026
PJM | AH2-116 | Garman - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 85 | 50 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2022 |  |  | 1/1/2026
PJM | AH2-117 | Dorton - Henry Clay 46 kV |  | KY | Pike | Active | AEP | 30 | 18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2022 |  |  | 12/31/2026
PJM | AH2-118 | Ripley Switch – Grayton 69kV |  | MD | Charles | Withdrawn | PEPCO | 100 | 85 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 2/23/2022 | 1/9/2024 |  | 12/1/2024
PJM | AH2-119 | Morgan Street - Titusville 34.5 kV |  | PA | Crawford | Active | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/25/2022 |  |  | 12/30/2025
PJM | AH2-120 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/26/2022 |  |  | 12/1/2028
PJM | AH2-121 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/26/2022 |  |  | 12/1/2028
PJM | AH2-122 | Nelson-Lee County 345 kV |  | IL | Lee | Active | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/26/2022 |  |  | 12/1/2028
PJM | AH2-123 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/26/2022 |  |  | 12/1/2028
PJM | AH2-124 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/26/2022 |  |  | 12/1/2028
PJM | AH2-125 | Kensington 138 kV |  | KY |  | Active | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/26/2022 |  |  | 12/1/2028
PJM | AH2-126 | Tidd 138 kV |  | OH | Jefferson | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/25/2022 |  |  | 10/31/2026
PJM | AH2-127 | Burlington 26 kV |  | NJ | Burlington | Active | PSEG | 15 | 18 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/25/2022 |  |  | 9/19/2023
PJM | AH2-128 | Stone Solar 34.5 kV |  | PA | Clarion | Active | APS | 8 | 5.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2022 |  |  | 5/29/2026
PJM | AH2-129 | Piney - Timblin 115 kV |  | PA | Armstrong | Active | APS | 36 | 23.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2022 |  |  | 5/29/2026
PJM | AH2-130 | Clark Co - Spencer Road 138 kV |  | KY |  | Active | EKPC | 85 | 50 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2022 |  |  | 1/1/2026
PJM | AH2-131 | Bridgeport 230kV |  | NJ | Gloucester | Active | AEC | 0 | 103.7 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/28/2022 |  |  | 3/1/2025
PJM | AH2-132 | Chambers 230kV |  | NJ | Salem | Active | AEC | 0 | 117 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/1/2022 |  |  | 6/1/2024
PJM | AH2-133 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/1/2022 |  |  | 3/1/2027
PJM | AH2-134 | TBD 34.5 kV |  | WV | Kanawha | Withdrawn | DPL | 4.95 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/1/2022 | 3/21/2022 |  | 12/31/2023
PJM | AH2-135 | Harwood- McAdoo 69 kV |  | PA | Luzerne | Active | PPL | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2022 |  |  | 6/19/2025
PJM | AH2-136 | Dunnsville 345 kV |  | VA | Essex | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2022 |  |  | 12/1/2024
PJM | AH2-137 | Monroe - Coolwell 12.47 kV |  | VA | Amherst | Active | AEP | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2022 |  |  | 12/1/2026
PJM | AH2-138 | Arrington Circuit 12.47 kV |  | VA | Nelson | Active | AEP | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2022 |  |  | 12/1/2026
PJM | AH2-139 |  |  | VA | Prince George | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/28/2022 | 4/14/2022 |  | 12/31/2024
PJM | AH2-140 |  |  | VA | Greensville | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/28/2022 | 4/14/2022 |  | 12/31/2024
PJM | AH2-141 |  |  | VA | Prince George | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/28/2022 | 4/14/2022 |  | 12/31/2024
PJM | AH2-142 |  |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/28/2022 | 4/14/2022 |  | 12/31/2024
PJM | AH2-143 |  |  | VA | City of Suffolk | Withdrawn | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 2/28/2022 | 4/14/2022 |  | 12/31/2024
PJM | AH2-144 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/28/2022 |  |  | 6/1/2027
PJM | AH2-145 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 52.3 | 52.3 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/28/2022 |  |  | 6/1/2027
PJM | AH2-146 | Adams - Seaman 69 kV |  | OH | Adams | Active | AEP | 87.2 | 52.3 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/28/2022 |  |  | 12/30/2027
PJM | AH2-147 | Marysville - Sorenson 765 kV |  | OH | Logan | Withdrawn | AEP | 119 | 108.4 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/1/2022 | 7/7/2023 |  | 2/25/2027
PJM | AH2-148 | East Lima - Marysville 345 kV |  | OH | Union | Active | AEP | 152 | 143.2 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/28/2022 |  |  | 2/25/2027
PJM | AH2-149 | Stinger - Valley 138 kV |  | MI | Van Buren | Active | AEP | 150 | 120 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/28/2022 |  |  | 6/29/2026
PJM | AH2-150 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 0 | 320 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/28/2022 |  |  | 12/1/2024
PJM | AH2-151 | SedgeHill - Person 230kV |  | VA | Halifax | Active | Dominion | 35 | 21 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/28/2022 |  |  | 6/1/2025
PJM | AH2-152 | Effort Mountain-Gilbert 138 kV IV |  | PA | Monroe | Withdrawn | PPL | 44.8 | 26.88 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/1/2022 | 8/26/2024 |  | 6/1/2025
PJM | AH2-153 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 180 | 140 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/28/2022 |  |  | 12/31/2024
PJM | AH2-154 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 118 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 2/28/2022 |  |  | 12/31/2024
PJM | AH2-155 | Lyons-Allen Jct 138 kV |  | OH | Fulton | Active | ATSI | 95 | 57 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2022 |  |  | 12/31/2025
PJM | AH2-156 | Buckeye P-Wakeman 69 kV |  | OH | Huron | Active | ATSI | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2022 |  |  | 12/31/2025
PJM | AH2-157 | Hooversville-Somerset 23 kV |  | PA | Somerset | Active | PENELEC | 12 | 7.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2022 |  |  | 12/31/2025
PJM | AH2-158 | Somerset-Hooversville 115 kV |  | PA | Somerset | Active | PENELEC | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2022 |  |  | 12/31/2025
PJM | AH2-159 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 49 | 29.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2022 |  |  | 12/31/2025
PJM | AH2-160 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2022 |  |  | 12/31/2025
PJM | AH2-161 | Prospect 25 kV |  | PA | Butler | Withdrawn | APS | 18.8 | 12.3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/4/2022 | 8/13/2024 |  | 12/31/2024
PJM | AH2-162 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Active | BGE | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/4/2022 |  |  | 3/1/2026
PJM | AH2-163 | Kittanning - Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 19.8 | 7.98 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2022 |  |  | 3/1/2026
PJM | AH2-164 | Chatfield 69 kV |  | OH | Crawford | Active | AEP | 85 | 50 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2022 |  |  | 1/1/2026
PJM | AH2-165 | Fayette - Lyons 138 kV |  | OH | Fulton | Active | ATSI | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2022 |  |  | 12/31/2025
PJM | AH2-166 | Lyons 138 kV |  | OH | Fulton | Active | ATSI | 45 | 27 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2022 |  |  | 12/31/2025
PJM | AH2-167 | Campbell Tap-McDowell 69 kV |  | PA | Mercer | Withdrawn | ATSI | 6.6 | 0 | Energy | Generation Interconnection | Diesel | Withdrawn |  |  |  | 3/5/2022 | 5/6/2022 |  | 7/1/2022
PJM | AH2-168 | Beatty - MT Hope 345 kV |  | OH | Madison | Active | ATSI | 185 | 111 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2022 |  |  | 12/31/2025
PJM | AH2-169 | Thornville - Pleasantville 69 kV |  | OH | Perry | Active | AEP | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2022 |  |  | 12/31/2025
PJM | AH2-170 | Byron 345 |  | IL | Will | Withdrawn | ComEd | 140 | 84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/7/2022 | 1/15/2025 |  | 12/31/2026
PJM | AH2-171 | Davis Creek 345 kV |  | IL | Kankakee | Withdrawn | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/7/2022 | 1/15/2025 |  | 12/31/2026
PJM | AH2-172 | Wilton 345 kV |  | IL | Will | Withdrawn | ComEd | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/7/2022 | 1/15/2025 |  | 12/31/2026
PJM | AH2-173 | Maryland 138 kV |  | IL | Ogle | Withdrawn | ComEd | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/7/2022 | 1/15/2025 |  | 12/31/2026
PJM | AH2-174 | PA- Fort Hill 12.47 kV |  | OH | Perry | Withdrawn | APS | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 1/3/2024 |  | 6/21/2024
PJM | AH2-175 | Montgomery 12 kV |  |  |  | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 1/5/2024 |  | 6/21/2024
PJM | AH2-176 | Hughesville 12 kV |  |  |  | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/8/2022 | 1/5/2024 |  | 6/21/2024
PJM | AH2-177 | Hamlin 12 kV |  |  |  | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/8/2022 | 1/5/2024 |  | 6/21/2024
PJM | AH2-178 | Trexlertown 12 kV |  |  |  | Withdrawn | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/8/2022 | 2/20/2024 |  | 6/21/2024
PJM | AH2-179 | Millville 12 kV |  |  |  | Withdrawn | PPL | 5 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/8/2022 | 1/5/2024 |  | 6/21/2024
PJM | AH2-180 | Rohrsburg 12 kV |  |  |  | Withdrawn | PPL | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/8/2022 | 1/5/2024 |  | 6/21/2024
PJM | AH2-181 | PA-Schwoyer 13.2 kV |  | PA | Mercer | Active | ME | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/8/2022 |  |  | 6/21/2024
PJM | AH2-182 | PA-Oknefski 12.47 kV |  | VA | Rockingham | Withdrawn | APS | 3 |  | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/7/2022 | 1/3/2024 |  | 6/21/2024
PJM | AH2-183 | PA-Montmorenci 12.47 kV |  | IL | Ogle | Withdrawn | APS | 3 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/8/2022 | 1/3/2024 |  | 6/21/2024
PJM | AH2-184 | PA- Shadeland 13 kV |  | PA | Crawford | Withdrawn | PENELEC | 2 |  | Energy | Generation Interconnection | Storage; Solar | Withdrawn |  |  |  | 3/7/2022 | 2/20/2024 |  | 6/21/2024
PJM | AH2-185 | PA-Beaver 13.2 kV |  | PA | Franklin | Withdrawn | PENELEC | 2 | 0 | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/7/2022 | 1/3/2024 |  | 6/21/2024
PJM | AH2-186 | Enfield 12kV |  | VA | King William | Withdrawn | Dominion | 20 | 13.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2022 | 5/17/2022 |  | 5/29/2026
PJM | AH2-187 | Burma – Seminole Road Junction 25 kV |  | PA | Clarion | Active | APS | 20 | 13.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 5/30/2025
PJM | AH2-188 | Youst Solar |  | PA | Tioga | Withdrawn | PENELEC | 35 | 21 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2022 | 6/3/2022 |  | 12/31/2025
PJM | AH2-189 | Fearnley Solar 34.5 kV |  | PA | Susquehanna | Active | PENELEC | 12 | 7.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2025
PJM | AH2-190 | Higgins Run Solar |  | PA | Somerset | Active | PENELEC | 12 | 7.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2025
PJM | AH2-191 | Hopkins 138 kV |  | WV |  | Active | AEP | 95 | 63 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/8/2022 |  |  | 3/10/2024
PJM | AH2-192 | Wharton 138 kV |  | WV |  | Active | AEP | 95 | 63 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/8/2022 |  |  | 3/10/2024
PJM | AH2-193 | Pax Branch 138 kV |  | WV |  | Active | AEP | 70 | 46 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/8/2022 |  |  | 3/10/2024
PJM | AH2-194 | Bergen 138kV |  | NJ | Bergen | Active | PSEG | 0 | 20 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/9/2022 |  |  | 4/30/2026
PJM | AH2-195 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 65 | 39 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2022 |  |  | 10/29/2027
PJM | AH2-196 |  |  | NJ | Monmouth | Withdrawn | JCPL | 1600 | 281.6 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/8/2022 | 4/7/2022 |  | 12/31/2031
PJM | AH2-197 | North Huntley - Pleasant Valley 138 kV |  | IL | McHenry | Active | ComEd | 50 | 40 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/8/2022 |  |  | 12/31/2025
PJM | AH2-198 | Mt. Hermon 69 kV |  | MD | Wicomico | Active | DPL | 74.715 | 53.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2022 |  |  | 6/30/2026
PJM | AH2-199 | Shorewood 138 kV |  | IL | Will | Active | ComEd | 51.7 | 36.3 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/8/2022 |  |  | 6/30/2026
PJM | AH2-200 | TBD 12kV |  | NJ |  | Withdrawn | AEC | 3 | 3 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 4/8/2024 |  | 1/1/2025
PJM | AH2-201 | TBD 12kV |  | NJ | Cumberland | Withdrawn | AEC | 5 | 5 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 1/3/2024 |  | 1/1/2025
PJM | AH2-202 | Hunterdon 34.5 kV |  | NJ | Hunterdon | Withdrawn | JCPL | 5 | 5 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 1/3/2024 |  | 1/1/2025
PJM | AH2-204 | Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 170 | 170 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-205 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 3/31/2026
PJM | AH2-206 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 3/31/2026
PJM | AH2-207 | Hopkins 138 kV |  | WV |  | Active | AEP | 85 | 57 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 3/10/2024
PJM | AH2-208 |  |  | VA | Lee | Withdrawn | Dominion | 45 | 31 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 3/17/2022 |  | 3/10/2024
PJM | AH2-209 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 95 | 63 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 3/10/2024
PJM | AH2-210 | Stillwell - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 78 | 78 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2025
PJM | AH2-211 | Olive - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 110 | 110 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2025
PJM | AH2-212 | Cardington 138 kV |  | OH | Madison | Active | ATSI | 115 | 69 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-213 | London 138 kV |  | IN | Randolph | Active | ATSI | 140 | 84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-214 |  |  | OH | Pickaway | Withdrawn | AEP | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2022 | 4/1/2022 |  | 12/31/2026
PJM | AH2-215 | Midway 138 kV |  | OH | Henry | Active | ATSI | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-216 |  |  | OH | Miami | Withdrawn | Dayton | 200 | 120 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2022 | 4/1/2022 |  | 12/31/2026
PJM | AH2-217 | Cardington 138 kV II |  | OH | Morrow | Active | ATSI | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-218 | London 138 kV II |  | OH | Morrow | Active | ATSI | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-219 |  |  | OH | Pickaway | Withdrawn | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/9/2022 | 4/1/2022 |  | 12/31/2026
PJM | AH2-220 | Midway 138 kV |  | OH | Henry | Active | ATSI | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-221 |  |  | OH | Miami | Withdrawn | Dayton | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/9/2022 | 4/1/2022 |  | 12/31/2026
PJM | AH2-222 | Millersburg 69 kV |  | KY |  | Withdrawn | EKPC | 60 | 36 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2022 | 1/14/2025 |  | 12/31/2026
PJM | AH2-223 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 50 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2025
PJM | AH2-224 | Millersburg 69 kV |  | KY |  | Withdrawn | EKPC | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/9/2022 | 1/14/2025 |  | 12/31/2026
PJM | AH2-225 | Southampton- Handsom 115kV |  | VA | Southampton | Withdrawn | Dominion | 125 | 125 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/9/2022 | 10/13/2022 |  | 12/31/2027
PJM | AH2-226 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 175 | 175 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2027
PJM | AH2-227 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/27/2026
PJM | AH2-228 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-229 | Bedforth North 115 kV |  | PA | Bedford | Active | PENELEC | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2027
PJM | AH2-230 | Gardners 115 kV |  | PA | Adams | Active | ME | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2027
PJM | AH2-232 |  |  | VA | Rockingham | Withdrawn | Dominion | 25 | 25 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/9/2022 | 4/15/2022 |  | 12/31/2027
PJM | AH2-233 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2026
PJM | AH2-234 | W Dekalb 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2027
PJM | AH2-235 | Orrtana 115 kV |  | PA | Adams | Active | ME | 125 | 125 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2027
PJM | AH2-236 | McDowell 138 kV |  | PA | Mercer | Active | ATSI | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2027
PJM | AH2-237 | Adams 138 kV |  | IN | Wells | Withdrawn | AEP | 125 | 75 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2022 | 1/17/2025 |  | 12/31/2026
PJM | AH2-238 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2027
PJM | AH2-239 | Trumbull138 kV |  | OH | Trumbull | Active | ATSI | 49 | 46.4 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/7/2027
PJM | AH2-240 | Oceanview 230 kV |  | NJ | Monmouth | Withdrawn | JCPL | 1493 | 424.872 | Capacity | Generation Interconnection | Offshore Wind | Withdrawn |  |  |  | 3/10/2022 | 4/1/2022 |  | 11/1/2027
PJM | AH2-241 | Loudoun 115kV |  | VA | City of Chesapeake | Active | Dominion | 45 | 45 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/1/2027
PJM | AH2-242 | Crown - New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 45 | 40.5 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 3/8/2027
PJM | AH2-243 | South Summitville 69 kV |  | IN | Madison | Withdrawn | AEP | 43 | 25.78 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/9/2022 | 8/30/2024 |  | 10/27/2028
PJM | AH2-244 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 9/29/2023
PJM | AH2-245 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 9/29/2023
PJM | AH2-246 | Polyester S/S 230kV |  | VA | Prince George | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2025
PJM | AH2-247 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 83.2836 | 14.6579 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2028
PJM | AH2-248 | Carrolltown 46 kV |  | PA | Cambria | Active | PENELEC | 83.2592 | 14.6536 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2028
PJM | AH2-249 | Busseyville 138 kV |  | KY | Lawrence | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 12/22/2027
PJM | AH2-250 | TBD 13.2 kV |  | PA | Bucks | Withdrawn | PECO | 9.25 | 3.885 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 7/23/2024 |  | 2/28/2024
PJM | AH2-251 | PA- Shorb Mill 13 kV |  | VA | Rockingham | Withdrawn | ME | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/11/2022 | 1/3/2024 |  | 6/21/2024
PJM | AH2-252 | Middleburg 12 kV |  |  |  | Active | PPL | 2 | 0 | Energy | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 6/21/2024
PJM | AH2-253 | Beaver Valley - Crescent 138 kV |  | PA | Beaver | Active | DL | 70 | 65 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 11/25/2025
PJM | AH2-254 |  |  | NJ | Mercer | Withdrawn | PSEG | 5 | 5 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 4/1/2022 |  | 1/1/2025
PJM | AH2-255 |  |  | WV | Preston | Withdrawn | APS | 70 | 65 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/9/2022 | 4/13/2022 |  | 11/25/2025
PJM | AH2-256 | Wheelabrator Frackville-Gilberton 69 kV II |  | PA | Schuylkill | Active | PPL | 50 | 40 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 12/31/2025
PJM | AH2-257 | Dequine - Eugene 345 kV |  | IN | Vermillion | Active | AEP | 400 | 240 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 9/29/2024
PJM | AH2-258 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 9/27/2024
PJM | AH2-259 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 9/27/2024
PJM | AH2-260 | Garrett - Albright 138 kV |  | WV | Preston | Active | APS | 70 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 6/30/2026
PJM | AH2-261 | Garrett - Albright 138 kV |  | WV | Preston | Active | APS | 28 | 28 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 6/30/2026
PJM | AH2-262 | Catoctin-Carroll 138 kV |  | MD | Frederick | Active | APS | 17 | 10.2 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/1/2026
PJM | AH2-263 | Marion Co - Marion Co industrial 161 kV |  | KY | Marion | Active | EKPC | 25.8 | 15.48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 3/1/2026
PJM | AH2-264 | Logtown - North Delphos 138 kV |  | OH | Van Wert | Active | AEP | 115 | 69 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2022 |  |  | 3/1/2026
PJM | AH2-265 | Oak Grove - Hawkins Gate 230kV |  | MD | Charles | Active | PEPCO | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/9/2022 |  |  | 3/1/2026
PJM | AH2-266 | Hughesville-Cedarville 69kV |  | MD | Charles | Active | SMECO | 25 | 15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 3/1/2026
PJM | AH2-267 | Modera - BioEnergy Tap 115 kV |  | PA | Clearfield | Active | PENELEC | 100 | 85 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2022 |  |  | 7/1/2025
PJM | AH2-268 | Sapony 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 37 | 33.7 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 7/1/2025
PJM | AH2-269 | Lakewood 230 kV |  | NJ | Ocean | Active | JCPL | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 6/1/2026
PJM | AH2-269A | Burches Hill-Chalk Point 500kV |  | MD | Prince George's | Active | PEPCO | 45 | 45 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/10/2022 |  |  | 11/2/2026
PJM | AH2-270 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 300 | 51 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2026
PJM | AH2-271 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2026
PJM | AH2-272 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2027
PJM | AH2-273 | Eagle Road 138 kV |  | OH | Union | Withdrawn | Dayton | 150 | 90 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/11/2022 | 1/14/2025 |  | 12/31/2026
PJM | AH2-274 | Eagle Road 138 kV |  | OH | Union | Withdrawn | Dayton | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/11/2022 | 1/14/2025 |  | 12/31/2026
PJM | AH2-275 | Carrollton Solar 138 kV |  | OH | Carroll | Withdrawn | ATSI | 100 | 42 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 1/21/2025 |  | 3/3/2023
PJM | AH2-276 | Second Fork 69 kV |  | KY | Pike | Active | AEP | 40 | 28 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/10/2024
PJM | AH2-277 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 60 | 42 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/10/2024
PJM | AH2-278 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/10/2024
PJM | AH2-279 | Whiteley 138 kV |  | PA | Greene | Active | APS | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/10/2024
PJM | AH2-280 | Noblesville - Fall Creek 345 kV |  | IN | Hamilton | Withdrawn | AEP | 120 | 72 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/11/2022 | 6/1/2022 |  | 5/31/2025
PJM | AH2-281 | Trego 34.5 kV |  | VA | Greensville | Active | Dominion | 26 | 15.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/30/2024
PJM | AH2-282 | Burnworth 138 kV |  | IN | Noble | Withdrawn | AEP | 75 | 75 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/10/2022 | 11/3/2023 |  | 12/1/2026
PJM | AH2-283 |  |  | OH | Morgan | Withdrawn | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/10/2022 | 4/12/2022 |  | 12/1/2026
PJM | AH2-284 | Adams 138 kV |  | OH | Adams | Withdrawn | AEP | 49.9 | 49.9 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/10/2022 | 12/13/2024 |  | 12/1/2026
PJM | AH2-285 |  |  | NJ | Middlesex | Withdrawn | JCPL | 1400 | 378 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/11/2022 | 4/8/2022 |  | 12/31/2029
PJM | AH2-287 |  |  | NJ | Monmouth | Withdrawn | JCPL | 600 | 162 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/10/2022 | 4/8/2022 |  | 12/31/2029
PJM | AH2-288 | Napoleon Muni 138 kV |  | OH | Henry | Active | AMPT | 0 | 82.4 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/1/2024
PJM | AH2-289 | East Fayette 138 kV II |  | OH | Fulton | Active | ATSI | 0 | 79.6 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/1/2024
PJM | AH2-290 | Sandwich 138 kV |  | IL | DeKalb | Active | ComEd | 0 | 34.4 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-291 | Rawlings-Clover 500kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 6/1/2026
PJM | AH2-292 | Bear Rock 230 kV |  | PA | Cambria | Active | PENELEC | 76.95 | 13.6 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-293 | Gilbert - Morris Park 115 kV |  | NJ | Warren | Withdrawn | JCPL | 50 | 34 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/11/2022 | 4/12/2023 |  | 6/30/2025
PJM | AH2-294 | Mazon Blue - Lasalle 138 kV |  | IL | Grundy | Withdrawn | ComEd | 40 | 29.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/11/2022 | 12/13/2024 |  | 6/1/2026
PJM | AH2-295 | Emerald 25 kV |  | PA | Greene | Active | APS | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 9/15/2025
PJM | AH2-296 |  |  | IL | Cook | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-297 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-298 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-299 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-300 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-301 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-302 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-303 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-304 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-305 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-306 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-307 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-308 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-309 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-310 |  |  | VA | City of Chesapeake | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-311 |  |  | IL | Cook | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-312 |  |  | IL | Cook | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-313 |  |  | IL | Cook | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-314 |  |  | IL | Cook | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-315 |  |  | IL | Cook | Withdrawn | PSEG |  |  | Energy | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/6/2022 |  | 12/1/2023
PJM | AH2-316 | Somerset 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 8/7/2024 |  | 3/29/2024
PJM | AH2-317 | Fredericksburg - North Lebanon 13.2 kV |  | PA | Lebanon | Withdrawn | ME | 10 | 6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 8/7/2024 |  | 3/29/2024
PJM | AH2-318 | Corry East 34.5 kV |  | PA | Warren | Active | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 3/29/2024
PJM | AH2-319 | Milan 34.5 kV |  | PA | Bradford | Withdrawn | PENELEC | 7.5 | 4.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 8/7/2024 |  | 3/29/2024
PJM | AH2-320 | Revloc 34.5 kV |  | PA | Cambria | Active | PENELEC | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 3/29/2024
PJM | AH2-321 | Cooper 34.5 kV |  | PA | York | Withdrawn | ME | 5 | 3 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 8/7/2024 |  | 3/29/2024
PJM | AH2-322 | East Danville-Smith Mountain 138 kV |  | VA | Pittsylvania | Active | AEP | 290 | 174 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2022 |  |  | 6/1/2025
PJM | AH2-330 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/11/2022 |  |  | 3/1/2027
PJM | AH2-331 | North Delphos - Logtown 138 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/31/2027
PJM | AH2-332 | Talbert 230kV |  | MD | Prince George's | Active | PEPCO | 115 | 115 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-333 | Orchard 230kV |  | NJ | Salem | Active | AEC | 415 | 415 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/11/2022 |  |  | 12/31/2025
PJM | AH2-334 | New Freedom 230 kV |  | NJ | Camden | Active | PSEG | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-335 | Roundtop 115 kV |  | PA | York | Active | ME | 130 | 130 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-336 | Kenney - Mt Olive 69 kV |  | MD | Worcester | Withdrawn | DPL | 70 | 70 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/10/2022 | 4/15/2022 |  | 2/27/2026
PJM | AH2-337 | Talbot 69 kV |  | MD | Worcester | Active | DPL | 100 | 80 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 2/27/2026
PJM | AH2-338 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 160 | 96 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 7/30/2027
PJM | AH2-339 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 0 | 64 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 7/30/2027
PJM | AH2-340 | Toulon 138kV |  | IL | Stark | Active | ComEd | 350 | 210 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 7/30/2027
PJM | AH2-341 | Toulon 138 kV |  | IL | Stark | Active | ComEd | 0 | 140 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 7/30/2027
PJM | AH2-342 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 280 | 168 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 7/30/2027
PJM | AH2-343 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 0 | 112 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 7/30/2027
PJM | AH2-344 | La Rue 138 kV |  | OH | Marion | Active | AEP | 45 | 30.2 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/7/2025
PJM | AH2-345 | Wellington 138 kV |  | OH | Lorain | Active | ATSI | 120 | 80.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 3/7/2025
PJM | AH2-346 | East Arlington 69 kV |  | OH | Hancock | Active | AEP | 47.5 | 31.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/7/2025
PJM | AH2-347 | Northern St. Joseph 138 kV |  | IN | St. Joseph | Active | AEP | 200 | 164 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/7/2025
PJM | AH2-348 | Jefferson - Rockport 765 kV |  | IN | Washington | Active | AEP | 700 | 420 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-349 | Sedge Hill- Person 230kV |  | VA | Halifax | Active | Dominion | 142 | 85.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-350 | Cartersville 230kV |  | VA | Cumberland | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-351 | Jefferson - Hanging Rock 765 kV |  | KY |  | Active | AEP | 1000 | 600 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2027
PJM | AH2-352 | Fall Creek 345 kV |  | IN |  | Active | AEP | 400 | 240 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2026
PJM | AH2-353 | Jefferson - Hanging Rock 765 kV |  | KY |  | Active | AEP | 1000 | 600 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2028
PJM | AH2-354 | Bishopville - Worcester 138 kV |  | MD | Worcester | Withdrawn | DPL | 30 | 18.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 7/29/2022 |  | 9/2/2024
PJM | AH2-355 | Emlenton - Clark Summit 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 7.5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 9/7/2023 |  | 12/31/2024
PJM | AH2-356 | Brookeville 34.5 kV |  | PA | Jefferson | Withdrawn | PENELEC | 10 | 6.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 9/7/2023 |  | 12/31/2024
PJM | AH2-357 | Crown - Piney 34.5 kV |  | PA | Clarion | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 9/7/2023 |  | 12/31/2024
PJM | AH2-359 | Rockwood 23kV |  | PA | Somerset | Withdrawn | PENELEC | 5 | 3.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 9/7/2023 |  | 12/31/2024
PJM | AH2-360 | Scalp Level 23 kV |  | PA | Somerset | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 9/7/2023 |  | 12/31/2024
PJM | AH2-361 | Scottdale - Iron Bridge 13.2 kV |  | PA | Westmoreland | Withdrawn | APS | 5 | 3.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 9/7/2023 |  | 12/31/2024
PJM | AH2-362 | Guilford - Upton 13 kV |  | PA | Franklin | Withdrawn | APS | 5 | 3.2 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 9/7/2023 |  | 12/31/2024
PJM | AH2-363 | Davis Creek - Bloom 345 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/31/2027
PJM | AH2-364 |  |  | PA | York | Withdrawn | ME | 0 | 13.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/15/2022 |  | 11/1/2024
PJM | AH2-365 | Easton - Steele 138 kV IV |  | MD | Talbot | Active | DPL | 0 | 10.787 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 6/1/2024
PJM | AH2-366 | Carville 138 kV V |  | MD | Queen Anne's | Withdrawn | DPL | 0 | 18.12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/8/2022 |  | 6/3/2024
PJM | AH2-367 |  |  | PA | Lebanon | Withdrawn | ME | 0 | 12.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/10/2022 | 4/13/2022 |  | 6/1/2024
PJM | AH2-369 | Nuttall 138 kV |  | WV | Fayette | Active | AEP | 0 | 16 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2022 |  |  | 12/1/2025
PJM | AH2-370 | Church - Oil City 138 kV III |  | MD | Caroline | Active | DPL | 0 | 17.816 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 11/15/2023
PJM | AH2-371 | Jay 138 kV |  | IN | Jay | Active | AEP | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2026
PJM | AH2-372 | Corbin – Cresent Ridge 138kV |  | IL | Stephenson | Active | ComEd | 52 | 52 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2028
PJM | AH2-373 | Blossom Trail 138 kV |  | MI | Berrien | Active | AEP | 180 | 132 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2028
PJM | AH2-374 | Milliron - Brookside 138 kV II |  | OH | Richland | Active | ATSI | 84 | 84 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2027
PJM | AH2-375 | Lena- Landcaster 138kV |  | IL | Stephenson | Active | ComEd | 106 | 106 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2027
PJM | AH2-376 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 153 | 153 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 10/31/2027
PJM | AH2-377 | Pontiac Midpoint – Dresden 345 kV |  | IL | Grundy | Active | ComEd | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 10/31/2024
PJM | AH2-378 | Appomattox ESC |  | VA | Prince George | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-378A | Monroe 138kV |  | NJ | Gloucester | Active | AEC | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-379 | Sign Post - Stockton 69 kV |  | MD | Worcester | Active | DPL | 28.3 | 16.98 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 3/1/2026
PJM | AH2-380 | Matteson - East Frankfort 138 kV |  | IL | Cook | Active | ComEd | 44 | 26.4 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 3/1/2026
PJM | AH2-381 | North Lebanon - Annville 69 kV |  | PA | Lebanon | Withdrawn | ME | 15.3 | 9.18 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/11/2022 | 3/29/2023 |  | 3/1/2026
PJM | AH2-382 | Wythe – Mount Airy 138 kV |  | VA | Wythe | Active | AEP | 75 | 75 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/11/2022 |  |  | 6/1/2027
PJM | AH2-383 | Goddard - Flemingsburg 138 kV |  | KY | Fleming | Active | EKPC | 70 | 56 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/11/2022 |  |  | 6/10/2027
PJM | AH2-384 | Everetts 34.5kV |  | NC | Martin | Active | Dominion | 10 | 7 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/15/2026
PJM | AH2-385 | Chinquapin-Everetts 230kV |  | NC | Pitt | Active | Dominion | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/15/2026
PJM | AH2-386 | North Franklin 138 kV |  | WV | Pendleton | Active | APS | 191.5 | 28.15 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2022 |  |  | 7/30/2027
PJM | AH2-387 | Long Carolyn PV 34.5 kV |  | PA | Indiana | Active | PENELEC | 9.99 | 5.99 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-388 | Long Carolyn 34.5 kV |  | PA | Indiana | Active | PENELEC | 0 | 3.85 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-389 | Devlin 69 kV |  | PA | Lawrence | Active | ATSI | 6 | 3.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-390 | Devlin Storage 69 kV |  | PA | Lawrence | Active | ATSI | 0 | 2.31 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-391 | Pomerico 69 kV |  | PA | Lawrence | Active | ATSI | 7 | 4.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-392 | Pomerico 69 kV II |  | PA | Lawrence | Active | ATSI | 0 | 2.8 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-393 | Nowacoski 34.5 kV |  | PA | Bradford | Active | PENELEC | 8 | 4.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-394 | Walters Karl 69 kV |  | PA | Lawrence | Active | ATSI | 6.3 | 3.78 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-395 | Walters Karl 69 kV II |  | PA | Lawrence | Active | ATSI | 0 | 2.31 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-396 | Nowacoski 34.5 kV II |  | PA | Bradford | Active | PENELEC | 0 | 3.08 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/29/2023
PJM | AH2-397 | Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 200 | 120 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2026
PJM | AH2-398 | Four Rivers- St. Johns 230kV |  | VA | Caroline | Active | Dominion | 80 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2026
PJM | AH2-399 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2026
PJM | AH2-400 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 10/1/2026
PJM | AH2-401 | Dubois 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 7/12/2024
PJM | AH2-402 | Philipsburg 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 9/13/2024
PJM | AH2-403 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 83.2836 | 14.6579 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2028
PJM | AH2-404 | East Danville - Banister 138kV |  | VA | Pittsylvania | Active | AEP | 35 | 35 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2026
PJM | AH2-405 | McConnellsburg-Guilford 138 kV |  | PA | Franklin | Active | APS | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2022 |  |  | 12/1/2026
PJM | AH2-406 | Mt. Pleasant-Lums Pond 138 kV II |  | DE | New Castle | Withdrawn | DPL | 34.5 | 34.5 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 3/10/2022 | 4/11/2022 |  | 9/24/2027
PJM | AH2-407 |  |  | DE | New Castle | Withdrawn | DPL | 34.5 | 20.7 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/10/2022 | 4/11/2022 |  | 9/24/2027
PJM | AH2-408 | Fostoria - Lemoyne 138 kV |  | OH | Wood | Active | ATSI | 49.9 | 29.94 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 6/1/2025
PJM | AH2-409 | Fostoria - Lemoyne 138 kV II |  | OH | Wood | Active | ATSI | 30.1 | 18.06 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/11/2022 |  |  | 6/1/2025
PJM | AH2-410 | New Castle 69 kV |  | KY |  | Active | EKPC | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 6/1/2025
PJM | AH2-411 | New Castle 69 kV |  | KY |  | Active | EKPC | 30 | 18 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 6/1/2025
PJM | AH2-412 | TBD 69kV |  | NJ | Cumberland | Active | AEC | 7.35 | 3.09 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2022
PJM | AH2-413 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 365 | 339 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/15/2026
PJM | AH2-414 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 350 | 350 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/11/2022 |  |  | 12/15/2026
PJM | AH2-415 | Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/15/2026
PJM | AH2-416 | Pontiac Midpoint 345 |  | IL | Livingston | Active | ComEd | 450 | 450 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/15/2026
PJM | AH2-418 | Riverside - Pokagon 138 kV |  | MI | Berrien | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2026
PJM | AH2-419 | Reynolds - Olive 345 kV |  | IN | LaPorte | Active | AEP | 210 | 210 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2026
PJM | AH2-420 | Morgan Street 115 kV |  | PA | Crawford | Active | PENELEC | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-421 | Dresden 138kV |  | IL | Grundy | Active | ComEd | 230 | 230 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-422 | Yukon 138 kV |  | PA | Westmoreland | Active | APS | 83 | 83 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/10/2022 |  |  | 12/31/2025
PJM | AH2-423 | Sollers 230kV |  | MD | Calvert | Active | SMECO | 180 | 180 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/11/2022 |  |  | 12/31/2025
PJM | AH2-424 | Durbin-Pickens 138 kV |  | WV | Randolph | Withdrawn | APS | 120 | 84 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 3/11/2022 | 3/21/2022 |  | 6/30/2025
PJM | AI1-001 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 2100 | 369.6 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 4/2/2022 |  |  | 10/10/2029
PJM | AI1-003 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 170 | 34 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-006 | Monterville - Pickens 138 kV |  | WV | Randolph | Active | APS | 103 | 18.128 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-009 | Pendleton - Tanners Creek 138 kV |  | IN | Rush | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-010 | Ladysmith CT 230 kV |  | VA | Caroline | Withdrawn | Dominion | 200 | 200 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/1/2022 | 5/9/2022 |  | 12/31/2026
PJM | AI1-011 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 46 | 27.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-012 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 0 | 18.4 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-013 | Chickahominy 230 kV |  | VA | Charles City | Active | Dominion | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-014 | Bismark-Doubs 500 kV |  | WV | Berkeley | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/1/2022 | 5/24/2022 |  | 12/31/2026
PJM | AI1-015 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 320 | 320 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/1/2022 | 5/24/2022 |  | 12/31/2026
PJM | AI1-016 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 0 | 24 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-017 | Septa 500 kV |  | VA | Surry | Active | Dominion | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-018 | Spotslvania 500 kV |  | VA | Spotsylvania | Active | Dominion | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-019 | Laurel - Cooper 161 kV |  | KY |  | Active | EKPC | 50 | 50 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/31/2026
PJM | AI1-020 | TBD |  |  |  | Active | DPL | 1.98 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 4/2/2022 |  |  | 3/31/2023
PJM | AI1-021 | Hillandale 115kV |  | VA | Pittsylvania | Active | Dominion | 105 | 63 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/1/2022 |  |  | 3/1/2027
PJM | AI1-022 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 450 | 450 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/15/2026
PJM | AI1-023 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/15/2026
PJM | AI1-024 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/1/2022 |  |  | 12/15/2026
PJM | AI1-026 | Ringtown 12 kV |  |  |  | Active | PPL | 5 | 0 | Energy | Generation Interconnection | Solar | In Progress |  |  |  | 4/2/2022 |  |  | 11/1/2023
PJM | AI1-029 |  |  | PA | Delaware | Withdrawn | PECO | 19.8 | 13.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/1/2022 | 5/4/2022 |  | 6/30/2024
PJM | AI1-030 | Corry East - Garland Jct 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 3.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/1/2022 |  |  | 12/13/2024
PJM | AI1-031 | Westmoreland - Oak Grove 230kV |  | VA | Richmond | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/1/2022 | 6/27/2024 |  | 12/31/2025
PJM | AI1-032 | Bristers 115kV |  | VA | Fauquier | Withdrawn | Dominion | 200 | 200 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 4/1/2022 | 6/27/2024 |  | 12/31/2025
PJM | AI1-033 | Somerville 26 kV |  | NJ | Somerset | Active | PSEG | 8 | 3.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/5/2022 |  |  | 12/22/2026
PJM | AI1-036 | Rockwood - Somerset 12.47 kV |  | PA | Somerset | Withdrawn | PENELEC | 13 | 7.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 4/8/2022 | 9/18/2023 |  | 9/30/2028
PJM | AI1-038 | Harwood-Siegfried 230kV II |  | PA | Carbon | Active | PPL | 95.76 | 61.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/12/2022 |  |  | 3/31/2024
PJM | AI1-039 | Moshannon-Milesburg 230 kV VIII |  | PA | Clearfield | Active | PENELEC | 200 | 160 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 4/19/2022 |  |  | 6/30/2025
PJM | AI1-040 | Ridgway - Elko 138 kV |  | PA | Elk | Active | APS | 250 | 150 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 4/29/2022 |  |  | 3/31/2025
PJM | AI1-044 | Breezewood 12.47 kV |  | PA | Bedford | Withdrawn | PENELEC | 7.5 | 4.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 5/13/2022 | 9/18/2023 |  | 5/1/2026
PJM | AI1-046 | Smithburg 500 kV |  | NJ | Monmouth | Active | JCPL | 1600 | 281.6 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 5/25/2022 |  |  | 12/31/2031
PJM | AI1-053 | McDowell - Campbell 69 kV |  | PA | Mercer | Active | ATSI | 6.6 | 0 | Energy | Generation Interconnection | Diesel; Solar | In Progress |  |  |  | 6/10/2022 |  |  | 12/1/2022
PJM | AI1-063 | Bear Peak East St. Clair 23 kV |  | PA | Bedford | Withdrawn | PENELEC | 15 | 9 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/21/2022 | 9/18/2023 |  | 6/1/2027
PJM | AI1-066 | Bear Peak Rostraver 12.47 kV |  | PA | Westmoreland | Withdrawn | APS | 7.5 | 4.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/23/2022 | 9/18/2023 |  | 6/1/2026
PJM | AI1-067 | Bear Peak Rostraver II 12.47 kV |  | PA | Westmoreland | Withdrawn | APS | 7.5 | 4.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/23/2022 | 9/18/2023 |  | 6/1/2027
PJM | AI1-073 | Bear Peak Antrim 34.5 kV |  | PA | Franklin | Withdrawn | APS | 20 | 12 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 6/30/2022 | 9/18/2023 |  | 6/1/2027
PJM | AI1-074 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 120 | 96 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/5/2022 |  |  | 12/15/2027
PJM | AI1-075 | Lee Co. EC 345kV |  | IL | Lee | Active | ComEd | 0 | 11.9 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 7/6/2022 |  |  | 9/1/2022
PJM | AI1-076 | TBD 13.2 kV |  | PA | Delaware | Active | PECO | 19.8 | 10.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/11/2022 |  |  | 6/30/2024
PJM | AI1-077 | Marengo 34.5 kV Line |  | IL | McHenry | Active | ComEd | 15.75 | 6.62 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/15/2022 |  |  | 10/1/2025
PJM | AI1-078 | New Carlisle - Bosserman 138 kV |  | IN | LaPorte | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/26/2022 |  |  | 12/31/2026
PJM | AI1-079 | Summer Shade - West Columbia 69 kV |  | KY | Adair | Active | EKPC | 64.8 | 64.8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/26/2022 |  |  | 12/31/2026
PJM | AI1-080 | Albion - Kendallville - 138 kV |  | IN | LaPorte | Active | AEP | 125 | 125 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/26/2022 |  |  | 12/31/2026
PJM | AI1-081 | Jay - DeSoto 138 kV |  | IN | Jay | Active | AEP | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 7/26/2022 |  |  | 12/31/2026
PJM | AI1-082 | Laurel 25 kV |  | PA | Westmoreland | Active | APS | 15 | 9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/28/2022 |  |  | 12/1/2026
PJM | AI1-084 | Fawkes - West Berea 138kV |  | KY | Madison | Active | EKPC | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/29/2022 |  |  | 12/1/2026
PJM | AI1-085 | Tanners Creek - DeSoto 345 kV |  | IN | Wayne | Active | AEP | 290 | 174 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 7/29/2022 |  |  | 9/15/2030
PJM | AI1-086 | Trego - Emporia 115 kV |  | VA | Greensville | Active | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/29/2022 |  |  | 9/1/2025
PJM | AI1-087 | Disputanta - Bakers Pond 115 kV |  | VA | Prince George | Active | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/29/2022 |  |  | 9/1/2025
PJM | AI1-088 | Poe- New Bohemia 115kV |  | VA | Prince George | Active | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/29/2022 |  |  | 9/1/2025
PJM | AI1-089 | Myrtle - Oak Ridge 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/29/2022 |  |  | 9/1/2025
PJM | AI1-091 | Bascom 69 kV |  | OH | Seneca | Active | AEP | 49.9 | 31.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/4/2022 |  |  | 7/1/2025
PJM | AI1-092 | Collinsville - Springfield Road 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 31.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/4/2022 |  |  | 7/1/2025
PJM | AI1-093 | Westmoreland 34.5 kV |  | PA | Westmoreland | Active | APS | 24 | 24 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/15/2022 |  |  | 7/1/2026
PJM | AI1-094 | Westmoreland 34.5 kV |  | PA | Westmoreland | Active | APS | 24 | 24 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/16/2022 |  |  | 7/1/2026
PJM | AI1-095 | Branchron - Keisters 25 kV |  | PA | Butler | Active | APS | 14 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/19/2022 |  |  | 12/1/2026
PJM | AI1-096 | Pemberton 138 kV |  | WV |  | Active | AEP | 42 | 42 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 8/23/2022 |  |  | 5/1/2027
PJM | AI1-097 | Newcomerstown 12.47 kV |  | OH | Tuscarawas | Withdrawn | AEP | 7 | 6.2 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 8/26/2022 | 8/30/2024 |  | 12/1/2025
PJM | AI1-098 | Circleville 138 kV |  | OH | Pickaway | Withdrawn | AEP | 40 | 30 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 8/30/2022 | 8/30/2024 |  | 10/1/2026
PJM | AI1-100 | Somerton - Norton 138 kV |  | OH | Belmont | Active | AEP | 150 | 140 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 8/30/2022 |  |  | 12/31/2025
PJM | AI1-101 | Pocono-Acahela 230 kV |  | PA | Lackawanna | Active | PPL | 100 | 63.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/30/2022 |  |  | 9/1/2029
PJM | AI1-102 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 8/30/2022 |  |  | 9/1/2029
PJM | AI1-103 | Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 200 | 127.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/30/2022 |  |  | 12/31/2029
PJM | AI1-104 | Timber Road 138 kV |  | OH | Paulding | Active | AEP | 135 | 86.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/30/2022 |  |  | 9/1/2029
PJM | AI1-105 | White Haven 2 Tap-White Haven DC 69 kV |  | PA | Luzerne | Active | PPL | 60 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 8/30/2022 |  |  | 12/19/2026
PJM | AI1-106 | Sinai 13.2 kV |  | VA | Halifax | Active | Dominion | 9.9 | 9.15 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 8/31/2022 |  |  | 12/31/2023
PJM | AI1-107 | Midlothian - North Pole 230 kV |  | VA | Chesterfield | Withdrawn | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 8/31/2022 | 6/27/2024 |  | 12/29/2028
PJM | AI1-108 | Endless Caverns - Timberville 115 kV |  | VA | Rockingham | Active | Dominion | 38.5 | 33.1 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 8/31/2022 |  |  | 1/1/2026
PJM | AI1-109 | Deans 500 kV |  | NJ | Middlesex | Active | PSEG | 1310 | 393 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 9/1/2022 |  |  | 12/31/2029
PJM | AI1-110 | Larrabee 230 kV V |  | NJ | Monmouth | Active | JCPL | 1310 | 393 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 9/1/2022 |  |  | 12/31/2029
PJM | AI1-111 | Werner 230 kV |  | NJ | Middlesex | Active | JCPL | 1310 | 393 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 9/1/2022 |  |  | 12/31/2029
PJM | AI1-112 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 85 | 50 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 8/31/2022 |  |  | 1/1/2026
PJM | AI1-113 | New Halifax - Dawson 115 kV |  | NC | Halifax | Withdrawn | Dominion | 74.9 | 74.9 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/2/2022 | 1/17/2024 |  | 6/1/2026
PJM | AI1-114 | Revloc 46 kV |  | PA | Cambria | Active | PENELEC | 9.9 | 9.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/2/2022 |  |  | 12/31/2025
PJM | AI1-115 | Glory 34.5 kV |  | PA | Clearfield | Active | PENELEC | 9.9 | 9.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/2/2022 |  |  | 12/31/2025
PJM | AI1-116 | Hopkins 138 kV |  | WV |  | Active | AEP | 70 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/6/2022 |  |  | 9/10/2024
PJM | AI1-117 | Hopkins 138 kV |  | WV |  | Active | AEP | 60 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/6/2022 |  |  | 9/10/2024
PJM | AI1-118 | Pequest river - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 37.6 | 15.792 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/6/2022 |  |  | 9/29/2025
PJM | AI1-119 | Shorewood 138kV |  | IL | Kendall | Active | ComEd | 28.8 | 18.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/6/2022 |  |  | 6/30/2026
PJM | AI1-120 | Pequest River - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 51.6 | 21.672 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/7/2022 |  |  | 9/29/2025
PJM | AI1-121 | North Muskingum 69 KV |  | OH | Morgan | Withdrawn | AEP | 90 | 90 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/7/2022 | 1/30/2024 |  | 12/31/2025
PJM | AI1-122 | Sparta LF Solar 34.5 kV |  | NJ | Sussex | Active | JCPL | 5.85 | 2.457 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/7/2022 |  |  | 9/29/2025
PJM | AI1-123 | Nutbush-Victoria DP 115kV |  | VA | Lunenburg | Active | Dominion | 59 | 35.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/8/2022 |  |  | 9/30/2026
PJM | AI1-124 | Nutbush - Victoria DP 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/8/2022 |  |  | 9/30/2026
PJM | AI1-125 | Mount Eagle 34.5 kV |  | VA | Albemarle | Active | Dominion | 22 | 13.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/8/2022 |  |  | 9/30/2024
PJM | AI1-126 | Farmville 12.47kV |  | VA | Cumberland | Active | Dominion | 10 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/8/2022 |  |  | 9/30/2024
PJM | AI1-127 | Dauphin 12 kV |  | PA | Dauphin | Active | PPL | 4.5 | 2.7 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/8/2022 |  |  | 9/9/2024
PJM | AI1-128 | Milesburg 12.47 kV |  | PA | Centre | Active | APS | 5 | 5 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/8/2022 |  |  | 9/9/2024
PJM | AI1-129 | Muncy 12 kV II |  | PA | Lycoming | Active | PPL | 4.5 | 2.7 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/8/2022 |  |  | 9/9/2024
PJM | AI1-130 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 9/7/2026
PJM | AI1-131 | TBD 115 kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 9/7/2026
PJM | AI1-132 | Fredricksburg 69 kV |  | KY | Washington | Active | EKPC | 83 | 83 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/8/2022 |  |  | 4/30/2029
PJM | AI1-133 | Hillsboro 69 kV |  | KY | Fleming | Active | EKPC | 50 | 50 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/8/2022 |  |  | 4/30/2029
PJM | AI1-134 | Greentown - Hummel Creek 138 kV |  | IN | Grant | Active | AEP | 200 | 200 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/8/2022 |  |  | 4/30/2029
PJM | AI1-135 | Perquimans 230 kV |  | NC | Chowan | Withdrawn | Dominion | 300 | 300 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/8/2022 | 12/4/2024 |  | 6/30/2026
PJM | AI1-136 | Brodnax 115 kV |  | VA | Brunswick | Withdrawn | Dominion | 200 | 200 | Capacity | Generation Interconnection | Solar; Storage | Withdrawn |  |  |  | 9/8/2022 | 1/17/2024 |  | 6/30/2026
PJM | AI1-137 | Greystone - Portland 230 kV |  | NJ | Warren | Active | JCPL | 155 | 65.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 9/29/2025
PJM | AI1-139 | Henrietta Township - New Russia Township 69 kV |  | OH | Lorain | Active | ATSI | 14.8 | 6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 4/1/2025
PJM | AI1-140 | Selma Parker - Richmond 138 kV |  | IN | Wayne | Active | AEP | 40 | 40 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 6/1/2025
PJM | AI1-141 | Blossom - Dowagi TSS 34.5 kV |  | MI | Cass | Active | AEP | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 6/1/2025
PJM | AI1-142 | Warren-National Forge 34.5 kV |  | PA | Warren | Withdrawn | PENELEC | 10 | 6.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2022 | 9/7/2023 |  | 6/30/2026
PJM | AI1-143 | Bell Township - Vandergrift 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 7.98 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 4/1/2025
PJM | AI1-144 | Gardners 13.2 kV III |  | PA | Adams | Active | ME | 10 | 8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-145 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 125 | 75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 9/30/2026
PJM | AI1-146 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 0 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 9/30/2026
PJM | AI1-147 | Sandwich 34kV |  | IL | DeKalb | Active | ComEd | 64 | 38.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2026
PJM | AI1-148 | Davis Creek 138kV |  | IL | Kankakee | Active | ComEd | 164 | 98.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 1/1/2026
PJM | AI1-149 | Pleasant Valley 345 kV |  | IL | McHenry | Active | ComEd | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 7/1/2025
PJM | AI1-150 | Locust - Todd 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 29.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-151 | Kyger Creek - Pierce 345 kV |  | OH | Adams | Active | AEP | 53.2 | 31.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2022 |  |  | 1/4/2027
PJM | AI1-152 | Siegfried - Nazareth 69 kV |  | PA | Northampton | Active | ME | 19.9 | 11.9 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-153 | North Hershey - Grantville 69 kV |  | PA | Dauphin | Active | ME | 20 | 12 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-154 | Goodings Grove 138 kV |  | IL | Will | Active | ComEd | 230 | 230 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-155 | Chicago Heights 138kV |  | IL | Cook | Active | ComEd | 110 | 110 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-156 | West Rutland 138 kV |  | IL | Kane | Active | ComEd | 170 | 170 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-157 | Pleasant Valley – Crystal Lake 138 kV |  | IL | McHenry | Active | ComEd | 54.4 | 32.64 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-158 | Pleasant Valley - Crystal Lake 138 kV |  | IL | McHenry | Active | ComEd | 80 | 80 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/4/2027
PJM | AI1-159 | Mount Sterling - Sideview 69 kV |  | KY | Montgomery | Active | EKPC | 35 | 35 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2028
PJM | AI1-160 | Crawford Solar 2 34.5 kV |  | PA | Crawford | Active | PENELEC | 0 | 1.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 1/1/2028
PJM | AI1-161 | Crawford Solar 3 34.5 kV |  | PA | Crawford | Active | PENELEC | 0 | 1.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/9/2022 |  |  | 1/1/2028
PJM | AI1-162 | Saltsburg-Vandergrift 138 kV |  | PA | Armstrong | Active | APS | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 9/15/2026
PJM | AI1-163 | Gates Hill - Luzerne 25 kV |  | PA | Fayette | Withdrawn | APS | 7.5 | 5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2022 | 9/7/2023 |  | 6/30/2026
PJM | AI1-164 | Clark Summit - Tionesta Junction 34.5 kV |  | PA | Venango | Withdrawn | PENELEC | 10 | 6.4 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 9/9/2022 | 9/7/2023 |  | 6/30/2026
PJM | AI1-165 | Magnolia - Summersville 69 kV |  | KY | Green | Active | EKPC | 85 | 50 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 1/1/2026
PJM | AI1-166 | Granger - Ontwa 138 kV |  | MI | Cass | Active | AEP | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2028
PJM | AI1-167 | Cedarville 138 kV |  | OH | Clermont | Active | DEOK | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2028
PJM | AI1-168 | Conesville 345 kV |  | OH | Coshocton | Active | AEP | 200 | 35.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 9/9/2022 |  |  | 8/31/2027
PJM | AI1-169 | Moyock 230 kV |  | NC | Currituck | Active | Dominion | 150 | 26.4 | Capacity | Generation Interconnection | Storage; Wind | In Progress |  |  |  | 9/9/2022 |  |  | 10/15/2026
PJM | AI1-170 | Glidden - Sugar Grove 138kV |  | IL | DeKalb | Active | ComEd | 100 | 80 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 10/31/2027
PJM | AI1-171 | Garden Plain - Rock Falls 138 kV |  | IL | Whiteside | Active | ComEd | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2022 |  |  | 4/30/2028
PJM | AI1-172 | Katydid Road - Goodings Grove 345 kV |  | IL | Grundy | Active | ComEd | 250 | 250 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 4/30/2028
PJM | AI1-173 | Lena - Freeport 34.5 kV |  | IL | Stephenson | Active | ComEd | 16 | 9.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2022 |  |  | 4/30/2027
PJM | AI1-174 | Garden Plain - Rock Falls 138 kV |  | IL | Stephenson | Active | ComEd | 118 | 94.4 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 4/30/2028
PJM | AI1-175 | Waldo - North Waldo 69 kV |  | OH | Marion | Active | AEP | 19.5 | 16.2 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-176 | Cheswick 138 kV |  | PA | Allegheny | Withdrawn | DL | 300 | 300 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2022 | 3/19/2024 |  | 12/31/2025
PJM | AI1-177 | Avon 345 kV II |  | OH | Lorain | Withdrawn | ATSI | 200 | 200 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2022 | 12/3/2024 |  | 12/31/2025
PJM | AI1-178 | Red House DP - Sugar Hill 115 kV |  | VA | Campbell | Active | Dominion | 80 | 80 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-179 | Colver Power Project 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-180 | Windsor 69 kV |  | KY |  | Active | EKPC | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-181 | Grandview 115 kV |  | PA | Venango | Active | PENELEC | 140 | 140 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-182 | Des Plaines 138 kV |  | IL | Cook | Withdrawn | ComEd | 80 | 80 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/9/2022 | 1/3/2024 |  | 12/31/2027
PJM | AI1-183 | DuPont - Marlboro 115 kV |  | VA | Richmond | Active | Dominion | 130 | 130 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-184 | Greenwood 138 kV |  | VA | Frederick | Active | APS | 110 | 110 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-185 | Valley 230 kV |  | VA | Augusta | Active | Dominion | 210 | 210 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-186 | Strasburg 138 kV |  | VA | Shenandoah | Active | APS | 140 | 140 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-187 | Glen Gardner 230 kV |  | NJ | Hunterdon | Active | JCPL | 280 | 280 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-188 | Buffalo 115 kV |  | PA | Erie | Active | PENELEC | 130 | 130 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-189 | Northeast - Windy Edge 115 kV |  | MD | Baltimore County | Active | BGE | 110 | 110 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-190 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 100 | 100 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2027
PJM | AI1-191 | Landcaster - Pecatonica 138 kV |  | IL | Stephenson | Active | ComEd | 200 | 35.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 9/9/2022 |  |  | 12/1/2027
PJM | AI1-192 | Price Hill - Pruntytown 138 kV |  | WV | Marion | Active | APS | 40 | 40 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 9/9/2022 |  |  | 6/1/2024
PJM | AI1-193 | Lincoln 13.2 kV II |  | PA | Adams | Active | ME | 10 | 8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-194 | Orrtanna 13.2 kV III |  | PA | Adams | Active | ME | 10 | 8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-195 | Orrtanna 13.2 kV IV |  | PA | Adams | Active | ME | 10 | 8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-196 | Gates Hill 25 kV |  | PA | Fayette | Active | ME | 9.8 | 7.88 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-197 | Gardners 13.2 kV |  | PA | Adams | Active | ME | 10 | 8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-198 | Gardners 13.2 kV II |  | PA | Adams | Active | ME | 7.1 | 5.76 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-199 | South Union 25 kV |  | PA | Fayette | Active | ME | 8.3 | 6.98 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/9/2022 |  |  | 12/31/2024
PJM | AI1-200 | Campbell 8.32 kV |  | PA | Lawrence | Active | ME | 5 | 4 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 12/31/2024
PJM | AI1-202 | Greenland Gap 500 kV |  | WV | Grant | Active | APS | 450 | 450 | Capacity | Generation Interconnection | Solar; Storage; Wind | In Progress |  |  |  | 9/10/2022 |  |  | 10/15/2026
PJM | AI1-203 | Clover - Rawling 500 kV |  | VA | Lunenburg | Active | Dominion | 300 | 180 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 9/10/2022 |  |  | 12/30/2027
PJM | AI1-204 | Brokaw 345 kV |  | IL |  | Withdrawn | ComEd | 300 | 300 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/11/2022 | 11/22/2022 |  | 12/30/2027
PJM | AI1-205 | Brokaw 345 kV |  | IL |  | Withdrawn | ComEd | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 9/10/2022 | 11/22/2022 |  | 12/30/2028
PJM | AI1-206 | Brokaw 345 kV |  | IL |  | Withdrawn | ComEd | 300 | 300 | Capacity | Generation Interconnection | Storage | Withdrawn |  |  |  | 9/10/2022 | 11/22/2022 |  | 12/31/2029
PJM | AI1-211 | Brandonville - Necessity 138 kV |  | WV | Preston | Active | APS | 68 | 68 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 12/31/2024
PJM | AI1-212 | Homer City - Stolle Road 345 kV |  | PA | Jefferson | Active | PENELEC | 182 | 182 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 6/30/2024
PJM | AI1-213 | Farmers Valley - Ridgeway 115 kV VI |  | PA | Elk | Active | APS | 174 | 174 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 6/30/2024
PJM | AI1-214 | Philipsburg 115 kV IV |  | PA | Centre | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 6/30/2024
PJM | AI1-215 | Philipsburg 115 kV V |  | PA | Centre | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 6/30/2024
PJM | AI1-216 | Philipsburg 115 kV VI |  | PA | Centre | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 6/30/2024
PJM | AI1-217 | Philipsburg 115 kV VII |  | PA | Centre | Active | PENELEC | 17 | 17 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 9/10/2022 |  |  | 6/30/2024
PJM | AI2-001 | Remington 115 kV |  | VA | Caroline | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 10/1/2022 |  |  | 5/26/2028
PJM | AI2-002 | Vanceville 138 kV |  | VA | Washington | Active | APS | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 10/1/2022 |  |  | 5/26/2028
PJM | AI2-004 | Danieltown – Brunswick 115 kV |  | VA | Brunswick | Active | Dominion | 80 | 71.8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 10/14/2022 |  |  | 1/1/2026
PJM | AI2-005 | Bremo 115 kV |  | VA | Fluvanna | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 10/24/2022 |  |  | 5/26/2028
PJM | AI2-006 | Elgin 138kV |  | IL | Kane | Active | ComEd | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 11/10/2022 |  |  | 6/1/2027
PJM | AI2-007 | Rocky Road 138kV |  | IL | Kane | Active | ComEd | 40 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 11/10/2022 |  |  | 6/1/2027
PJM | AI2-010 | Elmont 34.5 kV |  | VA | Hanover | Active | Dominion | 20 | 20 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/23/2022 |  |  | 12/30/2025
PJM | AI2-011 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 0 | 15 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/30/2022 |  |  | 12/31/2027
PJM | AI2-012 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 0 | 45 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 11/30/2022 |  |  | 12/31/2027
PJM | AI2-013 | Grundy - Goose Lake 138 kV |  | IL | Grundy | Active | ComEd | 24.1 | 17.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/30/2022 |  |  | 5/29/2026
PJM | AI2-014 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 37.9 | 20.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 11/30/2022 |  |  | 5/29/2026
PJM | AI2-015 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 0 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/1/2022 |  |  | 11/30/2025
PJM | AI2-017 | PA Centre Borealis 34.5 kV |  | PA | Centre | Active | APS | 5 | 3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/9/2022 |  |  | 12/1/2026
PJM | AI2-018 | TBD 23 kV |  | PA | Somerset | Active | PENELEC | 4 | 2.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/9/2022 |  |  | 12/1/2026
PJM | AI2-019 | TBD 12.47 kV |  | PA | Franklin | Active | APS | 5 | 3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/9/2022 |  |  | 12/1/2026
PJM | AI2-020 | Warren County 500 kV |  | VA | Warren | Active | Dominion | 19 | 11 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 12/10/2022 |  |  | 12/31/2022
PJM | AI2-022 | East Towanda 230 kV |  | PA | Bradford | Active | PENELEC | 30 | 60 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 12/20/2022 |  |  | 5/1/2025
PJM | AI2-023 | Lake - 270888 345kV |  | IN | Lake | Withdrawn | ComEd | 200 | 200 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/20/2022 | 1/15/2025 |  | 12/31/2028
PJM | AI2-024 | Racine - Ravenswood 69kV |  | OH | Meigs | Active | AEP | 60 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/22/2022 |  |  | 12/31/2028
PJM | AI2-025 |  |  | DE | New Castle | Active | DPL | 10 | 10 | Capacity | Generation Interconnection | Biomass | In Progress |  |  |  | 12/23/2022 |  |  | 10/31/2026
PJM | AI2-026 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Withdrawn | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 12/22/2022 | 9/18/2024 |  | 12/31/2028
PJM | AI2-027 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 12/22/2022 |  |  | 12/31/2028
PJM | AI2-028 | Beatty - Biers Run 345 kV |  | OH | Union | Active | AEP | 160 | 96 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/29/2022 |  |  | 12/20/2026
PJM | AI2-029 | Clarksburg - Biers Run 69 kV |  | OH | Union | Active | AEP | 70 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 12/31/2022 |  |  | 12/20/2026
PJM | AI2-030 | Poplar Flat Switch - Brown Hill 69 kV |  | OH | Adams | Active | AEP | 50 | 40 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 1/18/2023 |  |  | 12/20/2024
PJM | AI2-031 | Sapnony 34.5kV |  | VA | Sussex | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/24/2023 |  |  | 10/31/2024
PJM | AI2-032 | Distribution Circuit#324 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/25/2023 |  |  | 10/31/2024
PJM | AI2-033 | Sapony 34.5kV |  | VA | Sussex | Active | Dominion | 40 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/24/2023 |  |  | 10/31/2024
PJM | AI2-034 | Distribution circuit#332 35kV |  | VA | Sussex | Active | Dominion | 20 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/24/2023 |  |  | 10/31/2024
PJM | AI2-035 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/25/2023 |  |  | 12/31/2027
PJM | AI2-036 | Craigsville-Staunton 115kV |  | VA | Augusta | Active | Dominion | 100 | 60 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/25/2023 |  |  | 12/31/2027
PJM | AI2-037 | Lauraville-Dunbrooke 115kV |  | VA | King and Queen | Active | Dominion | 142 | 85 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/25/2023 |  |  | 12/31/2027
PJM | AI2-038 | St. Johns 115kV |  | VA | Spotsylvania | Active | Dominion | 150 | 90 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/25/2023 |  |  | 12/31/2027
PJM | AI2-039 | Poolesville 230kV |  | VA | Surry | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2023 |  |  | 9/30/2026
PJM | AI2-040 | Orange 115kV |  | VA | Orange | Active | Dominion | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2023 |  |  | 9/30/2026
PJM | AI2-041 | South Boston 115kV |  | VA | Halifax | Active | Dominion | 75 | 75 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2023 |  |  | 9/30/2026
PJM | AI2-042 | Paytes 115kV |  | VA | Louisa | Active | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2023 |  |  | 9/30/2026
PJM | AI2-043 | Pamplin 34.5kV |  | VA | Northumberland | Active | Dominion | 5 | 3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 1/31/2023 |  |  | 4/26/2024
PJM | AI2-044 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2023 |  |  | 12/31/2023
PJM | AI2-045 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/1/2023 |  |  | 12/31/2023
PJM | AI2-052 | Lakewood 230 kV II |  | NJ | Ocean | Active | JCPL | 70 | 70 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/17/2023 |  |  | 6/1/2027
PJM | AI2-053 | New Holland 69 kV |  | OH | Fayette | Active | Dayton | 100 | 17.6 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/24/2023 |  |  | 12/31/2026
PJM | AI2-054 | Rock Springs 500 kV |  | MD | Cecil | Active | DPL | 0 | 0 | Energy | Generation Interconnection | Storage | In Progress |  |  |  | 2/24/2023 |  |  | 6/1/2028
PJM | AI2-055 | Summit-West Fall 115kV II |  | PA | Blair | Active | PENELEC | 0 | 6.8 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/23/2023 |  |  | 12/10/2010
PJM | AI2-056 | Fairview East 34.5 kV |  | PA | Erie | Active | PENELEC | 0 | 3.78 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 2/6/2024
PJM | AI2-057 | Venango 34.5 kV |  | PA | Venango | Active | PENELEC | 0 | 6.58 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 2/20/2024
PJM | AI2-058 | Clark Summit-Emlenton 34.5 kV |  | PA | Venango | Active | PENELEC | 0 | 7.28 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 1/14/2025
PJM | AI2-059 | Wolfs Corners 34.5 kV |  | PA | Clarion | Active | PENELEC | 0 | 7.28 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 1/14/2024
PJM | AI2-060 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Active | ComEd | 0 | 40.74 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 10/1/2024
PJM | AI2-061 | Bedford North-Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 0 | 17.64 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/24/2023 |  |  | 12/15/2026
PJM | AI2-062 | Jack Frost - Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 0 | 18.34 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/24/2023 |  |  | 5/15/2027
PJM | AI2-063 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 0 | 82.48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 5/15/2027
PJM | AI2-064 | Desoto - Keystone 345 kV |  | IN | Blackford | Active | AEP | 0 | 35.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 1/1/2026
PJM | AI2-065 | Varner - Sours 138 kV |  | IN | DeKalb | Active | AEP | 0 | 12.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 6/1/2026
PJM | AI2-066 | Marion County 161 kV |  | KY | Marion | Active | EKPC | 0 | 16.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/23/2023 |  |  | 12/1/2024
PJM | AI2-067 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 0 | 20 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/24/2023 |  |  | 3/1/2027
PJM | AI2-068 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/24/2023 |  |  | 12/31/2026
PJM | AI2-069 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/24/2023 |  |  | 10/21/2026
PJM | AI2-070 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/24/2023 |  |  | 3/1/2027
PJM | AI2-071 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/24/2023 |  |  | 3/1/2027
PJM | AI2-072 | Steubenville 69 kV |  | OH | Jefferson | Active | AEP | 0 | 27.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/24/2023 |  |  | 5/15/2024
PJM | AI2-073 | Columbia-Sunbury 69 kV |  | PA | Snyder | Active | PPL | 0 | 9.93 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/24/2023 |  |  | 6/30/2024
PJM | AI2-074 | Beatty - Greene 345 kV |  | OH | Madison | Active | AEP | 0 | 87.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/24/2023 |  |  | 12/15/2023
PJM | AI2-075 | Face Rock-Kinzer #13 69 kV |  | PA | Lancaster | Active | PPL | 0 | 9.86 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/24/2023 |  |  | 7/1/2023
PJM | AI2-076 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 0 | 56 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/27/2023 |  |  | 3/15/2023
PJM | AI2-077 | Kanakee 138 kV |  | IL | Kankakee | Active | ComEd | 0 | 56 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 3/16/2023
PJM | AI2-078 | Myrtle-Windsor 115 kV |  | VA | Isle of Wight | Active | Dominion | 0 | 52.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-079 | Harmony Village-Shackleford 115 kV |  | VA | Fauquier | Active | Dominion | 0 | 40.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2023 |  |  | 12/31/2025
PJM | AI2-080 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 0 | 73.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2023 |  |  | 12/31/2025
PJM | AI2-081 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 0 | 271 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2023 |  |  | 12/31/2025
PJM | AI2-082 | Cardington-Liberty 69 kV IV |  | OH | Morrow | Active | ATSI | 0 | 34.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2023 |  |  | 12/31/2025
PJM | AI2-083 | National-Tangy 138kV V |  | OH | Madison | Withdrawn | ATSI | 0 | 26.6 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/28/2023 | 12/1/2023 |  | 12/31/2025
PJM | AI2-084 | Galion 138 kV VI |  | OH | Morrow | Active | ATSI | 0 | 78 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2023 |  |  | 12/31/2025
PJM | AI2-085 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Withdrawn | OVEC | 0 | 65 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 2/27/2023 | 12/13/2024 |  | 12/31/2025
PJM | AI2-086 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 0 | 45 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/27/2023 |  |  | 12/31/2025
PJM | AI2-087 | Gold-Sabinsville 115kV III |  | PA | Potter | Active | PENELEC | 0 | 42.5 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/27/2023 |  |  | 3/3/2023
PJM | AI2-088 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 0 | 229.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-089 | Cedar Creek 138 kV |  | DE | New Castle | Active | DPL | 0 | 71 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 11/15/2024
PJM | AI2-090 | Harrington 69 kV |  | DE |  | Active | DPL | 0 | 31 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 3/15/2025
PJM | AI2-091 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 0 | 22.7 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 2/27/2023
PJM | AI2-092 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 0 | 40.3 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-093 | Olive-DeQuine 345kV |  | IN | White | Active | AEP | 0 | 106.5 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-094 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 0 | 53.5 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-095 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 0 | 50.3 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-096 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 0 | 54 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-097 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 0 | 45.3 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-098 | Meadow Lake 345kV |  | IN | White | Active | AEP | 0 | 107 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-099 | Powerton-Goodings Grove 345kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 0 | 49.3 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-100 | Powerton - Dresden 345kv (CIR Increase) |  | IL | Livingston | Active | ComEd | 0 | 96 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/27/2023
PJM | AI2-101 | Haviland - Milan 138kV |  | OH | Paulding | Active | AEP | 0 | 42.6 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-102 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 0 | 46.8 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-103 | Desoto-Tanners Creek 345kV |  | IN | Randolph | Active | AEP | 0 | 106.4 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/27/2023
PJM | AI2-104 | Blue Mound I |  | IL | McLean | Active | ComEd | 0 | 100 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 2/27/2023
PJM | AI2-105 | Desoto-Tanners Creek #1 345kV |  | IN | Randolph | Active | AEP | 0 | 106.4 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/27/2023
PJM | AI2-106 | Pontiac MidPoint-Brokaw 345kV |  | IL | Livingston | Active | ComEd | 0 | 106.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 2/27/2023
PJM | AI2-107 | Ada-Dunkirk 69kV |  | OH | Hardin | Active | AEP | 0 | 31.7 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 2/27/2023
PJM | AI2-109 | Madoc - Delaware 138 kV |  | IN | Randolph | Active | AEP | 0 | 69 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 9/1/2024
PJM | AI2-110 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 0 | 46 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 10/31/2023
PJM | AI2-111 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 0 | 84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 10/31/2025
PJM | AI2-112 | Bluff Point-Randolph 138 kV |  | IN | Randolph | Active | AEP | 0 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 10/31/2026
PJM | AI2-113 | Old Church 230 kV |  | VA | Hanover | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 2/28/2023 |  |  | 9/18/2029
PJM | AI2-114 | Verona - Weyers Cave 115 kV |  | VA | Augusta | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/1/2023 |  |  | 9/1/2029
PJM | AI2-115 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 0 | 84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 10/31/2026
PJM | AI2-116 | Allen 345kV |  | IN | Allen | Active | AEP | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 10/31/2026
PJM | AI2-117 | Payne 69 kV |  | OH | Paulding | Active | AEP | 0 | 11.976 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 6/28/2023
PJM | AI2-118 | Continental 69 kV |  | OH | Putnam | Active | AEP | 0 | 11.976 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 6/28/2023
PJM | AI2-119 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/28/2021
PJM | AI2-120 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 0 | 52.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 10/31/2027
PJM | AI2-121 | Hector 115 kV |  | PA | Potter | Active | PENELEC | 0 | 19.95 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2024
PJM | AI2-122 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Active | ComEd | 0 | 66.95 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2024
PJM | AI2-123 | Goddard - Plumville 138 kV |  | KY | Fleming | Active | EKPC | 0 | 35 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 6/30/2025
PJM | AI2-124 | Goddard 138 kV |  | KY | Fleming | Active | EKPC | 0 | 23.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 6/30/2025
PJM | AI2-125 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 0 | 32.16 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2024
PJM | AI2-126 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 0 | 16.84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2024
PJM | AI2-127 | Cynthiana Tie - Headquarters 69 kV |  | KY | Harrison | Active | EKPC | 0 | 20.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 9/30/2024
PJM | AI2-128 | Cardiff 230 kV |  | NJ | Atlantic | Active | AEC | 0 | 1204.52 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 3/1/2023 |  |  | 9/30/2027
PJM | AI2-129 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 0 | 1675.59 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/28/2030
PJM | AI2-130 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 0 | 1037.2 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/28/2030
PJM | AI2-131 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 0 | 703.75 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/28/2030
PJM | AI2-132 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 0 | 355.02 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/28/2030
PJM | AI2-133 | Kincaid-Pana 345kV |  | IL | Christian | Active | ComEd | 0 | 84.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 10/31/2026
PJM | AI2-134 | Pontiac Midpoint 345 kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 0 | 84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2022
PJM | AI2-135 | McLean 345 kV (CIR Increase) |  | IL | McLean | Active | ComEd | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-136 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 0 | 47.98 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2022
PJM | AI2-137 | Stockton 138 kV |  | VA | Henry | Active | AEP | 0 | 21.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2022
PJM | AI2-138 | Marysville 345kV |  | OH | Union | Active | AEP | 0 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/26/2023
PJM | AI2-139 | Marysville 345kV |  | OH | Union | Active | AEP | 0 | 54 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/25/2023
PJM | AI2-141 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 0 | 18.75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 5/31/2023
PJM | AI2-143 | Clubhouse-Sappony 230 kV |  | VA | Sussex | Active | Dominion | 0 | 37.65 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2021
PJM | AI2-144 | Mottville 138 kV |  | MI | St. Joseph | Active | AEP | 0 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-145 | Claytor Lake - Edgemont 138 kV |  | VA | Montgomery | Active | AEP | 0 | 30.43 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2022
PJM | AI2-146 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 0 | 67.08 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2021
PJM | AI2-147 | Dequine - Eugene 345 kV |  | IN | Fountain | Active | AEP | 0 | 78 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2024
PJM | AI2-148 | Mississinewa- Gaston 138 kV |  | IN | Grant | Active | AEP | 0 | 38.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2022
PJM | AI2-149 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 0 | 67.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/24/2023
PJM | AI2-150 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 0 | 44.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-151 | AC1-053 Tap 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-152 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 0 | 28.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-153 | Louisa-South Anna 230 kV |  | VA | Louisa | Active | Dominion | 0 | 31.95 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2022
PJM | AI2-154 | Moshannon-Milesburg 230 kV IX |  | PA | Centre | Active | APS | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-155 | Baker 138 kV II |  | WV | Hardy | Active | APS | 0 | 29.84 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-156 | East Springfield-London 138 kV III |  | OH | Clark | Active | ATSI | 0 | 43.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/1/2026
PJM | AI2-157 | Elk 138 kV |  | OH | Vinton | Active | AEP | 0 | 47.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/25/2023
PJM | AI2-158 | Fentress - Sligo 230kV (CIR Increase) |  | VA | City of Chesapeake | Withdrawn | Dominion | 0 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/1/2023 | 9/12/2023 |  | 12/31/2024
PJM | AI2-159 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 0 | 43.52 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/1/2027
PJM | AI2-160 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2020
PJM | AI2-161 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-162 | Meridian - Twin Branch 345 kV |  | IN | Whitley | Active | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-163 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Active | ComEd | 0 | 68.8 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-164 | Fostoria Central - Lemoyn 345 kV |  | OH | Wood | Active | AEP | 0 | 72 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-165 | Clinton - Stuart 345 kV |  | OH | Clinton | Active | Dayton | 0 | 72 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/25/2023
PJM | AI2-166 | Lanesville-Brokaw |  | IL | Logan | Active | ComEd | 0 | 78 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 12/15/2025
PJM | AI2-167 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 0 | 78 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2024
PJM | AI2-168 | Magley 138 kV |  | IN | Adams | Active | AEP | 0 | 32.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2024
PJM | AI2-169 | Brody 138 kV |  | MI | Cass | Active | AEP | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2025
PJM | AI2-170 | Delaware - Van Buren 138 kV |  | IN | Delaware | Active | AEP | 0 | 39.12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2022
PJM | AI2-171 | Cole Road 345 kV |  | OH | Franklin | Active | AEP | 0 | 40 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/25/2023
PJM | AI2-172 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 0 | 37.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2022
PJM | AI2-173 | West Newton-Lynn 138 kV |  | OH | Hardin | Active | AEP | 0 | 26.43 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2021
PJM | AI2-174 | Kenzie Creek - Colby 138 kV |  | MI | Cass | Active | AEP | 0 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/25/2023
PJM | AI2-175 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 0 | 20 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-176 | Todd 69 kV |  | MD | Dorchester | Active | DPL | 0 | 14.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2021
PJM | AI2-177 | Todd 25 kV |  | MD | Dorchester | Active | DPL | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 7/31/2021
PJM | AI2-178 | LaSalle 138 kV |  | IL | Lasalle | Active | ComEd | 0 | 36.51 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 3/17/2023
PJM | AI2-179 | Brokaw-Pontiac 345kV |  | IL | McLean | Active | ComEd | 0 | 97.5 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 3/17/2023
PJM | AI2-180 | LaSalle 138kV |  | IL | Lasalle | Active | ComEd | 0 | 6.16 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 2/28/2023 |  |  | 2/28/2023
PJM | AI2-181 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 0 | 27.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 6/30/2023
PJM | AI2-182 | Jennings-Hazelton 138kV II |  | WV | Preston | Active | APS | 0 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 2/28/2023 |  |  | 12/31/2025
PJM | AI2-183 | Spotsylvania 500kV |  | VA | Spotsylvania | Active | Dominion | 0 | 123.75 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 1/1/2028
PJM | AI2-184 | Whitely 138 kV |  | PA | Greene | Active | APS | 0 | 8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/1/2023 |  |  | 9/10/2023
PJM | AI2-185 | Franklin 138 kV |  | PA | Greene | Active | APS | 0 | 41 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/1/2023 |  |  | 9/10/2023
PJM | AI2-186 | Franklin 138 kV |  | PA | Greene | Active | APS | 0 | 20.25 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/1/2023 |  |  | 9/10/2023
PJM | AI2-187 | Mt. Storm 500kV |  | WV | Grant | Active | Dominion | 0 | 445 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/1/2027
PJM | AI2-188 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 0 | 246.25 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/1/2023 |  |  | 3/15/2028
PJM | AI2-189 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 0 | 66.25 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 3/15/2028
PJM | AI2-190 | Carbondale 138 kV |  | WV | Fayette | Active | AEP | 0 | 40.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 3/15/2028
PJM | AI2-191 | Lyons - Moselem Springs 69 kV |  | PA | Berks | Active | ME | 0 | 6.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 8/31/2023
PJM | AI2-192 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 0 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 4/15/2025
PJM | AI2-193 | East Hartford - Murch 69 kV |  | MI | Van Buren | Active | AEP | 0 | 28.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/30/2024
PJM | AI2-194 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 0 | 15.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/30/2025
PJM | AI2-195 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 0 | 69.88 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 4/30/2025
PJM | AI2-196 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 0 | 51.52 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 4/30/2025
PJM | AI2-197 | Reynolds - Olive 345 kV |  | IN | Pulaski | Active | AEP | 0 | 108 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 12/31/2021
PJM | AI2-198 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 0 | 108 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/31/2021
PJM | AI2-199 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 0 | 108 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/31/2021
PJM | AI2-200 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 0 | 144 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/31/2021
PJM | AI2-201 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 0 | 108 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/1/2023 |  |  | 5/31/2021
PJM | AI2-202 | Bennett - Farmingdale 34.5 kV |  | NJ | Monmouth | Active | JCPL | 0 | 1.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/11/2023
PJM | AI2-203 | Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 0 | 1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/30/2023
PJM | AI2-204 | Brokaw 345kV (CIR Increase) |  | NJ | Gloucester | Active | PSEG | 0 | 1.55 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 4/1/2023
PJM | AI2-205 | Branchville - Sussex 34.5 kV |  | NJ | Sussex | Active | JCPL | 0 | 5.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/29/2023
PJM | AI2-206 | Cardiff 12 kV |  | NJ | Atlantic | Active | AEC | 0 | 1.57 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/30/2023
PJM | AI2-207 | Rockawalkin 69 kV |  | MD | Wicomico | Active | DPL | 0 | 5.35 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/30/2023
PJM | AI2-208 | Hawks 12.5 kV |  | NJ | Hunterdon | Active | JCPL | 0 | 1.55 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/29/2023
PJM | AI2-209 | Burlington 26kV (CIR Increase) |  | NJ | Burlington | Active | PSEG | 0 | 3.05 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/29/2023
PJM | AI2-210 | Ringoes-US Bronze 34kV |  | NJ | Hunterdon | Active | JCPL | 0 | 4.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 3/29/2023
PJM | AI2-211 | Price 25 kV |  | MD | Queen Anne's | Active | DPL | 0 | 2.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/3/2023
PJM | AI2-212 | Manitou-Pleasant Plains 34.5 kV |  | NJ | Ocean | Active | JCPL | 0 | 10.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 4/1/2023
PJM | AI2-213 | Allenwood-Larrabee 2 34.5 kV |  | NJ | Monmouth | Active | JCPL | 0 | 3.05 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/29/2023
PJM | AI2-214 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Active | AEP | 0 | 55 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/12/2025
PJM | AI2-215 | Pokagon - Corey 69 kV |  | MI | Cass | Active | AEP | 0 | 18.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/31/2026
PJM | AI2-216 | Wurno - Claytor lake 138 kV |  | VA | Pulaski | Active | AEP | 0 | 77 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 9/13/2028
PJM | AI2-217 | Greene - Beatty 345 kV |  | OH | Madison | Active | AEP | 0 | 56.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/30/2025
PJM | AI2-218 | Galion - South Berwick 345 kV |  | OH | Wyandot | Active | AEP | 0 | 43.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/30/2025
PJM | AI2-219 | Groton 138 kV II |  | OH | Erie | Active | ATSI | 0 | 45.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 11/30/2024
PJM | AI2-220 | Beaver-Davis Besse 345 kV II |  | OH | Erie | Active | ATSI | 0 | 103.1 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2024
PJM | AI2-221 | Snyder 69 kV II |  | OH | Williams | Active | ATSI | 0 | 17.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2024
PJM | AI2-222 | Chase City-Lunenburg 115kV |  | VA | Lunenburg | Active | Dominion | 0 | 47.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2024
PJM | AI2-223 | WinFall-Chowan 230kV |  | NC | Chowan | Active | Dominion | 0 | 56.4 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 5/28/2024
PJM | AI2-224 | Central-Chase City 115kV |  | VA | Charlotte | Active | Dominion | 0 | 55 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/30/2025
PJM | AI2-225 | Lexington-Low Moor 230kV |  | VA | Botetourt | Active | Dominion | 0 | 32 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 11/3/2025
PJM | AI2-226 | Jug Street 138 kV |  | OH | Licking | Active | AEP | 0 | 120 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 8/22/2022
PJM | AI2-227 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 0 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/1/2023
PJM | AI2-228 | Silver Lake 345 |  | IL | McHenry | Active | ComEd | 0 | 240 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 11/6/2024
PJM | AI2-229 | Silver Lake 138 |  | IL | McHenry | Active | ComEd | 0 | 120 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 11/6/2024
PJM | AI2-230 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Active | Dominion | 0 | 120 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/1/2023
PJM | AI2-231 | Gainesville-Loudoun 230 kV |  | VA | Prince William | Active | Dominion | 0 | 120 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 10/22/2023
PJM | AI2-231A | Cloverdale-Burlington Height 138 kV |  | VA | Botetourt | Active | AEP | 0 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 10/22/2023
PJM | AI2-232 | Shady Oaks Road 138 kV |  | IL | Lee | Active | ComEd | 0 | 99.5 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2023
PJM | AI2-233 | Eagle Valley 115kV II |  | PA | Centre | Active | PENELEC | 0 | 49.4 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2023
PJM | AI2-234 | Mole Creek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 0 | 92.4 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 4/1/2023
PJM | AI2-235 | King's Creek 138 kV |  | MD | Somerset | Active | DPL | 0 | 62.652 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/2/2023
PJM | AI2-236 | Smith Mountain - Candler Mountain 138 kV |  | VA | Campbell | Active | AEP | 0 | 22.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 3/1/2023
PJM | AI2-237 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 0 | 69.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 6/1/2024
PJM | AI2-238 | College Corner 138 kV |  | OH | Preble | Active | AEP | 0 | 39.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-239 | Harmony Village-Shackleford 115 kV |  | VA | Gloucester | Active | Dominion | 0 | 50.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2024
PJM | AI2-240 | Camden - Crystal 69 kV |  | OH | Preble | Active | Dayton | 0 | 25.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-241 | Congress-Toronto 138 kV II |  | OH | Columbiana | Active | ATSI | 0 | 55.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-242 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 0 | 63 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2024
PJM | AI2-243 | Ecogrove 138 kV (CIR Increase) |  | IL | Stephenson | Active | ComEd | 0 | 80.3 | Capacity | Generation Interconnection | Solar; Wind | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2027
PJM | AI2-244 | Victoria DP-Martin DP 115 kV |  | VA | Nottoway | Active | Dominion | 0 | 50.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2028
PJM | AI2-245 | TSS 968 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 0 | 55.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2028
PJM | AI2-246 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/30/2024
PJM | AI2-248 | Schauff Road 138 kV |  | IL | Lee | Active | ComEd | 0 | 40 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 11/25/2019
PJM | AI2-249 | Biers Run-Circleville 138 kV |  | OH | Ross | Active | AEP | 0 | 40 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 4/14/2023
PJM | AI2-250 | Greenfield 69 kV |  | OH | Fayette | Active | Dayton | 0 | 10 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/31/2024
PJM | AI2-251 | Buckskin 69kV |  | OH | Ross | Active | AEP | 0 | 10 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 7/31/2024
PJM | AI2-252 | Hillsboro-Clinton 138kV |  | OH | Ross | Active | AEP | 0 | 20 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 9/30/2024
PJM | AI2-253 | Chatfield-Howard 138kV |  | OH | Crawford | Active | AEP | 0 | 20 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 9/1/2025
PJM | AI2-254 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 0 | 15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2028
PJM | AI2-255 | Clubhouse- Purdy 115kV |  | VA | Greensville | Withdrawn | Dominion | 0 | 25 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/2/2023 | 11/21/2024 |  | 10/1/2028
PJM | AI2-256 | Gary 115kV |  | VA | Lunenburg | Withdrawn | Dominion | 0 | 20 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/2/2023 | 6/28/2023 |  | 10/1/2028
PJM | AI2-257 | Cordova 345kV (CIR Increase) |  | IL | Lee | Withdrawn | ComEd | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2028
PJM | AI2-259 | Greentown 138 kV |  | IN | Howard | Withdrawn | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/2/2023 | 11/23/2024 |  | 10/1/2028
PJM | AI2-260 | Keeney - Steele 230 kV |  | MD | Caroline | Active | DPL | 0 | 82.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/30/2025
PJM | AI2-261 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 0 | 25 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2028
PJM | AI2-263 | Nelson 345kV (CIR Increase) |  | IL | Lee | Withdrawn | ComEd | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2028
PJM | AI2-264 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2025
PJM | AI2-265 | Kincaid 345kV (CIR Increase) |  | IL | Christian | Withdrawn | ComEd | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2028
PJM | AI2-266 | R.P.Mone 345 kV |  | OH | Van Wert | Withdrawn | AEP | 0 | 24 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/2/2023 | 11/23/2024 |  | 10/1/2028
PJM | AI2-267 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 0 | 25 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/1/2028
PJM | AI2-269 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 0 | 32.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-270 | East Lima-Marysville 345kV |  | OH | Hardin | Active | AEP | 0 | 45 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 2/25/2023
PJM | AI2-271 | Smith Mountain-Bearskin 138 kV |  | VA | Pittsylvania | Active | AEP | 0 | 14.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 2/27/2023
PJM | AI2-272 | Pantago-Five Points 115kV |  | NC | Beaufort | Active | Dominion | 0 | 32.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 2/23/2023
PJM | AI2-273 | Boykins-Handsome 115kV |  | VA | Southampton | Active | Dominion | 0 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 2/25/2023
PJM | AI2-274 | Powhatan 34.5 kV |  | VA | Powhatan | Active | Dominion | 0 | 6.8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2023
PJM | AI2-275 | Garner-Northern Neck 115 kV |  | VA | Pittsylvania | Active | Dominion | 0 | 5.04 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 2/24/2023
PJM | AI2-277 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 0 | 45 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-278 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 0 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/1/2027
PJM | AI2-279 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 0 | 43 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-280 | Carson-Wake 500kV |  | VA | Brunswick | Active | Dominion | 0 | 34 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/2/2023 |  |  | 2/24/2023
PJM | AI2-281 | Heritage-Carson |  | VA | Greensville | Active | Dominion | 0 | 44.9 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2025
PJM | AI2-282 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 0 | 11.3 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/3/2023 |  |  | 2/27/2023
PJM | AI2-283 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 0 | 12.3 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/2/2023 |  |  | 2/27/2023
PJM | AI2-284 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 0 | 10.2 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/2/2023 |  |  | 3/1/2023
PJM | AI2-285 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 0 | 9.9 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/2/2023 |  |  | 2/27/2023
PJM | AI2-286 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 0 | 9.4 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/2/2023 |  |  | 2/27/2023
PJM | AI2-287 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 0 | 18.3 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/2/2023 |  |  | 2/27/2023
PJM | AI2-288 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 0 | 16.9 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/2/2023 |  |  | 2/27/2023
PJM | AI2-289 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 0 | 16.3 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 3/3/2023 |  |  | 2/27/2023
PJM | AI2-290 | Brookside-Cloverdale 138 kV II |  | OH | Wayne | Active | ATSI | 0 | 9.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-291 | Edison-Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 0 | 10.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-292 | Hunterstown-Texas Eastern Tap 115 kV III |  | PA | Adams | Active | ME | 0 | 4.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-293 | Edinboro South-Venango Junction 115 kV IV |  | PA | Crawford | Active | PENELEC | 0 | 8.16 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-294 | Laurel Mountain 138 kV |  | WV | Randolph | Active | APS | 0 | 52.9 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/3/2023 |  |  | 1/1/2028
PJM | AI2-295 | Cox-Whitakers 115kV |  | NC | Halifax | Active | Dominion | 0 | 20.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 1/1/2028
PJM | AI2-296 | Chickahominy 230kV |  | VA | Charles City | Active | Dominion | 0 | 83.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 6/25/2025
PJM | AI2-297 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 0 | 18.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 1/1/2028
PJM | AI2-298 | McConnellsburg-Texas Eastern 138 kV |  | PA | Franklin | Active | APS | 0 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 1/1/2028
PJM | AI2-299 | Benson-Dunbar 115 kV |  | NC | Edgecombe | Active | Dominion | 0 | 30.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/11/2020
PJM | AI2-300 | Elizabeth City 34.5 kV |  | NC | Pasquotank | Active | Dominion | 0 | 6.36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 10/18/2021
PJM | AI2-301 | Dawson-South Justice 115kV |  | NC | Halifax | Active | Dominion | 0 | 45.12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 6/30/2025
PJM | AI2-302 | Jacksonville Tap - Renaker 138 kV |  | KY | Harrison | Active | EKPC | 0 | 26.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 8/30/2024
PJM | AI2-303 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 0 | 18.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2025
PJM | AI2-304 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 0 | 36.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-305 | Ebersole #2-Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 0 | 33.64 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2025
PJM | AI2-306 | Osterburg - Bedford North 23 kV II |  | PA | Bedford | Active | PENELEC | 0 | 4.37 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 7/18/2025
PJM | AI2-307 | Colora 230 kV |  | MD | Cecil | Active | DPL | 0 | 60.48 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/3/2023 |  |  | 9/10/2026
PJM | AI2-308 | Snake Spring-Bedford Area 23 kV |  | PA | Bedford | Active | PENELEC | 0 | 4.37 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/27/2024
PJM | AI2-309 | Marysville-Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 0 | 90.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 4/15/2025
PJM | AI2-310 | Emlenton 34.5 kV II |  | PA | Venango | Active | PENELEC | 0 | 7.28 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/3/2025
PJM | AI2-311 | Ringgold 138 kV II |  | MD | Washington | Active | APS | 0 | 30 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 1/11/2025
PJM | AI2-312 | Clark Summit 34.5 kV II |  | PA | Venango | Active | PENELEC | 0 | 5.46 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/15/2022
PJM | AI2-313 | Ravenswood-Hemlock 69kV |  | OH | Meigs | Active | AEP | 0 | 17.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2023
PJM | AI2-314 | Molecreek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 0 | 27 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2025
PJM | AI2-315 | Mole Creek 345 kV |  | IL | Woodford | Active | ComEd | 0 | 90 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2025
PJM | AI2-316 | Powerton 345 kV (CIR increase) |  | IL | Woodford | Active | ComEd | 0 | 19 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2024
PJM | AI2-317 | Powertn - Goodings Grove 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 0 | 133 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2024
PJM | AI2-318 | White Marsh 34.5 kV |  | VA | Gloucester | Active | Dominion | 0 | 12.84 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-320 | Edinboro South - Erie South 25 kV |  | PA | Erie | Active | PENELEC | 0 | 5.05 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-321 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 0 | 8.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-322 | Findlay - Midfield 23 kV |  | PA | Allegheny | Active | DL | 0 | 1.18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-323 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 0 | 7.56 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-324 | Cowansville Junction – Long Run Tap 25 kV |  | PA | Armstrong | Active | APS | 0 | 3.72 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-325 | Oyster Creek 230 kV |  | NJ | Ocean | Active | JCPL | 0 | 178.7 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2024
PJM | AI2-326 | BL England 138 kV |  | NJ | Cape May | Active | AEC | 0 | 94.6 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2024
PJM | AI2-327 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 0 | 19.91 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 10/15/2023
PJM | AI2-328 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 0 | 100 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-329 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 0 | 100 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-330 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 0 | 83.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2028
PJM | AI2-331 | Hopkins 138 kV |  | WV |  | Active | AEP | 0 | 42.84 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/1/2025
PJM | AI2-332 | Gilboa-Jones Branch 138 kV IV |  | WV | Nicholas | Active | APS | 0 | 40 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 6/1/2030
PJM | AI2-333 | Johns Creek-Excel 138kV I |  | KY | Pike | Active | AEP | 0 | 40 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/1/2026
PJM | AI2-334 | Inez 138 kV |  | KY | Martin | Active | AEP | 0 | 34.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/30/2026
PJM | AI2-335 | Inez 138 kV |  | KY | Martin | Active | AEP | 0 | 34.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-336 | Nottingham Switch 138 kV |  | OH | Harrison | Active | AEP | 0 | 34.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/10/2026
PJM | AI2-337 | Broadview-Tangy 138 kV IV |  | OH | Madison | Active | ATSI | 0 | 30 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/1/2023
PJM | AI2-338 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 0 | 29.15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/1/2024
PJM | AI2-339 | Gilboa-Jones Branch 138 kV V |  | WV | Nicholas | Active | APS | 0 | 26.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/1/2024
PJM | AI2-340 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 0 | 23.1 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/1/2025
PJM | AI2-341 | Galion-Roberts South 138 kV III |  | OH | Marion | Active | ATSI | 0 | 22.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/1/2024
PJM | AI2-342 | Excel-Johns Creek 138 kV |  | KY | Pike | Active | AEP | 0 | 15.38 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 3/31/2027
PJM | AI2-343 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 0 | 15.25 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/3/2025
PJM | AI2-344 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 0 | 17 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/1/2024
PJM | AI2-345 | Amherst-Riverville138 kV |  | VA | Amherst | Active | AEP | 0 | 18 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 6/1/2025
PJM | AI2-346 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 0 | 20 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 9/10/2025
PJM | AI2-347 | Van Arsdell-Mercer Industrial 69kV |  | KY | Mercer | Active | EKPC | 0 | 17 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 9/1/2026
PJM | AI2-348 | Ford - Ceddarville 138 kV |  | OH | Clermont | Active | DEOK | 0 | 17.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-349 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 0 | 11 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 2/28/2029
PJM | AI2-350 | Hillsboro - Wye Mills 138 kV |  | MD | Queen Anne's | Active | DPL | 0 | 11.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 5/1/2025
PJM | AI2-351 | Lappans 34.5kV II |  | MD | Washington | Withdrawn | APS | 0 | 1 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/3/2023 | 9/11/2023 |  | 6/1/2025
PJM | AI2-352 | Martins Creek–Cherry Hill 69 kV |  | PA | Northampton | Withdrawn | PPL | 22 | 22 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/4/2023 | 6/26/2024 |  | 12/31/2025
PJM | AI2-353 | Carlos Jct. – Ridgeley 138 kV |  | MD | Allegany | Active | APS | 0 | 16 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/3/2023 |  |  | 4/1/2024
PJM | AI2-354 | Williams 138 kV |  | WV | Grant | Active | APS | 0 | 58.7 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/3/2023 |  |  | 1/1/2026
PJM | AI2-355 | Greenland Gap 500 kV |  | WV | Grant | Active | APS | 0 | 103.8 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/3/2023 |  |  | 4/3/2023
PJM | AI2-356 | Greenland Gap 500 kV II |  | WV | Grant | Active | APS | 0 | 57.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 7/31/2027
PJM | AI2-357 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 0 | 18.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/6/2023 |  |  | 12/31/2025
PJM | AI2-358 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 0 | 70 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/8/2023 |  |  | 5/1/2028
PJM | AI2-359 | Cross School 138 kV |  | WV | Mineral | Active | APS | 0 | 13.1 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 4/3/2023
PJM | AI2-360 | Elk Garden - Parr Run 138 kV |  | WV | Mineral | Active | APS | 0 | 45.9 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 4/3/2023
PJM | AI2-361 | Hooversville - Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 0 | 10.17 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 3/2/2023
PJM | AI2-362 | Rockwood - Meyersdale North 115 kV |  | PA | Somerset | Active | PENELEC | 0 | 13 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 4/3/2023
PJM | AI2-364 | Brokaw - Lanesville 345 kV (CIR Increase) |  | IL | Fulton | Active | ComEd | 0 | 79.91 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 4/20/2023
PJM | AI2-365 | Lake Lynn-Hazelton 138 kV II |  | WV | Preston | Active | APS | 0 | 32.06 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 9/30/2021
PJM | AI2-366 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 0 | 93.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 9/25/2024
PJM | AI2-367 | Sleepy Hollow 138 kV II |  | WV | Jefferson | Active | APS | 0 | 34 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 6/30/2023
PJM | AI2-368 | TSS 994 345 kV (CIR Increase) |  | IL | Logan | Active | ComEd | 0 | 77.87 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 4/17/2023
PJM | AI2-369 | Apple Grove 138 kV |  | WV | Mason | Active | AEP | 0 | 29.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 6/30/2023
PJM | AI2-370 | Twombley Road 138kV (CIR Increase) |  | IL | Ogle | Active | ComEd | 0 | 19.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 4/1/2026
PJM | AI2-371 | Walnut Grove - Asahi Tap 69 kV |  | KY | McLean | Active | EKPC | 0 | 17.78 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 9/25/2024
PJM | AI2-372 | Hill Topper 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 0 | 23.56 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/3/2023 |  |  | 3/30/2020
PJM | AI2-373 | Easton - Steele 138 kV |  | MD | Talbot | Active | DPL | 0 | 23.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 3/31/2026
PJM | AI2-374 | Hope-Blevins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 0 | 20.59 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 3/31/2025
PJM | AI2-375 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2026
PJM | AI2-376 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Withdrawn | EKPC | 0 | 21.84 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/3/2023 | 10/23/2024 |  | 3/31/2025
PJM | AI2-377 | Maysville 69 kV VI |  | PA | Mercer | Active | ATSI | 0 | 15.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/1/2024
PJM | AI2-378 | Merrill Creek 115 kV II |  | NJ | Warren | Active | JCPL | 0 | 28 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/1/2024
PJM | AI2-379 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 0 | 24.51 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/1/2024
PJM | AI2-380 | Altoona-Raystown 230 kV III |  | PA | Blair | Withdrawn | PENELEC | 0 | 30.16 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/4/2023 | 8/7/2024 |  | 12/1/2024
PJM | AI2-381 | Layland 69 kV |  | WV | Fayette | Withdrawn | AEP | 0 | 35.5 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/4/2023 | 1/16/2025 |  | 12/1/2024
PJM | AI2-383 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 0 | 26.29 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 12/1/2024
PJM | AI2-384 | Nelson 138kV (CIR Increase) |  | IL | Lee | Active | ComEd | 0 | 89.44 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 12/31/2027
PJM | AI2-385 | South Millville - Newport 69 kV |  | NJ | Cumberland | Active | AEC | 0 | 23.57 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 3/31/2025
PJM | AI2-386 | PG - Juniata 69 kV |  | PA | Dauphin | Active | PPL | 0 | 20.74 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 12/31/2026
PJM | AI2-387 | Carlls Corner - Sherman Ave 69 kV |  | NJ | Cumberland | Active | AEC | 0 | 19.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 12/31/2024
PJM | AI2-388 | Milton 69 kV |  | PA | Northumberland | Active | PPL | 0 | 20.15 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/4/2023 |  |  | 12/31/2024
PJM | AI2-389 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Withdrawn | ComEd | 0 | 134.16 | Capacity | Generation Interconnection | Wind | Withdrawn |  |  |  | 3/4/2023 | 1/16/2025 |  | 12/31/2027
PJM | AI2-390 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Active | ComEd | 0 | 134.16 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/4/2023 |  |  | 12/31/2027
PJM | AI2-391 | Emporia-Trego 115kV |  | VA | Greensville | Active | Dominion | 0 | 13 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2023 |  |  | 2/25/2023
PJM | AI2-392 | Beatty-London 138 kV |  | OH | Madison | Active | AEP | 0 | 31.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-393 | Hickory-Moyock 230 kV |  | NC | Currituck | Active | Dominion | 0 | 17.7 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-394 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 0 | 66 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-395 | Reynolds–Olive #1 345 kV |  | IN | White | Active | AEP | 0 | 59.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-396 | Jay-Desoto 138kV |  | IN | Blackford | Active | AEP | 0 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/3/2023 |  |  | 12/31/2026
PJM | AI2-397 | West Manchester-Crown 69kV |  | OH | Preble | Active | AEP | 0 | 19.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-398 | West Manchester 69 kV |  | OH | Preble | Active | AEP | 0 | 9.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-399 | Jay 138 kV |  | IN | Jay | Active | AEP | 0 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-400 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 0 | 25 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-401 | Olive-Reynolds #1 345 kV |  | IN | White | Active | AEP | 0 | 48 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-402 | Kirk - Newark Center 138 kV |  | OH | Licking | Active | AEP | 0 | 25.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-403 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 0 | 19.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-404 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 0 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-405 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 0 | 22.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-407 | Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 0 | 31.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2025
PJM | AI2-408 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 0 | 72 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-409 | Wayne-Byron 345 kV |  | IL | DeKalb | Active | ComEd | 0 | 72 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-410 | Glidden - Cherry Valley 138 kV |  | IL | DeKalb | Active | ComEd | 0 | 28.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-411 | Glidden - Waterman 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 0 | 22.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-412 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 0 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-413 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 0 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-414 | Lynnville-South Hamburg 69 kV |  | PA | Berks | Active | ME | 0 | 12.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-415 | Campbell-Kiesters 138 kV |  | PA | Butler | Active | APS | 0 | 20.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-416 | Lexington-Dooms 230 kV |  | VA | Augusta | Active | Dominion | 0 | 50 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-417 | Wayne 345kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-418 | Sowers 138 kV |  | IN | Allen | Active | AEP | 0 | 24 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2026
PJM | AI2-419 | Oak Grove – Saunders DP 230 kV |  | VA | Westmoreland | Withdrawn | Dominion | 0 | 25 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/2/2023 | 3/28/2023 |  | 12/31/2027
PJM | AI2-420 | Crego Road 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 0 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2027
PJM | AI2-421 | Varner 345 kV |  | IN | DeKalb | Active | AEP | 0 | 43.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2027
PJM | AI2-422 | Jay 138 kV |  | IN | Jay | Active | AEP | 0 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2027
PJM | AI2-423 | Jay 69 kV |  | IN | Jay | Active | AEP | 0 | 12 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2027
PJM | AI2-424 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 0 | 28 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2028
PJM | AI2-425 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 0 | 40 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2028
PJM | AI2-426 | Allen - RP Mone 345 kV |  | IN | Allen | Active | AEP | 0 | 43.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2027
PJM | AI2-427 | Hazelton - Kirk 138 kV |  | OH | Licking | Active | AEP | 0 | 26.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/2/2023 |  |  | 12/31/2027
PJM | AI2-428 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 0 | 20.1 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/9/2023 |  |  | 12/31/2025
PJM | AI2-429 | Mendota Hills 138 kV |  | IL | Lee | Active | ComEd | 0 | 22.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/9/2023 |  |  | 12/31/2025
PJM | AI2-430 | Auburn 69 kV |  | IN | DeKalb | Active | AEP | 11 | 10 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2023 |  |  | 7/1/2023
PJM | AI2-431 | Larrabee Collector Station 230 kV |  | NJ | Atlantic | Active | JCPL | 2138.85 | 2083 | Capacity | Generation Interconnection | Offshore Wind | In Progress |  |  |  | 3/10/2023 |  |  | 2/28/2030
PJM | AI2-432 | Philipsburg-Clarence 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 0 | 7.28 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2023 |  |  | 12/27/2022
PJM | AI2-433 | Dubois-Curwensville 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 0 | 7.28 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/9/2023 |  |  | 2/28/2023
PJM | AI2-434 |  |  | PA | Lycoming | Active | PPL | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2023 |  |  | 12/31/2026
PJM | AI2-435 | South Hamburg – St. Peters Village 69 kV |  | PA | Berks | Active | ME | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2023 |  |  | 12/31/2026
PJM | AI2-436 | Luthersburg - Curwensville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/9/2023 |  |  | 12/31/2026
PJM | AI2-437 | Glen Gardner - Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2024
PJM | AI2-438 | Apple Valley 138kV |  | OH | Knox | Active | AEP | 150 | 148 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 7/10/2027
PJM | AI2-439 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2027
PJM | AI2-440 | Phillipsburg 115 kV |  | PA | Centre | Active | PENELEC | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2027
PJM | AI2-441 | Salem - Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2027
PJM | AI2-442 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 20 | 20 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2027
PJM | AI2-443 | North Longview 500 kV |  | PA | Greene | Active | APS | 300 | 295 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 7/10/2027
PJM | AI2-444 | Rum Creek 138kV |  | WV |  | Active | AEP | 59.5 | 52.1 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 3/8/2026
PJM | AI2-445 | Parsons - William 138 kV |  | WV | Tucker | Active | APS | 148 | 128.8 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 3/8/2026
PJM | AI2-446 | Medera - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 150 | 150 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2027
PJM | AI2-447 | Hillsboro-Wildcat 138kV |  | OH | Highland | Active | AEP | 0 | 87.3 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 9/30/2023
PJM | AI2-448 | Curdsville-Willis Mtn 115 kV |  | VA | Buckingham | Active | Dominion | 0 | 36.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2025
PJM | AI2-449 | Disputanta-Poe 115 kV |  | VA | Prince George | Active | Dominion | 0 | 36.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2025
PJM | AI2-450 | DeSoto-Keystone 345 kV |  | IN | Blackford | Active | AEP | 0 | 48.6 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/11/2023 |  |  | 12/31/2025
PJM | AI2-451 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 0 | 13.9 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 12/31/2025
PJM | AI2-452 | Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 0 | 51.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 12/31/2025
PJM | AI2-453 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 0 | 28.2 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 12/31/2025
PJM | AI2-454 | Mazon-Oglesby 138kV (CIR Increase) |  | IL | Grundy | Active | ComEd | 0 | 42 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 12/31/2025
PJM | AI2-455 | W4-005 345kV (CIR Increase) |  | PA | Union | Active | ComEd | 0 | 162.8 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/11/2023 |  |  | 3/31/2023
PJM | AI2-456 | Birchwood - Fines Corner 230 kV |  | VA | King George | Active | Dominion | 150 | 150 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/11/2023 |  |  | 9/15/2027
PJM | AI2-457 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 1122 | 1122 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/11/2023 |  |  | 10/1/2027
PJM | AI2-458 | Bernville 34.5 kV 1 |  | PA | Berks | Active | ME | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-459 | Bernville 34.5 kV 2 |  | PA | Berks | Active | ME | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-460 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 0 | 36 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-461 | Wilton Center - Loretto 345 kV(CIR Increase) |  | IL | Kankakee | Active | ComEd | 0 | 173 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2026
PJM | AI2-462 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 0 | 48 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-463 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-464 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-465 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-466 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-467 | Maysville 138 kV |  | PA | Mercer | Active | ATSI | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-468 | Summit Road 12.5 kV |  | PA | Mercer | Active | ATSI | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-469 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-470 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-471 | Montour 230 kV |  | PA | Montour | Active | PPL | 0 | 29.464 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2025
PJM | AI2-472 | Montour 230 kV |  | PA | Montour | Active | PPL | 0 | 14.5 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2026
PJM | AI2-473 | Montour 230 kV |  | PA | Montour | Active | PPL | 0 | 29 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2026
PJM | AI2-474 | Montour 230 kV |  | PA | Montour | Active | PPL | 0 | 34.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2026
PJM | AI2-475 | Montour 230 kV |  | PA | Montour | Active | PPL | 0 | 40.6 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2026
PJM | AI2-476 | Snake Spring 115 kV |  | PA | Bedford | Active | PENELEC | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-477 | Snake Spring 115 kV II |  | PA | Bedford | Active | PENELEC | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-478 | Snake Spring 115 kV III |  | PA | Bedford | Withdrawn | PENELEC | 0 | 5.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/11/2023 | 10/24/2023 |  | 5/1/2027
PJM | AI2-479 | Snake Spring 115 kV |  | PA | Bedford | Withdrawn | PENELEC | 0 | 5.8 | Capacity | Generation Interconnection | Solar | Withdrawn |  |  |  | 3/11/2023 | 10/24/2023 |  | 5/1/2027
PJM | AI2-480 | Crawford 34.5 kV |  | PA | Crawford | Active | PENELEC | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2027
PJM | AI2-481 | Union City - French Road 12.5kV |  | PA | Erie | Active | PENELEC | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/11/2023 |  |  | 5/1/2026
PJM | AI2-482 | Copperstone-North Lebanon 230 kV IV |  | PA | Lebanon | Active | ME | 0 | 58 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/7/2023 |  |  | 12/1/2023
PJM | AI2-483 | Heath 69 kV |  | OH | Licking | Active | AEP | 0 | 13.44 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 3/7/2023 |  |  | 7/1/2025
PJM | AI2-484 | Heidelberg 69 kV |  | PA | Lebanon | Active | PPL | 0 | 5.8 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 5/1/2027
PJM | AI2-485 | Bruin Junction - Petrol Junction 25 kV |  | PA | Butler | Active | APS | 14 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 12/1/2028
PJM | AI2-486 | Bethelboro - Connellsville 25 kV |  | PA | Fayette | Active | APS | 14 | 8.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 3/10/2023 |  |  | 12/1/2028
PJM | AI2-487 | Kewanee-Hennepin Tap 138kV |  | IL | Bureau | Active | ComEd | 0 | 97.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2026
PJM | AI2-488 | Electric Junction - Nelson 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 0 | 97.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2026
PJM | AI2-489 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 0 | 97.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2023 |  |  | 12/31/2025
PJM | AI2-490 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 0 | 31.9 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2023 |  |  | 12/15/2023
PJM | AI2-491 | East Lima-Marysville 345kV |  | OH | Champaign | Active | AEP | 0 | 133 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2023 |  |  | 5/31/2021
PJM | AI2-492 | Deer Creek-Fisher Body-Mullin 138kV |  | IN | Grant | Active | AEP | 0 | 106.4 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/10/2023 |  |  | 12/26/2012
PJM | AI2-493 | New Baltimore 115kV (Stony Creek) |  | PA | Somerset | Active | PENELEC | 0 | 18.2 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 3/11/2023 |  |  | 8/31/2023
PJM | AJ1-001 | Boydton DP 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/21/2023 |  |  | 12/1/2028
PJM | AJ1-002 | North River Delivery Point 115 kV |  | VA | Rockingham | Active | Dominion | 100 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/21/2023 |  |  | 12/1/2028
PJM | AJ1-003 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 100 | 40 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 4/21/2023 |  |  | 12/1/2028
PJM | AJ1-008 | Zimmer 345 kV |  | OH | Clermont | Active | DEOK | 800 | 692.3 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 5/8/2023 |  |  | 10/1/2028
PJM | AJ1-009 |  |  | NJ | Essex | Active | PSEG | 60 | 60 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 5/18/2023 |  |  | 12/1/2027
PJM | AJ1-010 | Racine - Sarah Lane 69 kV |  | WV | Mason | Active | AEP | 35 | 7.098 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 5/22/2023 |  |  | 7/1/2025
PJM | AJ1-011 | Waukegan Unit 7 CIR Transfer |  | IL | Lake | Active | ComEd | 328 | 328 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 5/24/2023 |  |  | 6/1/2027
PJM | AJ1-012 | Waukegan Unit 8 CIR Transfer |  | IL | Lake | Active | ComEd | 354.4 | 354.4 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 5/24/2023 |  |  | 6/1/2027
PJM | AJ1-013 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 250 | 250 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 5/24/2023 |  |  | 6/1/2027
PJM | AJ1-014 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 260 | 260 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 5/24/2023 |  |  | 6/1/2027
PJM | AJ1-015 | Larrabee Collector 230 kV |  | NJ | Monmouth | Active | JCPL | 1342 | 403 | Capacity | Generation Interconnection | Wind | In Progress |  |  |  | 6/2/2023 |  |  | 5/1/2030
PJM | AJ1-016 | Cambria Slope 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 6/7/2023 |  |  | 11/9/2028
PJM | AJ1-018 | Bishopville – Worcester 138 kV |  | MD | Worcester | Active | DPL | 39 | 39 | Capacity | Generation Interconnection | Solar; Storage | In Progress |  |  |  | 6/22/2023 |  |  | 12/29/2028
PJM | AJ1-019 | Bell Avenue 115 kV |  | VA | Southampton | Active | Dominion | 100 | 100 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 6/28/2023 |  |  | 12/1/2028
PJM | AJ1-020 | St. Johns – Woodpecker 115 kV |  | VA | Caroline | Active | Dominion | 86.38 | 51.828 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/30/2023 |  |  | 12/15/2029
PJM | AJ1-021 | Woodpecker – Slabtown 115 kV |  | VA | Caroline | Active | Dominion | 16.2 | 10.0584 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/30/2023 |  |  | 12/15/2029
PJM | AJ1-022 | Kerr Dam - Henderson NC 115 kV |  | VA | Mecklenburg | Active | Dominion | 49 | 29.4 | Capacity | Generation Interconnection | Solar | In Progress |  |  |  | 6/30/2023 |  |  | 6/30/2027
PJM | AJ1-023 | Trumbull 345 kV |  | OH | Trumbull | Active | ATSI | 70 | 70 | Capacity | Generation Interconnection | Natural Gas | In Progress |  |  |  | 6/30/2023 |  |  | 12/1/2024
PJM | AJ1-037 | Northeast - CP Crane 115 kV |  | MD | Baltimore County | Active | BGE | 300 | 300 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 7/8/2023 |  |  | 10/1/2028
PJM | AJ1-038 | Penniman 34.5 kV |  | VA | York | Active | Dominion | 33 | 33 | Capacity | Generation Interconnection | Storage | In Progress |  |  |  | 6/29/2023 |  |  | 12/1/2025