## Data
Project ID | Name | Commercial Name | State | County | Status | Transmission Owner | MFO | MW Energy | MW Capacity | MW In Service | Capacity or Energy | Project Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim Interconnection Service Agreement | Interim/Interconnection Service Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Backfeed Date | Submitted Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Commercial Operation Milestone | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Project | Sliding Project
S14 | Dans Mountain | Dans Mountain | PA | Allegheny | Engineering and Procurement | APS | 70 | 54.9 | 14 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/s14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s14_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s14_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s14_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/s14_csa.pdf | Document Posted | N/A | N/A |  | 3/19/2007 | N/A | N/A | 11/1/2024 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
Z1-036 | WinFall-Chowan 230kV | Timbermill Wind Farm | NC | Perquimans | Under Construction | Dominion | 189 | 189 | 24.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1036_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/z1_036_csa.pdf | Document Posted | N/A | N/A | 10/15/2024 | 7/23/2013 | N/A | N/A | 11/1/2024 |  |  | 3/31/2025 | 3/31/2025 |  | N | No
AA1-038 | Lexington-Low Moor 230kV |  | VA | Botetourt | Engineering and Procurement | Dominion | 78.2 | 78.2 | 10.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_038_csa.pdf | Document Posted | N/A | N/A | 11/5/2025 | 8/19/2014 | N/A | N/A | 11/5/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AA1-102 | Kings Creek-Loretto 138kV | Perry Road Solar | MD | Somerset | Partially in Service - Under Construction | DPL | 150 | 150 | 57 | 118 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1102_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1102_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_102_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa1_102_csa.pdf | Document Posted | N/A | N/A |  | 10/30/2014 | N/A | N/A | 12/28/2017 |  |  | 12/31/2023 | 12/31/2023 | 12/28/2017 | N | No
AA2-119 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2119_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2119_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_119_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/aa2_119_csa.pdf | Document Posted | N/A | N/A | 8/31/2026 | 4/30/2015 | N/A | N/A | 3/31/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AB1-021 | West Caldwell 13kV | West Caldwell Solar | NJ | Essex | Partially in Service - Under Construction | PSEG | 2 | 2 | 0.3 | 0.3 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1021_wmpa.pdf |  | Not Required | N/A | N/A |  | 6/29/2015 | N/A | N/A | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 6/1/2018 | N | No
AB1-056 | Indian River 230kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Engineering and Procurement | DPL | 247.8 | 247.8 | 64.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1056_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1056_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_056_csa.pdf | Document Posted | N/A | N/A | 2/1/2027 | 8/31/2015 | N/A | N/A | 12/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AB1-063 | Locust St. 13kV | Cooper Solar | NJ | Camden | Partially in Service - Under Construction | PSEG; PSEG | 0.4 | 0.4 | 0 | 0.2 | Energy | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1063_wmpa.pdf |  | Not Required | N/A | N/A |  | 9/1/2015 | N/A | N/A | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 2/15/2017 | N | No
AB1-087 | Sullivan 345kV #1 | Sullivan Generating Station 1 | IN | Sullivan | Engineering and Procurement | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1087_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_087_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_087_csa.pdf | Document Posted | N/A | N/A |  | 10/1/2015 | N/A | N/A |  |  |  | 6/1/2025 | 6/1/2025 |  | N | No
AB1-088 | Sullivan 345kV #2 | Sullivan Generating Station 2 | IN | Sullivan | Engineering and Procurement | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_088_csa.pdf | Document Posted | N/A | N/A |  | 10/1/2015 | N/A | N/A |  |  |  | 6/1/2025 | 6/1/2025 |  | N | No
AB1-105 | Highland-Hanna 345kV | Trumbull Energy Center | OH | Trumbull | Under Construction | ATSI | 940 | 940 | 850 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1105_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1105_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_105_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_105_csa.pdf | Document Posted | N/A | N/A | 12/1/2024 | 10/22/2015 | N/A | N/A | 7/2/2025 |  |  | 8/12/2025 | 8/12/2025 |  | N | No
AB1-109 | Mountaineer | Mountaineer #1 | WV | Unknown | Partially in Service - Under Construction | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1109_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ab1_109_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 10/26/2015 | N/A | N/A |  |  |  | 6/1/2021 | 6/1/2021 | 12/31/2018 | N | No
AB1-124 | Carroll-Monocacy 34.5kV | Legore Bridge Solar Center Facility | MD | Frederick | Engineering and Procurement | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1124_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1124_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1124_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1124_wmpa.pdf | Not Required | N/A | N/A |  | 10/29/2015 | N/A | N/A | 4/30/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
AB1-125 | Carroll-Monocacy 34.5kV | Biggs Ford Solar Facility | MD | Frederick | Engineering and Procurement | APS | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1125_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1125_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1_125_csa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 4/30/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
AB1-132 | Thelma 230kV | Gaston Green Acres Solar | NC | Northhampton | Partially in Service - Under Construction | Dominion | 120 | 120 | 84 | 65 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1132_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1132_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_132_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab1_132_csa.pdf | Document Posted | N/A | N/A | 11/20/2023 | 11/2/2015 | N/A | N/A | 12/21/2023 |  |  | 12/25/2023 | 12/25/2023 |  | N | No
AB1-176 | Price 25kV II | Cedar Lane Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1176_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1176_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1176_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1176_wmpa.pdf | Not Required | N/A | N/A |  | 10/30/2015 | N/A | N/A | 3/31/2025 |  |  | 3/1/2024 | 3/1/2024 |  | N | No
AB2-036 | Church - Oil City 138kV | Waypost Solar Project | MD | Caroline | Engineering and Procurement | DPL | 92 | 92 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2036_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_036_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_036_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2016 | N/A | N/A | 12/30/2025 |  |  | 12/30/2025 | 12/30/2025 |  | N | No
AB2-037 | Keeney-Steele 230kV | Cherrywood Solar I | MD | Caroline | Engineering and Procurement | DPL | 202 | 202 | 76.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2037_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2037_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_037_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_037_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2016 | N/A | N/A | 12/30/2025 |  |  | 12/30/2025 | 12/30/2025 |  | N | No
AB2-040 | Brink 115kV | Brink Solar Project | VA | Greensville | Under Construction | Dominion | 80 | 80 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2040_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2040_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_040_csa.pdf | Document Posted | N/A | N/A | 9/12/2024 | 3/2/2016 | N/A | N/A | 10/4/2024 |  |  | 10/1/2024 | 10/1/2024 |  | N | No
AB2-092 | Bergen 138kV | Bergen Generating Station | NJ | Bergen | Partially in Service - Under Construction | PSEG | 1371.1 | 51.1 | 51.1 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_092_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/26/2016 | N/A | N/A | 12/31/2025 |  |  | 12/5/2019 | 12/5/2019 | 12/5/2019 | N | No
AB2-097 | Antietam 34.5kV | Hagerstown Plant | MD | Washington | Partially in Service - Under Construction | APS | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2097_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2097_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2097_wmpa.pdf | Not Required | N/A | N/A |  | 4/27/2016 | N/A | N/A | 12/31/2022 |  |  | 2/28/2020 | 2/28/2020 | 10/15/2020 | N | No
AB2-133 | Chestertown-Church 69kV | Morgnec Road Solar | MD | Kent | Engineering and Procurement | DPL | 55.8 | 55.8 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2133_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2133_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_133_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_133_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 8/16/2025 |  |  | 8/16/2025 | 8/16/2025 |  | N | No
AB2-135 | Church-Kent 69kV | Jones Farm Lane Solar | MD | Queen Anne's | Under Construction | DPL | 64 | 64 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2135_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2135_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_135_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_135_csa.pdf | Document Posted | N/A | N/A | 11/28/2024 | 4/30/2016 | N/A | N/A | 12/15/2024 |  |  | 10/30/2024 | 10/30/2024 |  | N | No
AB2-136 | Cambridge-West Cambridge 69kV | Egypt Road Solar | MD | Dorchester | Under Construction | DPL | 51.1 | 51.1 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2136_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2136_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_136_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_136_csa.pdf | Document Posted | N/A | N/A |  | 4/29/2016 | N/A | N/A | 9/30/2025 |  |  | 9/30/2025 | 9/30/2025 |  | N | No
AB2-160 | Reams 115kV | Reams Solar | VA | Dinwiddie | Engineering and Procurement | Dominion | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2160_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2160_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_160_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ab2_160_csa.pdf | Document Posted | N/A | N/A | 5/31/2026 | 4/30/2016 | N/A | N/A | 10/30/2026 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
AB2-175 | Peach Bottom 500kV | Peach Bottom Units #2 & #3 | PA | York | Partially in Service - Under Construction | PECO | 2709.8 | 44 | 44 | 44 | Capacity | Generation Interconnection | Nuclear |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2175_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ab2_175_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/29/2016 | N/A | N/A | 3/26/2019 |  |  | 12/31/2018 | 12/31/2018 | 3/26/2019 | N | No
AC1-001 | Delano 138kV | Salt City Solar | OH | Ross | Partially in Service - Under Construction | AEP | 49.9 | 49.9 | 33.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1001_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1001_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_001_csa.pdf | Document Posted | N/A | N/A | 6/29/2023 | 5/6/2016 | N/A | N/A | 6/29/2023 |  |  | 8/31/2023 | 8/31/2023 |  | N | No
AC1-010 | Gloucester 26kV | National Park NJ | NJ | Gloucester | Engineering and Procurement | PSEG | 6 | 6 | 2.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_010_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_010_csa.pdf | Document Posted | N/A | N/A | 11/15/2025 | 6/22/2016 | N/A | N/A | 12/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AC1-034 | Heartsease DP - Mayo Dunbar 115kV | Edgecome Solar Energy Center | NC | Edgecombe | Engineering and Procurement | Dominion | 75 | 75 | 42.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1034_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1034_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_034_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_034_csa.pdf | Document Posted | N/A | N/A | 6/13/2025 | 8/11/2016 | N/A | N/A | 12/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AC1-043 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1043_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1043_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_043_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_043_csa.pdf | Document Posted | N/A | N/A | 4/30/2026 | 8/31/2016 | N/A | N/A | 5/15/2026 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AC1-053 | Lanesville-Brokaw | Top Hat Wind Energy Center | IL | Logan | Under Construction | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1053_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1053_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_053_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_053_csa.pdf | Document Posted | N/A | N/A | 5/15/2025 | 9/1/2016 | N/A | N/A | 9/15/2025 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AC1-055 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 580 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1055_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ac1_055_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_055_csa.pdf | Document Posted | N/A | N/A | 8/31/2026 | 9/10/2016 | N/A | N/A | 3/31/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AC1-065 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1065_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1065_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_065_csa.pdf | Document Posted | N/A | N/A | 6/3/2025 | 9/22/2016 | N/A | N/A | 10/28/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AC1-068 | Atlanta 69kV I | Pickaway County Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_068_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_068_csa.pdf | Document Posted | N/A | N/A | 7/26/2024 | 9/28/2016 | N/A | N/A | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AC1-069 | Atlanta 69kV II | Pickaway County II Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1069_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1069_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_069_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_069_csa.pdf | Document Posted | N/A | N/A | 7/26/2024 | 9/27/2016 | N/A | N/A | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AC1-074 | Jacksonville-Renaker 138kV I | Bluebird Solar | KY | Harrison | Under Construction | EKPC | 80 | 80 | 56 | 1 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1074_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1074_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_074_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_074_csa.pdf | Document Posted | N/A | N/A | 9/30/2024 | 9/30/2016 | N/A | N/A | 10/30/2024 |  |  | 12/30/2024 | 12/30/2024 |  | N | No
AC1-076 | Locust Grove-Paytes 115kV | Pine Glade Solar | VA | Orange | Under Construction | Dominion | 62.5 | 62.5 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1076_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_076_csa.pdf | Document Posted | N/A | N/A | 5/30/2024 | 10/1/2016 | N/A | N/A | 7/11/2024 |  |  | 7/15/2024 | 7/15/2024 |  | N | No
AC1-082 | Ravenswood-Hemlock 69kV | Great Bend | OH | Meigs | Engineering and Procurement | AEP | 48 | 48 | 29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1082_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1082_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_082_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_082_csa.pdf | Document Posted | N/A | N/A | 7/29/2025 | 10/1/2016 | N/A | N/A | 8/29/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AC1-085 | Stuart-Clinton 345kV | Highland County Solar | OH | Highland | Partially in Service - Under Construction | Dayton | 400 | 400 | 152 | 366.6 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1085_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1085_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_085_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_085_csa.pdf | Document Posted | N/A | N/A |  | 10/1/2016 | N/A | N/A | 10/27/2023 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AC1-086 | Thelma 230kV | Cherry Solar | NC | Northhampton | Engineering and Procurement | Dominion | 180 | 180 | 123.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1086_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_086_csa.pdf | Document Posted | N/A | N/A |  | 10/11/2016 | N/A | N/A | 6/2/2025 |  |  | 8/31/2025 | 8/31/2025 |  | N | No
AC1-089 | Hillsboro-Wildcat 138kV | Willowbrook Solar | OH | Highland | Partially in Service - Under Construction | AEP | 150 | 150 | 57 | 121 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1089_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_089_csa.pdf | Document Posted | N/A | N/A | 11/13/2023 | 10/15/2016 | N/A | N/A | 11/13/2023 |  |  | 1/19/2024 | 1/19/2024 |  | N | No
AC1-091 | Cedar Creek 138kV I | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1091_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1091_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_091_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_091_csa.pdf | Document Posted | N/A | N/A |  | 10/19/2016 | N/A | N/A | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-092 | Cedar Creek 138kV II | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 39.6 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_092_csa.pdf | Document Posted | N/A | N/A |  | 10/20/2016 | N/A | N/A | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-093 | Cedar Creek 138kV III | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 58.4 | 18.8 | 7.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_093_csa.pdf | Document Posted | N/A | N/A |  | 10/20/2016 | N/A | N/A | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-094 | Cedar Creek 138kV IV | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 74.3 | 15.9 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1094_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1094_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_094_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_094_csa.pdf | Document Posted | N/A | N/A |  | 10/20/2016 | N/A | N/A | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC1-098 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Engineering and Procurement | Dominion | 60 | 60 | 37.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1098_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1098_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_098_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_098_csa.pdf | Document Posted | N/A | N/A | 6/15/2025 | 10/22/2016 | N/A | N/A | 7/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AC1-099 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Engineering and Procurement | Dominion | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1099_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1099_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_099_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_099_csa.pdf | Document Posted | N/A | N/A | 6/15/2025 | 10/22/2016 | N/A | N/A | 7/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AC1-161 | Septa 500kV | Cavalier | VA | Isle of Wight | Partially in Service - Under Construction | Dominion | 240 | 240 | 168.2 | 156.2 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1161_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1161_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_161_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_161_csa.pdf | Document Posted | N/A | N/A | 6/23/2023 | 11/2/2016 | N/A | N/A | 12/12/2023 |  |  | 1/1/2023 | 1/1/2023 |  | N | No
AC1-164 | Chickahominy 230kV | Keydet Solar Center One | VA | Charles City | Partially in Service - Under Construction | Dominion | 320 | 320 | 220.8 | 175 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1164_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1164_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_164_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_164_csa.pdf | Document Posted | N/A | N/A | 11/11/2021 | 10/31/2016 | N/A | N/A | 11/1/2024 |  |  | 6/30/2023 | 6/30/2023 |  | N | No
AC1-165 | Atlanta 69kV III | Buckeye Plains II Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1165_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1165_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_165_csa.pdf | Document Posted | N/A | N/A | 7/10/2024 | 11/2/2016 | N/A | N/A | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AC1-166 | Atlanta 69kV IV | Buckeye Plains Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1166_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1166_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_166_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_166_csa.pdf | Document Posted | N/A | N/A | 7/10/2024 | 11/2/2016 | N/A | N/A | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AC1-167 | Mark Center 69kV | Mark Center Solar Project | OH | Defiance | Engineering and Procurement | AEP | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1167_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1167_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_167_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_167_csa.pdf | Document Posted | N/A | N/A | 6/25/2025 | 11/1/2016 | N/A | N/A | 6/25/2025 |  |  | 11/30/2024 | 11/30/2024 |  | N | No
AC1-190 | East New Market 69kV | New Market Solar | MD | Dorchester | Engineering and Procurement | DPL | 50 | 50 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1190_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1190_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_190_csa.pdf | Document Posted | N/A | N/A |  | 10/31/2016 | N/A | N/A | 6/15/2026 |  |  | 7/1/2028 | 7/1/2028 |  | N | No
AC1-194 | Elk 138kV | Vinton Solar | OH | Vinton | Engineering and Procurement | AEP | 125 | 125 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1194_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1194_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_194_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_194_csa.pdf | Document Posted | N/A | N/A | 5/31/2025 | 10/31/2016 | N/A | N/A | 6/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AC1-221 | Halifax-Person 230kV | Alton Post Office Solar | VA | Halifax | Under Construction | Dominion | 29.2 | 29.2 | 14.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1221_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1221_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_221_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac1_221_csa.pdf | Document Posted | N/A | N/A | 8/28/2024 | 11/2/2016 | N/A | N/A | 9/25/2024 |  |  | 8/5/2024 | 8/5/2024 |  | N | No
AC2-009 | Pennington 13 kV | Pennington 13 kV Solar | NJ | Mercer | Partially in Service - Under Construction | PSEG | 0.59 | 0.59 | 0.1 | 0.55 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2009_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2009_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2009_wmpa.pdf | Not Required | N/A | N/A |  | 12/1/2016 | N/A | N/A | 6/1/2023 |  |  | 3/2/2018 | 3/2/2018 | 10/19/2017 | N | Yes
AC2-015 | Chatfield-Howard 138kV | Sycamore Creek Solar | OH | Crawford | Engineering and Procurement | AEP | 117 | 117 | 53.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2015_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_015_csa.pdf | Document Posted | N/A | N/A | 5/1/2025 | 12/29/2016 | N/A | N/A | 6/1/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
AC2-023 | Hebron 69kV | Porter Mill Solar | MD | Wicomico | Engineering and Procurement | DPL | 45.8 | 45.8 | 26.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2023_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_023_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_023_csa.pdf | Document Posted | N/A | N/A |  | 1/25/2017 | N/A | N/A | 5/1/2026 |  |  | 5/1/2026 | 5/1/2026 |  | N | No
AC2-060 | Buckskin 69kV | Ross County Solar | OH | Ross | Under Construction | AEP | 100 | 100 | 64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2060_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2060_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_060_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_060_csa.pdf | Document Posted | N/A | N/A | 8/1/2024 | 2/17/2017 | N/A | N/A | 8/1/2024 |  |  | 6/1/2024 | 6/1/2024 |  | N | No
AC2-061 | Hillsboro-Clinton 138kV | Dodson Creek Solar | OH | Ross | Engineering and Procurement | AEP | 117 | 117 | 58.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2061_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2061_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_061_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_061_csa.pdf | Document Posted | N/A | N/A | 11/1/2024 | 2/17/2017 | N/A | N/A | 12/1/2024 |  |  | 7/30/2024 | 7/30/2024 |  | N | No
AC2-075 | Jacksonville-Renaker 138 kV | Bluebird Solar | KY | Harrison | Under Construction | EKPC | 100 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_075_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 9/30/2024 | 2/28/2017 | N/A | N/A | 10/30/2024 |  |  | 12/1/2024 | 12/1/2024 |  | N | No
AC2-084 | Dawson-South Justice 115kV | American Beech Solar | NC | Halifax | Engineering and Procurement | Dominion | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_084_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_084_csa.pdf | Document Posted | N/A | N/A | 6/15/2025 | 3/2/2017 | N/A | N/A | 7/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AC2-090 | Losantville 345kV | Riverstart Solar Park III | IN | Randolph | Partially in Service - Under Construction | AEP | 100 | 100 | 38 | 79.93 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2090_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2090_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_090_csa.pdf | Document Posted | N/A | N/A | 3/26/2024 | 3/6/2017 | N/A | N/A | 6/5/2024 |  | Customer Milestone Not Met | 8/1/2024 | 8/1/2024 |  | N | No
AC2-100 | Halifax-Person 230kV | Powells Creek Solar | VA | Halifax | Partially in Service - Under Construction | Dominion | 50 | 50 | 33.6 | 50 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2100_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_100_csa.pdf | Document Posted | N/A | N/A | 7/26/2023 | 3/12/2017 | N/A | N/A | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 |  | N | No
AC2-110 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 70 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2110_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2110_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_110_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_110_csa.pdf | Document Posted | N/A | N/A |  | 3/14/2017 | N/A | N/A | 10/28/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AC2-123 | Jacksons Ferry 138kV | Wythe County Solar Project | VA | Wythe | Under Construction | AEP | 75 | 75 | 44.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2123_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2123_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_123_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_123_csa.pdf | Document Posted | N/A | N/A | 5/16/2024 | 3/25/2017 | N/A | N/A | 8/17/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
AC2-136 | East Hagerstown 12kV | East Hagerstown Solar | MD | Washington | Engineering and Procurement | APS | 11.8 | 11.8 | 5.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2136_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2136_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2136_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2017 | N/A | N/A | 10/4/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
AC2-141 | Septa 500kV | Sycamore Cross Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 240 | 240 | 168.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2141_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_141_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/30/2017 | N/A | N/A | 3/1/2026 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
AC2-157 | Sullivan 345 kV | Trade Post Solar Energy Center | IN | Sullivan | Engineering and Procurement | AEP | 200 | 200 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2157_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2157_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_157_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_157_csa.pdf | Document Posted | N/A | N/A | 4/30/2026 | 3/29/2017 | N/A | N/A | 5/31/2026 |  |  | 6/30/2026 | 6/30/2026 |  | N | No
AC2-165 | Bremo-Powhatan 230kV | Cartersville Solar | VA | Powhatan | Engineering and Procurement | Dominion | 99.9 | 99.9 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2165_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2165_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_165_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_165_csa.pdf | Document Posted | N/A | N/A |  | 3/30/2017 | N/A | N/A | 12/31/2025 |  |  | 3/15/2024 | 3/15/2024 |  | N | No
AC2-184 | Cedar Creek 138kV I | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 94.3 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2184_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_184_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_184_csa.pdf | Document Posted | N/A | N/A |  | 4/1/2017 | N/A | N/A | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC2-185 | Cedar Creek 138kV II | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 114.3 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_185_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_185_csa.pdf | Document Posted | N/A | N/A |  | 4/1/2017 | N/A | N/A | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
AC2-186 | Harrington 25kV | Raceway Solar | DE | Kent | Under Construction | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2186_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2186_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_186_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_186_csa.pdf | Document Posted | N/A | N/A |  | 4/1/2017 | N/A | N/A | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AC2-187 | Harrington 69kV | Raceway Solar | DE | Kent | Under Construction | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2187_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2187_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_187_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_187_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2017 | N/A | N/A | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AC2-188 | Harrington 69 kV | Raceway Solar | DE | Kent | Under Construction | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2188_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2188_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_188_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_188_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2017 | N/A | N/A | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AC2-195 | Galion-Roberts South 138 kV | Marion County Solar Project | OH | Marion | Engineering and Procurement | ATSI | 99.96 | 99.96 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2195_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2195_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2195_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_195_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ac2_195_csa.pdf | Document Posted | N/A | N/A | 8/2/2025 | 4/1/2017 | N/A | N/A | 11/17/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD1-013 | Twombly Road 138kV | Rochelle Solar | IL | Ogle | Engineering and Procurement | ComEd | 40 | 40 | 15.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1013_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1013_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_013_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_013_csa.pdf | Document Posted | N/A | N/A | 12/31/2025 | 4/6/2017 | N/A | N/A | 1/29/2026 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
AD1-020 | Hunterstown-Lincoln 115 kV | Adams Solar LLC | PA | Adams | Partially in Service - Under Construction | ME | 100 | 100 | 53.6 | 80 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1020_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_020_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_020_csa.pdf | Document Posted | N/A | N/A | 12/22/2023 | 6/9/2017 | N/A | N/A | 12/27/2023 |  |  | 2/25/2024 | 2/25/2024 |  | N | No
AD1-022 | Cashie-Trowbridge 230 kV | Sumac Solar | NC | Bertie | Engineering and Procurement | Dominion | 80 | 80 | 51.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1022_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_022_csa.pdf | Document Posted | N/A | N/A |  | 6/19/2017 | N/A | N/A | 5/1/2028 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-025 | Hopewell-Surry 230 kV | Spring Grove Solar II | VA | Surry | Engineering and Procurement | Dominion | 150 | 150 | 94.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1025_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1025_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_025_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_025_csa.pdf | Document Posted | N/A | N/A |  | 6/28/2017 | N/A | N/A | 3/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AD1-031 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Engineering and Procurement | ComEd | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1031_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1031_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_031_csa.pdf | Document Posted | N/A | N/A | 4/15/2027 | 7/24/2017 | N/A | N/A | 4/15/2027 |  |  | 6/15/2027 | 6/15/2027 |  | N | No
AD1-039 | Kendall-Tazewell & Dresden-Mole Creek | Three Rivers Energy Center | IL | Grundy | Partially in Service - Under Construction | ComEd | 1262.7 | 102.7 | 93 | 102.7 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1039_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_039_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/29/2017 | N/A | N/A |  |  |  | 2/28/2025 | 2/28/2025 | 6/16/2023 | N | No | This project slid to the next queue
AD1-041 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Under Construction | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1041_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1041_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_041_csa.pdf | Document Posted | N/A | N/A | 4/4/2024 | 8/2/2017 | N/A | N/A | 7/11/2024 |  |  | 6/28/2024 | 6/28/2024 |  | N | No
AD1-056 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 60 | 60 | 38.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1056_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1056_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_056_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_056_csa.pdf | Document Posted | N/A | N/A |  | 8/14/2017 | N/A | N/A | 12/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-057 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 33 | 33 | 21.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1057_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1057_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_057_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_057_csa.pdf | Document Posted | N/A | N/A |  | 8/14/2017 | N/A | N/A | 12/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-058 | Halifax-Person 230 kV | Alton Post Office Solar | VA | Halifax | Under Construction | Dominion | 75.1 | 45.9 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1058_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1058_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_058_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_058_csa.pdf | Document Posted | N/A | N/A | 8/28/2024 | 8/16/2017 | N/A | N/A | 9/25/2024 |  |  | 8/5/2024 | 8/5/2024 |  | N | No
AD1-073 | Buckskin 69 kV | Ross County Solar | OH | Ross | Engineering and Procurement | AEP | 120 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1073_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1073_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_073_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_073_csa.pdf | Document Posted | N/A | N/A | 8/1/2024 | 8/31/2017 | N/A | N/A | 8/1/2024 |  |  | 6/1/2024 | 6/1/2024 |  | N | No
AD1-074 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 300 | 300 | 198.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1074_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1074_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_074_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_074_csa.pdf | Document Posted | N/A | N/A | 12/27/2027 | 9/1/2017 | N/A | N/A | 1/27/2028 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AD1-075 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 75 | 75 | 49.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_075_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2017 | N/A | N/A | 12/27/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AD1-076 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 109 | 109 | 72.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1076_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_076_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_076_csa.pdf | Document Posted | N/A | N/A |  | 8/31/2017 | N/A | N/A | 12/27/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AD1-085 | North Shenandoah-Stanley 34.5 kV | North Shenandoah-Stanley 34.5kV | VA | Page | Engineering and Procurement | APS | 20 | 20 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1085_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1085_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1085_wmpa.pdf | Not Required | N/A | N/A |  | 9/14/2017 | N/A | N/A | 7/31/2026 |  |  | 9/8/2026 | 9/8/2026 |  | N | No
AD1-088 | Briery-Clover 230 kV | Seven Bridges Solar | VA | Mecklenburg | Engineering and Procurement | Dominion | 80 | 80 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_088_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_088_csa.pdf | Document Posted | N/A | N/A |  | 9/15/2017 | N/A | N/A | 11/1/2025 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-100 | Loretto-Wilton 345 kV & Braidwood-Davis Creek 345 kV |  | IL | Ford | Engineering and Procurement | ComEd | 850 | 850 | 150 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1100_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_100_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 9/22/2017 | N/A | N/A | 10/31/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AD1-105 | Kings Dominion DP 115 kV | Sweet Sue Solar | VA | King William | Under Construction | Dominion | 74 | 74 | 44.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1105_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1105_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1105_wmpa.pdf | Not Required | N/A | N/A |  | 9/23/2017 | N/A | N/A | 9/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AD1-115 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 150 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1115_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_115_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_115_csa.pdf | Document Posted | N/A | N/A | 4/30/2026 | 9/27/2017 | N/A | N/A | 5/15/2026 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AD1-119 | Payne 69 kV | Timber Road Solar Park | OH | Paulding | Partially in Service - Under Construction | AEP | 49.9 | 49.9 | 18.96 | 49.9 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1119_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1119_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_119_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_119_csa.pdf | Document Posted | N/A | N/A | 12/15/2022 | 9/28/2017 | N/A | N/A | 6/29/2023 |  |  | 11/30/2023 | 11/30/2023 |  | N | No
AD1-128 | Modoc-Delaware 138 kV | Riverstart Solar Park IV | IN | Randolph | Engineering and Procurement | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1128_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1128_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_128_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_128_csa.pdf | Document Posted | N/A | N/A | 3/5/2025 | 9/29/2017 | N/A | N/A | 4/5/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD1-130 | Hardin Switch 345 kV | Hardin Energy Center – Phase 2 | OH | Hardin | Under Construction | AEP | 150 | 150 | 101.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1130_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1130_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_130_csa.pdf | Document Posted | N/A | N/A | 5/22/2024 | 10/1/2017 | N/A | N/A | 8/5/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AD1-131 | Sedge Hill-Person 230 kV | Powells Creek Solar | VA | Halifax | Partially in Service - Under Construction | Dominion | 70 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1131_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1131_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_131_csa.pdf | Document Posted | N/A | N/A | 7/26/2023 | 9/30/2017 | N/A | N/A | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 |  | N | No
AD1-155 | Meadow Brook-Strasburg 138 kV | Foxglove Solar | VA | Frederick | Under Construction | APS | 75 | 75 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1155_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1155_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_155_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad1_155_csa.pdf | Document Posted | N/A | N/A | 7/22/2024 | 10/2/2017 | N/A | N/A | 9/13/2024 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
AD2-022 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 96 | 96 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2022_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_022_csa.pdf | Document Posted | N/A | N/A | 12/15/2024 | 12/2/2017 | N/A | N/A | 12/15/2024 |  |  | 2/28/2025 | 2/28/2025 |  | N | No
AD2-023 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 150 | 54 | 95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2023_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_023_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_023_csa.pdf | Document Posted | N/A | N/A | 12/15/2024 | 12/2/2017 | N/A | N/A | 12/15/2024 |  |  | 2/28/2025 | 2/28/2025 |  | N | No
AD2-031 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | Engineering and Procurement | Dayton | 49.9 | 49.9 | 19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2031_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2031_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_031_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_031_csa.pdf | Document Posted | N/A | N/A | 11/30/2024 | 12/15/2017 | N/A | N/A | 12/15/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AD2-038 | Powerton-Nevada 345 kV | Osagrove Flats Wind | IL | Lasalle | Engineering and Procurement | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2038_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_038_csa.pdf | Document Posted | N/A | N/A | 9/30/2026 | 1/21/2018 | N/A | N/A | 9/30/2026 |  |  | 10/30/2026 | 10/30/2026 |  | N | No
AD2-039 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 90 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2039_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2039_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_039_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_039_csa.pdf | Document Posted | N/A | N/A |  | 1/20/2018 | N/A | N/A | 10/28/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AD2-047 | Davis Creek 138 kV | Lower Crossing Wind | IL | Kankakee | Engineering and Procurement | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2047_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_047_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 1/31/2018 | N/A | N/A | 10/31/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AD2-048 | Cynthia-Headquarters 69 kV | Blue Moon Solar | KY | Harrison | Engineering and Procurement | EKPC | 70 | 70 | 46.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_048_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_048_csa.pdf | Document Posted | N/A | N/A | 9/1/2025 | 2/1/2018 | N/A | N/A | 10/1/2025 |  |  | 9/30/2025 | 9/30/2025 |  | N | No
AD2-066 | Mazon-Crescent Ridge 138 kV |  | IL | Grundy | Engineering and Procurement | ComEd | 116 | 116 | 69.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2066_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2066_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_066_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_066_csa.pdf | Document Posted | N/A | N/A | 10/10/2026 | 3/1/2018 | N/A | N/A | 11/30/2025 |  |  | 8/10/2026 | 8/10/2026 |  | N | No
AD2-086 | Hardin Switch 345 kV | Hardin Energy Center – Phase 3 | OH | Hardin | Under Construction | AEP | 230 | 230 | 138 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2086_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_086_csa.pdf | Document Posted | N/A | N/A | 9/2/2024 | 3/21/2018 | N/A | N/A | 9/16/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD2-091 | Hardin Tap 345kV | Hardin Energy Center – Storage I | OH | Hardin | Engineering and Procurement | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2091_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2091_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_091_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_091_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 3/20/2018 | N/A | N/A | 11/15/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AD2-092 | Marysville 345kV | Cadence Solar II Energy Center | OH | Union | Engineering and Procurement | AEP | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_092_csa.pdf | Document Posted | N/A | N/A | 11/18/2024 | 3/22/2018 | N/A | N/A | 12/18/2024 |  |  | 1/30/2026 | 1/30/2026 |  | N | No
AD2-093 | Marysville 345kV | Cadence Solar Energy Center | OH | Union | Under Construction | AEP | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_093_csa.pdf | Document Posted | N/A | N/A | 11/18/2024 | 3/21/2018 | N/A | N/A | 12/18/2024 |  |  | 1/30/2026 | 1/30/2026 |  | N | No
AD2-100 | Kincaid-Pana 345 kV | Broomstick Solar Energy Centergy Center | IL | Christian | Engineering and Procurement | ComEd | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2100_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_100_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_100_csa.pdf | Document Posted | N/A | N/A | 10/7/2028 | 3/23/2018 | N/A | N/A | 11/7/2028 |  |  | 12/7/2028 | 12/7/2028 |  | N | No
AD2-131 | Kincaid-Pana 345kV | Broomstick Solar Energy Centergy Center | IL | Christian | Engineering and Procurement | ComEd | 50 | 50 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2131_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2131_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_131_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_131_csa.pdf | Document Posted | N/A | N/A | 9/24/2026 | 3/24/2018 | N/A | N/A | 9/24/2026 |  |  | 12/7/2028 | 12/7/2028 |  | N | No
AD2-134 | Shady Oaks | Shady Oaks Wind Power Project | IL | Lee | Partially in Service - Under Construction | ComEd | 215.4 | 105.9 | 21.2 | 105.9 | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2134_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2134_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_134_csa.pdf | Document Posted | N/A | N/A | 9/7/2023 | 3/25/2018 | N/A | N/A | 9/16/2023 |  |  | 12/7/2027 | 12/7/2027 |  | N | No
AD2-135 | Williamstown 12kV | Monroe-Sicklerville Road LF Solar | NJ | Gloucester | Engineering and Procurement | AEC | 1.62 | 1.62 | 0.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2135_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2135_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2135_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2135_wmpa.pdf | Not Required | N/A | N/A |  | 3/23/2018 | N/A | N/A | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AD2-158 | Old Chapel-Millville 138kV | Wild Hill Solar | WV | Jefferson | Engineering and Procurement | APS | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2158_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2158_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_158_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 3/24/2018 | N/A | N/A | 12/15/2025 |  |  | 9/1/2024 | 9/1/2024 |  | N | No
AD2-192 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 625 | 45 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2192_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_192_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ad2_192_csa.pdf | Document Posted | N/A | N/A | 8/31/2026 | 3/31/2018 | N/A | N/A | 3/31/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
AD2-194 | Elwood 345 kV | Jackson Generation | IL | Will | Partially in Service - Under Construction | ComEd | 1260.9 | 60 | 120 | 19.49 | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2194_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_194_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/31/2018 | N/A | N/A | 6/1/2024 |  |  | 4/26/2024 | 4/26/2024 |  | N | No
AE1-004 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 110 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_004_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 4/7/2018 | N/A | N/A | 10/15/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AE1-040 | Greenfield 69 kV | Fayette Solar | OH | Fayette | Under Construction | Dayton | 48 | 48 | 31.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1040_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1040_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_040_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_040_csa.pdf | Document Posted | N/A | N/A | 10/18/2024 | 6/26/2018 | N/A | N/A | 12/16/2024 |  |  | 5/31/2024 | 5/31/2024 |  | N | No
AE1-050 | Gavin Unit 1 765 kV | Gavin Unit No. 1 | OH | Gallia | Partially in Service - Under Construction | AEP | 1349 | 18 | 18 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_050_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/20/2018 | N/A | N/A |  |  |  | 6/9/2024 | 6/9/2024 |  | N | No
AE1-070 - moved to TC1 | Elwood 345 kV |  | IL | Will | Active | ComEd | 1610 | 0 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1070_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2018 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE1-071 | Shade Gap-Roxbury 115 kV | Aspen Road Solar | PA | Franklin | Under Construction | PENELEC | 100.1 | 100.1 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1071_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1071_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_071_csa.pdf | Document Posted | N/A | N/A | 12/9/2024 | 7/31/2018 | N/A | N/A | 12/31/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AE1-072 | Shawboro-Sligo 230 kV | Shawboro Solar | NC | Currituck | Engineering and Procurement | Dominion | 150 | 150 | 98.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1072_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1072_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_072_csa.pdf | Document Posted | N/A | N/A |  | 7/31/2018 | N/A | N/A | 11/1/2027 |  |  | 12/1/2027 | 12/1/2027 |  | N | No
AE1-075 | Powhatan 34.5 kV | Powhatan Solar I, LLC | VA | Powhatan | Under Construction | Dominion | 18 | 18 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1075_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1075_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1075_wmpa.pdf | Not Required | N/A | N/A | 1/19/2024 | 8/2/2018 | N/A | N/A | 9/2/2024 |  |  | 12/1/2023 | 12/1/2023 |  | N | No
AE1-079 | Maysville-Sharon 69 kV | Welcome Solar, LLC | PA | Mercer | Engineering and Procurement | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1079_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1079_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_079_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_079_csa.pdf | Document Posted | N/A | N/A | 3/29/2024 | 8/11/2018 | N/A | N/A | 1/29/2026 |  |  | 5/29/2024 | 5/29/2024 |  | N | No
AE1-090 | Hardin Switch 345 kV | Hardin Energy Center - Phase 3 | OH | Hardin | Under Construction | AEP | 280 | 50 | 21.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1090_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1090_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_090_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_090_csa.pdf | Document Posted | N/A | N/A | 9/2/2024 | 9/1/2018 | N/A | N/A | 9/16/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE1-092 - moved to TC1 | Blue Jacket-Kirby 138 kV |  | OH | Union | Active | Dayton | 229.5 | 229.5 | 96.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1092_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-093 | Elk 138 kV | Vinton Energy Storage | OH | Vinton | Engineering and Procurement | AEP | 42 | 42 | 42 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1093_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_093_csa.pdf | Document Posted | N/A | N/A | 10/30/2026 | 8/31/2018 | N/A | N/A | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE1-106 | Lake Lynn-Hazelton 138 kV | Brandonville Solar | WV | Preston | Engineering and Procurement | APS | 99.6 | 99.6 | 59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1106_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1106_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_106_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_106_csa.pdf | Document Posted | N/A | N/A | 10/31/2026 | 9/11/2018 | N/A | N/A | 10/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE1-108 | Bremo-Scottsville 138 kV | Riverstone Solar | VA | Buckingham | Engineering and Procurement | AEP | 149.5 | 149.5 | 89.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1108_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1108_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_108_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_108_csa.pdf | Document Posted | N/A | N/A | 12/12/2025 | 9/13/2018 | N/A | N/A | 1/12/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
AE1-109 | Frenchs Mill 34 kV | Capon Bridge Solar | WV | Hampshire | Under Construction | APS | 20 | 20 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1109_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1109_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1109_wmpa.pdf | Not Required | N/A | N/A | 6/20/2024 | 9/14/2018 | N/A | N/A | 7/10/2024 |  |  | 7/31/2024 | 7/31/2024 |  | N | No
AE1-113 | Mole Creek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 300 | 300 | 66 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1113_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1113_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_113_csa.pdf | Document Posted | N/A | N/A | 9/21/2026 | 9/14/2018 | N/A | N/A | 9/21/2026 |  |  | 1/18/2027 | 1/18/2027 |  | N | No
AE1-114 - moved to TC1 | Maryland-Lancaster 138 kV |  | IL | Ogle | Active | ComEd | 150 | 150 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1114_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-143 | Marion County 161 kV | Northern Bobwhite Solar | KY | Marion | Engineering and Procurement | EKPC | 96 | 96 | 64.163 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1143_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1143_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_143_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_143_csa.pdf | Document Posted | N/A | N/A | 10/1/2025 | 9/25/2018 | N/A | N/A | 11/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE1-144 - moved to TC1 | Goddard-Plumville 138 kV |  | KY | Fleming | Active | EKPC | 100 | 100 | 66.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1144_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No | This project slid to the next queue
AE1-146 | Ebersole #2-Fostoria Central 138 kV | Border Basin | OH | Hancock | Engineering and Procurement | AEP | 120 | 120 | 81.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1146_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1146_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_146_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_146_csa.pdf | Document Posted | N/A | N/A | 10/3/2025 | 9/25/2018 | N/A | N/A | 11/3/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE1-148 - moved to TC1 | Kerr Dam-Ridge Rd 115 kV |  | VA | Mecklenburg | Active | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1148_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE1-155 | Garner-Northern Neck 115 kV | Bookers Mill Solar | VA | City of Richmond | Partially in Service - Under Construction | Dominion | 127 | 127 | 76.2 | 127 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1155_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1155_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_155_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_155_csa.pdf | Document Posted | N/A | N/A | 10/6/2023 | 9/26/2018 | N/A | N/A | 3/12/2024 |  |  | 5/14/2024 | 5/14/2024 |  | N | No
AE1-156 | Quakertown Solar II 34.5 kV | Quakertown Solar Farm | NJ | Hunterdon | Under Construction | JCPL | 17.6 | 7.6 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1156_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_156_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_156_csa.pdf | Document Posted | N/A | N/A |  | 9/25/2018 | N/A | N/A | 11/30/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AE1-163 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 350 | 350 | 49 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1163_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1163_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_163_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_163_csa.pdf | Document Posted | N/A | N/A | 11/1/2026 | 9/24/2018 | N/A | N/A | 11/1/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
AE1-166 | Loretto-Wilton & Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 1000 | 150 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1166_imp.html | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AE1-170 | Kenzie Creek-Colby 138 kV | Wingstem Solar Energy Farm | MI | Cass | Engineering and Procurement | AEP | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1170_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1170_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_170_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_170_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 9/25/2018 | N/A | N/A | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE1-172 - moved to TC1 | Loretto-Wilton Center |  | IL | Livingston | Active | ComEd | 255 | 255 | 44.88 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1172_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE1-173 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 800 | 800 | 480 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1173_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2018 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE1-179 | South Millville-Newport 69 kV | Buckshutem Solar I | NJ | Cumberland | Engineering and Procurement | AEC | 59.7 | 59.7 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1179_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1179_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1179_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_179_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_179_csa.pdf | Document Posted | N/A | N/A |  | 9/25/2018 | N/A | N/A | 1/31/2027 |  |  | 1/31/2027 | 1/31/2027 |  | N | No
AE1-183 | Maysville-McDowell 69 kV | Jackson Center Solar Facility | PA | Mercer | Engineering and Procurement | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1183_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1183_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_183_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_183_csa.pdf | Document Posted | N/A | N/A | 4/20/2025 | 9/26/2018 | N/A | N/A | 5/1/2025 |  |  | 5/15/2023 | 5/15/2023 |  | N | No
AE1-185 | Hokes-Jackson 69 kV | Cottontail Solar 1 | PA | York | Under Construction | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1185_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1185_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_185_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_185_csa.pdf | Document Posted | N/A | N/A | 3/9/2023 | 9/30/2018 | N/A | N/A | 7/16/2024 |  |  | 2/28/2024 | 2/28/2024 |  | N | No
AE1-190 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1190_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_190_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_190_csa.pdf | Document Posted | N/A | N/A | 4/4/2024 | 9/28/2018 | N/A | N/A | 7/11/2024 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
AE1-191 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Under Construction | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1191_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_191_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_191_csa.pdf | Document Posted | N/A | N/A | 4/4/2024 | 9/28/2018 | N/A | N/A | 7/11/2024 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
AE1-205 | McLean 345 kV |  | IL | Livingston | Active | ComEd | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1205_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1205_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2018 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE1-209 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Engineering and Procurement | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1209_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1209_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1209_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_209_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_209_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 9/27/2018 | N/A | N/A | 3/1/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE1-210 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Engineering and Procurement | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1210_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1210_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_210_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_210_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 9/27/2018 | N/A | N/A | 3/1/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE1-218 | Glassboro 12 kV | Glassboro LF Solar | NJ | Gloucester | Under Construction | AEC | 2 | 2 | 0.82 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1218_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1218_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1218_wmpa.pdf | Not Required | N/A | N/A |  | 9/28/2018 | N/A | N/A | 12/2/2024 |  |  | 7/31/2024 | 7/31/2024 |  | N | No
AE1-229 | Deepwater-Upper Pittsgrove 138 kV | Pilesgrove Solar Project | NJ | Salem | Engineering and Procurement | AEC | 149.3 | 149.3 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1229_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1229_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_229_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_229_csa.pdf | Document Posted | N/A | N/A |  | 9/18/2018 | N/A | N/A | 12/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE1-237 | Andover (Maysville) 69kV I | Welcome Solar II | PA | Crawford | Engineering and Procurement | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1237_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1237_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_237_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_237_csa.pdf | Document Posted | N/A | N/A | 3/29/2024 | 9/29/2018 | N/A | N/A | 6/25/2026 |  |  | 5/29/2024 | 5/29/2024 |  | N | No
AE1-243 | Warren Glen Storage 34.5 kV | Warren Glen Storage | NJ | Warren | Under Construction | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1243_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1243_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1243_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_243_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_243_csa.pdf | Document Posted | N/A | N/A | 10/28/2024 | 9/29/2018 | N/A | N/A | 10/29/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AE1-245 | Haviland 138 kV | Grover Hill Wind Project | OH | Paulding | Engineering and Procurement | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1245_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1245_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1245_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_245_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae1_245_csa.pdf | Document Posted | N/A | N/A | 11/4/2025 | 9/18/2018 | N/A | N/A | 12/4/2025 |  |  | 2/5/2026 | 2/5/2026 |  | N | No
AE1-246 | Barren County-Summer Shade 161 kV |  | KY | Barren | Active | EKPC | 85 | 85 | 57.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1246_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1246_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2018 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No | This project slid to the next queue
AE1-250 | Smith Mountain-E. Danville 138 kV | Blue Ridge Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1250_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1250_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1250_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_250_isa.pdf | Document Posted | N/A |  |  | N/A | N/A | 11/21/2027 | 8/31/2018 | N/A | N/A | 12/21/2027 |  |  | 1/21/2028 | 1/21/2028 |  | N | No
AE2-001 | Nittany-Zion 46 kV | Confer Solar I | PA | Centre | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2001_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2001_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_001_csa.pdf | Document Posted | N/A | N/A | 4/30/2025 | 10/2/2018 | N/A | N/A | 5/5/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AE2-005 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 130 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2005_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ae2_005_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_005_csa.pdf | Document Posted | N/A | N/A |  | 10/5/2018 | N/A | N/A | 10/15/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AE2-019 | New Road 230 kV | New Road Storage | VA | Loudoun | Engineering and Procurement | Dominion | 120 | 120 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2019_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2019_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_019_csa.pdf | Document Posted | N/A | N/A |  | 12/12/2018 | N/A | N/A | 6/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-020 | Cardiff 230 kV I | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2020_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2020_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_020_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_020_csa.pdf | Document Posted | N/A | N/A |  | 12/16/2018 | N/A | N/A | 8/31/2029 |  |  | 8/31/2029 | 8/31/2029 |  | N | No
AE2-021 | Cardiff 230 kV II | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2021_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2021_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_021_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_021_csa.pdf | Document Posted | N/A | N/A |  | 12/15/2018 | N/A | N/A | 8/31/2029 |  |  | 8/31/2029 | 8/31/2029 |  | N | No
AE2-022 | Cardiff 230 kV III | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2022_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_022_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_022_csa.pdf | Document Posted | N/A | N/A |  | 12/15/2018 | N/A | N/A | 8/31/2029 |  |  | 8/31/2029 | 8/31/2029 |  | N | No
AE2-029 | Grottoes-Merck 115kV | Stonewall Solar | VA | Rockingham | Engineering and Procurement | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2029_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2029_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_029_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_029_csa.pdf | Document Posted | N/A | N/A |  | 12/29/2018 | N/A | N/A | 6/1/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AE2-034 | Mackeys 230 kV | Albemarle Beach Solar | NC | Washington | Partially in Service - Under Construction | Dominion | 140 | 60 | 42 | 40 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2034_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_034_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 1/16/2019 | N/A | N/A | 10/1/2023 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-038 - moved to TC1 | Goddard-Plumsville 138 kV II |  | KY | Fleming | Active | EKPC | 180 | 80 | 53.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2038_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-041 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Engineering and Procurement | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2041_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2041_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_041_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_041_csa.pdf | Document Posted | N/A | N/A | 2/28/2027 | 1/24/2019 | N/A | N/A | 12/31/2027 |  |  | 3/1/2026 | 3/1/2026 |  | N | No
AE2-042 | Milton 69 kV | Northumberland Solar | PA | Northumberland | Engineering and Procurement | PPL | 65 | 65 | 43.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2042_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2042_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_042_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_042_csa.pdf | Document Posted | N/A | N/A | 10/4/2024 | 1/25/2019 | N/A | N/A | 10/15/2024 |  |  | 11/4/2024 | 11/4/2024 |  | N | No
AE2-045 | Olive-Reynolds 345 kV |  | IN | Lake | Active | AEP | 200 | 200 | 84.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2045_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-046 | Harwood-East Hazelton 69 kV | McAdoo Solar | PA | Schuylkill | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2046_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2046_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_046_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_046_csa.pdf | Document Posted | N/A | N/A | 2/12/2025 | 2/1/2019 | N/A | N/A | 3/12/2025 |  |  | 3/16/2025 | 3/16/2025 |  | N | No
AE2-047 | Ridgeway-Solite 69 kV | Henry County Solar Facility | VA | Henry | Engineering and Procurement | AEP | 50 | 50 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2047_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_047_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_047_csa.pdf | Document Posted | N/A | N/A | 6/30/2026 | 1/31/2019 | N/A | N/A | 8/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-048 | Muskingum-W. Millersport 345 kV |  | OH | Fairfield | Active | AEP | 220 | 220 | 147.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2048_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-051 | Carson-Septa 500 kV | Big Pine Solar | VA | Sussex | Engineering and Procurement | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2051_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2051_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ae2_051_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 1/31/2019 | N/A | N/A |  |  |  | 8/1/2031 | 8/1/2031 |  | N | No
AE2-054 | Warfordsburg 34 kV | Blairs Valley | PA | Franklin | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2054_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2054_wmpa.pdf | Not Required | N/A | N/A |  | 2/2/2019 | N/A | N/A | 8/30/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
AE2-059 | Derry Tap-Derry Bus 69 kV | Cottontail Solar 4 aka East Chilli Solar | PA | Northumberland | Under Construction | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2059_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2059_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_059_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_059_csa.pdf | Document Posted | N/A | N/A | 2/2/2024 | 2/6/2019 | N/A | N/A | 7/15/2024 |  |  | 5/31/2024 | 5/31/2024 |  | N | No
AE2-064 | Beaverbrook 13 kV | Kinsley 2 Beaverbrook Solar | NJ | Gloucester | Partially in Service - Under Construction | PSEG | 5.8 | 2 | 0.85 | 3.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_064_csa.pdf | Document Posted | N/A | N/A |  | 2/7/2019 | N/A | N/A | 1/30/2024 |  |  | 8/31/2020 | 8/31/2020 |  | N | No
AE2-065 | Romeoville 12 kV | Kinsley 2 Deptford Solar | NJ | Gloucester | Partially in Service - Under Construction | PSEG | 6.8 | 1.8 | 0.76 | 1.8 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_065_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_065_csa.pdf | Document Posted | N/A | N/A |  | 2/6/2019 | N/A | N/A | 6/1/2023 |  |  | 8/31/2020 | 8/31/2020 | 9/19/2020 | N | No
AE2-071 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | Partially in Service - Under Construction | EKPC | 35 | 35 | 21 | 35 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2071_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2071_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_071_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_071_csa.pdf | Document Posted | N/A | N/A | 4/1/2024 | 2/18/2019 | N/A | N/A | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 |  | N | No
AE2-072 | East Leipsic-Richland 138 kV | Powell Creek Solar | OH | Putnam | Engineering and Procurement | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2072_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2072_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_072_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_072_csa.pdf | Document Posted | N/A | N/A | 12/5/2024 | 2/15/2019 | N/A | N/A | 12/6/2024 |  |  | 6/2/2025 | 6/2/2025 |  | N | No
AE2-073 | Centerburg 138kV |  | OH | Licking | Active | AEP | 200 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2073_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/15/2019 | N/A | N/A |  |  |  | 11/1/2021 |  |  | N | No
AE2-074 | Potter 46 kV | Potter Solar | PA | Potter | Engineering and Procurement | APS | 35 | 35 | 15.11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2074_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2074_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2074_wmpa.pdf | Not Required | N/A | N/A |  | 2/20/2019 | N/A | N/A |  |  |  | 9/30/2023 | 9/30/2023 |  | N | No
AE2-089 | Pennville-Adams 138 kV | Skycrest Solar Energy Center | IN | Jay | Engineering and Procurement | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2089_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_089_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_089_csa.pdf | Document Posted | N/A | N/A | 4/15/2026 | 2/22/2019 | N/A | N/A | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-092 | Kidds Store-Sherwood 115 kV | Woodridge Solar | VA | Albemarle | Engineering and Procurement | Dominion | 138 | 138 | 82.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_092_csa.pdf | Document Posted | N/A | N/A | 11/12/2026 | 2/26/2019 | N/A | N/A | 12/1/2026 |  |  | 10/1/2026 | 10/1/2026 |  | N | No
AE2-093 | Easton-Steele 138 kV | Crockett Solar Project | MD | Talbot | Engineering and Procurement | DPL | 44 | 44 | 16.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_093_csa.pdf | Document Posted | N/A | N/A |  | 2/26/2019 | N/A | N/A | 3/31/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
AE2-094 | Carson-Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 300 | 300 | 207.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2094_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-104 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Engineering and Procurement | Dominion | 49 | 49 | 18.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2104_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2104_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_104_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_104_csa.pdf | Document Posted | N/A | N/A | 8/12/2025 | 3/2/2019 | N/A | N/A | 9/15/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AE2-113 | Farmers Valley-Ridgeway 115 kV | Ridgeway Solar | PA | McKean | Engineering and Procurement | PENELEC | 120 | 120 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2113_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2113_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_113_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_113_csa.pdf | Document Posted | N/A | N/A | 1/1/2025 | 3/1/2019 | N/A | N/A | 1/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AE2-117 | ABW Tap-Alexandria 46 kV | HU-Pauls | PA | Huntingdon | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2117_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2117_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_117_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_117_csa.pdf | Document Posted | N/A | N/A | 5/1/2025 | 3/1/2019 | N/A | N/A | 5/1/2025 |  |  | 5/20/2024 | 5/20/2024 |  | N | No
AE2-122 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 800.1 | 800.1 | 158.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2122_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AE2-125 | Stahlstown-Ligonier 25 kV | Stahlstown-Ligonier 25 kV | PA | Westmoreland | Under Construction | APS | 13.8 | 13.8 | 8.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2125_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2125_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2125_wmpa.pdf | Not Required | N/A | N/A | 8/30/2024 | 3/2/2019 | N/A | N/A | 9/15/2024 |  |  | 11/15/2024 | 11/15/2024 |  | N | No
AE2-134 | Locust Grove-Paytes 115 kV | Pine Glade Solar | VA | Orange | Under Construction | Dominion | 62.5 | 0 | 16.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_134_csa.pdf | Document Posted | N/A | N/A | 5/30/2024 | 3/5/2019 | N/A | N/A | 7/11/2024 |  |  | 7/15/2024 | 7/15/2024 |  | N | No
AE2-136 | Muskingum River-W. Millersport 345 kV |  | OH | Fairfield | Active | AEP | 114 | 114 | 83.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2136_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-138 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 260 | 260 | 189.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2138_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-139 | East Towanda-Grover 230 kV | Bradford Solar | PA | McKean | Engineering and Procurement | PENELEC | 100.5 | 100.5 | 60.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2139_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2139_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ae2_139_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 9/1/2026 | 3/9/2019 | N/A | N/A | 11/16/2026 |  |  | 12/15/2026 | 12/15/2026 |  | N | No
AE2-147 - moved to TC1 | Swamp 230 kV |  | NC | Perquimans | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2147_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/13/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-148 | Beatty-Greene 345 kV | Fox Squirrel Solar | OH | Madison | Partially in Service - Under Construction | AEP | 577 | 577 | 397.3 | 400 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2148_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2148_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_148_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_148_csa.pdf | Document Posted | N/A | N/A |  | 2/22/2019 | N/A | N/A | 11/14/2023 |  |  | 11/1/2023 | 11/1/2023 |  | N | No
AE2-152 | Loretto-Wilton & Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 1150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2152_imp.html | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2019 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AE2-156 - moved to TC1 | Yadkin 115 kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2156_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-160 | Kanawha River 138 kV |  | WV | Fayette | Active | AEP | 51 | 51 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2160_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2019 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AE2-166 | Stockton 138 kV | Rocky Ford Solar Energy Center | VA | Henry | Engineering and Procurement | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2166_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2166_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_166_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_166_csa.pdf | Document Posted | N/A | N/A | 3/30/2026 | 3/16/2019 | N/A | N/A | 5/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-172 | Mississinewa-Gaston 138 kV | Golden Aster Solar Energy Center | IN | Grant | Engineering and Procurement | AEP | 200 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2172_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2172_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_172_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_172_csa.pdf | Document Posted | N/A | N/A | 3/30/2026 | 3/15/2019 | N/A | N/A | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE2-173 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2173_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AE2-175 | Jackson-Long Pond 69 kV | Swiftwater Solar | PA | Monroe | Under Construction | PPL | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2175_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2175_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_175_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_175_csa.pdf | Document Posted | N/A | N/A | 10/31/2024 | 3/19/2019 | N/A | N/A | 11/29/2024 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
AE2-176 | Groton 138 kV Solar | Wheatsborough Solar | OH | Erie | Under Construction | ATSI | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2176_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2176_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_176_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_176_csa.pdf | Document Posted | N/A | N/A | 12/1/2024 | 3/19/2019 | N/A | N/A | 12/1/2024 |  |  | 4/30/2025 | 4/30/2025 |  | N | No
AE2-181 | Snyder 69kV | Montpelier Solar | OH | Williams | Engineering and Procurement | ATSI | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2181_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2181_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2181_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_181_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_181_csa.pdf | Document Posted | N/A | N/A | 9/30/2025 | 3/18/2019 | N/A | N/A | 9/30/2025 |  |  | 5/1/2025 | 5/1/2025 |  | N | No
AE2-185 - moved to TC1 | Gladys DP-Stonemill Switching Station 69 kV | Gladys II Solar Farm | VA | Campbell | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2185_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-187 - moved to TC1 | Shockoe DP-Chatham 69 kV |  | VA | Pittsylvania | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2187_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2019 | N/A | N/A |  |  |  | 9/1/2020 |  |  | N | No
AE2-204 | Bolivar 34.5 kV | Bolivar Solar | OH | Stark | Engineering and Procurement | AEP | 19.3 | 19.3 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2204_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2204_fac.pdf | Document Posted | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2204_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2204_wmpa.pdf | Not Required | N/A | N/A | 10/30/2026 | 3/19/2019 | N/A | N/A | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-206 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | Under Construction | Dayton | 99 | 99 | 41.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2206_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2206_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_206_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_206_csa.pdf | Document Posted | N/A | N/A | 6/1/2024 | 3/20/2019 | N/A | N/A | 12/16/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
AE2-210 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 90 | 90 | 65.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2210_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-212 | Harrowgate 34 kV | Harrowgate 1 | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2212_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2212_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2212_wmpa.pdf | Not Required | N/A | N/A |  | 3/20/2019 | N/A | N/A | 1/1/2025 |  |  | 3/30/2025 | 3/30/2025 |  | N | No
AE2-214 | Cole 345 kV | Pleasant Prairie Solar | OH | Franklin | Engineering and Procurement | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2214_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2214_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2214_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_214_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_214_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 3/23/2019 | N/A | N/A | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-216 | Hardin Switch 345 kV | Hardin Energy Center – Storage II | OH | Hardin | Engineering and Procurement | AEP | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2216_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2216_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2216_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_216_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_216_csa.pdf | Document Posted | N/A | N/A | 10/15/2026 | 3/21/2019 | N/A | N/A | 11/15/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-219 | Bluff Point-Randolph 138 kV | Riverstart Solar Park V | IN | Randolph | Engineering and Procurement | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2219_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2219_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2219_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_219_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_219_csa.pdf | Document Posted | N/A | N/A | 3/31/2026 | 3/21/2019 | N/A | N/A | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
AE2-220 | Losantville 345 kV | Riverstart Solar Park II | IN | Randolph | Active | AEP | 125 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2220_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2220_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-221 | Clinton-Stuart 345 kV | Yellow Wood Solar Energy Center | OH | Clinton | Engineering and Procurement | Dayton | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2221_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2221_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_221_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_221_csa.pdf | Document Posted | N/A | N/A | 6/30/2025 | 3/21/2019 | N/A | N/A | 11/24/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-223 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2223_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2223_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AE2-226 | Millville-Old Chapel 138 kV | Rippon | WV | Jefferson | Engineering and Procurement | APS | 99 | 99 | 59.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2226_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2226_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2226_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_226_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_226_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 3/22/2019 | N/A | N/A | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-227 | Iron Bridge 34 kV | Bradley Ridge Solar | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2227_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2227_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2227_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2227_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A | 5/1/2025 |  |  | 3/30/2025 | 3/30/2025 |  | N | No
AE2-228 | Tyler 34 kv | Bradley BridgeSolar | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2228_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2228_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2228_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2228_wmpa.pdf | Not Required | N/A | N/A |  | 3/22/2019 | N/A | N/A | 5/1/2025 |  |  | 3/30/2025 | 3/30/2025 |  | N | No
AE2-230 | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | Under Construction | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2230_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2230_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2230_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_230_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_230_csa.pdf | Document Posted | N/A | N/A | 10/11/2024 | 3/24/2019 | N/A | N/A | 10/25/2024 |  |  | 7/1/2024 | 7/1/2024 |  | N | No
AE2-231 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2231_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-234 | Liberty Center-Buckeye Tap 69 kV |  | IN | Huntington | Active | AEP | 35 | 35 | 24.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2234_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2234_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 7/31/2021 |  |  | N | No
AE2-249 | Bedford North-Pennsylvania Hollow 23 kV | BE-ASTOR | PA | Bedford | Engineering and Procurement | PENELEC | 16.6 | 16.6 | 9.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2249_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_249_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_249_csa.pdf | Document Posted | N/A | N/A | 6/30/2025 | 3/25/2019 | N/A | N/A | 6/30/2025 |  |  | 7/1/2021 | 7/1/2021 |  | N | No
AE2-250 - moved to TC1 | Purdy Sw.-Reams 115 kV |  | VA | Greensville | Active | Dominion | 82.5 | 82.5 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2250_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2250_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2019 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE2-255 | Molecreek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 400 | 100 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2255_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2255_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2255_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_255_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_255_csa.pdf | Document Posted | N/A | N/A | 9/21/2026 | 3/26/2019 | N/A | N/A | 9/21/2026 |  |  | 1/18/2027 | 1/18/2027 |  | N | No
AE2-256 | Copperstone-North Lebanon 230 kV | Lebanon Solar | PA | Lebanon | Engineering and Procurement | ME | 70 | 70 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2256_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2256_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2256_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_256_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_256_csa.pdf | Document Posted | N/A | N/A | 6/1/2026 | 3/27/2019 | N/A | N/A | 7/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AE2-259 | Curdsville-Willis Mtn 115 kV | Blue Rock Solar | VA | Buckingham | Engineering and Procurement | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2259_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2259_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2259_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ae2_259_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-261 - moved to TC1 | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 299 | 299 | 179.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2261_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2261_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-267 | Woodsdale 345 kV | Woodsdale Renewable Energy Center | OH | Butler | Engineering and Procurement | DEOK | 49 | 49 | 28.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2267_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2267_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2267_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_267_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_267_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 3/29/2019 | N/A | N/A | 5/1/2026 |  |  | 6/1/2026 | 6/1/2026 |  | N | No
AE2-275 - moved to TC1 | JK Smith-Fawkes 138 kV |  | KY | Madison | Active | EKPC | 90 | 90 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2275_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2275_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AE2-276 | Sullivan 345kV |  | IN | Sullivan | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2276_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2276_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2019 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AE2-281 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 400 | 50 | 7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2281_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2281_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2281_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_281_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_281_csa.pdf | Document Posted | N/A | N/A | 11/1/2026 | 3/29/2019 | N/A | N/A | 11/1/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
AE2-283 - moved to TC1 | Gladys-Stone Mill 69 kV |  | VA | Campbell | Active | Dominion | 53 | 53 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2283_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2283_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AE2-289 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2289_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2289_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2289_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-291 - moved to TC1 | Grit DP-Perth 115 kV |  | VA | Pittsylvania | Active | Dominion | 102 | 102 | 61.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2291_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 4/1/2021 |  |  | N | No
AE2-298 | Cavett Switch - West Van Wert 69 kV |  | OH | Van Wert | Active | AEP | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2298_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2298_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2298_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AE2-305 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2305_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2305_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 8/1/2021 |  |  | N | No
AE2-308 - moved to TC1 | Three Forks-Dale 138 kV | Madison Solar 1 | KY | Madison | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2308_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2308_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ae2_308_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AE2-313 - moved to TC1 | Carson-Rawlings 500 kV |  | VA | Dinwiddie | Active | Dominion | 314 | 314 | 188.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2313_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2313_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AE2-318 | Ford-Cedarville 138 kV | Clermont County Solar Project | OH | Clermont | Engineering and Procurement | DEOK | 100 | 100 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2318_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2318_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2318_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_318_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_318_csa.pdf | Document Posted | N/A | N/A | 9/1/2024 | 3/31/2019 | N/A | N/A | 10/1/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AE2-321 - moved to TC1 | Belvidere-Marengo 138 kV |  | IL | McHenry | Active | ComEd | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2321_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2321_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AE2-322 | Mark Center 69 kV | Mark Center Solar Project | OH | Defiance | Engineering and Procurement | AEP | 60 | 60 | 40.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2322_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2322_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2322_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_322_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_322_csa.pdf | Document Posted | N/A | N/A | 6/25/2025 | 3/30/2019 | N/A | N/A | 6/25/2025 |  |  | 5/31/2025 | 5/31/2025 |  | N | No
AE2-323 | Twin Branch-Guardian 138 kV | Elkhart County Solar Project | IN | Elkhart | Engineering and Procurement | AEP | 100 | 100 | 67.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2323_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2323_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2323_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_323_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_323_csa.pdf | Document Posted | N/A | N/A | 10/31/2025 | 3/30/2019 | N/A | N/A | 2/15/2026 |  |  | 5/1/2026 | 5/1/2026 |  | N | No
AE2-325 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2325_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2325_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-326 | Jacksons Ferry 138 kV |  | VA | Wythe | Active | AEP | 127.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2326_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2326_imp.html | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-333 | Bedington 138 kV | Bedington Energy Facility | MD | Frederick | Engineering and Procurement | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2333_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2333_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2333_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_333_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_333_csa.pdf | Document Posted | N/A | N/A | 6/15/2025 | 4/1/2019 | N/A | N/A | 6/15/2025 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
AE2-334 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Engineering and Procurement | AEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2334_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2334_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2334_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_334_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_334_csa.pdf | Document Posted | N/A | N/A |  | 4/1/2019 | N/A | N/A | 12/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AE2-339 | Avon 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2339_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2339_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2339_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-341 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 150 | 150 | 100.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2341_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2341_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AE2-342 | Woodstock 69 kV | Woodstock Solar | OH | Champaign | Engineering and Procurement | Dayton | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2342_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2342_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2342_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_342_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_342_csa.pdf | Document Posted | N/A | N/A | 2/15/2025 | 3/31/2019 | N/A | N/A | 3/17/2025 |  |  | 4/15/2025 | 4/15/2025 |  | N | No
AE2-343 | Andover (Maysville) 69 kV II | Welcome Solar III, LLC | PA | Crawford | Engineering and Procurement | ATSI | 17.9 | 17.9 | 12.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2343_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2343_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2343_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_343_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_343_csa.pdf | Document Posted | N/A | N/A | 3/29/2024 | 4/1/2019 | N/A | N/A | 7/30/2026 |  |  | 5/29/2024 | 5/29/2024 |  | N | No
AE2-345 | Hunterstown-Texas Eastern Tap 115 kV | Granite Hill Solar | PA | Adams | Engineering and Procurement | ME | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2345_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2345_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2345_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_345_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ae2_345_csa.pdf | Document Posted | N/A | N/A | 1/2/2026 | 3/13/2019 | N/A | N/A | 1/12/2026 |  |  | 2/1/2026 | 2/1/2026 |  | N | No
AF1-006 | Fairview East 34.5 kV | Erie Solar | PA | Erie | Engineering and Procurement | PENELEC | 20 | 20 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1006_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1006_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1006_wmpa.pdf | Not Required | N/A | N/A | 9/13/2024 | 4/2/2019 | N/A | N/A | 10/4/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AF1-007 | Indian River 230 kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Engineering and Procurement | DPL | 255.1 | 7.3 | 1.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1007_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1007_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_007_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_007_csa.pdf | Document Posted | N/A | N/A | 2/1/2027 | 4/1/2019 | N/A | N/A | 12/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF1-014 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 149.9 | 19.9 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_014_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_014_csa.pdf | Document Posted | N/A | N/A |  | 4/4/2019 | N/A | N/A | 10/28/2025 |  |  | 3/31/2025 | 3/31/2025 |  | N | No
AF1-015 | Easton-Steele 138 kV II | Crockett Solar Project | MD | Talbot | Engineering and Procurement | DPL | 59 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_015_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_015_csa.pdf | Document Posted | N/A | N/A |  | 4/3/2019 | N/A | N/A | 3/31/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
AF1-018 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Engineering and Procurement | Dominion | 80 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1018_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1018_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_018_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_018_csa.pdf | Document Posted | N/A | N/A |  | 4/3/2019 | N/A | N/A | 2/1/2026 |  |  | 3/1/2026 | 3/1/2026 |  | N | No
AF1-019 | Branchville-Holiday Lakes 34.5 kV | Viridity Energy Solutions Montague Storage | NJ | Sussex | Under Construction | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1019_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1019_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_019_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_019_csa.pdf | Document Posted | N/A | N/A | 10/31/2024 | 4/6/2019 | N/A | N/A | 11/30/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
AF1-021 | Bethelboro-Connellsville #1 25 kV | Pechin Solar | PA | Fayette | Under Construction | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1021_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1021_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1021_wmpa.pdf | Not Required | N/A | N/A | 7/31/2024 | 4/17/2019 | N/A | N/A | 8/30/2024 |  |  | 11/30/2024 | 11/30/2024 |  | N | No
AF1-022 | Lake Lynn-Uniontown 25 kV | Gans Solar Farm | PA | Fayette | Under Construction | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1022_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1022_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1022_wmpa.pdf | Not Required | N/A | N/A | 8/30/2024 | 4/16/2019 | N/A | N/A | 9/27/2024 |  |  | 11/30/2024 | 11/30/2024 |  | N | No
AF1-028 | Endless Caverns 115 kV | Prospect Power | VA | Rockingham | Engineering and Procurement | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1028_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_028_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_028_csa.pdf | Document Posted | N/A | N/A |  | 5/13/2019 | N/A | N/A | 1/1/2026 |  |  | 2/1/2026 | 2/1/2026 |  | N | No
AF1-030 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 250 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1030_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/17/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-038 | Sewellton Jct-Webbs Crossroads 69 kV | Mt Olive Creek Solar | KY | Russell | Engineering and Procurement | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_038_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_038_csa.pdf | Document Posted | N/A | N/A | 6/30/2026 | 6/8/2019 | N/A | N/A | 7/30/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
AF1-045 | Cedarville-Ford 138 kV | Clermont County Solar Project | OH | Clermont | Engineering and Procurement | DEOK | 152.2 | 52.2 | 31.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1045_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1045_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_045_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_045_csa.pdf | Document Posted | N/A | N/A | 9/1/2024 | 6/28/2019 | N/A | N/A | 10/1/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AF1-048 - moved to TC1 | Belvidere-Marengo |  | IL | McHenry | Active | ComEd | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1048_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-049 | Berry Hill 138 kV |  | VA | Pittsylvania | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1049_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/12/2019 | N/A | N/A |  |  |  | 11/25/2022 |  |  | N | No
AF1-050 | Summer Shade - Green County 161 kV | Horseshoe Bend Solar | KY | Green | Engineering and Procurement | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1050_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1050_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_050_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_050_csa.pdf | Document Posted | N/A | N/A | 8/31/2026 | 7/14/2019 | N/A | N/A | 9/15/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
AF1-051 | Gavin 765 kV | Gavin Unit No. 1 | OH | Gallia | Engineering and Procurement | AEP | 1360 | 11 | 11 |  | Capacity | Generation Interconnection | Coal |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_051_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 7/13/2019 | N/A | N/A | 5/20/2025 |  |  | 5/31/2024 | 5/31/2024 |  | N | No
AF1-053 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 118 | 40 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1053_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AF1-054 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 156.5 | 38.5 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1054_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AF1-062 | Jug Street 138 kV | Flint Grid | OH | Licking | Engineering and Procurement | AEP | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1062_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1062_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_062_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_062_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 7/31/2019 | N/A | N/A | 7/1/2026 |  |  | 11/1/2026 | 11/1/2026 |  | N | No
AF1-063 | Lockwood Road 138 kV |  | OH | Defiance | Active | AEP | 30 | 30 | 19.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1063_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_063_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 7/31/2019 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF1-064 | Weston 69 kV | Juliet Energy | OH | Wood | Engineering and Procurement | ATSI | 50 | 50 | 33.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1064_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1064_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_064_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_064_csa.pdf | Document Posted | N/A | N/A | 8/1/2025 | 7/31/2019 | N/A | N/A | 8/1/2025 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
AF1-069 | Carson-Rogers Rd 500 kV |  | VA | Sussex | Active | Dominion | 394 | 94 | 67.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1069_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-071 | College Corner 138 kV |  | OH | Preble | Active | AEP | 98 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1071_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2019 | N/A | N/A |  |  |  | 7/1/2019 |  |  | N | No
AF1-078 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | Under Construction | Dayton | 144 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1078_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_078_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 6/30/2024 | 8/27/2019 | N/A | N/A | 12/16/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
AF1-083 | Green County-Saloma 161 kV | Flat Run Solar | KY | Barren | Engineering and Procurement | EKPC | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1083_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1083_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_083_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_083_csa.pdf | Document Posted | N/A | N/A | 10/27/2026 | 8/31/2019 | N/A | N/A | 11/30/2026 |  |  | 12/15/2026 | 12/15/2026 |  | N | No
AF1-084 | Hartford-Almena 69 kV |  | MI | Van Buren | Active | AEP | 85 | 85 | 54.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1084_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1084_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AF1-086 | Madera-Westover South 115 kV | Rogue's Wind | PA | Clearfield | Engineering and Procurement | PENELEC | 109.9 | 109.9 | 20.54 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1086_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_086_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_086_csa.pdf | Document Posted | N/A | N/A | 8/15/2025 | 8/30/2019 | N/A | N/A | 9/30/2025 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AF1-090 | Kincaid-Pana |  | IL | Christian | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1090_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AF1-091 | Varner - Sowers 138 kV |  | IN | DeKalb | Active | AEP | 180 | 180 | 138.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1091_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-092 | Huntington Jct. 138 kV |  | IN | Huntington | Engineering and Procurement | AEP | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1092_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_092_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_092_csa.pdf | Document Posted | N/A | N/A | 5/28/2026 | 8/30/2019 | N/A | N/A | 6/30/2026 |  |  | 6/1/2022 |  |  | N | No
AF1-093 | Henderson-Stoneboro 69 kV | Jackson Center Solar II | PA | Mercer | Engineering and Procurement | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_093_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_093_csa.pdf | Document Posted | N/A | N/A | 10/15/2025 | 8/31/2019 | N/A | N/A | 10/20/2025 |  |  | 8/15/2024 | 8/15/2024 |  | N | No
AF1-094 | Union City-Cambridge Springs 34.5 kV | Franklin Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1094_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_094_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_094_csa.pdf | Document Posted | N/A | N/A | 7/6/2026 | 8/30/2019 | N/A | N/A | 7/6/2026 |  |  | 9/20/2026 | 9/20/2026 |  | N | No
AF1-099 - moved to TC1 | Moshannon-Milesburg 230 kV III |  | PA | Clearfield | Active | APS | 126.5 | 126.5 | 75.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1099_fea.pdf | Document Posted |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-104 | Erie West 34.5 kV | Elder West | PA | Erie | Engineering and Procurement | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1104_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1104_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1104_wmpa.pdf | Not Required | N/A | N/A |  | 9/10/2019 | N/A | N/A | 9/1/2026 |  |  | 10/15/2026 | 10/15/2026 |  | N | No
AF1-106 | East Sayre 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1106_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-112 | Centre Hall-Boalsburg 46 kV | Centre Hall | PA | Centre | Engineering and Procurement | APS | 15 | 15 | 8.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1112_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1112_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1112_wmpa.pdf | Not Required | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 10/31/2026 | 10/31/2026 |  | N | No
AF1-116 | Marion County 161 kV |  | KY | Washington | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af116_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/12/2019 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AF1-118 | Sorenson-Desoto 345 kV |  | IN | Wells | Active | AEP | 350 | 350 | 268.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1118_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-119 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1119_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-123 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 833 | 833 | 253.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1123_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_123_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_123_csa.pdf | Document Posted | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AF1-124 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 836 | 836 | 254.1 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1124_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_124_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_124_csa.pdf | Document Posted | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AF1-125 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 820 | 820 | 249.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1125_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_125_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_125_csa.pdf | Document Posted | N/A | N/A |  | 9/17/2019 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AF1-128 - moved to TC1 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1128_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_128_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_128_csa.pdf | Document Posted | N/A | N/A | 3/31/2028 | 9/18/2019 | N/A | N/A | 6/30/2028 |  |  | 6/1/2023 |  |  | N | No
AF1-129 | Chesterfield 230 kV | Chesterfield CT Units 3&4 | VA | Chesterfield | Engineering and Procurement | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1129_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1129_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_129_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_129_csa.pdf | Document Posted | N/A | N/A | 3/31/2028 | 9/18/2019 | N/A | N/A | 6/30/2028 |  |  | 12/31/2029 | 12/31/2029 |  | N | No
AF1-130 | Inez 138 kV | Martin County Solar Project | KY | Martin | Under Construction | AEP | 190 | 190 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1130_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1130_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_130_csa.pdf | Document Posted | N/A | N/A | 6/3/2024 | 9/19/2019 | N/A | N/A | 9/30/2024 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AF1-140 | Claysburg 23 kV | BL-Diamond Bear Rocks | PA | Adams | Engineering and Procurement | PENELEC | 16.3 | 16.3 | 9.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1140_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1140_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1140_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2019 | N/A | N/A | 10/31/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AF1-141 | Varner 138 kV |  | IN | DeKalb | Active | AEP | 96 | 96 | 62.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1141_imp.htm | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_141_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 8/30/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-142 - moved to TC1 | Moshannon-Milesburg 230 kV IV |  | PA | Clearfield | Active | APS | 202.4 | 202.4 | 121.44 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1142_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2019 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF1-143 | Lick Run 115 kV |  | PA | Somerset | Active | PENELEC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1143_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1143_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-147 | Poland Rd-Runway DP 230kV | Dulles Solar | VA | Loudoun | Engineering and Procurement | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1147_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1147_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_147_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_147_csa.pdf | Document Posted | N/A | N/A | 7/15/2025 | 9/20/2019 | N/A | N/A | 7/15/2026 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
AF1-148 | Sorenson-Desoto 345 kV |  | IN | Wells | Active | AEP | 159 | 159 | 95.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1148_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 4/30/2023 |  |  | N | No
AF1-152 - moved to TC1 | Swamp 230 kV |  | NC | Pasquotank | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1152_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AF1-155 | Paper City-Wilcox 46 kV | FR-Boyer Mill Guilford34.5 | PA | Elk | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1155_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1155_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1155_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2019 | N/A | N/A |  |  |  | 2/28/2023 | 2/28/2023 |  | N | No
AF1-158 | Edison-Gravel Pit 138 kV | Honeysuckle Solar Project | IN | St. Joseph | Partially in Service - Under Construction | AEP | 150 | 150 | 90 | 150 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1158_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1158_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_158_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_158_csa.pdf | Document Posted | N/A | N/A | 4/23/2024 | 9/24/2019 | N/A | N/A | 6/6/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
AF1-159 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | Engineering and Procurement | Dayton | 49.9 | 0 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1159_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1159_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_159_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_159_csa.pdf | Document Posted | N/A | N/A | 11/30/2024 | 9/20/2019 | N/A | N/A | 12/15/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AF1-161 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1161_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF1-162 | Inez 138 kV |  | KY | Martin | Active | AEP | 300 | 100 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1162_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_162_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF1-164 | Southwest Lima 345 kV |  | OH | Allen | Active | AEP | 300 | 300 | 195 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1164_imp.htm | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_164_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/20/2019 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF1-165 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1165_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-170 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Active | PENELEC | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1170_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 2/15/2023 |  |  | N | No
AF1-176 - moved to TC1 | Corey 138 kV |  | MI | St. Joseph | Active | AEP | 300 | 300 | 155.684 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1176_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF1-202 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1202_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1202_imp.html | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_202_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-203 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | Partially in Service - Under Construction | EKPC | 55 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1203_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1203_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1203_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_203_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_203_csa.pdf | Document Posted | N/A | N/A | 4/15/2024 | 9/29/2019 | N/A | N/A | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 |  | N | No
AF1-204 - moved to TC1 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 255 | 255 | 63.75 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1204_imp.html | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-206 | East Fayette 138 kV |  | OH | Fulton | Active | ATSI | 199 | 199 | 119.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1206_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1206_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 11/1/2022 |  |  | N | No
AF1-207 | Reynolds-Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 180 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1207_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1207_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-208 | Laurel-Roadstown 69 kV |  | NJ | Salem | Active | AEC | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1208_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1208_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1208_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-210 | Burma 23 kV | CL-Route 58 S | PA | Clarion | Engineering and Procurement | APS | 15.9 | 15.9 | 9.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1210_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1210_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1210_wmpa.pdf | Not Required | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-211 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1211_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1211_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-212 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1212_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/26/2019 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF1-215 | Olive-Reynolds 345 kV | Mammoth North Solar Project | IN | Starke | Under Construction | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1215_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1215_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1215_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_215_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_215_csa.pdf | Document Posted | N/A | N/A | 8/20/2024 | 9/28/2019 | N/A | N/A | 8/21/2024 |  |  | 7/31/2024 | 7/31/2024 |  | N | No
AF1-217 | Edinboro -Cambridge Springs 34.5 kV | Crawford Solar II | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1217_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1217_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1217_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1217_wmpa.pdf | Not Required | N/A | N/A |  | 9/28/2019 | N/A | N/A | 12/31/2025 |  |  | 3/29/2024 | 3/29/2024 |  | N | No
AF1-221 - moved to TC1 | College Corner-Drewersburg 138 kV |  | IN | Franklin | Active | AEP | 180 | 180 | 25.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1221_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF1-223 | Keystone-Desoto 345 kV |  | IN | Jay | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1223_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1223_imp.html | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-227 | Marysville – Gunn Road 345 kV | Union Solar | OH | Union | Partially in Service - Under Construction | AEP | 325 | 325 | 195 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1227_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1227_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1227_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_227_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_227_csa.pdf | Document Posted | N/A | N/A | 4/9/2024 | 9/30/2019 | N/A | N/A | 5/14/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AF1-228 | Beatty-Greene 345 kV | Springwater Solar | OH | Madison | Engineering and Procurement | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1228_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1228_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1228_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_228_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 4/21/2026 | 9/27/2019 | N/A | N/A | 4/21/2026 |  |  | 8/31/2026 | 8/31/2026 |  | N | No
AF1-229 | Galion-South Berwick 345 kV | Tymochtee Solar | OH | Wyandot | Engineering and Procurement | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1229_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1229_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_229_gia.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_229_csa.pdf | Document Posted | N/A | N/A | 4/21/2026 | 9/27/2019 | N/A | N/A | 4/21/2026 |  |  | 8/31/2026 | 8/31/2026 |  | N | No
AF1-231 | New Church 138 kV |  | VA | Accomack | Active | DPL | 19 | 19 | 7.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1231_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-233 - moved to TC1 | Flemingsburg – Spurlock 138kV | AEUG Fleming Solar | KY | Fleming | Active | EKPC | 188.5 | 188.5 | 113.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1233_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1233_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_233_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF1-237 | Mercer 230 kV | Lamberton Road Battery | NJ | Mercer | Engineering and Procurement | PSEG | 170 | 170 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1237_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1237_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_237_gia.pdf | Document Posted | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 8/11/2027 | 8/11/2027 |  | N | No | This project slid to the next queue
AF1-238 - moved to TC1 | Sherman Ave - West Vineland 69 kV |  | NJ | Cumberland | Active | AEC | 77.7 | 77.7 | 31 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1238_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1238_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No | This project slid to the next queue
AF1-239 | Sherman Ave - West Vineland 69 kV | South Orchard | NJ | Cumberland | Engineering and Procurement | AEC | 30 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1239_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1239_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1239_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1239_wmpa.pdf | Not Required | N/A | N/A | 3/1/2028 | 9/28/2019 | N/A | N/A | 5/1/2028 |  |  | 6/1/2028 | 6/1/2028 |  | N | No
AF1-240 - moved to TC1 | Timblin 34.5 kV |  | PA | Armstrong | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1240_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1240_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF1-245 | Hudson 230 kV |  | NJ | Hudson | Active | PSEG | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1245_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1245_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1245_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF1-249 | Nickel 12.47 kV | Nickel Solar | OH | Warren | Under Construction | DEOK | 19.92 | 19.92 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1249_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1249_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1249_wmpa.pdf | Not Required | N/A | N/A | 7/23/2024 | 10/2/2019 | N/A | N/A | 7/23/2024 |  |  | 7/30/2024 | 7/30/2024 |  | N | No
AF1-254 | Milnor-Huyetts 34.5 kV | FR-Williamsport | PA | Franklin | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1254_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1254_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1254_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1254_wmpa.pdf | Not Required | N/A | N/A | 10/31/2025 | 9/30/2019 | N/A | N/A | 11/28/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AF1-256 - moved to TC1 | Flemingsburg-Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1256_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1256_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF1-264 | Runnemede 13 kV | Owens Corning Solar | NJ | Gloucester | Partially in Service - Under Construction | PSEG | 3 | 0 | 1.3 | 3 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1264_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1264_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_264_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A | 5/1/2021 | 9/30/2019 | N/A | N/A | 5/15/2021 |  |  | 9/30/2023 | 9/30/2023 | 6/1/2021 | N | No
AF1-268 | Desoto-Jay 138 kV |  | IN | Delaware | Active | AEP | 83 | 83 | 57.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1268_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1268_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 1/31/2022 |  |  | N | No
AF1-271A | Gratz 69 kV | G Morris Solar | PA | Dauphin | Engineering and Procurement | PPL | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1271a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1271A_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1271a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_271a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_271a_csa.pdf | Document Posted | N/A | N/A | 1/31/2026 | 9/27/2019 | N/A | N/A | 3/2/2026 |  |  | 4/15/2026 | 4/15/2026 |  | N | No
AF1-272 | Lucerne 115 kV | Hoodlebug Solar Energy Center | PA | Indiana | Engineering and Procurement | PENELEC | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1272_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1272_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1272_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_272_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 5/31/2027 | 10/1/2019 | N/A | N/A | 6/21/2027 |  |  | 8/31/2027 | 8/31/2027 |  | N | No
AF1-275 | Cole 345 kV |  | OH | Franklin | Active | AEP | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1275_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1275_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF1-280 - moved to TC1 | Nelson-Lee County |  | IL | Lee | Active | ComEd | 200 | 200 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1280_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1280_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-282 | Stuart-Clinton 345 kV |  | OH | Highland | Active | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1282_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1282_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/20/2022 |  |  | N | No
AF1-283 | Stuart-Clinton 345 kV |  | OH | Highland | Active | Dayton | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1283_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1283_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AF1-291 | Tyler 34.5 kV | Chester Solar Technology Park | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1291_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1291_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1291_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A | 3/30/2025 |  |  | 10/31/2022 | 10/31/2022 |  | N | No
AF1-291A | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | Under Construction | APS | 80 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1291a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1291a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1291a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_291a_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_291a_csa.pdf | Document Posted | N/A | N/A | 10/11/2024 | 10/1/2019 | N/A | N/A | 10/25/2024 |  |  | 7/1/2024 | 7/1/2024 |  | N | No
AF1-292 | Fields 34.5kV | Jarratt Solar | VA | Greensville | Engineering and Procurement | Dominion | 14.9 | 14.9 | 8.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1292_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1292_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1292_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1292_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AF1-294 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 41 | 41 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1294_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1294_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF1-296 - moved to TC1 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 212.1 | 212.1 | 37.3296 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1296_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1296_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF1-299 | Otter Point 34.5 kV I | Fairview Farms II | MD | Harford | Under Construction | BGE | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1299_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1299_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1299_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1299_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A | 12/30/2024 |  |  | 12/30/2024 | 12/30/2024 |  | N | No
AF1-300 | Otter Point 34.5 kV II | Fairview Farms I | MD | Harford | Under Construction | BGE | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1300_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1300_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1300_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1300_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A | 12/30/2024 |  |  | 12/30/2024 | 12/30/2024 |  | N | No
AF1-302 | Brookville-Squab Hollow 138 kV |  | PA | Jefferson | Active | APS | 132 | 42 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1302_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1302_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF1-314 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 212 | 212 | 37.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1314_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AF1-319 | Honda Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 58 | 58 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1319_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1319_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF1-321 | Hooversville 115 kV I | SunEast Hooversville Solar | PA | Somerset | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1321_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1321_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1321_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_321_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_321_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 9/30/2019 | N/A | N/A | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF1-322 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1322_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1322_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2019 | N/A | N/A |  |  |  | 8/15/2022 |  |  | N | No
AF1-323 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1323_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1323_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF1-325 | Sparta-Woodruff's Gap 34.5 kV | Houses Corner Storage | NJ | Sussex | Engineering and Procurement | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1325_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1325_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1325_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_325_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_325_csa.pdf | Document Posted | N/A | N/A | 12/1/2025 | 9/30/2019 | N/A | N/A | 12/15/2025 |  |  | 1/1/2026 | 1/1/2026 |  | N | No
AF1-328 | Hackettstown-Pohatcong 34.5 kV | Mansfield #3 | NJ | Warren | Engineering and Procurement | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1328_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1328_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1328_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_328_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af1_328_csa.pdf | Document Posted | N/A | N/A | 2/17/2025 | 9/30/2019 | N/A | N/A | 2/18/2025 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
AF1-330 | Marengo 34.5 kV |  | IL | McHenry | Active | ComEd | 20 | 20 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1330_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1330_imp.htm | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AF1-331 | Twombley Road |  | IL | Ogle | Active | ComEd | 60 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1331_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1331_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2019 | N/A | N/A |  |  |  | 9/15/2021 |  |  | N | No
AF1-333 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1333_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1333_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1333_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-337 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1337_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1337_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1337_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-338 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1338_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1338_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1338_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF1-339 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1339_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1339_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1339_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/27/2019 | N/A | N/A |  |  |  | 3/1/2021 |  |  | N | No
AF2-001 | Hooversville 115 kV II | SunEast Hooversville Solar | PA | Somerset | Engineering and Procurement | PENELEC | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2001_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2001_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_001_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_001_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 10/1/2019 | N/A | N/A | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF2-002 | Hooversville 115 kV III | SunEast Hooversville Solar | PA | Somerset | Engineering and Procurement | PENELEC | 50 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2002_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2002_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_002_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_002_csa.pdf | Document Posted | N/A | N/A | 5/1/2026 | 10/1/2019 | N/A | N/A | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
AF2-004 | Beaver 345 kV |  | OH | Lorain | Active | ATSI | 378.2 | 33 | 33 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2004_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 11/1/2020 |  |  | N | No
AF2-005 | Beaver 138 kV |  | OH | Lorain | Active | ATSI | 95.2 | 8 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2005_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2019 | N/A | N/A |  |  |  | 11/1/2020 |  |  | N | No
AF2-010 - moved to TC1 | Union City-Titusville 115 kV |  | PA | Erie | Active | PENELEC | 77 | 77 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2010_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/11/2019 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-013 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2013_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2019 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AF2-014 | Maddox Creek 345 kV |  | OH | Van Wert | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2014_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/18/2019 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-018 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 200 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2018_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/1/2019 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-019 | Middle 69 kV |  | NJ | Cape May | Active | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2019_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-020 | Carll's Corner 69 kV |  | NJ | Cumberland | Active | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2020_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-024 | Mickleton 69 kV |  | NJ | Gloucester | Active | AEC | 24 | 24 | 9.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2024_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-025 - moved to TC1 | Ontario 69 kV |  | NJ | Atlantic | Active | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2025_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-027 | Zion Energy Center 345 kV |  | IL | Lake | Active | ComEd | 635 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2027_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/15/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-029 | Ronco 500 kV |  | PA | Fayette | Active | APS | 726 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2029_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-030 | Ontelaunee 230 kV |  | PA | Berks | Active | ME | 650 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2030_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-031 | Calumet |  | IL | Cook | Active | ComEd | 347 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2031_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-032 | Kincaid 345 kV |  | IL | Christian | Active | ComEd | 1132 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2032_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-034 - moved to TC1 | Kendall 345kV |  | IL | Kendall | Active | ComEd | 1238.8 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2034_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 10/28/2019 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-035 - moved to TC1 | St. Johns 115 kV |  | VA | Hanover | Active | Dominion | 72 | 72 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2035_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 11/27/2019 | N/A | N/A |  |  |  | 10/27/2023 |  |  | N | No
AF2-037 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 94 | 94 | 56.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2037_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 11/29/2019 | N/A | N/A |  |  |  | 7/1/2021 |  |  | N | No
AF2-039 | Shawville-Clearfield 34.5 kV |  | PA | Clearfield | Engineering and Procurement | PENELEC | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2039_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2039_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2039_wmpa.pdf | Not Required | N/A | N/A |  | 11/29/2019 | N/A | N/A | 7/3/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AF2-041 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2041_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2019 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-042 - moved to TC1 | Clover-Rawlings 500 kV |  | VA | Halifax | Active | Dominion | 500 | 500 | 300 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2042_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2019 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-046 - moved to TC1 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 150 | 150 | 99.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2046_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2019 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-048 | Rio-Lick 138 kV |  | OH | Jackson | Active | AEP | 140 | 70 | 46.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2048_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2019 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-050 - moved to TC1 | Bearrock-Johnstown 230 kV |  | PA | Cambria | Active | PENELEC | 150 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2050_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2019 | N/A | N/A |  |  |  | 9/1/2021 |  |  | N | No
AF2-054 | Wan 34.5 kV | Camellia Solar | VA | Gloucester | Engineering and Procurement | Dominion | 19.9 | 19.9 | 11.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2054_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2054_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2054_wmpa.pdf | Not Required | N/A | N/A |  | 1/10/2020 | N/A | N/A |  |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AF2-056 - moved to TC1 | Shenandoah Tap 1– Mahanoy Tap 2 69 kV |  | PA | Schuylkill | Active | PPL | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2056_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/16/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-060 | Wattsville 12 kV | Scout Storage I | VA | Accomack | Engineering and Procurement | DPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2060_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2060_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2060_wmpa.pdf | Not Required | N/A | N/A |  | 1/25/2020 | N/A | N/A | 10/1/2024 |  |  | 10/1/2024 | 10/1/2024 |  | N | No
AF2-061 | Wattsville 69kV |  | VA | Accomack | Active | DPL | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2061_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2020 | N/A | N/A |  |  |  | 6/30/2021 |  |  | N | No
AF2-063 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2063_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2020 | N/A | N/A |  |  |  | 2/1/2023 |  |  | N | No
AF2-066 | West Manchester-Crown 69kV |  | OH | Preble | Active | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2066_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-067 | West Manchester 69 kV |  | OH | Preble | Active | Dayton | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2067_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-068 - moved to TC1 | Jay 138 kV |  | IN | Blackford | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2068_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2020 | N/A | N/A |  |  |  | 10/3/2022 |  |  | N | No
AF2-069 - moved to TC1 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 88.7 | 9.3 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2069_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/4/2021 |  |  | N | No
AF2-070 - moved to TC1 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 72.6 | 18.15 | 3.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2070_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/4/2021 |  |  | N | No
AF2-075 | Bartonsville-Meadow Brook 138 kV III | Bartonsville Energy Facility | VA | Frederick | Under Construction | APS | 130 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_075_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_075_csa.pdf | Document Posted | N/A | N/A | 10/11/2024 | 2/1/2020 | N/A | N/A | 10/25/2024 |  |  | 7/1/2024 | 7/1/2024 |  | N | No
AF2-077 | White Marsh 34.5 kV | Winterberry Solar | VA | Gloucester | Partially in Service - Under Construction | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2077_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2077_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2077_wmpa.pdf | Not Required | N/A | N/A |  | 2/1/2020 | N/A | N/A | 6/26/2024 |  |  | 8/14/2024 | 8/14/2024 |  | N | No
AF2-078 | Reynolds-Olive #1 345 kV |  | IN | White | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2078_imp.html | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-080 - moved to TC1 | Chinquapin-Everetts 230 kV |  | NC | Pitt | Active | Dominion | 150 | 70 | 48.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2080_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AF2-081 - moved to TC1 | Moyock 230 kV |  | NC | Currituck | Active | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2081_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-082 | Dauphin PG Tie–Dauphin Juniata Tie 69 k |  | PA | Dauphin | Active | PPL | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2082_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-083 | Kenzie Creek-Stone Lake 69 kV |  | MI | Cass | Active | AEP | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2083_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_083_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 10/21/2022 |  |  | N | No
AF2-084 | Honda-Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 100 | 42 | 28.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2084_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AF2-086 | Scott Tap-Bowmans Mill Tap 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2086_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/3/2020 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AF2-088 | Shawville-Clearfield 34.5 kV II |  | PA | Clearfield | Engineering and Procurement | PENELEC | 20 | 6.5 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2088_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2088_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2088_wmpa.pdf | Not Required | N/A | N/A |  | 2/5/2020 | N/A | N/A | 7/3/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
AF2-090 | Central Hardin 138 kV |  | KY | Hardin | Active | EKPC | 110 | 110 | 73.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2090_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/6/2020 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AF2-091 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 134 | 34 | 14.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2091_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/7/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-094 | Huntington Jct. 138 kV |  | IN | Huntington | Active | AEP | 190 | 40 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2094_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2020 | N/A | N/A |  |  |  | 2/1/2022 |  |  | N | No
AF2-095 - moved to TC1 | Davis Creek 138 kV |  | IL | Kankakee | Active | ComEd | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2095_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/13/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-096 - moved to TC1 | Braidwood-East Frankfort 345 kV |  | IL | Will | Active | ComEd | 375 | 375 | 255 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2096_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2020 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AF2-103 | Haviland 138 kV | Northwest Ohio Wind | OH | Paulding | Partially in Service - Under Construction | AEP | 103.15 | 3.15 | 1.32 | 2 | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af2_103_isa.pdf | Document Posted | N/A |  | Not Required | N/A | N/A |  | 3/17/2020 | N/A | N/A |  |  |  | 2/1/2021 | 2/1/2021 | 6/1/2021 | N | No
AF2-105 | Morgans Cut-Glen Lyn #2 138 kV |  | VA | Pulaski | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2105_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2105_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/28/2022 |  |  | N | No
AF2-106 | Hazel Hollow-Glen Lyn #1 138 kV |  | VA | Pulaski | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2106_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2020 | N/A | N/A |  |  |  | 3/28/2022 |  |  | N | No
AF2-107 | Clifford 138 kV |  | VA | Amherst | Active | AEP | 50 | 50 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2107_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2020 | N/A | N/A |  |  |  | 2/1/2022 |  |  | N | No
AF2-110 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Engineering and Procurement | Dominion | 69 | 20 | 7.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af2_110_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_110_csa.pdf | Document Posted | N/A | N/A | 8/12/2025 | 2/27/2020 | N/A | N/A | 9/15/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AF2-111 - moved to TC1 | North Clark-Spurlock 345 kV |  | KY | Mason | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2111_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-114 | Old Chapel-Millville 138 kV II |  | WV | Jefferson | Active | APS | 92.5 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2114_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AF2-115 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 66 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2115_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-116 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 90 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2116_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2116_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-117 | Warfordsburg-McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 70 | 70 | 46.67 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2117_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-120 - moved to TC1 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2120_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_120_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_120_csa.pdf | Document Posted | N/A | N/A | 12/1/2025 | 2/28/2020 | N/A | N/A | 2/6/2026 |  |  | 12/1/2023 |  |  | N | No
AF2-121 - moved to TC1 | Philipsburg-Shawville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2121_imp.htm | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-122 | Kirk 138 kV | Union Ridge Solar | OH | Licking | Engineering and Procurement | AEP | 107.7 | 107.7 | 64.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2122_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2122_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_122_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_122_csa.pdf | Document Posted | N/A | N/A |  | 2/29/2020 | N/A | N/A | 10/15/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AF2-124 | Kyger Creek-Pierce 345 kV |  | OH | Highland | Active | OVEC | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2124_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-125 | Varner 138 kV |  | IN | DeKalb | Active | AEP | 150 | 54 | 35.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2125_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AF2-126 - moved to TC1 | Weston 69 kV II |  | OH | Wood | Active | ATSI | 62 | 12 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2126_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AF2-127 | Lockwood Road 138 kV |  | OH | Defiance | Active | AEP | 68 | 38 | 24.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2127_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_127_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A |  | 2/28/2020 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF2-130 | Wolfs Corners 34.5 kV | Cobalt Solar | PA | Clarion | Under Construction | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2130_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2130_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_130_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_130_csa.pdf | Document Posted | N/A | N/A | 8/30/2024 | 3/3/2020 | N/A | N/A | 9/2/2024 |  |  | 12/15/2024 | 12/15/2024 |  | N | No
AF2-132 | Reynolds-Olive #1 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2132_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-133 | Reynolds-Olive #2 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2133_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2020 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AF2-134 | Olive-Reynolds #2 345 kV | Mammoth North Solar Project | IN | Starke | Under Construction | AEP | 400 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2134_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2134_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_134_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_134_csa.pdf | Document Posted | N/A | N/A | 8/20/2024 | 3/6/2020 | N/A | N/A | 8/21/2024 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
AF2-137 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 500 | 500 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2137_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2137_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-140 | Saegers 230 kV |  | PA | Lycoming | Active | PPL | 907 | 0 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2140_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2020 | N/A | N/A |  |  |  | 5/1/2021 |  |  | N | No
AF2-142 - moved to TC1 | Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2142_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-143 - moved to TC1 | Powerton-Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2143_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-149 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2149_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2149_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-150 | Galion 138 kV | Blossom Solar | OH | Morrow | Engineering and Procurement | ATSI | 88 | 88 | 36.96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2150_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2150_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_150_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_150_csa.pdf | Document Posted | N/A | N/A | 1/31/2026 | 3/13/2020 | N/A | N/A | 1/31/2026 |  |  | 4/30/2026 | 4/30/2026 |  | N | No
AF2-162 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 245 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2162_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-165 | Clark Summit-Emlenton 34.5 kV | Cardinal Solar | PA | Venango | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2165_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2165_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2165_wmpa.pdf | Not Required | N/A | N/A |  | 3/18/2020 | N/A | N/A | 10/31/2024 |  |  | 12/15/2024 | 12/15/2024 |  | N | No
AF2-171 - moved to TC1 | Madisonville 115 kV |  | VA | Prince Edward | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2171_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AF2-173 - moved to TC1 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2173_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-177 - moved to TC1 | Sorenson-DeSoto #2 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2177_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2177_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/20/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-182 - moved to TC1 | Nelson-Lee County 345 kV II |  | IL | Lee | Active | ComEd | 500 | 300 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2182_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/21/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AF2-187 | Brookside-Cloverdale 138 kV |  | OH | Wayne | Active | ATSI | 120 | 120 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2187_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2187_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-191 | New Carlisle 138 kV |  | IN | St. Joseph | Active | AEP | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2191_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AF2-192 | Frenchtown Solar-West Flemington 34.5 kV | Barbertown Solar | NJ | Hunterdon | Engineering and Procurement | JCPL | 7 | 7 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2192_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2192_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_192_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_192_csa.pdf | Document Posted | N/A | N/A | 3/31/2026 | 3/23/2020 | N/A | N/A | 4/30/2026 |  |  | 6/30/2026 | 6/30/2026 |  | N | No
AF2-199 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 400 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2199_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2199_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-200 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2200_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2200_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AF2-201 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 199 | 199 | 51.4 |  | Capacity | Generation Interconnection | Wind; Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2201_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AF2-204 | Van Buren-Delaware 138 kV |  | IN | Grant | Active | AEP | 110 | 110 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2204_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AF2-205 | Olive-Reynolds #2 345 kV | Moss Creek Solar | IN | Pulaski | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2205_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2205_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_205_isa2.pdf | Interim Study | N/A |  |  | N/A | N/A | 10/30/2027 | 3/25/2020 | N/A | N/A | 11/30/2027 |  |  | 11/30/2027 | 11/30/2027 |  | N | No
AF2-209 - moved to TC1 | South Hicksville-Sowers 138 kV |  | OH | Defiance | Active | AEP | 140 | 140 | 19.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2209_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2209_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2020 | N/A | N/A |  |  |  | 6/2/2023 |  |  | N | No
AF2-221 | Scalp Level 22.9 kV | Stony Creek Solar | PA | Somerset | Engineering and Procurement | PENELEC | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2221_imp.html | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2221_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2221_wmpa.pdf | Not Required | N/A | N/A |  | 3/25/2020 | N/A | N/A | 8/1/2025 |  |  | 10/1/2025 | 10/1/2025 |  | N | No
AF2-222 - moved to TC1 | Madisonville DP-Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 167 | 167 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2222_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2222_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_222_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_222_csa.pdf | Document Posted | N/A | N/A | 12/31/2025 | 3/25/2020 | N/A | N/A | 3/31/2027 |  |  | 5/31/2023 |  |  | N | No
AF2-224 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2224_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2224_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AF2-225 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2225_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2225_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AF2-226 - moved to TC1 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2226_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2226_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-229 | Roxbury 23 kV |  | PA | Cumberland | Active | PENELEC | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2229_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AF2-233 | Penns-Richfield Tie #1 69 kV |  | PA | Snyder | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2233_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2233_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AF2-234 | Sunbury Yard #1-Richfield Tie #2 69 kV |  | PA | Snyder | Active | PPL | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2234_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2234_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AF2-235 | Titusville-Oil Creek 34.5 kV | Big Bell Solar | PA | Crawford | Engineering and Procurement | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2235_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2235_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2235_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af2_235_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 4/30/2027 | 3/27/2020 | N/A | N/A | 6/7/2027 |  |  | 7/31/2027 | 7/31/2027 |  | N | No
AF2-238 | Mansfield-South Troy 34.5 kV | Farmers Valley Solar | PA | Bradford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2238_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2238_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2238_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2020 | N/A | N/A |  |  |  | 7/31/2027 | 7/31/2027 |  | N | No
AF2-243 | Clark Summit 34.5 kV | Pearl Solar | PA | Venango | Engineering and Procurement | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2243_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2243_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2243_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2243_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 7/3/2026 |  |  | 9/2/2026 | 9/2/2026 |  | N | No
AF2-249 | Edgewood 12 kV II | Citron Storage | MD | Wicomico | Engineering and Procurement | DPL | 3 | 3 | 0.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2249_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2249_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2249_wmpa.pdf | Not Required | N/A | N/A |  | 3/27/2020 | N/A | N/A | 12/2/2024 |  |  | 11/30/2023 | 11/30/2023 |  | N | No
AF2-252 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 248 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2252_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2252_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-260 | Stephensburg-Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 85 | 85 | 53 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2260_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/27/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-291 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2291_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF2-295 | Wilcox-Paper City 46 kV | Evergreen Solar | PA | Elk | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2295_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2295_imp.htm | Document Posted |  | In Progress | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2295_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2295_wmpa.pdf | Not Required | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 7/30/2027 | 7/30/2027 |  | N | No
AF2-296 - moved to TC1 | Madera 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2296_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2296_imp.pdf | Document Posted |  | Withdrawn | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 10/1/2021 |  |  | N | No
AF2-297 - moved to TC1 | Sedge Hill 115 kV |  | VA | Halifax | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2297_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2297_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/28/2020 | N/A | N/A |  |  |  | 3/12/2022 |  |  | N | No
AF2-298 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2298_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2298_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 5/1/2022 |  |  | N | No
AF2-299 - moved to TC1 | Fields 34.5 kV | Jarratt Energy Facility 2 | VA | Greensville | Active | Dominion | 19.5 | 25 | 11.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2299_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2299_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-300 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 64 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2300_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2300_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-302 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 75 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2302_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2302_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/12/2022 |  |  | N | No
AF2-303 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2303_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2303_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No | This project slid to the next queue
AF2-304 | Surry-Hopewell 230 kV |  | VA | Surry | Active | Dominion | 89 | 89 | 89 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2304_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2304_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 8/3/2023 |  |  | N | No | This project slid to the next queue
AF2-306 | Hope-Blevins Valley Tap 69 kV |  | KY | Barren | Active | EKPC | 26 | 26 | 26 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2306_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2306_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-307 - moved to TC1 | Hope-Blevins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2307_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2307_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-308 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2308_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2308_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-309 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2309_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2309_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AF2-311 | Gilboa-Jones Branch 138 kV |  | WV | Nicholas | Active | APS | 100 | 100 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2311_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2311_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-316 | Gilboa-Jones Branch 138 kV II |  | WV | Nicholas | Active | APS | 150 | 150 | 82.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2316_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2316_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-319 - moved to TC1 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2319_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2319_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-321 - moved to TC1 | Stryker-Ridgeville 138 kV |  | OH | Williams | Active | ATSI | 148 | 148 | 88.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2321_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-324 - moved to TC1 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2324_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AF2-325 | Jacktown 12 kV | SBC Solar | MD | Dorchester | Engineering and Procurement | DPL | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2325_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2325_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2325_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2325_wmpa.pdf | Not Required | N/A | N/A |  | 3/30/2020 | N/A | N/A | 12/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
AF2-329 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 292.2 | 42.2 | 42.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2329_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2329_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-331 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2331_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2331_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-332 | Montour 230 kV |  | PA | Montour | Active | PPL | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2332_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2332_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-333 | Montour 230 kV |  | PA | Montour | Active | PPL | 120 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2333_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2333_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-334 | Montour 230 kV |  | PA | Montour | Active | PPL | 140 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2334_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2334_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-335 - moved to TC1 | Delaware-Royerton 138 kV |  | IN | Delaware | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2335_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2335_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-336 | Snake Spring 115 kV I |  | PA | Bedford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2336_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2336_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2336_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-337 | Snake Spring 115 kV II |  | PA | Bedford | Active | PENELEC | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2337_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2337_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2337_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-348 - moved to TC1 | North Clark-Spurlock 345 kV |  | KY | Madison | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2348_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2348_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-349 - moved to TC1 | SILVER LAKE- CHERRY VALLEY 345 KV |  | IL | McHenry | Active | ComEd | 300 | 300 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2349_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2349_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-350 - moved to TC1 | Kensington 138 kV |  | IL | Kankakee | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2350_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2350_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-352 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 248 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2352_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2352_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-354 | Washington 34.5 kV II | Washington Solar PH II | NJ | Warren | Engineering and Procurement | JCPL | 19.8 | 11 | 4.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2354_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2354_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af2_354_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_354_csa.pdf | Document Posted | N/A | N/A |  | 3/31/2020 | N/A | N/A | 6/29/2025 |  |  | 8/29/2025 | 8/29/2025 |  | N | No
AF2-355 - moved to TC1 | West Gerrard-J.K. Smith 345 kV |  | KY | Madison | Active | EKPC | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2355_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2355_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AF2-356 | Albright-Mt. Zion 138 kV | CPV Backbone Solar | MD | Garrett | Under Construction | APS | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2356_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2356_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2356_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_356_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/af2_356_csa.pdf | Document Posted | N/A | N/A | 11/8/2024 | 3/31/2020 | N/A | N/A | 11/10/2024 |  |  | 8/31/2025 | 8/31/2025 |  | N | No
AF2-358 - moved to TC1 | Airey-Vienna 69 kV |  | MD | Dorchester | Active | DPL | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2358_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2358_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-359 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2359_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2359_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-363 | Cherry Valley-Glidden 138 kV |  | IL | DeKalb | Active | ComEd | 81.4 | 81.4 | 48.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2363_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2363_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AF2-365 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2365_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2365_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-366 | Crego Rd 138 kV |  | IL | Adams | Active | ComEd | 94.9 | 94.9 | 56.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2366_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-367 | Neville 23 kV | Emsworth Back Channel Dam Hydroelectric Project | PA | Allegheny | Engineering and Procurement | DL | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2367_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2367_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2367_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2367_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 10/31/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AF2-368 | Pine Creek 23 kV | Allegheny Lock and Dam No. 2 Hydroelectric Project | PA | Allegheny | Engineering and Procurement | DL | 9.5 | 9.5 | 9.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2368_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2368_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2368_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2368_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 10/31/2029 |  |  | 12/31/2029 | 12/31/2029 |  | N | No
AF2-370 - moved to TC1 | Delaware-Royerton 138 kV |  | IN | Delaware | Active | AEP | 100 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2370_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2370_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-371 | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 84 | 84 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2371_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2371_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-375 | Ebersole-Fostoria 138 kV |  | OH | Hancock | Active | AEP | 129.6 | 129.6 | 77.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2375_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2375_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AF2-376 | Timber Switch 138 kV |  | OH | Paulding | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2376_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2376_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-377 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2377_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2377_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-378 | Cambridge 12 kV | GGC Solar | MD | Dorchester | Engineering and Procurement | DPL | 2.65 | 2.65 | 1.11 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2378_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2378_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2378_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2378_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A | 3/31/2026 |  |  | 3/31/2024 | 3/31/2024 |  | N | No
AF2-379 | Princess Anne 25 kV | RHC Solar | MD | Somerset | Under Construction | DPL | 3.9 | 3.9 | 1.638 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2379_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2379_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2379_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2379_wmpa.pdf | Not Required | N/A | N/A |  | 4/1/2020 | N/A | N/A | 12/1/2024 |  |  | 12/1/2024 | 12/1/2024 |  | N | No
AF2-380 | Karns City-Bear Creek 25 kV | Richardson Solar | PA | Clarion | Engineering and Procurement | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2380_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2380_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2380_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2380_wmpa.pdf | Not Required | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 7/30/2027 | 7/30/2027 |  | N | No
AF2-382 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2382_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2382_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-383 | Tolna 115 kV |  | PA | York | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2383_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2383_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-384 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2384_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2384_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AF2-388 - moved to TC1 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2388_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2388_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AF2-389 | Pokagon-Corey 69 kV |  | MI | Cass | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2389_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2389_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AF2-391 | Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2391_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2391_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AF2-392 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Lee | Active | ComEd | 199 | 199 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2392_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AF2-393 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Active | ComEd | 260 | 60 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2393_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2393_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AF2-394 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Active | ComEd | 300 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2394_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2394_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AF2-396 - moved to TC1 | Stinger 138 kV |  | MI | Cass | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2396_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2396_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-403 - moved to TC1 | Shockoe DP-Chatham 69 kV | Shockoe Storage / Shockoe DP-Chatham 69 kV | VA | Fluvanna | Active | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2403_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2403_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-404 - moved to TC1 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2404_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2404_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AF2-405 | East Sayre 34.5 kV III |  | PA | Bradford | Active | PENELEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2405_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2405_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AF2-407 - moved to TC1 | Fall Creek 345 kV |  | IN | Madison | Active | AEP | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2407_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2407_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-408 | Fall Creek 138 kV |  | IN | Madison | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2408_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2408_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-412 - moved to TC1 | Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2412_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-413 | Raritan River 230 kV |  | NJ | Atlantic | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2413_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-415 | Bergen 138 kV |  | NJ | Hudson | Active | PSEG | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2415_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2415_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2415_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-417 | West Damascus Tap-West Damascus 69 kV |  | PA | Adams | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2417_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2417_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AF2-421 | East Hazelton-Weatherly Tap 69 |  | PA | Adams | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2421_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2421_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-424 | Reed-Reed Tap #1 69 kV |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2424_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2424_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-425 | Sunbury-Eldred #2 69 kV |  | PA | Adams | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2425_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2425_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AF2-433 | Columbia-Geisinger Tap #1 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2433_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2433_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-434 | Columbia-Geisinger Tap #1 69 kV |  | MD | Anne Arundel | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2434_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2434_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AF2-440 | Hillsboro-Middleboro 138 kV |  | OH | Highland | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2440_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2440_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AF2-441 - moved to TC1 | Burnham 138kV |  | IL | Cook | Active | ComEd | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2441_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AF2-444 | Reed-Fairview Tap #2 69 kV |  | PA | Northumberland | Active | PPL | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2444_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2444_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2020 | N/A | N/A |  |  |  | 6/1/2021 |  |  | N | No
AG1-001 | US Silica-Unimin 69 kV |  | NJ | Cumberland | Active | AEC | 31 | 31 | 11.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1001_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/3/2020 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AG1-003 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 900 | 400 | 226 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1003_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-004 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 1100 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1004_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-005 - moved to TC1 | Corbin-Crescent Ridge 138 kV |  | IL | Stephenson | Active | ComEd | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1005_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG1-007 | Tar River 12.5 kV |  | NC | Edgecombe | Active | Dominion | 9.4 | 9.4 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1007_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/1/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG1-008 - moved to TC1 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1008_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/1/2020 | N/A | N/A |  |  |  | 12/15/2024 |  |  | N | No
AG1-017 | Jay 138 kV |  | IN | Jay | Active | AEP | 142.64 | 12.64 | 2.26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1017_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/6/2020 | N/A | N/A |  |  |  | 9/30/2020 |  |  | N | No
AG1-021 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 86 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1021_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2020 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AG1-022 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 95 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1022_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 5/26/2020 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AG1-024 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 285 | 85 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1024_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/1/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG1-031 | Elk Run D.P.-Gainesville 230 kV |  | VA | Fauquier | Active | Dominion | 90 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1031_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AG1-034 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 412.5 | 127.5 | 53.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1034_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/12/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG1-037 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1037_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1037_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1037_wmpa.pdf | Not Required | N/A | N/A |  | 6/16/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG1-038 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 176 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1038_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-039 | Galion 138 kV II |  | OH | Morrow | Active | ATSI | 144 | 56 | 23.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1039_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 6/18/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-040 | Morgan Street-Mount Hope 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1040_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1040_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 6/20/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AG1-047 | Jay 138 kV |  | IN | Jay | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1047_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/13/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG1-050 | Milton 69 kV |  | PA | Northumberland | Active | PPL | 90 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1050_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-051 - moved to TC1 | Maysville 69 kV III |  | PA | Mercer | Active | ATSI | 70 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1051_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-052 | Zionsview-Middletown 115 kV II |  | PA | York | Active | ME | 99.6 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1052_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AG1-053 | Jackson-Three Mile Island 230 kV III |  | PA | York | Active | ME | 95 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1053_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/17/2020 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG1-054 | Potter-Harlan 69 kV |  | PA | Lawrence | Active | ATSI | 40 | 40 | 25.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1054_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2020 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AG1-059 | Robbins 138 kV |  | PA | Westmoreland | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1059_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2020 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AG1-063 | Fairhaven 13,8 kV | Fairhaven Battery Energy Storage System | MD | Anne Arundel | Under Construction | BGE | 2.5 | 2.5 | 0.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1063_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1063_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1063_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2020 | N/A | N/A | 9/30/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
AG1-066 | Bonnyman 69 kV |  | KY | Perry | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1066_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 10/2/2024 |  |  | N | No
AG1-067 | Temple Hill 69 kV |  | KY | Barren | Active | EKPC | 38 | 38 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1067_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-070 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 45 | 45 | 32.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1070_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-071 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 55 | 55 | 37.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1071_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-075 - moved to TC1 | Purdy-Sapony 115 kV |  | VA | Greensville | Active | Dominion | 150 | 150 | 93.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1075_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N | No
AG1-082 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1082_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG1-083 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1083_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG1-086 | Findlay 23 kV | Findlay Solar Park | PA | Allegheny | Engineering and Procurement | DL | 17.5 | 17.5 | 10.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1086_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1086_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1086_wmpa.pdf | Not Required | N/A | N/A |  | 7/31/2020 | N/A | N/A | 12/31/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AG1-089 | Grandview-Clifftop 138 kV |  | WV | N/A | Active | AEP | 120 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1089_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG1-090 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1090_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/1/2020 | N/A | N/A |  |  |  | 8/1/2023 |  |  | N | No
AG1-091 | Hickman-River Bend 69 kV |  | VA | Pulaski | Active | AEP | 50 | 50 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1091_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 7/31/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-097 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 92.5 | 0 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1097_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/17/2020 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AG1-098 - moved to TC1 | Briery-Clover 230 kV |  | VA | Mecklenburg | Active | Dominion | 107 | 107 | 64.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1098_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/18/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-099 | Westernport 34.5 kV | Jade Meadow III | MD | Garrett | Engineering and Procurement | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1099_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1099_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1099_wmpa.pdf | Not Required | N/A | N/A |  | 8/18/2020 | N/A | N/A | 10/31/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
AG1-100 | Venango-Saegertown 34.5 kV | Henry Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1100_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ag1_100_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2026 | 8/18/2020 | N/A | N/A | 10/26/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-103 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Engineering and Procurement | AEC | 44 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ag1_103_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ag1_103_csa.pdf | Document Posted | N/A | N/A |  | 8/24/2020 | N/A | N/A | 12/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-104 | Waugh Chapel 230 kV |  | MD | Anne Arundel | Active | BGE | 300 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1104_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-105 - moved to TC1 | Mount Laurel-Barnes Junction 115 kV |  | VA | Halifax | Active | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1105_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-106 - moved to TC1 | Thelma 230 kV |  | NC | Northhampton | Active | Dominion | 325.5 | 25.5 | 17.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1106_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-107 | Hillsboro-Middleboro 138 kV |  | OH | Highland | Active | AEP | 200 | 150 | 85.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1107_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-109 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 50 | 0 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1109_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-118 - moved to TC1 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1118_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-120 - moved to TC1 | Glidden-Cherry Valley 138 kV |  | IL | DeKalb | Active | ComEd | 118.6 | 118.6 | 71.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1120_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-124 - moved to TC1 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 90 | 90 | 53.01 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1124_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-125 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 400 | 234.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1125_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-126 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 400 | 234.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1126_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-127 - moved to TC1 | Crego Rd 138 kV |  | IL | DeKalb | Active | ComEd | 190 | 95.1 | 57.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1127_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-135 - moved to TC1 | Garner-Lancaster 115 kV |  | VA | Richmond | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1135_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ag1_135_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ag1_135_csa.pdf | Document Posted | N/A | N/A | 12/1/2025 | 9/3/2020 | N/A | N/A | 2/1/2026 |  |  | 12/1/2024 |  |  | N | No
AG1-136 | Cloverdale-Burlington Height 138 kV |  | VA | Botetourt | Active | AEP | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1136_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2020 | N/A | N/A |  |  |  | 10/22/2023 |  |  | N | No
AG1-146 - moved to TC1 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1146_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-147 - moved to TC1 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 100 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1147_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-148 | McCarter 26.4 kV | Rutgers Generation | NJ | Essex | Partially in Service - Under Construction | PSEG | 5 | 5 | 0 | 0 | Energy | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1148_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1148_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1148_wmpa.pdf | Not Required | N/A | N/A |  | 9/12/2020 | N/A | N/A | 3/21/2024 |  |  | 1/12/2024 | 1/12/2024 |  | N | No
AG1-152 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1152_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-153 - moved to TC1 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 75 | 75 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1153_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ag1_153_isa2.pdf | Interim Study | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ag1_153_csa.pdf | Document Posted | N/A | N/A | 6/22/2028 | 9/10/2020 | N/A | N/A | 7/8/2028 |  |  | 12/1/2023 |  |  | N | No
AG1-154 - moved to TC1 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1154_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-156 | Jack Frost-Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 60 | 60 | 39.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1156_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2020 | N/A | N/A |  |  |  | 6/15/2024 |  |  | N | No
AG1-163 | West Millersport 138 kV |  | OH | Fairfield | Active | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1163_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-164 | East Hazelton-Weatherly Tap 69 kV |  | PA | Luzerne | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1164_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 8/15/2022 |  |  | N | No
AG1-165 | East Hazelton-Weatherly Tap 69 kV |  | PA | Luzerne | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1165_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  |  |  | 5/15/2022 |  |  | N | No
AG1-166 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 20 | 20 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1166_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-167 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1167_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-168 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1168_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-169 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1169_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1169_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-170 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 10 | 10 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1170_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-171 | Hopewell-Surry 230kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1171_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-172 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1172_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-173 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1173_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2020 | N/A | N/A |  |  |  | 10/15/2021 |  |  | N | No
AG1-182 | Millville-Old Chapel 138 kV |  | VA | Clarke | Active | APS | 100 | 100 | 65.21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1182_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-186 | Millville-Old Chapel 138 kV |  | VA | Clarke | Active | APS | 100 | 0 | 34.79 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1186_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-188 | Manitou-Oyster Creek 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1188_imp.htm | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  |  |  | 12/17/2021 |  |  | N | No
AG1-189 | Oyster Creek-Bamber Lake 34.5 |  | NJ | Ocean | Active | JCPL | 12 | 12 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1189_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1189_imp.htm | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2020 | N/A | N/A |  |  |  | 12/17/2021 |  |  | N | No
AG1-191 | Chester-Pohatcong Mountain 34.5 kV | South Combe | NJ | Morris | Engineering and Procurement | JCPL | 15.4 | 15.4 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1191_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1191_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ag1_191_isa.pdf | Document Posted | N/A | https://www.pjm.com/pub/planning/project-queues/csa/ag1_191_csa.pdf | Document Posted | N/A | N/A | 9/30/2024 | 9/17/2020 | N/A | N/A | 2/28/2025 |  |  | 3/12/2025 | 3/12/2025 |  | N | No
AG1-193 | Utica Junction 34.5 kV | Foster Run | PA | Venango | Engineering and Procurement | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1193_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1193_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1193_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1193_wmpa.pdf | Not Required | N/A | N/A |  | 9/18/2020 | N/A | N/A | 7/1/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
AG1-194 - moved to TC1 | Nuttall 138 kV |  | WV | Fayette | Active | AEP | 79 | 79 | 27 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1194_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/18/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-197 | Morgan Street-Cochranton 34.5 kV | Morgan Street-Cochranton 34.5 kV | PA | Crawford | Engineering and Procurement | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1197_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1197_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1197_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1197_wmpa.pdf | Not Required | N/A | N/A |  | 9/19/2020 | N/A | N/A | 1/10/2025 |  |  | 3/3/2025 | 3/3/2025 |  | N | No
AG1-198 | Union City 34.5 kV | Union City 34.5 kV | PA | Erie | Engineering and Procurement | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1198_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1198_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1198_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1198_wmpa.pdf | Not Required | N/A | N/A |  | 9/18/2020 | N/A | N/A | 1/10/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
AG1-207 | Vandalia 69 kV |  | OH | Montgomery | Active | Dayton | 85 | 85 | 85 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1207_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1207_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AG1-210 | Northern Neck 34.5 kV | Haynesville Energy Storage | VA | Richmond | Engineering and Procurement | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1210_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1210_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1210_wmpa.pdf | Not Required | N/A | N/A |  | 9/23/2020 | N/A | N/A |  |  |  | 8/9/2027 | 8/9/2027 |  | N | No
AG1-213 | St Johns 13.2 kV | Poplar Energy Storage | VA | Caroline | Engineering and Procurement | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1213_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1213_imp.pdf | Document Posted |  |  | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1213_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1213_wmpa.pdf | Not Required | N/A | N/A |  | 9/23/2020 | N/A | N/A | 12/31/2025 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
AG1-218 | Marysville-Tangy 345 kV |  | OH | Union | Active | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1218_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG1-221 | Poland Rd-Runway DP 230 kV |  | VA | Loudoun | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1221_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-222 | Guardian-Twin Branch 138 kV |  | IN | Elkhart | Active | AEP | 302.2 | 150 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1222_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG1-223 | Larrabee-Allaire 34.5 kV | Monmouth Solar 1 | NJ | Monmouth | Active | JCPL | 15.4 | 15.4 | 6.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1223_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1223_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1223_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2020 | N/A | N/A |  |  |  | 12/31/2026 | 12/31/2026 |  | N | No
AG1-226 - moved to TC1 | Eugene-Dequine 345 kV |  | IN | Fountain | Active | AEP | 450 | 450 | 142 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1226_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-231 | Glady Run–Xenia 69 kV |  | OH | Greene | Active | Dayton | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1231_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AG1-232 | Magley 138 kV |  | IN | Adams | Active | AEP | 135 | 135 | 81 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1232_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1232_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG1-233 | Hazleton - Lake Lynn 138 kV |  | WV | Preston | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1233_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG1-236 - moved to TC1 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 380 | 180 | 23.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1236_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG1-237 | Dequine-Eugene 345 kV |  | IN | N/A | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1237_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG1-239 | Blue Bell-Canton Central 138 kV |  | OH | Stark | Active | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1239_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1239_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG1-254 | Salem-Woodstown 69 kV |  | NJ | Atlantic | Active | AEC | 38 | 38 | 25.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1254_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1254_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/25/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-257 - moved to TC1 | Madisonburg Jct-Millheim 46 kV |  | PA | Centre | Active | APS | 19.9 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1257_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1257_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AG1-259 | Sunbury-Dalmatia 69 kV |  | PA | Northumberland | Active | PPL | 15.9 | 15.9 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1259_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1259_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AG1-260 | Sunbury-Dalmatia 69 kV |  | PA | Northumberland | Active | PPL | 31.8 | 15.9 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1260_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 8/1/2023 |  |  | N | No
AG1-272 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1272_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-273 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1273_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-274 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1274_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-277 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 40 | 40 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1277_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1277_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-278 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 60 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1278_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1278_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-279 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 80 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1279_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1279_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-281 | Claysburg-HCR Tap 46 kV | BL-Hileman Hollow | PA | Blair | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1281_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1281_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1281_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-282 | Dunnsville 34.5 kV | EX-Tidewater LLC | VA | Essex | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1282_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1282_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1282_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1282_wmpa.pdf | Not Required | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AG1-283 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Active | PPL | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1283_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1283_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 9/30/2023 |  |  | N | No
AG1-285 - moved to TC1 | Chase City-Central 115 kV |  | VA | Charlotte | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1285_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/28/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-291 | Neville 23 kV | Emsworth Main Channel Hydroelectric Project 2 | PA | Allegheny | Engineering and Procurement | DL | 16.8 | 16.8 | 13.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1291_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1291_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1291_wmpa.pdf | Not Required | N/A | N/A | 10/3/2025 | 9/28/2020 | N/A | N/A | 11/1/2025 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
AG1-297 - moved to TC1 | Hanna-Tanners Creek 345 kV |  | IN | Shelby | Active | AEP | 300 | 300 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1297_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-298 - moved to TC1 | Calumet-Burnham 345 kV |  | IL | Cook | Active | ComEd | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1298_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-301 | Miller REC-Warrior Ridge 46 kV |  | PA | Huntingdon | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1301_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1301_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG1-302 | Olive-Reynolds #1 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1302_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG1-303 | Geneva 115 kV |  | PA | Crawford | Active | PENELEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1303_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1303_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AG1-305 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 63 | 63 | 37.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1305_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1305_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AG1-307 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1307_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1307_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-311 | Apple Grove 138 kV |  | WV | Mason | Active | AEP | 99 | 99 | 69.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1311_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1311_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-318 | Ocean Bay 12 kV | Ocean City-Battery Storage | MD | Worcester | Under Construction | DPL | 1 | 1 | 0.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1318_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1318_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1318_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1318_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 12/31/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AG1-319 - moved to TC1 | Napoleon Muni 138 kV |  | OH | Henry | Active | AMPT | 206 | 166 | 99.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1319_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 11/1/2022 |  |  | N | No
AG1-320 | Glendale-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 82 | 82 | 54.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1320_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG1-323 - moved to TC1 | Blue Jacket 138 kV |  | OH | Logan | Active | Dayton | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1323_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1323_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AG1-324 | Jay-Desoto 138 kV |  | IN | Jay | Active | AEP | 39 | 39 | 27.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1324_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1324_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AG1-326 | Circleville-Biers Run 138 kV |  | OH | Ross | Active | AEP | 59 | 59 | 35.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1326_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No | This project slid to the next queue
AG1-341 | Summer Shade 161 kV |  | KY | Metcalfe | Active | EKPC | 106 | 106 | 63.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1341_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG1-342 - moved to TC1 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 36 | 36 | 21.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1342_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-343 - moved to TC1 | Boykins-Murphy 115 kV |  | VA | Southampton | Active | Dominion | 62.5 | 62.5 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1343_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-346 - moved to TC1 | Mount Jackson DP 115 kV |  | VA | Shenandoah | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1346_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1346_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AG1-348 | Pequest River-Washington 34.5 kV | Foul Rift Solar Farm | NJ | Warren | Under Construction | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1348_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1348_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1348_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ag1_348_gia.pdf | Document Posted | N/A |  |  | N/A | N/A | 10/15/2024 | 9/30/2020 | N/A | N/A | 10/16/2024 |  |  | 11/15/2025 | 11/15/2025 |  | N | No
AG1-349 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 260 | 260 | 156 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1349_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1349_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-351 | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 142 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1351_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-353 - moved to TC1 | Greene County-Marion County 161 kV |  | KY | Taylor | Active | EKPC | 98 | 98 | 58.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1353_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-354 - moved to TC1 | Summershade-Green County 161 kV |  | KY | Green | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1354_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-360 | Costen 25 kV | Costen Solar | MD | Somerset | Under Construction | DPL | 8.75 | 8.75 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1360_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1360_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1360_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1360_wmpa.pdf | Not Required | N/A | N/A |  | 10/1/2020 | N/A | N/A | 6/24/2024 |  |  | 8/30/2024 | 8/30/2024 |  | N | No
AG1-363 | Black Oak-Hatfield 500 kV |  | MD | Garrett | Active | APS | 300 | 300 | 220 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1363_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1363_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG1-365 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1365_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1365_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG1-366 | Allen 345 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1366_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1366_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG1-367 - moved to TC1 | DeSoto 345 kV |  | IN | Delaware | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1367_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG1-368 | Tillman 138 kV |  | IN | Allen | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1368_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1368_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG1-369 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1369_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1369_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG1-374 - moved to TC1 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1374_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG1-375 - moved to TC1 | Sorenson-Desoto 345 kV |  | IN | Blackford | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1375_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG1-377 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 120 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1377_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1377_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 8/15/2023 |  |  | N | No
AG1-378 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 140 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1378_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1378_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 8/15/2023 |  |  | N | No
AG1-382 | SGC Tap-Reese REC 46 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1382_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1382_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-384 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1384_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-386 | Smith-Francis Junction 25 kV | Smith-Francis Junction 25 kV | PA | Washington | Engineering and Procurement | APS | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1386_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1386_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1386_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1386_wmpa.pdf | Not Required | N/A | N/A |  | 10/1/2020 | N/A | N/A | 11/1/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AG1-392 - moved to TC1 | Gold 115 kV I |  | PA | Potter | Active | PENELEC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1392_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-392A - moved to TC1 | Gold 115 kV II |  | PA | Potter | Active | PENELEC | 80 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1391_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-392B - moved to TC1 | Gold 115 kV III |  | PA | Potter | Active | PENELEC | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1390_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-392C - moved to TC1 | Gold 115 kV IV |  | PA | Potter | Active | PENELEC | 120 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1389_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-393 - moved to TC1 | Fort Pickett DP 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1393_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1393_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-394 - moved to TC1 | Boykins 34.5 kV |  | VA | Southampton | Active | Dominion | 14.2 | 14.2 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1394_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1394_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/1/2022 |  |  | N | No
AG1-397 | Walston 12 kV | Walston Solar | MD | Wicomico | Engineering and Procurement | DPL | 9.972 | 9.972 | 4.1882 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1397_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1397_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1397_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1397_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 6/1/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
AG1-401 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Active | ComEd | 282 | 282 | 49.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1401_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No | This project slid to the next queue
AG1-403 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Active | ComEd | 188 | 188 | 33.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1403_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/24/2024 |  |  | N | No | This project slid to the next queue
AG1-405 | Walnut Grove-Asahi 69 kV |  | KY | McLean | Active | EKPC | 57 | 57 | 34.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1405_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1405_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-406 | Walnut Grove-Asahi 69 kV |  | KY | McLean | Active | EKPC | 79 | 22 | 22 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1406_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1406_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-410 - moved to TC1 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1410_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1410_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-411 - moved to TC1 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1411_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG1-412 - moved to TC1 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Active | Dominion | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1412_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1412_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-414 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1414_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-415 | Double Toll Date-Old Chapel 138 kV |  | VA | Clarke | Active | APS | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1415_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1415_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 1/2/2023 |  |  | N | No
AG1-416 | Sleepy Hollow 138 kV |  | WV | Jefferson | Active | APS | 125 | 125 | 91 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1416_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1416_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-417 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1417_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1417_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-418 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1418_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1418_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-419 | Lynnville-South Hamburg 69 kV |  | PA | Berks | Active | ME | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1419_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1419_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-420 | Campbell-Kiesters 138 kV |  | PA | Butler | Active | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1420_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1420_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-426 - moved to TC1 | Bremo-Scottsville 138 kV |  | VA | Buckingham | Active | AEP | 149.5 | 0 | 17 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1426_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG1-427 - moved to TC1 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Active | Dominion | 118.56 | 118.56 | 71.136 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1427_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG1-428 - moved to TC1 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Active | Dominion | 46.8 | 46.8 | 28.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1428_fea.pdf | Document Posted |  | Withdrawn |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  | 6/28/2024 |  | 12/31/2024 |  |  | N | No
AG1-433 - moved to TC1 | Keystone-DeSoto 345 kV |  | IN | Blackford | Active | AEP | 300 | 100 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1433_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-434 - moved to TC1 | Electric Junction-Nelson 345 kV |  | IL | Lee | Active | ComEd | 175 | 175 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1434_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-435 - moved to TC1 | Kewanee-Hennepin 138 kV |  | IL | Bureau | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1435_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-436 - moved to TC1 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 250 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1436_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1436_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-437 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1437_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-438 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1438_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-439 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Active | Dominion | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1439_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-442 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 135 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1442_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-443 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 135 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1443_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-444 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Active | Dominion | 330 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1444_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-447 - moved to TC1 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 305 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1447_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1447_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-449 - moved to TC1 | Rawlings-Carson 500 kV |  | VA | Dinwiddie | Active | Dominion | 436 | 122 | 122 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1449_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-450 - moved to TC1 | Airey-Vienna 69 kV II |  | MD | Dorchester | Active | DPL | 125 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1450_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1450_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-451 - moved to TC1 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Active | Dominion | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1451_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-455 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Active | PENELEC | 112.5 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1455_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG1-460 - moved to TC1 | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 329 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1460_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1460_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG1-462 - moved to TC1 | Cordova 345 kV |  | IL | Whiteside | Active | ComEd | 255 | 255 | 153 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1462_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG1-469 | Gordonsville 34.5 kV | Turkey Solar | VA | Louisa | Engineering and Procurement | Dominion | 14.04 | 14.04 | 9.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1469_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1469_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1469_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1469_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 8/29/2027 | 8/29/2027 |  | N | No
AG1-471 - moved to TC1 | Up Church-Wayne County 69 kV |  | KY | Wayne | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1471_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1471_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AG1-473 - moved to TC1 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Active | PENELEC | 53.9 | 53.9 | 32.34 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1473_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-478 | Wilmington 34.5 kV | Wilmington Solar Energy Project | IL | Will | Engineering and Procurement | ComEd | 19.9 | 19.9 | 15.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1478_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1478_imp.htm | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1478_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1478_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 2/1/2025 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
AG1-480 | Shawnee 34.5 kV |  | PA | Monroe | Active | ME | 18.2 | 18.2 | 18.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1480_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1480_imp.htm | Document Posted |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-482 | Hamilton 115 kV |  | PA | Mercer | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1482_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-483 - moved to TC1 | Dickerson 230 kV |  | MD | Montgomery | Active | PEPCO | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1483_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1483_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-485 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1485_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1485_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-486 | Orrtanna 115 kV |  | PA | Adams | Active | ME | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1486_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1486_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-487 | Gilbert 230 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1487_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1487_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-489 | McClelland-Hoytdale 345 kV |  | PA | Lawrence | Active | ATSI | 175 | 175 | 145 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1489_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1489_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-494 - moved to TC1 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1494_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG1-495 | Gilbert-Rocktown 34.5 kV | Ridge Road Solar Farm | NJ | Hunterdon | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1495_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1495_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1495_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/17/2021 |  |  | N | No
AG1-497 - moved to TC1 | Cartanza 230 kV |  | DE | Kent | Active | DPL | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1497_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1497_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-499 | Lambs 12.47 kV | Esky Solar Project | NJ | Gloucester | Under Construction | AEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1499_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1499_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1499_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1499_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A | 11/30/2024 |  |  | 6/1/2024 | 6/1/2024 |  | N | No
AG1-500 | Beaver 345 kV |  | OH | Lorain | Active | ATSI | 784.6 | 406.4 | 385.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1500_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AG1-501 | Beaver 138 kV |  | OH | Lorain | Active | ATSI | 106.5 | 11.3 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1501_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1501_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2022 |  |  | N | No
AG1-502 | Oak Green 115 kV |  | VA | Orange | Active | Dominion | 80 | 80 | 64 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1502_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-503 | Oak Green 115 kV |  | VA | Orange | Active | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1503_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG1-508 | Point Lookout 69 kV |  | VA | Grayson | Active | AEP | 63.3 | 63.3 | 9.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1508_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1508_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AG1-510 | Kittatinny-Blairstown 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1510_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1510_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1510_fac.pdf | Document Posted | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-511 | Kittatinny 230 kV |  | NJ | Warren | Active | JCPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1511_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1511_imp.htm | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-512 | University Park North 345 kV |  | IL | Will | Active | ComEd | 646 | 40 | 16 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1512_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1512_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-514 | Springdale CT III 138 kV |  | PA | Allegheny | Active | APS | 106 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1514_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1514_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-515 | Guilford 138 kV |  | PA | Franklin | Active | APS | 110 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1515_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1515_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-516 | Gans 138 kV |  | PA | Fayette | Active | APS | 106 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1516_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1516_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-517 | Osage 138 kV |  | WV | Monongalia | Active | APS | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1517_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1517_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 4/1/2022 |  |  | N | No
AG1-522 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1522_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-523 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 600 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1523_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-524 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 900 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1524_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-525 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 1200 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1525_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-526 - moved to TC1 | West Garrard 345 kV |  | KY | Garrard | Active | EKPC | 222 | 222 | 133.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1526_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-527 | Imperial-Joffre 138 kV |  | PA | Allegheny | Active | APS | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1527_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1527_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-528 | Tenmile 138 kV |  | WV | N/A | Active | AEP | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1528_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1528_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-529 - moved to TC1 | Farmview 138 kV |  | DE | Sussex | Active | DPL | 75 | 75 | 48.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1529_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1_529_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG1-532 | Fields 34.5 kV | Fields 2 | VA | Greensville | Engineering and Procurement | Dominion | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1532_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1532_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1532_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1532_wmpa.pdf | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 9/29/2027 | 9/29/2027 |  | N | No
AG1-533 | Bartonsville-Meadowbrook 138 kV IV |  | VA | Frederick | Active | APS | 170 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1533_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1533_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AG1-535 - moved to TC1 | State Line-S. Chicago Properties 138 kV |  | IL | Cook | Active | ComEd | 85 | 85 | 85 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1535_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1535_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG1-536 - moved to TC1 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1536_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG1-537 - moved to TC1 | Barterbrook-Stuarts Draft 115 kV |  | VA | Augusta | Active | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1537_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1537_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG1-548 - moved to TC1 | Erie South-Union City 115 kV |  | PA | Erie | Active | PENELEC | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1548_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG1-549 - moved to TC1 | Keystone 230 kV |  | PA | Armstrong | Active | PENELEC | 100 | 100 | 85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1549_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG1-551 - moved to TC1 | Parmele 12.5 kV |  | NC | Martin | Active | Dominion | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1551_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1551_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/15/2023 |  |  | N | No
AG1-552 - moved to TC1 | Carolina 13.2 kV |  | NC | Northhampton | Active | Dominion | 18 | 18 | 12.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1552_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/15/2023 |  |  | N | No
AG1-553 - moved to TC1 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 284 | 284 | 236.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1553_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG1-554 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 49.99 | 49.99 | 32.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1554_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1554_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG1-555 | Dequine 345 kV |  | IN | Tippecance | Active | AEP | 120 | 120 | 88.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1555_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1555_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG1-558 | Buckner 34.5 kV |  | VA | Louisa | Active | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1558_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1558_imp.pdf | Document Posted |  | Not Required | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/21/2022 |  |  | N | No
AG1-559 | Caroline Pines 22 kV |  | VA | Hanover | Active | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1559_fea.pdf | Document Posted |  | In Progress |  |  | N/A |  | N/A |  | Not Required | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 10/21/2022 |  |  | N | No
AG1-562 | Marysville-Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1562_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1562_imp.pdf | Document Posted |  | In Progress | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2020 | N/A | N/A |  |  |  | 12/4/2023 |  |  | N | No
AG2-001 | St. Johns DP 115 kV |  | VA | Essex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2020 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AG2-002 | Galion 138 kV III |  | OH | Morrow | Active | ATSI | 164 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-003 | West Millersport 138 kV |  | OH | Fairfield | Active | AEP | 120 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-004 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 164 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  |  |  | 11/30/2021 |  |  | N | No
AG2-005 | Garner-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 196 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-006 | Centerburg-Conesville 138 kV |  | OH | Licking | Active | AEP | 177.5 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-008 | Erie South-Warren 230 kV |  | PA | Erie | Active | PENELEC | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2020 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AG2-009 | Erie South-Warren 230 kV II |  | PA | Erie | Active | PENELEC | 80 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2020 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AG2-010 | Peninsula 115 kV |  | VA | City of Hampton | Active | Dominion | 189.8 | 189.8 | 75.96 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/9/2020 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AG2-011 | Laurel Mountain 138 kV |  | WV | Barbour | Active | APS | 56.3 | 56.3 | 34.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/13/2020 | N/A | N/A |  |  |  | 4/1/2024 |  |  | N | No
AG2-013 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 1300 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/16/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-014 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/19/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-016 | Oyster Creek-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2020 | N/A | N/A |  |  |  | 12/17/2021 |  |  | N | No
AG2-019 | Chase City 12.5 kV |  | VA | Mecklenburg | Active | Dominion | 15 | 15 | 6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AG2-020 | Arnolds Corner 34.5 kV |  | VA | King George | Active | Dominion | 7 | 7 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AG2-021 | Crossroads 13.2 kV |  | PA | York | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-022 | Ebenezer 12.47 kV |  | PA | Dauphin | Active | PPL | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-023 | Mechanicsburg 12.47 kV |  | PA | Cumberland | Active | PPL | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-024 | Allen 13.2 kV |  | PA | Cumberland | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-025 | Mountain 13.2 kV |  | PA | Cumberland | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-026 | Leesport 34.5 kV |  | PA | Berks | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-027 | Orrtanna 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-028 | Lincoln 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-029 | Forest G. Hipple-Collingwood 345 kV |  | IN | Noble | Active | AEP | 300 | 300 | 221.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/23/2020 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-031 | East Canton-Robertsville 69 kV |  | OH | Stark | Active | AEP | 49.9 | 30.2 | 22.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2020 | N/A | N/A |  |  |  | 1/1/2023 |  |  | N | No
AG2-032 | Mannington 230 kV |  | NJ | Salem | Active | AEC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-034 | Emporia-Pleasant Hill 115 kV |  | VA | Greensville | Active | Dominion | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/4/2020 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-035 | Fenwick Creek 69 kV |  | NJ | Salem | Active | AEC | 71 | 33 | 22 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG2-036 | Mantua 12 kV |  | NJ | Gloucester | Active | AEC | 10 | 10 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2020 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG2-037 | Findlay-Clinton 23 kV |  | PA | Allegheny | Active | DL | 4.7 | 4.7 | 2.82 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2020 | N/A | N/A |  |  |  | 12/1/2021 |  |  | N | No
AG2-038 | Boyers DP 25 kV |  | PA | Venango | Active | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  |  |  | 3/30/2022 |  |  | N | No
AG2-039 | Erie West-Fairview East 34.5 kV |  | PA | Erie | Active | PENELEC | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  |  |  | 3/30/2022 |  |  | N | No
AG2-040 | Garman-Greenwich Mine 34.5 kV |  | PA | Indiana | Active | PENELEC | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  |  |  | 3/30/2022 |  |  | N | No
AG2-041 | Jamestown Tap-Maysville 69 kV |  | PA | Mercer | Active | ATSI | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/16/2020 | N/A | N/A |  |  |  | 3/30/2022 |  |  | N | No
AG2-049 | Van Dorn 34.5 kV |  | VA | Arlington | Active | Dominion | 20 | 0 | 20 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/20/2020 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AG2-050 | Randle Cliff 13.8 kV | CHESAPEAKE BEACH BESS | MD | Calvert | Partially in Service - Under Construction | BGE | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  | N/A | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag2050_imp.pdf | Document Posted |  | Not Required | N/A | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag2050_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag2050_wmpa.pdf | Not Required | N/A | N/A |  | 11/25/2020 | N/A | N/A | 5/1/2023 |  |  | 5/1/2023 | 5/1/2023 |  | Y | No
AG2-051 | St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2020 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AG2-053 | Fulton 138 kV |  | OH | Fulton | Active | ATSI | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG2-054 | Fulton 138 kV |  | OH | Fulton | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/2/2020 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AG2-055 | Deans 500 kV |  | NJ | Middlesex | Active | PSEG | 1300 | 1300 | 370.92 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2020 | N/A | N/A |  |  |  | 11/1/2027 |  |  | N | No
AG2-056 | Gore 138 kV |  | VA | Frederick | Active | APS | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/4/2020 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AG2-057 | Cardington-Liberty 69 kV II |  | OH | Morrow | Active | ATSI | 81 | 17 | 7.14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/7/2020 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AG2-058 | Harmony Village-White Marsh 115 kV |  | VA | Gloucester | Active | Dominion | 70 | 70 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/8/2020 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-059 | Clubhouse-Lakeview 230 kV |  | VA | Greensville | Active | Dominion | 80 | 80 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/8/2020 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-060 | Hanover-Plymouth 69 kV |  | PA | Luzerne | Active | UGI | 12.6 | 12.6 | 7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2020 | N/A | N/A |  |  |  | 3/8/2022 |  |  | N | No
AG2-061 | Powerton-Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/11/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-062 | Williams 138 kV |  | WV | Grant | Active | APS | 147 | 147 | 21.609 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/15/2020 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AG2-063 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 54 | 54 | 34.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/16/2020 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-064 | St Johns DP 115 kV |  | VA | Caroline | Active | Dominion | 41 | 41 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/17/2020 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-066 | Rockcastle 138 kV |  | VA | Bedford | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/28/2020 | N/A | N/A |  |  |  | 5/30/2022 |  |  | N | No
AG2-067 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-068 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-069 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-070 | Chickhominy-Surry 500 kV |  | VA | Charles City | Active | Dominion | 325 | 325 | 228 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2020 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-072 | Rockport 765 kV |  | IN | Spencer | Active | AEP | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/6/2021 | N/A | N/A |  |  |  | 5/31/2026 |  |  | N | No
AG2-073 | Crooksville 69 kV |  | KY | Madison | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/11/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-074 | Meckesville Tap 69kV |  | PA | Carbon | Active | PPL | 38 | 38 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/15/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-077 | Clover-Rawlings 500 kV |  | VA | Charlotte | Active | Dominion | 700 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-078 | Lappans 34.5 kV |  | MD | Washington | Active | APS | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2021 | N/A | N/A |  |  |  | 5/23/2022 |  |  | N | No
AG2-079 | Clearville-Clearville Junction 34.5 kV |  | PA | Bedford | Active | APS | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/20/2021 | N/A | N/A |  |  |  | 4/11/2022 |  |  | N | No
AG2-080 | Lexington 115 kV |  | VA | Rockbridge | Active | Dominion | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-081 | Mt. Sterling-Fogg Pike 69 kV |  | KY | Montgomery | Active | EKPC | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-082 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 200 | 200 | 133.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-083 | Greentown 138 kV |  | IN | Howard | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-084 | Greentown 138 kV |  | IN | Howard | Active | AEP | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-085 | West Del-Royerton 138 kV |  | IN | Delaware | Active | AEP | 140 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-086 | Mt. Jackson DP-Mt. Jackson 115 kV |  | VA | Shenandoah | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2021 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AG2-088 | Trabue-Midlothian 230 kV line |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 4/15/2022 |  |  | N | No
AG2-089 | Pelikan-Kennaloyal 25 kV |  | PA | Westmoreland | Active | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 7/1/2022 |  |  | N | No
AG2-090 | Scalp Level 23 kV IV |  | PA | Somerset | Active | PENELEC | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 1/31/2023 |  |  | N | No
AG2-091 | Scalp Level 23 kV V |  | PA | Somerset | Active | PENELEC | 20 | 6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-092 | Todd 69 kV II |  | MD | Dorchester | Active | DPL | 50 | 0 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AG2-093 | Colonial Trail-Hopewell 230 kV |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-094 | Summer Shade-Green County 161 kV |  | KY | Metcalfe | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2021 | N/A | N/A |  |  |  | 4/1/2024 |  |  | N | No
AG2-095 | Hopewell 34.5 kV (Circuit 313) |  | VA | Prince George | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 12/8/2023 |  |  | N | No
AG2-096 | Dauphin PG Tie-Dauphin Juniata Tie 69 kV |  | PA | Dauphin | Active | PPL | 55 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AG2-097 | Altoona-Raystown 230 kV II |  | PA | Blair | Active | PENELEC | 80 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-098 | Copperstone-North Lebanon 230 kV II |  | PA | Lebanon | Active | ME | 70 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-099 | Moshannon-Milesburg 230 kV V |  | PA | Centre | Active | APS | 83.6 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-100 | Moshannon-Milesburg 230 kV VI |  | PA | Centre | Active | APS | 78.38 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-101 | Princess Anne–Loretto 69 kV |  | MD | Somerset | Active | DPL | 58.6 | 58.6 | 35.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-102 | Oak Hall-Perdue 69 kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-103 | Oak Hall-Hallwood 69 kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-104 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 400 | 253.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AG2-105 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 800 | 400 | 253.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AG2-106 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-107 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-108 | Milford-Cool Springs 230 kV |  | DE | Sussex | Active | DPL | 460 | 460 | 130.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AG2-109 | Fitchville-New London 69 kV |  | OH | Huron | Active | ATSI | 40 | 40 | 28.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-110 | Marysville-Tangy 345 kV |  | OH | Union | Active | AEP | 300 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-111 | Perth 34.5 kV Substation (Circuit 408) |  | VA | Campbell | Active | Dominion | 14.5 | 14.8 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 2/6/2023 |  |  | N | No
AG2-112 | Perth 34.5 kV Substation (Circuit 404) |  | VA | Halifax | Active | Dominion | 15.2 | 15.2 | 9.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 3/24/2023 |  |  | N | No
AG2-113 | Nokesville-Vint Hill 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 8/10/2022 |  |  | N | No
AG2-114 | Dresden-Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-115 | Mt. Hermon 25 kV |  | MD | Wicomico | Active | DPL | 8.47 | 8.466 | 3.5557 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 8/29/2022 |  |  | N | No
AG2-116 | Olive-Reynolds 345 #1 345 kV |  | IN | White | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-117 | Olive-Reynolds #2 345 kV |  | IN | White | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-118 | Ford-Cedarville 138 kV |  | OH | Clermont | Active | DEOK | 84 | 84 | 56.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-119 | Galion-Roberts South 138 kV II |  | OH | Marion | Active | ATSI | 160 | 160 | 106.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-120 | Everetts 34.5 kV |  | NC | Martin | Active | Dominion | 21 | 21 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/15/2024 |  |  | N | No
AG2-121 | Mackeys 230 kV |  | NC | Washington | Active | Dominion | 140 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-122 | Crystal Hill - Halifax 115 kV |  | VA | Halifax | Active | Dominion | 64.7 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-123 | Sedge Hill - Person 230 kV |  | VA | Halifax | Active | Dominion | 75.1 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-124 | Shackleford-Harmony 115 kV |  | VA | King and Queen | Active | Dominion | 149.9 | 0 | 33.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-125 | Camden-Crystal 69 kV |  | OH | Preble | Active | Dayton | 69.9 | 0 | 15.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-126 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-127 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-128 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AG2-129 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/30/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AG2-130 | Colby Tap-Valley 138 kV |  | MI | Van Buren | Active | AEP | 55 | 55 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/2/2021 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AG2-131 | Almena-Valley 69 kV |  | MI | Van Buren | Active | AEP | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2021 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AG2-132 | Hartford-South Haven 69 kV |  | MI | Van Buren | Active | AEP | 15 | 15 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2021 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AG2-137 | Surry-Chuckatuck 230 kV |  | VA | Isle of Wight | Active | Dominion | 70 | 70 | 43.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/8/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-139 | Lincoln 771-4 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/9/2021 | N/A | N/A |  |  |  | 8/1/2022 |  |  | N | No
AG2-143 | Burma-Sligo 25 kV |  | PA | Clarion | Active | APS | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2021 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AG2-147 | Pontiac Midpoint 34.5kV |  | IL | Livingston | Active | ComEd | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-148 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 130 | 130 | 86 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-149 | Galion-South Berwick 345 kV |  | OH | Crawford | Active | AEP | 400 | 400 | 267 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-150 | River Dock 23 kV |  | PA | Allegheny | Active | DL | 5.25 | 5.25 | 5.25 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-151 | Trices Lake - James River Tap 115 kV |  | VA | Cumberland | Active | Dominion | 100 | 102.2 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2021 | N/A | N/A |  |  |  | 2/2/2024 |  |  | N | No
AG2-152 | Banister-Bear Skin 138 kV |  | VA | Pittsylvania | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2021 | N/A | N/A |  |  |  | 2/2/2024 |  |  | N | No
AG2-153 | Headquarters-Sideview 69 kV |  | KY | Bourbon | Active | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-154 | Danville 12 kV |  | PA | Northumberland | Active | PPL | 1 | 1 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-155 | Linden 12 kV |  | PA | Lycoming | Active | PPL | 2.8 | 2.8 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-156 | Montgomery 12 kV |  | PA | Lycoming | Active | PPL | 5.1 | 5.1 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-157 | Ashfield 12 kV |  | PA | Carbon | Active | PPL | 1.5 | 1.5 | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AG2-159 | Williamstown 69 kV |  | KY | Grant | Active | EKPC | 61 | 61 | 43 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-161 | Wheelabrator Frackville-Gilberton 69 kV |  | PA | Schuylkill | Active | PPL | 43 | 43 | 39.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-162 | Hanna-Tanners Creek 345 kV |  | IN | Rush | Active | AEP | 115 | 115 | 76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-163 | Dequine-Eugene 345 kV |  | IN | Fountain | Active | AEP | 700 | 250 | 184 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-164 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 270 | 270 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-165 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 200 | 134 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-166 | Newville-Nottingham Tap 1 69 kV |  | PA | Cumberland | Active | PPL | 13.3 | 13.3 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 8/18/2023 |  |  | N | No
AG2-167 | Morgan Street-Cochranton 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-168 | Clinch River-Copper Ridge 138 kV |  | VA | Russell | Active | AEP | 95 | 95 | 63.3333 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-169 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 70 | 70 | 46.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-170 | Whitewater Valley Power Station 69 kV |  | IN | Wayne | Active | AEP | 88 | 88 | 58.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-171 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 60 | 68.4 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 7/3/2024 |  |  | N | No
AG2-172 | Kittatinny 230 kV |  | NJ | Warren | Active | JCPL | 450 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG2-173 | Twin Branch-Meridian 345 kV |  | IN | Whitley | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-174 | Jack Frost-Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/30/2024 |  |  | N | No
AG2-175 | Van Wert-Delphos 69 kV |  | OH | Van Wert | Active | AEP | 65 | 65 | 49 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-176 | Geneva 115 kV |  | PA | Crawford | Active | PENELEC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 1/31/2024 |  |  | N | No
AG2-177 | Limecrest-Woodruff's Gap 34.5 kV |  | NJ | Sussex | Active | JCPL | 8 | 8 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 2/23/2022 |  |  | N | No
AG2-178 | Remington 34.5 kV |  | VA | Fauquier | Active | Dominion | 14.125 | 14.125 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AG2-179 | Coburg 69 kV |  | KY | Adair | Active | EKPC | 60 | 60 | 42.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-180 | Paulsboro 69 kV |  | NJ | Gloucester | Active | AEC | 79 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 2/25/2021 |  |  | N | No
AG2-181 | Airey - Golden Hill 69 kV |  | MD | Dorchester | Active | DPL | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-182 | Doubs-Bismark 500 kV |  | VA | Frederick | Active | Dominion | 200 | 200 | 133.3333 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-184 | Spicewood-Softshell 138 kV |  | KY | Knott | Active | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-185 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Active | PPL | 40 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-186 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Active | PPL | 45.2 | 5.2 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-187 | Amherst-Riverville 138 kV |  | VA | Amherst | Active | AEP | 115 | 40 | 33.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-188 | Farmville-Bucking 230 kV |  | VA | Cumberland | Active | Dominion | 149.9 | 149.9 | 89.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-189 | Washington-Pequest River 34.5 kV |  | NJ | Warren | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 2/23/2022 |  |  | N | No
AG2-191 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AG2-192 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-193 | Turner 34.5 kV |  | VA | Henrico | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-194 | Pierce-Kyger Creek 345 kV |  | OH | Highland | Active | OVEC | 170 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-195 | Dowling 138 kV |  | OH | Wood | Active | ATSI | 53 | 53 | 22.26 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-197 | Nelson- Electrical Junction 345 kV |  | IL | Lee | Active | ComEd | 295.9 | 295.9 | 52 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-198 | Briery-Clover 230 kV |  | VA | Prince Edward | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2021 | N/A | N/A |  |  |  | 2/25/2024 |  |  | N | No
AG2-199 | Birchwood-NUG 230 kV |  | VA | King George | Active | Dominion | 55 | 55 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2021 | N/A | N/A |  |  |  | 10/10/2023 |  |  | N | No
AG2-200 | North Warren–Russell 34.5 kV |  | PA | Warren | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-202 | Reusens 12.47 kV |  | VA | City of Lynchburg | Active | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-203 | Perkins Park 12.47 kV |  | VA | City of Lynchburg | Active | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-204 | Athenia 26 kV |  | NJ | Essex | Active | PSEG | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-206 | Tennessee Gas-East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 48 | 48 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-207 | Brandon Shores 230 kV |  | MD | Anne Arundel | Active | BGE | 275 | 275 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2021 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AG2-208 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 70 | 79.2 | 44.47 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-209 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 70 | 0 | 20.76 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/5/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-212 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 400 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-213 | Gary D.P Tap - Gary D.P 115 kV |  | VA | Lunenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-214 | Red House D.P - Sugar Hill 115 kV |  | VA | Charlotte | Active | Dominion | 60 | 60.17 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-215 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 176 | 0 | 36.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-216 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 144 | 0 | 25.92 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-217 | Watkins Corner 34.5 kV |  | VA | Southampton | Active | Dominion | 20 | 20.9 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 4/29/2023 |  |  | N | No
AG2-218 | La Rue 69 kV |  | OH | Marion | Active | AEP | 49.5 | 49.5 | 32 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-219 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 600 | 330 | 220.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-220 | East Towanda-South Troy 115 kV |  | PA | Bradford | Active | PENELEC | 31 | 31 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AG2-221 | South Troy - North Towanda 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AG2-222 | Tanners Creek-Hanna 345 kV |  | IN | Rush | Active | AEP | 83 | 83 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-223 | Allen Junction 345 kV |  | OH | Lucas | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG2-225 | Wagner 115 kV |  | MD | Anne Arundel | Active | BGE | 135 | 115 | 46 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-226 | Martins Creek 69 kV II |  | PA | Northampton | Active | PPL | 52 | 52 | 20.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-228 | Pequest River-Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 11.2 | 11.2 | 4.704 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2021 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AG2-229 | Floyd 138 kV |  | VA | Floyd | Active | AEP | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2021 | N/A | N/A |  |  |  | 1/1/2024 |  |  | N | No
AG2-230 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/12/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-233 | Montgomery Hydroelectric 23 kV |  | PA | Beaver | Active | DL | 20 | 20 | 17.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-234 | Neville 23 kV |  | PA | Allegheny | Active | DL | 20 | 3.2 | 1.5 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-235 | Lincoln-Berrywood 69 kV |  | OH | Delaware | Active | AEP | 73 | 73 | 30.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-236 | Potter-Harlan 69 kV |  | PA | Lawrence | Active | ATSI | 60 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/15/2021 | N/A | N/A |  |  |  | 10/30/2024 |  |  | N | No
AG2-237 | Thelma 230kV |  | NC | Northhampton | Active | Dominion | 300 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-238 | Earleys 230 kV |  | NC | Hertford | Active | Dominion | 99.9 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-239 | Hickory-Shawboro 230 kV |  | NC | Currituck | Active | Dominion | 60 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-240 | Old Church 34.5 kV |  | VA | Hanover | Active | Dominion | 25 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AG2-241 | Roadstown 69 kV |  | NJ | Cumberland | Active | AEC | 47 | 47 | 31.3333 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-243 | Rome-Orwell 36 kV |  | OH | Ashtabula | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-244 | Winfield-Presrite Corp 36 kV |  | OH | Ashtabula | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-245 | Olive - Reynolds #1 345 kV |  | IN | Starke | Active | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/16/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-247 | Northwestern REC Dixonburg-Vernon 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-248 | East Elkhart 345 kV |  | IN | Elkhart | Active | AEP | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-249 | Stoneboro-Perry 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-250 | Stoneboro-Perry 69 kV II |  | PA | Mercer | Active | ATSI | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/17/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-251 | Dilworth 69 kV |  | OH | Trumbull | Active | ATSI | 29 | 29 | 17.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-252 | Dilworth 69 kV II |  | OH | Trumbull | Active | ATSI | 49 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-253 | Dilworth 69 kV III |  | OH | Trumbull | Active | ATSI | 69 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-254 | New Lisbon 12.47 kV |  | NJ | Burlington | Active | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 3/30/2022 |  |  | N | No
AG2-255 | South Hampton 13 kV |  | NJ | Burlington | Active | PSEG | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 3/30/2022 |  |  | N | No
AG2-258 | Carson – Rogers Road 500 kV |  | VA | Accomack | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-259 | Sherwood - Kidds Store 115 kV |  | VA | Fluvanna | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 3/4/2024 |  |  | N | No
AG2-260 | Crystal Hill - Perth 115 kV |  | VA | Halifax | Active | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-261 | Lake View - Clubhouse 230 kV |  | VA | Greensville | Active | Dominion | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-262 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 56 | 11 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/18/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-263 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Active | Dayton | 40 | 40 | 31.14 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-264 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Active | Dayton | 60 | 20 | 14.74 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-265 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Active | Dayton | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-268 | Sedge Hill 230 kV |  | VA | Halifax | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-269 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-270 | Clover 230 kV |  | VA | Halifax | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-271 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-272 | Berry Hill 138 kV |  | VA | Pittsylvania | Active | AEP | 55 | 55 | 21.35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-274 | Hebron 69 kV II |  | MD | Wicomico | Active | DPL | 45.8 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/19/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-275 | Southwest 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-276 | Tyler 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-277 | Robinson 69 kV |  | OH | Fayette | Active | Dayton | 40 | 40 | 34 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-278 | Robinson 69 kV |  | OH | Fayette | Active | Dayton | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-279 | Hagerstown-Conservit 34.5 kV |  | MD | Washington | Active | APS | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AG2-281 | Church 138 kV |  | MD | Queen Anne's | Active | DPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-282 | Kuranga Power Generator |  | OH | Butler | Active | DEOK | 10 | 10 | 3.102 |  | Capacity | Generation Interconnection | Solar; Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 2/10/2022 |  |  | N | No
AG2-283 | Yorktown 230 kV |  | VA | York | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-284 | Catharpin 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-285 | Loudoun 230 kV |  | VA | Loudoun | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-286 | Clifton 230 kV |  | VA | Fairfax | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-287 | Beaumeade 230 kV |  | VA | Loudoun | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-288 | Stonewall 138 kV |  | VA | Frederick | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-289 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 100 | 100 | 66.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-290 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 158 | 58 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-291 | Williams Central 115 kV |  | PA | Susquehanna | Active | PENELEC | 16 | 16 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-292 | Scotch Hollow 230 kV |  | PA | Bradford | Active | PENELEC | 16 | 16 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AG2-293 | Williams Potter Tap 115 kV |  | PA | Susquehanna | Active | PENELEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-294 | MacNew 115 kV |  | PA | Susquehanna | Active | PENELEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/22/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-296 | South Berwick - Galion 345 kV |  | OH | Crawford | Active | AEP | 430 | 30 | 19.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-297 | Cumberland 230 kV |  | NJ | Cumberland | Active | AEC | 19 | 19 | 11.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG2-298 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-299 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-300 | Meadow Brook 138 kV |  | VA | Frederick | Active | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-301 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-302 | Dickerson 230 kV |  | MD | Montgomery | Active | PEPCO | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-303 | Birchwood 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-304 | Liberty 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-305 | Bristers 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-306 | Possum Point 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-307 | Roundtable 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-308 | Cumberland 138 kV |  | MD | Allegany | Active | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-309 | Lanexa 230 kV |  | VA | New Kent | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-310 | Matt Funk 138 kV |  | VA | Roanoke | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-311 | Smith Mountain 138 kV |  | VA | Bedford | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-312 | Suffolk - Sunbury 230 kV |  | VA | City of Suffolk | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/23/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-314 | Gilboa-Jones Branch 138 kV III |  | WV | Nicholas | Active | APS | 150 | 0 | 67 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AG2-315 | Twin Branch - Guardian 138 kV |  | IN | Elkhart | Active | AEP | 302.2 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-316 | Sandwich-Plano 138 KV |  | IL | Kendall | Active | ComEd | 292.2 | 0 | 49.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AG2-317 | Barren - Summer Shade 161 kV |  | KY | Barren | Active | EKPC | 155 | 35 | 23.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-318 | Spotsylvania 115 kV |  | VA | Spotsylvania | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-319 | Brandon Shores 230 kV |  | MD | Anne Arundel | Active | BGE | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-320 | Ladysmith 230 kV |  | VA | Caroline | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-321 | Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-322 | Skiffs Creek 230 kV |  | VA | James City | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-323 | Shelhorn 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-324 | Buttermilk 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-325 | Pacific 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-326 | Reston 230 kV |  | VA | Fairfax | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-327 | Tennessee Gas - East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 68 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/24/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-328 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 600 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-329 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-330 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-331 | Jefferson - Greentown 765 kV |  | IN | Decatur | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-332 | East Elkhart – Elcona Tap 138 kV |  | IN | Elkhart | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-333 | Martinsville - Highland 69 kV |  | OH | Fayette | Active | Dayton | 49 | 49 | 38.05 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-334 | Miller REC - Warrior Ridge 46 kV |  | PA | Huntingdon | Active | PENELEC | 30 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-336 | Midway 138 kV |  | OH | Henry | Active | ATSI | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AG2-337 | Midway 138 kV II |  | OH | Henry | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AG2-338 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-339 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 140 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-341 | Ridge Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/25/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-342 | Milford - Cool Springs 230 kV II |  | DE | Sussex | Active | DPL | 900 | 440 | 124.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AG2-343 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-344 | Dequine 345 bkV |  | IN | N/A | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-345 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-347 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 448.8 | 448.8 | 121.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 8/31/2025 |  |  | N | No
AG2-348 | Indian River 230 kV II |  | DE | Sussex | Active | DPL | 897.6 | 897.6 | 242.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 8/31/2025 |  |  | N | No
AG2-351 | Beatty-London 138 kV III |  | OH | Madison | Active | ATSI | 196 | 0 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AG2-354 | Ragland - Grant Branch 138 kV |  | WV | Mingo | Active | AEP | 100 | 100 | 72.92 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AG2-355 | North Muskingum River - Philo 138 kV |  | OH | Morgan | Active | AEP | 125 | 125 | 82.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-356 | South Troy - Canton 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 1/15/2023 |  |  | N | No
AG2-357 | Wilton 345 kV |  | IL | Will | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AG2-358 | Midway 345 kV |  | OH | Henry | Active | ATSI | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AG2-359 | Hillcrest 345 kV |  | OH | Brown | Active | DEOK | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AG2-360 | Broadford 138 kV |  | VA | Smyth | Active | AEP | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AG2-361 | Lanexa – Dunnsville 230 kV |  | VA | New Kent | Active | Dominion | 100 | 100 | 63.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-362 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Active | Dominion | 100 | 0 | 36.54 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-363 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-364 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-365 | Conneaut Lake-Werner 69 kV |  | PA | Mercer | Active | ATSI | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-366 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-367 | VEPCO South Creek - Pamplin 115 kV |  | VA | Appomattox | Active | Dominion | 100 | 100.28 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-368 | Scottsville - CVEC Delivery 69 kV Point |  | VA | Buckingham | Active | AEP | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-369 | Vepco Heritage - Wake 500 kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-370 | Tillman 138 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/26/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-371 | Newville 12 kV |  | PA | Cumberland | Active | PPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-372 | Lock 34.5 kV |  | PA | Chester | Active | PECO | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-373 | Nittany-Zion 46 kV |  | PA | Centre | Active | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-375 | Fostoria Central 345 kV |  | OH | Hancock | Active | AEP | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AG2-376 | Beatty 345 kV |  | OH | Franklin | Active | AEP | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AG2-377 | West Unity – Exit 2/Holiday City Tap 69 kV |  | OH | Williams | Active | ATSI | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-378 | North Hampton – Medway 69 kV |  | OH | Clark | Active | ATSI | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-379 | Easton - Steele 138 kV III |  | MD | Talbot | Active | DPL | 79 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-380 | Carville 138 kV IV |  | MD | Queen Anne's | Active | DPL | 106 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-381 | Church - Oil City 138 kV II |  | MD | Caroline | Active | DPL | 112 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 9/15/2023 |  |  | N | No
AG2-382 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 9/20/2024 |  |  | N | No
AG2-384 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 60 | 60 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-385 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 54 | 54 | 36.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-386 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AG2-388 | Pole 249 6094 12.47 kV |  | VA | Campbell | Active | AEP | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Methane |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/29/2021 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AG2-398 | Fairfield 12 kV |  | PA | Lycoming | Active | PPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-400 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-401 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/15/2021 |  |  | N | No
AG2-402 | Allen 345 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-403 | Meadow Brook - Mt. Storm 500 kV |  | WV | Hardy | Active | APS | 125 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-404 | Meadow Brook - Mt. Storm 500 kV II |  | WV | Hardy | Active | APS | 425 | 425 | 172.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-405 | Continental 69 kV |  | OH | Putnam | Active | AEP | 49.9 | 0 | 10.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-406 | Payne 69 kV |  | OH | Paulding | Active | AEP | 49.9 | 0 | 10.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-407 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-408 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 0 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 9/30/2022 |  |  | N | No
AG2-410 | Watkins Corner 34.5 kV |  | VA | Southampton | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AG2-411 | Statler Hill 115 kV |  | PA | Somerset | Active | PENELEC | 63 | 63 | 40.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AG2-413 | Brush Junction - Pleasant Gap 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-414 | Axton 138 kV |  | VA | Henry | Active | AEP | 350 | 350 | 210 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-415 | Gold – Tennessee Gas 115 kV |  | PA | Potter | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-416 | Edinboro South - Venango Junction 115 kV II |  | PA | Crawford | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-417 | Clinton 69 kV II |  | PA | Lycoming | Active | PPL | 100 | 100 | 88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-418 | Blain 115 kV |  | PA | Perry | Active | PENELEC | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-419 | 3 Bridges Rd 34.5 kV |  | MD | Caroline | Active | DPL | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-420 | Eclipse #2 34.5 kV |  | PA | Venango | Active | PENELEC | 25 | 25 | 14 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-421 | High Street 12.47 kV |  | NJ | Cumberland | Active | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | Y | No
AG2-423 | Cherry Run–Harmony 138 kV |  | WV | Barbour | Active | APS | 80 | 80 | 58 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-424 | Bonnieville - Lebanon 138 kV |  | KY | Larue | Active | EKPC | 63.25 | 63.25 | 34.95 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-425 | Jackson Road - Nanty Glo 46 kV |  | PA | Cambria | Active | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | Withdrawn |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-426 | Wakefield - Waverly 115 kV |  | VA | Sussex | Active | Dominion | 59 | 59 | 47.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-427 | Waverly 115 kV |  | VA | Sussex | Active | Dominion | 85 | 85 | 66.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-428 | Sapony 230 kV |  | VA | Sussex | Active | Dominion | 170 | 170 | 135.66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-429 | Burma - Armstrong 138 kV |  | PA | Clarion | Active | APS | 69 | 69 | 53.86 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-430 | Sunbury-Dalmatia 69 kV II |  | PA | Northumberland | Active | PPL | 60 | 60 | 37.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-431 | Sapony 34.5 kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12.54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AG2-432 | Mount Airy - Wythe 138 kV |  | VA | Wythe | Active | AEP | 45 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-433 | Sabinsville 115 kV |  | PA | Tioga | Active | PENELEC | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AG2-434 | Rockwood 23 kV |  | PA | Somerset | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-435 | Crossroads 13.2 kV II |  | PA | York | Active | ME | 4.6 | 4.6 | 2.76 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AG2-436 | Carson - Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-437 | Monarch I Interconnection 500 kV |  | VA | Greensville | Active | Dominion | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-438 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 10 | 10 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG2-439 | Oxbow 34.5 kV |  | PA | Wyoming | Active | PENELEC | 9.8 | 9.8 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/15/2023 |  |  | N | No
AG2-440 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-441 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-442 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-443 | Benner 12 kV |  | OH | Montgomery | Active | Dayton | 4 | 4 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/28/2022 |  |  | N | No
AG2-444 | Bixby - Biers Run 345 kV |  | OH | Pickaway | Active | AEP | 346 | 346 | 207.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-445 | Adkins - Atlanta 345 kV |  | OH | Pickaway | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-446 | Cedar Creek 138 kV |  | DE | New Castle | Active | DPL | 114.3 | 0 | 25.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 11/15/2022 |  |  | N | No
AG2-447 | Cedar Creek 138 kV VII |  | DE | New Castle | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 2/1/2024 |  |  | N | No
AG2-448 | Cross School - Westvaco 138 kV |  | WV | Mineral | Active | APS | 150 | 150 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/24/2024 |  |  | N | No
AG2-449 | Tanners Creek - Hanna 345 kV |  | IN | Rush | Active | AEP | 235 | 120 | 81.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-450 | Bridgeport 230 kV |  | NJ | Gloucester | Active | AEC | 225 | 225 | 115.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AG2-451 | Chambers 230 kV |  | NJ | Salem | Active | AEC | 240 | 240 | 123 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-452 | SW Lima - Shelby 345 kV |  | OH | Auglaize | Active | AEP | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-453 | Lasalle - Plano 345 kV |  | IL | Kendall | Active | ComEd | 280 | 280 | 196 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-454 | Dequine - Eugene 345 kV |  | IN | Fountain | Active | AEP | 300 | 300 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-455 | Dequine - Sullivan 345 kV |  | IN | Fountain | Active | AEP | 280 | 280 | 196 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-456 | Pierce Brook-Lewis Run 230 kV |  | PA | McKean | Active | PENELEC | 80 | 80 | 55.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-457 | Farmers Valley-Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 80 | 80 | 55.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-458 | Kittatinny-Newton 34.5 kV II |  | NJ | Sussex | Active | JCPL | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AG2-459 | Allenwood - Larrabee 34.5 kV II |  | NJ | Monmouth | Active | JCPL | 7 | 0 | 0.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AG2-460 | East Flemington-Lebanon 34.5 kV II |  | NJ | Hunterdon | Active | JCPL | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-461 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Active | Dominion | 88 | 88 | 57.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N | No
AG2-462 | Wythe - Glen Lyn 138 kV |  | VA | Wythe | Active | AEP | 150 | 150 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-463 | Gold – Tennessee Gas 115 kV II |  | PA | Potter | Active | APS | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-464 | Feagans Mill - Stonewall 138 kV |  | WV | Jefferson | Active | APS | 80 | 80 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-465 | South Tiffin - West End Fostoria 138 kV |  | OH | Seneca | Active | AEP | 79 | 79 | 29.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-466 | Culloden - Wyoming 765 kV |  | WV | N/A | Active | AEP | 1000 | 1000 | 414 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/30/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-467 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-469 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-470 | Fostoria - Lemoyne 345 kV |  | OH | Wood | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-471 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-472 | Jennings-Hazelton 138kV |  | WV | Preston | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-473 | Brody 138 kV |  | MI | Cass | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-474 | Mottville 138 kV |  | MI | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-475 | Chickahominy - Surry 500 kV |  | VA | Charles City | Active | Dominion | 500 | 500 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-476 | Hokes-Grantley 69 kV II |  | PA | York | Active | ME | 20 | 0 | 0.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AG2-477 | Hokes-Jackson 69 kV III |  | PA | York | Active | ME | 20 | 0 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2022 |  |  | N | No
AG2-478 | Hokes-Jackson 69 kV IV |  | PA | York | Active | ME | 20 | 0 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/31/2022 |  |  | N | No
AG2-479 | Penns Tap-Richfield Tie 69 kV II |  | PA | Snyder | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-480 | Derry Tap-Derry Bus 69 kV II |  | PA | Montour | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AG2-481 | Derry Tap-Derry Bus 69 kV III |  | PA | Northumberland | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2022 |  |  | N | No
AG2-482 | Bowman's Mill-Scott 69 kV II |  | PA | Columbia | Active | PPL | 35 | 0 | 8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/15/2022 |  |  | N | No
AG2-483 | Bowman's Mill Tap-Scott 69 kV III |  | PA | Columbia | Active | PPL | 75 | 0 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/15/2022 |  |  | N | No
AG2-484 | Mifflintown Bus-Mifflintown Tap 69 kV II |  | PA | Juniata | Active | PPL | 20 | 0 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-485 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Active | PPL | 20 | 0 | 5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AG2-486 | Bloomsburg-Columbia 69 kV II |  | PA | Columbia | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AG2-487 | Madison - Tanners Creek 138 kV |  | IN | Henry | Active | AEP | 152.5 | 0 | 10.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2022 |  |  | N | No
AG2-488 | Southwest Lima 345 kV |  | OH | Allen | Active | AEP | 300 | 0 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-489 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Active | AEP | 75 | 0 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-490 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Active | AEP | 75 | 0 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-491 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-492 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-497 | Tangy 138 kV |  | OH | Delaware | Active | ATSI | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-498 | Obetz 138 kV |  | OH | Franklin | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-499 | Bixby 345 kV |  | OH | Franklin | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-500 | Townsend 138 kV II |  | DE | New Castle | Active | DPL | 50 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-501 | Sedge Hill - Mount Laurel 115 kV |  | VA | Halifax | Active | Dominion | 51 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-502 | Sedge Hill - Person 115 kV |  | VA | Halifax | Active | Dominion | 70 | 0 | 7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-503 | Adams 138 kV |  | OH | Adams | Active | AEP | 49.9 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-504 | Delano 138 kV |  | OH | Ross | Active | AEP | 49.9 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AG2-505 | Westvaco - Mt Zion 138 kV |  | MD | Garrett | Active | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-506 | Carson 230 kV |  | VA | Dinwiddie | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AG2-507 | Crewe - Victoria DP 115 kV |  | VA | Nottoway | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-508 | Dry Bread 230 kV |  | VA | Greensville | Active | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AG2-509 | Robinson 69 kV |  | WV | N/A | Active | AEP | 55 | 55 | 36.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-512 | Sulphur Creek-Loretto 69 kV |  | KY | Marion | Active | EKPC | 17.5 | 17.5 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-513 | Hodgenville-Sulphur Creek 69 kV |  | KY | Larue | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AG2-514 | Midway 345 kV II |  | OH | Henry | Active | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-515 | Midway 345 kV III |  | OH | Lucas | Active | ATSI | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-516 | Pecatonica 138kV |  | IL | Winnebago | Active | ComEd | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-517 | Cordova Energy Center 345kV |  | IL | Rock Island | Active | ComEd | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AG2-518 | Tech Drive 138 kV |  | VA | Montgomery | Active | AEP | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 1/1/2024 |  |  | N | No
AG2-519 | Royerton - Desoto 138 kV |  | IN | Delaware | Active | AEP | 112 | 112 | 87.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 2/29/2024 |  |  | N | No
AG2-520 | Ritchie 69 kV |  | MD | Prince George's | Active | PEPCO | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-521 | Fork Union 230 kV |  | VA | Fluvanna | Active | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/1/2024 |  |  | N | No
AG2-522 | Five Forks 115 kV |  | NC | Warren | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/30/2025 |  |  | N | No
AG2-524 | LaSalle Station - Mazon 138 kV |  | IL | Grundy | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-526 | Oak Grove – Saunders DP 230 kV |  | VA | Westmoreland | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-527 | Kewanee-Toulon 138 kV |  | IL | Stark | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AG2-528 | Bustleburg Tap - Fairfield DP 115 kV |  | VA | Rockbridge | Active | Dominion | 140 | 141.39 | 72.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-529 | Harrisonburg - Endless Caverns 230 kV |  | VA | Rockingham | Active | Dominion | 150 | 151.734 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-530 | Mannington Mills - Woodstown 69 kV |  | NJ | Salem | Active | AEC | 19.975 | 19.975 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-531 | Greystone - West Denville 34.5 kV |  | NJ | Morris | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2022 |  |  | N | No
AG2-532 | Newburgh-Newburgh Tap 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-533 | Newburgh-Pohatcong 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2021 |  |  | N | No
AG2-534 | Hackettstown-Pohatcong R722-7 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-535 | Hackettstown-Pohatcong J738-1 34.5 kV II |  | NJ | Warren | Active | JCPL | 40 | 20 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-536 | Buckeye - Ringoes 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-537 | Ringoes-Copper Hill Solar 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 8/31/2022 |  |  | N | No
AG2-538 | Ridgeway - Motion Control 46 kV |  | PA | Elk | Active | APS | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/15/2022 |  |  | N | No
AG2-539 | Mechanicsburg - Darby 138 kV |  | OH | Union | Active | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/14/2025 |  |  | N | No
AG2-540 | Clubhouse - Jarratt 115 kV |  | VA | Greensville | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-541 | Perth - Crystal Hill 115 kV |  | VA | Halifax | Active | Dominion | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-542 | North Shenandoah – Merck 115 kV |  | VA | Rockingham | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-543 | Suffolk - Earleys 230 kV |  | VA | City of Suffolk | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AG2-544 | Silver Lake 138 kV |  | IL | McHenry | Active | ComEd | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AG2-545 | Silver Lake 345 kV |  | IL | McHenry | Active | ComEd | 400 | 400 | 160 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AG2-546 | Van Buren - Delaware 138 kV |  | IN | Grant | Active | AEP | 150 | 40 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AG2-547 | New Liberty - Boutwell 138 kV |  | OH | Hancock | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-548 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-549 | Rineyville 69 kV |  | KY | Hardin | Active | EKPC | 40 | 40 | 26.6667 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AG2-550 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 200 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-551 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 250 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-552 | Bullitt County 161 kV |  | KY | Bullitt | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-553 | Bullitt County 161 kV |  | KY | Bullitt | Active | EKPC | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AG2-557 | Spring Mills - Millheim 46 kV |  | PA | Centre | Active | APS | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AG2-558 | Shawville - Phillipsburg 34.5 kV II |  | PA | Clearfield | Active | APS | 39.8 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AG2-559 | Shawville - Phillipsburg 34.5 kV III |  | PA | Clearfield | Active | APS | 59.7 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2024 |  |  | N | No
AG2-560 | Phillipsburg (Karthaus) 34.5 kV |  | PA | Clearfield | Active | APS | 79.6 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-561 | Glory - Glen Campbell 34.5 kV |  | PA | Indiana | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AG2-562 | Elderberry 345 kV |  | IN | St. Joseph | Active | AEP | 786 | 71 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AG2-563 | Gasburg 69 kV |  | VA | Brunswick | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/24/2024 |  |  | N | No
AG2-564 | Sulphur Springs 138 kV |  | OH | Crawford | Active | AEP | 49.99 | 49.99 | 32.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AG2-565 | Kidds Store - Sherwood 115 kV |  | VA | Fluvanna | Active | Dominion | 110 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AG2-566 | Briery - Clover 230 kV |  | VA | Prince Edward | Active | Dominion | 110 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AG2-567 | Stanville - Dewey 138 kV |  | KY | N/A | Active | AEP | 200 | 200 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/24/2024 |  |  | N | No
AG2-568 | Stink Run – Sundial 138 kV |  | WV | N/A | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 2/25/2024 |  |  | N | No
AG2-569 | Rogers Road - Carson 500 kV |  | VA | Greensville | Active | Dominion | 150 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/25/2024 |  |  | N | No
AG2-570 | Brunswick Collector - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AG2-571 | Brunswick Collector Bus - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 500 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AG2-575 | Glidden-Waterman 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-576 | Varner 345 kV |  | IN | DeKalb | Active | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-577 | Jay 138 kV |  | IN | Jay | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-578 | Jay 69 kV |  | IN | Jay | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-579 | Fostoria 138 kV |  | OH | Hancock | Active | AEP | 205 | 0 | 41 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AG2-580 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-581 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/29/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-582 | Belmont-Flint Run 500 kV |  | WV | Doddridge | Active | APS | 2100 | 2100 | 2100 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/1/2026 |  |  | N | No
AG2-583 | Bremo - Cartersville 230 kV |  | VA | Cumberland | Active | Dominion | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AG2-584 | Double Toll Gate - Meadowbrook 138 kV |  | VA | Frederick | Active | APS | 90 | 90 | 46.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-585 | Kensignton 138kV |  | IL | Kankakee | Active | ComEd | 225 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AG2-587 | Graceton 230 kV |  | MD | Harford | Active | BGE | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-588 | Kittatinny - Blairstown 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-589 | Ravenswood Hemlock 69 kV |  | OH | Meigs | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-590 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Active | PENELEC | 92.1 | 38.2 | 22.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-591 | Bluebell-Sancap Tap 69 kV |  | OH | Mahoning | Active | ATSI | 61 | 61 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-592 | West Cambridge - Vienna 69 kV |  | MD | Dorchester | Active | DPL | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-593 | Benton-Scott 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-594 | Benton-Scott 69 kV II |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-595 | LaRue - North Waldo 138 kV |  | OH | Marion | Active | AEP | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-596 | Renaker-Avon 138 kV |  | KY | Scott | Active | EKPC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-597 | Broadford 138 kV |  | VA | Smyth | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AG2-598 | Knob Lick-JB Galloway Tap 69 kV |  | KY | Metcalfe | Active | EKPC | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/30/2025 |  |  | N | No
AG2-599 | Furnace Brook-Warren 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AG2-600 | American Can-BASF 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AG2-601 | Milton 69 kV III |  | PA | Northumberland | Active | PPL | 90 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/16/2022 |  |  | N | No
AG2-602 | Maysville 69 kV V |  | PA | Mercer | Active | ATSI | 60.8 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AG2-603 | Huffman 138 kV |  | VA | Carroll | Active | AEP | 150 | 150 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-604 | Edgemont 138 kV |  | VA | Montgomery | Active | AEP | 94 | 94 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-605 | Skimmer - Abert 69 kV |  | VA | Amherst | Active | AEP | 37 | 37 | 24.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-606 | Sunbury-Juniata 500 kV |  | PA | Perry | Active | PPL | 89 | 89 | 53.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-607 | St. Johns - Dunbrook 34.5 kV |  | VA | King and Queen | Active | Dominion | 20 | 20 | 12.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AG2-608 | Unionville - Locust 115 kV |  | VA | Orange | Active | Dominion | 80 | 80 | 64 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/15/2023 |  |  | N | No
AG2-609 | Unionville - Locust Grove 115 kV |  | VA | Orange | Active | Dominion | 40 | 40 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/15/2023 |  |  | N | No
AG2-610 | Gold 12.5 kV |  | PA | Potter | Active | PENELEC | 4.998 | 4.998 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-611 | Hamlin 12 kV |  | PA | Wayne | Active | PPL | 4.998 | 4.998 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-612 | Lakeville 12 kV |  | PA | Wayne | Active | PPL | 4.998 | 4.998 | 4.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-614 | Mansfield 12 kV |  | PA | Tioga | Active | PENELEC | 5 | 5 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-615 | Carlos Junction 138 kV |  | MD | Allegany | Active | APS | 100 | 100 | 62.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-616 | Churchtown - Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 50 | 50 | 32.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-617 | Waugh Chapel 115 kV |  | MD | Anne Arundel | Active | BGE | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-618 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 110 | 110 | 69.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-621 | Hoytdale 138 kV |  | PA | Beaver | Active | ATSI | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AG2-624 | Pequest River-Furnace Brook Tap 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AG2-625 | Pequest River-Furnace Brook Tap 34.5 kV II |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AG2-626 | Pequest River-Furnace Brook Tap 34.5 kV III |  | NJ | Warren | Active | JCPL | 12.5 | 12.5 | 5.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/30/2021 |  |  | N | No
AG2-627 | Woodstown-High Street 69 kV |  | NJ | Gloucester | Active | AEC | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-628 | Spring Creek - Millcreek 138 kV |  | OH | Miami | Active | Dayton | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-630 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Active | Dominion | 118.56 | 0 | 47.43 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-631 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-632 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-633 | Gary DP - Lunenburg 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-634 | Gary DP – Lunenburg 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-635 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 270 | 270 | 162 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-636 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 270 | 0 | 108 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-637 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-638 | Kingsland 69 kV |  | IN | Wells | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-639 | Chickahominy 230 kV |  | VA | Charles City | Active | Dominion | 340 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-640 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Active | Dominion | 46.8 | 0 | 18.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-641 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-642 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 0 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-643 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Active | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-644 | Morrisville 230 kV |  | VA | Fauquier | Active | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AG2-645 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AG2-646 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/10/2024 |  |  | N | No
AG2-647 | Bolton - Bennsville 69 kV |  | MD | Charles | Active | SMECO | 9.2 | 9.2 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AG2-652 | Siegfried-Hauto 69 kV IV |  | PA | Carbon | Active | PPL | 20 | 20 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-653 | Siegfried-Hauto 69 kV V |  | PA | Carbon | Active | PPL | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AG2-654 | Cowansville Junction – Long Run Tap 25 kV |  | PA | Armstrong | Active | APS | 14.7 | 14.7 | 8.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AG2-655 | Mt. Storm 500 kV |  | WV | Grant | Active | Dominion | 800 | 800 | 330 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-656 | Kanawha River - Carbondale 138 kV |  | WV | Kanawha | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-657 | Carbondale 138 kV |  | WV | Fayette | Active | AEP | 90 | 90 | 49.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AG2-658 | Cowen 138 kV |  | WV | Webster | Active | APS | 210 | 210 | 135.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-659 | Five Forks - Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/30/2025 |  |  | N | No
AG2-660 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AG2-661 | Hopewell - Surry 230 kV |  | VA | Surry | Active | Dominion | 150 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AG2-662 | Stephensburg - Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 90 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-664 | TodHunter – Trenton 138 kV |  | OH | Butler | Active | DEOK | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AG2-665 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AG2-666 | Spurlock - Flemingsburg 138 kV |  | KY | Jackson | Active | EKPC | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-667 | Wakesfield - Poolesville 34.5 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12.53 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AG2-668 | Harvey Run 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AG2-670 | Greensburg 69 kV |  | KY | Green | Active | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-671 | Hope - Frenchburg 69 kV |  | KY | Montgomery | Active | EKPC | 19.9 | 19.9 | 11.94 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AG2-673 | Fitzell 33 kV |  | MD | Baltimore County | Active | BGE | 9.92 | 9.92 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 12/30/2022 |  |  | N | No
AG2-674 | Quad Cities - Sterling Steel 345 kV |  | IL | Whiteside | Active | ComEd | 212.1 | 212.1 | 37.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/1/2023 |  |  | N | No
AG2-675 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AG2-676 | Russell Co 161 kV |  | KY | Russell | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-677 | Russell Co J - Jamestown T 161 kV |  | KY | Russell | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-678 | Vicco - Beckham 138 kV |  | KY | Knott | Active | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-679 | Daisy - Collier 69 kV |  | KY | Letcher | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-680 | South Anna - Louisa 230 kV |  | VA | Madison | Active | Dominion | 202 | 202 | 121.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-681 | Soft Shell - Bonny Man 138 kV |  | KY | Perry | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-682 | Stinnett 161 kV |  | KY | Leslie | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-683 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-684 | Summer Shade 161 kV |  | KY | Metcalfe | Active | EKPC | 331 | 331 | 198.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-685 | Big Sandy-Inez 138 kV |  | KY | Martin | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-686 | Powell Mountain 138 kV |  | WV | Nicholas | Active | APS | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-687 | Garrard 345 kV |  | KY | Garrard | Active | EKPC | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-688 | Imperial-Joffre 138 kV |  | PA | Clearfield | Active | APS | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-689 | Tenmile 138 kV |  | WV | N/A | Active | AEP | 125 | 125 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-690 | Sullivan - Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AG2-691 | New Lebanon - Ohio Hutchings 69 kV |  | OH | Montgomery | Active | Dayton | 49.5 | 49.5 | 39.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/31/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-001 | Bartonsville-Meadowbrook 138 kV |  | VA | Frederick | Active | APS | 220 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2021 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AH1-002 | Hector 115 kV |  | PA | Potter | Active | PENELEC | 50 | 50 | 7.35 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-003 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Active | ComEd | 130 | 130 | 19.11 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-004 | Avon - Renaker 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/7/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-005 | East Towanda-South Troy 115 kV II |  | PA | Bradford | Active | PENELEC | 54 | 23 | 14.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/9/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AH1-010 | Stony River - Buffalo Coal 66 kV |  | WV | Grant | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-011 | Fulton - Tidd 69 kV |  | WV | Brooke | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-012 | Louisa - North Anna 230 kV |  | VA | Louisa | Active | Dominion | 90.8 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH1-013 | Hanna - Tanners Creek 345 kV |  | IN | Shelby | Active | AEP | 500 | 0 | 300 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/20/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-014 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 111.8 | 111.8 | 67.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-015 | Academia 138 kV |  | OH | Knox | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/22/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AH1-017 | Copperstone-North Lebanon 230 kV III |  | PA | Lebanon | Active | ME | 100 | 30 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/4/2021 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AH1-018 | Cunningham - Elmont 500 kV |  | VA | Fluvanna | Active | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-019 | Cunningham - Elmont 500 kV II |  | VA | Fluvanna | Active | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-020 | Kidds Store – Fork Union 115 kV |  | VA | Fluvanna | Active | Dominion | 38 | 38 | 22 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/13/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-021 | North Temple 781-1 13.2 kV |  | PA | Berks | Active | ME | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AH1-023 | Corning Glass-Bush Town Junction 34.5 kV |  | PA | Franklin | Active | APS | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AH1-024 | Lickdale 626-2 13.2 kV |  | PA | Lebanon | Active | ME | 2 | 2 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AH1-025 | Myerstown 751-2 13.2 kV |  | PA | Lebanon | Active | ME | 4.5 | 4.5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AH1-026 | Newberry 576-4 13.2 kV |  | PA | York | Active | ME | 4.5 | 4.5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/12/2021 | N/A | N/A |  |  |  | 11/30/2022 |  |  | N | No
AH1-027 | Cartanza 230 kV |  | DE | Kent | Active | DPL | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/20/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-032 | West Millersport 138 kV |  | OH | Fairfield | Active | AEP | 138 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-033 | Sligo 34.5 kV |  | NC | Currituck | Active | Dominion | 19.5 | 19.5 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 8/15/2024 |  |  | N | No
AH1-034 | Patton Road Junction - Summer Shade 69 kV |  | KY | Barren | Active | EKPC | 100 | 100 | 70 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 11/15/2025 |  |  | N | No
AH1-035 | Plymouth 34.5 kV |  | NC | Washington | Active | Dominion | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/14/2021 | N/A | N/A |  |  |  | 9/15/2024 |  |  | N | No
AH1-036 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 277.5 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/15/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-037 | Chippewa D557 8.320 kV |  | N/A | N/A | Active | ATSI | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/16/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH1-040 | Mackeys - Creswell 115 kV |  | NC | Washington | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2021 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH1-041 | Pennville 138 kV |  | IN | Jay | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/23/2021 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH1-042 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 154 | 154 | 99.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/25/2021 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AH1-043 | Sand Hills - Brunswick 69 kV |  | NJ | Middlesex | Active | PSEG | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2021 | N/A | N/A |  |  |  | 5/15/2024 |  |  | N | No
AH1-044 | Nelson - Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-045 | Zion Energy Center 345 kV |  | IL | Lake | Active | ComEd | 658 | 23 | 13.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/1/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-046 | Peach Bottom 500 kV |  | PA | York | Active | PECO | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/1/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-047 | Marengo - Belvidere 138 kV |  | IL | Boone | Active | ComEd | 61.6 | 61.6 | 37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/6/2021 | N/A | N/A |  |  |  | 9/13/2022 |  |  | N | No
AH1-048 | Riverton 138 |  | VA | Warren | Active | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  |  |  | 5/1/2024 |  |  | N | No
AH1-049 | Erie East – Union City Ckt 00234-31 34.5 kV |  | PA | Adams | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-050 | Eclipse-Piney 115 kV |  | PA | Venango | Active | PENELEC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-051 | Eclipse-Piney 115 kV II |  | PA | Venango | Active | PENELEC | 80 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-052 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 260 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/7/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AH1-054 | Upton-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 8.25 | 8.25 | 3.465 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/9/2021 | N/A | N/A |  |  |  | 7/8/2022 |  |  | N | No
AH1-055 | Kyger Creek - Don Marquis 345 kV |  | OH | Jackson | Active | OVEC | 220 | 220 | 148.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2021 | N/A | N/A |  |  |  | 11/15/2026 |  |  | N | No
AH1-056 | Red House D.P. 115kV |  | VA | Campbell | Active | Dominion | 100 | 100 | 68.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/14/2021 | N/A | N/A |  |  |  | 11/15/2026 |  |  | N | No
AH1-057 | Edgewood 12.47 kV |  | MD | Wicomico | Active | DPL | 7.2 | 7.2 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/15/2021 | N/A | N/A |  |  |  | 1/31/2023 |  |  | N | No
AH1-058 | Galion 138 kV IV |  | OH | Morrow | Active | ATSI | 204 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/16/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-059 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 120 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/16/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-060 | Cardington-Liberty 69 kV III |  | OH | Morrow | Active | ATSI | 101 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/20/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-061 | Bernville 13.2kV |  | PA | Berks | Active | ME | 5 | 5 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/21/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-062 | London-Tangy 69 kV II |  | OH | Madison | Active | ATSI | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/22/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-063 | Spring Creek – South Abingdon 138 kV |  | VA | Washington | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-064 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH1-065 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH1-066 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH1-067 | Minotola 12.47 kV |  | NJ | Gloucester | Active | AEC | 8.5 | 8.5 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/27/2021 | N/A | N/A |  |  |  | 12/10/2023 |  |  | N | No
AH1-068 | Williamstown 12.47 kV |  | NJ | Gloucester | Active | AEC | 12 | 12 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2021 | N/A | N/A |  |  |  | 12/10/2023 |  |  | N | No
AH1-069 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AH1-070 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 34 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AH1-071 | TBD 34.5 kV |  | VA | Powhatan | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-072 | Lick Fork 69 kV |  | VA | Dickenson | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AH1-073 | Lick Fork 69 kV |  | VA | Dickenson | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AH1-074 | Fitchville-New London 69 kV |  | OH | Huron | Active | ATSI | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-075 | North Waldo - Wild Creek 138 kV |  | OH | Marion | Active | AEP | 68 | 8 | 24.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-076 | Loyalhanna - Reed Junction 25 kV |  | PA | Westmoreland | Active | APS | 18 | 18 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-077 | TBD 34.5 kV |  | NJ | Burlington | Active | AEC | 3 | 3 | 1.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 8/9/2021 |  |  | N | No
AH1-078 | Paulsboro 69 kV II |  | NJ | Gloucester | Active | AEC | 79 | 0 | 58 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AH1-079 | Harmony Village 34.5kV |  | VA | Middlesex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-080 | Virginia Beach - Pendleton 115 kV |  | VA | City of Virginia Beach | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 1/1/2025 |  |  | N | No
AH1-081 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-082 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 104 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-083 | Summer Shade - Green County 161 kV |  | KY | Metcalfe | Active | EKPC | 250 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-086 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-087 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-088 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-089 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-090 | Surry - Hopewell 230 kV |  | VA | Surry | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AH1-091 | Ahoskie 34.5kV |  | NC | Hertford | Active | Dominion | 17 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AH1-092 | SedgeHill - Person 230 kV |  | VA | Halifax | Active | Dominion | 100 | 100 | 65 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-093 | SedgeHill - Person 230 kV |  | VA | Halifax | Active | Dominion | 160 | 60 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-094 | Wells - Shinrock 69 kV I |  | OH | Huron | Active | ATSI | 49.9 | 49.9 | 32.435 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-095 | Wells - Shinrock 69 kV II |  | OH | Huron | Active | ATSI | 69.9 | 20 | 13 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-096 | Wells - Shinrock 69 kv III |  | OH | Huron | Active | ATSI | 79.9 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-097 | Jubal Early - Pipers Gap 138 kV |  | VA | Carroll | Active | AEP | 20 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-098 | Jubal Early - Pipers Gap 138 kV |  | VA | Carroll | Active | AEP | 60 | 40 | 26 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-099 | Glady Run–Xenia 69 kV |  | OH | Greene | Active | Dayton | 20 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-100 | Effort Mountain-Gilbert 138 kV II |  | PA | Monroe | Active | PPL | 45.2 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-102 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 100 | 100 | 63.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-106 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AH1-107 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2021 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AH1-108 | Spruance NUG 230 kV |  | VA | City of Richmond | Active | Dominion | 66 | 0 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2021 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AH1-110 | Newville 12 kV II |  | PA | Cumberland | Active | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-111 | Walker 12 kV |  | PA | Juniata | Active | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/6/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-113 | North Pole - Russelville 34.5 kV |  | OH | Brown | Active | DEOK | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-114 | North Pole - Russelville 34.5 kV |  | OH | Brown | Active | DEOK | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/9/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-118 | Windsor 25 kV |  | WV | Brooke | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-119 | Bismark-Doubs 500 kV |  | VA | Frederick | Active | Dominion | 100 | 100 | 66.6667 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/13/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-122 | Dowling 138 kV II |  | OH | Wood | Active | ATSI | 75 | 22 | 9.24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/19/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-124 | Vint Hill 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-125 | Sycoline 12.5kV |  | VA | Loudoun | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-127 | Paradise 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-128 | Railroad 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-129 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2021 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AH1-130 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/24/2021 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AH1-131 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AH1-132 | Double Toll Gate - Strasburg 34.5 kV |  | VA | Frederick | Active | APS | 14.4 | 14.4 | 14.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 1/1/2022 |  |  | N | No
AH1-133 | Saltville - Tazewell 138 kV |  | VA | Tazewell | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-136 | Falcon -Middle Creek 46 kV |  | KY | N/A | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/25/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-138 | Penniman 34.5 kV |  | VA | City of Williamsburg | Active | Dominion | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 7/15/2022 |  |  | N | No
AH1-139 | Cooper 34.5kV |  | PA | York | Active | PECO | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | Y | No
AH1-140 | Vasco 138 kV |  | PA | Westmoreland | Active | APS | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/30/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-141 | Darbytown 230 kV |  | VA | Henrico | Active | Dominion | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-142 | Darbytown 230 kV II |  | VA | Henrico | Active | Dominion | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-143 | Darbytown 230 kV III |  | VA | Henrico | Active | Dominion | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-144 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-145 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 200 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-146 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-147 | Byron-Wayne 345 kV |  | IL | Ogle | Active | ComEd | 400 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-148 | Byron-Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-149 | Moselem-Saint Peters Tap 69 kV |  | PA | Berks | Active | ME | 8.375 | 8.375 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2021 | N/A | N/A |  |  |  | 9/19/2022 |  |  | N | No
AH1-150 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1000 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/28/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-151 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-152 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-153 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-154 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-156 | Cane Ridge 69 kV |  | KY | Bourbon | Active | EKPC | 40 | 40 | 25.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-157 | Penniman - Waller 230 kV |  | VA | York | Active | Dominion | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 1/1/2025 |  |  | N | No
AH1-158 | Eclipse-Piney 115 kV III |  | PA | Venango | Active | PENELEC | 80 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-159 | Conneaut-Conneaut Tap 69 kV |  | PA | Crawford | Active | ATSI | 20 | 20 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AH1-160 | Tower Hill 34.5 kV |  | PA | Tioga | Active | PENELEC | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AH1-161 | Canal 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AH1-162 | Curryville-RKB-Yellow Creek 23 kV |  | PA | Bedford | Active | PENELEC | 16 | 16 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | N | No
AH1-163 | Millersburg 69 kV |  | KY | N/A | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-164 | Oak Level - Tank Hill 138 kV |  | VA | Franklin | Active | AEP | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-165 | Will County 138 kV |  | IL | Will | Active | ComEd | 80 | 80 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-167 | Pinewood - St Johns 115 kV |  | VA | Caroline | Active | Dominion | 80 | 80 | 51.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AH1-168 | Pinewood - St Johns 115 kV II |  | VA | Caroline | Active | Dominion | 120 | 40 | 25.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AH1-169 | Greenbush 69kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-170 | Columbia DP 115kV |  | VA | Goochland | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-171 | Columbia DP 115kV |  | VA | Goochland | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/27/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-172 | Wolf Glade 34.5 kV |  | VA | Carroll | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-174 | Westlake 34.5 kV |  | VA | Franklin | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-175 | Sheffield 34.5 kV |  | VA | Henry | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-176 | Ridgeway 34.5 kV |  | VA | Henry | Active | AEP | 18.8 | 18.8 | 11.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-178 | Remington - Morrisville 34.5 kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-179 | Edinburg - Woodstock DP 34.5 kV |  | VA | Shenandoah | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-180 | Westlake 34.5 kV |  | VA | Franklin | Active | AEP | 9 | 9 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-181 | Stuart 34.5 |  | VA | Patrick | Active | AEP | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-182 | Peak Creek 34.5 |  | VA | Pulaski | Active | AEP | 11.45 | 11.45 | 6.87 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-184 | Powhatan - Powhatan DP 24.94 kV |  | VA | Powhatan | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-185 | Benn's Church - Smithfield 34.5 kV |  | VA | Isle of Wight | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-186 | Maysville-Sharon 69 kV II |  | PA | Mercer | Active | ATSI | 19.9 | 0 | 6.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 10/18/2024 |  |  | N | No
AH1-188 | Pigeon Creek 138 kV |  | WV | Mingo | Active | AEP | 185 | 185 | 129 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-189 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 185 | 185 | 129 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-190 | Waukegan 138 kV |  | IL | Lake | Active | ComEd | 80 | 80 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-191 | Powerton 138 kV |  | IL | Tazewell | Active | ComEd | 20.9 | 20.9 | 12.065 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-196 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 450 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2021 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH1-197 | Occoquan 230kV |  | VA | Fairfax | Active | Dominion | 98 | 0 | 7.1 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 8/20/2021 |  |  | N | No
AH1-198 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 1355 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-199 | Loretto 345 kV |  | IL | Livingston | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-201 | New Baltimore 115 kV (Mountain Ridge Solar) |  | PA | Somerset | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-202 | New Baltimore 115 kV II (Mountain Ridge Solar) |  | PA | Somerset | Active | PENELEC | 120 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-203 | Allegheny-Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-204 | Allegheny-Somerset 115 kV II |  | PA | Somerset | Active | PENELEC | 90 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/4/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-205 | New Baltimore 115 kV III |  | PA | Somerset | Active | PENELEC | 120 | 0 | 48 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/3/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-206 | Bethelboro 138 kV |  | PA | Fayette | Active | APS | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-207 | Bethelboro 25 kV-1 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-208 | Bethelboro 25 kV-2 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-209 | Bethelboro 25 kV-3 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-210 | Bethelboro 25 kV-4 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-211 | Bethelboro 25 kV-5 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-212 | Bethlehem - Lilly 46 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH1-215 | Central VA-Twitty 115 kV |  | VA | Charlotte | Active | Dominion | 31.5 | 31.5 | 18.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-216 | Smithfield-Surry 230 kV |  | VA | Isle of Wight | Active | Dominion | 132 | 132 | 79.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-217 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Active | Dominion | 57 | 57 | 34.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-220 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-221 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 75 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-222 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-223 | Poland Rd-Runway DP 230 kV |  | VA | Loudoun | Active | Dominion | 50 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-225 | Wood Solar 69 kV |  | OH | Wayne | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AH1-226 | Clubhouse - Sapony 230 kV |  | VA | City of Emporia | Active | Dominion | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-227 | Flemming - Fremont 69 kV |  | VA | Wise | Active | AEP | 51.8 | 51.8 | 30.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-228 | Marsh Run 230kV |  | VA | Fauquier | Active | Dominion | 615 | 18 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AH1-229 | Louisa 230kV |  | VA | Louisa | Active | Dominion | 564 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AH1-230 | Sabinsville 34.5kV |  | PA | Tioga | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-231 | Lanexa 230kV |  | VA | New Kent | Active | Dominion | 28.8 | 28.8 | 28.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-232 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-233 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 175 | 0 | 70 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-234 | Wempletown 345 kV |  | IL | Winnebago | Active | ComEd | 224 | 224 | 149.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/21/2025 |  |  | N | No
AH1-235 | Kilgore Compressor Facility 138 kV |  | OH | Harrison | Active | AEP | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AH1-236 | Bane 69 kV |  | OH | Carroll | Active | AEP | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-237 | Ladysmith- Elmont 230kV |  | VA | Caroline | Active | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-238 | Ladysmith- Elmont 230kV |  | VA | Caroline | Active | Dominion | 180 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-239 | Upchurch - Zula 69 kV |  | KY | Boone | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-240 | Wayne County 161 kV |  | KY | Boone | Active | EKPC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-241 | Cobbs Creek - James River Industrial 115kV |  | VA | Cumberland | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-242 | New Bethlehem-Armstrong 138kV |  | PA | Clarion | Active | APS | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-243 | New Bethlehem – Armstrong 138kV |  | PA | Clarion | Active | APS | 60 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-244 | Yukon-Bethelboro 138kV |  | PA | Fayette | Active | APS | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-245 | Yukon-Bethelboro 138kV |  | PA | Fayette | Active | APS | 160 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-246 | Osterberg 115kV |  | PA | Bedford | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-247 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-248 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 65 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-249 | Lardin – Lake Lynn 138kV |  | PA | Fayette | Active | APS | 145 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-251 | Todds Tavern- Spotsylvania/Goldsdale 115kV |  | VA | Spotsylvania | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-252 | Wharton - Sundial 138 kV |  | WV | Barbour | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-253 | Price 69kV |  | MD | Queen Anne's | Active | DPL | 15.5 | 15.5 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AH1-254 | Greenland Gap 500 kV II |  | WV | Barbour | Active | APS | 471.6 | 207.6 | 36.538 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-255 | Greenland Gap III |  | WV | Grant | Active | APS | 711.6 | 240 | 240 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-256 | Greeland Gap 500 kV IV |  | WV | Grant | Active | APS | 951.6 | 240 | 240 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 7/31/2025 |  |  | N | No
AH1-257 | Broadway - RichLine Hill Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-258 | Belford - Keansburg 34.5 kV |  | NJ | Monmouth | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-259 | Chesterfield- Centralia 115kV |  | VA | Chesterfield | Active | Dominion | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-260 | New Freedom 230 kV |  | NJ | Camden | Active | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AH1-261 | East Point - Golden Ring 115kV |  | MD | Baltimore County | Active | BGE | 135 | 135 | 135 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AH1-262 | Deep Creek 115 kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 11/30/2023 |  |  | N | No
AH1-263 | Chancellor 115 kV |  | VA | Spotsylvania | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AH1-264 | Suffolk- Sunbury 230kV |  | VA | City of Suffolk | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-265 | TBD 69kV |  | NJ | Camden | Active | AEC | 29.4 | 29.4 | 12.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-266 | Clubhouse – Lakeview 230 kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-267 | Papermill IND – Harmony Village 230 kV |  | VA | King and Queen | Active | Dominion | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-268 | Seward-Glory 115 kV II |  | PA | Indiana | Active | PENELEC | 100 | 0 | 36.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-269 | Claytor 138 kV |  | VA | Pulaski | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-270 | Hayden 345 kV |  | OH | Franklin | Active | AEP | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AH1-271 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 110 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 9/20/2024 |  |  | N | No
AH1-272 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-273 | Brown - Eastwood 138 kV |  | OH | Brown | Active | DEOK | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/26/2025 |  |  | N | No
AH1-274 | Monroe – North Central 69kV |  | NJ | Gloucester | Active | AEC | 16.7 | 16.7 | 7.014 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/23/2022 |  |  | N | No
AH1-275 | Chippewa D557 8.32 kV |  | N/A | N/A | Active | ATSI | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH1-277 | Indian River 230kV |  | DE | Sussex | Active | DPL | 1035 | 1035 | 279 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AH1-278 | Milford - Indian River/Cool Springs 230kV |  | DE | Sussex | Active | DPL | 1035 | 1035 | 279 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AH1-279 | Poolesville - Winchester 230 kV |  | VA | Isle of Wight | Active | Dominion | 104 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AH1-280 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 106 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/12/2023 |  |  | N | No
AH1-281 | Bluegrass Parkway Tap - Woodlawn 69 kV |  | KY | Nelson | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/7/2024 |  |  | N | No
AH1-282 | Galion - Ohio Central 345 kV |  | OH | Morrow | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-283 | Mount Storm-Pruntytown 500kV |  | MD | Garrett | Active | APS | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AH1-284 | West Willow 12 kV |  | PA | Adams | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | Y | No
AH1-285 | Sandwich 34.5 kV |  | IL | DeKalb | Active | ComEd | 86 | 86 | 51.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-286 | Bradford North 34.5kV |  | WV | Preston | Active | PENELEC | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH1-287 | Houseville – Cooperstown 25 kV |  | OH | Madison | Active | APS | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH1-288 | Chickahominy 230kV |  | VA | Charles City | Active | Dominion | 43.2 | 43.2 | 43.2 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-289 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 5/1/2028 |  |  | N | No
AH1-290 | BASF - Washburn Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 9/9/2022 |  |  | N | No
AH1-291 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 185 | 185 | 111 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-292 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-293 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 120 | 0 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-294 | Mclean 345 kV |  | IL | McLean | Active | ComEd | 600 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-295 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-296 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 660 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-297 | Kewanee - E.D. Edwards 138 kV |  | IL | Stark | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-298 | Twin Branch - Meridian 345 kV |  | IN | Whitley | Active | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-300 | Hacienda 138 kV |  | IN | Allen | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-301 | Milan 138 kV |  | IN | Allen | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-302 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-303 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-304 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 163 | 0 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-305 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 0 | 35.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-306 | Mississinewa - Gaston 138 kV |  | IN | Grant | Active | AEP | 160 | 0 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-307 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 213 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-308 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 205 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-309 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Active | AEP | 150 | 0 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-310 | Colby - Valley 138 kV |  | MI | Van Buren | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-311 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 75 | 0 | 2.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-312 | Shilo DP – Conetoe DP 115 kV |  | NC | Edgecombe | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-313 | Moshannon-Milesburg 230 kV VII |  | PA | Centre | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-314 | East Danville 138 kV |  | VA | Pittsylvania | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-316 | Todd 25kV |  | MD | Dorchester | Active | DPL | 20 | 0 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-317 | Greene - Beatty 345 kV |  | OH | Madison | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-318 | Cole 345 kV |  | OH | Franklin | Active | AEP | 310 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-319 | East Springfield-London 138 kV II |  | OH | Clark | Active | ATSI | 234 | 54 | 54 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-320 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 348.5 | 69 | 69 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-321 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 232 | 54 | 54 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-322 | Fostoria Central - Lemoyne 345 kV |  | OH | Miami | Active | AEP | 390 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-323 | Crittenden 230 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-324 | Hopewell – Surry 230 kV |  | VA | Surry | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-325 | Kirk 138 kV |  | OH | Licking | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-326 | West Newton - Lynn 138 kV |  | OH | Hardin | Active | AEP | 110 | 0 | 19.07 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-327 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 50 | 0 | 8.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-328 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 348.5 | 0 | 21.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-329 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Active | AEP | 130 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-330 | Tyner - McKee 69 kV |  | KY | N/A | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-331 | Edinboro South-Erie South 25kV |  | PA | Erie | Active | PENELEC | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-332 | West Hills - Craigsville Junction 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-333 | Miller - Canal 69kV |  | OH | Butler | Active | DEOK | 48 | 48 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 4/26/2024 |  |  | N | No
AH1-334 | Manchester - Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/9/2022 |  |  | N | No
AH1-335 | Furnace Brook Tap - Warren County Resource Recovery 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/9/2022 |  |  | N | No
AH1-336 | Bremo Bluff - Buckingham 230 kV |  | VA | Buckingham | Active | Dominion | 56 | 56 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-337 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AH1-338 | New Sub S2354 138kV |  | IL | Lee | Active | ComEd | 180 | 180 | 120.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/21/2025 |  |  | N | No
AH1-339 | West Crawford 69 kV |  | OH | Wyandot | Active | AEP | 80 | 80 | 53.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 11/21/2025 |  |  | N | No
AH1-340 | Cheat Lake-Ruthbelle 138 kV |  | WV | Preston | Active | APS | 48.89 | 48.89 | 29.33 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AH1-341 | ESS-H445 3B 138kv |  | IL | Ogle | Active | ComEd | 150 | 150 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/7/2025 |  |  | N | No
AH1-343 | Crystal Hill DP- Perth 115kV |  | VA | Halifax | Active | Dominion | 69 | 69 | 61.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AH1-345 | Remington 324 34.5 kV |  | VA | Fauquier | Active | Dominion | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AH1-346 | Harrisonburg 356 34.5 kV |  | VA | Rockingham | Active | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-347 | North Pole 492 34.5 kV |  | VA | Goochland | Active | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AH1-348 | Indian Creek 34.5 kV |  | VA | Wise | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/21/2023 |  |  | N | No
AH1-349 | Powhatan 406 34.5 kV |  | VA | Powhatan | Active | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-350 | Sunnyside – Carrolton 138 kV |  | OH | Stark | Active | AEP | 92.4 | 92.4 | 55.44 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-351 | Hillsboro-Wye Mills 138kV |  | MD | Queen Anne's | Active | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-352 | Red Eye 138 kV |  | VA | Campbell | Active | AEP | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2023 |  |  | N | No
AH1-353 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 219 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-354 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 259 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-355 | Owl Trap Switching Station 115kV |  | VA | Gloucester | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-356 | Kings Creek 138kV |  | MD | Somerset | Active | DPL | 180 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2023 |  |  | N | No
AH1-357 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-358 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-359 | Farmers Valley-Ridgeway 115kV |  | PA | McKean | Active | PENELEC | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-360 | Farmers Valley-Ridgeway 115kV |  | PA | McKean | Active | PENELEC | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-361 | Minonk 345 kV |  | IL | Woodford | Active | ComEd | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AH1-362 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-363 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-364 | Harmony Village 230kV |  | VA | Middlesex | Active | Dominion | 68 | 68 | 68 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-365 | Iron Bridge 230kV |  | VA | Chesterfield | Active | Dominion | 50.4 | 50.4 | 50.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-366 | Whitely 138 kV |  | PA | Greene | Active | APS | 30 | 30 | 22 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AH1-367 | Franklin 138 kV |  | PA | Greene | Active | APS | 74 | 74 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AH1-367A | Franklin 138 kV II |  | PA | Greene | Active | APS | 150 | 150 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AH1-368 | Cloverdale - Joshua Falls 765 kV |  | VA | Bedford | Active | AEP | 125 | 125 | 83.3333 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-370 | Mather - Stoney Point Junction 25 kV |  | PA | Greene | Active | APS | 8 | 8 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AH1-372 | Piney - Timblin 115 kV |  | PA | Armstrong | Active | APS | 16 | 16 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AH1-373 | Buckeye No. 3 - Cowell Junction 25kV |  | PA | Greene | Active | APS | 12.8 | 12.8 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/3/2024 |  |  | N | No
AH1-374 | Bremo-Cartersville 230 kV II |  | VA | Cumberland | Active | Dominion | 115 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-375 | Cobbs Creek- James River 115kV |  | VA | Fluvanna | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-376 | Ronceverte - Clenden 46 kV |  | WV | Greenbrier | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-377 | Clover- Farmville 230kV |  | VA | Prince Edward | Active | Dominion | 186 | 186 | 111.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-378 | Lunenburg- Butcher Creek 115kV |  | VA | Lunenburg | Active | Dominion | 51 | 51 | 30.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-379 | Hickman 69 kV |  | VA | Pulaski | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-380 | Mt Olive - Kenny 69kV |  | MD | Worcester | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-381 | Lone Gum - Rockcastle 138 kV |  | VA | Bedford | Active | AEP | 99.5 | 99.5 | 59.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-382 | Van Arsdell 69 kV |  | KY | Mercer | Active | EKPC | 20 | 20 | 17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/10/2025 |  |  | N | No
AH1-383 | Celanese 138 kV |  | VA | Giles | Active | AEP | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-384 | Indian River 230kV |  | DE | Sussex | Active | DPL | 1410 | 1410 | 380.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AH1-385 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 109 | 109 | 65.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-386 | Kerr Dam - Chase City 115 kV |  | VA | Mecklenburg | Active | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-387 | Meadowbrook-Mount Storm 500kV |  | WV | Hampshire | Active | APS | 150 | 150 | 22.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 1/9/2025 |  |  | N | No
AH1-388 | Chase City-Herbert 115 kV |  | VA | Mecklenburg | Active | Dominion | 115 | 115 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AH1-389 | Utica East Ohio Midstream 138 kV |  | OH | Warren | Active | ATSI | 19.95 | 19.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-390 | TBD 69 kV |  | PA | Northumberland | Active | PPL | 19.9 | 19.9 | 14.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/31/2023 |  |  | N | No
AH1-391 | Maple 138 kV |  | IN | St. Joseph | Active | AEP | 100 | 100 | 64.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/16/2025 |  |  | N | No
AH1-392 | Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 90 | 90 | 57.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/16/2025 |  |  | N | No
AH1-395 | Mainesburg 115 kV II |  | PA | Tioga | Active | PENELEC | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-396 | Gary 24.94 kV |  | VA | Lunenburg | Active | Dominion | 12 | 12 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AH1-397 | Shacklesfords 34.5 kV |  | VA | King and Queen | Active | Dominion | 19.818 | 19.818 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AH1-398 | Oak Grove 22.9 kV |  | VA | Westmoreland | Active | Dominion | 18 | 18 | 11.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AH1-399 | North Doswell 12.5 kV |  | VA | Hanover | Active | Dominion | 12 | 12 | 7.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/22/2021 | N/A | N/A |  |  |  | 10/2/2023 |  |  | N | No
AH1-400 | Jones Creek - Aladdin 138 kV |  | IN | Madison | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-401 | Jones Creek - Aliddin 138 kV |  | IN | Madison | Active | AEP | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-402 | Shelocta 115kV |  | PA | Indiana | Active | PENELEC | 85 | 85 | 55.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-403 | Shelocta 115kV |  | PA | Indiana | Active | PENELEC | 85 | 0 | 29.1 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-404 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Active | OVEC | 210 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-405 | Exchange Tap I 69 kV |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/18/2024 |  |  | N | No
AH1-406 | Exchange Tap 69 kV II |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/18/2024 |  |  | N | No
AH1-407 | Exchange Tap 69 kV III |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/18/2024 |  |  | N | No
AH1-408 | Freeman DP – Lawrenceville 115 kV |  | VA | Brunswick | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-409 | Brodhead - Maretburg 69 kV |  | KY | N/A | Active | EKPC | 58 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-410 | Union City Tap – JK Smith 138 kV |  | KY | Madison | Active | EKPC | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-411 | Phillipsburg - Ingersol Rand 34.5 kV |  | NJ | Warren | Active | JCPL | 5.75 | 5.75 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/8/2022 |  |  | N | No
AH1-412 | Franklintown 34.5 kV |  | WV | Jefferson | Active | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-413 | Wayne Trace 138 kV |  | IN | Allen | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-415 | Bremo Bluff 34.5kV |  | VA | Fluvanna | Active | Dominion | 15.975 | 15.975 | 8.6265 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/11/2023 |  |  | N | No
AH1-416 | Bellefontaine 69 kV |  | OH | Logan | Active | Dayton | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-417 | Castalia 69 kV |  | OH | Erie | Active | ATSI | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-418 | Elkhorn City - Second Fork 69 kV |  | KY | Pike | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-419 | Thompson 34.5 kV II |  | PA | Susquehanna | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-420 | Fentress 34.5kV |  | VA | City of Chesapeake | Active | Dominion | 20 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/26/2023 |  |  | N | No
AH1-421 | West Mingo 69 kV |  | OH | Champaign | Active | Dayton | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-422 | West Mingo 69 kV |  | OH | Champaign | Active | Dayton | 60 | 20 | 18.85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-423 | West Mingo 69 kV |  | OH | Champaign | Active | Dayton | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-424 | Sandborn 34.5 kV |  | OH | Ashtabula | Active | ATSI | 19.2 | 19.2 | 11.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-425 | Lemoyne 138kV |  | OH | Ottawa | Active | ATSI | 32 | 32 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH1-426 | Carbondale 138 kV |  | WV | Kanawha | Active | AEP | 200 | 200 | 184.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-426A | Jones Branch 138 kV |  | WV | Nicholas | Active | APS | 100 | 100 | 92.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-427 | Tommy Gooch - Garrard COunty 69 kV |  | KY | N/A | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-428 | Tommy Gooch - Garrard County 69 kV |  | KY | Boone | Active | EKPC | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-429 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-430 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 90 | 0 | 36 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-431 | Pennville 138 kV |  | IN | Jay | Active | AEP | 125 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH1-432 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AH1-433 | Kingsland 69 kV |  | IN | Wells | Active | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AH1-434 | Carolina- Earleys 115kV |  | NC | Northhampton | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-435 | Carolina- Earleys 115kV |  | NC | Northhampton | Active | Dominion | 75 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-436 | Mackeys- Creswell 115kV |  | NC | Washington | Active | Dominion | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH1-437 | Remington- Gordonsville 230kV |  | VA | Culpeper | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-438 | Remington- Gordonsville 230kV |  | VA | Culpeper | Active | Dominion | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-439 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-440 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 85 | 0 | 34 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AH1-441 | Cunningham - Elmont 500 kV III |  | VA | Fluvanna | Active | Dominion | 149 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-442 | Cunningham - Elmont 500 kV IV |  | VA | Fluvanna | Active | Dominion | 149 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-443 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Active | Dominion | 0 | 0 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH1-445 | Belleville 46 kV |  | PA | Mifflin | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2023 |  |  | N | No
AH1-446 | Sanders DP - Westmoreland 230 kV |  | VA | Westmoreland | Active | Dominion | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AH1-447 | Axton – Danville #2 138 kV |  | VA | Pittsylvania | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/2/2024 |  |  | N | No
AH1-449 | Muskingum River - Sporn 345 kV |  | OH | Washington | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AH1-450 | Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-451 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-452 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 8.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-453 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2028 |  |  | N | No
AH1-454 | Pinewood- St Johns 115kV |  | VA | Caroline | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-456 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-457 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Active | Dominion | 130 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-458 | Hampshire - Ridgeley 138 kV 1 |  | WV | Hampshire | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-459 | Hampshire - Ridgeley 138 kV 2 |  | WV | Hampshire | Active | APS | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AH1-460 | Hooversville - Scalp Level 115 kV |  | PA | Somerset | Active | PENELEC | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-461 | Buckhorn 138 kV |  | VA | Tazewell | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-462 | Rachel Hill 115 kV |  | PA | Cambria | Active | PENELEC | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-463 | Owingsville - Preston 69 kV |  | KY | Bath | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-465 | Carson – Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 350 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-466 | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 600 | 600 | 360 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-467 | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 900 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-469 | Derry Tap-Derry Bus 69 kV III |  | PA | Montour | Active | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-470 | Derry Tap- Derry Bus 69 kV IV |  | PA | Northumberland | Active | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-471 | Derry Tap- Derry Bus 69 kV VI |  | PA | Snyder | Active | PPL | 27.5 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-472 | Derry Tap- Derry Bus 69 kV VII |  | PA | Columbia | Active | PPL | 91 | 56 | 56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-474 | Edinboro South-Venango Junction 115 kV III |  | PA | Crawford | Active | PENELEC | 203.5 | 87 | 87 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-475 | Edinboro-Cambridge Springs 34.5 kV II |  | PA | Crawford | Active | PENELEC | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-476 | Hunterstown-Texas Eastern Tap 115 kV II |  | PA | Adams | Active | ME | 170.5 | 73 | 73 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/23/2024 |  |  | N | No
AH1-477 | Greentown 138 kV |  | IN | Howard | Active | AEP | 112 | 112 | 112 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-478 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Active | PPL | 60 | 40 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-479 | New Carlisle 138 kV |  | IN | St. Joseph | Active | AEP | 192 | 82 | 82 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-480 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Active | AEP | 132 | 57 | 57 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-481 | Reynolds - Meadow Lake #1 345 kV |  | IN | White | Active | AEP | 196 | 84 | 84 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AH1-482 | Olive - Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 455 | 195 | 195 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-483 | Honda Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 142 | 42 | 42 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/23/2024 |  |  | N | No
AH1-484 | Madison - Tanners Creek 138 kV |  | IN | Henry | Active | AEP | 267.5 | 115 | 115 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/24/2023 |  |  | N | No
AH1-486 | Maysville 69 kV 1 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-487 | Maysville 34.5 kV 2 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-488 | Maysville 34.5 kV 3 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-489 | Maysville 34.5 kV 4 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-490 | Venango Junction - Cambridge Springs 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-491 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-492 | Bernville 34.5 kV 1 |  | PA | Berks | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-493 | Bernville 34.5 kV 2 |  | PA | Berks | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-502 | Dequine - Eugene 345 kV |  | IN | Warren | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2028 |  |  | N | No
AH1-503 | Kings Fork – Chuckatuck 230 kV |  | VA | City of Suffolk | Active | Dominion | 150 | 150 | 127.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2025 |  |  | N | No
AH1-506 | Oceanview Wind 3 230 kV |  | NJ | Monmouth | Active | JCPL | 2056 | 730 | 300 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/30/2028 |  |  | N | No
AH1-507 | Oceanview Wind 4 230 kV |  | NJ | Monmouth | Active | JCPL | 2786 | 730 | 300 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/30/2028 |  |  | N | No
AH1-514 | Philipsburg - Emeigh 12.47 kV-1 |  | PA | Clearfield | Active | PENELEC | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH1-515 | Philipsburg - Emeigh 12.47 kV-2 |  | PA | Clearfield | Active | PENELEC | 5 | 5 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH1-516 | Springfield Road - Springfield Road 69 kV |  | OH | Butler | Active | DEOK | 70 | 70 | 44.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH1-518 | Pulaski Sub-New Wilmington 69kV |  | PA | Lawrence | Active | ATSI | 19 | 19 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AH1-520 | Blue Jacket-Kirby 138 kV V |  | OH | Union | Active | ATSI | 120 | 120 | 79.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N | No
AH1-521 | Blue Jacket-Kirby 138 kV VI |  | OH | Union | Active | ATSI | 100 | 100 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2024 |  |  | N | No
AH1-522 | Timber Switch 138 kV |  | OH | Paulding | Active | AEP | 47 | 47 | 28.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-523 | Heidelberg 69 kV |  | PA | Lebanon | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 7/30/2024 |  |  | N | No
AH1-526 | South Canton - Sammis 345 kV |  | OH | Carroll | Active | ATSI | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AH1-527 | Chase City- Herbert Plant Substation 115kV |  | VA | Mecklenburg | Active | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/30/2025 |  |  | N | No
AH1-528 | Rawlings 500kV |  | VA | Brunswick | Active | Dominion | 300.8 | 300.8 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/30/2025 |  |  | N | No
AH1-529 | Renaker - Avon 138 kV |  | KY | Bourbon | Active | EKPC | 89 | 24 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-530 | Fairfield – Reily 69 kV |  | OH | Butler | Active | DEOK | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-531 | Salyers Rd 34.5 kV |  | OH | Pike | Active | AEP | 21 | 21 | 12.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-532 | Marion County - Marion Co. Industrial 161 kV |  | KY | Marion | Active | EKPC | 37.8 | 37.8 | 22.68 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-533 | Sunbury-Juniata II |  | PA | Perry | Active | PPL | 185.2 | 96.2 | 57.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-534 | Sullivan Gardens - Walters 138 kV |  | TN | Greene | Active | AEP | 22.7 | 22.7 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-535 | Nagel - Cane River 230 kV |  | TN | Hawkins | Active | AEP | 133.6 | 133.6 | 80.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-536 | Church-Oil City 138kV |  | MD | Queen Anne's | Active | DPL | 42.7 | 42.7 | 25.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-537 | Pierce - DOE X-530 345 kV |  | OH | Highland | Active | OVEC | 178.5 | 178.5 | 107.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-538 | East Lima - Haviland 138 kV |  | OH | Van Wert | Active | AEP | 241.5 | 241.5 | 144.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-539 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 129.4 | 129.4 | 77.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-540 | Byron to Wayne 345 kV |  | IL | Ogle | Active | ComEd | 165 | 165 | 99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-541 | Chestnut 345 kV |  | IL | DeWitt | Active | ComEd | 92.4 | 92.4 | 55.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-542 | Crissinger-Delaware Business Park 138kV |  | OH | Marion | Active | ATSI | 132.2 | 132.2 | 79.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-543 | Powerton - Katydid Road 345 kV |  | IL | Livingston | Active | ComEd | 157.4 | 157.4 | 94.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-544 | La Salle 345 kV |  | IL | Lasalle | Active | ComEd | 67.7 | 67.7 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-545 | Wylie Ridge-Tidd 345kV |  | PA | Washington | Active | APS | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH1-546 | Bremo - Buckingham 230 kV |  | VA | Buckingham | Active | Dominion | 79.8 | 79.8 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 2/1/2025 |  |  | N | No
AH1-547 | Reynolds - Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 0 | 74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2022 |  |  | N | No
AH1-548 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-549 | Allen - RP Mone 345 kV |  | IN | Allen | Active | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-550 | Hazelton - Kirk 138 kV |  | OH | Licking | Active | AEP | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-552 | Chalk Point 230kV |  | MD | Prince George's | Active | PEPCO | 809.5 | 809.5 | 670.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-553 | Broadview -Tangy 138 kV II |  | OH | Madison | Active | ATSI | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-554 | Lick 138 kV |  | OH | Jackson | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-556 | Larrabee 230 kV III |  | NJ | Monmouth | Active | JCPL | 805.2 | 360 | 63.36 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2029 |  |  | N | No
AH1-557 | Larrabee 230 kV IV |  | NJ | Monmouth | Active | JCPL | 1300 | 1300 | 228.8 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/31/2029 |  |  | N | No
AH1-558 | Four Rivers 230kV |  | VA | Hanover | Active | Dominion | 996 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-560 | University Park 138 kV |  | IL | Will | Active | ComEd | 573 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-561 | Ironwood 230kV |  | PA | Lebanon | Active | ME | 1075 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-562 | Springdale 138kV |  | PA | Allegheny | Active | APS | 356 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-563 | Aurora E.C. 138kV |  | IL | N/A | Active | ComEd | 1306 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-564 | Rockford II 138 kV |  | IL | Winnebago | Active | ComEd | 430 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-565 | Lemoyne 345kV |  | OH | Wood | Active | ATSI | 950 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-566 | South Bend 500kV |  | PA | Armstrong | Active | APS | 1190 | 400 | 400 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-567 | University Park 138 kV |  | IL | Will | Active | ComEd | 578 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-568 | Keen Mountain 138 kV |  | VA | Buchanan | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH1-569 | Broadview - Tangy 138 kV III |  | OH | Union | Active | ATSI | 49.99 | 49.99 | 31.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-570 | Millersburg 69 kV |  | KY | N/A | Active | EKPC | 25 | 25 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-571 | Millersburg 69 kV |  | KY | N/A | Active | EKPC | 20 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-572 | South Morral 69 kV |  | OH | Marion | Active | AEP | 30 | 30 | 19.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-573 | South Morral 69 kV |  | OH | Marion | Active | AEP | 19.99 | 19.99 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH1-574 | Harrington 69kV |  | DE | Kent | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/25/2024 |  |  | N | No
AH1-575 | Harrington 69kV |  | DE | Kent | Active | DPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/25/2024 |  |  | N | No
AH1-576 | South Harrington 69kV |  | DE | Kent | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/25/2024 |  |  | N | No
AH1-577 | Tigers 69 kV |  | OH | Wayne | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2028 |  |  | N | No
AH1-578 | Tigers 69 kV |  | OH | Wayne | Active | AEP | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/15/2028 |  |  | N | No
AH1-579 | Marysville – Hyatt 345 kV |  | OH | Union | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2028 |  |  | N | No
AH1-580 | Nottingham Switch 138 kV |  | OH | Harrison | Active | AEP | 400 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AH1-582 | Marysville - Flatlick 765 kV |  | OH | Madison | Active | AEP | 800 | 0 | 146.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AH1-583 | Marysville - Flatlick 765 kV |  | OH | Madison | Active | AEP | 800 | 0 | 146.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AH1-584 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-585 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-586 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-587 | Farmers Valley – Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-588 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 240 | 240 | 144 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-589 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 410 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-590 | Cherry Ridge 66 kV |  | WV | Grant | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-591 | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-592 | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 145 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-593 | Hazelton 138 |  | WV | Preston | Active | APS | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-594 | Hazelton 138kV |  | WV | Preston | Active | APS | 97 | 32 | 32 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH1-595 | Fowler Ridge 345 kV |  | IN | Benton | Active | AEP | 150 | 150 | 96.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/3/2025 |  |  | N | No
AH1-596 | Fowler Ridge 345 kV |  | IN | Benton | Active | AEP | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/3/2025 |  |  | N | No
AH1-597 | LM Troy 138 kV |  | OH | Ashland | Active | ATSI | 110 | 110 | 70.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/3/2025 |  |  | N | No
AH1-598 | LM Troy 138 kV |  | OH | Ashland | Active | ATSI | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/3/2025 |  |  | N | No
AH1-609 | Milliron-Brookside 138kV |  | OH | Richland | Active | ATSI | 168.31 | 168.31 | 100.986 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 4/30/2025 |  |  | N | No
AH1-614 | Burns 69 kV |  | OH | Clermont | Active | DEOK | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-615 | Pine Creek 138 kV |  | PA | Allegheny | Active | DL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-616 | Chicago Heights 138 kV |  | IL | Cook | Active | ComEd | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AH1-617 | Beaver Creek 138 kV |  | KY | N/A | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AH1-618 | Beaver Creek 138 kV |  | KY | N/A | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AH1-619 | Beaver Creek 138 kV |  | KY | N/A | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AH1-620 | Carville 138kV |  | MD | Queen Anne's | Active | DPL | 76 | 76 | 45.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-621 | Steele-Milford 230kV |  | MD | Allegany | Active | DPL | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-622 | Five Fork 115kV |  | PA | York | Active | PECO | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-623 | South Anna - Desper 230 kV |  | VA | Louisa | Active | Dominion | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-624 | Mainesburg-Homer City 345kV |  | PA | Clearfield | Active | PENELEC | 230 | 230 | 138 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-625 | Cowen 138kV |  | WV | Webster | Active | APS | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH1-626 | Ladysmith 230 kV |  | VA | Caroline | Active | Dominion | 62.5 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/21/2025 |  |  | N | No
AH1-627 | Ladysmith 230 kV II |  | VA | Caroline | Active | Dominion | 125 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 3/21/2025 |  |  | N | No
AH1-630 | Penns Tap-Richfield Tie 69 kV V |  | PA | Snyder | Active | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/11/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-631 | Edinboro South 34.5 kV III |  | PA | Crawford | Active | PENELEC | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-632 | Mercersburg-Milnor 34.5 kV III |  | PA | Franklin | Active | APS | 27 | 12 | 12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2021 | N/A | N/A |  |  |  | 9/25/2023 |  |  | N | No
AH1-633 | Powerton to Katydid 345 kV |  | IL | Livingston | Active | ComEd | 288 | 288 | 172.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  |  |  | 9/26/2024 |  |  | N | No
AH1-634 | Indian River 230kV |  | DE | Sussex | Active | DPL | 323.1 | 68 | 17.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-637 | Oak Grove 34.5 kV |  | VA | Westmoreland | Active | Dominion | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  |  |  | 12/15/2022 |  |  | N | No
AH1-639 | Lordstown - Mansfield 345 kV |  | OH | Mahoning | Active | ATSI | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/13/2021 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AH1-640 | Gladys DP - Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  |  |  | 12/3/2025 |  |  | N | No
AH1-641 | Churchtown - Upper Pittsgrove 138kV |  | NJ | Salem | Active | AEC | 65 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/14/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-644 | Spicewood 138 kV |  | KY | N/A | Active | AEP | 100 | 100 | 65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/15/2021 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH1-646 | Lake Lynn – Gerards Fort 25 kV |  | PA | Fayette | Active | APS | 19.9 | 19.9 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-647 | Greensboro 25 kV |  | PA | Greene | Active | APS | 19.9 | 19.9 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/16/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH1-648 | Grays Ferry 230kV |  | PA | Philadelphia | Active | PECO | 168 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/17/2021 | N/A | N/A |  |  |  | 6/1/2022 |  |  | N | No
AH1-649 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-650 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-651 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-652 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-653 | Greentown 138 kV |  | IN | Howard | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-654 | Kincaid 345 kV |  | IL | Christian | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-655 | SE Canton 138 kV |  | OH | Stark | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/24/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-657 | Nelson 345 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-658 | R. P. Mone 345 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH1-659 | Cordova 345 kV |  | IL | Lee | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/23/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH1-661 | Philo – Cannelville Switch 138 kV |  | OH | Muskingum | Active | AEP | 15.32 | 15.32 | 15.32 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/29/2021 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AH1-663 | River EC 138 kV |  | IL | Cook | Active | ComEd | 57.78 | 57.78 | 57.78 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/30/2021 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AH2-001 | Rattlesnake Hill Waste Heat Recovery |  | PA | Susquehanna | Active | PENELEC | 3.6 | 3.6 | 2.9 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-002 | Temple Hill - Roseville 69 kV |  | KY | Barren | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/2/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-006 | Harrison - Good Hope 138 kV |  | OH | Pickaway | Active | AEP | 14.234 | 14.234 | 14.234 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH2-007 | Texas Eastern - Jeffersonville 69 kV |  | OH | Fayette | Active | Dayton | 10.12 | 10.12 | 10.12 |  | Capacity | Generation Interconnection | Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/4/2021 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH2-009 | Galion 138 kV V |  | OH | Morrow | Active | ATSI | 244 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/8/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-010 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 1455 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/7/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-013 | Cartersville 34.5 kV |  | VA | Cumberland | Active | Dominion | 15.996 | 15.996 | 15.996 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/12/2021 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH2-014 | Crane Solar 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/15/2021 | N/A | N/A |  |  |  | 12/16/2024 |  |  | N | No
AH2-015 | Nelson 138 kV |  | IL | Lee | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/20/2021 | N/A | N/A |  |  |  | 3/24/2025 |  |  | N | No
AH2-021 | Summer Shade - Barren County 161 kV |  | KY | Barren | Active | EKPC | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/27/2021 | N/A | N/A |  |  |  | 11/13/2026 |  |  | N | No
AH2-023 | McDowell 12.47 kV |  | PA | Mercer | Active | ATSI | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2021 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-024 | Kodiak Solar 13.2 kV |  | PA | Jefferson | Active | PENELEC | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/30/2021 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AH2-025 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/29/2021 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-028 | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 44 | 44 | 44 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2021 | N/A | N/A |  |  |  | 10/28/2025 |  |  | N | No
AH2-028A | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 64 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/2/2021 | N/A | N/A |  |  |  | 10/28/2025 |  |  | N | No
AH2-030 | Feagan's Mill 138 kV |  | WV | Jefferson | Active | APS | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-031 | Feagan's Mill 138 kV II |  | WV | Jefferson | Active | APS | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/3/2021 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-032 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-033 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-034 | Possum Point 230kV |  | VA | Prince William | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-035 | Possum Point 500kV |  | VA | Prince William | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/9/2021 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-036 | Young 12.47 |  | PA | Bradford | Active | PENELEC | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH2-037 | Booth 12.47 |  | PA | Fulton | Active | APS | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/11/2021 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AH2-038 | Weirton - Arroyo 25 kV |  | WV | Hancock | Active | APS | 10.75 | 10.75 | 5.4395 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-039 | Chesapeake - Paw Paw 23 kV |  | WV | Marion | Active | APS | 5.5 | 5.5 | 2.728 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-040 | William - Blackwater 69 kV |  | WV | Tucker | Active | APS | 11.5 | 11.5 | 5.7615 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-041 | Osage - Collins Ferry 23 kV |  | WV | Monongalia | Active | APS | 18.89 | 18.89 | 9.48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-042 | Marlowe - North Martinsburg 34.5 kV |  | WV | Berkeley | Active | APS | 5.75 | 5.75 | 3.6858 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/13/2021 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-043 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 200 | 200 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/19/2021 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-044 | Clearfield 12.5 kV |  | PA | Clearfield | Active | APS | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2021 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH2-045 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AH2-046 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/16/2021 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AH2-048 | Bayview 69kV |  | VA | Northampton | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-049 | Crisfield 69kV |  | MD | Somerset | Active | DPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-050 | Tasley 69kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/19/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-051 | Edge Moore 230kV |  | DE | New Castle | Active | DPL | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2021 | N/A | N/A |  |  |  | 6/2/2025 |  |  | N | No
AH2-052 | New Hope 12.47 kV |  | MD | Allegany | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2021 | N/A | N/A |  |  |  | 12/2/2022 |  |  | Y | No
AH2-053 | Mardela Springs 12.47 kV |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2021 | N/A | N/A |  |  |  | 12/2/2022 |  |  | Y | No
AH2-054 | Edgewood 12.47 kV I |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/21/2021 | N/A | N/A |  |  |  | 12/2/2022 |  |  | Y | No
AH2-055 | TBD 69kV |  | MD | Unknown | Active | DPL | 0.99 | 0.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2021 | N/A | N/A |  |  |  | 2/15/2022 |  |  | Y | No
AH2-056 | Chesterfield 230 kV II |  | VA | Chesterfield | Active | Dominion | 60 | 0 | 36 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH2-057 | Scottsville - CVEC Delivery Point 46 kV |  | VA | Buckingham | Active | AEP | 74.9 | 29.9 | 17.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2021 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH2-058 | Possum Point 115 kV |  | VA | Prince William | Active | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-059 | Possum Point 115 kV II |  | VA | Prince William | Active | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AH2-060 | Possum Point 230 kV |  | VA | Prince William | Active | Dominion | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/24/2021 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AH2-061 | Possum Point 230 kV II |  | VA | Prince William | Active | Dominion | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/23/2021 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-062 | TBD 34kV |  | PA | Chester | Active | PECO | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2021 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH2-063 | North Ramsey 23 kV |  | PA | Beaver | Active | DL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/30/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-064 | South Ramsey 23 kV |  | PA | Beaver | Active | DL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2021 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-065 | TBD 69kV |  | MD | Prince George's | Active | DPL | 1.992 | 1.992 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2021 | N/A | N/A |  |  |  | 12/1/2022 |  |  | Y | No
AH2-066 | Jefferson 12.5 kV |  | PA | Jefferson | Active | PENELEC | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/4/2022 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AH2-068 | Pemberville - West End Fostoria 69 kV |  | OH | Wood | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/13/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-069 | JAckson Ferry - Progress Park 138 kV |  | VA | Wythe | Active | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/13/2022 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AH2-070 | Edgewood 12.47 kV II |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2022 | N/A | N/A |  |  |  | 1/27/2023 |  |  | Y | No
AH2-071 | Edgewood 12.47 kV III |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/19/2022 | N/A | N/A |  |  |  | 1/27/2023 |  |  | Y | No
AH2-072 | Damascus 69 kV |  | VA | Washington | Active | AEP | 62.1 | 62.1 | 62.1 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2022 | N/A | N/A |  |  |  | 1/1/2025 |  |  | N | No
AH2-073 | Ashtabula County PV Project 2 |  | OH | Ashtabula | Active | ATSI | 10 | 10 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2022 | N/A | N/A |  |  |  | 9/14/2024 |  |  | N | No
AH2-074 | Ashtabula County PV Project 1 |  | OH | Ashtabula | Active | ATSI | 10 | 10 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/22/2022 | N/A | N/A |  |  |  | 9/14/2024 |  |  | N | No
AH2-075 | Hampton VA 2 |  | VA | City of Hampton | Active | Dominion | 29.12 | 29.12 | 29.12 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/21/2022 | N/A | N/A |  |  |  | 7/1/2024 |  |  | N | No
AH2-076 | Bonneyman - Softshell 138 kV |  | KY | Perry | Active | AEP | 52.5 | 52.5 | 48.17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/26/2022 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AH2-077 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-078 | Dryburg - Chase City 230 kV |  | VA | Charlotte | Active | Dominion | 99.67 | 99.67 | 59.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 1/3/2025 |  |  | N | No
AH2-080 | Brunswick - Gasburg 69 kV |  | VA | Brunswick | Active | Dominion | 52.65 | 52.65 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2022 | N/A | N/A |  |  |  | 1/3/2025 |  |  | N | No
AH2-081 | Bentley Farms 69 kV |  | OH | Fayette | Active | Dayton | 35.5 | 35.5 | 21.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 9/19/2025 |  |  | N | No
AH2-082 | New Holland - Washington Courthouse 69 kV |  | OH | Fayette | Active | Dayton | 33.25 | 33.25 | 19.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 1/3/2025 |  |  | N | No
AH2-083 | Correctional |  | VA | Caroline | Active | Dominion | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/27/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-084 | Sowego |  | VA | Fauquier | Active | Dominion | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-085 | Byron-Wayne 345 kV |  | IL | DeKalb | Active | ComEd | 145.335 | 145.335 | 87.201 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/28/2022 | N/A | N/A |  |  |  | 11/11/2026 |  |  | N | No
AH2-086 | Byron – Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-087 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-088 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-089 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-090 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-091 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-093 | Jasper 69 kV |  | OH | Greene | Active | Dayton | 32 | 32 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-094 | Lakeville 12 kV II |  | PA | Wayne | Active | PPL | 4.95 | 4.95 | 2.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 5/5/2023 |  |  | N | No
AH2-095 | Crawford 13.8 kV |  | PA | Crawford | Active | PENELEC | 3.3 | 3.3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 7/13/2022 |  |  | N | No
AH2-096 | West Cambridge - Airey 69 kV |  | MD | Dorchester | Active | DPL | 19.5 | 19.5 | 8.19 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 5/1/2023 |  |  | N | No
AH2-100 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-101 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-102 | Blaine - Roanoke 138 kV |  | VA | Franklin | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2022 | N/A | N/A |  |  |  | 5/4/2026 |  |  | N | No
AH2-103 | Gans - South Union 138 kV |  | PA | Fayette | Active | APS | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2022 | N/A | N/A |  |  |  | 5/4/2026 |  |  | N | No
AH2-104 | Willis Mts- Farmville 115kV |  | VA | Cumberland | Active | Dominion | 72 | 72 | 39.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2022 | N/A | N/A |  |  |  | 11/1/2024 |  |  | N | No
AH2-105 | Merck 34.5 kV |  | VA | Rockingham | Active | Dominion | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2022 | N/A | N/A |  |  |  | 1/1/2024 |  |  | N | No
AH2-106 | Wellsville 345 kV |  | OH | Columbiana | Active | ATSI | 1210 | 58 | 69 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/4/2022 | N/A | N/A |  |  |  | 2/28/2022 |  |  | N | No
AH2-107 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 69 | 69 | 69 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/12/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-109 | TBD 12.47kV |  | NJ | Unknown | Active | AEC | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/16/2022 | N/A | N/A |  |  |  | 12/1/2022 |  |  | Y | No
AH2-111 | Hannibal 138 kV |  | OH | Monroe | Active | AEP | 505 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/19/2022 | N/A | N/A |  |  |  | 6/30/2022 |  |  | N | No
AH2-112 | Olive - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 250 | 250 | 170 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2022 | N/A | N/A |  |  |  | 2/27/2026 |  |  | N | No
AH2-113 | Dresden – Pontiac Midpoint 345kV |  | IL | Livingston | Active | ComEd | 250 | 250 | 170 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/22/2022 | N/A | N/A |  |  |  | 2/27/2026 |  |  | N | No
AH2-115 | Mansfield - Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-116 | Garman - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-117 | Dorton - Henry Clay 46 kV |  | KY | Pike | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-119 | Morgan Street - Titusville 34.5 kV |  | PA | Crawford | Active | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2022 | N/A | N/A |  |  |  | 12/30/2025 |  |  | N | No
AH2-120 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-121 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 500 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-122 | Nelson-Lee County 345 kV |  | IL | Lee | Active | ComEd | 220 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-123 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 420 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-124 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-125 | Kensington 138 kV |  | KY | N/A | Active | ComEd | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/26/2022 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AH2-126 | Tidd 138 kV |  | OH | Jefferson | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2022 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AH2-127 | Burlington 26 kV |  | NJ | Burlington | Active | PSEG | 20 | 15 | 18 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/25/2022 | N/A | N/A |  |  |  | 9/19/2023 |  |  | N | No
AH2-128 | Stone Solar 34.5 kV |  | PA | Clarion | Active | APS | 8 | 8 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AH2-129 | Piney - Timblin 115 kV |  | PA | Armstrong | Active | APS | 52 | 36 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AH2-130 | Clark Co - Spencer Road 138 kV |  | KY | N/A | Active | EKPC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-131 | Bridgeport 230kV |  | NJ | Gloucester | Active | AEC | 225 | 0 | 103.7 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 3/1/2025 |  |  | N | No
AH2-132 | Chambers 230kV |  | NJ | Salem | Active | AEC | 240 | 0 | 117 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH2-133 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AH2-135 | Harwood- McAdoo 69 kV |  | PA | Luzerne | Active | PPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/19/2025 |  |  | N | No
AH2-136 | Dunnsville 345 kV |  | VA | Essex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-137 | Monroe - Coolwell 12.47 kV |  | VA | Amherst | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-138 | Arrington Circuit 12.47 kV |  | VA | Nelson | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-144 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-145 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 52.3 | 52.3 | 52.3 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-146 | Adams - Seaman 69 kV |  | OH | Adams | Active | AEP | 87.2 | 87.2 | 52.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/30/2027 |  |  | N | No
AH2-148 | East Lima - Marysville 345 kV |  | OH | Union | Active | AEP | 152 | 152 | 143.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 2/25/2027 |  |  | N | No
AH2-149 | Stinger - Valley 138 kV |  | MI | Van Buren | Active | AEP | 150 | 150 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/29/2026 |  |  | N | No
AH2-150 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 800 | 0 | 320 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-151 | SedgeHill - Person 230kV |  | VA | Halifax | Active | Dominion | 195 | 35 | 21 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-152 | Effort Mountain-Gilbert 138 kV IV |  | PA | Monroe | Active | PPL | 90 | 44.8 | 26.88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-153 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 180 | 180 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-154 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 118 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-155 | Lyons-Allen Jct 138 kV |  | OH | Fulton | Active | ATSI | 95 | 95 | 57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-156 | Buckeye P-Wakeman 69 kV |  | OH | Huron | Active | ATSI | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-157 | Hooversville-Somerset 23 kV |  | PA | Somerset | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-158 | Somerset-Hooversville 115 kV |  | PA | Somerset | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-159 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-160 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 69 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-161 | Prospect 25 kV |  | PA | Butler | Active | APS | 18.8 | 18.8 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AH2-162 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Active | BGE | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-163 | Kittanning - Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 49.8 | 19.8 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-164 | Chatfield 69 kV |  | OH | Crawford | Active | AEP | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AH2-165 | Fayette - Lyons 138 kV |  | OH | Fulton | Active | ATSI | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-166 | Lyons 138 kV |  | OH | Fulton | Active | ATSI | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-168 | Beatty - MT Hope 345 kV |  | OH | Madison | Active | ATSI | 185 | 185 | 111 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-169 | Thornville - Pleasantville 69 kV |  | OH | Perry | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-170 | Byron 345 |  | IL | Will | Active | ComEd | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-171 | Davis Creek 345 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-172 | Wilton 345 kV |  | IL | Will | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-173 | Maryland 138 kV |  | IL | Ogle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-181 | PA-Schwoyer 13.2 kV |  | PA | Mercer | Active | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 6/21/2024 |  |  | Y | No
AH2-187 | Burma – Seminole Road Junction 25 kV |  | PA | Clarion | Active | APS | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AH2-189 | Fearnley Solar 34.5 kV |  | PA | Susquehanna | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-190 | Higgins Run Solar |  | PA | Somerset | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-191 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-192 | Wharton 138 kV |  | WV | N/A | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-193 | Pax Branch 138 kV |  | WV | N/A | Active | AEP | 70 | 70 | 46 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-194 | Bergen 138kV |  | NJ | Bergen | Active | PSEG | 736 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 4/30/2026 |  |  | N | No
AH2-195 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 10/29/2027 |  |  | N | No
AH2-197 | North Huntley - Pleasant Valley 138 kV |  | IL | McHenry | Active | ComEd | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-198 | Mt. Hermon 69 kV |  | MD | Wicomico | Active | DPL | 74.715 | 74.715 | 53.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH2-199 | Shorewood 138 kV |  | IL | Will | Active | ComEd | 51.7 | 51.7 | 36.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH2-204 | Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-205 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/31/2026 |  |  | N | No
AH2-206 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/31/2026 |  |  | N | No
AH2-207 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 85 | 85 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-209 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-210 | Stillwell - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 78 | 78 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-211 | Olive - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-212 | Cardington 138 kV |  | OH | Madison | Active | ATSI | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-213 | London 138 kV |  | IN | Randolph | Active | ATSI | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-215 | Midway 138 kV |  | OH | Henry | Active | ATSI | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-217 | Cardington 138 kV II |  | OH | Morrow | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-218 | London 138 kV II |  | OH | Morrow | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-220 | Midway 138 kV |  | OH | Henry | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-222 | Millersburg 69 kV |  | KY | N/A | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-223 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-224 | Millersburg 69 kV |  | KY | N/A | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-226 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 175 | 175 | 175 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-227 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/27/2026 |  |  | N | No
AH2-228 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-229 | Bedforth North 115 kV |  | PA | Bedford | Active | PENELEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-230 | Gardners 115 kV |  | PA | Adams | Active | ME | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-233 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-234 | W Dekalb 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-235 | Orrtana 115 kV |  | PA | Adams | Active | ME | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-236 | McDowell 138 kV |  | PA | Mercer | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-237 | Adams 138 kV |  | IN | Wells | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-238 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-239 | Trumbull138 kV |  | OH | Trumbull | Active | ATSI | 49 | 49 | 46.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2027 |  |  | N | No
AH2-241 | Loudoun 115kV |  | VA | City of Chesapeake | Active | Dominion | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AH2-242 | Crown - New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 45 | 45 | 40.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/8/2027 |  |  | N | No
AH2-243 | South Summitville 69 kV |  | IN | Madison | Active | AEP | 43 | 43 | 25.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 10/27/2028 |  |  | N | No
AH2-244 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/29/2023 |  |  | N | No
AH2-245 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/29/2023 |  |  | N | No
AH2-246 | Polyester S/S 230kV |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-247 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 158.2836 | 83.2836 | 14.6579 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-248 | Carrolltown 46 kV |  | PA | Cambria | Active | PENELEC | 113.2592 | 83.2592 | 14.6536 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-249 | Busseyville 138 kV |  | KY | Lawrence | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/22/2027 |  |  | N | No
AH2-250 | TBD 13.2 kV |  | PA | Bucks | Active | PECO | 9.25 | 9.25 | 3.885 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 2/28/2024 |  |  | N | No
AH2-252 | Middleburg 12 kV |  | N/A | N/A | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/21/2024 |  |  | Y | No
AH2-253 | Beaver Valley - Crescent 138 kV |  | PA | Beaver | Active | DL | 70 | 70 | 65 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 11/25/2025 |  |  | N | No
AH2-256 | Wheelabrator Frackville-Gilberton 69 kV II |  | PA | Schuylkill | Active | PPL | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-257 | Dequine - Eugene 345 kV |  | IN | Vermillion | Active | AEP | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/29/2024 |  |  | N | No
AH2-258 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | 172 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/27/2024 |  |  | N | No
AH2-259 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | 172 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 9/27/2024 |  |  | N | No
AH2-260 | Garrett - Albright 138 kV |  | WV | Preston | Active | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH2-261 | Garrett - Albright 138 kV |  | WV | Preston | Active | APS | 98 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AH2-262 | Catoctin-Carroll 138 kV |  | MD | Frederick | Active | APS | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-263 | Marion Co - Marion Co industrial 161 kV |  | KY | Marion | Active | EKPC | 63.6 | 25.8 | 15.48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-264 | Logtown - North Delphos 138 kV |  | OH | Van Wert | Active | AEP | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-265 | Oak Grove - Hawkins Gate 230kV |  | MD | Charles | Active | PEPCO | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-266 | Hughesville-Cedarville 69kV |  | MD | Charles | Active | SMECO | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-267 | Modera - BioEnergy Tap 115 kV |  | PA | Clearfield | Active | PENELEC | 100 | 100 | 85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH2-268 | Sapony 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 37 | 37 | 33.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AH2-269 | Lakewood 230 kV |  | NJ | Ocean | Active | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AH2-269A | Burches Hill-Chalk Point 500kV |  | MD | Prince George's | Active | PEPCO | 845 | 45 | 45 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 11/2/2026 |  |  | N | No
AH2-270 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 300 | 300 | 51 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-271 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-272 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-273 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-274 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-275 | Carrollton Solar 138 kV |  | OH | Carroll | Active | ATSI | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/3/2023 |  |  | N | No
AH2-276 | Second Fork 69 kV |  | KY | Pike | Active | AEP | 40 | 40 | 28 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-277 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-278 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-279 | Whiteley 138 kV |  | PA | Greene | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/10/2024 |  |  | N | No
AH2-281 | Trego 34.5 kV |  | VA | Greensville | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/30/2024 |  |  | N | No
AH2-284 | Adams 138 kV |  | OH | Adams | Active | AEP | 49.9 | 49.9 | 49.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-288 | Napoleon Muni 138 kV |  | OH | Henry | Active | AMPT | 206 | 0 | 82.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-289 | East Fayette 138 kV II |  | OH | Fulton | Active | ATSI | 199 | 0 | 79.6 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AH2-290 | Sandwich 138 kV |  | IL | DeKalb | Active | ComEd | 86 | 0 | 34.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-291 | Rawlings-Clover 500kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AH2-292 | Bear Rock 230 kV |  | PA | Cambria | Active | PENELEC | 76.95 | 76.95 | 13.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-294 | Mazon Blue - Lasalle 138 kV |  | IL | Grundy | Active | ComEd | 150 | 40 | 29.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AH2-295 | Emerald 25 kV |  | PA | Greene | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 9/15/2025 |  |  | N | No
AH2-316 | Somerset 23 kV |  | PA | Somerset | Active | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-317 | Fredericksburg - North Lebanon 13.2 kV |  | PA | Lebanon | Active | ME | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-318 | Corry East 34.5 kV |  | PA | Warren | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-319 | Milan 34.5 kV |  | PA | Bradford | Active | PENELEC | 7.5 | 7.5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-320 | Revloc 34.5 kV |  | PA | Cambria | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-321 | Cooper 34.5 kV |  | PA | York | Active | ME | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/29/2024 |  |  | N | No
AH2-322 | East Danville-Smith Mountain 138 kV |  | VA | Pittsylvania | Active | AEP | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-330 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AH2-331 | North Delphos - Logtown 138 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/31/2027 |  |  | N | No
AH2-332 | Talbert 230kV |  | MD | Prince George's | Active | PEPCO | 115 | 115 | 115 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-333 | Orchard 230kV |  | NJ | Salem | Active | AEC | 415 | 415 | 415 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-334 | New Freedom 230 kV |  | NJ | Camden | Active | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-335 | Roundtop 115 kV |  | PA | York | Active | ME | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-337 | Talbot 69 kV |  | MD | Worcester | Active | DPL | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 2/27/2026 |  |  | N | No
AH2-338 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-339 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 160 | 0 | 64 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-340 | Toulon 138kV |  | IL | Stark | Active | ComEd | 350 | 350 | 210 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-341 | Toulon 138 kV |  | IL | Stark | Active | ComEd | 350 | 0 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-342 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 280 | 280 | 168 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-343 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 280 | 0 | 112 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-344 | La Rue 138 kV |  | OH | Marion | Active | AEP | 94.5 | 45 | 30.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-345 | Wellington 138 kV |  | OH | Lorain | Active | ATSI | 120 | 120 | 80.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-346 | East Arlington 69 kV |  | OH | Hancock | Active | AEP | 47.5 | 47.5 | 31.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-347 | Northern St. Joseph 138 kV |  | IN | St. Joseph | Active | AEP | 200 | 200 | 164 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/7/2025 |  |  | N | No
AH2-348 | Jefferson - Rockport 765 kV |  | IN | Washington | Active | AEP | 700 | 700 | 420 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-349 | Sedge Hill- Person 230kV |  | VA | Halifax | Active | Dominion | 142 | 142 | 85.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-350 | Cartersville 230kV |  | VA | Cumberland | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-351 | Jefferson - Hanging Rock 765 kV |  | KY | N/A | Active | AEP | 1000 | 1000 | 600 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-352 | Fall Creek 345 kV |  | IN | N/A | Active | AEP | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-353 | Jefferson - Hanging Rock 765 kV |  | KY | N/A | Active | AEP | 1000 | 1000 | 600 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-363 | Davis Creek - Bloom 345 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/31/2027 |  |  | N | No
AH2-365 | Easton - Steele 138 kV IV |  | MD | Talbot | Active | DPL | 79 | 0 | 10.787 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AH2-369 | Nuttall 138 kV |  | WV | Fayette | Active | AEP | 200 | 0 | 16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AH2-370 | Church - Oil City 138 kV III |  | MD | Caroline | Active | DPL | 112 | 0 | 17.816 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 11/15/2023 |  |  | N | No
AH2-371 | Jay 138 kV |  | IN | Jay | Active | AEP | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-372 | Corbin – Cresent Ridge 138kV |  | IL | Stephenson | Active | ComEd | 302 | 52 | 52 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AH2-373 | Blossom Trail 138 kV |  | MI | Berrien | Active | AEP | 180 | 180 | 132 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AH2-374 | Milliron - Brookside 138 kV II |  | OH | Richland | Active | ATSI | 252.31 | 84 | 84 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2027 |  |  | N | No
AH2-375 | Lena- Landcaster 138kV |  | IL | Stephenson | Active | ComEd | 318 | 106 | 106 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AH2-376 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 365.1 | 153 | 153 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AH2-377 | Pontiac Midpoint – Dresden 345 kV |  | IL | Grundy | Active | ComEd | 450 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AH2-378 | Appomattox ESC |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-378A | Monroe 138kV |  | NJ | Gloucester | Active | AEC | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-379 | Sign Post - Stockton 69 kV |  | MD | Worcester | Active | DPL | 28.3 | 28.3 | 16.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-380 | Matteson - East Frankfort 138 kV |  | IL | Cook | Active | ComEd | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 3/1/2026 |  |  | N | No
AH2-382 | Wythe – Mount Airy 138 kV |  | VA | Wythe | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AH2-383 | Goddard - Flemingsburg 138 kV |  | KY | Fleming | Active | EKPC | 70 | 70 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/10/2027 |  |  | N | No
AH2-384 | Everetts 34.5kV |  | NC | Martin | Active | Dominion | 25 | 10 | 7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-385 | Chinquapin-Everetts 230kV |  | NC | Pitt | Active | Dominion | 80 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-386 | North Franklin 138 kV |  | WV | Pendleton | Active | APS | 191.5 | 191.5 | 28.15 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/30/2027 |  |  | N | No
AH2-387 | Long Carolyn PV 34.5 kV |  | PA | Indiana | Active | PENELEC | 9.99 | 9.99 | 5.99 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-388 | Long Carolyn 34.5 kV |  | PA | Indiana | Active | PENELEC | 9.99 | 0 | 3.85 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-389 | Devlin 69 kV |  | PA | Lawrence | Active | ATSI | 6 | 6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-390 | Devlin Storage 69 kV |  | PA | Lawrence | Active | ATSI | 6 | 0 | 2.31 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-391 | Pomerico 69 kV |  | PA | Lawrence | Active | ATSI | 7 | 7 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-392 | Pomerico 69 kV II |  | PA | Lawrence | Active | ATSI | 7 | 0 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-393 | Nowacoski 34.5 kV |  | PA | Bradford | Active | PENELEC | 8 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-394 | Walters Karl 69 kV |  | PA | Lawrence | Active | ATSI | 6.3 | 6.3 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-395 | Walters Karl 69 kV II |  | PA | Lawrence | Active | ATSI | 6.3 | 0 | 2.31 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-396 | Nowacoski 34.5 kV II |  | PA | Bradford | Active | PENELEC | 8 | 0 | 3.08 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/29/2023 |  |  | N | No
AH2-397 | Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-398 | Four Rivers- St. Johns 230kV |  | VA | Caroline | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-399 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-400 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AH2-401 | Dubois 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 7/12/2024 |  |  | N | No
AH2-402 | Philipsburg 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 9/13/2024 |  |  | N | No
AH2-403 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 148.2836 | 83.2836 | 14.6579 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AH2-404 | East Danville - Banister 138kV |  | VA | Pittsylvania | Active | AEP | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-405 | McConnellsburg-Guilford 138 kV |  | PA | Franklin | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AH2-408 | Fostoria - Lemoyne 138 kV |  | OH | Wood | Active | ATSI | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-409 | Fostoria - Lemoyne 138 kV II |  | OH | Wood | Active | ATSI | 80 | 30.1 | 18.06 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-410 | New Castle 69 kV |  | KY | N/A | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-411 | New Castle 69 kV |  | KY | N/A | Active | EKPC | 50 | 30 | 18 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AH2-412 | TBD 69kV |  | NJ | Cumberland | Active | AEC | 7.35 | 7.35 | 3.09 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AH2-413 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 365 | 365 | 339 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-414 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 689 | 350 | 350 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-415 | Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-416 | Pontiac Midpoint 345 |  | IL | Livingston | Active | ComEd | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AH2-418 | Riverside - Pokagon 138 kV |  | MI | Berrien | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-419 | Reynolds - Olive 345 kV |  | IN | LaPorte | Active | AEP | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AH2-420 | Morgan Street 115 kV |  | PA | Crawford | Active | PENELEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-421 | Dresden 138kV |  | IL | Grundy | Active | ComEd | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-422 | Yukon 138 kV |  | PA | Westmoreland | Active | APS | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AH2-423 | Sollers 230kV |  | MD | Calvert | Active | SMECO | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-001 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 2100 | 2100 | 369.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2022 | N/A | N/A |  |  |  | 10/10/2029 |  |  | N | No
AI1-003 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 170 | 170 | 34 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-006 | Monterville - Pickens 138 kV |  | WV | Randolph | Active | APS | 103 | 103 | 18.128 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-009 | Pendleton - Tanners Creek 138 kV |  | IN | Rush | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-011 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 131 | 46 | 27.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-012 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 131 | 0 | 18.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-013 | Chickahominy 230 kV |  | VA | Charles City | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-016 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 260 | 0 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-017 | Septa 500 kV |  | VA | Surry | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-018 | Spotslvania 500 kV |  | VA | Spotsylvania | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-019 | Laurel - Cooper 161 kV |  | KY | N/A | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-020 | TBD |  | N/A | N/A | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2022 | N/A | N/A |  |  |  | 3/31/2023 |  |  | Y | No
AI1-021 | Hillandale 115kV |  | VA | Pittsylvania | Active | Dominion | 105 | 105 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI1-022 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI1-023 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI1-024 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI1-026 | Ringtown 12 kV |  | N/A | N/A | Active | PPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/2/2022 | N/A | N/A |  |  |  | 11/1/2023 |  |  | Y | No
AI1-030 | Corry East - Garland Jct 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/1/2022 | N/A | N/A |  |  |  | 12/13/2024 |  |  | N | No
AI1-033 | Somerville 26 kV |  | NJ | Somerset | Active | PSEG | 8 | 8 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/5/2022 | N/A | N/A |  |  |  | 12/22/2026 |  |  | N | No
AI1-038 | Harwood-Siegfried 230kV II |  | PA | Carbon | Active | PPL | 95.76 | 95.76 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/12/2022 | N/A | N/A |  |  |  | 3/31/2024 |  |  | N | No
AI1-039 | Moshannon-Milesburg 230 kV VIII |  | PA | Clearfield | Active | PENELEC | 200 | 200 | 160 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/19/2022 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI1-040 | Ridgway - Elko 138 kV |  | PA | Elk | Active | APS | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/29/2022 | N/A | N/A |  |  |  | 3/31/2025 |  |  | N | No
AI1-046 | Smithburg 500 kV |  | NJ | Monmouth | Active | JCPL | 1600 | 1600 | 281.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/25/2022 | N/A | N/A |  |  |  | 12/31/2031 |  |  | N | No
AI1-053 | McDowell - Campbell 69 kV |  | PA | Mercer | Active | ATSI | 6.6 | 6.6 | 0 |  | Energy | Generation Interconnection | Diesel; Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/10/2022 | N/A | N/A |  |  |  | 12/1/2022 |  |  | N | No
AI1-074 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 120 | 120 | 96 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/5/2022 | N/A | N/A |  |  |  | 12/15/2027 |  |  | N | No
AI1-075 | Lee Co. EC 345kV |  | IL | Lee | Active | ComEd | 239.8 | 0 | 11.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/6/2022 | N/A | N/A |  |  |  | 9/1/2022 |  |  | N | No
AI1-076 | TBD 13.2 kV |  | PA | Delaware | Active | PECO | 19.8 | 19.8 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/11/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-077 | Marengo 34.5 kV Line |  | IL | McHenry | Active | ComEd | 15.75 | 15.75 | 6.62 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/15/2022 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AI1-078 | New Carlisle - Bosserman 138 kV |  | IN | LaPorte | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-079 | Summer Shade - West Columbia 69 kV |  | KY | Adair | Active | EKPC | 64.8 | 64.8 | 64.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-080 | Albion - Kendallville - 138 kV |  | IN | LaPorte | Active | AEP | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-081 | Jay - DeSoto 138 kV |  | IN | Jay | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/26/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-082 | Laurel 25 kV |  | PA | Westmoreland | Active | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/28/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI1-084 | Fawkes - West Berea 138kV |  | KY | Madison | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI1-085 | Tanners Creek - DeSoto 345 kV |  | IN | Wayne | Active | AEP | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/15/2030 |  |  | N | No
AI1-086 | Trego - Emporia 115 kV |  | VA | Greensville | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-087 | Disputanta - Bakers Pond 115 kV |  | VA | Prince George | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-088 | Poe- New Bohemia 115kV |  | VA | Prince George | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-089 | Myrtle - Oak Ridge 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/29/2022 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI1-091 | Bascom 69 kV |  | OH | Seneca | Active | AEP | 49.9 | 49.9 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI1-092 | Collinsville - Springfield Road 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 49.9 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/4/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI1-093 | Westmoreland 34.5 kV |  | PA | Westmoreland | Active | APS | 24 | 24 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/15/2022 | N/A | N/A |  |  |  | 7/1/2026 |  |  | N | No
AI1-094 | Westmoreland 34.5 kV |  | PA | Westmoreland | Active | APS | 24 | 24 | 24 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/16/2022 | N/A | N/A |  |  |  | 7/1/2026 |  |  | N | No
AI1-095 | Branchron - Keisters 25 kV |  | PA | Butler | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/19/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI1-096 | Pemberton 138 kV |  | WV | N/A | Active | AEP | 42 | 42 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/23/2022 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI1-097 | Newcomerstown 12.47 kV |  | OH | Tuscarawas | Active | AEP | 7 | 7 | 6.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/26/2022 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No
AI1-098 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 40 | 40 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 10/1/2026 |  |  | N | No
AI1-100 | Somerton - Norton 138 kV |  | OH | Belmont | Active | AEP | 150 | 150 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-101 | Pocono-Acahela 230 kV |  | PA | Lackawanna | Active | PPL | 100 | 100 | 63.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 9/1/2029 |  |  | N | No
AI1-102 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 9/1/2029 |  |  | N | No
AI1-103 | Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 200 | 200 | 127.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-104 | Timber Road 138 kV |  | OH | Paulding | Active | AEP | 135 | 135 | 86.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 9/1/2029 |  |  | N | No
AI1-105 | White Haven 2 Tap-White Haven DC 69 kV |  | PA | Luzerne | Active | PPL | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/30/2022 | N/A | N/A |  |  |  | 12/19/2026 |  |  | N | No
AI1-106 | Sinai 13.2 kV |  | VA | Halifax | Active | Dominion | 9.9 | 9.9 | 9.15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2022 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI1-108 | Endless Caverns - Timberville 115 kV |  | VA | Rockingham | Active | Dominion | 38.5 | 38.5 | 33.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI1-109 | Deans 500 kV |  | NJ | Middlesex | Active | PSEG | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-110 | Larrabee 230 kV V |  | NJ | Monmouth | Active | JCPL | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-111 | Werner 230 kV |  | NJ | Middlesex | Active | JCPL | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/1/2022 | N/A | N/A |  |  |  | 12/31/2029 |  |  | N | No
AI1-112 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 8/31/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI1-114 | Revloc 46 kV |  | PA | Cambria | Active | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-115 | Glory 34.5 kV |  | PA | Clearfield | Active | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/2/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-116 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AI1-117 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 9/10/2024 |  |  | N | No
AI1-118 | Pequest river - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 37.6 | 37.6 | 15.792 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-119 | Shorewood 138kV |  | IL | Kendall | Active | ComEd | 28.8 | 28.8 | 18.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/6/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AI1-120 | Pequest River - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 51.6 | 51.6 | 21.672 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-122 | Sparta LF Solar 34.5 kV |  | NJ | Sussex | Active | JCPL | 5.85 | 5.85 | 2.457 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/7/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-123 | Nutbush-Victoria DP 115kV |  | VA | Lunenburg | Active | Dominion | 59 | 59 | 35.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-124 | Nutbush - Victoria DP 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-125 | Mount Eagle 34.5 kV |  | VA | Albemarle | Active | Dominion | 22 | 22 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AI1-126 | Farmville 12.47kV |  | VA | Cumberland | Active | Dominion | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AI1-127 | Dauphin 12 kV |  | PA | Dauphin | Active | PPL | 4.5 | 4.5 | 2.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/9/2024 |  |  | N | No
AI1-128 | Milesburg 12.47 kV |  | PA | Centre | Active | APS | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/9/2024 |  |  | N | No
AI1-129 | Muncy 12 kV II |  | PA | Lycoming | Active | PPL | 4.5 | 4.5 | 2.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 9/9/2024 |  |  | N | No
AI1-130 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/7/2026 |  |  | N | No
AI1-131 | TBD 115 kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/7/2026 |  |  | N | No
AI1-132 | Fredricksburg 69 kV |  | KY | Washington | Active | EKPC | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 4/30/2029 |  |  | N | No
AI1-133 | Hillsboro 69 kV |  | KY | Fleming | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 4/30/2029 |  |  | N | No
AI1-134 | Greentown - Hummel Creek 138 kV |  | IN | Grant | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 4/30/2029 |  |  | N | No
AI1-135 | Perquimans 230 kV |  | NC | Chowan | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/8/2022 | N/A | N/A |  |  |  | 6/30/2026 |  |  | N | No
AI1-137 | Greystone - Portland 230 kV |  | NJ | Warren | Active | JCPL | 155 | 155 | 65.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/29/2025 |  |  | N | No
AI1-139 | Henrietta Township - New Russia Township 69 kV |  | OH | Lorain | Active | ATSI | 14.8 | 14.8 | 6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AI1-140 | Selma Parker - Richmond 138 kV |  | IN | Wayne | Active | AEP | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI1-141 | Blossom - Dowagi TSS 34.5 kV |  | MI | Cass | Active | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI1-143 | Bell Township - Vandergrift 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 4/1/2025 |  |  | N | No
AI1-144 | Gardners 13.2 kV III |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-145 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-146 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 125 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI1-147 | Sandwich 34kV |  | IL | DeKalb | Active | ComEd | 150 | 64 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI1-148 | Davis Creek 138kV |  | IL | Kankakee | Active | ComEd | 164 | 164 | 98.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI1-149 | Pleasant Valley 345 kV |  | IL | McHenry | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI1-150 | Locust - Todd 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-151 | Kyger Creek - Pierce 345 kV |  | OH | Adams | Active | AEP | 231.7 | 53.2 | 31.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-152 | Siegfried - Nazareth 69 kV |  | PA | Northampton | Active | ME | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-153 | North Hershey - Grantville 69 kV |  | PA | Dauphin | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-154 | Goodings Grove 138 kV |  | IL | Will | Active | ComEd | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-155 | Chicago Heights 138kV |  | IL | Cook | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-156 | West Rutland 138 kV |  | IL | Kane | Active | ComEd | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-157 | Pleasant Valley – Crystal Lake 138 kV |  | IL | McHenry | Active | ComEd | 54.4 | 54.4 | 32.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-158 | Pleasant Valley - Crystal Lake 138 kV |  | IL | McHenry | Active | ComEd | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/4/2027 |  |  | N | No
AI1-159 | Mount Sterling - Sideview 69 kV |  | KY | Montgomery | Active | EKPC | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI1-160 | Crawford Solar 2 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI1-161 | Crawford Solar 3 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI1-162 | Saltsburg-Vandergrift 138 kV |  | PA | Armstrong | Active | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 9/15/2026 |  |  | N | No
AI1-165 | Magnolia - Summersville 69 kV |  | KY | Green | Active | EKPC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI1-166 | Granger - Ontwa 138 kV |  | MI | Cass | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI1-167 | Cedarville 138 kV |  | OH | Clermont | Active | DEOK | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI1-168 | Conesville 345 kV |  | OH | Coshocton | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 8/31/2027 |  |  | N | No
AI1-169 | Moyock 230 kV |  | NC | Currituck | Active | Dominion | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Storage; Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 10/15/2026 |  |  | N | No
AI1-170 | Glidden - Sugar Grove 138kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AI1-171 | Garden Plain - Rock Falls 138 kV |  | IL | Whiteside | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 4/30/2028 |  |  | N | No
AI1-172 | Katydid Road - Goodings Grove 345 kV |  | IL | Grundy | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 4/30/2028 |  |  | N | No
AI1-173 | Lena - Freeport 34.5 kV |  | IL | Stephenson | Active | ComEd | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 4/30/2027 |  |  | N | No
AI1-174 | Garden Plain - Rock Falls 138 kV |  | IL | Stephenson | Active | ComEd | 118 | 118 | 94.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 4/30/2028 |  |  | N | No
AI1-175 | Waldo - North Waldo 69 kV |  | OH | Marion | Active | AEP | 19.5 | 19.5 | 16.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-177 | Avon 345 kV II |  | OH | Lorain | Active | ATSI | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI1-178 | Red House DP - Sugar Hill 115 kV |  | VA | Campbell | Active | Dominion | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-179 | Colver Power Project 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-180 | Windsor 69 kV |  | KY | N/A | Active | EKPC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-181 | Grandview 115 kV |  | PA | Venango | Active | PENELEC | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-183 | DuPont - Marlboro 115 kV |  | VA | Richmond | Active | Dominion | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-184 | Greenwood 138 kV |  | VA | Frederick | Active | APS | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-185 | Valley 230 kV |  | VA | Augusta | Active | Dominion | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-186 | Strasburg 138 kV |  | VA | Shenandoah | Active | APS | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-187 | Glen Gardner 230 kV |  | NJ | Hunterdon | Active | JCPL | 280 | 280 | 280 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-188 | Buffalo 115 kV |  | PA | Erie | Active | PENELEC | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-189 | Northeast - Windy Edge 115 kV |  | MD | Baltimore County | Active | BGE | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-190 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI1-191 | Landcaster - Pecatonica 138 kV |  | IL | Stephenson | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI1-192 | Price Hill - Pruntytown 138 kV |  | WV | Marion | Active | APS | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI1-193 | Lincoln 13.2 kV II |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-194 | Orrtanna 13.2 kV III |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-195 | Orrtanna 13.2 kV IV |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-196 | Gates Hill 25 kV |  | PA | Fayette | Active | ME | 9.8 | 9.8 | 7.88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-197 | Gardners 13.2 kV |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-198 | Gardners 13.2 kV II |  | PA | Adams | Active | ME | 7.1 | 7.1 | 5.76 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-199 | South Union 25 kV |  | PA | Fayette | Active | ME | 8.3 | 8.3 | 6.98 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/9/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-200 | Campbell 8.32 kV |  | PA | Lawrence | Active | ME | 5 | 5 | 4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-202 | Greenland Gap 500 kV |  | WV | Grant | Active | APS | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Solar; Storage; Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 10/15/2026 |  |  | N | No
AI1-203 | Clover - Rawling 500 kV |  | VA | Lunenburg | Active | Dominion | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 12/30/2027 |  |  | N | No
AI1-211 | Brandonville - Necessity 138 kV |  | WV | Preston | Active | APS | 68 | 68 | 68 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI1-212 | Homer City - Stolle Road 345 kV |  | PA | Jefferson | Active | PENELEC | 182 | 182 | 182 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-213 | Farmers Valley - Ridgeway 115 kV VI |  | PA | Elk | Active | APS | 174 | 174 | 174 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-214 | Philipsburg 115 kV IV |  | PA | Centre | Active | PENELEC | 160 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-215 | Philipsburg 115 kV V |  | PA | Centre | Active | PENELEC | 180 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-216 | Philipsburg 115 kV VI |  | PA | Centre | Active | PENELEC | 200 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI1-217 | Philipsburg 115 kV VII |  | PA | Centre | Active | PENELEC | 217 | 17 | 17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 9/10/2022 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI2-001 | Remington 115 kV |  | VA | Caroline | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2022 | N/A | N/A |  |  |  | 5/26/2028 |  |  | N | No
AI2-002 | Vanceville 138 kV |  | VA | Washington | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/1/2022 | N/A | N/A |  |  |  | 5/26/2028 |  |  | N | No
AI2-004 | Danieltown – Brunswick 115 kV |  | VA | Brunswick | Active | Dominion | 80 | 80 | 71.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/14/2022 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI2-005 | Bremo 115 kV |  | VA | Fluvanna | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 10/24/2022 | N/A | N/A |  |  |  | 5/26/2028 |  |  | N | No
AI2-006 | Elgin 138kV |  | IL | Kane | Active | ComEd | 484 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/10/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-007 | Rocky Road 138kV |  | IL | Kane | Active | ComEd | 450.8 | 40 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/10/2022 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-010 | Elmont 34.5 kV |  | VA | Hanover | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/23/2022 | N/A | N/A |  |  |  | 12/30/2025 |  |  | N | No
AI2-011 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 100 | 0 | 15 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-012 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 300 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-013 | Grundy - Goose Lake 138 kV |  | IL | Grundy | Active | ComEd | 24.1 | 24.1 | 17.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AI2-014 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 37.9 | 37.9 | 20.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 11/30/2022 | N/A | N/A |  |  |  | 5/29/2026 |  |  | N | No
AI2-015 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/1/2022 | N/A | N/A |  |  |  | 11/30/2025 |  |  | N | No
AI2-017 | PA Centre Borealis 34.5 kV |  | PA | Centre | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-018 | TBD 23 kV |  | PA | Somerset | Active | PENELEC | 4 | 4 | 2.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-019 | TBD 12.47 kV |  | PA | Franklin | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/9/2022 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-020 | Warren County 500 kV |  | VA | Warren | Active | Dominion | 1518 | 19 | 11 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/10/2022 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-022 | East Towanda 230 kV |  | PA | Bradford | Active | PENELEC | 937.5 | 30 | 60 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2022 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-023 | Lake - 270888 345kV |  | IN | Lake | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/20/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-024 | Racine - Ravenswood 69kV |  | OH | Meigs | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-026 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-027 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/22/2022 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-028 | Beatty - Biers Run 345 kV |  | OH | Union | Active | AEP | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/29/2022 | N/A | N/A |  |  |  | 12/20/2026 |  |  | N | No
AI2-029 | Clarksburg - Biers Run 69 kV |  | OH | Union | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 12/31/2022 | N/A | N/A |  |  |  | 12/20/2026 |  |  | N | No
AI2-030 | Poplar Flat Switch - Brown Hill 69 kV |  | OH | Adams | Active | AEP | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/18/2023 | N/A | N/A |  |  |  | 12/20/2024 |  |  | N | No
AI2-031 | Sapnony 34.5kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-032 | Distribution Circuit#324 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-033 | Sapony 34.5kV |  | VA | Sussex | Active | Dominion | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-034 | Distribution circuit#332 35kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/24/2023 | N/A | N/A |  |  |  | 10/31/2024 |  |  | N | No
AI2-035 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-036 | Craigsville-Staunton 115kV |  | VA | Augusta | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-037 | Lauraville-Dunbrooke 115kV |  | VA | King and Queen | Active | Dominion | 142 | 142 | 85 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-038 | St. Johns 115kV |  | VA | Spotsylvania | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/25/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-039 | Poolesville 230kV |  | VA | Surry | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-040 | Orange 115kV |  | VA | Orange | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-041 | South Boston 115kV |  | VA | Halifax | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-042 | Paytes 115kV |  | VA | Louisa | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-043 | Pamplin 34.5kV |  | VA | Northumberland | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 1/31/2023 | N/A | N/A |  |  |  | 4/26/2024 |  |  | N | No
AI2-044 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI2-045 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/1/2023 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI2-052 | Lakewood 230 kV II |  | NJ | Ocean | Active | JCPL | 170 | 70 | 70 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/17/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-053 | New Holland 69 kV |  | OH | Fayette | Active | Dayton | 100 | 100 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-054 | Rock Springs 500 kV |  | MD | Cecil | Active | DPL | 784 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 6/1/2028 |  |  | N | No
AI2-055 | Summit-West Fall 115kV II |  | PA | Blair | Active | PENELEC | 38 | 0 | 6.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 12/10/2010 |  |  | N | No
AI2-056 | Fairview East 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 0 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 2/6/2024 |  |  | N | No
AI2-057 | Venango 34.5 kV |  | PA | Venango | Active | PENELEC | 20 | 0 | 6.58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 2/20/2024 |  |  | N | No
AI2-058 | Clark Summit-Emlenton 34.5 kV |  | PA | Venango | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 1/14/2025 |  |  | N | No
AI2-059 | Wolfs Corners 34.5 kV |  | PA | Clarion | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 1/14/2024 |  |  | N | No
AI2-060 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Active | ComEd | 70 | 0 | 40.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AI2-061 | Bedford North-Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 60 | 0 | 17.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 12/15/2026 |  |  | N | No
AI2-062 | Jack Frost - Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 60 | 0 | 18.34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 5/15/2027 |  |  | N | No
AI2-063 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 280 | 0 | 82.48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 5/15/2027 |  |  | N | No
AI2-064 | Desoto - Keystone 345 kV |  | IN | Blackford | Active | AEP | 245 | 0 | 35.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI2-065 | Varner - Sours 138 kV |  | IN | DeKalb | Active | AEP | 180 | 0 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 6/1/2026 |  |  | N | No
AI2-066 | Marion County 161 kV |  | KY | Marion | Active | EKPC | 96 | 0 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/23/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-067 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 60 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI2-068 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-069 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 10/21/2026 |  |  | N | No
AI2-070 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI2-071 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 3/1/2027 |  |  | N | No
AI2-072 | Steubenville 69 kV |  | OH | Jefferson | Active | AEP | 49.5 | 0 | 27.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 5/15/2024 |  |  | N | No
AI2-073 | Columbia-Sunbury 69 kV |  | PA | Snyder | Active | PPL | 19.8 | 0 | 9.93 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI2-074 | Beatty - Greene 345 kV |  | OH | Madison | Active | AEP | 577 | 0 | 87.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AI2-075 | Face Rock-Kinzer #13 69 kV |  | PA | Lancaster | Active | PPL | 19.8 | 0 | 9.86 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/24/2023 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AI2-076 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 175 | 0 | 56 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 3/15/2023 |  |  | N | No
AI2-077 | Kanakee 138 kV |  | IL | Kankakee | Active | ComEd | 175 | 0 | 56 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 3/16/2023 |  |  | N | No
AI2-078 | Myrtle-Windsor 115 kV |  | VA | Isle of Wight | Active | Dominion | 91 | 0 | 52.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-079 | Harmony Village-Shackleford 115 kV |  | VA | Fauquier | Active | Dominion | 70 | 0 | 40.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-080 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 134 | 0 | 73.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-081 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 500 | 0 | 271 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-082 | Cardington-Liberty 69 kV IV |  | OH | Morrow | Active | ATSI | 101 | 0 | 34.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-084 | Galion 138 kV VI |  | OH | Morrow | Active | ATSI | 244 | 0 | 78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-085 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Active | OVEC | 120 | 0 | 65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-086 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 80 | 0 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-087 | Gold-Sabinsville 115kV III |  | PA | Potter | Active | PENELEC | 90 | 0 | 42.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/27/2023 | N/A | N/A |  |  |  | 3/3/2023 |  |  | N | No
AI2-088 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 412.5 | 0 | 229.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-089 | Cedar Creek 138 kV |  | DE | New Castle | Active | DPL | 114.3 | 0 | 71 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 11/15/2024 |  |  | N | No
AI2-090 | Harrington 69 kV |  | DE | N/A | Active | DPL | 50 | 0 | 31 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2025 |  |  | N | No
AI2-091 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 49.2 | 0 | 22.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-092 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 75.9 | 0 | 40.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-093 | Olive-DeQuine 345kV |  | IN | White | Active | AEP | 202 | 0 | 106.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-094 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 104 | 0 | 53.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-095 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 50.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-096 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 54 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-097 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 45.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-098 | Meadow Lake 345kV |  | IN | White | Active | AEP | 200 | 0 | 107 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-099 | Powerton-Goodings Grove 345kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 102 | 0 | 49.3 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-100 | Powerton - Dresden 345kv (CIR Increase) |  | IL | Livingston | Active | ComEd | 198 | 0 | 96 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-101 | Haviland - Milan 138kV |  | OH | Paulding | Active | AEP | 99 | 0 | 42.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-102 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 101 | 0 | 46.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-103 | Desoto-Tanners Creek 345kV |  | IN | Randolph | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-104 | Blue Mound I |  | IL | McLean | Active | ComEd | 198 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-105 | Desoto-Tanners Creek #1 345kV |  | IN | Randolph | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-106 | Pontiac MidPoint-Brokaw 345kV |  | IL | Livingston | Active | ComEd | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-107 | Ada-Dunkirk 69kV |  | OH | Hardin | Active | AEP | 66 | 0 | 31.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-109 | Madoc - Delaware 138 kV |  | IN | Randolph | Active | AEP | 150 | 0 | 69 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-110 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 100 | 0 | 46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2023 |  |  | N | No
AI2-111 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2025 |  |  | N | No
AI2-112 | Bluff Point-Randolph 138 kV |  | IN | Randolph | Active | AEP | 100 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-113 | Old Church 230 kV |  | VA | Hanover | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 9/18/2029 |  |  | N | No
AI2-114 | Verona - Weyers Cave 115 kV |  | VA | Augusta | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/1/2029 |  |  | N | No
AI2-115 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-116 | Allen 345kV |  | IN | Allen | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-117 | Payne 69 kV |  | OH | Paulding | Active | AEP | 49.9 | 0 | 11.976 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/28/2023 |  |  | N | No
AI2-118 | Continental 69 kV |  | OH | Putnam | Active | AEP | 49.9 | 0 | 11.976 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/28/2023 |  |  | N | No
AI2-119 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/28/2021 |  |  | N | No
AI2-120 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 125 | 0 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2027 |  |  | N | No
AI2-121 | Hector 115 kV |  | PA | Potter | Active | PENELEC | 50 | 0 | 19.95 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-122 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Active | ComEd | 130 | 0 | 66.95 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-123 | Goddard - Plumville 138 kV |  | KY | Fleming | Active | EKPC | 120 | 0 | 35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-124 | Goddard 138 kV |  | KY | Fleming | Active | EKPC | 200 | 0 | 23.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-125 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 96 | 0 | 32.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-126 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 54 | 0 | 16.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-127 | Cynthiana Tie - Headquarters 69 kV |  | KY | Harrison | Active | EKPC | 70 | 0 | 20.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AI2-128 | Cardiff 230 kV |  | NJ | Atlantic | Active | AEC | 1509.6 | 0 | 1204.52 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/30/2027 |  |  | N | No
AI2-129 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 2250 | 0 | 1675.59 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-130 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 1300 | 0 | 1037.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-131 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 882 | 0 | 703.75 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-132 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 445.2 | 0 | 355.02 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-133 | Kincaid-Pana 345kV |  | IL | Christian | Active | ComEd | 260 | 0 | 84.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 10/31/2026 |  |  | N | No
AI2-134 | Pontiac Midpoint 345 kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-135 | McLean 345 kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-136 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 0 | 47.98 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-137 | Stockton 138 kV |  | VA | Henry | Active | AEP | 90 | 0 | 21.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-138 | Marysville 345kV |  | OH | Union | Active | AEP | 175 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/26/2023 |  |  | N | No
AI2-139 | Marysville 345kV |  | OH | Union | Active | AEP | 225 | 0 | 54 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-141 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 75 | 0 | 18.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 5/31/2023 |  |  | N | No
AI2-143 | Clubhouse-Sappony 230 kV |  | VA | Sussex | Active | Dominion | 149 | 0 | 37.65 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-144 | Mottville 138 kV |  | MI | St. Joseph | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-145 | Claytor Lake - Edgemont 138 kV |  | VA | Montgomery | Active | AEP | 126.65 | 0 | 30.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-146 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 348.5 | 0 | 67.08 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-147 | Dequine - Eugene 345 kV |  | IN | Fountain | Active | AEP | 200 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-148 | Mississinewa- Gaston 138 kV |  | IN | Grant | Active | AEP | 160 | 0 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-149 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 280 | 0 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/24/2023 |  |  | N | No
AI2-150 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 185 | 0 | 44.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-151 | AC1-053 Tap 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 600 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-152 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 120 | 0 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-153 | Louisa-South Anna 230 kV |  | VA | Louisa | Active | Dominion | 127 | 0 | 31.95 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-154 | Moshannon-Milesburg 230 kV IX |  | PA | Centre | Active | APS | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-155 | Baker 138 kV II |  | WV | Hardy | Active | APS | 80 | 0 | 29.84 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-156 | East Springfield-London 138 kV III |  | OH | Clark | Active | ATSI | 234 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-157 | Elk 138 kV |  | OH | Vinton | Active | AEP | 125 | 0 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-159 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 232 | 0 | 43.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI2-160 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2020 |  |  | N | No
AI2-161 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-162 | Meridian - Twin Branch 345 kV |  | IN | Whitley | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-163 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Active | ComEd | 200 | 0 | 68.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-164 | Fostoria Central - Lemoyn 345 kV |  | OH | Wood | Active | AEP | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-165 | Clinton - Stuart 345 kV |  | OH | Clinton | Active | Dayton | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-166 | Lanesville-Brokaw |  | IL | Logan | Active | ComEd | 200 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/15/2025 |  |  | N | No
AI2-167 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 400 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-168 | Magley 138 kV |  | IN | Adams | Active | AEP | 135 | 0 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-169 | Brody 138 kV |  | MI | Cass | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-170 | Delaware - Van Buren 138 kV |  | IN | Delaware | Active | AEP | 163 | 0 | 39.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-171 | Cole Road 345 kV |  | OH | Franklin | Active | AEP | 310 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-172 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 205 | 0 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2022 |  |  | N | No
AI2-173 | West Newton-Lynn 138 kV |  | OH | Hardin | Active | AEP | 110 | 0 | 26.43 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-174 | Kenzie Creek - Colby 138 kV |  | MI | Cass | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/25/2023 |  |  | N | No
AI2-175 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 80 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-176 | Todd 69 kV |  | MD | Dorchester | Active | DPL | 50 | 0 | 14.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-177 | Todd 25 kV |  | MD | Dorchester | Active | DPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 7/31/2021 |  |  | N | No
AI2-178 | LaSalle 138 kV |  | IL | Lasalle | Active | ComEd | 105.6 | 0 | 36.51 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 3/17/2023 |  |  | N | No
AI2-179 | Brokaw-Pontiac 345kV |  | IL | McLean | Active | ComEd | 250 | 0 | 97.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 3/17/2023 |  |  | N | No
AI2-180 | LaSalle 138kV |  | IL | Lasalle | Active | ComEd | 191 | 0 | 6.16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AI2-181 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 170 | 0 | 27.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AI2-182 | Jennings-Hazelton 138kV II |  | WV | Preston | Active | APS | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 2/28/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-183 | Spotsylvania 500kV |  | VA | Spotsylvania | Active | Dominion | 485 | 0 | 123.75 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-184 | Whitely 138 kV |  | PA | Greene | Active | APS | 30 | 0 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AI2-185 | Franklin 138 kV |  | PA | Greene | Active | APS | 150 | 0 | 41 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AI2-186 | Franklin 138 kV |  | PA | Greene | Active | APS | 74 | 0 | 20.25 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 9/10/2023 |  |  | N | No
AI2-187 | Mt. Storm 500kV |  | WV | Grant | Active | Dominion | 800 | 0 | 445 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI2-188 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 425 | 0 | 246.25 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2028 |  |  | N | No
AI2-189 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 125 | 0 | 66.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2028 |  |  | N | No
AI2-190 | Carbondale 138 kV |  | WV | Fayette | Active | AEP | 90 | 0 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 3/15/2028 |  |  | N | No
AI2-191 | Lyons - Moselem Springs 69 kV |  | PA | Berks | Active | ME | 20 | 0 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AI2-192 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 40 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/15/2025 |  |  | N | No
AI2-193 | East Hartford - Murch 69 kV |  | MI | Van Buren | Active | AEP | 85 | 0 | 28.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/30/2024 |  |  | N | No
AI2-194 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 49.9 | 0 | 15.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-195 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 194.11 | 0 | 69.88 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 4/30/2025 |  |  | N | No
AI2-196 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 143.11 | 0 | 51.52 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/30/2025 |  |  | N | No
AI2-197 | Reynolds - Olive 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 12/31/2021 |  |  | N | No
AI2-198 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-199 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-200 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 400 | 0 | 144 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-201 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/1/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-202 | Bennett - Farmingdale 34.5 kV |  | NJ | Monmouth | Active | JCPL | 2 | 0 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/11/2023 |  |  | N | No
AI2-203 | Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 2 | 0 | 1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AI2-204 | Brokaw 345kV (CIR Increase) |  | NJ | Gloucester | Active | PSEG | 3 | 0 | 1.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AI2-205 | Branchville - Sussex 34.5 kV |  | NJ | Sussex | Active | JCPL | 10 | 0 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-206 | Cardiff 12 kV |  | NJ | Atlantic | Active | AEC | 2.6 | 0 | 1.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AI2-207 | Rockawalkin 69 kV |  | MD | Wicomico | Active | DPL | 15 | 0 | 5.35 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/30/2023 |  |  | N | No
AI2-208 | Hawks 12.5 kV |  | NJ | Hunterdon | Active | JCPL | 3 | 0 | 1.55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-209 | Burlington 26kV (CIR Increase) |  | NJ | Burlington | Active | PSEG | 7 | 0 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-210 | Ringoes-US Bronze 34kV |  | NJ | Hunterdon | Active | JCPL | 10 | 0 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-211 | Price 25 kV |  | MD | Queen Anne's | Active | DPL | 6 | 0 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/3/2023 |  |  | N | No
AI2-212 | Manitou-Pleasant Plains 34.5 kV |  | NJ | Ocean | Active | JCPL | 20 | 0 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AI2-213 | Allenwood-Larrabee 2 34.5 kV |  | NJ | Monmouth | Active | JCPL | 7 | 0 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/29/2023 |  |  | N | No
AI2-214 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Active | AEP | 149.5 | 0 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/12/2025 |  |  | N | No
AI2-215 | Pokagon - Corey 69 kV |  | MI | Cass | Active | AEP | 50 | 0 | 18.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/31/2026 |  |  | N | No
AI2-216 | Wurno - Claytor lake 138 kV |  | VA | Pulaski | Active | AEP | 180 | 0 | 77 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/13/2028 |  |  | N | No
AI2-217 | Greene - Beatty 345 kV |  | OH | Madison | Active | AEP | 155 | 0 | 56.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AI2-218 | Galion - South Berwick 345 kV |  | OH | Wyandot | Active | AEP | 120 | 0 | 43.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AI2-219 | Groton 138 kV II |  | OH | Erie | Active | ATSI | 125 | 0 | 45.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/30/2024 |  |  | N | No
AI2-220 | Beaver-Davis Besse 345 kV II |  | OH | Erie | Active | ATSI | 297.66 | 0 | 103.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AI2-221 | Snyder 69 kV II |  | OH | Williams | Active | ATSI | 49 | 0 | 17.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2024 |  |  | N | No
AI2-222 | Chase City-Lunenburg 115kV |  | VA | Lunenburg | Active | Dominion | 130 | 0 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-223 | WinFall-Chowan 230kV |  | NC | Chowan | Active | Dominion | 189 | 0 | 56.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/28/2024 |  |  | N | No
AI2-224 | Central-Chase City 115kV |  | VA | Charlotte | Active | Dominion | 149.5 | 0 | 55 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/30/2025 |  |  | N | No
AI2-225 | Lexington-Low Moor 230kV |  | VA | Botetourt | Active | Dominion | 78.2 | 0 | 32 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/3/2025 |  |  | N | No
AI2-226 | Jug Street 138 kV |  | OH | Licking | Active | AEP | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 8/22/2022 |  |  | N | No
AI2-227 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AI2-228 | Silver Lake 345 |  | IL | McHenry | Active | ComEd | 400 | 0 | 240 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AI2-229 | Silver Lake 138 |  | IL | McHenry | Active | ComEd | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/6/2024 |  |  | N | No
AI2-230 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Active | Dominion | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AI2-231 | Gainesville-Loudoun 230 kV |  | VA | Prince William | Active | Dominion | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/22/2023 |  |  | N | No
AI2-231A | Cloverdale - Burlington Height 138 kV |  | VA | Botetourt | Active | AEP | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/22/2023 |  |  | N | No
AI2-232 | Shady Oaks Road 138 kV |  | IL | Lee | Active | ComEd | 215.4 | 0 | 99.5 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AI2-233 | Eagle Valley 115kV II |  | PA | Centre | Active | PENELEC | 137.6 | 0 | 49.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AI2-234 | Mole Creek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 200 | 0 | 92.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/1/2023 |  |  | N | No
AI2-235 | King's Creek 138 kV |  | MD | Somerset | Active | DPL | 118 | 0 | 62.652 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/2/2023 |  |  | N | No
AI2-236 | Smith Mountain - Candler Mountain 138 kV |  | VA | Campbell | Active | AEP | 80 | 0 | 22.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AI2-237 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 196 | 0 | 69.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI2-238 | College Corner 138 kV |  | OH | Preble | Active | AEP | 98 | 0 | 39.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-239 | Harmony Village-Shackleford 115 kV |  | VA | Gloucester | Active | Dominion | 150 | 0 | 50.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI2-240 | Camden - Crystal 69 kV |  | OH | Preble | Active | Dayton | 69.9 | 0 | 25.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-241 | Congress-Toronto 138 kV II |  | OH | Columbiana | Active | ATSI | 145 | 0 | 55.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-242 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 164 | 0 | 63 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2024 |  |  | N | No
AI2-243 | Ecogrove 138 kV (CIR Increase) |  | IL | Stephenson | Active | ComEd | 199 | 0 | 80.3 |  | Capacity | Generation Interconnection | Solar; Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AI2-244 | Victoria DP-Martin DP 115 kV |  | VA | Nottoway | Active | Dominion | 150 | 0 | 50.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2028 |  |  | N | No
AI2-245 | TSS 968 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 200 | 0 | 55.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2028 |  |  | N | No
AI2-246 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/30/2024 |  |  | N | No
AI2-248 | Schauff Road 138 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 40 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 11/25/2019 |  |  | N | No
AI2-249 | Biers Run-Circleville 138 kV |  | OH | Ross | Active | AEP | 274 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/14/2023 |  |  | N | No
AI2-250 | Greenfield 69 kV |  | OH | Fayette | Active | Dayton | 48 | 0 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/31/2024 |  |  | N | No
AI2-251 | Buckskin 69kV |  | OH | Ross | Active | AEP | 120 | 0 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 7/31/2024 |  |  | N | No
AI2-252 | Hillsboro-Clinton 138kV |  | OH | Ross | Active | AEP | 117 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/30/2024 |  |  | N | No
AI2-253 | Chatfield-Howard 138kV |  | OH | Crawford | Active | AEP | 117 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/1/2025 |  |  | N | No
AI2-254 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 60 | 0 | 15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-255 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-257 | Cordova 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-259 | Greentown 138 kV |  | IN | Howard | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-260 | Keeney - Steele 230 kV |  | MD | Caroline | Active | DPL | 189 | 0 | 82.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/30/2025 |  |  | N | No
AI2-261 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-263 | Nelson 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-264 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2025 |  |  | N | No
AI2-265 | Kincaid 345kV (CIR Increase) |  | IL | Christian | Active | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-266 | R.P.Mone 345 kV |  | OH | Van Wert | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-267 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AI2-269 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 70 | 0 | 32.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-270 | East Lima-Marysville 345kV |  | OH | Hardin | Active | AEP | 150 | 0 | 45 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/25/2023 |  |  | N | No
AI2-271 | Smith Mountain-Bearskin 138 kV |  | VA | Pittsylvania | Active | AEP | 120 | 0 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-272 | Pantago-Five Points 115kV |  | NC | Beaufort | Active | Dominion | 74 | 0 | 32.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/23/2023 |  |  | N | No
AI2-273 | Boykins-Handsome 115kV |  | VA | Southampton | Active | Dominion | 100 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/25/2023 |  |  | N | No
AI2-274 | Powhatan 34.5 kV |  | VA | Powhatan | Active | Dominion | 17 | 0 | 6.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2023 |  |  | N | No
AI2-275 | Garner-Northern Neck 115 kV |  | VA | Pittsylvania | Active | Dominion | 42 | 0 | 5.04 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/24/2023 |  |  | N | No
AI2-277 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 75 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-278 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2027 |  |  | N | No
AI2-279 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 75 | 0 | 43 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-280 | Carson-Wake 500kV |  | VA | Brunswick | Active | Dominion | 1525.5 | 0 | 34 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/24/2023 |  |  | N | No
AI2-281 | Heritage-Carson |  | VA | Greensville | Active | Dominion | 1756 | 0 | 44.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-282 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 11.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-283 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 12.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-284 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 10.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/1/2023 |  |  | N | No
AI2-285 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-286 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 9.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-287 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 18.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-288 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 16.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-289 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 16.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 2/27/2023 |  |  | N | No
AI2-290 | Brookside-Cloverdale 138 kV II |  | OH | Wayne | Active | ATSI | 130 | 0 | 9.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-291 | Edison-Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 150 | 0 | 10.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-292 | Hunterstown-Texas Eastern Tap 115 kV III |  | PA | Adams | Active | ME | 70 | 0 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-293 | Edinboro South-Venango Junction 115 kV IV |  | PA | Crawford | Active | PENELEC | 116.5 | 0 | 8.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-294 | Laurel Mountain 138 kV |  | WV | Randolph | Active | APS | 125 | 0 | 52.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-295 | Cox-Whitakers 115kV |  | NC | Halifax | Active | Dominion | 80 | 0 | 20.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-297 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 70 | 0 | 18.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2028 |  |  | N | No
AI2-299 | Benson-Dunbar 115 kV |  | NC | Edgecombe | Active | Dominion | 100 | 0 | 30.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/11/2020 |  |  | N | No
AI2-300 | Elizabeth City 34.5 kV |  | NC | Pasquotank | Active | Dominion | 20 | 0 | 6.36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 10/18/2021 |  |  | N | No
AI2-301 | Dawson-South Justice 115kV |  | NC | Halifax | Active | Dominion | 140 | 0 | 45.12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 6/30/2025 |  |  | N | No
AI2-302 | Jacksonville Tap - Renaker 138 kV |  | KY | Harrison | Active | EKPC | 100 | 0 | 26.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 8/30/2024 |  |  | N | No
AI2-303 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 49.9 | 0 | 18.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-304 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 100 | 0 | 36.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-305 | Ebersole #2-Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 120 | 0 | 33.64 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-306 | Osterburg - Bedford North 23 kV II |  | PA | Bedford | Active | PENELEC | 12 | 0 | 4.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 7/18/2025 |  |  | N | No
AI2-307 | Colora 230 kV |  | MD | Cecil | Active | DPL | 100.8 | 0 | 60.48 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/10/2026 |  |  | N | No
AI2-308 | Snake Spring-Bedford Area 23 kV |  | PA | Bedford | Active | PENELEC | 12 | 0 | 4.37 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/27/2024 |  |  | N | No
AI2-309 | Marysville-Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 250 | 0 | 90.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 4/15/2025 |  |  | N | No
AI2-310 | Emlenton 34.5 kV II |  | PA | Venango | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/3/2025 |  |  | N | No
AI2-311 | Ringgold 138 kV II |  | MD | Washington | Active | APS | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 1/11/2025 |  |  | N | No
AI2-312 | Clark Summit 34.5 kV II |  | PA | Venango | Active | PENELEC | 15 | 0 | 5.46 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/15/2022 |  |  | N | No
AI2-313 | Ravenswood-Hemlock 69kV |  | OH | Meigs | Active | AEP | 48 | 0 | 17.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2023 |  |  | N | No
AI2-314 | Molecreek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 100 | 0 | 27 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-315 | Mole Creek 345 kV |  | IL | Woodford | Active | ComEd | 300 | 0 | 90 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-316 | Powerton 345 kV (CIR increase) |  | IL | Woodford | Active | ComEd | 50 | 0 | 19 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-317 | Powertn - Goodings Grove 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 350 | 0 | 133 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-318 | White Marsh 34.5 kV |  | VA | Gloucester | Active | Dominion | 19 | 0 | 12.84 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-320 | Edinboro South - Erie South 25 kV |  | PA | Erie | Active | PENELEC | 19.9 | 0 | 5.05 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-321 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 0 | 8.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-322 | Findlay - Midfield 23 kV |  | PA | Allegheny | Active | DL | 4.7 | 0 | 1.18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-323 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 30 | 0 | 7.56 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-324 | Cowansville Junction – Long Run Tap 25 kV |  | PA | Armstrong | Active | APS | 14.7 | 0 | 3.72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-325 | Oyster Creek 230 kV |  | NJ | Ocean | Active | JCPL | 816 | 0 | 178.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-326 | BL England 138 kV |  | NJ | Cape May | Active | AEC | 432 | 0 | 94.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-327 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 55 | 0 | 19.91 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 10/15/2023 |  |  | N | No
AI2-328 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-329 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-330 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 83.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-331 | Hopkins 138 kV |  | WV | N/A | Active | AEP | 180 | 0 | 42.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-332 | Gilboa-Jones Branch 138 kV IV |  | WV | Nicholas | Active | APS | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 6/1/2030 |  |  | N | No
AI2-333 | Johns Creek-Excel 138kV I |  | KY | Pike | Active | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/1/2026 |  |  | N | No
AI2-334 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 0 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/30/2026 |  |  | N | No
AI2-335 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 0 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-336 | Nottingham Switch 138 kV |  | OH | Harrison | Active | AEP | 400 | 0 | 34.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/10/2026 |  |  | N | No
AI2-337 | Broadview-Tangy 138 kV IV |  | OH | Madison | Active | ATSI | 180 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2023 |  |  | N | No
AI2-338 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 154 | 0 | 29.15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-339 | Gilboa-Jones Branch 138 kV V |  | WV | Nicholas | Active | APS | 100 | 0 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-340 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 100 | 0 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-341 | Galion-Roberts South 138 kV III |  | OH | Marion | Active | ATSI | 99.96 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-342 | Excel-Johns Creek 138 kV |  | KY | Pike | Active | AEP | 75 | 0 | 15.38 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 3/31/2027 |  |  | N | No
AI2-343 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 0 | 15.25 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/3/2025 |  |  | N | No
AI2-344 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 100 | 0 | 17 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/1/2024 |  |  | N | No
AI2-345 | Amherst-Riverville138 kV |  | VA | Amherst | Active | AEP | 75 | 0 | 18 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 6/1/2025 |  |  | N | No
AI2-346 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 400 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 9/10/2025 |  |  | N | No
AI2-347 | Van Arsdell-Mercer Industrial 69kV |  | KY | Mercer | Active | EKPC | 95 | 0 | 17 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/1/2026 |  |  | N | No
AI2-348 | Ford - Ceddarville 138 kV |  | OH | Clermont | Active | DEOK | 152.2 | 0 | 17.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-349 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 0 | 11 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 2/28/2029 |  |  | N | No
AI2-350 | Hillsboro - Wye Mills 138 kV |  | MD | Queen Anne's | Active | DPL | 50 | 0 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-353 | Carlos Jct. – Ridgeley 138 kV |  | MD | Allegany | Active | APS | 54.9 | 0 | 16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 4/1/2024 |  |  | N | No
AI2-354 | Williams 138 kV |  | WV | Grant | Active | APS | 147 | 0 | 58.7 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 1/1/2026 |  |  | N | No
AI2-355 | Greenland Gap 500 kV |  | WV | Grant | Active | APS | 300 | 0 | 103.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-356 | Greenland Gap 500 kV II |  | WV | Grant | Active | APS | 471.6 | 0 | 57.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 7/31/2027 |  |  | N | No
AI2-357 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 260 | 0 | 18.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/6/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-358 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 300 | 0 | 70 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/8/2023 | N/A | N/A |  |  |  | 5/1/2028 |  |  | N | No
AI2-359 | Cross School 138 kV |  | WV | Mineral | Active | APS | 53.7 | 0 | 13.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-360 | Elk Garden - Parr Run 138 kV |  | WV | Mineral | Active | APS | 110 | 0 | 45.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-361 | Hooversville - Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 29.4 | 0 | 10.17 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 3/2/2023 |  |  | N | No
AI2-362 | Rockwood - Meyersdale North 115 kV |  | PA | Somerset | Active | PENELEC | 37.8 | 0 | 13 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/3/2023 |  |  | N | No
AI2-364 | Brokaw - Lanesville 345 kV (CIR Increase) |  | IL | Fulton | Active | ComEd | 200 | 0 | 79.91 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/20/2023 |  |  | N | No
AI2-365 | Lake Lynn-Hazelton 138 kV II |  | WV | Preston | Active | APS | 99.6 | 0 | 32.06 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 9/30/2021 |  |  | N | No
AI2-366 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 300 | 0 | 93.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AI2-367 | Sleepy Hollow 138 kV II |  | WV | Jefferson | Active | APS | 125 | 0 | 34 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AI2-368 | TSS 994 345 kV (CIR Increase) |  | IL | Logan | Active | ComEd | 187.5 | 0 | 77.87 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/17/2023 |  |  | N | No
AI2-369 | Apple Grove 138 kV |  | WV | Mason | Active | AEP | 99 | 0 | 29.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 6/30/2023 |  |  | N | No
AI2-370 | Twombley Road 138kV (CIR Increase) |  | IL | Ogle | Active | ComEd | 60 | 0 | 19.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 4/1/2026 |  |  | N | No
AI2-371 | Walnut Grove - Asahi Tap 69 kV |  | KY | McLean | Active | EKPC | 57 | 0 | 17.78 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 9/25/2024 |  |  | N | No
AI2-372 | Hill Topper 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 65 | 0 | 23.56 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/30/2020 |  |  | N | No
AI2-373 | Easton - Steele 138 kV |  | MD | Talbot | Active | DPL | 79 | 0 | 23.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 3/31/2026 |  |  | N | No
AI2-374 | Hope-Blevins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 66 | 0 | 20.59 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/31/2025 |  |  | N | No
AI2-375 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 80 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-376 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 70 | 0 | 21.84 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 3/31/2025 |  |  | N | No
AI2-377 | Maysville 69 kV VI |  | PA | Mercer | Active | ATSI | 50 | 0 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-378 | Merrill Creek 115 kV II |  | NJ | Warren | Active | JCPL | 70 | 0 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-379 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 78.38 | 0 | 24.51 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-380 | Altoona-Raystown 230 kV III |  | PA | Blair | Active | PENELEC | 80 | 0 | 30.16 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-381 | Layland 69 kV |  | WV | Fayette | Active | AEP | 75 | 0 | 35.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-383 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 83.6 | 0 | 26.29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AI2-384 | Nelson 138kV (CIR Increase) |  | IL | Lee | Active | ComEd | 200 | 0 | 89.44 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-385 | South Millville - Newport 69 kV |  | NJ | Cumberland | Active | AEC | 59.7 | 0 | 23.57 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 3/31/2025 |  |  | N | No
AI2-386 | PG - Juniata 69 kV |  | PA | Dauphin | Active | PPL | 55 | 0 | 20.74 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-387 | Carlls Corner - Sherman Ave 69 kV |  | NJ | Cumberland | Active | AEC | 49.7 | 0 | 19.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-388 | Milton 69 kV |  | PA | Northumberland | Active | PPL | 70 | 0 | 20.15 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-389 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 134.16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-390 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 134.16 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/4/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-391 | Emporia-Trego 115kV |  | VA | Greensville | Active | Dominion | 80 | 0 | 13 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 2/25/2023 |  |  | N | No
AI2-392 | Beatty-London 138 kV |  | OH | Madison | Active | AEP | 196 | 0 | 31.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-393 | Hickory-Moyock 230 kV |  | NC | Currituck | Active | Dominion | 100 | 0 | 17.7 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-394 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 0 | 66 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-395 | Reynolds–Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 0 | 59.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-396 | Jay-Desoto 138kV |  | IN | Blackford | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/3/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-397 | West Manchester-Crown 69kV |  | OH | Preble | Active | AEP | 80 | 0 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-398 | West Manchester 69 kV |  | OH | Preble | Active | AEP | 40 | 0 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-399 | Jay 138 kV |  | IN | Jay | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-400 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 72.6 | 0 | 25 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-401 | Olive-Reynolds #1 345 kV |  | IN | White | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-402 | Kirk - Newark Center 138 kV |  | OH | Licking | Active | AEP | 107.7 | 0 | 25.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-403 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 81.4 | 0 | 19.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-404 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-405 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 94.9 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-407 | Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 205 | 0 | 31.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-408 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-409 | Wayne-Byron 345 kV |  | IL | DeKalb | Active | ComEd | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-410 | Glidden - Cherry Valley 138 kV |  | IL | DeKalb | Active | ComEd | 118.6 | 0 | 28.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-411 | Glidden - Waterman 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 95.1 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-412 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-413 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-415 | Campbell-Kiesters 138 kV |  | PA | Butler | Active | PPL | 70 | 0 | 20.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-416 | Lexington-Dooms 230 kV |  | VA | Augusta | Active | Dominion | 200 | 0 | 50 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-417 | Wayne 345kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-418 | Sowers 138 kV |  | IN | Allen | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-420 | Crego Road 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 100 | 0 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-421 | Varner 345 kV |  | IN | DeKalb | Active | AEP | 180 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-422 | Jay 138 kV |  | IN | Jay | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-423 | Jay 69 kV |  | IN | Jay | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-424 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 111.8 | 0 | 28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-425 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 160 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2028 |  |  | N | No
AI2-426 | Allen - RP Mone 345 kV |  | IN | Allen | Active | AEP | 180 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-427 | Hazelton - Kirk 138 kV |  | OH | Licking | Active | AEP | 110 | 0 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/2/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-428 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 88.7 | 0 | 20.1 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-429 | Mendota Hills 138 kV |  | IL | Lee | Active | ComEd | 76.1 | 0 | 22.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-430 | Auburn 69 kV |  | IN | DeKalb | Active | AEP | 11 | 11 | 10 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 7/1/2023 |  |  | N | No
AI2-431 | Larrabee Collector Station 230 kV |  | NJ | Atlantic | Active | JCPL | 2138.85 | 2138.85 | 2083 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 2/28/2030 |  |  | N | No
AI2-432 | Philipsburg-Clarence 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/27/2022 |  |  | N | No
AI2-433 | Dubois-Curwensville 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 2/28/2023 |  |  | N | No
AI2-435 | South Hamburg – St. Peters Village 69 kV |  | PA | Berks | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-436 | Luthersburg - Curwensville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/9/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-437 | Glen Gardner - Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2024 |  |  | N | No
AI2-438 | Apple Valley 138kV |  | OH | Knox | Active | AEP | 150 | 150 | 148 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 7/10/2027 |  |  | N | No
AI2-439 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 237 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-440 | Phillipsburg 115 kV |  | PA | Centre | Active | PENELEC | 257 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-441 | Salem - Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 100 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-442 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-443 | North Longview 500 kV |  | PA | Greene | Active | APS | 300 | 300 | 295 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 7/10/2027 |  |  | N | No
AI2-444 | Rum Creek 138kV |  | WV | N/A | Active | AEP | 59.5 | 59.5 | 52.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 3/8/2026 |  |  | N | No
AI2-445 | Parsons - William 138 kV |  | WV | Tucker | Active | APS | 148 | 148 | 128.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 3/8/2026 |  |  | N | No
AI2-446 | Medera - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2027 |  |  | N | No
AI2-447 | Hillsboro-Wildcat 138kV |  | OH | Highland | Active | AEP | 150 | 0 | 87.3 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 9/30/2023 |  |  | N | No
AI2-448 | Curdsville-Willis Mtn 115 kV |  | VA | Buckingham | Active | Dominion | 100 | 0 | 36.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-449 | Disputanta-Poe 115 kV |  | VA | Prince George | Active | Dominion | 100 | 0 | 36.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-450 | DeSoto-Keystone 345 kV |  | IN | Blackford | Active | AEP | 100 | 0 | 48.6 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-451 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 38.5 | 0 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-452 | Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 130 | 0 | 51.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-453 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 78 | 0 | 28.2 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-454 | Mazon-Oglesby 138kV (CIR Increase) |  | IL | Grundy | Active | ComEd | 116 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-455 | W4-005 345kV (CIR Increase) |  | PA | Union | Active | ComEd | 306 | 0 | 162.8 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 3/31/2023 |  |  | N | No
AI2-456 | Birchwood - Fines Corner 230 kV |  | VA | King George | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 9/15/2027 |  |  | N | No
AI2-457 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 1122 | 1122 | 1122 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 10/1/2027 |  |  | N | No
AI2-458 | Bernville 34.5 kV 1 |  | PA | Berks | Active | ME | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-459 | Bernville 34.5 kV 2 |  | PA | Berks | Active | ME | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-460 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-461 | Wilton Center - Loretto 345 kV(CIR Increase) |  | IL | Kankakee | Active | ComEd | 850 | 0 | 173 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-462 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 150 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-463 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-464 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-465 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-466 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-467 | Maysville 138 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-468 | Summit Road 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-469 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-470 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-471 | Montour 230 kV |  | PA | Montour | Active | PPL | 101.6 | 0 | 29.464 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2025 |  |  | N | No
AI2-472 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 0 | 14.5 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-473 | Montour 230 kV |  | PA | Montour | Active | PPL | 100 | 0 | 29 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-474 | Montour 230 kV |  | PA | Montour | Active | PPL | 120 | 0 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-475 | Montour 230 kV |  | PA | Montour | Active | PPL | 140 | 0 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-476 | Snake Spring 115 kV |  | PA | Bedford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-477 | Snake Spring 115 kV II |  | PA | Bedford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-480 | Crawford 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-481 | Union City - French Road 12.5kV |  | PA | Erie | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 5/1/2026 |  |  | N | No
AI2-482 | Copperstone-North Lebanon 230 kV IV |  | PA | Lebanon | Active | ME | 100 | 0 | 58 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2023 | N/A | N/A |  |  |  | 12/1/2023 |  |  | N | No
AI2-483 | Heath 69 kV |  | OH | Licking | Active | AEP | 22.4 | 0 | 13.44 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/7/2023 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AI2-484 | Heidelberg 69 kV |  | PA | Lebanon | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/1/2027 |  |  | N | No
AI2-485 | Bruin Junction - Petrol Junction 25 kV |  | PA | Butler | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AI2-486 | Bethelboro - Connellsville 25 kV |  | PA | Fayette | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AI2-487 | Kewanee-Hennepin Tap 138kV |  | IL | Bureau | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-488 | Electric Junction - Nelson 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2026 |  |  | N | No
AI2-489 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/31/2025 |  |  | N | No
AI2-490 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 80 | 0 | 31.9 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/15/2023 |  |  | N | No
AI2-491 | East Lima-Marysville 345kV |  | OH | Champaign | Active | AEP | 250 | 0 | 133 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 5/31/2021 |  |  | N | No
AI2-492 | Deer Creek-Fisher Body-Mullin 138kV |  | IN | Grant | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/10/2023 | N/A | N/A |  |  |  | 12/26/2012 |  |  | N | No
AI2-493 | New Baltimore 115kV (Stony Creek) |  | PA | Somerset | Active | PENELEC | 52.5 | 0 | 18.2 |  | Capacity | Generation Interconnection | Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 3/11/2023 | N/A | N/A |  |  |  | 8/31/2023 |  |  | N | No
AJ1-001 | Boydton DP 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-002 | North River Delivery Point 115 kV |  | VA | Rockingham | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-003 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 4/21/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-008 | Zimmer 345 kV |  | OH | Clermont | Active | DEOK | 800 | 800 | 692.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/8/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AJ1-010 | Racine - Sarah Lane 69 kV |  | WV | Mason | Active | AEP | 35 | 35 | 7.098 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/22/2023 | N/A | N/A |  |  |  | 7/1/2025 |  |  | N | No
AJ1-011 | Waukegan Unit 7 CIR Transfer |  | IL | Lake | Active | ComEd | 328 | 328 | 328 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-012 | Waukegan Unit 8 CIR Transfer |  | IL | Lake | Active | ComEd | 354.4 | 354.4 | 354.4 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-013 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-014 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 260 | 260 | 260 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 5/24/2023 | N/A | N/A |  |  |  | 6/1/2027 |  |  | N | No
AJ1-015 | Larrabee Collector 230 kV |  | NJ | Monmouth | Active | JCPL | 1342 | 1342 | 1275 |  | Capacity | Generation Interconnection | Offshore Wind |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/2/2023 | N/A | N/A |  |  |  | 5/1/2030 |  |  | N | No
AJ1-016 | Cambria Slope 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/7/2023 | N/A | N/A |  |  |  | 11/9/2028 |  |  | N | No
AJ1-018 | Bishopville – Worcester 138 kV |  | MD | Worcester | Active | DPL | 39 | 39 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/22/2023 | N/A | N/A |  |  |  | 12/29/2028 |  |  | N | No
AJ1-019 | Bell Avenue 115 kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/28/2023 | N/A | N/A |  |  |  | 12/1/2028 |  |  | N | No
AJ1-020 | St. Johns – Woodpecker 115 kV |  | VA | Caroline | Active | Dominion | 86.38 | 86.38 | 51.828 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/15/2029 |  |  | N | No
AJ1-021 | Woodpecker – Slabtown 115 kV |  | VA | Caroline | Active | Dominion | 16.2 | 16.2 | 10.0584 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/15/2029 |  |  | N | No
AJ1-022 | Kerr Dam - Henderson NC 115 kV |  | VA | Mecklenburg | Active | Dominion | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 6/30/2027 |  |  | N | No
AJ1-023 | Trumbull 345 kV |  | OH | Trumbull | Active | ATSI | 1010 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/30/2023 | N/A | N/A |  |  |  | 12/1/2024 |  |  | N | No
AJ1-037 | Northeast - CP Crane 115 kV |  | MD | Baltimore County | Active | BGE | 500 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 7/8/2023 | N/A | N/A |  |  |  | 10/1/2028 |  |  | N | No
AJ1-038 | Penniman 34.5 kV |  | VA | York | Active | Dominion | 33 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  | N/A |  | In Progress |  |  |  |  | N/A |  | N/A |  |  | N/A | N/A |  | 6/29/2023 | N/A | N/A |  |  |  | 12/1/2025 |  |  | N | No

## Definitions-Mapping
Column Names from Data Tab
Project ID | Project/OASIS ID
Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
Commercial Name | The commercial name becomes public after the System Impact Study is issued. Not all developers have a commercial name once the System Impact Study is posted and there is no tariff requirement for them to have one. Also, the name users search under may vary. For ARR upgrades, the project name is the source and sink. Name is also referred to as the following: PJM Substation, Terminals, Customer Name and Source + Sink.
State | The state the project resides in.
County | Point of Interconnection County
Status | Contains the following statuses: Active, Active-In Service, Annulled, Cancelled, Confirmed, Engineering Procurement, In Service, Pending, Renewal, Retracted, Suspended, Under Construction, Under Construction - In Service & Withdrawn
Transmission Owner | A member that owns or leases, with rights equivalent to ownership, Transmission Facilities. Taking transmission service is not sufficient to qualify a Member as a Transmission Owner. Path name is included.
MFO | Maximum Facility Output
MW Energy | The MW energy for the interconnection request (winter net).
MW Capacity | The Capacity interconnection request for the position (summer net).
MW In Service | The number of megawatts when the project is in service.
Capacity or Energy
Project Type | GI: Generation Interconnection, TI: Transmission Interconnection, LTFT: Long-Term Firm Transmission, UR: Upgrade Request
Fuel | The type of fuel the project is running.
Project (AC/DC) | AC or DC
Rights (MW) | The type of rights the terminal has.
Initial Study
Feasibility Study | A Feasibility Study assesses project practicality and developer cost to interconnect to PJM and is the first study in the interconnection process.
Feasibility Study Status
System Impact Study | A System Impact Study provides a comprehensive and detailed system analysis that tests deliverability under peak load conditions as well as tests impacts on system stability.
System Impact Study Status
Facilities Study | A Facilities Study encompasses the engineering design work necessary to begin construction of required expansion plan upgrades identified by PJM to accommodate an interconnection request.
Facilities Study Status
Interim Interconnection Service Agreement | Under certain circumstances, an applicant for an ISA may wish to initiate project construction activities on an expedited basis prior to completion of the Facilities Study.
Interim Interconnection Service Agreement Status
Wholesale Market Participation Agreement | The WMPA request is placed into the interconnection request process so that PJM may assess the impact of any such wholesale power transactions on the PJM bulk power system.
Generation Interconnection Agreement | After the project’s required study work is completed, PJM will tender a Generation Interconnection Agreement (“GIA”) to be executed by the Project Developer, the Transmission Owner, and PJM.
Construction Service Agreement | The terms and conditions of a Construction Service Agreement govern the construction of all transmission facilities for interconnection to the PJM transmission system. PJM and the developer execute a separate CSA with each impacted transmission owner. A developer retains the right (“Option to Build”), but not the obligation to design, procure, construct and install all or any portion of required transmission upgrades which are otherwise the obligation of the Transmission Owner to construct.
Construction Service Agreement Status
Upgrade Construction Service Agreement | The terms and conditions of an Upgrade Construction Service Agreement govern the construction activities associated with the upgrade of capability along an existing PJM bulk electric system circuit in order to accommodate a merchant transmission interconnection request. Facilities constructed under an UCSA are not owned by a developer. All ownership rights of the physical facilities are retained by the respective Transmission Owner following the completion of construction. PJM and the developer execute a separate UCSA with each impacted transmission owner.
Upgrade Construction Service Agreement Status
BackFeed Date
Submitted Date
LTF Service Start Date
LTF Service End Date
Test Energy Date
Withdrawal Date
Withdrawn Remarks | CIW: Customer Initiated Withdraw, CMN: Customer Milestone Not Met, QNR: Queue Not Required, WBSD: Withdrawn Before Study Due
Revised In Service Date
Actual In Service Date
Date Suspended
Attachment Type | N, Y, BB = Generation Interconnection, S = Transmission Interconnection, EE = Upgrade Request, FF = Transmission Service
Alternate Project
Sliding Project