## Sheet1
ISO | Project ID | Application Status | Queue Date | Withdrawal Date | Done Date | Proposed In-Service/Initial Backfeed Date | Transmission Owner/Developer | Nearest Town or County | State | Study Cycle | Study Group | Study Phase | Service Type | POI Name | Summer MW | Winter MW | Fuel | Technology | Post GIA Status | Projected COD | Decision Point 1 ERIS MW | Decision Point 1 NRIS MW | Decision Point 2 ERIS MW | Decision Point 2 NRIS MW
MISO | J1000 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-04-02T04:00:00+00:00 | 2021-10-01T04:00:00+00:00 | American Transmission Co. LLC | Grant County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Nelson Dewey - Lancaster 138kV Line | 50 | 50 | Solar | Photovoltaic | In Service | 2023-03-27T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1001 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lincoln County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Buffalo Ridge 115kV Substation | 40 | 40 | Solar | Photovoltaic | Not Started |  | 40 | 40 | 0 | 0
MISO | J1002 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-05T04:00:00+00:00 | 2021-10-01T04:00:00+00:00 | American Transmission Co. LLC | Waushara County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Wautoma 138kV Switchyard | 99 | 99 | Solar | Photovoltaic | In Service | 2023-01-26T05:00:00+00:00 | 99 | 99 | 99 | 99
MISO | J1003 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-05T04:00:00+00:00 | 2021-10-01T04:00:00+00:00 | American Transmission Co. LLC | Dodge County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | North Beaver Dam 69 kV Substation | 50 | 50 | Solar | Photovoltaic | In Service | 2023-06-06T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1004 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-11-01T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | METC | Mecosta County,Montcalm County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Kenowa - Nelson Road 345kV Line Tap | 800 | 800 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1005 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-06-30T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | METC | Midland County,Saginaw County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Murphy 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1006 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Brookings County | South Dakota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Brookings - Yankee 115kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1007 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-08-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Marion - Marked Tree 161kV Line Tap | 200 | 200 | Solar | Photovoltaic | Under Construction | 2023-06-01T04:00:00+00:00 | 200 | 200 | 180 | 180
MISO | J1008 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | ITC MIDWEST | Faribault County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Blue Earth IPL - Blue Earth 69kV Line Tap | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1009 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-05-19T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | American Transmission Co. LLC | Kenosha County,Racine County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Pleasant Prairie - Racine 345kV Line Tap | 400 | 400 | Solar | Photovoltaic | Not Started |  | 400 | 400 | 0 | 0
MISO | J1010 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-05-19T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | American Transmission Co. LLC | Kenosha County,Racine County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Arcadian - Zion 345kV Line Tap | 400 | 400 | Solar | Photovoltaic | Not Started |  | 400 | 400 | 0 | 0
MISO | J1011 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-05-19T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | American Transmission Co. LLC | Kenosha County,Racine County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Arcadian - Zion 345kV Line Tap | 400 | 400 | Solar | Photovoltaic | Not Started |  | 400 | 400 | 0 | 0
MISO | J1012 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-28T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | PRAIRIE POWER, INC. | Scott County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Jacksonville Ind. Park - Winchester 138kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1013 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-12-02T05:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | METC | Branch County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Batavia 138kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1014 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-12-02T05:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | METC | Jackson County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Tompkins - Blackstone 138kV Line | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1015 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-27T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | METC | Otsego County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Gaylord 138kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1016 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-06T05:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Francisco - Toyota Z75 138kV Line Tap | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1017 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-03T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | Duke Energy | Carroll County,White County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Springboro 138 kV Substation | 125 | 125 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1018 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-03T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | Duke Energy | Miami County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Peru South East - Greentown 230 kV Line Tap | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1019 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-03T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | Ameren Missouri | Boone County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Overton - McCredie 345 kV Line Tap | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1020 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-24T05:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | COOPERATIVE ENERGY | Jasper County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Missionary 230kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
MISO | J1021 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-02T05:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Piatt County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Goose Creek 345kV Switchyard | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1022 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-08-01T04:00:00+00:00 | AMEREN ILLINOIS | McLean County | Illinois | DPP-2018-APR | Central | GIA | Energy Resource Interconnection Service (ERIS) | Weedman Substation 138kV Bus | 150 | 150 | Wind | Wind Turbine | In Service | 2022-05-27T04:00:00+00:00 | 150 | 150 | 150 | 0
MISO | J1023 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-07-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Osceola - Wilson 161 kV Line Tap | 82 | 82 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1024 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2022-09-30T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Nodaway County | Missouri | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Maryville - Clarinda 161 kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J1025 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-04-04T04:00:00+00:00 | 2023-04-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Knox County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Zachary - Maywood 345 kV Line Tap | 300 | 300 | Wind | Wind Turbine | Not Started | 2025-06-01T04:00:00+00:00 | 300 | 300 | 290 | 290
MISO | J1026 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-04-01T04:00:00+00:00 | 2020-09-30T04:00:00+00:00 | Ameren Missouri | Audrain County,Ralls County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek 345 kV Substation | 400 | 400 | Wind | Wind Turbine | Not Started | 2023-06-01T04:00:00+00:00 | 400 | 350 | 380 | 265
MISO | J1027 | Done | 2018-03-12T04:00:00+00:00 |  |  | 2021-01-02T05:00:00+00:00 | HOOSIER ENERGY | Pike County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Ratts 161 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started | 2022-11-15T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1028 | Done | 2018-03-12T04:00:00+00:00 |  |  | 2021-01-02T05:00:00+00:00 | HOOSIER ENERGY | Pike County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Ratts - Victory 161 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started | 2022-06-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1029 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-13T04:00:00+00:00 |  | 2020-09-28T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Feliciana Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Fancy Point 230 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1030 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-10-22T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Polk County | Texas | DPP-2018-APR | South | GIA | Energy Resource Interconnection Service (ERIS) | Poco - Menard 138kV Line Tao | 150 | 150 | Solar | Photovoltaic | In Service | 2023-01-23T05:00:00+00:00 | 150 | 0 | 150 | 0
MISO | J1031 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-07T05:00:00+00:00 |  | 2020-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Fall Creek - New Castle 138 kV Line Tap | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1032 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Wabasha County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Briggs Rd. - N. Rochester 345 kV Line Tap | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1033 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-10T05:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | Ameren Missouri | Stoddard County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Stoddard - Morely 161 kV Line Tap | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1034 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-10-31T04:00:00+00:00 | Ameren Missouri | Stoddard County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Stoddard - Morley 161kV Line Tap | 225 | 225 | Solar | Photovoltaic | Under Construction | 2024-06-01T04:00:00+00:00 | 225 | 225 | 225 | 225
MISO | J1035 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-15T04:00:00+00:00 |  | 2021-07-01T04:00:00+00:00 | AMEREN ILLINOIS | Washington County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Fayetteville - Marigold 138 kV Line Tap | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1036 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-02-15T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | Xcel Energy | Cottonwood County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lakefield Generation SW 345kV Substation | 130 | 130 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1037 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-15T04:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | GREAT RIVER ENERGY | Murray County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Moon Lake 69kV Substation | 15 | 15 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1038 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Grant County | Minnesota | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Grant Co. - E. Fergus Falls - Hoot Lake 115 kV Line Tap | 32.5 | 32.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1039 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-10T05:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | Ameren Missouri | Warren County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Enon - Montogomery 345kV Line Tap | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1040 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | McIntosh County | North Dakota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Wishek Junction 230 kV Substation | 250 | 250 | Wind | Wind Turbine | Under Construction | 2023-05-14T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J1041 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | ITC MIDWEST | Jackson County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Brewster - Heron Lake 161 kV Line | 20 | 20 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1042 | Withdrawn | 2018-03-09T05:00:00+00:00 | 2023-08-09T04:00:00+00:00 | 2021-05-18T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | American Transmission Co. LLC | Walworth County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | North Lake Geneva 138kV Substation | 200 | 200 | Solar | Photovoltaic | Withdrawn | 2023-09-15T04:00:00+00:00 | 200 | 200 | 180 | 180
MISO | J1043 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2023-02-09T05:00:00+00:00 | 2021-05-03T04:00:00+00:00 | 2021-06-13T04:00:00+00:00 | METC | Montcalm County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Vergennes - Nelson Rd 345 kV Line Tap | 374.4 | 374.4 | Wind | Wind Turbine | Withdrawn | 2024-05-31T04:00:00+00:00 | 374.4 | 374.4 | 374.4 | 374.4
MISO | J1044 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | American Transmission Co. LLC | Walworth County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | North Lake Geneva - Sugar Creek - Burlington 138kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1045 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-10-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Murray County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Fenton - Chanarambie 115kV Line Tap | 20 | 20 | Battery Storage | Battery Storage | Under Construction | 2024-07-30T04:00:00+00:00 | 20 | 20 | 20 | 20
MISO | J1046 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-11-21T05:00:00+00:00 |  | 2020-10-31T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Majestic - Lemoyne 345 kV Line Tap | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1047 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | American Transmission Co. LLC | Walworth County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | North Lake Geneva - Sugar Creek - Burlington 138kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1048 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-28T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | METC | Mecosta County,Montcalm County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Vergennes - Nelson Road 345kV Line Tap | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1049 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | COOPERATIVE ENERGY | Forrest County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Purvis 161 kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1050 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-01-17T05:00:00+00:00 | 2022-06-03T04:00:00+00:00 | ITC MIDWEST | Boone County,Hamilton County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Doud Tap 161 kV Substation | 225 | 225 | Wind | Wind Turbine | In Service | 2022-07-01T04:00:00+00:00 | 225 | 225 | 225 | 225
MISO | J1051 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-05-19T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | American Transmission Co. LLC | Jefferson County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Concord 138kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1052 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-27T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | METC | Jackson County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Beecher - Seamless East 138kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1053 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-05-19T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | American Transmission Co. LLC | Jefferson County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Concord SW YD 138 kV Substation | 300 | 300 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1054 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Goodhue County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Cannon Falls 115kV Substation | 30 | 30 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1055 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-11-13T05:00:00+00:00 | 2020-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Mason Substation 138 kV Bus | 144 | 144 | Wind | Wind Turbine | In Service | 2020-10-15T04:00:00+00:00 | 144 | 144 | 144 | 144
MISO | J1056 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-11-21T05:00:00+00:00 |  | 2020-10-31T04:00:00+00:00 | ITC MIDWEST | Monroe County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Lulu - Monroe 345 kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1057 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | ITC MIDWEST | Jackson County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Brewster - Heron Lake 161 kV Line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1058 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-10-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Lake County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer-St. John 345kV Line Tap | 300 | 300 | Solar | Photovoltaic | Under Construction | 2024-06-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1059 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-07T05:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | Ameren Missouri | Cape Girardeau County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Kelso - Lutesville 345 kV Line Tap | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1060 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-08-19T04:00:00+00:00 | 2021-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | St. Francis County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | West Memphis - Keo 500 kV Line Tap | 500 | 500 | Solar | Photovoltaic | Under Construction | 2023-05-01T04:00:00+00:00 | 500 | 500 | 450 | 400
MISO | J1061 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Wabasha County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Briggs Rd - N. Rochester 345 kV Line Tap | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1062 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-04-23T04:00:00+00:00 | 2021-10-31T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Majestic - Lemoyne 345 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started | 2023-06-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1063 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-03-09T05:00:00+00:00 | 2022-10-31T04:00:00+00:00 | Duke Energy | Clinton County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | New London - Frankfort 230kV Line Tap | 195 | 195 | Solar | Photovoltaic | Under Construction | 2022-08-01T04:00:00+00:00 | 195 | 195 | 195 | 195
MISO | J1064 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-11-21T05:00:00+00:00 |  | 2020-10-31T04:00:00+00:00 | METC | Ionia County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Marquette - Vergennes 138 kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1065 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-11-21T05:00:00+00:00 |  | 2020-10-31T04:00:00+00:00 | METC | Gratiot County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Alma - Vestaburg 138kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1066 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-05-17T04:00:00+00:00 |  | 2019-07-31T04:00:00+00:00 | PRAIRIE POWER, INC. | Pike County | Illinois | DPP-2018-APR | Central | GIA | External Network Resource Interconnection Service (E-NRIS) | El Dara Junction - Pittsfield 69 kV Line Tap | 44 | 44 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1067 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Pulaski County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Reynolds - Burr Oak 345kV Line | 240 | 240 | Solar | Photovoltaic | Under Construction | 2023-10-20T04:00:00+00:00 | 240 | 240 | 240 | 240
MISO | J1068 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-11-21T05:00:00+00:00 |  | 2020-10-31T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Dorset 120 kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1069 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Pulaski County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Reynolds 345kV Substation | 200 | 200 | Wind | Wind Turbine | Under Construction | 2023-04-20T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1070 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Washington County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | SE Greenville 115kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1071 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-03-26T04:00:00+00:00 | 2021-01-20T05:00:00+00:00 | METC | Oceana County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Donaldson 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2021-01-15T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1072 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | 2020-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Mower County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Adams 345 kV Substation | 150 | 150 | Solar | Photovoltaic | Under Construction | 2023-08-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1073 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Webre 500 kV Substation | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1074 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2023-10-27T04:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Francisco 138 kV sub | 200 | 200 | Solar | Photovoltaic | Withdrawn | 2022-11-15T05:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1075 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-11-01T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | METC | Cass County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Argenta - Weeds Lake - Hiple 345kV Line Tap | 350 | 350 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1076 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-01-06T05:00:00+00:00 | 2021-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. James Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Vacherie Sub 230 kV Substation | 200 | 200 | Solar | Photovoltaic | Under Construction | 2022-09-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1077 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-11-01T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | METC | Cass County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Argenta - Weeds Lake - Hiple 345kV Line Tap | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1078 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | San Souci 500 kV Substation | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1079 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Charles Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Waterford 1&2 230 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1080 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-22T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | AMEREN ILLINOIS | DeWitt County,McLean County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Brokaw - Clinton 345kV Line Tap | 99 | 99 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1081 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-28T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Polk County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Winger 115kV Substation | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1082 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-28T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | Ameren Missouri | Grundy County,Mercer County | Missouri | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Zachary 345 kV Substation | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1083 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-12-02T05:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | METC | Eaton County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Oneida138kV Substation | 70 | 70 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1084 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | 2020-09-01T04:00:00+00:00 | ITC MIDWEST | Clinton County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Rock Creek 345 kV Substation | 150 | 150 | Solar | Photovoltaic | Under Construction | 2023-09-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1085 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-05-19T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | American Transmission Co. LLC | Marathon County,Taylor County,Wood County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Gardner Park - J821 POI - Stone Lake 345 kV Line Tap | 300 | 300 | Wind | Wind Turbine | Not Started |  | 300 | 300 | 0 | 0
MISO | J1086 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | ITC MIDWEST | Nobles County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Elk - Brewster 161 kV Line Tap | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1087 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-01-02T05:00:00+00:00 | Ameren Missouri | Scott County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Miner - Kelso 161 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Under Construction | 2023-12-02T05:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1088 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-02-04T05:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | METC | Shiawassee County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Cornell - Layton 138 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Withdrawn |  | 150 | 150 | 150 | 150
MISO | J1089 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-02-04T05:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | METC | Shiawassee County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Cornell - Bell Rd 138 kV Line Tap | 170 | 170 | Solar | Photovoltaic | Not Started |  | 170 | 170 | 170 | 170
MISO | J1090 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-02-04T05:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | METC | Ingham County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Tompkins - Churchill Jct 138 kV Line Tap | 90 | 90 | Solar | Photovoltaic | Not Started |  | 90 | 90 | 90 | 90
MISO | J1091 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Power Line Road 161 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1092 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | 2022-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Saint Croix County | Wisconsin | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Three Lakes 115 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started | 2023-10-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1093 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Desha County,Drew County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Reed Switch 115kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1094 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-01-02T05:00:00+00:00 | AMEREN ILLINOIS | Washington County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Prest 138kV Switching Station | 150 | 150 | Solar | Photovoltaic | Under Construction | 2024-01-15T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1095 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | DeSoto County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Twinkletown 230kV Substation | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1096 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-01-02T05:00:00+00:00 | AMEREN ILLINOIS | Saline County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Norris City North - Muddy 138 kV Line | 150 | 150 | Solar | Photovoltaic | Under Construction | 2024-01-01T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1097 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke County,Pulaski County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | KEO EHV 500 kV Substation | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1098 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2022-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Jackson County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lakefield 345 kV Substation | 40 | 40 | Solar | Photovoltaic | Not Started |  | 40 | 40 | 0 | 0
MISO | J1099 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Derrick 230 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1100 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ENTERGY TEXAS, INC. | Grimes County | Texas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Grimes 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1101 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-04-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | American Transmission Co. LLC | Manitowoc County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Kewaunee 138kV Substation | 20 | 20 | Battery Storage | Battery Storage | Under Construction |  | 20 | 20 | 20 | 20
MISO | J1102 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-09-13T04:00:00+00:00 | 2021-06-13T04:00:00+00:00 | AMEREN ILLINOIS | Logan County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Fogarty 138 kV Substation | 70 | 70 | Solar | Photovoltaic | Under Construction | 2021-12-15T05:00:00+00:00 | 70 | 70 | 70 | 70
MISO | J1103 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-06-30T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | ITC MIDWEST | Tuscola County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Bauer - (Kirk) - Ringle 345kV Line Tap | 20 | 20 | Battery Storage | Battery Storage | Not Started |  | 20 | 20 | 0 | 0
MISO | J1104 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | American Transmission Co. LLC | Washington County,Waukesha County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Germantown - Bark River 138kV Line | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1105 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hampton Corners 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1106 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2021-08-01T04:00:00+00:00 | GREAT RIVER ENERGY | Redwood County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lyon County - Cedar Mountain 345 kV Circuit 2 Line | 414 | 414 | Wind | Wind Turbine | Not Started |  | 414 | 414 | 0 | 0
MISO | J1107 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | Ameren Missouri | Cape Girardeau County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Kelso - Lutesville 345 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Under Construction | 2023-11-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1108 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-06-13T04:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES | Douglas County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Alexandria 345 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1109 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass County | North Dakota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Bison 345kV Substation | 207 | 207 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1110 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-06-18T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | SMMPA | Mower County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | North Austin 161 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1111 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-10T05:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | Southern Illinois Power Cooperative | Jackson County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Campbell Hill - Jackson 161 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1112 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-10T05:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Kosciusko County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Leesburg 138kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1113 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Sunflower County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Delta - Ruleville 115kV Line Tap | 85 | 85 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1114 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Plymouth County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | J506 Substation on Raun - Highland 345 kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1115 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Macon County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Latham - Oreana 345kV Line | 200 | 200 | Wind | Wind Turbine | Under Construction | 2024-09-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1116 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-03T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | Duke Energy Corporation | Hancock County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Greensboro - Greenfield 138 kV Line Tap | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1117 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-05-30T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | METC | Ingham County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Green 138kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1118 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-03T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Piatt County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Mahomet - Weedman 138 kV Line Tap | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1119 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-06-10T04:00:00+00:00 |  | 2021-01-01T05:00:00+00:00 | METC | Jackson County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Tompkins 345 kV Substation | 600 | 600 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1120 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-23T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson County | Texas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Big Hill CO - Bayou Farms CO 138 kV Line Tap | 145 | 145 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1121 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-05-19T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | American Transmission Co. LLC | Marathon County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Stone Lake - (Pershing) - Gardner Park 345 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1122 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Pottawattamie County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Council Bluffs - Fallow Avenue 345 kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J1123 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-02T05:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | Ameren Missouri | Audrain County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek 345 kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1124 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | 2021-09-15T04:00:00+00:00 | SMMPA | Olmsted County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Byron 345kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2024-06-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1125 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-08-12T04:00:00+00:00 | 2021-07-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Wynne South - Wynne East AECC 161 kV Line Tap | 135 | 135 | Solar | Photovoltaic | Under Construction | 2023-03-01T05:00:00+00:00 | 135 | 135 | 135 | 135
MISO | J1126 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-11-01T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | ITC MIDWEST | Tuscola County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | ITC Bauer - Grassmere - Rapson (Kirk Sub) 345kV Substation | 1.1 | 1.1 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1127 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-10-25T04:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | American Transmission Co. LLC | Green County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Albany - Bass Creek 138 kV Line Tap | 49.9 | 49.9 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1128 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | SMMPA | Freeborn County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hayward - Murphy Creek 161 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1129 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-10-25T04:00:00+00:00 |  | 2021-01-02T05:00:00+00:00 | American Transmission Co. LLC | Rock County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Paddock - Townline Rd 138 kV Line Tap | 65 | 65 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1130 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2023-05-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Warren County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Baxter Wilson SES 115/500 kV Sw YD | 966 | 1110 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1131 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-16T04:00:00+00:00 | 2023-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Scott County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Sub 56 Davenport 161 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2024-06-30T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1132 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-10-01T04:00:00+00:00 | ITC MIDWEST | Union County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Creston East 69 kV Substation | 50 | 50 | Solar | Photovoltaic | Under Construction | 2024-06-01T04:00:00+00:00 | 50 | 50 | 50 | 0
MISO | J1133 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-01T04:00:00+00:00 |  | 2021-08-11T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Richland Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Dunn - Oakridge 115kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1134 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-06-05T04:00:00+00:00 |  | 2021-08-11T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | White County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Griffithville - Searcy Price 115 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1135 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-10-01T04:00:00+00:00 | ITC MIDWEST | Des Moines County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Huntwoods 69 kV substation | 50 | 50 | Solar | Photovoltaic | Not Started | 2024-06-01T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1136 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-06-05T04:00:00+00:00 |  | 2021-08-11T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Hinds County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Tinnin Road 230kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1137 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2021-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Swifton - Hoxie South 161 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1138 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-12-07T05:00:00+00:00 |  | 2020-09-23T04:00:00+00:00 | American Transmission Co. LLC | Baraga County | Michigan | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | M38 138 kV Substation | 70 | 70 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1139 | Done | 2018-03-12T04:00:00+00:00 |  |  | 2020-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Champaign County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Sidney Substation 138 kV Bus | 150 | 150 | Solar | Photovoltaic | Not Started | 2023-10-01T04:00:00+00:00 | 150 | 150 | 135 | 135
MISO | J1140 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2020-08-01T04:00:00+00:00 | MINNESOTA POWER | Benton County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Platte River 115 kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 80 | 80 | 0 | 0
MISO | J1141 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-09-07T04:00:00+00:00 |  | 2019-10-01T04:00:00+00:00 | METC | Manistee County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Filer - BoxbdJ - Stronach 138kV Line Tap | 17 | 17 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1142 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-07-10T04:00:00+00:00 | 2020-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. James Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Vacherie 230kV Substation | 20 | 20 | Solar | Photovoltaic | In Service (with Provisional GIA) | 2020-07-01T04:00:00+00:00 | 20 | 20 | 20 | 20
MISO | J1143 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-08-01T04:00:00+00:00 | MINNESOTA POWER | Morrison County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Blanchard - Little Falls 115 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1144 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-09-10T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | COOPERATIVE ENERGY | Covington County,Lamar County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Moselle - Columbia 161kV Line Tap | 96 | 96 | Solar | Photovoltaic | Under Construction | 2022-06-01T04:00:00+00:00 | 96 | 96 | 96 | 96
MISO | J1145 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-03-31T04:00:00+00:00 | 2021-04-01T04:00:00+00:00 | Ameren Missouri | Callaway County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Overton - (McCrede) - Montgomery 345 kV Line Tap | 250 | 250 | Solar | Photovoltaic | Not Started | 2024-06-01T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J1146 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-08-12T04:00:00+00:00 | 2019-01-04T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | San Souci 500 kV Substation | 10 | 10 | Coal | Combined Cycle | In Service | 2020-10-10T04:00:00+00:00 | 10 | 10 | 10 | 10
MISO | J1147 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-24T05:00:00+00:00 |  | 2021-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | St. Francis County | Arkansas | DPP-2018-APR | South | GIA | Energy Resource Interconnection Service (ERIS) | Moses - McCrory 161 kV Line tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 0 | 0 | 0
MISO | J1148 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-07T05:00:00+00:00 |  | 2022-06-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | AB Brown 138 kV Substation | 54 | 54 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1149 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-11-15T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Yellow Medicine County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hazel Creek 230 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1150 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-08-10T04:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Deedsville 345 kV Substation | 30 | 30 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1151 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ascension Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Brittany 230kV Substation | 219 | 252 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1152 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2022-07-19T04:00:00+00:00 |  | 2021-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Hancock County,Shelby County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Gwynneville 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1153 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2021-04-01T04:00:00+00:00 | American Transmission Co. LLC | Sheboygan County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Holland 138 kV Substation | 150 | 150 | Solar | Photovoltaic | In Service | 2022-06-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1154 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2021-04-01T04:00:00+00:00 | American Transmission Co. LLC | Jefferson County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Jefferson 138 kV Substation | 75 | 75 | Solar | Photovoltaic | Under Construction | 2023-05-15T04:00:00+00:00 | 75 | 75 | 75 | 75
MISO | J1155 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-08-12T04:00:00+00:00 | 2020-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Driver 230 kV Substation | 150 | 150 | Solar | Photovoltaic | Under Construction | 2022-09-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1156 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Kuhn Rd. - Parkin 161 kV line tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1157 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Hinds County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Tinnin Road 230 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1158 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-12-07T05:00:00+00:00 | 2020-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. James Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Vacherie 230 kV Substation | 70 | 70 | Solar | Photovoltaic | Under Construction | 2022-12-01T05:00:00+00:00 | 70 | 70 | 70 | 70
MISO | J1159 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Walker County | Texas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Mount Zion 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1160 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-01-31T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | American Transmission Co. LLC | Adams County,Wood County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Sand Lake - Port Edwards 138 kV Line Tap | 100.23 | 100.23 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1161 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-07T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | Ameren Missouri | Scott County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Miner - Kelso 161 kV Line Tap | 100.23 | 100.23 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1162 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson County | Texas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Jacinto - China 230 kV Line Tap | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1163 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Quitman County,Tunica County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Crenshaw - Tunica 115kv Line Tap | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1164 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-04-06T04:00:00+00:00 | 2021-08-01T04:00:00+00:00 | ITC MIDWEST | Rock County | Minnesota | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Magnolia 161 kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started | 2024-08-01T04:00:00+00:00 | 80 | 80 | 80 | 0
MISO | J1165 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | LC Bulk - Henning 138 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1166 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Bayou Cove - Richard 138 kV Line Tap | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1167 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-01-14T05:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | St. Francis County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | AECC Forrest City West 161 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1168 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty County | Texas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Pintail 138 kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1169 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-08-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | McCook County | South Dakota | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Grant 115 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started | 2024-07-30T04:00:00+00:00 | 50 | 50 | 50 | 0
MISO | J1170 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass County | North Dakota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Bison 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1171 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2021-08-01T04:00:00+00:00 | American Transmission Co. LLC | Dodge County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Butternut 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2023-01-26T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1172 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-03T04:00:00+00:00 | 2021-07-01T04:00:00+00:00 | METC | Genesee County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Dort - Garfield 138 kV Line Tap | 50 | 50 | Solar | Photovoltaic | Under Construction | 2023-08-01T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1173 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-06-30T04:00:00+00:00 |  | 2019-12-01T05:00:00+00:00 | CONSUMERS ENERGY COMPANY | Lenawee County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Raisin - METC Tap 138kV Line Tap | 80 | 80 | Solar | Photovoltaic | Not Started |  | 80 | 80 | 0 | 0
MISO | J1174 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-10-31T04:00:00+00:00 | ITC MIDWEST | Worth County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Ledyard - Colby 345 kV Line Tap | 165 | 165 | Solar | Photovoltaic | Under Construction | 2024-06-30T04:00:00+00:00 | 165 | 165 | 165 | 165
MISO | J1175 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-10-31T04:00:00+00:00 | ITC MIDWEST | Worth County | Iowa | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Ledyard - Colby 345kV Line Tap | 165 | 165 | Wind | Wind Turbine | Not Started | 2024-06-30T04:00:00+00:00 | 165 | 165 | 165 | 0
MISO | J1176 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-15T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo County,Worth County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lime Creek 161 kV Substation | 145 | 145 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1177 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Schuyler County | Missouri | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hughes 345 kV Switching Station (J541 POI) | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1178 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-08-06T04:00:00+00:00 | 2021-05-03T04:00:00+00:00 | 2020-07-01T04:00:00+00:00 | METC | Eaton County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Oneida 138 kV Substation | 65 | 65 | Solar | Photovoltaic | Withdrawn | 2023-08-01T04:00:00+00:00 | 65 | 65 | 65 | 65
MISO | J1179 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chisago County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Rush City - Red Rock 230 kV Line Tap | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1180 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2020-08-14T04:00:00+00:00 | AMEREN ILLINOIS | Clark County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Casey West - Sullivan 345 kV Line | 75 | 75 | Solar | Photovoltaic | Under Construction | 2023-05-01T04:00:00+00:00 | 75 | 75 | 75 | 75
MISO | J1181 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | 2021-10-31T04:00:00+00:00 | ITC MIDWEST | Chickasaw County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hazleton - Mitchell county 345 kV line | 200 | 200 | Wind | Wind Turbine | In Service | 2022-10-31T04:00:00+00:00 | 200 | 200 | 200 | 0
MISO | J1182 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-03-18T04:00:00+00:00 | 2021-11-15T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Adair County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Zachary Substation 345 kV Bus | 250 | 250 | Solar | Photovoltaic | Under Construction | 2024-11-15T05:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J1183 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-04-02T04:00:00+00:00 | 2019-01-31T05:00:00+00:00 | American Transmission Co. LLC | Delta County | Michigan | DPP-2018-APR | East (ATC) | GIA | Energy Resource Interconnection Service (ERIS) | Heritage Garden substation | 1.35 | 1.35 | Solar | Photovoltaic | Under Construction | 2019-10-15T04:00:00+00:00 | 1.35 | 0 | 1.35 | 0
MISO | J1184 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-10-09T04:00:00+00:00 | 2020-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Lagen Holton-Franklinton 115kV Line Tap | 50 | 50 | Solar | Photovoltaic | Under Construction | 2021-04-09T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1185 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-04-24T04:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | Ameren Missouri | Putnam County | Missouri | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Adair - Appanoose 161 kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1186 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-28T04:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | San Jacinto County | Texas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Pelican Road - Shepard 138 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1187 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2022-05-01T04:00:00+00:00 | GREAT RIVER ENERGY | Mercer County | North Dakota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Stanton 230 kV Substation | 151.8 | 151.8 | Wind | Wind Turbine | Not Started |  | 151.8 | 151.8 | 0 | 0
MISO | J1188 | Active | 2018-03-12T04:00:00+00:00 |  | 2021-05-18T04:00:00+00:00 | 2021-08-31T04:00:00+00:00 | American Transmission Co. LLC | Rock County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Sheepskin 69 kV Substation | 50 | 50 | Solar | Photovoltaic | In Service | 2022-06-01T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1189 | Done | 2018-03-12T04:00:00+00:00 |  |  | 2019-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Brown County,Martin County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Crane Solar 69kV Substation | 5 | 5 | Battery Storage | Battery Storage | Under Construction |  | 4.95 | 4.95 | 4.95 | 4.95
MISO | J1190 | Done | 2019-01-22T05:00:00+00:00 |  | 2023-01-26T05:00:00+00:00 | 2023-10-01T04:00:00+00:00 | ITC MIDWEST | Clinton County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Calamus East 161 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-08-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1191 | Active | 2019-02-04T05:00:00+00:00 |  |  | 2022-07-31T04:00:00+00:00 | City of Columbia, MO | Boone County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Bolstad 69 kV Substation | 64 | 64 | Solar | Photovoltaic | Not Started |  | 64 | 64 | 64 | 64
MISO | J1192 | Withdrawn | 2019-03-25T04:00:00+00:00 | 2022-10-25T04:00:00+00:00 | 2022-08-17T04:00:00+00:00 | 2021-07-01T04:00:00+00:00 | METC | Eaton County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Oneida 138kV Substation | 35 | 35 | Solar | Photovoltaic | Withdrawn | 2024-07-01T04:00:00+00:00 | 35 | 35 | 35 | 35
MISO | J1193 | Withdrawn | 2019-04-22T04:00:00+00:00 | 2020-04-28T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Morton County | North Dakota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Heskitt 115 kV Switchyard | 103.1 | 103.1 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J1194 | Active | 2019-04-24T04:00:00+00:00 |  |  | 2021-10-01T04:00:00+00:00 | METC | Midland County,Saginaw County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Murphy 138 kV Substation | 225.2 | 225.2 | Wind | Wind Turbine | In Service (with Provisional GIA) | 2021-11-01T04:00:00+00:00 | 225.2 | 225.2 | 225.2 | 225.2
MISO | J1195 | Withdrawn | 2019-04-24T04:00:00+00:00 | 2020-01-03T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | METC | Branch County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Wagner 138 kV Substation | 150.4 | 150.4 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1196 | Done | 2019-04-25T04:00:00+00:00 |  | 2022-10-31T04:00:00+00:00 | 2022-08-29T04:00:00+00:00 | ITC MIDWEST | Sanilac County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Greenwood - Rapson (Banner) 345 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-08-09T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1197 | Withdrawn | 2019-04-25T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | AMEREN ILLINOIS | LaSalle County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Corbin 138kV Substation | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1198 | Active | 2019-04-25T04:00:00+00:00 |  |  | 2021-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Jasper County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Newton 345kV Substation | 51.8 | 51.8 | Hybrid | Solar/Battery | Not Started | 2023-04-01T04:00:00+00:00 | 51.8 | 51.8 | 51.8 | 51.8
MISO | J1199 | Done | 2019-04-25T04:00:00+00:00 |  |  | 2021-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Fulton County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Duck Creek 345kV Substation | 20 | 20 | Hybrid | Solar/Battery | Not Started | 2023-06-01T04:00:00+00:00 | 20 | 20 | 20 | 20
MISO | J1200 | Done | 2019-04-25T04:00:00+00:00 |  |  | 2021-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Putnam County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Putnam 138kV Substation | 24.2 | 24.2 | Hybrid | Solar/Battery | Not Started | 2024-06-01T04:00:00+00:00 | 24.2 | 24.2 | 24.2 | 24.2
MISO | J1201 | Active | 2019-04-25T04:00:00+00:00 |  |  | 2021-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | North Coffeen 138kV Substation | 44.2 | 44.2 | Hybrid | Solar/Battery | Not Started | 2024-06-01T04:00:00+00:00 | 44.2 | 44.2 | 44.2 | 44.2
MISO | J1202 | Done | 2019-04-25T04:00:00+00:00 |  |  | 2021-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Randolph County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Baldwin Plant 345kV Switchyard - Baldwin Unit 2 | 68.4 | 68.4 | Hybrid | Solar/Battery | Not Started | 2024-06-01T04:00:00+00:00 | 68.4 | 68.4 | 68.4 | 68.4
MISO | J1203 | Done | 2019-04-25T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2022-06-01T04:00:00+00:00 | METC | Genesee County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Thetford 345kV Substation | 125 | 125 | Solar | Photovoltaic | Under Construction | 2025-05-15T04:00:00+00:00 | 125 | 125 | 125 | 125
MISO | J1204 | Withdrawn | 2019-04-26T04:00:00+00:00 | 2024-05-03T04:00:00+00:00 |  | 2022-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Casey West 345kV Substation | 199.3 | 199.3 | Solar | Photovoltaic | Withdrawn | 2025-06-01T04:00:00+00:00 | 199.3 | 199.3 | 199.3 | 199.3
MISO | J1205 | Done | 2019-04-26T04:00:00+00:00 |  | 2021-11-30T05:00:00+00:00 | 2021-10-31T04:00:00+00:00 | CLECO POWER LLC | Allen Parish | Louisiana | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Centennial - West Bay 138kV Line | 125 | 125 | Solar | Photovoltaic | Under Construction | 2023-09-30T04:00:00+00:00 | 125 | 125 | 125 | 0
MISO | J1206 | Withdrawn | 2019-04-26T04:00:00+00:00 | 2021-02-10T05:00:00+00:00 |  | 2021-04-01T04:00:00+00:00 | METC | Branch County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Newton 138kV Substation | 50 | 50 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J1207 | Withdrawn | 2019-04-26T04:00:00+00:00 | 2022-12-02T05:00:00+00:00 | 2022-08-17T04:00:00+00:00 | 2021-04-01T04:00:00+00:00 | METC | Branch County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Newton 138kV Substation | 50 | 50 | Gas | Combustion Turbine (Simple Cycle) | Withdrawn |  | 50 | 49.5 | 49.5 | 49.5
MISO | J1208 | Done | 2019-04-27T04:00:00+00:00 |  |  | 2023-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Saline County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Muddy - Crab Orchard 138 kV line | 80 | 80 | Solar | Photovoltaic | Not Started | 2023-11-04T04:00:00+00:00 | 80 | 80 | 80 | 80
MISO | J1209 | Done | 2019-04-27T04:00:00+00:00 |  |  | 2023-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Saline County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Muddy - Crab Orchard 138kV Line | 80 | 80 | Solar | Photovoltaic | Not Started | 2023-11-04T04:00:00+00:00 | 80 | 80 | 80 | 80
MISO | J1210 | Done | 2019-04-27T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2023-10-31T04:00:00+00:00 | METC | Iosco County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Whittemore - Twining 138kV Line | 50 | 50 | Solar | Photovoltaic | Not Started | 2025-03-31T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1211 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-02-11T05:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | CONSUMERS ENERGY COMPANY | Isabella County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Vernon - METC Tap 138kV Line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1212 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Murray County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Chanarambie-Ellsborough 115kV Line | 60 | 60 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1213 | Done | 2019-04-27T04:00:00+00:00 |  |  | 2022-12-31T05:00:00+00:00 | Ameren Missouri | Iron County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Taum Sauk 138kV Switchyard, Bus 1 & 2 | 60 | 60 | Hydro | Hydroelectric | Not Started | 2024-11-02T04:00:00+00:00 | 60 | 60 | 60 | 60
MISO | J1214 | Done | 2019-04-27T04:00:00+00:00 |  |  | 2022-10-30T04:00:00+00:00 | American Transmission Co. LLC | Dane County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Rockdale 345 kV Substation | 300 | 300 | Solar | Photovoltaic | Not Started | 2025-06-01T04:00:00+00:00 | 300 | 300 | 300 | 240
MISO | J1215 | Done | 2019-04-27T04:00:00+00:00 |  | 2022-01-25T05:00:00+00:00 | 2022-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Stuttgart Ricuskey - Woodward 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started | 2024-06-01T04:00:00+00:00 | 155 | 155 | 155 | 155
MISO | J1216 | Active | 2019-04-27T04:00:00+00:00 |  |  | 2023-10-30T04:00:00+00:00 | AMEREN ILLINOIS | Washington County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Ashley 138 kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started | 2026-06-01T04:00:00+00:00 | 185 | 185 | 185 | 185
MISO | J1217 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-03-18T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | CLECO POWER LLC | St. Landry Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Ville Platte - West Fork 230 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1218 | Done | 2019-04-27T04:00:00+00:00 |  | 2023-01-26T05:00:00+00:00 | 2023-10-30T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Muscatine County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Sub 92 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started | 2026-06-30T04:00:00+00:00 | 200 | 200 | 200 | 160
MISO | J1219 | Done | 2019-04-27T04:00:00+00:00 |  | 2021-11-30T05:00:00+00:00 | 2022-10-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Chicken Farm - Amite 115 kV Line | 100 | 100 | Solar | Photovoltaic | Under Construction | 2024-09-24T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1220 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | CLECO POWER LLC | Rapides Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Rapides - Rodemacher 230 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1221 | Active | 2019-04-27T04:00:00+00:00 |  |  | 2023-10-30T04:00:00+00:00 | GREAT RIVER ENERGY | Wadena County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Wing River- Riverton 230kV line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 120
MISO | J1222 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | Ameren Missouri | Ralls County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1223 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-03-18T04:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Pike County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Colonial Pipeline - Kentwood 115 kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 75 | 75 | 0 | 0
MISO | J1224 | Done | 2019-04-27T04:00:00+00:00 |  |  | 2022-10-30T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Majestic - Milan 345 kV Line Tap | 170 | 170 | Solar | Photovoltaic | Under Construction | 2025-10-30T04:00:00+00:00 | 170 | 170 | 153 | 153
MISO | J1225 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2023-09-29T04:00:00+00:00 | AMEREN ILLINOIS | Washington County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Ashley-Turkey Hill Line 1482, between the Okawville and North Nashville substations | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1226 | Active | 2019-04-27T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2023-09-29T04:00:00+00:00 | METC | Lenawee County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Morocco 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Under Construction | 2024-08-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1227 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2023-09-29T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Spencer County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Dubois - FB Culley 138 kV Line Tap | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1228 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2019-11-05T05:00:00+00:00 |  | 2023-09-29T04:00:00+00:00 | ITC MIDWEST | Faribault County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Huntley 161 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1229 | Done | 2019-04-29T04:00:00+00:00 |  | 2023-01-26T05:00:00+00:00 | 2023-10-30T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Muscatine County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Sub 92 345 kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started | 2026-06-30T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1230 | Withdrawn | 2019-04-27T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | GREAT RIVER ENERGY | Wadena County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Wing River- Riverton 230kV line | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1231 | Done | 2019-04-28T04:00:00+00:00 |  |  | 2022-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Lyon County | Kentucky | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Barkley - Caldwell 161kV Line | 125 | 125 | Solar | Photovoltaic | Not Started | 2025-09-01T04:00:00+00:00 | 125 | 125 | 125 | 125
MISO | J1232 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | AMEREN ILLINOIS | Coles County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Chesterville - Mattoon West 138kV Line | 99 | 99 | Solar | Photovoltaic | Not Started | 2025-07-01T04:00:00+00:00 | 99 | 99 | 99 | 99
MISO | J1233 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2023-02-06T05:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Pike County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Cato 138 kV Substation | 32.5 | 32.5 | Battery Storage | Battery Storage | Not Started |  | 32.5 | 32.5 | 32.5 | 32.5
MISO | J1234 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Edwardsport - Washington Mun, Linton 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started | 2023-09-15T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1235 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Edwardsport - Washington Mun, Linton 138kV Line | 50 | 50 | Solar | Photovoltaic | Not Started | 2023-09-15T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1236 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | CLECO POWER LLC | St. Landry Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Ville Platte - West Form 230 kV Line Tap | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1237 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-01-03T05:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Majestic - Milan 345kV Line | 175 | 175 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1238 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | CLECO POWER LLC | Rapides Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Rapides - Rodemacher 230 kV Line Tap | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1239 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2023-04-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita Parish | Louisiana | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Rilla 115 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2024-10-15T04:00:00+00:00 | 100 | 70 | 100 | 0
MISO | J1240 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2019-11-01T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | Ameren Missouri | Audrain County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek 345kV Substation | 135 | 135 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1241 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Jefferson County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | West Mt Vernon - Xenia 345kV Line | 200 | 200 | Solar | Photovoltaic | Not Started | 2024-12-10T05:00:00+00:00 | 165 | 165 | 165 | 165
MISO | J1242 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-05-15T04:00:00+00:00 | AMEREN ILLINOIS | Hancock County | Illinois | DPP-2019 | Central | GIA | External Network Resource Interconnection Service (E-NRIS) | Hamilton Line 796 Tap to Audrian 69kV Line | 25 | 25 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1243 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-05-15T04:00:00+00:00 | AMEREN ILLINOIS | McDonough County | Illinois | DPP-2019 | Central | GIA | External Network Resource Interconnection Service (E-NRIS) | Macomb West #2 - Blandlnsville Tap 69kV Line | 25 | 25 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1244 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-03-08T05:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | American Transmission Co. LLC | Houghton County | Michigan | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Winona - Toivola - Portage Tap - Atlantic Mine 69kV Line | 38.4 | 38.4 | Wind | Wind Turbine | Not Started |  | 38.4 | 38.4 | 0 | 0
MISO | J1245 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Stuttgart Ricuskey - Woodward 230 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1246 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-04-06T04:00:00+00:00 | 2023-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Bayou Labutte 500kV Substation | 725.2 | 725.2 | Gas | Combined Cycle | Not Started | 2025-09-20T04:00:00+00:00 | 705 | 705 | 705.2 | 705.2
MISO | J1247 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-05-31T04:00:00+00:00 | 2020-08-01T04:00:00+00:00 | CLECO POWER LLC | St. Mary,St. Mary Parish | Louisiana | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Ivanhoe 138kV Substation | 16.98 | 16.98 | Waste Heat Recovery | Co-gen | Under Construction | 2021-10-31T04:00:00+00:00 | 30.98 | 0 | 30.98 | 0
MISO | J1248 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2021-08-01T04:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Marshall - Black Stone 138 kV line | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-09-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1249 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-01-20T05:00:00+00:00 | 2022-03-01T05:00:00+00:00 | COOPERATIVE ENERGY | Lamar County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Morrow 161 kV Substation | 600 | 600 | Gas | Combined Cycle | In Service | 2022-07-24T04:00:00+00:00 | 600 | 600 | 600 | 600
MISO | J1250 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Datto-Corning North 161 kV line | 35 | 35 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1251 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-09-08T04:00:00+00:00 | 2022-10-30T04:00:00+00:00 | American Transmission Co. LLC | Marquette County | Michigan | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Arnold - Perkins 138 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Under Construction | 2025-06-12T04:00:00+00:00 | 100 | 100 | 100 | 80
MISO | J1252 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-02-08T05:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | American Transmission Co. LLC | Marquette County | Michigan | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Arnold - Perkins 138 kV Line Tap | 20 | 20 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1253 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-08-01T04:00:00+00:00 | American Transmission Co. LLC | Fond du Lac County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | South Fond Du Lac to Fitzgerald 345 kV line | 100 | 100 | Solar | Photovoltaic | Not Started | 2024-08-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1254 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Merom - Gibson - Wheatland 345kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1255 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-10-31T04:00:00+00:00 | 2022-10-30T04:00:00+00:00 | METC | Ionia County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Marquette - Vergennes 138 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Under Construction | 2025-10-30T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1256 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-05-06T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Dorset 120 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1257 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-30T05:00:00+00:00 | 2022-10-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Chicken Farm - Amite 115 kV Line | 20 | 20 | Battery Storage | Battery Storage | Under Construction | 2024-09-24T04:00:00+00:00 | 20 | 20 | 20 | 20
MISO | J1258 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2023-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | KEO EHV 500 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started | 2024-10-15T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1259 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Pike County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Colonial Pipeline - Kentwood 115 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1260 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-05T04:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Desha County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Dumas - Reed 115kV Line | 164 | 164 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1261 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-05T04:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Clarendon - Brinkley East 115kV Line | 90 | 90 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1262 | Active | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2019-06-01T04:00:00+00:00 | ITC MIDWEST | Wayne County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Energy Resource Interconnection Service (ERIS) | Waterman 120kV Substation | 25 | 25 | Gas | Combined Cycle | Not Started |  | 25 | 0 | 25 | 0
MISO | J1263 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-01-01T05:00:00+00:00 | AMEREN ILLINOIS | Clark County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Casey - Kansas West 345kV Line | 408.6 | 408.6 | Hybrid | Solar/Battery | Not Started | 2025-01-01T05:00:00+00:00 | 408.6 | 408.6 | 408.6 | 408.6
MISO | J1264 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-05-11T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | American Transmission Co. LLC | Schoolcraft County | Michigan | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Blaney Park - Engadine - Hiawatha - Alger - Munising 69kV Line | 20 | 20 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J1265 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2023-01-31T05:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaGrange County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Wolcottville - South Milford 69kV Line | 43 | 43 | Solar | Photovoltaic | Not Started |  | 43 | 43 | 43 | 43
MISO | J1266 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | AMEREN ILLINOIS | Marion County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Kinmundy - Salem 138kV Line | 99 | 99 | Solar | Photovoltaic | Not Started | 2025-07-01T04:00:00+00:00 | 99 | 99 | 99 | 99
MISO | J1267 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-06T04:00:00+00:00 |  | 2022-05-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Fisher - Cherry Valley 161kV Line | 135 | 135 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1268 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-11-30T05:00:00+00:00 | Ameren Missouri | Lincoln County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Pike - Troy 161kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2023-12-01T05:00:00+00:00 | 150 | 88 | 150 | 70
MISO | J1269 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Warrick County | Indiana | DPP-2019 | Central | GIA | Energy Resource Interconnection Service (ERIS) | Elliott 69kV Substation | 100 | 100 | Hybrid | Solar/Battery | Under Construction | 2025-07-01T04:00:00+00:00 | 100 | 47.6 | 100 | 0
MISO | J1270 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-09-29T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Palo Alto County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Kossuth - O'Brien 345 kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started | 2024-10-19T04:00:00+00:00 | 200 | 200 | 200 | 0
MISO | J1271 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Vanderburgh County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Oak Grove 138kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1272 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-09-02T04:00:00+00:00 | 2022-07-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Vanderburgh County | Indiana | DPP-2019 | Central | GIA | Energy Resource Interconnection Service (ERIS) | Angel Mound 138kV Substation | 50 | 50 | Battery Storage | Battery Storage | Under Construction | 2025-07-01T04:00:00+00:00 | 50 | 23.6 | 50 | 0
MISO | J1273 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2019-11-05T05:00:00+00:00 |  | 2023-09-29T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Marshall County,Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Burr Oak - East Winnamac 138 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1274 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Point 69kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1275 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson County | Kentucky | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Henderson 161 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1276 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2023-03-07T05:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | Indiana | DPP-2019 | Central | GIA | Energy Resource Interconnection Service (ERIS) | Point 69kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 47.1 | 100 | 0
MISO | J1277 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty County | Texas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Pintail 138 kV Substation | 130 | 130 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1278 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-05T04:00:00+00:00 |  | 2022-03-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Polk County | Texas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Corrigan Bulk - Staley 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1279 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-18T04:00:00+00:00 |  | 2022-03-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin County | Texas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Rye - Cypress 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J1280 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-05T04:00:00+00:00 |  | 2022-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Brinkley East - Clarendon 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1281 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ashley County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Crossett - Monticello East 115kV Line | 75 | 75 | Solar | Photovoltaic | Not Started | 2024-10-31T04:00:00+00:00 | 75 | 75 | 75 | 75
MISO | J1282 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-18T04:00:00+00:00 |  | 2022-03-01T05:00:00+00:00 | CLECO POWER LLC | Beauregard Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Cooper - Penton Road 230kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1283 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2019-09-05T04:00:00+00:00 |  | 2023-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | White Bluff - Arsenal C and White Bluff - Arsenal D 115kV Line | 269.99 | 269.99 | Waste Heat Recovery | Co-gen | Not Started |  | 0 | 0 | 0 | 0
MISO | J1284 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | ITC MIDWEST | Linn County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Duane Arnold - Tiffin (MEC) 345 kV Line Tap | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1285 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | ITC MIDWEST | Linn County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Duane Arnold - Tiffin (MEC) 345 kV Line Tap | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1286 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2022-10-30T04:00:00+00:00 | CLECO POWER LLC | Evangeline Parish | Louisiana | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Manuel 138 kV Substation | 150 | 150 | Solar | Photovoltaic | Under Construction | 2025-04-01T04:00:00+00:00 | 125 | 125 | 125 | 0
MISO | J1287 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-05T04:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Tunica County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Tunica - Crenshaw 115kV Line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1288 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-04-16T04:00:00+00:00 |  | 2023-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Cayuga - Sugar Creek 345kVLine | 606.7 | 667.2 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1289 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-20T04:00:00+00:00 | AMEREN ILLINOIS | Morgan County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Turner - Austin 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started | 2024-11-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1290 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | CLECO POWER LLC | Evangeline Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Manuel 138 kV Substation | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1291 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-01-14T05:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Catahoula Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Standard - Red Gum 115 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1292 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2021-05-01T04:00:00+00:00 | METC | Ionia County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Energy Resource Interconnection Service (ERIS) | Thompson Road 138kV Substation | 198 | 198 | Wind | Wind Turbine | Not Started | 2024-09-01T04:00:00+00:00 | 198 | 198 | 198 | 0
MISO | J1293 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Brinkley East - Moro 115 kV Line Tap | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1294 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-01-25T05:00:00+00:00 | 2022-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Sunflower County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Indianola - Cleveland 115kV Line | 99 | 99 | Solar | Photovoltaic | Under Construction | 2023-12-31T05:00:00+00:00 | 99 | 99 | 99 | 99
MISO | J1295 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2023-02-28T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Gibson County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Gibson - Francisco 345kV Line | 280 | 280 | Solar | Photovoltaic | Under Construction | 2023-12-31T05:00:00+00:00 | 280 | 280 | 280 | 280
MISO | J1296 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-12-01T05:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Francisco 138kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1297 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2021-12-01T05:00:00+00:00 | METC | Shiawassee County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Cornell - Bell Road 138 kV Line | 170 | 170 | Solar | Photovoltaic | Under Construction | 2024-12-01T05:00:00+00:00 | 170 | 170 | 170 | 170
MISO | J1298 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2023-02-02T05:00:00+00:00 |  | 2021-12-01T05:00:00+00:00 | SMMPA | Freeborn County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hayward - Murphy Creek 161kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1299 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-01T05:00:00+00:00 | Ameren Missouri | Scott County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Miner - Kelso 161kV Line | 200 | 200 | Solar | Photovoltaic | Under Construction | 2025-04-30T04:00:00+00:00 | 149 | 149 | 149 | 149
MISO | J1300 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2021-12-01T05:00:00+00:00 | ITC MIDWEST | Nobles County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Brewster - Elk 161kV Line | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1301 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2021-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Washington County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Prest 138kV Switching Station | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1302 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Saline County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Muddy - Norris City 138kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-02-01T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1303 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-01T05:00:00+00:00 | Southern Illinois Power Cooperative | Jackson County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Campbell Hill - Jackson 161kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2026-06-01T04:00:00+00:00 | 95 | 95 | 95 | 95
MISO | J1304 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-01T05:00:00+00:00 | American Transmission Co. LLC | Rock County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Paddock - Townline Road 138kV Line | 65 | 65 | Solar | Photovoltaic | In Service | 2023-08-11T04:00:00+00:00 | 65 | 65 | 65 | 65
MISO | J1305 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-01T05:00:00+00:00 | American Transmission Co. LLC | Green County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Albany - Bass Creek 138kV Line | 49.9 | 49.9 | Solar | Photovoltaic | In Service | 2023-05-05T04:00:00+00:00 | 49.9 | 49.9 | 49.9 | 49.9
MISO | J1306 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Perry County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Commodore-Jordan 345kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1307 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-03-08T05:00:00+00:00 |  | 2022-12-01T05:00:00+00:00 | METC | Eaton County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Oneida - Battle Creek 345kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1308 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-01T05:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | AB Brown - Gibson 345kV Line | 300 | 300 | Solar | Photovoltaic | Not Started | 2024-04-01T04:00:00+00:00 | 300 | 300 | 270 | 270
MISO | J1309 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2019-09-12T04:00:00+00:00 |  | 2021-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Gillett 115 kV Substation | 129.9 | 129.9 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1310 | Active | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2022-06-30T04:00:00+00:00 | METC | Jackson County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Blackstone - Marshall 138 kV Line | 125 | 125 | Solar | Photovoltaic | Under Construction | 2024-10-01T04:00:00+00:00 | 125 | 125 | 125 | 125
MISO | J1311 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2022-06-30T04:00:00+00:00 | AMEREN ILLINOIS | St. Clair County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Fayetteville Bee Hollow Road 138 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-06-30T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1312 | Done | 2019-04-29T04:00:00+00:00 |  | 2023-01-26T05:00:00+00:00 | 2022-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | McCook County | South Dakota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Grant 115 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started | 2025-06-30T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1313 | Done | 2019-04-29T04:00:00+00:00 |  | 2023-01-26T05:00:00+00:00 | 2022-06-30T04:00:00+00:00 | ITC MIDWEST | Greene County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | 161kV bus at Karma substation | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-06-30T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1314 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-26T04:00:00+00:00 | 2022-06-30T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Polk County | Wisconsin | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Apple River 161 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2025-06-30T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1315 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 |  | 2022-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cottonwood County,Murray County,Redwood County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lyon County - Cedar Mountain 345 kV Line Tap | 600 | 600 | Wind | Wind Turbine | Not Started |  | 600 | 600 | 600 | 0
MISO | J1316 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-10-30T04:00:00+00:00 | American Transmission Co. LLC | Kenosha County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Paris 138 kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started | 2025-10-30T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1317 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-01-03T05:00:00+00:00 |  | 2022-10-01T04:00:00+00:00 | ITC MIDWEST | Sanilac County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Bennet 120kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1318 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Rush County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Rushville 69kV Substation | 25 | 25 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1319 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-09-30T04:00:00+00:00 | ITC MIDWEST | Huron County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Rapson 120kV Substation | 117.5 | 117.5 | Wind | Wind Turbine | In Service | 2022-08-01T04:00:00+00:00 | 117.5 | 117.5 | 112 | 112
MISO | J1320 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2019-04-20T04:00:00+00:00 | METC | Branch County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Coldwater - Batavia 138kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-04-20T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1321 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-21T05:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Story County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | O'Brien - Kossuth 345 kV Line Tap | 65 | 65 | Battery Storage | Battery Storage | Not Started |  | 65 | 65 | 0 | 0
MISO | J1322 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-01-26T05:00:00+00:00 |  | 2022-04-20T04:00:00+00:00 | METC | Eaton County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Battle Creek - Oneida 345kV Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1323 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaGrange County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Lagrange 138 kV Substation | 25 | 25 | Battery Storage | Battery Storage | Not Started | 2025-06-01T04:00:00+00:00 | 25 | 25 | 25 | 25
MISO | J1324 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-05-11T04:00:00+00:00 |  | 2022-04-20T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery County | Illinois |  |  | GIA | Network Resource Interconnection Service (NRIS) | Midway 138kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1325 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-23T04:00:00+00:00 | 2022-06-30T04:00:00+00:00 | ITC MIDWEST | Rock County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Magnolia 161 kV substation | 200 | 200 | Solar | Photovoltaic | Under Construction | 2025-06-30T04:00:00+00:00 | 80 | 80 | 80 | 72
MISO | J1326 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-10-30T04:00:00+00:00 | American Transmission Co. LLC | Dane County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Rockdale 345 kV Substation | 75 | 75 | Battery Storage | Battery Storage | Not Started | 2025-06-01T04:00:00+00:00 | 75 | 75 | 75 | 75
MISO | J1327 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-02-08T05:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | METC | Ionia County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Marquette - Vergennes 138 kV Line Tap | 20 | 20 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1328 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-22T05:00:00+00:00 |  | 2022-04-20T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Grant County | South Dakota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Big Stone South 345kV Sub | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J1329 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-10-31T04:00:00+00:00 | 2022-10-30T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Majestic - Milan 345 kV Line Tap | 20 | 20 | Battery Storage | Battery Storage | Under Construction | 2025-10-30T04:00:00+00:00 | 20 | 20 | 20 | 20
MISO | J1330 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-04-20T04:00:00+00:00 | AMEREN ILLINOIS | Randolph County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Baldwin 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1331 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2022-06-30T04:00:00+00:00 | ITC MIDWEST | St. Clair County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Greenwood 120 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-02-28T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1332 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2024-03-08T05:00:00+00:00 |  | 2022-04-20T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Rollin Schahfer - Lake George 345kV Line | 200 | 200 | Solar | Photovoltaic | Withdrawn | 2025-04-20T04:00:00+00:00 | 200 | 200 | 194 | 194
MISO | J1333 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Under Construction | 2024-06-15T04:00:00+00:00 | 199.5 | 199.5 | 199.5 | 199.5
MISO | J1334 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started | 2024-06-15T04:00:00+00:00 | 199.5 | 199.5 | 199.5 | 199.5
MISO | J1335 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started | 2024-06-24T04:00:00+00:00 | 199.5 | 199.5 | 199.5 | 199.5
MISO | J1336 | Done | 2019-04-29T04:00:00+00:00 |  | 2023-01-30T05:00:00+00:00 | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started | 2025-02-01T05:00:00+00:00 | 199.5 | 199.5 | 199.5 | 199.5
MISO | J1337 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Sherburne County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Sherburne County 345 kV substation | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1338 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-07-15T04:00:00+00:00 | Ameren Missouri | Audrain County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek - Montgomery 345 kV Line Tap | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1339 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started | 2025-08-01T04:00:00+00:00 | 199.5 | 199.5 | 199.5 | 199.5
MISO | J1340 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer - Burr Oak 345kV Line | 199.5 | 199.5 | Hybrid | Solar/Battery | Not Started | 2025-06-01T04:00:00+00:00 | 199.5 | 199.5 | 199.5 | 199.5
MISO | J1341 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | ITC MIDWEST | Buchanan County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hazleton 345kV Substation | 398 | 398 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1342 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-05-20T04:00:00+00:00 |  | 2023-06-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Starke County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Starke 138kV Substation | 99 | 99 | Solar | Photovoltaic | Not Started |  | 99 | 99 | 0 | 0
MISO | J1343 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-03-05T05:00:00+00:00 |  | 2022-09-15T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Emery - Lime Creek 161 kV Line Tap | 96 | 96 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1344 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-03-05T05:00:00+00:00 |  | 2022-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Mills County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hastings 69 kV Substation | 48 | 48 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1345 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-03-08T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | American Transmission Co. LLC | Dodge County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | North Beaver Dam 69kV Substation | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 25 | 25 | 0 | 0
MISO | J1346 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-05-29T04:00:00+00:00 |  | 2022-01-01T05:00:00+00:00 | ITC MIDWEST | Wayne County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Brownstown 345kV Substation | 334 | 382 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J1347 | Done | 2019-04-26T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Scott County | Mississippi | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Pelahatchie - Scott 115 kV Line Tap | 175 | 175 | Solar | Photovoltaic | In Service | 2023-06-01T04:00:00+00:00 | 175 | 0 | 175 | 0
MISO | J1348 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-20T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Cayuga - Sugar Creek 345kV Line | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-04-20T04:00:00+00:00 | 200 | 200 | 0 | 0
MISO | J1349 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-22T05:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cottonwood County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Crandall 345 kV Substation | 335 | 335 | Hybrid | Solar/Wind | Not Started |  | 335 | 335 | 0 | 0
MISO | J1350 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2023-04-07T04:00:00+00:00 | 2022-10-31T04:00:00+00:00 | 2022-04-20T04:00:00+00:00 | METC | Monroe County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Milan – Monroe – Morocco 345 kV Point | 150 | 150 | Solar | Photovoltaic | Withdrawn | 2025-04-20T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1351 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-05T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Madison Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Tallulah - Delhi 115kV Line Tap | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1352 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-20T04:00:00+00:00 | Ameren Missouri | Montgomery County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek - Montgomery 345kV Line | 100 | 100 | Solar | Photovoltaic | Not Started | 2024-12-01T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1353 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2023-09-05T04:00:00+00:00 |  | 2023-05-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Lake County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Green Acres138kV Subtation | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 150 | 150 | 150 | 150
MISO | J1354 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-05-30T04:00:00+00:00 | HOOSIER ENERGY | Decatur County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Decatur County 138kV Switching Station | 146 | 146 | Battery Storage | Battery Storage | Not Started | 2025-10-15T04:00:00+00:00 | 118 | 118 | 118 | 118
MISO | J1355 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-05-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Stillwell 138kV Subtation | 160 | 160 | Battery Storage | Battery Storage | Not Started | 2026-05-30T04:00:00+00:00 | 131 | 131 | 131 | 131
MISO | J1356 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-05-20T04:00:00+00:00 |  | 2023-05-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Martin County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Whitfield 138kV Substation | 160 | 160 | Solar | Photovoltaic | Not Started |  | 135 | 74 | 0 | 0
MISO | J1357 | Done | 2019-04-29T04:00:00+00:00 |  | 2023-01-31T05:00:00+00:00 | 2023-05-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Madison County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Madison 138 KV SUBSTATION | 150 | 150 | Battery Storage | Battery Storage | Not Started | 2025-09-30T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1358 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-05-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Luchtman - Michigan City138kV Line | 125 | 125 | Battery Storage | Battery Storage | Not Started | 2026-05-30T04:00:00+00:00 | 125 | 125 | 125 | 125
MISO | J1359 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2022-03-01T05:00:00+00:00 | ITC MIDWEST | Linn County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Oakridge 69 kV Substation | 95 | 95 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 95 | 95 | 95 | 95
MISO | J1360 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-20T04:00:00+00:00 | AMEREN ILLINOIS | Piatt County | Illinois | DPP-2019 | Central | GIA | Energy Resource Interconnection Service (ERIS) | Goose Creek 345kV Switchyard | 300 | 300 | Wind | Wind Turbine | Not Started | 2024-06-01T04:00:00+00:00 | 300 | 300 | 300 | 0
MISO | J1361 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2021-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Lagen Holton - Franklinton 115kV Line (J1184) | 50 | 50 | Solar | Photovoltaic | Under Construction | 2024-01-15T05:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1362 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-02-13T05:00:00+00:00 |  | 2021-08-27T04:00:00+00:00 | METC | Muskegon County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Kenowa - Ludington 345 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1363 | Withdrawn | 2019-04-26T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-07-15T04:00:00+00:00 | Ameren Missouri | Audrain County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek - Montgomery 345 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1364 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-05T04:00:00+00:00 |  | 2022-07-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Marked Tree - Marion 161 kV Line tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1365 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | ITC MIDWEST | Tama County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Traer 161-kV Substation | 169.4 | 169.4 | Wind | Wind Turbine | Not Started | 2024-09-06T04:00:00+00:00 | 169.4 | 169.4 | 169.4 | 0
MISO | J1366 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-04-02T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Eau Claire County | Wisconsin | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Tremval - Seven Mile 161 kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1367 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-04-15T04:00:00+00:00 | 2021-07-01T04:00:00+00:00 | CLECO POWER LLC | St. Mary,St. Mary Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Caneland 230kV Substation | 95 | 95 | Solar | Photovoltaic | Under Construction | 2022-09-19T04:00:00+00:00 | 95 | 95 | 95 | 48.65
MISO | J1368 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-30T05:00:00+00:00 | 2022-07-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Pointe Coupee,Pointe Coupee Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Fancy Point - Waterloo 230 kV Line | 200 | 200 | Solar | Photovoltaic | In Service | 2023-06-01T04:00:00+00:00 | 200 | 130 | 200 | 40
MISO | J1369 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Dubois County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Dubois - Culley 138kV line | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-07-01T04:00:00+00:00 | 100 | 100 | 100 | 85
MISO | J1370 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-03-08T05:00:00+00:00 |  | 2021-03-01T05:00:00+00:00 | American Transmission Co. LLC | Chippewa County | Michigan | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | 9 Mile SW STA - Dafter 69kV Line | 50 | 50 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 50 | 50 | 0 | 0
MISO | J1371 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-07T05:00:00+00:00 |  | 2023-08-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Yellow Medicine County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Astoria 345kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
MISO | J1372 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-30T05:00:00+00:00 | 2022-07-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Pointe Coupee,Pointe Coupee Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Fancy Point - Waterloo 230 kV Line (J1368 POI) | 100 | 100 | Solar | Photovoltaic | In Service | 2023-06-01T04:00:00+00:00 | 100 | 65 | 100 | 20
MISO | J1373 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | White County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Griffithville - Searcy Price 115 kV Line Tap | 95 | 95 | Solar | Photovoltaic | In Service | 2023-03-15T04:00:00+00:00 | 95 | 80.75 | 95 | 80.75
MISO | J1374 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-09-08T04:00:00+00:00 | 2021-08-01T04:00:00+00:00 | American Transmission Co. LLC | Grant County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | ATC Ebenezer Sub on Lancaster-Eden 138kv line | 95 | 95 | Wind | Wind Turbine | Not Started | 2024-08-08T04:00:00+00:00 | 67.2 | 67.2 | 67.2 | 67.2
MISO | J1375 | Active | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2023-09-29T04:00:00+00:00 | METC | Muskegon County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Du Pont - Cobb -White Lake 138kv | 100 | 100 | Solar | Photovoltaic | Under Construction | 2025-05-12T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1376 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-07-15T04:00:00+00:00 | Ameren Missouri | Cooper County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Barnett - Georgetown Overton 161 kV Line Tap | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1377 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-15T04:00:00+00:00 | American Transmission Co. LLC | Rock County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Wempletown - Rockdale 345kV Line Tap | 98.56 | 98.56 | Solar | Photovoltaic | Not Started | 2025-07-15T04:00:00+00:00 | 98.56 | 98.56 | 98.56 | 98.56
MISO | J1378 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Veedersburg West 230 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2024-11-15T05:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1379 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2023-10-01T04:00:00+00:00 | METC | Montcalm County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Eureka - Vestaburg 138 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-12-19T05:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1380 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-07-17T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | CLECO POWER LLC | Beauregard Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Cooper - Penton 230 kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1381 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Howard County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Greentown 230 kV substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2026-10-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1382 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Clark County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Hutsonville - Neoga 138 kV Line tap | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-05-31T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1383 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Fulton County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Ipava 138 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-06-15T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1384 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-07-22T04:00:00+00:00 |  | 2022-04-30T04:00:00+00:00 | CLECO POWER LLC | Evangeline Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Ville Platte - West Fork 230 kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1385 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Hendricks County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Stilesville 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1386 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Lake County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Green Acres 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-07-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1387 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-31T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County | Indiana | DPP-2019 | Central | GIA | Energy Resource Interconnection Service (ERIS) | Circuit 6958 69 kV Line Tap | 60 | 60 | Solar | Photovoltaic | Not Started | 2024-04-26T04:00:00+00:00 | 60 | 0 | 60 | 0
MISO | J1388 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-31T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Gibson County | Indiana | DPP-2019 | Central | GIA | Energy Resource Interconnection Service (ERIS) | Oakland City - Old Ben Coal 138 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started | 2024-12-15T05:00:00+00:00 | 150 | 0 | 150 | 0
MISO | J1389 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | METC | Saginaw County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Murphy Station - Nelson Road 345 kV Line tap | 120 | 120 | Solar | Photovoltaic | Not Started | 2025-04-01T04:00:00+00:00 | 120 | 120 | 120 | 120
MISO | J1390 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Bartholomew County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Gallagher Station - Columbus 230 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Under Construction | 2025-08-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1391 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Dubois County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Duff 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-05-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1392 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaGrange County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Lagrange 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-06-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1393 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-30T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Pike County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Cato 138 kV Substation | 130 | 130 | Solar | Photovoltaic | Not Started | 2026-04-01T04:00:00+00:00 | 130 | 130 | 130 | 130
MISO | J1394 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-02-08T05:00:00+00:00 |  | 2021-12-01T05:00:00+00:00 | METC | Shiawassee County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Cornell - Layton138kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1395 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lyon County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hawks Nest Lake - Lyon County 345 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1396 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-12-01T05:00:00+00:00 | HOOSIER ENERGY | Pike County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Ratts-Victory 161kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2024-08-20T04:00:00+00:00 | 60 | 60 | 60 | 60
MISO | J1397 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-05-18T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Juneau County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Whistling Wings 69 kV Substation | 25 | 25 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1398 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-12-01T05:00:00+00:00 | HOOSIER ENERGY | Pike County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Ratts 161kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1399 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2021-12-01T05:00:00+00:00 | METC | Ingham County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Delhi - Churchill - Tompkins 138kV Line | 90 | 90 | Solar | Photovoltaic | Not Started | 2025-03-01T05:00:00+00:00 | 90 | 90 | 90 | 90
MISO | J1400 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-07-30T04:00:00+00:00 |  | 2021-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Marked Tree - Marion 161 kV Line Tap | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1401 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2023-11-17T05:00:00+00:00 | METC | Branch County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Batavia - Wagner 138kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2024-04-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1402 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2021-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Cash - Newport AB161kV Line | 0 | 0 | Battery Storage | Battery Storage | Not Started | 2023-02-01T05:00:00+00:00 | 0 | 0 | 0 | 0
MISO | J1403 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-03-08T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | METC | Ionia County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Marquette 138 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1404 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-07-23T04:00:00+00:00 |  | 2022-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Sunflower County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Drew 115kV Substation | 167 | 167 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1405 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-05-20T04:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Greene County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Sanborn - Linton 138 kV Line Tap | 140 | 140 | Solar | Photovoltaic | Not Started |  | 140 | 140 | 0 | 0
MISO | J1406 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-02-07T05:00:00+00:00 |  | 2021-09-03T04:00:00+00:00 | METC | Muskegon County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Kenowa - Ludington 345 kV Line Tap | 25.2 | 25.2 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1407 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | South Valparaiso 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-08-01T04:00:00+00:00 | 100 | 100 | 100 | 70
MISO | J1408 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Macoupin County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Virden 138kV Substation | 100 | 100 | Hybrid | Solar/Wind/Battery | Not Started | 2026-06-15T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1409 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson County | Kentucky | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Henderson 161 kV Substation | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1410 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-10-30T04:00:00+00:00 | American Transmission Co. LLC | Dane County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | N. Madison 345 kV Substation | 300 | 300 | Solar | Photovoltaic | Under Construction | 2025-10-30T04:00:00+00:00 | 300 | 300 | 300 | 240
MISO | J1411 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-10-30T04:00:00+00:00 | American Transmission Co. LLC | Dane County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | N. Madison 345 kV Substation | 75 | 75 | Battery Storage | Battery Storage | Not Started | 2025-10-30T04:00:00+00:00 | 75 | 75 | 75 | 75
MISO | J1412 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-04-15T04:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Lake George - Schahfer GEN STA 345 kV Line Tap | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1413 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ITC MIDWEST | Howard County,Mitchell County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hazleton - Mitchell County 345 kV Line tap | 300 | 300 | Solar | Photovoltaic | Not Started |  | 235 | 215 | 235 | 188
MISO | J1414 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Datto-Corning North 161 kV line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1415 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2023-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | KEO EHV 500 kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started | 2024-10-15T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J1416 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-21T05:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ITC MIDWEST | Worth County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Worth County - Glenworth 161 kV Line tap | 149 | 149 | Solar | Photovoltaic | Not Started |  | 149 | 149 | 0 | 0
MISO | J1417 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-21T05:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ITC MIDWEST | Worth County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Ledyard - Colby 345 kV Line Tap | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 75 | 75 | 0 | 0
MISO | J1418 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-01-02T05:00:00+00:00 |  | 2021-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Pulaski County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Joppa-Joppa North Bus 161kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1419 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-05-20T04:00:00+00:00 |  | 2022-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Greene County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Edwardsport - Amo 345 kV Line Tap | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
MISO | J1420 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-03-05T05:00:00+00:00 |  | 2022-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Rock Island County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Sub #107 69 kV Substation | 48 | 48 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1421 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-10-20T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Feliciana Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Moler 230 kV Substation | 300 | 300 | Solar | Photovoltaic | Under Construction | 2024-12-01T05:00:00+00:00 | 300 | 300 | 300 | 300
MISO | J1422 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2021-10-20T04:00:00+00:00 | AMEREN ILLINOIS | Edwards County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Albion - Olney 138 kV Line Tap | 150 | 150 | Hybrid | Solar/Battery | Not Started | 2024-10-20T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1423 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-06-11T04:00:00+00:00 |  | 2022-04-20T04:00:00+00:00 | METC | Ottawa County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Campbell - Blendon 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1424 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2022-08-01T04:00:00+00:00 | CLECO POWER LLC | Beauregard Parish | Louisiana | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Cooper - Penton Road 230kV Line | 200 | 200 | Solar | Photovoltaic | Under Construction | 2024-09-15T04:00:00+00:00 | 200 | 200 | 200 | 0
MISO | J1425 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-01-27T05:00:00+00:00 | 2020-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service only for an Existing Generating Facility (NRIS-Only) | Pine Bluff International Paper 115 kV substation | 114 | 114 | Gas | Combined Cycle | In Service |  | 0 | 114 | 0 | 114
MISO | J1426 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-26T04:00:00+00:00 | 2022-08-01T04:00:00+00:00 | GREAT RIVER ENERGY | Benton County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Benton County 115kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2025-08-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1427 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ITC MIDWEST | Benton County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Duane Arnold 345kV Substation | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1428 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Cass County | North Dakota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Buffalo 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1429 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-05-18T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Juneau County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Whistiling Wings 69 kV Substation | 24 | 24 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1430 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2022-08-01T04:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Verona - Foundary 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started | 2023-08-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1431 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-04-07T04:00:00+00:00 | 2021-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. James Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Vacherie 230kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2024-05-01T04:00:00+00:00 | 90 | 90 | 90 | 90
MISO | J1432 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-10-31T04:00:00+00:00 | 2022-08-01T04:00:00+00:00 | ITC MIDWEST | Clinton County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Salem - Rock Creek 345kV Line | 250 | 250 | Wind | Wind Turbine | Not Started | 2025-09-01T04:00:00+00:00 | 250 | 250 | 250 | 0
MISO | J1433 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2019-10-22T04:00:00+00:00 |  | 2021-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Lagen Holton-Franklinton 115kV (J1184) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1434 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-01-25T05:00:00+00:00 | 2022-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | J907 230kV Sub, Brinkley East - Aubrey 230 kV Line | 100 | 100 | Solar | Photovoltaic | Under Construction | 2024-04-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1435 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ITC MIDWEST | Dubuque County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Center Grove 161kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1436 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-11-29T05:00:00+00:00 | 2022-11-15T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse Parish | Louisiana | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Oak Ridge 115 kV Substation | 50 | 50 | Solar | Photovoltaic | In Service | 2023-07-01T04:00:00+00:00 | 50 | 0 | 50 | 0
MISO | J1437 | Done | 2019-04-29T04:00:00+00:00 |  | 2021-12-22T05:00:00+00:00 | 2021-04-30T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Carroll County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | AECC Dry Creek 161kV Switchyard Station | 180 | 180 | Wind | Wind Turbine | Under Construction | 2024-05-01T04:00:00+00:00 | 180 | 180 | 180 | 180
MISO | J1438 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-06-28T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ITC MIDWEST | Fayette County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Windsor - Hazelton 161kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1439 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-04T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Tunica County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Lula - Tunica 115 kV Line | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1440 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-01-25T05:00:00+00:00 | 2023-10-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Tunica County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Lula - Tunica 115 kV Line | 160 | 160 | Solar | Photovoltaic | Under Construction | 2024-12-15T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1441 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-04-19T04:00:00+00:00 | 2022-04-06T04:00:00+00:00 | 2022-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Terrebonne Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Schriever 230 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-05-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1442 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-04T04:00:00+00:00 | 2023-10-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Polk County | Texas | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Rich (SHECO) - Livingston 138 kV Line Tap | 165 | 165 | Solar | Photovoltaic | Under Construction | 2025-05-01T04:00:00+00:00 | 105 | 105 | 105 | 0
MISO | J1443 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-01-14T05:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Texas Eastern F SS - Strong SS 115 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1444 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2015-08-01T04:00:00+00:00 | ITC MIDWEST | Linn County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Duane Arnold 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-09-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1445 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Benton County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Mayhew Lake 115kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2025-10-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1446 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-21T05:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Wright County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lake Pulaski 115kV Substation | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 150 | 150 | 0 | 0
MISO | J1447 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2024-02-27T05:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer - Green Acres 345kV Line | 250 | 250 | Solar | Photovoltaic | Withdrawn | 2025-07-25T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J1448 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-05-20T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Caldwell County | Kentucky | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Hopkins - Caldwell County - Barkely 161kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1449 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-02-10T05:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | METC | Monroe County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Morocco 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1450 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Webster County | Kentucky | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Hopkins - Reid161kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-08-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1451 | Withdrawn | 2019-04-26T04:00:00+00:00 | 2020-05-06T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Dorset 120 kV Substation | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1452 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-18T04:00:00+00:00 |  | 2022-10-30T04:00:00+00:00 | CLECO POWER LLC | Red River Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Carroll - Mansfield 138 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 75 | 75 | 0 | 0
MISO | J1453 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Havana - Shockey 138 kV Line Tap | 188.3 | 188.3 | Wind | Wind Turbine | In Service | 2022-05-03T04:00:00+00:00 | 165 | 165 | 165 | 165
MISO | J1454 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason County | Illinois | DPP-2019 | Central | GIA | Energy Resource Interconnection Service (ERIS) | Mason 138 kV Substation | 58.5 | 58.5 | Wind | Wind Turbine | In Service (with Provisional GIA) | 2021-08-18T04:00:00+00:00 | 40.9 | 40.9 | 40.9 | 0
MISO | J1455 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-09-12T04:00:00+00:00 | 2022-04-15T04:00:00+00:00 | 2022-08-01T04:00:00+00:00 | CLECO POWER LLC | St. Mary,St. Mary Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Teche - Morbihan 138kV Line | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-09-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1456 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Sheridan County | North Dakota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Harvey - Underwood 230 kV Line Tap | 300 | 300 | Wind | Wind Turbine | Not Started |  | 300 | 300 | 300 | 300
MISO | J1457 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-08-05T04:00:00+00:00 |  | 2022-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Sugar Creek - Cayuga 345 kV Line Tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1458 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-01-25T05:00:00+00:00 | 2022-08-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Washington County | Mississippi | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Ray Braswell - Tinnin - Gerald Andrus 230kV Line | 200 | 200 | Solar | Photovoltaic | Under Construction | 2024-12-15T05:00:00+00:00 | 200 | 170 | 200 | 170
MISO | J1459 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-01-27T05:00:00+00:00 |  | 2024-03-01T05:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Argenta - Tompkins 345 kV Line Tap | 670 | 670 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1460 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-06-30T04:00:00+00:00 | American Transmission Co. LLC | Rock County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Sunrise 138 kV Substation | 200 | 200 | Solar | Photovoltaic | Under Construction | 2025-06-30T04:00:00+00:00 | 200 | 200 | 200 | 170
MISO | J1461 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Carver County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | McLeod - Blue Lake 230kV Line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1462 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-06T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Acadia - Scanlan 138kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1463 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2024-06-04T04:00:00+00:00 | 2022-04-07T04:00:00+00:00 | 2021-10-20T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Baton Rouge Parish | Louisiana | DPP-2019 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Addis - Big Cajun 230 kV Line Tap (J639) | 150 | 150 | Solar | Photovoltaic | Withdrawn | 2023-11-01T04:00:00+00:00 | 150 | 45 | 150 | 0
MISO | J1464 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-30T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Macoupin County,Morgan County,Sangamon County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Meredosia - Austin 345 kV Line tap | 592.8 | 592.8 | Solar | Photovoltaic | Not Started | 2024-03-03T05:00:00+00:00 | 592.8 | 592.8 | 592.8 | 592.8
MISO | J1465 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-04-15T04:00:00+00:00 | 2022-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Pointe Coupee,Pointe Coupee Parish | Louisiana | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Livonia - Colonial Springs 138kV line | 150 | 150 | Solar | Photovoltaic | Not Started | 2024-12-01T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1466 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson County | Kentucky | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Reid EHV 161 kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started | 2025-08-01T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J1467 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ITC MIDWEST | Fayette County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | ITC 161kV Windsor - Hazleton 161kV Line | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1468 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-21T05:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | West Hastings 115kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J1469 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-08-06T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Marion - Marked Tree 161kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1470 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2019-04-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Benton County,Warren County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service only for an Existing Generating Facility (NRIS-Only) | Cayuga CT 345kV Substation | 30 | 30 | Wind | Wind Turbine | Not Started | 2023-03-21T04:00:00+00:00 | 0 | 30 | 0 | 30
MISO | J1471 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-21T05:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ITC MIDWEST | Lee County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | ITC 161kV Wever Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1472 | Done | 2019-04-29T04:00:00+00:00 |  | 2022-08-17T04:00:00+00:00 | 2022-08-01T04:00:00+00:00 | METC | Jackson County | Michigan | DPP-2019 | East (ITC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Leoni - Parr Raod 138kV line | 100 | 100 | Solar | Photovoltaic | Not Started | 2024-03-31T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1473 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chisago County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lawrence Creek - Shafer 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1474 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2023-11-14T05:00:00+00:00 | 2023-01-26T05:00:00+00:00 | 2022-07-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chippewa County | Wisconsin | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Pine Lake - Eagle Point 115kV Line | 200 | 200 | Solar | Photovoltaic | Withdrawn | 2025-07-01T04:00:00+00:00 | 200 | 200 | 180 | 180
MISO | J1475 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-04-18T04:00:00+00:00 | AMEREN ILLINOIS | Clark County | Illinois | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Casey West - Sullivan 345 kV Line Tap | 75 | 75 | Solar | Photovoltaic | Not Started | 2023-05-02T04:00:00+00:00 | 75 | 75 | 75 | 75
MISO | J1476 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2021-03-24T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | ITC MIDWEST | Union County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Creston East 69 kV Substation (J1132) | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1477 | Done | 2019-04-29T04:00:00+00:00 |  | 2023-01-26T05:00:00+00:00 | 2021-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Scott County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Sub 56 161 kV Substation (J1131) | 50 | 50 | Battery Storage | Battery Storage | Not Started | 2024-10-01T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1478 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-18T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | ITC MIDWEST | Des Moines County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Huntwoods 69 kV substation (J1135) | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 25 | 25 | 0 | 0
MISO | J1479 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-18T05:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | ITC MIDWEST | Des Moines County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Burlington 161 kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J1480 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-04-14T04:00:00+00:00 |  | 2020-08-04T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Black Hawk County | Iowa | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Shawlis - Electric Farms 161kV Line | 70 | 70 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1481 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Howard County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Greentown 230 kV substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-08-15T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1482 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2022-08-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White County | Indiana | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Monticello - Springboro 138 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started | 2024-05-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1483 | Done | 2019-04-29T04:00:00+00:00 |  |  | 2023-10-30T04:00:00+00:00 | American Transmission Co. LLC | Iowa County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Energy Resource Interconnection Service (ERIS) | Hill Valley 345 kV Substation | 99 | 99 | Wind | Wind Turbine | Not Started | 2026-09-01T04:00:00+00:00 | 99 | 0 | 99 | 0
MISO | J1484 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-01-14T05:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union County | Arkansas | DPP-2019 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Texas Eastern F SS - Strong SS 115 kV Line Tap | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1485 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2022-10-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Deuel County | South Dakota | DPP-2019 | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Astoria 345 kV Substation (J493/J510) | 250 | 250 | Wind | Wind Turbine | Not Started |  | 250 | 0 | 250 | 0
MISO | J1486 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-03-17T04:00:00+00:00 |  | 2021-12-31T05:00:00+00:00 | American Transmission Co. LLC | Waupaca County | Wisconsin | DPP-2019 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Harrison North 138kV Substation | 2.5 | 2.5 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1487 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2022-02-18T05:00:00+00:00 |  | 2021-05-01T04:00:00+00:00 | ITC MIDWEST | Freeborn County | Minnesota | DPP-2019 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Freeborn 161kV substation | 120 | 120 | Wind | Wind Turbine | Not Started |  | 120 | 120 | 0 | 0
MISO | J1488 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2024-03-31T04:00:00+00:00 | Ameren Missouri | Randolph County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | McCredie - Montgomery 345 kV Line Tap | 500 | 500 |  |  | Not Started |  | 500 | 500 | 500 | 500
MISO | J1489 | Withdrawn | 2019-04-29T04:00:00+00:00 | 2020-05-22T04:00:00+00:00 |  | 2024-03-31T04:00:00+00:00 | Ameren Missouri | Ralls County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | Maywood - Spencer Creek 345 kV Line Tap | 500 | 500 |  |  | Not Started |  | 0 | 0 | 0 | 0
MISO | J1490 | Active | 2019-04-29T04:00:00+00:00 |  |  | 2024-03-31T04:00:00+00:00 | Ameren Missouri | Randolph County | Missouri | DPP-2019 | Central | GIA | Network Resource Interconnection Service (NRIS) | McCredie - Montgomery 345 kV Line Tap | 1000 | 1000 |  |  | Not Started |  | 1000 | 1000 | 1000 | 940
MISO | J1491 | Active | 2020-06-03T04:00:00+00:00 |  |  | 2022-12-15T05:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Marion | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | IPL EW Stout North Yard 138 kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 200 | 200
MISO | J1492 | Withdrawn | 2020-06-12T04:00:00+00:00 | 2023-02-22T05:00:00+00:00 |  | 2023-08-15T04:00:00+00:00 | METC | Kent | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Gaines 138kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 150 | 150 | 0 | 0
MISO | J1493 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2021-01-05T05:00:00+00:00 |  | 2023-10-15T04:00:00+00:00 | GREAT RIVER ENERGY | Hubbard | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hubbard 115kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1494 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2023-01-31T05:00:00+00:00 |  | 2023-10-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chisago | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Chisago 115kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1495 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2023-01-31T05:00:00+00:00 |  | 2023-10-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Goodhue | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | North Rochester 161kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1496 | Withdrawn | 2020-06-18T04:00:00+00:00 |  |  | 2023-10-15T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Byron 161kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1497 | Withdrawn | 2020-06-11T04:00:00+00:00 | 2023-06-29T04:00:00+00:00 |  | 2024-10-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Jefferson | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Concord 138 kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 125 | 110 | 125 | 110
MISO | J1498 | Withdrawn | 2020-06-09T04:00:00+00:00 | 2023-01-31T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Murray | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Chanarambie 115 kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1499 | Withdrawn | 2020-06-08T04:00:00+00:00 | 2023-02-10T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | El Dorado East - Sterlington 115 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1500 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-10-30T04:00:00+00:00 | COOPERATIVE ENERGY | George | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | SE Greene Co 230kV substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1501 | Withdrawn | 2020-06-17T04:00:00+00:00 | 2021-04-20T04:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Sangamon | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Auburn North 138kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1502 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-03-31T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Juneau | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Briggs Road - North Madison 345KV | 225 | 225 | Solar | Photovoltaic | Not Started |  | 225 | 225 | 225 | 225
MISO | J1503 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ITC MIDWEST | Faribault | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Huntley 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started | 2027-10-31T04:00:00+00:00 | 150 | 120 | 150 | 120
MISO | J1504 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ITC MIDWEST | Faribault | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Huntley 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 120 | 150 | 120
MISO | J1505 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-22T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Talisheek - Bogalusa 230 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1506 | Withdrawn | 2020-06-09T04:00:00+00:00 | 2020-12-22T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Barkers Corner - Bogalusa 230 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1507 | Withdrawn | 2020-06-09T04:00:00+00:00 | 2020-12-22T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Barkers Corner - Bogalusa 230 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1508 | Active | 2020-06-19T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marathon | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | B-54 Wien to McMillan 115KV | 98.9 | 98.9 | Wind | Wind Turbine | Not Started |  | 98.9 | 98.9 | 98.9 | 98.9
MISO | J1509 | Withdrawn | 2020-06-10T04:00:00+00:00 | 2024-01-17T05:00:00+00:00 | 2023-01-18T05:00:00+00:00 | 2023-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Leflore | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Greenwood - Pickens 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started | 2026-06-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1510 | Withdrawn | 2020-06-16T04:00:00+00:00 | 2023-11-17T05:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Wood | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Arpin 345kV | 100 | 100 | Solar | Photovoltaic | Withdrawn |  | 100 | 100 | 100 | 100
MISO | J1511 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2021-01-06T05:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chisago | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Scandia to Lawrence Creek 69kV | 26 | 26 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1512 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Lafayette | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Darlington 138KV | 98.9 | 98.9 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1513 | Done | 2022-02-22T05:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Waupaca | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Clintonville | 300 | 300 | Solar | Photovoltaic | Not Started | 2026-08-01T04:00:00+00:00 | 300 | 300 | 300 | 200
MISO | J1514 | Active | 2021-12-08T05:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2020 | South | Phase 3 |  | Driver 230kV | 100 | 100 | Solar | Photovoltaic | Under Construction | 2023-03-01T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1515 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2021-01-23T05:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | METC | Midland | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Tittabawassee to Murphy 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1516 | Active | 2020-06-15T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Fitz 120kV | 100 | 100 | Solar | Photovoltaic | Not Started | 2026-08-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1517 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-10-02T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Hillsdale North 230 kV | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1518 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-10-06T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Hillsdale North 230 kV | 185 | 185 | Solar | Photovoltaic | Not Started |  | 185 | 185 | 185 | 185
MISO | J1519 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMEREN MISSOURI | Bollinger | MO | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | St. Francois to Lutesville 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1520 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ITC MIDWEST | Worth | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Ledyard - Colby 345 kV | 135 | 135 | Solar | Photovoltaic | Not Started |  | 135 | 108 | 135 | 108
MISO | J1521 | Withdrawn | 2020-06-23T04:00:00+00:00 |  |  | 2022-10-31T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Day | SD | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Big Stone to Ellendale (BS3ELR) 345kV (J933) | 199.5 | 199.5 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1522 | Withdrawn | 2020-06-12T04:00:00+00:00 | 2020-11-30T05:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | METC | Muskegon | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Grassmere 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1523 | Withdrawn | 2020-06-10T04:00:00+00:00 | 2023-02-10T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Leflore | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Greenwood - Pickens 115 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1524 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2021-01-06T05:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Pipestone | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Buffalo Ridge to Pipestone 115kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1525 | Active | 2020-06-12T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | ITC | Huron | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Grassmere 345kV | 200 | 200 | Hybrid | Photovoltaic | Not Started | 2026-04-30T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1526 | Active | 2020-06-14T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Greenwood 345kV | 200 | 200 | Hybrid | Photovoltaic | Not Started | 2026-05-13T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1527 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | METC | Ottawa | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Kenowa 345kV | 200 | 200 | Solar | Photovoltaic | Not Started | 2026-04-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1528 | Active | 2022-03-17T04:00:00+00:00 |  |  | 2024-06-06T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dunn | WI | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | EAU CLAIRE (ENDPOINT A) TO AS KING (ENDPOINT B) 345 KV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1529 | Active | 2021-04-16T04:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Carroll | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Tap Carroll (635320) - Auburn (635328) 69 kV line at about midpoint | 50 | 50 | Solar | Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
MISO | J1530 | Active | 2021-04-16T04:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Mills | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Tap Hastings (635033) - Macedonia (635069) 69 kV line at about midpoint | 50 | 50 | Solar | Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
MISO | J1531 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-05-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Sherburne | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Sheroc Substation 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1532 | Active | 2021-04-16T04:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Page | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Clarinda-Coburg 69 kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
MISO | J1533 | Withdrawn | 2020-06-18T04:00:00+00:00 |  |  | 2024-06-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Adams | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Creston-Adams County 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1534 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-06-01T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2020 | West | Phase 3 |  | Byron 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1535 | Withdrawn | 2020-06-10T04:00:00+00:00 | 2021-03-15T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Edwardsport - Peabody Tap 138 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1536 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2020-11-24T05:00:00+00:00 |  | 2024-10-31T04:00:00+00:00 | METC | Isabella | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Summerton (1) 138 kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1537 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2022-12-01T05:00:00+00:00 |  | 2024-07-04T04:00:00+00:00 | METC | Genesee | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Thetford #1 - Dort 138kV T-Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1538 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-09-16T04:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Livingston | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Hammond - Coly 230 kV | 268 | 268 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1539 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Baton Rouge | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | J683 POI 138 kV | 146 | 146 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1540 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2020-12-02T05:00:00+00:00 |  | 2024-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass | ND | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Bison-Alexandria 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1541 | Withdrawn | 2020-06-21T04:00:00+00:00 | 2020-09-18T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Donaldsonville 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1542 | Active | 2020-06-14T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. James | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Thibodaux - Vacherie 230kV | 135 | 135 | Solar | Photovoltaic | Not Started | 2026-06-01T04:00:00+00:00 | 150 | 30 | 135 | 0
MISO | J1543 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2020-09-18T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | METC | Grand Traverse | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Ludington to Keystone 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1544 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Morton | ND | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Mandan BN-Northwest Mandan 115kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1545 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2020-12-21T05:00:00+00:00 |  | 2024-01-15T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Crossett North to North Bastrop 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1546 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2020-11-24T05:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ITC | Monroe | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Milan - Monroe 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1547 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-10-01T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ITC MIDWEST | Hardin | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Killdeer to Blackhawk 345kV Line Tap | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1548 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2024-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Amo-Edwardsport IGCC 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1549 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2024-06-01T04:00:00+00:00 | ITC MIDWEST | Clinton | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Rock Creek-DeWitt 161kV line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1550 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-07-04T04:00:00+00:00 | METC | Branch | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Batavia - Tap Kinderhook distribution station, 138kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-09-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1551 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2020-12-21T05:00:00+00:00 |  | 2024-01-15T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Crossett North to North Bastrop 115 kV | 195 | 195 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1552 | Withdrawn | 2020-06-22T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | METC | Jackson | MI | DPP-2020 | East (ITC) | Phase 2 |  | Blackstone to Marshall 138kV (J1310 POI) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1553 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | METC | Clinton | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | BINGHAM | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-08-02T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1554 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-11-24T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | METC | Ionia | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | American Bumper Junction to David Junction 138Kv | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1555 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-11-24T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | METC | Hillsdale | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Moore Road Substation 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1556 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2021-02-23T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | METC | Ottawa | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Northern Fibre 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1557 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Greenwood to Banner 345 kV Line | 293 | 293 | Wind | Wind Turbine | Not Started | 2026-08-01T04:00:00+00:00 | 293 | 293 | 293 | 293
MISO | J1558 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pope | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | MORELAND | 200 | 200 | Solar | Photovoltaic | Not Started | 2026-04-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1559 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Conway | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Morrilton East Substation (161kV bus) | 200 | 200 | Solar | Photovoltaic | Under Construction | 2026-04-01T04:00:00+00:00 | 200 | 200 | 200 | 140
MISO | J1560 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2021-10-12T04:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | CLECO POWER LLC | Iberia | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Patoutville Substation (138kV bus) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1561 | Active | 2021-10-20T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-10-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Richard 138kV | 75 | 75 | Solar | Photovoltaic | Not Started | 2026-04-01T04:00:00+00:00 | 75 | 75 | 75 | 75
MISO | J1562 | Active | 2020-06-12T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Blytheville I-55 to AECC Blytheville North 161kV | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-01-31T05:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1563 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Whitesville - Wabash River 230kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1564 | Active | 2020-06-08T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Talisheek - Bogalusa 230 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-12-22T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1565 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2024-01-16T05:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Lawrence | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Bedford - Columbus 345kV line (Line #34517) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1566 | Active | 2022-02-11T05:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Martin | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Rutland Substation 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1567 | Withdrawn | 2022-02-22T05:00:00+00:00 | 2023-06-22T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Outagamie | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Werber W - Hiway 22 345 kV line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1568 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2021-01-05T05:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Renville | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Franklin 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1569 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2021-01-05T05:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Pierce | WI | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Red Wing to Herbert 69kV (Redwing - Bay City - Esdaile - Herbert) | 44 | 44 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1570 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ITC MIDWEST | Rock | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Magnolia 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1571 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | METC | Lenawee | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | MOROCCO | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-04-15T04:00:00+00:00 | 175 | 175 | 175 | 175
MISO | J1572 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-10-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Faribault | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Huntley to Blue Earth 161kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 150 | 150 | 150 | 150
MISO | J1573 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Plover 115kV | 250 | 250 | Solar | Photovoltaic | Not Started | 2026-09-01T04:00:00+00:00 | 250 | 250 | 250 | 130
MISO | J1574 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-08-03T04:00:00+00:00 |  | 2023-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Carroll | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Darnell 115kV | 99 | 99 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1575 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2025-12-01T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Marshall | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | 115 kV transmission line from Warsaw to Donaldson owned by Otter Tail Power Company | 70 | 70 | Wind | Wind Turbine | Not Started |  | 70 | 70 | 70 | 70
MISO | J1576 | Active | 2022-03-03T05:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2026-01-15T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Angie to Adams Creek 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started | 2026-11-01T04:00:00+00:00 | 200 | 70 | 200 | 0
MISO | J1577 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2024-01-15T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Hardin West SS (Endpoint A) to Sheridan (Endpoint B) 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-05-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1578 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Bartholomew | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Columbus -Greenwood Clark Twp 230kV line (Circuit ID 23019) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1579 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Edwards | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Albion-Crossville 138kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1580 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2020-11-30T05:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | METC | Ottawa | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Cobb - Archer Junction 138kV #2 | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1581 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Nobles | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | NOBLES COUNTY | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1582 | Withdrawn | 2022-02-28T05:00:00+00:00 | 2023-01-31T05:00:00+00:00 |  | 2024-06-06T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | St. Croix | WI | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Pine Lake to Three Lakes 115 kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 160 | 160 | 0 | 0
MISO | J1583 | Active | 2020-06-14T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Donaldsonville - Evergreen 230kV | 175 | 175 | Solar | Photovoltaic | Not Started | 2025-06-01T04:00:00+00:00 | 175 | 175 | 175 | 175
MISO | J1584 | Withdrawn | 2020-06-21T04:00:00+00:00 | 2020-09-18T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Toomey 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1585 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2023-11-28T05:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | AMEREN MISSOURI | Moniteau | MO | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Apache Tap - Barnett 161kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1586 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-30T04:00:00+00:00 | ITC | Calhoun | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Argenta to Tompkins 345kV line | 499 | 499 | Hybrid | Solar/Battery | Not Started | 2025-06-01T04:00:00+00:00 | 499 | 499 | 499 | 499
MISO | J1587 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | ITC | Muskegon | MI | DPP-2020 | East (ITC) | Phase 2 |  | Du Pont to Cobb 138 KV (J1375 POI) | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-09-08T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1588 | Active | 2024-04-30T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass | ND | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | BISON | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1589 | Withdrawn | 2020-06-23T04:00:00+00:00 |  |  | 2022-12-15T05:00:00+00:00 | METC | Clinton | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Hubbardston - Tech Drive 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1590 | Active | 2024-06-05T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Plymouth | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | REMSEN TOWNSHIP | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 40 | 200 | 40
MISO | J1591 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clay | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Staunton 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1592 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2023-12-08T05:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pope | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | MORRILTON EAST - Atkins 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1593 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Rush | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Greensboro-Gwynneville 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1594 | Withdrawn | 2020-06-25T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Clark | SD | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Big Stone to Ellendale 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1595 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2021-01-05T05:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Martin | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Kirk 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1596 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2021-02-24T05:00:00+00:00 |  | 2023-10-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Waushara | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Sand Lake 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1597 | Withdrawn | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | GREAT RIVER ENERGY | Wadena | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Wing River Substation 230kV | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1598 | Active | 2023-12-11T05:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Goos Ferry | 325 | 325 | Solar | Photovoltaic | Not Started | 2026-09-01T04:00:00+00:00 | 325 | 0 | 325 | 0
MISO | J1599 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | CLECO POWER LLC | Iberia | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Morbihan - Hopkins 138kV | 100 | 100 | Hybrid | Solar/Battery | Not Started | 2025-09-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1600 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2022-10-31T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Meade | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Flaherty Tap to Custer 69kV | 40 | 40 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1601 | Withdrawn | 2020-06-09T04:00:00+00:00 | 2021-03-15T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Marion | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Merom - Gibson Station Tap 345 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1602 | Active | 2021-11-02T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-04-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Rilla 115kV substation (Same as J1239) | 25 | 25 | Battery Storage | Battery Storage | Not Started | 2024-10-15T04:00:00+00:00 | 25 | 25 | 25 | 25
MISO | J1603 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | METC | Otsego | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Vantyle 138kV | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-08-02T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1604 | Active | 2020-07-10T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | HENDERSON UTILITY COMM DBA HENDERSON MUNICIPAL POWER AND LIGHT | Henderson | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | HMPL Substation #7 69kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 50 | 50 | 50 | 50
MISO | J1605 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Sherburne | MN | DPP-2020 | West | Phase 3 |  | Sherburne 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1606 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-15T05:00:00+00:00 |  | 2023-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Attica 230kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1607 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2024-01-15T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Hardin West SS to Sheridan 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started | 2025-05-01T04:00:00+00:00 | 0 | 0 | 0 | 0
MISO | J1608 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-11-24T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | METC | Ingham | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Tihart to Lovejoy Junction 138kv | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1609 | Withdrawn | 2020-06-20T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | CONSUMERS ENERGY COMPANY | St. Joseph | MI |  |  | Phase 2 | Network Resource Interconnection Service (NRIS) | Simpson 138kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1610 | Active | 2020-06-16T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | CITY WATER LIGHT & POWER | Sangamon | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Auburn North to Chatham Main 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1611 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | MINNESOTA POWER INC. | Morrison | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Langola 115kV Tap | 174 | 174 | Solar | Photovoltaic | Not Started |  | 120 | 120 | 120 | 120
MISO | J1612 | Active | 2020-06-08T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | El Dorado East - Sterlington 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started | 2024-11-24T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1613 | Withdrawn | 2020-06-25T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass | ND | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Bison Substation 345 kV | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1614 | Active | 2020-06-11T04:00:00+00:00 |  |  | 2024-02-15T05:00:00+00:00 | METC | Muskegon | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | White Road - Four Mile 138kV line | 250 | 250 | Solar | Photovoltaic | Not Started | 2025-08-26T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J1615 | Done | 2020-06-17T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Oconto | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Morgan 138kV | 150 | 150 | Solar | Photovoltaic | Not Started | 2026-08-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1616 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Edwardsport | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1617 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Bunsonville 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1618 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2024-02-09T05:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ascension | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | ST. JAMES - WELCOME 230KV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1619 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Reid Switchyard 161kV | 160 | 160 | Solar | Photovoltaic | Not Started | 2024-04-15T04:00:00+00:00 | 160 | 160 | 160 | 160
MISO | J1620 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Pipestone | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Split Rock - Pipestone 115.0kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 125 | 0 | 125 | 0
MISO | J1621 | Withdrawn | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | McPherson | SD | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Big Stone South to Ellendale 345kV | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1622 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2022-12-13T05:00:00+00:00 |  | 2024-06-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Sheridan | ND | DPP-2020 | West | Phase 3 |  | Harvey-Underwood 230kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J1623 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2024-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Orange | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Mitchell Lost River 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1624 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-08-04T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Bartholomew | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Columbus Denois Cr - Columbus 345 230 kV Transmission Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1625 | Active | 2021-08-20T04:00:00+00:00 |  |  | 2024-08-05T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tipton | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Kokomo - Tipton 230kV Transmission line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 120 | 120 | 120 | 120
MISO | J1626 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2024-08-05T04:00:00+00:00 | AMEREN ILLINOIS | Fayette | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Ramsey East 138kV bus | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1627 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2022-08-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Reynolds 345KV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1628 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2022-08-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Goodland to Reynolds 138KV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1629 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-07-18T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Columbia SW YD(ALTE) - South Fond Du Lac SW YD 345 KV T-Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1630 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Gerald Andrus-Tinnin Road 230 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1631 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-11-24T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Clark | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Stonelake to Gardner Park 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1632 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Caldwell | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Caldwell County - Barkley 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1633 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2022-03-01T05:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2020 | South | Phase 3 |  | Cooper Switching - Penton Road 230 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1634 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2022-03-01T05:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | COOPER SWITCHING - PENTON ROAD 230 KV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1635 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2022-02-01T05:00:00+00:00 | METC | Branch | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | 138kV Michigan Ave to Newton | 100 | 100 | Battery Storage | Battery Storage | Not Started | 2025-02-01T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1636 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | AMEREN MISSOURI | Pike | MO | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Peno Creek Substation 161kV | 44 | 44 | Solar | Photovoltaic | Not Started |  | 44 | 44 | 44 | 44
MISO | J1637 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Wheatland Substation 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1638 | Active | 2022-02-11T05:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Hancock | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Skillman Substation 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1639 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2022-02-01T05:00:00+00:00 | METC | Lenawee | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | 345kV Allen Junction to Morocco | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1640 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-09-22T04:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Beech Grove - Ray Braswell 115 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1641 | Active | 2024-03-15T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | HOOSIER ENERGY | Greene | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Worthington Substation 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1642 | Active | 2022-02-17T05:00:00+00:00 |  |  | 2023-10-15T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Spencer | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | North East (Castle) - Culley 138kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 200 | 200 | 200 | 200
MISO | J1643 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-11-30T05:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | METC | Genesee | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Delaney 138kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1644 | Active | 2020-06-10T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-10-01T04:00:00+00:00 | CLECO POWER LLC | St. Landry | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Champange - Plaisance | 150 | 150 | Solar | Photovoltaic | Under Construction | 2024-12-15T05:00:00+00:00 | 150 | 0 | 150 | 0
MISO | J1645 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-23T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | GREAT RIVER ENERGY | Renville | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Panther 230kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1646 | Active | 2020-06-10T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Newton | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Morrison Ditch 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1647 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-11-19T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chippewa | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Maynard XMSN 115kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1648 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-14T05:00:00+00:00 |  | 2021-08-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Searcy | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Searcy Price 161kV | 10 | 10 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1649 | Active | 2021-03-10T05:00:00+00:00 |  |  | 2022-10-31T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | McCracken | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Shell - McCracken County 69.0kV | 60 | 60 | Solar | Photovoltaic | Not Started |  | 60 | 60 | 60 | 60
MISO | J1650 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Logan | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Latham 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1651 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Logan | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Howlett 138 kV Substation | 149.5 | 149.5 | Solar | Photovoltaic | Not Started |  | 105 | 105 | 105 | 105
MISO | J1652 | Withdrawn | 2021-12-03T05:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Sidney 138kV | 116 | 116 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1653 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | San Jose Rail 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 147
MISO | J1654 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2023-02-22T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | METC | Genesee | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Goss-Thetford 345kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1655 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2022-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Jefferson | IL | DPP-2020 | Central | Phase 2 |  | West Mt Vernon - Xenia 345kV Line (J1241) | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 50 | 50
MISO | J1656 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2023-07-14T04:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Sydney to Bunsonville 345kV Line | 412 | 412 | Hybrid | Solar/Wind | Not Started |  | 0 | 0 | 0 | 0
MISO | J1657 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | St. Croix | WI | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Pine Lake to Apple River 161 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 0 | 100 | 0
MISO | J1658 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | METC | Hillsdale | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Coldwater to Moore Road 138kV Line | 180 | 180 | Solar | Photovoltaic | Not Started | 2025-12-12T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1659 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2022-02-01T05:00:00+00:00 | ITC | Washtenaw | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | 120 kV Dorset | 100 | 100 | Battery Storage | Battery Storage | Under Construction | 2025-02-01T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1660 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | METC | Genesee | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Goss-Thetford 345kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1661 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-02-23T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | ITC | Lapeer | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Imlay Pump 120kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1662 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2023-10-17T04:00:00+00:00 |  | 2023-08-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Newton | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Goodland Substation 138kV (Bus Name: 17Goodland) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1663 | Active | 2021-12-03T05:00:00+00:00 |  | 2023-03-07T05:00:00+00:00 | 2023-09-15T04:00:00+00:00 | METC | Ottawa | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Argenta to Tallmadge 345kV | 200 | 200 | Solar | Photovoltaic | Under Construction | 2025-08-02T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J1664 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Carrigan 120kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2026-09-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1665 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Carrigan 120kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1666 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2023-04-20T04:00:00+00:00 | METC | Ingham | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Oneida - Majestic 345 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1667 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2023-04-20T04:00:00+00:00 | METC | Midland | MI | DPP-2020 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Bard Rd to Clare Junction 138 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1668 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Donaldsonville - Evergreen 230 kV | 194 | 194 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1669 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2020 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | LAKE CHARLES BULK | 165 | 165 | Solar | Photovoltaic | Not Started | 2025-12-04T05:00:00+00:00 | 165 | 0 | 165 | 0
MISO | J1670 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-10-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2020 | South | Phase 3 |  | Crooked Lake 161kV at J586 POI | 50 | 50 | Solar | Photovoltaic | Not Started | 2025-03-15T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1671 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | ENTERGY TEXAS, INC. | Walker | TX | DPP-2020 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Rocky Creek to Lewis Creek 230kV | 150 | 150 | Solar | Photovoltaic | Under Construction | 2025-12-04T05:00:00+00:00 | 150 | 0 | 150 | 0
MISO | J1672 | Active | 2020-06-23T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-08-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Tinnin Road 230kV | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-11-16T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1673 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2024-01-15T05:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Fisher to Mansfield Compressor 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started | 2025-03-01T05:00:00+00:00 | 200 | 100 | 200 | 100
MISO | J1674 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-21T05:00:00+00:00 |  | 2023-08-02T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Tammany | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Talisheek - North Slidell 230kV Line | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1675 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2021-02-13T05:00:00+00:00 |  | 2023-12-15T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Edgar | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Kansas 345kV | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1676 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-04-20T04:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Brokaw - Clinton 345 kV line | 300 | 300 | Wind | Wind Turbine | Not Started |  | 300 | 300 | 300 | 300
MISO | J1677 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-04-20T04:00:00+00:00 | AMEREN ILLINOIS | Macon | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Leghorn 345 kV | 180 | 180 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1678 | Active | 2022-04-06T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Deedsville 345 kV | 74.7 | 74.7 | Battery Storage | Battery Storage | Not Started |  | 74.7 | 74.7 | 74.7 | 74.7
MISO | J1679 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-04-20T04:00:00+00:00 | AMEREN ILLINOIS | Clay | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Xenia - West Mt Vernon 345 kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 125 | 125 | 125 | 125
MISO | J1680 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-04-20T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Cass | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | 345 kV Walton Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1681 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2024-10-31T04:00:00+00:00 | AMEREN MISSOURI | Maries | MO | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Bland to Franks 345kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1682 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Boone | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Hortonville to Whitestown 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1683 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-14T05:00:00+00:00 |  | 2023-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Babcock - Lake George 345 kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1684 | Active | 2023-08-04T04:00:00+00:00 |  |  | 2025-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC |  |  | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) |  | 0 | 0 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1685 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-09-24T04:00:00+00:00 |  | 2023-09-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ascension | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Donaldsonville to Evergreen 230kV line | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1686 | Active | 2022-07-07T04:00:00+00:00 |  |  | 2023-09-04T04:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Coughlin - Plaisance 138 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started | 2026-09-01T04:00:00+00:00 | 100 | 100 | 100 | 70
MISO | J1687 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | HOOSIER ENERGY | Decatur | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Decatur Switching Station 161kv | 160 | 160 | Solar | Photovoltaic | Not Started |  | 160 | 160 | 160 | 160
MISO | J1688 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-10-02T04:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Rising 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1689 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Cadiz 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1690 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-03-15T04:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Lewisville 138kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1691 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Sullivan | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Merom - Gibson 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1692 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-03T05:00:00+00:00 |  | 2023-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Cass | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Walton 345 kV Substation | 65 | 65 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1693 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-11-19T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chippewa | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Maynard XMSN 115kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1694 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2024-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Lawrence | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Lost River 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1695 | Active | 2023-12-12T05:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Aster 138kV Substation (Rebuild of North Coulterville 138kV) | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 50 | 50
MISO | J1696 | Active | 2020-06-11T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Reid EHV 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1697 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Lawrence | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Shawswick to Pleasant Grove 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1698 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-21T05:00:00+00:00 |  | 2023-08-02T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Tammany | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Talisheek - North Slidell 230kV Line | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1699 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | HOOSIER ENERGY | Shelby | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | HE Lewis Creek 69 kV | 43 | 43 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1700 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-10-22T04:00:00+00:00 |  | 2023-04-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Johnson | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | FRANKLIN 230KV | 288 | 288 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1701 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | AMEREN ILLINOIS | McDonough | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Macomb to Ipava 138kV line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 200 | 200
MISO | J1702 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-14T05:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Shelby | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Faraday 345 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1703 | Withdrawn | 2022-02-11T05:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Webster | KY | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Reid to Hopkins County 161kV | 74 | 74 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1704 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2023-11-28T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Shelby | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Gwynneville 345kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 50 | 50
MISO | J1705 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-02-23T05:00:00+00:00 |  | 2024-02-20T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | South Fond du Lac (Endpoint A) to Columbia (Endpoint B) 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1706 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Green | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | North Monroe 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1707 | Withdrawn | 2021-10-22T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Dubois | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | DUFF 345KV | 72 | 72 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1708 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2023-06-22T04:00:00+00:00 |  | 2025-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Grant | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | J947 Interconnection Substation | 75 | 75 | Solar | Photovoltaic | Not Started |  | 75 | 75 | 75 | 75
MISO | J1709 | Active | 2022-01-21T05:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2022-02-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Grimes | TX | DPP-2020 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | 138 kV Grimes | 100 | 100 | Battery Storage | Battery Storage | Not Started | 2025-02-01T05:00:00+00:00 | 100 | 0 | 100 | 0
MISO | J1710 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-13T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | KEO EHV | 300 | 300 | Solar | Photovoltaic | Not Started | 2026-09-13T04:00:00+00:00 | 300 | 300 | 300 | 300
MISO | J1711 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-11-30T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Green | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | North Monroe 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1712 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2022-12-15T05:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | North Coulterville - COMM 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 300 | 300 | 300 | 300
MISO | J1713 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Macon | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Faraday (138 kV) | 147.2 | 147.2 | Wind | Wind Turbine | Not Started |  | 147.19 | 147.19 | 147.19 | 147.19
MISO | J1714 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Fayette | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Ramsey East 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1715 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | HOOSIER ENERGY | Decatur | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | HE Westport 138kV | 145 | 145 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1716 | Done | 2020-06-24T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Fond du Lac | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Fitzgerald to South Fond Du Lac 345 kV | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-08-01T04:00:00+00:00 | 100 | 0 | 100 | 0
MISO | J1717 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Decatur | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Greensburg 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1718 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-09-18T04:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Bunsonville 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1719 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Waushara | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Sand Lake 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1720 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2024-05-20T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Fountain Prairie -North Randolph 138kV Transmission Line | 99 | 99 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1721 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Vigo-Worthington 138kV | 175.12 | 175.12 | Solar | Photovoltaic | Not Started |  | 175.12 | 175.12 | 175.12 | 175.12
MISO | J1722 | Withdrawn | 2020-06-22T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2024-02-09T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Galloway - Remigton 115kV Transmission Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1723 | Withdrawn | 2021-11-02T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2020 | South | Phase 3 |  | Wynne East to Wynne South 161kV line (J1125 sub) | 10 | 10 | Battery Storage | Battery Storage | Not Started |  | 10 | 10 | 10 | 10
MISO | J1724 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | LNG - STILLWELL 138kV line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1725 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | San Jose Rail Splitter 138KV (G515) | 100 | 100 | Wind | Wind Turbine | Not Started |  | 100 | 100 | 100 | 100
MISO | J1726 | Active | 2020-06-15T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Pulaski | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Reynolds - Burr 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1727 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | ITC MIDWEST | Hancock | IA | DPP-2020 | West | Phase 3 |  | Lime Creek 161kV | 33.75 | 33.75 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1728 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | ITC MIDWEST | Story | IA | DPP-2020 | West | Phase 3 |  | Story County Substation 161kV | 39 | 39 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1729 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | ITC MIDWEST | Hancock | IA | DPP-2020 | West | Phase 3 |  | Lime Creek 161kV | 43 | 43 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1730 | Active | 2022-03-17T04:00:00+00:00 |  |  | 2024-06-06T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dunn | WI | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Eau Claire to AS King 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 300 | 300 | 300 | 300
MISO | J1731 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-03-12T05:00:00+00:00 |  | 2022-02-01T05:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Madison | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Noblesville to Fall Creek 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1732 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2024-12-31T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | LEWISTON ACEC A03-TRIENDA (138KV ) | 98.4 | 98.4 | Solar | Photovoltaic | Not Started |  | 98.4 | 98.4 | 98.4 | 98.4
MISO | J1733 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | ITC MIDWEST | Allamakee | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lansing 161 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1734 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | ITC MIDWEST | Lee | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Wever 161 kV | 150 | 150 | Solar | Photovoltaic | Not Started | 2024-06-30T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J1735 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2023-06-22T04:00:00+00:00 |  | 2025-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Rock | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | J1304 POI 138 kV Substation | 75 | 75 | Solar | Photovoltaic | Not Started |  | 75 | 75 | 75 | 75
MISO | J1736 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Dubois | IN | DPP-2020 | Central | Phase 2 |  | Duff 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1737 | Withdrawn | 2021-10-22T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Rush | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Gwynville 345 kV | 210 | 210 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1738 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-02T05:00:00+00:00 |  | 2023-05-15T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | McPherson | SD | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Leola Substation 41.6kV | 20 | 20 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1739 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-02-23T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Waushara | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Sand Lake 138kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1740 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Walworth | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | University to Mukwanago 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1741 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-03T05:00:00+00:00 |  | 2023-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Cass | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Walton 345kV Substation | 270 | 270 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1742 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-14T05:00:00+00:00 |  | 2023-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Babcock - Lake George 345 kV | 294.1 | 294.1 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1743 | Active | 2022-04-06T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Deedsville 345 kV Substation | 292.9 | 292.9 | Solar | Photovoltaic | Not Started |  | 292.89 | 292.89 | 292.89 | 292.89
MISO | J1744 | Active | 2022-04-05T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Hutsonville - Neoga 138 kV | 149.5 | 149.5 | Solar | Photovoltaic | Not Started |  | 149.5 | 149.5 | 149.5 | 149.5
MISO | J1745 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Winnebago | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Fitzgerald 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1746 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Columbia 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1747 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2022-02-28T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | J830 POI | 50 | 50 | Solar | Photovoltaic | Under Construction | 2024-07-31T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J1748 | Active | 2020-07-17T04:00:00+00:00 |  | 2022-11-29T05:00:00+00:00 | 2023-08-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | DeSoto | MS | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Twinkletown 230 kV | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-04-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1749 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2022-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Baton Rouge | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Addis - Big Cajun 230kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1750 | Active | 2022-04-06T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marquette | MI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Huron - Empire 138kV line | 149.7 | 149.7 | Solar | Photovoltaic | Not Started |  | 149.7 | 149.7 | 149.7 | 149.7
MISO | J1751 | Active | 2022-04-06T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Wood | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | ACEC Badger West - Saratoga 138 kV | 150.5 | 150.5 | Solar | Photovoltaic | Not Started |  | 150.5 | 150.5 | 150.5 | 150.5
MISO | J1752 | Active | 2022-05-06T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Golden Sands - Arnott (O-119) | 148.1 | 148.1 | Solar | Photovoltaic | Not Started |  | 148.1 | 148.1 | 148.1 | 148.1
MISO | J1753 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-12-01T05:00:00+00:00 |  | 2024-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Green | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Columbia-South Fond du Lac 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1754 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2022-12-12T05:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | GREAT RIVER ENERGY | McHenry | ND | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | McHenry ND | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J1755 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2022-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Bureau | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Bureau County 138 kV | 147.2 | 147.2 | Wind | Wind Turbine | Not Started |  | 147.19 | 147.19 | 147.19 | 147.19
MISO | J1756 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-03-31T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Shelby | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Gwynneville to Sunnyside 345kV | 309 | 309 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1757 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-14T05:00:00+00:00 |  | 2023-04-20T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Coles | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Kansas - Faraday 345 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1758 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Barnes | ND | DPP-2020 | West | Phase 3 |  | Pillsburry Substation 230kV | 42 | 42 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1759 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2024-01-15T05:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2020 | South | Phase 3 |  | Fisher to Mansfield Compressor 230 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started | 2025-03-01T05:00:00+00:00 | 0 | 0 | 0 | 0
MISO | J1760 | Active | 2020-06-15T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-10-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Timberland 230kV | 205 | 205 | Solar | Photovoltaic | Not Started | 2023-06-01T04:00:00+00:00 | 215 | 60 | 205 | 60
MISO | J1761 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Barnes | ND | DPP-2020 | West | Phase 3 |  | Maple River 230kV | 39 | 39 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1762 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-02-19T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Iron | MI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Crystal Falls - Aspen 69 kV | 22.5 | 22.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1763 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-21T05:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Cavalier | ND | DPP-2020 | West | Phase 3 |  | Langdon Substation 115kV | 33 | 33 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1764 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2020-12-01T05:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | WABASH VALLEY POWER ASSOCIATION, INC. | Perry | MO | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Seminary/Perryville 138kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1765 | Withdrawn | 2020-06-11T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tipton | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Tipton West Substation 230kV | 93.2 | 93.2 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1766 | Withdrawn | 2020-06-24T04:00:00+00:00 |  |  | 2023-10-15T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Fallon | MT | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Keystone XL (Pumping station - 14) - 115kV | 20 | 20 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1767 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | ITC MIDWEST | Hancock | IA | DPP-2020 | West | Phase 3 |  | Burt to Emery 161kV | 37 | 37 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1768 | Withdrawn | 2020-06-16T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Orange | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Lost River Substation 345 | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1769 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-10-01T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Howard | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Beaver Creek to Rice 161 kV line tap (same POI as J898) | 120 | 120 | Wind | Wind Turbine | Not Started |  | 80 | 0 | 80 | 0
MISO | J1770 | Active | 2020-06-19T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2020 | Central | Phase 2 | Energy Resource Interconnection Service (ERIS) | Hoopston 138kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 0 | 150 | 0
MISO | J1771 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-03-15T04:00:00+00:00 |  | 2023-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Casey - Sullivan 345 kV | 197.3 | 197.3 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1772 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Reynolds 345KV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1773 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Lafayette | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Hill Valley to Cardinal 345kV | 300 | 300 | Wind | Wind Turbine | Not Started | 2027-04-01T04:00:00+00:00 | 300 | 300 | 300 | 300
MISO | J1774 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2023-07-20T04:00:00+00:00 |  | 2023-05-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Warren | IN | DPP-2020 | Central | Phase 2 |  | Cayuga 345kV | 50 | 50 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1775 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-11-11T05:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Calumet | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Forest Junction Substation 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1776 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | ITC MIDWEST | Osceola | IA | DPP-2020 | West | Phase 3 |  | Dickinson County Switch Yard 161kV | 34 | 34 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1777 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Aster 138kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1778 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Kenosha | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Paris 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 50 | 100 | 50
MISO | J1779 | Active | 2021-09-01T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dane | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Rockdale 345kV substation | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 200 | 200 | 200 | 200
MISO | J1780 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-08-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Other_ | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1781 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Lafayette | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Hill Valley 345kV | 300 | 300 | Wind | Wind Turbine | Under Construction | 2027-04-01T04:00:00+00:00 | 300 | 300 | 300 | 300
MISO | J1782 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | WABASH RIVER GEN. STA. TO WHITESVILLE SOUTH SUB 230kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1783 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | WABASH RIVER GEN. STA. TO WHITESVILLE SOUTH SUB 230 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1784 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | New Castle to Hagerstown 69 kV | 39 | 39 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1785 | Active | 2022-01-11T05:00:00+00:00 |  |  | 2024-07-12T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Maple 69 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 100 | 100
MISO | J1786 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Sullivan | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Merom - Gibson 345kv | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J1787 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-09-22T04:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2020 | South | Phase 3 |  | Beech Grove - Ray Braswell 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1788 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-09-24T04:00:00+00:00 |  | 2023-02-28T05:00:00+00:00 | CLECO POWER LLC | St. Mary | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Caneland 230 kV | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1789 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Brinkley East to Clarendon 115 kV | 5.99 | 5.99 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1790 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2023-02-16T05:00:00+00:00 |  | 2022-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ashley | AR | DPP-2020 | South | Phase 3 |  | Crossett - Monticello East 115 kV Line | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1791 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2020 | South | Phase 3 |  | Gerald Andrus-Tinnin Road 230 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1792 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-02-19T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Houghton | MI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | New Tap of the Ontonagan to Rockland Jct 69kV Line approx. 2.2 mi. north of Rockland Jct. | 22.5 | 22.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1793 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Sheboygan | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Holland 138 kV | 75 | 75 | Solar | Photovoltaic | Not Started |  | 75 | 75 | 75 | 75
MISO | J1794 | Active | 2020-06-22T04:00:00+00:00 |  | 2022-11-18T05:00:00+00:00 | 2023-08-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2020 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Richard to Scott 138kV line | 150 | 150 | Solar | Photovoltaic | Not Started | 2025-05-26T04:00:00+00:00 | 150 | 0 | 150 | 0
MISO | J1795 | Active | 2020-06-22T04:00:00+00:00 |  |  | 2023-08-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2020 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Bayou Cove to Richard 138kV (Circuit 258) | 100 | 100 | Solar | Photovoltaic | Not Started | 2025-12-04T05:00:00+00:00 | 100 | 0 | 100 | 0
MISO | J1796 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-02-28T05:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Pine Prairie to Coughlin 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1797 | Withdrawn | 2020-06-18T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. John the Baptist | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Waterford 230kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1798 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2021-06-01T04:00:00+00:00 | ITC | Wayne | MI | DPP-2020 | East (ITC) | Phase 2 |  | Waterman 120kV | 0 | 25 | Gas | Combined Cycle | Not Started |  | 25 | 0 | 25 | 0
MISO | J1799 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2021-02-13T05:00:00+00:00 |  | 2022-02-15T05:00:00+00:00 | AMEREN ILLINOIS | Pulaski | IL | DPP-2020 | Central | Phase 2 | External Network Resource Interconnection Service (E-NRIS) | Joppa 345 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1800 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-10-08T04:00:00+00:00 |  | 2023-12-01T05:00:00+00:00 | ITC MIDWEST | Mower | MN | DPP-2020 | West | Phase 3 |  | Adams Switch Yard 161kV | 25 | 25 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1801 | Withdrawn | 2020-06-25T04:00:00+00:00 |  |  | 2023-12-01T05:00:00+00:00 | ITC MIDWEST | Story | IA | DPP-2020 | West | Phase 3 |  | Story County Substation 161kV | 39 | 39 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1802 | Active | 2020-06-18T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Marshall | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Burr Oak 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 150 | 150
MISO | J1803 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2023-02-28T05:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Houghton | MI | DPP-2020 | East (ATC) | Phase 3 |  | Winona-Atlantic 69 kV | 1.6 | 1.6 | Wind | Wind Turbine | Not Started |  | 1.6 | 1.6 | 0 | 0
MISO | J1804 | Withdrawn | 2022-02-28T05:00:00+00:00 | 2023-01-31T05:00:00+00:00 |  | 2024-06-06T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | St. Croix | WI | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | PINE LAKE TO THREE LAKES 115 KV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1805 | Active | 2022-01-11T05:00:00+00:00 |  |  | 2024-04-12T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Maple 69 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1806 | Withdrawn | 2020-06-20T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry | IN | DPP-2020 | Central | Phase 2 |  | Greensboro Substation 345kV | 30 | 30 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1807 | Withdrawn | 2020-06-23T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2023-05-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Washington | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Mount Tabor 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1808 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-02-28T05:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Barron | WI | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Barron 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 148 | 0 | 148 | 0
MISO | J1809 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-02-19T05:00:00+00:00 |  | 2023-08-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Houghton | MI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Atlantic -Silver River 138 kV | 62.5 | 62.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1810 | Withdrawn | 2020-06-20T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2023-09-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Reynolds 345kV to Burr Oaks 345kV | 60 | 60 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1811 | Withdrawn | 2020-06-19T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Independence | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Independence 161 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1812 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2024-09-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Chambers | TX | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Stowell 230 kV | 294.25 | 294.25 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1813 | Active | 2022-07-07T04:00:00+00:00 |  |  | 2020-03-20T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | DeSoto | MS | DPP-2020 | South | Phase 3 |  | Entergy Freeport 230 kV Substation | 920 | 1005 | Gas | Combined Cycle | Not Started |  | 205 | 0 | 205 | 0
MISO | J1814 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dickinson | MI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Nordic | 22.5 | 22.5 | Solar | Photovoltaic | Not Started | 2026-09-15T04:00:00+00:00 | 22.5 | 22.5 | 22.5 | 22.5
MISO | J1815 | Active | 2022-03-16T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Linden Junction - Crawfordsville 138 kV | 180 | 180 | Solar | Photovoltaic | Not Started |  | 130 | 130 | 130 | 130
MISO | J1816 | Active | 2022-03-17T04:00:00+00:00 |  |  | 2024-01-15T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Fisher (Endpoint A) to Cherry Valley (Endpoint B) 161 kV line | 135 | 135 | Solar | Photovoltaic | Not Started | 2025-11-01T04:00:00+00:00 | 135 | 100 | 135 | 100
MISO | J1817 | Withdrawn | 2020-07-28T04:00:00+00:00 | 2023-02-28T05:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Houghton | MI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | ATC WInona-Atlantic Minw 69 kV tap (J1244) | 20 | 20 | Wind | Wind Turbine | Not Started |  | 20 | 20 | 0 | 0
MISO | J1818 | Active | 2020-06-19T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-10-01T04:00:00+00:00 | LAFAYETTE UTILITIES SYSTEM | Lafayette | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Northeast (Moss) 69kV | 80 | 80 | Solar | Photovoltaic | Not Started | 2026-06-30T04:00:00+00:00 | 80 | 80 | 80 | 80
MISO | J1819 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-13T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | KEO EHV | 0 | 0 | Battery Storage | Battery Storage | Not Started | 2026-09-13T04:00:00+00:00 | 0 | 0 | 0 | 0
MISO | J1820 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-13T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Entergy Keo-West Memphis 500kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started | 2026-09-13T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J1821 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-09-13T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Entergy Keo -West Memphis 500kV Line tap | 0 | 0 | Battery Storage | Battery Storage | Not Started | 2026-09-13T04:00:00+00:00 | 0 | 0 | 0 | 0
MISO | J1822 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-01-04T05:00:00+00:00 |  | 2023-06-01T04:00:00+00:00 | ITC MIDWEST | Franklin | IA | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | KILLDEER3 (631199) 345 KV TO BLACKHAWK (636199) 345 kv line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1823 | Withdrawn | 2020-06-24T04:00:00+00:00 | 2021-02-19T05:00:00+00:00 |  | 2023-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Houghton | MI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Portage (UPPCO) - Atlantic 69 kV | 62.5 | 62.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1824 | Active | 2020-06-24T04:00:00+00:00 |  |  | 2024-12-31T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2020 | East (ATC) | Phase 3 | Network Resource Interconnection Service (NRIS) | Academy 138KV | 73.8 | 73.8 | Solar | Photovoltaic | Not Started |  | 67 | 67 | 67 | 67
MISO | J1825 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2020-12-18T05:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Decatur | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Westport | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1826 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2022-03-01T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota | MN | DPP-2020 | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Cannon Falls Transmission 69 kV | 4 | 4 | Hydro | Hydroelectric | Not Started | 2024-08-30T04:00:00+00:00 | 4 | 0 | 4 | 0
MISO | J1827 | Active | 2021-10-20T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2023-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Bastrop tap point | 90 | 90 | Solar | Photovoltaic | Not Started | 2026-04-01T04:00:00+00:00 | 90 | 90 | 90 | 0
MISO | J1828 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-03-12T05:00:00+00:00 |  | 2024-08-20T04:00:00+00:00 | AMEREN ILLINOIS | Sangamon | IL | DPP-2020 | Central | Phase 2 | Energy Resource Interconnection Service (ERIS) | Austin-1 138 kV substation | 99.2 | 99.2 | Hybrid | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J1829 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Shelby | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | DEI's Columbus to Clark Twp. 230 kV (one of the two 230 kV circuits going from Columbus to Five Poin | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1830 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Pulaski | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Kelso - Joppa (Massac) 345 kV line | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 200 | 200 | 200 | 200
MISO | J1831 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Menard | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Shockey 138kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 200 | 200
MISO | J1832 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | CLECO POWER LLC | St. Landry | LA | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Plaisance 138kV | 145.09 | 145.09 | Solar | Photovoltaic | Under Construction | 2024-07-15T04:00:00+00:00 | 150 | 150 | 145 | 90
MISO | J1833 | Active | 2021-10-19T04:00:00+00:00 |  | 2023-01-18T05:00:00+00:00 | 2026-05-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lafourche | LA | DPP-2020 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | Leeville 115kV | 115.1 | 115.1 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started | 2025-10-01T04:00:00+00:00 | 115.1 | 115.1 | 115.1 | 0
MISO | J1834 | Active | 2021-12-16T05:00:00+00:00 |  |  | 2025-04-25T04:00:00+00:00 | ENTERGY TEXAS, INC. | Orange | TX | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Sabine 138/230 kV Substation | 66.7 | 126 | Gas | Combined Cycle | Not Started | 2025-05-25T04:00:00+00:00 | 126 | 66.7 | 126 | 66.7
MISO | J1835 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-06-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Spencer | IN | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Culley to Grandview 138 KV line tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 200 | 200
MISO | J1836 | Active | 2020-06-23T04:00:00+00:00 |  |  | 2025-08-01T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Montgomery- Callaway- 7 | 300 | 300 | Solar | Photovoltaic | Not Started |  | 300 | 300 | 300 | 300
MISO | J1837 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-03-12T05:00:00+00:00 |  | 2023-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Shelby | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Pana - Route 51 138kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1838 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-02-23T05:00:00+00:00 |  | 2025-02-12T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dane | WI | DPP-2020 | East (ATC) | Phase 3 |  | Christiana 138 kV | 320 | 320 | Gas | Combined-Cycle – Steam Plant | Not Started |  | 0 | 0 | 0 | 0
MISO | J1839 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2027-01-01T05:00:00+00:00 | AMEREN ILLINOIS | Macon | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Decatur ADM North 138 kV | 325 | 340.3 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 340.3 | 340.3 | 340.3 | 340.3
MISO | J1840 | Active | 2020-06-25T04:00:00+00:00 |  |  | 2023-08-30T04:00:00+00:00 | AMEREN ILLINOIS | De Witt | IL | DPP-2020 | Central | Phase 2 | Network Resource Interconnection Service (NRIS) | Clinton to Goose Creek-4545 345kV line | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 250 | 250
MISO | J1841 | Withdrawn | 2020-06-25T04:00:00+00:00 | 2021-12-08T05:00:00+00:00 |  | 2023-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2020 | South | Phase 3 | Network Resource Interconnection Service (NRIS) | Forrest City to Wynne S 161 KV Line | 52 | 52 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1842 | Active | 2021-10-19T04:00:00+00:00 |  |  | 2026-02-02T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2020 | South | Phase 3 | Energy Resource Interconnection Service (ERIS) | FORREST CITY N SS - WYNNE SOUTH 161.0kV | 135 | 135 | Wind | Wind Turbine | Not Started | 2024-10-31T04:00:00+00:00 | 135 | 0 | 135 | 0
MISO | J1843 | Withdrawn | 2022-01-06T05:00:00+00:00 | 2023-06-22T04:00:00+00:00 |  | 2023-03-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dane | WI | DPP-2020 | East (ATC) | Phase 3 |  | Christiana 138 kV | 12 | 12 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 12 | 12 | 12 | 12
MISO | J1844 | Active | 2020-12-31T05:00:00+00:00 |  |  | 2024-10-07T04:00:00+00:00 | ITC | Washtenaw | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | 19CVTRY | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J1845 | Active | 2020-12-31T05:00:00+00:00 |  |  | 2025-10-06T04:00:00+00:00 | METC | Calhoun | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | 18BATTLC | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J1846 | Active | 2021-07-22T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | GREAT RIVER ENERGY | Renville | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Panther 230kV Substation | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 200 | 200 | 0 | 0
MISO | J1847 | Active | 2021-08-09T04:00:00+00:00 |  |  | 2024-06-01T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Mower | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Murphy Creek 161kV substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1848 | Withdrawn | 2021-08-12T04:00:00+00:00 | 2023-08-15T04:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | ITC | Van Buren | MI | DPP-2021 | East (ITC) | Phase 1 |  | Covert | 1128 | 1235 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J1849 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Cypress 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 0 | 0 | 0
MISO | J1850 | Active | 2021-11-24T05:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Martin | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Kirk - Cecelia 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 0 | 0 | 0
MISO | J1851 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Crossett North to North Bastrop 115 kV | 195 | 195 | Solar | Photovoltaic | Not Started |  | 195 | 80 | 0 | 0
MISO | J1852 | Withdrawn | 2022-06-16T04:00:00+00:00 | 2023-10-09T04:00:00+00:00 |  | 2025-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Bison 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1853 | Withdrawn | 2021-08-17T04:00:00+00:00 | 2023-10-09T04:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | ITC MIDWEST | Des Moines | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Denmark - Newport | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1854 | Withdrawn | 2021-08-18T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Wabash | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Wabash - Greentown 138kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J1855 | Active | 2021-11-17T05:00:00+00:00 |  |  | 2026-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | MALLORY 161 | 500 | 500 | Solar | Photovoltaic | Not Started |  | 500 | 500 | 0 | 0
MISO | J1856 | Active | 2021-11-17T05:00:00+00:00 |  |  | 2026-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | SHOFFNER - NEWPORT | 150 | 150 | Solar | Photovoltaic | Not Started |  | 147 | 147 | 0 | 0
MISO | J1857 | Active | 2021-11-17T05:00:00+00:00 |  |  | 2026-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | EBONY SS - 5WM LEHI-W | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
MISO | J1858 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2026-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Sandy Bayou | 440 | 440 | Solar | Photovoltaic | Not Started |  | 440 | 440 | 0 | 0
MISO | J1859 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pottawattamie | IA | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Council Bluffs - Fallow Avenue 345kV Line Tap | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J1860 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | METC | Lenawee | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Morocco to Beecher 138kV (8.36 miles from Morocco) | 60 | 60 | Battery Storage | Battery Storage | Not Started |  | 60 | 60 | 0 | 0
MISO | J1861 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | LNG - STILLWELL 138kV Line | 45 | 45 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1862 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | METC | Clinton | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Bingham West 138kV | 45 | 45 | Battery Storage | Battery Storage | Not Started |  | 45 | 45 | 0 | 0
MISO | J1863 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | METC | Otsego | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Vantyle 138kV | 60 | 60 | Battery Storage | Battery Storage | Not Started |  | 60 | 60 | 0 | 0
MISO | J1864 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo | IA | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Emery 161kV | 250 | 250 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J1865 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ITC MIDWEST | Hardin | IA | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Quinn-Blackhawk 345kV | 250 | 250 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J1866 | Withdrawn | 2021-08-16T04:00:00+00:00 | 2023-10-09T04:00:00+00:00 |  | 2024-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Clark | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | T Corners 115kV Sub | 125 | 125 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1867 | Active | 2021-11-22T05:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | ITC MIDWEST | Franklin | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Quinn | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J1868 | Withdrawn | 2021-08-16T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Winn | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Winnfield to Standard 115kV | 260 | 260 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1869 | Withdrawn | 2021-08-16T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Winn | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Winnfield to Standard 115kV | 78 | 78 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1870 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Independence Substation 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1871 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Independence Substation 230kV | 60 | 60 | Battery Storage | Battery Storage | Not Started |  | 60 | 60 | 0 | 0
MISO | J1872 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | El Dorado 500kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
MISO | J1873 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | El Dorado 500kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
MISO | J1874 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | El Dorado 500kV Substation | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 75 | 75 | 0 | 0
MISO | J1875 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | El Dorado 500kV Substation | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 75 | 75 | 0 | 0
MISO | J1876 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Decatur | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Greensburg | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1877 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Decatur | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Greensburg 138kV | 45 | 45 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1878 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Decatur | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | HE Westport 138kV | 145 | 145 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J1879 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Decatur | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | HE Westport 138kV | 43.5 | 43.5 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J1880 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | METC | Ottawa | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Argenta to Tallmadge 345kV (33 miles from Argenta) | 60 | 60 | Battery Storage | Battery Storage | Not Started |  | 60 | 60 | 0 | 0
MISO | J1881 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | HOOSIER ENERGY | Decatur | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Decatur Switching Station 161kV | 48 | 48 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J1882 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | San Jose Rail 138kV | 45 | 45 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1883 | Active | 2021-07-21T04:00:00+00:00 |  |  | 2023-06-10T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita | LA | DPP-2021 | South | Phase 1 |  | Rilla 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 100 | 0 | 0
MISO | J1884 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Columbia 345 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J1885 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | REID EHV 345 KV SUBSTATION | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1886 | Withdrawn | 2021-08-17T04:00:00+00:00 | 2022-11-22T05:00:00+00:00 |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | REID EHV 345 KV SUBSTATION | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1887 | Withdrawn | 2021-08-13T04:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Martin | LA | DPP-2021 | South |  | Network Resource Interconnection Service (NRIS) | St John 69kV | 90 | 90 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J1888 | Active | 2022-01-25T05:00:00+00:00 |  |  | 2024-04-01T04:00:00+00:00 | MINNESOTA POWER INC. | Oliver | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | SQUARE BUTTE EAST 230 kV (AC side) | 175 | 175 | Wind | Wind Turbine | Not Started |  | 175 | 175 | 0 | 0
MISO | J1889 | Active | 2021-08-04T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | ITC MIDWEST | Linn | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Mt Vernon Substation | 60 | 60 | Solar | Photovoltaic | Not Started |  | 60 | 60 | 0 | 0
MISO | J1890 | Active | 2021-11-17T05:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Hartburg - AEP Layfield 500 kV | 270 | 270 | Solar | Photovoltaic | Not Started |  | 270 | 270 | 0 | 0
MISO | J1891 | Active | 2021-08-19T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Attala | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | 230 kV McAdams Substation | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 200 | 200 | 0 | 0
MISO | J1892 | Withdrawn | 2021-08-24T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | METC | Otsego | MI | DPP-2021 | East (ITC) |  | Network Resource Interconnection Service (NRIS) | Livingston - Keystone 345 kV | 64.8 | 64.8 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J1893 | Active | 2021-11-01T04:00:00+00:00 |  |  | 2024-04-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Morton | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Mandan 230 kV | 500 | 500 | Wind | Wind Turbine | Not Started |  | 500 | 500 | 0 | 0
MISO | J1894 | Active | 2021-10-29T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | METC | Kalamazoo | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Jaguar | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J1895 | Active | 2023-10-03T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Kenosha | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | BALSAM | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J1896 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Henderson to AB Brown 138 kV | 100 | 100 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J1897 | Active | 2021-12-14T05:00:00+00:00 |  |  | 2024-08-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | DELL EHV - SAN SOUCI 500.0kV | 500 | 500 | Hybrid | Solar/Battery | Not Started |  | 500 | 500 | 0 | 0
MISO | J1898 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Byron 161 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J1899 | Active | 2021-12-22T05:00:00+00:00 |  |  | 2024-08-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | DELL EHV - SAN SOUCI 500.0kV | 500 | 500 | Hybrid | Solar/Battery | Not Started |  | 500 | 500 | 0 | 0
MISO | J1900 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | ITC | Wayne | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | BROWNSTOWN 120kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J1901 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Webster | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | South Henderson 161kV (future) | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1902 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | ITC | Wayne | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | IRONTON 120 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J1903 | Active | 2021-08-03T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ITC MIDWEST | Osceola | IA | DPP-2021 | West | Study Not Started |  | Osceola (43.431167, -95.416667) | 140 | 140 | Wind | Wind Turbine | Not Started |  | 0 | 140 | 0 | 0
MISO | J1904 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2025-11-08T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Richard 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 0 | 0 | 0
MISO | J1905 | Withdrawn | 2021-08-23T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Banner-Rapson 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1906 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Bogalusa 230 | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J1907 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | ENTERGY TEXAS, INC. | Newton | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Hartburg 230 | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J1908 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Cocodrie | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J1909 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Gallagher-Tittabawassee 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1910 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Gallagher-Tittabawassee 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1911 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Livingston | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Madrid - Blackfoot 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1912 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Greenwood-Rapson 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1913 | Withdrawn | 2021-08-19T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Midland | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Murphy-Tittabawassee 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1914 | Active | 2023-10-05T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | METC | Presque Isle | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Rockport-Port calcite 138kV Transmission line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1915 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Almeda Junction-Shale 138kV Transmission Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1916 | Active | 2023-10-19T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | METC | Branch | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Newton 138 kV substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J1917 | Active | 2021-08-19T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | ITC | Livingston | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Madrid- Majestic 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 165 | 165 | 0 | 0
MISO | J1918 | Active | 2021-08-24T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | METC | Montcalm | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Nelson Road-Kenowa 345kV Transmission Line | 132 | 132 | Solar | Photovoltaic | Not Started |  | 132 | 132 | 0 | 0
MISO | J1919 | Withdrawn | 2021-08-24T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | METC | Ingham | MI | DPP-2021 | East (ITC) |  | Network Resource Interconnection Service (NRIS) | Oneida-Majestic 345 kV | 132 | 132 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J1920 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Leelanau | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Tuscola-Arrowhead 120kV Transmission Line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1921 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Montcalm | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Deja- Derby Jct 138kV Transmission line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1922 | Withdrawn | 2021-08-19T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Cottage Grove-Karn 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1923 | Withdrawn | 2021-08-19T04:00:00+00:00 | 2021-12-22T05:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Huron | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Rapson 120 kV substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1924 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Cottage Grove-Seven Mile 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1925 | Withdrawn | 2021-08-17T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Livingston | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Tihart-Latson 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1926 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Huff - Towerline 138kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1927 | Active | 2021-12-03T05:00:00+00:00 |  |  | 2024-07-15T04:00:00+00:00 | MUSCATINE POWER AND WATER | Muscatine | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Grandview Substation 69 kV | 23.4 | 23.4 | Solar | Photovoltaic | Not Started |  | 24 | 24 | 0 | 0
MISO | J1928 | Withdrawn | 2021-08-24T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Grant | WI | DPP-2021 | East (ATC) |  | Network Resource Interconnection Service (NRIS) | Hill Valley 345kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J1929 | Active | 2021-08-24T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | METC | Cheboygan | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 110 | 110 | Solar | Photovoltaic | Not Started |  | 110 | 110 | 0 | 0
MISO | J1930 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-06-05T04:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | N Madison - Columbia | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1931 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Iowa | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Hill Valley 345kV | 40 | 40 | Wind | Wind Turbine | Not Started |  | 40 | 12 | 0 | 0
MISO | J1932 | Active | 2021-08-24T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | METC | Gladwin | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Grout Junction - Alger Junction 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J1933 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Bastrop Tap 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1934 | Active | 2021-08-24T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Kenosha | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Lakeview 138kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 150 | 150 | 0 | 0
MISO | J1935 | Active | 2021-11-29T05:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dane | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | N. Madison 69kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 50 | 50 | 0 | 0
MISO | J1936 | Withdrawn | 2021-11-29T05:00:00+00:00 | 2023-06-05T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Werner West - Rocky Run 345kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1937 | Withdrawn | 2021-11-29T05:00:00+00:00 | 2023-06-05T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Werner West - Rocky Run 345kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1938 | Active | 2021-11-29T05:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Werner West - Rocky Run 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1939 | Active | 2023-10-18T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | METC | Saginaw | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Layton-Cornell White 138 kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 125 | 125 | 0 | 0
MISO | J1940 | Withdrawn | 2021-08-23T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Monroe | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Monroe-Lallendorf 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1941 | Withdrawn | 2021-08-25T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Polk | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Crookston | 60 | 60 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J1942 | Withdrawn | 2021-08-23T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Monroe | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Seville TP-Niles TP 120 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1943 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | N Madison - Columbia 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1944 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Banner-Rapson 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 185 | 185 | 0 | 0
MISO | J1945 | Active | 2021-11-29T05:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Werner West - Rocky Run 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J1946 | Active | 2021-08-19T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | COOPERATIVE ENERGY | Jasper | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | 230 kV Missionary Substation | 350 | 350 | Hybrid | Solar/Battery | Not Started |  | 350 | 350 | 0 | 0
MISO | J1947 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Attica - Veedersburg 230kV | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1948 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMEREN MISSOURI | Marion | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hannibal west 161 kV | 195 | 195 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1949 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | METC | Antrim | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Mancelona - Westwood 69kV | 99.6 | 99.6 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1950 | Withdrawn | 2021-08-24T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Gibson | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Francisco - Toyota 138kV | 83.16 | 83.16 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J1951 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | ITC | Monroe | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Lemoyne-Majestic 345kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1952 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Cerro Gordo | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Emery-Floyd 161kV | 180 | 180 | Wind | Wind Turbine | Not Started |  | 180 | 54 | 0 | 0
MISO | J1953 | Withdrawn | 2022-07-20T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Red Gum 115kV | 264.6 | 264.6 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1954 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-06-05T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Walworth | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | SW Delavan 138kV | 35 | 35 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1955 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-06-05T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Walworth | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | SW Delavan 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1956 | Withdrawn | 2021-11-30T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. John the Baptist | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Waterford 230kV | 60 | 60 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1957 | Withdrawn | 2021-11-29T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Coahoma | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Clarksdale-Roundaway 115kV (co-located with J2284) | 90 | 90 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1958 | Withdrawn | 2021-11-30T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. John the Baptist | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Waterford 230kV | 60 | 60 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1959 | Withdrawn | 2021-11-30T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. John the Baptist | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Waterford-Vacherie 230kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1960 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Starke - Flint Lake 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1961 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Cass | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Buffalo 115kV | 190 | 190 | Wind | Wind Turbine | Not Started |  | 190 | 57 | 0 | 0
MISO | J1962 | Withdrawn | 2021-08-23T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Polk | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Livingston - Rich 138kV | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1963 | Withdrawn | 2021-11-29T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Polk | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Livingston - Rich 138kV | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1964 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | N Madison - Columbia | 90 | 90 | Battery Storage | Battery Storage | Not Started |  | 90 | 90 | 0 | 0
MISO | J1965 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | McCredie-Montgomery 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1966 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | WABASH VALLEY POWER ASSOCIATION, INC. | Clinton | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Frankfort-Cayuga 230kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1967 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Rantoul East 138kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J1968 | Withdrawn | 2021-08-18T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Polk | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Crookston | 30 | 30 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J1969 | Withdrawn | 2021-08-23T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | ITC | Monroe | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Lemoyne-Majestic 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1970 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mira-Sydney 138kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1971 | Withdrawn | 2021-11-30T05:00:00+00:00 | 2023-06-05T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dane | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Cardinal | 45 | 45 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1972 | Withdrawn | 2021-08-17T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Des Moines | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Denmark - Newport | 115 | 115 | Solar | Photovoltaic | Not Started |  | 115 | 115 | 0 | 0
MISO | J1973 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mira Tap-Sydney 138kV | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1974 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Coles | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mattoon West 138kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1975 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Coles | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mattoon West 138kV | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1976 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Starke - Flint Lake 138kV | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1977 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | METC | Washtenaw | MI | DPP-2021 | East (ITC) |  | Network Resource Interconnection Service (NRIS) | Trenton 120kV | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J1978 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pocahontas | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Lemars Tap-Little Sioux 161kV | 175 | 175 | Wind | Wind Turbine | Not Started |  | 170 | 52.5 | 0 | 0
MISO | J1979 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ITC MIDWEST | Howard | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Hazleton-Mitchell County 345kV line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 60 | 0 | 0
MISO | J1980 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | METC | Kent | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Vergennes 138kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1981 | Withdrawn | 2021-08-25T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Gibson | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Francisco - Toyota 138kV | 15 | 15 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J1982 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | METC | Gladwin | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Grout Junction - Alger Junction 138kV | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 25 | 25 | 0 | 0
MISO | J1983 | Active | 2021-11-29T05:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dane | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | N. Madison 69kV | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 25 | 25 | 0 | 0
MISO | J1984 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | METC | Ottawa | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Tallmadge 138kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J1985 | Withdrawn | 2021-11-30T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Chicken Farm - Amite | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1986 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN MISSOURI | St. Charles | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Montgomery 161kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1987 | Withdrawn | 2021-08-23T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | ITC | Washtenaw | MI | DPP-2021 | East (ITC) |  | Network Resource Interconnection Service (NRIS) | Coventry | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J1988 | Withdrawn | 2021-11-29T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Coahoma | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Roundaway Cepa 115kV | 120.96 | 120.96 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J1989 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Brown | SD | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Twin Brooks-Ellendale 345kV | 250 | 250 | Wind | Wind Turbine | Not Started |  | 250 | 75 | 0 | 0
MISO | J1990 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Stutsman | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Ellendale 345kV | 250 | 250 | Wind | Wind Turbine | Not Started |  | 215 | 75 | 0 | 0
MISO | J1991 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Genpower Keo 500kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J1992 | Withdrawn | 2021-08-25T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Genpower Keo 500kV | 110 | 110 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J1993 | Active | 2021-12-01T05:00:00+00:00 |  |  | 2025-07-23T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Columbia - South Fon Du Lac | 99 | 99 | Solar | Photovoltaic | Not Started |  | 99 | 99 | 0 | 0
MISO | J1994 | Active | 2021-07-30T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Fond du Lac | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Metomen 138 kV | 97.08 | 97.08 | Solar | Photovoltaic | Not Started |  | 97.08 | 97.08 | 0 | 0
MISO | J1995 | Active | 2021-08-04T04:00:00+00:00 |  |  | 2025-07-23T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Richland | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | OAK RIDGE (LA) | 180 | 180 | Solar | Photovoltaic | Not Started |  | 180 | 0 | 0 | 0
MISO | J1996 | Active | 2021-08-11T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Shawano | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | West Shawano 138kV - Badger 138kV | 99 | 99 | Hybrid | Solar/Battery | Not Started |  | 99 | 99 | 0 | 0
MISO | J1997 | Active | 2021-08-11T04:00:00+00:00 |  |  | 2024-03-01T05:00:00+00:00 | CLECO POWER LLC | Calcasieu | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Nelson (EES) - Longville 138kV | 80 | 80 | Solar | Photovoltaic | Not Started |  | 80 | 0 | 0 | 0
MISO | J1998 | Active | 2021-08-04T04:00:00+00:00 |  |  | 2024-06-30T04:00:00+00:00 | ITC MIDWEST | Franklin | IA | DPP-2021 | West | Study Not Started |  | Nuthatch Switching Station | 66 | 66 | Wind | Wind Turbine | Not Started |  | 66 | 66 | 0 | 0
MISO | J1999 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Rodemacher | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J2000 | Active | 2021-08-10T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Frankfort to Cayuga 230kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2001 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | METC | Newaygo | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Ludington to Kenowa 345kV | 220 | 220 | Solar | Photovoltaic | Not Started |  | 220 | 220 | 0 | 0
MISO | J2002 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-03-13T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Washington | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | 345 kV Sub T Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2003 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Deuel | SD | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Astoria 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2004 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Attica - Veedersburg 230kV | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2005 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Deuel | SD | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Astoria 345kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2006 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Robert E Ritchie - Stuttgart Rcuskey 230kV | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2007 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Genpower Keo 500kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2008 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | McCredie-Montgomery 345kV | 65 | 65 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2009 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Robert E Ritchie - Stuttgart Rcuskey 230kV | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2010 | Active | 2021-08-26T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Stuttgart Ricuskey to Woodward 230kV | 75 | 75 | Solar | Photovoltaic | Not Started |  | 75 | 75 | 0 | 0
MISO | J2011 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Bastrop Tap 115kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2012 | Withdrawn | 2021-11-30T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Chicken Farm-Amite | 20 | 20 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2013 | Withdrawn | 2021-11-30T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Chicken Farm-Amite | 52.92 | 52.92 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2014 | Withdrawn | 2021-11-23T05:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Clark | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Eau Claire - Arpin 345kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2015 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Lula-Tunica (same POI as J1440) | 90 | 90 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2016 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Daviess | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | F.B Culley to Northeast | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2017 | Withdrawn | 2021-08-26T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Daviess | KY | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | F B Culley- Northeast 138kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2018 | Withdrawn | 2021-11-23T05:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Clark | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Eau Claire - Arpin 345kV | 190 | 190 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2019 | Withdrawn | 2021-08-27T04:00:00+00:00 |  |  | 2025-02-17T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Rolette | ND | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Rugby-Glenborough 230 kV Line | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J2020 | Withdrawn | 2021-08-10T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-09-01T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | CLECO Cooper-Penton Road 230kV Line | 260 | 260 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2021 | Active | 2021-07-30T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Trempealeau | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Tremval 69kV | 48.43 | 48.43 | Solar | Photovoltaic | Not Started |  | 48.43 | 48.43 | 0 | 0
MISO | J2022 | Active | 2021-10-18T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | GREAT RIVER ENERGY | Mower | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Pleasant Valley 345 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2023 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-04-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Amite | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Gloster to Liberty 138 kV | 94.1 | 94.1 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2024 | Withdrawn | 2021-08-13T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-01-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Cypress 230 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2025 | Withdrawn | 2021-08-16T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. James | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Vacherie 230 kV | 95 | 95 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2026 | Active | 2021-11-15T05:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | ITC | Gratiot | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Regal | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J2027 | Active | 2021-07-20T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | GREAT RIVER ENERGY | Dakota | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Chub Lake - Hampton Corners 345 kV Line [See Operating Agreement 5 for Correction Discussion] | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J2028 | Active | 2021-08-10T04:00:00+00:00 |  |  | 2024-05-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Kuhn Rd to Parkin | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 0 | 0 | 0
MISO | J2029 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marquette | MI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Perch Lake Substation | 62.5 | 62.5 | Solar | Photovoltaic | Not Started |  | 62.5 | 62.5 | 0 | 0
MISO | J203 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2012-09-01T04:00:00+00:00 | ITC MIDWEST | Sanilac County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Greenwood - Banner 345kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2030 | Active | 2021-07-21T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | GREAT RIVER ENERGY | Isanti | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | ISANTTI TAP to ATHNSSW 69kV | 120 | 120 | Solar | Photovoltaic | Not Started |  | 56 | 56 | 0 | 0
MISO | J2031 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-03-13T04:00:00+00:00 | ITC MIDWEST | Tama | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | 161 kV Toledo Substation | 100 | 100 | Wind | Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
MISO | J2032 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Marion | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hanna 345kV | 70 | 70 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2033 | Active | 2021-08-26T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | AMEREN ILLINOIS | Clay | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Xenia - West Mt Vernon 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2034 | Withdrawn | 2022-04-05T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-05-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lafourche | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Thibodaux | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2035 | Withdrawn | 2022-04-05T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-05-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lafourche | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Thibodaux | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2036 | Active | 2022-04-05T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hutsonville - Neoga 138 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2037 | Withdrawn | 2021-07-20T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Byron 345 kV Substation | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2038 | Active | 2021-08-26T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Kokomo Webster - Walton 230 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2039 | Active | 2021-08-26T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Sangamon | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Meredosia to Ipava 345 kV | 400 | 400 | Hybrid | Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2040 | Active | 2021-08-03T04:00:00+00:00 |  |  | 2024-11-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Dickinson | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Lakefield - Obrien Co 345 kV (43.497803, -95.318336) | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
MISO | J2041 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Amelia North substation | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 150 | 150 | 0 | 0
MISO | J2042 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Crossett North to North Bastrop 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2043 | Active | 2022-04-05T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Overton - McCredie 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2044 | Active | 2022-03-29T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Newton | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Goodland 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2045 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Newton | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Goodland 138 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2046 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Wabash | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Miami Wabash - Mier 138 kV (40.723889, -85.812019) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2047 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | DeSoto | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Robinsonville 230 kV | 199 | 199 | Solar | Photovoltaic | Not Started |  | 199 | 0 | 0 | 0
MISO | J2048 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Benton | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Morrison (255159) to Goodland (255129) 138 kV | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2049 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Shelby | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2050 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMEREN MISSOURI | Macon | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Thomas Hill-Adair-1 161kV | 208.43 | 208.43 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2051 | Withdrawn | 2021-11-23T05:00:00+00:00 | 2023-11-10T05:00:00+00:00 |  | 2024-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | 161 kV line tap of DELL EAST to Blytheville | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2052 | Active | 2022-04-05T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Overton - McCredie 345kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2053 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2025-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Redwood | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Lyon County to Cedar Mountain 345kV | 151.47 | 151.47 | Wind | Wind Turbine | Not Started |  | 151.47 | 122 | 0 | 0
MISO | J2054 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-06-30T04:00:00+00:00 | ITC MIDWEST | Freeborn | MN | DPP-2021 | West | Study Not Started |  | Freeborn | 67 | 67 | Wind | Wind Turbine | Not Started |  | 67 | 67 | 0 | 0
MISO | J2055 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Sheboygan | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | ATC South Sheboygan Falls Substation (SSF) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J2056 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | METC | Lenawee | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Morocco to Beecher 138 kV line | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 110 | 110 | 0 | 0
MISO | J2057 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | METC | Montcalm | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Nelson Road to Kenowa 345 kV line | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2058 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2021-09-07T04:00:00+00:00 |  | 2024-10-01T04:00:00+00:00 | ITC | Monroe | MI | DPP-2021 | East (ITC) |  | Network Resource Interconnection Service (NRIS) | Monroe to Wayne | 100 | 100 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J2059 | Active | 2022-03-18T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tippecanoe | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Springboro - Lafayette 138 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2060 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tippecanoe | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Springboro - Lafayette 138 kV | 170 | 170 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2061 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | METC | Saginaw | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Murphy | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2062 | Withdrawn | 2021-08-16T04:00:00+00:00 | 2023-06-05T04:00:00+00:00 |  | 2024-04-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Columbia 345 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2063 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-07-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Wheatland 345kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2064 | Active | 2021-11-08T05:00:00+00:00 |  |  | 2024-10-07T04:00:00+00:00 | METC | Jackson | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Tompkins 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J2065 | Active | 2021-07-14T04:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Pipestone | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Buffalo Ridge to Pipestone 115kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2066 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | ITC MIDWEST | Henry | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Denmark 161 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J2067 | Withdrawn | 2021-09-14T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | GREAT RIVER ENERGY | Clay | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Tamarac | 39.4 | 39.4 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J2068 | Active | 2021-07-19T04:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Pierce | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Herbert 69 kV Substation | 75 | 75 | Solar | Photovoltaic | Not Started |  | 75 | 75 | 0 | 0
MISO | J2069 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | ITC | Montcalm | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Eureka - Vestaburg 138kV Transmission Line (J1379 POI) | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2070 | Active | 2021-10-18T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | St. Croix | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Three Lakes - Pine Lake 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J2071 | Active | 2021-09-14T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Rye Co - Cypress 138kV | 198 | 198 | Solar | Photovoltaic | Not Started |  | 198 | 0 | 0 | 0
MISO | J2072 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Woodward 115kV - H.S. EHV 115 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2073 | Active | 2021-11-29T05:00:00+00:00 |  |  | 2024-10-15T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Ohio | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 345 kV Wilson Substation | 91.53 | 91.53 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2074 | Active | 2021-10-18T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Outagamie | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Werner West 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 75 | 75 | 0 | 0
MISO | J2075 | Active | 2021-08-27T04:00:00+00:00 |  |  | 2024-10-04T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | China (Bus# 334204) to Sheco Batiste Creek (Bus# 334240) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2076 | Withdrawn | 2021-08-09T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | San Jacinto | TX | DPP-2021 | South |  | Network Resource Interconnection Service (NRIS) | COLEY CREEK to PELICAN ROAD 138 kV | 225 | 225 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J2077 | Withdrawn | 2021-12-10T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-04-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Livingston | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Independence (6INDEPD) | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2078 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | ITC MIDWEST | Story | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Fernald Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2079 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ITC MIDWEST | Hancock | IA | DPP-2021 | West | Study Not Started |  | Lime Creek 161 kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 150 | 0 | 0
MISO | J2080 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-05-01T04:00:00+00:00 | MINNESOTA POWER INC. | Oliver | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Square Butte East 230 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J2081 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 |  | Sans Souci 500kV | 20 | 20 | Coal | Steam Turbine (including Nuclear, Geothermal and Solar Steam) | Not Started |  | 15 | 15 | 0 | 0
MISO | J2082 | Active | 2021-09-02T04:00:00+00:00 |  |  | 2024-10-04T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Shady Oaks (Bus# 500780) to Coughlin (Bus# 500230) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 50 | 50 | 0 | 0
MISO | J2083 | Withdrawn | 2021-12-21T05:00:00+00:00 | 2023-11-10T05:00:00+00:00 |  | 2024-10-31T04:00:00+00:00 | CLECO POWER LLC | Allen | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Caney | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2084 | Active | 2021-11-01T04:00:00+00:00 |  |  | 2024-11-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Emmons | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Linton NW (not in power flow case yet) | 45 | 45 | Solar | Photovoltaic | Not Started |  | 45 | 45 | 0 | 0
MISO | J2085 | Active | 2021-11-01T04:00:00+00:00 |  |  | 2024-11-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Emmons | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Linton NW 115 kV (radial to Wishek 115 kV) | 40 | 40 | Solar | Photovoltaic | Not Started |  | 40 | 40 | 0 | 0
MISO | J2086 | Active | 2021-08-09T04:00:00+00:00 |  |  | 2025-03-31T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Barnes | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Buffalo 345 kV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 500 | 500 | 0 | 0
MISO | J2087 | Active | 2021-07-19T04:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Renville | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Franklin 115kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 125 | 125 | 0 | 0
MISO | J2088 | Active | 2022-07-13T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | WEST MEMPHIS EHV - KEO EHV 500 kV (854.0) | 400 | 400 | Solar | Photovoltaic | Not Started |  | 400 | 400 | 0 | 0
MISO | J2089 | Active | 2021-11-23T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Line tap DELL to Manilla AECC 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2090 | Withdrawn | 2022-07-13T04:00:00+00:00 | 2023-11-07T05:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | 161 kV Parkin to Kuhn RoadLine Tap | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2091 | Active | 2022-01-11T05:00:00+00:00 |  |  | 2025-02-22T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | DeSoto | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | TWINKLETOWN 230 KV | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 250 | 250 | 0 | 0
MISO | J2092 | Withdrawn | 2021-08-12T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | GREAT RIVER ENERGY | Wright | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Dickinson Sub | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2093 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | West Memphis to Hughes 161 kV Line Tap | 144 | 144 | Solar | Photovoltaic | Not Started |  | 144 | 0 | 0 | 0
MISO | J2094 | Withdrawn | 2021-08-03T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2022-11-30T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Sargent | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Forman 230 kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2095 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2024-04-15T04:00:00+00:00 | ITC MIDWEST | Tama | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Belle Plaine Junction to Toledo Transmission | 212 | 212 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2096 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Terrebonne | LA | DPP-2021 | South |  | Energy Resource Interconnection Service (ERIS) | Schriever 230 kV Substation | 180 | 180 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2097 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | MINNESOTA POWER INC. | Morton | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Tri-County 230 kV Substation | 100 | 100 | Wind | Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
MISO | J2098 | Active | 2021-08-22T04:00:00+00:00 |  |  | 2025-03-31T04:00:00+00:00 | ITC | Calhoun | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Oneida - Majestic 345 kV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 309 | 309 | 0 | 0
MISO | J2099 | Active | 2022-06-22T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Rocky Run to Werner West 345 kV | 399.03 | 399.03 | Solar | Photovoltaic | Not Started |  | 399.03 | 399.03 | 0 | 0
MISO | J2100 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | METC | Van Buren | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Palisades | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 250 | 250 | 0 | 0
MISO | J2101 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Morton | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Mandan 230 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J2102 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Buffalo | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Alma | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 150 | 150 | 0 | 0
MISO | J2103 | Withdrawn | 2021-09-01T04:00:00+00:00 | 2021-12-03T05:00:00+00:00 |  | 2024-10-04T04:00:00+00:00 | ENTERGY TEXAS, INC. | Jasper | TX | DPP-2021 | South |  | Network Resource Interconnection Service (NRIS) | Buna SW to Call Transmission Line | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2104 | Active | 2021-08-04T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Murray | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Lyon County 345 kV - Cedar Mountain 345 kV | 550 | 550 | Wind | Wind Turbine | Not Started |  | 230 | 230 | 0 | 0
MISO | J2105 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2024-04-15T04:00:00+00:00 | ITC MIDWEST | Franklin | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Killdeer 345 kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2106 | Active | 2021-08-03T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ITC MIDWEST | Story | IA | DPP-2021 | West | Study Not Started |  | Story County 161 kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 150 | 0 | 0
MISO | J2107 | Active | 2022-06-22T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Rocky Run to Werner West 345 kV line | 399.03 | 399.03 | Solar | Photovoltaic | Not Started |  | 399.03 | 399.03 | 0 | 0
MISO | J2108 | Withdrawn | 2021-08-09T04:00:00+00:00 | 2023-10-10T04:00:00+00:00 |  | 2024-11-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Johnson | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | IC ENRON - SUB JIC 161 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2109 | Withdrawn | 2021-08-25T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. James | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Vacherie 230 kV | 25 | 25 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2110 | Withdrawn | 2021-08-25T04:00:00+00:00 |  |  | 2025-09-16T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2021 | South |  | Energy Resource Interconnection Service (ERIS) | Gilmore 161kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2111 | Withdrawn | 2021-08-25T04:00:00+00:00 |  |  | 2025-09-16T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2021 | South |  | Energy Resource Interconnection Service (ERIS) | Marion to Marked Tree 161kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2112 | Active | 2021-12-01T05:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Warren to Kountze 138 kV | 115 | 115 | Solar | Photovoltaic | Not Started |  | 115 | 0 | 0 | 0
MISO | J2113 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Daviess | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reid - Daviess Co 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2114 | Active | 2021-12-01T05:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Tyler | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | DOUCETTE to DEER 138 kV | 140 | 140 | Hybrid | Solar/Battery | Not Started |  | 140 | 0 | 0 | 0
MISO | J2115 | Active | 2021-08-20T04:00:00+00:00 |  |  | 2024-09-16T04:00:00+00:00 | AMEREN ILLINOIS | Macon | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Faraday 138kV | 98.3 | 98.3 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2116 | Active | 2023-12-08T05:00:00+00:00 |  |  | 2022-09-01T04:00:00+00:00 | GREAT RIVER ENERGY | Cook | MN | DPP-2021 | West | Study Not Started |  | Colvill | 18 | 18 | Diesel | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 18 | 0 | 0
MISO | J2117 | Active | 2022-04-05T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Wood | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | ACEC Badger West - Saratoga 138 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2118 | Withdrawn | 2021-09-29T04:00:00+00:00 | 2023-09-06T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | METC | Monroe | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Whiting - Morocco 138kV | 125 | 125 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2119 | Active | 2022-01-18T05:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | ITC | Hillsdale | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 50 | 50 | Solar | Solar/Battery | Not Started |  | 30 | 12.6 | 0 | 0
MISO | J2120 | Active | 2021-08-04T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | ITC MIDWEST | Linn | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Fairfax 161 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J2121 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | McCredie - Overton 345 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2122 | Active | 2021-08-04T04:00:00+00:00 |  |  | 2024-06-30T04:00:00+00:00 | ITC MIDWEST | Franklin | IA | DPP-2021 | West | Study Not Started |  | Nuthatch Switching Substation | 33 | 33 | Wind | Wind Turbine | Not Started |  | 33 | 33 | 0 | 0
MISO | J2123 | Active | 2021-09-01T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Dubois | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Duff 138KV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2124 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Champaign | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Rising 345 kV Bus 1 | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2125 | Withdrawn | 2021-08-21T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Clay | IL | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Xenia to W Mt Vernon 345 kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2126 | Withdrawn | 2021-08-25T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2021 | South |  | Network Resource Interconnection Service (NRIS) | Garner SS to Seracy Price 115kV line | 100 | 100 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J2127 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | COOPERATIVE ENERGY | Jefferson Davis | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Silver Creek 115kV | 172.5 | 172.5 | Hybrid | Solar/Battery | Not Started |  | 172.5 | 172.5 | 0 | 0
MISO | J2128 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Coles | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Farady to Kansas 345 kV | 300 | 300 | Hybrid | Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2129 | Active | 2021-08-26T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Barry | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Bradley 138 kV Substation | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2130 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Clinton 230kV | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2131 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | AMEREN ILLINOIS | Jasper | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Newton 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2132 | Active | 2022-10-31T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Cayuga 230 kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J2133 | Active | 2021-08-26T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | White | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Garner 115 kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2134 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | White Bluff EHV - Wrightsville 115 kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 195 | 195 | 0 | 0
MISO | J2135 | Active | 2021-08-11T04:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Ville Platte - West Fork 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 0 | 0 | 0
MISO | J2136 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Iroquois | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gilman substation 138 kV | 190.9 | 190.9 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2137 | Withdrawn | 2021-10-26T04:00:00+00:00 |  |  | 2024-10-15T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Ohio | KY | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | 345 kV Wilson Substation | 78.23 | 78.23 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J2138 | Active | 2021-09-14T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Rye Co - Cypress 138kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2139 | Active | 2021-09-02T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | ITC | Livingston | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | 345kV Blackfoot-Madrid Line | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 250 | 250 | 0 | 0
MISO | J2140 | Withdrawn | 2021-09-14T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Brinkley East to Clarendon 115 kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2141 | Withdrawn | 2021-09-14T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Brinkley East to Clarendon 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2142 | Active | 2021-11-03T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | AMEREN MISSOURI | Adair | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Maywood - Zachary 345 kV line | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2143 | Active | 2021-10-15T04:00:00+00:00 |  |  | 2025-02-15T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Lake Village Bagby 115 KV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 0 | 0 | 0
MISO | J2144 | Withdrawn | 2021-09-02T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Schahfer 345 kV Sub | 155.2 | 195 | Hybrid | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J2145 | Active | 2021-11-29T05:00:00+00:00 |  |  | 2024-10-15T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Ohio | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 345 kV Wilson Substation | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2146 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Hopkins | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hopkins County 161kV Substation | 45 | 45 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2147 | Active | 2021-11-24T05:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Daviess | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Daviess County - Utica 69kV | 56 | 56 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2148 | Active | 2021-10-18T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Outagamie | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Werner West 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J2149 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Saline | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | White Bluff - Mabelvale 115 kV line | 240 | 240 | Solar | Photovoltaic | Not Started |  | 112 | 112 | 0 | 0
MISO | J2150 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Jefferson | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Madison 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2151 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2025-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Saline | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Muddy to West Frankfort 138 kV line | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2152 | Active | 2023-11-30T05:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | INDEPENDENCE [LA] - HAMMOND 230.0kV | 120 | 120 | Hybrid | Solar/Battery | Not Started |  | 120 | 0 | 0 | 0
MISO | J2153 | Active | 2021-08-11T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ashley | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Ashley County Switchyard | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 145 | 0 | 0 | 0
MISO | J2154 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2021 | South | Phase 1 | Energy Resource Interconnection Service (ERIS) | Carlyss - Nelson 230kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 150 | 0 | 0 | 0
MISO | J2155 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-05-31T04:00:00+00:00 | AMEREN MISSOURI | New Madrid | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reelfoot - Sikeston 161 kV Line MTEP Project 19852 Facility ID 26201 | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2156 | Active | 2022-06-28T04:00:00+00:00 |  |  | 2024-05-31T04:00:00+00:00 | AMEREN ILLINOIS | Johnson | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Massac - Jordan 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2157 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2025-05-01T04:00:00+00:00 | MINNESOTA POWER INC. | Morton | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Tri-County 230 kV Substation | 100 | 100 | Wind | Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
MISO | J2158 | Active | 2021-08-24T04:00:00+00:00 |  |  | 2024-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Clark | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hutsonville - Neoga 138KV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2159 | Active | 2021-08-24T04:00:00+00:00 |  |  | 2024-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Clark | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hutsonville - Neoga 138KV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2160 | Active | 2021-09-01T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Bartholomew | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gallagher to Columbus 230KV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2161 | Active | 2021-08-31T04:00:00+00:00 |  |  | 2024-08-31T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Fulton | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ipava 138KV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2162 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-08-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Leflore | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Itta Benna - Moorhead 115KV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J2163 | Active | 2022-07-13T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | 230 kV: Penton Road to Roy S Nelson 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2164 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Pike | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Petersburg 345 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2165 | Active | 2021-11-03T04:00:00+00:00 |  |  | 2023-11-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2021 | South | Phase 1 | Energy Resource Interconnection Service (ERIS) | JACINTO - SHECO BATISTE CREEK 230kV | 145 | 145 | Solar | Photovoltaic | Not Started |  | 145 | 0 | 0 | 0
MISO | J2166 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Taylor | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Clarinda - Braddyville 161 kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2167 | Withdrawn | 2021-11-03T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Chalkley - Solac 230kV | 198 | 198 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2168 | Withdrawn | 2021-08-13T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-12-31T05:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | China Substation | 693 | 693 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2169 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2023-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Deridder - Centennial 138-kV | 98.9 | 98.9 | Solar | Photovoltaic | Not Started |  | 99 | 99 | 0 | 0
MISO | J2170 | Active | 2022-04-05T04:00:00+00:00 |  |  | 2024-01-01T05:00:00+00:00 | AMEREN ILLINOIS | Clark | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Snyder 345 kV (J1180/J1475 POI) | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2171 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-05-01T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Aster to Commodore | 500 | 500 | Solar | Solar/Wind | Not Started |  | 0 | 0 | 0 | 0
MISO | J2172 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | AMEREN ILLINOIS | McDonough | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Macomb Northeast | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2173 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | BOLTON | 396 | 396 | Hybrid | Solar/Battery | Not Started |  | 396 | 396 | 0 | 0
MISO | J2174 | Withdrawn | 2021-08-22T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-03-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Tunica to Robinson 230 kV | 390 | 390 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2175 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-03-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Indianola to Gerald Andrus 230 kV | 350 | 350 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2176 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-03-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Hartburg - Rhodes 500 kV | 680 | 680 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2177 | Active | 2021-08-09T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tipton | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Tipton West 230 kV | 67 | 67 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2178 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Merom 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2179 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | AMEREN MISSOURI | Montgomery | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Montgomery 345 kV | 100 | 100 | Hybrid | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2180 | Active | 2022-07-13T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Fisher | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
MISO | J2181 | Active | 2022-07-13T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | 161 kV line tap of DELL EAST to Blytheville | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2182 | Withdrawn | 2021-08-12T04:00:00+00:00 | 2021-09-17T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tallahatchie | MS | DPP-2021 | South |  | Network Resource Interconnection Service (NRIS) | webb 115 kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2183 | Withdrawn | 2021-09-01T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2022-12-31T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Pointe Coupee | LA | DPP-2021 | South | Phase 1 |  | Fancy Point - Waterloo | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2184 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Brinkley West Substation 115kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2185 | Active | 2022-06-22T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Rocky Run to Werner West 345 kV line | 399.03 | 399.03 | Solar | Photovoltaic | Not Started |  | 399.03 | 399.03 | 0 | 0
MISO | J2186 | Active | 2022-06-22T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Fulton | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ipava-Maple Ridge 345kV (4573) | 820.6 | 820.6 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2187 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-10-20T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Stillwell 138kV | 124 | 124 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2188 | Active | 2021-12-01T05:00:00+00:00 |  |  | 2025-07-23T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Columbia - South Fon Du Lac | 99 | 99 | Solar | Photovoltaic | Not Started |  | 99 | 99 | 0 | 0
MISO | J2189 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2019-12-01T05:00:00+00:00 | AMEREN ILLINOIS | McDonough | IL | DPP-2021 | Central | Phase 1 |  | Hornsby Switching Station | 15.6 | 15.6 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2190 | Active | 2021-08-24T04:00:00+00:00 |  |  | 2027-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Dell to San Souci 500kv | 500 | 500 | Hybrid | Solar/Battery | Not Started |  | 500 | 500 | 0 | 0
MISO | J2191 | Withdrawn | 2021-10-28T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-12-15T05:00:00+00:00 | CLECO POWER LLC | St. Mary | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Caneland 230kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2192 | Active | 2022-06-14T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sidney-Bunsonville 345kV | 99.9 | 99.9 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2193 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Waushara | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Sand Lake 138kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2194 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Sullivan | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Merom - Gibson 345 kV Line | 350 | 350 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2195 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2024-10-07T04:00:00+00:00 | AMEREN ILLINOIS | Fayette | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ramsey East 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2196 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2028-04-30T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | AUSTIN 138 KV | 100 | 100 | Hybrid | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2197 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-10-07T04:00:00+00:00 | AMEREN ILLINOIS | Clay | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Xenia 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2198 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMEREN MISSOURI | Jefferson | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Joachim 138kV | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2199 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Anoka | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | COON CREEK | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J2200 | Withdrawn | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Scott | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | BLUE LAKE | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J2201 | Active | 2021-12-07T05:00:00+00:00 |  |  | 2024-11-29T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Harrison | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ramsey to Kenzig Road | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2202 | Withdrawn | 2021-08-17T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2022-12-02T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Lacassine 69 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2203 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Adams | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | EAST QUINCY | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2204 | Withdrawn | 2021-10-29T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | DUPO FERRY | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J2205 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | J1145 New 345kV POI Substation (Ameren Overton-Montgomery 345kV Line) | 300 | 300 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2206 | Withdrawn | 2021-08-19T04:00:00+00:00 | 2023-04-04T04:00:00+00:00 |  | 2025-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Attica Substation 230kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2207 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Henderson to AB Brown 138 kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2208 | Active | 2021-08-27T04:00:00+00:00 |  |  | 2024-10-04T04:00:00+00:00 | CLECO POWER LLC | De Soto | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Mansfield (Bus #500530) to Red River Tap (Bus #500762) 138 kV | 99 | 99 | Solar | Photovoltaic | Not Started |  | 99 | 99 | 0 | 0
MISO | J2209 | Active | 2021-12-23T05:00:00+00:00 |  |  | 2025-09-16T04:00:00+00:00 | AMEREN MISSOURI | Scott | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Oran 161kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2210 | Withdrawn | 2021-08-26T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Derrick 230 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2211 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Brown | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | TOWER DRIVE | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 200 | 200 | 0 | 0
MISO | J2212 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2025-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Jefferson | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Madison 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2213 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Marshall | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | BURR OAK | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2214 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Fisher 230 kV | 62 | 62 | Battery Storage | Battery Storage | Not Started |  | 62 | 62 | 0 | 0
MISO | J2215 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Lake | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Schahfer - St John 345kV Line (at J1058 POI) | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2216 | Active | 2022-04-08T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sandcut-Rockville 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2217 | Withdrawn | 2021-12-21T05:00:00+00:00 | 2023-11-10T05:00:00+00:00 |  | 2024-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Brinkley East - Aubrey 230 kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2218 | Active | 2021-08-13T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Manitowoc | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | SHOTO | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 150 | 150 | 0 | 0
MISO | J2219 | Active | 2021-07-22T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Olmsted | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Rochester - Wabaco 161kV Line (Dairyland Power) | 180 | 180 | Hybrid | Solar/Battery | Not Started |  | 180 | 180 | 0 | 0
MISO | J2220 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Donaldsonville - Evergreen 230 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J2221 | Active | 2021-08-20T04:00:00+00:00 |  |  | 2025-09-16T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clark | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Speed | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2222 | Withdrawn | 2021-12-21T05:00:00+00:00 | 2023-11-07T05:00:00+00:00 |  | 2024-10-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Penton Road to Nelson 230 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2223 | Withdrawn | 2021-12-21T05:00:00+00:00 | 2023-11-07T05:00:00+00:00 |  | 2024-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Cash - Newport AB 161 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2224 | Active | 2021-08-25T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Iberville | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Derrick 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 0 | 0 | 0
MISO | J2225 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | REID EHV 345 KV SUBSTATION | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2226 | Active | 2022-06-14T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Newton | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Morrison Ditch - Goodland 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2227 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Trempealeau | WI | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | N-3 Bridge Creek to Independence 69kV Line [See Operating Agreement 5 for Correction Discussion] | 89 | 89 | Solar | Photovoltaic | Not Started |  | 89 | 89 | 0 | 0
MISO | J2228 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Red Gum | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2229 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Wabash | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Miami Wabash - Mier 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2230 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2021 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | Merom Substation 345kV | 400 | 400 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2231 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-02-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Sherrill 115kV | 97.49 | 97.49 | Solar | Photovoltaic | Not Started |  | 97.49 | 97.49 | 0 | 0
MISO | J2232 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tipton | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Tipton West 230 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2233 | Active | 2022-06-14T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sidney - Bunsonville 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2234 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Henderson to AB Brown 138 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2235 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | EAST TEXAS ELECTRIC COOPERATIVE, INC. | San Jacinto | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Shepherd 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J2236 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Howard | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Greentown 230 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2237 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Brinkley East - Aubrey 230 kV Line | 185 | 185 | Solar | Photovoltaic | Not Started |  | 185 | 185 | 0 | 0
MISO | J2238 | Active | 2022-03-18T04:00:00+00:00 |  |  | 2024-02-15T05:00:00+00:00 | AMEREN MISSOURI | Maries | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | The Franks (Bus #300041) - Bland (Bus #344154) 345 kV Line | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2239 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | AMEREN MISSOURI | Washington | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Belgrade - Pilot Knob 161 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2240 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-02-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Nevada | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Prescott 337507 to Emmett 337505 | 120 | 120 | Solar | Photovoltaic | Not Started |  | 120 | 120 | 0 | 0
MISO | J2241 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Benton | IN | DPP-2021 | Central | Phase 1 |  | Cayuga sub (Jordan Creek Wind J515 POI) 345 kV | 320 | 320 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2242 | Active | 2021-08-23T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Polk | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | SHECO | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 100 | 100 | 0 | 0
MISO | J2243 | Withdrawn | 2021-08-12T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-02-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Tyler | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Warren 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2244 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | MABELVALE EHV to WHITE BLUFF EHV 115kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2245 | Withdrawn | 2021-08-30T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-10-30T04:00:00+00:00 | CLECO POWER LLC | St. Tammany | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Mandeville - North Slidell 230kV Line (not listed on TTF, but both substations seem to have breakers | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2246 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | REID EHV 345 kV Substation | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2247 | Active | 2022-03-25T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Marshall | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Woodhall | 178 | 178 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2248 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | White Bluff EHV to Wrightsville 115kV | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2249 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Bayou Cove | 144 | 144 | Solar | Photovoltaic | Not Started |  | 144 | 144 | 0 | 0
MISO | J2250 | Active | 2021-11-01T04:00:00+00:00 |  |  | 2024-04-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Stutsman | ND | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Ellendale sub 345 kV (46.009357, -98.567742) | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J2251 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Grant | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Greentown 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2252 | Active | 2022-07-13T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Cash - Newport AB | 300 | 300 | Solar | Photovoltaic | Not Started |  | 300 | 300 | 0 | 0
MISO | J2253 | Active | 2021-08-17T04:00:00+00:00 |  |  | 2022-12-02T05:00:00+00:00 | EAST TEXAS ELECTRIC COOPERATIVE, INC. | Tyler | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Fork Creek Substation 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 100 | 100 | 0 | 0
MISO | J2254 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Pike | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Petersburg 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2255 | Active | 2021-08-06T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Ripley | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Batesville 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2256 | Withdrawn | 2021-08-16T04:00:00+00:00 |  |  | 2024-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Humboldt | IA | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Irvington - Webster 345kV Line | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J2257 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-03-01T05:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Ville Platte - Westfork 230kV | 80 | 80 | Solar | Photovoltaic | Not Started |  | 80 | 0 | 0 | 0
MISO | J2258 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-05-31T04:00:00+00:00 | AMEREN ILLINOIS | Adams | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | East Quincy-Fishhook 138kV | 175 | 175 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2259 | Active | 2021-08-12T04:00:00+00:00 |  |  | 2024-11-01T04:00:00+00:00 | WABASH VALLEY POWER ASSOCIATION, INC. | Hendricks | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Amo 345kV | 199.99 | 199.99 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2260 | Active | 2021-10-07T04:00:00+00:00 |  |  | 2023-07-31T04:00:00+00:00 | METC | Presque Isle | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Port Calcite- Hammond Bay 138 kV | 251.5 | 251.5 | Wind | Wind Turbine | Not Started |  | 149.24 | 149.24 | 0 | 0
MISO | J2261 | Active | 2021-10-11T04:00:00+00:00 |  |  | 2024-02-02T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | INDEPENDENCE-ISES - POWERLINE ROAD 500.0kV | 652 | 652 | Solar | Photovoltaic | Not Started |  | 652 | 652 | 0 | 0
MISO | J2262 | Active | 2021-10-11T04:00:00+00:00 |  |  | 2024-02-02T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Independence(A) (500kV) -Powerline(B) (500kV) | 652 | 652 | Solar | Photovoltaic | Not Started |  | 652 | 652 | 0 | 0
MISO | J2263 | Active | 2021-08-31T04:00:00+00:00 |  |  | 2024-08-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Edwardsport 345KV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2264 | Withdrawn | 2021-10-11T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-02-02T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Prairie | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Desarc(A) (500kV) -Griffithville(B) (500kV) | 88 | 88 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2265 | Active | 2021-09-07T04:00:00+00:00 |  |  | 2024-02-15T05:00:00+00:00 | AMEREN MISSOURI | Bollinger | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | St. Francois (Bus #345773) - Lutesville (Bus #344974) 345 kV Line | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2266 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2025-03-31T04:00:00+00:00 | AMEREN ILLINOIS | Edgar | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Kansas (endpoint A) - Sugar Creek (endpoint B) 345 kV | 175 | 175 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2267 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2025-03-31T04:00:00+00:00 | AMEREN ILLINOIS | Williamson | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 345 kV Stilleys Substation | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2268 | Active | 2021-08-11T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | ITC MIDWEST | Linn | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Duane Arnold Energy Center | 400 | 400 | Solar | Photovoltaic | Not Started |  | 370 | 370 | 0 | 0
MISO | J2269 | Active | 2022-06-14T04:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Veedersburg West - Lafayette 230kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2270 | Active | 2021-08-16T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Merom 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2271 | Active | 2021-07-21T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | South Fond du Lac to Columbia 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2272 | Active | 2021-07-22T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | ITC MIDWEST | Clinton | IA | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | 161kV East Calamus Substation | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 250 | 250 | 0 | 0
MISO | J2273 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2024-03-31T04:00:00+00:00 | AMEREN ILLINOIS | Clinton | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Tabor 138kV Substation | 175 | 175 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2274 | Active | 2021-07-21T04:00:00+00:00 |  |  | 2024-10-01T04:00:00+00:00 | AMEREN MISSOURI | Lincoln | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Pike - Troy 161kV | 170 | 170 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2275 | Active | 2022-03-22T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Peoria | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Fargo to Sandburg 345kV | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2276 | Active | 2022-04-11T04:00:00+00:00 |  |  | 2022-01-01T05:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | Douglas | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | ALEXANDRIA | 39.5 | 39.5 | Solar | Solar/Wind | Not Started |  | 39.5 | 39.5 | 0 | 0
MISO | J2277 | Active | 2022-05-06T04:00:00+00:00 |  |  | 2023-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Golden Sands - Arnott (O-119) | 0 | 0 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2278 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | AMEREN ILLINOIS | Edgar | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 60 | 60 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2279 | Active | 2021-07-21T04:00:00+00:00 |  |  | 2025-08-01T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Ionia | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Burnips to Tremaine 138 kV line | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 150 | 150 | 0 | 0
MISO | J2280 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2023-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC |  | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | GREENWOOD CLARK TOWNSHIP | 198 | 198 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2281 | Withdrawn | 2021-08-20T04:00:00+00:00 |  |  | 2024-10-07T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Reynolds 138 kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J2282 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2025-10-25T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Ohio | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | BR Tap -- New Hardinsburg 161kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2283 | Active | 2021-11-19T05:00:00+00:00 |  |  | 2020-10-01T04:00:00+00:00 | METC | Hillsdale | MI | DPP-2021 | East (ITC) | Phase 1 |  | 18Knowles (MISO node #256632) | 16.1 | 16.1 | Wind | Wind Turbine | Not Started |  | 16.1 | 16.1 | 0 | 0
MISO | J2284 | Withdrawn | 2021-09-08T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-12-30T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Coahoma | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Clarksdale-Delta 115kV line | 65.96 | 65.96 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2285 | Withdrawn | 2021-07-14T04:00:00+00:00 | 2021-09-10T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Polk | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Praire - Winger | 45 | 45 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J2286 | Withdrawn | 2021-07-14T04:00:00+00:00 | 2021-09-10T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Polk | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Praire - Winger 230kV | 90 | 90 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2287 | Active | 2021-09-07T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | DELTA SES SWITCHYARD 115kV | 135 | 135 | Solar | Photovoltaic | Not Started |  | 135 | 0 | 0 | 0
MISO | J2288 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | AMEREN MISSOURI | Audrain | MO | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | J956 collector substation (345kv; same ownership as other project connecting to sub, so no consent a | 175 | 175 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2289 | Active | 2021-09-09T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2021 | South | Phase 1 | Energy Resource Interconnection Service (ERIS) | Indianola | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 0 | 0 | 0
MISO | J2290 | Withdrawn | 2022-02-17T05:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2025-10-25T04:00:00+00:00 | CLECO POWER LLC | Avoyelles | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | CLECO Yellow Bayou 138kV Substation | 130 | 130 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2291 | Withdrawn | 2021-09-07T04:00:00+00:00 |  |  | 2025-07-23T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Polk | MN | DPP-2021 | West |  | Network Resource Interconnection Service (NRIS) | Winger | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2292 | Active | 2021-09-15T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Goos Ferry | 50 | 50 | Solar | Photovoltaic | Not Started |  | 50 | 0 | 0 | 0
MISO | J2293 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Adams | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 50 | 50 | 0 | 0
MISO | J2294 | Active | 2021-08-10T04:00:00+00:00 |  |  | 2024-05-01T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Mississippi | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Dell to Nucor 161 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 250 | 250 | 0 | 0
MISO | J2295 | Withdrawn | 2021-09-09T04:00:00+00:00 | 2023-04-04T04:00:00+00:00 |  | 2025-04-01T04:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2021 | Central |  | Energy Resource Interconnection Service (ERIS) | Merom Substation 345kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2296 | Active | 2022-03-24T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2021 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | Merom Substation 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2297 | Active | 2021-09-09T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2021 | South | Phase 1 | Energy Resource Interconnection Service (ERIS) | Indianola | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 0 | 0 | 0
MISO | J2298 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Greene | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | AECC Gainesville | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 0 | 0
MISO | J2299 | Withdrawn | 2021-09-09T04:00:00+00:00 | 2023-04-04T04:00:00+00:00 |  | 2025-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Greene | AR | DPP-2021 | South |  | Network Resource Interconnection Service (NRIS) | Marmaduke | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2300 | Active | 2021-11-30T05:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Greene | AR | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | AECC Gainesville | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 50 | 50 | 0 | 0
MISO | J2301 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2302 | Active | 2021-11-10T05:00:00+00:00 |  |  | 2024-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Helena | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | McKnight to Victor J. Daniel 500kV Line | 400 | 400 | Hybrid | Solar/Battery | Not Started |  | 400 | 400 | 0 | 0
MISO | J2303 | Withdrawn | 2021-07-19T04:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Waushara | WI | DPP-2021 | East (ATC) |  | Network Resource Interconnection Service (NRIS) | Sand Lake 138kV Substation | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2304 | Active | 2021-12-02T05:00:00+00:00 |  |  | 2024-04-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2021 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Rockdale to Columbia | 400 | 400 | Battery Storage | Battery Storage | Not Started |  | 400 | 400 | 0 | 0
MISO | J2305 | Withdrawn | 2021-08-17T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Henderson - AB Brown 138 kV | 139 | 139 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2306 | Withdrawn | 2021-07-21T04:00:00+00:00 |  |  | 2024-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2021 | Central |  | Network Resource Interconnection Service (NRIS) | Commodore-Jordan | 150 | 150 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J2307 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Greentown-Walton | 130 | 130 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2308 | Active | 2022-03-23T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Greentown-Walton 230kV | 35 | 35 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2309 | Active | 2021-09-07T04:00:00+00:00 |  |  | 2024-10-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Murray | MN | DPP-2021 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Chanarambie - Ellsborough 115 kV line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 100 | 100 | 0 | 0
MISO | J2310 | Withdrawn | 2021-09-09T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2024-04-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Beauregard | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Rhodes | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2311 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-02-09T05:00:00+00:00 | AMEREN ILLINOIS | LaSalle | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hickock | 145 | 145 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2312 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2024-02-09T05:00:00+00:00 | AMEREN ILLINOIS | Putnam | IL | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hickock | 47.9 | 47.9 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2313 | Active | 2021-09-10T04:00:00+00:00 |  |  | 2023-12-31T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 80 | 80 | Solar | Photovoltaic | Not Started |  | 80 | 80 | 0 | 0
MISO | J2314 | Active | 2021-09-10T04:00:00+00:00 |  |  | 2023-12-31T05:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Petry Woods | 150 | 150 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J2315 | Withdrawn | 2021-09-10T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2023-12-31T05:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Petry Woods | 75.3 | 75.3 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2316 | Active | 2021-09-16T04:00:00+00:00 |  |  | 2023-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dickinson | MI | DPP-2021 | East (ATC) | Phase 1 |  | Nordic 138kV Substation | 77.5 | 77.5 | Solar | Photovoltaic | Not Started |  | 77.5 | 77.5 | 0 | 0
MISO | J2317 | Active | 2021-12-21T05:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | CLECO POWER LLC | Ouachita | LA | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Sterlington - Bastrop 115 kV | 225 | 225 | Solar | Photovoltaic | Not Started |  | 225 | 225 | 0 | 0
MISO | J2318 | Active | 2022-03-28T04:00:00+00:00 |  |  | 2025-10-25T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Warren | IN | DPP-2021 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | North East (Castle) - Culley 138 kV (J1642 POI) | 75 | 75 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2319 | Withdrawn | 2021-08-24T04:00:00+00:00 | 2021-12-22T05:00:00+00:00 |  | 2023-11-01T04:00:00+00:00 | ITC | Huron | MI | DPP-2021 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Stein 345 kV substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2320 | Withdrawn | 2021-09-10T04:00:00+00:00 | 2023-10-25T04:00:00+00:00 |  | 2023-12-31T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2021 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Inverness | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2321 | Withdrawn | 2022-05-16T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2025-04-30T04:00:00+00:00 | COOPERATIVE ENERGY | Lamar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Columbia to Plant Morrow 161kV | 180 | 180 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2322 | Active | 2022-05-17T04:00:00+00:00 |  |  | 2025-07-02T04:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Pine Prairie to Coughlin 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2323 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Webster | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Webster-Lehigh 345kV | 145 | 145 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2324 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2027-02-24T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Winnebago | IL | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Shirland Ave Tap (Y-54) to Shaw 69kV | 35 | 35 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2325 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2025-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bastrop to Sterlington 115 kV | 175 | 175 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2326 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-10-28T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Outagamie | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Werner West - Highway 22 345 kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2327 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | LaMoure | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Ellendale 345 kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2328 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Keo 500kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2329 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Wabash River-Whitesville South 230 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2330 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Leflore | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Winona to Greenwood 115 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2331 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Franklin | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | West Frankfort East Substation 345kV | 127 | 127 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2332 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cottonwood | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Lyon County - Cedar Mountain 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2333 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | McPherson | SD | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Ellendale - Twin Brooks 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2334 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Redhawk Substation 138kV | 195 | 195 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2335 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Plover 115 kV Substation (J1573 substation) | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2336 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-08-29T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Union | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Sterlington - Downsville 115 kV Line | 125 | 125 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2337 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMEREN MISSOURI | St. Francois | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | St. Francois 138kV 4ST FRANC 1 bus 345774 | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2338 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | McPherson | SD | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Ellendale - Twin Brooks 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2339 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cocodrie-Forest Hill 230kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2340 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Rush | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | RUSHVILLE 69 kV - HEMILROY 69 kV | 43 | 43 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2341 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Ricuskey-Woodward 230kV | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2342 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-05-15T04:00:00+00:00 | ITC MIDWEST | Worth | IA | DPP-2022 | West | Phase 1 |  | Worth County | 230 | 230 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2343 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Marion | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 138 kV line from Georgetown substation (Bus# 254598) to North Substation (Bus# 254630) | 130 | 130 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2344 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Stutsman | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Jamestown 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2345 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2028-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marathon | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gardner Park-Stone Lake 345kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2346 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cottonwood | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Lyon County - Cedar Mountain 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2347 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | METC | Roscommon | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Higgins - Mio Dam 138 kV Line | 40 | 40 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2348 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Minden to Sarepta 115 kV | 225 | 225 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2349 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | Southern Illinois Power Cooperative | Jackson | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Jackson to Campbell Hill 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2350 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | J2134 POI to White Bluff 115kV Line | 115.5 | 115.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2351 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC RECTOR NORTH - RECTOR 161kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2352 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Woodbury | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Raun - Lehigh 345 kV | 118 | 118 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2353 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds - Burr Oak 345 kV Line | 278 | 278 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2354 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marinette | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Crivitz | 65 | 65 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2355 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-11-30T05:00:00+00:00 | AMEREN ILLINOIS | Greene | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | A Tap on 4JERSEYVL-4ROODHSE | 70 | 70 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2356 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cash-Newport AB 161 kV line | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2357 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-05-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lafourche | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Thibodaux 230 kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2358 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Other_ | 113.98 | 113.98 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2359 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | AMEREN MISSOURI | Madison | MS | DPP-2022 | Central | Study Not Started | Network Resource Interconnection Service (NRIS) | Mannsdale - Catlett 230 kV | 58.5 | 58.5 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2360 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-05-07T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | TH Pfizer Jct. - Worthington (HED), Linton | 90 | 90 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2361 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-22T04:00:00+00:00 |  | 2026-05-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Perry | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Oppelo 161 kV Substation | 105 | 105 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2362 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | VEEDERSBURG WEST 230kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2363 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | ITC MIDWEST | Washington | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Marshalltown-Laurel 161kV | 226 | 226 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2364 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2030-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Page | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Madison-Orient 345kV | 175 | 175 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2365 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Werner West - Rocky Run 345kV | 115 | 115 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2366 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Werner West - Rocky Run 345kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2367 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | LaMoure | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Ellendale 345kV SS | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2368 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | LaMoure | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Ellendale 345kV SS | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2369 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Taylor | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Madison-Orient 345kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2370 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bolton - Raymond Calpine 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2371 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Dunn - Oak Ridge 115 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2372 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-03-01T05:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bloomington Brokaw 138kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2373 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-01-25T05:00:00+00:00 |  | 2025-01-06T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 230kV Graywood or (new) Big Lake | 40 | 40 | Waste Heat Recovery | Steam Turbine (including Nuclear, Geothermal and Solar Steam) | Not Started |  | 0 | 0 | 0 | 0
MISO | J2374 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Greenwood to Banner 345 kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2375 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-05-07T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Macon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Faraday 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2376 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Shelby | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4PANA-4SHELBYVL 138kV | 60 | 60 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2377 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Peoria | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bloomington Brokaw 345 kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2378 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | ITC | Macomb | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Lenox - St. Clair 120 kV line | 190 | 190 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2379 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Clay | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Xenia 345kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2380 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-11-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Meade | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Meade County 161kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2381 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Union | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | DOWNSVILLE- RUSTON EAST (LAGEN) 115 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2382 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-04-24T04:00:00+00:00 | AMEREN MISSOURI | Randolph | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 5ADAIR - 5THMHIL (AECI) 161 kV | 115 | 115 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2383 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-05-07T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Macon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Faraday 345kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2384 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Shelby | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4PANA-4SHELBYVL 138kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2385 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Franklin | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | SWARTZ 115 KV | 179 | 179 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2386 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Marked Tree 161 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2387 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | AMEREN MISSOURI | Stoddard | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Stoddard 161 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2388 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Macon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Faraday 345kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2389 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Adams | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Monument 138kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2390 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Fulton | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ipava 138kV | 350 | 350 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2391 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tallahatchie | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Webb 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2392 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | METC | Mason | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | PERE MARQUETTE 138 KV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2393 | Active | 2023-08-25T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Coles | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Kansas West Substation 138kV | 164 | 164 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2394 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Independence ISES - Powerline Road 500 kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2395 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Sheridan EHV - El Dorado EHV 500 kV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2396 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | SHERIDAN EHV - EL DORADO EHV 500 kV (851.1) | 400 | 400 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2397 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | SHERIDAN EHV - EL DORADO EHV 500 kV (851.1) | 160 | 160 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2398 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Independence ISES - Powerline Road 500 kV | 160 | 160 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2399 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Independence ISES - Powerline Road 500 kV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2400 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Bienville | LA | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Sailes Substation 115kV | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2401 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | AMEREN ILLINOIS | Johnson | IL | DPP-2022 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | 7E W FKFT - 7SHAWNEE FP (TVA) 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2402 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | AMEREN ILLINOIS | Johnson | IL | DPP-2022 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | 7E W FKFT - 7SHAWNEE FP (TVA) 345kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2403 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Massac | IL | DPP-2022 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | Jordan - Massac 345 kV (Future Line: MTEP ID - 11925) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2404 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Baton Rouge | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | EAST | 38.8 | 38.8 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2405 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Peters Road 230 kV substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2406 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Pickens - Canton 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2407 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Sullivan | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Dresser-Merom (HED) 345kV line break | 198 | 198 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2408 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-03-07T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Switzerland | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Fairview 138 kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2409 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Independence | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | INDEPENDENCE-ISES 500kV Substation | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2410 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pottawattamie | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Pony Creek-Rolling Hills Wind 345kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2411 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | CLECO POWER LLC | De Soto | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Red River-Mansfield 138kV | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2412 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | LR Alexander 115kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2413 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hoopeston West 138kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2414 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hoopeston 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2415 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Richard 138kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2416 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Trempealeau | WI | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | North Rochester-Briggs Road 345kV | 125 | 125 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2417 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Trempealeau | WI | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | North Rochester-Briggs Road 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2418 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Marshall | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Burr Oak 138kV | 140 | 140 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2419 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ITC MIDWEST | Faribault | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Huntley 345kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2420 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ITC MIDWEST | Faribault | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Huntley 345kV | 95 | 95 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2421 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Rush | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Greensboro-Gwynneville 345kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2422 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-10-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Washington | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Baldwin | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2423 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Columbia-North Madison 345kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2424 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Manuel 138kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2425 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMEREN MISSOURI | Montgomery | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7ENON - 7MONTGMRY 345kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2426 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Marion | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Kinmundy 138kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2427 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Marion | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Kinmundy 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2428 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Coahoma | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Clarksdale 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2429 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dane | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | North Madison 69kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2430 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Red Gum 115kV | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2431 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | St. Francis | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Memphis-Genpower Keo 500kV Line Break (located at "CHALKBLUFFPV" 500kV POI SS, co-located with | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2432 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Lula-Tunica 115kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2433 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-10-01T04:00:00+00:00 | GREAT RIVER ENERGY | Wadena | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Wing River-Riverton 230kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2434 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2028-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hoopeston West 138kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2435 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Webster | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Webster-Wright 161kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2436 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | CEDAR FALLS MUNICIPAL ELECTRIC UTILITY | Webster | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Webster-Lehigh 345kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2437 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC AUBREY to BRINKLEY EAST 230kV | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2438 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-10-01T04:00:00+00:00 | AMEREN MISSOURI | Montgomery | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7MONTGMRY -7ENON 345kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2439 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2028-10-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marathon | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gardner Park-Stone Lake 345kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2440 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-07-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Benton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | GOODLAND to MORRISON DITCH 138kV | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2441 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Bay - Centennial 138 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2442 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Ripley | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Batesville 138 kV | 84 | 84 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2443 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Kosciusko | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Leesburg 345 kV | 500 | 500 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2444 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-08-01T04:00:00+00:00 | METC | Van Buren | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Argenta - Twin Branch 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2445 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-09-01T04:00:00+00:00 | ITC MIDWEST | Greene | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Karma 161kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2446 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dunn | WI | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Allen S King 345kV - Eau Claire 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2447 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Redwood | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Lyon County - Cedar Mountain 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2448 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Haynesville South to Sarepta 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2449 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Faulkner | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Mayflower EHV 500 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2450 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tippecanoe | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | WESTWOOD 345 KV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2451 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Gerald Andrus SES Switchyard-Lake Village Bagby 230 Kv | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2452 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cleveland | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Sheridan EHV- EL Dorado EHV 500 Kv | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2453 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2022 | Central | Phase 1 |  | Casey West 345kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2454 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-12T05:00:00+00:00 | METC | Montcalm | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Eureka - Vestaburg 138kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2455 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | La Crosse | WI | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | French Island 69 kV Substation | 92 | 92 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2456 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC AUBREY-RITCHIE SES SWITCHYARD 230 KV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2457 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ENTERGY NEW ORLEANS, LLC | Orleans | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | PATERSON | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2458 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Conway | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Pleasant Hill 500kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2459 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | White Bluff EHV 500kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2460 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | White Bluff EHV 500kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2461 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2022-11-30T05:00:00+00:00 |  | 2026-11-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Christian | IL | DPP-2022 | Central | Study Not Started | Network Resource Interconnection Service (NRIS) | Pana 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2462 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ITC MIDWEST | Worth | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Ledyard-Colby 345kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2463 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Washington | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Baldwin | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2464 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ITC MIDWEST | Worth | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Ledyard-Colby 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2465 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2028-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Logan | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Goose Creek Energy Center to Maroa East 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2466 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Howard | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Hazleton-Mitchell County 345kV line | 130 | 130 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2467 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Manuel 138kV | 105 | 105 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2468 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado East 115kV | 130 | 130 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2469 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ITC MIDWEST | Linn | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Sub K (Tiffin)-Duane Arnold 345kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2470 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Donahue-Marksville 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2471 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ITC | Lenawee | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Beecher-Cement City 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2472 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-05-07T04:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Merom 345kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2473 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Marion | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hanna 138kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2474 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Sangamon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4Austin to 4Virden 138kV t-line | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2475 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ITC | Monroe | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Toll Rd 120kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2476 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Fayette | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Otego 138kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2477 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Memphis EHV to Keo EHV 500 kV | 600 | 600 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2478 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | INDEPENDENCE-ISES - POWERLINE ROAD 500 kV | 700 | 700 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2479 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Red Gum to Metropolis 115 kV | 140 | 140 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2480 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Daviess | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reid to Daviess County 161 kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2481 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2030-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pocahontas | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Webster-Irvington 345kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2482 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Memphis EHV to Keo EHV 500 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2483 | Withdrawn | 2022-09-09T04:00:00+00:00 | 2023-03-21T04:00:00+00:00 |  | 2025-11-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Amite | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | GILLSBURG SS (CE)-LIBERTY115 Kv | 105 | 105 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2484 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | Monroe | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Seville TP-Niles TP 120 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2485 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | Livingston | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Madrid - Blackfoot 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2486 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | Monroe | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Monroe-Lallendorf 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2487 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gallagher-Tittabawassee 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2488 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Almeda Junction-Shale 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2489 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Red River | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Western Kraft-Layfield 230 kV | 140 | 140 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2490 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | Tuscola | MI | DPP-2022 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Tuscola-Arrowhead 120kV Transmission Line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2491 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Midland | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Edenville - Price Rd. Jct 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2492 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-10-31T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Wilkin | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Wahpeton 230kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2493 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Arenac | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gallagher - Tittabawassee 345 kV | 184 | 184 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2494 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-11-01T04:00:00+00:00 | METC | Midland | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Clare Jct to Vernon Jct 138 kV | 178 | 178 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2495 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-04-29T04:00:00+00:00 | GREAT RIVER ENERGY | Benton | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Benton County 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2496 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-03-07T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds 345 kV Substation | 400 | 400 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2497 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2026-03-07T05:00:00+00:00 | AMEREN ILLINOIS | Jefferson | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | West Mt. Vernon | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2498 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-03-07T05:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Hamilton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hortonville-Noblesville Line 345 kV | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2499 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2026-03-07T05:00:00+00:00 | METC | Ottawa | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Blendon 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2500 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY TEXAS, INC. | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bon Wier to Cooper 138 kV | 175 | 175 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2501 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2024-11-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Goodhue | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | North Rochester 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2502 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-02-27T05:00:00+00:00 | MINNESOTA POWER INC. | Morton | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Square Butte East 230 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2503 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lincoln | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Downsville - Ruston East 115 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2504 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Coles | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mattoon East 138 kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2505 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bon Wier to Cooper 138 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2506 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | CITY OF COLUMBIA, MISSOURI (WATER AND LIGHT DEPT.) | Boone | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 5BOLSTAD 161kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2507 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Pike | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gibson Sta to Petersburg (IP&L) 345 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2508 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado Ehv - Sarepta 345kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2509 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Tippecanoe | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Westwood 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2510 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Stuttgart Rcuskey - Woodward 230kV | 350 | 350 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2511 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Conway | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Pleasant Hill 500kV Substation | 85 | 85 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2512 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Kosciusko | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Leesburg 345 kV | 173 | 173 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2513 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Wabash River-Whitesville South 230 kV | 220 | 220 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2514 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Pike | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gibson Sta to Petersburg (IP&L) 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2515 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | White Bluff EHV 500kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2516 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | White Bluff EHV 500kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2517 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Aubrey to Brinkley East 230 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2518 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2024-11-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | LaMoure | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Jamestown 345 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2519 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Richland | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BAXTER WILSON SES SWYD - PERRYVILLE 500 500 kV (181.1,503.0) | 600 | 600 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2520 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Adams | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Saratoga-ACEC Badger West 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2521 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Marked Tree 161 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2522 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Manila - Dell EHV 161 kV (J2089 POI) | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2523 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Independence | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | INDEPENDENCE-ISES 500kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2524 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | AMEREN MISSOURI | Stoddard | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 5STODDARD - 5MORLEY (AECI) 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2525 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-11-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Dunn - Oak Ridge 115 kV | 175 | 175 | Hybrid | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2526 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Red River | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Western Kraft-Layfield 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2527 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | CLECO POWER LLC | Allen | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Caney 138 kV | 140 | 140 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2528 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Parkin to Kuhn Road 161 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2529 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cocodrie - Hineston 230kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2530 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clinton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Thorntown to Kokomo HP 230 kV | 170 | 170 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2531 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Union | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bernice - Vienna 115 kV | 140 | 140 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2532 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Sangamon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Latham 345 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2533 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Union | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bernice - Vienna 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2534 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | METC | Mason | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Pere Marquette 138 KV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2535 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Vermilion | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cooper - Leesville 138 kV | 210 | 210 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2536 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | AMEREN ILLINOIS | LaSalle | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Fox River - Ottawa 138kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2537 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Shawano | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Highway 22 345 kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2538 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clark | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Speed - Trimble (LGEE) 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2539 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clark | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Trimble (LGEE) - Speed 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2540 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-03-01T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Graves | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bryan Road | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2541 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-03-01T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Graves | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bryan Road | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2542 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clark | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Vesta Rd 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2543 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Bay - Centennial 138 kV | 175 | 175 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2544 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Shawano | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Highway 22 345 kV Substation | 95 | 95 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2545 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ITC MIDWEST | Buchanan | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Duane Arnold 345 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2546 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Deuel | SD | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Astoria 345kV | 185 | 185 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2547 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-07-18T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | McCracken | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | McCracken co sub to Bryan rd sub 161kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2548 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-07-18T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | McCracken | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | McCracken County Sub to Bryan Rd Sub 161kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2549 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-07-18T04:00:00+00:00 | AMEREN MISSOURI | Clark | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sub T to Maywood 345kV line | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2550 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2030-07-18T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Yellow Medicine | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Hazel Creek 345kV Substation | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2551 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-18T04:00:00+00:00 | AMEREN ILLINOIS | Putnam | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Putnam 138kV Substation, MTEP20 Project ID 13709 | 110 | 110 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2552 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-18T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Whiteside | IL | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Cordova to Sub 39 345kV line | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2553 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Killdeer | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2554 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-18T04:00:00+00:00 | AMEREN ILLINOIS | Putnam | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Putnam 138kV Substation, MTEP20 Project ID 13709 | 220 | 220 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2555 | Active | 2023-08-28T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | METC | Ingham | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | DELHI to TOMPKINS 138kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2556 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-18T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Whiteside | IL | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Cordova to Sub 39 345kV line | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2557 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2029-07-18T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Wood | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Arpin 345kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2558 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-07-18T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Delta Ms - Ruleville 115kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2559 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2029-07-18T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Wood | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Arpin 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2560 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cleveland South - Indianola 115kV | 130 | 130 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2561 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2030-07-18T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Yellow Medicine | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Hazel Creek 345kV Substation | 153 | 153 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2562 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-11-20T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Dewitt - Deluce | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2563 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Jackson | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Crandall | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2564 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 138kV Crawfordsville | 18.9 | 18.9 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2565 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Iroquois | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4GILMAN-4PAXTON E 138kV | 265 | 265 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2566 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-08-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Daviess | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gibson - Bedford 345 kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2567 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | METC | Ottawa | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | KENOWA | 240 | 240 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2568 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-04-01T04:00:00+00:00 | CLECO POWER LLC | Acadia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Habetz - Sellers Road 138 kV Line | 120 | 120 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2569 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | MINNESOTA POWER INC. | St. Louis | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Arrowhead 115 kV Substation | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2570 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lafourche | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Thibodaux 230 kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2571 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-01-31T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2022 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | New J866 Substation (Batesville - Robert E. Ritchie 230 kV line) | 176.6 | 176.6 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2572 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Hamilton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Noblesville STA - Hortonsville 345 kV line | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2573 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Washington | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gallagher to Bedford 138kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2574 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | STUTTGART RICUSKEY - WOODWARD 230 kV | 172 | 172 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2575 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Cincinnati 138 kV Substation | 198 | 198 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2576 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-01-31T05:00:00+00:00 | ITC MIDWEST | Louisa | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Denmark 161kV - Newport 161kV | 164.1 | 164.1 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2577 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Parkin 161kV | 260 | 260 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2578 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | METC | Tuscola | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Thetford (Atlanta) - Karn 138kV | 240 | 240 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2579 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-10T05:00:00+00:00 |  | 2027-06-15T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Cincinnati 138 kV Substation | 362 | 362 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2580 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Winn | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Montgomery to Winnfield 230 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2581 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Ripley | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Batesville 138kV Substation | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2582 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clark | IN | DPP-2022 | Central |  | Network Resource Interconnection Service (NRIS) | Speed 138 kV substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2583 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | METC | Eaton | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Battle Creek - Island Road 138 kV Line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2584 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-01T04:00:00+00:00 | AMEREN MISSOURI | Warren | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Warrenton 161kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2585 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-04-01T04:00:00+00:00 | HOOSIER ENERGY | Greene | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Worthington Primary - Merom Primary 345 kV line | 240 | 240 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2586 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clark | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | SPEED 345 | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2587 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sugar Creek - Cayuga 345 kV Transmission Line | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2588 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | METC | Jackson | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Tompkins - Vrooman 138 kV Line | 120 | 120 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2589 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | METC | Jackson | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Tompkins - Vrooman 138 kV line | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2590 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | ITC | Huron | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Stein - Rapson 345 kV line | 500 | 500 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2591 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2028-10-02T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Choctaw | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | WOLF CREEK 500 kV | 500 | 500 | High Voltage DC | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2592 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | METC | Tuscola | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Thetford (Atlanta) - Karn 138 kV line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2593 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-04-24T04:00:00+00:00 | AMEREN MISSOURI | Gasconade | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bland 138 kV Substation | 140 | 140 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2594 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Ray Braswell 230 kV | 650 | 650 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2595 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-06-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | LAKEOVER EHV-RAY BRASWELL EHV 500 kV | 650 | 650 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2596 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Memphis 500 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2597 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Memphis 500 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2598 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ITC MIDWEST | Mower | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Adams to Hayward 161 kV Tap | 198 | 198 | Solar | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2599 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Redwood | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Lyon County 345kV Substation | 216 | 216 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2600 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Wabasha | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Wabaco to Alma 161 kV Tap | 245 | 245 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2601 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Wabasha | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | North Rochester to Briggs Road 345 kV Tap | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2602 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | DeSoto | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Twinkletown 230 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2603 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Havana-Shockey 138 kV | 320 | 320 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2604 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Clinton | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | South Centralia 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2605 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | Steele | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | ALEXANDRIA 345 KV | 339 | 339 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2606 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | Steele | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Alexandria 345kV | 361 | 361 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2607 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Redhawk 138 kV - MTEP Project (17976) | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2608 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Stevens | MN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hancock 161kV Substation | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2609 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Waushara | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Sand Lake 138kV Sub | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2610 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Bond | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4GREENVIL to 4HOOKDALE 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2611 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | METC | Alcona | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | IOSCO-SPRUCE ROAD 138 | 215 | 215 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2612 | Active | 2023-09-07T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Flora 115kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2613 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Independent - Holland Bottom 500kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2614 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Henry | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Oak Grove 161 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2615 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Warren | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | FB Culley to Dubois Transmission Line | 145 | 145 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2616 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Scanlan (Cajun) to Bosco SS 138 kV line | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2617 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | METC | Van Buren | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Palisades to Argenta 345 kV | 240 | 240 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2618 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ITC | Macomb | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Lenox 120kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2619 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | METC | Montcalm | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Kenowa to Nelson Rd. 345kV | 140 | 140 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2620 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ouachita | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bearden to Camden North 115 kV | 164 | 164 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2621 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | St. Croix | WI | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Pine Lake 161 kV Substation | 115 | 115 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2622 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Drew | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Wilmar to Monticello South 115 kV | 107 | 107 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2623 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Hot Spring | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | H.S. EHV to Friendship 115 kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2624 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-01-01T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Stevens | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Big Stone South 345kV Substation | 450 | 450 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2625 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Marion | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Maywood 345kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2626 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 345kV Commodore to Jordan | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2627 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Adams | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | East Quincy 138 kV substation | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2628 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-07-01T04:00:00+00:00 | ITC | Huron | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Rapson 345 kV | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2629 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Newton | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Leach to Newton Bulk 138 kV Line | 175 | 175 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2630 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Woodruff | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Des Arc to Cotton Plant 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2631 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Stuttgart Ricuskey- Tarleton 230 KV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2632 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Sarpeta to Minden 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2633 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Van Buren | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Clinton Industrial - AECC Clinton West 161 KV | 61 | 61 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2634 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ouachita | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Camden Maguire - Smackover 115 KV | 131.1 | 131.1 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2635 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Cane 138 kV | 52 | 52 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2636 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clark | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BISMARCK-AECC ALPINE 115 KV | 78.5 | 78.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2637 | Withdrawn | 2022-09-10T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cotton Plant- Brinkley West 115KV | 64.5 | 64.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2638 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Nevada | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Emmet SS - Hope East SS 115KV | 58 | 58 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2639 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Bradley | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Hermitage South - Hilo 115KV | 105.8 | 105.8 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2640 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Sheridan EHV - El Dorado EHV 500KV | 394.5 | 394.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2641 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | New Port 161kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2642 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bogalusa 115 kV - Dexter 115 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2643 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bogslusa 115 kV - Dexter 115 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2644 | Active | 2022-09-10T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Eudora - Chickasaw (LAGEN) | 90 | 90 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2645 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4PREST - 4BALDWIN 138 kV | 199 | 199 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2646 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lincoln | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | REESE 115 - TRUSSELS CROSSING (LAGEN) | 130 | 130 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2647 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-01-02T05:00:00+00:00 | AMEREN ILLINOIS | Franklin | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | West Frankfort East 345 kV (7E W FKFT) | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2648 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-02T04:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sidney 138 kV | 135 | 135 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2649 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-09-02T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | WEST MEMPHIS EHV - KEO EHV 500kv | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2650 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2024-02-05T05:00:00+00:00 |  | 2027-09-30T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Hancock | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sunnyside to Hanna 345 kV | 236 | 236 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2651 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Baton Rouge | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Colfel - Moler 230 kV line | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2652 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Rosemount - Nininger (GRE) 115 kV line | 197 | 197 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2653 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-05-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Polk | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Army Post 161kV Substation | 170 | 170 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2654 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clinton | IN | DPP-2022 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | Tap on Frankfort - New London 230 kV Line | 180 | 180 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2655 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Polk | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Army Post 161 kV Substation | 170 | 170 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2656 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | AMEREN ILLINOIS | Macon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4LATHAM-4N DEC E 138 kV | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2657 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-05-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds - Burr Oak 345 kV Line | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2658 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-23T04:00:00+00:00 |  | 2026-05-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7CASEY-7NEWTON 345kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2659 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-20T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Sangamon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Turner Switchyard Substation 345 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2660 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-23T04:00:00+00:00 |  | 2027-05-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7CASEY-7NEWTON 345kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2661 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | AMEREN ILLINOIS | Marion | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7Xenia- 7MT Vrnon 345 KV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2662 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7CASEY-7NEWTON 345kV | 395 | 395 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2663 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds - Burr Oak 345 kV Line | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2664 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Cayuga Sta - Nucor 345 kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2665 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Mercer | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Coyote Switchyard 345kV Substation | 347 | 347 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2666 | Active | 2024-01-09T05:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Walworth | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Brick Church 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2667 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Greenwood-Rapson 345 kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2668 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Mason | MI | DPP-2022 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Lake County to Pere Marquette 138 kV | 225 | 225 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2669 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Mason | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Lake County to Pere Marquette 138 kV | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2670 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Mason | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Ludington to Keystone 345 kV | 223 | 223 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2671 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Arenac | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Whittemore to Twining 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2672 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Shiawassee | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Cornell to Bingham 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2673 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Clare | MI | DPP-2022 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Bard Rd to Warren 138 kV | 225 | 225 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2674 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Clinton | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Bingham to Marquette 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2675 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Gladwin | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | BARD ROAD - GALLAGHER 138 KV | 170 | 170 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2676 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | Huron | MI | DPP-2022 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Rapson -Stein 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2677 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Greenwood 120 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2678 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Delta | MI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Chandler 138 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2679 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ITC | Livingston | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | COLFAX to Madrid 120 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2680 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-20T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Dunklin | MO | DPP-2022 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Jim Hill-Hayti South 161 kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2681 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Columbia | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Springhill 115kV (A) to Taylor 115kV (B) | 170 | 170 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2682 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-02T05:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Independence-ISES- Newport 161 KV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2683 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | New Substation on Rye Co - Cypress 138 kV (Same POI as J2071) | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2684 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | ITC | St. Clair | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | BUNCE (120kV) (Bus Name: 19BUNCE1) | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2685 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sharkey | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Rolling Fork 115 kV Substation | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2686 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Muscatine | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Walcott 345 kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2687 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Hancock | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sunnyside to Gwynneville 345kV line | 300 | 300 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2688 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-26T04:00:00+00:00 | ENTERGY TEXAS, INC. | Newton | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | NEWTON 138 kV | 130 | 130 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2689 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-26T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | JACINTO 230 kV | 180 | 180 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2690 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | AMEREN ILLINOIS | Washington | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Prairie State-W. Mt. Vernon-4541 | 500 | 500 | Hybrid | Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2691 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | AMEREN MISSOURI | Bollinger | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Rush-Baldwin-4585 345 kV | 500 | 500 | Hybrid | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2692 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2028-10-02T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Choctaw | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | WOLF CREEK 500 kV | 500 | 500 | High Voltage DC | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2693 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Franklin | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 115 kV WISNER | 105 | 105 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2694 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | AMEREN ILLINOIS | Christian | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7COFFEEN-7PANA 345 kV | 500 | 500 | Hybrid | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2695 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Carroll | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 234 | 234 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2696 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | SANDY BAYOU 500 kV MTEP Project 22530 | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2697 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Aster - Commodore 345 kV MTEP Project# 11928/11929 | 500 | 500 | Hybrid | Solar/Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2698 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2028-10-02T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Choctaw | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | WOLF CREEK 500 kV | 500 | 500 | High Voltage DC | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2699 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Carroll | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 115 kV DARNELL | 58.1 | 58.1 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2700 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 138 kV LAKE CHARLES BULK | 170 | 170 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2701 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | COLONIAL WELSH 138 | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2702 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Fulton | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ipava-Macomb, West-1429 138 kV | 100.8 | 100.8 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2703 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Scott | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Meredosia 345 kV | 398 | 398 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2704 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BAXTER WILSON SES SWYD - PERRYVILLE 500 500 kV (181.1,503.0) | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2705 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Assumption | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | NAPOLEONVILLE 115 kV | 220 | 220 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2706 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BAXTER WILSON SES SWYD - PERRYVILLE 500 500 kV (181.1,503.0) | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2707 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Assumption | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | PAINCOURTVILLE 115 kV | 165 | 165 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2708 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BAXTER WILSON SES SWYD - PERRYVILLE 500 500 kV (181.1,503.0) | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2709 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-04-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | DEEDSVILLE 345 | 228 | 228 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2710 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Clinton | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Mulliken Jct.- Chester 69 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2711 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | FLINT LAKE - SOUTH VALPARAISO 138 kV | 122 | 122 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2712 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Clinton 230 | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2713 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Mercer | IL | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | OAK GROVE - MERCER CO (AMRN) | 47.6 | 47.6 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2714 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | CLECO POWER LLC | St. Landry | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | EUNICE 138 kV | 162 | 162 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2715 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | COLONIAL ACADEMY CO 138 kV | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2716 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | HAMPTON 345 KV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2717 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-10-23T04:00:00+00:00 |  | 2029-05-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Hot Spring | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | ETTA 500kV Substation | 600 | 600 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2718 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | AMEREN MISSOURI | New Madrid | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2719 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | METC | Gladwin | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | BARD ROAD 138kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2720 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-04-25T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Yazoo | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Midway SS (CE) - Yazoo City SS 115 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2721 | Active | 2023-10-19T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Panola | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Senatobia-Sardis 115 kV Line | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2722 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clinton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Tap on Frankfort - New London 230 kV Line | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2723 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Warren | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | EAST WINAMAC-MONTICELLO 138kV | 249 | 249 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2724 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Cumberland | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7NEOGA-7HOLLAND 345 kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2725 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | METC | Ionia | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Marquette - North Belding 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2726 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | AMEREN MISSOURI | Montgomery | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7Enon- 7Montgmry 345 KV | 248 | 248 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2727 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Pickens - Midway SS (CE) 115kV | 140 | 140 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2728 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-07-24T04:00:00+00:00 | ITC MIDWEST | Freeborn | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Glenworth | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2729 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-02-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Baton Rouge | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | ADDIS-BIG CAJUN #1 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2730 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-07-24T04:00:00+00:00 | Southern Illinois Power Cooperative | Jackson | MN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Jackson North 161kV Substation | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2731 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-07-24T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Maple Leaf | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2732 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | METC | Ogemaw | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gallagher to Twinning 138kV | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2733 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lawrence | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Swifton - AECC Hoxie South 161kV | 126 | 126 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2734 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Gilmore to Wilson 161kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2735 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2022-12-06T05:00:00+00:00 |  | 2026-09-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita | LA | DPP-2022 | South |  | Network Resource Interconnection Service (NRIS) | Selman Field 69 kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2736 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Rosedale to Stringtown 115kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2737 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Sabine | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Hartburg - AEP Layfield 500kV Line | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2738 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-02-01T05:00:00+00:00 | MIDAMERICAN ENERGY CO. | Rock Island | IL | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Sub 17 161 kV | 128 | 128 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2739 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Ohio | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 5WLSNBR 161 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2740 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | SHELBY SS | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2741 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | DELTA SES SWITCHYARD | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2742 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | White | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BEEBE | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2743 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BOGALUSA | 175 | 175 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2744 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Wilkinson | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | CENTREVILLE | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2745 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Humphreys | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BELZONI | 90 | 90 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2746 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-07-04T04:00:00+00:00 | HOOSIER ENERGY | Rush | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Boyd - Sexton | 70 | 70 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2747 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-04T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Greene | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Edwardsport IGCC - Amo 345kV Line | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2748 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-04T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Clearwater | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Winger - Wilton 230kV Transmission | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2749 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-04T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Polk | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Winger 115kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2750 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 230kV Ritchie SES Switchyard - Tarleton line | 197.5 | 197.5 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2751 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 115kV Stringtown substation | 175 | 175 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2752 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Montgomery | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | ELLIOTT SS-SAWYER SS(CE) 115 kv line (New Substation Added) | 130 | 130 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2753 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Carroll | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | New substation on the 115kV Darnell - Tallulah line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2754 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Polk | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 138kV Bragg - SHECO Menard Line | 170 | 170 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2755 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pike | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AMITY SS-AECC MURFREESBORO EAST 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2756 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Livingston | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Burna Tap(340091) - Joy2(340092) 69 kV | 65 | 65 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2757 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Cherokee | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Little Sioux - Clipper | 160.3 | 160.3 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2758 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-02-27T05:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Stuttgart Ricuskey to Woodward 230kV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2759 | Active | 2023-09-12T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Woodward-Ricuskey 230 kV Line | 170 | 170 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2760 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | MINNESOTA POWER INC. | Hubbard | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | BADOURA4 (608610) 230 kV Substation | 68 | 68 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2761 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-30T04:00:00+00:00 | COOPERATIVE ENERGY | Marion | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Columbia | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2762 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-13T04:00:00+00:00 |  | 2025-11-05T05:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4TAZEWELL-4FLINT 138kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2763 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cleveland/South- Steiner(CE) 115 KV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2764 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Jonesboro (APL) - Cash 161 KV" | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2765 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Carroll | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Darnell 115 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2766 | Active | 2023-08-21T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Howard | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 400 | 400 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2767 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-04T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Hightower - Rye 138kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2768 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Shelby SS - Roundaway SS (CE) 115 kV Line | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2769 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Helena | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Amite - Gillsburg Tap 115 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2770 | Active | 2023-09-12T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | CLECO POWER LLC | Grant | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Colfax-Montgomery (EES) 230 kV Line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2771 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Coahoma | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 6CROSSROADS! (337100) - 6MOONLAKE% (337107) 230 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2772 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Mercer | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Coyote Switchyard 345 kV Substation | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2773 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2022 | South |  | Network Resource Interconnection Service (NRIS) | Newport - Fisher 161 kV Line | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2774 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-07-20T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Ionia | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | 69kV Portland - Tremaine | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2775 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 125 | 125 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2776 | Withdrawn | 2022-09-07T04:00:00+00:00 | 2023-03-22T04:00:00+00:00 |  | 2025-01-01T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Fulton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | WINAMAC to BRUCE LAKE 69kV (Circuit ID 6913) NIPSCO AREA | 10 | 10 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2777 | Withdrawn | 2022-09-07T04:00:00+00:00 | 2023-03-22T04:00:00+00:00 |  | 2025-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Madison | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Cadiz Lapel Brockway Glass 69kV | 35 | 35 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2778 | Active | 2022-09-07T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Deedsville North Manchester Switching Sta 69kV (Circuit Number 6974). | 15 | 15 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2779 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clinton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Lafayette to Middlefork 69kV Line (Circuit 6909) | 40 | 40 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2780 | Active | 2023-10-05T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Pulaski | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | STARKE (Actual POI is on ASPHALTUM to MEDARYVILLE 69kV Circuit 6919 an appendix G facility) | 33 | 33 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2781 | Active | 2022-09-07T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | MONTICELLO 69kV (acutal POI is at the MILROY 69kV Substation on Circuit 6918 an appendix G Facility) | 35 | 35 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2782 | Active | 2022-09-07T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Newton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | KENTLAND-MOROCCO 69kV | 38 | 38 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2783 | Active | 2022-09-07T04:00:00+00:00 |  |  | 2025-01-01T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Monticello 69kV (Acutal POI is a tap on GUERNSEY - Monon Circuit 6907 an appendix G facility) | 33 | 33 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2784 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-20T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Sangamon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Turner 345kv Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2785 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado - Sheridan 500 kV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2786 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-07-01T04:00:00+00:00 | METC | Allegan | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Argenta - Tallmadge 345 kV | 189.25 | 189.25 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2787 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-27T04:00:00+00:00 |  | 2025-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BRINKLEY EAST-AECC AUBREY 230kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2788 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-08-07T04:00:00+00:00 | ITC | Wayne | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Dayton 120kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2789 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-08T05:00:00+00:00 |  | 2025-11-05T05:00:00+00:00 | AMEREN ILLINOIS | Jasper | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4NEWTON-4ROBNSNAM 138kV | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2790 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-13T04:00:00+00:00 |  | 2026-02-05T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Christian | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7Pana-7Austin 345kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2791 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-05-01T04:00:00+00:00 | LAFAYETTE UTILITIES SYSTEM | Lafayette | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Doc Bonin 69kV | 219.79 | 262.71 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J2792 | Withdrawn | 2022-08-31T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Persimmon Mill--Red Gum 115kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2793 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Saline | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Muddy 138 kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2794 | Active | 2022-08-23T04:00:00+00:00 |  |  | 2027-12-27T05:00:00+00:00 | AMEREN ILLINOIS | Fayette | IL | DPP-2022 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | A Tap on Kinmundy-Otego 138kv line | 90 | 90 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2795 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Union | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | DOWNSVILLE | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2796 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Newport Ab-Cash 161kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2797 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-15T04:00:00+00:00 | AMEREN ILLINOIS | White | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7NORRIS 345kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2798 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-08-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | E. Winamac - Monticello 138 kV line | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2799 | Active | 2022-09-14T04:00:00+00:00 |  |  |  | METC | Van Buren | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Argenta-Palisades 345 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2800 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2028-09-29T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Columbia | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | EL DORADO EHV - SAREPTA 345/115KV SW STA 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2801 | Active | 2023-09-11T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Woodruff | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Hunter North-McCrory 161 kV | 130 | 130 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2802 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-04-06T04:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Singer J1424 to Penton 230 kV line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2803 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Carroll | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Winona (3WINONA! 337060) - Carrollton (3CARROLLTON+ 337056) 115 kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2804 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2017-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Carroll | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Oak Grove - Galion 115kV Tap | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2805 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | VEEDERSBURG WEST 230 Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2806 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | AMEREN MISSOURI | Warren | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Warrenton 161kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2807 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-01T04:00:00+00:00 | METC | Ingham | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | DELHI to TOMPKINS 138kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2808 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Fayette | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ramsey East 138 sub (co-located with Dressor and Switchgrass) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2809 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Iroquois | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4GILMAN - 4PAXTON E 138 kV | 133 | 133 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2810 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-01T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Killdeer 345/161 sub (Emery station 161 outlet) | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2811 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Killdeer 345kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2812 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | METC | Hillsdale | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Moore Road 138kV Sub | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2813 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-02-15T05:00:00+00:00 | METC | Saginaw | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Slate Goss 345 KV Line | 195 | 195 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2814 | Active | 2022-09-07T04:00:00+00:00 |  |  | 2026-02-15T05:00:00+00:00 | METC | Kalamazoo | MI | DPP-2022 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Argenta Morrow 138 kV | 220 | 220 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2815 | Active | 2022-08-30T04:00:00+00:00 |  |  | 2025-02-15T05:00:00+00:00 | METC | Barry | MI | DPP-2022 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Argenta - Verona 138kV Line | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2816 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-03-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Rilla (Endpoint A) - Riverton (Endpoint B) | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2817 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | EAST TEXAS ELECTRIC COOPERATIVE, INC. | Liberty | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Batiste Creek 230kV Substation | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2818 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ouachita | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC CAMDEN SOUTH - STEPHENS 115kV | 130 | 130 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2819 | Active | 2022-09-07T04:00:00+00:00 |  |  | 2025-02-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Red River | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Carroll (CLECO) - Ringgold 138 kV | 80 | 80 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2820 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Daviess | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bon Harbor Tap-Stanley Tap 69kv | 35 | 35 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2821 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Crittenden | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sullivan - Marion Jct 69 kV | 30 | 30 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2822 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | MICHIGAN PUBLIC POWER AGENCY | Van Buren | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Palisades - Vergennes 345 kV | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2823 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Jefferson | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Madison West 138kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2824 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Yazoo | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Picken - Midway SS (CE) 115 kV | 70 | 70 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2825 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Panola | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | COMO - CRENSHAW 115kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2826 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | HOOSIER ENERGY | Greene | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Worthington (07WORTH) - Sandborn Primary (07SAND61) 161kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2827 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Norrell 230kV Substation | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2828 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | L.R. 145th St - Wrightsville 115kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2829 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Scott | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Scottsburg - Speed 69kV | 30 | 30 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2830 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | HOOSIER ENERGY | Jennings | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Brewersville - Dabney 69kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2831 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | CLECO POWER LLC | Natchitoches | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Colfax-Rodemacher 230 kV | 36 | 36 | Hydro | Hydroelectric | Not Started |  | 0 | 0 | 0 | 0
MISO | J2832 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Carroll | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Darnell - Tallulah 115 kV | 110 | 110 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2833 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Wood | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Sigel - Auburndale Tap (Y-107) 69kV | 40 | 40 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2834 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Fond du Lac | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | South Fond du Lac - North Fond du Lac 69kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2835 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Jefferson | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Madison - Scottsburg 138kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2836 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Livingston | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Burna Tap-Burna 69kv | 45 | 45 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2837 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Jennings | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | North Vernon - Madison 138 kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2838 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Richland | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Dunn - Oak Ridge (LA) 115kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2839 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ascension | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Donaldsonville to Evergreen 230 kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2840 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-30T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Byron 161 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2841 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Independence | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Independent - Holland Bottom 500kV | 500 | 500 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2842 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mason 138kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2843 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Hendricks | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Qualitech 345kV - Amo 345kV | 110 | 110 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2844 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Henderson | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | AB Brown 345 - Reid EHV (BREC Terminal) | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2845 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-15T04:00:00+00:00 | ITC MIDWEST | Freeborn | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Hayward - Adams 161kV line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2846 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-01T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Pulaski | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds--Burr Oak 345kV line | 700 | 700 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2847 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Starke | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds--Burr Oak 345kV Line | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2848 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-01T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Hamilton | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Noblesville--Fall Creek 345kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2849 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-01T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Pulaski | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds--Burr Oak 345kV line | 245 | 245 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2850 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bagby to Gerald Andrus 230 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2851 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2022-12-09T05:00:00+00:00 |  | 2027-06-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Walker | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Rocky Creek | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2852 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-04-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Roberts | SD | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Browns Valley 230kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2853 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-08-30T04:00:00+00:00 | CITY WATER LIGHT & POWER | Sangamon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Westchester 138 kV station - PSSE bus 343513 | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2854 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | White | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Griffithville - SERCY Price 115 kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2855 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Lawrence | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bedford - Edwardsport 138 kV line | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2856 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-06-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Jefferson | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Franklin EHV - Grand Gulf Transmission 500 kV | 500 | 500 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2857 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-06-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Banks SS (CE) - Hambrick SS (CE) 115 kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2858 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-11-20T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bayou Cove - Richard 138 kV circuit 2 | 110 | 110 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2859 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-11-20T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC KEO-BAUCUM 115 kV | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2860 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Roy S Nelson - DeRidder Mill 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2861 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Mower | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Rochester 161kV (A) to Adams 161kV (B) | 147 | 147 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2862 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Bradley | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Hermitage South-Hilo 115kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2863 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Fillmore | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Other_ | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2864 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Nevada | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | McNeil EHV to Etta EHV 500kV | 375 | 375 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2865 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ouachita | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado EHV - McNeil EHV 500kV | 375 | 375 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2866 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Nevada | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | McNeil 500kV (A) to Etta 500kV (B) | 375 | 375 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2867 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Wabasha | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Lake City (A) to Zumbro Falls (B) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2868 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-12-01T05:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Jackson | WI | DPP-2022 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Alma Center- Merrillan (DCP) 69 KV | 46.2 | 46.2 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2869 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | GERALDANDRUS SES SWITCHYARD-INDIANOLA 230 KV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2870 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-12-01T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Sawyer | WI | DPP-2022 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Stone Lake 345kV | 243.6 | 243.6 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2871 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Mississippi | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Dell to Nucor-Yamato 161 kV Switching Station | 70 | 70 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2872 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-12-01T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Hampton 345kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2873 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | COOPERATIVE ENERGY | Simpson | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Magee - White Oak 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2874 | Active | 2022-08-31T04:00:00+00:00 |  |  | 2025-11-15T05:00:00+00:00 | METC | Bay | MI | DPP-2022 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | METC Hampton 345 kV | 85 | 85 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2875 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Presque Isle | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Port Calcite- Rockport 138 KV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2876 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Arenac | MI | DPP-2022 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Whittemore to Twining 138 kV | 175 | 175 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2877 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Midland | MI | DPP-2022 | East (ITC) | Phase 2 | Network Resource Interconnection Service (NRIS) | Murphy-Tittabawassee 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2878 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2022 | East (ITC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Greenwood-Rapson 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2879 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Washington | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Chemolite 115 kV Substation | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2880 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Woodward - Stuttgart Ricuskey 230 kV Line | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2881 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Pinebergen AECC to Glendale 115 kV Line | 125 | 125 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2882 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cooper-Penton Road 230kV | 410 | 410 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2883 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Mercer | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Coyote Switchyard 345kV Substation | 347 | 347 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2884 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cooper to Penton Road 230kV | 276 | 276 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2885 | Active | 2022-09-06T04:00:00+00:00 |  |  | 2025-01-10T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Red Lake | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Plummer Pipe | 130 | 130 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2886 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Sangamon | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4Auburn N-4Jacksnvl 138kV | 115 | 115 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2887 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | COOPERATIVE ENERGY | Simpson | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Magee 161kV - White Oak 161kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2888 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Lafayette | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Baxter Wilson SES SWYD 500 kV | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2889 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-08-01T04:00:00+00:00 | METC | Allegan | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Argenta 138 kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2890 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Lake Charles Bulk 138kV Substation | 440 | 440 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2891 | Active | 2024-01-09T05:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Kenosha | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | 138kV line X-137 (Spring Valley to State Line) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2892 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ITC MIDWEST | Franklin | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Blackhawk (MEC) - Quinn 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2893 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-08-18T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bowling Green SS - Durant 115 kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2894 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-05-07T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Hendricks | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Westland Jct - Westline 69kV Line | 22.77 | 22.77 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2895 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clark | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bethlehem 138kV Substation | 120 | 120 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2896 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-04-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Sargent | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Gwinner 115kV Substation | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2897 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | San Jacinto | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Rivtrin - Staley 138kV Line #2 (Southern Line) | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2898 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-04-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Amite | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Franklin EHV - McKnight 500kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2899 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-04-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Chalkley Co to Goos Ferry 230kV | 250 | 250 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2900 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-04-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Amite | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Franklin EHV - McKnight 500kV | 400 | 400 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2901 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Columbia | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taylor - Macedonia 115 kV | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2902 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Warren | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Beech Grove SS 115 kV Substation | 70 | 70 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2903 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-02-01T05:00:00+00:00 | COOPERATIVE ENERGY | Lincoln | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bookhaven - Mallalieu 115kV | 130 | 130 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2904 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Plantation | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2905 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | COOPERATIVE ENERGY | Washington | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Entergy Hollandale - Nittayuma SS (CE) 115kV Line | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2906 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-09-30T04:00:00+00:00 | METC | Kalamazoo | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Jaguar 138kV substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2907 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-26T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | SHERIDAN 500 kV | 400 | 400 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2908 | Active | 2022-07-27T04:00:00+00:00 |  |  | 2023-07-30T04:00:00+00:00 | AMEREN ILLINOIS | Morgan | IL | DPP-2022 | Central | Phase 1 |  | Jacksonville North | 30 | 30 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2909 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-27T04:00:00+00:00 |  | 2027-06-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Remington AECC to Lonoke E 115kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2910 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-22T04:00:00+00:00 |  | 2026-06-14T04:00:00+00:00 | ENTERGY TEXAS, INC. | Chambers | TX | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Stowell 230kV | 303 | 303 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2911 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | CLECO POWER LLC | Calcasieu | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Penton 230KV Substation | 810 | 810 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2912 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Mercer | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Coyote Switchyard 345kV Substation | 347 | 347 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2913 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-04-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Sargent | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Forman 115kV Substation | 90 | 90 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2914 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-04-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Tammany | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Plant Daniel - McKnight 500kV | 450 | 450 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2915 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2028-07-18T04:00:00+00:00 | AMEREN MISSOURI | Clark | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sub T to Maywood 345kV line | 223 | 223 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2916 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | East Leesville-Rodemacher 230 KV | 400 | 400 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2917 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-03-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ouachita | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Prairie Road 115kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2918 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | AMEREN ILLINOIS | Jasper | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4EFFINGHM N - 4NEWTON 138kV | 97 | 97 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2919 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Montgomery | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Kokomo Webster St. to Walton 230 kV | 142.59 | 142.59 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2920 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | J1673 Interconnection Substation | 92 | 92 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2921 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-31T04:00:00+00:00 | ITC | Calhoun | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | DUCK LAKE - MAJESTIC 345 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2922 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Jasper | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Newton Switchyard 345 kV Substation | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2923 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2028-05-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Columbia | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | EL DORADO EHV - SARPETA 345/115 KV SW STA 345kV | 240 | 240 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2924 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Columbia | AR | DPP-2022 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | EL DORADO EHV - SARPETA 345/115 kV SW STA 345 kV | 240 | 240 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2925 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | AMEREN ILLINOIS | Logan | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gillett | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2926 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | AMEREN ILLINOIS | Franklin | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ashley to West Frankfort-1536 | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2927 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | AMEREN ILLINOIS | Randolph | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Tibbs | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2928 | Withdrawn | 2022-09-02T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Harrisburg 161 kV Substation | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2929 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Henderson 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2930 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Henderson | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | AB Brown 345 kV - Reid 345 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2931 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Henderson | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reid 345 kV - AB Brown 345 kV | 400 | 400 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2932 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-10-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Henderson 161kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2933 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gallagher-Tittabawassee 345kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2934 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Saginaw | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Thetford to Murphy 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2935 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | METC | Saginaw | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Thetford to Murphy 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2936 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-02T05:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Independence (A)(500kV) to Powerline (B) (500 kV) | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2937 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | PANA -OAKLEY 138 KV LINE Pana-Oakley-1466 | 186 | 186 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2938 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Knox | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Castro-Galesburg Monmouth Blvd.-1427 | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2939 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | COOPERATIVE ENERGY | Tunica | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Hambrick Switching Station 115kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2940 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-11-30T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sharkey | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Nitta Yuma SS (CE) - Rolling Fork 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2941 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-11-30T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Macon Lake SS - Lake Chicot Pump STA 115kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2942 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started |  | Cooper to Penton Road 230 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2943 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Minden to Sarepta 115 kV | 140 | 140 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2944 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Portage | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Rocky Run - Garder Park 345 kV | 350 | 350 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J2945 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Washington | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | 1 | 350 | 350 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J2946 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | ITC MIDWEST | Dubuque | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Salem - Hickory Creek 345 kV line | 160 | 160 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J2947 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-04-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Rock | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Rock River 138 kV Substations 1 (6 RICE) and 2 (5 RICE) | 205 | 205 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J2948 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-09-01T04:00:00+00:00 | ITC MIDWEST | Marshall | IA | DPP-2022 | West | Phase 1 |  | Marshalltown | 15 | 75 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J2949 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | ITC MIDWEST | Marshall | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Marshalltown 161 kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2950 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2018-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Clay | IA | DPP-2022 | West | Phase 1 |  | Clay County | 299.3 | 299.3 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2951 | Active | 2022-09-05T04:00:00+00:00 |  |  | 2024-06-01T04:00:00+00:00 | ITC MIDWEST | Union | IA | DPP-2022 | West | Phase 1 |  | Creston Roadhouse | 50 | 50 | Solar | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2952 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Chambers | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Crooked Bayou to Stowell 138 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2953 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Orange | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | CHISHOLM RD - SABINE 230 kV | 400 | 400 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2954 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC CORNING NORTH Ã¢?? DATTO 161 KV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2955 | Active | 2023-11-07T05:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Saline | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | WRIGHTSVILLE Ã¢?? WHITE BLUFF EHV 115 KV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2956 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Galion 115 kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2957 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-01-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Panola | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Como - Crenshaw 115 kV Line | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2958 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Claiborne | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Haynesville South 115kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2959 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Starke | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Rollin Schahfer (17SCHAHFER 255110) 345 kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2960 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-01-01T05:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Spencer | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 10CULY13 253500 (F.B. Culley ) - 10AEP_T 353586 (tap between Culley (10CULY13 253500) - Grandview ( | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2961 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Daviess | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Edwardsport Station (08EDWRDS 249722) - Whitefield (08WHTFLD 249876) 138 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2962 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-12-01T05:00:00+00:00 | Southern Illinois Power Cooperative | Hamilton | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Akin - Hamilton 138 kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2963 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Havana - Shockey 161kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2964 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Tallahatchie | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Webb 115 kV | 220 | 220 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2965 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Ashley | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Oak Grove 115kV | 230 | 230 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2966 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2025-10-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Quitman | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Batesville to Moon Lake ss 230kV Line | 450 | 450 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2967 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-10-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Lowe Grout Rd to Jennings 138kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2968 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2023-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2022 | South | Study Not Started |  | LC Bulk to Henning 138kV Line (Circuit 28) | 165 | 165 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2969 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2002-11-01T05:00:00+00:00 | MICHIGAN PUBLIC POWER AGENCY | Kalkaska | MI | DPP-2022 | East (ITC) | Study Not Started |  | Kalkaska Gen | 13.4 | 13.4 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J2970 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-15T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Posey | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | AB Brown 345 - Gibson(Duke Terminal) 345 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2971 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-08-15T04:00:00+00:00 | COOPERATIVE ENERGY | Covington | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Southwest Lone Star 161 kV - Mississippi Hub 161 kV | 280 | 280 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2972 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-15T04:00:00+00:00 | AMEREN ILLINOIS | Adams | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4Hull - 4Herleman 138 kV | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2973 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Shelby | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7Pana - 7Faraday 345 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2974 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-15T04:00:00+00:00 | AMEREN ILLINOIS | Adams | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4Hull - 4Herleman 138 kV | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2975 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | EAST TEXAS ELECTRIC COOPERATIVE, INC. | Jefferson | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bevil Substation 230 kV | 44.1 | 44.1 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2976 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-05-31T04:00:00+00:00 | EAST TEXAS ELECTRIC COOPERATIVE, INC. | Jasper | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Mill Creek SW Station 138 kV | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J2977 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Bradley | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC Hermitage south- Hilo 115Kv | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2978 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Memphis EHV to Keo 500 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2979 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2023-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mason City West 69 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2980 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2023-10-02T04:00:00+00:00 | COOPERATIVE ENERGY | Perry | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Hintonville 161/69 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2981 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2023-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Audrain | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ameren Centralia 69 kV Substation | 30 | 30 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2982 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2023-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Warren | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Line 6629 Monmouth 69 kV Switching Station | 35 | 35 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2983 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Woodward- AECC Grapevine 115 Kv | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2984 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Corning North to Datto 161kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2985 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Chicot - Eudora 115kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2986 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Deluce - Gillette 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2987 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | HOOSIER ENERGY | Greene | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Worthington - Merom 345kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J2988 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-03-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Humboldt | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | J2256 POI - Irvington 345kV line | 175 | 175 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2989 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-06-15T04:00:00+00:00 | ITC MIDWEST | Hardin | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Blackhawk (MEC)- Quinn 345 KV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2990 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-06-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pottawattamie | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Overland - J1859 POI 345kV Line Tap | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J2991 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ITC | Wayne | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Dayton 120kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2992 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | COOPERATIVE ENERGY | Perry | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Hintonville 161kV Substation | 160 | 160 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2993 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Woodward-Grapevine 115kV line | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2994 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-09-15T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Deluce 115kV | 40 | 40 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2995 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | CHICOT115kV Substation | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2996 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Corning North to Datto 161kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2997 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ITC | Livingston | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Colfax - Madrid 120kV | 175 | 175 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2998 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Fayetteville Bee Hollow Road 138kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J2999 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | COOPERATIVE ENERGY | Perry | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Hintonville 161kV | 400 | 400 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3000 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | HOOSIER ENERGY | Greene | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Worthington - Merom 345kV Line | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3001 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | J2134 POI to White Bluff 115kV Line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3002 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-30T04:00:00+00:00 | MINNESOTA POWER INC. | Pine | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Arrowhead - Bear Creek (GRE) 230 kV | 325 | 325 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3003 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4Havana2-4Cincinnati 138kV | 180 | 180 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3004 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Cane | 170 | 170 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3005 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Havana-Shockey (138kV) | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3006 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-01-02T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Milwaukee | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Granville 345kV Substation | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3007 | Active | 2022-08-25T04:00:00+00:00 |  |  | 2025-05-15T04:00:00+00:00 | METC | Mason | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | PERE MARQUETTE - LINDEMAN 138.0kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3008 | Withdrawn | 2022-08-24T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-05-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Cook | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Sheffield - Burnham 345 (Tie line between CE and NIPS, NIPS owns 1.87 miles) | 270 | 270 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3009 | Active | 2022-08-25T04:00:00+00:00 |  |  | 2025-05-15T04:00:00+00:00 | ITC | Washtenaw | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Dorset 120kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3010 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-09-27T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clay | IN | DPP-2022 | Central | Phase 1 | Energy Resource Interconnection Service (ERIS) | TAP ON THE CARBON TO BRAZIL 69KV LINE | 60 | 60 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3011 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Prairie State Plant Switchyard 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3012 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Coles | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Mattoon East 138 kV | 287 | 287 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3013 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Washington | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ashley | 100 | 100 | Battery Storage | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3014 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cooper to Leesville 138kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3015 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Ford | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Gilman - Watseka 138kV | 400 | 400 | Hybrid | Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3016 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Cass | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Walton | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3017 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Grant | SD | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Big Stone South 345 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3018 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pottawattamie | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Overland Trail - Fallow Avenue 345 kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3019 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Feliciana | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Fancy Point to Port Hudson 230 kV | 180 | 180 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3020 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lyon | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Lake Yankton to Buffalo Ridge 115kV | 165 | 165 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3021 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lyon | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Lake Yankton to Lyon County 115kV | 235 | 235 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3022 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Taylor | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Orient to Atchison County 345 kV | 400 | 400 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3023 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Hot Spring | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | H.S. EHV 500 kV Substation | 400 | 400 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3024 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-27T04:00:00+00:00 |  | 2026-03-07T05:00:00+00:00 | ITC MIDWEST | Louisa | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Newport 161 kV Bus High Side of T91 XFRMR 161/69 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3025 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Douglas | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Alexandria to Hudson 115 kV | 188 | 188 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3026 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Deridder Mill - Roy S Nelson 138 kV | 175 | 175 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3027 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | McLean | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | SANDBURG-7FARGO 345kV | 300 | 300 | Hybrid | Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3028 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | COOPERATIVE ENERGY | Perry | MS | DPP-2022 | South |  | Network Resource Interconnection Service (NRIS) | Hintonville to Waynesboro 161 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3029 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ITC MIDWEST | Freeborn | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Freeborn 161 kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3030 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | White Bluff to Sheridan 500kV | 450 | 450 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3031 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Jefferson | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4WLTNVL TP 138 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3032 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Sarepta | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3033 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Webster | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reid EHV 345 kV | 75 | 75 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3034 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-04T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | BRINKLEY WEST - BRINKLEY EAST 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3035 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-04T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Desha | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | REED SS - ROHWER 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3036 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2022 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | REMINGTON SS - LONOKE EAST 115kV line | 105 | 105 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3037 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2022 | South | Phase 1 | Network Resource Interconnection Service (NRIS) | Eldorado Upland SS 115kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3038 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado Upland SS 115kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3039 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Byron 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3040 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ouachita | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado EHV - McNeil EHV 500kV | 365 | 365 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3041 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-08-31T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Olmsted | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Byron 161kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3042 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. John the Baptist | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | 230kV Vacherie - Waterford Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3043 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Edwards | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3044 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Edwards | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3045 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Orange | TX | DPP-2022 | South |  | Network Resource Interconnection Service (NRIS) | Chisholm RD- Hartburg 230kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3046 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2025-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Red Gum to Metropolis 115 kV | 140 | 140 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3047 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2029-09-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Adair | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Orient-Atchison County 345kV | 263 | 263 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3048 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crawford | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | MOSES SES to AECC HUNTER NORTH | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3049 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Lakeover EHV - McAdams EHV 500 kV | 188 | 188 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3050 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | METC | Calhoun | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Oneida to Majestic 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3051 | Active | 2024-01-09T05:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | GREAT RIVER ENERGY | Chisago | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Rush City 230 kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3052 | Active | 2022-09-14T04:00:00+00:00 |  |  | 1990-03-01T05:00:00+00:00 | METC | Midland | MI | DPP-2022 | East (ITC) | Study Not Started |  | MCV | 300 | 300 | Gas | Steam Turbine (including Nuclear, Geothermal and Solar Steam) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3053 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Lakeover EHV - McAdams EHV 500 kV | 169 | 169 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3054 | Withdrawn | 2022-09-13T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2017-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bogslusa 500 kV - Franklin EHV 500 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3055 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bogalusa 500 kV - Franklin EHV 500 kV | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3056 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bogalusa 500 kV - Franklin EHV 500 kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3057 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Richard (Bus #335366) to Colonial Academy (Bus #335375) 138kV | 75 | 75 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3058 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Tarleton 230 kV | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3059 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-20T04:00:00+00:00 | METC | Midland | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | 18GLENRJ-18BULLOCKW | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3060 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-20T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 7CMDR-7ASTER 345 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3061 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lawrence | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Walnut Ridge (Bus #338208) to Sedgewick (Bus #338206) 115kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3062 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-06T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Edwards to Bolton 115 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3063 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-20T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Commodore - Jordan 345 kV MTEP Project 20465 | 143 | 143 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3064 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-20T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Commodore - Jordan 345 kV MTEP Project 20465 | 157 | 157 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3065 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-03-30T04:00:00+00:00 | METC | Oceana | MI | DPP-2022 | East (ITC) | Study Not Started |  | Donaldson 138 kV Bus | 20 | 20 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3066 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Osceola | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Hersey Transmission Station, 138 kV, Bus #263771 | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3067 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | North Bastrop (Bus #337443) - Beekman (Bus #337441) | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3068 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-04-17T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Helena | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Amite (A) - Gillsburg (B) 115kV TL | 110 | 110 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3069 | Active | 2022-09-02T04:00:00+00:00 |  |  | 2027-12-27T05:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Tap on line Fayetteville 138kV (endpoint A) to HERZOG 138kV (endpoint B) | 70 | 70 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3070 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-02-27T05:00:00+00:00 | MINNESOTA POWER INC. | Morton | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Square Butte East 230 kV | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3071 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | St. Francis | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Entergy Hughes - Forest City South 161 kV | 140 | 140 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3072 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-27T04:00:00+00:00 |  | 2024-12-30T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Wilkinson | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Woodviille - Centreville 115 kV | 120 | 120 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3073 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-25T04:00:00+00:00 |  | 2026-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | INDEPENDENCE-ISES - POWERLINE ROAD 500 kV | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3074 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Randolph | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Prest-Steeleville | 250 | 250 | Hybrid | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3075 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Merom Primary- Worthington Primary 345kV | 900 | 900 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3076 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-11-30T05:00:00+00:00 | AMEREN ILLINOIS | Wabash | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 08GiBSON (PSI) to 7ALBION 345 kV | 770 | 770 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3077 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-11-30T05:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Gibson | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Francisco 345 kV | 1000 | 1000 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3078 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Peoria | IL | DPP-2022 | Central | Phase 1 |  | Fargo to Sandburg 345kV | 252 | 252 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3079 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | EAST TEXAS ELECTRIC COOPERATIVE, INC. | Jasper | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Jasper-Holly Springs 138 kV line tap | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3080 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-29T04:00:00+00:00 | AMEREN ILLINOIS | Pulaski | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ameren owned Kelso - Joppa (Massac) 345 kV Tie-Line | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3081 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Hot Spring | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Entergy Arkansas Owned Social Hill - De Gray 115 kV Line | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3082 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Franklin | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping the 'Gilbert / 3GILBERT_LA (303322)' to 'Winnsboro / 3WINNSBORO! (337330)' 115kV line. | 135 | 135 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3083 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2022-07-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Pointe Coupee | LA | DPP-2022 | South | Study Not Started |  | MISO Model (J1368 POI) - Bus 43684. This POI is a tap on Fancy Point - Waterloo 230kV Line. NRIS Pro | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3084 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Sullivan | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Merom (HED) - Dresser 345kV | 580.5 | 641.8 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J3085 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | AMEREN MISSOURI | Madison | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Fredericktown 138 kV Substation | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3086 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-11-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Peoria | TX | DPP-2022 | Central | Phase 1 |  | New 345kV switchyard, looping in the Fargo-Sandburg 345kV | 252.96 | 252.96 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3087 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-11-01T04:00:00+00:00 | AMEREN ILLINOIS | Logan | TX | DPP-2022 | Central | Phase 1 |  | Shockey | 204.6 | 204.6 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3088 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-02-01T05:00:00+00:00 | MIDAMERICAN ENERGY CO. | Woodbury | IA | DPP-2022 | West | Phase 1 | Energy Resource Interconnection Service (ERIS) | Raun to Sioux City | 300 | 300 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3089 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2029-04-30T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Webster | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reid EHV | 696 | 696 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J3090 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2025-10-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | West Memphis EHV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3091 | Withdrawn | 2022-09-12T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-01-01T05:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Logan | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | East Bismarck Junction to Wishek Junction | 145 | 145 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3092 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Entergy's SHELBY SS 115 kV | 115 | 115 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3093 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Lakeover EHV - McAdams EHV 500 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3094 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Washington | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Pumpkin Center 230kV | 115 | 115 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3095 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Ford | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4PAXTON - 4GIBSONC_E 138 KV LINE | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3096 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-10-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Henderson | KY | DPP-2022 | Central |  | Network Resource Interconnection Service (NRIS) | Reid 161 kV to Henderson 161 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3097 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-08-29T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Amite | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Entergy Mississippi Gillsburg Tap - Gillsburg on the Amite - Gillsburg115 kV Line | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3098 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Franklin | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | RED GUM - WINNSBORO 115 kV (122.5,122.6,122.7) | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3099 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-27T04:00:00+00:00 |  | 2027-06-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Faulkner | AR | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | Hamlet to Gravel Ridge 161kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J310 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-02-11T05:00:00+00:00 |  | 2017-09-01T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Dodge County,Steele County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | West Owatonna-AL Corn Dist-Byron 161kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3100 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | METC | Roscommon | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Higgins - Mio Dam 138 kV line | 75 | 75 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3101 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-06-13T04:00:00+00:00 |  | 2025-08-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2022 | South | Study Not Started |  | Shaw-Indianola 115kV | 20 | 20 | Solar | Solar/Wind | Not Started |  | 0 | 0 | 0 | 0
MISO | J3102 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-08-30T04:00:00+00:00 | AMEREN MISSOURI | Pemiscot | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Dell to New Madrid 500kV line | 500 | 500 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3103 | Active | 2022-06-22T04:00:00+00:00 |  |  | 2026-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Fountain | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Lafayette - Veedersburg West 230 kV | 145 | 145 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3104 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Hinds | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Tinnin Road 230kV Substation | 85 | 85 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3105 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Amite | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Franklin EHV - McKnight 500 kV | 400 | 400 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3106 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-08-30T04:00:00+00:00 | AMEREN MISSOURI | Pemiscot | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Dell to New Madrid 500 kV line | 500 | 500 | Solar | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3107 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-08-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Johnson | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Enron Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3108 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | COOPERATIVE ENERGY | Jasper | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Missionary 161kV Substation | 180 | 180 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3109 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping the 'Carlisle / 3CARISLE! (338003)' to 'Screeton / 3SCREETON (338005)' 115kV line | 120 | 120 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3110 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Powerline Road / 8POWERLN_RD% (338156) 500kV Substation | 400 | 400 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3111 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC TRUMANN WEST - POWERLINE ROAD 161kv | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3112 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Barton - West Helena 115kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3113 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2022-12-06T05:00:00+00:00 |  | 2026-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Greene | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Edwardsport IGCC - Amo 345kV | 300 | 300 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3114 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | HOOSIER ENERGY | Greene | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Taping 'Sandborn Primary / 07SAND61 (248465)' to 'Worthington Primary / 07WORTH (248784)' 161kV line | 300 | 300 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3115 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | COOPERATIVE ENERGY | Sharkey | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping the 'Onward / 3ONWARD+ (336967)' to 'Rolling Fork / 3ROLING FRK! (336968)' 115kV line | 216 | 216 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3116 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping 'AECC Aubrey / 6AUBREY# (338885)' to 'Ritchie SES Switchyard / 6RITCHIE-2! (337991)' 230kV Li | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3117 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping the 'Texas Eastern Station 8 / ST.E.P/ S-8 (338229)' to 'McDougal / 5MCDOUGAL# (338695)' 161k | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3118 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping the 'Galion / 3GALION (337444)' to 'Oak Grove / 3OAK_GROVE! (337445)' 115kV line | 160 | 160 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3119 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2022-12-06T05:00:00+00:00 |  | 2026-06-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Pulaski | IN | DPP-2022 | Central | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping 'Reynolds / 17REYNOLDS (255205)' to 'Burr Oak / 17BURR_OAK (255101)' 22.4mi from Reynolds 345 | 350 | 350 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3120 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Taping 'Newport AB / NEWPORTSOLAR (338177)' to 'Cash / 5CASH (338171)' 161kV Line. | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3121 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2027-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Wayne | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Centerville 69 kV Substation | 50 | 50 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3122 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-04-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Bob White 161 kV SS (J1007 POI) | 200 | 200 | Hybrid | Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3123 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Orange | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Chisholm RD- Hartburg 230kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3124 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-08-31T04:00:00+00:00 | METC | Saginaw | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Murphy 345 kV Substation | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3125 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Watonwan | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Crandall 345 kV Substation | 289 | 289 | Hybrid | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3126 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Washington | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Stringtown-Greenville/North 115kV Transmission Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3127 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Brinkley East - Clarendon 115 kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3128 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Feliciana | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Starhill Substation 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3129 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Feliciana | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Starhill 138 kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3130 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Marion | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Kinmundy to Salem 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3131 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado EHV - Sarepta 345/115KV SW STA 345 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3132 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | El Dorado EHV - Sarepta 345/115KV SW STA 345 kV | 150 | 150 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3133 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-08-31T04:00:00+00:00 | MICHIGAN PUBLIC POWER AGENCY | Saginaw | MI | DPP-2022 | East (ITC) |  | Network Resource Interconnection Service (NRIS) | Murphy to Nelson Road 345 kV | 120 | 120 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3134 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Otsego | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gaylord Transmission Station, 138 kV, Bus #263662 | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3135 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-07-31T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Commodore-Aster-4513 | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3136 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | HOOSIER ENERGY | Daviess | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hoosier's Sandborn - Grain Processing Center 161kV (GPC Primary - Sandborn Primary) | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3137 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-05-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pocahontas | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Sac - Pocahontas 161 kV | 156.3 | 156.3 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3138 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-30T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Rapides 230kV Substation | 49.3 | 49.3 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3139 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Pickens 230 kV Substation | 225 | 225 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3140 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-08-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Porter | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | South Valparaiso 138 kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3141 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2022 | South | Study Not Started |  | Ritchie Plant Substation 230kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3142 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Johnson | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Circuit ID# 6950 - Columbus North (08COLNRT) - Franklin Forsythe St (08FRSYTH) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3143 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Jackson Township (08JCKSN_TWNS) - Heritage Lake (08HERITL) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3144 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Amo - Wheatland 69kV Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3145 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Amo - Wheatland Line | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3146 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Amo - Wheatland Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3147 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Johnson | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Trafalgar Switchyard (08TRFLGJ) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3148 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Greene | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Drager to Grand Junction | 131 | 131 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3149 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Mills | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Hastings to Bunge | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3150 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Panola | MS | DPP-2022 | Central | Study Not Started | Network Resource Interconnection Service (NRIS) | Crenshaw to Como | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3151 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Sheboygan | WI | DPP-2022 | East (ATC) | Study Not Started |  | Sheboygan Falls | 110 | 150 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3152 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Iowa | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Spring Green 138 kV | 160 | 160 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3153 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | ITC MIDWEST | Clinton | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Beaver Channel 161 kV Substation | 160 | 160 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3154 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Franklin | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Blackhawk (MEC) - Quinn 345 (shared POI with J2892) | 160 | 160 | Gas | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3155 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Winnebago | WI | DPP-2022 | East (ATC) | Study Not Started |  | Neevin | 110 | 150 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3156 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Rock | WI | DPP-2022 | East (ATC) | Study Not Started |  | Townline Road | 60 | 100 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J3157 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-12-31T05:00:00+00:00 | ITC MIDWEST | Winnebago | IA | DPP-2022 | West | Phase 1 |  | Bison | 198.8 | 198.8 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3158 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Colby 345 kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3159 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | ITC MIDWEST | Dubuque | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Gardner 69 kV substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3160 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Fond du Lac | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | South Fond du Lac 345 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3161 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Sheboygan | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Huebner 138 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3162 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Rock | WI | DPP-2022 | East (ATC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Beloit Gateway 138 kV substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3163 | Active | 2022-07-26T04:00:00+00:00 |  |  | 2028-03-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass | ND | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | BISON | 473 | 479 | Hybrid | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3164 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Ouachita | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | McClellan 138 kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3165 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-08-31T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Breckinridge | KY | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | New Hardinsburg 161 kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3166 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Edwardsport Station IGCC 345kV Substation | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3167 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Fulton | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Ipava 138 kV Substation | 220 | 220 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3168 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Reynolds 345 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3169 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Cypress 138 kV Substation | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3170 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | CLECO POWER LLC | Avoyelles | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Eola-Marksville 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3171 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Drew | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Monticello East-Reed SS 115 kV | 300 | 300 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3172 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | GREAT RIVER ENERGY | Dakota | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | GRE-NININGR7 115 kV | 100 | 100 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3173 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Swifton to Hoxie 161 kV | 220 | 220 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3174 | Active | 2022-09-09T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | PRAIRIE POWER, INC. | Scott | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Jacksonville Industrial Pk-Winchester Switching Station 138 kV | 180 | 180 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3175 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Robinsonville 230kV | 160 | 160 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3176 | Withdrawn | 2022-11-05T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Plaquemines | LA | DPP-2022 | South | Study Not Started |  | Derrick | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3177 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Robinsonville 230kV Substation | 80 | 80 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3178 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | CLECO POWER LLC | De Soto | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Dolet Hills | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3179 | Withdrawn | 2022-11-05T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-10-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Plaquemines | LA | DPP-2022 | South | Study Not Started |  | Derrick | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3180 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | CLECO POWER LLC | De Soto | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Dolet Hills | 110 | 110 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3181 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-01-01T05:00:00+00:00 | AMEREN ILLINOIS | Logan | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Fogarty 138 kV Substation | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3182 | Withdrawn | 2022-09-11T04:00:00+00:00 | 2023-02-16T05:00:00+00:00 |  | 2027-06-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Mercer | ND | DPP-2022 | West | Study Not Started | Network Resource Interconnection Service (NRIS) | Coyote | 200 | 200 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3183 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Grant | SD | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Big Stone South 230KV Substation | 125 | 125 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3184 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | South Belleville (4S BELLVLLE 348811) 138 kV | 145 | 145 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3185 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-02-01T05:00:00+00:00 | AMEREN ILLINOIS | Effingham | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Effingham - Newton 138KV (4EFFINGHM 347025 -4NEWTON 347831) | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3186 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-01-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Rosedale - Delta 115 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3187 | Active | 2022-08-31T04:00:00+00:00 |  |  | 2024-12-31T05:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Havana 138 kV Sub | 37 | 37 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3188 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2023-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Marshall | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Hallock 138 kV | 35 | 35 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3189 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2023-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | St. Johns 138 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3190 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2023-09-30T04:00:00+00:00 | AMEREN MISSOURI | Audrain | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Pike 161 kV Substation | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3191 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | AECC BALCH-FISHER 161kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3192 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Mallory 161 kV Substation | 500 | 500 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3193 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Hot Spring | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | POYEN-GIFFORD 115 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3194 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-02-27T05:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | ENTERGY TEXAS, INC. | Hardin | TX | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | RYE CO-CYPRESS 138 kV | 198 | 198 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3195 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-02-27T05:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | White Bluff EHV - Wrightsville 115 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3196 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-02-27T05:00:00+00:00 |  | 2025-10-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Starke | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Burr Oak to East Winamac 138 kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3197 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-12-22T05:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | EAST LEESVILLE -RODEMACHER 230 | 250 | 250 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3198 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-12-22T05:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Barron | WI | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Barron 161KV | 80 | 80 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3199 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-12-22T05:00:00+00:00 | AMEREN ILLINOIS | Adair | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Zachary 345kV | 300 | 300 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3200 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2025-03-01T05:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Turkey Hill 345kV | 250 | 250 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3201 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | COOPERATIVE ENERGY | Walthall | MS | DPP-2022 | South |  | Network Resource Interconnection Service (NRIS) | Tylertown-Bogalusa 115 kV | 148 | 148 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3202 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | AMEREN MISSOURI | Iron | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Clark-Pilot Knob-1 | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3203 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-07-20T04:00:00+00:00 | METC | Clinton | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Bingham - Lookng GL J 138kV | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3204 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Clark | WI | DPP-2022 | East (ATC) | Phase 1 | Network Resource Interconnection Service (NRIS) | Gardner Park - Stone Lake 345kV Line | 208 | 208 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3205 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Franklin | MS | DPP-2022 | South |  | Network Resource Interconnection Service (NRIS) | Arlington to Smithdale 115 kV | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3206 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Killdeer 345 kV Substation | 194 | 194 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3207 | Active | 2022-03-10T05:00:00+00:00 |  |  | 2024-05-06T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Starke | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Stillwell - Plymouth 138 kV | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3208 | Active | 2022-09-08T04:00:00+00:00 |  |  | 2023-09-22T04:00:00+00:00 | HOOSIER ENERGY | Dubois | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | HUNTINBURG-ST ANTHONY 69kV (New substation Patoka 69kV) | 10 | 10 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3209 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-03-01T05:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Hineston 230kV Substation | 467 | 467 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3210 | Active | 2022-09-13T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | CLECO POWER LLC | St. Tammany | LA | DPP-2022 | South | Study Not Started |  | J2245 Substation | 100 | 100 | Solar | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3211 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Washington | LA | DPP-2022 | South | Study Not Started |  | J1564 Substation | 100 | 100 | Solar | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3212 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-09-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Mills | IA | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | 69 kV Glenwood 8 bus 635075 | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3213 | Active | 2022-09-01T04:00:00+00:00 |  |  | 2026-12-31T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Hennepin | MN | DPP-2022 | West | Phase 1 |  | Riverside 115kV Substation | 51 | 51 | Gas | Combined-Cycle – Steam Plant | Not Started |  | 0 | 0 | 0 | 0
MISO | J3214 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | ITC MIDWEST | Lee | IA | DPP-2022 | West | Phase 1 | External Network Resource Interconnection Service (E-NRIS) | WEVER / POI J1471 | 185 | 185 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3215 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2025-07-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Stillwell to Babcock 345kV Transmission Line | 500 | 594 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J3216 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Peoria | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Bloomington Brokaw 138 kV | 300 | 300 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3217 | Withdrawn | 2022-09-14T04:00:00+00:00 | 2023-03-24T04:00:00+00:00 |  | 2026-01-01T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Jackson | MN | DPP-2022 | West | Phase 1 | Network Resource Interconnection Service (NRIS) | Crandall 345kV Substation | 60 | 60 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3218 | Active | 2022-09-12T04:00:00+00:00 |  |  | 2025-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Nevada | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Prescott (#337507) to Emmett (#337505) | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3219 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2023-04-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota | MN | DPP-2022 | West | Phase 1 |  | Cannon Falls 69 kV | 4 | 4 | Hydro | Hydroelectric | Not Started |  | 0 | 0 | 0 | 0
MISO | J3220 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | METC | Ionia | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Peddler | 200 | 200 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J3221 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2024-11-30T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2022 | South | Study Not Started | Energy Resource Interconnection Service (ERIS) | LA_ORD_115 | 49 | 49 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3222 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Moultrie | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Arland to Faraday 345 kV Line Tap | 109 | 109 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J3223 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | AMEREN ILLINOIS | Edwards | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | Olney (4JASPER 347868) - Albion (4ALBION N 346510) 138 kV | 88 | 88 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3224 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Marion | IL | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4KINMUNDY-4TANNER 138kv | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3225 | Withdrawn | 2022-09-15T04:00:00+00:00 | 2022-12-05T05:00:00+00:00 |  | 2026-08-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | BABCOCK-STILLWELL 345 kV | 150 | 150 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3226 | Active | 2022-09-15T04:00:00+00:00 |  |  | 2026-08-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Marshall | IN | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | BURR OAK-PLYMOUTH 138 kV | 130 | 130 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3227 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-12-31T05:00:00+00:00 | METC | Ogemaw | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Gallagher to Livingston 345 kV Segment on the Livingston â€“ Tittabawassee 345 kV Line | 80 | 80 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3228 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-09-15T04:00:00+00:00 | METC | Midland | MI | DPP-2022 | East (ITC) | Study Not Started | Network Resource Interconnection Service (NRIS) | Redstone-Tittabawassee 138 kV Line | 26 | 26 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J3229 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2026-04-24T04:00:00+00:00 | AMEREN MISSOURI | Maries | MO | DPP-2022 | Central | Phase 1 | Network Resource Interconnection Service (NRIS) | 4DILLON-4LKSIDE TP2 138 KV | 140 | 140 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3230 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2025-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Crittenden | AR | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Parkin - Gilmore - Wilson 161 kV (POI is on segment between Parkin and Gilmore) | 200 | 200 | Hybrid | Wind/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3231 | Active | 2022-09-14T04:00:00+00:00 |  |  | 2024-11-29T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Amite | MS | DPP-2022 | South | Study Not Started | Network Resource Interconnection Service (NRIS) | Gloster - Liberty 115 kV | 100 | 100 | Hybrid | Solar/Battery | Not Started |  | 0 | 0 | 0 | 0
MISO | J3232 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2028-10-31T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2023 | Central |  |  | CAYUGA STATION | 475.5 | 500 | Gas | Combined Cycle |  |  | 0 | 0 | 0 | 0
MISO | J3233 | Active | 2024-03-28T04:00:00+00:00 |  |  | 2028-01-15T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Yellow Medicine | MN | DPP-2023 | West |  |  | Canby 115 kV Substation | 140 | 140 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3234 | Active | 2024-03-28T04:00:00+00:00 |  |  | 2028-01-15T05:00:00+00:00 | GREAT RIVER ENERGY | Carver | MN | DPP-2023 | West |  |  | ST BONIFACIUS | 130 | 130 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3235 | Active | 2024-03-28T04:00:00+00:00 |  |  | 2028-01-15T05:00:00+00:00 | GREAT RIVER ENERGY | Benton | MN | DPP-2023 | West |  |  | BENTON COUNTY | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3236 | Active | 2024-03-28T04:00:00+00:00 |  |  | 2028-01-15T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chisago | MN | DPP-2023 | West |  |  | Chisago County 115kV Substation | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3237 | Active | 2024-04-09T04:00:00+00:00 |  |  | 2028-06-09T04:00:00+00:00 | MINNESOTA POWER INC. | Itasca | MN | DPP-2023 | West |  |  | National Tac Plant 115kV (Customer-owned) | 86 | 86 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3238 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | CLECO POWER LLC | Evangeline | LA | DPP-2023 | South |  |  | Cocodrie - Ville Platte 230.0kV | 155 | 155 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3239 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Christian | IL | DPP-2023 | Central |  |  | Pana 138kV | 175 | 175 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3240 | Active | 2024-04-14T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Fulton | IL | DPP-2023 | Central |  |  | Other_ | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3241 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | COOPERATIVE ENERGY | Lincoln | MS | DPP-2023 | South |  |  | ARLINGTON GOAB | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3242 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Tazewell | IL | DPP-2023 | Central |  |  | Flint 138 kv | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3243 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Parke | IN | DPP-2023 | Central |  |  | Parke County REMC | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3244 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Parke | IN | DPP-2023 | Central |  |  | Parke County REMC | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3245 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Breckinridge | KY | DPP-2023 | Central |  |  | Meade County - New Hardinsburg 161.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3246 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2028-01-15T05:00:00+00:00 | PRAIRIE POWER, INC. | Sangamon | IL | DPP-2023 | Central |  |  | Fancy Creek 138kV Substation | 120 | 120 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3247 | Active | 2024-04-14T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2023 | Central |  |  | SPELTERVILLE | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3248 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | CEDAR FALLS MUNICIPAL ELECTRIC UTILITY | Posey | IN | DPP-2023 | West |  |  | Savitran 138/34.5kV (facilities above 100kV) | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3249 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | CEDAR FALLS MUNICIPAL ELECTRIC UTILITY | Vanderburgh | IN | DPP-2023 | West |  |  | Elliott 138/69kV (facilities above 100kV) | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3250 | Active | 2024-04-14T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Cerro Gordo | IA | DPP-2023 | West |  |  | FLOYD - EMERY (ITCM) 161.0kV | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3251 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | METC | Genesee | MI | DPP-2023 | East (ITC) |  |  | THETFORD | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3252 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2023 | East (ITC) |  |  | FITZ | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3253 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Woodruff | AR | DPP-2023 | South |  |  | Bailey | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3254 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2026-12-30T05:00:00+00:00 | AMEREN MISSOURI | Pulaski | IL | DPP-2023 | Central |  |  | 5CAPE GIR3 - 5JOPPA SR 161.0kV | 175 | 175 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3255 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - MCADAMS EHV 230.0kV | 350 | 350 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3256 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Clark | IL | DPP-2023 | Central |  |  | 4GALLATIN - 4KANSAS 138.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3257 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2023 | Central |  |  | EAST WINAMAC - MONTICELLO 138.0kV | 320 | 320 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3258 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-06T04:00:00+00:00 | METC | Ottawa | MI | DPP-2023 | East (ITC) |  |  | TYLER | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3259 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-06T04:00:00+00:00 | GREAT RIVER ENERGY | Renville | MN | DPP-2023 | West |  |  | Cedar Mountain | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3260 | Active | 2024-03-28T04:00:00+00:00 |  |  | 2028-01-15T05:00:00+00:00 | AMEREN ILLINOIS | LaSalle | IL | DPP-2023 | Central |  |  | 4NLASALLE RB - 4WED_FOXR 138.0kV | 97 | 97 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3261 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Tunica | MS | DPP-2023 | South |  |  | Tunica 230 kV (337160) | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3262 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson | TX | DPP-2023 | South |  |  | Stowell | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3263 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Desha | AK | DPP-2023 | South |  |  | Dumas North | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3264 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Otsego | MI | DPP-2023 | South |  |  | LIVINGSTON CO | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3265 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2028-08-17T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Brookings | SD | DPP-2023 | West |  |  | BROOKINGS COUNTY | 175 | 175 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3266 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2028-08-17T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Sargent | ND | DPP-2023 | West |  |  | Forman 230 kV Substation | 175 | 175 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3267 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | METC | Genesee | MI | DPP-2023 | East (ITC) |  |  | THETFORD | 50 | 50 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3268 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-10T04:00:00+00:00 | METC | Gratiot | MI | DPP-2023 | East (ITC) |  |  | REGAL | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3269 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-11-02T04:00:00+00:00 | AMEREN ILLINOIS | Hamilton | IL | DPP-2023 | Central |  |  | 7W_FRFT_E - 7NORRIS 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3270 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-04T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2023 | South |  |  | AECC AUBREY - RITCHIE SWYD 230.0kV | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3271 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-04T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Mississippi | AR | DPP-2023 | South |  |  | AECC Dell 161kV - Nucor-Yamato 161kV Switching Station 161.0kV | 230 | 230 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3272 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2028-04-09T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Concordia | LA | DPP-2023 | South |  |  | VIDALIA | 85 | 85 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3273 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Madison | LA | DPP-2023 | South |  |  | BAXTER WILSON SES SWYD - PERRYVILLE 500 SWYD 500.0kV | 473.8 | 473.8 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3274 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | METC | Ogemaw | MI | DPP-2023 | East (ITC) |  |  | GALLAGHER - TWINING 138.0kV | 290 | 290 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3275 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-04T04:00:00+00:00 | MINNESOTA POWER INC. | Benton | MN | DPP-2023 | West |  |  | Mud Lake - Benton County (GRE) 230kV | 249 | 249 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3276 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Pulaski | IL | DPP-2023 | Central |  |  | Mound City | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3277 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-17T04:00:00+00:00 | METC | Bay | MI | DPP-2023 | East (ITC) |  |  | Other_ | 175 | 175 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3278 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | GREAT RIVER ENERGY | Swift | MN | DPP-2023 | West |  |  | SWENODA TAP - DUBLIN TAP - SS360 - 360WSM1 115.0kV | 90 | 90 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3279 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-04T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Day | SD | DPP-2023 | West |  |  | Ellendale 345 - Twin Brooks 345.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3280 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Dickey | ND | DPP-2023 | West |  |  | Ellendale 345 | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3281 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-09-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marquette | MI | DPP-2023 | East (ATC) |  |  | Presque Isle - Perch Lake 138.0kV | 170 | 170 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3282 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | METC | Mason | MI | DPP-2023 | East (ITC) |  |  | KEYSTONE - LUDINGTON 345.0kV | 297 | 297 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3283 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | METC | Grand Traverse | MI | DPP-2023 | East (ITC) |  |  | KEYSTONE - WEXFORD 138.0kV | 135 | 135 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3284 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Woodford | IL | DPP-2023 | Central |  |  | Spring Bay | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3285 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2023 | Central |  |  | TH Pfizer Jct. - Worthington (HED) | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3286 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2023 | East (ITC) |  |  | KILGORE - MICAH 120.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3287 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Osceola | MI | DPP-2023 | East (ITC) |  |  | Hersey - Baldwin 138.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3288 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Carroll | IN | DPP-2023 | Central |  |  | Kokomo Webster St. - Walton 230.0kV | 125 | 125 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3289 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | GREAT RIVER ENERGY | Sherburne | MN | DPP-2023 | West |  |  | ELK RIVER 14 | 0 | 35 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3290 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2023 | Central |  |  | MAGNETATION | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3291 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaGrange | IN | DPP-2023 | Central |  |  | HIPLE | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3292 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2023 | South |  |  | RITCHIE SWYD - TARLETON 230.0kV | 193 | 193 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3293 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2023 | Central |  |  | Edwardsport IGCC - Amo 345.0kV | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3294 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | HOOSIER ENERGY | Daviess | IN | DPP-2023 | Central |  |  | GPC Primary - Sandborn Primary 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3295 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2023 | South |  |  | Cole - Penton Road 230.0kV | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3296 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | AMEREN ILLINOIS | Hamilton | IL | DPP-2023 | Central |  |  | Hamilton | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3297 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | AMEREN ILLINOIS | St. Clair | IL | DPP-2023 | Central |  |  | Herzog | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3298 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2023 | Central |  |  | Towerline | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3299 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson | TX | DPP-2023 | South |  |  | BEVIL | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3300 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2023 | South |  |  | CASH - NEWPORT AB 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3301 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Prairie | AR | DPP-2023 | South |  |  | DES ARC - COTTON PLANT 115.0kV | 180 | 180 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3302 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2023 | South |  |  | P.B. SOUTH - VARNER 115.0kV | 105 | 105 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3303 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Prairie | AR | DPP-2023 | South |  |  | WEST MEMPHIS EHV - KEO EHV 500.0kV | 400 | 400 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3304 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clark | AR | DPP-2023 | South |  |  | ETTA - MCNEIL EHV 500.0kV | 350 | 350 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3305 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | MIDAMERICAN ENERGY CO. | Adams | IA | DPP-2023 | West |  |  | Other_ | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3306 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Perry | IL | DPP-2023 | Central |  |  | 7JORD - 7CMDR 345.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3307 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-11-02T04:00:00+00:00 | AMEREN MISSOURI | Callaway | MO | DPP-2023 | Central |  |  | Callaway | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3308 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Woodruff | AR | DPP-2023 | South |  |  | MOSES SWYD - AECC HUNTER NORTH 161.0kV | 180 | 180 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3309 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Copiah | MS | DPP-2023 | South |  |  | FRANKLIN EHV - RAY BRASWELL EHV 500.0kV | 200 | 200 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3310 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Lincoln | MS | DPP-2023 | South |  |  | BROOKHAVEN | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3311 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-10T04:00:00+00:00 | ITC MIDWEST | St. Landry | LA | DPP-2023 | West |  |  | WELLS | 400 | 400 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3312 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Washington | MN | DPP-2023 | West |  |  | RAPTOR | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3313 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | METC | Lenawee | MI | DPP-2023 | East (ITC) |  |  | MOROCCO - ALLEN JUNCTION 345.0kV | 263 | 263 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3314 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Clayton | IA | DPP-2023 | West |  |  | Postville | 200 | 200 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3315 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Pike | MS | DPP-2023 | South |  |  | COLONIAL PIPELINE - FERNWOOD 115.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3316 | Active | 2024-05-06T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Washington | IL | DPP-2023 | Central |  |  | Okawville 138kV. | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3317 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2023 | Central |  |  | Terre Haute Pfizer | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3318 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | HOOSIER ENERGY | Sullivan | IN | DPP-2023 | Central |  |  | Merom 345 kV Substation | 300 | 300 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3319 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Webster | LA | DPP-2023 | South |  | Energy Resource Interconnection Service (ERIS) | SAREPTA 345/115 SS | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3320 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | METC | Ottawa | MI | DPP-2023 | East (ITC) |  |  | ROOSEVELT | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3321 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Wayne | IL | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3322 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2023 | South |  |  | NELSON 500 SWYD - RICHARD 500.0kV | 325 | 325 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3323 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Knox | IL | DPP-2023 | West |  |  | Other_ | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3324 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2029-09-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Palo Alto | IA | DPP-2023 | West |  |  | PALO ALTO - KOSSUTH COUNTY 345.0kV | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3325 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Cherokee | IA | DPP-2023 | West |  |  | LITTLE SIOUX - LEMARS TAP 161.0kV | 140 | 140 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3326 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | Lyon | MN | DPP-2023 | West |  |  | Lyon County - Brookings County 345.0kV | 250 | 250 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3327 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-05-01T04:00:00+00:00 | CEDAR FALLS MUNICIPAL ELECTRIC UTILITY | Pike | IN | DPP-2023 | West |  |  | Cato 138/69kV (facilities above 100kV) | 130 | 130 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3328 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2023 | Central |  |  | Hoopeston West | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3329 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Sullivan | IN | DPP-2023 | Central |  |  | Merom (HED) - Dresser 345.0kV | 145 | 145 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3330 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Kenosha | WI | DPP-2023 | East (ATC) |  |  | Pleasant Prairie - Arcadian 345.0kV | 705 | 705 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3331 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Sullivan | IN | DPP-2023 | Central |  |  | Petersburg - Sullivan (AEP/PJM) 345.0kV | 470 | 470 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3332 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Calumet | WI | DPP-2023 | East (ATC) |  |  | Forest Junction - Cypress 345.0kV | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3333 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | ITC | Washtenaw | MI | DPP-2023 | East (ITC) |  |  | MAJESTIC - MILAN 345.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3334 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | LaPorte | IN | DPP-2023 | Central |  |  | MAPLE | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3335 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-01T04:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2023 | Central |  |  | Other_ | 222 | 222 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3336 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | ITC | Tuscola | MI | DPP-2023 | East (ITC) |  |  | RINGLE | 41.8 | 41.8 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3337 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | AMEREN MISSOURI | Stoddard | MO | DPP-2023 | Central |  |  | 5STODDARD - 5MORLEY (AECI) 161.0kV | 230 | 230 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3338 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-28T04:00:00+00:00 | AMEREN ILLINOIS | Hamilton | IL | DPP-2023 | Central |  |  | 7W_FRFT_E - 7NORRIS 345.0kV | 199.99 | 199.99 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3339 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2029-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Hendricks | IN | DPP-2023 | Central |  |  | AMO | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3340 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2023 | Central |  |  | Rossville 138kV on the Hoopeston to Vermillion 138kV Line | 175 | 175 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3341 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2023 | Central |  |  | 7BUNSONVILLE - 7SIDNEY 345.0kV | 100 | 100 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3342 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2023 | Central |  |  | 7BUNSONVILLE - 7SIDNEY 345.0kV | 180 | 180 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3343 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Knox | IL | DPP-2023 | Central |  |  | 4MONM BLVD W - 4CASTRO_JCT 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3344 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Knox | IL | DPP-2023 | Central |  |  | 7FARGO - 7SANDBURG 345.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3345 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Moultrie | IL | DPP-2023 | Central |  |  | Faraday | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3346 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | Lyon | MN | DPP-2023 | West |  |  | Lyon County - Brookings County 345.0kV | 250 | 250 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3347 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Hancock | IN | DPP-2023 | Central |  |  | Greenfield Hastings Park - Greensboro 138.0kV | 140 | 140 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3348 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Marshall | IN | DPP-2023 | Central |  |  | PLYMOUTH - KOSCIUSKO & LEESBURG & KOSCIUSKO CO REMC - NORTHWEST 138.0kV | 110 | 110 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3349 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Fulton | IL | DPP-2023 | Central |  |  | Ipava | 400 | 400 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3350 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | AMEREN MISSOURI | Randolph | MO | DPP-2023 | Central |  |  | 5MOBERLY - 5OVERTON 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3351 | Active | 2024-04-04T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Putnam | IL | DPP-2023 | Central |  |  | Hickok | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3352 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | AMEREN MISSOURI | Cape Girardeau | MO | DPP-2023 | Central |  |  | LUTESVILLE | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3353 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Champaign | IL | DPP-2023 | Central |  |  | Rising | 191.3 | 191.3 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3354 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clinton | IN | DPP-2023 | Central |  |  | Hanover | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3355 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2027-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Fulton | IL | DPP-2023 | Central |  |  | 4IPAVA 3 - 4HAVANA2 138.0kV | 100.6 | 100.6 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3356 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | HOOSIER ENERGY | Pike | IN | DPP-2023 | Central |  |  | RATTS - ALGIERS 69.0kV | 65 | 65 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3357 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-12-31T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Kosciusko | IN | DPP-2023 | Central |  |  | LEESBURG | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3358 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-12-31T05:00:00+00:00 | AMEREN ILLINOIS | De Witt | IL | DPP-2023 | Central |  |  | 4SCLINTON TP - 4CLT_RT54 B1 138.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3359 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-12-31T05:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2023 | Central |  |  | 4TAZEWELL - 4EASTERN 138.0kV | 80 | 80 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3360 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-01-01T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Morgan | IL | DPP-2023 | Central |  |  | Meredosia | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3361 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2027-12-03T05:00:00+00:00 | METC | Bay | MI | DPP-2023 | East (ITC) |  |  | Other_ | 254 | 254 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3362 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ITC | Oakland | MI | DPP-2023 | East (ITC) |  |  | BLACKFOOT - MADRID 345.0kV | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3363 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tensas | LA | DPP-2023 | South |  |  | BAXTER WILSON SES SWYD - PERRYVILLE 500 SWYD 500.0kV | 400 | 400 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3364 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Martin | LA | DPP-2023 | South |  |  | ST MARTINVILLE (L-625A) TAP - CADE SS 69.0kV | 50 | 50 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3365 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Tangipahoa | LA | DPP-2023 | South |  |  | Amite substation | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3366 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - TILLATOBA 230.0kV | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3367 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | CLECO POWER LLC | Avoyelles | LA | DPP-2023 | South |  |  | Marksville - Yellow Bayou 138.0kV | 88 | 88 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3368 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-30T04:00:00+00:00 | CLECO POWER LLC | St. Landry | LA | DPP-2023 | South |  |  | West Fork | 199.9 | 199.9 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3369 | Active | 2024-03-28T04:00:00+00:00 |  |  | 2028-01-15T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Scott | MN | DPP-2023 | West |  |  | BLUE LAKE | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3370 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Kittson | MN | DPP-2023 | West |  |  | Other_ | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3371 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3372 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Macoupin | IL | DPP-2023 | Central |  |  | Rezzy | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3373 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2023 | South |  |  | HARRISBURG SS - HARRISBURG 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3374 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2023 | South |  |  | RITCHIE SWYD - TARLETON 230.0kV | 65 | 65 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3375 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Washington | MS | DPP-2023 | South |  |  | Gerald Andrus 230 kV Substation | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3376 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Mississippi | AR | DPP-2023 | South |  |  | Blytheville North | 130 | 130 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3377 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Madison | LA | DPP-2023 | South |  |  | DELHI - TALLULAH 115.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3378 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jackson | LA | DPP-2023 | South |  |  | DANVILLE [LA] | 140 | 140 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3379 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-02-18T05:00:00+00:00 | AMEREN ILLINOIS | Johnson | IL | DPP-2023 | Central |  |  | 7JORD - 7MASS 345.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3380 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cleveland | AR | DPP-2023 | South |  |  | AECC PINEBERGEN - AECC GLENDALE 115.0kV | 155 | 155 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3381 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | St. Francis | AR | DPP-2023 | South |  |  | FORREST CITY SOUTH - HUGHES 161.0kV | 150.92 | 150.92 | Solar | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3382 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Piatt | IL | DPP-2023 | Central |  |  | 4WEEDMAN - 4MAHOMET 1 138.0kV | 171 | 171 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3383 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Boone | IN | DPP-2024 | Central |  |  | Nucor - Whitestown 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3384 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-10-31T04:00:00+00:00 | GREAT RIVER ENERGY | Stevens | MN | DPP-2023 | West |  |  | Ownership Change (OTP MORRIS) - JOHNSON JUNCTION 115.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3385 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | PRAIRIE POWER, INC. | Pike | IL | DPP-2023 | Central |  |  | Pittsfield Trans. - Liberty 138.0kV | 50 | 50 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3386 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2023 | South |  |  | SHERIDAN EHV - EL DORADO EHV 500.0kV | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3387 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry | IN | DPP-2023 | Central |  |  | Greensboro - New Castle 138 138.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3388 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2023 | South |  |  | SHERIDAN EHV - EL DORADO EHV 500.0kV | 400 | 400 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3389 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Clay | IL | DPP-2023 | Central |  |  | 4KINMUNDY S - 4TANNER 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3390 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2023 | Central |  |  | Kokomo East - Converse 69.0kV | 37 | 37 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3391 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2027-09-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Coles | IL | DPP-2023 | Central |  |  | 7CASEY - 7KANSAS 345.0kV | 200.3 | 200.3 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3392 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | PRAIRIE POWER, INC. | Scott | IL | DPP-2023 | Central |  |  | Murrayville Jct. W - Roodhouse 69.0kV | 25 | 25 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3393 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | HENDERSON UTILITY COMM DBA HENDERSON MUNICIPAL POWER AND LIGHT | Henderson | KY | DPP-2023 | Central |  |  | HMPL Sub No.4 | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3394 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | CLECO POWER LLC | St. Landry | LA | DPP-2023 | South |  |  | Ville Platte - West Fork 230.0kV | 155.6 | 155.6 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3395 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | PRAIRIE POWER, INC. | Sangamon | IL | DPP-2023 | Central |  |  | Andrew Bkr - Fancy Creek 69.0kV | 30 | 30 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3396 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | PRAIRIE POWER, INC. | Scott | IL | DPP-2023 | Central |  |  | Winchester - Hillview Tap 69.0kV | 30 | 30 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3397 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2026-08-15T04:00:00+00:00 | ITC MIDWEST | Rock | MN | DPP-2023 | West |  |  | Magnolia | 80 | 80 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3398 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | PRAIRIE POWER, INC. | Greene | IL | DPP-2023 | Central |  |  | Walkerville - Eldred 69.0kV | 30 | 30 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3399 | Active | 2024-04-09T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Goodhue | MN | DPP-2023 | West |  |  | Hampton - Prairie Island 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3400 | Active | 2024-03-20T04:00:00+00:00 |  |  | 2028-04-19T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Deuel | SD | DPP-2023 | West |  |  | Astoria 345kV substation | 142.2 | 142.2 | Hybrid | Piston (Engine), Internal Combustion (Diesel) |  |  | 0 | 0 | 0 | 0
MISO | J3401 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-02T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2023 | South |  |  | DELL EHV - SAN SOUCI 500.0kV | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3402 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Juneau | WI | DPP-2023 | West |  |  | Briggs Road (NSP) - North Madison (ATC) 345.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3403 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2030-08-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Macon | MO | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3404 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2030-08-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Macon | MO | DPP-2023 | Central |  |  | Other_ | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3405 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2028-06-09T04:00:00+00:00 | MINNESOTA POWER INC. | St. Louis | MN | DPP-2023 | West |  |  | Shannon - Minntac 230kV | 144 | 144 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3406 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-04-09T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2023 | South |  |  | Nelson - Carlyss (J2154 POI) | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3407 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2028-10-31T04:00:00+00:00 | METC | Manistee | MI | DPP-2023 | East (ITC) |  |  | LINDEMAN - TIPPY 138.0kV | 300 | 300 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3408 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2023 | South |  |  | HARTBURG - AEP LAYFIELD 500.0kV | 450 | 450 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3409 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | ENTERGY TEXAS, INC. | Newton | TX | DPP-2023 | South |  |  | HARTBURG - CYPRESS 500.0kV | 400 | 400 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3410 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | AMEREN ILLINOIS | Washington | IL | DPP-2023 | Central |  |  | 7PR STATE - 7MTVERNW 345.0kV | 120 | 120 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3411 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | AMEREN MISSOURI | Randolph | MO | DPP-2023 | Central |  |  | 5ADAIR - 5THMHIL (AECI) 161.0kV | 120 | 120 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3412 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-12-01T05:00:00+00:00 | AMEREN ILLINOIS | Ford | IL | DPP-2023 | Central |  |  | Other_ | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3413 | Active | 2024-03-29T04:00:00+00:00 |  |  | 2028-07-18T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pulaski | AR | DPP-2023 | South |  |  | L.R. 145TH ST | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3414 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Posey | IN | DPP-2023 | Central |  |  | AB Brown 345 - Gibson (Duke Terminal) 345.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3415 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Mercer | ND | DPP-2023 | West |  |  | Coyote Switchyard | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3416 | Active | 2024-03-21T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | METC | Otsego | MI | DPP-2023 | East (ITC) |  |  | VAN TYLE | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3417 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-06T04:00:00+00:00 | AMEREN ILLINOIS | Macon | IL | DPP-2023 | Central |  |  | Oreana | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3418 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Sangamon | IL | DPP-2023 | Central |  |  | 7AUSTIN - 7TURNER 345.0kV | 220 | 220 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3419 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-12-01T05:00:00+00:00 | ITC | Huron | MI | DPP-2023 | East (ITC) |  |  | SEASIDE | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3420 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | McPherson | SD | DPP-2023 | West |  |  | Ellendale 345 - Twin Brooks 345.0kV | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3421 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ITC | Huron | MI | DPP-2023 | East (ITC) |  |  | SEASIDE | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3422 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lawrence | AR | DPP-2023 | South |  |  | AECC HOXIE SOUTH | 145 | 145 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3423 | Active | 2024-05-16T04:00:00+00:00 |  |  | 2028-09-04T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jackson | AR | DPP-2023 | South |  |  | PECAN ST - AECC BALCH 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3424 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Posey | IN | DPP-2023 | Central |  |  | AB Brown 345 - Gibson (Duke Terminal) 345.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3425 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | EAST TEXAS ELECTRIC COOPERATIVE, INC. | Jasper | TX | DPP-2023 | South |  |  | Peachtree Substation | 59.2 | 59.2 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3426 | Active | 2024-03-19T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Chicot | AR | DPP-2023 | South |  |  | MACON LAKE SS | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3427 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2023 | South |  |  | DELL EHV - NEW MADRID (AECI) 500.0kV | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3428 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | McPherson | SD | DPP-2023 | West |  |  | Other_ | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3429 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pemiscot | MO | DPP-2023 | South |  |  | JIM HILL - HAYTI SOUTH 161.0kV | 160 | 160 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3430 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Lawrence | IL | DPP-2023 | Central |  |  | 4LAWRNCVL - 4JASPER 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3431 | Active | 2024-03-19T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - MCADAMS EHV 230.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3432 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Lawrence | IL | DPP-2023 | Central |  |  | 4LAWRNCVL - 4JASPER 138.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3433 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Barron | WI | DPP-2023 | West |  |  | BARRON - WASHCO 161.0kV | 115 | 115 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3434 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-12-01T05:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | Kandiyohi | MN | DPP-2023 | West |  |  | Willmar | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3435 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2023 | South |  |  | STUTTGART RICUSKEY - WOODWARD 230 SUB 230.0kV | 210 | 210 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3436 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Daviess | MO | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3437 | Active | 2024-05-06T04:00:00+00:00 |  |  | 2027-09-30T04:00:00+00:00 | METC | Ogemaw | MI | DPP-2023 | East (ITC) |  |  | GALLEGHER | 160 | 160 | Hybrid | Solar/Wind/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3438 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | METC | Saginaw | MI | DPP-2023 | East (ITC) |  |  | MURPHY | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3439 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2026-10-31T04:00:00+00:00 | GridUnity | Sherburne | MN | DPP-2023 | West |  |  | RICE LAKE SWITCH ELSM11 - ZIMMERMAN TAP - SS2858 - ELS1 69.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3440 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Daviess | MO | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3441 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Houston | TX | DPP-2023 | South |  |  | ROCKY CREEK - CROCKETT (SWEPCO) 345.0kV | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3442 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN MISSOURI | Scott | MO | DPP-2023 | Central |  |  | 5STODDARD - 5MORLEY (AECI) 161.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3443 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2030-06-01T04:00:00+00:00 | GridUnity | Big Stone | MN | DPP-2023 | West |  |  | Other_ | 250 | 250 | Hybrid | Wind/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3444 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Jefferson | AR | DPP-2023 | South |  |  | AECC PINEBERGEN | 125 | 125 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3445 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | GridUnity | Olmsted | MN | DPP-2023 | West |  |  | Westside | 49.9 | 49.9 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3446 | Active | 2024-04-04T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | METC | Kent | MI | DPP-2023 | East (ITC) |  |  | Gaines substation 138kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3447 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | COOPERATIVE ENERGY | Perry | MS | DPP-2023 | South |  |  | Purvis Bulk 161 - Hintonville 161 161.0kV | 125 | 125 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3448 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Grant | WI | DPP-2023 | West |  |  | NELSON DEWEY (ATC) - GRAN GRAE (ATC) 161.0kV | 180 | 180 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3449 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Pope | AR | DPP-2023 | South |  |  | MORRILTON EAST - ATKINS 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3450 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Panola | MS | DPP-2023 | South |  |  | BATESVILLE [MS] - MOON LAKE SS 230.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3451 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | METC | Alcona | MI | DPP-2023 | East (ITC) |  |  | Other_ | 120 | 120 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3452 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2023 | South |  |  | BAXTER WILSON SES SWYD - PERRYVILLE 500 SWYD 500.0kV | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3453 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - MCADAMS EHV 230.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3454 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2023 | South |  |  | BAXTER WILSON SES SWYD - PERRYVILLE 500 SWYD 500.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3455 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Trinity | TX | DPP-2023 | South |  |  | ONALASKA | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3456 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | AMEREN ILLINOIS | Tazewell | IL | DPP-2023 | Central |  |  | San Jose Rail Switching Station | 100 | 100 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3457 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2027-02-28T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2023 | South |  |  | STUTTGART RICUSKEY - WOODWARD 230 SUB 230.0kV | 225 | 225 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3458 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2023 | South |  |  | TWIST - PARKIN 161.0kV | 170 | 170 | Solar | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3459 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2023 | South |  |  | CASH - NEWPORT AB 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3460 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2023 | East (ITC) |  |  | FITZ | 290 | 290 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3461 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Muscatine | IA | DPP-2023 | West |  |  | SUB 56 - SUB 89 161.0kV | 156 | 156 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3462 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | ITC MIDWEST | Tama | IA | DPP-2023 | West |  |  | Dysart - Traer 161kV | 187 | 187 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3463 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Jefferson | MS | DPP-2023 | South |  |  | LORMAN SS (CE) - FAYETTE 115.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3464 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ITC MIDWEST | Story | IA | DPP-2023 | West |  |  | Fernald | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3465 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2026-06-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Isanti | MN | DPP-2023 | Central |  |  | CAMBRIDGE | 0 | 40 | Diesel | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3466 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Winnebago | WI | DPP-2023 | East (ATC) |  |  | Sunset Point - Ellinwood 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3467 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2023 | Central |  |  | Bloomington Brokaw | 200 | 200 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3468 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Day | SD | DPP-2023 | West |  |  | Ellendale - Twin Brooks 345.0kV | 300 | 300 | Hybrid | Wind/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3469 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2026-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marathon | WI | DPP-2023 | East (ATC) |  |  | Stratford - McMillan 115.0kV | 100 | 100 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3470 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | GridUnity | Tuscola | MI | DPP-2023 | East (ITC) |  |  | Other_ | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3471 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | METC | Branch | MI | DPP-2023 | East (ITC) |  |  | WAGNER - BATAVIA 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3472 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | ITC | Lapeer | MI | DPP-2023 | East (ITC) |  |  | Other_ | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3473 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2023 | East (ITC) |  |  | Other_ | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3474 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | METC | Allegan | MI | DPP-2023 | East (ITC) |  |  | BUCK CREEK - HAZELWOOD 138.0kV | 128 | 128 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3475 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-13T04:00:00+00:00 | PRAIRIE POWER, INC. | Mason | IL | DPP-2023 | Central |  |  | MTEP Facility 24979 | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3476 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | St. Croix | WI | DPP-2023 | West |  |  | Pine Lake Tap - APPLE RIVER (DPC) 161.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3477 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2029-04-06T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Carroll | IA | DPP-2023 | West |  |  | Other_ | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3478 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | GridUnity | Vigo | IN | DPP-2023 | Central |  |  | Other_ | 35 | 35 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3479 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2027-02-28T05:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2023 | South |  |  | Hineston | 225 | 225 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3480 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-05-25T04:00:00+00:00 | METC | Allegan | MI | DPP-2023 | East (ITC) |  |  | SCOTT LAKE | 199.9 | 199.9 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3481 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2027-02-28T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2023 | South |  |  | J1577 Sub | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3482 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2023 | Central |  |  | Other_ | 350 | 350 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3483 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2023 | Central |  |  | 4RANTOUL - 4RISING 138.0kV | 137.4 | 137.4 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3484 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2027-02-28T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Union | AR | DPP-2023 | South |  |  | EL DORADO EHV - SAREPTA 345/115 SS 345.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3485 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ITC | Wayne | MI | DPP-2023 | East (ITC) |  |  | JEFFERSON | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3486 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | GridUnity | Muskegon | MI | DPP-2023 | East (ITC) |  |  | Rogers 138 kV Substation | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3487 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2023 | Central |  |  | CAYUGA 345 | 400 | 400 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3488 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2023 | Central |  |  | CAYUGA 345 | 400 | 400 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3489 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | GridUnity | McDonough | IL | DPP-2023 | Central |  |  | Other_ | 105 | 105 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3490 | Active | 2024-03-21T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Caldwell | KY | DPP-2023 | Central |  |  | Caldwell County | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3491 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Posey | IN | DPP-2023 | Central |  |  | AB Brown 345 - Gibson (Duke Terminal) 345.0kV | 45 | 45 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3492 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Posey | IN | DPP-2023 | Central |  |  | AB Brown 345 - Gibson (Duke Terminal) 345.0kV | 45 | 45 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3493 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | GridUnity | McDonough | IL | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3494 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Greene | IN | DPP-2023 | Central |  |  | TH Pfizer Jct. - Worthington (HED) | 175 | 175 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3495 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | HOOSIER ENERGY | Greene | IN | DPP-2023 | Central |  |  | Merom Primary - Worthington Primary 345.0kV | 220 | 220 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3496 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2027-12-03T05:00:00+00:00 | ITC | Sanilac | MI | DPP-2023 | East (ITC) |  |  | GREENWOOD - RAPSON (BANNER) 345.0kV | 222.08 | 222.08 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3497 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Pulaski | IL | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3498 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Knox | IL | DPP-2023 | Central |  |  | 7FARGO - 7SANDBURG 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3499 | Active | 2024-04-14T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Kosciusko | IN | DPP-2023 | Central |  |  | LEESBURG - DEEDSVILLE (DUKE) 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3500 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Chisago | MN | DPP-2023 | West |  |  | CHISAGO COUNTY | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3501 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | METC | Wexford | MI | DPP-2023 | East (ITC) |  |  | KEYSTONE - TIPPY 138.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3502 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | METC | Van Buren | MI | DPP-2023 | East (ITC) |  |  | ARGENTA - PALISADES 345.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3503 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2030-01-01T05:00:00+00:00 | GridUnity | Newton | IN | DPP-2023 | Central |  |  | Morrison Ditch 345 kV substation (LRTP projects 15 & 16) - BUS #255210 | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3504 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN MISSOURI | Bollinger | MO | DPP-2023 | Central |  |  | 5HERITAGE - 5FREDTN 161.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3505 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN MISSOURI | Bollinger | MO | DPP-2023 | Central |  |  | 5HERITAGE - 5FREDTN 161.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3506 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Pike | IL | DPP-2023 | Central |  |  | Hull 138kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3507 | Active | 2024-04-01T04:00:00+00:00 |  |  | 2027-04-30T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery | IL | DPP-2023 | Central |  |  | Coffeen North 138kV Substation | 17 | 17 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3508 | Active | 2024-04-01T04:00:00+00:00 |  |  | 2027-04-30T04:00:00+00:00 | GridUnity | Fulton | IL | DPP-2023 | Central |  |  | Duck Creek 345kV substation | 16.3 | 16.3 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3509 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | CITY WATER LIGHT & POWER | Sangamon | IL | DPP-2023 | Central |  |  | 343505 Interstate | 380 | 380 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3510 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2023 | South |  |  | FISHER - CHERRY VALLEY 161.0kV | 175 | 175 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3511 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2023 | South |  |  | STUTTGART RICUSKEY - WOODWARD 230 SUB 230.0kV | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3512 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ITC | Bay | MI | DPP-2023 | East (ITC) |  |  | MONITOR | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3513 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Acadia | LA | DPP-2023 | South |  |  | RICHARD - WELLS 500.0kV | 550 | 550 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3514 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Chippewa | MI | DPP-2023 | East (ATC) |  |  | Pine River 69 kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3515 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-05-25T04:00:00+00:00 | CITY WATER LIGHT & POWER | Sangamon | IL | DPP-2023 | Central |  |  | 343505 Interstate | 199.9 | 199.9 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3516 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-05-25T04:00:00+00:00 | AMEREN ILLINOIS | Jackson | IL | DPP-2023 | Central |  |  | Makanda North | 83.4 | 83.4 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3517 | Active | 2024-04-19T04:00:00+00:00 |  |  | 2028-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Williamson | IL | DPP-2024 | Central |  |  | Ordill | 190 | 190 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3518 | Active | 2024-04-19T04:00:00+00:00 |  |  | 2028-10-31T04:00:00+00:00 | AMEREN MISSOURI | Gasconade | MO | DPP-2024 | Central |  |  | BLAND | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3519 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-10-30T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2023 | Central |  |  | Quiver | 199.9 | 199.9 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3520 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2023 | Central |  |  | 4WEEDMAN - 4MAHOMET 1 138.0kV | 215 | 215 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3521 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | AMEREN ILLINOIS | Shelby | IL | DPP-2023 | Central |  |  | 7NEOGA - 7HOLLAND 345.0kV | 350 | 350 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3522 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass | ND | DPP-2023 | West |  |  | Bison | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3523 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Barron | WI | DPP-2023 | West |  |  | BARRON - WASHCO 161.0kV | 115 | 115 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3524 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Watonwan | MN | DPP-2023 | West |  |  | Crandall - Fieldon 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3525 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-06T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Rock Island | IL | DPP-2023 | West |  |  | SUB 47 | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3526 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2027-12-31T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Goodhue | MN | DPP-2023 | West |  |  | NORTH ROCHESTER | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3527 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-03-01T05:00:00+00:00 | ITC MIDWEST | Allamakee | IA | DPP-2023 | West |  |  | Lansing - Postville (DPC) 161kV | 136 | 136 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3528 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2026-12-30T05:00:00+00:00 | AMEREN ILLINOIS | Jasper | IL | DPP-2023 | Central |  |  | 7CASEY - 7NEWTON 345.0kV | 225 | 225 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3529 | Active | 2024-05-20T04:00:00+00:00 |  |  | 2028-05-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Mahnomen | MN | DPP-2023 | West |  |  | Mahnomen - Winger 115.0kV | 80 | 80 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3530 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Saline | AR | DPP-2023 | South |  |  | SHERIDAN EHV - MAGNET COVE 500.0kV | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3531 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | White | AR | DPP-2023 | South |  |  | Other_ | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3532 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Roseau | MN | DPP-2023 | West |  |  | ROSEAU COUNTY | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3533 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | AMEREN MISSOURI | Randolph | MO | DPP-2023 | Central |  |  | 5MOBERLY - SALSBRY5 (KCPL) 161.0kV | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3534 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Madison | LA | DPP-2023 | South |  |  | DELHI - TALLULAH 115.0kV | 125 | 125 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3535 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Dunklin | MO | DPP-2023 | Central |  |  | JIM HILL - HAYTI SOUTH 161.0kV | 200 | 200 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3536 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2023 | South |  |  | TRUMANN | 190 | 190 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3537 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | METC | Kalamazoo | MI | DPP-2023 | East (ITC) |  |  | Weeds Lake 138kV substation (Bus Number 256510) | 265 | 265 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3538 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-03-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Warren | MS | DPP-2023 | South |  |  | Baxter 115/34kV | 730 | 770 | Gas | Combined-Cycle – Steam Plant |  |  | 0 | 0 | 0 | 0
MISO | J3539 | Active | 2024-03-28T04:00:00+00:00 |  |  | 2027-04-01T04:00:00+00:00 | METC | Alcona | MI | DPP-2023 | East (ITC) |  |  | ALPENA - SPRUCE ROAD 138.0kV | 116.9 | 116.9 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3540 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-05-13T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Monroe | AR | DPP-2023 | South |  |  | RITCHIE SWYD - TARLETON 230.0kV | 400 | 400 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3541 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-05-13T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2023 | South |  |  | CLEVELAND/SOUTH | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3542 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Lincoln | MS | DPP-2023 | South |  |  | BROOKHAVEN - BROOKHAVEN/SOUTH 115.0kV | 80 | 80 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3543 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | GREAT RIVER ENERGY | Dakota | MN | DPP-2023 | West |  |  | Chub Lake 115 kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3544 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-30T04:00:00+00:00 | ITC MIDWEST | Tama | IA | DPP-2023 | West |  |  | Abbott | 62 | 62 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3545 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | METC | Ionia | MI | DPP-2023 | East (ITC) |  |  | BINGHAM - MARQUETTE 138.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3546 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lincoln | SD | DPP-2023 | West |  |  | Yankee - Brookings CO. 115.0kV | 120 | 120 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3547 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Martin | MN | DPP-2023 | West |  |  | LAKEFIELD | 0 | 79.8 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3548 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-10-30T04:00:00+00:00 | ITC MIDWEST | Marshall | IA | DPP-2023 | West |  |  | Laurel | 62 | 62 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3549 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2025-06-01T04:00:00+00:00 | GREAT RIVER ENERGY | Mower | MN | DPP-2023 | West |  |  | PLEASANT VALLEY | 485 | 30.5 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3550 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-10T04:00:00+00:00 | CEDAR FALLS MUNICIPAL ELECTRIC UTILITY | Dubois | IN | DPP-2023 | West |  |  | Duff 345/138kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3551 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-10T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Mahaska | IA | DPP-2023 | West |  |  | BEACON | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3552 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-10-31T04:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | McLeod | MN | DPP-2023 | West |  |  | Hutchinson Municipal - GRE Big Swan 115.0kV | 112 | 112 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3553 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2029-03-01T05:00:00+00:00 | MIDAMERICAN ENERGY CO. | Adair | IA | DPP-2023 | West |  |  | Orient Energy Center Substation | 244 | 263 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3554 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-10-30T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Adair | IA | DPP-2023 | West |  |  | SOUTHERN HILLS | 96 | 96 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3555 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-10-30T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Boone | IA | DPP-2023 | West |  |  | BEAVER CREEK | 84 | 84 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3556 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery | IL | DPP-2023 | Central |  |  | 7COFFEEN - 7PANA 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3557 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Morgan | IN | DPP-2023 | Central |  |  | Heartland Crossing Tap - Eagle Valley 138.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3558 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-10T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Champaign | IL | DPP-2023 | Central |  |  | Rising | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3559 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-10T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Hancock | KY | DPP-2023 | Central |  |  | Coleman Switchyard | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3560 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2027-04-30T04:00:00+00:00 | AMEREN ILLINOIS | Putnam | IL | DPP-2023 | Central |  |  | Putnam 138kV Substation | 20 | 20 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3561 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ITC MIDWEST | Jo Daviess | IL | DPP-2023 | West |  |  | Galena (DPC) - Savanna 161kV | 135 | 135 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3562 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Vermilion | IL | DPP-2023 | Central |  |  | 4VERMILION - 4NCHAMPGN W 138.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3563 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Franklin | IL | DPP-2023 | Central |  |  | 7W_FRFT_E - 7MTVERNW 345.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3564 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | GridUnity | Newton | IN | DPP-2023 | Central |  |  | Other_ | 275 | 275 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3565 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Champaign | IL | DPP-2023 | Central |  |  | Rising | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3566 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2023 | Central |  |  | Bloomington Brokaw | 198 | 198 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3567 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-06-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2023 | South |  |  | SHERIDAN EHV - EL DORADO EHV 500.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3568 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-05-13T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Leflore | MS | DPP-2023 | South |  |  | SCHLATER | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3569 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2023 | South |  |  | TRUMANN - HARRISBURG SS 161.0kV | 300 | 300 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3570 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2023 | South |  |  | AECC WYNNE EAST - PARKIN 161.0kV | 300 | 300 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3571 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Poinsett | AR | DPP-2023 | South |  |  | MARKED TREE - TWIST 161.0kV | 250 | 250 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3572 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Catahoula | LA | DPP-2023 | South |  |  | METROPOLIS - RED GUM 115.0kV | 200 | 200 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3573 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2023 | South |  |  | GALION - OAK GROVE 115 SUB 115.0kV | 200 | 200 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3574 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Wayne | IN | DPP-2023 | Central |  |  | Other_ | 60 | 60 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3575 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2023 | South |  |  | GILMORE - WILSON 161.0kV | 300 | 300 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3576 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Walthall | MS | DPP-2024 | South |  |  | BOGALUSA 500 SS - FRANKLIN EHV 500.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3577 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-11-15T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Simpson | MS | DPP-2023 | South |  |  | MAGEE | 120 | 120 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3578 | Active | 2024-04-09T04:00:00+00:00 |  |  | 2027-04-15T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Greene | AR | DPP-2023 | South |  |  | Gainesville Switching Station | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3579 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-12-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2023 | South |  |  | MARIANNA WEST SS - MARIANNA 115.0kV | 135 | 135 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3580 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Mississippi | AR | DPP-2023 | South |  |  | AECC Dell 161kV - Nucor-Yamato 161kV Switching Station 161.0kV | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3581 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | CLECO POWER LLC | Avoyelles | LA | DPP-2023 | South |  |  | Eola - Marksville 138.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3582 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | CLECO POWER LLC | Beauregard | LA | DPP-2023 | South |  |  | Longville - Nelson (EES) 138.0kV | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3583 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2023 | South |  |  | KEO EHV | 600 | 600 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3584 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2023 | South |  |  | BRINKLEY EAST - AECC AUBREY 230.0kV | 215 | 215 | Hybrid | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3585 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Sabine | LA | DPP-2023 | South |  |  | HARTBURG - AEP LAYFIELD 500.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3586 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Grenada | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - TILLATOBA 230.0kV | 250.55 | 250.55 | Solar | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3587 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-07-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson | TX | DPP-2023 | South |  |  | PORT ACRES BULK | 110 | 110 | Gas | Co-gen |  |  | 0 | 0 | 0 | 0
MISO | J3588 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lawrence | AR | DPP-2023 | South |  |  | SWIFTON - AECC HOXIE SOUTH 161.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3589 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Lincoln | MS | DPP-2023 | South |  |  | FRANKLIN EHV - MCCOMB 115.0kV | 160 | 160 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3590 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-12-31T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Humphreys | MS | DPP-2023 | South |  |  | BELZONI - BELZONI TAP SS 115.0kV | 75 | 75 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3591 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Helena | LA | DPP-2023 | South |  |  | MCKNIGHT - PLANT DANIEL 500.0kV | 400 | 400 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3592 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - TILLATOBA 230.0kV | 57 | 57 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3593 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Clay | IN | DPP-2023 | Central |  |  | Wabash River - Staunton 230.0kV | 250 | 250 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3594 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-12-30T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2023 | South |  |  | ELTON - COMPTON TAP 69.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3595 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-02T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - TILLATOBA 230.0kV | 230 | 230 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3596 | Active | 2024-04-19T04:00:00+00:00 |  |  | 2029-07-02T04:00:00+00:00 | ENTERGY TEXAS, INC. | Harris | TX | DPP-2024 | South |  |  | BEVIL - CYPRESS 230.0kV | 460 | 460 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3597 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2023 | South |  |  | WEST MEMPHIS EHV - KEO EHV 500.0kV | 348 | 348 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3598 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | GridUnity | McLean | IL | DPP-2023 | Central |  |  | Other_ | 9 | 9 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3599 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2027-06-01T04:00:00+00:00 | ARKANSAS ELECTRIC COOPERATIVE CORPORATION | Craighead | AR | DPP-2023 | South |  |  | Lunsford | 60 | 60 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3600 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2023 | South |  |  | OAK RIDGE (LA) - SWARTZ 115.0kV | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3601 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2023 | South |  |  | OAK RIDGE (LA) - SWARTZ 115.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3602 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | GridUnity | McLean | IL | DPP-2023 | Central |  |  | Other_ | 110 | 110 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3603 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2023 | South |  |  | OAK RIDGE (LA) - STERLINGTON 115 SWYD 115.0kV | 175 | 175 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3604 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Sullivan | IN | DPP-2023 | Central |  |  | Merom (HED) - Dresser 345.0kV | 631 | 650 | Gas | Combined Cycle |  |  | 0 | 0 | 0 | 0
MISO | J3605 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-15T04:00:00+00:00 | ENTERGY TEXAS, INC. | Liberty | TX | DPP-2023 | South |  |  | JACINTO | 430 | 465 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3606 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2023 | South |  |  | PARKIN - GILMORE 161.0kV | 197.7 | 197.7 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3607 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry | IN | DPP-2023 | Central |  |  | New Castle I Avenue | 47.4 | 47.4 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3608 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Henry | IN | DPP-2023 | Central |  |  | New Castle I Avenue | 77.6 | 77.6 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3609 | Active | 2024-04-02T04:00:00+00:00 |  |  | 2027-12-27T05:00:00+00:00 | GridUnity | Beauregard | LA | DPP-2023 | South |  |  | NELSON 138 SWYD - LONGVILLE (CLECO) 138.0kV | 93.1 | 93.1 | Solar | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3610 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Tyler | TX | DPP-2023 | South |  |  | DOUCETTE | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3611 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-12-30T05:00:00+00:00 | AMEREN ILLINOIS | Hamilton | IL | DPP-2023 | Central |  |  | 7W_FRFT_E - 7NORRIS 345.0kV | 140 | 140 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3612 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2023 | South |  |  | Fisher - Many 138.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3613 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ashley | AR | DPP-2023 | South |  |  | CROSSETT NORTH - HAMBURG 115.0kV | 180 | 180 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3614 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Ashley | AR | DPP-2023 | South |  |  | CROSSETT NORTH - HAMBURG 115.0kV | 180 | 180 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3615 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2023 | South |  |  | STUTTGART NORTH SS | 125 | 125 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3616 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Arkansas | AR | DPP-2023 | South |  |  | STUTTGART NORTH SS | 125 | 125 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3617 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay | AR | DPP-2023 | South |  |  | DATTO | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3618 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clay | AR | DPP-2023 | South |  |  | DATTO | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3619 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2023 | South |  |  | MONETTE JUNCTION - PARAGOULD 161.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3620 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2023 | South |  |  | MONETTE JUNCTION - PARAGOULD 161.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3621 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2023 | South |  |  | HERGETT - POWERLINE ROAD 161.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3622 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2023 | South |  |  | HERGETT - POWERLINE ROAD 161.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3623 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2023 | South |  |  | Indianola | 350 | 350 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3624 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Columbia | AR | DPP-2023 | South |  |  | MAGNOLIA SOUTH - SHULER 115.0kV | 155 | 155 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3625 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2027-10-27T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Winn | LA | DPP-2023 | South |  |  | JELD WEN - WINNFIELD 115 SUB 115.0kV | 82 | 82 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3626 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-12-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2023 | South |  |  | INDEPENDENCE-ISES - POWERLINE ROAD 500.0kV | 500 | 500 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3627 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-12-31T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Craighead | AR | DPP-2023 | South |  |  | JONESBORO (APL) - CASH 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3628 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-12-31T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Jefferson | MS | DPP-2023 | South |  |  | FRANKLIN EHV - GRAND GULF TRANSMISSION 500.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3629 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-12-15T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Bolivar | MS | DPP-2023 | South |  |  | DELTA SWYD - DREW [MS] 115.0kV | 210 | 210 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3630 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-15T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | East Feliciana | LA | DPP-2023 | South |  |  | MOLER - COLFEL 230.0kV | 117 | 117 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3631 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-12-15T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Vermilion | LA | DPP-2023 | South |  |  | GUEYDAN TAP - MORSE 69.0kV | 60 | 60 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3632 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2029-04-22T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cleveland | AR | DPP-2023 | South |  |  | TEXAS EASTERN P.S. G SS - FORDYCE ORIENT SS 115.0kV | 100 | 100 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3633 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | ITC | Sanilac | MI | DPP-2023 | East (ITC) |  |  | GREENWOOD - RAPSON (BANNER) 345.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3634 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2027-12-31T05:00:00+00:00 | METC | Gratiot | MI | DPP-2023 | East (ITC) |  |  | NELSON ROAD | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3635 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2027-12-31T05:00:00+00:00 | METC | Kent | MI | DPP-2023 | East (ITC) |  |  | GAINES | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3636 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-31T04:00:00+00:00 | ITC | Tuscola | MI | DPP-2023 | East (ITC) |  |  | BAUER | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3637 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-06-30T04:00:00+00:00 | METC | Otsego | MI | DPP-2023 | East (ITC) |  |  | LIVINGSTON - TITTABAWASSEE 345.0kV | 90 | 90 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3638 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-16T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dickinson | MI | DPP-2023 | East (ATC) |  |  | Niagara Of Wis Tap 1 (78662) - Niagra Paper Of Wisconsin 138.0kV | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3639 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Columbia | WI | DPP-2023 | East (ATC) |  |  | Columbia - Rockdale 345.0kV | 250 | 250 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3640 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | MICHIGAN PUBLIC POWER AGENCY | Shiawassee | MI | DPP-2023 | East (ITC) |  |  | MURPHY - NELSON ROAD 345.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3641 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-16T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dickinson | MI | DPP-2023 | East (ATC) |  |  | Niagara Of Wis Tap 1 (78662) - Niagra Paper Of Wisconsin 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3642 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-16T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Dickinson | MI | DPP-2023 | East (ATC) |  |  | Nordic | 60 | 60 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3643 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-16T04:00:00+00:00 | METC | Midland | MI | DPP-2023 | East (ITC) |  |  | REDSTONE - TITTABAWASSEE 138.0kV | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3644 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | METC | Bay | MI | DPP-2023 | East (ITC) |  |  | Other_ | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3645 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ITC | Huron | MI | DPP-2023 | East (ITC) |  |  | RAPSON | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3646 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | ITC | St. Clair | MI | DPP-2023 | East (ITC) |  |  | ST. CLAIR | 220 | 220 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3647 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-11-15T05:00:00+00:00 | METC | Gratiot | MI | DPP-2023 | East (ITC) |  |  | NELSON ROAD | 220 | 220 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3648 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Baraga | MI | DPP-2023 | East (ATC) |  |  | Silver River - M-38 138.0kV | 120 | 120 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3649 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Houghton | MI | DPP-2023 | East (ATC) |  |  | Winona | 200 | 200 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3650 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-11-15T05:00:00+00:00 | METC | Genesee | MI | DPP-2023 | East (ITC) |  |  | BEVERIDGE | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3651 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | METC | Lenawee | MI | DPP-2023 | East (ITC) |  |  | BEECHER - KNOWLES 138.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3652 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Lenawee | MI | DPP-2023 | East (ITC) |  |  | BEECHER - KNOWLES 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3653 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2030-01-01T05:00:00+00:00 | ITC | Washtenaw | MI | DPP-2023 | East (ITC) |  |  | Superior 120 kV | 80 | 80 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3654 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2030-01-01T05:00:00+00:00 | ITC | Washtenaw | MI | DPP-2023 | East (ITC) |  |  | SUPERIOR 120 kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3655 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Dallas | IA | DPP-2023 | West |  |  | OVERLAND TRAIL - FALLOW AVENUE 345.0kV | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3656 | Active | 2024-03-26T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ITC | Saginaw | MI | DPP-2023 | East (ITC) |  |  | BAUER | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3657 | Active | 2024-04-04T04:00:00+00:00 |  |  | 2028-06-15T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Washington | MS | DPP-2023 | South |  |  | Greer Solar substation J1458 | 50 | 50 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3658 | Active | 2024-03-25T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Clark | AR | DPP-2023 | South |  |  | GURDON - BEIRNE 115.0kV | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3659 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-12-27T05:00:00+00:00 | CLECO POWER LLC | Avoyelles | LA | DPP-2023 | South |  |  | Yellow Bayou | 90.25 | 90.25 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3660 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Rock Island | IL | DPP-2023 | West |  |  | Oak Grove 161 kV sub | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3661 | Active | 2024-04-14T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | GridUnity | Henry | IA | DPP-2023 | West |  |  | 7MAYWOOD - 7SUB T 3 345.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3662 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | GridUnity | Monroe | IL | DPP-2023 | Central |  |  | Valmeyer 138kV. | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3663 | Active | 2024-04-13T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Morehouse | LA | DPP-2023 | South |  |  | OAK RIDGE (LA) - STERLINGTON 115 SWYD 115.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3664 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-12-30T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaGrange | IN | DPP-2023 | Central |  |  | Other_ | 80 | 80 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3665 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-12-30T05:00:00+00:00 | GridUnity | Redwood | MN | DPP-2023 | West |  |  | Redwood Falls Tap - Redwood Falls West 115.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3666 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Morgan | IN | DPP-2023 | Central |  |  | Petersburg - Thompson 345.0kV | 371.09 | 378.82 | Gas | Combustion Turbine (Simple Cycle) |  |  | 0 | 0 | 0 | 0
MISO | J3667 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-12-31T05:00:00+00:00 | GridUnity | Dickey | ND | DPP-2023 | West |  |  | Other_ | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3668 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | METC | Cheboygan | MI | DPP-2023 | East (ITC) |  |  | PORT CALCITE - RIGGSVILLE 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3669 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-02-01T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Stevens | MN | DPP-2023 | West |  |  | Riverview - Alexandria MRES 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3670 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | GridUnity | LaSalle | IL | DPP-2023 | Central |  |  | Corbin 138 kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3671 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-07-27T04:00:00+00:00 | AMEREN ILLINOIS | Shelby | IL | DPP-2023 | Central |  |  | 4NEOGA 2 - 4SHELBYVL E 138.0kV | 120 | 120 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3672 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Traverse | MN | DPP-2023 | West |  |  | Graceville - Dumont 115.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3673 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Newton | IN | DPP-2023 | Central |  |  | GOODLAND - MORRISON DITCH 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3674 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Jasper | IL | DPP-2023 | Central |  |  | 4NEWTON - 4WISEMAN 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3675 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Roseau | MN | DPP-2023 | West |  |  | Moranville (Bus# 657999) | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3676 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-12-15T05:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Otsego | MI | DPP-2023 | East (ITC) |  |  | Gaylord - Atlanta 138.0kV | 93 | 93 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3677 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Daviess | IN | DPP-2023 | Central |  |  | Other_ | 148 | 148 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3678 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-09-10T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2023 | Central |  |  | CAYUGA 345 | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3679 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-31T05:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | LaPorte | IN | DPP-2023 | Central |  |  | BABCOCK - STILLWELL 345.0kV | 149 | 149 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3680 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-11-15T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Scott | MS | DPP-2023 | South |  |  | PELAHATCHIE | 189 | 189 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3681 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | AMEREN ILLINOIS | McLean | IL | DPP-2023 | Central |  |  | 7CLINTON - 7BROKAW 345.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3682 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | METC | Muskegon | MI | DPP-2023 | East (ITC) |  |  | FOUR MILE - WHITE ROAD 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3683 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Scott | IL | DPP-2023 | Central |  |  | 4BALLARD - 4MEREDOSA 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3684 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Morgan | IL | DPP-2023 | Central |  |  | 4JACK_IND N - 4YATES 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3685 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Pike | IL | DPP-2023 | Central |  |  | 4HULL - 4MEPPEN T 138.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3686 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Christian | IL | DPP-2023 | Central |  |  | 4AUSTIN - 4TAYLORVL 138.0kV | 190 | 190 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3687 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-07-23T04:00:00+00:00 | AMEREN ILLINOIS | Fayette | IL | DPP-2023 | Central |  |  | 4OTEGO - 4KINMUNDY 138.0kV | 140 | 140 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3688 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2023 | Central |  |  | MONTICELLO - SPRINGBORO(DUKE) 138.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3689 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Montgomery | IN | DPP-2023 | Central |  |  | Other_ | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3690 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN MISSOURI | Scott | MO | DPP-2023 | Central |  |  | 5STODDARD - 5MORLEY (AECI) 161.0kV | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3691 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White | IN | DPP-2023 | Central |  |  | REYNOLDS | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3692 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | METC | Cheboygan | MI | DPP-2023 | East (ITC) |  |  | PORT CALCITE - RIGGSVILLE 138.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3693 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Marshall | IN | DPP-2023 | Central |  |  | BURR OAK - LEESBURG 345.0kV | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3694 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vermillion | IN | DPP-2023 | Central |  |  | Sugar Creek - Cayuga CT 345.0kV | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3695 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Clark | IL | DPP-2023 | Central |  |  | 7CASEY - 7SNYDER 345.0kV | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3696 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2026-12-30T05:00:00+00:00 | METC | Montcalm | MI | DPP-2023 | East (ITC) |  |  | NELSON ROAD - VERGENNES 345.0kV | 225 | 225 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3697 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | GridUnity | Jennings | IN | DPP-2023 | Central |  |  | Other_ | 44 | 44 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3698 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-16T04:00:00+00:00 | METC | Roscommon | MI | DPP-2023 | East (ITC) |  |  | HIGGINS - MIO DAM 138.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3699 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Henry | IL | DPP-2023 | Central |  |  | SUB 39 - OAK GROVE 345.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3700 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Champaign | IL | DPP-2023 | Central |  |  | 7BUNSONVILLE - 7SIDNEY 345.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3701 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Taylor | IA | DPP-2023 | West |  |  | ORIENT - NORTHBORO 345.0kV | 400 | 400 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3702 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Mitchell | IA | DPP-2023 | West |  |  | ADAMS | 180 | 180 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3703 | Active | 2024-03-25T04:00:00+00:00 |  |  | 2028-06-15T04:00:00+00:00 | GridUnity | Itasca | MN | DPP-2023 | West |  |  | Blackberry 230/115kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3704 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Redwood | MN | DPP-2023 | West |  |  | Cedar Mountain - Lyon County 345.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3705 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Redwood | MN | DPP-2023 | West |  |  | Cedar Mountain - Lyon County 345.0kV | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3706 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-05-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Mississippi | AR | DPP-2023 | South |  |  | GILMORE - WILSON 161.0kV | 150 | 150 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3707 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-09-15T04:00:00+00:00 | GridUnity | Putnam | IN | DPP-2023 | Central |  |  | Other_ | 40 | 40 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3708 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-04-30T04:00:00+00:00 | ENTERGY TEXAS, INC. | Jefferson | TX | DPP-2023 | South |  |  | LEGEND | 735 | 770 | Gas | Combined-Cycle – Steam Plant |  |  | 0 | 0 | 0 | 0
MISO | J3709 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-07-31T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Marion | IN | DPP-2023 | Central |  |  | Georgetown | 47 | 47 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3710 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-07-31T04:00:00+00:00 | AMEREN ILLINOIS | Jersey | IL | DPP-2023 | Central |  |  | Jerseyville Northwest | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3711 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2029-07-02T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Calhoun | AR | DPP-2023 | South |  |  | SHERIDAN EHV - EL DORADO EHV 500.0kV | 400 | 400 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3712 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Peoria | IL | DPP-2023 | Central |  |  | 7FARGO - 7SANDBURG 345.0kV | 400 | 400 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3713 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | ITC MIDWEST | Wapello | IA | DPP-2023 | West |  |  | Ottumwa Generation - Woody 161kV | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3714 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | COOPERATIVE ENERGY | Scott | MS | DPP-2023 | South |  |  | Homewood 69 - Lake 69.0kV | 95 | 95 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3715 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | HOOSIER ENERGY | Jackson | IN | DPP-2023 | Central |  |  | Other_ | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3716 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-07-03T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - MCADAMS EHV 230.0kV | 199 | 199 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3717 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-07-03T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Yalobusha | MS | DPP-2023 | South |  |  | ENID - TILLATOBA 230.0kV | 199 | 199 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3718 | Active | 2024-03-20T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Greene | IL | DPP-2023 | Central |  |  | Roodhouse West | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3719 | Active | 2024-03-20T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Miami | IN | DPP-2023 | Central |  |  | Greentown - Walton. 230.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3720 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN MISSOURI | Ralls | MO | DPP-2023 | Central |  |  | 5SPALDNG (AECI) - 5PENOCRK 161.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3721 | Active | 2024-03-20T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Spencer | IN | DPP-2023 | Central |  |  | Culley - Dubois 138.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3722 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | METC | Hillsdale | MI | DPP-2023 | East (ITC) |  |  | COLDWATER - MOORE ROAD 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3723 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | METC | Wexford | MI | DPP-2023 | East (ITC) |  |  | KEYSTONE - LUDINGTON 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3724 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Vigo | IN | DPP-2023 | Central |  |  | Dresser - Wabash River 138.0kV | 133 | 133 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3725 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Louisa | IA | DPP-2023 | West |  |  | SUB 93 LOUISA - SUB T HASKINS 345.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3726 | Active | 2024-03-18T04:00:00+00:00 |  |  | 2027-01-15T05:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Hancock | KY | DPP-2023 | Central |  |  | Skillman | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3727 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | AMEREN ILLINOIS | Madison | IL | DPP-2023 | Central |  |  | Mississippi | 225 | 225 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3728 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-02-01T05:00:00+00:00 | Southern Illinois Power Cooperative | Franklin | IL | DPP-2023 | Central |  |  | Ameren E. West Frankfort - Franklin 138.0kV | 400 | 400 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3729 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-02-01T05:00:00+00:00 | AMEREN ILLINOIS | Franklin | IL | DPP-2023 | Central |  |  | Benton Northwest | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3730 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | AMEREN ILLINOIS | Macoupin | IL | DPP-2023 | Central |  |  | MORO 345 kV Substation | 444 | 444 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3731 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-01-31T05:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2023 | Central |  |  | Edwardsport - Vincennes 138.0kV | 160 | 160 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3732 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2026-12-30T05:00:00+00:00 | AMEREN ILLINOIS | Saline | IL | DPP-2023 | Central |  |  | 4HARCO - 4MUDDY 138.0kV | 175 | 175 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3733 | Active | 2024-05-25T04:00:00+00:00 |  |  | 2028-04-17T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Gibson | IN | DPP-2023 | Central |  |  | Oakland City - Old Ben Coal 138.0kV | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3734 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ITC | Oakland | MI | DPP-2023 | East (ITC) |  |  | STRATFORD | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3735 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | METC | Genesee | MI | DPP-2023 | East (ITC) |  |  | BEVERIDGE 138kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3736 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2027-12-03T05:00:00+00:00 | AMEREN MISSOURI | Osage | MO | DPP-2023 | Central |  |  | LOOSE CREEK | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3737 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Mills | IA | DPP-2023 | West |  |  | HASTINGS | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3738 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-12-09T05:00:00+00:00 | GridUnity | Vermilion | LA | DPP-2023 | South |  |  | Gueydan Entergy Power Station 69kV | 65 | 65 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3739 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | GridUnity | Warren | IL | DPP-2023 | Central |  |  | 138kV LINE TAP BETWEEN GALESBURG MONMOUTH BOULEVARD (BUS 348956) AND CASTRO JCT (BUS 348917) SUBSTAT | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3740 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2027-09-15T04:00:00+00:00 | GridUnity | Putnam | IN | DPP-2023 | Central |  |  | Other_ | 40 | 40 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3741 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cleveland | AR | DPP-2023 | South |  |  | WOODWARD 115 SUB - RISON 115.0kV | 155 | 155 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3742 | Active | 2024-06-06T04:00:00+00:00 |  |  | 2030-12-15T05:00:00+00:00 | GREAT RIVER ENERGY | Otter Tail | MN | DPP-2023 | West |  |  | Wahpeton - Fergus Falls 230.0kV | 160 | 160 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3743 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2027-05-01T04:00:00+00:00 | ITC | Tuscola | MI | DPP-2023 | East (ITC) |  |  | ARROWHEAD | 175.5 | 175.5 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3744 | Active | 2024-04-18T04:00:00+00:00 |  |  | 1995-10-23T04:00:00+00:00 | METC | Mason | MI | DPP-2023 | East (ITC) |  |  | MICHIGAN POWER - PEREMARQUETTE 138.0kV | 15 | 15 | Gas | Combined Cycle |  |  | 0 | 0 | 0 | 0
MISO | J3745 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-07-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Dearborn | IN | DPP-2023 | Central |  |  | Sunman Weisburg | 150 | 150 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3746 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | CLECO POWER LLC | Grant | LA | DPP-2023 | South |  |  | Rodemacher - Sherwood 230.0kV | 250 | 250 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3747 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lonoke | AR | DPP-2023 | South |  |  | WHITE BLUFF EHV - KEO EHV 500.0kV | 300 | 300 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3748 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | GridUnity | Washington | MS | DPP-2023 | South |  |  | Gerald Andrus 230 kV | 200 | 200 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3749 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lyon | MN | DPP-2023 | West |  |  | LYON COUNTY | 200 | 200 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3750 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-30T04:00:00+00:00 | AMEREN ILLINOIS | Mercer | IL | DPP-2023 | Central |  |  | 5SANDBURG - 5MERCER 161.0kV | 250 | 250 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3751 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-31T04:00:00+00:00 | AMEREN ILLINOIS | Madison | IL | DPP-2023 | Central |  |  | 7COFFEEN - 7ROXFORD 345.0kV | 236 | 236 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3752 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-10-01T04:00:00+00:00 | MINNESOTA POWER INC. | Aitkin | MN | DPP-2023 | West |  |  | Cromwell (GRE) - Riverton 115kV | 220 | 220 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3753 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | GridUnity | Iroquois | IL | DPP-2023 | Central |  |  | Other_ | 195.55 | 195.55 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3754 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | GridUnity | Iroquois | IL | DPP-2023 | Central |  |  | Other_ | 146.66 | 146.66 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3755 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | GridUnity | Iroquois | IL | DPP-2023 | Central |  |  | Other_ | 146.66 | 146.66 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3756 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2019-01-21T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Marquette | MI | DPP-2023 | East (ATC) |  |  | Huron | 4.2 | 4.2 | Gas | Piston (Engine), Internal Combustion (Diesel) |  |  | 0 | 0 | 0 | 0
MISO | J3757 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ITC MIDWEST | Dubuque | IA | DPP-2023 | West |  |  | Salem 161kv | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3758 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-15T04:00:00+00:00 | GridUnity | Macon | MO | DPP-2023 | Central |  |  | Other_ | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3759 | Active | 2024-04-01T04:00:00+00:00 |  |  | 2027-04-30T04:00:00+00:00 | AMEREN ILLINOIS | Jasper | IL | DPP-2023 | Central |  |  | Newton Switchyard | 15 | 15 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3760 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Richland | LA | DPP-2023 | South |  |  | BAXTER WILSON SES SWYD - PERRYVILLE 500 SWYD 500.0kV | 405 | 405 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3761 | Active | 2024-04-05T04:00:00+00:00 |  |  | 2027-11-01T04:00:00+00:00 | METC | Ogemaw | MI | DPP-2023 | East (ITC) |  |  | GALLAGHER - TWINING 138.0kV | 145.8 | 145.8 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3762 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | GREAT RIVER ENERGY | Clay | MN | DPP-2023 | West |  |  | ALEXANDRIA - BISON 345.0kV | 430 | 430 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3763 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-06-01T04:00:00+00:00 | ITC | Wayne | MI | DPP-2023 | East (ITC) |  |  | DBGEN GIS | 7.5 | 7.5 | Waste Heat Recovery | Combined-Cycle – Steam Plant |  |  | 0 | 0 | 0 | 0
MISO | J3764 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | GridUnity | Madison | MS | DPP-2023 | South |  |  | Virlilia Substation 230 kV | 170 | 170 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3765 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2024-04-18T04:00:00+00:00 | GridUnity | St. James | LA | DPP-2023 | South |  |  | ST JAMES | 8 | 8 | Hybrid | Steam Turbine (including Nuclear, Geothermal and Solar Steam) |  |  | 0 | 0 | 0 | 0
MISO | J3766 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-10-30T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Pottawattamie | IA | DPP-2023 | West |  |  | ROLLING HILLS - PONY CREEK 345.0kV | 235 | 235 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3767 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | HOOSIER ENERGY | Crawford | IN | DPP-2023 | Central |  |  | ECKERTY - BUECHLER 69.0kV | 38 | 38 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3768 | Active | 2024-04-10T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Walker | TX | DPP-2023 | South |  |  | ROCKY CREEK | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3769 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | WOLVERINE POWER SUPPLY COOPERATIVE | Saginaw | MI | DPP-2023 | East (ITC) |  |  | MURPHY - NELSON ROAD 345.0kV | 250 | 250 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3770 | Active | 2024-04-01T04:00:00+00:00 |  |  | 2027-04-30T04:00:00+00:00 | AMEREN ILLINOIS | Randolph | IL | DPP-2023 | Central |  |  | The Baldwin 345kV substation found in the drop down. But please note the POI is same as J1202. The p | 45.8 | 45.8 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3771 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | CLECO POWER LLC | Sabine | LA | DPP-2023 | South |  |  | Fisher - Many 138.0kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3772 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-07-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Panola | MS | DPP-2023 | South |  |  | BATESVILLE [MS] - MARKS 115.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3773 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-07-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Drew | AR | DPP-2023 | South |  |  | MONTICELLO EAST - REED SS 115.0kV | 265 | 265 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3774 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-07-31T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2023 | South |  |  | INDIANOLA 230/115 SUB - TILLATOBA 230.0kV | 303 | 303 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3775 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2028-12-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Desha | AR | DPP-2023 | South |  |  | DUMAS - REED SS 115.0kV | 160 | 160 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3776 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | METC | Midland | MI | DPP-2023 | East (ITC) |  |  | TittabawASSEE | 150 | 150 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3777 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | GridUnity | Cheboygan | MI | DPP-2023 | East (ITC) |  |  | Other_ | 91.8 | 91.8 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3778 | Active | 2024-04-15T04:00:00+00:00 |  |  | 2031-01-01T05:00:00+00:00 | MISSOURI RIVER ENERGY SERVICES - TRANSMISSION | Otter Tail | MN | DPP-2023 | West |  |  | Fergus Falls MRES | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3779 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-10-15T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Centerpoint Energy Indiana South | Henderson | KY | DPP-2023 | Central |  |  | AB Brown 345 - Reid EHV (BREC Terminal) 345.0kV | 100 | 100 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3780 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ITC MIDWEST | Buchanan | IA | DPP-2023 | West |  |  | Hazleton | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3781 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-07-27T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | Jefferson Davis | LA | DPP-2023 | South |  |  | HEBERT (SLEMCO) - HENNING 138.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3782 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-07-26T04:00:00+00:00 | METC | Saginaw | MI | DPP-2023 | East (ITC) |  |  | 18MURPHY | 180 | 180 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3783 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2023 | South |  |  | AECC WYNNE EAST - PARKIN 161.0kV | 200 | 200 | Hybrid | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3784 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Ozaukee | WI | DPP-2023 | East (ATC) |  |  | Saukville (Cedarsauk) | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3785 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Kenosha | MI | DPP-2023 | East (ATC) |  |  | Pleasant Prairie | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3786 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | GridUnity | Washtenaw | MI | DPP-2023 | East (ITC) |  |  | Coventry 230kV | 200 | 200 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3787 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Stutsman | ND | DPP-2023 | West |  |  | Jamestown 345 kV Substation | 247 | 247 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3788 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Grant | AR | DPP-2023 | South |  |  | AECC GRAPEVINE - CARTHAGE (AR) 115.0kV | 150 | 150 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3789 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-07-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Hancock | IN | DPP-2023 | Central |  |  | FOUNTAINTOWN | 77 | 77 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3790 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Lee | AR | DPP-2023 | South |  |  | MARIANNA - WEST HELENA 115.0kV | 120 | 120 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3791 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-05-07T04:00:00+00:00 | SOUTHERN MINNESOTA MUNICIPAL POWER AGENCY | Houston | MN | DPP-2023 | West |  |  | Caledonia | 50 | 50 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3792 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | METC | Gratiot | MI | DPP-2023 | East (ITC) |  |  | ALMA - VESTABURG 138.0kV | 125 | 125 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3793 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | CLECO POWER LLC | Rapides | LA | DPP-2023 | South |  |  | East Leesville - Rodemacher 230.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3794 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | GridUnity | Daviess | KY | DPP-2023 | Central |  |  | Daviess County - Utica 69.0kV | 50 | 50 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3795 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | GridUnity | Knox | MO | DPP-2023 | Central |  |  | 7FABIUS - 7MAYWOOD 345.0kV | 91 | 91 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3796 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-11-30T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Calcasieu | LA | DPP-2023 | South |  |  | NELSON 230 SWYD | 735 | 770 | Gas | Combined-Cycle – Steam Plant |  |  | 0 | 0 | 0 | 0
MISO | J3797 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Edgar | IL | DPP-2023 | Central |  |  | 7KANSAS - 08SUGCRK 345.0kV | 141.23 | 141.23 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3798 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | ITC MIDWEST | Winnebago | IA | DPP-2023 | West |  |  | Bison - Colby 345kV | 320 | 320 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3799 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2030-04-01T04:00:00+00:00 | METC | Livingston | MI | DPP-2024 | East (ITC) |  |  | BLACKFOOT - MADRID 345.0kV | 1452 | 1452 | Gas | Combined Cycle |  |  | 0 | 0 | 0 | 0
MISO | J3800 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2019-01-21T05:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Baraga | MI | DPP-2023 | East (ATC) |  |  | Silver River | 1.8 | 1.8 | Gas | Piston (Engine), Internal Combustion (Diesel) |  |  | 0 | 0 | 0 | 0
MISO | J3801 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-03-31T04:00:00+00:00 | MIDAMERICAN ENERGY CO. | Mercer | IL | DPP-2023 | Central |  |  | OAK GROVE - SANDBURG (AMRN) 345.0kV | 195.64 | 195.64 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3802 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-04T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2023 | South |  |  | RITCHIE SWYD - TARLETON 230.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3803 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-04-01T04:00:00+00:00 | METC | Monroe | MI | DPP-2023 | East (ITC) |  |  | LEMOYNE - MAJESTIC 345.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3804 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2023 | Central |  |  | Edwardsport IGCC - Amo 345.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3805 | Active | 2024-03-27T04:00:00+00:00 |  |  | 2027-09-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Fayette | IL | DPP-2023 | Central |  |  | Coffeen North-Ramsey East-4557 | 250 | 250 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3806 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Sunflower | MS | DPP-2023 | South |  |  | STEINER (CE) - SHAW SS (CE) 115.0kV | 100 | 100 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3807 | Active | 2024-04-09T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | GridUnity | Goodhue | MN | DPP-2023 | West |  |  | Hampton - Prairie Island 345.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3808 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-05-01T04:00:00+00:00 | GridUnity | Webster | IA | DPP-2023 | West |  |  | IRVINGTON - WEBSTER 345.0kV | 300 | 300 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3809 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Mason | IL | DPP-2023 | Central |  |  | POWERTON;RT - 4TOWERLINE 138.0kV | 199.99 | 199.99 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3810 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-10-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Knox | IN | DPP-2023 | Central |  |  | Edwardsport IGCC - Amo 345.0kV | 300 | 300 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3811 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | GridUnity | Clay | IL | DPP-2023 | Central |  |  | 4KINMUNDY S - 4TANNER 138.0kV | 200 | 200 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3812 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY ARKANSAS, LLC | Phillips | AR | DPP-2023 | South |  |  | AECC AUBREY - RITCHIE SWYD 230.0kV | 158.59 | 158.59 | Solar | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3813 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-06-30T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Putnam | IN | DPP-2023 | Central |  |  | Edwardsport IGCC - Amo 345.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3814 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-10-30T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | Cross | AR | DPP-2023 | South |  |  | FORREST CITY N SS - WYNNE SOUTH 161.0kV | 135 | 135 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3815 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2026-10-22T04:00:00+00:00 | ENTERGY LOUISIANA, LLC | St. Charles | LA | DPP-2023 | South |  |  | Waterford 3 SWYD | 153.1 | 59.5 | Nuclear | Nuclear |  |  | 0 | 0 | 0 | 0
MISO | J3816 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | METC | Saginaw | MI | DPP-2023 | East (ITC) |  |  | BULLOCK - SAGINAW RIVER 138.0kV | 100 | 100 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3817 | Active | 2024-04-11T04:00:00+00:00 |  |  | 2028-08-17T04:00:00+00:00 | METC | Allegan | MI | DPP-2023 | East (ITC) |  |  | Other_ | 175 | 175 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3818 | Active | 2024-06-07T04:00:00+00:00 |  |  | 2028-03-01T05:00:00+00:00 | AMEREN ILLINOIS | Shelby | IL | DPP-2023 | Central |  |  | 4PANA 1 - 4SHELBYVL E 138.0kV | 40 | 40 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3819 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2027-05-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Madison | MS | DPP-2023 | South |  |  | CATLETT - TINNIN ROAD 230.0kV | 36.1 | 36.1 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3820 | Active | 2024-04-16T04:00:00+00:00 |  |  | 2028-06-01T04:00:00+00:00 | GridUnity | Hancock | IL | DPP-2023 | Central |  |  | LRTP Line | 127 | 127 | Wind | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | J3821 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-08-01T04:00:00+00:00 | ENTERGY TEXAS, INC. | Walker | TX | DPP-2023 | South |  |  | RIVTRIN | 175 | 175 | Hybrid | Solar/Battery |  |  | 0 | 0 | 0 | 0
MISO | J3822 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | Pointe Coupee | LA | DPP-2023 | South |  |  | DEVIN - LIVONIA 138.0kV | 139.58 | 139.58 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3823 | Active | 2024-04-12T04:00:00+00:00 |  |  | 2028-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Watonwan | MN | DPP-2023 | West |  |  | Crandall - Fieldon 345.0kV | 300 | 300 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3824 | Withdrawn | 2024-04-18T04:00:00+00:00 | 2024-06-28T04:00:00+00:00 |  | 2028-09-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Roberts | SD | DPP-2023 | West |  |  | Twin Brooks 345 kV Substation | 250 | 250 | Battery Storage | Battery Storage |  |  | 0 | 0 | 0 | 0
MISO | J3825 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2028-01-01T05:00:00+00:00 | GridUnity | Hinds | MS | DPP-2023 | South |  |  | Entergy 500kV / 230kV / 115kV Lakeover Substation | 730 | 770 | Gas | Combined-Cycle – Steam Plant |  |  | 0 | 0 | 0 | 0
MISO | J3826 | Active | 2024-04-17T04:00:00+00:00 |  |  | 2026-11-01T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC. | Holmes | MS | DPP-2023 | South |  |  | 3Pickens | 198 | 198 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J3827 | Active | 2024-04-18T04:00:00+00:00 |  |  | 2028-11-01T04:00:00+00:00 | AMERICAN TRANSMISSION COMPANY | Mackinac | MI | DPP-2024 | East (ATC) |  |  | Indian Lake - Hiawatha 138.0kV | 160 | 160 | Solar | Photovoltaic |  |  | 0 | 0 | 0 | 0
MISO | J418 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2016-11-01T04:00:00+00:00 | Entergy | Polk County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Rich - Livingston 138kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J441 | Withdrawn | 2015-04-15T04:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2018-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dodge County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Byron 345 kV Substation | 170 | 170 | Wind | Wind Turbine | Withdrawn | 2019-09-18T04:00:00+00:00 | 170 | 170 | 170 | 170
MISO | J444 | Withdrawn | 2015-05-07T04:00:00+00:00 | 2018-04-12T04:00:00+00:00 |  | 2017-01-31T05:00:00+00:00 | ITC MIDWEST | Wayne County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Waterman/Navarre 230kV | 235 | 235 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J446 | Withdrawn |  | 2023-02-21T05:00:00+00:00 | [10 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | J447 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2021-07-01T04:00:00+00:00 | ITC MIDWEST | Cerro Gordo County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Emery 161 kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J458 | Withdrawn | 2015-05-18T04:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2019-09-30T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Clark County | South Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | On proposed Big Stone-Ellendale 345 kV line approx. 76 miles west of Big Stone | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J467 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2017-11-15T05:00:00+00:00 | AMEREN ILLINOIS | Douglas County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Sidnay-Kansas 345kV Line | 102 | 102 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J478 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-04-17T04:00:00+00:00 |  | 2018-07-01T04:00:00+00:00 | Duke Energy Corporation | Clinton County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Thorntown - New London - Kokomo 230kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J502 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | Entergy | Orange County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | McLewis 230 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J508 | Withdrawn | 2015-11-16T05:00:00+00:00 | 2017-07-17T04:00:00+00:00 |  | 2017-04-01T04:00:00+00:00 | Entergy | Clark County | Arkansas | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | tap 115 kV line betwwen W Arkadelphia sub and Delarc sub at 3.85 miles from West Arkadelphia substat | 42.7 | 42.7 | Gas | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J522 | Withdrawn | 2015-11-16T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | ITC MIDWEST | Mower County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Adams substation at 69 kV | 20 | 20 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J544 | Done |  |  |  | 2018-09-01T04:00:00+00:00 | [8 empty] | 0 | 0 |  |  | In Service | 2021-09-15T04:00:00+00:00 | 98.1 | 98.1 | 98.1 | 98.1
MISO | J545 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2020-08-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lincoln County | Minnesota | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Buffalo 115kV Substation | 110 | 110 | Wind | Wind Turbine | In Service | 2022-12-15T05:00:00+00:00 | 110 | 0 | 110 | 0
MISO | J556 | Withdrawn | 2016-04-04T04:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2019-12-31T05:00:00+00:00 | GREAT RIVER ENERGY | Renville County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Panther 230kV Substation | 102 | 102 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J570 | Withdrawn | 2016-05-06T04:00:00+00:00 | 2019-08-05T04:00:00+00:00 |  | 2018-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Atchison County | Missouri | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Cooper - Atchison 345kV Line | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
MISO | J579 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2018-10-01T04:00:00+00:00 | METC | Allegan County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Argenta 345kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J580 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Burleigh County | North Dakota | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Nepoleon Sub 230kV | 298 | 298 | Wind | Wind Turbine | Not Started |  | 298 | 0 | 0 | 0
MISO | J584 | Withdrawn | 2016-05-09T04:00:00+00:00 | 2020-09-29T04:00:00+00:00 | 2019-03-26T04:00:00+00:00 | 2018-09-15T04:00:00+00:00 | American Transmission Co. LLC | Green County | Wisconsin | DPP-2017-FEB | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Blacksmith Tap - Spring Grove 69kV Line | 60 | 60 | Wind | Wind Turbine | Withdrawn | 2021-05-15T04:00:00+00:00 | 60 | 60 | 60 | 60
MISO | J625 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-02-04T05:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Meeker County,Renville County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Blue Lake 345kV Substation | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J628 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-11-09T05:00:00+00:00 | 2021-09-12T04:00:00+00:00 | 2022-07-01T04:00:00+00:00 | GREAT RIVER ENERGY | Grand Forks County,Nelson County | North Dakota | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Ramsey - Prairie 230kV Line Tap | 400 | 400 | Wind | Wind Turbine | Not Started |  | 400 | 400 | 400 | 0
MISO | J632 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2018-09-15T04:00:00+00:00 | METC | Berrien County,Van Buren County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Argenta - Plaisades 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J635 | Withdrawn | 2016-05-09T04:00:00+00:00 | 2017-06-15T04:00:00+00:00 |  | 2018-02-28T05:00:00+00:00 | Entergy | Concordia Parish | Louisiana | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Tap - Entergy 115kV T-line Natchez/South Plantation (ID:668) 1mile from Plantation Sub | 35 | 35 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J636 | Withdrawn | 2016-05-09T04:00:00+00:00 | 2017-06-20T04:00:00+00:00 |  | 2016-05-31T04:00:00+00:00 | CLECO POWER LLC | Rapides Parish | Louisiana | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Shady Oaks - Coughlin 138kV Line | 52 | 52 |  |  | Not Started |  | 0 | 0 | 0 | 0
MISO | J639 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2022-10-31T04:00:00+00:00 | 2019-12-02T05:00:00+00:00 | 2019-04-01T04:00:00+00:00 | Entergy | West Baton Rouge Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Addis - Big Cajun 230kV Line | 50 | 50 | Solar | Photovoltaic | Withdrawn | 2020-11-25T05:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J640 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-04-01T04:00:00+00:00 | Entergy | St. Helena Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Amite - Liberty 115kV Line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J646 | Done | 2016-06-16T04:00:00+00:00 |  | 2019-04-26T04:00:00+00:00 | 2010-07-01T04:00:00+00:00 | ITC MIDWEST | Macomb County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Energy Resource Interconnection Service (ERIS) | Carbon - connecting to ITC at Jewel, St-Clair and Spokane substations | 1.6 | 0 |  |  | Under Construction | 2010-07-01T04:00:00+00:00 | 1.6 | 0 | 1.6 | 0
MISO | J647 | Withdrawn | 2016-06-20T04:00:00+00:00 | 2018-09-06T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | METC | Muskegon County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | BC Cobb - Four Mile 138kV Line | 147.4 | 147.4 | Solar | Photovoltaic | Not Started |  | 124.95 | 124.95 | 0 | 0
MISO | J657 | Withdrawn | 2016-07-08T04:00:00+00:00 | 2018-04-10T04:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | American Transmission Co. LLC | Manitowoc County | Wisconsin | DPP-2017-FEB | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Kewaunee - Shoto 138kV Line (at the existing Mishicot Tap) | 100.8 | 100.8 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J658 | Withdrawn | 2016-07-07T04:00:00+00:00 | 2017-06-21T04:00:00+00:00 |  | 2018-09-15T04:00:00+00:00 | Ameren Missouri | Audrain County | Missouri | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Spencer Creek 345 kV Substation | 100.05 | 100.05 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J659 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-04-01T04:00:00+00:00 | Entergy | Franklin Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Winnsboro to Gilbert 115 kV line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J662 | Withdrawn | 2016-07-11T04:00:00+00:00 | 2019-01-03T05:00:00+00:00 | 2018-10-09T04:00:00+00:00 | 2018-10-15T04:00:00+00:00 | Entergy | Crittenden County | Arkansas | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Marked Tree - Marion 161kV Line | 100.05 | 100.05 | Wind | Wind Turbine | Withdrawn | 2020-07-31T04:00:00+00:00 | 100.05 | 100.05 | 100.05 | 100.05
MISO | J663 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-03-20T04:00:00+00:00 | 2018-10-01T04:00:00+00:00 | Entergy | Phillips County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Robert E Ritchie 230kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2022-05-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J679 | Done | 2016-07-11T04:00:00+00:00 |  | 2018-10-12T04:00:00+00:00 | 2018-05-15T04:00:00+00:00 | Entergy | Carroll County | Mississippi | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Greenwood - Winona 115kV | 100 | 100 | Solar | Photovoltaic | In Service | 2021-04-15T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J680 | Done | 2016-07-11T04:00:00+00:00 |  | 2018-10-09T04:00:00+00:00 | 2018-04-15T04:00:00+00:00 | Entergy | Ashley County | Arkansas | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Crosset West 115kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2021-04-15T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J683 | Done | 2016-07-11T04:00:00+00:00 |  | 2018-09-11T04:00:00+00:00 | 2018-02-28T05:00:00+00:00 | Entergy | West Baton Rouge Parish | Louisiana | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Wilbert - Livonia 138kV Substation (~1.5 mi from Wilbert) | 50 | 50 | Solar | Photovoltaic | In Service | 2020-01-31T05:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J687 | Withdrawn | 2016-07-11T04:00:00+00:00 | 2017-02-17T05:00:00+00:00 |  | 2019-06-01T04:00:00+00:00 | Entergy | Orleans Parish | Louisiana | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Nasa 115kV Substation | 20 | 20 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J697 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-11-25T05:00:00+00:00 | 2022-10-15T04:00:00+00:00 | Entergy | Morehouse Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Oak Ridge 115 kV Substation | 150 | 150 | Solar | Photovoltaic | In Service | 2022-10-15T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J698 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2015-11-01T04:00:00+00:00 | Entergy | Chicot County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Lake Village Bagby 115 kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J701 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-05-06T04:00:00+00:00 | 2017-09-15T04:00:00+00:00 | ITC MIDWEST | Tuscola County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Rapson - Grasssmere - Bauer 345kV Line Tap (Kirk 345 kV Sub) | 49 | 49 | Wind | Wind Turbine | In Service | 2018-10-01T04:00:00+00:00 | 49 | 49 | 49 | 49
MISO | J703 | Done | 2016-09-08T04:00:00+00:00 |  |  | 2019-03-01T05:00:00+00:00 | American Transmission Co. LLC | Marquette County | Michigan | DPP-2016 AUG/2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Huron 138kV Substation -looping Lines FREG11 (National to Freeman) & Goose Lake (PI to Empire) | 128.1 | 128.1 | Gas | Piston (Engine), Internal Combustion (Diesel) | In Service | 2018-12-01T05:00:00+00:00 | 128.1 | 128.1 | 128.1 | 128.1
MISO | J704 | Done | 2016-09-08T04:00:00+00:00 |  |  | 2019-03-01T05:00:00+00:00 | American Transmission Co. LLC | Baraga County | Michigan | DPP-2016 AUG/2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | M38 Substation 138kV | 54.9 | 54.9 | Gas | Piston (Engine), Internal Combustion (Diesel) | In Service | 2018-12-01T05:00:00+00:00 | 54.9 | 54.9 | 54.9 | 54.9
MISO | J705 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | MINNESOTA POWER INC. | Morton County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Tri-county 230 kV substation | 100 | 100 | Wind | Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
MISO | J706 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | MINNESOTA POWER INC. | Morton County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Tri-county 230kV sub | 100 | 100 | Wind | Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
MISO | J707 | Withdrawn | 2016-09-09T04:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2020-09-23T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Barnes County | North Dakota | DPP-2017-FEB | West | GIA | Energy Resource Interconnection Service (ERIS) | Buffalo 345kV | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J708 | Withdrawn | 2016-09-09T04:00:00+00:00 | 2019-05-02T04:00:00+00:00 |  | 2022-06-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Posey County | Indiana | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | AB Brown 138 kV sub | 847 | 847 | Combined Cycle | Combined Cycle | Not Started | 2019-07-01T04:00:00+00:00 | 847 | 847 | 847 | 847
MISO | J709 | Withdrawn | 2016-09-09T04:00:00+00:00 | 2019-01-11T05:00:00+00:00 | 2018-10-17T04:00:00+00:00 | 2020-04-01T04:00:00+00:00 | SOUTH MISSISSIPPI ELECTRIC POWER ASSOCIATION | Greene County | Mississippi | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Green Substation 230kV | 100 | 100 | Solar | Photovoltaic | Withdrawn | 2020-04-01T04:00:00+00:00 | 60 | 60 | 60 | 60
MISO | J710 | Withdrawn | 2016-09-09T04:00:00+00:00 | 2018-01-24T05:00:00+00:00 | 2018-01-24T05:00:00+00:00 | 2018-06-01T04:00:00+00:00 | Entergy | Lafayette Parish | Louisiana | DPP-2017-FEB | South | GIA | Network Resource Interconnection Service (NRIS) | Duson - Scott line 69kV | 20 | 20 | Solar | Photovoltaic | Not Started | 2018-11-01T04:00:00+00:00 | 20 | 20 | 0 | 0
MISO | J711 | Withdrawn | 2016-09-09T04:00:00+00:00 | 2018-12-10T05:00:00+00:00 |  | 2020-09-23T04:00:00+00:00 | American Transmission Co. LLC | Baraga County | Michigan | DPP-2016 AUG/2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Silver River 138kV | 130 | 130 | Wind | Wind Turbine | Withdrawn | 2020-09-23T04:00:00+00:00 | 130 | 130 | 130 | 130
MISO | J712 | Withdrawn | 2016-09-09T04:00:00+00:00 | 2018-04-10T04:00:00+00:00 |  | 2020-09-20T04:00:00+00:00 | American Transmission Co. LLC | Iowa County | Wisconsin | DPP-2017-FEB | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Hill Valley 138kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J713 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | MINNESOTA POWER INC. | Oliver County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Square Butte East 230kV Substation | 300 | 300 | Wind | Wind Turbine | Not Started |  | 300 | 300 | 0 | 0
MISO | J714 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-04-17T04:00:00+00:00 |  | 2019-08-31T04:00:00+00:00 | Duke Energy Corporation | Montgomery County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Frankfurt - Cayuga 230kV line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 192 | 192 | 0 | 0
MISO | J715 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-09T05:00:00+00:00 | 2019-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Marshall County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | McLean County-Oglesby 138kV Line 1382 | 100 | 100 | Wind | Wind Turbine | In Service | 2021-05-01T04:00:00+00:00 | 98 | 98 | 98 | 98
MISO | J717 | Done | 2016-09-12T04:00:00+00:00 |  | 2019-10-08T04:00:00+00:00 | 2019-09-03T04:00:00+00:00 | METC | Isabella County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Edenville Junction to Warren 138 kV Line | 200.1 | 200.1 | Wind | Wind Turbine | In Service | 2020-06-30T04:00:00+00:00 | 200.1 | 200.1 | 200.1 | 200.1
MISO | J718 | Done | 2016-09-13T04:00:00+00:00 |  | 2020-04-21T04:00:00+00:00 | 2020-12-31T05:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Fillmore County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Cherry Grove 69kV Substation | 49.98 | 49.98 | Solar | Photovoltaic | Under Construction | 2023-09-01T04:00:00+00:00 | 49.98 | 49.98 | 45 | 45
MISO | J720 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | ITC MIDWEST | Jackson County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lakefield - Raun 345 kV line | 200 | 200 | Wind | Wind Turbine | Under Construction | 2021-09-01T04:00:00+00:00 | 200 | 200 | 0 | 0
MISO | J721 | Withdrawn | 2016-10-24T04:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Codington County,Deuel County | South Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Big Stone South substation, Big Stone City | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J722 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-10-04T04:00:00+00:00 | 2021-09-15T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Codington County,Deuel County | South Dakota | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Big Stone South 230kV Substation | 200 | 200 | Wind | Wind Turbine | Under Construction |  | 200 | 200 | 200 | 0
MISO | J725 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-02-15T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | GREAT RIVER ENERGY | Murray County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Cedar Mountain 345 kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J726 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-11-19T05:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | GREAT RIVER ENERGY | Cottonwood County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Cedar Mountain 345kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J728 | Done | 2016-11-02T04:00:00+00:00 |  | 2019-10-08T04:00:00+00:00 | 2019-09-03T04:00:00+00:00 | METC | Isabella County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Edenville Junction to Warren 138 kV Line | 200.1 | 200.1 | Wind | Wind Turbine | In Service | 2020-06-30T04:00:00+00:00 | 200.1 | 200.1 | 186.3 | 186.3
MISO | J731 | Withdrawn | 2016-11-08T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2020-09-23T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Palo Alto County | Iowa | DPP-2017-FEB | West | GIA | Energy Resource Interconnection Service (ERIS) | Kossuth-O'Brien 345kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J732 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-07-29T04:00:00+00:00 | 2021-06-08T04:00:00+00:00 | American Transmission Co. LLC | Douglas County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Arrowhead - Stone Lake 345kV Line | 527.8 | 561.5 | Combined Cycle | Combined Cycle | Under Construction | 2023-11-10T05:00:00+00:00 | 561.5 | 561.5 | 561.5 | 561.5
MISO | J733 | Withdrawn | 2016-11-08T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2020-09-23T04:00:00+00:00 | ITC MIDWEST | Franklin County | Iowa | DPP-2017-FEB | West | GIA | Energy Resource Interconnection Service (ERIS) | J416 345 kV Interconnection Facilitities to be Owned by ITCM | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J734 | Done | 2016-11-10T05:00:00+00:00 |  | 2019-02-19T05:00:00+00:00 | 2017-06-01T04:00:00+00:00 | AMEREN ILLINOIS | Ford County | Illinois | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service only for an Existing Generating Facility (NRIS-Only) | Gibson City South Substation | 57.1 | 57.1 | Gas | Combustion Turbine (Simple Cycle) | In Service | 2017-09-01T04:00:00+00:00 | 11.5 | 11.5 | 11.5 | 11.5
MISO | J739 | Withdrawn | 2016-11-11T05:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lyon County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Lyon County 345kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J740 | Withdrawn | 2016-11-11T05:00:00+00:00 | 2020-08-10T04:00:00+00:00 | 2019-03-15T04:00:00+00:00 | 2020-09-23T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,Pulaski County | Indiana | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Reynold 345kV substation | 200 | 200 | Wind | Wind Turbine | Withdrawn | 2020-10-15T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J741 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Emmons County,Logan County | North Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Wishek - Linton 115kV | 51 | 51 | Wind | Wind Turbine | Not Started |  | 50.4 | 50.4 | 0 | 0
MISO | J743 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2020-07-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Bison 345kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J745 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2021-06-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Nobles County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Nobles-Fenton 115kV | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J746 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2020-08-01T04:00:00+00:00 | GREAT RIVER ENERGY | McHenry County,McLean County,Ward County | North Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Stanton-McHenry 230kV | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J747 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2017-10-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Deuel County | South Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Brooking County - Big Stone South (J510 Tap - J630 Tap) 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J748 | Done | 2016-11-14T05:00:00+00:00 |  | 2020-03-20T04:00:00+00:00 | 2020-10-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Plymouth County | Iowa | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Highland - Raun 345kV Line Tap | 200 | 200 | Wind | Wind Turbine | In Service | 2021-10-01T04:00:00+00:00 | 200 | 200 | 200 | 175
MISO | J749 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2018-05-01T04:00:00+00:00 |  | 2018-09-01T04:00:00+00:00 | METC | Gratiot County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Redstone 138 kV Substation | 20 | 20 | Battery Storage |  | Not Started |  | 0 | 0 | 0 | 0
MISO | J750 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-01-14T05:00:00+00:00 | 2019-08-15T04:00:00+00:00 | City of Springfield, IL - CWLP | Morgan County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Westchester 138kV Substation | 150 | 150 | Wind | Wind Turbine | Under Construction | 2022-05-15T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J752 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-10-10T04:00:00+00:00 | 2020-01-02T05:00:00+00:00 | ITC MIDWEST | Tuscola County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Ringle 345kV Switchyard | 100 | 100 | Wind | Wind Turbine | In Service | 2019-10-04T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J753 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-03-08T05:00:00+00:00 | 2021-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Breckinridge County | Kentucky | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Hardinsburg Sub 161kV | 100 | 100 | Solar | Photovoltaic | Under Construction | 2021-04-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J754 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2020-09-30T04:00:00+00:00 | 2019-04-11T04:00:00+00:00 | 2019-03-08T05:00:00+00:00 | Duke Energy Corporation | Montgomery County | Indiana | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Cayuga - Nucor 345kV | 303.6 | 303.6 | Wind | Wind Turbine | Withdrawn | 2020-04-30T04:00:00+00:00 | 303.6 | 303.6 | 303.6 | 303.6
MISO | J756 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-03-26T04:00:00+00:00 | 2019-08-15T04:00:00+00:00 | AMEREN ILLINOIS | Logan County | Illinois | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Mason City to Fogarty 138kV | 202.4 | 202.4 | Wind | Wind Turbine | In Service | 2020-04-23T04:00:00+00:00 | 202.4 | 202.4 | 202.4 | 202.4
MISO | J757 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-05-31T04:00:00+00:00 | 2020-08-14T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Morgan County,Sangamon County | Illinois | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Austin-Meredosia 345kV line | 303.6 | 303.6 | Wind | Wind Turbine | In Service | 2021-10-31T04:00:00+00:00 | 303.6 | 303.6 | 303.6 | 303.6
MISO | J758 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-10-25T04:00:00+00:00 | 2018-10-01T04:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2017-FEB | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Verona-Foundry 138kV | 200 | 200 | Solar | Photovoltaic | In Service | 2022-04-08T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J759 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-02-15T05:00:00+00:00 | 2021-04-01T04:00:00+00:00 | HOOSIER ENERGY REC, INC | Spencer County | Indiana | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Troy 161kV Sub | 70 | 70 | Solar | Photovoltaic | In Service | 2020-07-02T04:00:00+00:00 | 70 | 69.9 | 70 | 69.9
MISO | J760 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-03-27T04:00:00+00:00 | 2019-04-08T04:00:00+00:00 | American Transmission Co. LLC | Rock County | Wisconsin | DPP-2017-FEB | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | New Kitty Hawk 345kV substation | 30 | 30 | Gas | Combustion Turbine (Simple Cycle) | In Service |  | 30 | 30 | 30 | 30
MISO | J761 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | ITC MIDWEST | Faribault County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Huntley 345 kV sub | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J762 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-03-08T05:00:00+00:00 | 2021-04-01T04:00:00+00:00 | BIG RIVERS ELECTRIC CORPORATION | Meade County | Kentucky | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Meade Sub 161kV | 200 | 200 | Solar | Photovoltaic | Under Construction | 2021-04-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J766 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2018-01-01T05:00:00+00:00 | MINNESOTA POWER INC. | Oliver County | North Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Square Butte 230kV Substation | 3.84 | 3.84 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J767 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2019-01-01T05:00:00+00:00 | ITC MIDWEST | Hancock County | Iowa | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Lime Creek 161 kV substation | 12 | 12 | Wind | Wind Turbine | Not Started |  | 12 | 12 | 0 | 0
MISO | J768 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2019-01-01T05:00:00+00:00 | ITC MIDWEST | Story County | Iowa | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Story County Substation | 12 | 12 | Wind | Wind Turbine | Not Started |  | 12 | 12 | 0 | 0
MISO | J769 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2019-07-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Renville County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Kingman Run-Bird Island 69kV | 33 | 33 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J770 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2019-07-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Renville County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Bird Island to Henryville Tap 69kV Line | 90 | 90 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J771 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2019-07-31T04:00:00+00:00 | GREAT RIVER ENERGY | Stearns County | Minnesota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Lake Koronis-Paynesville 69kV | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J776 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2019-11-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Franklin County | Iowa | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Black Hawk-Killdeer 345kV | 99 | 99 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J777 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2019-11-01T04:00:00+00:00 | ITC MIDWEST | Franklin County | Iowa | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Whispering Willow 161kV substation | 99 | 99 | Wind | Wind Turbine | Not Started |  | 99 | 99 | 0 | 0
MISO | J779 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-08-09T04:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Emmons County,Logan County | North Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Bismarck-Linton 115kV | 51 | 51 | Wind | Wind Turbine | Not Started |  | 50.4 | 50.4 | 0 | 0
MISO | J780 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2019-04-09T04:00:00+00:00 |  | 2020-12-15T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Sheridan County | North Dakota | DPP-2017-FEB | West | GIA | Network Resource Interconnection Service (NRIS) | Harvey - Underwood 230kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J782 | Withdrawn | 2016-11-14T05:00:00+00:00 | 2018-05-31T04:00:00+00:00 |  | 2021-04-01T04:00:00+00:00 | Ameren Missouri | Stoddard County | Missouri | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Stoddart sub 161kV | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J783 | Done | 2016-11-14T05:00:00+00:00 |  | 2019-07-24T04:00:00+00:00 | 2021-04-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Spencer County | Indiana | DPP-2017-FEB | Central | Phase 3 | Network Resource Interconnection Service (NRIS) | Grandview Sub | 70 | 70 | Solar | Photovoltaic | Under Construction | 2021-04-01T04:00:00+00:00 | 70 | 69.9 | 70 | 69.9
MISO | J785 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | ITC MIDWEST | Jackson County,Martin County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lakefield Junction - Huntley 345 kV line (Tap) | 105 | 105 | Wind | Wind Turbine | Not Started |  | 105 | 105 | 0 | 0
MISO | J793 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-10-26T04:00:00+00:00 | 2021-05-14T04:00:00+00:00 | ITC MIDWEST | St. Clair County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Belle River - Fitz #2 345 kV Line Tap | 1175 | 1175 | Combined Cycle | Combined Cycle | In Service | 2021-05-14T04:00:00+00:00 | 1209 | 1209 | 1209 | 1175
MISO | J794 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-06-18T04:00:00+00:00 | 2018-09-10T04:00:00+00:00 | METC | Gratiot County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | J589 138kV Substation (Regal - Summerton 138kV Line) | 12.5 | 12.5 | Wind | Wind Turbine | In Service | 2018-10-26T04:00:00+00:00 | 12.5 | 12.5 | 12.5 | 12.5
MISO | J795 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | Southern Illinois Power Cooperative | Gallatin County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Gallatin Junction 161 kV Substation | 69 | 69 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J796 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-06-12T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | METC | Shiawassee County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Goss 138kV Substation | 239 | 239 | Solar | Photovoltaic | In Service | 2020-11-20T05:00:00+00:00 | 239 | 239 | 239 | 239
MISO | J797 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-05-30T04:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Washington County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Ashley 138 kV Substation | 70 | 70 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J798 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | American Transmission Co. LLC | Walworth County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | University - Mukwanago UNIG52 Line Tap | 124 | 124 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J799 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-05-13T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Milan - Pioneer 120kV Line Tap | 189 | 189 | Solar | Photovoltaic | Under Construction | 2021-11-11T05:00:00+00:00 | 189 | 189 | 189 | 189
MISO | J800 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-22T04:00:00+00:00 | 2020-09-30T04:00:00+00:00 | AMEREN ILLINOIS | White County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Crossville West Substation 138kV Bus - Albion South - Norris City 138 kV Line | 250 | 250 | Solar | Photovoltaic | Under Construction | 2022-10-01T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J801 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2020-09-01T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Pierce County | Wisconsin | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Crystal Cave-Rock Elm 161kV line tap | 74 | 74 | Solar | Photovoltaic | Under Construction | 2023-11-10T05:00:00+00:00 | 74 | 74 | 74 | 0
MISO | J802 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-05-22T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | Duke Energy Corporation | Vermillion County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Cayuga 345 kV Substation | 1244 | 1244 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J803 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2023-04-25T04:00:00+00:00 | 2021-05-19T04:00:00+00:00 | 2019-10-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lyon County | Minnesota | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Tracy 69 kV line | 32.5 | 32.5 | Solar | Photovoltaic | Withdrawn | 2023-11-01T04:00:00+00:00 | 32.5 | 0 | 32.5 | 0
MISO | J804 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-04-16T04:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | HOOSIER ENERGY REC, INC | Decatur County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Decatur 138kV Substation | 119 | 119 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J805 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-05-08T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | Duke Energy Corporation | Shelby County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Gwynneville 345kV Substation | 199 | 199 | Solar | Photovoltaic | Under Construction | 2022-05-01T04:00:00+00:00 | 199 | 199 | 199 | 199
MISO | J806 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-05-11T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Rice Creek - Vrooman 138kV Line Tap | 149 | 149 | Solar | Photovoltaic | In Service | 2021-06-01T04:00:00+00:00 | 149 | 149 | 149 | 149
MISO | J807 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-05-26T04:00:00+00:00 | 2019-10-17T04:00:00+00:00 | 2020-09-15T04:00:00+00:00 | American Transmission Co. LLC | Lafayette County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Darlington - Hillman 138kV Line (Falcon Substation J395) | 41.4 | 41.4 | Wind | Wind Turbine | Withdrawn | 2021-08-27T04:00:00+00:00 | 41.4 | 41.4 | 41.4 | 41.4
MISO | J808 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-05-06T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Randolph County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Aster Substation 138kV Bus | 99 | 99 | Solar | Photovoltaic | In Service | 2020-07-01T04:00:00+00:00 | 99 | 99 | 99 | 99
MISO | J809 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | METC | Ottawa County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Bass Creek - Black River 138 kV Line Tap | 99 | 99 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J810 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-08-31T04:00:00+00:00 |  | 2023-04-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Audubon County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Atlantic to Adair 161 kV line | 139.6 | 145.5 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J811 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-03-25T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Fayette County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Ramsey East 138kV Substation | 99 | 99 | Solar | Photovoltaic | In Service | 2021-05-28T04:00:00+00:00 | 99 | 99 | 99 | 99
MISO | J812 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-10-26T04:00:00+00:00 |  | 2017-06-16T04:00:00+00:00 | METC | Van Buren County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Covert - Palisades 345kV Line | 1108 | 1217 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J813 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-16T05:00:00+00:00 | 2020-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Clay County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Louisville South Substation 138kV Line | 275 | 275 | Solar | Photovoltaic | Under Construction | 2021-10-29T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J814 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-02-04T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Clark County | Wisconsin | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Eau Claire - Arpin 345kV Line | 99.9 | 99.9 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J815 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-16T04:00:00+00:00 | 2020-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Christian County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Taylorville South-Austin (formerly Pawnee)138kV Line | 250 | 250 | Solar | Photovoltaic | Under Construction | 2022-10-28T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J816 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2022-09-15T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Cass County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Buffalo 115kV Substation | 60 | 60 | Solar | Photovoltaic | Not Started |  | 60 | 60 | 0 | 0
MISO | J817 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-17T05:00:00+00:00 | 2019-09-01T04:00:00+00:00 | Ameren Missouri | Warren County | Missouri | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Warrenton 161kV Substation | 139 | 139 | Solar | Photovoltaic | Under Construction | 2021-10-29T04:00:00+00:00 | 139 | 139 | 139 | 139
MISO | J818 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-05-06T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | American Transmission Co. LLC | Jefferson County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Jefferson 138kV Substation | 149 | 149 | Solar | Photovoltaic | Under Construction | 2022-04-01T04:00:00+00:00 | 149 | 149 | 149 | 149
MISO | J819 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-05-26T04:00:00+00:00 | 2020-05-20T04:00:00+00:00 | 2020-09-15T04:00:00+00:00 | American Transmission Co. LLC | Lafayette County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Darlington 138kV Substation | 99.9 | 99.9 | Wind | Wind Turbine | Withdrawn | 2021-09-01T04:00:00+00:00 | 99.9 | 99.9 | 99.9 | 99.9
MISO | J820 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-08-03T04:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | METC | Eaton County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Oneida 345kV Substation | 100.05 | 100.05 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J821 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-05-26T04:00:00+00:00 | 2019-10-17T04:00:00+00:00 | 2020-09-15T04:00:00+00:00 | American Transmission Co. LLC | Marathon County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Wein - Stratford 115 kV Line Tap | 99.9 | 99.9 | Wind | Wind Turbine | Withdrawn | 2021-08-27T04:00:00+00:00 | 99.9 | 99.9 | 99.9 | 99.9
MISO | J822 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2019-01-30T05:00:00+00:00 | Entergy | Lonoke County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Lynch SES Switchyard - Carlisle 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J823 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-02-06T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | ITC MIDWEST | Clark County | Missouri | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Twin Rivers - Twin Rivers Tap - Palmyra 161kV Line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J824 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-04-17T04:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | Duke Energy Corporation | Sullivan County,Vigo County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Vigo-Farmersburg Junction 138kV Line | 245 | 245 | Solar | Photovoltaic | Not Started |  | 150 | 150 | 0 | 0
MISO | J825 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | American Transmission Co. LLC | Green County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | North Monroe - Albany 138kV Line | 99.9 | 99.9 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J826 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-17T05:00:00+00:00 | 2020-09-01T04:00:00+00:00 | AMEREN ILLINOIS | McLean County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Weedman Substation 138kV Bus | 100 | 100 | Wind | Wind Turbine | In Service | 2021-05-28T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J827 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | Duke Energy Corporation | Fountain County,Montgomery County,Tippecanoe County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Lafayette - Veedsburg West - Attica 230kV Line | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J828 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-02-07T05:00:00+00:00 |  | 2020-08-01T04:00:00+00:00 | Duke Energy Corporation | Montgomery County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Crawfordsville - Linden Tap 138kV Line | 151.8 | 151.8 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J829 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-05-26T04:00:00+00:00 | 2020-09-30T04:00:00+00:00 | Duke Energy Corporation | Sullivan County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Dresser - Merom 345kV Line | 250 | 250 | Solar | Photovoltaic | Under Construction | 2022-09-01T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J830 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-03-05T05:00:00+00:00 | 2020-06-01T04:00:00+00:00 | Entergy | Madison County | Mississippi | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Canton South to Hoy Road 230 kV Line | 100 | 100 | Solar | Photovoltaic | Under Construction | 2021-11-15T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J831 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-11-12T05:00:00+00:00 | 2017-06-16T04:00:00+00:00 | American Transmission Co. LLC | Ozaukee County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Port Washington Generating Switchyard 138 kV | 40 | 48 | Combined Cycle | Combined Cycle | In Service | 2019-10-28T04:00:00+00:00 | 48 | 48 | 48 | 48
MISO | J832 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-06-02T04:00:00+00:00 | 2020-06-12T04:00:00+00:00 | 2020-04-01T04:00:00+00:00 | METC | Cheboygan County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Port Calcite - Riggsville 138kV Line | 100 | 100 | Solar | Photovoltaic | Withdrawn | 2022-12-31T05:00:00+00:00 | 91 | 91 | 91 | 91
MISO | J833 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-10-22T04:00:00+00:00 | 2020-06-17T04:00:00+00:00 | 2020-04-01T04:00:00+00:00 | ITC MIDWEST | Washtenaw County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Milan-Pioneer 120kV line tap | 100 | 100 | Solar | Photovoltaic | Withdrawn | 2022-04-29T04:00:00+00:00 | 50 | 50 | 50 | 50
MISO | J834 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-03-06T05:00:00+00:00 | 2020-09-01T04:00:00+00:00 | Entergy | Phillips County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Robert E Ritchie 230kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2021-11-15T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J835 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-04-17T04:00:00+00:00 |  | 2020-07-01T04:00:00+00:00 | AMEREN ILLINOIS | Morgan County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Meredosia - Austin 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J836 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2021-11-01T04:00:00+00:00 | ITC MIDWEST | Kossuth County | Iowa | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Ledyard 345kV Substation | 200 | 200 | Wind | Wind Turbine | In Service | 2022-09-30T04:00:00+00:00 | 200 | 0 | 200 | 0
MISO | J837 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-10-21T04:00:00+00:00 | 2020-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Reynolds 345kV Substation | 200.1 | 200.1 | Wind | Wind Turbine | In Service | 2021-08-15T04:00:00+00:00 | 200.1 | 80 | 200.1 | 80
MISO | J838 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-10-21T04:00:00+00:00 | 2020-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Reynolds 345kV Substation | 200.1 | 200.1 | Wind | Wind Turbine | In Service | 2021-08-15T04:00:00+00:00 | 100 | 40 | 100 | 40
MISO | J839 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-05-27T04:00:00+00:00 |  | 2020-04-01T04:00:00+00:00 | ITC MIDWEST | Lapeer County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Otsego Tap - Otsego 120 kV Line Tap | 100 | 100 | Solar | Photovoltaic | Withdrawn | 2023-03-31T04:00:00+00:00 | 58 | 58 | 58 | 58
MISO | J840 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-07-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Humboldt County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Kossuth - Webster 345 kV Line | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
MISO | J841 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-01-24T05:00:00+00:00 |  | 2020-04-01T04:00:00+00:00 | METC | Saginaw County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Orr RD 138 kV Substation | 702 | 725 | Combined Cycle | Combined Cycle | Not Started |  | 725 | 725 | 725 | 702
MISO | J842 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-02-10T05:00:00+00:00 |  | 2020-07-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Gibson County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Gibson - Brown 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started | 2022-09-14T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J843 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-02-10T05:00:00+00:00 |  | 2020-07-01T04:00:00+00:00 | Duke Energy Corporation | Gibson County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Gibson - Francisco 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started | 2021-09-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J844 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-10T05:00:00+00:00 | 2020-09-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Knox County | Illinois | DPP-2017-AUG | Central | GIA | Energy Resource Interconnection Service (ERIS) | Sandburg Substation 138kV Bus | 300 | 300 | Wind | Wind Turbine | Under Construction | 2021-05-28T04:00:00+00:00 | 147 | 0 | 147 | 0
MISO | J845 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-06T05:00:00+00:00 | 2020-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Ford County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Gibson City South - Paxton East 138kV Line | 120 | 120 | Wind | Wind Turbine | In Service | 2021-06-01T04:00:00+00:00 | 120 | 52 | 120 | 52
MISO | J846 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2020-04-01T04:00:00+00:00 | METC | Hillsdale County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Moore Roadtyd - Coldwater Creek 138 kV Line Tap | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J847 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-09-17T04:00:00+00:00 | 2020-04-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Schahfer Tap 138kV Substation | 90 | 90 | Solar | Photovoltaic | Under Construction | 2021-04-01T04:00:00+00:00 | 90 | 90 | 90 | 90
MISO | J848 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-17T04:00:00+00:00 | 2020-09-30T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Christian County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Pana Substation 138kV Bus | 250 | 250 | Wind | Wind Turbine | Under Construction | 2021-05-28T04:00:00+00:00 | 250 | 250 | 235 | 235
MISO | J849 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2022-04-19T04:00:00+00:00 | 2019-06-26T04:00:00+00:00 | 2020-04-01T04:00:00+00:00 | American Transmission Co. LLC | Delta County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Chandler 138 kV Substation | 125 | 125 | Solar | Photovoltaic | Withdrawn | 2022-04-01T04:00:00+00:00 | 125 | 125 | 125 | 125
MISO | J850 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-24T04:00:00+00:00 | 2021-09-30T04:00:00+00:00 | American Transmission Co. LLC | Rock County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | RCEC Bradford - W. Darien 138kV Line | 250 | 250 | Solar | Photovoltaic | Under Construction | 2022-09-24T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J851 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2019-10-01T04:00:00+00:00 | Duke Energy Corporation | Henry County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Fall Creek - New Castle 138kV Line | 50 | 50 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J852 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-07-01T04:00:00+00:00 | Entergy | Ouachita Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Rilla - Riverton 115kV Line Tap | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J853 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-20T05:00:00+00:00 | 2019-09-01T04:00:00+00:00 | AMEREN ILLINOIS | White County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Norris City North Substation 138kV Bus | 149 | 149 | Solar | Photovoltaic | In Service | 2021-05-28T04:00:00+00:00 | 149 | 149 | 149 | 149
MISO | J854 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-08-08T04:00:00+00:00 |  | 2019-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Randolph County | Illinois | DPP-2017-AUG | Central | GIA | Energy Resource Interconnection Service (ERIS) | Baldwin 138KV Substation | 30 | 30 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J855 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-11-14T05:00:00+00:00 | 2019-08-01T04:00:00+00:00 | American Transmission Co. LLC | Grant County,Iowa County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Lancaster - Eden 138 kV Line Tap | 100 | 100 | Wind | Wind Turbine | Under Construction | 2020-11-06T05:00:00+00:00 | 100 | 100 | 99.99 | 99.99
MISO | J856 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2023-03-07T05:00:00+00:00 | 2019-11-15T05:00:00+00:00 | 2021-04-01T04:00:00+00:00 | Southern Indiana Gas & Electric Company d/b/a Vectren Energy Delivery of Indiana, Inc. | Vanderburgh County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Scott (TWP 138/69) 138 kV Substation | 80 | 80 | Solar | Photovoltaic | Withdrawn | 2021-03-15T04:00:00+00:00 | 80 | 80 | 80 | 80
MISO | J857 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-06-10T04:00:00+00:00 | 2019-09-01T04:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Verona - Foundry 138 kV Line Tap | 124.95 | 124.95 | Solar | Photovoltaic | Under Construction | 2022-02-07T05:00:00+00:00 | 124.95 | 124.95 | 124.95 | 124.95
MISO | J858 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-09-01T04:00:00+00:00 |  | 2019-09-29T04:00:00+00:00 | Entergy | Bradley County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Hilo 115 kV Switch | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J859 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-01-23T05:00:00+00:00 | 2019-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Cass County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Frederick North - Meredosia East 138kV Line | 149.94 | 149.94 | Solar | Photovoltaic | Under Construction | 2022-05-31T04:00:00+00:00 | 149.94 | 149.94 | 149.94 | 149.94
MISO | J860 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-03-30T04:00:00+00:00 | Entergy | Jefferson Davis Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | New Jefferson Davis 138 kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J861 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-05-22T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | American Transmission Co. LLC | Marquette County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Dead River - Arnold 345 kV Line | 99.96 | 99.96 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J862 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-03-25T04:00:00+00:00 |  | 2019-05-31T04:00:00+00:00 | Entergy | Orleans Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | NASA-Michoud 115 kV Line | 20 | 20 | Solar | Photovoltaic | Not Started |  | 20 | 20 | 0 | 0
MISO | J863 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-12-18T05:00:00+00:00 |  | 2021-01-01T05:00:00+00:00 | NORTHERN STATES POWER COMPANY | Dakota County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Rosemount - Nininger 115kV Line | 220 | 220 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J864 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-27T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | American Transmission Co. LLC | Richland County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Lone Rock 69kV Substation | 49.98 | 49.98 | Solar | Photovoltaic | In Service | 2022-09-01T04:00:00+00:00 | 49.98 | 49.98 | 49.98 | 49.98
MISO | J865 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | ITC MIDWEST | St. Clair County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Lee - Menlo 120kV Line | 79.97 | 79.97 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J866 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-06T04:00:00+00:00 | 2020-03-30T04:00:00+00:00 | Entergy | Tunica County | Mississippi | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Batesville - Robert E. Ritchie 230 kV line | 200 | 200 | Wind | Wind Turbine | Under Construction | 2021-07-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J867 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-09-29T04:00:00+00:00 | Entergy | Polk County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Gulf Livingston - SHECO Menard | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J868 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-03-05T05:00:00+00:00 |  | Entergy | Concordia Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Plantation 115 kV Substation | 37.2 | 37.2 |  |  | Under Construction | 1990-12-03T05:00:00+00:00 | 0 | 25.33 | 0 | 23.5
MISO | J869 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | GREAT RIVER ENERGY | Sherburne County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Cable - Cable Tap 69kV Substation | 49.98 | 49.98 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J870 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-02-21T05:00:00+00:00 | 2021-09-10T04:00:00+00:00 | American Transmission Co. LLC | Grant County,Iowa County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Eden - Wyoming Valley 138kV Line Tap | 200 | 200 | Solar | Photovoltaic | In Service | 2020-08-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J871 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-02-21T05:00:00+00:00 | 2021-09-10T04:00:00+00:00 | American Transmission Co. LLC | Grant County,Iowa County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Eden - Wyoming Valley 138kV Line Tap | 100 | 100 | Solar | Photovoltaic | Under Construction | 2021-08-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J872 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Macon County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Blue Mount tap on the Pana-Route 51D-1462 138kV line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J873 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-07-01T04:00:00+00:00 | ITC MIDWEST | Hardin County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Killdeer- Blackhawk 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J874 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2021-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Murray County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Fenton - Chanarambie 115kV Line | 150 | 150 | Solar | Photovoltaic | Under Construction | 2024-07-30T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J875 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-08-06T04:00:00+00:00 | 2020-09-10T04:00:00+00:00 | METC | Lenawee County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Par - Raisin Road 138kV Line | 150 | 150 | Solar | Photovoltaic | Under Construction | 2022-11-18T05:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J876 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-07-23T04:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | ITC MIDWEST | Faribault County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Huntley 345kV sub | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J877 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-05-19T04:00:00+00:00 | 2021-09-30T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Palo Alto County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Obrien - Kossuth 345kV Line (J529 & J590 New Substation) | 250 | 250 | Solar | Photovoltaic | Under Construction | 2023-07-01T04:00:00+00:00 | 250 | 250 | 250 | 250
MISO | J878 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-28T04:00:00+00:00 | 2021-09-10T04:00:00+00:00 | American Transmission Co. LLC | Kenosha County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Paris 138kV Substation | 200 | 200 | Solar | Photovoltaic | Under Construction | 2022-09-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J879 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-05-11T04:00:00+00:00 |  | 2020-09-23T04:00:00+00:00 | American Transmission Co. LLC | Baraga County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | North Lake 138 kV Substation | 70 | 70 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J880 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Ward County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Magic City 230kV sub | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J881 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-07-17T04:00:00+00:00 |  | 2019-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Jasper County | Illinois | DPP-2017-AUG | Central | GIA | Energy Resource Interconnection Service (ERIS) | Newton 138kV Substation | 45 | 45 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J882 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-08-08T04:00:00+00:00 |  | 2019-04-01T04:00:00+00:00 | AMEREN ILLINOIS | Montgomery County | Illinois | DPP-2017-AUG | Central | GIA | Energy Resource Interconnection Service (ERIS) | Coffeen North 138kV Substation | 15 | 15 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J883 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-12-04T05:00:00+00:00 | 2019-12-04T05:00:00+00:00 | 2020-10-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Pulaski County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Monticello-East Winamac | 80 | 80 | Wind | Wind Turbine | Withdrawn | 2022-05-01T04:00:00+00:00 | 80 | 80 | 80 | 80
MISO | J884 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-12-18T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | AMEREN ILLINOIS | McLean County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Brokaw - Gibson City South 138 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started | 2021-05-28T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J885 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | ITC MIDWEST | Worth County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | J407 Glenworth 161kV Substation | 64 | 64 | Wind | Wind Turbine | Not Started |  | 64 | 64 | 0 | 0
MISO | J886 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-11-25T05:00:00+00:00 | 2020-09-15T04:00:00+00:00 | American Transmission Co. LLC | Manitowoc County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Kewaunee 138 kV Substation | 150 | 150 | Solar | Photovoltaic | In Service | 2020-08-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J887 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | AMEREN ILLINOIS | Knox County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | G545 138kV Substation | 75 | 75 | Wind | Wind Turbine | Not Started | 2019-09-15T04:00:00+00:00 | 0 | 0 | 0 | 0
MISO | J888 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-08-19T04:00:00+00:00 | 2019-01-01T05:00:00+00:00 | SOUTH MISSISSIPPI ELECTRIC POWER ASSOCIATION | George County | Mississippi | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Benndale 69kV Substation | 25 | 25 | Gas | Combustion Turbine (Simple Cycle) | In Service | 2019-07-22T04:00:00+00:00 | 25 | 25 | 25 | 25
MISO | J889 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | GREAT RIVER ENERGY | Nelson County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Ramsey - Prairie 230KV Line Tap | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J890 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | METC | Presque Isle County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Port Calcite - Riggsville 138kV Line | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J891 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-07-23T04:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Pipestone County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Buffalo Ridge - Pipestone 115kV Line Tap | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J892 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-03-12T04:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | American Transmission Co. LLC | Walworth County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Bluff Creek (Tap) to Sugar Creek 138 kV line tap | 74.97 | 74.97 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J893 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-11-20T05:00:00+00:00 | 2021-08-01T04:00:00+00:00 | Entergy | White County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Searcy Price Sub 161kV | 100 | 100 | Solar | Photovoltaic | In Service | 2021-08-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J894 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-04-01T04:00:00+00:00 | Entergy | Woodruff County | Arkansas | DPP-2017-AUG | South | GIA | Energy Resource Interconnection Service (ERIS) | McCrory - Moses 161kV Substation | 45 | 45 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J895 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-04-01T04:00:00+00:00 | Entergy | Lonoke County | Arkansas | DPP-2017-AUG | South | GIA | Energy Resource Interconnection Service (ERIS) | Carlisle - Lonoke East 115kV Line Tap | 33 | 33 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J896 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-06-18T04:00:00+00:00 |  | 2019-10-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Crawford County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Victory 161 kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J897 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2023-07-17T04:00:00+00:00 | 2022-08-03T04:00:00+00:00 | 2021-10-01T04:00:00+00:00 | GREAT RIVER ENERGY | Grand Forks County | North Dakota | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Prairie - Ramsey 230 kV line | 190 | 190 | Wind | Wind Turbine | Withdrawn | 2024-10-01T04:00:00+00:00 | 190 | 190 | 190 | 0
MISO | J898 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-09-26T04:00:00+00:00 | 2021-10-01T04:00:00+00:00 | DAIRYLAND POWER COOPERATIVE | Howard County | Iowa | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Rice - Beaver Creek 161kV line tap | 100 | 100 | Wind | Wind Turbine | Under Construction | 2023-11-30T05:00:00+00:00 | 100 | 100 | 100 | 0
MISO | J899 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-03-25T04:00:00+00:00 |  | 2019-10-15T04:00:00+00:00 | Entergy | Carroll County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Green Forest South - Harrison West 161kV | 180 | 180 | Wind | Wind Turbine | Not Started |  | 180 | 180 | 0 | 0
MISO | J900 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | Entergy | Livingston Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Coly - Vignes 230kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J901 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-05-26T04:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Redwood County | Minnesota | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Lyon County - Cedar Mountain Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 200 | 0
MISO | J902 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-09-01T04:00:00+00:00 | Entergy | Ashley County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | AECC Mist to Montrose 115 kV line | 99.96 | 99.96 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J903 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-06T05:00:00+00:00 | 2020-09-15T04:00:00+00:00 | Duke Energy Corporation | Henry County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Greensboro 138 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2023-05-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J904 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | Entergy | Ashley County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Hamburg - Mist 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J905 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Pipestone County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Buffalo Ridge 115kV Substation | 40 | 40 | Solar | Photovoltaic | Not Started |  | 40 | 40 | 0 | 0
MISO | J906 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-02-07T05:00:00+00:00 |  | 2020-07-01T04:00:00+00:00 | METC | Muskegon County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Kenowa - Ludington 345 kV Line Tap | 100 | 100 | Wind | Wind Turbine | Withdrawn |  | 100 | 100 | 100 | 100
MISO | J907 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-03-24T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 | Entergy | Monroe County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Brinkley East - Aubrey 230 kV Line | 200 | 200 | Solar | Photovoltaic | Under Construction | 2022-06-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J908 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-03-04T05:00:00+00:00 | 2021-09-01T04:00:00+00:00 | Entergy | Tallahatchie County | Mississippi | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Webb 115kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2023-06-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J909 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-11-22T05:00:00+00:00 | 2021-09-01T04:00:00+00:00 | Entergy | Tangipahoa Parish | Louisiana | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Amite 115 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2022-02-15T05:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J910 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | Entergy | Hinds County | Mississippi | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Clinton Industrial 230kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J911 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | Entergy | Montgomery County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Porter 230kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J912 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-16T04:00:00+00:00 | 2020-09-15T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Christian County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Pana Substation 138kV Bus | 100 | 100 | Solar | Photovoltaic | Under Construction | 2023-09-15T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J913 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-03T05:00:00+00:00 | 2020-08-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | White County | Indiana | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Reynolds 345kV Substation | 200 | 200 | Solar | Photovoltaic | In Service | 2022-08-15T04:00:00+00:00 | 200 | 160 | 200 | 160
MISO | J914 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2019-10-01T04:00:00+00:00 | METC | Manistee County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Filer City 138 kV Substation | 30 | 30 | Gas | Combustion Turbine (Simple Cycle) | Not Started |  | 0 | 0 | 0 | 0
MISO | J915 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | Entergy | Liberty County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Parkway - East Gate 138kV line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J916 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2020-07-06T04:00:00+00:00 | ITC MIDWEST | Cottonwood County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Mountain Lake 69kV Substation | 2 | 2 | Diesel | Combustion Turbine (Simple Cycle) | Not Started |  | 2 | 2 | 0 | 0
MISO | J917 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-11-01T04:00:00+00:00 | Entergy | Liberty County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Tarkington - New Long John 138kV line tap | 78 | 78 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J919 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-11-21T05:00:00+00:00 | 2021-08-01T04:00:00+00:00 | Entergy | Jackson County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Cash - Newport AB 161 kV Line Tap | 180 | 180 | Solar | Photovoltaic | Under Construction | 2022-02-02T05:00:00+00:00 | 180 | 180 | 180 | 180
MISO | J920 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-08-29T04:00:00+00:00 |  | 2019-08-31T04:00:00+00:00 | AMEREN ILLINOIS | Pulaski County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Joppa 161 kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J921 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-04-23T04:00:00+00:00 |  | 2019-07-01T04:00:00+00:00 | METC | Ionia County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Thompson Road 138 kV Substation | 146.7 | 146.7 | Wind | Wind Turbine | Not Started |  | 146.7 | 146.7 | 0 | 0
MISO | J922 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-06-30T04:00:00+00:00 | Entergy | Chicot County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Lake Village Bagby - Chicot 115kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J923 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | Entergy | Montgomery County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Porter 230kV Substation | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J924 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-08T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | Entergy | Monroe County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Brinkley East - Aubrey 230 kV line | 50 | 50 | Battery Storage | Battery Storage | Not Started |  | 0 | 0 | 0 | 0
MISO | J925 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-04-24T04:00:00+00:00 |  | 2019-06-30T04:00:00+00:00 | METC | Shiawassee County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | North Cournna - Bell Road 138 kV line | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J926 | Done | 2017-06-16T04:00:00+00:00 |  | 2021-06-03T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Saint Croix County | Wisconsin | DPP-2017-AUG | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Pine Lake - Apple River 161 kV Line | 101.28 | 101.28 | Solar | Photovoltaic | Under Construction | 2023-09-15T04:00:00+00:00 | 101.28 | 101.28 | 101.28 | 0
MISO | J927 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-10-01T04:00:00+00:00 | ITC MIDWEST | Faribault County,Freeborn County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Walters 69 kV Substation | 100 | 100 | Wind | Wind Turbine | Not Started |  | 100 | 100 | 0 | 0
MISO | J928 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-04-19T04:00:00+00:00 | 2019-08-15T04:00:00+00:00 | American Transmission Co. LLC | Delta County,Schoolcraft County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Garden Corners 138 kV Substation | 79.99 | 79.99 | Wind | Wind Turbine | In Service | 2019-10-01T04:00:00+00:00 | 79.99 | 79.99 | 79.99 | 79.99
MISO | J929 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-10-24T04:00:00+00:00 |  | 2021-06-30T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | McIntosh County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Wishek 41.6 kV Substation | 25 | 25 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J930 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-11-16T05:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Sioux County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Boyden - Sheldon 69kV line | 38 | 38 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J931 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-04-23T04:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | METC | Ottawa County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Kenowa 345kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
MISO | J932 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | Entergy | Liberty County | Texas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Porter - China 230 kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J933 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-01-29T05:00:00+00:00 |  | 2021-09-15T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Day County | South Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Ellendale - Big Stone South 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J934 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-02-28T05:00:00+00:00 | 2021-09-01T04:00:00+00:00 | Entergy | Crittenden County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Kuhn 161kV Substation | 200 | 200 | Solar | Photovoltaic | Under Construction | 2022-06-01T04:00:00+00:00 | 180 | 180 | 180 | 180
MISO | J935 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-02-04T05:00:00+00:00 |  | 2020-09-15T04:00:00+00:00 | MINNESOTA POWER INC. | Hubbard County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Hubbard - Badoura 230kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J936 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-09T05:00:00+00:00 |  | 2020-05-01T04:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Argenta - Tompkins 345kV Line Tap | 507 | 535 | Combined Cycle | Combined Cycle | Not Started |  | 0 | 0 | 0 | 0
MISO | J937 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2020-10-21T04:00:00+00:00 | 2020-06-11T04:00:00+00:00 | 2020-05-01T04:00:00+00:00 | METC | Calhoun County | Michigan | DPP-2017-AUG | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Argenta - Tompkins 345kV Line Tap | 507 | 535 | Combined Cycle | Combined Cycle | Withdrawn | 2022-12-29T05:00:00+00:00 | 535 | 535 | 535 | 507
MISO | J938 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2017-10-09T04:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Palo Alto County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Emmestburg - Freedom 69kV Line | 50 | 50 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J939 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-10-12T04:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Wright County | Iowa | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Clarion-Eagle Grove 69kV line | 38 | 38 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J940 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-02-06T05:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Burleigh County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Jamestown - Center 345kV Line | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J941 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2018-11-01T04:00:00+00:00 |  | 2020-07-01T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Grant County | South Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Big Stone-Brookings County 345KV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J942 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-03-25T04:00:00+00:00 |  | 2021-08-01T04:00:00+00:00 | Entergy | Craighead County | Arkansas | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Cash - Newport AB 161kV Line Tap | 107 | 107 | Solar | Photovoltaic | Not Started |  | 107 | 107 | 0 | 0
MISO | J943 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-03-12T04:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lincoln County | Minnesota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | J460 substation on the Brookings - H081 345kV Line | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J944 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-17T05:00:00+00:00 | 2021-09-01T04:00:00+00:00 | Entergy | New Madrid County | Missouri | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Portageville - New Madrid 161kV Line | 200 | 200 | Solar | Photovoltaic | Under Construction | 2022-10-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J945 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2019-09-15T04:00:00+00:00 | Entergy | Washington County | Mississippi | DPP-2017-AUG | South | GIA | Network Resource Interconnection Service (NRIS) | Gerald Andrus - Clinton Industrial 230 kV Line | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J946 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2021-05-26T04:00:00+00:00 |  | 2020-07-31T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Cass County | North Dakota | DPP-2017-AUG | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Bison 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 200 | 200 | 200 | 200
MISO | J947 | Done | 2017-06-16T04:00:00+00:00 |  | 2020-04-17T04:00:00+00:00 | 2019-09-15T04:00:00+00:00 | American Transmission Co. LLC | Grant County | Wisconsin | DPP-2017-AUG | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Potosis - Hillman 138kV Line | 200 | 200 | Solar | Photovoltaic | In Service | 2023-07-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J948 | Withdrawn | 2017-06-16T04:00:00+00:00 | 2019-01-07T05:00:00+00:00 |  | 2020-06-01T04:00:00+00:00 | Entergy | Poinsett County | Arkansas | DPP-2017-AUG | South | GIA | Energy Resource Interconnection Service (ERIS) | Harrisburg Tap - Harrisburg 161kV Line | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J949 | Done | 2017-06-16T04:00:00+00:00 |  | 2019-12-10T05:00:00+00:00 | 2020-08-31T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Coles County | Illinois | DPP-2017-AUG | Central | GIA | Network Resource Interconnection Service (NRIS) | Kansas Substation 138kV Bus #3 | 200 | 200 | Solar | Photovoltaic | In Service | 2020-10-31T04:00:00+00:00 | 200 | 170 | 200 | 170
MISO | J951 | Withdrawn | 2018-02-02T05:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2018-11-15T05:00:00+00:00 | OTTER TAIL POWER COMPANY | Kittson County | Minnesota | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Donaldson - Warsaw 115 kV Line Tap | 80 | 80 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J952 | Withdrawn | 2018-02-05T05:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | Corson County | South Dakota | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | McLaughlin - McIntosh Junction 115 kV Line Tap | 54 | 54 | Wind | Wind Turbine | Not Started |  | 54 | 54 | 0 | 0
MISO | J953 | Done | 2018-03-08T05:00:00+00:00 |  | 2022-08-12T04:00:00+00:00 | 2006-01-01T05:00:00+00:00 | ITC MIDWEST | Johnson County | Iowa | DPP-2018-APR | West | Phase 3 | External Network Resource Interconnection Service (E-NRIS) | AMIL.IOW_AFRYT | 1.83 | 2 | Diesel | Piston (Engine), Internal Combustion (Diesel) | Not Started |  | 1.83 | 2 | 1.83 | 2
MISO | J954 | Done | 2018-03-08T05:00:00+00:00 |  | 2022-08-12T04:00:00+00:00 | 2016-10-30T04:00:00+00:00 | ITC MIDWEST | Johnson County | Iowa | DPP-2018-APR | West | Phase 3 | External Network Resource Interconnection Service (E-NRIS) | AMIL.IOW_AFRYT | 1.4 | 1.4 | Solar | Photovoltaic | Not Started |  | 1.4 | 1.4 | 1.4 | 1.4
MISO | J955 | Done | 2018-03-08T05:00:00+00:00 |  | 2022-04-26T04:00:00+00:00 | 2021-11-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Sangamon County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Austin Substation 345kV Bus | 1040 | 1165 | Gas | Combined Cycle | Under Construction | 2025-01-31T05:00:00+00:00 | 1165 | 1165 | 1165 | 1165
MISO | J956 | Done | 2018-03-09T05:00:00+00:00 |  | 2021-12-22T05:00:00+00:00 | 2021-09-15T04:00:00+00:00 | Ameren Missouri | Ralls County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Spencer Creek 345kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started | 2024-06-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J957 | Withdrawn | 2018-03-09T05:00:00+00:00 | 2019-03-19T04:00:00+00:00 |  | 2010-09-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Mercer County,Putnam County,Sullivan County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Maywood 345kV Substation | 800 | 800 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J958 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Lincoln County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Buffalo Ridge 115kV Substation | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J959 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | SMMPA | Fayette County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Windsor 161kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 150 | 0 | 0
MISO | J960 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-21T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | METC | Presque Isle County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Livingston 345kV Substation | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J961 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-01-31T05:00:00+00:00 | ENTERGY LOUISIANA, LLC | West Baton Rouge Parish | Louisiana | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Livonia - Wilbert 138 kV Line Tap | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J962 | Done | 2018-03-12T04:00:00+00:00 |  | 2020-08-12T04:00:00+00:00 | 2021-01-31T05:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | DeSoto County | Mississippi | DPP-2018-APR | South | GIA | Energy Resource Interconnection Service (ERIS) | Twinkletown 230 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2022-06-30T04:00:00+00:00 | 100 | 0 | 100 | 0
MISO | J963 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | 2017-01-01T05:00:00+00:00 | ITC MIDWEST | Cedar County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Bennett (CIPCO) - Graham 69 Kv Line Tap | 9 | 9 | Diesel | Piston (Engine), Internal Combustion (Diesel) | Not Started | 2017-01-01T05:00:00+00:00 | 9 | 9 | 9 | 9
MISO | J964 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2020-10-02T04:00:00+00:00 | ENTERGY MISSISSIPPI, LLC | Hinds County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Edwards - Bolton 115kV Line Tap | 70 | 70 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J965 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-11-19T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | Xcel Energy | Cottonwood County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Lakefield Generation SW 345kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J966 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-12-01T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Putnam County,Sullivan County | Missouri | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Zachary 345kV Substation | 400 | 400 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J967 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-06-15T04:00:00+00:00 | 2020-09-01T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Mower County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Adams 345kV Substation | 150 | 150 | Wind | Wind Turbine | Under Construction | 2023-08-01T04:00:00+00:00 | 150 | 150 | 150 | 0
MISO | J968 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2022-09-01T04:00:00+00:00 | NORTHERN INDIANA PUBLIC SERVICE COMPANY LLC | Jasper County,White County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Reynolds 345kV Substation | 200 | 200 | Wind | Wind Turbine | In Service | 2023-04-20T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J969 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-11-01T04:00:00+00:00 |  | 2020-12-01T05:00:00+00:00 | ITC MIDWEST | Tuscola County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Kirk 345kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J970 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-10-17T04:00:00+00:00 |  | 2020-01-01T05:00:00+00:00 | METC | Oscoda County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Mio Dam - Gaylord 138 kV Line Tap | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J971 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-30T04:00:00+00:00 | NORTHERN STATES POWER COMPANY | Nobles County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Nobles Co - Fenton 115 kV Line Tap | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J972 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2021-10-31T04:00:00+00:00 | ENTERGY ARKANSAS, LLC | St. Francis County | Arkansas | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | Hughes-Forest City South 161kv line | 140 | 140 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J973 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-03-19T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Coles County,Edgar County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Kansas West 345kV Substation | 250 | 250 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J974 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Fulton County,Peoria County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Mapleridge 345kV Switching Station | 250 | 250 | Wind | Wind Turbine | Under Construction | 2023-10-15T04:00:00+00:00 | 250 | 250 | 225 | 225
MISO | J975 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-07-28T04:00:00+00:00 |  | 2023-10-31T04:00:00+00:00 | OTTER TAIL POWER COMPANY | Cass County | North Dakota | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Buffalo 115kV Substation | 150 | 150 | Wind | Wind Turbine | Not Started |  | 150 | 150 | 150 | 0
MISO | J976 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-10-31T04:00:00+00:00 | Ameren Missouri | Warren County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Montgomery - Enon 345kV Line Tap | 300 | 300 | Solar | Photovoltaic | Under Construction | 2024-06-01T04:00:00+00:00 | 300 | 300 | 300 | 300
MISO | J977 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2021-03-01T05:00:00+00:00 | ITC MIDWEST | Jackson County,Martin County | Minnesota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Jackson North 161kV Substation | 300 | 300 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J978 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-11-21T05:00:00+00:00 |  | 2021-03-01T05:00:00+00:00 | METC | Montcalm County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Eureka - Vestaburg 138kV Line Tap | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J979 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-10-18T04:00:00+00:00 |  | 2021-03-01T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Christian County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Pana Substation 345kV Bus | 200 | 200 | Wind | Wind Turbine | Not Started |  | 170 | 170 | 170 | 170
MISO | J980 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-06T05:00:00+00:00 |  | 2021-03-01T05:00:00+00:00 | AMEREN TRANSMISSION COMPANY OF ILLINOIS | Christian County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Pana Substation 345kV Bus | 200 | 200 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J981 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2021-03-09T05:00:00+00:00 |  | 2021-03-01T05:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Washington County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Sub T 345kV Substation | 200 | 200 | Wind | Wind Turbine | Not Started |  | 200 | 200 | 0 | 0
MISO | J982 | Done | 2018-03-12T04:00:00+00:00 |  | 2022-02-07T05:00:00+00:00 | 2021-06-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Dickinson County,Emmet County | Iowa | DPP-2018-APR | West | Phase 3 | Energy Resource Interconnection Service (ERIS) | Obrien County - Kossuth 345 kV Line Tap | 300 | 300 | Wind | Wind Turbine | Not Started | 2024-03-15T04:00:00+00:00 | 300 | 300 | 300 | 0
MISO | J983 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2018-11-01T04:00:00+00:00 |  | 2021-03-01T05:00:00+00:00 | AMEREN ILLINOIS | Brown County,LaSalle County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Oglesby - Minonk Tap 138kV Line Tap | 100 | 100 | Wind | Wind Turbine | Not Started |  | 0 | 0 | 0 | 0
MISO | J984 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-07T04:00:00+00:00 | 2021-06-01T04:00:00+00:00 | METC | Gratiot County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Nelson Road – Murphy 345kV line | 200 | 200 | Wind | Wind Turbine | Under Construction | 2022-10-31T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J985 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-06T05:00:00+00:00 |  | 2020-12-01T05:00:00+00:00 | Ameren Missouri | Scott County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Miner - Kelso 161kV Line Tap | 120 | 120 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J986 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-05-05T04:00:00+00:00 | 2020-09-01T04:00:00+00:00 | American Transmission Co. LLC | Wood County | Wisconsin | DPP-2018-APR | East (ATC) | GIA | Network Resource Interconnection Service (NRIS) | Port Edwards - Sand Lake 138kV | 149.76 | 149.76 | Solar | Photovoltaic | Not Started | 2022-06-01T04:00:00+00:00 | 149.76 | 149.76 | 149.76 | 149.76
MISO | J987 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | Ameren Missouri | Montgomery County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Montgomery 161kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2023-10-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J988 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-08-29T04:00:00+00:00 |  | 2022-09-01T04:00:00+00:00 | COOPERATIVE ENERGY | Wayne County | Mississippi | DPP-2018-APR | South | GIA | Network Resource Interconnection Service (NRIS) | W Waynesboro 230kV Substation | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J989 | Withdrawn | 2018-02-12T05:00:00+00:00 | 2020-06-30T04:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | METC | Oakland County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Halsey 138kV Substation | 80 | 80 | Solar | Photovoltaic | Not Started |  | 80 | 80 | 0 | 0
MISO | J990 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2019-02-15T05:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | ITC MIDWEST | Dubuque County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Salem 345kV Substation | 150 | 150 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J991 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Clay County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Xenia 345kV Switching Station | 200 | 200 | Solar | Photovoltaic | Under Construction | 2023-10-01T04:00:00+00:00 | 150 | 150 | 150 | 150
MISO | J992 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | DUKE ENERGY INDIANA, LLC | Cass County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Walton 230kV Substation | 200 | 200 | Solar | Photovoltaic | Under Construction | 2023-10-31T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J993 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | INDIANAPOLIS POWER & LIGHT COMPANY | Boone County | Indiana | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Hortonville - Whitestown 345kV Line Tap | 200 | 200 | Solar | Photovoltaic | Under Construction | 2023-11-01T04:00:00+00:00 | 200 | 200 | 200 | 200
MISO | J994 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-10-12T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | Ameren Missouri | Callaway County | Missouri | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | Guthrie 161 kV Substation | 100 | 100 | Solar | Photovoltaic | Under Construction | 2023-08-01T04:00:00+00:00 | 100 | 100 | 100 | 100
MISO | J995 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-01-06T05:00:00+00:00 |  | 2021-09-01T04:00:00+00:00 | AMEREN ILLINOIS | Brown County,Jersey County | Illinois | DPP-2018-APR | Central | GIA | Network Resource Interconnection Service (NRIS) | NW Jerseyville Northwest Substation 138kV Bus | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J996 | Done | 2018-03-12T04:00:00+00:00 |  | 2021-04-27T04:00:00+00:00 | 2021-09-01T04:00:00+00:00 | METC | Lenawee County | Michigan | DPP-2018-APR | East (ITC) | GIA | Network Resource Interconnection Service (NRIS) | Beecher - Moraco 138kV Line | 80 | 80 | Solar | Photovoltaic | Under Construction | 2022-10-31T04:00:00+00:00 | 80 | 80 | 80 | 80
MISO | J997 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | MONTANA-DAKOTA UTILITIES CO. | LaMoure County | North Dakota | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Ellendale 345 kV Sub, 230 kV Bus - 661098 | 200 | 200 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J998 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | MIDAMERICAN ENERGY COMPANY | Dallas County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Adel - Waukee 69kV Line Tap | 50 | 50 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO | J999 | Withdrawn | 2018-03-12T04:00:00+00:00 | 2020-03-25T04:00:00+00:00 |  | 2020-09-01T04:00:00+00:00 | ITC MIDWEST | Linn County | Iowa | DPP-2018-APR | West | Phase 3 | Network Resource Interconnection Service (NRIS) | Fairfax 161kV Substation | 100 | 100 | Solar | Photovoltaic | Not Started |  | 0 | 0 | 0 | 0
MISO |  | Done | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 |  | Lawrence | MS | DPP-2023 | Central |  |  | GP-Monticello | 50 | 50 | Hybrid | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO |  | Done | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 |  | Lawrence | MS | DPP-2023 | East (ITC) |  |  | GP-Monticello | 50 | 50 | Hybrid | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO |  | Done | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 |  | Lawrence | MS | DPP-2023 | South |  |  | GP-Monticello | 50 | 50 | Hybrid | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO |  | Done | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 |  | Lawrence | MS | DPP-2023 | West |  |  | GP-Monticello | 50 | 50 | Hybrid | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO |  | Done | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 |  | Lawrence | MS | DPP-2024 | South |  |  | GP-Monticello | 50 | 50 | Hybrid | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO |  | Done | 2024-04-17T04:00:00+00:00 |  |  | 2027-10-01T04:00:00+00:00 |  | Lawrence | MS | DPP-TEST | South |  |  | GP-Monticello | 50 | 50 | Hybrid | Wind Turbine |  |  | 0 | 0 | 0 | 0
MISO | R1000 | Done | 2019-06-24T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1001 | Done | 2020-05-15T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1002 | Done | 2020-07-01T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1003 | Done | 2020-08-05T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1004 | Done | 2020-12-30T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1005 | Withdrawn | 2021-01-19T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1006 | Withdrawn | 2021-02-15T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1007 | Withdrawn | 2021-03-29T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1008 | Done | 2021-04-12T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1009 | Done | 2021-05-28T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1010 | Done | 2021-07-21T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1011 | Done | 2021-10-04T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1012 | Withdrawn | 2021-09-30T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1013 | Withdrawn | 2021-11-16T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1014 | Active | 2022-02-04T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1015 | Active | 2022-02-13T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1016 | Active | 2022-02-18T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1017 | Active | 2022-02-15T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1018 | Active | 2022-02-23T05:00:00+00:00 | 2024-03-11T04:00:00+00:00 | [10 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1019 | Active | 2022-02-15T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1020 | Active | 2022-03-31T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1021 | Active | 2022-05-31T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1022 | Active | 2022-05-31T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1023 | Active | 2022-09-29T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1024 | Active | 2022-10-12T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1025 | Active | 2022-10-14T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1026 | Active | 2022-11-22T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1027 | Active | 2022-11-22T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1028 | Active | 2022-11-22T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1029 | Active | 2022-12-12T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  | 2024-12-01T05:00:00+00:00 | 0 | 0 | 0 | 0
MISO | R1030 | Active | 2023-01-05T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1031 | Active | 2023-03-07T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1032 | Active | 2023-01-20T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1033 | Active | 2023-02-13T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1034 | Active | 2023-07-20T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1035 | Active | 2023-04-19T04:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | R1036 | Active | 2022-12-28T05:00:00+00:00 | [11 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1000 | Done | 2020-06-20T04:00:00+00:00 | [11 empty] | 10 | 10 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1001 | Done | 2020-06-25T04:00:00+00:00 | [11 empty] | 7.5 | 7.5 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1002 | Withdrawn | 2020-10-01T04:00:00+00:00 | [11 empty] | 70 | 70 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1004 | Done | 2020-10-28T04:00:00+00:00 | [11 empty] | 30 | 30 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1005 | Done | 2021-04-02T04:00:00+00:00 | [11 empty] | 60 | 60 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1006 | Active | 2021-04-02T04:00:00+00:00 | [11 empty] | 75 | 75 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1007 | Active | 2021-07-08T04:00:00+00:00 | [11 empty] | 70 | 70 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1008 | Active | 2021-08-04T04:00:00+00:00 | [11 empty] | 250 | 250 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1009 | Active | 2021-08-17T04:00:00+00:00 | [11 empty] | 92 | 92 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1010 | Withdrawn | 2021-10-15T04:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1011 | Withdrawn | 2021-10-15T04:00:00+00:00 | [11 empty] | 100 | 100 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1012 | Withdrawn | 2021-10-15T04:00:00+00:00 | [11 empty] | 80 | 80 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1013 | Active | 2022-01-26T05:00:00+00:00 | [11 empty] | 200 | 200 |  |  |  | 2026-06-30T04:00:00+00:00 | 0 | 0 | 0 | 0
MISO | S1014 | Active | 2022-03-09T05:00:00+00:00 |  |  |  | MONTANA-DAKOTA UTILITIES CO. | [7 empty] | 9 | 9 |  |  |  | 2028-09-01T04:00:00+00:00 | 0 | 0 | 0 | 0
MISO | S1015 | Active | 2022-04-11T04:00:00+00:00 | [11 empty] | 55 | 55 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1016 | Active | 2022-04-15T04:00:00+00:00 | [11 empty] | 25 | 25 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1017 | Active | 2022-04-11T04:00:00+00:00 | [11 empty] | 100 | 100 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1018 | Active | 2022-04-20T04:00:00+00:00 | [11 empty] | 75 | 75 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1019 | Active | 2022-04-25T04:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1020 | Active | 2022-04-25T04:00:00+00:00 | [11 empty] | 100 | 100 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1021 | Active | 2022-04-25T04:00:00+00:00 | [11 empty] | 80 | 80 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1022 | Active | 2022-05-02T04:00:00+00:00 | [11 empty] | 3 | 3 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1023 | Active | 2022-05-16T04:00:00+00:00 | [11 empty] | 25 | 25 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1024 | Active | 2022-05-16T04:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1025 | Active | 2022-05-16T04:00:00+00:00 | [11 empty] | 25 | 25 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1026 | Active | 2022-05-26T04:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1027 | Active | 2022-05-26T04:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1028 | Done | 2022-05-31T04:00:00+00:00 | [11 empty] | 60 | 60 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1029 | Active | 2022-06-03T04:00:00+00:00 | [11 empty] | 99 | 99 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1030 | Active | 2022-06-13T04:00:00+00:00 | [11 empty] | 99 | 99 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1031 | Active | 2022-08-19T04:00:00+00:00 | [11 empty] | 90 | 90 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1032 | Active | 2022-08-19T04:00:00+00:00 | [11 empty] | 90 | 90 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1033 | Active | 2022-08-15T04:00:00+00:00 | [11 empty] | 25 | 25 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1034 | Active | 2022-08-15T04:00:00+00:00 | [11 empty] | 25 | 25 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1035 | Active | 2022-08-15T04:00:00+00:00 | [11 empty] | 33 | 33 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1036 | Active | 2022-09-09T04:00:00+00:00 | [11 empty] | 400 | 400 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1037 | Withdrawn | 2022-10-26T04:00:00+00:00 | 2023-03-22T04:00:00+00:00 | [10 empty] | 50.4 | 50.4 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1038 | Active | 2022-12-07T05:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1039 | Active | 2022-09-01T04:00:00+00:00 | [11 empty] | 100 | 100 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1040 | Active | 2022-12-16T05:00:00+00:00 | [11 empty] | 135 | 135 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1041 | Active | 2023-05-19T04:00:00+00:00 | [11 empty] | 135 | 135 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1042 | Active | 2022-12-20T05:00:00+00:00 | [11 empty] | 100 | 100 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1043 | Active | 2023-04-17T04:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1044 | Active | 2023-04-17T04:00:00+00:00 | [11 empty] | 50 | 50 |  |  |  |  | 0 | 0 | 0 | 0
MISO | S1045 | Active | [12 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0