## Sheet1
ISO | Project ID | POI Name | Project Name | State | Nearest Town or County | Project Status | Transmission Owner/Developer | MFO | Energy | Capacity (MW) | MW In Service | Capacity or Energy | Service Type | Fuel | Project (AC/DC) | Rights (MW) | Initial Study | Feasibility Study | Feasibility Study Status | System Impact Study | System Impact Study Status | Facilities Study | Facilities Study Status | Interim Interconnection Service Agreement | Interconnection Agreement Status | Wholesale Market Participation Agreement | Construction Service Agreement | Construction Service Agreement Status | Upgrade Construction Service Agreement | Upgrade Construction Service Agreement Status | Proposed In-Service/Initial Backfeed Date | Interconnection Request Receive Date | Long-Term Firm Service Start Date | Long-Term Firm Service End Date | Test Energy Date | Withdrawal Date | Withdrawn Remarks | Projected COD | Revised In Service Date | Actual In Service Date | Attachment Type | Alternate Project | Sliding Project
PJM | S14 | Dans Mountain | Dans Mountain | PA | Allegheny | Engineering and Procurement | APS | 70 | 54.9 | 14 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/s14_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/s14_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/s14_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/s14_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/s14_csa.pdf | Document Posted |  |  |  | 3/19/2007 |  |  | 11/1/2024 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
PJM | Z1-036 | WinFall-Chowan 230kV | Timbermill Wind Farm | NC | Perquimans | Under Construction | Dominion | 189 | 189 | 24.5 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/z1036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/z1036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/z1036_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/z1_036_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/z1_036_csa.pdf | Document Posted |  |  | 10/15/2024 | 7/23/2013 |  |  | 11/1/2024 |  |  | 3/31/2025 | 3/31/2025 |  | N | No
PJM | AA1-038 | Lexington-Low Moor 230kV |  | VA | Botetourt | Engineering and Procurement | Dominion | 78.2 | 78.2 | 10.1 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_038_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/aa1_038_csa.pdf | Document Posted |  |  | 11/5/2025 | 8/19/2014 |  |  | 11/5/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AA1-102 | Kings Creek-Loretto 138kV | Perry Road Solar | MD | Somerset | Partially in Service - Under Construction | DPL | 150 | 150 | 57 | 118 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa1102_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa1102_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa1102_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa1_102_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/aa1_102_csa.pdf | Document Posted |  |  |  | 10/30/2014 |  |  | 12/28/2017 |  |  | 12/31/2023 | 12/31/2023 | 12/28/2017 | N | No
PJM | AA2-119 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 550 | 550 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/aa2119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/aa2119_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/aa2119_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/aa2_119_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/aa2_119_csa.pdf | Document Posted |  |  | 8/31/2026 | 4/30/2015 |  |  | 3/31/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
PJM | AB1-021 | West Caldwell 13kV | West Caldwell Solar | NJ | Essex | Partially in Service - Under Construction | PSEG | 2 | 2 | 0.3 | 0.3 | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1021_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1021_wmpa.pdf |  | Not Required |  |  |  | 6/29/2015 |  |  | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 6/1/2018 | N | No
PJM | AB1-056 | Indian River 230kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Engineering and Procurement | DPL | 247.8 | 247.8 | 64.4 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1056_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1056_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_056_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab1_056_csa.pdf | Document Posted |  |  | 2/1/2027 | 8/31/2015 |  |  | 12/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
PJM | AB1-063 | Locust St. 13kV | Cooper Solar | NJ | Camden | Partially in Service - Under Construction | PSEG; PSEG | 0.4 | 0.4 | 0 | 0.2 | Energy | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1063_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1063_wmpa.pdf |  | Not Required |  |  |  | 9/1/2015 |  |  | 6/1/2023 |  |  | 12/1/2016 | 12/1/2016 | 2/15/2017 | N | No
PJM | AB1-087 | Sullivan 345kV #1 | Sullivan Generating Station 1 | IN | Sullivan | Engineering and Procurement | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1087_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1087_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1087_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_087_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab1_087_csa.pdf | Document Posted |  |  |  | 10/1/2015 | [5 empty] | 6/1/2025 | 6/1/2025 |  | N | No
PJM | AB1-088 | Sullivan 345kV #2 | Sullivan Generating Station 2 | IN | Sullivan | Engineering and Procurement | AEP | 575 | 575 | 550 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_088_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab1_088_csa.pdf | Document Posted |  |  |  | 10/1/2015 | [5 empty] | 6/1/2025 | 6/1/2025 |  | N | No
PJM | AB1-105 | Highland-Hanna 345kV | Trumbull Energy Center | OH | Trumbull | Under Construction | ATSI | 940 | 940 | 850 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1105_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1105_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_105_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab1_105_csa.pdf | Document Posted |  |  | 12/1/2024 | 10/22/2015 |  |  | 7/2/2025 |  |  | 8/12/2025 | 8/12/2025 |  | N | No
PJM | AB1-109 | Mountaineer | Mountaineer #1 | WV | Unknown | Partially in Service - Under Construction | AEP | 1356 | 36 | 36 | 36 | Capacity | Generation Interconnection | Coal |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1109_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ab1_109_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 10/26/2015 | [5 empty] | 6/1/2021 | 6/1/2021 | 12/31/2018 | N | No
PJM | AB1-124 | Carroll-Monocacy 34.5kV | Legore Bridge Solar Center Facility | MD | Frederick | Engineering and Procurement | APS | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1124_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1124_fac.pdf | Document Posted |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1124_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1124_wmpa.pdf | Not Required |  |  |  | 10/29/2015 |  |  | 4/30/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
PJM | AB1-125 | Carroll-Monocacy 34.5kV | Biggs Ford Solar Facility | MD | Frederick | Engineering and Procurement | APS | 15 | 15 | 5.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1125_imp.pdf | Document Posted |  |  |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1125_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1_125_csa.pdf | Not Required |  |  |  | 10/30/2015 |  |  | 4/30/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
PJM | AB1-132 | Thelma 230kV | Gaston Green Acres Solar | NC | Northhampton | Partially in Service - Under Construction | Dominion | 120 | 120 | 84 | 65 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1132_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1132_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab1_132_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab1_132_csa.pdf | Document Posted |  |  | 11/20/2023 | 11/2/2015 |  |  | 12/21/2023 |  |  | 12/25/2023 | 12/25/2023 |  | N | No
PJM | AB1-176 | Price 25kV II | Cedar Lane Solar | MD | Queen Anne's | Engineering and Procurement | DPL | 4 | 4 | 1.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab1176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab1176_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab1176_fac.pdf | Document Posted |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab1176_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab1176_wmpa.pdf | Not Required |  |  |  | 10/30/2015 |  |  | 3/31/2025 |  |  | 3/1/2024 | 3/1/2024 |  | N | No
PJM | AB2-036 | Church - Oil City 138kV | Waypost Solar Project | MD | Caroline | Engineering and Procurement | DPL | 92 | 92 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2036_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2036_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2036_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_036_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab2_036_csa.pdf | Document Posted |  |  |  | 2/26/2016 |  |  | 12/30/2025 |  |  | 12/30/2025 | 12/30/2025 |  | N | No
PJM | AB2-037 | Keeney-Steele 230kV | Cherrywood Solar I | MD | Caroline | Engineering and Procurement | DPL | 202 | 202 | 76.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2037_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2037_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_037_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab2_037_csa.pdf | Document Posted |  |  |  | 2/26/2016 |  |  | 12/30/2025 |  |  | 12/30/2025 | 12/30/2025 |  | N | No
PJM | AB2-040 | Brink 115kV | Brink Solar Project | VA | Greensville | Under Construction | Dominion | 80 | 80 | 44 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2040_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2040_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_040_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab2_040_csa.pdf | Document Posted |  |  | 9/12/2024 | 3/2/2016 |  |  | 10/4/2024 |  |  | 10/1/2024 | 10/1/2024 |  | N | No
PJM | AB2-092 | Bergen 138kV | Bergen Generating Station | NJ | Bergen | Partially in Service - Under Construction | PSEG | 1371.1 | 51.1 | 51.1 | 16 | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_092_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 4/26/2016 |  |  | 12/31/2025 |  |  | 12/5/2019 | 12/5/2019 | 12/5/2019 | N | No
PJM | AB2-097 | Antietam 34.5kV | Hagerstown Plant | MD | Washington | Partially in Service - Under Construction | APS | 10 | 10 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2097_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ab2097_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ab2097_wmpa.pdf | Not Required |  |  |  | 4/27/2016 |  |  | 12/31/2022 |  |  | 2/28/2020 | 2/28/2020 | 10/15/2020 | N | No
PJM | AB2-133 | Chestertown-Church 69kV | Morgnec Road Solar | MD | Kent | Engineering and Procurement | DPL | 55.8 | 55.8 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2133_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2133_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_133_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab2_133_csa.pdf | Document Posted |  |  |  | 4/29/2016 |  |  | 8/16/2025 |  |  | 8/16/2025 | 8/16/2025 |  | N | No
PJM | AB2-135 | Church-Kent 69kV | Jones Farm Lane Solar | MD | Queen Anne's | Under Construction | DPL | 64 | 64 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2135_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2135_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_135_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab2_135_csa.pdf | Document Posted |  |  | 11/28/2024 | 4/30/2016 |  |  | 12/15/2024 |  |  | 10/30/2024 | 10/30/2024 |  | N | No
PJM | AB2-136 | Cambridge-West Cambridge 69kV | Egypt Road Solar | MD | Dorchester | Under Construction | DPL | 51.1 | 51.1 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2136_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2136_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_136_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab2_136_csa.pdf | Document Posted |  |  |  | 4/29/2016 |  |  | 9/30/2025 |  |  | 9/30/2025 | 9/30/2025 |  | N | No
PJM | AB2-160 | Reams 115kV | Reams Solar | VA | Dinwiddie | Engineering and Procurement | Dominion | 80 | 80 | 30.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2160_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ab2160_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ab2_160_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ab2_160_csa.pdf | Document Posted |  |  | 5/31/2026 | 4/30/2016 |  |  | 10/30/2026 |  |  | 12/31/2022 | 12/31/2022 |  | N | No
PJM | AB2-175 | Peach Bottom 500kV | Peach Bottom Units #2 & #3 | PA | York | Partially in Service - Under Construction | PECO | 2709.8 | 44 | 44 | 44 | Capacity | Generation Interconnection | Nuclear |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ab2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ab2175_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ab2_175_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 4/29/2016 |  |  | 3/26/2019 |  |  | 12/31/2018 | 12/31/2018 | 3/26/2019 | N | No
PJM | AC1-001 | Delano 138kV | Salt City Solar | OH | Ross | Partially in Service - Under Construction | AEP | 49.9 | 49.9 | 33.93 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1001_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1001_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_001_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_001_csa.pdf | Document Posted |  |  | 6/29/2023 | 5/6/2016 |  |  | 6/29/2023 |  |  | 8/31/2023 | 8/31/2023 |  | N | No
PJM | AC1-010 | Gloucester 26kV | National Park NJ | NJ | Gloucester | Engineering and Procurement | PSEG | 6 | 6 | 2.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1010_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac1_010_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_010_csa.pdf | Document Posted |  |  | 11/15/2025 | 6/22/2016 |  |  | 12/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AC1-034 | Heartsease DP - Mayo Dunbar 115kV | Edgecome Solar Energy Center | NC | Edgecombe | Engineering and Procurement | Dominion | 75 | 75 | 42.75 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1034_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1034_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_034_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_034_csa.pdf | Document Posted |  |  | 6/13/2025 | 8/11/2016 |  |  | 12/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AC1-043 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 100 | 100 | 38 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1043_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1043_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1043_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_043_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_043_csa.pdf | Document Posted |  |  | 4/30/2026 | 8/31/2016 |  |  | 5/15/2026 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
PJM | AC1-053 | Lanesville-Brokaw | Top Hat Wind Energy Center | IL | Logan | Under Construction | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1053_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1053_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_053_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_053_csa.pdf | Document Posted |  |  | 5/15/2025 | 9/1/2016 |  |  | 9/15/2025 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
PJM | AC1-055 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 580 | 30 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1055_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1055_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ac1_055_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_055_csa.pdf | Document Posted |  |  | 8/31/2026 | 9/10/2016 |  |  | 3/31/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
PJM | AC1-065 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 50 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1065_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1065_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_065_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_065_csa.pdf | Document Posted |  |  | 6/3/2025 | 9/22/2016 |  |  | 10/28/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AC1-068 | Atlanta 69kV I | Pickaway County Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 34 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1068_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1068_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_068_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_068_csa.pdf | Document Posted |  |  | 7/26/2024 | 9/28/2016 |  |  | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AC1-069 | Atlanta 69kV II | Pickaway County II Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 34 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1069_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1069_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_069_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_069_csa.pdf | Document Posted |  |  | 7/26/2024 | 9/27/2016 |  |  | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AC1-074 | Jacksonville-Renaker 138kV I | Bluebird Solar | KY | Harrison | Under Construction | EKPC | 80 | 80 | 56 | 1 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1074_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1074_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_074_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_074_csa.pdf | Document Posted |  |  | 9/30/2024 | 9/30/2016 |  |  | 10/30/2024 |  |  | 12/30/2024 | 12/30/2024 |  | N | No
PJM | AC1-076 | Locust Grove-Paytes 115kV | Pine Glade Solar | VA | Orange | Under Construction | Dominion | 62.5 | 62.5 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1076_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_076_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_076_csa.pdf | Document Posted |  |  | 5/30/2024 | 10/1/2016 |  |  | 7/11/2024 |  |  | 7/15/2024 | 7/15/2024 |  | N | No
PJM | AC1-082 | Ravenswood-Hemlock 69kV | Great Bend | OH | Meigs | Engineering and Procurement | AEP | 48 | 48 | 29 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1082_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1082_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_082_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_082_csa.pdf | Document Posted |  |  | 7/29/2025 | 10/1/2016 |  |  | 8/29/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AC1-085 | Stuart-Clinton 345kV | Highland County Solar | OH | Highland | Partially in Service - Under Construction | Dayton | 400 | 400 | 152 | 366.6 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1085_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1085_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_085_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_085_csa.pdf | Document Posted |  |  |  | 10/1/2016 |  |  | 10/27/2023 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AC1-086 | Thelma 230kV | Cherry Solar | NC | Northhampton | Engineering and Procurement | Dominion | 180 | 180 | 123.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1086_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_086_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_086_csa.pdf | Document Posted |  |  |  | 10/11/2016 |  |  | 6/2/2025 |  |  | 8/31/2025 | 8/31/2025 |  | N | No
PJM | AC1-089 | Hillsboro-Wildcat 138kV | Willowbrook Solar | OH | Highland | Partially in Service - Under Construction | AEP | 150 | 150 | 57 | 121 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1089_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_089_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_089_csa.pdf | Document Posted |  |  | 11/13/2023 | 10/15/2016 |  |  | 11/13/2023 |  |  | 1/19/2024 | 1/19/2024 |  | N | No
PJM | AC1-091 | Cedar Creek 138kV I | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 19.8 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1091_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1091_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_091_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_091_csa.pdf | Document Posted |  |  |  | 10/19/2016 |  |  | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
PJM | AC1-092 | Cedar Creek 138kV II | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 39.6 | 19.8 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_092_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_092_csa.pdf | Document Posted |  |  |  | 10/20/2016 |  |  | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
PJM | AC1-093 | Cedar Creek 138kV III | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 58.4 | 18.8 | 7.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_093_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_093_csa.pdf | Document Posted |  |  |  | 10/20/2016 |  |  | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
PJM | AC1-094 | Cedar Creek 138kV IV | Cedar Creek Solar | DE | New Castle | Engineering and Procurement | DPL | 74.3 | 15.9 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1094_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1094_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_094_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_094_csa.pdf | Document Posted |  |  |  | 10/20/2016 |  |  | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
PJM | AC1-098 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Engineering and Procurement | Dominion | 60 | 60 | 37.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1098_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1098_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1098_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_098_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_098_csa.pdf | Document Posted |  |  | 6/15/2025 | 10/22/2016 |  |  | 7/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
PJM | AC1-099 | Dawson-South Justice 115kV | American Beech Solar | NC | Alamance | Engineering and Procurement | Dominion | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1099_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1099_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_099_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_099_csa.pdf | Document Posted |  |  | 6/15/2025 | 10/22/2016 |  |  | 7/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
PJM | AC1-161 | Septa 500kV | Cavalier | VA | Isle of Wight | Partially in Service - Under Construction | Dominion | 240 | 240 | 168.2 | 156.2 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1161_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1161_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_161_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_161_csa.pdf | Document Posted |  |  | 6/23/2023 | 11/2/2016 |  |  | 12/12/2023 |  |  | 1/1/2023 | 1/1/2023 |  | N | No
PJM | AC1-164 | Chickahominy 230kV | Keydet Solar Center One | VA | Charles City | Partially in Service - Under Construction | Dominion | 320 | 320 | 220.8 | 175 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1164_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1164_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_164_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_164_csa.pdf | Document Posted |  |  | 11/11/2021 | 10/31/2016 |  |  | 11/1/2024 |  |  | 6/30/2023 | 6/30/2023 |  | N | No
PJM | AC1-165 | Atlanta 69kV III | Buckeye Plains II Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1165_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1165_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_165_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_165_csa.pdf | Document Posted |  |  | 7/10/2024 | 11/2/2016 |  |  | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AC1-166 | Atlanta 69kV IV | Buckeye Plains Solar | OH | Pickaway | Under Construction | Dayton | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1166_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1166_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_166_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_166_csa.pdf | Document Posted |  |  | 7/10/2024 | 11/2/2016 |  |  | 7/26/2024 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AC1-167 | Mark Center 69kV | Mark Center Solar Project | OH | Defiance | Engineering and Procurement | AEP | 49.9 | 49.9 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1167_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1167_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_167_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_167_csa.pdf | Document Posted |  |  | 6/25/2025 | 11/1/2016 |  |  | 6/25/2025 |  |  | 11/30/2024 | 11/30/2024 |  | N | No
PJM | AC1-190 | East New Market 69kV | New Market Solar | MD | Dorchester | Engineering and Procurement | DPL | 50 | 50 | 35 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1190_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1190_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_190_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_190_csa.pdf | Document Posted |  |  |  | 10/31/2016 |  |  | 6/15/2026 |  |  | 7/1/2028 | 7/1/2028 |  | N | No
PJM | AC1-194 | Elk 138kV | Vinton Solar | OH | Vinton | Engineering and Procurement | AEP | 125 | 125 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1194_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1194_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_194_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_194_csa.pdf | Document Posted |  |  | 5/31/2025 | 10/31/2016 |  |  | 6/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AC1-221 | Halifax-Person 230kV | Alton Post Office Solar | VA | Halifax | Under Construction | Dominion | 29.2 | 29.2 | 14.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac1221_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac1221_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac1_221_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac1_221_csa.pdf | Document Posted |  |  | 8/28/2024 | 11/2/2016 |  |  | 9/25/2024 |  |  | 8/5/2024 | 8/5/2024 |  | N | No
PJM | AC2-009 | Pennington 13 kV | Pennington 13 kV Solar | NJ | Mercer | Partially in Service - Under Construction | PSEG | 0.59 | 0.59 | 0.1 | 0.55 | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2009_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2009_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2009_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2009_wmpa.pdf | Not Required |  |  |  | 12/1/2016 |  |  | 6/1/2023 |  |  | 3/2/2018 | 3/2/2018 | 10/19/2017 | N | Yes
PJM | AC2-015 | Chatfield-Howard 138kV | Sycamore Creek Solar | OH | Crawford | Engineering and Procurement | AEP | 117 | 117 | 53.55 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2015_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2015_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_015_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_015_csa.pdf | Document Posted |  |  | 5/1/2025 | 12/29/2016 |  |  | 6/1/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
PJM | AC2-023 | Hebron 69kV | Porter Mill Solar | MD | Wicomico | Engineering and Procurement | DPL | 45.8 | 45.8 | 26.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2023_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_023_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_023_csa.pdf | Document Posted |  |  |  | 1/25/2017 |  |  | 5/1/2026 |  |  | 5/1/2026 | 5/1/2026 |  | N | No
PJM | AC2-060 | Buckskin 69kV | Ross County Solar | OH | Ross | Under Construction | AEP | 100 | 100 | 64 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2060_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2060_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_060_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_060_csa.pdf | Document Posted |  |  | 8/1/2024 | 2/17/2017 |  |  | 8/1/2024 |  |  | 6/1/2024 | 6/1/2024 |  | N | No
PJM | AC2-061 | Hillsboro-Clinton 138kV | Dodson Creek Solar | OH | Ross | Engineering and Procurement | AEP | 117 | 117 | 58.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2061_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2061_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_061_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_061_csa.pdf | Document Posted |  |  | 11/1/2024 | 2/17/2017 |  |  | 12/1/2024 |  |  | 7/30/2024 | 7/30/2024 |  | N | No
PJM | AC2-075 | Jacksonville-Renaker 138 kV | Bluebird Solar | KY | Harrison | Under Construction | EKPC | 100 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_075_isa.pdf | Document Posted |  |  | Not Required |  |  | 9/30/2024 | 2/28/2017 |  |  | 10/30/2024 |  |  | 12/1/2024 | 12/1/2024 |  | N | No
PJM | AC2-084 | Dawson-South Justice 115kV | American Beech Solar | NC | Halifax | Engineering and Procurement | Dominion | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2084_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_084_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_084_csa.pdf | Document Posted |  |  | 6/15/2025 | 3/2/2017 |  |  | 7/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
PJM | AC2-090 | Losantville 345kV | Riverstart Solar Park III | IN | Randolph | Partially in Service - Under Construction | AEP | 100 | 100 | 38 | 79.93 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2090_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2090_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_090_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_090_csa.pdf | Document Posted |  |  | 3/26/2024 | 3/6/2017 |  |  | 6/5/2024 |  | Customer Milestone Not Met | 8/1/2024 | 8/1/2024 |  | N | No
PJM | AC2-100 | Halifax-Person 230kV | Powells Creek Solar | VA | Halifax | Partially in Service - Under Construction | Dominion | 50 | 50 | 33.6 | 50 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2100_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_100_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_100_csa.pdf | Document Posted |  |  | 7/26/2023 | 3/12/2017 |  |  | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 |  | N | No
PJM | AC2-110 | Harmony Village-Shackleford 115kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 70 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2110_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2110_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_110_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_110_csa.pdf | Document Posted |  |  |  | 3/14/2017 |  |  | 10/28/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AC2-123 | Jacksons Ferry 138kV | Wythe County Solar Project | VA | Wythe | Under Construction | AEP | 75 | 75 | 44.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2123_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2123_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_123_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_123_csa.pdf | Document Posted |  |  | 5/16/2024 | 3/25/2017 |  |  | 8/17/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
PJM | AC2-136 | East Hagerstown 12kV | East Hagerstown Solar | MD | Washington | Engineering and Procurement | APS | 11.8 | 11.8 | 5.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2136_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ac2136_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ac2136_wmpa.pdf | Not Required |  |  |  | 3/28/2017 |  |  | 10/4/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
PJM | AC2-141 | Septa 500kV | Sycamore Cross Solar | VA | Isle of Wight | Engineering and Procurement | Dominion | 240 | 240 | 168.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2141_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_141_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 3/30/2017 |  |  | 3/1/2026 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
PJM | AC2-157 | Sullivan 345 kV | Trade Post Solar Energy Center | IN | Sullivan | Engineering and Procurement | AEP | 200 | 200 | 76 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2157_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2157_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2157_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_157_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_157_csa.pdf | Document Posted |  |  | 4/30/2026 | 3/29/2017 |  |  | 5/31/2026 |  |  | 6/30/2026 | 6/30/2026 |  | N | No
PJM | AC2-165 | Bremo-Powhatan 230kV | Cartersville Solar | VA | Powhatan | Engineering and Procurement | Dominion | 99.9 | 99.9 | 57 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2165_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2165_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_165_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_165_csa.pdf | Document Posted |  |  |  | 3/30/2017 |  |  | 12/31/2025 |  |  | 3/15/2024 | 3/15/2024 |  | N | No
PJM | AC2-184 | Cedar Creek 138kV I | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 94.3 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2184_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2184_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_184_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_184_csa.pdf | Document Posted |  |  |  | 4/1/2017 |  |  | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
PJM | AC2-185 | Cedar Creek 138kV II | Cedar Creek Solar | DE | Kent | Engineering and Procurement | DPL | 114.3 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2185_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ac2_185_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_185_csa.pdf | Document Posted |  |  |  | 4/1/2017 |  |  | 3/1/2025 |  |  | 6/15/2025 | 6/15/2025 |  | N | No
PJM | AC2-186 | Harrington 25kV | Raceway Solar | DE | Kent | Under Construction | DPL | 10 | 10 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2186_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2186_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_186_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_186_csa.pdf | Document Posted |  |  |  | 4/1/2017 |  |  | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
PJM | AC2-187 | Harrington 69kV | Raceway Solar | DE | Kent | Under Construction | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2187_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2187_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_187_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_187_csa.pdf | Document Posted |  |  |  | 3/31/2017 |  |  | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
PJM | AC2-188 | Harrington 69 kV | Raceway Solar | DE | Kent | Under Construction | DPL | 20 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2188_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2188_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_188_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_188_csa.pdf | Document Posted |  |  |  | 3/31/2017 |  |  | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
PJM | AC2-195 | Galion-Roberts South 138 kV | Marion County Solar Project | OH | Marion | Engineering and Procurement | ATSI | 99.96 | 99.96 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ac2195_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ac2195_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ac2195_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ac2_195_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ac2_195_csa.pdf | Document Posted |  |  | 8/2/2025 | 4/1/2017 |  |  | 11/17/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AD1-013 | Twombly Road 138kV | Rochelle Solar | IL | Ogle | Engineering and Procurement | ComEd | 40 | 40 | 15.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1013_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1013_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_013_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_013_csa.pdf | Document Posted |  |  | 12/31/2025 | 4/6/2017 |  |  | 1/29/2026 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
PJM | AD1-020 | Hunterstown-Lincoln 115 kV | Adams Solar LLC | PA | Adams | Partially in Service - Under Construction | ME | 100 | 100 | 53.6 | 80 | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1020_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1020_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_020_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_020_csa.pdf | Document Posted |  |  | 12/22/2023 | 6/9/2017 |  |  | 12/27/2023 |  |  | 2/25/2024 | 2/25/2024 |  | N | No
PJM | AD1-022 | Cashie-Trowbridge 230 kV | Sumac Solar | NC | Bertie | Engineering and Procurement | Dominion | 80 | 80 | 51.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1022_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_022_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_022_csa.pdf | Document Posted |  |  |  | 6/19/2017 |  |  | 5/1/2028 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AD1-025 | Hopewell-Surry 230 kV | Spring Grove Solar II | VA | Surry | Engineering and Procurement | Dominion | 150 | 150 | 94.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1025_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1025_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_025_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_025_csa.pdf | Document Posted |  |  |  | 6/28/2017 |  |  | 3/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
PJM | AD1-031 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Engineering and Procurement | ComEd | 70 | 70 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1031_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1031_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_031_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_031_csa.pdf | Document Posted |  |  | 4/15/2027 | 7/24/2017 |  |  | 4/15/2027 |  |  | 6/15/2027 | 6/15/2027 |  | N | No
PJM | AD1-039 | Kendall-Tazewell & Dresden-Mole Creek | Three Rivers Energy Center | IL | Grundy | Partially in Service - Under Construction | ComEd | 1262.7 | 102.7 | 93 | 102.7 | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1039_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_039_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 7/29/2017 | [5 empty] | 2/28/2025 | 2/28/2025 | 6/16/2023 | N | No | This project slid to the next queue
PJM | AD1-041 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Under Construction | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1041_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1041_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_041_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_041_csa.pdf | Document Posted |  |  | 4/4/2024 | 8/2/2017 |  |  | 7/11/2024 |  |  | 6/28/2024 | 6/28/2024 |  | N | No
PJM | AD1-056 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 60 | 60 | 38.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1056_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1056_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_056_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_056_csa.pdf | Document Posted |  |  |  | 8/14/2017 |  |  | 12/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AD1-057 | Hornertown-Hathaway 230 kV | Sweetleaf Solar | NC | Halifax | Engineering and Procurement | Dominion | 33 | 33 | 21.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1057_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1057_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1057_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_057_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_057_csa.pdf | Document Posted |  |  |  | 8/14/2017 |  |  | 12/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AD1-058 | Halifax-Person 230 kV | Alton Post Office Solar | VA | Halifax | Under Construction | Dominion | 75.1 | 45.9 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1058_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1058_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1058_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_058_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_058_csa.pdf | Document Posted |  |  | 8/28/2024 | 8/16/2017 |  |  | 9/25/2024 |  |  | 8/5/2024 | 8/5/2024 |  | N | No
PJM | AD1-073 | Buckskin 69 kV | Ross County Solar | OH | Ross | Engineering and Procurement | AEP | 120 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1073_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1073_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_073_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_073_csa.pdf | Document Posted |  |  | 8/1/2024 | 8/31/2017 |  |  | 8/1/2024 |  |  | 6/1/2024 | 6/1/2024 |  | N | No
PJM | AD1-074 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 300 | 300 | 198.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1074_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1074_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_074_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_074_csa.pdf | Document Posted |  |  | 12/27/2027 | 9/1/2017 |  |  | 1/27/2028 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
PJM | AD1-075 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 75 | 75 | 49.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_075_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_075_csa.pdf | Document Posted |  |  |  | 8/31/2017 |  |  | 12/27/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
PJM | AD1-076 | Trowbridge 230 kV | Macadamia Solar | NC | Washington | Engineering and Procurement | Dominion | 109 | 109 | 72.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1076_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1076_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1076_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_076_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_076_csa.pdf | Document Posted |  |  |  | 8/31/2017 |  |  | 12/27/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
PJM | AD1-085 | North Shenandoah-Stanley 34.5 kV | North Shenandoah-Stanley 34.5kV | VA | Page | Engineering and Procurement | APS | 20 | 20 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1085_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1085_imp.pdf | Document Posted |  |  |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1085_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1085_wmpa.pdf | Not Required |  |  |  | 9/14/2017 |  |  | 7/31/2026 |  |  | 9/8/2026 | 9/8/2026 |  | N | No
PJM | AD1-088 | Briery-Clover 230 kV | Seven Bridges Solar | VA | Mecklenburg | Engineering and Procurement | Dominion | 80 | 80 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1088_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1088_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_088_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_088_csa.pdf | Document Posted |  |  |  | 9/15/2017 |  |  | 11/1/2025 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AD1-100 | Loretto-Wilton 345 kV & Braidwood-Davis Creek 345 kV |  | IL | Ford | Engineering and Procurement | ComEd | 850 | 850 | 150 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1100_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_100_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_100_csa.pdf | Document Posted |  |  | 10/31/2026 | 9/22/2017 |  |  | 10/31/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
PJM | AD1-105 | Kings Dominion DP 115 kV | Sweet Sue Solar | VA | King William | Under Construction | Dominion | 74 | 74 | 44.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1105_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad1105_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad1105_wmpa.pdf | Not Required |  |  |  | 9/23/2017 |  |  | 9/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AD1-115 | Mountain Run-Mitchell 115 kV | Greenwood Solar | VA | Culpeper | Engineering and Procurement | Dominion | 150 | 50 | 19 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1115_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad1_115_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_115_csa.pdf | Document Posted |  |  | 4/30/2026 | 9/27/2017 |  |  | 5/15/2026 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
PJM | AD1-119 | Payne 69 kV | Timber Road Solar Park | OH | Paulding | Partially in Service - Under Construction | AEP | 49.9 | 49.9 | 18.96 | 49.9 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1119_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1119_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_119_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_119_csa.pdf | Document Posted |  |  | 12/15/2022 | 9/28/2017 |  |  | 6/29/2023 |  |  | 11/30/2023 | 11/30/2023 |  | N | No
PJM | AD1-128 | Modoc-Delaware 138 kV | Riverstart Solar Park IV | IN | Randolph | Engineering and Procurement | AEP | 150 | 150 | 57 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1128_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1128_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_128_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_128_csa.pdf | Document Posted |  |  | 3/5/2025 | 9/29/2017 |  |  | 4/5/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AD1-130 | Hardin Switch 345 kV | Hardin Energy Center – Phase 2 | OH | Hardin | Under Construction | AEP | 150 | 150 | 101.47 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1130_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1130_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_130_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_130_csa.pdf | Document Posted |  |  | 5/22/2024 | 10/1/2017 |  |  | 8/5/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AD1-131 | Sedge Hill-Person 230 kV | Powells Creek Solar | VA | Halifax | Partially in Service - Under Construction | Dominion | 70 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1131_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1131_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_131_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_131_csa.pdf | Document Posted |  |  | 7/26/2023 | 9/30/2017 |  |  | 7/31/2023 |  |  | 11/1/2023 | 11/1/2023 |  | N | No
PJM | AD1-155 | Meadow Brook-Strasburg 138 kV | Foxglove Solar | VA | Frederick | Under Construction | APS | 75 | 75 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad1155_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad1155_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad1_155_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad1_155_csa.pdf | Document Posted |  |  | 7/22/2024 | 10/2/2017 |  |  | 9/13/2024 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
PJM | AD2-022 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 96 | 96 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2022_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_022_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_022_csa.pdf | Document Posted |  |  | 12/15/2024 | 12/2/2017 |  |  | 12/15/2024 |  |  | 2/28/2025 | 2/28/2025 |  | N | No
PJM | AD2-023 | East Danville - Roxborough 230 kV | Firefly Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 150 | 54 | 95 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2023_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2023_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2023_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_023_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_023_csa.pdf | Document Posted |  |  | 12/15/2024 | 12/2/2017 |  |  | 12/15/2024 |  |  | 2/28/2025 | 2/28/2025 |  | N | No
PJM | AD2-031 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | Engineering and Procurement | Dayton | 49.9 | 49.9 | 19 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2031_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2031_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_031_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_031_csa.pdf | Document Posted |  |  | 11/30/2024 | 12/15/2017 |  |  | 12/15/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AD2-038 | Powerton-Nevada 345 kV | Osagrove Flats Wind | IL | Lasalle | Engineering and Procurement | ComEd | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2038_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_038_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_038_csa.pdf | Document Posted |  |  | 9/30/2026 | 1/21/2018 |  |  | 9/30/2026 |  |  | 10/30/2026 | 10/30/2026 |  | N | No
PJM | AD2-039 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 90 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2039_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2039_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_039_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_039_csa.pdf | Document Posted |  |  |  | 1/20/2018 |  |  | 10/28/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AD2-047 | Davis Creek 138 kV | Lower Crossing Wind | IL | Kankakee | Engineering and Procurement | ComEd | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2047_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_047_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_047_csa.pdf | Document Posted |  |  | 10/31/2026 | 1/31/2018 |  |  | 10/31/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
PJM | AD2-048 | Cynthia-Headquarters 69 kV | Blue Moon Solar | KY | Harrison | Engineering and Procurement | EKPC | 70 | 70 | 46.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2048_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2048_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_048_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_048_csa.pdf | Document Posted |  |  | 9/1/2025 | 2/1/2018 |  |  | 10/1/2025 |  |  | 9/30/2025 | 9/30/2025 |  | N | No
PJM | AD2-066 | Mazon-Crescent Ridge 138 kV |  | IL | Grundy | Engineering and Procurement | ComEd | 116 | 116 | 69.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2066_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2066_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_066_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_066_csa.pdf | Document Posted |  |  | 10/10/2026 | 3/1/2018 |  |  | 11/30/2025 |  |  | 8/10/2026 | 8/10/2026 |  | N | No
PJM | AD2-086 | Hardin Switch 345 kV | Hardin Energy Center – Phase 3 | OH | Hardin | Under Construction | AEP | 230 | 230 | 138 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2086_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_086_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_086_csa.pdf | Document Posted |  |  | 9/2/2024 | 3/21/2018 |  |  | 9/16/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AD2-091 | Hardin Tap 345kV | Hardin Energy Center – Storage I | OH | Hardin | Engineering and Procurement | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2091_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2091_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_091_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_091_csa.pdf | Document Posted |  |  | 10/15/2025 | 3/20/2018 |  |  | 11/15/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AD2-092 | Marysville 345kV | Cadence Solar II Energy Center | OH | Union | Engineering and Procurement | AEP | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_092_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_092_csa.pdf | Document Posted |  |  | 11/18/2024 | 3/22/2018 |  |  | 12/18/2024 |  |  | 1/30/2026 | 1/30/2026 |  | N | No
PJM | AD2-093 | Marysville 345kV | Cadence Solar Energy Center | OH | Union | Under Construction | AEP | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_093_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_093_csa.pdf | Document Posted |  |  | 11/18/2024 | 3/21/2018 |  |  | 12/18/2024 |  |  | 1/30/2026 | 1/30/2026 |  | N | No
PJM | AD2-100 | Kincaid-Pana 345 kV | Broomstick Solar Energy Centergy Center | IL | Christian | Engineering and Procurement | ComEd | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2100_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_100_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_100_csa.pdf | Document Posted |  |  | 10/7/2028 | 3/23/2018 |  |  | 11/7/2028 |  |  | 12/7/2028 | 12/7/2028 |  | N | No
PJM | AD2-131 | Kincaid-Pana 345kV | Broomstick Solar Energy Centergy Center | IL | Christian | Engineering and Procurement | ComEd | 50 | 50 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2131_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2131_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2131_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_131_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_131_csa.pdf | Document Posted |  |  | 9/24/2026 | 3/24/2018 |  |  | 9/24/2026 |  |  | 12/7/2028 | 12/7/2028 |  | N | No
PJM | AD2-134 | Shady Oaks | Shady Oaks Wind Power Project | IL | Lee | Partially in Service - Under Construction | ComEd | 215.4 | 105.9 | 21.2 | 105.9 | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2134_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2134_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_134_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_134_csa.pdf | Document Posted |  |  | 9/7/2023 | 3/25/2018 |  |  | 9/16/2023 |  |  | 12/7/2027 | 12/7/2027 |  | N | No
PJM | AD2-135 | Williamstown 12kV | Monroe-Sicklerville Road LF Solar | NJ | Gloucester | Engineering and Procurement | AEC | 1.62 | 1.62 | 0.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2135_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2135_fac.pdf | Document Posted |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ad2135_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ad2135_wmpa.pdf | Not Required |  |  |  | 3/23/2018 |  |  | 3/1/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
PJM | AD2-158 | Old Chapel-Millville 138kV | Wild Hill Solar | WV | Jefferson | Engineering and Procurement | APS | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2158_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ad2158_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ad2_158_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_158_csa.pdf | Document Posted |  |  | 10/15/2025 | 3/24/2018 |  |  | 12/15/2025 |  |  | 9/1/2024 | 9/1/2024 |  | N | No
PJM | AD2-192 | Glen Falls 138kV | Glen Falls Facility | WV | Harrison | Engineering and Procurement | APS | 625 | 45 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2192_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_192_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ad2_192_csa.pdf | Document Posted |  |  | 8/31/2026 | 3/31/2018 |  |  | 3/31/2027 |  |  | 3/31/2028 | 3/31/2028 |  | N | No
PJM | AD2-194 | Elwood 345 kV | Jackson Generation | IL | Will | Partially in Service - Under Construction | ComEd | 1260.9 | 60 | 120 | 19.49 | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ad2194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ad2194_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ad2_194_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 3/31/2018 |  |  | 6/1/2024 |  |  | 4/26/2024 | 4/26/2024 |  | N | No
PJM | AE1-004 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 110 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1004_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_004_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 4/7/2018 |  |  | 10/15/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AE1-040 | Greenfield 69 kV | Fayette Solar | OH | Fayette | Under Construction | Dayton | 48 | 48 | 31.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1040_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1040_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_040_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_040_csa.pdf | Document Posted |  |  | 10/18/2024 | 6/26/2018 |  |  | 12/16/2024 |  |  | 5/31/2024 | 5/31/2024 |  | N | No
PJM | AE1-050 | Gavin Unit 1 765 kV | Gavin Unit No. 1 | OH | Gallia | Partially in Service - Under Construction | AEP | 1349 | 18 | 18 |  | Capacity | Generation Interconnection | Coal |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1050_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_050_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 7/20/2018 | [5 empty] | 6/9/2024 | 6/9/2024 |  | N | No
PJM | AE1-070 - moved to TC1 | Elwood 345 kV |  | IL | Will | Active | ComEd | 1610 | 0 | 135 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1070_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/31/2018 | [5 empty] | 12/31/2020 |  |  | N | No
PJM | AE1-071 | Shade Gap-Roxbury 115 kV | Aspen Road Solar | PA | Franklin | Under Construction | PENELEC | 100.1 | 100.1 | 62.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1071_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1071_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_071_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_071_csa.pdf | Document Posted |  |  | 12/9/2024 | 7/31/2018 |  |  | 12/31/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AE1-072 | Shawboro-Sligo 230 kV | Shawboro Solar | NC | Currituck | Engineering and Procurement | Dominion | 150 | 150 | 98.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1072_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1072_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_072_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_072_csa.pdf | Document Posted |  |  |  | 7/31/2018 |  |  | 11/1/2027 |  |  | 12/1/2027 | 12/1/2027 |  | N | No
PJM | AE1-075 | Powhatan 34.5 kV | Powhatan Solar I, LLC | VA | Powhatan | Under Construction | Dominion | 18 | 18 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1075_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1075_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1075_wmpa.pdf | Not Required |  |  | 1/19/2024 | 8/2/2018 |  |  | 9/2/2024 |  |  | 12/1/2023 | 12/1/2023 |  | N | No
PJM | AE1-079 | Maysville-Sharon 69 kV | Welcome Solar, LLC | PA | Mercer | Engineering and Procurement | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1079_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1079_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1079_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_079_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_079_csa.pdf | Document Posted |  |  | 3/29/2024 | 8/11/2018 |  |  | 1/29/2026 |  |  | 5/29/2024 | 5/29/2024 |  | N | No
PJM | AE1-090 | Hardin Switch 345 kV | Hardin Energy Center - Phase 3 | OH | Hardin | Under Construction | AEP | 280 | 50 | 21.56 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1090_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1090_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_090_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_090_csa.pdf | Document Posted |  |  | 9/2/2024 | 9/1/2018 |  |  | 9/16/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE1-092 - moved to TC1 | Blue Jacket-Kirby 138 kV |  | OH | Union | Active | Dayton | 229.5 | 229.5 | 96.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1092_imp.htm | Document Posted |  | In Progress | [8 empty] | 8/31/2018 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AE1-093 | Elk 138 kV | Vinton Energy Storage | OH | Vinton | Engineering and Procurement | AEP | 42 | 42 | 42 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1093_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_093_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_093_csa.pdf | Document Posted |  |  | 10/30/2026 | 8/31/2018 |  |  | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE1-106 | Lake Lynn-Hazelton 138 kV | Brandonville Solar | WV | Preston | Engineering and Procurement | APS | 99.6 | 99.6 | 59 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1106_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1106_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_106_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_106_csa.pdf | Document Posted |  |  | 10/31/2026 | 9/11/2018 |  |  | 10/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE1-108 | Bremo-Scottsville 138 kV | Riverstone Solar | VA | Buckingham | Engineering and Procurement | AEP | 149.5 | 149.5 | 89.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1108_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1108_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1108_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_108_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_108_csa.pdf | Document Posted |  |  | 12/12/2025 | 9/13/2018 |  |  | 1/12/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
PJM | AE1-109 | Frenchs Mill 34 kV | Capon Bridge Solar | WV | Hampshire | Under Construction | APS | 20 | 20 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1109_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1109_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1109_wmpa.pdf | Not Required |  |  | 6/20/2024 | 9/14/2018 |  |  | 7/10/2024 |  |  | 7/31/2024 | 7/31/2024 |  | N | No
PJM | AE1-113 | Mole Creek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 300 | 300 | 66 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1113_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1113_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_113_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_113_csa.pdf | Document Posted |  |  | 9/21/2026 | 9/14/2018 |  |  | 9/21/2026 |  |  | 1/18/2027 | 1/18/2027 |  | N | No
PJM | AE1-114 - moved to TC1 | Maryland-Lancaster 138 kV |  | IL | Ogle | Active | ComEd | 150 | 150 | 34 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1114_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/13/2018 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AE1-143 | Marion County 161 kV | Northern Bobwhite Solar | KY | Marion | Engineering and Procurement | EKPC | 96 | 96 | 64.163 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1143_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1143_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_143_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_143_csa.pdf | Document Posted |  |  | 10/1/2025 | 9/25/2018 |  |  | 11/1/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE1-144 - moved to TC1 | Goddard-Plumville 138 kV |  | KY | Fleming | Active | EKPC | 100 | 100 | 66.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1144_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1144_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/24/2018 | [5 empty] | 6/1/2022 |  |  | N | No | This project slid to the next queue
PJM | AE1-146 | Ebersole #2-Fostoria Central 138 kV | Border Basin | OH | Hancock | Engineering and Procurement | AEP | 120 | 120 | 81.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1146_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1146_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_146_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_146_csa.pdf | Document Posted |  |  | 10/3/2025 | 9/25/2018 |  |  | 11/3/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE1-148 - moved to TC1 | Kerr Dam-Ridge Rd 115 kV |  | VA | Mecklenburg | Active | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1148_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/24/2018 | [5 empty] | 12/1/2021 |  |  | N | No
PJM | AE1-155 | Garner-Northern Neck 115 kV | Bookers Mill Solar | VA | City of Richmond | Partially in Service - Under Construction | Dominion | 127 | 127 | 76.2 | 127 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1155_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1155_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_155_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_155_csa.pdf | Document Posted |  |  | 10/6/2023 | 9/26/2018 |  |  | 3/12/2024 |  |  | 5/14/2024 | 5/14/2024 |  | N | No
PJM | AE1-156 | Quakertown Solar II 34.5 kV | Quakertown Solar Farm | NJ | Hunterdon | Under Construction | JCPL | 17.6 | 7.6 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1156_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_156_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_156_csa.pdf | Document Posted |  |  |  | 9/25/2018 |  |  | 11/30/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AE1-163 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 350 | 350 | 49 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1163_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1163_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_163_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_163_csa.pdf | Document Posted |  |  | 11/1/2026 | 9/24/2018 |  |  | 11/1/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
PJM | AE1-166 | Loretto-Wilton & Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 1000 | 150 | 78 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1166_imp.html | Document Posted |  | In Progress | [8 empty] | 9/24/2018 | [5 empty] | 9/30/2020 |  |  | N | No
PJM | AE1-170 | Kenzie Creek-Colby 138 kV | Wingstem Solar Energy Farm | MI | Cass | Engineering and Procurement | AEP | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1170_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1170_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_170_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_170_csa.pdf | Document Posted |  |  | 10/31/2025 | 9/25/2018 |  |  | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE1-172 - moved to TC1 | Loretto-Wilton Center |  | IL | Livingston | Active | ComEd | 255 | 255 | 44.88 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1172_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2018 | [5 empty] | 10/1/2021 |  |  | N | No
PJM | AE1-173 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 800 | 800 | 480 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1173_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2018 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AE1-179 | South Millville-Newport 69 kV | Buckshutem Solar I | NJ | Cumberland | Engineering and Procurement | AEC | 59.7 | 59.7 | 35 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1179_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1179_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1179_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_179_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_179_csa.pdf | Document Posted |  |  |  | 9/25/2018 |  |  | 1/31/2027 |  |  | 1/31/2027 | 1/31/2027 |  | N | No
PJM | AE1-183 | Maysville-McDowell 69 kV | Jackson Center Solar Facility | PA | Mercer | Engineering and Procurement | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1183_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1183_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1183_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_183_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_183_csa.pdf | Document Posted |  |  | 4/20/2025 | 9/26/2018 |  |  | 5/1/2025 |  |  | 5/15/2023 | 5/15/2023 |  | N | No
PJM | AE1-185 | Hokes-Jackson 69 kV | Cottontail Solar 1 | PA | York | Under Construction | ME | 20 | 20 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1185_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1185_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_185_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_185_csa.pdf | Document Posted |  |  | 3/9/2023 | 9/30/2018 |  |  | 7/16/2024 |  |  | 2/28/2024 | 2/28/2024 |  | N | No
PJM | AE1-190 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1190_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1190_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_190_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_190_csa.pdf | Document Posted |  |  | 4/4/2024 | 9/28/2018 |  |  | 7/11/2024 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
PJM | AE1-191 | Harmony Village-Shackleford 115 kV | Carvers Creek Solar | VA | Gloucester | Under Construction | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1191_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae1_191_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_191_csa.pdf | Document Posted |  |  | 4/4/2024 | 9/28/2018 |  |  | 7/11/2024 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
PJM | AE1-205 | McLean 345 kV |  | IL | Livingston | Active | ComEd | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1205_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1205_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/26/2018 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AE1-209 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Engineering and Procurement | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1209_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1209_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1209_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_209_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_209_csa.pdf | Document Posted |  |  | 10/31/2025 | 9/27/2018 |  |  | 3/1/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
PJM | AE1-210 | Desoto 345 kV | Headwaters Wind Farm III | IN | Randolph | Engineering and Procurement | AEP | 100 | 100 | 13 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1210_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1210_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_210_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_210_csa.pdf | Document Posted |  |  | 10/31/2025 | 9/27/2018 |  |  | 3/1/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
PJM | AE1-218 | Glassboro 12 kV | Glassboro LF Solar | NJ | Gloucester | Under Construction | AEC | 2 | 2 | 0.82 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1218_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae1218_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae1218_wmpa.pdf | Not Required |  |  |  | 9/28/2018 |  |  | 12/2/2024 |  |  | 7/31/2024 | 7/31/2024 |  | N | No
PJM | AE1-229 | Deepwater-Upper Pittsgrove 138 kV | Pilesgrove Solar Project | NJ | Salem | Engineering and Procurement | AEC | 149.3 | 149.3 | 89 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1229_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1229_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_229_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_229_csa.pdf | Document Posted |  |  |  | 9/18/2018 |  |  | 12/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE1-237 | Andover (Maysville) 69kV I | Welcome Solar II | PA | Crawford | Engineering and Procurement | ATSI | 19.9 | 19.9 | 13.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1237_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1237_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_237_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_237_csa.pdf | Document Posted |  |  | 3/29/2024 | 9/29/2018 |  |  | 6/25/2026 |  |  | 5/29/2024 | 5/29/2024 |  | N | No
PJM | AE1-243 | Warren Glen Storage 34.5 kV | Warren Glen Storage | NJ | Warren | Under Construction | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1243_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1243_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1243_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_243_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_243_csa.pdf | Document Posted |  |  | 10/28/2024 | 9/29/2018 |  |  | 10/29/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AE1-245 | Haviland 138 kV | Grover Hill Wind Project | OH | Paulding | Engineering and Procurement | AEP | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1245_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1245_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1245_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_245_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae1_245_csa.pdf | Document Posted |  |  | 11/4/2025 | 9/18/2018 |  |  | 12/4/2025 |  |  | 2/5/2026 | 2/5/2026 |  | N | No
PJM | AE1-246 | Barren County-Summer Shade 161 kV |  | KY | Barren | Active | EKPC | 85 | 85 | 57.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1246_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1246_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/24/2018 | [5 empty] | 6/1/2022 |  |  | N | No | This project slid to the next queue
PJM | AE1-250 | Smith Mountain-E. Danville 138 kV | Blue Ridge Solar | VA | Pittsylvania | Engineering and Procurement | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae1250_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae1250_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae1250_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae1_250_isa.pdf | Document Posted | [5 empty] | 11/21/2027 | 8/31/2018 |  |  | 12/21/2027 |  |  | 1/21/2028 | 1/21/2028 |  | N | No
PJM | AE2-001 | Nittany-Zion 46 kV | Confer Solar I | PA | Centre | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2001_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2001_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_001_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_001_csa.pdf | Document Posted |  |  | 4/30/2025 | 10/2/2018 |  |  | 5/5/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
PJM | AE2-005 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 130 | 20 | 7.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2005_imp.pdf | Document Posted |  |  | https://www.pjm.com/pub/planning/project-queues/isa/ae2_005_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_005_csa.pdf | Document Posted |  |  |  | 10/5/2018 |  |  | 10/15/2025 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AE2-019 | New Road 230 kV | New Road Storage | VA | Loudoun | Engineering and Procurement | Dominion | 120 | 120 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2019_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2019_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_019_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_019_csa.pdf | Document Posted |  |  |  | 12/12/2018 |  |  | 6/1/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-020 | Cardiff 230 kV I | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2020_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2020_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_020_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_020_csa.pdf | Document Posted |  |  |  | 12/16/2018 |  |  | 8/31/2029 |  |  | 8/31/2029 | 8/31/2029 |  | N | No
PJM | AE2-021 | Cardiff 230 kV II | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 604.8 | 604.8 | 106.44 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2021_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2021_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_021_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_021_csa.pdf | Document Posted |  |  |  | 12/15/2018 |  |  | 8/31/2029 |  |  | 8/31/2029 | 8/31/2029 |  | N | No
PJM | AE2-022 | Cardiff 230 kV III | Atlantic Shores Offshore Wind Project 1 | NJ | Atlantic | Engineering and Procurement | AEC | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2022_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2022_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_022_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_022_csa.pdf | Document Posted |  |  |  | 12/15/2018 |  |  | 8/31/2029 |  |  | 8/31/2029 | 8/31/2029 |  | N | No
PJM | AE2-029 | Grottoes-Merck 115kV | Stonewall Solar | VA | Rockingham | Engineering and Procurement | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2029_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2029_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_029_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_029_csa.pdf | Document Posted |  |  |  | 12/29/2018 |  |  | 6/1/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AE2-034 | Mackeys 230 kV | Albemarle Beach Solar | NC | Washington | Partially in Service - Under Construction | Dominion | 140 | 60 | 42 | 40 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2034_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_034_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 1/16/2019 |  |  | 10/1/2023 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-038 - moved to TC1 | Goddard-Plumsville 138 kV II |  | KY | Fleming | Active | EKPC | 180 | 80 | 53.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2038_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/22/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-041 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Engineering and Procurement | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2041_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2041_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_041_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_041_csa.pdf | Document Posted |  |  | 2/28/2027 | 1/24/2019 |  |  | 12/31/2027 |  |  | 3/1/2026 | 3/1/2026 |  | N | No
PJM | AE2-042 | Milton 69 kV | Northumberland Solar | PA | Northumberland | Engineering and Procurement | PPL | 65 | 65 | 43.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2042_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2042_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_042_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_042_csa.pdf | Document Posted |  |  | 10/4/2024 | 1/25/2019 |  |  | 10/15/2024 |  |  | 11/4/2024 | 11/4/2024 |  | N | No
PJM | AE2-045 | Olive-Reynolds 345 kV |  | IN | Lake | Active | AEP | 200 | 200 | 84.28 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2045_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/29/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AE2-046 | Harwood-East Hazelton 69 kV | McAdoo Solar | PA | Schuylkill | Engineering and Procurement | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2046_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2046_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_046_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_046_csa.pdf | Document Posted |  |  | 2/12/2025 | 2/1/2019 |  |  | 3/12/2025 |  |  | 3/16/2025 | 3/16/2025 |  | N | No
PJM | AE2-047 | Ridgeway-Solite 69 kV | Henry County Solar Facility | VA | Henry | Engineering and Procurement | AEP | 50 | 50 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2047_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2047_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_047_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_047_csa.pdf | Document Posted |  |  | 6/30/2026 | 1/31/2019 |  |  | 8/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-048 | Muskingum-W. Millersport 345 kV |  | OH | Fairfield | Active | AEP | 220 | 220 | 147.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2048_imp.htm | Document Posted |  | In Progress | [8 empty] | 1/31/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-051 | Carson-Septa 500 kV | Big Pine Solar | VA | Sussex | Engineering and Procurement | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2051_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2051_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ae2_051_gia.pdf | Document Posted | [6 empty] | 1/31/2019 | [5 empty] | 8/1/2031 | 8/1/2031 |  | N | No
PJM | AE2-054 | Warfordsburg 34 kV | Blairs Valley | PA | Franklin | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2054_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2054_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2054_wmpa.pdf | Not Required |  |  |  | 2/2/2019 |  |  | 8/30/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
PJM | AE2-059 | Derry Tap-Derry Bus 69 kV | Cottontail Solar 4 aka East Chilli Solar | PA | Northumberland | Under Construction | PPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2059_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2059_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_059_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_059_csa.pdf | Document Posted |  |  | 2/2/2024 | 2/6/2019 |  |  | 7/15/2024 |  |  | 5/31/2024 | 5/31/2024 |  | N | No
PJM | AE2-064 | Beaverbrook 13 kV | Kinsley 2 Beaverbrook Solar | NJ | Gloucester | Partially in Service - Under Construction | PSEG | 5.8 | 2 | 0.85 | 3.8 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2064_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_064_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_064_csa.pdf | Document Posted |  |  |  | 2/7/2019 |  |  | 1/30/2024 |  |  | 8/31/2020 | 8/31/2020 |  | N | No
PJM | AE2-065 | Romeoville 12 kV | Kinsley 2 Deptford Solar | NJ | Gloucester | Partially in Service - Under Construction | PSEG | 6.8 | 1.8 | 0.76 | 1.8 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2065_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2065_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_065_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_065_csa.pdf | Document Posted |  |  |  | 2/6/2019 |  |  | 6/1/2023 |  |  | 8/31/2020 | 8/31/2020 | 9/19/2020 | N | No
PJM | AE2-071 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | Partially in Service - Under Construction | EKPC | 35 | 35 | 21 | 35 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2071_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2071_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_071_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_071_csa.pdf | Document Posted |  |  | 4/1/2024 | 2/18/2019 |  |  | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 |  | N | No
PJM | AE2-072 | East Leipsic-Richland 138 kV | Powell Creek Solar | OH | Putnam | Engineering and Procurement | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2072_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2072_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2072_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_072_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_072_csa.pdf | Document Posted |  |  | 12/5/2024 | 2/15/2019 |  |  | 12/6/2024 |  |  | 6/2/2025 | 6/2/2025 |  | N | No
PJM | AE2-073 | Centerburg 138kV |  | OH | Licking | Active | AEP | 200 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2073_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2073_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/15/2019 | [5 empty] | 11/1/2021 |  |  | N | No
PJM | AE2-074 | Potter 46 kV | Potter Solar | PA | Potter | Engineering and Procurement | APS | 35 | 35 | 15.11 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2074_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2074_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2074_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2074_wmpa.pdf | Not Required |  |  |  | 2/20/2019 | [5 empty] | 9/30/2023 | 9/30/2023 |  | N | No
PJM | AE2-089 | Pennville-Adams 138 kV | Skycrest Solar Energy Center | IN | Jay | Engineering and Procurement | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2089_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2089_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_089_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_089_csa.pdf | Document Posted |  |  | 4/15/2026 | 2/22/2019 |  |  | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-092 | Kidds Store-Sherwood 115 kV | Woodridge Solar | VA | Albemarle | Engineering and Procurement | Dominion | 138 | 138 | 82.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2092_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_092_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_092_csa.pdf | Document Posted |  |  | 11/12/2026 | 2/26/2019 |  |  | 12/1/2026 |  |  | 10/1/2026 | 10/1/2026 |  | N | No
PJM | AE2-093 | Easton-Steele 138 kV | Crockett Solar Project | MD | Talbot | Engineering and Procurement | DPL | 44 | 44 | 16.72 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_093_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_093_csa.pdf | Document Posted |  |  |  | 2/26/2019 |  |  | 3/31/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
PJM | AE2-094 | Carson-Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 300 | 300 | 207.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2094_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/26/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-104 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Engineering and Procurement | Dominion | 49 | 49 | 18.92 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2104_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2104_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_104_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_104_csa.pdf | Document Posted |  |  | 8/12/2025 | 3/2/2019 |  |  | 9/15/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AE2-113 | Farmers Valley-Ridgeway 115 kV | Ridgeway Solar | PA | McKean | Engineering and Procurement | PENELEC | 120 | 120 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2113_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2113_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2113_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_113_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_113_csa.pdf | Document Posted |  |  | 1/1/2025 | 3/1/2019 |  |  | 1/1/2025 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
PJM | AE2-117 | ABW Tap-Alexandria 46 kV | HU-Pauls | PA | Huntingdon | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2117_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2117_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_117_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_117_csa.pdf | Document Posted |  |  | 5/1/2025 | 3/1/2019 |  |  | 5/1/2025 |  |  | 5/20/2024 | 5/20/2024 |  | N | No
PJM | AE2-122 | Birdneck-Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 800.1 | 800.1 | 158.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2122_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/28/2019 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AE2-125 | Stahlstown-Ligonier 25 kV | Stahlstown-Ligonier 25 kV | PA | Westmoreland | Under Construction | APS | 13.8 | 13.8 | 8.28 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2125_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2125_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2125_wmpa.pdf | Not Required |  |  | 8/30/2024 | 3/2/2019 |  |  | 9/15/2024 |  |  | 11/15/2024 | 11/15/2024 |  | N | No
PJM | AE2-134 | Locust Grove-Paytes 115 kV | Pine Glade Solar | VA | Orange | Under Construction | Dominion | 62.5 | 0 | 16.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2134_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_134_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_134_csa.pdf | Document Posted |  |  | 5/30/2024 | 3/5/2019 |  |  | 7/11/2024 |  |  | 7/15/2024 | 7/15/2024 |  | N | No
PJM | AE2-136 | Muskingum River-W. Millersport 345 kV |  | OH | Fairfield | Active | AEP | 114 | 114 | 83.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2136_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/6/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-138 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 260 | 260 | 189.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2138_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2138_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/8/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-139 | East Towanda-Grover 230 kV | Bradford Solar | PA | McKean | Engineering and Procurement | PENELEC | 100.5 | 100.5 | 60.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2139_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2139_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2139_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ae2_139_gia.pdf | Document Posted | [5 empty] | 9/1/2026 | 3/9/2019 |  |  | 11/16/2026 |  |  | 12/15/2026 | 12/15/2026 |  | N | No
PJM | AE2-147 - moved to TC1 | Swamp 230 kV |  | NC | Perquimans | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2147_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/13/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AE2-148 | Beatty-Greene 345 kV | Fox Squirrel Solar | OH | Madison | Partially in Service - Under Construction | AEP | 577 | 577 | 397.3 | 400 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2148_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2148_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_148_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_148_csa.pdf | Document Posted |  |  |  | 2/22/2019 |  |  | 11/14/2023 |  |  | 11/1/2023 | 11/1/2023 |  | N | No
PJM | AE2-152 | Loretto-Wilton & Braidwood-Davis Creek |  | IL | Kankakee | Active | ComEd | 1150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2152_imp.html | Document Posted |  | In Progress | [8 empty] | 3/4/2019 | [5 empty] | 9/30/2020 |  |  | N | No
PJM | AE2-156 - moved to TC1 | Yadkin 115 kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2156_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/15/2019 | [5 empty] | 12/1/2021 |  |  | N | No
PJM | AE2-160 | Kanawha River 138 kV |  | WV | Fayette | Active | AEP | 51 | 51 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2160_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2160_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/15/2019 | [5 empty] | 10/1/2021 |  |  | N | No
PJM | AE2-166 | Stockton 138 kV | Rocky Ford Solar Energy Center | VA | Henry | Engineering and Procurement | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2166_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2166_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_166_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_166_csa.pdf | Document Posted |  |  | 3/30/2026 | 3/16/2019 |  |  | 5/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-172 | Mississinewa-Gaston 138 kV | Golden Aster Solar Energy Center | IN | Grant | Engineering and Procurement | AEP | 200 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2172_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2172_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2172_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_172_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_172_csa.pdf | Document Posted |  |  | 3/30/2026 | 3/15/2019 |  |  | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
PJM | AE2-173 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2173_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/18/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AE2-175 | Jackson-Long Pond 69 kV | Swiftwater Solar | PA | Monroe | Under Construction | PPL | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2175_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2175_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2175_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_175_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_175_csa.pdf | Document Posted |  |  | 10/31/2024 | 3/19/2019 |  |  | 11/29/2024 |  |  | 6/30/2025 | 6/30/2025 |  | N | No
PJM | AE2-176 | Groton 138 kV Solar | Wheatsborough Solar | OH | Erie | Under Construction | ATSI | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2176_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2176_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_176_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_176_csa.pdf | Document Posted |  |  | 12/1/2024 | 3/19/2019 |  |  | 12/1/2024 |  |  | 4/30/2025 | 4/30/2025 |  | N | No
PJM | AE2-181 | Snyder 69kV | Montpelier Solar | OH | Williams | Engineering and Procurement | ATSI | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2181_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2181_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2181_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_181_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_181_csa.pdf | Document Posted |  |  | 9/30/2025 | 3/18/2019 |  |  | 9/30/2025 |  |  | 5/1/2025 | 5/1/2025 |  | N | No
PJM | AE2-185 - moved to TC1 | Gladys DP-Stonemill Switching Station 69 kV | Gladys II Solar Farm | VA | Campbell | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2185_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2185_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/18/2019 | [5 empty] | 9/1/2020 |  |  | N | No
PJM | AE2-187 - moved to TC1 | Shockoe DP-Chatham 69 kV |  | VA | Pittsylvania | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2187_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/18/2019 | [5 empty] | 9/1/2020 |  |  | N | No
PJM | AE2-204 | Bolivar 34.5 kV | Bolivar Solar | OH | Stark | Engineering and Procurement | AEP | 19.3 | 19.3 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2204_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2204_fac.pdf | Document Posted |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2204_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2204_wmpa.pdf | Not Required |  |  | 10/30/2026 | 3/19/2019 |  |  | 11/30/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-206 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | Under Construction | Dayton | 99 | 99 | 41.58 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2206_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2206_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_206_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_206_csa.pdf | Document Posted |  |  | 6/1/2024 | 3/20/2019 |  |  | 12/16/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
PJM | AE2-210 - moved to TC1 | Avon-North Clark 345 kV |  | KY | Clark | Active | EKPC | 90 | 90 | 65.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2210_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/20/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-212 | Harrowgate 34 kV | Harrowgate 1 | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2212_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2212_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2212_wmpa.pdf | Not Required |  |  |  | 3/20/2019 |  |  | 1/1/2025 |  |  | 3/30/2025 | 3/30/2025 |  | N | No
PJM | AE2-214 | Cole 345 kV | Pleasant Prairie Solar | OH | Franklin | Engineering and Procurement | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2214_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2214_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2214_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_214_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_214_csa.pdf | Document Posted |  |  | 10/31/2025 | 3/23/2019 |  |  | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE2-216 | Hardin Switch 345 kV | Hardin Energy Center – Storage II | OH | Hardin | Engineering and Procurement | AEP | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2216_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2216_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2216_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_216_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_216_csa.pdf | Document Posted |  |  | 10/15/2026 | 3/21/2019 |  |  | 11/15/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-219 | Bluff Point-Randolph 138 kV | Riverstart Solar Park V | IN | Randolph | Engineering and Procurement | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2219_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2219_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2219_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_219_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_219_csa.pdf | Document Posted |  |  | 3/31/2026 | 3/21/2019 |  |  | 4/30/2026 |  |  | 5/31/2026 | 5/31/2026 |  | N | No
PJM | AE2-220 | Losantville 345 kV | Riverstart Solar Park II | IN | Randolph | Active | AEP | 125 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2220_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2220_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/21/2019 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AE2-221 | Clinton-Stuart 345 kV | Yellow Wood Solar Energy Center | OH | Clinton | Engineering and Procurement | Dayton | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2221_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2221_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_221_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_221_csa.pdf | Document Posted |  |  | 6/30/2025 | 3/21/2019 |  |  | 11/24/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE2-223 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 150 | 19.5 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2223_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2223_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/22/2019 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AE2-226 | Millville-Old Chapel 138 kV | Rippon | WV | Jefferson | Engineering and Procurement | APS | 99 | 99 | 59.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2226_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2226_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2226_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_226_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_226_csa.pdf | Document Posted |  |  | 10/15/2025 | 3/22/2019 |  |  | 11/30/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE2-227 | Iron Bridge 34 kV | Bradley Ridge Solar | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2227_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2227_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2227_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2227_wmpa.pdf | Not Required |  |  |  | 3/22/2019 |  |  | 5/1/2025 |  |  | 3/30/2025 | 3/30/2025 |  | N | No
PJM | AE2-228 | Tyler 34 kv | Bradley BridgeSolar | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2228_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2228_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ae2228_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ae2228_wmpa.pdf | Not Required |  |  |  | 3/22/2019 |  |  | 5/1/2025 |  |  | 3/30/2025 | 3/30/2025 |  | N | No
PJM | AE2-230 | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | Under Construction | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2230_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2230_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2230_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_230_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_230_csa.pdf | Document Posted |  |  | 10/11/2024 | 3/24/2019 |  |  | 10/25/2024 |  |  | 7/1/2024 | 7/1/2024 |  | N | No
PJM | AE2-231 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2231_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/22/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AE2-234 | Liberty Center-Buckeye Tap 69 kV |  | IN | Huntington | Active | AEP | 35 | 35 | 24.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2234_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2234_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/22/2019 | [5 empty] | 7/31/2021 |  |  | N | No
PJM | AE2-249 | Bedford North-Pennsylvania Hollow 23 kV | BE-ASTOR | PA | Bedford | Engineering and Procurement | PENELEC | 16.6 | 16.6 | 9.96 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2249_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ae2_249_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_249_csa.pdf | Document Posted |  |  | 6/30/2025 | 3/25/2019 |  |  | 6/30/2025 |  |  | 7/1/2021 | 7/1/2021 |  | N | No
PJM | AE2-250 - moved to TC1 | Purdy Sw.-Reams 115 kV |  | VA | Greensville | Active | Dominion | 82.5 | 82.5 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2250_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2250_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/26/2019 | [5 empty] | 9/30/2021 |  |  | N | No
PJM | AE2-255 | Molecreek 345 kV | Panther Grove 2 | IL | Woodford | Engineering and Procurement | ComEd | 400 | 100 | 25 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2255_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2255_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2255_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_255_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_255_csa.pdf | Document Posted |  |  | 9/21/2026 | 3/26/2019 |  |  | 9/21/2026 |  |  | 1/18/2027 | 1/18/2027 |  | N | No
PJM | AE2-256 | Copperstone-North Lebanon 230 kV | Lebanon Solar | PA | Lebanon | Engineering and Procurement | ME | 70 | 70 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2256_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2256_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2256_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_256_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_256_csa.pdf | Document Posted |  |  | 6/1/2026 | 3/27/2019 |  |  | 7/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
PJM | AE2-259 | Curdsville-Willis Mtn 115 kV | Blue Rock Solar | VA | Buckingham | Engineering and Procurement | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2259_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2259_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2259_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ae2_259_gia.pdf | Document Posted | [6 empty] | 3/28/2019 | [5 empty] | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-261 - moved to TC1 | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 299 | 299 | 179.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2261_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2261_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/28/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-267 | Woodsdale 345 kV | Woodsdale Renewable Energy Center | OH | Butler | Engineering and Procurement | DEOK | 49 | 49 | 28.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2267_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2267_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2267_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_267_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_267_csa.pdf | Document Posted |  |  | 5/1/2026 | 3/29/2019 |  |  | 5/1/2026 |  |  | 6/1/2026 | 6/1/2026 |  | N | No
PJM | AE2-275 - moved to TC1 | JK Smith-Fawkes 138 kV |  | KY | Madison | Active | EKPC | 90 | 90 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2275_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2275_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/28/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AE2-276 | Sullivan 345kV |  | IN | Sullivan | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2276_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2276_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/28/2019 | [5 empty] | 12/31/2020 |  |  | N | No
PJM | AE2-281 | Powerton-Nevada 345 kV | Panther Grove Wind | IL | Woodford | Engineering and Procurement | ComEd | 400 | 50 | 7 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2281_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2281_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2281_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_281_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_281_csa.pdf | Document Posted |  |  | 11/1/2026 | 3/29/2019 |  |  | 11/1/2026 |  |  | 2/1/2027 | 2/1/2027 |  | N | No
PJM | AE2-283 - moved to TC1 | Gladys-Stone Mill 69 kV |  | VA | Campbell | Active | Dominion | 53 | 53 | 28 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2283_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2283_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/29/2019 | [5 empty] | 9/30/2021 |  |  | N | No
PJM | AE2-289 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 80 | 80 | 11.76 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2289_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2289_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2289_fac.pdf | Document Posted | [8 empty] | 3/29/2019 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AE2-291 - moved to TC1 | Grit DP-Perth 115 kV |  | VA | Pittsylvania | Active | Dominion | 102 | 102 | 61.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2291_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/29/2019 | [5 empty] | 4/1/2021 |  |  | N | No
PJM | AE2-298 | Cavett Switch - West Van Wert 69 kV |  | OH | Van Wert | Active | AEP | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2298_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2298_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2298_fac.pdf | Document Posted | [8 empty] | 3/22/2019 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AE2-305 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 78 | 78 | 46.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2305_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2305_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/29/2019 | [5 empty] | 8/1/2021 |  |  | N | No
PJM | AE2-308 - moved to TC1 | Three Forks-Dale 138 kV | Madison Solar 1 | KY | Madison | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2308_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2308_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ae2_308_isa2.pdf | Interim Study | [6 empty] | 3/29/2019 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AE2-313 - moved to TC1 | Carson-Rawlings 500 kV |  | VA | Dinwiddie | Active | Dominion | 314 | 314 | 188.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2313_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2313_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/29/2019 | [5 empty] | 9/15/2022 |  |  | N | No
PJM | AE2-318 | Ford-Cedarville 138 kV | Clermont County Solar Project | OH | Clermont | Engineering and Procurement | DEOK | 100 | 100 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2318_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2318_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2318_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_318_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_318_csa.pdf | Document Posted |  |  | 9/1/2024 | 3/31/2019 |  |  | 10/1/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AE2-321 - moved to TC1 | Belvidere-Marengo 138 kV |  | IL | McHenry | Active | ComEd | 100 | 100 | 67 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2321_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2321_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2019 | [5 empty] | 12/1/2021 |  |  | N | No
PJM | AE2-322 | Mark Center 69 kV | Mark Center Solar Project | OH | Defiance | Engineering and Procurement | AEP | 60 | 60 | 40.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2322_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2322_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2322_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_322_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_322_csa.pdf | Document Posted |  |  | 6/25/2025 | 3/30/2019 |  |  | 6/25/2025 |  |  | 5/31/2025 | 5/31/2025 |  | N | No
PJM | AE2-323 | Twin Branch-Guardian 138 kV | Elkhart County Solar Project | IN | Elkhart | Engineering and Procurement | AEP | 100 | 100 | 67.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2323_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2323_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2323_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_323_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_323_csa.pdf | Document Posted |  |  | 10/31/2025 | 3/30/2019 |  |  | 2/15/2026 |  |  | 5/1/2026 | 5/1/2026 |  | N | No
PJM | AE2-325 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2325_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2325_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AE2-326 | Jacksons Ferry 138 kV |  | VA | Wythe | Active | AEP | 127.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2326_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2326_imp.html | Document Posted |  | In Progress | [8 empty] | 3/30/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AE2-333 | Bedington 138 kV | Bedington Energy Facility | MD | Frederick | Engineering and Procurement | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2333_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2333_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2333_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_333_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_333_csa.pdf | Document Posted |  |  | 6/15/2025 | 4/1/2019 |  |  | 6/15/2025 |  |  | 10/31/2025 | 10/31/2025 |  | N | No
PJM | AE2-334 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Engineering and Procurement | AEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2334_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2334_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2334_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_334_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_334_csa.pdf | Document Posted |  |  |  | 4/1/2019 |  |  | 12/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AE2-339 | Avon 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2339_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2339_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2339_fac.pdf | Document Posted | [8 empty] | 3/31/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AE2-341 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 150 | 150 | 100.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2341_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2341_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AE2-342 | Woodstock 69 kV | Woodstock Solar | OH | Champaign | Engineering and Procurement | Dayton | 40 | 40 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2342_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2342_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2342_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_342_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_342_csa.pdf | Document Posted |  |  | 2/15/2025 | 3/31/2019 |  |  | 3/17/2025 |  |  | 4/15/2025 | 4/15/2025 |  | N | No
PJM | AE2-343 | Andover (Maysville) 69 kV II | Welcome Solar III, LLC | PA | Crawford | Engineering and Procurement | ATSI | 17.9 | 17.9 | 12.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2343_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2343_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2343_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_343_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_343_csa.pdf | Document Posted |  |  | 3/29/2024 | 4/1/2019 |  |  | 7/30/2026 |  |  | 5/29/2024 | 5/29/2024 |  | N | No
PJM | AE2-345 | Hunterstown-Texas Eastern Tap 115 kV | Granite Hill Solar | PA | Adams | Engineering and Procurement | ME | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ae2345_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ae2345_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ae2345_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ae2_345_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ae2_345_csa.pdf | Document Posted |  |  | 1/2/2026 | 3/13/2019 |  |  | 1/12/2026 |  |  | 2/1/2026 | 2/1/2026 |  | N | No
PJM | AF1-006 | Fairview East 34.5 kV | Erie Solar | PA | Erie | Engineering and Procurement | PENELEC | 20 | 20 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1006_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1006_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1006_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1006_wmpa.pdf | Not Required |  |  | 9/13/2024 | 4/2/2019 |  |  | 10/4/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AF1-007 | Indian River 230 kV I | Maryland Offshore Wind Energy Project (MOWEP) | DE | Sussex | Engineering and Procurement | DPL | 255.1 | 7.3 | 1.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1007_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1007_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_007_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_007_csa.pdf | Document Posted |  |  | 2/1/2027 | 4/1/2019 |  |  | 12/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
PJM | AF1-014 | Harmony Village-Shackleford 115 kV | Walnut Solar I | VA | King and Queen | Under Construction | Dominion | 149.9 | 19.9 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1014_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_014_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_014_csa.pdf | Document Posted |  |  |  | 4/4/2019 |  |  | 10/28/2025 |  |  | 3/31/2025 | 3/31/2025 |  | N | No
PJM | AF1-015 | Easton-Steele 138 kV II | Crockett Solar Project | MD | Talbot | Engineering and Procurement | DPL | 59 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1015_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1015_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_015_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_015_csa.pdf | Document Posted |  |  |  | 4/3/2019 |  |  | 3/31/2026 |  |  | 3/31/2026 | 3/31/2026 |  | N | No
PJM | AF1-018 | Harmony Village 230 kV | Drake Storage | VA | Middlesex | Engineering and Procurement | Dominion | 80 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1018_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1018_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_018_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_018_csa.pdf | Document Posted |  |  |  | 4/3/2019 |  |  | 2/1/2026 |  |  | 3/1/2026 | 3/1/2026 |  | N | No
PJM | AF1-019 | Branchville-Holiday Lakes 34.5 kV | Viridity Energy Solutions Montague Storage | NJ | Sussex | Under Construction | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1019_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1019_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_019_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_019_csa.pdf | Document Posted |  |  | 10/31/2024 | 4/6/2019 |  |  | 11/30/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
PJM | AF1-021 | Bethelboro-Connellsville #1 25 kV | Pechin Solar | PA | Fayette | Under Construction | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1021_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1021_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1021_wmpa.pdf | Not Required |  |  | 7/31/2024 | 4/17/2019 |  |  | 8/30/2024 |  |  | 11/30/2024 | 11/30/2024 |  | N | No
PJM | AF1-022 | Lake Lynn-Uniontown 25 kV | Gans Solar Farm | PA | Fayette | Under Construction | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1022_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1022_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1022_wmpa.pdf | Not Required |  |  | 8/30/2024 | 4/16/2019 |  |  | 9/27/2024 |  |  | 11/30/2024 | 11/30/2024 |  | N | No
PJM | AF1-028 | Endless Caverns 115 kV | Prospect Power | VA | Rockingham | Engineering and Procurement | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1028_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1028_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1028_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_028_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_028_csa.pdf | Document Posted |  |  |  | 5/13/2019 |  |  | 1/1/2026 |  |  | 2/1/2026 | 2/1/2026 |  | N | No
PJM | AF1-030 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 250 | 100 | 66.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1030_imp.pdf | Document Posted |  | In Progress | [8 empty] | 5/17/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AF1-038 | Sewellton Jct-Webbs Crossroads 69 kV | Mt Olive Creek Solar | KY | Russell | Engineering and Procurement | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1038_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1038_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_038_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_038_csa.pdf | Document Posted |  |  | 6/30/2026 | 6/8/2019 |  |  | 7/30/2026 |  |  | 9/30/2026 | 9/30/2026 |  | N | No
PJM | AF1-045 | Cedarville-Ford 138 kV | Clermont County Solar Project | OH | Clermont | Engineering and Procurement | DEOK | 152.2 | 52.2 | 31.3 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1045_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1045_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1045_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_045_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_045_csa.pdf | Document Posted |  |  | 9/1/2024 | 6/28/2019 |  |  | 10/1/2024 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AF1-048 - moved to TC1 | Belvidere-Marengo |  | IL | McHenry | Active | ComEd | 152.2 | 52.2 | 31.32 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1048_imp.pdf | Document Posted |  | In Progress | [8 empty] | 6/28/2019 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF1-049 | Berry Hill 138 kV |  | VA | Pittsylvania | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1049_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1049_imp.htm | Document Posted |  | In Progress | [8 empty] | 7/12/2019 | [5 empty] | 11/25/2022 |  |  | N | No
PJM | AF1-050 | Summer Shade - Green County 161 kV | Horseshoe Bend Solar | KY | Green | Engineering and Procurement | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1050_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1050_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_050_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_050_csa.pdf | Document Posted |  |  | 8/31/2026 | 7/14/2019 |  |  | 9/15/2026 |  |  | 11/30/2026 | 11/30/2026 |  | N | No
PJM | AF1-051 | Gavin 765 kV | Gavin Unit No. 1 | OH | Gallia | Engineering and Procurement | AEP | 1360 | 11 | 11 |  | Capacity | Generation Interconnection | Coal |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1051_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_051_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 7/13/2019 |  |  | 5/20/2025 |  |  | 5/31/2024 | 5/31/2024 |  | N | No
PJM | AF1-053 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 118 | 40 | 16 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1053_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/31/2019 | [5 empty] | 12/1/2021 |  |  | N | No
PJM | AF1-054 | Givens-Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 156.5 | 38.5 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1054_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/31/2019 | [5 empty] | 12/1/2021 |  |  | N | No
PJM | AF1-062 | Jug Street 138 kV | Flint Grid | OH | Licking | Engineering and Procurement | AEP | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1062_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1062_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1062_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_062_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_062_csa.pdf | Document Posted |  |  | 5/1/2026 | 7/31/2019 |  |  | 7/1/2026 |  |  | 11/1/2026 | 11/1/2026 |  | N | No
PJM | AF1-063 | Lockwood Road 138 kV |  | OH | Defiance | Active | AEP | 30 | 30 | 19.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1063_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_063_isa2.pdf | Interim Study | [6 empty] | 7/31/2019 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AF1-064 | Weston 69 kV | Juliet Energy | OH | Wood | Engineering and Procurement | ATSI | 50 | 50 | 33.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1064_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1064_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1064_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_064_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_064_csa.pdf | Document Posted |  |  | 8/1/2025 | 7/31/2019 |  |  | 8/1/2025 |  |  | 11/30/2025 | 11/30/2025 |  | N | No
PJM | AF1-069 | Carson-Rogers Rd 500 kV |  | VA | Sussex | Active | Dominion | 394 | 94 | 67.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1069_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/9/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF1-071 | College Corner 138 kV |  | OH | Preble | Active | AEP | 98 | 18 | 6.84 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1071_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/13/2019 | [5 empty] | 7/1/2019 |  |  | N | No
PJM | AF1-078 | East Sidney-Quincy 138 kV | Clearview Solar I | OH | Champaign | Under Construction | Dayton | 144 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1078_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_078_isa.pdf | Document Posted |  |  | Not Required |  |  | 6/30/2024 | 8/27/2019 |  |  | 12/16/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
PJM | AF1-083 | Green County-Saloma 161 kV | Flat Run Solar | KY | Barren | Engineering and Procurement | EKPC | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1083_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1083_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_083_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_083_csa.pdf | Document Posted |  |  | 10/27/2026 | 8/31/2019 |  |  | 11/30/2026 |  |  | 12/15/2026 | 12/15/2026 |  | N | No
PJM | AF1-084 | Hartford-Almena 69 kV |  | MI | Van Buren | Active | AEP | 85 | 85 | 54.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1084_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1084_fac.pdf | Document Posted | [8 empty] | 8/30/2019 | [5 empty] | 10/1/2022 |  |  | N | No
PJM | AF1-086 | Madera-Westover South 115 kV | Rogue's Wind | PA | Clearfield | Engineering and Procurement | PENELEC | 109.9 | 109.9 | 20.54 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1086_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1086_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_086_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_086_csa.pdf | Document Posted |  |  | 8/15/2025 | 8/30/2019 |  |  | 9/30/2025 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
PJM | AF1-090 | Kincaid-Pana |  | IL | Christian | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1090_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/30/2019 | [5 empty] | 9/1/2022 |  |  | N | No
PJM | AF1-091 | Varner - Sowers 138 kV |  | IN | DeKalb | Active | AEP | 180 | 180 | 138.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1091_imp.htm | Document Posted |  | In Progress | [8 empty] | 8/30/2019 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AF1-092 | Huntington Jct. 138 kV |  | IN | Huntington | Engineering and Procurement | AEP | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1092_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1092_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1092_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_092_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_092_csa.pdf | Document Posted |  |  | 5/28/2026 | 8/30/2019 |  |  | 6/30/2026 |  |  | 6/1/2022 |  |  | N | No
PJM | AF1-093 | Henderson-Stoneboro 69 kV | Jackson Center Solar II | PA | Mercer | Engineering and Procurement | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1093_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1093_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1093_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_093_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_093_csa.pdf | Document Posted |  |  | 10/15/2025 | 8/31/2019 |  |  | 10/20/2025 |  |  | 8/15/2024 | 8/15/2024 |  | N | No
PJM | AF1-094 | Union City-Cambridge Springs 34.5 kV | Franklin Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1094_imp.htm | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_094_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_094_csa.pdf | Document Posted |  |  | 7/6/2026 | 8/30/2019 |  |  | 7/6/2026 |  |  | 9/20/2026 | 9/20/2026 |  | N | No
PJM | AF1-099 - moved to TC1 | Moshannon-Milesburg 230 kV III |  | PA | Clearfield | Active | APS | 126.5 | 126.5 | 75.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1099_fea.pdf | Document Posted | [12 empty] | 9/4/2019 | [5 empty] | 4/1/2022 |  |  | N | No
PJM | AF1-104 | Erie West 34.5 kV | Elder West | PA | Erie | Engineering and Procurement | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1104_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1104_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1104_wmpa.pdf | Not Required |  |  |  | 9/10/2019 |  |  | 9/1/2026 |  |  | 10/15/2026 | 10/15/2026 |  | N | No
PJM | AF1-106 | East Sayre 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage; Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1106_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/10/2019 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AF1-112 | Centre Hall-Boalsburg 46 kV | Centre Hall | PA | Centre | Engineering and Procurement | APS | 15 | 15 | 8.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1112_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1112_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1112_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1112_wmpa.pdf | Not Required |  |  |  | 9/10/2019 | [5 empty] | 10/31/2026 | 10/31/2026 |  | N | No
PJM | AF1-116 | Marion County 161 kV |  | KY | Washington | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af116_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/12/2019 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AF1-118 | Sorenson-Desoto 345 kV |  | IN | Wells | Active | AEP | 350 | 350 | 268.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1118_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1118_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/13/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF1-119 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1119_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1119_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/13/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF1-123 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 833 | 833 | 253.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1123_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1123_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_123_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_123_csa.pdf | Document Posted |  |  |  | 9/17/2019 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AF1-124 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 836 | 836 | 254.1 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1124_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_124_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_124_csa.pdf | Document Posted |  |  |  | 9/17/2019 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AF1-125 - moved to TC1 | Oceana 230 kV |  | VA | City of Chesapeake | Active | Dominion | 820 | 820 | 249.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1125_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_125_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_125_csa.pdf | Document Posted |  |  |  | 9/17/2019 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AF1-128 - moved to TC1 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1128_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1128_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_128_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_128_csa.pdf | Document Posted |  |  | 3/31/2028 | 9/18/2019 |  |  | 6/30/2028 |  |  | 6/1/2023 |  |  | N | No
PJM | AF1-129 | Chesterfield 230 kV | Chesterfield CT Units 3&4 | VA | Chesterfield | Engineering and Procurement | Dominion | 569 | 569 | 569 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1129_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1129_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1129_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_129_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_129_csa.pdf | Document Posted |  |  | 3/31/2028 | 9/18/2019 |  |  | 6/30/2028 |  |  | 12/31/2029 | 12/31/2029 |  | N | No
PJM | AF1-130 | Inez 138 kV | Martin County Solar Project | KY | Martin | Under Construction | AEP | 190 | 190 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1130_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1130_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_130_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_130_csa.pdf | Document Posted |  |  | 6/3/2024 | 9/19/2019 |  |  | 9/30/2024 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
PJM | AF1-140 | Claysburg 23 kV | BL-Diamond Bear Rocks | PA | Adams | Engineering and Procurement | PENELEC | 16.3 | 16.3 | 9.78 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1140_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1140_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1140_wmpa.pdf | Not Required |  |  |  | 9/19/2019 |  |  | 10/31/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AF1-141 | Varner 138 kV |  | IN | DeKalb | Active | AEP | 96 | 96 | 62.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1141_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1141_imp.htm | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_141_isa2.pdf | Interim Study | [6 empty] | 8/30/2019 | [5 empty] | 5/31/2022 |  |  | N | No
PJM | AF1-142 - moved to TC1 | Moshannon-Milesburg 230 kV IV |  | PA | Clearfield | Active | APS | 202.4 | 202.4 | 121.44 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1142_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/4/2019 | [5 empty] | 4/1/2022 |  |  | N | No
PJM | AF1-143 | Lick Run 115 kV |  | PA | Somerset | Active | PENELEC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1143_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1143_fac.pdf | Document Posted | [8 empty] | 9/18/2019 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AF1-147 | Poland Rd-Runway DP 230kV | Dulles Solar | VA | Loudoun | Engineering and Procurement | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1147_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1147_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_147_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_147_csa.pdf | Document Posted |  |  | 7/15/2025 | 9/20/2019 |  |  | 7/15/2026 |  |  | 12/31/2023 | 12/31/2023 |  | N | No
PJM | AF1-148 | Sorenson-Desoto 345 kV |  | IN | Wells | Active | AEP | 159 | 159 | 95.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1148_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/19/2019 | [5 empty] | 4/30/2023 |  |  | N | No
PJM | AF1-152 - moved to TC1 | Swamp 230 kV |  | NC | Pasquotank | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1152_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/19/2019 | [5 empty] | 10/2/2023 |  |  | N | No
PJM | AF1-155 | Paper City-Wilcox 46 kV | FR-Boyer Mill Guilford34.5 | PA | Elk | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1155_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1155_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1155_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1155_wmpa.pdf | Not Required |  |  |  | 9/19/2019 | [5 empty] | 2/28/2023 | 2/28/2023 |  | N | No
PJM | AF1-158 | Edison-Gravel Pit 138 kV | Honeysuckle Solar Project | IN | St. Joseph | Partially in Service - Under Construction | AEP | 150 | 150 | 90 | 150 | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1158_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1158_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1158_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_158_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_158_csa.pdf | Document Posted |  |  | 4/23/2024 | 9/24/2019 |  |  | 6/6/2024 |  |  | 1/31/2025 | 1/31/2025 |  | N | No
PJM | AF1-159 | Martinsville-Wilmington 69 kV | Clinton Solar | OH | Clinton | Engineering and Procurement | Dayton | 49.9 | 0 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1159_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1159_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1159_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_159_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_159_csa.pdf | Document Posted |  |  | 11/30/2024 | 9/20/2019 |  |  | 12/15/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AF1-161 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1161_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1161_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/20/2019 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AF1-162 | Inez 138 kV |  | KY | Martin | Active | AEP | 300 | 100 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1162_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_162_isa2.pdf | Interim Study | [6 empty] | 9/20/2019 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF1-164 | Southwest Lima 345 kV |  | OH | Allen | Active | AEP | 300 | 300 | 195 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1164_imp.htm | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_164_isa2.pdf | Interim Study | [6 empty] | 9/20/2019 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AF1-165 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1165_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/23/2019 | [5 empty] | 5/1/2022 |  |  | N | No
PJM | AF1-170 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Active | PENELEC | 77.5 | 77.5 | 46.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1170_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/23/2019 | [5 empty] | 2/15/2023 |  |  | N | No
PJM | AF1-176 - moved to TC1 | Corey 138 kV |  | MI | St. Joseph | Active | AEP | 300 | 300 | 155.684 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1176_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1176_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2019 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AF1-202 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 34 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1202_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1202_imp.html | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_202_isa2.pdf | Interim Study | [6 empty] | 9/25/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF1-203 | Patton Rd-Summer Shade 69 kV | Glover Creek Solar | KY | Metcalfe | Partially in Service - Under Construction | EKPC | 55 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1203_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1203_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1203_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_203_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_203_csa.pdf | Document Posted |  |  | 4/15/2024 | 9/29/2019 |  |  | 5/2/2024 |  |  | 4/30/2024 | 4/30/2024 |  | N | No
PJM | AF1-204 - moved to TC1 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 255 | 255 | 63.75 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1204_imp.html | Document Posted |  | In Progress | [8 empty] | 9/25/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF1-206 | East Fayette 138 kV |  | OH | Fulton | Active | ATSI | 199 | 199 | 119.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1206_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1206_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1206_fac.pdf | Document Posted | [8 empty] | 9/26/2019 | [5 empty] | 11/1/2022 |  |  | N | No
PJM | AF1-207 | Reynolds-Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 180 | 34 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1207_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1207_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/27/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF1-208 | Laurel-Roadstown 69 kV |  | NJ | Salem | Active | AEC | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1208_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1208_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1208_fac.pdf | Document Posted | [8 empty] | 9/26/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AF1-210 | Burma 23 kV | CL-Route 58 S | PA | Clarion | Engineering and Procurement | APS | 15.9 | 15.9 | 9.54 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1210_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1210_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1210_wmpa.pdf | Not Required |  |  |  | 9/26/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF1-211 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1211_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1211_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/26/2019 | [5 empty] | 5/1/2022 |  |  | N | No
PJM | AF1-212 | Campbelltown-Millars Quarry 69 kV |  | PA | Lebanon | Active | ME | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1212_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1212_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/26/2019 | [5 empty] | 5/1/2022 |  |  | N | No
PJM | AF1-215 | Olive-Reynolds 345 kV | Mammoth North Solar Project | IN | Starke | Under Construction | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1215_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1215_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1215_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_215_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_215_csa.pdf | Document Posted |  |  | 8/20/2024 | 9/28/2019 |  |  | 8/21/2024 |  |  | 7/31/2024 | 7/31/2024 |  | N | No
PJM | AF1-217 | Edinboro -Cambridge Springs 34.5 kV | Crawford Solar II | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1217_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1217_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1217_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1217_wmpa.pdf | Not Required |  |  |  | 9/28/2019 |  |  | 12/31/2025 |  |  | 3/29/2024 | 3/29/2024 |  | N | No
PJM | AF1-221 - moved to TC1 | College Corner-Drewersburg 138 kV |  | IN | Franklin | Active | AEP | 180 | 180 | 25.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1221_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/27/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF1-223 | Keystone-Desoto 345 kV |  | IN | Jay | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1223_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1223_imp.html | Document Posted |  | In Progress | [8 empty] | 9/27/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF1-227 | Marysville – Gunn Road 345 kV | Union Solar | OH | Union | Partially in Service - Under Construction | AEP | 325 | 325 | 195 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1227_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1227_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1227_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_227_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_227_csa.pdf | Document Posted |  |  | 4/9/2024 | 9/30/2019 |  |  | 5/14/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AF1-228 | Beatty-Greene 345 kV | Springwater Solar | OH | Madison | Engineering and Procurement | AEP | 155 | 155 | 93 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1228_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1228_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1228_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_228_gia.pdf | Document Posted | [5 empty] | 4/21/2026 | 9/27/2019 |  |  | 4/21/2026 |  |  | 8/31/2026 | 8/31/2026 |  | N | No
PJM | AF1-229 | Galion-South Berwick 345 kV | Tymochtee Solar | OH | Wyandot | Engineering and Procurement | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1229_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1229_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_229_gia.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_229_csa.pdf | Document Posted |  |  | 4/21/2026 | 9/27/2019 |  |  | 4/21/2026 |  |  | 8/31/2026 | 8/31/2026 |  | N | No
PJM | AF1-231 | New Church 138 kV |  | VA | Accomack | Active | DPL | 19 | 19 | 7.6 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1231_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/27/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF1-233 - moved to TC1 | Flemingsburg – Spurlock 138kV | AEUG Fleming Solar | KY | Fleming | Active | EKPC | 188.5 | 188.5 | 113.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1233_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1233_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af1_233_isa2.pdf | Interim Study | [6 empty] | 9/27/2019 | [5 empty] | 5/31/2022 |  |  | N | No
PJM | AF1-237 | Mercer 230 kV | Lamberton Road Battery | NJ | Mercer | Engineering and Procurement | PSEG | 170 | 170 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1237_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1237_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_237_gia.pdf | Document Posted | [6 empty] | 9/27/2019 | [5 empty] | 8/11/2027 | 8/11/2027 |  | N | No | This project slid to the next queue
PJM | AF1-238 - moved to TC1 | Sherman Ave - West Vineland 69 kV |  | NJ | Cumberland | Active | AEC | 77.7 | 77.7 | 31 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1238_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1238_imp.pdf | Document Posted |  | Withdrawn | [8 empty] | 9/28/2019 | [5 empty] | 5/31/2023 |  |  | N | No | This project slid to the next queue
PJM | AF1-239 | Sherman Ave - West Vineland 69 kV | South Orchard | NJ | Cumberland | Engineering and Procurement | AEC | 30 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1239_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1239_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1239_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1239_wmpa.pdf | Not Required |  |  | 3/1/2028 | 9/28/2019 |  |  | 5/1/2028 |  |  | 6/1/2028 | 6/1/2028 |  | N | No
PJM | AF1-240 - moved to TC1 | Timblin 34.5 kV |  | PA | Armstrong | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1240_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1240_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 7/1/2022 |  |  | N | No
PJM | AF1-245 | Hudson 230 kV |  | NJ | Hudson | Active | PSEG | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1245_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1245_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1245_fac.pdf | Document Posted | [8 empty] | 9/30/2019 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AF1-249 | Nickel 12.47 kV | Nickel Solar | OH | Warren | Under Construction | DEOK | 19.92 | 19.92 | 14 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1249_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1249_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1249_wmpa.pdf | Not Required |  |  | 7/23/2024 | 10/2/2019 |  |  | 7/23/2024 |  |  | 7/30/2024 | 7/30/2024 |  | N | No
PJM | AF1-254 | Milnor-Huyetts 34.5 kV | FR-Williamsport | PA | Franklin | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1254_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1254_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1254_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1254_wmpa.pdf | Not Required |  |  | 10/31/2025 | 9/30/2019 |  |  | 11/28/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AF1-256 - moved to TC1 | Flemingsburg-Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1256_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1256_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AF1-264 | Runnemede 13 kV | Owens Corning Solar | NJ | Gloucester | Partially in Service - Under Construction | PSEG | 3 | 0 | 1.3 | 3 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1264_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1264_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af1_264_isa.pdf | Document Posted |  |  | Not Required |  |  | 5/1/2021 | 9/30/2019 |  |  | 5/15/2021 |  |  | 9/30/2023 | 9/30/2023 | 6/1/2021 | N | No
PJM | AF1-268 | Desoto-Jay 138 kV |  | IN | Delaware | Active | AEP | 83 | 83 | 57.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1268_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1268_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 1/31/2022 |  |  | N | No
PJM | AF1-271A | Gratz 69 kV | G Morris Solar | PA | Dauphin | Engineering and Procurement | PPL | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1271a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1271A_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1271a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_271a_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_271a_csa.pdf | Document Posted |  |  | 1/31/2026 | 9/27/2019 |  |  | 3/2/2026 |  |  | 4/15/2026 | 4/15/2026 |  | N | No
PJM | AF1-272 | Lucerne 115 kV | Hoodlebug Solar Energy Center | PA | Indiana | Engineering and Procurement | PENELEC | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1272_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1272_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1272_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af1_272_gia.pdf | Document Posted | [5 empty] | 5/31/2027 | 10/1/2019 |  |  | 6/21/2027 |  |  | 8/31/2027 | 8/31/2027 |  | N | No
PJM | AF1-275 | Cole 345 kV |  | OH | Franklin | Active | AEP | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1275_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1275_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF1-280 - moved to TC1 | Nelson-Lee County |  | IL | Lee | Active | ComEd | 200 | 200 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1280_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1280_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/10/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AF1-282 | Stuart-Clinton 345 kV |  | OH | Highland | Active | Dayton | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1282_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1282_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 8/20/2022 |  |  | N | No
PJM | AF1-283 | Stuart-Clinton 345 kV |  | OH | Highland | Active | Dayton | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1283_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1283_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 8/1/2022 |  |  | N | No
PJM | AF1-291 | Tyler 34.5 kV | Chester Solar Technology Park | VA | Chesterfield | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1291_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1291_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1291_wmpa.pdf | Not Required |  |  |  | 9/30/2019 |  |  | 3/30/2025 |  |  | 10/31/2022 | 10/31/2022 |  | N | No
PJM | AF1-291A | Bartonsville-Meadow Brook 138 kV | Bartonsville Energy Facility | VA | Frederick | Under Construction | APS | 80 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1291a_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1291a_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1291a_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_291a_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_291a_csa.pdf | Document Posted |  |  | 10/11/2024 | 10/1/2019 |  |  | 10/25/2024 |  |  | 7/1/2024 | 7/1/2024 |  | N | No
PJM | AF1-292 | Fields 34.5kV | Jarratt Solar | VA | Greensville | Engineering and Procurement | Dominion | 14.9 | 14.9 | 8.94 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1292_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1292_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1292_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1292_wmpa.pdf | Not Required |  |  |  | 9/30/2019 | [5 empty] | 8/29/2027 | 8/29/2027 |  | N | No
PJM | AF1-294 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 41 | 41 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1294_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1294_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AF1-296 - moved to TC1 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 212.1 | 212.1 | 37.3296 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1296_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1296_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 9/15/2022 |  |  | N | No
PJM | AF1-299 | Otter Point 34.5 kV I | Fairview Farms II | MD | Harford | Under Construction | BGE | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1299_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1299_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1299_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1299_wmpa.pdf | Not Required |  |  |  | 9/30/2019 |  |  | 12/30/2024 |  |  | 12/30/2024 | 12/30/2024 |  | N | No
PJM | AF1-300 | Otter Point 34.5 kV II | Fairview Farms I | MD | Harford | Under Construction | BGE | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1300_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1300_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af1300_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af1300_wmpa.pdf | Not Required |  |  |  | 9/30/2019 |  |  | 12/30/2024 |  |  | 12/30/2024 | 12/30/2024 |  | N | No
PJM | AF1-302 | Brookville-Squab Hollow 138 kV |  | PA | Jefferson | Active | APS | 132 | 42 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1302_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1302_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AF1-314 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 212 | 212 | 37.2 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1314_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2019 | [5 empty] | 9/15/2022 |  |  | N | No
PJM | AF1-319 | Honda Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 58 | 58 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1319_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1319_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AF1-321 | Hooversville 115 kV I | SunEast Hooversville Solar | PA | Somerset | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1321_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1321_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1321_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_321_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_321_csa.pdf | Document Posted |  |  | 5/1/2026 | 9/30/2019 |  |  | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
PJM | AF1-322 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1322_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1322_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/23/2019 | [5 empty] | 8/15/2022 |  |  | N | No
PJM | AF1-323 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1323_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1323_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 12/12/2022 |  |  | N | No
PJM | AF1-325 | Sparta-Woodruff's Gap 34.5 kV | Houses Corner Storage | NJ | Sussex | Engineering and Procurement | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1325_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1325_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1325_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_325_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_325_csa.pdf | Document Posted |  |  | 12/1/2025 | 9/30/2019 |  |  | 12/15/2025 |  |  | 1/1/2026 | 1/1/2026 |  | N | No
PJM | AF1-328 | Hackettstown-Pohatcong 34.5 kV | Mansfield #3 | NJ | Warren | Engineering and Procurement | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1328_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1328_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1328_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af1_328_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af1_328_csa.pdf | Document Posted |  |  | 2/17/2025 | 9/30/2019 |  |  | 2/18/2025 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
PJM | AF1-330 | Marengo 34.5 kV |  | IL | McHenry | Active | ComEd | 20 | 20 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1330_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1330_imp.htm | Document Posted |  | Not Required |  |  |  |  | Not Required |  |  |  | 9/30/2019 | [5 empty] | 9/15/2021 |  |  | N | No
PJM | AF1-331 | Twombley Road |  | IL | Ogle | Active | ComEd | 60 | 20 | 20 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1331_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1331_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2019 | [5 empty] | 9/15/2021 |  |  | N | No
PJM | AF1-333 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1333_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1333_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1333_fac.pdf | Document Posted | [8 empty] | 9/27/2019 | [5 empty] | 3/1/2021 |  |  | N | No
PJM | AF1-337 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1337_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1337_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1337_fac.pdf | Document Posted | [8 empty] | 9/27/2019 | [5 empty] | 3/1/2021 |  |  | N | No
PJM | AF1-338 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1338_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1338_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1338_fac.pdf | Document Posted | [8 empty] | 9/27/2019 | [5 empty] | 3/1/2021 |  |  | N | No
PJM | AF1-339 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af1339_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af1339_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af1339_fac.pdf | Document Posted | [8 empty] | 9/27/2019 | [5 empty] | 3/1/2021 |  |  | N | No
PJM | AF2-001 | Hooversville 115 kV II | SunEast Hooversville Solar | PA | Somerset | Engineering and Procurement | PENELEC | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2001_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2001_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_001_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_001_csa.pdf | Document Posted |  |  | 5/1/2026 | 10/1/2019 |  |  | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
PJM | AF2-002 | Hooversville 115 kV III | SunEast Hooversville Solar | PA | Somerset | Engineering and Procurement | PENELEC | 50 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2002_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2002_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2002_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_002_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_002_csa.pdf | Document Posted |  |  | 5/1/2026 | 10/1/2019 |  |  | 5/1/2026 |  |  | 8/1/2026 | 8/1/2026 |  | N | No
PJM | AF2-004 | Beaver 345 kV |  | OH | Lorain | Active | ATSI | 378.2 | 33 | 33 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2004_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/1/2019 | [5 empty] | 11/1/2020 |  |  | N | No
PJM | AF2-005 | Beaver 138 kV |  | OH | Lorain | Active | ATSI | 95.2 | 8 | 8 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2005_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2005_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/1/2019 | [5 empty] | 11/1/2020 |  |  | N | No
PJM | AF2-010 - moved to TC1 | Union City-Titusville 115 kV |  | PA | Erie | Active | PENELEC | 77 | 77 | 46 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2010_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2010_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/11/2019 | [5 empty] | 12/15/2022 |  |  | N | No
PJM | AF2-013 | Arnold's Corner-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2013_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2013_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/15/2019 | [5 empty] | 10/1/2023 |  |  | N | No
PJM | AF2-014 | Maddox Creek 345 kV |  | OH | Van Wert | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2014_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2014_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/18/2019 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-018 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 200 | 133.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2018_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2018_imp.htm | Document Posted |  | In Progress | [8 empty] | 11/1/2019 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-019 | Middle 69 kV |  | NJ | Cape May | Active | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2019_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2019_imp.pdf | Document Posted |  | In Progress | [8 empty] | 11/15/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-020 | Carll's Corner 69 kV |  | NJ | Cumberland | Active | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2020_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2020_imp.pdf | Document Posted |  | In Progress | [8 empty] | 11/15/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-024 | Mickleton 69 kV |  | NJ | Gloucester | Active | AEC | 24 | 24 | 9.6 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2024_imp.htm | Document Posted |  | In Progress | [8 empty] | 11/15/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-025 - moved to TC1 | Ontario 69 kV |  | NJ | Atlantic | Active | AEC | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2025_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2025_imp.pdf | Document Posted |  | In Progress | [8 empty] | 11/15/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-027 | Zion Energy Center 345 kV |  | IL | Lake | Active | ComEd | 635 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2027_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2027_imp.pdf | Document Posted |  | In Progress | [8 empty] | 11/15/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-029 | Ronco 500 kV |  | PA | Fayette | Active | APS | 726 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2029_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2029_imp.htm | Document Posted |  | In Progress | [8 empty] | 10/28/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-030 | Ontelaunee 230 kV |  | PA | Berks | Active | ME | 650 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2030_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2030_imp.htm | Document Posted |  | In Progress | [8 empty] | 10/28/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-031 | Calumet |  | IL | Cook | Active | ComEd | 347 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2031_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/28/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-032 | Kincaid 345 kV |  | IL | Christian | Active | ComEd | 1132 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2032_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2032_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/28/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-034 - moved to TC1 | Kendall 345kV |  | IL | Kendall | Active | ComEd | 1238.8 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2034_imp.pdf | Document Posted |  | In Progress | [8 empty] | 10/28/2019 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-035 - moved to TC1 | St. Johns 115 kV |  | VA | Hanover | Active | Dominion | 72 | 72 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2035_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2035_imp.pdf | Document Posted |  | Withdrawn | [8 empty] | 11/27/2019 | [5 empty] | 10/27/2023 |  |  | N | No
PJM | AF2-037 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 94 | 94 | 56.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2037_imp.pdf | Document Posted |  | In Progress | [8 empty] | 11/29/2019 | [5 empty] | 7/1/2021 |  |  | N | No
PJM | AF2-039 | Shawville-Clearfield 34.5 kV |  | PA | Clearfield | Engineering and Procurement | PENELEC | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2039_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2039_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2039_wmpa.pdf | Not Required |  |  |  | 11/29/2019 |  |  | 7/3/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
PJM | AF2-041 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2041_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2041_imp.pdf | Document Posted |  | In Progress | [8 empty] | 12/9/2019 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AF2-042 - moved to TC1 | Clover-Rawlings 500 kV |  | VA | Halifax | Active | Dominion | 500 | 500 | 300 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2042_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2042_imp.pdf | Document Posted |  | In Progress | [8 empty] | 12/9/2019 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF2-046 - moved to TC1 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 150 | 150 | 99.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2046_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2046_imp.pdf | Document Posted |  | In Progress | [8 empty] | 12/19/2019 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-048 | Rio-Lick 138 kV |  | OH | Jackson | Active | AEP | 140 | 70 | 46.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2048_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2048_imp.htm | Document Posted |  | In Progress | [8 empty] | 12/19/2019 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AF2-050 - moved to TC1 | Bearrock-Johnstown 230 kV |  | PA | Cambria | Active | PENELEC | 150 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2050_imp.pdf | Document Posted |  | In Progress | [8 empty] | 12/23/2019 | [5 empty] | 9/1/2021 |  |  | N | No
PJM | AF2-054 | Wan 34.5 kV | Camellia Solar | VA | Gloucester | Engineering and Procurement | Dominion | 19.9 | 19.9 | 11.94 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2054_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2054_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2054_wmpa.pdf | Not Required |  |  |  | 1/10/2020 | [5 empty] | 8/29/2027 | 8/29/2027 |  | N | No
PJM | AF2-056 - moved to TC1 | Shenandoah Tap 1– Mahanoy Tap 2 69 kV |  | PA | Schuylkill | Active | PPL | 50 | 50 | 33 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2056_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2056_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/16/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AF2-060 | Wattsville 12 kV | Scout Storage I | VA | Accomack | Engineering and Procurement | DPL | 9 | 9 | 9 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2060_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2060_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2060_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2060_wmpa.pdf | Not Required |  |  |  | 1/25/2020 |  |  | 10/1/2024 |  |  | 10/1/2024 | 10/1/2024 |  | N | No
PJM | AF2-061 | Wattsville 69kV |  | VA | Accomack | Active | DPL | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2061_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2061_imp.htm | Document Posted |  | In Progress | [8 empty] | 1/24/2020 | [5 empty] | 6/30/2021 |  |  | N | No
PJM | AF2-063 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2063_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/29/2020 | [5 empty] | 2/1/2023 |  |  | N | No
PJM | AF2-066 | West Manchester-Crown 69kV |  | OH | Preble | Active | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2066_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/30/2020 | [5 empty] | 10/3/2022 |  |  | N | No
PJM | AF2-067 | West Manchester 69 kV |  | OH | Preble | Active | Dayton | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2067_imp.htm | Document Posted |  | In Progress | [8 empty] | 1/30/2020 | [5 empty] | 10/3/2022 |  |  | N | No
PJM | AF2-068 - moved to TC1 | Jay 138 kV |  | IN | Blackford | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2068_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2068_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/30/2020 | [5 empty] | 10/3/2022 |  |  | N | No
PJM | AF2-069 - moved to TC1 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 88.7 | 9.3 | 2.2 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2069_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2069_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/31/2020 | [5 empty] | 10/4/2021 |  |  | N | No
PJM | AF2-070 - moved to TC1 | Crescent Ridge 138 kV |  | IL | Bureau | Active | ComEd | 72.6 | 18.15 | 3.1 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2070_fea.pdf | Document Posted |  | In Progress | [10 empty] | 1/31/2020 | [5 empty] | 10/4/2021 |  |  | N | No
PJM | AF2-075 | Bartonsville-Meadow Brook 138 kV III | Bartonsville Energy Facility | VA | Frederick | Under Construction | APS | 130 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2075_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2075_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2075_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_075_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_075_csa.pdf | Document Posted |  |  | 10/11/2024 | 2/1/2020 |  |  | 10/25/2024 |  |  | 7/1/2024 | 7/1/2024 |  | N | No
PJM | AF2-077 | White Marsh 34.5 kV | Winterberry Solar | VA | Gloucester | Partially in Service - Under Construction | Dominion | 20 | 20 | 12 | 20 | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2077_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2077_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2077_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2077_wmpa.pdf | Not Required |  |  |  | 2/1/2020 |  |  | 6/26/2024 |  |  | 8/14/2024 | 8/14/2024 |  | N | No
PJM | AF2-078 | Reynolds-Olive #1 345 kV |  | IN | White | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2078_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2078_imp.html | Document Posted |  | In Progress | [8 empty] | 2/1/2020 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AF2-080 - moved to TC1 | Chinquapin-Everetts 230 kV |  | NC | Pitt | Active | Dominion | 150 | 70 | 48.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2080_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2080_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/31/2020 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AF2-081 - moved to TC1 | Moyock 230 kV |  | NC | Currituck | Active | Dominion | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2081_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2081_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/31/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-082 | Dauphin PG Tie–Dauphin Juniata Tie 69 k |  | PA | Dauphin | Active | PPL | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2082_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2082_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/31/2020 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AF2-083 | Kenzie Creek-Stone Lake 69 kV |  | MI | Cass | Active | AEP | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2083_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2083_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_083_isa2.pdf | Interim Study | [6 empty] | 1/31/2020 | [5 empty] | 10/21/2022 |  |  | N | No
PJM | AF2-084 | Honda-Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 100 | 42 | 28.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2084_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2084_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/31/2020 | [5 empty] | 12/30/2022 |  |  | N | No
PJM | AF2-086 | Scott Tap-Bowmans Mill Tap 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2086_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/3/2020 | [5 empty] | 8/1/2022 |  |  | N | No
PJM | AF2-088 | Shawville-Clearfield 34.5 kV II |  | PA | Clearfield | Engineering and Procurement | PENELEC | 20 | 6.5 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2088_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2088_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2088_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2088_wmpa.pdf | Not Required |  |  |  | 2/5/2020 |  |  | 7/3/2026 |  |  | 9/1/2026 | 9/1/2026 |  | N | No
PJM | AF2-090 | Central Hardin 138 kV |  | KY | Hardin | Active | EKPC | 110 | 110 | 73.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2090_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2090_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/6/2020 | [5 empty] | 10/1/2022 |  |  | N | No
PJM | AF2-091 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 134 | 34 | 14.28 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2091_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/7/2020 | [5 empty] | 11/30/2021 |  |  | N | No
PJM | AF2-094 | Huntington Jct. 138 kV |  | IN | Huntington | Active | AEP | 190 | 40 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2094_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2094_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/12/2020 | [5 empty] | 2/1/2022 |  |  | N | No
PJM | AF2-095 - moved to TC1 | Davis Creek 138 kV |  | IL | Kankakee | Active | ComEd | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2095_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2095_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/13/2020 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AF2-096 - moved to TC1 | Braidwood-East Frankfort 345 kV |  | IL | Will | Active | ComEd | 375 | 375 | 255 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2096_fea.pdf | Document Posted |  | In Progress | [10 empty] | 2/12/2020 | [5 empty] | 5/31/2022 |  |  | N | No
PJM | AF2-103 | Haviland 138 kV | Northwest Ohio Wind | OH | Paulding | Partially in Service - Under Construction | AEP | 103.15 | 3.15 | 1.32 | 2 | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af2_103_isa.pdf | Document Posted |  |  | Not Required |  |  |  | 3/17/2020 | [5 empty] | 2/1/2021 | 2/1/2021 | 6/1/2021 | N | No
PJM | AF2-105 | Morgans Cut-Glen Lyn #2 138 kV |  | VA | Pulaski | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2105_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2105_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2105_fac.pdf | Document Posted | [8 empty] | 1/31/2020 | [5 empty] | 3/28/2022 |  |  | N | No
PJM | AF2-106 | Hazel Hollow-Glen Lyn #1 138 kV |  | VA | Pulaski | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2106_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2106_imp.pdf | Document Posted |  | In Progress | [8 empty] | 1/31/2020 | [5 empty] | 3/28/2022 |  |  | N | No
PJM | AF2-107 | Clifford 138 kV |  | VA | Amherst | Active | AEP | 50 | 50 | 32.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2107_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/24/2020 | [5 empty] | 2/1/2022 |  |  | N | No
PJM | AF2-110 | Suffolk 115 kV | Switchgrass Solar 1 | VA | Accomack | Engineering and Procurement | Dominion | 69 | 20 | 7.72 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2110_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2110_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af2_110_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_110_csa.pdf | Document Posted |  |  | 8/12/2025 | 2/27/2020 |  |  | 9/15/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AF2-111 - moved to TC1 | North Clark-Spurlock 345 kV |  | KY | Mason | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2111_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2111_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/28/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-114 | Old Chapel-Millville 138 kV II |  | WV | Jefferson | Active | APS | 92.5 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2114_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2114_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/28/2020 | [5 empty] | 9/30/2022 |  |  | N | No
PJM | AF2-115 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 66 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2115_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2115_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/28/2020 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AF2-116 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 90 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2116_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2116_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2116_fac.pdf | Document Posted | [8 empty] | 2/28/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AF2-117 | Warfordsburg-McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 70 | 70 | 46.67 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2117_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2117_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/28/2020 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AF2-120 - moved to TC1 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 62 | 62 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2120_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2120_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_120_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_120_csa.pdf | Document Posted |  |  | 12/1/2025 | 2/28/2020 |  |  | 2/6/2026 |  |  | 12/1/2023 |  |  | N | No
PJM | AF2-121 - moved to TC1 | Philipsburg-Shawville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2121_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2121_imp.htm | Document Posted |  | Withdrawn | [8 empty] | 2/28/2020 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-122 | Kirk 138 kV | Union Ridge Solar | OH | Licking | Engineering and Procurement | AEP | 107.7 | 107.7 | 64.62 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2122_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2122_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2122_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_122_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_122_csa.pdf | Document Posted |  |  |  | 2/29/2020 |  |  | 10/15/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AF2-124 | Kyger Creek-Pierce 345 kV |  | OH | Highland | Active | OVEC | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2124_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/28/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-125 | Varner 138 kV |  | IN | DeKalb | Active | AEP | 150 | 54 | 35.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2125_imp.htm | Document Posted |  | In Progress | [8 empty] | 2/28/2020 | [5 empty] | 4/3/2023 |  |  | N | No
PJM | AF2-126 - moved to TC1 | Weston 69 kV II |  | OH | Wood | Active | ATSI | 62 | 12 | 8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2126_imp.pdf | Document Posted |  | In Progress | [8 empty] | 2/28/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AF2-127 | Lockwood Road 138 kV |  | OH | Defiance | Active | AEP | 68 | 38 | 24.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2127_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2127_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_127_isa2.pdf | Interim Study | [6 empty] | 2/28/2020 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AF2-130 | Wolfs Corners 34.5 kV | Cobalt Solar | PA | Clarion | Under Construction | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2130_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2130_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2130_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_130_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_130_csa.pdf | Document Posted |  |  | 8/30/2024 | 3/3/2020 |  |  | 9/2/2024 |  |  | 12/15/2024 | 12/15/2024 |  | N | No
PJM | AF2-132 | Reynolds-Olive #1 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2132_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2132_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/4/2020 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AF2-133 | Reynolds-Olive #2 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2133_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2133_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/4/2020 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AF2-134 | Olive-Reynolds #2 345 kV | Mammoth North Solar Project | IN | Starke | Under Construction | AEP | 400 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2134_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2134_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2134_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_134_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_134_csa.pdf | Document Posted |  |  | 8/20/2024 | 3/6/2020 |  |  | 8/21/2024 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
PJM | AF2-137 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 500 | 500 | 210 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2137_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2137_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/6/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-140 | Saegers 230 kV |  | PA | Lycoming | Active | PPL | 907 | 0 | 30 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2140_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2140_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/11/2020 | [5 empty] | 5/1/2021 |  |  | N | No
PJM | AF2-142 - moved to TC1 | Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2142_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2142_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/12/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-143 - moved to TC1 | Powerton-Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2143_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2143_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/12/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-149 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2149_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2149_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/12/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-150 | Galion 138 kV | Blossom Solar | OH | Morrow | Engineering and Procurement | ATSI | 88 | 88 | 36.96 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2150_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2150_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2150_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_150_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_150_csa.pdf | Document Posted |  |  | 1/31/2026 | 3/13/2020 |  |  | 1/31/2026 |  |  | 4/30/2026 | 4/30/2026 |  | N | No
PJM | AF2-162 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 245 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2162_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2162_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/16/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AF2-165 | Clark Summit-Emlenton 34.5 kV | Cardinal Solar | PA | Venango | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2165_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2165_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2165_wmpa.pdf | Not Required |  |  |  | 3/18/2020 |  |  | 10/31/2024 |  |  | 12/15/2024 | 12/15/2024 |  | N | No
PJM | AF2-171 - moved to TC1 | Madisonville 115 kV |  | VA | Prince Edward | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2171_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2171_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/19/2020 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AF2-173 - moved to TC1 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 200 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2173_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2173_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/19/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-177 - moved to TC1 | Sorenson-DeSoto #2 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2177_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2177_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/20/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-182 - moved to TC1 | Nelson-Lee County 345 kV II |  | IL | Lee | Active | ComEd | 500 | 300 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2182_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/21/2020 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AF2-187 | Brookside-Cloverdale 138 kV |  | OH | Wayne | Active | ATSI | 120 | 120 | 78 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2187_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2187_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2187_fac.pdf | Document Posted | [8 empty] | 3/22/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AF2-191 | New Carlisle 138 kV |  | IN | St. Joseph | Active | AEP | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2191_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/22/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AF2-192 | Frenchtown Solar-West Flemington 34.5 kV | Barbertown Solar | NJ | Hunterdon | Engineering and Procurement | JCPL | 7 | 7 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2192_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2192_imp.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2192_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_192_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_192_csa.pdf | Document Posted |  |  | 3/31/2026 | 3/23/2020 |  |  | 4/30/2026 |  |  | 6/30/2026 | 6/30/2026 |  | N | No
PJM | AF2-199 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 400 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2199_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2199_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/24/2020 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AF2-200 - moved to TC1 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2200_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2200_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/24/2020 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AF2-201 - moved to TC1 | Lena - Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 199 | 199 | 51.4 |  | Capacity | Generation Interconnection | Wind; Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2201_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/24/2020 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AF2-204 | Van Buren-Delaware 138 kV |  | IN | Grant | Active | AEP | 110 | 110 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2204_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2204_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/24/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AF2-205 | Olive-Reynolds #2 345 kV | Moss Creek Solar | IN | Pulaski | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2205_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2205_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_205_isa2.pdf | Interim Study | [5 empty] | 10/30/2027 | 3/25/2020 |  |  | 11/30/2027 |  |  | 11/30/2027 | 11/30/2027 |  | N | No
PJM | AF2-209 - moved to TC1 | South Hicksville-Sowers 138 kV |  | OH | Defiance | Active | AEP | 140 | 140 | 19.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2209_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2209_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/25/2020 | [5 empty] | 6/2/2023 |  |  | N | No
PJM | AF2-221 | Scalp Level 22.9 kV | Stony Creek Solar | PA | Somerset | Engineering and Procurement | PENELEC | 15 | 15 | 6.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2221_imp.html | Document Posted |  |  |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2221_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2221_wmpa.pdf | Not Required |  |  |  | 3/25/2020 |  |  | 8/1/2025 |  |  | 10/1/2025 | 10/1/2025 |  | N | No
PJM | AF2-222 - moved to TC1 | Madisonville DP-Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 167 | 167 | 100 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2222_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2222_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/af2_222_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_222_csa.pdf | Document Posted |  |  | 12/31/2025 | 3/25/2020 |  |  | 3/31/2027 |  |  | 5/31/2023 |  |  | N | No
PJM | AF2-224 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2224_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2224_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/26/2020 | [5 empty] | 9/30/2022 |  |  | N | No
PJM | AF2-225 - moved to TC1 | McLean 345 kV |  | IL | McLean | Active | ComEd | 150 | 150 | 63 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2225_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2225_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/26/2020 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AF2-226 - moved to TC1 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2226_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2226_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/26/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-229 | Roxbury 23 kV |  | PA | Cumberland | Active | PENELEC | 20 | 20 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2229_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2229_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/26/2020 | [5 empty] | 11/30/2021 |  |  | N | No
PJM | AF2-233 | Penns-Richfield Tie #1 69 kV |  | PA | Snyder | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2233_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2233_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/26/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AF2-234 | Sunbury Yard #1-Richfield Tie #2 69 kV |  | PA | Snyder | Active | PPL | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2234_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2234_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/26/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AF2-235 | Titusville-Oil Creek 34.5 kV | Big Bell Solar | PA | Crawford | Engineering and Procurement | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2235_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2235_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2235_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/af2_235_gia.pdf | Document Posted | [5 empty] | 4/30/2027 | 3/27/2020 |  |  | 6/7/2027 |  |  | 7/31/2027 | 7/31/2027 |  | N | No
PJM | AF2-238 | Mansfield-South Troy 34.5 kV | Farmers Valley Solar | PA | Bradford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2238_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2238_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2238_fac.pdf | Document Posted | [8 empty] | 3/26/2020 | [5 empty] | 7/31/2027 | 7/31/2027 |  | N | No
PJM | AF2-243 | Clark Summit 34.5 kV | Pearl Solar | PA | Venango | Engineering and Procurement | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2243_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2243_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2243_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2243_wmpa.pdf | Not Required |  |  |  | 3/27/2020 |  |  | 7/3/2026 |  |  | 9/2/2026 | 9/2/2026 |  | N | No
PJM | AF2-249 | Edgewood 12 kV II | Citron Storage | MD | Wicomico | Engineering and Procurement | DPL | 3 | 3 | 0.6 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2249_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2249_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2249_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2249_wmpa.pdf | Not Required |  |  |  | 3/27/2020 |  |  | 12/2/2024 |  |  | 11/30/2023 | 11/30/2023 |  | N | No
PJM | AF2-252 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 248 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2252_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2252_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/27/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-260 | Stephensburg-Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 85 | 85 | 53 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2260_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/27/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-291 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2291_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/28/2020 | [5 empty] | 5/1/2022 |  |  | N | No
PJM | AF2-295 | Wilcox-Paper City 46 kV | Evergreen Solar | PA | Elk | Engineering and Procurement | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2295_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2295_imp.htm | Document Posted |  | In Progress |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2295_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2295_wmpa.pdf | Not Required |  |  |  | 3/28/2020 | [5 empty] | 7/30/2027 | 7/30/2027 |  | N | No
PJM | AF2-296 - moved to TC1 | Madera 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2296_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2296_imp.pdf | Document Posted |  | Withdrawn | [8 empty] | 3/28/2020 | [5 empty] | 10/1/2021 |  |  | N | No
PJM | AF2-297 - moved to TC1 | Sedge Hill 115 kV |  | VA | Halifax | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2297_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2297_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/28/2020 | [5 empty] | 3/12/2022 |  |  | N | No
PJM | AF2-298 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2298_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2298_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 5/1/2022 |  |  | N | No
PJM | AF2-299 - moved to TC1 | Fields 34.5 kV | Jarratt Energy Facility 2 | VA | Greensville | Active | Dominion | 19.5 | 25 | 11.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2299_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2299_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/12/2022 |  |  | N | No
PJM | AF2-300 | St. Johns 115 kV |  | VA | Caroline | Active | Dominion | 64 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2300_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2300_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/12/2022 |  |  | N | No
PJM | AF2-302 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 75 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2302_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2302_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/12/2022 |  |  | N | No
PJM | AF2-303 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2303_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2303_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 8/3/2023 |  |  | N | No | This project slid to the next queue
PJM | AF2-304 | Surry-Hopewell 230 kV |  | VA | Surry | Active | Dominion | 89 | 89 | 89 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2304_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2304_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 8/3/2023 |  |  | N | No | This project slid to the next queue
PJM | AF2-306 | Hope-Blevins Valley Tap 69 kV |  | KY | Barren | Active | EKPC | 26 | 26 | 26 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2306_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2306_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AF2-307 - moved to TC1 | Hope-Blevins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2307_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2307_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AF2-308 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2308_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2308_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AF2-309 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2309_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2309_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AF2-311 | Gilboa-Jones Branch 138 kV |  | WV | Nicholas | Active | APS | 100 | 100 | 55 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2311_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2311_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-316 | Gilboa-Jones Branch 138 kV II |  | WV | Nicholas | Active | APS | 150 | 150 | 82.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2316_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2316_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-319 - moved to TC1 | Katydid Road 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2319_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2319_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-321 - moved to TC1 | Stryker-Ridgeville 138 kV |  | OH | Williams | Active | ATSI | 148 | 148 | 88.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2321_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-324 - moved to TC1 | Edgecombe 230 kV |  | NC | Edgecombe | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2324_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/30/2020 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AF2-325 | Jacktown 12 kV | SBC Solar | MD | Dorchester | Engineering and Procurement | DPL | 10 | 10 | 4.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2325_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2325_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2325_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2325_wmpa.pdf | Not Required |  |  |  | 3/30/2020 |  |  | 12/31/2027 |  |  | 12/31/2027 | 12/31/2027 |  | N | No
PJM | AF2-329 - moved to TC1 | Sandwich-Plano 138 kV |  | IL | Kendall | Active | ComEd | 292.2 | 42.2 | 42.2 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2329_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2329_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-331 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2331_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2331_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-332 | Montour 230 kV |  | PA | Montour | Active | PPL | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2332_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2332_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-333 | Montour 230 kV |  | PA | Montour | Active | PPL | 120 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2333_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2333_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-334 | Montour 230 kV |  | PA | Montour | Active | PPL | 140 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2334_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2334_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-335 - moved to TC1 | Delaware-Royerton 138 kV |  | IN | Delaware | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2335_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2335_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-336 | Snake Spring 115 kV I |  | PA | Bedford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2336_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2336_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2336_fac.pdf | Document Posted | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-337 | Snake Spring 115 kV II |  | PA | Bedford | Active | PENELEC | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2337_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2337_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2337_fac.pdf | Document Posted | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-348 - moved to TC1 | North Clark-Spurlock 345 kV |  | KY | Madison | Active | EKPC | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2348_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2348_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 7/1/2022 |  |  | N | No
PJM | AF2-349 - moved to TC1 | SILVER LAKE- CHERRY VALLEY 345 KV |  | IL | McHenry | Active | ComEd | 300 | 300 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2349_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2349_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-350 - moved to TC1 | Kensington 138 kV |  | IL | Kankakee | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2350_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2350_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-352 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 248 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2352_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2352_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-354 | Washington 34.5 kV II | Washington Solar PH II | NJ | Warren | Engineering and Procurement | JCPL | 19.8 | 11 | 4.62 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2354_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2354_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/af2_354_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_354_csa.pdf | Document Posted |  |  |  | 3/31/2020 |  |  | 6/29/2025 |  |  | 8/29/2025 | 8/29/2025 |  | N | No
PJM | AF2-355 - moved to TC1 | West Gerrard-J.K. Smith 345 kV |  | KY | Madison | Active | EKPC | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2355_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2355_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 7/1/2022 |  |  | N | No
PJM | AF2-356 | Albright-Mt. Zion 138 kV | CPV Backbone Solar | MD | Garrett | Under Construction | APS | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2356_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2356_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2356_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/af2_356_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/af2_356_csa.pdf | Document Posted |  |  | 11/8/2024 | 3/31/2020 |  |  | 11/10/2024 |  |  | 8/31/2025 | 8/31/2025 |  | N | No
PJM | AF2-358 - moved to TC1 | Airey-Vienna 69 kV |  | MD | Dorchester | Active | DPL | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2358_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2358_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AF2-359 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2359_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2359_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AF2-363 | Cherry Valley-Glidden 138 kV |  | IL | DeKalb | Active | ComEd | 81.4 | 81.4 | 48.84 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2363_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2363_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2020 |  |  | N | No
PJM | AF2-365 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2365_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2365_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF2-366 | Crego Rd 138 kV |  | IL | Adams | Active | ComEd | 94.9 | 94.9 | 56.94 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2366_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/31/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF2-367 | Neville 23 kV | Emsworth Back Channel Dam Hydroelectric Project | PA | Allegheny | Engineering and Procurement | DL | 12 | 12 | 12 |  | Capacity | Generation Interconnection | Hydro |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2367_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2367_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2367_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2367_wmpa.pdf | Not Required |  |  |  | 3/31/2020 |  |  | 10/31/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AF2-368 | Pine Creek 23 kV | Allegheny Lock and Dam No. 2 Hydroelectric Project | PA | Allegheny | Engineering and Procurement | DL | 9.5 | 9.5 | 9.5 |  | Capacity | Generation Interconnection | Hydro |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2368_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2368_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2368_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2368_wmpa.pdf | Not Required |  |  |  | 3/31/2020 |  |  | 10/31/2029 |  |  | 12/31/2029 | 12/31/2029 |  | N | No
PJM | AF2-370 - moved to TC1 | Delaware-Royerton 138 kV |  | IN | Delaware | Active | AEP | 100 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2370_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2370_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-371 | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 84 | 84 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2371_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2371_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-375 | Ebersole-Fostoria 138 kV |  | OH | Hancock | Active | AEP | 129.6 | 129.6 | 77.76 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2375_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2375_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AF2-376 | Timber Switch 138 kV |  | OH | Paulding | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2376_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2376_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-377 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2377_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2377_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-378 | Cambridge 12 kV | GGC Solar | MD | Dorchester | Engineering and Procurement | DPL | 2.65 | 2.65 | 1.11 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2378_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2378_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2378_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2378_wmpa.pdf | Not Required |  |  |  | 3/31/2020 |  |  | 3/31/2026 |  |  | 3/31/2024 | 3/31/2024 |  | N | No
PJM | AF2-379 | Princess Anne 25 kV | RHC Solar | MD | Somerset | Under Construction | DPL | 3.9 | 3.9 | 1.638 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2379_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2379_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2379_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2379_wmpa.pdf | Not Required |  |  |  | 4/1/2020 |  |  | 12/1/2024 |  |  | 12/1/2024 | 12/1/2024 |  | N | No
PJM | AF2-380 | Karns City-Bear Creek 25 kV | Richardson Solar | PA | Clarion | Engineering and Procurement | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2380_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2380_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/af2380_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/af2380_wmpa.pdf | Not Required |  |  |  | 3/31/2020 | [5 empty] | 7/30/2027 | 7/30/2027 |  | N | No
PJM | AF2-382 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2382_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2382_imp.htm | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-383 | Tolna 115 kV |  | PA | York | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2383_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2383_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-384 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2384_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2384_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AF2-388 - moved to TC1 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2388_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2388_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AF2-389 | Pokagon-Corey 69 kV |  | MI | Cass | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2389_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2389_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AF2-391 | Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2391_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2391_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 6/15/2023 |  |  | N | No
PJM | AF2-392 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Lee | Active | ComEd | 199 | 199 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2392_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/31/2020 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AF2-393 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Active | ComEd | 260 | 60 | 55 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2393_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2393_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AF2-394 - moved to TC1 | Nelson-Dixon 138 kV |  | IL | Adams | Active | ComEd | 300 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2394_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2394_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AF2-396 - moved to TC1 | Stinger 138 kV |  | MI | Cass | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2396_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2396_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-403 - moved to TC1 | Shockoe DP-Chatham 69 kV | Shockoe Storage / Shockoe DP-Chatham 69 kV | VA | Fluvanna | Active | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2403_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2403_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/15/2022 |  |  | N | No
PJM | AF2-404 - moved to TC1 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2404_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2404_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/15/2022 |  |  | N | No
PJM | AF2-405 | East Sayre 34.5 kV III |  | PA | Bradford | Active | PENELEC | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2405_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2405_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AF2-407 - moved to TC1 | Fall Creek 345 kV |  | IN | Madison | Active | AEP | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2407_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2407_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-408 | Fall Creek 138 kV |  | IN | Madison | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2408_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2408_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-412 - moved to TC1 | Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2412_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/31/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-413 | Raritan River 230 kV |  | NJ | Atlantic | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2413_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/31/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-415 | Bergen 138 kV |  | NJ | Hudson | Active | PSEG | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2415_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2415_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/af2415_fac.pdf | Document Posted | [8 empty] | 3/31/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-417 | West Damascus Tap-West Damascus 69 kV |  | PA | Adams | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2417_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2417_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 4/1/2022 |  |  | N | No
PJM | AF2-421 | East Hazelton-Weatherly Tap 69 |  | PA | Adams | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2421_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2421_imp.pdf | Document Posted |  | In Progress | [8 empty] | 4/1/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AF2-424 | Reed-Reed Tap #1 69 kV |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2424_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2424_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AF2-425 | Sunbury-Eldred #2 69 kV |  | PA | Adams | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2425_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2425_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AF2-433 | Columbia-Geisinger Tap #1 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2433_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2433_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-434 | Columbia-Geisinger Tap #1 69 kV |  | MD | Anne Arundel | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2434_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2434_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AF2-440 | Hillsboro-Middleboro 138 kV |  | OH | Highland | Active | AEP | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2440_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2440_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AF2-441 - moved to TC1 | Burnham 138kV |  | IL | Cook | Active | ComEd | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2441_fea.pdf | Document Posted |  | In Progress | [10 empty] | 3/31/2020 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AF2-444 | Reed-Fairview Tap #2 69 kV |  | PA | Northumberland | Active | PPL | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/af2444_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/af2444_imp.pdf | Document Posted |  | In Progress | [8 empty] | 3/31/2020 | [5 empty] | 6/1/2021 |  |  | N | No
PJM | AG1-001 | US Silica-Unimin 69 kV |  | NJ | Cumberland | Active | AEC | 31 | 31 | 11.78 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1001_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1001_imp.pdf | Document Posted |  | In Progress | [8 empty] | 4/3/2020 | [5 empty] | 3/1/2023 |  |  | N | No
PJM | AG1-003 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 900 | 400 | 226 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1003_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1003_imp.pdf | Document Posted |  | In Progress | [8 empty] | 4/20/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-004 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 1100 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1004_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1004_imp.pdf | Document Posted |  | In Progress | [8 empty] | 4/20/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-005 - moved to TC1 | Corbin-Crescent Ridge 138 kV |  | IL | Stephenson | Active | ComEd | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1005_fea.pdf | Document Posted |  | In Progress | [10 empty] | 4/29/2020 | [5 empty] | 10/1/2023 |  |  | N | No
PJM | AG1-007 | Tar River 12.5 kV |  | NC | Edgecombe | Active | Dominion | 9.4 | 9.4 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1007_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1007_imp.pdf | Document Posted |  | In Progress | [8 empty] | 5/1/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG1-008 - moved to TC1 | Tunis-Mapleton 115 kV |  | NC | Hertford | Active | Dominion | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1008_fea.pdf | Document Posted |  | In Progress | [10 empty] | 5/1/2020 | [5 empty] | 12/15/2024 |  |  | N | No
PJM | AG1-017 | Jay 138 kV |  | IN | Jay | Active | AEP | 142.64 | 12.64 | 2.26 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1017_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1017_imp.pdf | Document Posted |  | In Progress | [8 empty] | 5/6/2020 | [5 empty] | 9/30/2020 |  |  | N | No
PJM | AG1-021 - moved to TC1 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 86 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1021_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1021_imp.pdf | Document Posted |  | In Progress | [8 empty] | 5/26/2020 | [5 empty] | 12/12/2023 |  |  | N | No
PJM | AG1-022 - moved to TC1 | Scottsville-Colleen 138 kV |  | VA | Albemarle | Active | AEP | 95 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1022_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1022_imp.pdf | Document Posted |  | In Progress | [8 empty] | 5/26/2020 | [5 empty] | 12/12/2023 |  |  | N | No
PJM | AG1-024 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 285 | 85 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1024_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1024_imp.pdf | Document Posted |  | In Progress | [8 empty] | 6/1/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG1-031 | Elk Run D.P.-Gainesville 230 kV |  | VA | Fauquier | Active | Dominion | 90 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1031_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1031_imp.pdf | Document Posted |  | In Progress | [8 empty] | 6/10/2020 | [5 empty] | 11/30/2021 |  |  | N | No
PJM | AG1-034 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 412.5 | 127.5 | 53.55 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1034_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1034_imp.pdf | Document Posted |  | In Progress | [8 empty] | 6/12/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG1-037 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1037_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1037_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1037_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1037_wmpa.pdf | Not Required |  |  |  | 6/16/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG1-038 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 176 | 45 | 18.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1038_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1038_imp.pdf | Document Posted |  | In Progress | [8 empty] | 6/16/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG1-039 | Galion 138 kV II |  | OH | Morrow | Active | ATSI | 144 | 56 | 23.52 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1039_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1039_imp.pdf | Document Posted |  | In Progress | [8 empty] | 6/18/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-040 | Morgan Street-Mount Hope 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1040_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1040_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1040_fac.pdf | Document Posted | [8 empty] | 6/20/2020 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AG1-047 | Jay 138 kV |  | IN | Jay | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1047_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1047_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/13/2020 | [5 empty] | 10/1/2023 |  |  | N | No
PJM | AG1-050 | Milton 69 kV |  | PA | Northumberland | Active | PPL | 90 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1050_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/17/2020 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG1-051 - moved to TC1 | Maysville 69 kV III |  | PA | Mercer | Active | ATSI | 70 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1051_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1051_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/17/2020 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG1-052 | Zionsview-Middletown 115 kV II |  | PA | York | Active | ME | 99.6 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1052_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1052_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/17/2020 | [5 empty] | 9/30/2021 |  |  | N | No
PJM | AG1-053 | Jackson-Three Mile Island 230 kV III |  | PA | York | Active | ME | 95 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1053_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1053_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/17/2020 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG1-054 | Potter-Harlan 69 kV |  | PA | Lawrence | Active | ATSI | 40 | 40 | 25.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1054_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1054_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/21/2020 | [5 empty] | 5/1/2023 |  |  | N | No
PJM | AG1-059 | Robbins 138 kV |  | PA | Westmoreland | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1059_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1059_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/29/2020 | [5 empty] | 1/1/2023 |  |  | N | No
PJM | AG1-063 | Fairhaven 13,8 kV | Fairhaven Battery Energy Storage System | MD | Anne Arundel | Under Construction | BGE | 2.5 | 2.5 | 0.7 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1063_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1063_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1063_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1063_wmpa.pdf | Not Required |  |  |  | 7/31/2020 |  |  | 9/30/2024 |  |  | 9/30/2024 | 9/30/2024 |  | N | No
PJM | AG1-066 | Bonnyman 69 kV |  | KY | Perry | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1066_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1066_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/30/2020 | [5 empty] | 10/2/2024 |  |  | N | No
PJM | AG1-067 | Temple Hill 69 kV |  | KY | Barren | Active | EKPC | 38 | 38 | 24.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1067_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1067_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/30/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-070 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 45 | 45 | 32.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1070_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1070_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-071 | Bon Ayr 69 kV |  | KY | Barren | Active | EKPC | 55 | 55 | 37.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1071_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1071_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-075 - moved to TC1 | Purdy-Sapony 115 kV |  | VA | Greensville | Active | Dominion | 150 | 150 | 93.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1075_fea.pdf | Document Posted |  | In Progress | [10 empty] | 7/31/2020 | [5 empty] | 10/15/2024 |  |  | N | No
PJM | AG1-082 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1082_fea.pdf | Document Posted |  | In Progress | [10 empty] | 7/31/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG1-083 - moved to TC1 | Ahoskie 34.5 kV |  | NC | Hertford | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1083_fea.pdf | Document Posted |  | In Progress | [10 empty] | 7/31/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG1-086 | Findlay 23 kV | Findlay Solar Park | PA | Allegheny | Engineering and Procurement | DL | 17.5 | 17.5 | 10.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1086_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1086_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1086_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1086_wmpa.pdf | Not Required |  |  |  | 7/31/2020 |  |  | 12/31/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AG1-089 | Grandview-Clifftop 138 kV |  | WV |  | Active | AEP | 120 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1089_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1089_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/31/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG1-090 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1090_fea.pdf | Document Posted |  | In Progress | [10 empty] | 8/1/2020 | [5 empty] | 8/1/2023 |  |  | N | No
PJM | AG1-091 | Hickman-River Bend 69 kV |  | VA | Pulaski | Active | AEP | 50 | 50 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1091_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1091_imp.pdf | Document Posted |  | In Progress | [8 empty] | 7/31/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-097 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 92.5 | 0 | 13 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1097_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1097_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/17/2020 | [5 empty] | 9/30/2022 |  |  | N | No
PJM | AG1-098 - moved to TC1 | Briery-Clover 230 kV |  | VA | Mecklenburg | Active | Dominion | 107 | 107 | 64.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1098_fea.pdf | Document Posted |  | In Progress | [10 empty] | 8/18/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-099 | Westernport 34.5 kV | Jade Meadow III | MD | Garrett | Engineering and Procurement | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1099_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1099_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1099_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1099_wmpa.pdf | Not Required |  |  |  | 8/18/2020 |  |  | 10/31/2025 |  |  | 12/31/2025 | 12/31/2025 |  | N | No
PJM | AG1-100 | Venango-Saegertown 34.5 kV | Henry Solar | PA | Crawford | Engineering and Procurement | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1100_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1100_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1100_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ag1_100_gia.pdf | Document Posted | [5 empty] | 10/15/2026 | 8/18/2020 |  |  | 10/26/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AG1-103 | Clayton-Williamstown 69 kV | Gloucester Solar I | NJ | Gloucester | Engineering and Procurement | AEC | 44 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1103_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1103_imp.pdf | Document Posted |  | Not Required | https://www.pjm.com/pub/planning/project-queues/isa/ag1_103_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ag1_103_csa.pdf | Document Posted |  |  |  | 8/24/2020 |  |  | 12/31/2026 |  |  | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AG1-104 | Waugh Chapel 230 kV |  | MD | Anne Arundel | Active | BGE | 300 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1104_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1104_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/25/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-105 - moved to TC1 | Mount Laurel-Barnes Junction 115 kV |  | VA | Halifax | Active | Dominion | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1105_fea.pdf | Document Posted |  | In Progress | [10 empty] | 8/27/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-106 - moved to TC1 | Thelma 230 kV |  | NC | Northhampton | Active | Dominion | 325.5 | 25.5 | 17.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1106_fea.pdf | Document Posted |  | In Progress | [10 empty] | 8/28/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-107 | Hillsboro-Middleboro 138 kV |  | OH | Highland | Active | AEP | 200 | 150 | 85.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1107_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1107_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/31/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-109 - moved to TC1 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 50 | 0 | 25 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1109_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1109_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/31/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AG1-118 - moved to TC1 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1118_fea.pdf | Document Posted |  | In Progress | [10 empty] | 8/31/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-120 - moved to TC1 | Glidden-Cherry Valley 138 kV |  | IL | DeKalb | Active | ComEd | 118.6 | 118.6 | 71.16 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1120_fea.pdf | Document Posted |  | In Progress | [10 empty] | 8/31/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-124 - moved to TC1 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 90 | 90 | 53.01 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1124_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1124_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/31/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-125 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 400 | 234.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1125_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1125_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/31/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-126 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 400 | 234.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1126_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1126_imp.pdf | Document Posted |  | In Progress | [8 empty] | 8/31/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-127 - moved to TC1 | Crego Rd 138 kV |  | IL | DeKalb | Active | ComEd | 190 | 95.1 | 57.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1127_fea.pdf | Document Posted |  | In Progress | [10 empty] | 8/31/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-135 - moved to TC1 | Garner-Lancaster 115 kV |  | VA | Richmond | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1135_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1135_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ag1_135_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/ag1_135_csa.pdf | Document Posted |  |  | 12/1/2025 | 9/3/2020 |  |  | 2/1/2026 |  |  | 12/1/2024 |  |  | N | No
PJM | AG1-136 | Cloverdale-Burlington Height 138 kV |  | VA | Botetourt | Active | AEP | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1136_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1136_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/3/2020 | [5 empty] | 10/22/2023 |  |  | N | No
PJM | AG1-146 - moved to TC1 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1146_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1146_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/9/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-147 - moved to TC1 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 100 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1147_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1147_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/9/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-148 | McCarter 26.4 kV | Rutgers Generation | NJ | Essex | Partially in Service - Under Construction | PSEG | 5 | 5 | 0 | 0 | Energy | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1148_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1148_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1148_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1148_wmpa.pdf | Not Required |  |  |  | 9/12/2020 |  |  | 3/21/2024 |  |  | 1/12/2024 | 1/12/2024 |  | N | No
PJM | AG1-152 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1152_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1152_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/10/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG1-153 - moved to TC1 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 75 | 75 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1153_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1153_imp.pdf | Document Posted |  | In Progress | https://www.pjm.com/pub/planning/project-queues/isa/ag1_153_isa2.pdf | Interim Study |  | https://www.pjm.com/pub/planning/project-queues/csa/ag1_153_csa.pdf | Document Posted |  |  | 6/22/2028 | 9/10/2020 |  |  | 7/8/2028 |  |  | 12/1/2023 |  |  | N | No
PJM | AG1-154 - moved to TC1 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1154_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1154_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/10/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG1-156 | Jack Frost-Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 60 | 60 | 39.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1156_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1156_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/10/2020 | [5 empty] | 6/15/2024 |  |  | N | No
PJM | AG1-163 | West Millersport 138 kV |  | OH | Fairfield | Active | AEP | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1163_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1163_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/14/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-164 | East Hazelton-Weatherly Tap 69 kV |  | PA | Luzerne | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1164_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1164_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/16/2020 | [5 empty] | 8/15/2022 |  |  | N | No
PJM | AG1-165 | East Hazelton-Weatherly Tap 69 kV |  | PA | Luzerne | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1165_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1165_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/17/2020 | [5 empty] | 5/15/2022 |  |  | N | No
PJM | AG1-166 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 20 | 20 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1166_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1166_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-167 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1167_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1167_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-168 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1168_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1168_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-169 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 15 | 15 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1169_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1169_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-170 - moved to TC1 | Lone Pine 115 kV |  | VA | Nottoway | Active | Dominion | 10 | 10 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1170_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1170_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-171 | Hopewell-Surry 230kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1171_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-172 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1172_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-173 | Hopewell-Surry 230 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1173_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/16/2020 | [5 empty] | 10/15/2021 |  |  | N | No
PJM | AG1-182 | Millville-Old Chapel 138 kV |  | VA | Clarke | Active | APS | 100 | 100 | 65.21 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1182_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1182_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/17/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-186 | Millville-Old Chapel 138 kV |  | VA | Clarke | Active | APS | 100 | 0 | 34.79 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1186_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1186_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/17/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-188 | Manitou-Oyster Creek 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1188_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1188_imp.htm | Document Posted | [10 empty] | 9/17/2020 | [5 empty] | 12/17/2021 |  |  | N | No
PJM | AG1-189 | Oyster Creek-Bamber Lake 34.5 |  | NJ | Ocean | Active | JCPL | 12 | 12 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1189_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1189_imp.htm | Document Posted | [10 empty] | 9/17/2020 | [5 empty] | 12/17/2021 |  |  | N | No
PJM | AG1-191 | Chester-Pohatcong Mountain 34.5 kV | South Combe | NJ | Morris | Engineering and Procurement | JCPL | 15.4 | 15.4 | 6.5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1191_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1191_imp.html | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1191_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/isa/ag1_191_isa.pdf | Document Posted |  | https://www.pjm.com/pub/planning/project-queues/csa/ag1_191_csa.pdf | Document Posted |  |  | 9/30/2024 | 9/17/2020 |  |  | 2/28/2025 |  |  | 3/12/2025 | 3/12/2025 |  | N | No
PJM | AG1-193 | Utica Junction 34.5 kV | Foster Run | PA | Venango | Engineering and Procurement | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1193_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1193_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1193_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1193_wmpa.pdf | Not Required |  |  |  | 9/18/2020 |  |  | 7/1/2025 |  |  | 9/1/2025 | 9/1/2025 |  | N | No
PJM | AG1-194 - moved to TC1 | Nuttall 138 kV |  | WV | Fayette | Active | AEP | 79 | 79 | 27 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1194_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1194_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/18/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG1-197 | Morgan Street-Cochranton 34.5 kV | Morgan Street-Cochranton 34.5 kV | PA | Crawford | Engineering and Procurement | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1197_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1197_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1197_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1197_wmpa.pdf | Not Required |  |  |  | 9/19/2020 |  |  | 1/10/2025 |  |  | 3/3/2025 | 3/3/2025 |  | N | No
PJM | AG1-198 | Union City 34.5 kV | Union City 34.5 kV | PA | Erie | Engineering and Procurement | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1198_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1198_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1198_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1198_wmpa.pdf | Not Required |  |  |  | 9/18/2020 |  |  | 1/10/2025 |  |  | 3/1/2025 | 3/1/2025 |  | N | No
PJM | AG1-207 | Vandalia 69 kV |  | OH | Montgomery | Active | Dayton | 85 | 85 | 85 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1207_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1207_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/22/2020 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AG1-210 | Northern Neck 34.5 kV | Haynesville Energy Storage | VA | Richmond | Engineering and Procurement | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1210_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1210_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1210_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1210_wmpa.pdf | Not Required |  |  |  | 9/23/2020 | [5 empty] | 8/9/2027 | 8/9/2027 |  | N | No
PJM | AG1-213 | St Johns 13.2 kV | Poplar Energy Storage | VA | Caroline | Engineering and Procurement | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1213_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1213_imp.pdf | Document Posted |  |  |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1213_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1213_wmpa.pdf | Not Required |  |  |  | 9/23/2020 |  |  | 12/31/2025 |  |  | 6/30/2024 | 6/30/2024 |  | N | No
PJM | AG1-218 | Marysville-Tangy 345 kV |  | OH | Union | Active | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1218_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1218_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/23/2020 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG1-221 | Poland Rd-Runway DP 230 kV |  | VA | Loudoun | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1221_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1221_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/23/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-222 | Guardian-Twin Branch 138 kV |  | IN | Elkhart | Active | AEP | 302.2 | 150 | 90 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1222_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/23/2020 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AG1-223 | Larrabee-Allaire 34.5 kV | Monmouth Solar 1 | NJ | Monmouth | Active | JCPL | 15.4 | 15.4 | 6.47 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1223_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1223_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1223_fac.pdf | Document Posted | [8 empty] | 9/23/2020 | [5 empty] | 12/31/2026 | 12/31/2026 |  | N | No
PJM | AG1-226 - moved to TC1 | Eugene-Dequine 345 kV |  | IN | Fountain | Active | AEP | 450 | 450 | 142 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1226_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/24/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-231 | Glady Run–Xenia 69 kV |  | OH | Greene | Active | Dayton | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1231_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1231_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2020 | [5 empty] | 3/31/2023 |  |  | N | No
PJM | AG1-232 | Magley 138 kV |  | IN | Adams | Active | AEP | 135 | 135 | 81 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1232_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1232_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2020 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG1-233 | Hazleton - Lake Lynn 138 kV |  | WV | Preston | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1233_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/25/2020 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG1-236 - moved to TC1 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 380 | 180 | 23.4 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1236_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/25/2020 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG1-237 | Dequine-Eugene 345 kV |  | IN |  | Active | AEP | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1237_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1237_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2020 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG1-239 | Blue Bell-Canton Central 138 kV |  | OH | Stark | Active | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1239_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1239_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2020 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG1-254 | Salem-Woodstown 69 kV |  | NJ | Atlantic | Active | AEC | 38 | 38 | 25.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1254_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1254_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/25/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-257 - moved to TC1 | Madisonburg Jct-Millheim 46 kV |  | PA | Centre | Active | APS | 19.9 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1257_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1257_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/28/2020 | [5 empty] | 8/1/2022 |  |  | N | No
PJM | AG1-259 | Sunbury-Dalmatia 69 kV |  | PA | Northumberland | Active | PPL | 15.9 | 15.9 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1259_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1259_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/28/2020 | [5 empty] | 8/1/2022 |  |  | N | No
PJM | AG1-260 | Sunbury-Dalmatia 69 kV |  | PA | Northumberland | Active | PPL | 31.8 | 15.9 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1260_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1260_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/28/2020 | [5 empty] | 8/1/2023 |  |  | N | No
PJM | AG1-272 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1272_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/29/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AG1-273 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1273_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/28/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-274 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1274_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/28/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-277 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 40 | 40 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1277_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1277_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/28/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-278 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 60 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1278_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1278_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/28/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-279 - moved to TC1 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 80 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1279_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1279_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/28/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-281 | Claysburg-HCR Tap 46 kV | BL-Hileman Hollow | PA | Blair | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1281_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1281_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1281_fac.pdf | Document Posted | [8 empty] | 9/30/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AG1-282 | Dunnsville 34.5 kV | EX-Tidewater LLC | VA | Essex | Engineering and Procurement | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1282_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1282_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1282_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1282_wmpa.pdf | Not Required |  |  |  | 9/28/2020 | [5 empty] | 8/29/2027 | 8/29/2027 |  | N | No
PJM | AG1-283 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Active | PPL | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1283_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1283_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/28/2020 | [5 empty] | 9/30/2023 |  |  | N | No
PJM | AG1-285 - moved to TC1 | Chase City-Central 115 kV |  | VA | Charlotte | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1285_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/28/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-291 | Neville 23 kV | Emsworth Main Channel Hydroelectric Project 2 | PA | Allegheny | Engineering and Procurement | DL | 16.8 | 16.8 | 13.5 |  | Capacity | Generation Interconnection | Hydro |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1291_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1291_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1291_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1291_wmpa.pdf | Not Required |  |  | 10/3/2025 | 9/28/2020 |  |  | 11/1/2025 |  |  | 12/15/2025 | 12/15/2025 |  | N | No
PJM | AG1-297 - moved to TC1 | Hanna-Tanners Creek 345 kV |  | IN | Shelby | Active | AEP | 300 | 300 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1297_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/29/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-298 - moved to TC1 | Calumet-Burnham 345 kV |  | IL | Cook | Active | ComEd | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1298_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/29/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-301 | Miller REC-Warrior Ridge 46 kV |  | PA | Huntingdon | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1301_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1301_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/29/2020 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG1-302 | Olive-Reynolds #1 345 kV |  | IN | Pulaski | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1302_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/29/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG1-303 | Geneva 115 kV |  | PA | Crawford | Active | PENELEC | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1303_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1303_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/29/2020 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AG1-305 - moved to TC1 | Louisa-North Anna 230 kV |  | VA | Louisa | Active | Dominion | 63 | 63 | 37.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1305_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1305_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/29/2020 | [5 empty] | 7/1/2022 |  |  | N | No
PJM | AG1-307 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 80 | 80 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1307_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1307_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/29/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-311 | Apple Grove 138 kV |  | WV | Mason | Active | AEP | 99 | 99 | 69.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1311_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1311_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/29/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-318 | Ocean Bay 12 kV | Ocean City-Battery Storage | MD | Worcester | Under Construction | DPL | 1 | 1 | 0.3 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1318_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1318_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1318_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1318_wmpa.pdf | Not Required |  |  |  | 9/30/2020 |  |  | 12/31/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AG1-319 - moved to TC1 | Napoleon Muni 138 kV |  | OH | Henry | Active | AMPT | 206 | 166 | 99.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1319_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 11/1/2022 |  |  | N | No
PJM | AG1-320 | Glendale-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 82 | 82 | 54.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1320_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/1/2023 |  |  | N | No
PJM | AG1-323 - moved to TC1 | Blue Jacket 138 kV |  | OH | Logan | Active | Dayton | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1323_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1323_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AG1-324 | Jay-Desoto 138 kV |  | IN | Jay | Active | AEP | 39 | 39 | 27.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1324_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1324_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AG1-326 | Circleville-Biers Run 138 kV |  | OH | Ross | Active | AEP | 59 | 59 | 35.4 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1326_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No | This project slid to the next queue
PJM | AG1-341 | Summer Shade 161 kV |  | KY | Metcalfe | Active | EKPC | 106 | 106 | 63.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1341_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/15/2023 |  |  | N | No
PJM | AG1-342 - moved to TC1 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 36 | 36 | 21.6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1342_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG1-343 - moved to TC1 | Boykins-Murphy 115 kV |  | VA | Southampton | Active | Dominion | 62.5 | 62.5 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1343_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG1-346 - moved to TC1 | Mount Jackson DP 115 kV |  | VA | Shenandoah | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1346_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1346_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AG1-348 | Pequest River-Washington 34.5 kV | Foul Rift Solar Farm | NJ | Warren | Under Construction | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1348_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1348_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1348_fac.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/gia/ag1_348_gia.pdf | Document Posted | [5 empty] | 10/15/2024 | 9/30/2020 |  |  | 10/16/2024 |  |  | 11/15/2025 | 11/15/2025 |  | N | No
PJM | AG1-349 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 260 | 260 | 156 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1349_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1349_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-351 | Harrison-Good Hope 138 kV |  | OH | Fairfield | Active | AEP | 142 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1351_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-353 - moved to TC1 | Greene County-Marion County 161 kV |  | KY | Taylor | Active | EKPC | 98 | 98 | 58.8 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1353_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-354 - moved to TC1 | Summershade-Green County 161 kV |  | KY | Green | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1354_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-360 | Costen 25 kV | Costen Solar | MD | Somerset | Under Construction | DPL | 8.75 | 8.75 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1360_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1360_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1360_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1360_wmpa.pdf | Not Required |  |  |  | 10/1/2020 |  |  | 6/24/2024 |  |  | 8/30/2024 | 8/30/2024 |  | N | No
PJM | AG1-363 | Black Oak-Hatfield 500 kV |  | MD | Garrett | Active | APS | 300 | 300 | 220 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1363_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1363_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG1-365 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1365_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1365_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG1-366 | Allen 345 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1366_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1366_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG1-367 - moved to TC1 | DeSoto 345 kV |  | IN | Delaware | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1367_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG1-368 | Tillman 138 kV |  | IN | Allen | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1368_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1368_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG1-369 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1369_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1369_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG1-374 - moved to TC1 | Blue Mound 345 kV |  | IL | McLean | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1374_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG1-375 - moved to TC1 | Sorenson-Desoto 345 kV |  | IN | Blackford | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1375_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG1-377 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 120 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1377_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1377_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 8/15/2023 |  |  | N | No
PJM | AG1-378 - moved to TC1 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 140 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1378_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1378_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 8/15/2023 |  |  | N | No
PJM | AG1-382 | SGC Tap-Reese REC 46 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1382_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1382_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AG1-384 - moved to TC1 | Twitty's Creek 115 kV |  | VA | Charlotte | Active | Dominion | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1384_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-386 | Smith-Francis Junction 25 kV | Smith-Francis Junction 25 kV | PA | Washington | Engineering and Procurement | APS | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1386_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1386_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1386_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1386_wmpa.pdf | Not Required |  |  |  | 10/1/2020 |  |  | 11/1/2024 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AG1-392 - moved to TC1 | Gold 115 kV I |  | PA | Potter | Active | PENELEC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1392_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-392A - moved to TC1 | Gold 115 kV II |  | PA | Potter | Active | PENELEC | 80 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1391_fea.pdf | Document Posted |  | In Progress | [10 empty] | 10/1/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-392B - moved to TC1 | Gold 115 kV III |  | PA | Potter | Active | PENELEC | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1390_fea.pdf | Document Posted |  | In Progress | [10 empty] | 10/1/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-392C - moved to TC1 | Gold 115 kV IV |  | PA | Potter | Active | PENELEC | 120 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1389_fea.pdf | Document Posted |  | In Progress | [10 empty] | 10/1/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-393 - moved to TC1 | Fort Pickett DP 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1393_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1393_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AG1-394 - moved to TC1 | Boykins 34.5 kV |  | VA | Southampton | Active | Dominion | 14.2 | 14.2 | 5 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1394_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1394_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 3/1/2022 |  |  | N | No
PJM | AG1-397 | Walston 12 kV | Walston Solar | MD | Wicomico | Engineering and Procurement | DPL | 9.972 | 9.972 | 4.1882 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1397_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1397_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1397_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1397_wmpa.pdf | Not Required |  |  |  | 9/30/2020 |  |  | 6/1/2025 |  |  | 12/31/2024 | 12/31/2024 |  | N | No
PJM | AG1-401 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Active | ComEd | 282 | 282 | 49.6 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1401_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 9/25/2024 |  |  | N | No | This project slid to the next queue
PJM | AG1-403 | Blue Mound-Chestnut 345 kV |  | IL | McLean | Active | ComEd | 188 | 188 | 33.1 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1403_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 9/24/2024 |  |  | N | No | This project slid to the next queue
PJM | AG1-405 | Walnut Grove-Asahi 69 kV |  | KY | McLean | Active | EKPC | 57 | 57 | 34.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1405_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1405_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AG1-406 | Walnut Grove-Asahi 69 kV |  | KY | McLean | Active | EKPC | 79 | 22 | 22 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1406_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1406_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AG1-410 - moved to TC1 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1410_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1410_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AG1-411 - moved to TC1 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1411_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AG1-412 - moved to TC1 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Active | Dominion | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1412_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1412_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG1-414 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1414_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-415 | Double Toll Date-Old Chapel 138 kV |  | VA | Clarke | Active | APS | 50 | 50 | 25 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1415_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1415_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 1/2/2023 |  |  | N | No
PJM | AG1-416 | Sleepy Hollow 138 kV |  | WV | Jefferson | Active | APS | 125 | 125 | 91 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1416_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1416_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-417 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1417_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1417_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-418 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1418_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1418_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-419 | Lynnville-South Hamburg 69 kV |  | PA | Berks | Active | ME | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1419_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1419_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-420 | Campbell-Kiesters 138 kV |  | PA | Butler | Active | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1420_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1420_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-426 - moved to TC1 | Bremo-Scottsville 138 kV |  | VA | Buckingham | Active | AEP | 149.5 | 0 | 17 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1426_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG1-427 - moved to TC1 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Active | Dominion | 118.56 | 118.56 | 71.136 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1427_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG1-428 - moved to TC1 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Active | Dominion | 46.8 | 46.8 | 28.08 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1428_fea.pdf | Document Posted |  | Withdrawn | [10 empty] | 9/30/2020 |  |  |  | 6/28/2024 |  | 12/31/2024 |  |  | N | No
PJM | AG1-433 - moved to TC1 | Keystone-DeSoto 345 kV |  | IN | Blackford | Active | AEP | 300 | 100 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1433_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-434 - moved to TC1 | Electric Junction-Nelson 345 kV |  | IL | Lee | Active | ComEd | 175 | 175 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1434_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-435 - moved to TC1 | Kewanee-Hennepin 138 kV |  | IL | Bureau | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1435_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-436 - moved to TC1 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 250 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1436_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1436_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-437 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1437_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-438 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1438_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-439 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Active | Dominion | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1439_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-442 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 135 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1442_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-443 - moved to TC1 | Cashie-Earleys 230 kV |  | NC | Bertie | Active | Dominion | 135 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1443_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-444 - moved to TC1 | Chinquapin 230 kV |  | NC | Edgecombe | Active | Dominion | 330 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1444_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-447 - moved to TC1 | Olive-University Park 345 kV |  | IN | LaPorte | Active | AEP | 305 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1447_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1447_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-449 - moved to TC1 | Rawlings-Carson 500 kV |  | VA | Dinwiddie | Active | Dominion | 436 | 122 | 122 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1449_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG1-450 - moved to TC1 | Airey-Vienna 69 kV II |  | MD | Dorchester | Active | DPL | 125 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1450_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1450_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG1-451 - moved to TC1 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Active | Dominion | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1451_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG1-455 | Springboro-Venango Junction 115 kV |  | PA | Crawford | Active | PENELEC | 112.5 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1455_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG1-460 - moved to TC1 | Kincaid-Pana 345 kV |  | IL | Christian | Active | ComEd | 329 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1460_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1460_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG1-462 - moved to TC1 | Cordova 345 kV |  | IL | Whiteside | Active | ComEd | 255 | 255 | 153 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1462_fea.pdf | Document Posted |  | In Progress | [10 empty] | 10/1/2020 | [5 empty] | 10/1/2023 |  |  | N | No
PJM | AG1-469 | Gordonsville 34.5 kV | Turkey Solar | VA | Louisa | Engineering and Procurement | Dominion | 14.04 | 14.04 | 9.36 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1469_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1469_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1469_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1469_wmpa.pdf | Not Required |  |  |  | 9/30/2020 | [5 empty] | 8/29/2027 | 8/29/2027 |  | N | No
PJM | AG1-471 - moved to TC1 | Up Church-Wayne County 69 kV |  | KY | Wayne | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1471_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1471_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/2/2023 |  |  | N | No
PJM | AG1-473 - moved to TC1 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Active | PENELEC | 53.9 | 53.9 | 32.34 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1473_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-478 | Wilmington 34.5 kV | Wilmington Solar Energy Project | IL | Will | Engineering and Procurement | ComEd | 19.9 | 19.9 | 15.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1478_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1478_imp.htm | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1478_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1478_wmpa.pdf | Not Required |  |  |  | 9/30/2020 |  |  | 2/1/2025 |  |  | 4/1/2026 | 4/1/2026 |  | N | No
PJM | AG1-480 | Shawnee 34.5 kV |  | PA | Monroe | Active | ME | 18.2 | 18.2 | 18.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1480_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1480_imp.htm | Document Posted | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-482 | Hamilton 115 kV |  | PA | Mercer | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1482_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-483 - moved to TC1 | Dickerson 230 kV |  | MD | Montgomery | Active | PEPCO | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1483_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1483_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-485 | Brunot Island 138 kV |  | PA | Allegheny | Active | DL | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1485_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1485_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-486 | Orrtanna 115 kV |  | PA | Adams | Active | ME | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1486_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1486_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-487 | Gilbert 230 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1487_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1487_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-489 | McClelland-Hoytdale 345 kV |  | PA | Lawrence | Active | ATSI | 175 | 175 | 145 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1489_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1489_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-494 - moved to TC1 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1494_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG1-495 | Gilbert-Rocktown 34.5 kV | Ridge Road Solar Farm | NJ | Hunterdon | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1495_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1495_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1495_fac.pdf | Document Posted | [8 empty] | 9/30/2020 | [5 empty] | 12/17/2021 |  |  | N | No
PJM | AG1-497 - moved to TC1 | Cartanza 230 kV |  | DE | Kent | Active | DPL | 120 | 120 | 84 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1497_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1497_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-499 | Lambs 12.47 kV | Esky Solar Project | NJ | Gloucester | Under Construction | AEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1499_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1499_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1499_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1499_wmpa.pdf | Not Required |  |  |  | 9/30/2020 |  |  | 11/30/2024 |  |  | 6/1/2024 | 6/1/2024 |  | N | No
PJM | AG1-500 | Beaver 345 kV |  | OH | Lorain | Active | ATSI | 784.6 | 406.4 | 385.5 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1500_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/1/2022 |  |  | N | No
PJM | AG1-501 | Beaver 138 kV |  | OH | Lorain | Active | ATSI | 106.5 | 11.3 | 10 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1501_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1501_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/1/2022 |  |  | N | No
PJM | AG1-502 | Oak Green 115 kV |  | VA | Orange | Active | Dominion | 80 | 80 | 64 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1502_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-503 | Oak Green 115 kV |  | VA | Orange | Active | Dominion | 20 | 20 | 16 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1503_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG1-508 | Point Lookout 69 kV |  | VA | Grayson | Active | AEP | 63.3 | 63.3 | 9.3 |  | Capacity | Generation Interconnection | Wind |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1508_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1508_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AG1-510 | Kittatinny-Blairstown 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1510_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1510_imp.htm | Document Posted | https://www.pjm.com/pub/planning/project-queues/facilities/ag1510_fac.pdf | Document Posted | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-511 | Kittatinny 230 kV |  | NJ | Warren | Active | JCPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1511_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1511_imp.htm | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-512 | University Park North 345 kV |  | IL | Will | Active | ComEd | 646 | 40 | 16 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1512_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1512_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-514 | Springdale CT III 138 kV |  | PA | Allegheny | Active | APS | 106 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1514_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1514_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-515 | Guilford 138 kV |  | PA | Franklin | Active | APS | 110 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1515_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1515_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-516 | Gans 138 kV |  | PA | Fayette | Active | APS | 106 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1516_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1516_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-517 | Osage 138 kV |  | WV | Monongalia | Active | APS | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1517_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1517_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 4/1/2022 |  |  | N | No
PJM | AG1-522 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1522_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-523 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 600 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1523_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-524 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 900 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1524_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-525 - moved to TC1 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 1200 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1525_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-526 - moved to TC1 | West Garrard 345 kV |  | KY | Garrard | Active | EKPC | 222 | 222 | 133.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1526_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-527 | Imperial-Joffre 138 kV |  | PA | Allegheny | Active | APS | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1527_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1527_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-528 | Tenmile 138 kV |  | WV |  | Active | AEP | 225 | 225 | 135 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1528_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1528_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-529 - moved to TC1 | Farmview 138 kV |  | DE | Sussex | Active | DPL | 75 | 75 | 48.9 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1529_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1_529_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG1-532 | Fields 34.5 kV | Fields 2 | VA | Greensville | Engineering and Procurement | Dominion | 13.5 | 13.5 | 8.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1532_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1532_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag1532_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag1532_wmpa.pdf | Not Required |  |  |  | 9/30/2020 | [5 empty] | 9/29/2027 | 9/29/2027 |  | N | No
PJM | AG1-533 | Bartonsville-Meadowbrook 138 kV IV |  | VA | Frederick | Active | APS | 170 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1533_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1533_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/12/2023 |  |  | N | No
PJM | AG1-535 - moved to TC1 | State Line-S. Chicago Properties 138 kV |  | IL | Cook | Active | ComEd | 85 | 85 | 85 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1535_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1535_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG1-536 - moved to TC1 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1536_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG1-537 - moved to TC1 | Barterbrook-Stuarts Draft 115 kV |  | VA | Augusta | Active | Dominion | 75 | 75 | 32 |  | Capacity | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1537_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1537_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG1-548 - moved to TC1 | Erie South-Union City 115 kV |  | PA | Erie | Active | PENELEC | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1548_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG1-549 - moved to TC1 | Keystone 230 kV |  | PA | Armstrong | Active | PENELEC | 100 | 100 | 85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1549_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG1-551 - moved to TC1 | Parmele 12.5 kV |  | NC | Martin | Active | Dominion | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1551_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1551_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/15/2023 |  |  | N | No
PJM | AG1-552 - moved to TC1 | Carolina 13.2 kV |  | NC | Northhampton | Active | Dominion | 18 | 18 | 12.2 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1552_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 10/15/2023 |  |  | N | No
PJM | AG1-553 - moved to TC1 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 284 | 284 | 236.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1553_fea.pdf | Document Posted |  | In Progress | [10 empty] | 9/30/2020 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG1-554 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 49.99 | 49.99 | 32.7 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1554_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1554_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG1-555 | Dequine 345 kV |  | IN | Tippecance | Active | AEP | 120 | 120 | 88.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1555_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1555_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG1-558 | Buckner 34.5 kV |  | VA | Louisa | Active | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1558_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1558_imp.pdf | Document Posted |  | Not Required |  |  |  |  | Not Required |  |  |  | 9/30/2020 | [5 empty] | 10/21/2022 |  |  | N | No
PJM | AG1-559 | Caroline Pines 22 kV |  | VA | Hanover | Active | Dominion | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1559_fea.pdf | Document Posted |  | In Progress | [6 empty] | Not Required |  |  |  | 9/30/2020 | [5 empty] | 10/21/2022 |  |  | N | No
PJM | AG1-562 | Marysville-Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag1562_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag1562_imp.pdf | Document Posted |  | In Progress | [8 empty] | 9/30/2020 | [5 empty] | 12/4/2023 |  |  | N | No
PJM | AG2-001 | St. Johns DP 115 kV |  | VA | Essex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/1/2020 | [5 empty] | 9/30/2022 |  |  | N | No
PJM | AG2-002 | Galion 138 kV III |  | OH | Morrow | Active | ATSI | 164 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/2/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-003 | West Millersport 138 kV |  | OH | Fairfield | Active | AEP | 120 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/2/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-004 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 164 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/2/2020 | [5 empty] | 11/30/2021 |  |  | N | No
PJM | AG2-005 | Garner-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 196 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/2/2020 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-006 | Centerburg-Conesville 138 kV |  | OH | Licking | Active | AEP | 177.5 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/2/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-008 | Erie South-Warren 230 kV |  | PA | Erie | Active | PENELEC | 60 | 60 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/8/2020 | [5 empty] | 3/30/2023 |  |  | N | No
PJM | AG2-009 | Erie South-Warren 230 kV II |  | PA | Erie | Active | PENELEC | 80 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/8/2020 | [5 empty] | 3/30/2023 |  |  | N | No
PJM | AG2-010 | Peninsula 115 kV |  | VA | City of Hampton | Active | Dominion | 189.8 | 189.8 | 75.96 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/9/2020 | [5 empty] | 1/1/2023 |  |  | N | No
PJM | AG2-011 | Laurel Mountain 138 kV |  | WV | Barbour | Active | APS | 56.3 | 56.3 | 34.2 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/13/2020 | [5 empty] | 4/1/2024 |  |  | N | No
PJM | AG2-013 | Marysville-Sorenson 765 kV |  | OH | Logan | Active | AEP | 1300 | 200 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/16/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-014 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/19/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-016 | Oyster Creek-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/20/2020 | [5 empty] | 12/17/2021 |  |  | N | No
PJM | AG2-019 | Chase City 12.5 kV |  | VA | Mecklenburg | Active | Dominion | 15 | 15 | 6 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/30/2022 |  |  | N | No
PJM | AG2-020 | Arnolds Corner 34.5 kV |  | VA | King George | Active | Dominion | 7 | 7 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/30/2022 |  |  | N | No
PJM | AG2-021 | Crossroads 13.2 kV |  | PA | York | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-022 | Ebenezer 12.47 kV |  | PA | Dauphin | Active | PPL | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-023 | Mechanicsburg 12.47 kV |  | PA | Cumberland | Active | PPL | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-024 | Allen 13.2 kV |  | PA | Cumberland | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-025 | Mountain 13.2 kV |  | PA | Cumberland | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-026 | Leesport 34.5 kV |  | PA | Berks | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-027 | Orrtanna 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-028 | Lincoln 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-029 | Forest G. Hipple-Collingwood 345 kV |  | IN | Noble | Active | AEP | 300 | 300 | 221.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/23/2020 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-031 | East Canton-Robertsville 69 kV |  | OH | Stark | Active | AEP | 49.9 | 30.2 | 22.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/30/2020 | [5 empty] | 1/1/2023 |  |  | N | No
PJM | AG2-032 | Mannington 230 kV |  | NJ | Salem | Active | AEC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 10/30/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-034 | Emporia-Pleasant Hill 115 kV |  | VA | Greensville | Active | Dominion | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 11/4/2020 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG2-035 | Fenwick Creek 69 kV |  | NJ | Salem | Active | AEC | 71 | 33 | 22 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/11/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG2-036 | Mantua 12 kV |  | NJ | Gloucester | Active | AEC | 10 | 10 | 5.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/13/2020 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG2-037 | Findlay-Clinton 23 kV |  | PA | Allegheny | Active | DL | 4.7 | 4.7 | 2.82 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/13/2020 | [5 empty] | 12/1/2021 |  |  | N | No
PJM | AG2-038 | Boyers DP 25 kV |  | PA | Venango | Active | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/16/2020 | [5 empty] | 3/30/2022 |  |  | N | No
PJM | AG2-039 | Erie West-Fairview East 34.5 kV |  | PA | Erie | Active | PENELEC | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/16/2020 | [5 empty] | 3/30/2022 |  |  | N | No
PJM | AG2-040 | Garman-Greenwich Mine 34.5 kV |  | PA | Indiana | Active | PENELEC | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/16/2020 | [5 empty] | 3/30/2022 |  |  | N | No
PJM | AG2-041 | Jamestown Tap-Maysville 69 kV |  | PA | Mercer | Active | ATSI | 19.8 | 19.8 | 11.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/16/2020 | [5 empty] | 3/30/2022 |  |  | N | No
PJM | AG2-049 | Van Dorn 34.5 kV |  | VA | Arlington | Active | Dominion | 20 | 0 | 20 |  | Capacity | Generation Interconnection | Other |  |  |  |  | In Progress | [12 empty] | 11/20/2020 | [5 empty] | 12/31/2020 |  |  | N | No
PJM | AG2-050 | Randle Cliff 13.8 kV | CHESAPEAKE BEACH BESS | MD | Calvert | Partially in Service - Under Construction | BGE | 1 | 1 | 0 | 1 | Energy | Generation Interconnection | Storage |  |  |  | https://www.pjm.com/pub/planning/project-queues/feas_docs/ag2050_fea.pdf | Document Posted | https://www.pjm.com/pub/planning/project-queues/impact_studies/ag2050_imp.pdf | Document Posted |  | Not Required |  | Wholesale Market Participation Agreement | https://www.pjm.com/pub/planning/project-queues/wmpa/ag2050_wmpa.pdf | https://www.pjm.com/pub/planning/project-queues/csa/ag2050_wmpa.pdf | Not Required |  |  |  | 11/25/2020 |  |  | 5/1/2023 |  |  | 5/1/2023 | 5/1/2023 |  | Y | No
PJM | AG2-051 | St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/2/2020 | [5 empty] | 3/31/2023 |  |  | N | No
PJM | AG2-053 | Fulton 138 kV |  | OH | Fulton | Active | ATSI | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/2/2020 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AG2-054 | Fulton 138 kV |  | OH | Fulton | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/2/2020 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AG2-055 | Deans 500 kV |  | NJ | Middlesex | Active | PSEG | 1300 | 1300 | 370.92 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 12/4/2020 | [5 empty] | 11/1/2027 |  |  | N | No
PJM | AG2-056 | Gore 138 kV |  | VA | Frederick | Active | APS | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/4/2020 | [5 empty] | 5/31/2022 |  |  | N | No
PJM | AG2-057 | Cardington-Liberty 69 kV II |  | OH | Morrow | Active | ATSI | 81 | 17 | 7.14 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/7/2020 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AG2-058 | Harmony Village-White Marsh 115 kV |  | VA | Gloucester | Active | Dominion | 70 | 70 | 46 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/8/2020 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AG2-059 | Clubhouse-Lakeview 230 kV |  | VA | Greensville | Active | Dominion | 80 | 80 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/8/2020 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AG2-060 | Hanover-Plymouth 69 kV |  | PA | Luzerne | Active | UGI | 12.6 | 12.6 | 7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/10/2020 | [5 empty] | 3/8/2022 |  |  | N | No
PJM | AG2-061 | Powerton-Nevada 345 kV |  | IL | Lasalle | Active | ComEd | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/11/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-062 | Williams 138 kV |  | WV | Grant | Active | APS | 147 | 147 | 21.609 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 12/15/2020 | [5 empty] | 8/1/2022 |  |  | N | No
PJM | AG2-063 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 54 | 54 | 34.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/16/2020 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-064 | St Johns DP 115 kV |  | VA | Caroline | Active | Dominion | 41 | 41 | 24.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/17/2020 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-066 | Rockcastle 138 kV |  | VA | Bedford | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/28/2020 | [5 empty] | 5/30/2022 |  |  | N | No
PJM | AG2-067 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/30/2020 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-068 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/30/2020 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-069 | Heritage-Wake 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/30/2020 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-070 | Chickhominy-Surry 500 kV |  | VA | Charles City | Active | Dominion | 325 | 325 | 228 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 12/30/2020 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG2-072 | Rockport 765 kV |  | IN | Spencer | Active | AEP | 700 | 700 | 700 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 1/6/2021 | [5 empty] | 5/31/2026 |  |  | N | No
PJM | AG2-073 | Crooksville 69 kV |  | KY | Madison | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/11/2021 | [5 empty] | 5/1/2024 |  |  | N | No
PJM | AG2-074 | Meckesville Tap 69kV |  | PA | Carbon | Active | PPL | 38 | 38 | 26.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/15/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-077 | Clover-Rawlings 500 kV |  | VA | Charlotte | Active | Dominion | 700 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/19/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-078 | Lappans 34.5 kV |  | MD | Washington | Active | APS | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/20/2021 | [5 empty] | 5/23/2022 |  |  | N | No
PJM | AG2-079 | Clearville-Clearville Junction 34.5 kV |  | PA | Bedford | Active | APS | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/20/2021 | [5 empty] | 4/11/2022 |  |  | N | No
PJM | AG2-080 | Lexington 115 kV |  | VA | Rockbridge | Active | Dominion | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/21/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-081 | Mt. Sterling-Fogg Pike 69 kV |  | KY | Montgomery | Active | EKPC | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/21/2021 | [5 empty] | 5/1/2024 |  |  | N | No
PJM | AG2-082 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 200 | 200 | 133.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/22/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-083 | Greentown 138 kV |  | IN | Howard | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-084 | Greentown 138 kV |  | IN | Howard | Active | AEP | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-085 | West Del-Royerton 138 kV |  | IN | Delaware | Active | AEP | 140 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-086 | Mt. Jackson DP-Mt. Jackson 115 kV |  | VA | Shenandoah | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/22/2021 | [5 empty] | 12/30/2022 |  |  | N | No
PJM | AG2-088 | Trabue-Midlothian 230 kV line |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/26/2021 | [5 empty] | 4/15/2022 |  |  | N | No
PJM | AG2-089 | Pelikan-Kennaloyal 25 kV |  | PA | Westmoreland | Active | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/26/2021 | [5 empty] | 7/1/2022 |  |  | N | No
PJM | AG2-090 | Scalp Level 23 kV IV |  | PA | Somerset | Active | PENELEC | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/26/2021 | [5 empty] | 1/31/2023 |  |  | N | No
PJM | AG2-091 | Scalp Level 23 kV V |  | PA | Somerset | Active | PENELEC | 20 | 6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/26/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-092 | Todd 69 kV II |  | MD | Dorchester | Active | DPL | 50 | 0 | 11 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/26/2021 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AG2-093 | Colonial Trail-Hopewell 230 kV |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/26/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-094 | Summer Shade-Green County 161 kV |  | KY | Metcalfe | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/27/2021 | [5 empty] | 4/1/2024 |  |  | N | No
PJM | AG2-095 | Hopewell 34.5 kV (Circuit 313) |  | VA | Prince George | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 12/8/2023 |  |  | N | No
PJM | AG2-096 | Dauphin PG Tie-Dauphin Juniata Tie 69 kV |  | PA | Dauphin | Active | PPL | 55 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AG2-097 | Altoona-Raystown 230 kV II |  | PA | Blair | Active | PENELEC | 80 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-098 | Copperstone-North Lebanon 230 kV II |  | PA | Lebanon | Active | ME | 70 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-099 | Moshannon-Milesburg 230 kV V |  | PA | Centre | Active | APS | 83.6 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-100 | Moshannon-Milesburg 230 kV VI |  | PA | Centre | Active | APS | 78.38 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-101 | Princess Anne–Loretto 69 kV |  | MD | Somerset | Active | DPL | 58.6 | 58.6 | 35.16 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-102 | Oak Hall-Perdue 69 kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/28/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-103 | Oak Hall-Hallwood 69 kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | Withdrawn | [12 empty] | 1/28/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-104 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 400 | 253.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 9/1/2025 |  |  | N | No
PJM | AG2-105 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 800 | 400 | 253.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AG2-106 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-107 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-108 | Milford-Cool Springs 230 kV |  | DE | Sussex | Active | DPL | 460 | 460 | 130.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 10/31/2026 |  |  | N | No
PJM | AG2-109 | Fitchville-New London 69 kV |  | OH | Huron | Active | ATSI | 40 | 40 | 28.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-110 | Marysville-Tangy 345 kV |  | OH | Union | Active | AEP | 300 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-111 | Perth 34.5 kV Substation (Circuit 408) |  | VA | Campbell | Active | Dominion | 14.5 | 14.8 | 8.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 2/6/2023 |  |  | N | No
PJM | AG2-112 | Perth 34.5 kV Substation (Circuit 404) |  | VA | Halifax | Active | Dominion | 15.2 | 15.2 | 9.12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 3/24/2023 |  |  | N | No
PJM | AG2-113 | Nokesville-Vint Hill 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 8/10/2022 |  |  | N | No
PJM | AG2-114 | Dresden-Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 3/1/2024 |  |  | N | No
PJM | AG2-115 | Mt. Hermon 25 kV |  | MD | Wicomico | Active | DPL | 8.47 | 8.466 | 3.5557 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 8/29/2022 |  |  | N | No
PJM | AG2-116 | Olive-Reynolds 345 #1 345 kV |  | IN | White | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-117 | Olive-Reynolds #2 345 kV |  | IN | White | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-118 | Ford-Cedarville 138 kV |  | OH | Clermont | Active | DEOK | 84 | 84 | 56.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-119 | Galion-Roberts South 138 kV II |  | OH | Marion | Active | ATSI | 160 | 160 | 106.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-120 | Everetts 34.5 kV |  | NC | Martin | Active | Dominion | 21 | 21 | 14 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/15/2024 |  |  | N | No
PJM | AG2-121 | Mackeys 230 kV |  | NC | Washington | Active | Dominion | 140 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-122 | Crystal Hill - Halifax 115 kV |  | VA | Halifax | Active | Dominion | 64.7 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-123 | Sedge Hill - Person 230 kV |  | VA | Halifax | Active | Dominion | 75.1 | 0 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-124 | Shackleford-Harmony 115 kV |  | VA | King and Queen | Active | Dominion | 149.9 | 0 | 33.34 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-125 | Camden-Crystal 69 kV |  | OH | Preble | Active | Dayton | 69.9 | 0 | 15.44 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-126 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG2-127 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-128 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/30/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AG2-129 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/30/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AG2-130 | Colby Tap-Valley 138 kV |  | MI | Van Buren | Active | AEP | 55 | 55 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/2/2021 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AG2-131 | Almena-Valley 69 kV |  | MI | Van Buren | Active | AEP | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/1/2021 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AG2-132 | Hartford-South Haven 69 kV |  | MI | Van Buren | Active | AEP | 15 | 15 | 7.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/1/2021 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AG2-137 | Surry-Chuckatuck 230 kV |  | VA | Isle of Wight | Active | Dominion | 70 | 70 | 43.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/8/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AG2-139 | Lincoln 771-4 13.2 kV |  | PA | Adams | Active | ME | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/9/2021 | [5 empty] | 8/1/2022 |  |  | N | No
PJM | AG2-143 | Burma-Sligo 25 kV |  | PA | Clarion | Active | APS | 20 | 20 | 10 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/16/2021 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AG2-147 | Pontiac Midpoint 34.5kV |  | IL | Livingston | Active | ComEd | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/22/2021 | [5 empty] | 3/1/2024 |  |  | N | No
PJM | AG2-148 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 130 | 130 | 86 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/22/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-149 | Galion-South Berwick 345 kV |  | OH | Crawford | Active | AEP | 400 | 400 | 267 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/22/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-150 | River Dock 23 kV |  | PA | Allegheny | Active | DL | 5.25 | 5.25 | 5.25 |  | Capacity | Generation Interconnection | Hydro |  |  |  |  | In Progress | [12 empty] | 2/23/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-151 | Trices Lake - James River Tap 115 kV |  | VA | Cumberland | Active | Dominion | 100 | 102.2 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2021 | [5 empty] | 2/2/2024 |  |  | N | No
PJM | AG2-152 | Banister-Bear Skin 138 kV |  | VA | Pittsylvania | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2021 | [5 empty] | 2/2/2024 |  |  | N | No
PJM | AG2-153 | Headquarters-Sideview 69 kV |  | KY | Bourbon | Active | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG2-154 | Danville 12 kV |  | PA | Northumberland | Active | PPL | 1 | 1 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-155 | Linden 12 kV |  | PA | Lycoming | Active | PPL | 2.8 | 2.8 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-156 | Montgomery 12 kV |  | PA | Lycoming | Active | PPL | 5.1 | 5.1 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-157 | Ashfield 12 kV |  | PA | Carbon | Active | PPL | 1.5 | 1.5 | 0.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AG2-159 | Williamstown 69 kV |  | KY | Grant | Active | EKPC | 61 | 61 | 43 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 9/15/2023 |  |  | N | No
PJM | AG2-161 | Wheelabrator Frackville-Gilberton 69 kV |  | PA | Schuylkill | Active | PPL | 43 | 43 | 39.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG2-162 | Hanna-Tanners Creek 345 kV |  | IN | Rush | Active | AEP | 115 | 115 | 76 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-163 | Dequine-Eugene 345 kV |  | IN | Fountain | Active | AEP | 700 | 250 | 184 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-164 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 270 | 270 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-165 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 200 | 134 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-166 | Newville-Nottingham Tap 1 69 kV |  | PA | Cumberland | Active | PPL | 13.3 | 13.3 | 8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 8/18/2023 |  |  | N | No
PJM | AG2-167 | Morgan Street-Cochranton 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-168 | Clinch River-Copper Ridge 138 kV |  | VA | Russell | Active | AEP | 95 | 95 | 63.3333 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-169 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 70 | 70 | 46.6667 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-170 | Whitewater Valley Power Station 69 kV |  | IN | Wayne | Active | AEP | 88 | 88 | 58.6667 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-171 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 60 | 68.4 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 7/3/2024 |  |  | N | No
PJM | AG2-172 | Kittatinny 230 kV |  | NJ | Warren | Active | JCPL | 450 | 30 | 30 |  | Capacity | Generation Interconnection | Hydro |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG2-173 | Twin Branch-Meridian 345 kV |  | IN | Whitley | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-174 | Jack Frost-Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 20 | 20 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/30/2024 |  |  | N | No
PJM | AG2-175 | Van Wert-Delphos 69 kV |  | OH | Van Wert | Active | AEP | 65 | 65 | 49 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-176 | Geneva 115 kV |  | PA | Crawford | Active | PENELEC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 1/31/2024 |  |  | N | No
PJM | AG2-177 | Limecrest-Woodruff's Gap 34.5 kV |  | NJ | Sussex | Active | JCPL | 8 | 8 | 3.36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 2/23/2022 |  |  | N | No
PJM | AG2-178 | Remington 34.5 kV |  | VA | Fauquier | Active | Dominion | 14.125 | 14.125 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/30/2022 |  |  | N | No
PJM | AG2-179 | Coburg 69 kV |  | KY | Adair | Active | EKPC | 60 | 60 | 42.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 9/15/2023 |  |  | N | No
PJM | AG2-180 | Paulsboro 69 kV |  | NJ | Gloucester | Active | AEC | 79 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 2/25/2021 |  |  | N | No
PJM | AG2-181 | Airey - Golden Hill 69 kV |  | MD | Dorchester | Active | DPL | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-182 | Doubs-Bismark 500 kV |  | VA | Frederick | Active | Dominion | 200 | 200 | 133.3333 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-184 | Spicewood-Softshell 138 kV |  | KY | Knott | Active | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-185 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Active | PPL | 40 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 5/1/2024 |  |  | N | No
PJM | AG2-186 | Effort Mountain-Gilbert 138 kV |  | PA | Monroe | Active | PPL | 45.2 | 5.2 | 3.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-187 | Amherst-Riverville 138 kV |  | VA | Amherst | Active | AEP | 115 | 40 | 33.2 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-188 | Farmville-Bucking 230 kV |  | VA | Cumberland | Active | Dominion | 149.9 | 149.9 | 89.94 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 3/1/2024 |  |  | N | No
PJM | AG2-189 | Washington-Pequest River 34.5 kV |  | NJ | Warren | Active | JCPL | 19.8 | 19.8 | 8.316 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 2/23/2022 |  |  | N | No
PJM | AG2-191 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 11/30/2023 |  |  | N | No
PJM | AG2-192 | Mississinewa 138 kV |  | IN | Grant | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-193 | Turner 34.5 kV |  | VA | Henrico | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-194 | Pierce-Kyger Creek 345 kV |  | OH | Highland | Active | OVEC | 170 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-195 | Dowling 138 kV |  | OH | Wood | Active | ATSI | 53 | 53 | 22.26 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-197 | Nelson- Electrical Junction 345 kV |  | IL | Lee | Active | ComEd | 295.9 | 295.9 | 52 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-198 | Briery-Clover 230 kV |  | VA | Prince Edward | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2021 | [5 empty] | 2/25/2024 |  |  | N | No
PJM | AG2-199 | Birchwood-NUG 230 kV |  | VA | King George | Active | Dominion | 55 | 55 | 35.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2021 | [5 empty] | 10/10/2023 |  |  | N | No
PJM | AG2-200 | North Warren–Russell 34.5 kV |  | PA | Warren | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-202 | Reusens 12.47 kV |  | VA | City of Lynchburg | Active | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/4/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG2-203 | Perkins Park 12.47 kV |  | VA | City of Lynchburg | Active | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/4/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG2-204 | Athenia 26 kV |  | NJ | Essex | Active | PSEG | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/4/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG2-206 | Tennessee Gas-East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 48 | 48 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-207 | Brandon Shores 230 kV |  | MD | Anne Arundel | Active | BGE | 275 | 275 | 110 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/4/2021 | [5 empty] | 3/31/2023 |  |  | N | No
PJM | AG2-208 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 70 | 79.2 | 44.47 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/5/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-209 | Greenwood DP - St. Johns DP 115 kV |  | VA | Louisa | Active | Dominion | 70 | 0 | 20.76 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/5/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-212 | Dumont-Greentown 765 kV |  | IN | Marshall | Active | AEP | 400 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-213 | Gary D.P Tap - Gary D.P 115 kV |  | VA | Lunenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-214 | Red House D.P - Sugar Hill 115 kV |  | VA | Charlotte | Active | Dominion | 60 | 60.17 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-215 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 176 | 0 | 36.92 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-216 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 144 | 0 | 25.92 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-217 | Watkins Corner 34.5 kV |  | VA | Southampton | Active | Dominion | 20 | 20.9 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2021 | [5 empty] | 4/29/2023 |  |  | N | No
PJM | AG2-218 | La Rue 69 kV |  | OH | Marion | Active | AEP | 49.5 | 49.5 | 32 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-219 | Jefferson-Greentown 765 kV |  | IN | Decatur | Active | AEP | 600 | 330 | 220.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-220 | East Towanda-South Troy 115 kV |  | PA | Bradford | Active | PENELEC | 31 | 31 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2021 | [5 empty] | 9/30/2025 |  |  | N | No
PJM | AG2-221 | South Troy - North Towanda 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 14 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AG2-222 | Tanners Creek-Hanna 345 kV |  | IN | Rush | Active | AEP | 83 | 83 | 55 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-223 | Allen Junction 345 kV |  | OH | Lucas | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG2-225 | Wagner 115 kV |  | MD | Anne Arundel | Active | BGE | 135 | 115 | 46 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-226 | Martins Creek 69 kV II |  | PA | Northampton | Active | PPL | 52 | 52 | 20.8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-228 | Pequest River-Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 11.2 | 11.2 | 4.704 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/12/2021 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AG2-229 | Floyd 138 kV |  | VA | Floyd | Active | AEP | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/12/2021 | [5 empty] | 1/1/2024 |  |  | N | No
PJM | AG2-230 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/12/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-233 | Montgomery Hydroelectric 23 kV |  | PA | Beaver | Active | DL | 20 | 20 | 17.5 |  | Capacity | Generation Interconnection | Hydro |  |  |  |  | In Progress | [12 empty] | 3/15/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-234 | Neville 23 kV |  | PA | Allegheny | Active | DL | 20 | 3.2 | 1.5 |  | Capacity | Generation Interconnection | Hydro |  |  |  |  | In Progress | [12 empty] | 3/15/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-235 | Lincoln-Berrywood 69 kV |  | OH | Delaware | Active | AEP | 73 | 73 | 30.66 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/15/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-236 | Potter-Harlan 69 kV |  | PA | Lawrence | Active | ATSI | 60 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/15/2021 | [5 empty] | 10/30/2024 |  |  | N | No
PJM | AG2-237 | Thelma 230kV |  | NC | Northhampton | Active | Dominion | 300 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 12/15/2025 |  |  | N | No
PJM | AG2-238 | Earleys 230 kV |  | NC | Hertford | Active | Dominion | 99.9 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 12/15/2025 |  |  | N | No
PJM | AG2-239 | Hickory-Shawboro 230 kV |  | NC | Currituck | Active | Dominion | 60 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 12/15/2025 |  |  | N | No
PJM | AG2-240 | Old Church 34.5 kV |  | VA | Hanover | Active | Dominion | 25 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 12/15/2025 |  |  | N | No
PJM | AG2-241 | Roadstown 69 kV |  | NJ | Cumberland | Active | AEC | 47 | 47 | 31.3333 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 9/15/2023 |  |  | N | No
PJM | AG2-243 | Rome-Orwell 36 kV |  | OH | Ashtabula | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-244 | Winfield-Presrite Corp 36 kV |  | OH | Ashtabula | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-245 | Olive - Reynolds #1 345 kV |  | IN | Starke | Active | AEP | 210 | 210 | 126 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/16/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG2-247 | Northwestern REC Dixonburg-Vernon 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/17/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-248 | East Elkhart 345 kV |  | IN | Elkhart | Active | AEP | 150 | 150 | 100 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/17/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-249 | Stoneboro-Perry 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/17/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-250 | Stoneboro-Perry 69 kV II |  | PA | Mercer | Active | ATSI | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/17/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-251 | Dilworth 69 kV |  | OH | Trumbull | Active | ATSI | 29 | 29 | 17.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-252 | Dilworth 69 kV II |  | OH | Trumbull | Active | ATSI | 49 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-253 | Dilworth 69 kV III |  | OH | Trumbull | Active | ATSI | 69 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-254 | New Lisbon 12.47 kV |  | NJ | Burlington | Active | JCPL | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 3/30/2022 |  |  | N | No
PJM | AG2-255 | South Hampton 13 kV |  | NJ | Burlington | Active | PSEG | 4 | 4 | 1.68 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 3/30/2022 |  |  | N | No
PJM | AG2-258 | Carson – Rogers Road 500 kV |  | VA | Accomack | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 3/1/2024 |  |  | N | No
PJM | AG2-259 | Sherwood - Kidds Store 115 kV |  | VA | Fluvanna | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 3/4/2024 |  |  | N | No
PJM | AG2-260 | Crystal Hill - Perth 115 kV |  | VA | Halifax | Active | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-261 | Lake View - Clubhouse 230 kV |  | VA | Greensville | Active | Dominion | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-262 | Dryburg 115 kV |  | VA | Halifax | Active | Dominion | 56 | 11 | 6.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/18/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG2-263 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Active | Dayton | 40 | 40 | 31.14 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-264 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Active | Dayton | 60 | 20 | 14.74 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-265 | Jeffersonville-South Charleston 69 kV |  | OH | Fayette | Active | Dayton | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-268 | Sedge Hill 230 kV |  | VA | Halifax | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-269 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-270 | Clover 230 kV |  | VA | Halifax | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-271 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-272 | Berry Hill 138 kV |  | VA | Pittsylvania | Active | AEP | 55 | 55 | 21.35 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG2-274 | Hebron 69 kV II |  | MD | Wicomico | Active | DPL | 45.8 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/19/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-275 | Southwest 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-276 | Tyler 230 kV |  | VA | Chesterfield | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-277 | Robinson 69 kV |  | OH | Fayette | Active | Dayton | 40 | 40 | 34 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-278 | Robinson 69 kV |  | OH | Fayette | Active | Dayton | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-279 | Hagerstown-Conservit 34.5 kV |  | MD | Washington | Active | APS | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AG2-281 | Church 138 kV |  | MD | Queen Anne's | Active | DPL | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 5/1/2024 |  |  | N | No
PJM | AG2-282 | Kuranga Power Generator |  | OH | Butler | Active | DEOK | 10 | 10 | 3.102 |  | Capacity | Generation Interconnection | Solar; Wind |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 2/10/2022 |  |  | N | No
PJM | AG2-283 | Yorktown 230 kV |  | VA | York | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-284 | Catharpin 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-285 | Loudoun 230 kV |  | VA | Loudoun | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-286 | Clifton 230 kV |  | VA | Fairfax | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-287 | Beaumeade 230 kV |  | VA | Loudoun | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-288 | Stonewall 138 kV |  | VA | Frederick | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-289 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 100 | 100 | 66.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-290 | Amsden – Fremont Center 69 kV |  | OH | Seneca | Active | AEP | 158 | 58 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-291 | Williams Central 115 kV |  | PA | Susquehanna | Active | PENELEC | 16 | 16 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-292 | Scotch Hollow 230 kV |  | PA | Bradford | Active | PENELEC | 16 | 16 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 11/30/2023 |  |  | N | No
PJM | AG2-293 | Williams Potter Tap 115 kV |  | PA | Susquehanna | Active | PENELEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-294 | MacNew 115 kV |  | PA | Susquehanna | Active | PENELEC | 18 | 18 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/22/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-296 | South Berwick - Galion 345 kV |  | OH | Crawford | Active | AEP | 430 | 30 | 19.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-297 | Cumberland 230 kV |  | NJ | Cumberland | Active | AEC | 19 | 19 | 11.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG2-298 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 60 | 40 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-299 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-300 | Meadow Brook 138 kV |  | VA | Frederick | Active | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-301 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-302 | Dickerson 230 kV |  | MD | Montgomery | Active | PEPCO | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-303 | Birchwood 230 kV |  | VA | King George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-304 | Liberty 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-305 | Bristers 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-306 | Possum Point 230 kV |  | VA | Prince William | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-307 | Roundtable 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-308 | Cumberland 138 kV |  | MD | Allegany | Active | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-309 | Lanexa 230 kV |  | VA | New Kent | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-310 | Matt Funk 138 kV |  | VA | Roanoke | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-311 | Smith Mountain 138 kV |  | VA | Bedford | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-312 | Suffolk - Sunbury 230 kV |  | VA | City of Suffolk | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/23/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-314 | Gilboa-Jones Branch 138 kV III |  | WV | Nicholas | Active | APS | 150 | 0 | 67 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 5/1/2024 |  |  | N | No
PJM | AG2-315 | Twin Branch - Guardian 138 kV |  | IN | Elkhart | Active | AEP | 302.2 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG2-316 | Sandwich-Plano 138 KV |  | IL | Kendall | Active | ComEd | 292.2 | 0 | 49.4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AG2-317 | Barren - Summer Shade 161 kV |  | KY | Barren | Active | EKPC | 155 | 35 | 23.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-318 | Spotsylvania 115 kV |  | VA | Spotsylvania | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-319 | Brandon Shores 230 kV |  | MD | Anne Arundel | Active | BGE | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-320 | Ladysmith 230 kV |  | VA | Caroline | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-321 | Landstown 230 kV |  | VA | City of Virginia Beach | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-322 | Skiffs Creek 230 kV |  | VA | James City | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-323 | Shelhorn 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-324 | Buttermilk 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-325 | Pacific 230 kV |  | VA | Loudoun | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-326 | Reston 230 kV |  | VA | Fairfax | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-327 | Tennessee Gas - East Towanda 115 kV |  | PA | Bradford | Active | PENELEC | 68 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/24/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-328 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 600 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-329 | S Berwick - Galion 345 kV |  | OH | Wyandot | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-330 | Dumont - Greentown 765 kV |  | IN | Marshall | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-331 | Jefferson - Greentown 765 kV |  | IN | Decatur | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-332 | East Elkhart – Elcona Tap 138 kV |  | IN | Elkhart | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-333 | Martinsville - Highland 69 kV |  | OH | Fayette | Active | Dayton | 49 | 49 | 38.05 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-334 | Miller REC - Warrior Ridge 46 kV |  | PA | Huntingdon | Active | PENELEC | 30 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-336 | Midway 138 kV |  | OH | Henry | Active | ATSI | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 11/30/2023 |  |  | N | No
PJM | AG2-337 | Midway 138 kV II |  | OH | Henry | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 11/30/2023 |  |  | N | No
PJM | AG2-338 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-339 | Rogers Road - Carson 500 kV |  | VA | Sussex | Active | Dominion | 140 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-341 | Ridge Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/25/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-342 | Milford - Cool Springs 230 kV II |  | DE | Sussex | Active | DPL | 900 | 440 | 124.9 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 10/31/2026 |  |  | N | No
PJM | AG2-343 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-344 | Dequine 345 bkV |  | IN |  | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-345 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-347 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 448.8 | 448.8 | 121.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 8/31/2025 |  |  | N | No
PJM | AG2-348 | Indian River 230 kV II |  | DE | Sussex | Active | DPL | 897.6 | 897.6 | 242.3 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 8/31/2025 |  |  | N | No
PJM | AG2-351 | Beatty-London 138 kV III |  | OH | Madison | Active | ATSI | 196 | 0 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 2/28/2023 |  |  | N | No
PJM | AG2-354 | Ragland - Grant Branch 138 kV |  | WV | Mingo | Active | AEP | 100 | 100 | 72.92 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AG2-355 | North Muskingum River - Philo 138 kV |  | OH | Morgan | Active | AEP | 125 | 125 | 82.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-356 | South Troy - Canton 34.5 kV |  | PA | Bradford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 1/15/2023 |  |  | N | No
PJM | AG2-357 | Wilton 345 kV |  | IL | Will | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AG2-358 | Midway 345 kV |  | OH | Henry | Active | ATSI | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AG2-359 | Hillcrest 345 kV |  | OH | Brown | Active | DEOK | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AG2-360 | Broadford 138 kV |  | VA | Smyth | Active | AEP | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AG2-361 | Lanexa – Dunnsville 230 kV |  | VA | New Kent | Active | Dominion | 100 | 100 | 63.46 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-362 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Active | Dominion | 100 | 0 | 36.54 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-363 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AG2-364 | Powerton 345 kV |  | IL | Tazewell | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AG2-365 | Conneaut Lake-Werner 69 kV |  | PA | Mercer | Active | ATSI | 35 | 35 | 21 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AG2-366 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-367 | VEPCO South Creek - Pamplin 115 kV |  | VA | Appomattox | Active | Dominion | 100 | 100.28 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-368 | Scottsville - CVEC Delivery 69 kV Point |  | VA | Buckingham | Active | AEP | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-369 | Vepco Heritage - Wake 500 kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-370 | Tillman 138 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/26/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-371 | Newville 12 kV |  | PA | Cumberland | Active | PPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG2-372 | Lock 34.5 kV |  | PA | Chester | Active | PECO | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG2-373 | Nittany-Zion 46 kV |  | PA | Centre | Active | APS | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG2-375 | Fostoria Central 345 kV |  | OH | Hancock | Active | AEP | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AG2-376 | Beatty 345 kV |  | OH | Franklin | Active | AEP | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AG2-377 | West Unity – Exit 2/Holiday City Tap 69 kV |  | OH | Williams | Active | ATSI | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AG2-378 | North Hampton – Medway 69 kV |  | OH | Clark | Active | ATSI | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AG2-379 | Easton - Steele 138 kV III |  | MD | Talbot | Active | DPL | 79 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 9/15/2023 |  |  | N | No
PJM | AG2-380 | Carville 138 kV IV |  | MD | Queen Anne's | Active | DPL | 106 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 9/15/2023 |  |  | N | No
PJM | AG2-381 | Church - Oil City 138 kV II |  | MD | Caroline | Active | DPL | 112 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 9/15/2023 |  |  | N | No
PJM | AG2-382 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 9/20/2024 |  |  | N | No
PJM | AG2-384 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 60 | 60 | 24 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-385 | North Hampton 69 kV |  | OH | Clark | Active | ATSI | 54 | 54 | 36.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AG2-386 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 4/1/2023 |  |  | N | No
PJM | AG2-388 | Pole 249 6094 12.47 kV |  | VA | Campbell | Active | AEP | 6 | 6 | 6 |  | Capacity | Generation Interconnection | Methane |  |  |  |  | In Progress | [12 empty] | 3/29/2021 | [5 empty] | 9/1/2022 |  |  | N | No
PJM | AG2-398 | Fairfield 12 kV |  | PA | Lycoming | Active | PPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | Withdrawn | [12 empty] | 3/30/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG2-400 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-401 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/15/2021 |  |  | N | No
PJM | AG2-402 | Allen 345 kV |  | IN | Allen | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-403 | Meadow Brook - Mt. Storm 500 kV |  | WV | Hardy | Active | APS | 125 | 125 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-404 | Meadow Brook - Mt. Storm 500 kV II |  | WV | Hardy | Active | APS | 425 | 425 | 172.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-405 | Continental 69 kV |  | OH | Putnam | Active | AEP | 49.9 | 0 | 10.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG2-406 | Payne 69 kV |  | OH | Paulding | Active | AEP | 49.9 | 0 | 10.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG2-407 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-408 | Allen 345 kV |  | IN | Allen | Active | AEP | 100 | 0 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 9/30/2022 |  |  | N | No
PJM | AG2-410 | Watkins Corner 34.5 kV |  | VA | Southampton | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AG2-411 | Statler Hill 115 kV |  | PA | Somerset | Active | PENELEC | 63 | 63 | 40.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AG2-413 | Brush Junction - Pleasant Gap 46 kV |  | PA | Centre | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-414 | Axton 138 kV |  | VA | Henry | Active | AEP | 350 | 350 | 210 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-415 | Gold – Tennessee Gas 115 kV |  | PA | Potter | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-416 | Edinboro South - Venango Junction 115 kV II |  | PA | Crawford | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-417 | Clinton 69 kV II |  | PA | Lycoming | Active | PPL | 100 | 100 | 88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-418 | Blain 115 kV |  | PA | Perry | Active | PENELEC | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AG2-419 | 3 Bridges Rd 34.5 kV |  | MD | Caroline | Active | DPL | 40 | 40 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AG2-420 | Eclipse #2 34.5 kV |  | PA | Venango | Active | PENELEC | 25 | 25 | 14 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AG2-421 | High Street 12.47 kV |  | NJ | Cumberland | Active | AEC | 1 | 1 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2022 |  |  | Y | No
PJM | AG2-423 | Cherry Run–Harmony 138 kV |  | WV | Barbour | Active | APS | 80 | 80 | 58 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-424 | Bonnieville - Lebanon 138 kV |  | KY | Larue | Active | EKPC | 63.25 | 63.25 | 34.95 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AG2-425 | Jackson Road - Nanty Glo 46 kV |  | PA | Cambria | Active | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | Withdrawn | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-426 | Wakefield - Waverly 115 kV |  | VA | Sussex | Active | Dominion | 59 | 59 | 47.66 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 2/29/2024 |  |  | N | No
PJM | AG2-427 | Waverly 115 kV |  | VA | Sussex | Active | Dominion | 85 | 85 | 66.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 2/29/2024 |  |  | N | No
PJM | AG2-428 | Sapony 230 kV |  | VA | Sussex | Active | Dominion | 170 | 170 | 135.66 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 2/29/2024 |  |  | N | No
PJM | AG2-429 | Burma - Armstrong 138 kV |  | PA | Clarion | Active | APS | 69 | 69 | 53.86 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 2/29/2024 |  |  | N | No
PJM | AG2-430 | Sunbury-Dalmatia 69 kV II |  | PA | Northumberland | Active | PPL | 60 | 60 | 37.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-431 | Sapony 34.5 kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12.54 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AG2-432 | Mount Airy - Wythe 138 kV |  | VA | Wythe | Active | AEP | 45 | 45 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-433 | Sabinsville 115 kV |  | PA | Tioga | Active | PENELEC | 50 | 50 | 21 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AG2-434 | Rockwood 23 kV |  | PA | Somerset | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG2-435 | Crossroads 13.2 kV II |  | PA | York | Active | ME | 4.6 | 4.6 | 2.76 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AG2-436 | Carson - Rogers Road 500 kV |  | VA | Sussex | Active | Dominion | 500 | 500 | 500 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-437 | Monarch I Interconnection 500 kV |  | VA | Greensville | Active | Dominion | 400 | 400 | 400 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-438 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 10 | 10 | 6.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/15/2023 |  |  | N | No
PJM | AG2-439 | Oxbow 34.5 kV |  | PA | Wyoming | Active | PENELEC | 9.8 | 9.8 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/15/2023 |  |  | N | No
PJM | AG2-440 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-441 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-442 | Twittys Creek - Madisonville 115 kV |  | VA | Charlotte | Active | Dominion | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-443 | Benner 12 kV |  | OH | Montgomery | Active | Dayton | 4 | 4 | 1.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/28/2022 |  |  | N | No
PJM | AG2-444 | Bixby - Biers Run 345 kV |  | OH | Pickaway | Active | AEP | 346 | 346 | 207.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-445 | Adkins - Atlanta 345 kV |  | OH | Pickaway | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-446 | Cedar Creek 138 kV |  | DE | New Castle | Active | DPL | 114.3 | 0 | 25.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 11/15/2022 |  |  | N | No
PJM | AG2-447 | Cedar Creek 138 kV VII |  | DE | New Castle | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 2/1/2024 |  |  | N | No
PJM | AG2-448 | Cross School - Westvaco 138 kV |  | WV | Mineral | Active | APS | 150 | 150 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/24/2024 |  |  | N | No
PJM | AG2-449 | Tanners Creek - Hanna 345 kV |  | IN | Rush | Active | AEP | 235 | 120 | 81.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-450 | Bridgeport 230 kV |  | NJ | Gloucester | Active | AEC | 225 | 225 | 115.3 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AG2-451 | Chambers 230 kV |  | NJ | Salem | Active | AEC | 240 | 240 | 123 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-452 | SW Lima - Shelby 345 kV |  | OH | Auglaize | Active | AEP | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-453 | Lasalle - Plano 345 kV |  | IL | Kendall | Active | ComEd | 280 | 280 | 196 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-454 | Dequine - Eugene 345 kV |  | IN | Fountain | Active | AEP | 300 | 300 | 210 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-455 | Dequine - Sullivan 345 kV |  | IN | Fountain | Active | AEP | 280 | 280 | 196 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-456 | Pierce Brook-Lewis Run 230 kV |  | PA | McKean | Active | PENELEC | 80 | 80 | 55.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-457 | Farmers Valley-Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 80 | 80 | 55.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-458 | Kittatinny-Newton 34.5 kV II |  | NJ | Sussex | Active | JCPL | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 5/31/2022 |  |  | N | No
PJM | AG2-459 | Allenwood - Larrabee 34.5 kV II |  | NJ | Monmouth | Active | JCPL | 7 | 0 | 0.7 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AG2-460 | East Flemington-Lebanon 34.5 kV II |  | NJ | Hunterdon | Active | JCPL | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 8/31/2022 |  |  | N | No
PJM | AG2-461 | Lanexa - Dunnsville 230 kV |  | VA | New Kent | Active | Dominion | 88 | 88 | 57.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/15/2024 |  |  | N | No
PJM | AG2-462 | Wythe - Glen Lyn 138 kV |  | VA | Wythe | Active | AEP | 150 | 150 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-463 | Gold – Tennessee Gas 115 kV II |  | PA | Potter | Active | APS | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-464 | Feagans Mill - Stonewall 138 kV |  | WV | Jefferson | Active | APS | 80 | 80 | 24 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-465 | South Tiffin - West End Fostoria 138 kV |  | OH | Seneca | Active | AEP | 79 | 79 | 29.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-466 | Culloden - Wyoming 765 kV |  | WV |  | Active | AEP | 1000 | 1000 | 414 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/30/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-467 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-469 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-470 | Fostoria - Lemoyne 345 kV |  | OH | Wood | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-471 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-472 | Jennings-Hazelton 138kV |  | WV | Preston | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-473 | Brody 138 kV |  | MI | Cass | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-474 | Mottville 138 kV |  | MI | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-475 | Chickahominy - Surry 500 kV |  | VA | Charles City | Active | Dominion | 500 | 500 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-476 | Hokes-Grantley 69 kV II |  | PA | York | Active | ME | 20 | 0 | 0.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AG2-477 | Hokes-Jackson 69 kV III |  | PA | York | Active | ME | 20 | 0 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/30/2022 |  |  | N | No
PJM | AG2-478 | Hokes-Jackson 69 kV IV |  | PA | York | Active | ME | 20 | 0 | 0.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/31/2022 |  |  | N | No
PJM | AG2-479 | Penns Tap-Richfield Tie 69 kV II |  | PA | Snyder | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG2-480 | Derry Tap-Derry Bus 69 kV II |  | PA | Montour | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2022 |  |  | N | No
PJM | AG2-481 | Derry Tap-Derry Bus 69 kV III |  | PA | Northumberland | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/31/2022 |  |  | N | No
PJM | AG2-482 | Bowman's Mill-Scott 69 kV II |  | PA | Columbia | Active | PPL | 35 | 0 | 8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/15/2022 |  |  | N | No
PJM | AG2-483 | Bowman's Mill Tap-Scott 69 kV III |  | PA | Columbia | Active | PPL | 75 | 0 | 2.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/15/2022 |  |  | N | No
PJM | AG2-484 | Mifflintown Bus-Mifflintown Tap 69 kV II |  | PA | Juniata | Active | PPL | 20 | 0 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 8/31/2022 |  |  | N | No
PJM | AG2-485 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Active | PPL | 20 | 0 | 5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AG2-486 | Bloomsburg-Columbia 69 kV II |  | PA | Columbia | Active | PPL | 20 | 0 | 4.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/15/2022 |  |  | N | No
PJM | AG2-487 | Madison - Tanners Creek 138 kV |  | IN | Henry | Active | AEP | 152.5 | 0 | 10.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2022 |  |  | N | No
PJM | AG2-488 | Southwest Lima 345 kV |  | OH | Allen | Active | AEP | 300 | 0 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-489 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Active | AEP | 75 | 0 | 3.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-490 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Active | AEP | 75 | 0 | 1.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-491 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-492 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-497 | Tangy 138 kV |  | OH | Delaware | Active | ATSI | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-498 | Obetz 138 kV |  | OH | Franklin | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-499 | Bixby 345 kV |  | OH | Franklin | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-500 | Townsend 138 kV II |  | DE | New Castle | Active | DPL | 50 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AG2-501 | Sedge Hill - Mount Laurel 115 kV |  | VA | Halifax | Active | Dominion | 51 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AG2-502 | Sedge Hill - Person 115 kV |  | VA | Halifax | Active | Dominion | 70 | 0 | 7 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AG2-503 | Adams 138 kV |  | OH | Adams | Active | AEP | 49.9 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AG2-504 | Delano 138 kV |  | OH | Ross | Active | AEP | 49.9 | 0 | 5 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AG2-505 | Westvaco - Mt Zion 138 kV |  | MD | Garrett | Active | APS | 15 | 15 | 15 |  | Capacity | Generation Interconnection | Hydro |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-506 | Carson 230 kV |  | VA | Dinwiddie | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AG2-507 | Crewe - Victoria DP 115 kV |  | VA | Nottoway | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-508 | Dry Bread 230 kV |  | VA | Greensville | Active | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AG2-509 | Robinson 69 kV |  | WV |  | Active | AEP | 55 | 55 | 36.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-512 | Sulphur Creek-Loretto 69 kV |  | KY | Marion | Active | EKPC | 17.5 | 17.5 | 11 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AG2-513 | Hodgenville-Sulphur Creek 69 kV |  | KY | Larue | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AG2-514 | Midway 345 kV II |  | OH | Henry | Active | ATSI | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-515 | Midway 345 kV III |  | OH | Lucas | Active | ATSI | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-516 | Pecatonica 138kV |  | IL | Winnebago | Active | ComEd | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-517 | Cordova Energy Center 345kV |  | IL | Rock Island | Active | ComEd | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AG2-518 | Tech Drive 138 kV |  | VA | Montgomery | Active | AEP | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 1/1/2024 |  |  | N | No
PJM | AG2-519 | Royerton - Desoto 138 kV |  | IN | Delaware | Active | AEP | 112 | 112 | 87.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 2/29/2024 |  |  | N | No
PJM | AG2-520 | Ritchie 69 kV |  | MD | Prince George's | Active | PEPCO | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/1/2024 |  |  | N | No
PJM | AG2-521 | Fork Union 230 kV |  | VA | Fluvanna | Active | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/1/2024 |  |  | N | No
PJM | AG2-522 | Five Forks 115 kV |  | NC | Warren | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/30/2025 |  |  | N | No
PJM | AG2-524 | LaSalle Station - Mazon 138 kV |  | IL | Grundy | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-526 | Oak Grove – Saunders DP 230 kV |  | VA | Westmoreland | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-527 | Kewanee-Toulon 138 kV |  | IL | Stark | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AG2-528 | Bustleburg Tap - Fairfield DP 115 kV |  | VA | Rockbridge | Active | Dominion | 140 | 141.39 | 72.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-529 | Harrisonburg - Endless Caverns 230 kV |  | VA | Rockingham | Active | Dominion | 150 | 151.734 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-530 | Mannington Mills - Woodstown 69 kV |  | NJ | Salem | Active | AEC | 19.975 | 19.975 | 10 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-531 | Greystone - West Denville 34.5 kV |  | NJ | Morris | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/31/2022 |  |  | N | No
PJM | AG2-532 | Newburgh-Newburgh Tap 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 8/31/2022 |  |  | N | No
PJM | AG2-533 | Newburgh-Pohatcong 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 8/31/2021 |  |  | N | No
PJM | AG2-534 | Hackettstown-Pohatcong R722-7 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 8/31/2022 |  |  | N | No
PJM | AG2-535 | Hackettstown-Pohatcong J738-1 34.5 kV II |  | NJ | Warren | Active | JCPL | 40 | 20 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 8/31/2022 |  |  | N | No
PJM | AG2-536 | Buckeye - Ringoes 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 8/31/2022 |  |  | N | No
PJM | AG2-537 | Ringoes-Copper Hill Solar 34.5 kV |  | NJ | Hunterdon | Active | JCPL | 20 | 20 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 8/31/2022 |  |  | N | No
PJM | AG2-538 | Ridgeway - Motion Control 46 kV |  | PA | Elk | Active | APS | 20 | 20 | 15.42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/15/2022 |  |  | N | No
PJM | AG2-539 | Mechanicsburg - Darby 138 kV |  | OH | Union | Active | Dayton | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/14/2025 |  |  | N | No
PJM | AG2-540 | Clubhouse - Jarratt 115 kV |  | VA | Greensville | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AG2-541 | Perth - Crystal Hill 115 kV |  | VA | Halifax | Active | Dominion | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AG2-542 | North Shenandoah – Merck 115 kV |  | VA | Rockingham | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AG2-543 | Suffolk - Earleys 230 kV |  | VA | City of Suffolk | Active | Dominion | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AG2-544 | Silver Lake 138 kV |  | IL | McHenry | Active | ComEd | 200 | 200 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/6/2024 |  |  | N | No
PJM | AG2-545 | Silver Lake 345 kV |  | IL | McHenry | Active | ComEd | 400 | 400 | 160 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/6/2024 |  |  | N | No
PJM | AG2-546 | Van Buren - Delaware 138 kV |  | IN | Grant | Active | AEP | 150 | 40 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AG2-547 | New Liberty - Boutwell 138 kV |  | OH | Hancock | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-548 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-549 | Rineyville 69 kV |  | KY | Hardin | Active | EKPC | 40 | 40 | 26.6667 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AG2-550 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 200 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-551 | Bluff Point - Randolph 138 kV |  | IN | Randolph | Active | AEP | 250 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-552 | Bullitt County 161 kV |  | KY | Bullitt | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-553 | Bullitt County 161 kV |  | KY | Bullitt | Active | EKPC | 50 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AG2-557 | Spring Mills - Millheim 46 kV |  | PA | Centre | Active | APS | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2023 |  |  | N | No
PJM | AG2-558 | Shawville - Phillipsburg 34.5 kV II |  | PA | Clearfield | Active | APS | 39.8 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2023 |  |  | N | No
PJM | AG2-559 | Shawville - Phillipsburg 34.5 kV III |  | PA | Clearfield | Active | APS | 59.7 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2024 |  |  | N | No
PJM | AG2-560 | Phillipsburg (Karthaus) 34.5 kV |  | PA | Clearfield | Active | APS | 79.6 | 19.9 | 8.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-561 | Glory - Glen Campbell 34.5 kV |  | PA | Indiana | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AG2-562 | Elderberry 345 kV |  | IN | St. Joseph | Active | AEP | 786 | 71 | 35 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AG2-563 | Gasburg 69 kV |  | VA | Brunswick | Active | Dominion | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/24/2024 |  |  | N | No
PJM | AG2-564 | Sulphur Springs 138 kV |  | OH | Crawford | Active | AEP | 49.99 | 49.99 | 32.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AG2-565 | Kidds Store - Sherwood 115 kV |  | VA | Fluvanna | Active | Dominion | 110 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AG2-566 | Briery - Clover 230 kV |  | VA | Prince Edward | Active | Dominion | 110 | 30 | 12 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AG2-567 | Stanville - Dewey 138 kV |  | KY |  | Active | AEP | 200 | 200 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/24/2024 |  |  | N | No
PJM | AG2-568 | Stink Run – Sundial 138 kV |  | WV |  | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 2/25/2024 |  |  | N | No
PJM | AG2-569 | Rogers Road - Carson 500 kV |  | VA | Greensville | Active | Dominion | 150 | 50 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/25/2024 |  |  | N | No
PJM | AG2-570 | Brunswick Collector - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AG2-571 | Brunswick Collector Bus - Wake 500 kV |  | VA | Brunswick | Active | Dominion | 500 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AG2-575 | Glidden-Waterman 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-576 | Varner 345 kV |  | IN | DeKalb | Active | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-577 | Jay 138 kV |  | IN | Jay | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-578 | Jay 69 kV |  | IN | Jay | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-579 | Fostoria 138 kV |  | OH | Hancock | Active | AEP | 205 | 0 | 41 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AG2-580 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG2-581 | Rawlings-Clover 500 kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/29/2021 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG2-582 | Belmont-Flint Run 500 kV |  | WV | Doddridge | Active | APS | 2100 | 2100 | 2100 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/1/2026 |  |  | N | No
PJM | AG2-583 | Bremo - Cartersville 230 kV |  | VA | Cumberland | Active | Dominion | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AG2-584 | Double Toll Gate - Meadowbrook 138 kV |  | VA | Frederick | Active | APS | 90 | 90 | 46.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-585 | Kensignton 138kV |  | IL | Kankakee | Active | ComEd | 225 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AG2-587 | Graceton 230 kV |  | MD | Harford | Active | BGE | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-588 | Kittatinny - Blairstown 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-589 | Ravenswood Hemlock 69 kV |  | OH | Meigs | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-590 | Shingletown-Lewistown 230 kV |  | PA | Huntingdon | Active | PENELEC | 92.1 | 38.2 | 22.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-591 | Bluebell-Sancap Tap 69 kV |  | OH | Mahoning | Active | ATSI | 61 | 61 | 36.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-592 | West Cambridge - Vienna 69 kV |  | MD | Dorchester | Active | DPL | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-593 | Benton-Scott 69 kV |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-594 | Benton-Scott 69 kV II |  | PA | Columbia | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-595 | LaRue - North Waldo 138 kV |  | OH | Marion | Active | AEP | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-596 | Renaker-Avon 138 kV |  | KY | Scott | Active | EKPC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-597 | Broadford 138 kV |  | VA | Smyth | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AG2-598 | Knob Lick-JB Galloway Tap 69 kV |  | KY | Metcalfe | Active | EKPC | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/30/2025 |  |  | N | No
PJM | AG2-599 | Furnace Brook-Warren 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/30/2021 |  |  | N | No
PJM | AG2-600 | American Can-BASF 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/30/2021 |  |  | N | No
PJM | AG2-601 | Milton 69 kV III |  | PA | Northumberland | Active | PPL | 90 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/16/2022 |  |  | N | No
PJM | AG2-602 | Maysville 69 kV V |  | PA | Mercer | Active | ATSI | 60.8 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 9/15/2022 |  |  | N | No
PJM | AG2-603 | Huffman 138 kV |  | VA | Carroll | Active | AEP | 150 | 150 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-604 | Edgemont 138 kV |  | VA | Montgomery | Active | AEP | 94 | 94 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-605 | Skimmer - Abert 69 kV |  | VA | Amherst | Active | AEP | 37 | 37 | 24.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-606 | Sunbury-Juniata 500 kV |  | PA | Perry | Active | PPL | 89 | 89 | 53.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-607 | St. Johns - Dunbrook 34.5 kV |  | VA | King and Queen | Active | Dominion | 20 | 20 | 12.74 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AG2-608 | Unionville - Locust 115 kV |  | VA | Orange | Active | Dominion | 80 | 80 | 64 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/15/2023 |  |  | N | No
PJM | AG2-609 | Unionville - Locust Grove 115 kV |  | VA | Orange | Active | Dominion | 40 | 40 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/15/2023 |  |  | N | No
PJM | AG2-610 | Gold 12.5 kV |  | PA | Potter | Active | PENELEC | 4.998 | 4.998 | 3.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-611 | Hamlin 12 kV |  | PA | Wayne | Active | PPL | 4.998 | 4.998 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-612 | Lakeville 12 kV |  | PA | Wayne | Active | PPL | 4.998 | 4.998 | 4.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-614 | Mansfield 12 kV |  | PA | Tioga | Active | PENELEC | 5 | 5 | 4.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-615 | Carlos Junction 138 kV |  | MD | Allegany | Active | APS | 100 | 100 | 62.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-616 | Churchtown - Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 50 | 50 | 32.35 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-617 | Waugh Chapel 115 kV |  | MD | Anne Arundel | Active | BGE | 55 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-618 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 110 | 110 | 69.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-621 | Hoytdale 138 kV |  | PA | Beaver | Active | ATSI | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AG2-624 | Pequest River-Furnace Brook Tap 34.5 kV |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/30/2021 |  |  | N | No
PJM | AG2-625 | Pequest River-Furnace Brook Tap 34.5 kV II |  | NJ | Warren | Active | JCPL | 19.6 | 19.6 | 8.232 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/30/2021 |  |  | N | No
PJM | AG2-626 | Pequest River-Furnace Brook Tap 34.5 kV III |  | NJ | Warren | Active | JCPL | 12.5 | 12.5 | 5.25 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/30/2021 |  |  | N | No
PJM | AG2-627 | Woodstown-High Street 69 kV |  | NJ | Gloucester | Active | AEC | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-628 | Spring Creek - Millcreek 138 kV |  | OH | Miami | Active | Dayton | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-630 | Chase City-Drakes Branch 115 kV |  | VA | Mecklenburg | Active | Dominion | 118.56 | 0 | 47.43 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-631 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-632 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-633 | Gary DP - Lunenburg 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-634 | Gary DP – Lunenburg 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-635 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 270 | 270 | 162 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-636 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 270 | 0 | 108 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-637 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-638 | Kingsland 69 kV |  | IN | Wells | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-639 | Chickahominy 230 kV |  | VA | Charles City | Active | Dominion | 340 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-640 | Danieltown DP–Brunswick 69 kV |  | VA | Brunswick | Active | Dominion | 46.8 | 0 | 18.7 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-641 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-642 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 0 | 32 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-643 | Curdsville DP-Willis Mt. 115 kV |  | VA | Buckingham | Active | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-644 | Morrisville 230 kV |  | VA | Fauquier | Active | Dominion | 200 | 0 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AG2-645 | Gladys DP-Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 60 | 0 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/15/2022 |  |  | N | No
PJM | AG2-646 | Chesterfield 230 kV |  | VA | Chesterfield | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/10/2024 |  |  | N | No
PJM | AG2-647 | Bolton - Bennsville 69 kV |  | MD | Charles | Active | SMECO | 9.2 | 9.2 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/31/2023 |  |  | N | No
PJM | AG2-652 | Siegfried-Hauto 69 kV IV |  | PA | Carbon | Active | PPL | 20 | 20 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-653 | Siegfried-Hauto 69 kV V |  | PA | Carbon | Active | PPL | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AG2-654 | Cowansville Junction – Long Run Tap 25 kV |  | PA | Armstrong | Active | APS | 14.7 | 14.7 | 8.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AG2-655 | Mt. Storm 500 kV |  | WV | Grant | Active | Dominion | 800 | 800 | 330 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-656 | Kanawha River - Carbondale 138 kV |  | WV | Kanawha | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-657 | Carbondale 138 kV |  | WV | Fayette | Active | AEP | 90 | 90 | 49.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AG2-658 | Cowen 138 kV |  | WV | Webster | Active | APS | 210 | 210 | 135.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-659 | Five Forks - Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/30/2025 |  |  | N | No
PJM | AG2-660 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AG2-661 | Hopewell - Surry 230 kV |  | VA | Surry | Active | Dominion | 150 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AG2-662 | Stephensburg - Central Hardin 69 kV |  | KY | Hardin | Active | EKPC | 90 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-664 | TodHunter – Trenton 138 kV |  | OH | Butler | Active | DEOK | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AG2-665 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AG2-666 | Spurlock - Flemingsburg 138 kV |  | KY | Jackson | Active | EKPC | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-667 | Wakesfield - Poolesville 34.5 kV |  | VA | Surry | Active | Dominion | 20 | 20 | 12.53 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AG2-668 | Harvey Run 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AG2-670 | Greensburg 69 kV |  | KY | Green | Active | EKPC | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-671 | Hope - Frenchburg 69 kV |  | KY | Montgomery | Active | EKPC | 19.9 | 19.9 | 11.94 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AG2-673 | Fitzell 33 kV |  | MD | Baltimore County | Active | BGE | 9.92 | 9.92 | 3.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 12/30/2022 |  |  | N | No
PJM | AG2-674 | Quad Cities - Sterling Steel 345 kV |  | IL | Whiteside | Active | ComEd | 212.1 | 212.1 | 37.3 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/1/2023 |  |  | N | No
PJM | AG2-675 | Cordova 345 kV |  | IL | Rock Island | Active | ComEd | 80 | 80 | 32 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AG2-676 | Russell Co 161 kV |  | KY | Russell | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-677 | Russell Co J - Jamestown T 161 kV |  | KY | Russell | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-678 | Vicco - Beckham 138 kV |  | KY | Knott | Active | AEP | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-679 | Daisy - Collier 69 kV |  | KY | Letcher | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-680 | South Anna - Louisa 230 kV |  | VA | Madison | Active | Dominion | 202 | 202 | 121.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-681 | Soft Shell - Bonny Man 138 kV |  | KY | Perry | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-682 | Stinnett 161 kV |  | KY | Leslie | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-683 | Sullivan-Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-684 | Summer Shade 161 kV |  | KY | Metcalfe | Active | EKPC | 331 | 331 | 198.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-685 | Big Sandy-Inez 138 kV |  | KY | Martin | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-686 | Powell Mountain 138 kV |  | WV | Nicholas | Active | APS | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-687 | Garrard 345 kV |  | KY | Garrard | Active | EKPC | 215 | 215 | 129 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-688 | Imperial-Joffre 138 kV |  | PA | Clearfield | Active | APS | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-689 | Tenmile 138 kV |  | WV |  | Active | AEP | 125 | 125 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-690 | Sullivan - Rockport 765 kV |  | IN | Sullivan | Active | AEP | 300 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AG2-691 | New Lebanon - Ohio Hutchings 69 kV |  | OH | Montgomery | Active | Dayton | 49.5 | 49.5 | 39.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/31/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AH1-001 | Bartonsville-Meadowbrook 138 kV |  | VA | Frederick | Active | APS | 220 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/1/2021 | [5 empty] | 12/12/2023 |  |  | N | No
PJM | AH1-002 | Hector 115 kV |  | PA | Potter | Active | PENELEC | 50 | 50 | 7.35 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 4/1/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-003 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Active | ComEd | 130 | 130 | 19.11 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 4/1/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-004 | Avon - Renaker 138 kV |  | KY | Fayette | Active | EKPC | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/7/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AH1-005 | East Towanda-South Troy 115 kV II |  | PA | Bradford | Active | PENELEC | 54 | 23 | 14.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/9/2021 | [5 empty] | 9/30/2025 |  |  | N | No
PJM | AH1-010 | Stony River - Buffalo Coal 66 kV |  | WV | Grant | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/19/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-011 | Fulton - Tidd 69 kV |  | WV | Brooke | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/19/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-012 | Louisa - North Anna 230 kV |  | VA | Louisa | Active | Dominion | 90.8 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/19/2021 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AH1-013 | Hanna - Tanners Creek 345 kV |  | IN | Shelby | Active | AEP | 500 | 0 | 300 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/20/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-014 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 111.8 | 111.8 | 67.08 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/19/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-015 | Academia 138 kV |  | OH | Knox | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/22/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AH1-017 | Copperstone-North Lebanon 230 kV III |  | PA | Lebanon | Active | ME | 100 | 30 | 12.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/4/2021 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AH1-018 | Cunningham - Elmont 500 kV |  | VA | Fluvanna | Active | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/13/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-019 | Cunningham - Elmont 500 kV II |  | VA | Fluvanna | Active | Dominion | 149 | 149 | 89 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/13/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-020 | Kidds Store – Fork Union 115 kV |  | VA | Fluvanna | Active | Dominion | 38 | 38 | 22 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/13/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-021 | North Temple 781-1 13.2 kV |  | PA | Berks | Active | ME | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/12/2021 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AH1-023 | Corning Glass-Bush Town Junction 34.5 kV |  | PA | Franklin | Active | APS | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/12/2021 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AH1-024 | Lickdale 626-2 13.2 kV |  | PA | Lebanon | Active | ME | 2 | 2 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/12/2021 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AH1-025 | Myerstown 751-2 13.2 kV |  | PA | Lebanon | Active | ME | 4.5 | 4.5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/12/2021 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AH1-026 | Newberry 576-4 13.2 kV |  | PA | York | Active | ME | 4.5 | 4.5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/12/2021 | [5 empty] | 11/30/2022 |  |  | N | No
PJM | AH1-027 | Cartanza 230 kV |  | DE | Kent | Active | DPL | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/20/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AH1-032 | West Millersport 138 kV |  | OH | Fairfield | Active | AEP | 138 | 18 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/14/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-033 | Sligo 34.5 kV |  | NC | Currituck | Active | Dominion | 19.5 | 19.5 | 13 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/14/2021 | [5 empty] | 8/15/2024 |  |  | N | No
PJM | AH1-034 | Patton Road Junction - Summer Shade 69 kV |  | KY | Barren | Active | EKPC | 100 | 100 | 70 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/14/2021 | [5 empty] | 11/15/2025 |  |  | N | No
PJM | AH1-035 | Plymouth 34.5 kV |  | NC | Washington | Active | Dominion | 20 | 20 | 13.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/14/2021 | [5 empty] | 9/15/2024 |  |  | N | No
PJM | AH1-036 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 277.5 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 6/15/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-037 | Chippewa D557 8.320 kV |  |  |  | Active | ATSI | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/16/2021 | [5 empty] | 11/1/2023 |  |  | Y | No
PJM | AH1-040 | Mackeys - Creswell 115 kV |  | NC | Washington | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/23/2021 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AH1-041 | Pennville 138 kV |  | IN | Jay | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/23/2021 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AH1-042 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 154 | 154 | 99.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/25/2021 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AH1-043 | Sand Hills - Brunswick 69 kV |  | NJ | Middlesex | Active | PSEG | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 6/28/2021 | [5 empty] | 5/15/2024 |  |  | N | No
PJM | AH1-044 | Nelson - Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-045 | Zion Energy Center 345 kV |  | IL | Lake | Active | ComEd | 658 | 23 | 13.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/1/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AH1-046 | Peach Bottom 500 kV |  | PA | York | Active | PECO | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/1/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AH1-047 | Marengo - Belvidere 138 kV |  | IL | Boone | Active | ComEd | 61.6 | 61.6 | 37 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/6/2021 | [5 empty] | 9/13/2022 |  |  | N | No
PJM | AH1-048 | Riverton 138 |  | VA | Warren | Active | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/7/2021 | [5 empty] | 5/1/2024 |  |  | N | No
PJM | AH1-049 | Erie East – Union City Ckt 00234-31 34.5 kV |  | PA | Adams | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/7/2021 | [5 empty] | 7/1/2023 |  |  | N | No
PJM | AH1-050 | Eclipse-Piney 115 kV |  | PA | Venango | Active | PENELEC | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/7/2021 | [5 empty] | 7/1/2023 |  |  | N | No
PJM | AH1-051 | Eclipse-Piney 115 kV II |  | PA | Venango | Active | PENELEC | 80 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/7/2021 | [5 empty] | 7/1/2023 |  |  | N | No
PJM | AH1-052 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 260 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/7/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AH1-054 | Upton-Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 8.25 | 8.25 | 3.465 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/9/2021 | [5 empty] | 7/8/2022 |  |  | N | No
PJM | AH1-055 | Kyger Creek - Don Marquis 345 kV |  | OH | Jackson | Active | OVEC | 220 | 220 | 148.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/14/2021 | [5 empty] | 11/15/2026 |  |  | N | No
PJM | AH1-056 | Red House D.P. 115kV |  | VA | Campbell | Active | Dominion | 100 | 100 | 68.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/14/2021 | [5 empty] | 11/15/2026 |  |  | N | No
PJM | AH1-057 | Edgewood 12.47 kV |  | MD | Wicomico | Active | DPL | 7.2 | 7.2 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/15/2021 | [5 empty] | 1/31/2023 |  |  | N | No
PJM | AH1-058 | Galion 138 kV IV |  | OH | Morrow | Active | ATSI | 204 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/16/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-059 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 120 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/16/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-060 | Cardington-Liberty 69 kV III |  | OH | Morrow | Active | ATSI | 101 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/20/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-061 | Bernville 13.2kV |  | PA | Berks | Active | ME | 5 | 5 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/21/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-062 | London-Tangy 69 kV II |  | OH | Madison | Active | ATSI | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/22/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-063 | Spring Creek – South Abingdon 138 kV |  | VA | Washington | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/26/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-064 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/27/2021 | [5 empty] | 5/1/2023 |  |  | N | No
PJM | AH1-065 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 20 | 20 | 8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/27/2021 | [5 empty] | 5/1/2023 |  |  | N | No
PJM | AH1-066 | Hopewell 34.5kV |  | VA | City of Hopewell | Active | Dominion | 10 | 10 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/27/2021 | [5 empty] | 5/1/2023 |  |  | N | No
PJM | AH1-067 | Minotola 12.47 kV |  | NJ | Gloucester | Active | AEC | 8.5 | 8.5 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/27/2021 | [5 empty] | 12/10/2023 |  |  | N | No
PJM | AH1-068 | Williamstown 12.47 kV |  | NJ | Gloucester | Active | AEC | 12 | 12 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/28/2021 | [5 empty] | 12/10/2023 |  |  | N | No
PJM | AH1-069 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/28/2021 | [5 empty] | 11/30/2023 |  |  | N | No
PJM | AH1-070 | Jerome – Mohicanville 69 kV |  | OH | Ashland | Active | ATSI | 34 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/28/2021 | [5 empty] | 11/30/2023 |  |  | N | No
PJM | AH1-071 | TBD 34.5 kV |  | VA | Powhatan | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2021 | [5 empty] | 7/1/2023 |  |  | N | No
PJM | AH1-072 | Lick Fork 69 kV |  | VA | Dickenson | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AH1-073 | Lick Fork 69 kV |  | VA | Dickenson | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2021 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AH1-074 | Fitchville-New London 69 kV |  | OH | Huron | Active | ATSI | 20 | 20 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-075 | North Waldo - Wild Creek 138 kV |  | OH | Marion | Active | AEP | 68 | 8 | 24.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-076 | Loyalhanna - Reed Junction 25 kV |  | PA | Westmoreland | Active | APS | 18 | 18 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-077 | TBD 34.5 kV |  | NJ | Burlington | Active | AEC | 3 | 3 | 1.24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 8/9/2021 |  |  | N | No
PJM | AH1-078 | Paulsboro 69 kV II |  | NJ | Gloucester | Active | AEC | 79 | 0 | 58 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 9/1/2022 |  |  | N | No
PJM | AH1-079 | Harmony Village 34.5kV |  | VA | Middlesex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-080 | Virginia Beach - Pendleton 115 kV |  | VA | City of Virginia Beach | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 1/1/2025 |  |  | N | No
PJM | AH1-081 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-082 | Knob Lick 69kV |  | KY | Metcalfe | Active | EKPC | 104 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-083 | Summer Shade - Green County 161 kV |  | KY | Metcalfe | Active | EKPC | 250 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-086 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 90 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-087 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-088 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-089 | Morrisville 230kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-090 | Surry - Hopewell 230 kV |  | VA | Surry | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AH1-091 | Ahoskie 34.5kV |  | NC | Hertford | Active | Dominion | 17 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AH1-092 | SedgeHill - Person 230 kV |  | VA | Halifax | Active | Dominion | 100 | 100 | 65 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-093 | SedgeHill - Person 230 kV |  | VA | Halifax | Active | Dominion | 160 | 60 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-094 | Wells - Shinrock 69 kV I |  | OH | Huron | Active | ATSI | 49.9 | 49.9 | 32.435 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-095 | Wells - Shinrock 69 kV II |  | OH | Huron | Active | ATSI | 69.9 | 20 | 13 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-096 | Wells - Shinrock 69 kv III |  | OH | Huron | Active | ATSI | 79.9 | 10 | 6.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-097 | Jubal Early - Pipers Gap 138 kV |  | VA | Carroll | Active | AEP | 20 | 20 | 12.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-098 | Jubal Early - Pipers Gap 138 kV |  | VA | Carroll | Active | AEP | 60 | 40 | 26 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-099 | Glady Run–Xenia 69 kV |  | OH | Greene | Active | Dayton | 20 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-100 | Effort Mountain-Gilbert 138 kV II |  | PA | Monroe | Active | PPL | 45.2 | 0 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-102 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 100 | 100 | 63.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-106 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/4/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AH1-107 | Winterpock 34.5kV |  | VA | Chesterfield | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/4/2021 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AH1-108 | Spruance NUG 230 kV |  | VA | City of Richmond | Active | Dominion | 66 | 0 | 9 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 8/4/2021 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AH1-110 | Newville 12 kV II |  | PA | Cumberland | Active | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/6/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-111 | Walker 12 kV |  | PA | Juniata | Active | PPL | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/6/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-113 | North Pole - Russelville 34.5 kV |  | OH | Brown | Active | DEOK | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/9/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-114 | North Pole - Russelville 34.5 kV |  | OH | Brown | Active | DEOK | 40 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/9/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-118 | Windsor 25 kV |  | WV | Brooke | Active | APS | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/13/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-119 | Bismark-Doubs 500 kV |  | VA | Frederick | Active | Dominion | 100 | 100 | 66.6667 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/13/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-122 | Dowling 138 kV II |  | OH | Wood | Active | ATSI | 75 | 22 | 9.24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/19/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-124 | Vint Hill 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/23/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-125 | Sycoline 12.5kV |  | VA | Loudoun | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/23/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-127 | Paradise 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/23/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-128 | Railroad 34.5kV |  | VA | Prince William | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/23/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-129 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/24/2021 | [5 empty] | 2/28/2023 |  |  | N | No
PJM | AH1-130 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/24/2021 | [5 empty] | 2/28/2023 |  |  | N | No
PJM | AH1-131 | Gretna-Mt. Airy 69kV |  | VA | Pittsylvania | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/23/2021 | [5 empty] | 2/28/2023 |  |  | N | No
PJM | AH1-132 | Double Toll Gate - Strasburg 34.5 kV |  | VA | Frederick | Active | APS | 14.4 | 14.4 | 14.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 8/23/2021 | [5 empty] | 1/1/2022 |  |  | N | No
PJM | AH1-133 | Saltville - Tazewell 138 kV |  | VA | Tazewell | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/23/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-136 | Falcon -Middle Creek 46 kV |  | KY |  | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/25/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-138 | Penniman 34.5 kV |  | VA | City of Williamsburg | Active | Dominion | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 7/15/2022 |  |  | N | No
PJM | AH1-139 | Cooper 34.5kV |  | PA | York | Active | PECO | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/31/2022 |  |  | Y | No
PJM | AH1-140 | Vasco 138 kV |  | PA | Westmoreland | Active | APS | 150 | 150 | 115 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/30/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-141 | Darbytown 230 kV |  | VA | Henrico | Active | Dominion | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/26/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-142 | Darbytown 230 kV II |  | VA | Henrico | Active | Dominion | 4 | 4 | 4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-143 | Darbytown 230 kV III |  | VA | Henrico | Active | Dominion | 2 | 2 | 2 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/26/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-144 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 120 | 120 | 50.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/26/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-145 | Peter's Mountain 138 kV |  | VA | Giles | Active | AEP | 200 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/26/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-146 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/26/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-147 | Byron-Wayne 345 kV |  | IL | Ogle | Active | ComEd | 400 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-148 | Byron-Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/26/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-149 | Moselem-Saint Peters Tap 69 kV |  | PA | Berks | Active | ME | 8.375 | 8.375 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/28/2021 | [5 empty] | 9/19/2022 |  |  | N | No
PJM | AH1-150 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1000 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/28/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-151 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-152 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-153 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-154 | Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 150 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-156 | Cane Ridge 69 kV |  | KY | Bourbon | Active | EKPC | 40 | 40 | 25.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/30/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-157 | Penniman - Waller 230 kV |  | VA | York | Active | Dominion | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 1/1/2025 |  |  | N | No
PJM | AH1-158 | Eclipse-Piney 115 kV III |  | PA | Venango | Active | PENELEC | 80 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/1/2021 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AH1-159 | Conneaut-Conneaut Tap 69 kV |  | PA | Crawford | Active | ATSI | 20 | 20 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/30/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AH1-160 | Tower Hill 34.5 kV |  | PA | Tioga | Active | PENELEC | 20 | 20 | 13.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AH1-161 | Canal 69 kV |  | PA | Mercer | Active | ATSI | 20 | 20 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/30/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AH1-162 | Curryville-RKB-Yellow Creek 23 kV |  | PA | Bedford | Active | PENELEC | 16 | 16 | 11 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 11/1/2023 |  |  | N | No
PJM | AH1-163 | Millersburg 69 kV |  | KY |  | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/1/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AH1-164 | Oak Level - Tank Hill 138 kV |  | VA | Franklin | Active | AEP | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-165 | Will County 138 kV |  | IL | Will | Active | ComEd | 80 | 80 | 10 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-167 | Pinewood - St Johns 115 kV |  | VA | Caroline | Active | Dominion | 80 | 80 | 51.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 6/1/2026 |  |  | N | No
PJM | AH1-168 | Pinewood - St Johns 115 kV II |  | VA | Caroline | Active | Dominion | 120 | 40 | 25.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 6/1/2026 |  |  | N | No
PJM | AH1-169 | Greenbush 69kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-170 | Columbia DP 115kV |  | VA | Goochland | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-171 | Columbia DP 115kV |  | VA | Goochland | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/27/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-172 | Wolf Glade 34.5 kV |  | VA | Carroll | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-174 | Westlake 34.5 kV |  | VA | Franklin | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-175 | Sheffield 34.5 kV |  | VA | Henry | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-176 | Ridgeway 34.5 kV |  | VA | Henry | Active | AEP | 18.8 | 18.8 | 11.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-178 | Remington - Morrisville 34.5 kV |  | VA | Fauquier | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-179 | Edinburg - Woodstock DP 34.5 kV |  | VA | Shenandoah | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-180 | Westlake 34.5 kV |  | VA | Franklin | Active | AEP | 9 | 9 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-181 | Stuart 34.5 |  | VA | Patrick | Active | AEP | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-182 | Peak Creek 34.5 |  | VA | Pulaski | Active | AEP | 11.45 | 11.45 | 6.87 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-184 | Powhatan - Powhatan DP 24.94 kV |  | VA | Powhatan | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-185 | Benn's Church - Smithfield 34.5 kV |  | VA | Isle of Wight | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-186 | Maysville-Sharon 69 kV II |  | PA | Mercer | Active | ATSI | 19.9 | 0 | 6.4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/1/2021 | [5 empty] | 10/18/2024 |  |  | N | No
PJM | AH1-188 | Pigeon Creek 138 kV |  | WV | Mingo | Active | AEP | 185 | 185 | 129 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-189 | Hopkins 138 kV |  | WV |  | Active | AEP | 185 | 185 | 129 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/31/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-190 | Waukegan 138 kV |  | IL | Lake | Active | ComEd | 80 | 80 | 10 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/1/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-191 | Powerton 138 kV |  | IL | Tazewell | Active | ComEd | 20.9 | 20.9 | 12.065 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/1/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-196 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 450 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/2/2021 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AH1-197 | Occoquan 230kV |  | VA | Fairfax | Active | Dominion | 98 | 0 | 7.1 |  | Capacity | Generation Interconnection | Other |  |  |  |  | In Progress | [12 empty] | 9/1/2021 | [5 empty] | 8/20/2021 |  |  | N | No
PJM | AH1-198 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 1355 | 55 | 33 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/1/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-199 | Loretto 345 kV |  | IL | Livingston | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/3/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-201 | New Baltimore 115 kV (Mountain Ridge Solar) |  | PA | Somerset | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/3/2021 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AH1-202 | New Baltimore 115 kV II (Mountain Ridge Solar) |  | PA | Somerset | Active | PENELEC | 120 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/4/2021 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AH1-203 | Allegheny-Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/3/2021 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AH1-204 | Allegheny-Somerset 115 kV II |  | PA | Somerset | Active | PENELEC | 90 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/4/2021 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AH1-205 | New Baltimore 115 kV III |  | PA | Somerset | Active | PENELEC | 120 | 0 | 48 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/3/2021 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AH1-206 | Bethelboro 138 kV |  | PA | Fayette | Active | APS | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-207 | Bethelboro 25 kV-1 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-208 | Bethelboro 25 kV-2 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-209 | Bethelboro 25 kV-3 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-210 | Bethelboro 25 kV-4 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-211 | Bethelboro 25 kV-5 |  | PA | Fayette | Active | APS | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-212 | Bethlehem - Lilly 46 kV |  | PA | Cambria | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/7/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH1-215 | Central VA-Twitty 115 kV |  | VA | Charlotte | Active | Dominion | 31.5 | 31.5 | 18.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 2/1/2025 |  |  | N | No
PJM | AH1-216 | Smithfield-Surry 230 kV |  | VA | Isle of Wight | Active | Dominion | 132 | 132 | 79.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 2/1/2025 |  |  | N | No
PJM | AH1-217 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Active | Dominion | 57 | 57 | 34.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 2/1/2025 |  |  | N | No
PJM | AH1-220 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AH1-221 | Heritage 500 kV |  | VA | Brunswick | Active | Dominion | 75 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AH1-222 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AH1-223 | Poland Rd-Runway DP 230 kV |  | VA | Loudoun | Active | Dominion | 50 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AH1-225 | Wood Solar 69 kV |  | OH | Wayne | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AH1-226 | Clubhouse - Sapony 230 kV |  | VA | City of Emporia | Active | Dominion | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-227 | Flemming - Fremont 69 kV |  | VA | Wise | Active | AEP | 51.8 | 51.8 | 30.78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-228 | Marsh Run 230kV |  | VA | Fauquier | Active | Dominion | 615 | 18 | 18 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AH1-229 | Louisa 230kV |  | VA | Louisa | Active | Dominion | 564 | 6 | 6 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AH1-230 | Sabinsville 34.5kV |  | PA | Tioga | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-231 | Lanexa 230kV |  | VA | New Kent | Active | Dominion | 28.8 | 28.8 | 28.8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-232 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 175 | 175 | 105 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AH1-233 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 175 | 0 | 70 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AH1-234 | Wempletown 345 kV |  | IL | Winnebago | Active | ComEd | 224 | 224 | 149.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 11/21/2025 |  |  | N | No
PJM | AH1-235 | Kilgore Compressor Facility 138 kV |  | OH | Harrison | Active | AEP | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/25/2023 |  |  | N | No
PJM | AH1-236 | Bane 69 kV |  | OH | Carroll | Active | AEP | 8 | 8 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-237 | Ladysmith- Elmont 230kV |  | VA | Caroline | Active | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-238 | Ladysmith- Elmont 230kV |  | VA | Caroline | Active | Dominion | 180 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-239 | Upchurch - Zula 69 kV |  | KY | Boone | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-240 | Wayne County 161 kV |  | KY | Boone | Active | EKPC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-241 | Cobbs Creek - James River Industrial 115kV |  | VA | Cumberland | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-242 | New Bethlehem-Armstrong 138kV |  | PA | Clarion | Active | APS | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-243 | New Bethlehem – Armstrong 138kV |  | PA | Clarion | Active | APS | 60 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-244 | Yukon-Bethelboro 138kV |  | PA | Fayette | Active | APS | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-245 | Yukon-Bethelboro 138kV |  | PA | Fayette | Active | APS | 160 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-246 | Osterberg 115kV |  | PA | Bedford | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-247 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-248 | Lardin - Lake Lynn 138kV |  | PA | Fayette | Active | APS | 65 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-249 | Lardin – Lake Lynn 138kV |  | PA | Fayette | Active | APS | 145 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-251 | Todds Tavern- Spotsylvania/Goldsdale 115kV |  | VA | Spotsylvania | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-252 | Wharton - Sundial 138 kV |  | WV | Barbour | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-253 | Price 69kV |  | MD | Queen Anne's | Active | DPL | 15.5 | 15.5 | 9.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AH1-254 | Greenland Gap 500 kV II |  | WV | Barbour | Active | APS | 471.6 | 207.6 | 36.538 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AH1-255 | Greenland Gap III |  | WV | Grant | Active | APS | 711.6 | 240 | 240 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AH1-256 | Greeland Gap 500 kV IV |  | WV | Grant | Active | APS | 951.6 | 240 | 240 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 7/31/2025 |  |  | N | No
PJM | AH1-257 | Broadway - RichLine Hill Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-258 | Belford - Keansburg 34.5 kV |  | NJ | Monmouth | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-259 | Chesterfield- Centralia 115kV |  | VA | Chesterfield | Active | Dominion | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-260 | New Freedom 230 kV |  | NJ | Camden | Active | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AH1-261 | East Point - Golden Ring 115kV |  | MD | Baltimore County | Active | BGE | 135 | 135 | 135 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AH1-262 | Deep Creek 115 kV |  | VA | City of Chesapeake | Active | Dominion | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 11/30/2023 |  |  | N | No
PJM | AH1-263 | Chancellor 115 kV |  | VA | Spotsylvania | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AH1-264 | Suffolk- Sunbury 230kV |  | VA | City of Suffolk | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-265 | TBD 69kV |  | NJ | Camden | Active | AEC | 29.4 | 29.4 | 12.35 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-266 | Clubhouse – Lakeview 230 kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-267 | Papermill IND – Harmony Village 230 kV |  | VA | King and Queen | Active | Dominion | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-268 | Seward-Glory 115 kV II |  | PA | Indiana | Active | PENELEC | 100 | 0 | 36.6 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-269 | Claytor 138 kV |  | VA | Pulaski | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-270 | Hayden 345 kV |  | OH | Franklin | Active | AEP | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AH1-271 | Cashie 230 kV |  | NC | Bertie | Active | Dominion | 110 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 9/20/2024 |  |  | N | No
PJM | AH1-272 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AH1-273 | Brown - Eastwood 138 kV |  | OH | Brown | Active | DEOK | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/26/2025 |  |  | N | No
PJM | AH1-274 | Monroe – North Central 69kV |  | NJ | Gloucester | Active | AEC | 16.7 | 16.7 | 7.014 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/23/2022 |  |  | N | No
PJM | AH1-275 | Chippewa D557 8.32 kV |  |  |  | Active | ATSI | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 11/1/2023 |  |  | Y | No
PJM | AH1-277 | Indian River 230kV |  | DE | Sussex | Active | DPL | 1035 | 1035 | 279 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/31/2027 |  |  | N | No
PJM | AH1-278 | Milford - Indian River/Cool Springs 230kV |  | DE | Sussex | Active | DPL | 1035 | 1035 | 279 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/31/2027 |  |  | N | No
PJM | AH1-279 | Poolesville - Winchester 230 kV |  | VA | Isle of Wight | Active | Dominion | 104 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/12/2023 |  |  | N | No
PJM | AH1-280 | Jetersville-Ponton 115 kV |  | VA | Amelia | Active | Dominion | 106 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/12/2023 |  |  | N | No
PJM | AH1-281 | Bluegrass Parkway Tap - Woodlawn 69 kV |  | KY | Nelson | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 6/7/2024 |  |  | N | No
PJM | AH1-282 | Galion - Ohio Central 345 kV |  | OH | Morrow | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AH1-283 | Mount Storm-Pruntytown 500kV |  | MD | Garrett | Active | APS | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AH1-284 | West Willow 12 kV |  | PA | Adams | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | Y | No
PJM | AH1-285 | Sandwich 34.5 kV |  | IL | DeKalb | Active | ComEd | 86 | 86 | 51.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-286 | Bradford North 34.5kV |  | WV | Preston | Active | PENELEC | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 11/1/2023 |  |  | Y | No
PJM | AH1-287 | Houseville – Cooperstown 25 kV |  | OH | Madison | Active | APS | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 11/1/2023 |  |  | Y | No
PJM | AH1-288 | Chickahominy 230kV |  | VA | Charles City | Active | Dominion | 43.2 | 43.2 | 43.2 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-289 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 300 | 300 | 52.8 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 5/1/2028 |  |  | N | No
PJM | AH1-290 | BASF - Washburn Solar 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 9/9/2022 |  |  | N | No
PJM | AH1-291 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 185 | 185 | 111 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-292 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 200 | 0 | 44 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-293 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 120 | 0 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-294 | Mclean 345 kV |  | IL | McLean | Active | ComEd | 600 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-295 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-296 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 660 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-297 | Kewanee - E.D. Edwards 138 kV |  | IL | Stark | Active | ComEd | 200 | 200 | 26 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-298 | Twin Branch - Meridian 345 kV |  | IN | Whitley | Active | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/14/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-300 | Hacienda 138 kV |  | IN | Allen | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-301 | Milan 138 kV |  | IN | Allen | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-302 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-303 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 275 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-304 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 163 | 0 | 9.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-305 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 0 | 35.72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-306 | Mississinewa - Gaston 138 kV |  | IN | Grant | Active | AEP | 160 | 0 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-307 | Delaware-Van Buren 138 kV |  | IN | Delaware | Active | AEP | 213 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-308 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 205 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-309 | Kenzie Creek-Colby 138 kV |  | MI | Cass | Active | AEP | 150 | 0 | 27 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-310 | Colby - Valley 138 kV |  | MI | Van Buren | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-311 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 75 | 0 | 2.25 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-312 | Shilo DP – Conetoe DP 115 kV |  | NC | Edgecombe | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-313 | Moshannon-Milesburg 230 kV VII |  | PA | Centre | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-314 | East Danville 138 kV |  | VA | Pittsylvania | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-316 | Todd 25kV |  | MD | Dorchester | Active | DPL | 20 | 0 | 4.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-317 | Greene - Beatty 345 kV |  | OH | Madison | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-318 | Cole 345 kV |  | OH | Franklin | Active | AEP | 310 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-319 | East Springfield-London 138 kV II |  | OH | Clark | Active | ATSI | 234 | 54 | 54 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-320 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 348.5 | 69 | 69 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-321 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 232 | 54 | 54 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-322 | Fostoria Central - Lemoyne 345 kV |  | OH | Miami | Active | AEP | 390 | 90 | 90 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-323 | Crittenden 230 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-324 | Hopewell – Surry 230 kV |  | VA | Surry | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-325 | Kirk 138 kV |  | OH | Licking | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-326 | West Newton - Lynn 138 kV |  | OH | Hardin | Active | AEP | 110 | 0 | 19.07 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-327 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 50 | 0 | 8.44 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-328 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 348.5 | 0 | 21.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-329 | Circleville - Biers Run 138 kV |  | OH | Pickaway | Active | AEP | 130 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-330 | Tyner - McKee 69 kV |  | KY |  | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-331 | Edinboro South-Erie South 25kV |  | PA | Erie | Active | PENELEC | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AH1-332 | West Hills - Craigsville Junction 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AH1-333 | Miller - Canal 69kV |  | OH | Butler | Active | DEOK | 48 | 48 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 4/26/2024 |  |  | N | No
PJM | AH1-334 | Manchester - Whitings 34.5 kV |  | NJ | Ocean | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/9/2022 |  |  | N | No
PJM | AH1-335 | Furnace Brook Tap - Warren County Resource Recovery 34.5 kV |  | NJ | Warren | Active | JCPL | 19.25 | 19.25 | 8.085 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/9/2022 |  |  | N | No
PJM | AH1-336 | Bremo Bluff - Buckingham 230 kV |  | VA | Buckingham | Active | Dominion | 56 | 56 | 33.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-337 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2025 |  |  | N | No
PJM | AH1-338 | New Sub S2354 138kV |  | IL | Lee | Active | ComEd | 180 | 180 | 120.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 11/21/2025 |  |  | N | No
PJM | AH1-339 | West Crawford 69 kV |  | OH | Wyandot | Active | AEP | 80 | 80 | 53.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 11/21/2025 |  |  | N | No
PJM | AH1-340 | Cheat Lake-Ruthbelle 138 kV |  | WV | Preston | Active | APS | 48.89 | 48.89 | 29.33 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AH1-341 | ESS-H445 3B 138kv |  | IL | Ogle | Active | ComEd | 150 | 150 | 99 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/7/2025 |  |  | N | No
PJM | AH1-343 | Crystal Hill DP- Perth 115kV |  | VA | Halifax | Active | Dominion | 69 | 69 | 61.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2025 |  |  | N | No
PJM | AH1-345 | Remington 324 34.5 kV |  | VA | Fauquier | Active | Dominion | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/31/2023 |  |  | N | No
PJM | AH1-346 | Harrisonburg 356 34.5 kV |  | VA | Rockingham | Active | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-347 | North Pole 492 34.5 kV |  | VA | Goochland | Active | Dominion | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/31/2023 |  |  | N | No
PJM | AH1-348 | Indian Creek 34.5 kV |  | VA | Wise | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/21/2023 |  |  | N | No
PJM | AH1-349 | Powhatan 406 34.5 kV |  | VA | Powhatan | Active | Dominion | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-350 | Sunnyside – Carrolton 138 kV |  | OH | Stark | Active | AEP | 92.4 | 92.4 | 55.44 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-351 | Hillsboro-Wye Mills 138kV |  | MD | Queen Anne's | Active | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AH1-352 | Red Eye 138 kV |  | VA | Campbell | Active | AEP | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2023 |  |  | N | No
PJM | AH1-353 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 219 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-354 | Lena 138 kV |  | IL | Stephenson | Active | ComEd | 259 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-355 | Owl Trap Switching Station 115kV |  | VA | Gloucester | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-356 | Kings Creek 138kV |  | MD | Somerset | Active | DPL | 180 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2023 |  |  | N | No
PJM | AH1-357 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-358 | Pierce Brook-Lewis Run 230kV |  | PA | McKean | Active | PENELEC | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-359 | Farmers Valley-Ridgeway 115kV |  | PA | McKean | Active | PENELEC | 100 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-360 | Farmers Valley-Ridgeway 115kV |  | PA | McKean | Active | PENELEC | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-361 | Minonk 345 kV |  | IL | Woodford | Active | ComEd | 250 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AH1-362 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-363 | Reedy Creek- Kinderton 115kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-364 | Harmony Village 230kV |  | VA | Middlesex | Active | Dominion | 68 | 68 | 68 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-365 | Iron Bridge 230kV |  | VA | Chesterfield | Active | Dominion | 50.4 | 50.4 | 50.4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-366 | Whitely 138 kV |  | PA | Greene | Active | APS | 30 | 30 | 22 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2023 |  |  | N | No
PJM | AH1-367 | Franklin 138 kV |  | PA | Greene | Active | APS | 74 | 74 | 54 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2023 |  |  | N | No
PJM | AH1-367A | Franklin 138 kV II |  | PA | Greene | Active | APS | 150 | 150 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/10/2023 |  |  | N | No
PJM | AH1-368 | Cloverdale - Joshua Falls 765 kV |  | VA | Bedford | Active | AEP | 125 | 125 | 83.3333 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-370 | Mather - Stoney Point Junction 25 kV |  | PA | Greene | Active | APS | 8 | 8 | 5.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AH1-372 | Piney - Timblin 115 kV |  | PA | Armstrong | Active | APS | 16 | 16 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AH1-373 | Buckeye No. 3 - Cowell Junction 25kV |  | PA | Greene | Active | APS | 12.8 | 12.8 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/3/2024 |  |  | N | No
PJM | AH1-374 | Bremo-Cartersville 230 kV II |  | VA | Cumberland | Active | Dominion | 115 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-375 | Cobbs Creek- James River 115kV |  | VA | Fluvanna | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-376 | Ronceverte - Clenden 46 kV |  | WV | Greenbrier | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-377 | Clover- Farmville 230kV |  | VA | Prince Edward | Active | Dominion | 186 | 186 | 111.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-378 | Lunenburg- Butcher Creek 115kV |  | VA | Lunenburg | Active | Dominion | 51 | 51 | 30.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-379 | Hickman 69 kV |  | VA | Pulaski | Active | AEP | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-380 | Mt Olive - Kenny 69kV |  | MD | Worcester | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-381 | Lone Gum - Rockcastle 138 kV |  | VA | Bedford | Active | AEP | 99.5 | 99.5 | 59.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AH1-382 | Van Arsdell 69 kV |  | KY | Mercer | Active | EKPC | 20 | 20 | 17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/10/2025 |  |  | N | No
PJM | AH1-383 | Celanese 138 kV |  | VA | Giles | Active | AEP | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-384 | Indian River 230kV |  | DE | Sussex | Active | DPL | 1410 | 1410 | 380.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/31/2027 |  |  | N | No
PJM | AH1-385 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 109 | 109 | 65.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-386 | Kerr Dam - Chase City 115 kV |  | VA | Mecklenburg | Active | Dominion | 130 | 130 | 78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-387 | Meadowbrook-Mount Storm 500kV |  | WV | Hampshire | Active | APS | 150 | 150 | 22.5 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 1/9/2025 |  |  | N | No
PJM | AH1-388 | Chase City-Herbert 115 kV |  | VA | Mecklenburg | Active | Dominion | 115 | 115 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AH1-389 | Utica East Ohio Midstream 138 kV |  | OH | Warren | Active | ATSI | 19.95 | 19.95 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-390 | TBD 69 kV |  | PA | Northumberland | Active | PPL | 19.9 | 19.9 | 14.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/31/2023 |  |  | N | No
PJM | AH1-391 | Maple 138 kV |  | IN | St. Joseph | Active | AEP | 100 | 100 | 64.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/16/2025 |  |  | N | No
PJM | AH1-392 | Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 90 | 90 | 57.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/16/2025 |  |  | N | No
PJM | AH1-395 | Mainesburg 115 kV II |  | PA | Tioga | Active | PENELEC | 6 | 6 | 2.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-396 | Gary 24.94 kV |  | VA | Lunenburg | Active | Dominion | 12 | 12 | 7.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/2/2023 |  |  | N | No
PJM | AH1-397 | Shacklesfords 34.5 kV |  | VA | King and Queen | Active | Dominion | 19.818 | 19.818 | 13.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/2/2023 |  |  | N | No
PJM | AH1-398 | Oak Grove 22.9 kV |  | VA | Westmoreland | Active | Dominion | 18 | 18 | 11.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/22/2021 | [5 empty] | 10/2/2023 |  |  | N | No
PJM | AH1-399 | North Doswell 12.5 kV |  | VA | Hanover | Active | Dominion | 12 | 12 | 7.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/22/2021 | [5 empty] | 10/2/2023 |  |  | N | No
PJM | AH1-400 | Jones Creek - Aladdin 138 kV |  | IN | Madison | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-401 | Jones Creek - Aliddin 138 kV |  | IN | Madison | Active | AEP | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-402 | Shelocta 115kV |  | PA | Indiana | Active | PENELEC | 85 | 85 | 55.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-403 | Shelocta 115kV |  | PA | Indiana | Active | PENELEC | 85 | 0 | 29.1 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-404 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Active | OVEC | 210 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-405 | Exchange Tap I 69 kV |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/18/2024 |  |  | N | No
PJM | AH1-406 | Exchange Tap 69 kV II |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/18/2024 |  |  | N | No
PJM | AH1-407 | Exchange Tap 69 kV III |  | PA | Northumberland | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/18/2024 |  |  | N | No
PJM | AH1-408 | Freeman DP – Lawrenceville 115 kV |  | VA | Brunswick | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-409 | Brodhead - Maretburg 69 kV |  | KY |  | Active | EKPC | 58 | 58 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-410 | Union City Tap – JK Smith 138 kV |  | KY | Madison | Active | EKPC | 68 | 68 | 40.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-411 | Phillipsburg - Ingersol Rand 34.5 kV |  | NJ | Warren | Active | JCPL | 5.75 | 5.75 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/8/2022 |  |  | N | No
PJM | AH1-412 | Franklintown 34.5 kV |  | WV | Jefferson | Active | APS | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-413 | Wayne Trace 138 kV |  | IN | Allen | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-415 | Bremo Bluff 34.5kV |  | VA | Fluvanna | Active | Dominion | 15.975 | 15.975 | 8.6265 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/11/2023 |  |  | N | No
PJM | AH1-416 | Bellefontaine 69 kV |  | OH | Logan | Active | Dayton | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-417 | Castalia 69 kV |  | OH | Erie | Active | ATSI | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-418 | Elkhorn City - Second Fork 69 kV |  | KY | Pike | Active | AEP | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-419 | Thompson 34.5 kV II |  | PA | Susquehanna | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-420 | Fentress 34.5kV |  | VA | City of Chesapeake | Active | Dominion | 20 | 20 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/26/2023 |  |  | N | No
PJM | AH1-421 | West Mingo 69 kV |  | OH | Champaign | Active | Dayton | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-422 | West Mingo 69 kV |  | OH | Champaign | Active | Dayton | 60 | 20 | 18.85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-423 | West Mingo 69 kV |  | OH | Champaign | Active | Dayton | 80 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-424 | Sandborn 34.5 kV |  | OH | Ashtabula | Active | ATSI | 19.2 | 19.2 | 11.52 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-425 | Lemoyne 138kV |  | OH | Ottawa | Active | ATSI | 32 | 32 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH1-426 | Carbondale 138 kV |  | WV | Kanawha | Active | AEP | 200 | 200 | 184.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-426A | Jones Branch 138 kV |  | WV | Nicholas | Active | APS | 100 | 100 | 92.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-427 | Tommy Gooch - Garrard COunty 69 kV |  | KY |  | Active | EKPC | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-428 | Tommy Gooch - Garrard County 69 kV |  | KY | Boone | Active | EKPC | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-429 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-430 | Flemingsburg - Spurlock 138 kV |  | KY | Fleming | Active | EKPC | 90 | 0 | 36 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-431 | Pennville 138 kV |  | IN | Jay | Active | AEP | 125 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AH1-432 | Randolph - Hodgin 138 kV |  | IN | Randolph | Active | AEP | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AH1-433 | Kingsland 69 kV |  | IN | Wells | Active | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AH1-434 | Carolina- Earleys 115kV |  | NC | Northhampton | Active | Dominion | 75 | 75 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-435 | Carolina- Earleys 115kV |  | NC | Northhampton | Active | Dominion | 75 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-436 | Mackeys- Creswell 115kV |  | NC | Washington | Active | Dominion | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AH1-437 | Remington- Gordonsville 230kV |  | VA | Culpeper | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-438 | Remington- Gordonsville 230kV |  | VA | Culpeper | Active | Dominion | 150 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-439 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 85 | 85 | 51 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-440 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 85 | 0 | 34 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AH1-441 | Cunningham - Elmont 500 kV III |  | VA | Fluvanna | Active | Dominion | 149 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-442 | Cunningham - Elmont 500 kV IV |  | VA | Fluvanna | Active | Dominion | 149 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-443 | Kidds Store - Fork Union 115 kV II |  | VA | Fluvanna | Active | Dominion | 0 | 0 | 15 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH1-445 | Belleville 46 kV |  | PA | Mifflin | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2023 |  |  | N | No
PJM | AH1-446 | Sanders DP - Westmoreland 230 kV |  | VA | Westmoreland | Active | Dominion | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AH1-447 | Axton – Danville #2 138 kV |  | VA | Pittsylvania | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/2/2024 |  |  | N | No
PJM | AH1-449 | Muskingum River - Sporn 345 kV |  | OH | Washington | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AH1-450 | Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-451 | Hopkins 138 kV |  | WV |  | Active | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AH1-452 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 8.35 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AH1-453 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2028 |  |  | N | No
PJM | AH1-454 | Pinewood- St Johns 115kV |  | VA | Caroline | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-456 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-457 | Moran DP – Flatcreek 115 kV |  | VA | Spotsylvania | Active | Dominion | 130 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-458 | Hampshire - Ridgeley 138 kV 1 |  | WV | Hampshire | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-459 | Hampshire - Ridgeley 138 kV 2 |  | WV | Hampshire | Active | APS | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AH1-460 | Hooversville - Scalp Level 115 kV |  | PA | Somerset | Active | PENELEC | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-461 | Buckhorn 138 kV |  | VA | Tazewell | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-462 | Rachel Hill 115 kV |  | PA | Cambria | Active | PENELEC | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-463 | Owingsville - Preston 69 kV |  | KY | Bath | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-465 | Carson – Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 350 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-466 | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 600 | 600 | 360 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-467 | Baker - Broadford 765 kV |  | KY | Boone | Active | AEP | 900 | 300 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-469 | Derry Tap-Derry Bus 69 kV III |  | PA | Montour | Active | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-470 | Derry Tap- Derry Bus 69 kV IV |  | PA | Northumberland | Active | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-471 | Derry Tap- Derry Bus 69 kV VI |  | PA | Snyder | Active | PPL | 27.5 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-472 | Derry Tap- Derry Bus 69 kV VII |  | PA | Columbia | Active | PPL | 91 | 56 | 56 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-474 | Edinboro South-Venango Junction 115 kV III |  | PA | Crawford | Active | PENELEC | 203.5 | 87 | 87 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-475 | Edinboro-Cambridge Springs 34.5 kV II |  | PA | Crawford | Active | PENELEC | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-476 | Hunterstown-Texas Eastern Tap 115 kV II |  | PA | Adams | Active | ME | 170.5 | 73 | 73 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 9/23/2024 |  |  | N | No
PJM | AH1-477 | Greentown 138 kV |  | IN | Howard | Active | AEP | 112 | 112 | 112 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-478 | Columbia-West Bloomsburg 69 kV II |  | PA | Columbia | Active | PPL | 60 | 40 | 40 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-479 | New Carlisle 138 kV |  | IN | St. Joseph | Active | AEP | 192 | 82 | 82 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-480 | Haviland – Cavett Switch 69 kV |  | OH | Van Wert | Active | AEP | 132 | 57 | 57 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-481 | Reynolds - Meadow Lake #1 345 kV |  | IN | White | Active | AEP | 196 | 84 | 84 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AH1-482 | Olive - Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 455 | 195 | 195 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-483 | Honda Marysville Tap 69 kV |  | OH | Union | Active | Dayton | 142 | 42 | 42 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/23/2024 |  |  | N | No
PJM | AH1-484 | Madison - Tanners Creek 138 kV |  | IN | Henry | Active | AEP | 267.5 | 115 | 115 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 9/24/2023 |  |  | N | No
PJM | AH1-486 | Maysville 69 kV 1 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-487 | Maysville 34.5 kV 2 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-488 | Maysville 34.5 kV 3 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-489 | Maysville 34.5 kV 4 |  | PA | Mercer | Active | ATSI | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-490 | Venango Junction - Cambridge Springs 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-491 | Union City 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-492 | Bernville 34.5 kV 1 |  | PA | Berks | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-493 | Bernville 34.5 kV 2 |  | PA | Berks | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-502 | Dequine - Eugene 345 kV |  | IN | Warren | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2028 |  |  | N | No
PJM | AH1-503 | Kings Fork – Chuckatuck 230 kV |  | VA | City of Suffolk | Active | Dominion | 150 | 150 | 127.5 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2025 |  |  | N | No
PJM | AH1-506 | Oceanview Wind 3 230 kV |  | NJ | Monmouth | Active | JCPL | 2056 | 730 | 300 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/30/2028 |  |  | N | No
PJM | AH1-507 | Oceanview Wind 4 230 kV |  | NJ | Monmouth | Active | JCPL | 2786 | 730 | 300 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/30/2028 |  |  | N | No
PJM | AH1-514 | Philipsburg - Emeigh 12.47 kV-1 |  | PA | Clearfield | Active | PENELEC | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH1-515 | Philipsburg - Emeigh 12.47 kV-2 |  | PA | Clearfield | Active | PENELEC | 5 | 5 | 2.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH1-516 | Springfield Road - Springfield Road 69 kV |  | OH | Butler | Active | DEOK | 70 | 70 | 44.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AH1-518 | Pulaski Sub-New Wilmington 69kV |  | PA | Lawrence | Active | ATSI | 19 | 19 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AH1-520 | Blue Jacket-Kirby 138 kV V |  | OH | Union | Active | ATSI | 120 | 120 | 79.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/15/2024 |  |  | N | No
PJM | AH1-521 | Blue Jacket-Kirby 138 kV VI |  | OH | Union | Active | ATSI | 100 | 100 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/15/2024 |  |  | N | No
PJM | AH1-522 | Timber Switch 138 kV |  | OH | Paulding | Active | AEP | 47 | 47 | 28.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-523 | Heidelberg 69 kV |  | PA | Lebanon | Active | PPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 7/30/2024 |  |  | N | No
PJM | AH1-526 | South Canton - Sammis 345 kV |  | OH | Carroll | Active | ATSI | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AH1-527 | Chase City- Herbert Plant Substation 115kV |  | VA | Mecklenburg | Active | Dominion | 149 | 149 | 89.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/30/2025 |  |  | N | No
PJM | AH1-528 | Rawlings 500kV |  | VA | Brunswick | Active | Dominion | 300.8 | 300.8 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/30/2025 |  |  | N | No
PJM | AH1-529 | Renaker - Avon 138 kV |  | KY | Bourbon | Active | EKPC | 89 | 24 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-530 | Fairfield – Reily 69 kV |  | OH | Butler | Active | DEOK | 28 | 28 | 16.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-531 | Salyers Rd 34.5 kV |  | OH | Pike | Active | AEP | 21 | 21 | 12.6 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-532 | Marion County - Marion Co. Industrial 161 kV |  | KY | Marion | Active | EKPC | 37.8 | 37.8 | 22.68 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-533 | Sunbury-Juniata II |  | PA | Perry | Active | PPL | 185.2 | 96.2 | 57.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-534 | Sullivan Gardens - Walters 138 kV |  | TN | Greene | Active | AEP | 22.7 | 22.7 | 13.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-535 | Nagel - Cane River 230 kV |  | TN | Hawkins | Active | AEP | 133.6 | 133.6 | 80.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-536 | Church-Oil City 138kV |  | MD | Queen Anne's | Active | DPL | 42.7 | 42.7 | 25.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-537 | Pierce - DOE X-530 345 kV |  | OH | Highland | Active | OVEC | 178.5 | 178.5 | 107.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-538 | East Lima - Haviland 138 kV |  | OH | Van Wert | Active | AEP | 241.5 | 241.5 | 144.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-539 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 129.4 | 129.4 | 77.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-540 | Byron to Wayne 345 kV |  | IL | Ogle | Active | ComEd | 165 | 165 | 99 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-541 | Chestnut 345 kV |  | IL | DeWitt | Active | ComEd | 92.4 | 92.4 | 55.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-542 | Crissinger-Delaware Business Park 138kV |  | OH | Marion | Active | ATSI | 132.2 | 132.2 | 79.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-543 | Powerton - Katydid Road 345 kV |  | IL | Livingston | Active | ComEd | 157.4 | 157.4 | 94.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-544 | La Salle 345 kV |  | IL | Lasalle | Active | ComEd | 67.7 | 67.7 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-545 | Wylie Ridge-Tidd 345kV |  | PA | Washington | Active | APS | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH1-546 | Bremo - Buckingham 230 kV |  | VA | Buckingham | Active | Dominion | 79.8 | 79.8 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 2/1/2025 |  |  | N | No
PJM | AH1-547 | Reynolds - Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 0 | 74 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/31/2022 |  |  | N | No
PJM | AH1-548 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-549 | Allen - RP Mone 345 kV |  | IN | Allen | Active | AEP | 180 | 180 | 108 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-550 | Hazelton - Kirk 138 kV |  | OH | Licking | Active | AEP | 110 | 110 | 66 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-552 | Chalk Point 230kV |  | MD | Prince George's | Active | PEPCO | 809.5 | 809.5 | 670.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-553 | Broadview -Tangy 138 kV II |  | OH | Madison | Active | ATSI | 66 | 66 | 39.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-554 | Lick 138 kV |  | OH | Jackson | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-556 | Larrabee 230 kV III |  | NJ | Monmouth | Active | JCPL | 805.2 | 360 | 63.36 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/31/2029 |  |  | N | No
PJM | AH1-557 | Larrabee 230 kV IV |  | NJ | Monmouth | Active | JCPL | 1300 | 1300 | 228.8 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/31/2029 |  |  | N | No
PJM | AH1-558 | Four Rivers 230kV |  | VA | Hanover | Active | Dominion | 996 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-560 | University Park 138 kV |  | IL | Will | Active | ComEd | 573 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-561 | Ironwood 230kV |  | PA | Lebanon | Active | ME | 1075 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-562 | Springdale 138kV |  | PA | Allegheny | Active | APS | 356 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-563 | Aurora E.C. 138kV |  | IL |  | Active | ComEd | 1306 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-564 | Rockford II 138 kV |  | IL | Winnebago | Active | ComEd | 430 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-565 | Lemoyne 345kV |  | OH | Wood | Active | ATSI | 950 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-566 | South Bend 500kV |  | PA | Armstrong | Active | APS | 1190 | 400 | 400 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-567 | University Park 138 kV |  | IL | Will | Active | ComEd | 578 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-568 | Keen Mountain 138 kV |  | VA | Buchanan | Active | AEP | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH1-569 | Broadview - Tangy 138 kV III |  | OH | Union | Active | ATSI | 49.99 | 49.99 | 31.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-570 | Millersburg 69 kV |  | KY |  | Active | EKPC | 25 | 25 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-571 | Millersburg 69 kV |  | KY |  | Active | EKPC | 20 | 20 | 12.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-572 | South Morral 69 kV |  | OH | Marion | Active | AEP | 30 | 30 | 19.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-573 | South Morral 69 kV |  | OH | Marion | Active | AEP | 19.99 | 19.99 | 12.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH1-574 | Harrington 69kV |  | DE | Kent | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/25/2024 |  |  | N | No
PJM | AH1-575 | Harrington 69kV |  | DE | Kent | Active | DPL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/25/2024 |  |  | N | No
PJM | AH1-576 | South Harrington 69kV |  | DE | Kent | Active | DPL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/25/2024 |  |  | N | No
PJM | AH1-577 | Tigers 69 kV |  | OH | Wayne | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/15/2028 |  |  | N | No
PJM | AH1-578 | Tigers 69 kV |  | OH | Wayne | Active | AEP | 28 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/15/2028 |  |  | N | No
PJM | AH1-579 | Marysville – Hyatt 345 kV |  | OH | Union | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2028 |  |  | N | No
PJM | AH1-580 | Nottingham Switch 138 kV |  | OH | Harrison | Active | AEP | 400 | 200 | 134 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AH1-582 | Marysville - Flatlick 765 kV |  | OH | Madison | Active | AEP | 800 | 0 | 146.3 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AH1-583 | Marysville - Flatlick 765 kV |  | OH | Madison | Active | AEP | 800 | 0 | 146.3 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AH1-584 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-585 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-586 | Nelson-Indian River 138kV |  | DE | Sussex | Active | DPL | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-587 | Farmers Valley – Ridgeway 115 kV |  | PA | McKean | Active | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-588 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 240 | 240 | 144 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-589 | Lewis Run - Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 410 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-590 | Cherry Ridge 66 kV |  | WV | Grant | Active | APS | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-591 | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 100 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-592 | Cherry Ridge 66kV |  | WV | Grant | Active | APS | 145 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-593 | Hazelton 138 |  | WV | Preston | Active | APS | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-594 | Hazelton 138kV |  | WV | Preston | Active | APS | 97 | 32 | 32 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH1-595 | Fowler Ridge 345 kV |  | IN | Benton | Active | AEP | 150 | 150 | 96.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/3/2025 |  |  | N | No
PJM | AH1-596 | Fowler Ridge 345 kV |  | IN | Benton | Active | AEP | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/3/2025 |  |  | N | No
PJM | AH1-597 | LM Troy 138 kV |  | OH | Ashland | Active | ATSI | 110 | 110 | 70.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/3/2025 |  |  | N | No
PJM | AH1-598 | LM Troy 138 kV |  | OH | Ashland | Active | ATSI | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/3/2025 |  |  | N | No
PJM | AH1-609 | Milliron-Brookside 138kV |  | OH | Richland | Active | ATSI | 168.31 | 168.31 | 100.986 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 4/30/2025 |  |  | N | No
PJM | AH1-614 | Burns 69 kV |  | OH | Clermont | Active | DEOK | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-615 | Pine Creek 138 kV |  | PA | Allegheny | Active | DL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-616 | Chicago Heights 138 kV |  | IL | Cook | Active | ComEd | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AH1-617 | Beaver Creek 138 kV |  | KY |  | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AH1-618 | Beaver Creek 138 kV |  | KY |  | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AH1-619 | Beaver Creek 138 kV |  | KY |  | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AH1-620 | Carville 138kV |  | MD | Queen Anne's | Active | DPL | 76 | 76 | 45.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-621 | Steele-Milford 230kV |  | MD | Allegany | Active | DPL | 120 | 120 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-622 | Five Fork 115kV |  | PA | York | Active | PECO | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-623 | South Anna - Desper 230 kV |  | VA | Louisa | Active | Dominion | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-624 | Mainesburg-Homer City 345kV |  | PA | Clearfield | Active | PENELEC | 230 | 230 | 138 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-625 | Cowen 138kV |  | WV | Webster | Active | APS | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH1-626 | Ladysmith 230 kV |  | VA | Caroline | Active | Dominion | 62.5 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/21/2025 |  |  | N | No
PJM | AH1-627 | Ladysmith 230 kV II |  | VA | Caroline | Active | Dominion | 125 | 62.5 | 62.5 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 3/21/2025 |  |  | N | No
PJM | AH1-630 | Penns Tap-Richfield Tie 69 kV V |  | PA | Snyder | Active | PPL | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/11/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-631 | Edinboro South 34.5 kV III |  | PA | Crawford | Active | PENELEC | 35 | 15 | 15 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-632 | Mercersburg-Milnor 34.5 kV III |  | PA | Franklin | Active | APS | 27 | 12 | 12 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2021 | [5 empty] | 9/25/2023 |  |  | N | No
PJM | AH1-633 | Powerton to Katydid 345 kV |  | IL | Livingston | Active | ComEd | 288 | 288 | 172.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/13/2021 | [5 empty] | 9/26/2024 |  |  | N | No
PJM | AH1-634 | Indian River 230kV |  | DE | Sussex | Active | DPL | 323.1 | 68 | 17.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/13/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-637 | Oak Grove 34.5 kV |  | VA | Westmoreland | Active | Dominion | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/13/2021 | [5 empty] | 12/15/2022 |  |  | N | No
PJM | AH1-639 | Lordstown - Mansfield 345 kV |  | OH | Mahoning | Active | ATSI | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/13/2021 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AH1-640 | Gladys DP - Stonemill 69 kV |  | VA | Campbell | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/14/2021 | [5 empty] | 12/3/2025 |  |  | N | No
PJM | AH1-641 | Churchtown - Upper Pittsgrove 138kV |  | NJ | Salem | Active | AEC | 65 | 15 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/14/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-644 | Spicewood 138 kV |  | KY |  | Active | AEP | 100 | 100 | 65 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/15/2021 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AH1-646 | Lake Lynn – Gerards Fort 25 kV |  | PA | Fayette | Active | APS | 19.9 | 19.9 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/16/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-647 | Greensboro 25 kV |  | PA | Greene | Active | APS | 19.9 | 19.9 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/16/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH1-648 | Grays Ferry 230kV |  | PA | Philadelphia | Active | PECO | 168 | 5 | 5 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 9/17/2021 | [5 empty] | 6/1/2022 |  |  | N | No
PJM | AH1-649 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-650 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-651 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/24/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-652 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-653 | Greentown 138 kV |  | IN | Howard | Active | AEP | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-654 | Kincaid 345 kV |  | IL | Christian | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-655 | SE Canton 138 kV |  | OH | Stark | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/24/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-657 | Nelson 345 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-658 | R. P. Mone 345 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH1-659 | Cordova 345 kV |  | IL | Lee | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/23/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH1-661 | Philo – Cannelville Switch 138 kV |  | OH | Muskingum | Active | AEP | 15.32 | 15.32 | 15.32 |  | Capacity | Generation Interconnection | Other |  |  |  |  | In Progress | [12 empty] | 9/29/2021 | [5 empty] | 7/1/2023 |  |  | N | No
PJM | AH1-663 | River EC 138 kV |  | IL | Cook | Active | ComEd | 57.78 | 57.78 | 57.78 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/30/2021 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AH2-001 | Rattlesnake Hill Waste Heat Recovery |  | PA | Susquehanna | Active | PENELEC | 3.6 | 3.6 | 2.9 |  | Capacity | Generation Interconnection | Other |  |  |  |  | In Progress | [12 empty] | 10/1/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH2-002 | Temple Hill - Roseville 69 kV |  | KY | Barren | Active | EKPC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/2/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-006 | Harrison - Good Hope 138 kV |  | OH | Pickaway | Active | AEP | 14.234 | 14.234 | 14.234 |  | Capacity | Generation Interconnection | Other |  |  |  |  | In Progress | [12 empty] | 10/4/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AH2-007 | Texas Eastern - Jeffersonville 69 kV |  | OH | Fayette | Active | Dayton | 10.12 | 10.12 | 10.12 |  | Capacity | Generation Interconnection | Other |  |  |  |  | In Progress | [12 empty] | 10/4/2021 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AH2-009 | Galion 138 kV V |  | OH | Morrow | Active | ATSI | 244 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/8/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-010 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 1455 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/7/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-013 | Cartersville 34.5 kV |  | VA | Cumberland | Active | Dominion | 15.996 | 15.996 | 15.996 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 10/12/2021 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH2-014 | Crane Solar 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/15/2021 | [5 empty] | 12/16/2024 |  |  | N | No
PJM | AH2-015 | Nelson 138 kV |  | IL | Lee | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/20/2021 | [5 empty] | 3/24/2025 |  |  | N | No
PJM | AH2-021 | Summer Shade - Barren County 161 kV |  | KY | Barren | Active | EKPC | 150 | 150 | 105 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 10/27/2021 | [5 empty] | 11/13/2026 |  |  | N | No
PJM | AH2-023 | McDowell 12.47 kV |  | PA | Mercer | Active | ATSI | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/29/2021 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH2-024 | Kodiak Solar 13.2 kV |  | PA | Jefferson | Active | PENELEC | 3 | 3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 10/30/2021 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AH2-025 | Eugene - Dequine 345 kV |  | IN | Fountain | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 10/29/2021 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AH2-028 | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 44 | 44 | 44 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 11/2/2021 | [5 empty] | 10/28/2025 |  |  | N | No
PJM | AH2-028A | Watertower - Kingston 69 kV |  | OH | Pickaway | Active | AEP | 64 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/2/2021 | [5 empty] | 10/28/2025 |  |  | N | No
PJM | AH2-030 | Feagan's Mill 138 kV |  | WV | Jefferson | Active | APS | 90 | 90 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/3/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-031 | Feagan's Mill 138 kV II |  | WV | Jefferson | Active | APS | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/3/2021 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-032 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/9/2021 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-033 | Possum Point 115kV |  | VA | Prince William | Active | Dominion | 60 | 60 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/9/2021 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-034 | Possum Point 230kV |  | VA | Prince William | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/9/2021 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AH2-035 | Possum Point 500kV |  | VA | Prince William | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/9/2021 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AH2-036 | Young 12.47 |  | PA | Bradford | Active | PENELEC | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/11/2021 | [5 empty] | 11/1/2023 |  |  | Y | No
PJM | AH2-037 | Booth 12.47 |  | PA | Fulton | Active | APS | 4.99 | 4.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/11/2021 | [5 empty] | 11/1/2023 |  |  | Y | No
PJM | AH2-038 | Weirton - Arroyo 25 kV |  | WV | Hancock | Active | APS | 10.75 | 10.75 | 5.4395 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/13/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-039 | Chesapeake - Paw Paw 23 kV |  | WV | Marion | Active | APS | 5.5 | 5.5 | 2.728 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/13/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-040 | William - Blackwater 69 kV |  | WV | Tucker | Active | APS | 11.5 | 11.5 | 5.7615 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/13/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-041 | Osage - Collins Ferry 23 kV |  | WV | Monongalia | Active | APS | 18.89 | 18.89 | 9.48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/13/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH2-042 | Marlowe - North Martinsburg 34.5 kV |  | WV | Berkeley | Active | APS | 5.75 | 5.75 | 3.6858 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/13/2021 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-043 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 200 | 200 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 11/19/2021 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-044 | Clearfield 12.5 kV |  | PA | Clearfield | Active | APS | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/30/2021 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH2-045 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 12/16/2021 | [5 empty] | 12/15/2025 |  |  | N | No
PJM | AH2-046 | Kerr Dam - Buggs Island 115kV |  | VA | Mecklenburg | Active | Dominion | 60 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/16/2021 | [5 empty] | 12/15/2025 |  |  | N | No
PJM | AH2-048 | Bayview 69kV |  | VA | Northampton | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/20/2021 | [5 empty] | 6/2/2025 |  |  | N | No
PJM | AH2-049 | Crisfield 69kV |  | MD | Somerset | Active | DPL | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/20/2021 | [5 empty] | 6/2/2025 |  |  | N | No
PJM | AH2-050 | Tasley 69kV |  | VA | Accomack | Active | ODEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/19/2021 | [5 empty] | 6/2/2025 |  |  | N | No
PJM | AH2-051 | Edge Moore 230kV |  | DE | New Castle | Active | DPL | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/20/2021 | [5 empty] | 6/2/2025 |  |  | N | No
PJM | AH2-052 | New Hope 12.47 kV |  | MD | Allegany | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/21/2021 | [5 empty] | 12/2/2022 |  |  | Y | No
PJM | AH2-053 | Mardela Springs 12.47 kV |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/22/2021 | [5 empty] | 12/2/2022 |  |  | Y | No
PJM | AH2-054 | Edgewood 12.47 kV I |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/21/2021 | [5 empty] | 12/2/2022 |  |  | Y | No
PJM | AH2-055 | TBD 69kV |  | MD | Unknown | Active | DPL | 0.99 | 0.99 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/22/2021 | [5 empty] | 2/15/2022 |  |  | Y | No
PJM | AH2-056 | Chesterfield 230 kV II |  | VA | Chesterfield | Active | Dominion | 60 | 0 | 36 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/24/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH2-057 | Scottsville - CVEC Delivery Point 46 kV |  | VA | Buckingham | Active | AEP | 74.9 | 29.9 | 17.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/23/2021 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH2-058 | Possum Point 115 kV |  | VA | Prince William | Active | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/24/2021 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AH2-059 | Possum Point 115 kV II |  | VA | Prince William | Active | Dominion | 30 | 30 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/24/2021 | [5 empty] | 12/1/2027 |  |  | N | No
PJM | AH2-060 | Possum Point 230 kV |  | VA | Prince William | Active | Dominion | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/24/2021 | [5 empty] | 12/1/2027 |  |  | N | No
PJM | AH2-061 | Possum Point 230 kV II |  | VA | Prince William | Active | Dominion | 55 | 55 | 55 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/23/2021 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AH2-062 | TBD 34kV |  | PA | Chester | Active | PECO | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/31/2021 | [5 empty] | 5/1/2023 |  |  | N | No
PJM | AH2-063 | North Ramsey 23 kV |  | PA | Beaver | Active | DL | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/30/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH2-064 | South Ramsey 23 kV |  | PA | Beaver | Active | DL | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/31/2021 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH2-065 | TBD 69kV |  | MD | Prince George's | Active | DPL | 1.992 | 1.992 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/31/2021 | [5 empty] | 12/1/2022 |  |  | Y | No
PJM | AH2-066 | Jefferson 12.5 kV |  | PA | Jefferson | Active | PENELEC | 5 | 5 | 3.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/4/2022 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AH2-068 | Pemberville - West End Fostoria 69 kV |  | OH | Wood | Active | AEP | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/13/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-069 | JAckson Ferry - Progress Park 138 kV |  | VA | Wythe | Active | AEP | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/13/2022 | [5 empty] | 5/30/2025 |  |  | N | No
PJM | AH2-070 | Edgewood 12.47 kV II |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/19/2022 | [5 empty] | 1/27/2023 |  |  | Y | No
PJM | AH2-071 | Edgewood 12.47 kV III |  | MD | Wicomico | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/19/2022 | [5 empty] | 1/27/2023 |  |  | Y | No
PJM | AH2-072 | Damascus 69 kV |  | VA | Washington | Active | AEP | 62.1 | 62.1 | 62.1 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/21/2022 | [5 empty] | 1/1/2025 |  |  | N | No
PJM | AH2-073 | Ashtabula County PV Project 2 |  | OH | Ashtabula | Active | ATSI | 10 | 10 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/22/2022 | [5 empty] | 9/14/2024 |  |  | N | No
PJM | AH2-074 | Ashtabula County PV Project 1 |  | OH | Ashtabula | Active | ATSI | 10 | 10 | 2.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/22/2022 | [5 empty] | 9/14/2024 |  |  | N | No
PJM | AH2-075 | Hampton VA 2 |  | VA | City of Hampton | Active | Dominion | 29.12 | 29.12 | 29.12 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/21/2022 | [5 empty] | 7/1/2024 |  |  | N | No
PJM | AH2-076 | Bonneyman - Softshell 138 kV |  | KY | Perry | Active | AEP | 52.5 | 52.5 | 48.17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/26/2022 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AH2-077 | Indian River 230 kV |  | DE | Sussex | Active | DPL | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/27/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AH2-078 | Dryburg - Chase City 230 kV |  | VA | Charlotte | Active | Dominion | 99.67 | 99.67 | 59.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/27/2022 | [5 empty] | 1/3/2025 |  |  | N | No
PJM | AH2-080 | Brunswick - Gasburg 69 kV |  | VA | Brunswick | Active | Dominion | 52.65 | 52.65 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/28/2022 | [5 empty] | 1/3/2025 |  |  | N | No
PJM | AH2-081 | Bentley Farms 69 kV |  | OH | Fayette | Active | Dayton | 35.5 | 35.5 | 21.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/27/2022 | [5 empty] | 9/19/2025 |  |  | N | No
PJM | AH2-082 | New Holland - Washington Courthouse 69 kV |  | OH | Fayette | Active | Dayton | 33.25 | 33.25 | 19.95 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/27/2022 | [5 empty] | 1/3/2025 |  |  | N | No
PJM | AH2-083 | Correctional |  | VA | Caroline | Active | Dominion | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/27/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AH2-084 | Sowego |  | VA | Fauquier | Active | Dominion | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/28/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AH2-085 | Byron-Wayne 345 kV |  | IL | DeKalb | Active | ComEd | 145.335 | 145.335 | 87.201 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/28/2022 | [5 empty] | 11/11/2026 |  |  | N | No
PJM | AH2-086 | Byron – Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-087 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-088 | Byron - Wayne 345 kV |  | IL | Ogle | Active | ComEd | 600 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-089 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-090 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-091 | Nelson-Electric Junction 345kV |  | IL | Lee | Active | ComEd | 1200 | 0 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-093 | Jasper 69 kV |  | OH | Greene | Active | Dayton | 32 | 32 | 32 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-094 | Lakeville 12 kV II |  | PA | Wayne | Active | PPL | 4.95 | 4.95 | 2.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 5/5/2023 |  |  | N | No
PJM | AH2-095 | Crawford 13.8 kV |  | PA | Crawford | Active | PENELEC | 3.3 | 3.3 | 2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 7/13/2022 |  |  | N | No
PJM | AH2-096 | West Cambridge - Airey 69 kV |  | MD | Dorchester | Active | DPL | 19.5 | 19.5 | 8.19 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/1/2022 | [5 empty] | 5/1/2023 |  |  | N | No
PJM | AH2-100 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-101 | Briery Substation 29.4kV |  | VA | Prince Edward | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-102 | Blaine - Roanoke 138 kV |  | VA | Franklin | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 1/31/2022 | [5 empty] | 5/4/2026 |  |  | N | No
PJM | AH2-103 | Gans - South Union 138 kV |  | PA | Fayette | Active | APS | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2022 | [5 empty] | 5/4/2026 |  |  | N | No
PJM | AH2-104 | Willis Mts- Farmville 115kV |  | VA | Cumberland | Active | Dominion | 72 | 72 | 39.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/4/2022 | [5 empty] | 11/1/2024 |  |  | N | No
PJM | AH2-105 | Merck 34.5 kV |  | VA | Rockingham | Active | Dominion | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/4/2022 | [5 empty] | 1/1/2024 |  |  | N | No
PJM | AH2-106 | Wellsville 345 kV |  | OH | Columbiana | Active | ATSI | 1210 | 58 | 69 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 2/4/2022 | [5 empty] | 2/28/2022 |  |  | N | No
PJM | AH2-107 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 69 | 69 | 69 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/12/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-109 | TBD 12.47kV |  | NJ | Unknown | Active | AEC | 1.5 | 1.5 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/16/2022 | [5 empty] | 12/1/2022 |  |  | Y | No
PJM | AH2-111 | Hannibal 138 kV |  | OH | Monroe | Active | AEP | 505 | 20 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 2/19/2022 | [5 empty] | 6/30/2022 |  |  | N | No
PJM | AH2-112 | Olive - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 250 | 250 | 170 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/22/2022 | [5 empty] | 2/27/2026 |  |  | N | No
PJM | AH2-113 | Dresden – Pontiac Midpoint 345kV |  | IL | Livingston | Active | ComEd | 250 | 250 | 170 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/22/2022 | [5 empty] | 2/27/2026 |  |  | N | No
PJM | AH2-115 | Mansfield - Mainesburg 115 kV |  | PA | Tioga | Active | PENELEC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AH2-116 | Garman - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AH2-117 | Dorton - Henry Clay 46 kV |  | KY | Pike | Active | AEP | 30 | 30 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-119 | Morgan Street - Titusville 34.5 kV |  | PA | Crawford | Active | PENELEC | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/25/2022 | [5 empty] | 12/30/2025 |  |  | N | No
PJM | AH2-120 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2022 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AH2-121 | Garden Prairie 345 kV |  | IL | McHenry | Active | ComEd | 500 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2022 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AH2-122 | Nelson-Lee County 345 kV |  | IL | Lee | Active | ComEd | 220 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2022 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AH2-123 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 420 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2022 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AH2-124 | Nelson - Lee County 345 kV |  | IL | Lee | Active | ComEd | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2022 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AH2-125 | Kensington 138 kV |  | KY |  | Active | ComEd | 200 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/26/2022 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AH2-126 | Tidd 138 kV |  | OH | Jefferson | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/25/2022 | [5 empty] | 10/31/2026 |  |  | N | No
PJM | AH2-127 | Burlington 26 kV |  | NJ | Burlington | Active | PSEG | 20 | 15 | 18 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/25/2022 | [5 empty] | 9/19/2023 |  |  | N | No
PJM | AH2-128 | Stone Solar 34.5 kV |  | PA | Clarion | Active | APS | 8 | 8 | 5.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 5/29/2026 |  |  | N | No
PJM | AH2-129 | Piney - Timblin 115 kV |  | PA | Armstrong | Active | APS | 52 | 36 | 23.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2022 | [5 empty] | 5/29/2026 |  |  | N | No
PJM | AH2-130 | Clark Co - Spencer Road 138 kV |  | KY |  | Active | EKPC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AH2-131 | Bridgeport 230kV |  | NJ | Gloucester | Active | AEC | 225 | 0 | 103.7 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 3/1/2025 |  |  | N | No
PJM | AH2-132 | Chambers 230kV |  | NJ | Salem | Active | AEC | 240 | 0 | 117 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2022 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AH2-133 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2022 | [5 empty] | 3/1/2027 |  |  | N | No
PJM | AH2-135 | Harwood- McAdoo 69 kV |  | PA | Luzerne | Active | PPL | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 6/19/2025 |  |  | N | No
PJM | AH2-136 | Dunnsville 345 kV |  | VA | Essex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH2-137 | Monroe - Coolwell 12.47 kV |  | VA | Amherst | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AH2-138 | Arrington Circuit 12.47 kV |  | VA | Nelson | Active | AEP | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AH2-144 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AH2-145 | Birchwood-NUG 230kV |  | VA | King George | Active | Dominion | 52.3 | 52.3 | 52.3 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AH2-146 | Adams - Seaman 69 kV |  | OH | Adams | Active | AEP | 87.2 | 87.2 | 52.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 12/30/2027 |  |  | N | No
PJM | AH2-148 | East Lima - Marysville 345 kV |  | OH | Union | Active | AEP | 152 | 152 | 143.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 2/25/2027 |  |  | N | No
PJM | AH2-149 | Stinger - Valley 138 kV |  | MI | Van Buren | Active | AEP | 150 | 150 | 120 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 6/29/2026 |  |  | N | No
PJM | AH2-150 | Carson-Suffolk 500 kV |  | VA | Sussex | Active | Dominion | 800 | 0 | 320 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH2-151 | SedgeHill - Person 230kV |  | VA | Halifax | Active | Dominion | 195 | 35 | 21 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-152 | Effort Mountain-Gilbert 138 kV IV |  | PA | Monroe | Active | PPL | 90 | 44.8 | 26.88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-153 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 180 | 180 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-154 | Eugene 345 kV |  | IN | Vermillion | Active | AEP | 150 | 150 | 118 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-155 | Lyons-Allen Jct 138 kV |  | OH | Fulton | Active | ATSI | 95 | 95 | 57 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-156 | Buckeye P-Wakeman 69 kV |  | OH | Huron | Active | ATSI | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-157 | Hooversville-Somerset 23 kV |  | PA | Somerset | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-158 | Somerset-Hooversville 115 kV |  | PA | Somerset | Active | PENELEC | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-159 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-160 | Buckskin – Worley 69 kV |  | OH | Highland | Active | AEP | 69 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-161 | Prospect 25 kV |  | PA | Butler | Active | APS | 18.8 | 18.8 | 12.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AH2-162 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Active | BGE | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/4/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-163 | Kittanning - Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 49.8 | 19.8 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-164 | Chatfield 69 kV |  | OH | Crawford | Active | AEP | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AH2-165 | Fayette - Lyons 138 kV |  | OH | Fulton | Active | ATSI | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-166 | Lyons 138 kV |  | OH | Fulton | Active | ATSI | 45 | 45 | 27 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-168 | Beatty - MT Hope 345 kV |  | OH | Madison | Active | ATSI | 185 | 185 | 111 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-169 | Thornville - Pleasantville 69 kV |  | OH | Perry | Active | AEP | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-170 | Byron 345 |  | IL | Will | Active | ComEd | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/7/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-171 | Davis Creek 345 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/7/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-172 | Wilton 345 kV |  | IL | Will | Active | ComEd | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/7/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-173 | Maryland 138 kV |  | IL | Ogle | Active | ComEd | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/7/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-181 | PA-Schwoyer 13.2 kV |  | PA | Mercer | Active | ME | 3 | 3 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 6/21/2024 |  |  | Y | No
PJM | AH2-187 | Burma – Seminole Road Junction 25 kV |  | PA | Clarion | Active | APS | 20 | 20 | 13.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 5/30/2025 |  |  | N | No
PJM | AH2-189 | Fearnley Solar 34.5 kV |  | PA | Susquehanna | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-190 | Higgins Run Solar |  | PA | Somerset | Active | PENELEC | 12 | 12 | 7.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-191 | Hopkins 138 kV |  | WV |  | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-192 | Wharton 138 kV |  | WV |  | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-193 | Pax Branch 138 kV |  | WV |  | Active | AEP | 70 | 70 | 46 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-194 | Bergen 138kV |  | NJ | Bergen | Active | PSEG | 736 | 0 | 20 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 4/30/2026 |  |  | N | No
PJM | AH2-195 | Seward-Glory 115 kV |  | PA | Indiana | Active | PENELEC | 65 | 65 | 39 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 10/29/2027 |  |  | N | No
PJM | AH2-197 | North Huntley - Pleasant Valley 138 kV |  | IL | McHenry | Active | ComEd | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-198 | Mt. Hermon 69 kV |  | MD | Wicomico | Active | DPL | 74.715 | 74.715 | 53.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH2-199 | Shorewood 138 kV |  | IL | Will | Active | ComEd | 51.7 | 51.7 | 36.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/8/2022 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH2-204 | Lancaster 138 kV |  | IL | Stephenson | Active | ComEd | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-205 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/31/2026 |  |  | N | No
PJM | AH2-206 | I.C. Air Rights 12.5 kV |  | IL | Cook | Active | ComEd | 10 | 10 | 10 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/31/2026 |  |  | N | No
PJM | AH2-207 | Hopkins 138 kV |  | WV |  | Active | AEP | 85 | 85 | 57 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-209 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 95 | 95 | 63 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-210 | Stillwell - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 78 | 78 | 78 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-211 | Olive - Dumont 345 kV |  | IN | St. Joseph | Active | AEP | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-212 | Cardington 138 kV |  | OH | Madison | Active | ATSI | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-213 | London 138 kV |  | IN | Randolph | Active | ATSI | 140 | 140 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-215 | Midway 138 kV |  | OH | Henry | Active | ATSI | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-217 | Cardington 138 kV II |  | OH | Morrow | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-218 | London 138 kV II |  | OH | Morrow | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-220 | Midway 138 kV |  | OH | Henry | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-222 | Millersburg 69 kV |  | KY |  | Active | EKPC | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-223 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 50 | 50 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-224 | Millersburg 69 kV |  | KY |  | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-226 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 175 | 175 | 175 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-227 | Bluff Point 138 kV |  | IN | Jay | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/27/2026 |  |  | N | No
PJM | AH2-228 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-229 | Bedforth North 115 kV |  | PA | Bedford | Active | PENELEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-230 | Gardners 115 kV |  | PA | Adams | Active | ME | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-233 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-234 | W Dekalb 138 kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-235 | Orrtana 115 kV |  | PA | Adams | Active | ME | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-236 | McDowell 138 kV |  | PA | Mercer | Active | ATSI | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-237 | Adams 138 kV |  | IN | Wells | Active | AEP | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-238 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-239 | Trumbull138 kV |  | OH | Trumbull | Active | ATSI | 49 | 49 | 46.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/7/2027 |  |  | N | No
PJM | AH2-241 | Loudoun 115kV |  | VA | City of Chesapeake | Active | Dominion | 45 | 45 | 45 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/1/2027 |  |  | N | No
PJM | AH2-242 | Crown - New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 45 | 45 | 40.5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/8/2027 |  |  | N | No
PJM | AH2-243 | South Summitville 69 kV |  | IN | Madison | Active | AEP | 43 | 43 | 25.78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 10/27/2028 |  |  | N | No
PJM | AH2-244 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 9/29/2023 |  |  | N | No
PJM | AH2-245 | Swickley - Ambridge 23 kV |  | PA | Allegheny | Active | DL | 25 | 25 | 25 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 9/29/2023 |  |  | N | No
PJM | AH2-246 | Polyester S/S 230kV |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-247 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 158.2836 | 83.2836 | 14.6579 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AH2-248 | Carrolltown 46 kV |  | PA | Cambria | Active | PENELEC | 113.2592 | 83.2592 | 14.6536 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AH2-249 | Busseyville 138 kV |  | KY | Lawrence | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/22/2027 |  |  | N | No
PJM | AH2-250 | TBD 13.2 kV |  | PA | Bucks | Active | PECO | 9.25 | 9.25 | 3.885 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 2/28/2024 |  |  | N | No
PJM | AH2-252 | Middleburg 12 kV |  |  |  | Active | PPL | 2 | 2 | 0 |  | Energy | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/21/2024 |  |  | Y | No
PJM | AH2-253 | Beaver Valley - Crescent 138 kV |  | PA | Beaver | Active | DL | 70 | 70 | 65 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 11/25/2025 |  |  | N | No
PJM | AH2-256 | Wheelabrator Frackville-Gilberton 69 kV II |  | PA | Schuylkill | Active | PPL | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-257 | Dequine - Eugene 345 kV |  | IN | Vermillion | Active | AEP | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 9/29/2024 |  |  | N | No
PJM | AH2-258 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | 172 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 9/27/2024 |  |  | N | No
PJM | AH2-259 | Plano 345 kV |  | IL | Kendall | Active | ComEd | 172 | 172 | 172 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 9/27/2024 |  |  | N | No
PJM | AH2-260 | Garrett - Albright 138 kV |  | WV | Preston | Active | APS | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH2-261 | Garrett - Albright 138 kV |  | WV | Preston | Active | APS | 98 | 28 | 28 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AH2-262 | Catoctin-Carroll 138 kV |  | MD | Frederick | Active | APS | 17 | 17 | 10.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-263 | Marion Co - Marion Co industrial 161 kV |  | KY | Marion | Active | EKPC | 63.6 | 25.8 | 15.48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-264 | Logtown - North Delphos 138 kV |  | OH | Van Wert | Active | AEP | 115 | 115 | 69 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-265 | Oak Grove - Hawkins Gate 230kV |  | MD | Charles | Active | PEPCO | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-266 | Hughesville-Cedarville 69kV |  | MD | Charles | Active | SMECO | 25 | 25 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-267 | Modera - BioEnergy Tap 115 kV |  | PA | Clearfield | Active | PENELEC | 100 | 100 | 85 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2022 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AH2-268 | Sapony 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 37 | 37 | 33.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AH2-269 | Lakewood 230 kV |  | NJ | Ocean | Active | JCPL | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/1/2026 |  |  | N | No
PJM | AH2-269A | Burches Hill-Chalk Point 500kV |  | MD | Prince George's | Active | PEPCO | 845 | 45 | 45 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 11/2/2026 |  |  | N | No
PJM | AH2-270 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 300 | 300 | 51 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-271 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-272 | Central VA- Chase City 115kV |  | VA | Mecklenburg | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-273 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-274 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-275 | Carrollton Solar 138 kV |  | OH | Carroll | Active | ATSI | 100 | 100 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/3/2023 |  |  | N | No
PJM | AH2-276 | Second Fork 69 kV |  | KY | Pike | Active | AEP | 40 | 40 | 28 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-277 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 60 | 60 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-278 | Cabin Creek 138 kV |  | WV | Kanawha | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-279 | Whiteley 138 kV |  | PA | Greene | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/10/2024 |  |  | N | No
PJM | AH2-281 | Trego 34.5 kV |  | VA | Greensville | Active | Dominion | 26 | 26 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/30/2024 |  |  | N | No
PJM | AH2-284 | Adams 138 kV |  | OH | Adams | Active | AEP | 49.9 | 49.9 | 49.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AH2-288 | Napoleon Muni 138 kV |  | OH | Henry | Active | AMPT | 206 | 0 | 82.4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH2-289 | East Fayette 138 kV II |  | OH | Fulton | Active | ATSI | 199 | 0 | 79.6 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AH2-290 | Sandwich 138 kV |  | IL | DeKalb | Active | ComEd | 86 | 0 | 34.4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-291 | Rawlings-Clover 500kV |  | VA | Brunswick | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/1/2026 |  |  | N | No
PJM | AH2-292 | Bear Rock 230 kV |  | PA | Cambria | Active | PENELEC | 76.95 | 76.95 | 13.6 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-294 | Mazon Blue - Lasalle 138 kV |  | IL | Grundy | Active | ComEd | 150 | 40 | 29.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 6/1/2026 |  |  | N | No
PJM | AH2-295 | Emerald 25 kV |  | PA | Greene | Active | APS | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 9/15/2025 |  |  | N | No
PJM | AH2-316 | Somerset 23 kV |  | PA | Somerset | Active | PENELEC | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AH2-317 | Fredericksburg - North Lebanon 13.2 kV |  | PA | Lebanon | Active | ME | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AH2-318 | Corry East 34.5 kV |  | PA | Warren | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AH2-319 | Milan 34.5 kV |  | PA | Bradford | Active | PENELEC | 7.5 | 7.5 | 4.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AH2-320 | Revloc 34.5 kV |  | PA | Cambria | Active | PENELEC | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AH2-321 | Cooper 34.5 kV |  | PA | York | Active | ME | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/29/2024 |  |  | N | No
PJM | AH2-322 | East Danville-Smith Mountain 138 kV |  | VA | Pittsylvania | Active | AEP | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-330 | Fentress- Landstown 230kV |  | VA | City of Chesapeake | Active | Dominion | 400 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 3/1/2027 |  |  | N | No
PJM | AH2-331 | North Delphos - Logtown 138 kV |  | OH | Van Wert | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/31/2027 |  |  | N | No
PJM | AH2-332 | Talbert 230kV |  | MD | Prince George's | Active | PEPCO | 115 | 115 | 115 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-333 | Orchard 230kV |  | NJ | Salem | Active | AEC | 415 | 415 | 415 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-334 | New Freedom 230 kV |  | NJ | Camden | Active | PSEG | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-335 | Roundtop 115 kV |  | PA | York | Active | ME | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-337 | Talbot 69 kV |  | MD | Worcester | Active | DPL | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 2/27/2026 |  |  | N | No
PJM | AH2-338 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/30/2027 |  |  | N | No
PJM | AH2-339 | Wempletown 138 kV |  | IL | Winnebago | Active | ComEd | 160 | 0 | 64 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/30/2027 |  |  | N | No
PJM | AH2-340 | Toulon 138kV |  | IL | Stark | Active | ComEd | 350 | 350 | 210 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/30/2027 |  |  | N | No
PJM | AH2-341 | Toulon 138 kV |  | IL | Stark | Active | ComEd | 350 | 0 | 140 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/30/2027 |  |  | N | No
PJM | AH2-342 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 280 | 280 | 168 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/30/2027 |  |  | N | No
PJM | AH2-343 | Edwards - Kewanee East 138kV |  | IL | Stark | Active | ComEd | 280 | 0 | 112 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/30/2027 |  |  | N | No
PJM | AH2-344 | La Rue 138 kV |  | OH | Marion | Active | AEP | 94.5 | 45 | 30.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/7/2025 |  |  | N | No
PJM | AH2-345 | Wellington 138 kV |  | OH | Lorain | Active | ATSI | 120 | 120 | 80.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/7/2025 |  |  | N | No
PJM | AH2-346 | East Arlington 69 kV |  | OH | Hancock | Active | AEP | 47.5 | 47.5 | 31.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/7/2025 |  |  | N | No
PJM | AH2-347 | Northern St. Joseph 138 kV |  | IN | St. Joseph | Active | AEP | 200 | 200 | 164 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/7/2025 |  |  | N | No
PJM | AH2-348 | Jefferson - Rockport 765 kV |  | IN | Washington | Active | AEP | 700 | 700 | 420 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-349 | Sedge Hill- Person 230kV |  | VA | Halifax | Active | Dominion | 142 | 142 | 85.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-350 | Cartersville 230kV |  | VA | Cumberland | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-351 | Jefferson - Hanging Rock 765 kV |  | KY |  | Active | AEP | 1000 | 1000 | 600 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-352 | Fall Creek 345 kV |  | IN |  | Active | AEP | 400 | 400 | 240 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-353 | Jefferson - Hanging Rock 765 kV |  | KY |  | Active | AEP | 1000 | 1000 | 600 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AH2-363 | Davis Creek - Bloom 345 kV |  | IL | Kankakee | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/31/2027 |  |  | N | No
PJM | AH2-365 | Easton - Steele 138 kV IV |  | MD | Talbot | Active | DPL | 79 | 0 | 10.787 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AH2-369 | Nuttall 138 kV |  | WV | Fayette | Active | AEP | 200 | 0 | 16 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AH2-370 | Church - Oil City 138 kV III |  | MD | Caroline | Active | DPL | 112 | 0 | 17.816 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 11/15/2023 |  |  | N | No
PJM | AH2-371 | Jay 138 kV |  | IN | Jay | Active | AEP | 150 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2026 |  |  | N | No
PJM | AH2-372 | Corbin – Cresent Ridge 138kV |  | IL | Stephenson | Active | ComEd | 302 | 52 | 52 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AH2-373 | Blossom Trail 138 kV |  | MI | Berrien | Active | AEP | 180 | 180 | 132 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AH2-374 | Milliron - Brookside 138 kV II |  | OH | Richland | Active | ATSI | 252.31 | 84 | 84 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2027 |  |  | N | No
PJM | AH2-375 | Lena- Landcaster 138kV |  | IL | Stephenson | Active | ComEd | 318 | 106 | 106 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AH2-376 | Garden Plain 138 kV |  | IL | Whiteside | Active | ComEd | 365.1 | 153 | 153 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/31/2027 |  |  | N | No
PJM | AH2-377 | Pontiac Midpoint – Dresden 345 kV |  | IL | Grundy | Active | ComEd | 450 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AH2-378 | Appomattox ESC |  | VA | Prince George | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-378A | Monroe 138kV |  | NJ | Gloucester | Active | AEC | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-379 | Sign Post - Stockton 69 kV |  | MD | Worcester | Active | DPL | 28.3 | 28.3 | 16.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-380 | Matteson - East Frankfort 138 kV |  | IL | Cook | Active | ComEd | 44 | 44 | 26.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 3/1/2026 |  |  | N | No
PJM | AH2-382 | Wythe – Mount Airy 138 kV |  | VA | Wythe | Active | AEP | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AH2-383 | Goddard - Flemingsburg 138 kV |  | KY | Fleming | Active | EKPC | 70 | 70 | 56 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 6/10/2027 |  |  | N | No
PJM | AH2-384 | Everetts 34.5kV |  | NC | Martin | Active | Dominion | 25 | 10 | 7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AH2-385 | Chinquapin-Everetts 230kV |  | NC | Pitt | Active | Dominion | 80 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AH2-386 | North Franklin 138 kV |  | WV | Pendleton | Active | APS | 191.5 | 191.5 | 28.15 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/30/2027 |  |  | N | No
PJM | AH2-387 | Long Carolyn PV 34.5 kV |  | PA | Indiana | Active | PENELEC | 9.99 | 9.99 | 5.99 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-388 | Long Carolyn 34.5 kV |  | PA | Indiana | Active | PENELEC | 9.99 | 0 | 3.85 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-389 | Devlin 69 kV |  | PA | Lawrence | Active | ATSI | 6 | 6 | 3.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-390 | Devlin Storage 69 kV |  | PA | Lawrence | Active | ATSI | 6 | 0 | 2.31 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-391 | Pomerico 69 kV |  | PA | Lawrence | Active | ATSI | 7 | 7 | 4.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-392 | Pomerico 69 kV II |  | PA | Lawrence | Active | ATSI | 7 | 0 | 2.8 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-393 | Nowacoski 34.5 kV |  | PA | Bradford | Active | PENELEC | 8 | 8 | 4.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-394 | Walters Karl 69 kV |  | PA | Lawrence | Active | ATSI | 6.3 | 6.3 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-395 | Walters Karl 69 kV II |  | PA | Lawrence | Active | ATSI | 6.3 | 0 | 2.31 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-396 | Nowacoski 34.5 kV II |  | PA | Bradford | Active | PENELEC | 8 | 0 | 3.08 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/29/2023 |  |  | N | No
PJM | AH2-397 | Somerset 115 kV |  | PA | Somerset | Active | PENELEC | 200 | 200 | 120 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2026 |  |  | N | No
PJM | AH2-398 | Four Rivers- St. Johns 230kV |  | VA | Caroline | Active | Dominion | 80 | 80 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2026 |  |  | N | No
PJM | AH2-399 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2026 |  |  | N | No
PJM | AH2-400 | TBD 34.5kV |  | VA | Rockingham | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 10/1/2026 |  |  | N | No
PJM | AH2-401 | Dubois 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 7/12/2024 |  |  | N | No
PJM | AH2-402 | Philipsburg 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 9/13/2024 |  |  | N | No
PJM | AH2-403 | Krayn 115 kV |  | PA | Cambria | Active | PENELEC | 148.2836 | 83.2836 | 14.6579 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AH2-404 | East Danville - Banister 138kV |  | VA | Pittsylvania | Active | AEP | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-405 | McConnellsburg-Guilford 138 kV |  | PA | Franklin | Active | APS | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AH2-408 | Fostoria - Lemoyne 138 kV |  | OH | Wood | Active | ATSI | 49.9 | 49.9 | 29.94 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-409 | Fostoria - Lemoyne 138 kV II |  | OH | Wood | Active | ATSI | 80 | 30.1 | 18.06 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-410 | New Castle 69 kV |  | KY |  | Active | EKPC | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-411 | New Castle 69 kV |  | KY |  | Active | EKPC | 50 | 30 | 18 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AH2-412 | TBD 69kV |  | NJ | Cumberland | Active | AEC | 7.35 | 7.35 | 3.09 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AH2-413 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 365 | 365 | 339 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AH2-414 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 689 | 350 | 350 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AH2-415 | Pontiac Midpoint 345 kV |  | IL | Livingston | Active | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AH2-416 | Pontiac Midpoint 345 |  | IL | Livingston | Active | ComEd | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AH2-418 | Riverside - Pokagon 138 kV |  | MI | Berrien | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-419 | Reynolds - Olive 345 kV |  | IN | LaPorte | Active | AEP | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AH2-420 | Morgan Street 115 kV |  | PA | Crawford | Active | PENELEC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-421 | Dresden 138kV |  | IL | Grundy | Active | ComEd | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-422 | Yukon 138 kV |  | PA | Westmoreland | Active | APS | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AH2-423 | Sollers 230kV |  | MD | Calvert | Active | SMECO | 180 | 180 | 180 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI1-001 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 2100 | 2100 | 369.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 4/2/2022 | [5 empty] | 10/10/2029 |  |  | N | No
PJM | AI1-003 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 170 | 170 | 34 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-006 | Monterville - Pickens 138 kV |  | WV | Randolph | Active | APS | 103 | 103 | 18.128 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-009 | Pendleton - Tanners Creek 138 kV |  | IN | Rush | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-011 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 131 | 46 | 27.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-012 | Buckingham- Farmville 230kV |  | VA | Cumberland | Active | Dominion | 131 | 0 | 18.4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-013 | Chickahominy 230 kV |  | VA | Charles City | Active | Dominion | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-016 | Boydton Plank Road 115 kV |  | VA | Mecklenburg | Active | Dominion | 260 | 0 | 24 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-017 | Septa 500 kV |  | VA | Surry | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-018 | Spotslvania 500 kV |  | VA | Spotsylvania | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-019 | Laurel - Cooper 161 kV |  | KY |  | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-020 | TBD |  |  |  | Active | DPL | 1.98 | 1.98 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/2/2022 | [5 empty] | 3/31/2023 |  |  | Y | No
PJM | AI1-021 | Hillandale 115kV |  | VA | Pittsylvania | Active | Dominion | 105 | 105 | 63 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 3/1/2027 |  |  | N | No
PJM | AI1-022 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AI1-023 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AI1-024 | Twin Groves 345 kV |  | IL | McLean | Active | ComEd | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AI1-026 | Ringtown 12 kV |  |  |  | Active | PPL | 5 | 5 | 0 |  | Energy | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/2/2022 | [5 empty] | 11/1/2023 |  |  | Y | No
PJM | AI1-030 | Corry East - Garland Jct 34.5 kV |  | PA | Erie | Active | PENELEC | 5 | 5 | 3.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/1/2022 | [5 empty] | 12/13/2024 |  |  | N | No
PJM | AI1-033 | Somerville 26 kV |  | NJ | Somerset | Active | PSEG | 8 | 8 | 3.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/5/2022 | [5 empty] | 12/22/2026 |  |  | N | No
PJM | AI1-038 | Harwood-Siegfried 230kV II |  | PA | Carbon | Active | PPL | 95.76 | 95.76 | 61.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/12/2022 | [5 empty] | 3/31/2024 |  |  | N | No
PJM | AI1-039 | Moshannon-Milesburg 230 kV VIII |  | PA | Clearfield | Active | PENELEC | 200 | 200 | 160 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 4/19/2022 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AI1-040 | Ridgway - Elko 138 kV |  | PA | Elk | Active | APS | 250 | 250 | 150 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 4/29/2022 | [5 empty] | 3/31/2025 |  |  | N | No
PJM | AI1-046 | Smithburg 500 kV |  | NJ | Monmouth | Active | JCPL | 1600 | 1600 | 281.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 5/25/2022 | [5 empty] | 12/31/2031 |  |  | N | No
PJM | AI1-053 | McDowell - Campbell 69 kV |  | PA | Mercer | Active | ATSI | 6.6 | 6.6 | 0 |  | Energy | Generation Interconnection | Diesel; Solar |  |  |  |  | In Progress | [12 empty] | 6/10/2022 | [5 empty] | 12/1/2022 |  |  | N | No
PJM | AI1-074 | Corwin - Elk 138 kV |  | OH | Jackson | Active | AEP | 120 | 120 | 96 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/5/2022 | [5 empty] | 12/15/2027 |  |  | N | No
PJM | AI1-075 | Lee Co. EC 345kV |  | IL | Lee | Active | ComEd | 239.8 | 0 | 11.9 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 7/6/2022 | [5 empty] | 9/1/2022 |  |  | N | No
PJM | AI1-076 | TBD 13.2 kV |  | PA | Delaware | Active | PECO | 19.8 | 19.8 | 10.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/11/2022 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI1-077 | Marengo 34.5 kV Line |  | IL | McHenry | Active | ComEd | 15.75 | 15.75 | 6.62 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/15/2022 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AI1-078 | New Carlisle - Bosserman 138 kV |  | IN | LaPorte | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/26/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-079 | Summer Shade - West Columbia 69 kV |  | KY | Adair | Active | EKPC | 64.8 | 64.8 | 64.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/26/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-080 | Albion - Kendallville - 138 kV |  | IN | LaPorte | Active | AEP | 125 | 125 | 125 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/26/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-081 | Jay - DeSoto 138 kV |  | IN | Jay | Active | AEP | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 7/26/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-082 | Laurel 25 kV |  | PA | Westmoreland | Active | APS | 15 | 15 | 9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/28/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI1-084 | Fawkes - West Berea 138kV |  | KY | Madison | Active | EKPC | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI1-085 | Tanners Creek - DeSoto 345 kV |  | IN | Wayne | Active | AEP | 290 | 290 | 174 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 7/29/2022 | [5 empty] | 9/15/2030 |  |  | N | No
PJM | AI1-086 | Trego - Emporia 115 kV |  | VA | Greensville | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/29/2022 | [5 empty] | 9/1/2025 |  |  | N | No
PJM | AI1-087 | Disputanta - Bakers Pond 115 kV |  | VA | Prince George | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/29/2022 | [5 empty] | 9/1/2025 |  |  | N | No
PJM | AI1-088 | Poe- New Bohemia 115kV |  | VA | Prince George | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/29/2022 | [5 empty] | 9/1/2025 |  |  | N | No
PJM | AI1-089 | Myrtle - Oak Ridge 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/29/2022 | [5 empty] | 9/1/2025 |  |  | N | No
PJM | AI1-091 | Bascom 69 kV |  | OH | Seneca | Active | AEP | 49.9 | 49.9 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/4/2022 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AI1-092 | Collinsville - Springfield Road 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 49.9 | 31.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/4/2022 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AI1-093 | Westmoreland 34.5 kV |  | PA | Westmoreland | Active | APS | 24 | 24 | 24 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/15/2022 | [5 empty] | 7/1/2026 |  |  | N | No
PJM | AI1-094 | Westmoreland 34.5 kV |  | PA | Westmoreland | Active | APS | 24 | 24 | 24 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/16/2022 | [5 empty] | 7/1/2026 |  |  | N | No
PJM | AI1-095 | Branchron - Keisters 25 kV |  | PA | Butler | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/19/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI1-096 | Pemberton 138 kV |  | WV |  | Active | AEP | 42 | 42 | 42 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/23/2022 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI1-097 | Newcomerstown 12.47 kV |  | OH | Tuscarawas | Active | AEP | 7 | 7 | 6.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/26/2022 | [5 empty] | 12/1/2025 |  |  | N | No
PJM | AI1-098 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 40 | 40 | 30 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/30/2022 | [5 empty] | 10/1/2026 |  |  | N | No
PJM | AI1-100 | Somerton - Norton 138 kV |  | OH | Belmont | Active | AEP | 150 | 150 | 140 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/30/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI1-101 | Pocono-Acahela 230 kV |  | PA | Lackawanna | Active | PPL | 100 | 100 | 63.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/30/2022 | [5 empty] | 9/1/2029 |  |  | N | No
PJM | AI1-102 | Suffolk 115 kV |  | VA | City of Suffolk | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 8/30/2022 | [5 empty] | 9/1/2029 |  |  | N | No
PJM | AI1-103 | Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 200 | 200 | 127.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/30/2022 | [5 empty] | 12/31/2029 |  |  | N | No
PJM | AI1-104 | Timber Road 138 kV |  | OH | Paulding | Active | AEP | 135 | 135 | 86.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/30/2022 | [5 empty] | 9/1/2029 |  |  | N | No
PJM | AI1-105 | White Haven 2 Tap-White Haven DC 69 kV |  | PA | Luzerne | Active | PPL | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 8/30/2022 | [5 empty] | 12/19/2026 |  |  | N | No
PJM | AI1-106 | Sinai 13.2 kV |  | VA | Halifax | Active | Dominion | 9.9 | 9.9 | 9.15 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/31/2022 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AI1-108 | Endless Caverns - Timberville 115 kV |  | VA | Rockingham | Active | Dominion | 38.5 | 38.5 | 33.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/31/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AI1-109 | Deans 500 kV |  | NJ | Middlesex | Active | PSEG | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/1/2022 | [5 empty] | 12/31/2029 |  |  | N | No
PJM | AI1-110 | Larrabee 230 kV V |  | NJ | Monmouth | Active | JCPL | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/1/2022 | [5 empty] | 12/31/2029 |  |  | N | No
PJM | AI1-111 | Werner 230 kV |  | NJ | Middlesex | Active | JCPL | 1310 | 1310 | 393 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 9/1/2022 | [5 empty] | 12/31/2029 |  |  | N | No
PJM | AI1-112 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 8/31/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AI1-114 | Revloc 46 kV |  | PA | Cambria | Active | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI1-115 | Glory 34.5 kV |  | PA | Clearfield | Active | PENELEC | 9.9 | 9.9 | 9.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/2/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI1-116 | Hopkins 138 kV |  | WV |  | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/6/2022 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AI1-117 | Hopkins 138 kV |  | WV |  | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/6/2022 | [5 empty] | 9/10/2024 |  |  | N | No
PJM | AI1-118 | Pequest river - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 37.6 | 37.6 | 15.792 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/6/2022 | [5 empty] | 9/29/2025 |  |  | N | No
PJM | AI1-119 | Shorewood 138kV |  | IL | Kendall | Active | ComEd | 28.8 | 28.8 | 18.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/6/2022 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AI1-120 | Pequest River - Gilbert 115 kV |  | NJ | Warren | Active | JCPL | 51.6 | 51.6 | 21.672 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/7/2022 | [5 empty] | 9/29/2025 |  |  | N | No
PJM | AI1-122 | Sparta LF Solar 34.5 kV |  | NJ | Sussex | Active | JCPL | 5.85 | 5.85 | 2.457 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/7/2022 | [5 empty] | 9/29/2025 |  |  | N | No
PJM | AI1-123 | Nutbush-Victoria DP 115kV |  | VA | Lunenburg | Active | Dominion | 59 | 59 | 35.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI1-124 | Nutbush - Victoria DP 115 kV |  | VA | Lunenburg | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI1-125 | Mount Eagle 34.5 kV |  | VA | Albemarle | Active | Dominion | 22 | 22 | 13.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AI1-126 | Farmville 12.47kV |  | VA | Cumberland | Active | Dominion | 10 | 10 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AI1-127 | Dauphin 12 kV |  | PA | Dauphin | Active | PPL | 4.5 | 4.5 | 2.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 9/9/2024 |  |  | N | No
PJM | AI1-128 | Milesburg 12.47 kV |  | PA | Centre | Active | APS | 5 | 5 | 5 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 9/9/2024 |  |  | N | No
PJM | AI1-129 | Muncy 12 kV II |  | PA | Lycoming | Active | PPL | 4.5 | 4.5 | 2.7 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 9/9/2024 |  |  | N | No
PJM | AI1-130 | Northeast-CP Crane 115kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 9/7/2026 |  |  | N | No
PJM | AI1-131 | TBD 115 kV |  | MD | Baltimore County | Active | BGE | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 9/7/2026 |  |  | N | No
PJM | AI1-132 | Fredricksburg 69 kV |  | KY | Washington | Active | EKPC | 83 | 83 | 83 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 4/30/2029 |  |  | N | No
PJM | AI1-133 | Hillsboro 69 kV |  | KY | Fleming | Active | EKPC | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 4/30/2029 |  |  | N | No
PJM | AI1-134 | Greentown - Hummel Creek 138 kV |  | IN | Grant | Active | AEP | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 4/30/2029 |  |  | N | No
PJM | AI1-135 | Perquimans 230 kV |  | NC | Chowan | Active | Dominion | 300 | 300 | 300 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/8/2022 | [5 empty] | 6/30/2026 |  |  | N | No
PJM | AI1-137 | Greystone - Portland 230 kV |  | NJ | Warren | Active | JCPL | 155 | 155 | 65.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 9/29/2025 |  |  | N | No
PJM | AI1-139 | Henrietta Township - New Russia Township 69 kV |  | OH | Lorain | Active | ATSI | 14.8 | 14.8 | 6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AI1-140 | Selma Parker - Richmond 138 kV |  | IN | Wayne | Active | AEP | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI1-141 | Blossom - Dowagi TSS 34.5 kV |  | MI | Cass | Active | AEP | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI1-143 | Bell Township - Vandergrift 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 19.9 | 7.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 4/1/2025 |  |  | N | No
PJM | AI1-144 | Gardners 13.2 kV III |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-145 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 125 | 125 | 75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI1-146 | Farmville - Moran DP 115 kV |  | VA | Prince Edward | Active | Dominion | 125 | 0 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI1-147 | Sandwich 34kV |  | IL | DeKalb | Active | ComEd | 150 | 64 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI1-148 | Davis Creek 138kV |  | IL | Kankakee | Active | ComEd | 164 | 164 | 98.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AI1-149 | Pleasant Valley 345 kV |  | IL | McHenry | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AI1-150 | Locust - Todd 69 kV |  | OH | Butler | Active | Dayton | 49.9 | 49.9 | 29.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-151 | Kyger Creek - Pierce 345 kV |  | OH | Adams | Active | AEP | 231.7 | 53.2 | 31.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-152 | Siegfried - Nazareth 69 kV |  | PA | Northampton | Active | ME | 19.9 | 19.9 | 11.9 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-153 | North Hershey - Grantville 69 kV |  | PA | Dauphin | Active | ME | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-154 | Goodings Grove 138 kV |  | IL | Will | Active | ComEd | 230 | 230 | 230 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-155 | Chicago Heights 138kV |  | IL | Cook | Active | ComEd | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-156 | West Rutland 138 kV |  | IL | Kane | Active | ComEd | 170 | 170 | 170 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-157 | Pleasant Valley – Crystal Lake 138 kV |  | IL | McHenry | Active | ComEd | 54.4 | 54.4 | 32.64 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-158 | Pleasant Valley - Crystal Lake 138 kV |  | IL | McHenry | Active | ComEd | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/4/2027 |  |  | N | No
PJM | AI1-159 | Mount Sterling - Sideview 69 kV |  | KY | Montgomery | Active | EKPC | 35 | 35 | 35 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI1-160 | Crawford Solar 2 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/1/2028 |  |  | N | No
PJM | AI1-161 | Crawford Solar 3 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 1.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/1/2028 |  |  | N | No
PJM | AI1-162 | Saltsburg-Vandergrift 138 kV |  | PA | Armstrong | Active | APS | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 9/15/2026 |  |  | N | No
PJM | AI1-165 | Magnolia - Summersville 69 kV |  | KY | Green | Active | EKPC | 85 | 85 | 50 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AI1-166 | Granger - Ontwa 138 kV |  | MI | Cass | Active | AEP | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI1-167 | Cedarville 138 kV |  | OH | Clermont | Active | DEOK | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI1-168 | Conesville 345 kV |  | OH | Coshocton | Active | AEP | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 8/31/2027 |  |  | N | No
PJM | AI1-169 | Moyock 230 kV |  | NC | Currituck | Active | Dominion | 150 | 150 | 26.4 |  | Capacity | Generation Interconnection | Storage; Wind |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 10/15/2026 |  |  | N | No
PJM | AI1-170 | Glidden - Sugar Grove 138kV |  | IL | DeKalb | Active | ComEd | 100 | 100 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 10/31/2027 |  |  | N | No
PJM | AI1-171 | Garden Plain - Rock Falls 138 kV |  | IL | Whiteside | Active | ComEd | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 4/30/2028 |  |  | N | No
PJM | AI1-172 | Katydid Road - Goodings Grove 345 kV |  | IL | Grundy | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 4/30/2028 |  |  | N | No
PJM | AI1-173 | Lena - Freeport 34.5 kV |  | IL | Stephenson | Active | ComEd | 16 | 16 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 4/30/2027 |  |  | N | No
PJM | AI1-174 | Garden Plain - Rock Falls 138 kV |  | IL | Stephenson | Active | ComEd | 118 | 118 | 94.4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 4/30/2028 |  |  | N | No
PJM | AI1-175 | Waldo - North Waldo 69 kV |  | OH | Marion | Active | AEP | 19.5 | 19.5 | 16.2 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-177 | Avon 345 kV II |  | OH | Lorain | Active | ATSI | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI1-178 | Red House DP - Sugar Hill 115 kV |  | VA | Campbell | Active | Dominion | 80 | 80 | 80 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-179 | Colver Power Project 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-180 | Windsor 69 kV |  | KY |  | Active | EKPC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-181 | Grandview 115 kV |  | PA | Venango | Active | PENELEC | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-183 | DuPont - Marlboro 115 kV |  | VA | Richmond | Active | Dominion | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-184 | Greenwood 138 kV |  | VA | Frederick | Active | APS | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-185 | Valley 230 kV |  | VA | Augusta | Active | Dominion | 210 | 210 | 210 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-186 | Strasburg 138 kV |  | VA | Shenandoah | Active | APS | 140 | 140 | 140 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-187 | Glen Gardner 230 kV |  | NJ | Hunterdon | Active | JCPL | 280 | 280 | 280 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-188 | Buffalo 115 kV |  | PA | Erie | Active | PENELEC | 130 | 130 | 130 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-189 | Northeast - Windy Edge 115 kV |  | MD | Baltimore County | Active | BGE | 110 | 110 | 110 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-190 | Eagle Road 138 kV |  | OH | Union | Active | Dayton | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI1-191 | Landcaster - Pecatonica 138 kV |  | IL | Stephenson | Active | ComEd | 200 | 200 | 35.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/1/2027 |  |  | N | No
PJM | AI1-192 | Price Hill - Pruntytown 138 kV |  | WV | Marion | Active | APS | 40 | 40 | 40 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AI1-193 | Lincoln 13.2 kV II |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-194 | Orrtanna 13.2 kV III |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-195 | Orrtanna 13.2 kV IV |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-196 | Gates Hill 25 kV |  | PA | Fayette | Active | ME | 9.8 | 9.8 | 7.88 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-197 | Gardners 13.2 kV |  | PA | Adams | Active | ME | 10 | 10 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-198 | Gardners 13.2 kV II |  | PA | Adams | Active | ME | 7.1 | 7.1 | 5.76 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-199 | South Union 25 kV |  | PA | Fayette | Active | ME | 8.3 | 8.3 | 6.98 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/9/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-200 | Campbell 8.32 kV |  | PA | Lawrence | Active | ME | 5 | 5 | 4 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-202 | Greenland Gap 500 kV |  | WV | Grant | Active | APS | 450 | 450 | 450 |  | Capacity | Generation Interconnection | Solar; Storage; Wind |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 10/15/2026 |  |  | N | No
PJM | AI1-203 | Clover - Rawling 500 kV |  | VA | Lunenburg | Active | Dominion | 300 | 300 | 180 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 12/30/2027 |  |  | N | No
PJM | AI1-211 | Brandonville - Necessity 138 kV |  | WV | Preston | Active | APS | 68 | 68 | 68 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI1-212 | Homer City - Stolle Road 345 kV |  | PA | Jefferson | Active | PENELEC | 182 | 182 | 182 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI1-213 | Farmers Valley - Ridgeway 115 kV VI |  | PA | Elk | Active | APS | 174 | 174 | 174 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI1-214 | Philipsburg 115 kV IV |  | PA | Centre | Active | PENELEC | 160 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI1-215 | Philipsburg 115 kV V |  | PA | Centre | Active | PENELEC | 180 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI1-216 | Philipsburg 115 kV VI |  | PA | Centre | Active | PENELEC | 200 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI1-217 | Philipsburg 115 kV VII |  | PA | Centre | Active | PENELEC | 217 | 17 | 17 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 9/10/2022 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI2-001 | Remington 115 kV |  | VA | Caroline | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/1/2022 | [5 empty] | 5/26/2028 |  |  | N | No
PJM | AI2-002 | Vanceville 138 kV |  | VA | Washington | Active | APS | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/1/2022 | [5 empty] | 5/26/2028 |  |  | N | No
PJM | AI2-004 | Danieltown – Brunswick 115 kV |  | VA | Brunswick | Active | Dominion | 80 | 80 | 71.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 10/14/2022 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AI2-005 | Bremo 115 kV |  | VA | Fluvanna | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 10/24/2022 | [5 empty] | 5/26/2028 |  |  | N | No
PJM | AI2-006 | Elgin 138kV |  | IL | Kane | Active | ComEd | 484 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/10/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AI2-007 | Rocky Road 138kV |  | IL | Kane | Active | ComEd | 450.8 | 40 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/10/2022 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AI2-010 | Elmont 34.5 kV |  | VA | Hanover | Active | Dominion | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/23/2022 | [5 empty] | 12/30/2025 |  |  | N | No
PJM | AI2-011 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 100 | 0 | 15 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/30/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-012 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 300 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 11/30/2022 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-013 | Grundy - Goose Lake 138 kV |  | IL | Grundy | Active | ComEd | 24.1 | 24.1 | 17.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/30/2022 | [5 empty] | 5/29/2026 |  |  | N | No
PJM | AI2-014 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 37.9 | 37.9 | 20.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 11/30/2022 | [5 empty] | 5/29/2026 |  |  | N | No
PJM | AI2-015 | Nelson-Electric Junction 345 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/1/2022 | [5 empty] | 11/30/2025 |  |  | N | No
PJM | AI2-017 | PA Centre Borealis 34.5 kV |  | PA | Centre | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/9/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI2-018 | TBD 23 kV |  | PA | Somerset | Active | PENELEC | 4 | 4 | 2.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/9/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI2-019 | TBD 12.47 kV |  | PA | Franklin | Active | APS | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/9/2022 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI2-020 | Warren County 500 kV |  | VA | Warren | Active | Dominion | 1518 | 19 | 11 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  |  |  | In Progress | [12 empty] | 12/10/2022 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-022 | East Towanda 230 kV |  | PA | Bradford | Active | PENELEC | 937.5 | 30 | 60 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 12/20/2022 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AI2-023 | Lake - 270888 345kV |  | IN | Lake | Active | ComEd | 200 | 200 | 200 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/20/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI2-024 | Racine - Ravenswood 69kV |  | OH | Meigs | Active | AEP | 60 | 60 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/22/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI2-026 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/22/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI2-027 | Buckingham-Bremo 230 kV |  | VA | Buckingham | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 12/22/2022 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI2-028 | Beatty - Biers Run 345 kV |  | OH | Union | Active | AEP | 160 | 160 | 96 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/29/2022 | [5 empty] | 12/20/2026 |  |  | N | No
PJM | AI2-029 | Clarksburg - Biers Run 69 kV |  | OH | Union | Active | AEP | 70 | 70 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 12/31/2022 | [5 empty] | 12/20/2026 |  |  | N | No
PJM | AI2-030 | Poplar Flat Switch - Brown Hill 69 kV |  | OH | Adams | Active | AEP | 50 | 50 | 40 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 1/18/2023 | [5 empty] | 12/20/2024 |  |  | N | No
PJM | AI2-031 | Sapnony 34.5kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/24/2023 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AI2-032 | Distribution Circuit#324 34.5 kV |  | VA | Dinwiddie | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/25/2023 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AI2-033 | Sapony 34.5kV |  | VA | Sussex | Active | Dominion | 40 | 40 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/24/2023 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AI2-034 | Distribution circuit#332 35kV |  | VA | Sussex | Active | Dominion | 20 | 20 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/24/2023 | [5 empty] | 10/31/2024 |  |  | N | No
PJM | AI2-035 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/25/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-036 | Craigsville-Staunton 115kV |  | VA | Augusta | Active | Dominion | 100 | 100 | 60 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/25/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-037 | Lauraville-Dunbrooke 115kV |  | VA | King and Queen | Active | Dominion | 142 | 142 | 85 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/25/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-038 | St. Johns 115kV |  | VA | Spotsylvania | Active | Dominion | 150 | 150 | 90 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/25/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-039 | Poolesville 230kV |  | VA | Surry | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2023 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI2-040 | Orange 115kV |  | VA | Orange | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2023 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI2-041 | South Boston 115kV |  | VA | Halifax | Active | Dominion | 75 | 75 | 75 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2023 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI2-042 | Paytes 115kV |  | VA | Louisa | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2023 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI2-043 | Pamplin 34.5kV |  | VA | Northumberland | Active | Dominion | 5 | 5 | 3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 1/31/2023 | [5 empty] | 4/26/2024 |  |  | N | No
PJM | AI2-044 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2023 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AI2-045 | Oceana 230kV |  | VA | City of Virginia Beach | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/1/2023 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AI2-052 | Lakewood 230 kV II |  | NJ | Ocean | Active | JCPL | 170 | 70 | 70 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/17/2023 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AI2-053 | New Holland 69 kV |  | OH | Fayette | Active | Dayton | 100 | 100 | 17.6 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-054 | Rock Springs 500 kV |  | MD | Cecil | Active | DPL | 784 | 0 | 0 |  | Energy | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 6/1/2028 |  |  | N | No
PJM | AI2-055 | Summit-West Fall 115kV II |  | PA | Blair | Active | PENELEC | 38 | 0 | 6.8 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 12/10/2010 |  |  | N | No
PJM | AI2-056 | Fairview East 34.5 kV |  | PA | Erie | Active | PENELEC | 20 | 0 | 3.78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 2/6/2024 |  |  | N | No
PJM | AI2-057 | Venango 34.5 kV |  | PA | Venango | Active | PENELEC | 20 | 0 | 6.58 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 2/20/2024 |  |  | N | No
PJM | AI2-058 | Clark Summit-Emlenton 34.5 kV |  | PA | Venango | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 1/14/2025 |  |  | N | No
PJM | AI2-059 | Wolfs Corners 34.5 kV |  | PA | Clarion | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 1/14/2024 |  |  | N | No
PJM | AI2-060 | Kewanee - E.D. Edwards 138 kV |  | IL | Henry | Active | ComEd | 70 | 0 | 40.74 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AI2-061 | Bedford North-Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 60 | 0 | 17.64 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 12/15/2026 |  |  | N | No
PJM | AI2-062 | Jack Frost - Lake Harmony 69 kV |  | PA | Carbon | Active | PPL | 60 | 0 | 18.34 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 5/15/2027 |  |  | N | No
PJM | AI2-063 | Lewis Run-Pierce Brook 230 kV |  | PA | McKean | Active | PENELEC | 280 | 0 | 82.48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 5/15/2027 |  |  | N | No
PJM | AI2-064 | Desoto - Keystone 345 kV |  | IN | Blackford | Active | AEP | 245 | 0 | 35.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AI2-065 | Varner - Sours 138 kV |  | IN | DeKalb | Active | AEP | 180 | 0 | 12.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 6/1/2026 |  |  | N | No
PJM | AI2-066 | Marion County 161 kV |  | KY | Marion | Active | EKPC | 96 | 0 | 16.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/23/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AI2-067 | Lunenburg-Nutbush 115 kV |  | VA | Lunenburg | Active | Dominion | 60 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 3/1/2027 |  |  | N | No
PJM | AI2-068 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-069 | Larabee - Atlantic 230 kV |  | NJ | Monmouth | Active | JCPL | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 10/21/2026 |  |  | N | No
PJM | AI2-070 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 3/1/2027 |  |  | N | No
PJM | AI2-071 | Dorothy - Lewis 138 kV |  | NJ | Atlantic | Active | AEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 3/1/2027 |  |  | N | No
PJM | AI2-072 | Steubenville 69 kV |  | OH | Jefferson | Active | AEP | 49.5 | 0 | 27.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 5/15/2024 |  |  | N | No
PJM | AI2-073 | Columbia-Sunbury 69 kV |  | PA | Snyder | Active | PPL | 19.8 | 0 | 9.93 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI2-074 | Beatty - Greene 345 kV |  | OH | Madison | Active | AEP | 577 | 0 | 87.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AI2-075 | Face Rock-Kinzer #13 69 kV |  | PA | Lancaster | Active | PPL | 19.8 | 0 | 9.86 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/24/2023 | [5 empty] | 7/1/2023 |  |  | N | No
PJM | AI2-076 | Kankakee 138 kV |  | IL | Kankakee | Active | ComEd | 175 | 0 | 56 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 3/15/2023 |  |  | N | No
PJM | AI2-077 | Kanakee 138 kV |  | IL | Kankakee | Active | ComEd | 175 | 0 | 56 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 3/16/2023 |  |  | N | No
PJM | AI2-078 | Myrtle-Windsor 115 kV |  | VA | Isle of Wight | Active | Dominion | 91 | 0 | 52.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-079 | Harmony Village-Shackleford 115 kV |  | VA | Fauquier | Active | Dominion | 70 | 0 | 40.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-080 | Oak Grove-Dahlgren 230 kV |  | VA | King George | Active | Dominion | 134 | 0 | 73.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-081 | Marysville - Sorenson 765 kV |  | OH | Logan | Active | AEP | 500 | 0 | 271 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-082 | Cardington-Liberty 69 kV IV |  | OH | Morrow | Active | ATSI | 101 | 0 | 34.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-084 | Galion 138 kV VI |  | OH | Morrow | Active | ATSI | 244 | 0 | 78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-085 | Pierce - Kyger Creek 345 kV |  | OH | Highland | Active | OVEC | 120 | 0 | 65 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-086 | Sharp Road 69 kV |  | OH | Knox | Active | AEP | 80 | 0 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-087 | Gold-Sabinsville 115kV III |  | PA | Potter | Active | PENELEC | 90 | 0 | 42.5 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/27/2023 | [5 empty] | 3/3/2023 |  |  | N | No
PJM | AI2-088 | Centerburg 138 kV |  | OH | Licking | Active | AEP | 412.5 | 0 | 229.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-089 | Cedar Creek 138 kV |  | DE | New Castle | Active | DPL | 114.3 | 0 | 71 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 11/15/2024 |  |  | N | No
PJM | AI2-090 | Harrington 69 kV |  | DE |  | Active | DPL | 50 | 0 | 31 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 3/15/2025 |  |  | N | No
PJM | AI2-091 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 49.2 | 0 | 22.7 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-092 | Logtown 138 kV |  | OH | Paulding | Active | AEP | 75.9 | 0 | 40.3 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-093 | Olive-DeQuine 345kV |  | IN | White | Active | AEP | 202 | 0 | 106.5 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-094 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 104 | 0 | 53.5 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-095 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 50.3 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-096 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 54 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-097 | Olive-Dequine 345kV |  | IN | White | Active | AEP | 99 | 0 | 45.3 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-098 | Meadow Lake 345kV |  | IN | White | Active | AEP | 200 | 0 | 107 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-099 | Powerton-Goodings Grove 345kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 102 | 0 | 49.3 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-100 | Powerton - Dresden 345kv (CIR Increase) |  | IL | Livingston | Active | ComEd | 198 | 0 | 96 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-101 | Haviland - Milan 138kV |  | OH | Paulding | Active | AEP | 99 | 0 | 42.6 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-102 | Lincoln-Sterling 138kV |  | OH | Paulding | Active | AEP | 101 | 0 | 46.8 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-103 | Desoto-Tanners Creek 345kV |  | IN | Randolph | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-104 | Blue Mound I |  | IL | McLean | Active | ComEd | 198 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-105 | Desoto-Tanners Creek #1 345kV |  | IN | Randolph | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-106 | Pontiac MidPoint-Brokaw 345kV |  | IL | Livingston | Active | ComEd | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-107 | Ada-Dunkirk 69kV |  | OH | Hardin | Active | AEP | 66 | 0 | 31.7 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-109 | Madoc - Delaware 138 kV |  | IN | Randolph | Active | AEP | 150 | 0 | 69 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AI2-110 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 100 | 0 | 46 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 10/31/2023 |  |  | N | No
PJM | AI2-111 | Meadow Lake 345 kV |  | IN | White | Active | AEP | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 10/31/2025 |  |  | N | No
PJM | AI2-112 | Bluff Point-Randolph 138 kV |  | IN | Randolph | Active | AEP | 100 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 10/31/2026 |  |  | N | No
PJM | AI2-113 | Old Church 230 kV |  | VA | Hanover | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 9/18/2029 |  |  | N | No
PJM | AI2-114 | Verona - Weyers Cave 115 kV |  | VA | Augusta | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 9/1/2029 |  |  | N | No
PJM | AI2-115 | Desoto 345 kV |  | IN | Delaware | Active | AEP | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 10/31/2026 |  |  | N | No
PJM | AI2-116 | Allen 345kV |  | IN | Allen | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 10/31/2026 |  |  | N | No
PJM | AI2-117 | Payne 69 kV |  | OH | Paulding | Active | AEP | 49.9 | 0 | 11.976 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 6/28/2023 |  |  | N | No
PJM | AI2-118 | Continental 69 kV |  | OH | Putnam | Active | AEP | 49.9 | 0 | 11.976 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 6/28/2023 |  |  | N | No
PJM | AI2-119 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/28/2021 |  |  | N | No
PJM | AI2-120 | Losantville 345 kV |  | IN | Randolph | Active | AEP | 125 | 0 | 52.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 10/31/2027 |  |  | N | No
PJM | AI2-121 | Hector 115 kV |  | PA | Potter | Active | PENELEC | 50 | 0 | 19.95 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-122 | Tazewell - AB1-122 345 kV |  | IL | Lasalle | Active | ComEd | 130 | 0 | 66.95 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-123 | Goddard - Plumville 138 kV |  | KY | Fleming | Active | EKPC | 120 | 0 | 35 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AI2-124 | Goddard 138 kV |  | KY | Fleming | Active | EKPC | 200 | 0 | 23.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AI2-125 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 96 | 0 | 32.16 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-126 | East Danville - Roxboro 230 kV |  | VA | Pittsylvania | Active | AEP | 54 | 0 | 16.84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-127 | Cynthiana Tie - Headquarters 69 kV |  | KY | Harrison | Active | EKPC | 70 | 0 | 20.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AI2-128 | Cardiff 230 kV |  | NJ | Atlantic | Active | AEC | 1509.6 | 0 | 1204.52 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 9/30/2027 |  |  | N | No
PJM | AI2-129 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 2250 | 0 | 1675.59 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/28/2030 |  |  | N | No
PJM | AI2-130 | Larrabee 230 kV |  | NJ | Monmouth | Active | JCPL | 1300 | 0 | 1037.2 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/28/2030 |  |  | N | No
PJM | AI2-131 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 882 | 0 | 703.75 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/28/2030 |  |  | N | No
PJM | AI2-132 | Larrabee 230 kV |  | NJ | Ocean | Active | JCPL | 445.2 | 0 | 355.02 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/28/2030 |  |  | N | No
PJM | AI2-133 | Kincaid-Pana 345kV |  | IL | Christian | Active | ComEd | 260 | 0 | 84.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 10/31/2026 |  |  | N | No
PJM | AI2-134 | Pontiac Midpoint 345 kV (CIR Increase) |  | IL | Livingston | Active | ComEd | 200 | 0 | 84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-135 | McLean 345 kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-136 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 275 | 0 | 47.98 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-137 | Stockton 138 kV |  | VA | Henry | Active | AEP | 90 | 0 | 21.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-138 | Marysville 345kV |  | OH | Union | Active | AEP | 175 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/26/2023 |  |  | N | No
PJM | AI2-139 | Marysville 345kV |  | OH | Union | Active | AEP | 225 | 0 | 54 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/25/2023 |  |  | N | No
PJM | AI2-141 | Heartsease DP - Mayo Dunbar 115kV |  | NC | Edgecombe | Active | Dominion | 75 | 0 | 18.75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 5/31/2023 |  |  | N | No
PJM | AI2-143 | Clubhouse-Sappony 230 kV |  | VA | Sussex | Active | Dominion | 149 | 0 | 37.65 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AI2-144 | Mottville 138 kV |  | MI | St. Joseph | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-145 | Claytor Lake - Edgemont 138 kV |  | VA | Montgomery | Active | AEP | 126.65 | 0 | 30.43 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-146 | Blue Jacket - Kirby 138 kV |  | OH | Logan | Active | Dayton | 348.5 | 0 | 67.08 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AI2-147 | Dequine - Eugene 345 kV |  | IN | Fountain | Active | AEP | 200 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-148 | Mississinewa- Gaston 138 kV |  | IN | Grant | Active | AEP | 160 | 0 | 38.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-149 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 280 | 0 | 67.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/24/2023 |  |  | N | No
PJM | AI2-150 | Rock Creek 138 kV |  | IN | Huntington | Active | AEP | 185 | 0 | 44.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-151 | AC1-053 Tap 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 600 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-152 | Makahoy 138 kV |  | IN | Madison | Active | AEP | 120 | 0 | 28.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-153 | Louisa-South Anna 230 kV |  | VA | Louisa | Active | Dominion | 127 | 0 | 31.95 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-154 | Moshannon-Milesburg 230 kV IX |  | PA | Centre | Active | APS | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-155 | Baker 138 kV II |  | WV | Hardy | Active | APS | 80 | 0 | 29.84 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-156 | East Springfield-London 138 kV III |  | OH | Clark | Active | ATSI | 234 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI2-157 | Elk 138 kV |  | OH | Vinton | Active | AEP | 125 | 0 | 47.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/25/2023 |  |  | N | No
PJM | AI2-159 | Eldean 138 kV |  | OH | Miami | Active | Dayton | 232 | 0 | 43.52 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/1/2027 |  |  | N | No
PJM | AI2-160 | Sullivan 345 kV |  | IN | Sullivan | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2020 |  |  | N | No
PJM | AI2-161 | Sullivan - Dequine 345 kV |  | IN | Vermillion | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-162 | Meridian - Twin Branch 345 kV |  | IN | Whitley | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-163 | Brokaw to Mt Pulaski 345 kV |  | IL | McLean | Active | ComEd | 200 | 0 | 68.8 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-164 | Fostoria Central - Lemoyn 345 kV |  | OH | Wood | Active | AEP | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-165 | Clinton - Stuart 345 kV |  | OH | Clinton | Active | Dayton | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/25/2023 |  |  | N | No
PJM | AI2-166 | Lanesville-Brokaw |  | IL | Logan | Active | ComEd | 200 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/15/2025 |  |  | N | No
PJM | AI2-167 | Lanesville-Brokaw 345 kV |  | IL | Logan | Active | ComEd | 400 | 0 | 78 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-168 | Magley 138 kV |  | IN | Adams | Active | AEP | 135 | 0 | 32.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-169 | Brody 138 kV |  | MI | Cass | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-170 | Delaware - Van Buren 138 kV |  | IN | Delaware | Active | AEP | 163 | 0 | 39.12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-171 | Cole Road 345 kV |  | OH | Franklin | Active | AEP | 310 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/25/2023 |  |  | N | No
PJM | AI2-172 | Pennville - Adams 138 kV |  | IN | Jay | Active | AEP | 205 | 0 | 37.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2022 |  |  | N | No
PJM | AI2-173 | West Newton-Lynn 138 kV |  | OH | Hardin | Active | AEP | 110 | 0 | 26.43 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AI2-174 | Kenzie Creek - Colby 138 kV |  | MI | Cass | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/25/2023 |  |  | N | No
PJM | AI2-175 | Westmoreland – Oak Grove 230 kV |  | VA | Westmoreland | Active | Dominion | 80 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-176 | Todd 69 kV |  | MD | Dorchester | Active | DPL | 50 | 0 | 14.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AI2-177 | Todd 25 kV |  | MD | Dorchester | Active | DPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 7/31/2021 |  |  | N | No
PJM | AI2-178 | LaSalle 138 kV |  | IL | Lasalle | Active | ComEd | 105.6 | 0 | 36.51 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 3/17/2023 |  |  | N | No
PJM | AI2-179 | Brokaw-Pontiac 345kV |  | IL | McLean | Active | ComEd | 250 | 0 | 97.5 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 3/17/2023 |  |  | N | No
PJM | AI2-180 | LaSalle 138kV |  | IL | Lasalle | Active | ComEd | 191 | 0 | 6.16 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 2/28/2023 |  |  | N | No
PJM | AI2-181 | Hardin Switch 345 kV |  | OH | Hardin | Active | AEP | 170 | 0 | 27.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AI2-182 | Jennings-Hazelton 138kV II |  | WV | Preston | Active | APS | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 2/28/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-183 | Spotsylvania 500kV |  | VA | Spotsylvania | Active | Dominion | 485 | 0 | 123.75 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 1/1/2028 |  |  | N | No
PJM | AI2-184 | Whitely 138 kV |  | PA | Greene | Active | APS | 30 | 0 | 8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 9/10/2023 |  |  | N | No
PJM | AI2-185 | Franklin 138 kV |  | PA | Greene | Active | APS | 150 | 0 | 41 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 9/10/2023 |  |  | N | No
PJM | AI2-186 | Franklin 138 kV |  | PA | Greene | Active | APS | 74 | 0 | 20.25 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 9/10/2023 |  |  | N | No
PJM | AI2-187 | Mt. Storm 500kV |  | WV | Grant | Active | Dominion | 800 | 0 | 445 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/1/2027 |  |  | N | No
PJM | AI2-188 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 425 | 0 | 246.25 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 3/15/2028 |  |  | N | No
PJM | AI2-189 | Mt. Storm - Meadow Brook 500 kV |  | WV | Hardy | Active | APS | 125 | 0 | 66.25 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 3/15/2028 |  |  | N | No
PJM | AI2-190 | Carbondale 138 kV |  | WV | Fayette | Active | AEP | 90 | 0 | 40.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 3/15/2028 |  |  | N | No
PJM | AI2-191 | Lyons - Moselem Springs 69 kV |  | PA | Berks | Active | ME | 20 | 0 | 6.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AI2-192 | Woodstock 69 kV |  | OH | Champaign | Active | Dayton | 40 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 4/15/2025 |  |  | N | No
PJM | AI2-193 | East Hartford - Murch 69 kV |  | MI | Van Buren | Active | AEP | 85 | 0 | 28.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/30/2024 |  |  | N | No
PJM | AI2-194 | South Kenton 138 kV |  | OH | Hardin | Active | AEP | 49.9 | 0 | 15.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AI2-195 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 194.11 | 0 | 69.88 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 4/30/2025 |  |  | N | No
PJM | AI2-196 | Lycoming-Lock Haven 69 kV |  | PA | Lycoming | Active | PPL | 143.11 | 0 | 51.52 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 4/30/2025 |  |  | N | No
PJM | AI2-197 | Reynolds - Olive 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 12/31/2021 |  |  | N | No
PJM | AI2-198 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AI2-199 | Olive-Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AI2-200 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 400 | 0 | 144 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AI2-201 | Reynolds - Olive 345 kV |  | IN | Starke | Active | AEP | 300 | 0 | 108 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/1/2023 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AI2-202 | Bennett - Farmingdale 34.5 kV |  | NJ | Monmouth | Active | JCPL | 2 | 0 | 1.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/11/2023 |  |  | N | No
PJM | AI2-203 | Upper Pittsgrove 138 kV |  | NJ | Salem | Active | AEC | 2 | 0 | 1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/30/2023 |  |  | N | No
PJM | AI2-204 | Brokaw 345kV (CIR Increase) |  | NJ | Gloucester | Active | PSEG | 3 | 0 | 1.55 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 4/1/2023 |  |  | N | No
PJM | AI2-205 | Branchville - Sussex 34.5 kV |  | NJ | Sussex | Active | JCPL | 10 | 0 | 5.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/29/2023 |  |  | N | No
PJM | AI2-206 | Cardiff 12 kV |  | NJ | Atlantic | Active | AEC | 2.6 | 0 | 1.57 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/30/2023 |  |  | N | No
PJM | AI2-207 | Rockawalkin 69 kV |  | MD | Wicomico | Active | DPL | 15 | 0 | 5.35 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/30/2023 |  |  | N | No
PJM | AI2-208 | Hawks 12.5 kV |  | NJ | Hunterdon | Active | JCPL | 3 | 0 | 1.55 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/29/2023 |  |  | N | No
PJM | AI2-209 | Burlington 26kV (CIR Increase) |  | NJ | Burlington | Active | PSEG | 7 | 0 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/29/2023 |  |  | N | No
PJM | AI2-210 | Ringoes-US Bronze 34kV |  | NJ | Hunterdon | Active | JCPL | 10 | 0 | 4.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 3/29/2023 |  |  | N | No
PJM | AI2-211 | Price 25 kV |  | MD | Queen Anne's | Active | DPL | 6 | 0 | 2.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/3/2023 |  |  | N | No
PJM | AI2-212 | Manitou-Pleasant Plains 34.5 kV |  | NJ | Ocean | Active | JCPL | 20 | 0 | 10.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 4/1/2023 |  |  | N | No
PJM | AI2-213 | Allenwood-Larrabee 2 34.5 kV |  | NJ | Monmouth | Active | JCPL | 7 | 0 | 3.05 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/29/2023 |  |  | N | No
PJM | AI2-214 | Scottsville - Bremo 138 kV |  | VA | Buckingham | Active | AEP | 149.5 | 0 | 55 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/12/2025 |  |  | N | No
PJM | AI2-215 | Pokagon - Corey 69 kV |  | MI | Cass | Active | AEP | 50 | 0 | 18.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/31/2026 |  |  | N | No
PJM | AI2-216 | Wurno - Claytor lake 138 kV |  | VA | Pulaski | Active | AEP | 180 | 0 | 77 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/13/2028 |  |  | N | No
PJM | AI2-217 | Greene - Beatty 345 kV |  | OH | Madison | Active | AEP | 155 | 0 | 56.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/30/2025 |  |  | N | No
PJM | AI2-218 | Galion - South Berwick 345 kV |  | OH | Wyandot | Active | AEP | 120 | 0 | 43.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/30/2025 |  |  | N | No
PJM | AI2-219 | Groton 138 kV II |  | OH | Erie | Active | ATSI | 125 | 0 | 45.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 11/30/2024 |  |  | N | No
PJM | AI2-220 | Beaver-Davis Besse 345 kV II |  | OH | Erie | Active | ATSI | 297.66 | 0 | 103.1 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AI2-221 | Snyder 69 kV II |  | OH | Williams | Active | ATSI | 49 | 0 | 17.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2024 |  |  | N | No
PJM | AI2-222 | Chase City-Lunenburg 115kV |  | VA | Lunenburg | Active | Dominion | 130 | 0 | 47.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-223 | WinFall-Chowan 230kV |  | NC | Chowan | Active | Dominion | 189 | 0 | 56.4 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/28/2024 |  |  | N | No
PJM | AI2-224 | Central-Chase City 115kV |  | VA | Charlotte | Active | Dominion | 149.5 | 0 | 55 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/30/2025 |  |  | N | No
PJM | AI2-225 | Lexington-Low Moor 230kV |  | VA | Botetourt | Active | Dominion | 78.2 | 0 | 32 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 11/3/2025 |  |  | N | No
PJM | AI2-226 | Jug Street 138 kV |  | OH | Licking | Active | AEP | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 8/22/2022 |  |  | N | No
PJM | AI2-227 | Boxwood-Riverville 138 kV |  | VA | Amherst | Active | AEP | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AI2-228 | Silver Lake 345 |  | IL | McHenry | Active | ComEd | 400 | 0 | 240 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 11/6/2024 |  |  | N | No
PJM | AI2-229 | Silver Lake 138 |  | IL | McHenry | Active | ComEd | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 11/6/2024 |  |  | N | No
PJM | AI2-230 | Ladysmith CT-Mine Road 230 kV |  | VA | Caroline | Active | Dominion | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AI2-231 | Gainesville-Loudoun 230 kV |  | VA | Prince William | Active | Dominion | 200 | 0 | 120 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/22/2023 |  |  | N | No
PJM | AI2-231A | Cloverdale - Burlington Height 138 kV |  | VA | Botetourt | Active | AEP | 100 | 0 | 60 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/22/2023 |  |  | N | No
PJM | AI2-232 | Shady Oaks Road 138 kV |  | IL | Lee | Active | ComEd | 215.4 | 0 | 99.5 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AI2-233 | Eagle Valley 115kV II |  | PA | Centre | Active | PENELEC | 137.6 | 0 | 49.4 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AI2-234 | Mole Creek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 200 | 0 | 92.4 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 4/1/2023 |  |  | N | No
PJM | AI2-235 | King's Creek 138 kV |  | MD | Somerset | Active | DPL | 118 | 0 | 62.652 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/2/2023 |  |  | N | No
PJM | AI2-236 | Smith Mountain - Candler Mountain 138 kV |  | VA | Campbell | Active | AEP | 80 | 0 | 22.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 3/1/2023 |  |  | N | No
PJM | AI2-237 | Garner DP-Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 196 | 0 | 69.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AI2-238 | College Corner 138 kV |  | OH | Preble | Active | AEP | 98 | 0 | 39.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-239 | Harmony Village-Shackleford 115 kV |  | VA | Gloucester | Active | Dominion | 150 | 0 | 50.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AI2-240 | Camden - Crystal 69 kV |  | OH | Preble | Active | Dayton | 69.9 | 0 | 25.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-241 | Congress-Toronto 138 kV II |  | OH | Columbiana | Active | ATSI | 145 | 0 | 55.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-242 | East Sidney-Quincy 138 kV |  | OH | Champaign | Active | Dayton | 164 | 0 | 63 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2024 |  |  | N | No
PJM | AI2-243 | Ecogrove 138 kV (CIR Increase) |  | IL | Stephenson | Active | ComEd | 199 | 0 | 80.3 |  | Capacity | Generation Interconnection | Solar; Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AI2-244 | Victoria DP-Martin DP 115 kV |  | VA | Nottoway | Active | Dominion | 150 | 0 | 50.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2028 |  |  | N | No
PJM | AI2-245 | TSS 968 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 200 | 0 | 55.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2028 |  |  | N | No
PJM | AI2-246 | East Leipsic - Richland 138 kV |  | OH | Putnam | Active | AEP | 150 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/30/2024 |  |  | N | No
PJM | AI2-248 | Schauff Road 138 kV |  | IL | Lee | Active | ComEd | 200 | 0 | 40 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 11/25/2019 |  |  | N | No
PJM | AI2-249 | Biers Run-Circleville 138 kV |  | OH | Ross | Active | AEP | 274 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 4/14/2023 |  |  | N | No
PJM | AI2-250 | Greenfield 69 kV |  | OH | Fayette | Active | Dayton | 48 | 0 | 10 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/31/2024 |  |  | N | No
PJM | AI2-251 | Buckskin 69kV |  | OH | Ross | Active | AEP | 120 | 0 | 10 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 7/31/2024 |  |  | N | No
PJM | AI2-252 | Hillsboro-Clinton 138kV |  | OH | Ross | Active | AEP | 117 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 9/30/2024 |  |  | N | No
PJM | AI2-253 | Chatfield-Howard 138kV |  | OH | Crawford | Active | AEP | 117 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 9/1/2025 |  |  | N | No
PJM | AI2-254 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 60 | 0 | 15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-255 | Clubhouse- Purdy 115kV |  | VA | Greensville | Active | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-257 | Cordova 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-259 | Greentown 138 kV |  | IN | Howard | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-260 | Keeney - Steele 230 kV |  | MD | Caroline | Active | DPL | 189 | 0 | 82.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/30/2025 |  |  | N | No
PJM | AI2-261 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-263 | Nelson 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-264 | Olive - Reynolds 345 kV |  | IN | Pulaski | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2025 |  |  | N | No
PJM | AI2-265 | Kincaid 345kV (CIR Increase) |  | IL | Christian | Active | ComEd | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-266 | R.P.Mone 345 kV |  | OH | Van Wert | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-267 | Southampton- Handsom 115kV |  | VA | Southampton | Active | Dominion | 100 | 0 | 25 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AI2-269 | Circleville 138 kV |  | OH | Pickaway | Active | AEP | 70 | 0 | 32.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-270 | East Lima-Marysville 345kV |  | OH | Hardin | Active | AEP | 150 | 0 | 45 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 2/25/2023 |  |  | N | No
PJM | AI2-271 | Smith Mountain-Bearskin 138 kV |  | VA | Pittsylvania | Active | AEP | 120 | 0 | 14.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-272 | Pantago-Five Points 115kV |  | NC | Beaufort | Active | Dominion | 74 | 0 | 32.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/23/2023 |  |  | N | No
PJM | AI2-273 | Boykins-Handsome 115kV |  | VA | Southampton | Active | Dominion | 100 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/25/2023 |  |  | N | No
PJM | AI2-274 | Powhatan 34.5 kV |  | VA | Powhatan | Active | Dominion | 17 | 0 | 6.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2023 |  |  | N | No
PJM | AI2-275 | Garner-Northern Neck 115 kV |  | VA | Pittsylvania | Active | Dominion | 42 | 0 | 5.04 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/24/2023 |  |  | N | No
PJM | AI2-277 | Rogers Road 500 kV |  | VA | Greensville | Active | Dominion | 75 | 0 | 45 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-278 | Garner Delivery Point - Lancaster 115 kV |  | VA | Lancaster | Active | Dominion | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/1/2027 |  |  | N | No
PJM | AI2-279 | Garner-Northern Neck 115 kV |  | VA | Richmond | Active | Dominion | 75 | 0 | 43 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-280 | Carson-Wake 500kV |  | VA | Brunswick | Active | Dominion | 1525.5 | 0 | 34 |  | Capacity | Generation Interconnection | Natural Gas; Other |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/24/2023 |  |  | N | No
PJM | AI2-281 | Heritage-Carson |  | VA | Greensville | Active | Dominion | 1756 | 0 | 44.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-282 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 11.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-283 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 209 | 0 | 12.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-284 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 10.2 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/1/2023 |  |  | N | No
PJM | AI2-285 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 9.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-286 | Ladysmith CT 230 kV |  | VA | Caroline | Active | Dominion | 190 | 0 | 9.4 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-287 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 18.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-288 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 16.9 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-289 | Remington CT 230 kV |  | VA | Fauquier | Active | Dominion | 190 | 0 | 16.3 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 2/27/2023 |  |  | N | No
PJM | AI2-290 | Brookside-Cloverdale 138 kV II |  | OH | Wayne | Active | ATSI | 130 | 0 | 9.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-291 | Edison-Gravel Pit 138 kV |  | IN | St. Joseph | Active | AEP | 150 | 0 | 10.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-292 | Hunterstown-Texas Eastern Tap 115 kV III |  | PA | Adams | Active | ME | 70 | 0 | 4.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-293 | Edinboro South-Venango Junction 115 kV IV |  | PA | Crawford | Active | PENELEC | 116.5 | 0 | 8.16 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-294 | Laurel Mountain 138 kV |  | WV | Randolph | Active | APS | 125 | 0 | 52.9 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 1/1/2028 |  |  | N | No
PJM | AI2-295 | Cox-Whitakers 115kV |  | NC | Halifax | Active | Dominion | 80 | 0 | 20.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 1/1/2028 |  |  | N | No
PJM | AI2-297 | McConnellsburg 138 kV |  | PA | Fulton | Active | APS | 70 | 0 | 18.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 1/1/2028 |  |  | N | No
PJM | AI2-299 | Benson-Dunbar 115 kV |  | NC | Edgecombe | Active | Dominion | 100 | 0 | 30.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/11/2020 |  |  | N | No
PJM | AI2-300 | Elizabeth City 34.5 kV |  | NC | Pasquotank | Active | Dominion | 20 | 0 | 6.36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 10/18/2021 |  |  | N | No
PJM | AI2-301 | Dawson-South Justice 115kV |  | NC | Halifax | Active | Dominion | 140 | 0 | 45.12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 6/30/2025 |  |  | N | No
PJM | AI2-302 | Jacksonville Tap - Renaker 138 kV |  | KY | Harrison | Active | EKPC | 100 | 0 | 26.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 8/30/2024 |  |  | N | No
PJM | AI2-303 | Crown-New Lebanon 69 kV |  | OH | Montgomery | Active | Dayton | 49.9 | 0 | 18.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-304 | Sporn South-Leon 138 kV |  | WV | Mason | Active | AEP | 100 | 0 | 36.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-305 | Ebersole #2-Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 120 | 0 | 33.64 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-306 | Osterburg - Bedford North 23 kV II |  | PA | Bedford | Active | PENELEC | 12 | 0 | 4.37 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 7/18/2025 |  |  | N | No
PJM | AI2-307 | Colora 230 kV |  | MD | Cecil | Active | DPL | 100.8 | 0 | 60.48 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 9/10/2026 |  |  | N | No
PJM | AI2-308 | Snake Spring-Bedford Area 23 kV |  | PA | Bedford | Active | PENELEC | 12 | 0 | 4.37 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/27/2024 |  |  | N | No
PJM | AI2-309 | Marysville-Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 250 | 0 | 90.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 4/15/2025 |  |  | N | No
PJM | AI2-310 | Emlenton 34.5 kV II |  | PA | Venango | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/3/2025 |  |  | N | No
PJM | AI2-311 | Ringgold 138 kV II |  | MD | Washington | Active | APS | 50 | 0 | 30 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 1/11/2025 |  |  | N | No
PJM | AI2-312 | Clark Summit 34.5 kV II |  | PA | Venango | Active | PENELEC | 15 | 0 | 5.46 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/15/2022 |  |  | N | No
PJM | AI2-313 | Ravenswood-Hemlock 69kV |  | OH | Meigs | Active | AEP | 48 | 0 | 17.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2023 |  |  | N | No
PJM | AI2-314 | Molecreek 345kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 100 | 0 | 27 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-315 | Mole Creek 345 kV |  | IL | Woodford | Active | ComEd | 300 | 0 | 90 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-316 | Powerton 345 kV (CIR increase) |  | IL | Woodford | Active | ComEd | 50 | 0 | 19 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-317 | Powertn - Goodings Grove 345 kV (CIR Increase) |  | IL | Woodford | Active | ComEd | 350 | 0 | 133 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-318 | White Marsh 34.5 kV |  | VA | Gloucester | Active | Dominion | 19 | 0 | 12.84 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-320 | Edinboro South - Erie South 25 kV |  | PA | Erie | Active | PENELEC | 19.9 | 0 | 5.05 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-321 | Clementine-Clementine Jct. 25 kV |  | PA | Armstrong | Active | APS | 19.9 | 0 | 8.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-322 | Findlay - Midfield 23 kV |  | PA | Allegheny | Active | DL | 4.7 | 0 | 1.18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-323 | Kittanning-Rural Valley 25 kV |  | PA | Armstrong | Active | APS | 30 | 0 | 7.56 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-324 | Cowansville Junction – Long Run Tap 25 kV |  | PA | Armstrong | Active | APS | 14.7 | 0 | 3.72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-325 | Oyster Creek 230 kV |  | NJ | Ocean | Active | JCPL | 816 | 0 | 178.7 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-326 | BL England 138 kV |  | NJ | Cape May | Active | AEC | 432 | 0 | 94.6 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-327 | Patton Rd-Summer Shade 69 kV |  | KY | Metcalfe | Active | EKPC | 55 | 0 | 19.91 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 10/15/2023 |  |  | N | No
PJM | AI2-328 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-329 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 100 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-330 | Marysville-Flatlick 765 kV |  | OH | Madison | Active | AEP | 400 | 0 | 83.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI2-331 | Hopkins 138 kV |  | WV |  | Active | AEP | 180 | 0 | 42.84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AI2-332 | Gilboa-Jones Branch 138 kV IV |  | WV | Nicholas | Active | APS | 150 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 6/1/2030 |  |  | N | No
PJM | AI2-333 | Johns Creek-Excel 138kV I |  | KY | Pike | Active | AEP | 100 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/1/2026 |  |  | N | No
PJM | AI2-334 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 0 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/30/2026 |  |  | N | No
PJM | AI2-335 | Inez 138 kV |  | KY | Martin | Active | AEP | 200 | 0 | 34.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-336 | Nottingham Switch 138 kV |  | OH | Harrison | Active | AEP | 400 | 0 | 34.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/10/2026 |  |  | N | No
PJM | AI2-337 | Broadview-Tangy 138 kV IV |  | OH | Madison | Active | ATSI | 180 | 0 | 30 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/1/2023 |  |  | N | No
PJM | AI2-338 | Providence Forge-Turner 115kV |  | VA | Charles City | Active | Dominion | 154 | 0 | 29.15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AI2-339 | Gilboa-Jones Branch 138 kV V |  | WV | Nicholas | Active | APS | 100 | 0 | 26.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AI2-340 | Valley 138 kV |  | MI | Van Buren | Active | AEP | 100 | 0 | 23.1 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AI2-341 | Galion-Roberts South 138 kV III |  | OH | Marion | Active | ATSI | 99.96 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AI2-342 | Excel-Johns Creek 138 kV |  | KY | Pike | Active | AEP | 75 | 0 | 15.38 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 3/31/2027 |  |  | N | No
PJM | AI2-343 | Hurley 69 kV |  | VA | Buchanan | Active | AEP | 75 | 0 | 15.25 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/3/2025 |  |  | N | No
PJM | AI2-344 | Gladstone 138 kV |  | VA | Nelson | Active | AEP | 100 | 0 | 17 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/1/2024 |  |  | N | No
PJM | AI2-345 | Amherst-Riverville138 kV |  | VA | Amherst | Active | AEP | 75 | 0 | 18 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 6/1/2025 |  |  | N | No
PJM | AI2-346 | Nottingham 138 kV |  | OH | Harrison | Active | AEP | 400 | 0 | 20 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 9/10/2025 |  |  | N | No
PJM | AI2-347 | Van Arsdell-Mercer Industrial 69kV |  | KY | Mercer | Active | EKPC | 95 | 0 | 17 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 9/1/2026 |  |  | N | No
PJM | AI2-348 | Ford - Ceddarville 138 kV |  | OH | Clermont | Active | DEOK | 152.2 | 0 | 17.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-349 | Loretto 69 kV |  | KY | Marion | Active | EKPC | 60 | 0 | 11 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 2/28/2029 |  |  | N | No
PJM | AI2-350 | Hillsboro - Wye Mills 138 kV |  | MD | Queen Anne's | Active | DPL | 50 | 0 | 11.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AI2-353 | Carlos Jct. – Ridgeley 138 kV |  | MD | Allegany | Active | APS | 54.9 | 0 | 16 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 4/1/2024 |  |  | N | No
PJM | AI2-354 | Williams 138 kV |  | WV | Grant | Active | APS | 147 | 0 | 58.7 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 1/1/2026 |  |  | N | No
PJM | AI2-355 | Greenland Gap 500 kV |  | WV | Grant | Active | APS | 300 | 0 | 103.8 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 4/3/2023 |  |  | N | No
PJM | AI2-356 | Greenland Gap 500 kV II |  | WV | Grant | Active | APS | 471.6 | 0 | 57.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 7/31/2027 |  |  | N | No
PJM | AI2-357 | Olive-Reynolds #2 345 kV |  | IN | Pulaski | Active | AEP | 260 | 0 | 18.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/6/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-358 | Argenta - Twin Branch 345 kV |  | MI | Van Buren | Active | AEP | 300 | 0 | 70 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/8/2023 | [5 empty] | 5/1/2028 |  |  | N | No
PJM | AI2-359 | Cross School 138 kV |  | WV | Mineral | Active | APS | 53.7 | 0 | 13.1 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 4/3/2023 |  |  | N | No
PJM | AI2-360 | Elk Garden - Parr Run 138 kV |  | WV | Mineral | Active | APS | 110 | 0 | 45.9 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 4/3/2023 |  |  | N | No
PJM | AI2-361 | Hooversville - Central City West 115 kV |  | PA | Somerset | Active | PENELEC | 29.4 | 0 | 10.17 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 3/2/2023 |  |  | N | No
PJM | AI2-362 | Rockwood - Meyersdale North 115 kV |  | PA | Somerset | Active | PENELEC | 37.8 | 0 | 13 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 4/3/2023 |  |  | N | No
PJM | AI2-364 | Brokaw - Lanesville 345 kV (CIR Increase) |  | IL | Fulton | Active | ComEd | 200 | 0 | 79.91 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 4/20/2023 |  |  | N | No
PJM | AI2-365 | Lake Lynn-Hazelton 138 kV II |  | WV | Preston | Active | APS | 99.6 | 0 | 32.06 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 9/30/2021 |  |  | N | No
PJM | AI2-366 | Maddox Creek-RP Mone 345 kV |  | OH | Van Wert | Active | AEP | 300 | 0 | 93.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AI2-367 | Sleepy Hollow 138 kV II |  | WV | Jefferson | Active | APS | 125 | 0 | 34 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AI2-368 | TSS 994 345 kV (CIR Increase) |  | IL | Logan | Active | ComEd | 187.5 | 0 | 77.87 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 4/17/2023 |  |  | N | No
PJM | AI2-369 | Apple Grove 138 kV |  | WV | Mason | Active | AEP | 99 | 0 | 29.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 6/30/2023 |  |  | N | No
PJM | AI2-370 | Twombley Road 138kV (CIR Increase) |  | IL | Ogle | Active | ComEd | 60 | 0 | 19.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 4/1/2026 |  |  | N | No
PJM | AI2-371 | Walnut Grove - Asahi Tap 69 kV |  | KY | McLean | Active | EKPC | 57 | 0 | 17.78 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 9/25/2024 |  |  | N | No
PJM | AI2-372 | Hill Topper 345kV (CIR Increase) |  | IL | Logan | Active | ComEd | 65 | 0 | 23.56 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 3/30/2020 |  |  | N | No
PJM | AI2-373 | Easton - Steele 138 kV |  | MD | Talbot | Active | DPL | 79 | 0 | 23.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 3/31/2026 |  |  | N | No
PJM | AI2-374 | Hope-Blevins Valley Tap 69 kV |  | KY | Bath | Active | EKPC | 66 | 0 | 20.59 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 3/31/2025 |  |  | N | No
PJM | AI2-375 | Old Chapel-Millville 138 kV |  | WV | Jefferson | Active | APS | 80 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-376 | Central Hardin-Stephensburg 69 kV |  | KY | Hardin | Active | EKPC | 70 | 0 | 21.84 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 3/31/2025 |  |  | N | No
PJM | AI2-377 | Maysville 69 kV VI |  | PA | Mercer | Active | ATSI | 50 | 0 | 15.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AI2-378 | Merrill Creek 115 kV II |  | NJ | Warren | Active | JCPL | 70 | 0 | 28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AI2-379 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 78.38 | 0 | 24.51 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AI2-380 | Altoona-Raystown 230 kV III |  | PA | Blair | Active | PENELEC | 80 | 0 | 30.16 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AI2-381 | Layland 69 kV |  | WV | Fayette | Active | AEP | 75 | 0 | 35.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AI2-383 | Moshannon-Milesburg 230 kV X |  | PA | Centre | Active | APS | 83.6 | 0 | 26.29 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AI2-384 | Nelson 138kV (CIR Increase) |  | IL | Lee | Active | ComEd | 200 | 0 | 89.44 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-385 | South Millville - Newport 69 kV |  | NJ | Cumberland | Active | AEC | 59.7 | 0 | 23.57 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 3/31/2025 |  |  | N | No
PJM | AI2-386 | PG - Juniata 69 kV |  | PA | Dauphin | Active | PPL | 55 | 0 | 20.74 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-387 | Carlls Corner - Sherman Ave 69 kV |  | NJ | Cumberland | Active | AEC | 49.7 | 0 | 19.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-388 | Milton 69 kV |  | PA | Northumberland | Active | PPL | 70 | 0 | 20.15 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-389 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 134.16 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-390 | Bluemond-Chestnut 345kV (CIR Increase) |  | IL | McLean | Active | ComEd | 300 | 0 | 134.16 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/4/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-391 | Emporia-Trego 115kV |  | VA | Greensville | Active | Dominion | 80 | 0 | 13 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 2/25/2023 |  |  | N | No
PJM | AI2-392 | Beatty-London 138 kV |  | OH | Madison | Active | AEP | 196 | 0 | 31.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-393 | Hickory-Moyock 230 kV |  | NC | Currituck | Active | Dominion | 100 | 0 | 17.7 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-394 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 0 | 66 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-395 | Reynolds–Olive #1 345 kV |  | IN | White | Active | AEP | 180 | 0 | 59.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-396 | Jay-Desoto 138kV |  | IN | Blackford | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/3/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-397 | West Manchester-Crown 69kV |  | OH | Preble | Active | AEP | 80 | 0 | 19.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-398 | West Manchester 69 kV |  | OH | Preble | Active | AEP | 40 | 0 | 9.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-399 | Jay 138 kV |  | IN | Jay | Active | AEP | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-400 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 72.6 | 0 | 25 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-401 | Olive-Reynolds #1 345 kV |  | IN | White | Active | AEP | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-402 | Kirk - Newark Center 138 kV |  | OH | Licking | Active | AEP | 107.7 | 0 | 25.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-403 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 81.4 | 0 | 19.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-404 | Munfordville KU Tap-Horse Cave Jct. 69 kV |  | KY | Hart | Active | EKPC | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-405 | Glidden-Waterman 138 kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 94.9 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-407 | Fostoria Central 138 kV |  | OH | Hancock | Active | AEP | 205 | 0 | 31.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-408 | Sugar Grove-Waterman 138kV |  | IL | DeKalb | Active | ComEd | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-409 | Wayne-Byron 345 kV |  | IL | DeKalb | Active | ComEd | 300 | 0 | 72 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-410 | Glidden - Cherry Valley 138 kV |  | IL | DeKalb | Active | ComEd | 118.6 | 0 | 28.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-411 | Glidden - Waterman 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 95.1 | 0 | 22.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-412 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-413 | Gateway 69 kV |  | IN | Whitley | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-415 | Campbell-Kiesters 138 kV |  | PA | Butler | Active | PPL | 70 | 0 | 20.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-416 | Lexington-Dooms 230 kV |  | VA | Augusta | Active | Dominion | 200 | 0 | 50 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-417 | Wayne 345kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 200 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-418 | Sowers 138 kV |  | IN | Allen | Active | AEP | 100 | 0 | 24 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-420 | Crego Road 138kV (CIR Increase) |  | IL | DeKalb | Active | ComEd | 100 | 0 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-421 | Varner 345 kV |  | IN | DeKalb | Active | AEP | 180 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-422 | Jay 138 kV |  | IN | Jay | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-423 | Jay 69 kV |  | IN | Jay | Active | AEP | 50 | 0 | 12 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-424 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 111.8 | 0 | 28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI2-425 | Sorenson 345 kV |  | IN | Huntington | Active | AEP | 160 | 0 | 40 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2028 |  |  | N | No
PJM | AI2-426 | Allen - RP Mone 345 kV |  | IN | Allen | Active | AEP | 180 | 0 | 43.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-427 | Hazelton - Kirk 138 kV |  | OH | Licking | Active | AEP | 110 | 0 | 26.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/2/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-428 | Crescent Ridge 138kV (CIR Increase) |  | IL | Bureau | Active | ComEd | 88.7 | 0 | 20.1 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-429 | Mendota Hills 138 kV |  | IL | Lee | Active | ComEd | 76.1 | 0 | 22.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-430 | Auburn 69 kV |  | IN | DeKalb | Active | AEP | 11 | 11 | 10 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 7/1/2023 |  |  | N | No
PJM | AI2-431 | Larrabee Collector Station 230 kV |  | NJ | Atlantic | Active | JCPL | 2138.85 | 2138.85 | 2083 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 2/28/2030 |  |  | N | No
PJM | AI2-432 | Philipsburg-Clarence 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 12/27/2022 |  |  | N | No
PJM | AI2-433 | Dubois-Curwensville 34.5 kV II |  | PA | Clearfield | Active | PENELEC | 20 | 0 | 7.28 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 2/28/2023 |  |  | N | No
PJM | AI2-435 | South Hamburg – St. Peters Village 69 kV |  | PA | Berks | Active | ME | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-436 | Luthersburg - Curwensville 34.5 kV |  | PA | Clearfield | Active | PENELEC | 20 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/9/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-437 | Glen Gardner - Washington 34.5 kV |  | NJ | Warren | Active | JCPL | 20 | 20 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2024 |  |  | N | No
PJM | AI2-438 | Apple Valley 138kV |  | OH | Knox | Active | AEP | 150 | 150 | 148 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 7/10/2027 |  |  | N | No
PJM | AI2-439 | Philipsburg 115 kV |  | PA | Centre | Active | PENELEC | 237 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-440 | Phillipsburg 115 kV |  | PA | Centre | Active | PENELEC | 257 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-441 | Salem - Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 100 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-442 | Salem-Beacon Power 69 kV |  | PA | Luzerne | Active | PPL | 120 | 20 | 20 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-443 | North Longview 500 kV |  | PA | Greene | Active | APS | 300 | 300 | 295 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 7/10/2027 |  |  | N | No
PJM | AI2-444 | Rum Creek 138kV |  | WV |  | Active | AEP | 59.5 | 59.5 | 52.1 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 3/8/2026 |  |  | N | No
PJM | AI2-445 | Parsons - William 138 kV |  | WV | Tucker | Active | APS | 148 | 148 | 128.8 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 3/8/2026 |  |  | N | No
PJM | AI2-446 | Medera - Westover South 115 kV |  | PA | Cambria | Active | PENELEC | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2027 |  |  | N | No
PJM | AI2-447 | Hillsboro-Wildcat 138kV |  | OH | Highland | Active | AEP | 150 | 0 | 87.3 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 9/30/2023 |  |  | N | No
PJM | AI2-448 | Curdsville-Willis Mtn 115 kV |  | VA | Buckingham | Active | Dominion | 100 | 0 | 36.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-449 | Disputanta-Poe 115 kV |  | VA | Prince George | Active | Dominion | 100 | 0 | 36.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-450 | DeSoto-Keystone 345 kV |  | IN | Blackford | Active | AEP | 100 | 0 | 48.6 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-451 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 38.5 | 0 | 13.9 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-452 | Gunn Road 345 kV |  | OH | Hardin | Active | AEP | 130 | 0 | 51.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-453 | Givens - Mechanicsburg 138 kV |  | OH | Champaign | Active | Dayton | 78 | 0 | 28.2 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-454 | Mazon-Oglesby 138kV (CIR Increase) |  | IL | Grundy | Active | ComEd | 116 | 0 | 42 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-455 | W4-005 345kV (CIR Increase) |  | PA | Union | Active | ComEd | 306 | 0 | 162.8 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 3/31/2023 |  |  | N | No
PJM | AI2-456 | Birchwood - Fines Corner 230 kV |  | VA | King George | Active | Dominion | 150 | 150 | 150 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 9/15/2027 |  |  | N | No
PJM | AI2-457 | Morgantown 230 kV |  | MD | Charles | Active | PEPCO | 1122 | 1122 | 1122 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 10/1/2027 |  |  | N | No
PJM | AI2-458 | Bernville 34.5 kV 1 |  | PA | Berks | Active | ME | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-459 | Bernville 34.5 kV 2 |  | PA | Berks | Active | ME | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-460 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 150 | 0 | 36 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-461 | Wilton Center - Loretto 345 kV(CIR Increase) |  | IL | Kankakee | Active | ComEd | 850 | 0 | 173 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AI2-462 | AD1-100 345kV (CIR Increase) |  | IL | Kankakee | Active | ComEd | 150 | 0 | 48 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-463 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-464 | Laurelton-Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-465 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-466 | Laurelton - Mifflinburg 69 kV |  | PA | Union | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-467 | Maysville 138 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-468 | Summit Road 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-469 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-470 | Mercer 12.5 kV |  | PA | Mercer | Active | ATSI | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-471 | Montour 230 kV |  | PA | Montour | Active | PPL | 101.6 | 0 | 29.464 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2025 |  |  | N | No
PJM | AI2-472 | Montour 230 kV |  | PA | Montour | Active | PPL | 50 | 0 | 14.5 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AI2-473 | Montour 230 kV |  | PA | Montour | Active | PPL | 100 | 0 | 29 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AI2-474 | Montour 230 kV |  | PA | Montour | Active | PPL | 120 | 0 | 34.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AI2-475 | Montour 230 kV |  | PA | Montour | Active | PPL | 140 | 0 | 40.6 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AI2-476 | Snake Spring 115 kV |  | PA | Bedford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-477 | Snake Spring 115 kV II |  | PA | Bedford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-480 | Crawford 34.5 kV |  | PA | Crawford | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-481 | Union City - French Road 12.5kV |  | PA | Erie | Active | PENELEC | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 5/1/2026 |  |  | N | No
PJM | AI2-482 | Copperstone-North Lebanon 230 kV IV |  | PA | Lebanon | Active | ME | 100 | 0 | 58 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/7/2023 | [5 empty] | 12/1/2023 |  |  | N | No
PJM | AI2-483 | Heath 69 kV |  | OH | Licking | Active | AEP | 22.4 | 0 | 13.44 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 3/7/2023 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AI2-484 | Heidelberg 69 kV |  | PA | Lebanon | Active | PPL | 20 | 0 | 5.8 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/1/2027 |  |  | N | No
PJM | AI2-485 | Bruin Junction - Petrol Junction 25 kV |  | PA | Butler | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AI2-486 | Bethelboro - Connellsville 25 kV |  | PA | Fayette | Active | APS | 14 | 14 | 8.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AI2-487 | Kewanee-Hennepin Tap 138kV |  | IL | Bureau | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-488 | Electric Junction - Nelson 345kV (CIR Increase) |  | IL | Lee | Active | ComEd | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2026 |  |  | N | No
PJM | AI2-489 | Keystone-Desoto 345 kV |  | IN | Blackford | Active | AEP | 200 | 0 | 97.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/31/2025 |  |  | N | No
PJM | AI2-490 | Frostburg 138 kV |  | MD | Allegany | Active | APS | 80 | 0 | 31.9 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/15/2023 |  |  | N | No
PJM | AI2-491 | East Lima-Marysville 345kV |  | OH | Champaign | Active | AEP | 250 | 0 | 133 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 5/31/2021 |  |  | N | No
PJM | AI2-492 | Deer Creek-Fisher Body-Mullin 138kV |  | IN | Grant | Active | AEP | 200 | 0 | 106.4 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/10/2023 | [5 empty] | 12/26/2012 |  |  | N | No
PJM | AI2-493 | New Baltimore 115kV (Stony Creek) |  | PA | Somerset | Active | PENELEC | 52.5 | 0 | 18.2 |  | Capacity | Generation Interconnection | Wind |  |  |  |  | In Progress | [12 empty] | 3/11/2023 | [5 empty] | 8/31/2023 |  |  | N | No
PJM | AJ1-001 | Boydton DP 115 kV |  | VA | Mecklenburg | Active | Dominion | 50 | 50 | 50 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/21/2023 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AJ1-002 | North River Delivery Point 115 kV |  | VA | Rockingham | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/21/2023 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AJ1-003 | Palmer Springs 115 kV |  | VA | Mecklenburg | Active | Dominion | 100 | 100 | 40 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 4/21/2023 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AJ1-008 | Zimmer 345 kV |  | OH | Clermont | Active | DEOK | 800 | 800 | 692.3 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 5/8/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AJ1-010 | Racine - Sarah Lane 69 kV |  | WV | Mason | Active | AEP | 35 | 35 | 7.098 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 5/22/2023 | [5 empty] | 7/1/2025 |  |  | N | No
PJM | AJ1-011 | Waukegan Unit 7 CIR Transfer |  | IL | Lake | Active | ComEd | 328 | 328 | 328 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 5/24/2023 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AJ1-012 | Waukegan Unit 8 CIR Transfer |  | IL | Lake | Active | ComEd | 354.4 | 354.4 | 354.4 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 5/24/2023 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AJ1-013 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 250 | 250 | 250 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 5/24/2023 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AJ1-014 | Will County Unit 4 CIR Transfer |  | IL | Will | Active | ComEd | 260 | 260 | 260 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 5/24/2023 | [5 empty] | 6/1/2027 |  |  | N | No
PJM | AJ1-015 | Larrabee Collector 230 kV |  | NJ | Monmouth | Active | JCPL | 1342 | 1342 | 1275 |  | Capacity | Generation Interconnection | Offshore Wind |  |  |  |  | In Progress | [12 empty] | 6/2/2023 | [5 empty] | 5/1/2030 |  |  | N | No
PJM | AJ1-016 | Cambria Slope 115 kV |  | PA | Cambria | Active | PENELEC | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 6/7/2023 | [5 empty] | 11/9/2028 |  |  | N | No
PJM | AJ1-018 | Bishopville – Worcester 138 kV |  | MD | Worcester | Active | DPL | 39 | 39 | 39 |  | Capacity | Generation Interconnection | Solar; Storage |  |  |  |  | In Progress | [12 empty] | 6/22/2023 | [5 empty] | 12/29/2028 |  |  | N | No
PJM | AJ1-019 | Bell Avenue 115 kV |  | VA | Southampton | Active | Dominion | 100 | 100 | 100 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 6/28/2023 | [5 empty] | 12/1/2028 |  |  | N | No
PJM | AJ1-020 | St. Johns – Woodpecker 115 kV |  | VA | Caroline | Active | Dominion | 86.38 | 86.38 | 51.828 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/30/2023 | [5 empty] | 12/15/2029 |  |  | N | No
PJM | AJ1-021 | Woodpecker – Slabtown 115 kV |  | VA | Caroline | Active | Dominion | 16.2 | 16.2 | 10.0584 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/30/2023 | [5 empty] | 12/15/2029 |  |  | N | No
PJM | AJ1-022 | Kerr Dam - Henderson NC 115 kV |  | VA | Mecklenburg | Active | Dominion | 49 | 49 | 29.4 |  | Capacity | Generation Interconnection | Solar |  |  |  |  | In Progress | [12 empty] | 6/30/2023 | [5 empty] | 6/30/2027 |  |  | N | No
PJM | AJ1-023 | Trumbull 345 kV |  | OH | Trumbull | Active | ATSI | 1010 | 70 | 70 |  | Capacity | Generation Interconnection | Natural Gas |  |  |  |  | In Progress | [12 empty] | 6/30/2023 | [5 empty] | 12/1/2024 |  |  | N | No
PJM | AJ1-037 | Northeast - CP Crane 115 kV |  | MD | Baltimore County | Active | BGE | 500 | 300 | 300 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 7/8/2023 | [5 empty] | 10/1/2028 |  |  | N | No
PJM | AJ1-038 | Penniman 34.5 kV |  | VA | York | Active | Dominion | 33 | 33 | 33 |  | Capacity | Generation Interconnection | Storage |  |  |  |  | In Progress | [12 empty] | 6/29/2023 | [5 empty] | 12/1/2025 |  |  | N | No