## Sheet1
ISO | Queue Position | Transmission Owner/Developer | Project Name | Interconnection Request Receive Date | MAX Summer MW | MAX Winter MW | Fuel | Nearest Town or County | State | POI Name | Utility | Project Status | Date Updated | Availability of Studies | IA Signed Date | CY/FS Complete Date | Proposed In-Service/Initial Backfeed Date | Proposed Sync Date | Proposed COD
NYISO | 0276 | Homer Solar Energy Center LLC | Homer Solar Energy Center | 2008-01-30 | 90 | 90 | Solar | Cortland | NY | Cortland - Fenner 115kV | NM-NG | IA Completed | 2023-07-31 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 03-2026 | 03-2026 | 04-2026
NYISO | 0396A | New York State Electric & Gas | Wood Street Transformer | 2012-12-14 |  |  | AC | Putnam | NY | Wood St. 345/115kV | NYSEG | Under Construction | 2024-05-31 | SIS |  |  | 12/2024
NYISO | 0429 | Orange & Rockland | North Rockland Station | 2014-02-12 |  |  | AC | Steuben | NY | Line Y88 345kV | ConEd | Under Construction | 2022-03-31 | SIS |  |  | 06/2024
NYISO | 0430 | H.Q. Energy Services U.S. Inc. | Cedar Rapids Transmission | 2014-03-05 |  |  | AC | St. Lawrence | NY | Dennison - Alcoa 115kV | NM-NG | Under Construction | 2019-12-31 | SIS, FS | 2018-10-02 | 2018-03-19 | 10/2021
NYISO | 0495 | Mohawk Solar LLC | Mohawk Solar | 2015-04-02 | 90.5 | 90.5 | Solar | Montgomery | NY | St. Johnsville - Marshville 115kV | NM-NG | IA Completed | 2022-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 06/2027 | 10/2027 | 11/2027
NYISO | 0519 | Canisteo Wind Energy LLC | Canisteo Wind | 2015-11-02 | 289.8 | 289.8 | Wind | Steuben | NY | Bennett 115kV | NYSEG | Accepted Cost Allocation/IA in Progress | 2022-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 10-2026 | 01-2027 | 12-2027
NYISO | 0521 | Bull Run Energy LLC | Bull Run II Wind | 2015-12-15 | 449 | 449 | Wind | Clinton | NY | Patnode-Duley, Ryan-Plattsburgh 230kV | NYPA | Accepted Cost Allocation/IA in Progress | 2022-11-30 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 05-2026 | 12-2026
NYISO | 0522 | NYC Energy LLC | NYC Energy | 2015-12-16 | 79.9 | 79.9 | Energy Storage | Kings | NY | Hudson Avenue East 138kV | ConEd | Accepted Cost Allocation/IA in Progress | 2024-10-31 | FES, SRIS |  |  | 05-2027 | 05-2027 | 06-2027
NYISO | 0535 | Riverhead Solar 2, LLC | Riverhead Solar 2 | 2016-02-23 | 36 | 36 | Solar | Suffolk | NY | Edwards 138kV | LIPA | IA Completed | 2024-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 09-2026 | 12-2026 | 01-2027
NYISO | 0543 | National Grid | Segment B Knickerbocker-PV | 2016-05-04 |  |  | AC | Albany-Dutchess | NY | Greenbush - PV 345kV | NM-NG/NYSEG/ CHGE/ConEd | Under Construction | 2022-04-30 | SIS |  |  | 12/2023
NYISO | 0545 | Sky High Solar, LLC | Sky High Solar | 2016-05-16 | 20 | 20 | Solar | Onondaga | NY | Tilden -Tully Center 115kV | NM-NG | IA Completed | 2022-01-31 | FES, SIS, FS | 2019-10-01 | 2019-09-17 | 06-2025 | 05-2025 | 06-2025
NYISO | 0564 | Rock District Solar, LLC | Rock District Solar | 2016-07-25 | 20 | 20 | Solar | Schoharie | NY | Sharon - Cobleskill 69kV | NM-NG | IA Completed | 2021-08-31 | SIS, FS | 2020-07-10 | 2020-06-03 | 01-2027 | 12-2026 | 02-2027
NYISO | 0565 | Tayandenega Solar, LLC | Tayandenega Solar | 2016-07-25 | 20 | 20 | Solar | Montgomery | NY | St. Johnsville - Inghams 115kV | NM-NG | IA Completed | 2024-07-31 | SIS, FS | 2020-07-01 | 2020-06-03 | 01-2027 | 12-2026 | 02-2027
NYISO | 0566 | New York Power Authority | MA 1 & 2 Rebuild | 2016-08-04 |  |  | AC | St. Lawrence-Lewis | NY | Moses & Adirondack 230kV | NYPA | Under Construction | 2022-09-30 | SIS |  |  | 6-2023
NYISO | 0571 | Heritage Wind, LLC | Heritage Wind | 2016-09-01 | 200.1 | 200.1 | Wind | Genesee | NY | Lockport - Mortimer 115kV | NM-NG | IA Completed | 2023-09-30 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 06-2026 | 09-2026
NYISO | 0572 | Hecate Energy Greene 1 LLC | Greene County 1 | 2016-09-06 | 20 | 20 | Solar | Greene | NY | Coxsackie - North Catskill 69kV | CHG&E | IA Completed | 2022-01-31 | SIS, FS | 2020-02-18 | 2020-01-24 | 03-2025 | 03-2025 | 05-2025
NYISO | 0573 | Hecate Energy Greene 2 LLC | Greene County 2 | 2016-09-06 | 10 | 10 | Solar | Greene | NY | Coxsackie 13.8kV | CHG&E | IA Completed | 2022-01-31 | SIS, FS | 2020-02-18 | 2020-01-24 | 03-2025 | 03-2025 | 05-2025
NYISO | 0575 | Little Pond Solar, LLC | Little Pond Solar | 2016-09-16 | 20 | 20 | Solar | Orange | NY | Mongaup - Shoemaker 69kV | O&R | IA Completed | 2024-02-29 | FES, SIS, FS | 2021-01-29 | 2020-12-16 | 01-2025 | 01-2025 | 01-2025
NYISO | 0580 | Genesee County Economic Devel. | WNY STAMP | 2016-09-27 | 300 | 300 | Load | Genesee | NY | Kintigh/Niagara - New Rochester 345kV | NYPA | Under Construction | 2023-07-31 | SIS |  |  | 12/2024
NYISO | 0581 | SunEast Hills Solar LLC | Hills Solar | 2016-10-06 | 20 | 20 | Solar | Herkimer | NY | Fairfield - Inghams 115kV | NM-NG | IA Completed | 2024-05-31 | FES, SIS, FS | 2020-04-07 | 2020-02-11 | 10-2026 | 06-2026 | 12-2026
NYISO | 0584 | SunEast Dog Corners Solar LLC | Dog Corners Solar | 2016-11-02 | 20 | 20 | Solar | Cayuga | NY | Aurora 34.5kV | NYSEG | IA Completed | 2024-05-31 | SIS, FS | 2019-06-21 | 2019-05-08 | 03-2026 | 03-2026 | 04-2026
NYISO | 0586 | SunEast Watkins Road Solar LLC | Watkins Rd Solar | 2016-11-08 | 20 | 20 | Solar | Herkimer | NY | Watkins Rd - Ilion 115kV | NM-NG | IA Completed | 2024-04-30 | SIS, FS | 2020-02-18 | 2019-11-25 | 03-2026 | 02-2026 | 07-2026
NYISO | 0590 | SunEast Scipio Solar LLC. | Scipio Solar | 2016-12-02 | 18 | 18 | Solar | Cayuga | NY | Scipio 34.5kV | NYSEG | IA Completed | 2023-06-30 | SIS, FS | 2019-05-22 | 2019-03-21 | 09-2024 | 09-2024 | 12-2024
NYISO | 0591 | SunEast Highview Solar LLC | Highview Solar | 2016-12-02 | 20 | 20 | Solar | Wyoming | NY | South Perry 34.5kV | NYSEG | IA Completed | 2024-05-31 | SIS, FS | 2021-02-08 | 2021-02-08 | 02-2025 | 01-2025 | 02-2025
NYISO | 0592 | Niagara NY Solar LLC | Niagara Solar | 2016-12-02 | 20 | 20 | Solar | Wyoming | NY | Bennington 34.5kV | NYSEG | IA Completed | 2024-09-30 | SIS, FS | 2019-05-22 | 2019-04-18 | 03-2025 | 04-2025 | 12-2026
NYISO | 0596 | Alle-Catt Wind Energy LLC | Alle Catt II Wind | 2017-01-04 | 339.1 | 339.1 | Wind | Cattaraugus | NY | Stolle Rd - Five Mile Rd 345kV | NM-NG | Under Construction | 2022-09-30 | SRIS, FS | 2021-02-08 | 2021-02-08 | 05-2026 | 05-2026 | 12-2026
NYISO | 0617 | Watkins Glen Solar Energy Center, LLC | Watkins Glen Solar | 2017-03-27 | 50 | 50 | Solar | Schuyler | NY | Bath - Montour Falls 115kV | NYSEG | IA Completed | 2024-04-30 | SRIS, FS | 2020-12-04 | 2021-02-08 | 12-2024 | 12-2024 | 01-2025
NYISO | 0620 | North Side Energy Center, LLC | North Side Solar | 2017-03-27 | 180 | 180 | Solar | St. Lawrence | NY | Massena - Moses 230kV | NYPA | IA Completed | 2022-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 10-2024 | 11-2024 | 12-2024
NYISO | 0631 | CHPE LLC | NS Power Express | 2017-05-02 | 1000 | 1000 | DC | Quebec - New York | NY | Astoria Annex 345kV | NYPA | Under Construction | 2023-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 05-2026 | 05-2026 | 05-2026
NYISO | 0637 | Flint Mine Solar LLC | Flint Mine Solar | 2017-06-29 | 100 | 100 | Solar | Greene | NY | LaFarge - Pleasant Valley 115kV, Feura Bush - North Catskill 115kV | NM-NG | IA Completed | 2022-09-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2025 | 12-2025 | 5-2026
NYISO | 0644 | Hecate Energy Columbia County 1, LLC | Columbia County 1 | 2017-07-26 | 60 | 60 | Solar | Columbia | NY | Craryville 115kV | NYSEG | IA Completed | 2024-06-30 | FES, SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2026 | 12-2026 | 2-2027
NYISO | 0670 | SunEast Skyline Solar LLC | SunEast Skyline Solar LLC | 2017-09-21 | 20 | 20 | Solar | Westmoreland | NY | Campus Rd - Clinton 46kV | NM-NG | IA Completed | 2023-07-31 | FES, SIS, FS | 2020-08-13 | 2020-07-31 | 11/2027 | 10/2027 | 4/2028
NYISO | 0683 | KCE NY 2, LLC | KCE NY 2 | 2018-01-18 | 200 | 200 | Energy Storage | Montgomery | NY | Coldenham 115kV | CHG&E | IA Completed | 2024-03-31 | SRIS, FS | 2021-03-16 | 2021-02-08 | 05-2027 | 05-2027 | 06-2027
NYISO | 0704 | Bear Ridge Solar, LLC | Bear Ridge Solar | 2018-03-20 | 100 | 100 | Solar | Niagara | NY | Mountain- Lockport 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS, FS | 2021-02-08 | 2021-02-08 | 01-2025 | 02-2025 | 02-2025
NYISO | 0706 | High Bridge Wind, LLC | High Bridge Wind | 2018-04-25 | 100.8 | 100.8 | Wind | Chenango | NY | E. Norwich - Jennison 115kV | NYSEG | IA Completed | 2024-05-31 | SRIS, FS |  | 2021-02-08 | 12-2024 | 12-2024 | 02-2025
NYISO | 0710 | Horseshoe Solar Energy LLC | Horseshoe Solar | 2018-05-29 | 180 | 180 | Solar | Livingston | NY | Golah 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-03-31 | FES, FS | 2023-01-11 | 2023-01-11 | 12-2025 | 11-2025 | 12-2025
NYISO | 0716 | EDF Renewables Development, Inc. | Moraine Solar Energy Center | 2018-06-04 | 93.5 | 93.5 | Solar | Allegany | NY | Moraine 115kV | NYSEG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | FES, SRIS |  |  | 04-2027 | 04-2027 | 10-2027
NYISO | 0720 | Trelina Solar Energy Center, LLC | Trelina Solar Energy Center | 2018-06-07 | 79.8 | 79.8 | Solar | Seneca | NY | Border City - Station 168 115 KV | NYSEG | IA Completed | 2024-04-30 | SRIS, FS | 2021-02-08 | 2021-02-08 | 12-2024 | 12-2024 | 01-2025
NYISO | 0721 | Excelsior Energy Center, LLC | Excelsior Energy Center | 2018-06-07 | 280 | 280 | Solar | Genesee | NY | Dysinger - N. Rochester 345kV | NYPA | IA Completed | 2022-09-30 | SRIS, FS | 2021-01-22 | 2021-02-08 | 12-2024 | 12-2024 | 02-2025
NYISO | 0734 | ELP Ticonderoga Solar LLC | Ticonderoga Solar | 2018-06-12 | 20 | 20 | Solar | Essex | NY | Ticonderoga 115kV - Republic Line 2 | NM-NG | IA Completed | 2024-05-31 | FES, SIS, FS | 2021-03-18 | 2021-07-31 | 01-2025 | 02-2025 | 03-2025
NYISO | 0737 | Empire Offshore Wind LLC | Empire Wind 1 | 2018-06-12 | 816 | 816 | Off-Shore Wind | Kings | NY | Gowanus 345kV | ConEd | IA Completed | 2024-01-31 | SRIS, FS | 2021-02-08 | 2021-02-08 | 06-2025 | 11-2025 | 12-2026
NYISO | 0744 | Mitchell Energy Facility, LLC | Magruder BESS | 2018-07-18 | 20 | 20 | Energy Storage | Ulster | NY | East Walden - Modena 115kV | CHG&E | IA Completed | 2024-05-31 | SIS, FS | 2021-04-06 | 2021-03-04 | 09-2024 | 10-2024 | 01-2025
NYISO | 0766 | Sunrise Wind LLC | Sunrise Wind | 2018-09-28 | 880 | 880 | Off-Shore Wind | Suffolk | NY | Holbrook 138kV & West Bus 138kV | LIPA | IA Completed | 2023-09-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 06-2025 | 08-2025 | 03-2026
NYISO | 0774 | EDF Renewables Development, Inc. | Tracy Solar Energy Centre | 2018-10-18 | 119 | 119 | Solar | Jefferson | NY | Thousand Island - Lyme 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 05-2028 | 05-2028 | 11-2028
NYISO | 0776 | Greenidge Generation LLC | Greenidge Load | 2018-10-22 | 60 | 60 | Load | Yates | NY | Greenidge 115kV | NYSEG | FS Pending | 2024-04-30 | SIS |  |  | 06-2025
NYISO | 0777 | White Creek Solar, LLC | White Creek Solar | 2018-11-01 | 135 | 135 | Solar | Livingston | NY | Sta 82 - Sta 128 115kV | RG&E | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 10-2027 | 10-2027 | 11-2027
NYISO | 0783 | ConnectGen Chautauqua County LLC | South Ripley Solar and BESS | 2018-12-07 | 270 | 270 | Energy Storage + Solar | Chautauqua | NY | South Ripley Substation 230kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-07-31 | FES, SRIS, FS | 2023-01-11 | 2023-01-11 | 11-2026 | 11-2026 | 01-2027
NYISO | 0787 | Levy Grid, LLC | Levy Grid, LLC | 2018-12-20 | 150 | 150 | Energy Storage | Erie | NY | Gardenville Subsation 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2022-11-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 08-2025 | 08-2025 | 08-2025
NYISO | 0800 | EDF Renewables Development, Inc. | Rich Road Solar Energy Center | 2019-02-20 | 240 | 240 | Energy Storage + Solar | St. Lawrence | NY | Moses - Adirondack 230 kV Line #2 (MA2) | NYPA | Accepted Cost Allocation/IA in Progress | 2024-10-31 | FES, SRIS |  |  | 10-2027 | 10-2027 | 04-2028
NYISO | 0801 | Prattsburgh Wind, LLC | Prattsburgh Wind Farm | 2019-02-21 | 147 | 147 | Wind | Steuben | NY | Stoney Ridge - Canadaigua 230kV | NYSEG | Accepted Cost Allocation/IA in Progress | 2022-07-31 | SRIS, FS | 2023-01-11 | 2023-01-11 | 10-2025 | 10-2025 | 12-2025
NYISO | 0804 | KCE NY 10, LLC | KCE NY 10 | 2019-03-22 | 20 | 20 | Energy Storage | Erie | NY | Erie Substation 34.5kV | NYSEG | IA Completed | 2024-04-30 | FES, SIS, FS | 2022-10-20 | 2022-04-28 | 08-2026 | 08-2026 | 10-2026
NYISO | 0805 | Oxbow Hill Solar, LLC | Oxbow Hill Solar | 2019-03-22 | 140 | 140 | Solar | Madison | NY | Fenner 115kV Substation | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-04-30 | FES, FS | 2023-02-09 | 2023-01-11 | 10-2025 | 10-2025 | 12-2026
NYISO | 0807 | SunEast Hilltop Solar LLC | Hilltop Solar | 2019-03-28 | 20 | 20 | Solar | Rensselaer | NY | Eastover - Schaghticoke 115kV | NM-NG | IA Completed | 2024-09-30 | SIS, FS | 2021-04-07 | 2021-02-23 | 04/2028 | 03/2028 | 05/2028
NYISO | 0811 | Hecate Energy Cider Solar LLC | Cider Solar | 2019-04-03 | 500 | 500 | Solar | Genesee | NY | Dysinger - New Rochester 345kV | NYPA | IA Completed | 2024-06-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 05/2026 | 05/2026 | 01-2027
NYISO | 0815 | Bayonne Energy Center | Bayonne Energy Center III | 2019-04-05 | 49.8 | 49.8 | Energy Storage | Kings | NY | Gowanus 345kV | ConEd | Accepted Cost Allocation/IA in Progress | 2024-09-30 | SRIS, FS | 2023-04-25 | 2023-01-11 | 07-2026 | 08-2026 | 09-2026
NYISO | 0825 | Setauket Energy Storage, LLC | Setauket Energy Storage | 2019-04-15 | 65.3 | 65.3 | Energy Storage | Suffolk | NY | Port Jefferson - Terryville 69kV | LIPA | FS in Progress | 2023-05-31 | FES, SRIS |  |  | 01-2028 | 03-2028 | 04-2028
NYISO | 0827 | GB Arthur Kill Storage LLC | Arthur Kill Energy Storage 1 | 2019-04-22 | 15 | 15 | Energy Storage | Richmond | NY | Fresh Kills 13.8kV | ConEd | IA Completed | 2023-11-30 | FS | 2022-07-07 | 2022-01-20 | 04-2025 | 07-2025 | 09-2025
NYISO | 0828 | SunEast Valley Solar LLC | Valley Solar | 2019-04-24 | 20 | 20 | Solar | Tioga | NY | Owego 34.5kV Substation | NYSEG | IA Completed | 2022-04-30 | SIS, FS | 2021-01-22 | 2020-11-03 | 08-2024 | 09-2024 | 11-2024
NYISO | 0832 | Granada Solar, LLC | CS Hawthorn Solar | 2019-05-06 | 20 | 20 | Solar | Rensselaer | NY | North Troy - Hoosick 115kV | NM-NG | IA Completed | 2024-05-31 | FES, FS | 2022-07-13 | 2022-06-27 | 05-2026 | 04-2026 | 12-2026
NYISO | 0833 | Dolan Solar, LLC | Dolan Solar | 2019-05-06 | 20 | 20 | Solar | Washington | NY | Battenkill - Mohican 115kV | NM-NG | IA Completed | 2024-05-31 | SIS, FS | 2021-04-13 | 2021-03-01 | 03-2025 | 02-2025 | 12-2026
NYISO | 0834 | Astoria Generating Company, LP | Luyster Creek Energy Storage 2 | 2019-05-07 | 79 | 79 | Energy Storage | Queens | NY | Astoria West 138kV | ConEd | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 01-2027 | 01-2027 | 05-2027
NYISO | 0835 | Astoria Generating Company, LP | Luyster Creek Energy Storage 1 | 2019-05-07 | 56.3 | 57.3 | Energy Storage | Queens | NY | Astoria West 138kV | ConEd | Accepted Cost Allocation/IA in Progress | 2023-01-31 | SRIS, FS | 2023-02-22 | 2023-01-11 | 02-2026 | 03-2026 | 05-2026
NYISO | 0843 | Sandy Creek Solar LLC | NY37 Solar | 2019-05-17 | 20 | 20 | Solar | Jefferson | NY | Coffeen - West Adams 115kV Substation | NM-NG | Accepted Cost Allocation/IA in Progress | 2023-05-31 | SIS, FS | 2023-05-17 | 2023-04-04 | 11-2025 | 10-2025 | 11-2025
NYISO | 0848 | SunEast Fairway Solar LLC | Fairway Solar | 2019-05-20 | 20 | 20 | Solar | St. Lawrence | NY | McIntyre - Corning 115kV (Line#6) | NM-NG | IA Completed | 2022-03-31 | SIS, FS | 2021-05-10 | 2021-05-05 | 02-2025 | 02-2025 | 03-2025
NYISO | 0850 | Cayuga Operating Company, LLC | Cayuga Load | 2019-05-21 | 50 | 50 | Load | Cayuga | NY | Milliken 115kV | NYSEG | FS Pending | 2024-04-30 | SIS |  |  | 12-2026
NYISO | 0855 | Bald Mountain Solar LLC | NY13 Solar | 2019-05-24 | 20 | 20 | Solar | Washington | NY | Mohican - Schaghticoke 115kV | NM-NG | IA Completed | 2022-04-30 | SIS, FS | 2021-10-07 | 2021-08-27 | 06-2025 | 06-2025 | 06-2025
NYISO | 0863 | Highbanks Solar LLC | Highbanks Solar | 2019-05-29 | 20 | 20 | Solar | Livingston | NY | S158 High banks 34.5 kV | RG&E | Accepted Cost Allocation/IA in Progress | 2024-04-30 | SIS, FS | 2022-10-17 | 2022-08-05 | 12-2025 | 01-2026 | 02-2026
NYISO | 0864 | Greens Corners Solar LLC | NY38 Solar | 2019-05-29 | 120 | 120 | Solar | Jefferson | NY | Coffeen - West Adams 115kV | NM-NG | IA Completed | 2024-04-30 | SRIS, FS | 2023-01-11 | 2023-01-11 | 12-2026 | 11-2026 | 12-2026
NYISO | 0865 | SunEast Flat Hill Solar LLC | Flat Hill Solar | 2019-05-31 | 20 | 20 | Solar | Herkimer | NY | Inghams-Valley 46kV Line 27 | NM-NG | IA Completed | 2023-08-31 | SIS, FS | 2022-09-15 | 2022-08-19 | 11-2025 | 11-2025 | 12-2025
NYISO | 0880 | Brookside Solar, LLC | Brookside Solar | 2019-06-10 | 100 | 100 | Solar | Franklin | NY | Chateaugay - Willis 115kV | NYSEG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 01-2027 | 01-2027 | 06-2027
NYISO | 0882 | Riverside Solar, LLC | Riverside Solar | 2019-06-10 | 100 | 100 | Solar | Jefferson | NY | Lyme Substation 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | FES, SRIS |  |  | 09-2027 | 09-2027 | 12-2027
NYISO | 0883 | Garnet Energy Center, LLC | Garnet Energy Center | 2019-06-11 | 200 | 200 | Solar | Cayuga | NY | Pannell - Clay 345kV | NYPA | Accepted Cost Allocation/IA in Progress | 2023-01-31 | FS | 2023-01-11 | 2023-01-11 | 10-2025 | 10-2025 | 11-2025
NYISO | 0885 | SunEast Grassy Knoll Solar LLC | Grassy Knoll Solar | 2019-06-12 | 20 | 20 | Solar | Herkimer | NY | Watkins Rd - Inghams 115kV | NM-NG | IA Completed | 2023-08-31 | SIS, FS | 2022-09-15 | 2022-08-15 | 11-2025 | 11-2025 | 12-2025
NYISO | 0887 | CHPE LLC | CH Uprate | 2019-06-12 | 250 | 250 | DC | Quebec-NY | NY | Astoria Annex 345kV | NYPA | Under Construction | 2023-06-30 | SRIS, FS | 2022-07-08 | 2023-01-11 | 05-2026 | 05-2026 | 05-2026
NYISO | 0899 | Sithe/Independence Power Partners, LP | Scriba-Volney Series Reactor | 2019-08-02 |  |  | AC | Oswego | NY | Volney - Scriba 345 kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-02-08 | SIS |  |  | 03-2026
NYISO | 0907 | Harlem River ESS, LLC | Harlem River Yard | 2019-09-04 | 79.9 | 79.9 | Energy Storage | Queens | NY | Hell Gate 138kV | NYPA | Accepted Cost Allocation/IA in Progress | 2023-01-31 | SRIS, FS | 2023-02-10 | 2023-01-11 | 10-2026 | 10-2026 | 12-2026
NYISO | 0930 | Astoria Generating Company, LP | Astoria BES to 27kV North Queens | 2019-10-25 | 15 | 15 | Energy Storage | Queens | NY | North Queens 27kV | ConEd | Accepted Cost Allocation/IA in Progress | 2024-05-31 | SIS, FS |  | 2024-04-16 | 04-2025 | 05-2025 | 12-2025
NYISO | 0931 | East River ESS, LLC | Astoria Energy Storage | 2019-10-28 | 100 | 100 | Energy Storage | Queens | NY | Astoria West 138kV | ConEd | Accepted Cost Allocation/IA in Progress | 2023-03-31 | SRIS, FS | 2023-01-11 | 2023-01-11 | 10-2026 | 04-2026 | 03-2026
NYISO | 0932 | Hatchery Solar LLC | Hatchery Solar | 2019-10-29 | 20 | 20 | Solar | Livingston | NY | Caledonia - Golah 34.5 kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-11-30 | SIS, FS |  | 2024-10-10 | 04-2025 | 05-2025 | 05-2025
NYISO | 0950 | Hemlock Ridge Solar LLC | Hemlock Ridge Solar | 2019-11-21 | 200 | 200 | Solar | Orleans | NY | Lockport - Mortimer 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 06-2027 | 06-2027 | 08-2027
NYISO | 0953 | Sugar Maple Solar, LLC | Sugar Maple Solar | 2019-12-05 | 125 | 125 | Solar | Lewis | NY | North Carthage - Taylorville #8 and Black River - Taylorville #2 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 09-2027 | 09-2027 | 12-2027
NYISO | 0956 | Holtsville Energy Storage, LLC | Holtsville 138kV Energy Storage | 2019-12-10 | 110 | 110 | Energy Storage | Suffolk | NY | West Bus 138 kV | LIPA | IA Completed | 2024-03-31 | SRIS, FS | 2023-01-11 | 2023-01-11 | 06-2026 | 07-2026 | 09-2026
NYISO | 0957 | Holbrook Energy Storage, LLC | Holbrook Energy Storage | 2019-12-10 | 76.8 | 76.8 | Energy Storage | Suffolk | NY | Holtsville - Patchogue 69kV | LIPA | FS in Progress | 2024-01-31 | SRIS |  |  | 06-2027 | 10-2027 | 12-2027
NYISO | 0960 | SWEB Development USA, LLC | Cobleskill Solar | 2019-12-12 | 20 | 20 | Solar | Schoharie | NY | Cobleskill - Schoharie 69KV | NM-NG | FS in Progress | 2023-10-31 | FES, SIS |  |  | 11-2025 | 11-2025 | 12-2025
NYISO | 0965 | Yaphank Energy Storage, LLC | Yaphank Energy Storage | 2019-12-21 | 76.8 | 77.6 | Energy Storage | Suffolk | NY | William Floyd - Brookhaven 69kV | LIPA | IA Completed | 2024-06-30 | FS | 2024-05-31 | 2023-01-11 | 03-2026 | 08-2026 | 09-2026
NYISO | 0967 | KCE NY 5 LLC | KCE NY 5 | 2019-12-27 | 94 | 94 | Energy Storage | Ulster | NY | Ohioville 115 kV | CHG&E | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 11-2027 | 11-2027 | 12-2027
NYISO | 0971 | Savion, LLC | East Setauket Energy Storage | 2020-01-10 | 125 | 125 | Energy Storage | Suffolk | NY | Holbrook - Miller Place 138kV | LIPA | FS in Progress | 2023-12-31 |  |  |  | 02-2027 | 03-2027 | 04-2027
NYISO | 0972 | SWEB Development USA, LLC | Warner Hill Solar | 2020-01-10 | 20 | 20 | Solar | Schoharie | NY | Middleburg Tap - Middleburg 69kV | NM-NG | FS in Progress | 2023-09-30 | FES, SIS |  |  | 03-2026 | 03-2026 | 05-2026
NYISO | 0979 | North Country Data Center | North Country Data Center | 2020-01-22 | 176 | 176 | Load | St. Lawrence | NY | Reynolds 115kV | NYPA | SRIS/SIS Approved | 2023-07-31 | SIS |  |  | 12-2024
NYISO | 0987 | Sunrise Wind LLC | Sunrise Wind II | 2020-01-29 | 44 | 44 | Off-Shore Wind | Suffolk | NY | Holbrook 138kV | LIPA | IA Completed | 2023-09-30 | FS | 2023-01-11 | 2023-01-11 | 06-2025 | 08-2025 | 03-2026
NYISO | 0995 | Alabama Solar Park LLC | Alabama Solar Park LLC | 2020-02-27 | 130 | 130 | Solar | Genesee | NY | Lockport - Batavia 115kV (Line#112) | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 |  |  |  | 07-2028 | 07-2028 | 10-2028
NYISO | 1000 | SED NY Holdings LLC | SunEast Flat Stone Solar LLC | 2020-03-18 | 20 | 20 | Solar | Oneida | NY | Oneida - Rome 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-03-31 | SIS, FS |  | 2024-03-14 | 09-2026 | 09-2026 | 11-2026
NYISO | 1003 | Clear View LLC | Clear View Solar | 2020-04-06 | 20 | 20 | Solar | Steuben | NY | Eelpot Road 34.5 kV | NYSEG | IA Completed | 2024-05-31 | SIS, FS | 2022-09-06 | 2022-07-08 | 11-2025 | 10-2025 | 12-2025
NYISO | 1007 | NYC Energy | NYC Energy LLC - Phase 2 | 2020-04-22 | 220.1 | 220.1 | Energy Storage | Kings | NY | Hudson Ave 138 kV | ConEd | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 05-2027 | 05-2027 | 06-2027
NYISO | 1009 | Yellow Barn Solar, LLC | Yellow Barn Solar | 2020-04-30 | 160 | 160 | Solar | Tompkins | NY | Milliken - Etna 115 kV line #975 | NYSEG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 11-2025 | 11-2025 | 12-2025
NYISO | 1012 | Suffolk County Energy Storage II | Suffolk County Storage II | 2020-05-04 | 76.8 | 76.8 | Energy Storage | Suffolk | NY | Southold 69 kV | LIPA | FS in Progress | 2023-05-31 | FES, SRIS |  |  | 01-2028 | 03-2028 | 04-2028
NYISO | 1015 | Granada Solar, LLC | Somers Solar, LLC | 2020-05-05 | 20 | 20 | Solar | Washington | NY | Mohican - Battenkill 115kV | NM-NG | IA Completed | 2024-12-31 | FS |  | 2024-03-14 | 09-2026 | 10-2026 | 12-2026
NYISO | 1031 | ConnectGen Montgomery County LLC | Mill Point Solar | 2020-06-18 | 250 | 250 | Energy Storage + Solar | Montgomery | NY | Marcy - New Scotland 345kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 07-2028 | 07-2028 | 12-2028
NYISO | 1039 | SED NY Holdings LLC | Morris Solar | 2021-01-06 | 20 | 20 | Solar | St. Lawrence | NY | Battle Hill - Balmat 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-03-31 | SIS, FS |  | 2024-03-14 | 10-2025 | 11-2025 | 12-2025
NYISO | 1047 | SED NY Holdings LLC | Millers Grove Solar | 2020-07-09 | 20 | 20 | Solar | Herkimer | NY | Porter - Watkins 115kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-05-31 | SIS, FS |  | 2024-03-28 | 09-2026 | 09-2026 | 12-2026
NYISO | 1051 | SED NY Holding LLC | Transit Solar | 2020-07-21 | 20 | 20 | Solar | Genesee | NY | S.E Batavia - Golah 115kV | NM-NG | FS in Progress | 2024-03-31 | SIS, FS |  | 2024-03-14 | 08-2025 | 09-2025 | 12-2025
NYISO | 1061 | ACE DEVCO NC, LLC | Teele | 2020-07-31 | 19.8 | 19.8 | Solar | St. Lawrence | NY | Alcoa - N. Ogdensburg 115 kV | NM-NG | FS in Progress | 2024-01-31 | SIS |  |  | 03-2026 | 05-2026 | 06-2026
NYISO | 1079 | Somerset Solar, LLC | Somerset Solar | 2020-08-18 | 125 | 125 | Solar | Niagara | NY | Kintigh 345 kV | NYSEG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 01-2027 | 01-2027 | 03-2027
NYISO | 1080 | Mineral Basin Solar Power, LLC | Mineral Basin Solar Power | 2020-08-21 | 401.6 | 401.6 | Solar | Clearfield | PA | Homer City - Mainesburg 345KV | NYSEG | FS in Progress | 2024-10-31 | SRIS |  |  | 10-2027 | 10-2027 | 05-2028
NYISO | 1089 | SED NY Holding LLC | Flat Creek Solar | 2020-09-04 | 200 | 200 | Solar | Montgomery | NY | Edic to Princetown 345kV Line 352 | NYPA | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 10-2028 | 10-2028 | 11-2028
NYISO | 1096 | Northland Power U.S. Projects | Alfred Oaks Solar | 2020-09-14 | 100 | 100 | Energy Storage + Solar | Allegany | NY | Andover - Palmeter 115 kV, Line 932 | NYSEG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 09-2027 | 09-2027 | 11-2027
NYISO | 1113 | Caithness LI Energy Storage, LLC | CLIES 20 MW | 2020-11-18 | 20 | 20 | Energy Storage | Suffolk | NY | Sills Road 138 kV | LIPA | Accepted Cost Allocation/IA in Progress | 2024-07-31 | SIS, FS |  | 2024-06-13 | 12-2025 | 10-2025 | 12-2025
NYISO | 1115 | SED NY Holdings LLC | Flat Creek Solar 2 | 2020-11-23 | 100 | 100 | Solar | Montgomery | NY | Edic - Princetown 345 kV Line# 352 | NYPA | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 10-2028 | 10-2028 | 11-2028
NYISO | 1117 | Caithness LI Energy Storage, LLC | CLIES 70MW | 2020-11-25 | 70 | 70 | Energy Storage | Suffolk | NY | Sills Road 138kV | LIPA | FS in Progress | 2024-09-30 | SRIS |  |  | 12-2026 | 12-2026 | 12-2026
NYISO | 1122 | Microgrid Networks, LLC | East Fishkill | 2020-12-11 | 205 | 205 | Energy Storage | Dutchess | NY | Shenandoah 115kV | CHG&E | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 05-2028 | 05-2028 | 11-2028
NYISO | 1123 | KCE NY 29, LLC | KCE NY 29 | 2020-12-14 | 150 | 150 | Energy Storage | Suffolk | NY | Kings 138 kV | LIPA | Accepted Cost Allocation/IA in Progress | 2024-10-31 |  |  |  | 09-2027 | 09-2027 | 10-2027
NYISO | 1125 | New York Power Authority and National Grid | Northern New York Priority Transmission Project (NNYPTP) | 2020-12-22 |  |  | AC | St. Lawrence-Lewis | NY | 1. Moses 230 kV substation 2. Haverstock 345 kV sub (new) 3. Massena 230 kV substation 4. Adirondack 345 kV sub (new) 5. Willis 230 kV substation 6. Ryan & Patnode 230 kV substations 7. Chases Lake 345 kV sub (new) 8. Marcy 345 kV sub 9. Edic 345 kV sub | NYPA, NM-NG | Accepted Cost Allocation/IA in Progress | 2023-05-31 | FS |  | 2023-02-14 | 12-2025
NYISO | 1130 | Liberty Renewables Inc. | Hoffman Falls Wind | 2021-01-27 | 72 | 72 | Wind | Madison | NY | Cortland - Fenner 115kV Line #3 | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 |  |  |  | 10-2027 | 10-2027 | 12-2027
NYISO | 1148 | Liberty Renewables Inc. | Agricola Wind | 2021-03-10 | 97 | 97 | Wind | Cayuga | NY | Milliken to Wright Ave 115 kV line #973 | NYSEG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 10-2027 | 10-2027 | 12-2027
NYISO | 1150 | Moss Ridge Solar 1, LLC | Moss Ridge Solar | 2021-03-16 | 60 | 60 | Solar | St. Lawrence | NY | Corning - Battle Hill 115 kV line #4 | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 09-2028 | 10-2028 | 11-2028
NYISO | 1151 | York Run Solar, LLC | York Run Solar | 2021-03-18 | 90 | 90 | Solar | Chautauqua | NY | Falconer - Warren 115 kV line #171 | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 05-2026 | 06-2026 | 08-2026
NYISO | 1156 | Green Power Energy, LLC | Cody Road Wind Farm | 2021-04-08 | 19.9 | 19.9 | Wind | Madison | NY | Cortland - Fenner Line #3 115 kV | NM-NG | FS in Progress | 2024-03-31 | FES, SIS |  |  | 07-2025 | 07-2025 | 07-2025
NYISO | 1166 | BR Project 1 LLC | BR Benson Mines Solar | 2021-05-07 | 12.1 | 12.1 | Solar | St. Lawrence | NY | Brown's Falls to Newton Falls #22 34.5kV Line | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-11-30 | SIS, FS |  | 2024-10-16 | 07-2026 | 08-2026 | 10-2026
NYISO | 1171 | ELP Stuyvesant Solar LLC | ELP Stuyvesant Solar | 2021-05-14 | 20 | 20 | Solar | Columbia | NY | Valkin - Falls Park 115 kV line #19 | Transco | FS in Progress | 2024-01-31 | SIS |  |  | 08-2026 | 08-2026 | 11-2026
NYISO | 1183 | Fort Covington Solar LLC | NY125A - Fort Covington Solar | 2021-05-20 | 250 | 250 | Solar | Franklin | NY | Moses-Willis 230 kV (MW1) | NYPA | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 07-2027 | 07-2027 | 08-2027
NYISO | 1184 | Boralex US Development | NY125B - Two Rivers Solar | 2021-05-20 | 200 | 200 | Solar | St-Lawrence | NY | Moses-Willis 230kV (MW2) | NYPA | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 07-2027 | 07-2027 | 08-2027
NYISO | 1188 | North Seneca Solar Project | North Seneca Solar Project, LLC | 2021-05-27 | 105 | 105 | Solar | Seneca | NY | Hooks Road - Elbridge 115kV line#7 | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 06-2027 | 06-2027 | 09-2027
NYISO | 1194 | Crane Brook Solar Project | Crane Brook Solar Project, LLC | 2021-06-03 | 130 | 130 | Solar | Cayuga | NY | State St - Clinton Corn 115kV Line | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 07-2027 | 08-2027 | 09-2027
NYISO | 1213 | Petawatt Holdings, Inc. | St Lawrence Data and Agricultural Center | 2021-06-28 | 200 | 200 | Load | St. Lawrence | NY | Dennison 115kV substation | NM-NG | SRIS/SIS Approved | 2023-01-14 | SIS |  |  | 01-2026
NYISO | 1227 | Nexamp Solar | 18405 Scotch Ridge | 2021-08-04 | 20 | 20 | Solar | Schenectady | NY | Rotterdam-Schoharie 69kV line#18 | NM-NG | FS in Progress | 2024-03-31 | SIS |  |  | 09-2025 | 10-2025 | 12-2025
NYISO | 1237 | Sugar Maple Solar | Sugar Maple Energy Storage | 2021-08-24 | 20 | 20 | Energy Storage | Jefferson | NY | North Carthage-Taylorville #8 and Black River-Taylorville #2 115 kV lines | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SIS |  |  | 06-2026 | 09-2026 | 12-2026
NYISO | 1254 | Barrett Hempstead Battery Storage | Barrett Hempstead Battery Storage | 2021-09-22 | 40 | 40 | Energy Storage | Nassau | NY | Barrett to Long Beach 33 kV circuit No 1(33-224) | LIPA | FS in Progress | 2023-05-31 | SRIS |  |  | 12-2024 | 01-2025 | 03-2025
NYISO | 1255 | Holtsville Brookhaven Battery Storage | Holtsville Brookhaven Battery Storage | 2021-09-22 | 79.9 | 79.9 | Energy Storage | Suffolk | NY | Line 69-849 from West Yaphank to North Bellport | LIPA | FS in Progress | 2023-04-30 | SRIS |  |  | 12-2025 | 01-2026 | 03-2026
NYISO | 1256 | Canal Southampton Battery Storage | Canal Southampton Battery Storage | 2021-09-22 | 100 | 100 | Energy Storage | Suffolk | NY | Canal Substation 138kV | LIPA | FS in Progress | 2023-05-31 | SRIS |  |  | 12-2024 | 01-2025 | 03-2025
NYISO | 1257 | Edwards Calverton Battery Storage | Edwards Calverton Battery Storage | 2021-09-22 | 60 | 60 | Energy Storage | Suffolk | NY | Edwards Avenue Substation at 138 kV | LIPA | FS in Progress | 2023-05-31 | SRIS |  |  | 12-2024 | 01-2025 | 03-2025
NYISO | 1288 | Clean Path New York LLC | CPNY-X | 2021-11-23 | 1300 | 1300 | DC | Delaware, Queens | NY | Fraser 345 kV and Rainey 345 kV substations | NYSEG, ConEd | Accepted Cost Allocation/IA in Progress | 2024-10-31 | SRIS |  |  | 06-2028 | 06-2028 | 12-2028
NYISO | 1289 | New York Power Authority / New York Transco LLC. | Propel NY Energy - Alternate Solution 5 | 2021-10-11 |  |  | AC | Nassau, Queens, Bronx, Westchester | NY | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | LIPA, ConEd, NYPA | FS in Progress | 2024-12-31 | SIS |  |  | 12-2028
NYISO | 1308 | New York Power Authority | Richmond Spoke | 2021-12-02 |  |  | AC | Richmond | NY | Goethals - Gowanus 345 kV | ConEd | SRIS/SIS Approved | 2022-07-31 | SIS |  |  | 12-2030
NYISO | 1313 | Saturn Energy Storage LLC | Queensbury BESS | 2021-12-12 | 20 | 20 | Energy Storage | Warren | NY | Queensbury 34.5 kV substation | NM-NG | FS in Progress | 2024-05-31 | SIS |  |  | 09-2026 | 11-2026 | 12-2026
NYISO | 1315 | Sabey Data Center Properties, LLC | SDC St. Lawrence | 2021-12-20 | 120 | 120 | Load | St. Lawrence | NY | Moses-Reynolds MRG-1 and Moses-Reynolds MRG-2 at 115kV | NYPA | SRIS/SIS Approved | 2022-09-30 | SIS |  |  | 08-2025
NYISO | 1329 | ELP Granby Solar II LLC | ELP Granby Solar II | 2022-02-11 | 20 | 20 | Energy Storage + Solar | Oswego | NY | Curtis Street - Teall 115 kV | NM-NG | Accepted Cost Allocation/IA in Progress | 2024-11-30 | FES, SIS, FS |  | 2024-10-07 | 09-2026 | 10-2026 | 12-2026
NYISO | 1365 | Queensboro Development, LLC | Queensboro Renewable Express Circuit A | 2022-04-15 |  |  | DC | Queens | NY | Rainey 345 kV substation and Vernon 138 kV substation | ConEd | SRIS/SIS Approved | 2022-07-31 | SIS |  |  | 04-2029
NYISO | 1366 | Queensboro Development, LLC | Queensboro Renewable Express Circuit B | 2022-04-15 |  |  | DC | Queens | NY | Rainey 345 kV substation and Vernon 138 kV substation | ConEd | SRIS/SIS Approved | 2024-03-31 | SIS |  |  | 04-2029
NYISO | 1435 | New York Power Authority & LS Power Grid New York Corporation II | Kings Spoke | 2022-09-12 |  |  | AC | Kings | NY | Greenwood-Bensonhurst and Farragut-Brownsville 138 kV feeders | ConEd | SRIS/SIS Pending | 2023-04-30 |  |  |  | 12-2028
NYISO | 1446 | Air Products and Chemicals Inc | Massena Green Hydrogen | 2022-10-05 | 110 | 110 | Load | St Lawrence | NY | Haverstock - Adirondack 345 kV line 1 | NYPA | SRIS/SIS Approved | 2023-12-31 | SIS |  |  | 10-2025
NYISO | 1465 | Digihost Technologies, Inc. | Digihost load | 2022-11-14 | 50.2 | 50.2 | Load | Niagara | NY | Walck Rd. 115kV | NM-NG | SRIS/SIS Pending | 2023-06-30 |  |  |  | 04-2024
NYISO | 1484 | GCEDC | 580 STAMP load increase | 2022-12-02 | 300 | 300 | Load | Genesee | NY | 115 kv STAMP substation | NM-NG | SRIS/SIS Approved | 2023-12-31 | SIS |  |  | 12-2025
NYISO | 1530 | New York Power Authority | Westchester Wind | 2023-03-02 |  |  | AC | Westchester | NY | Sprainbrook-Eastview 345kV #1N, #1S, and #2S. | ConEd | SRIS/SIS Pending | 2023-05-31 |  |  |  | 12-2028
NYISO | 1536 | Micron New York Semiconductor Manufacturing LLC | White Pine Phase 1 | 2023-03-11 | 480 | 480 | Load | Onondaga | NY | Clay 345 kV Substation | NM-NG | SRIS/SIS in Progress | 2024-02-29 |  |  |  | 06-2026
NYISO | 1555 | North Bergen Liberty Generating LLC | Liberty Green Line | 2023-05-12 |  |  | AC | New York County | NY | Con Edison W 49th St 345kV Substation | ConEd, PJM | FES Pending | 2023-08-31 |  |  |  | 01-2029
NYISO | 1627 | Micron New York Semiconductor Manufacturing LLC | Micron Fab 2 | 2023-10-31 | 576 | 507 | Load | Onondaga | NY | National Grid Clay 345 kV Substation | NM-NG | SRIS/SIS in Progress | 2024-06-30 |  |  |  | 09-2030
NYISO | 1646 | P&M Brick LLC | POWI Project | 2023-11-30 | 50 | 50 | Load | Albany | NY | New Scotland to Knickerbocker 345kV line | NM-NG | SRIS/SIS in Progress | 2024-07-31 |  |  |  | 01-2027
NYISO | 1667 | Consolidated Edison Company of New York | Designated Public Policy Project Rainey Breaker Replacement | 2024-01-12 |  |  | AC | New York | NY | Rainey 345kV Substation | ConEd | FS Pending | 2024-07-31 |  |  |  | 05-2030
NYISO | 1670 | Lake Mariner Data LLC | Lake Mariner Data II | 2024-01-23 | 250 | 250 | Load | Niagara | NY | Kintigh 345kV Substation | NYSEG | SRIS/SIS in Progress | 2024-07-31 |  |  |  | 04-2025
NYISO | 1671 | NYSEG | Meyer Substation Rebuild and South Perry Substation Rebuild | 2024-02-02 |  |  | AC | Wyoming/Livingston | NY | Meyer 115kV, 34.5, 230kV South Perry 115kV, 34.5kV, 69kV | NYSEG | SRIS/SIS Pending | 2024-03-31 |  |  |  | 12-2030
NYISO | 1672 | National Grid | Ames Road Station | 2024-02-05 |  |  | AC | Montgomery | NY | 345kV Edic Princetown 351 345kV Edic Princetwon 352 115kV Saint Johnsville Mashville 11 115kV Clinton Marshville 12 | NM-NG, NYPA | SRIS/SIS Pending | 2024-02-29 |  |  |  | 01-2028
NYISO | 1681 | Niagara Falls Redevelopment LLC | Niagara Digital Campus | 2024-04-09 | 140 | 140 | Load | Niagara | NY | Adams to Packard 115kV lines 187 and 188 | NM-NG | SRIS/SIS Pending | 2024-07-31 |  |  |  | 06-2026
NYISO | 1683 | Cayuga Operating Company, LLC | Cayuga Compute | 2024-04-24 | 150 | 150 | Load | Tompkins | NY | Milliken substation 115kV | NYSEG | SRIS/SIS in Progress | 2024-06-30 |  |  |  | 10-2025
NYISO | 1685 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #1 | 2024-05-30 |  |  | DC | Richmond,Kings,Queens,West Chester | NY | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 12-2032
NYISO | 1686 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #2 | 2024-05-30 |  |  | DC | New York, Richmond, Kings | NY | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; West 49 St - East13 St 345kV lines; Goethals 345kV, | CONED | SRIS/SIS Pending | 2024-07-31 |  |  |  | 12-2032
NYISO | 1687 | energyRe Giga-Projects USA, LLC | Clean Borough Power Link #3 | 2024-05-30 |  |  | DC | Richmond, New York, Kings, Queens | NY | Brooklyn Clean Energy Hub 345kV; Mott Haven - Rainey 345kV lines; Rainey 345kV; Astoria West 138kV; Farragut 345kV; Astoria Annex 345kV, Goethals 345 kV | CONED, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 12-2032
NYISO | 1688 | Viridon New York Inc. | Liberty Link 1 | 2024-05-31 |  |  | DC | Kings, Westchester, Richmond | NY | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | Con Edison | SRIS/SIS Pending | 2024-08-31 |  |  |  | 12-2032
NYISO | 1689 | Viridon New York Inc. | Liberty Link 2 | 2024-05-31 |  |  | DC | Kings, Westchester, Richmond | NY | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | Con Edison | SRIS/SIS Pending | 2024-08-31 |  |  |  | 12-2032
NYISO | 1690 | Viridon New York Inc. | Liberty Link 3 | 2024-05-31 |  |  | DC | Kings, New York, Richmond | NY | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, W49th Street 345kV - E13th Street 345 kV lines, Goethals 345kV | Con Edison | SRIS/SIS Pending | 2024-08-31 |  |  |  | 12-2032
NYISO | 1691 | New York Transco LLC | Energy Link New York Solution 1 | 2024-06-13 |  |  | DC | Kings, Westchester, Queens, Richmond | NY | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 01-2033
NYISO | 1692 | New York Transco LLC | Energy Link New York Solution 2 | 2024-06-13 |  |  | DC | Kings, Westchester, Queens, Richmond | NY | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | CONED, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 01-2033
NYISO | 1693 | New York Transco LLC | Energy Link New York Solution 3 | 2024-06-13 |  |  | DC | Kings, Westchester, Queens, Richmond | NY | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV, Gowanus- Goethals 345 kV lines | CONED, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 01-2033
NYISO | 1694 | New York Transco LLC | Energy Link New York Solution 4 | 2024-06-13 |  |  | DC | Kings, Westchester, Queens, Richmond | NY | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | CONED, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 01-2033
NYISO | 1695 | New York Transco LLC | Energy Link New York Solution 5 | 2024-06-13 |  |  | DC | Kings, Richmond, Queens, Westchester | NY | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | CONED, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 01-2033
NYISO | 1696 | New York Transco LLC | Energy Link New York Solution 6 | 2024-06-13 |  |  | DC | Kings, Westchester, Queens, Richmond | NY | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV; Astoria Annex 345kV; Sprain Brook 345kV | CONED, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 01-2033
NYISO | 1697 | New York Transco LLC | Energy Link New York Solution 7 | 2024-06-13 |  |  | DC | Brooklyn & Staten Island | NY | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV, Astoria Annex 345kV; Sprain Brook 345kV; Gowanus- Goethals 345kV lines | CONED, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 01-2033
NYISO | 1698 | New York Transco LLC | Energy Link New York Solution 10 | 2024-06-13 |  |  | DC | Kings, Westchester, Queens, Richmond | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Sprain Brook 345kV , Astoria Annex 345kV , Goethals 345kV , Mott Haven - Rainey 345kV substations, Gowanus - Goethals 345kV , Astoria West 345 kV, Rainey 345 kV | CONED, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 01-2033
NYISO | 1699 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Mint | 2024-06-13 |  |  | DC | Kings,Queens,NY,Bronx,Delaware, | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV | CONED, NYPA, NYSEG | SRIS/SIS Pending | 2024-08-31 |  |  |  | 10-2032
NYISO | 1700 | New York Transco LLC | Energy Link New York Solution 8 | 2024-06-15 |  |  | DC | Kings,Bronx,Queens,Westchester,Richmond | NY | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV ; Goethals 345 kV | CONED | SRIS/SIS Pending | 2024-07-31 |  |  |  | 01-2033
NYISO | 1701 | New York Transco LLC | Energy Link New York Solution 9 | 2024-06-15 |  |  | DC | Kings,Bronx,Queens,Westchester,Richmond | NY | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV, Goethals 345 kV | CONED | SRIS/SIS Pending | 2024-07-31 |  |  |  | 01-2033
NYISO | 1702 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Sage | 2024-06-15 |  |  | DC | Kings, Queens, New York, Bronx | NY | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Academy 345 kV, Astoria Annex 345 kV, Mott Haven 345 kV, Mott Haven - Rainey 345 kV Lines, | CONED, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 09-2032
NYISO | 1703 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect - Ruby | 2024-06-15 |  |  | DC | Kings, Queens, New York, Bronx | NY | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | CONED, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 09-2032
NYISO | 1704 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect - Rose | 2024-06-15 |  |  | DC | Kings, Queens, New York, Bronx | NY | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | CONED, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 09-2032
NYISO | 1705 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Olive | 2024-06-15 |  |  | DC | Kings/Queens/NY/Bronx/Delaware | NY | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, Academy 345 kV, Mott Haven 345 kV, Astoria Annex 345kV , Fraser, Mott Haven - Rainey 345kV Lines, | CONED, NYPA, NYSEG | SRIS/SIS Pending | 2024-08-31 |  |  |  | 06-2033
NYISO | 1706 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Kelly | 2024-06-17 |  |  | DC | Kings, Queens, New York, Bronx | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345 kV, Astoria Annex 345kV, Tremont 345kV, Mott Haven - Rainey 345kV Lines, | Con Edison, NYPA | SRIS/SIS Pending | 2024-07-31 |  |  |  | 08-2033
NYISO | 1707 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Hazel | 2024-06-17 |  |  | DC | Kings/Queens/NY/Bronx/Delaware | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV, Mott Haven - Rainey 345kV Lines, | Con Edison, NYPA, NYSEG | SRIS/SIS Pending | 2024-08-31 |  |  |  | 12-2033
NYISO | 1708 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Navy | 2024-06-17 |  |  | DC | Kings,Queens,Bronx,Richmond,Westchester | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Astoria Annex 345kV, Mott Haven 345kV, Rainey 345kV, Dunwoodie 345kV, Sprain Brook 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | Con Edison, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 09-2032
NYISO | 1709 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Royal | 2024-06-17 |  |  | DC | Kings,Queens,Bronx,Richmond,Westchester, | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Astoria Annex 345kV, Mott Haven 345kV, Tremont 345kV, W49th St 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | Con Edison, NYPA | SRIS/SIS Pending | 2024-08-31 |  |  |  | 05-2033
NYISO | 1710 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Golden | 2024-06-17 |  |  | DC | Kings,Queens,NY,Bronx,Westchester,Delawa | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Dunwoodie 345kV, Fraser 345kV, Vernon 138kV, Mott Haven - Rainey 345kV Lines | Con Edison, NYPA, NYSEG, | SRIS/SIS Pending | 2024-08-31 |  |  |  | 10-2033
NYISO | 1711 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Honey | 2024-06-17 |  |  | DC | Kings,Queens,NY,Bronx,Delaware | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Vernon 138kV, Fraser 345kV, | Con Edison, NYPA, NYSEG, | SRIS/SIS Pending | 2024-08-31 |  |  |  | 10-2033
NYISO | 1712 | New York Power Authority & LS Power Grid New York Corporation I | Five Boro Energy Connect ? Cobalt | 2024-06-17 |  |  | DC | Kings,Queens,NY,Bronx,Richmond,Delaware | NY | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Fraser 345kV, Gowanus 345 | Con Edison, NYPA, NYSEG | SRIS/SIS Pending | 2024-08-31 |  |  |  | 10-2033
NYISO | 1713 | Project Sycamore - Orangeburg | Project Sycamore Orangeburg | 2024-06-19 | 25.3 | 25.3 | Load | Rockland | NY | Oak Street 138kV | O&R | SRIS/SIS Pending | 2024-08-31 |  |  |  | 01-2025
NYISO | 1714 | Robert Delcalzo | Hudson Valley Data Center | 2024-07-02 | 25 | 25 | Load | Rockland | NY | Line 60 138KV - Ramp to Tallman | O&R | SRIS/SIS Pending | 2024-07-31 |  |  |  | 02-2027
NYISO | 1715 | Jerry Martin | 1547 CSR - Orangeburg LLC | 2024-07-02 | 60 | 60 | Load | Rockland | NJ | 138kV Line 703 between Corporate Drive and Harings Corner | O&R | SRIS/SIS Pending | 2024-08-31 |  |  |  | 01-2027
NYISO | 1716 | DataBank Holdings, LLC | Orangeburg Expansion Phase 2 | 2024-08-05 | 60 | 60 | Load | Orange | NY | Oak St 38kV substation | O&R | SRIS/SIS Pending | 2024-10-31 |  |  |  | 12-2027
NYISO | 1717 | Holtec Decommissioning International (HDI) | Proposed Datacenters at 450 Broadway, Buchanan, NY, 10511 | 2024-08-07 | 200 | 200 | Load | Westchester | NY | Buchanan 138kV Substation | ConEd | SRIS/SIS Pending | 2024-09-30 |  |  |  | 09-2026
NYISO | 1718 | Seven Creek Energy, LLC | Erie East BESS | 2024-09-10 |  |  | AC | Erie | PA | Erie East 230kV (First Energy, Erie PA) | PJM | Scoping Meeting Pending | 2024-12-31 |  |  |  | 06-2027
NYISO | 1719 | ZeroC Data Centers, LLC | New York State Artificial Intelligence Data Center | 2024-09-18 | 300 | 300 | Load | St. Lawrence | NY | Dennison 115kV substation | NM-NG | SRIS/SIS Pending | 2024-09-30 |  |  |  | 12-2025
NYISO | 1720 | Elk Run Storage LLC | Elk Run Storage | 2024-10-16 |  |  | AC | Tioga | PA | Mainesburg 115 kV Substation | PJM | Scoping Meeting Pending | 2024-10-31 |  |  |  | 11-2027
NYISO | 1721 | WF Industrial XII LLC | Brookhaven Logistics Center | 2024-10-28 | 176.6 | 176.6 | Load | Suffolk | NY | 138-872 Holbrook to Sills Rd or 138-873 West Bus to Sills Rd. | LIPA | SRIS/SIS Pending |  |  |  |  | 01-2027
NYISO | 1722 | Treebeard BESS Project Co LLC | Treebeard BESS | 2024-10-29 |  |  | AC | New Milford | CT | 115 kV line 1555 between Rocky River and Bulls Bridge substations | ISO-NE | Scoping Meeting Pending | 2024-11-30 |  |  |  | 02-2027
NYISO | 1723 | Olean Digital LLC | Olean Digital Data Center | 2024-11-07 | 150 | 150 | Load | Cattaraugus | NY | Homer Hill Olean Substation | NM-NG | Scoping Meeting Pending |  |  |  |  | 06-2026