NEISO | New Haven Harbor | 71 | 2000-05-22 | [24 empty] | New Haven | CT |  |  | East Shore Substation |  | 2003-06-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Bridgeport Harbor Station | 71 | 2000-05-22 | [24 empty] | Fairfield | CT |  |  | Pequonnock 115 kV Substation |  | 2003-06-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | New York Interface LTF PtP Out Service | 70 | 2000-04-25 | [28 empty] | Increase Export Capability to New York |  | 2003-07-31 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Neptune HVDC Cable Project | 69 | 2000-04-20 | [28 empty] | HVDC from Maine/ Maritimes to Boston Area and CT S |  | 2004-03-31 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Bridgeport Long Island HVDC | 68 | 2000-03-09 | [24 empty] | Fairfield | CT |  |  | HVDC to Long Island, NY from Bridgeport, CT |  | 2003-05-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Lowell Power Expansion | 67 | 2000-02-25 | [24 empty] | Middlesex | MA |  |  | Lowell Power 115 kV Station |  | 2001-05-01 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | AEC Expansion | 66 | 1999-12-20 | [24 empty] | Franklin | ME |  |  | Riley Road 115 kV Substation |  | 2001-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | EPMI LTF Pt to Pt In Svce. | 65 | 1999-12-02 | [30 empty] | 2002-01-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | West Springfield Station | 64 | 1999-11-08 |  |  |  | ST |  |  |  | NG RFO | [16 empty] | Hampden | MA |  |  | West Springfield 115 kV Substation |  | 2002-06-07 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Seabrook Unit One Uprate | 64 | 1999-11-08 | [24 empty] | Rockingham | NH |  |  | Increase Existing Unit Capacity |  | 2002-05-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | WESC LTF Pt to Pt In Svce | 63 | 1999-11-04 | [28 empty] | Increase Import Capability from NY |  | 2000-02-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | New York Interface Import Expansion | 62 | 1999-10-05 | [28 empty] | Increase Import Capability from NY |  | 2000-01-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | New York Interface Import Expansion | 61 | 1999-09-15 | [28 empty] | Increase Import Capability from NY |  | 1999-12-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Sithe LTF Pt to Pt In Svce. | 60 | 1999-09-01 | [28 empty] | Increase Import Capability from NY |  | 2000-03-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Milford Power Uprate | 59 | 1999-08-18 | [24 empty] | New Haven | CT |  |  | Increase Existing Unit Capacity |  | 2001-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Berkshire Power Uprate | 59 | 1999-08-18 | [24 empty] | Hampden | MA |  |  | Increase Existing Unit Capacity |  | 2001-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | CPS LTF Pt to Pt In Svc. | 58 | 1999-08-05 | [28 empty] | Increase Import Capability from NY |  | 1999-11-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Norwich Power Station | 57 | 1999-06-04 | [24 empty] | New London | CT |  |  | Bean Hill Substation |  | 2002-01-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | New York Interface Import Expansion | 56 | 1999-02-25 | [28 empty] | Increase Import Capability from New York |  | 1999-05-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Cross Sound Cable | 55 | 1999-01-21 | [24 empty] | New Haven | CT |  |  | HVDC terminal adjacent to East Shore 345kV Substat |  | 2003-09-01 | [38 empty] | ETU | [43 empty] | TRUE | TRUE
NEISO | Redington Mountain Wind Farm | 54 | 1999-01-05 | [24 empty] | Franklin | ME |  |  | Bigelow 115 kV Substation |  | 2002-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Tractebel LTF Int + Internal PtP | 53 | 1998-11-30 | [28 empty] | Import from the New Brunswick System |  | 2002-05-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Haddam Station | 52 | 1998-11-13 | [24 empty] | Middlesex | CT |  |  | Site of the Former CT Yankee Plant |  | 2002-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Haddam Station Phase II | 52 | 1998-11-13 | [24 empty] | Middlesex | CT |  |  | Site of the Former CT Yankee Plant |  | 2002-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | MEPCO-New England Interface Expansion | 51 | 1998-10-30 | [28 empty] | Import Capability from MEPCO |  | 2000-01-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Patriot Cabot Street Station | 50 | 1998-10-29 | [24 empty] | Hampden | MA |  |  | Holyoke Substation |  | 2001-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Irving Oil LTF PtP | 49 | 1998-09-14 | [28 empty] | Import from NB Via MEPCO |  | 2001-04-01 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Bennington Energy Park | 48 | 1998-09-09 | [24 empty] | Bennington | VT |  |  | TBD |  | 2001-11-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Rutland Energy Park | 48 | 1998-09-09 | [24 empty] | Rutland | VT |  |  | TBD |  | 2001-11-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Nickel Hill Energy Project | 47 | 1998-08-26 | [24 empty] | Middlesex | MA |  |  | Tewksbury 230 kV Substation |  | 2001-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Campello Power Co. | 46 | 1998-08-18 | [24 empty] | Plymouth | MA |  |  |  |  | 2002-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Kendall Repowering Project | 45 | 1998-07-17 |  |  |  | CC |  |  |  | NG | [16 empty] | Suffolk | MA |  |  | Kendall Station in Cambridge |  | 2002-12-18 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Brockton Power Project | 44 | 1998-07-10 | [24 empty] | Plymouth | MA |  |  | Industrial Blvd. |  | 2001-01-31 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Tractebel LTF PtP | 43 | 1998-06-08 | [28 empty] | Import from the New Brunswick System |  | 2002-12-31 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Wiscassett | 42 | 1998-06-05 | [24 empty] | Lincoln | ME |  |  | Maine Yankee 345 KV |  | 2001-10-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Canal 2 Repowering | 41 | 1998-06-04 | [24 empty] | Barnstable | MA |  |  | Canal 345 kV Station |  | 2001-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Glen Charlie Unit One | 40 | 1998-06-01 | [24 empty] | Plymouth | MA |  |  | Wareham 115 kV Substation |  | 2001-03-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | CVPS/GMP LTF PtP | 39 | 1998-05-28 | [24 empty] | Clinton | NY |  |  | Import from NY via PV20 |  | 2001-12-31 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | HQ Highgate2 HVDC | 39 | 1998-05-28 | [24 empty] | Franklin | VT |  |  | Located on the Hydro Quebec sys. N. near Highgate, |  | 2001-12-31 | [38 empty] | ETU | [43 empty] | FALSE | FALSE
NEISO | Rocky River Power | 38 | 1998-05-08 | [24 empty] | Litchfield | CT |  |  | Long Mountain 345 kV Station |  | 2001-07-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | FPLE RISE, LLC (R.I. Hope Energy) | 37 | 1998-04-29 |  |  |  | CC |  |  |  | NG | [16 empty] | Providence | RI |  |  | S 171 and S 172 Lines |  | 2002-11-05 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | FPL Energy (Bedford) | 36 | 1998-04-14 | [24 empty] | Bristol | MA |  |  | Industrial Park 115 kV Substation |  | 2000-11-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Mason | 35 | 1998-04-02 | [24 empty] | Lincoln | ME |  |  | Mason 345 kV Substation |  | 2000-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Wyman A | 35 | 1998-04-02 | [24 empty] | Cumberland | ME |  |  | Wyman 115 kV Station |  | 2000-01-02 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Wyman B | 35 | 1998-04-02 | [24 empty] | Cumberland | ME |  |  | Wyman 115 kV Station |  | 2000-01-03 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | WEG-Norwich | 34 | 1998-04-01 | [24 empty] | New London | CT |  |  | Montville 115 kV Substation |  | 2005-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Sithe Framingham Station Expansion | 33 | 1998-03-31 | [24 empty] | Middlesex | MA |  |  | Framingham 230 kV |  | 2001-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Sithe Medway | 33 | 1998-03-31 | [24 empty] | Norfolk | MA |  |  | Existing Medway Station 345 kV |  | 2001-12-31 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Westbrook Power | 33 | 1998-03-31 |  |  |  | CC |  |  |  | NG | [16 empty] | Cumberland | ME |  |  | Spring St. 115 kV Substation |  | 2001-04-13 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Sithe Edgar Station Expansion (Fore River) | 33 | 1998-03-31 |  |  |  | CC |  |  |  | NG | [16 empty] | Norfolk | MA |  |  | Holbrook 345 kV |  | 2003-08-04 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Sithe Mystic Station Expansion Unit 8 | 33 | 1998-03-31 |  |  |  | CC |  |  |  | NG | [16 empty] | Suffolk | MA |  |  | Mystic 345 kV |  | 2003-04-13 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Sithe Mystic Station Expansion Unit 9 | 33 | 1998-03-31 |  |  |  | CC |  |  |  | NG | [16 empty] | Suffolk | MA |  |  | Mystic 345 kV |  | 2003-06-11 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Towantic Energy | 32 | 1998-03-30 | [24 empty] | New Haven | CT |  |  | Beacon Falls 115 kV |  | 2002-12-31 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | North Smithfield | 31 | 1998-03-26 | [24 empty] | Providence | RI |  |  | W. Farnum 345 kV |  | 2002-06-30 | [38 empty] | G | [43 empty] | TRUE | FALSE
NEISO | Norwich Power Station | 30 | 1998-03-25 | [24 empty] | New London | CT |  |  | Bean Hill Substation |  | 2000-12-31 | [38 empty] | G | [43 empty] | TRUE | FALSE
NEISO | Engage Energy LTF PtP | 30 | 1998-03-25 | [28 empty] | Import from New Brunswick via MEPCO |  | 2000-12-31 | [38 empty] | ETU | [43 empty] | TRUE | FALSE
NEISO | Bucksport Energy, L.P. | 29 | 1998-03-24 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | Hancock | ME |  |  | Belfast 115 kV bus |  | 2001-01-01 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Newington Energy Center | 28 | 1998-03-18 | [24 empty] | Rockingham | NH |  |  | Newington 345 kV Station |  | 2001-03-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | AES Carpenter | 27 | 1998-03-13 | [24 empty] | Hartford | CT |  |  | Southington 345 kV Substation |  | 2001-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | S&P Cogeneration | 26 | 1998-03-06 | [24 empty] | Essex | MA |  |  | Lynn 115 kV |  | 2001-12-31 | [38 empty] | G | [43 empty] | TRUE | FALSE
NEISO | Patriot Power | 25 | 1998-02-27 | [24 empty] | Bristol | MA |  |  | Bridgewater 345 kV Line |  | 2001-03-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Orrington Generation | 24 | 1998-02-25 | [24 empty] | Penobscot | ME |  |  | Orrington 345 kV Station |  | 2001-06-30 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | HQ-Surowiec | 23 | 1998-02-19 | [24 empty] | Cumberland | ME |  |  | Surowiec 345 kV or MEPCO |  | 2002-12-31 | [38 empty] | ETU | [43 empty] | TRUE | FALSE
NEISO | Meriden Power | 22 | 1998-02-16 | [24 empty] | New Haven | CT |  |  | Sectionalize 362 Line |  | 2003-06-30 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Wallingford Power Units 1&3 | 21 | 1998-02-11 |  |  |  | GT |  |  |  | NG | [16 empty] | New Haven | CT |  |  | Wallingford 115 kV Substation |  | 2001-12-31 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Wallingford Power Unit 4 | 21 | 1998-02-11 |  |  |  | GT |  |  |  | NG | [16 empty] | New Haven | CT |  |  | Wallingford 115 kV Substation |  | 2002-01-23 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Wallingford Power Units 2&5 | 21 | 1998-02-11 |  |  |  | GT |  |  |  | NG | [16 empty] | New Haven | CT |  |  | Wallingford 115 kV Substation |  | 2002-02-07 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | AES Londonderry (Granite Ridge) | 21 | 1998-02-11 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | Rockingham | NH |  |  | N. Litchfield 230 kV Station and Watts Brook 115 k |  | 2003-04-01 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Housatonic Power | 20 | 1998-01-20 | [24 empty] | Fairfield | CT |  |  | 398 Line |  | 2001-01-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Livermore Falls | 19 | 1998-01-14 | [24 empty] | Androscoggin | ME |  |  | Livermore Falls 115 kV Substation |  | 2000-12-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Versaille Energy Center | 18 | 1998-01-13 | [24 empty] | New London | CT |  |  | Tunnel 115 kV Substation |  | 2000-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | White Mountain Cogen.Center | 18 | 1998-01-13 | [24 empty] | Coos | NH |  |  | Lost Nation 115 kV Substation |  | 2000-12-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Sprague Newington (Piscataqua Power) | 18 | 1998-01-13 | [24 empty] | Rockingham | NH |  |  | Newington 345 kV Station |  | 2000-01-01 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | SEI Newington (ConEd) | 17 | 1997-12-12 |  |  |  | CC |  |  |  | JF NG | [16 empty] | Rockingham | NH |  |  | Newington 345 kV Station |  | 2002-09-18 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Lake Road Generating Units 1&2 | 17 | 1997-12-12 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | Windham | CT |  |  | Line 347 |  | 2002-03-15 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Lake Road Generating Unit 3 | 17 | 1997-12-12 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | Windham | CT |  |  | Line 347 |  | 2002-05-22 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | ANP Gorham | 16 | 1997-10-24 | [24 empty] | Cumberland | ME |  |  | S. Gorham 345 kV Substation |  | 2000-07-01 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | South Norwalk | 15 | 1997-10-09 | [24 empty] | Fairfield | CT |  |  | Norwalk 115 kV Substation |  | 2000-01-01 | [38 empty] | G | [43 empty] | TRUE | FALSE
NEISO | Cabot Power | 14 | 1997-09-30 | [24 empty] | Middlesex | MA |  |  | Mystic 345 kV Station |  | 2000-06-30 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Summit Power | 13 | 1997-08-22 | [24 empty] | Hampden | MA |  |  | 1302 Line |  | 2001-03-31 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Milford Power Unit 1 | 13 | 1997-08-22 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | New Haven | CT |  |  | Devon 115 kV Substation |  | 2004-02-12 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Milford Power Unit 2 | 13 | 1997-08-22 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | New Haven | CT |  |  | Devon 115 kV Substation |  | 2004-05-03 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Berkshire Power | 12 | 1997-08-15 |  |  |  | CC |  |  |  | NG | [16 empty] | Hampden | MA |  |  | South Agawam Jct. 115 kV Station |  | 2000-06-19 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Wareham | 11 | 1997-08-05 | [24 empty] | Plymouth | MA |  |  | Adjacent to the Tremont Substation |  | 2001-02-28 | [38 empty] | G | [43 empty] | FALSE | FALSE
NEISO | Maine Independence | 10 | 1997-07-24 |  |  |  | CC |  |  |  | NG | [16 empty] | Penobscot | ME |  |  | Located at Graham Station in Veazie, ME |  | 2000-05-01 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | IDC Bellingham | 9 | 1997-07-22 | [24 empty] | Norfolk | MA |  |  | Sectionalize 336 Line |  | 2002-12-31 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | ANP Bellingham Energy Project Unit 1 | 8 | 1997-07-15 |  |  |  | CC |  |  |  | NG | [16 empty] | Norfolk | MA |  |  | Sectionalize Line 303 |  | 2002-10-24 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | ANP Bellingham Energy Project Unit 2 | 8 | 1997-07-15 |  |  |  | CC |  |  |  | NG | [16 empty] | Norfolk | MA |  |  | Sectionalize Line 303 |  | 2002-12-28 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | ANP Blackstone Energy Project Unit 1 | 8 | 1997-07-15 |  |  |  | CC |  |  |  | NG | [16 empty] | Worcester | MA |  |  | Sectionalize 336 Line |  | 2001-06-07 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | ANP Blackstone Energy Project Unit 2 | 8 | 1997-07-15 |  |  |  | CC |  |  |  | NG | [16 empty] | Worcester | MA |  |  | Sectionalize 336 Line |  | 2001-07-13 | [38 empty] | G | [41 empty] | 2009-10-02 |  | TRUE | TRUE
NEISO | Bridgeport Harbor Station | 7 | 1997-06-25 |  |  |  | CC |  |  |  | NG | [16 empty] | Fairfield | CT |  |  | Pequonnock 115 kV Substation |  | 1999-07-24 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Rumford Power Associates | 6 | 1997-06-12 |  |  |  | CC |  |  |  | NG | [16 empty] | Oxford | ME |  |  | Rumford 115 kV Substation |  | 2000-10-16 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Brayton Pt | 5 | 1997-05-09 | [24 empty] | Bristol | MA |  |  | Brayton Point 345 kV Station |  | 2001-12-31 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | EMI Dighton Power Project | 4 | 1997-04-10 |  |  |  | CC |  |  |  | NG | [16 empty] | Bristol | MA |  |  | U6 Line |  | 1999-08-01 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Androscoggin Energy Center | 3 | 1997-02-13 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | Franklin | ME |  |  | Jay 115 kV Substation |  | 2000-12-28 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | EMI-Tiverton | 2 | 1996-11-08 |  |  |  | CC |  |  |  | NG | [16 empty] | Newport | RI |  |  | Near Tiverton 115 kV Substation |  | 2000-08-18 | [38 empty] | G | [43 empty] | TRUE | TRUE
NEISO | Millennium+K117 | 1 | 35223 |  |  |  | CC |  |  |  | DFO NG | [16 empty] | Worcester | MA |  |  | W 123 Line |  | 36987 | [38 empty] | G | [43 empty] | TRUE | TRUE
NYISO | Homer Solar Energy Center | 0276 | 2008-01-30 | [7 empty] | Solar | [16 empty] | Cortland | NY | NM-NG |  | Cortland - Fenner 115kV | 03-2026 | [9 empty] | Homer Solar Energy Center LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 90 | 90 |  | 2023-07-31 | 03-2026 |  |  |  | FES, SRIS, FS | 2021-02-08 | 04-2026
NYISO | Wood Street Transformer | 0396A | 2012-12-14 | [7 empty] | AC | [16 empty] | Putnam | NY | NYSEG |  | Wood St. 345/115kV | 12/2024 | [9 empty] | New York State Electric & Gas | [37 empty] | Under Construction | [33 empty] | 2024-05-31 |  |  |  |  | SIS
NYISO | North Rockland Station | 0429 | 2014-02-12 | [7 empty] | AC | [16 empty] | Steuben | NY | ConEd |  | Line Y88 345kV | 06/2024 | [9 empty] | Orange & Rockland | [37 empty] | Under Construction | [33 empty] | 2022-03-31 |  |  |  |  | SIS
NYISO | Cedar Rapids Transmission | 0430 | 2014-03-05 | [7 empty] | AC | [16 empty] | St. Lawrence | NY | NM-NG |  | Dennison - Alcoa 115kV | 10/2021 | [9 empty] | H.Q. Energy Services U.S. Inc. | [8 empty] | 2018-10-02 | [28 empty] | Under Construction | [33 empty] | 2019-12-31 |  |  |  |  | SIS, FS | 2018-03-19
NYISO | Mohawk Solar | 0495 | 2015-04-02 | [7 empty] | Solar | [16 empty] | Montgomery | NY | NM-NG |  | St. Johnsville - Marshville 115kV | 06/2027 | [9 empty] | Mohawk Solar LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 90.5 | 90.5 |  | 2022-09-30 | 10/2027 |  |  |  | FES, SRIS, FS | 2021-02-08 | 11/2027
NYISO | Canisteo Wind | 0519 | 2015-11-02 | [7 empty] | Wind | [16 empty] | Steuben | NY | NYSEG |  | Bennett 115kV | 10-2026 | [9 empty] | Canisteo Wind Energy LLC | [8 empty] | 2021-02-08 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 289.8 | 289.8 |  | 2022-09-30 | 01-2027 |  |  |  | FES, SRIS, FS | 2021-02-08 | 12-2027
NYISO | Bull Run II Wind | 0521 | 2015-12-15 | [7 empty] | Wind | [16 empty] | Clinton | NY | NYPA |  | Patnode-Duley, Ryan-Plattsburgh 230kV | 05-2026 | [9 empty] | Bull Run Energy LLC | [8 empty] | 2023-01-11 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 449 | 449 |  | 2022-11-30 | 05-2026 |  |  |  | FES, SRIS, FS | 2023-01-11 | 12-2026
NYISO | NYC Energy | 0522 | 2015-12-16 | [7 empty] | Energy Storage | [16 empty] | Kings | NY | ConEd |  | Hudson Avenue East 138kV | 05-2027 | [9 empty] | NYC Energy LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 79.9 | 79.9 |  | 2024-10-31 | 05-2027 |  |  |  | FES, SRIS |  | 06-2027
NYISO | Riverhead Solar 2 | 0535 | 2016-02-23 | [7 empty] | Solar | [16 empty] | Suffolk | NY | LIPA |  | Edwards 138kV | 09-2026 | [9 empty] | Riverhead Solar 2, LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 36 | 36 |  | 2024-09-30 | 12-2026 |  |  |  | FES, SRIS, FS | 2021-02-08 | 01-2027
NYISO | Segment B Knickerbocker-PV | 0543 | 2016-05-04 | [7 empty] | AC | [16 empty] | Albany-Dutchess | NY | NM-NG/NYSEG/ CHGE/ConEd |  | Greenbush - PV 345kV | 12/2023 | [9 empty] | National Grid | [37 empty] | Under Construction | [33 empty] | 2022-04-30 |  |  |  |  | SIS
NYISO | Sky High Solar | 0545 | 2016-05-16 | [7 empty] | Solar | [16 empty] | Onondaga | NY | NM-NG |  | Tilden -Tully Center 115kV | 06-2025 | [9 empty] | Sky High Solar, LLC | [8 empty] | 2019-10-01 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2022-01-31 | 05-2025 |  |  |  | FES, SIS, FS | 2019-09-17 | 06-2025
NYISO | Rock District Solar | 0564 | 2016-07-25 | [7 empty] | Solar | [16 empty] | Schoharie | NY | NM-NG |  | Sharon - Cobleskill 69kV | 01-2027 | [9 empty] | Rock District Solar, LLC | [8 empty] | 2020-07-10 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2021-08-31 | 12-2026 |  |  |  | SIS, FS | 2020-06-03 | 02-2027
NYISO | Tayandenega Solar | 0565 | 2016-07-25 | [7 empty] | Solar | [16 empty] | Montgomery | NY | NM-NG |  | St. Johnsville - Inghams 115kV | 01-2027 | [9 empty] | Tayandenega Solar, LLC | [8 empty] | 2020-07-01 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-07-31 | 12-2026 |  |  |  | SIS, FS | 2020-06-03 | 02-2027
NYISO | MA 1 & 2 Rebuild | 0566 | 2016-08-04 | [7 empty] | AC | [16 empty] | St. Lawrence-Lewis | NY | NYPA |  | Moses & Adirondack 230kV | 6-2023 | [9 empty] | New York Power Authority | [37 empty] | Under Construction | [33 empty] | 2022-09-30 |  |  |  |  | SIS
NYISO | Heritage Wind | 0571 | 2016-09-01 | [7 empty] | Wind | [16 empty] | Genesee | NY | NM-NG |  | Lockport - Mortimer 115kV | 05-2026 | [9 empty] | Heritage Wind, LLC | [8 empty] | 2023-01-11 | [28 empty] | IA Completed | [30 empty] | 200.1 | 200.1 |  | 2023-09-30 | 06-2026 |  |  |  | FES, SRIS, FS | 2023-01-11 | 09-2026
NYISO | Greene County 1 | 0572 | 2016-09-06 | [7 empty] | Solar | [16 empty] | Greene | NY | CHG&E |  | Coxsackie - North Catskill 69kV | 03-2025 | [9 empty] | Hecate Energy Greene 1 LLC | [8 empty] | 2020-02-18 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2022-01-31 | 03-2025 |  |  |  | SIS, FS | 2020-01-24 | 05-2025
NYISO | Greene County 2 | 0573 | 2016-09-06 | [7 empty] | Solar | [16 empty] | Greene | NY | CHG&E |  | Coxsackie 13.8kV | 03-2025 | [9 empty] | Hecate Energy Greene 2 LLC | [8 empty] | 2020-02-18 | [28 empty] | IA Completed | [30 empty] | 10 | 10 |  | 2022-01-31 | 03-2025 |  |  |  | SIS, FS | 2020-01-24 | 05-2025
NYISO | Little Pond Solar | 0575 | 2016-09-16 | [7 empty] | Solar | [16 empty] | Orange | NY | O&R |  | Mongaup - Shoemaker 69kV | 01-2025 | [9 empty] | Little Pond Solar, LLC | [8 empty] | 2021-01-29 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-02-29 | 01-2025 |  |  |  | FES, SIS, FS | 2020-12-16 | 01-2025
NYISO | WNY STAMP | 0580 | 2016-09-27 | [7 empty] | Load | [16 empty] | Genesee | NY | NYPA |  | Kintigh/Niagara - New Rochester 345kV | 12/2024 | [9 empty] | Genesee County Economic Devel. | [37 empty] | Under Construction | [30 empty] | 300 | 300 |  | 2023-07-31 |  |  |  |  | SIS
NYISO | Hills Solar | 0581 | 2016-10-06 | [7 empty] | Solar | [16 empty] | Herkimer | NY | NM-NG |  | Fairfield - Inghams 115kV | 10-2026 | [9 empty] | SunEast Hills Solar LLC | [8 empty] | 2020-04-07 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 06-2026 |  |  |  | FES, SIS, FS | 2020-02-11 | 12-2026
NYISO | Dog Corners Solar | 0584 | 2016-11-02 | [7 empty] | Solar | [16 empty] | Cayuga | NY | NYSEG |  | Aurora 34.5kV | 03-2026 | [9 empty] | SunEast Dog Corners Solar LLC | [8 empty] | 2019-06-21 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 03-2026 |  |  |  | SIS, FS | 2019-05-08 | 04-2026
NYISO | Watkins Rd Solar | 0586 | 2016-11-08 | [7 empty] | Solar | [16 empty] | Herkimer | NY | NM-NG |  | Watkins Rd - Ilion 115kV | 03-2026 | [9 empty] | SunEast Watkins Road Solar LLC | [8 empty] | 2020-02-18 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-04-30 | 02-2026 |  |  |  | SIS, FS | 2019-11-25 | 07-2026
NYISO | Scipio Solar | 0590 | 2016-12-02 | [7 empty] | Solar | [16 empty] | Cayuga | NY | NYSEG |  | Scipio 34.5kV | 09-2024 | [9 empty] | SunEast Scipio Solar LLC. | [8 empty] | 2019-05-22 | [28 empty] | IA Completed | [30 empty] | 18 | 18 |  | 2023-06-30 | 09-2024 |  |  |  | SIS, FS | 2019-03-21 | 12-2024
NYISO | Highview Solar | 0591 | 2016-12-02 | [7 empty] | Solar | [16 empty] | Wyoming | NY | NYSEG |  | South Perry 34.5kV | 02-2025 | [9 empty] | SunEast Highview Solar LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 01-2025 |  |  |  | SIS, FS | 2021-02-08 | 02-2025
NYISO | Niagara Solar | 0592 | 2016-12-02 | [7 empty] | Solar | [16 empty] | Wyoming | NY | NYSEG |  | Bennington 34.5kV | 03-2025 | [9 empty] | Niagara NY Solar LLC | [8 empty] | 2019-05-22 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-09-30 | 04-2025 |  |  |  | SIS, FS | 2019-04-18 | 12-2026
NYISO | Alle Catt II Wind | 0596 | 2017-01-04 | [7 empty] | Wind | [16 empty] | Cattaraugus | NY | NM-NG |  | Stolle Rd - Five Mile Rd 345kV | 05-2026 | [9 empty] | Alle-Catt Wind Energy LLC | [8 empty] | 2021-02-08 | [28 empty] | Under Construction | [30 empty] | 339.1 | 339.1 |  | 2022-09-30 | 05-2026 |  |  |  | SRIS, FS | 2021-02-08 | 12-2026
NYISO | Watkins Glen Solar | 0617 | 2017-03-27 | [7 empty] | Solar | [16 empty] | Schuyler | NY | NYSEG |  | Bath - Montour Falls 115kV | 12-2024 | [9 empty] | Watkins Glen Solar Energy Center, LLC | [8 empty] | 2020-12-04 | [28 empty] | IA Completed | [30 empty] | 50 | 50 |  | 2024-04-30 | 12-2024 |  |  |  | SRIS, FS | 2021-02-08 | 01-2025
NYISO | North Side Solar | 0620 | 2017-03-27 | [7 empty] | Solar | [16 empty] | St. Lawrence | NY | NYPA |  | Massena - Moses 230kV | 10-2024 | [9 empty] | North Side Energy Center, LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 180 | 180 |  | 2022-09-30 | 11-2024 |  |  |  | FES, SRIS, FS | 2021-02-08 | 12-2024
NYISO | NS Power Express | 0631 | 2017-05-02 | [7 empty] | DC | [16 empty] | Quebec - New York | NY | NYPA |  | Astoria Annex 345kV | 05-2026 | [9 empty] | CHPE LLC | [8 empty] | 2023-01-11 | [28 empty] | Under Construction | [30 empty] | 1000 | 1000 |  | 2023-06-30 | 05-2026 |  |  |  | SRIS, FS | 2023-01-11 | 05-2026
NYISO | Flint Mine Solar | 0637 | 2017-06-29 | [7 empty] | Solar | [16 empty] | Greene | NY | NM-NG |  | LaFarge - Pleasant Valley 115kV, Feura Bush - North Catskill 115kV | 12-2025 | [9 empty] | Flint Mine Solar LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 100 | 100 |  | 2022-09-30 | 12-2025 |  |  |  | FES, SRIS, FS | 2021-02-08 | 5-2026
NYISO | Columbia County 1 | 0644 | 2017-07-26 | [7 empty] | Solar | [16 empty] | Columbia | NY | NYSEG |  | Craryville 115kV | 12-2026 | [9 empty] | Hecate Energy Columbia County 1, LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 60 | 60 |  | 2024-06-30 | 12-2026 |  |  |  | FES, SRIS, FS | 2021-02-08 | 2-2027
NYISO | SunEast Skyline Solar LLC | 0670 | 2017-09-21 | [7 empty] | Solar | [16 empty] | Westmoreland | NY | NM-NG |  | Campus Rd - Clinton 46kV | 11/2027 | [9 empty] | SunEast Skyline Solar LLC | [8 empty] | 2020-08-13 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2023-07-31 | 10/2027 |  |  |  | FES, SIS, FS | 2020-07-31 | 4/2028
NYISO | KCE NY 2 | 0683 | 2018-01-18 | [7 empty] | Energy Storage | [16 empty] | Montgomery | NY | CHG&E |  | Coldenham 115kV | 05-2027 | [9 empty] | KCE NY 2, LLC | [8 empty] | 2021-03-16 | [28 empty] | IA Completed | [30 empty] | 200 | 200 |  | 2024-03-31 | 05-2027 |  |  |  | SRIS, FS | 2021-02-08 | 06-2027
NYISO | Bear Ridge Solar | 0704 | 2018-03-20 | [7 empty] | Solar | [16 empty] | Niagara | NY | NM-NG |  | Mountain- Lockport 115kV | 01-2025 | [9 empty] | Bear Ridge Solar, LLC | [8 empty] | 2021-02-08 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 100 | 100 |  | 2024-10-31 | 02-2025 |  |  |  | SRIS, FS | 2021-02-08 | 02-2025
NYISO | High Bridge Wind | 0706 | 2018-04-25 | [7 empty] | Wind | [16 empty] | Chenango | NY | NYSEG |  | E. Norwich - Jennison 115kV | 12-2024 | [9 empty] | High Bridge Wind, LLC | [37 empty] | IA Completed | [30 empty] | 100.8 | 100.8 |  | 2024-05-31 | 12-2024 |  |  |  | SRIS, FS | 2021-02-08 | 02-2025
NYISO | Horseshoe Solar | 0710 | 2018-05-29 | [7 empty] | Solar | [16 empty] | Livingston | NY | NM-NG |  | Golah 115kV | 12-2025 | [9 empty] | Horseshoe Solar Energy LLC | [8 empty] | 2023-01-11 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 180 | 180 |  | 2024-03-31 | 11-2025 |  |  |  | FES, FS | 2023-01-11 | 12-2025
NYISO | Moraine Solar Energy Center | 0716 | 2018-06-04 | [7 empty] | Solar | [16 empty] | Allegany | NY | NYSEG |  | Moraine 115kV | 04-2027 | [9 empty] | EDF Renewables Development, Inc. | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 93.5 | 93.5 |  | 2024-10-31 | 04-2027 |  |  |  | FES, SRIS |  | 10-2027
NYISO | Trelina Solar Energy Center | 0720 | 2018-06-07 | [7 empty] | Solar | [16 empty] | Seneca | NY | NYSEG |  | Border City - Station 168 115 KV | 12-2024 | [9 empty] | Trelina Solar Energy Center, LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 79.8 | 79.8 |  | 2024-04-30 | 12-2024 |  |  |  | SRIS, FS | 2021-02-08 | 01-2025
NYISO | Excelsior Energy Center | 0721 | 2018-06-07 | [7 empty] | Solar | [16 empty] | Genesee | NY | NYPA |  | Dysinger - N. Rochester 345kV | 12-2024 | [9 empty] | Excelsior Energy Center, LLC | [8 empty] | 2021-01-22 | [28 empty] | IA Completed | [30 empty] | 280 | 280 |  | 2022-09-30 | 12-2024 |  |  |  | SRIS, FS | 2021-02-08 | 02-2025
NYISO | Ticonderoga Solar | 0734 | 2018-06-12 | [7 empty] | Solar | [16 empty] | Essex | NY | NM-NG |  | Ticonderoga 115kV - Republic Line 2 | 01-2025 | [9 empty] | ELP Ticonderoga Solar LLC | [8 empty] | 2021-03-18 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 02-2025 |  |  |  | FES, SIS, FS | 2021-07-31 | 03-2025
NYISO | Empire Wind 1 | 0737 | 2018-06-12 | [7 empty] | Off-Shore Wind | [16 empty] | Kings | NY | ConEd |  | Gowanus 345kV | 06-2025 | [9 empty] | Empire Offshore Wind LLC | [8 empty] | 2021-02-08 | [28 empty] | IA Completed | [30 empty] | 816 | 816 |  | 2024-01-31 | 11-2025 |  |  |  | SRIS, FS | 2021-02-08 | 12-2026
NYISO | Magruder BESS | 0744 | 2018-07-18 | [7 empty] | Energy Storage | [16 empty] | Ulster | NY | CHG&E |  | East Walden - Modena 115kV | 09-2024 | [9 empty] | Mitchell Energy Facility, LLC | [8 empty] | 2021-04-06 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 10-2024 |  |  |  | SIS, FS | 2021-03-04 | 01-2025
NYISO | Sunrise Wind | 0766 | 2018-09-28 | [7 empty] | Off-Shore Wind | [16 empty] | Suffolk | NY | LIPA |  | Holbrook 138kV & West Bus 138kV | 06-2025 | [9 empty] | Sunrise Wind LLC | [8 empty] | 2023-01-11 | [28 empty] | IA Completed | [30 empty] | 880 | 880 |  | 2023-09-30 | 08-2025 |  |  |  | SRIS, FS | 2023-01-11 | 03-2026
NYISO | Tracy Solar Energy Centre | 0774 | 2018-10-18 | [7 empty] | Solar | [16 empty] | Jefferson | NY | NM-NG |  | Thousand Island - Lyme 115kV | 05-2028 | [9 empty] | EDF Renewables Development, Inc. | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 119 | 119 |  | 2024-10-31 | 05-2028 |  |  |  | SRIS |  | 11-2028
NYISO | Greenidge Load | 0776 | 2018-10-22 | [7 empty] | Load | [16 empty] | Yates | NY | NYSEG |  | Greenidge 115kV | 06-2025 | [9 empty] | Greenidge Generation LLC | [37 empty] | FS Pending | [30 empty] | 60 | 60 |  | 2024-04-30 |  |  |  |  | SIS
NYISO | White Creek Solar | 0777 | 2018-11-01 | [7 empty] | Solar | [16 empty] | Livingston | NY | RG&E |  | Sta 82 - Sta 128 115kV | 10-2027 | [9 empty] | White Creek Solar, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 135 | 135 |  | 2024-10-31 | 10-2027 |  |  |  | SRIS |  | 11-2027
NYISO | South Ripley Solar and BESS | 0783 | 2018-12-07 | [7 empty] | Energy Storage + Solar | [16 empty] | Chautauqua | NY | NM-NG |  | South Ripley Substation 230kV | 11-2026 | [9 empty] | ConnectGen Chautauqua County LLC | [8 empty] | 2023-01-11 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 270 | 270 |  | 2024-07-31 | 11-2026 |  |  |  | FES, SRIS, FS | 2023-01-11 | 01-2027
NYISO | Levy Grid, LLC | 0787 | 2018-12-20 | [7 empty] | Energy Storage | [16 empty] | Erie | NY | NM-NG |  | Gardenville Subsation 115kV | 08-2025 | [9 empty] | Levy Grid, LLC | [8 empty] | 2023-01-11 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 150 | 150 |  | 2022-11-30 | 08-2025 |  |  |  | SRIS, FS | 2023-01-11 | 08-2025
NYISO | Rich Road Solar Energy Center | 0800 | 2019-02-20 | [7 empty] | Energy Storage + Solar | [16 empty] | St. Lawrence | NY | NYPA |  | Moses - Adirondack 230 kV Line #2 (MA2) | 10-2027 | [9 empty] | EDF Renewables Development, Inc. | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 240 | 240 |  | 2024-10-31 | 10-2027 |  |  |  | FES, SRIS |  | 04-2028
NYISO | Prattsburgh Wind Farm | 0801 | 2019-02-21 | [7 empty] | Wind | [16 empty] | Steuben | NY | NYSEG |  | Stoney Ridge - Canadaigua 230kV | 10-2025 | [9 empty] | Prattsburgh Wind, LLC | [8 empty] | 2023-01-11 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 147 | 147 |  | 2022-07-31 | 10-2025 |  |  |  | SRIS, FS | 2023-01-11 | 12-2025
NYISO | KCE NY 10 | 0804 | 2019-03-22 | [7 empty] | Energy Storage | [16 empty] | Erie | NY | NYSEG |  | Erie Substation 34.5kV | 08-2026 | [9 empty] | KCE NY 10, LLC | [8 empty] | 2022-10-20 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-04-30 | 08-2026 |  |  |  | FES, SIS, FS | 2022-04-28 | 10-2026
NYISO | Oxbow Hill Solar | 0805 | 2019-03-22 | [7 empty] | Solar | [16 empty] | Madison | NY | NM-NG |  | Fenner 115kV Substation | 10-2025 | [9 empty] | Oxbow Hill Solar, LLC | [8 empty] | 2023-02-09 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 140 | 140 |  | 2024-04-30 | 10-2025 |  |  |  | FES, FS | 2023-01-11 | 12-2026
NYISO | Hilltop Solar | 0807 | 2019-03-28 | [7 empty] | Solar | [16 empty] | Rensselaer | NY | NM-NG |  | Eastover - Schaghticoke 115kV | 04/2028 | [9 empty] | SunEast Hilltop Solar LLC | [8 empty] | 2021-04-07 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-09-30 | 03/2028 |  |  |  | SIS, FS | 2021-02-23 | 05/2028
NYISO | Cider Solar | 0811 | 2019-04-03 | [7 empty] | Solar | [16 empty] | Genesee | NY | NYPA |  | Dysinger - New Rochester 345kV | 05/2026 | [9 empty] | Hecate Energy Cider Solar LLC | [8 empty] | 2023-01-11 | [28 empty] | IA Completed | [30 empty] | 500 | 500 |  | 2024-06-30 | 05/2026 |  |  |  | SRIS, FS | 2023-01-11 | 01-2027
NYISO | Bayonne Energy Center III | 0815 | 2019-04-05 | [7 empty] | Energy Storage | [16 empty] | Kings | NY | ConEd |  | Gowanus 345kV | 07-2026 | [9 empty] | Bayonne Energy Center | [8 empty] | 2023-04-25 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 49.8 | 49.8 |  | 2024-09-30 | 08-2026 |  |  |  | SRIS, FS | 2023-01-11 | 09-2026
NYISO | Setauket Energy Storage | 0825 | 2019-04-15 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Port Jefferson - Terryville 69kV | 01-2028 | [9 empty] | Setauket Energy Storage, LLC | [37 empty] | FS in Progress | [30 empty] | 65.3 | 65.3 |  | 2023-05-31 | 03-2028 |  |  |  | FES, SRIS |  | 04-2028
NYISO | Arthur Kill Energy Storage 1 | 0827 | 2019-04-22 | [7 empty] | Energy Storage | [16 empty] | Richmond | NY | ConEd |  | Fresh Kills 13.8kV | 04-2025 | [9 empty] | GB Arthur Kill Storage LLC | [8 empty] | 2022-07-07 | [28 empty] | IA Completed | [30 empty] | 15 | 15 |  | 2023-11-30 | 07-2025 |  |  |  | FS | 2022-01-20 | 09-2025
NYISO | Valley Solar | 0828 | 2019-04-24 | [7 empty] | Solar | [16 empty] | Tioga | NY | NYSEG |  | Owego 34.5kV Substation | 08-2024 | [9 empty] | SunEast Valley Solar LLC | [8 empty] | 2021-01-22 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2022-04-30 | 09-2024 |  |  |  | SIS, FS | 2020-11-03 | 11-2024
NYISO | CS Hawthorn Solar | 0832 | 2019-05-06 | [7 empty] | Solar | [16 empty] | Rensselaer | NY | NM-NG |  | North Troy - Hoosick 115kV | 05-2026 | [9 empty] | Granada Solar, LLC | [8 empty] | 2022-07-13 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 04-2026 |  |  |  | FES, FS | 2022-06-27 | 12-2026
NYISO | Dolan Solar | 0833 | 2019-05-06 | [7 empty] | Solar | [16 empty] | Washington | NY | NM-NG |  | Battenkill - Mohican 115kV | 03-2025 | [9 empty] | Dolan Solar, LLC | [8 empty] | 2021-04-13 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 02-2025 |  |  |  | SIS, FS | 2021-03-01 | 12-2026
NYISO | Luyster Creek Energy Storage 2 | 0834 | 2019-05-07 | [7 empty] | Energy Storage | [16 empty] | Queens | NY | ConEd |  | Astoria West 138kV | 01-2027 | [9 empty] | Astoria Generating Company, LP | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 79 | 79 |  | 2024-10-31 | 01-2027 |  |  |  | SRIS |  | 05-2027
NYISO | Luyster Creek Energy Storage 1 | 0835 | 2019-05-07 | [7 empty] | Energy Storage | [16 empty] | Queens | NY | ConEd |  | Astoria West 138kV | 02-2026 | [9 empty] | Astoria Generating Company, LP | [8 empty] | 2023-02-22 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 56.3 | 57.3 |  | 2023-01-31 | 03-2026 |  |  |  | SRIS, FS | 2023-01-11 | 05-2026
NYISO | NY37 Solar | 0843 | 2019-05-17 | [7 empty] | Solar | [16 empty] | Jefferson | NY | NM-NG |  | Coffeen - West Adams 115kV Substation | 11-2025 | [9 empty] | Sandy Creek Solar LLC | [8 empty] | 2023-05-17 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2023-05-31 | 10-2025 |  |  |  | SIS, FS | 2023-04-04 | 11-2025
NYISO | Fairway Solar | 0848 | 2019-05-20 | [7 empty] | Solar | [16 empty] | St. Lawrence | NY | NM-NG |  | McIntyre - Corning 115kV (Line#6) | 02-2025 | [9 empty] | SunEast Fairway Solar LLC | [8 empty] | 2021-05-10 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2022-03-31 | 02-2025 |  |  |  | SIS, FS | 2021-05-05 | 03-2025
NYISO | Cayuga Load | 0850 | 2019-05-21 | [7 empty] | Load | [16 empty] | Cayuga | NY | NYSEG |  | Milliken 115kV | 12-2026 | [9 empty] | Cayuga Operating Company, LLC | [37 empty] | FS Pending | [30 empty] | 50 | 50 |  | 2024-04-30 |  |  |  |  | SIS
NYISO | NY13 Solar | 0855 | 2019-05-24 | [7 empty] | Solar | [16 empty] | Washington | NY | NM-NG |  | Mohican - Schaghticoke 115kV | 06-2025 | [9 empty] | Bald Mountain Solar LLC | [8 empty] | 2021-10-07 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2022-04-30 | 06-2025 |  |  |  | SIS, FS | 2021-08-27 | 06-2025
NYISO | Highbanks Solar | 0863 | 2019-05-29 | [7 empty] | Solar | [16 empty] | Livingston | NY | RG&E |  | S158 High banks 34.5 kV | 12-2025 | [9 empty] | Highbanks Solar LLC | [8 empty] | 2022-10-17 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-04-30 | 01-2026 |  |  |  | SIS, FS | 2022-08-05 | 02-2026
NYISO | NY38 Solar | 0864 | 2019-05-29 | [7 empty] | Solar | [16 empty] | Jefferson | NY | NM-NG |  | Coffeen - West Adams 115kV | 12-2026 | [9 empty] | Greens Corners Solar LLC | [8 empty] | 2023-01-11 | [28 empty] | IA Completed | [30 empty] | 120 | 120 |  | 2024-04-30 | 11-2026 |  |  |  | SRIS, FS | 2023-01-11 | 12-2026
NYISO | Flat Hill Solar | 0865 | 2019-05-31 | [7 empty] | Solar | [16 empty] | Herkimer | NY | NM-NG |  | Inghams-Valley 46kV Line 27 | 11-2025 | [9 empty] | SunEast Flat Hill Solar LLC | [8 empty] | 2022-09-15 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2023-08-31 | 11-2025 |  |  |  | SIS, FS | 2022-08-19 | 12-2025
NYISO | Brookside Solar | 0880 | 2019-06-10 | [7 empty] | Solar | [16 empty] | Franklin | NY | NYSEG |  | Chateaugay - Willis 115kV | 01-2027 | [9 empty] | Brookside Solar, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 100 | 100 |  | 2024-10-31 | 01-2027 |  |  |  | SRIS |  | 06-2027
NYISO | Riverside Solar | 0882 | 2019-06-10 | [7 empty] | Solar | [16 empty] | Jefferson | NY | NM-NG |  | Lyme Substation 115kV | 09-2027 | [9 empty] | Riverside Solar, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 100 | 100 |  | 2024-10-31 | 09-2027 |  |  |  | FES, SRIS |  | 12-2027
NYISO | Garnet Energy Center | 0883 | 2019-06-11 | [7 empty] | Solar | [16 empty] | Cayuga | NY | NYPA |  | Pannell - Clay 345kV | 10-2025 | [9 empty] | Garnet Energy Center, LLC | [8 empty] | 2023-01-11 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 200 | 200 |  | 2023-01-31 | 10-2025 |  |  |  | FS | 2023-01-11 | 11-2025
NYISO | Grassy Knoll Solar | 0885 | 2019-06-12 | [7 empty] | Solar | [16 empty] | Herkimer | NY | NM-NG |  | Watkins Rd - Inghams 115kV | 11-2025 | [9 empty] | SunEast Grassy Knoll Solar LLC | [8 empty] | 2022-09-15 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2023-08-31 | 11-2025 |  |  |  | SIS, FS | 2022-08-15 | 12-2025
NYISO | CH Uprate | 0887 | 2019-06-12 | [7 empty] | DC | [16 empty] | Quebec-NY | NY | NYPA |  | Astoria Annex 345kV | 05-2026 | [9 empty] | CHPE LLC | [8 empty] | 2022-07-08 | [28 empty] | Under Construction | [30 empty] | 250 | 250 |  | 2023-06-30 | 05-2026 |  |  |  | SRIS, FS | 2023-01-11 | 05-2026
NYISO | Scriba-Volney Series Reactor | 0899 | 2019-08-02 | [7 empty] | AC | [16 empty] | Oswego | NY | NM-NG |  | Volney - Scriba 345 kV | 03-2026 | [9 empty] | Sithe/Independence Power Partners, LP | [37 empty] | Accepted Cost Allocation/IA in Progress | [33 empty] | 2024-02-08 |  |  |  |  | SIS
NYISO | Harlem River Yard | 0907 | 2019-09-04 | [7 empty] | Energy Storage | [16 empty] | Queens | NY | NYPA |  | Hell Gate 138kV | 10-2026 | [9 empty] | Harlem River ESS, LLC | [8 empty] | 2023-02-10 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 79.9 | 79.9 |  | 2023-01-31 | 10-2026 |  |  |  | SRIS, FS | 2023-01-11 | 12-2026
NYISO | Astoria BES to 27kV North Queens | 0930 | 2019-10-25 | [7 empty] | Energy Storage | [16 empty] | Queens | NY | ConEd |  | North Queens 27kV | 04-2025 | [9 empty] | Astoria Generating Company, LP | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 15 | 15 |  | 2024-05-31 | 05-2025 |  |  |  | SIS, FS | 2024-04-16 | 12-2025
NYISO | Astoria Energy Storage | 0931 | 2019-10-28 | [7 empty] | Energy Storage | [16 empty] | Queens | NY | ConEd |  | Astoria West 138kV | 10-2026 | [9 empty] | East River ESS, LLC | [8 empty] | 2023-01-11 | [28 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 100 | 100 |  | 2023-03-31 | 04-2026 |  |  |  | SRIS, FS | 2023-01-11 | 03-2026
NYISO | Hatchery Solar | 0932 | 2019-10-29 | [7 empty] | Solar | [16 empty] | Livingston | NY | NM-NG |  | Caledonia - Golah 34.5 kV | 04-2025 | [9 empty] | Hatchery Solar LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-11-30 | 05-2025 |  |  |  | SIS, FS | 2024-10-10 | 05-2025
NYISO | Hemlock Ridge Solar | 0950 | 2019-11-21 | [7 empty] | Solar | [16 empty] | Orleans | NY | NM-NG |  | Lockport - Mortimer 115kV | 06-2027 | [9 empty] | Hemlock Ridge Solar LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 200 | 200 |  | 2024-10-31 | 06-2027 |  |  |  | SRIS |  | 08-2027
NYISO | Sugar Maple Solar | 0953 | 2019-12-05 | [7 empty] | Solar | [16 empty] | Lewis | NY | NM-NG |  | North Carthage - Taylorville #8 and Black River - Taylorville #2 115kV | 09-2027 | [9 empty] | Sugar Maple Solar, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 125 | 125 |  | 2024-10-31 | 09-2027 |  |  |  | SRIS |  | 12-2027
NYISO | Holtsville 138kV Energy Storage | 0956 | 2019-12-10 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | West Bus 138 kV | 06-2026 | [9 empty] | Holtsville Energy Storage, LLC | [8 empty] | 2023-01-11 | [28 empty] | IA Completed | [30 empty] | 110 | 110 |  | 2024-03-31 | 07-2026 |  |  |  | SRIS, FS | 2023-01-11 | 09-2026
NYISO | Holbrook Energy Storage | 0957 | 2019-12-10 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Holtsville - Patchogue 69kV | 06-2027 | [9 empty] | Holbrook Energy Storage, LLC | [37 empty] | FS in Progress | [30 empty] | 76.8 | 76.8 |  | 2024-01-31 | 10-2027 |  |  |  | SRIS |  | 12-2027
NYISO | Cobleskill Solar | 0960 | 2019-12-12 | [7 empty] | Solar | [16 empty] | Schoharie | NY | NM-NG |  | Cobleskill - Schoharie 69KV | 11-2025 | [9 empty] | SWEB Development USA, LLC | [37 empty] | FS in Progress | [30 empty] | 20 | 20 |  | 2023-10-31 | 11-2025 |  |  |  | FES, SIS |  | 12-2025
NYISO | Yaphank Energy Storage | 0965 | 2019-12-21 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | William Floyd - Brookhaven 69kV | 03-2026 | [9 empty] | Yaphank Energy Storage, LLC | [8 empty] | 2024-05-31 | [28 empty] | IA Completed | [30 empty] | 76.8 | 77.6 |  | 2024-06-30 | 08-2026 |  |  |  | FS | 2023-01-11 | 09-2026
NYISO | KCE NY 5 | 0967 | 2019-12-27 | [7 empty] | Energy Storage | [16 empty] | Ulster | NY | CHG&E |  | Ohioville 115 kV | 11-2027 | [9 empty] | KCE NY 5 LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 94 | 94 |  | 2024-10-31 | 11-2027 |  |  |  | SRIS |  | 12-2027
NYISO | East Setauket Energy Storage | 0971 | 2020-01-10 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Holbrook - Miller Place 138kV | 02-2027 | [9 empty] | Savion, LLC | [37 empty] | FS in Progress | [30 empty] | 125 | 125 |  | 2023-12-31 | 03-2027 | [5 empty] | 04-2027
NYISO | Warner Hill Solar | 0972 | 2020-01-10 | [7 empty] | Solar | [16 empty] | Schoharie | NY | NM-NG |  | Middleburg Tap - Middleburg 69kV | 03-2026 | [9 empty] | SWEB Development USA, LLC | [37 empty] | FS in Progress | [30 empty] | 20 | 20 |  | 2023-09-30 | 03-2026 |  |  |  | FES, SIS |  | 05-2026
NYISO | North Country Data Center | 0979 | 2020-01-22 | [7 empty] | Load | [16 empty] | St. Lawrence | NY | NYPA |  | Reynolds 115kV | 12-2024 | [9 empty] | North Country Data Center | [37 empty] | SRIS/SIS Approved | [30 empty] | 176 | 176 |  | 2023-07-31 |  |  |  |  | SIS
NYISO | Sunrise Wind II | 0987 | 2020-01-29 | [7 empty] | Off-Shore Wind | [16 empty] | Suffolk | NY | LIPA |  | Holbrook 138kV | 06-2025 | [9 empty] | Sunrise Wind LLC | [8 empty] | 2023-01-11 | [28 empty] | IA Completed | [30 empty] | 44 | 44 |  | 2023-09-30 | 08-2025 |  |  |  | FS | 2023-01-11 | 03-2026
NYISO | Alabama Solar Park LLC | 0995 | 2020-02-27 | [7 empty] | Solar | [16 empty] | Genesee | NY | NM-NG |  | Lockport - Batavia 115kV (Line#112) | 07-2028 | [9 empty] | Alabama Solar Park LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 130 | 130 |  | 2024-10-31 | 07-2028 | [5 empty] | 10-2028
NYISO | SunEast Flat Stone Solar LLC | 1000 | 2020-03-18 | [7 empty] | Solar | [16 empty] | Oneida | NY | NM-NG |  | Oneida - Rome 115kV | 09-2026 | [9 empty] | SED NY Holdings LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-03-31 | 09-2026 |  |  |  | SIS, FS | 2024-03-14 | 11-2026
NYISO | Clear View Solar | 1003 | 2020-04-06 | [7 empty] | Solar | [16 empty] | Steuben | NY | NYSEG |  | Eelpot Road 34.5 kV | 11-2025 | [9 empty] | Clear View LLC | [8 empty] | 2022-09-06 | [28 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-05-31 | 10-2025 |  |  |  | SIS, FS | 2022-07-08 | 12-2025
NYISO | NYC Energy LLC - Phase 2 | 1007 | 2020-04-22 | [7 empty] | Energy Storage | [16 empty] | Kings | NY | ConEd |  | Hudson Ave 138 kV | 05-2027 | [9 empty] | NYC Energy | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 220.1 | 220.1 |  | 2024-10-31 | 05-2027 |  |  |  | SRIS |  | 06-2027
NYISO | Yellow Barn Solar | 1009 | 2020-04-30 | [7 empty] | Solar | [16 empty] | Tompkins | NY | NYSEG |  | Milliken - Etna 115 kV line #975 | 11-2025 | [9 empty] | Yellow Barn Solar, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 160 | 160 |  | 2024-10-31 | 11-2025 |  |  |  | SRIS |  | 12-2025
NYISO | Suffolk County Storage II | 1012 | 2020-05-04 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Southold 69 kV | 01-2028 | [9 empty] | Suffolk County Energy Storage II | [37 empty] | FS in Progress | [30 empty] | 76.8 | 76.8 |  | 2023-05-31 | 03-2028 |  |  |  | FES, SRIS |  | 04-2028
NYISO | Somers Solar, LLC | 1015 | 2020-05-05 | [7 empty] | Solar | [16 empty] | Washington | NY | NM-NG |  | Mohican - Battenkill 115kV | 09-2026 | [9 empty] | Granada Solar, LLC | [37 empty] | IA Completed | [30 empty] | 20 | 20 |  | 2024-12-31 | 10-2026 |  |  |  | FS | 2024-03-14 | 12-2026
NYISO | Mill Point Solar | 1031 | 2020-06-18 | [7 empty] | Energy Storage + Solar | [16 empty] | Montgomery | NY | NM-NG |  | Marcy - New Scotland 345kV | 07-2028 | [9 empty] | ConnectGen Montgomery County LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 250 | 250 |  | 2024-10-31 | 07-2028 |  |  |  | SRIS |  | 12-2028
NYISO | Morris Solar | 1039 | 2021-01-06 | [7 empty] | Solar | [16 empty] | St. Lawrence | NY | NM-NG |  | Battle Hill - Balmat 115kV | 10-2025 | [9 empty] | SED NY Holdings LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-03-31 | 11-2025 |  |  |  | SIS, FS | 2024-03-14 | 12-2025
NYISO | Millers Grove Solar | 1047 | 2020-07-09 | [7 empty] | Solar | [16 empty] | Herkimer | NY | NM-NG |  | Porter - Watkins 115kV | 09-2026 | [9 empty] | SED NY Holdings LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-05-31 | 09-2026 |  |  |  | SIS, FS | 2024-03-28 | 12-2026
NYISO | Transit Solar | 1051 | 2020-07-21 | [7 empty] | Solar | [16 empty] | Genesee | NY | NM-NG |  | S.E Batavia - Golah 115kV | 08-2025 | [9 empty] | SED NY Holding LLC | [37 empty] | FS in Progress | [30 empty] | 20 | 20 |  | 2024-03-31 | 09-2025 |  |  |  | SIS, FS | 2024-03-14 | 12-2025
NYISO | Teele | 1061 | 2020-07-31 | [7 empty] | Solar | [16 empty] | St. Lawrence | NY | NM-NG |  | Alcoa - N. Ogdensburg 115 kV | 03-2026 | [9 empty] | ACE DEVCO NC, LLC | [37 empty] | FS in Progress | [30 empty] | 19.8 | 19.8 |  | 2024-01-31 | 05-2026 |  |  |  | SIS |  | 06-2026
NYISO | Somerset Solar | 1079 | 2020-08-18 | [7 empty] | Solar | [16 empty] | Niagara | NY | NYSEG |  | Kintigh 345 kV | 01-2027 | [9 empty] | Somerset Solar, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 125 | 125 |  | 2024-10-31 | 01-2027 |  |  |  | SRIS |  | 03-2027
NYISO | Mineral Basin Solar Power | 1080 | 2020-08-21 | [7 empty] | Solar | [16 empty] | Clearfield | PA | NYSEG |  | Homer City - Mainesburg 345KV | 10-2027 | [9 empty] | Mineral Basin Solar Power, LLC | [37 empty] | FS in Progress | [30 empty] | 401.6 | 401.6 |  | 2024-10-31 | 10-2027 |  |  |  | SRIS |  | 05-2028
NYISO | Flat Creek Solar | 1089 | 2020-09-04 | [7 empty] | Solar | [16 empty] | Montgomery | NY | NYPA |  | Edic to Princetown 345kV Line 352 | 10-2028 | [9 empty] | SED NY Holding LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 200 | 200 |  | 2024-10-31 | 10-2028 |  |  |  | SRIS |  | 11-2028
NYISO | Alfred Oaks Solar | 1096 | 2020-09-14 | [7 empty] | Energy Storage + Solar | [16 empty] | Allegany | NY | NYSEG |  | Andover - Palmeter 115 kV, Line 932 | 09-2027 | [9 empty] | Northland Power U.S. Projects | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 100 | 100 |  | 2024-10-31 | 09-2027 |  |  |  | SRIS |  | 11-2027
NYISO | CLIES 20 MW | 1113 | 2020-11-18 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Sills Road 138 kV | 12-2025 | [9 empty] | Caithness LI Energy Storage, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-07-31 | 10-2025 |  |  |  | SIS, FS | 2024-06-13 | 12-2025
NYISO | Flat Creek Solar 2 | 1115 | 2020-11-23 | [7 empty] | Solar | [16 empty] | Montgomery | NY | NYPA |  | Edic - Princetown 345 kV Line# 352 | 10-2028 | [9 empty] | SED NY Holdings LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 100 | 100 |  | 2024-10-31 | 10-2028 |  |  |  | SRIS |  | 11-2028
NYISO | CLIES 70MW | 1117 | 2020-11-25 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Sills Road 138kV | 12-2026 | [9 empty] | Caithness LI Energy Storage, LLC | [37 empty] | FS in Progress | [30 empty] | 70 | 70 |  | 2024-09-30 | 12-2026 |  |  |  | SRIS |  | 12-2026
NYISO | East Fishkill | 1122 | 2020-12-11 | [7 empty] | Energy Storage | [16 empty] | Dutchess | NY | CHG&E |  | Shenandoah 115kV | 05-2028 | [9 empty] | Microgrid Networks, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 205 | 205 |  | 2024-10-31 | 05-2028 |  |  |  | SRIS |  | 11-2028
NYISO | KCE NY 29 | 1123 | 2020-12-14 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Kings 138 kV | 09-2027 | [9 empty] | KCE NY 29, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 150 | 150 |  | 2024-10-31 | 09-2027 | [5 empty] | 10-2027
NYISO | Northern New York Priority Transmission Project (NNYPTP) | 1125 | 2020-12-22 | [7 empty] | AC | [16 empty] | St. Lawrence-Lewis | NY | NYPA, NM-NG |  | 1. Moses 230 kV substation 2. Haverstock 345 kV sub (new) 3. Massena 230 kV substation 4. Adirondack 345 kV sub (new) 5. Willis 230 kV substation 6. Ryan & Patnode 230 kV substations 7. Chases Lake 345 kV sub (new) 8. Marcy 345 kV sub 9. Edic 345 kV sub | 12-2025 | [9 empty] | New York Power Authority and National Grid | [37 empty] | Accepted Cost Allocation/IA in Progress | [33 empty] | 2023-05-31 |  |  |  |  | FS | 2023-02-14
NYISO | Hoffman Falls Wind | 1130 | 2021-01-27 | [7 empty] | Wind | [16 empty] | Madison | NY | NM-NG |  | Cortland - Fenner 115kV Line #3 | 10-2027 | [9 empty] | Liberty Renewables Inc. | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 72 | 72 |  | 2024-10-31 | 10-2027 | [5 empty] | 12-2027
NYISO | Agricola Wind | 1148 | 2021-03-10 | [7 empty] | Wind | [16 empty] | Cayuga | NY | NYSEG |  | Milliken to Wright Ave 115 kV line #973 | 10-2027 | [9 empty] | Liberty Renewables Inc. | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 97 | 97 |  | 2024-10-31 | 10-2027 |  |  |  | SRIS |  | 12-2027
NYISO | Moss Ridge Solar | 1150 | 2021-03-16 | [7 empty] | Solar | [16 empty] | St. Lawrence | NY | NM-NG |  | Corning - Battle Hill 115 kV line #4 | 09-2028 | [9 empty] | Moss Ridge Solar 1, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 60 | 60 |  | 2024-10-31 | 10-2028 |  |  |  | SRIS |  | 11-2028
NYISO | York Run Solar | 1151 | 2021-03-18 | [7 empty] | Solar | [16 empty] | Chautauqua | NY | NM-NG |  | Falconer - Warren 115 kV line #171 | 05-2026 | [9 empty] | York Run Solar, LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 90 | 90 |  | 2024-10-31 | 06-2026 |  |  |  | SRIS |  | 08-2026
NYISO | Cody Road Wind Farm | 1156 | 2021-04-08 | [7 empty] | Wind | [16 empty] | Madison | NY | NM-NG |  | Cortland - Fenner Line #3 115 kV | 07-2025 | [9 empty] | Green Power Energy, LLC | [37 empty] | FS in Progress | [30 empty] | 19.9 | 19.9 |  | 2024-03-31 | 07-2025 |  |  |  | FES, SIS |  | 07-2025
NYISO | BR Benson Mines Solar | 1166 | 2021-05-07 | [7 empty] | Solar | [16 empty] | St. Lawrence | NY | NM-NG |  | Brown's Falls to Newton Falls #22 34.5kV Line | 07-2026 | [9 empty] | BR Project 1 LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 12.1 | 12.1 |  | 2024-11-30 | 08-2026 |  |  |  | SIS, FS | 2024-10-16 | 10-2026
NYISO | ELP Stuyvesant Solar | 1171 | 2021-05-14 | [7 empty] | Solar | [16 empty] | Columbia | NY | Transco |  | Valkin - Falls Park 115 kV line #19 | 08-2026 | [9 empty] | ELP Stuyvesant Solar LLC | [37 empty] | FS in Progress | [30 empty] | 20 | 20 |  | 2024-01-31 | 08-2026 |  |  |  | SIS |  | 11-2026
NYISO | NY125A - Fort Covington Solar | 1183 | 2021-05-20 | [7 empty] | Solar | [16 empty] | Franklin | NY | NYPA |  | Moses-Willis 230 kV (MW1) | 07-2027 | [9 empty] | Fort Covington Solar LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 250 | 250 |  | 2024-10-31 | 07-2027 |  |  |  | SRIS |  | 08-2027
NYISO | NY125B - Two Rivers Solar | 1184 | 2021-05-20 | [7 empty] | Solar | [16 empty] | St-Lawrence | NY | NYPA |  | Moses-Willis 230kV (MW2) | 07-2027 | [9 empty] | Boralex US Development | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 200 | 200 |  | 2024-10-31 | 07-2027 |  |  |  | SRIS |  | 08-2027
NYISO | North Seneca Solar Project, LLC | 1188 | 2021-05-27 | [7 empty] | Solar | [16 empty] | Seneca | NY | NM-NG |  | Hooks Road - Elbridge 115kV line#7 | 06-2027 | [9 empty] | North Seneca Solar Project | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 105 | 105 |  | 2024-10-31 | 06-2027 |  |  |  | SRIS |  | 09-2027
NYISO | Crane Brook Solar Project, LLC | 1194 | 2021-06-03 | [7 empty] | Solar | [16 empty] | Cayuga | NY | NM-NG |  | State St - Clinton Corn 115kV Line | 07-2027 | [9 empty] | Crane Brook Solar Project | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 130 | 130 |  | 2024-10-31 | 08-2027 |  |  |  | SRIS |  | 09-2027
NYISO | St Lawrence Data and Agricultural Center | 1213 | 2021-06-28 | [7 empty] | Load | [16 empty] | St. Lawrence | NY | NM-NG |  | Dennison 115kV substation | 01-2026 | [9 empty] | Petawatt Holdings, Inc. | [37 empty] | SRIS/SIS Approved | [30 empty] | 200 | 200 |  | 2023-01-14 |  |  |  |  | SIS
NYISO | 18405 Scotch Ridge | 1227 | 2021-08-04 | [7 empty] | Solar | [16 empty] | Schenectady | NY | NM-NG |  | Rotterdam-Schoharie 69kV line#18 | 09-2025 | [9 empty] | Nexamp Solar | [37 empty] | FS in Progress | [30 empty] | 20 | 20 |  | 2024-03-31 | 10-2025 |  |  |  | SIS |  | 12-2025
NYISO | Sugar Maple Energy Storage | 1237 | 2021-08-24 | [7 empty] | Energy Storage | [16 empty] | Jefferson | NY | NM-NG |  | North Carthage-Taylorville #8 and Black River-Taylorville #2 115 kV lines | 06-2026 | [9 empty] | Sugar Maple Solar | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-10-31 | 09-2026 |  |  |  | SIS |  | 12-2026
NYISO | Barrett Hempstead Battery Storage | 1254 | 2021-09-22 | [7 empty] | Energy Storage | [16 empty] | Nassau | NY | LIPA |  | Barrett to Long Beach 33 kV circuit No 1(33-224) | 12-2024 | [9 empty] | Barrett Hempstead Battery Storage | [37 empty] | FS in Progress | [30 empty] | 40 | 40 |  | 2023-05-31 | 01-2025 |  |  |  | SRIS |  | 03-2025
NYISO | Holtsville Brookhaven Battery Storage | 1255 | 2021-09-22 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Line 69-849 from West Yaphank to North Bellport | 12-2025 | [9 empty] | Holtsville Brookhaven Battery Storage | [37 empty] | FS in Progress | [30 empty] | 79.9 | 79.9 |  | 2023-04-30 | 01-2026 |  |  |  | SRIS |  | 03-2026
NYISO | Canal Southampton Battery Storage | 1256 | 2021-09-22 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Canal Substation 138kV | 12-2024 | [9 empty] | Canal Southampton Battery Storage | [37 empty] | FS in Progress | [30 empty] | 100 | 100 |  | 2023-05-31 | 01-2025 |  |  |  | SRIS |  | 03-2025
NYISO | Edwards Calverton Battery Storage | 1257 | 2021-09-22 | [7 empty] | Energy Storage | [16 empty] | Suffolk | NY | LIPA |  | Edwards Avenue Substation at 138 kV | 12-2024 | [9 empty] | Edwards Calverton Battery Storage | [37 empty] | FS in Progress | [30 empty] | 60 | 60 |  | 2023-05-31 | 01-2025 |  |  |  | SRIS |  | 03-2025
NYISO | CPNY-X | 1288 | 2021-11-23 | [7 empty] | DC | [16 empty] | Delaware, Queens | NY | NYSEG, ConEd |  | Fraser 345 kV and Rainey 345 kV substations | 06-2028 | [9 empty] | Clean Path New York LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 1300 | 1300 |  | 2024-10-31 | 06-2028 |  |  |  | SRIS |  | 12-2028
NYISO | Propel NY Energy - Alternate Solution 5 | 1289 | 2021-10-11 | [7 empty] | AC | [16 empty] | Nassau, Queens, Bronx, Westchester | NY | LIPA, ConEd, NYPA |  | Sprain Brook 345 kV; Tremont 345 kV; East Garden City 345 kV; Barrett 138 kV; East Garden City 138 kV; Shore Road 138 kV; Syosset 138 kV; Ruland Rd 138 kV | 12-2028 | [9 empty] | New York Power Authority / New York Transco LLC. | [37 empty] | FS in Progress | [33 empty] | 2024-12-31 |  |  |  |  | SIS
NYISO | Richmond Spoke | 1308 | 2021-12-02 | [7 empty] | AC | [16 empty] | Richmond | NY | ConEd |  | Goethals - Gowanus 345 kV | 12-2030 | [9 empty] | New York Power Authority | [37 empty] | SRIS/SIS Approved | [33 empty] | 2022-07-31 |  |  |  |  | SIS
NYISO | Queensbury BESS | 1313 | 2021-12-12 | [7 empty] | Energy Storage | [16 empty] | Warren | NY | NM-NG |  | Queensbury 34.5 kV substation | 09-2026 | [9 empty] | Saturn Energy Storage LLC | [37 empty] | FS in Progress | [30 empty] | 20 | 20 |  | 2024-05-31 | 11-2026 |  |  |  | SIS |  | 12-2026
NYISO | SDC St. Lawrence | 1315 | 2021-12-20 | [7 empty] | Load | [16 empty] | St. Lawrence | NY | NYPA |  | Moses-Reynolds MRG-1 and Moses-Reynolds MRG-2 at 115kV | 08-2025 | [9 empty] | Sabey Data Center Properties, LLC | [37 empty] | SRIS/SIS Approved | [30 empty] | 120 | 120 |  | 2022-09-30 |  |  |  |  | SIS
NYISO | ELP Granby Solar II | 1329 | 2022-02-11 | [7 empty] | Energy Storage + Solar | [16 empty] | Oswego | NY | NM-NG |  | Curtis Street - Teall 115 kV | 09-2026 | [9 empty] | ELP Granby Solar II LLC | [37 empty] | Accepted Cost Allocation/IA in Progress | [30 empty] | 20 | 20 |  | 2024-11-30 | 10-2026 |  |  |  | FES, SIS, FS | 2024-10-07 | 12-2026
NYISO | Queensboro Renewable Express Circuit A | 1365 | 2022-04-15 | [7 empty] | DC | [16 empty] | Queens | NY | ConEd |  | Rainey 345 kV substation and Vernon 138 kV substation | 04-2029 | [9 empty] | Queensboro Development, LLC | [37 empty] | SRIS/SIS Approved | [33 empty] | 2022-07-31 |  |  |  |  | SIS
NYISO | Queensboro Renewable Express Circuit B | 1366 | 2022-04-15 | [7 empty] | DC | [16 empty] | Queens | NY | ConEd |  | Rainey 345 kV substation and Vernon 138 kV substation | 04-2029 | [9 empty] | Queensboro Development, LLC | [37 empty] | SRIS/SIS Approved | [33 empty] | 2024-03-31 |  |  |  |  | SIS
NYISO | Kings Spoke | 1435 | 2022-09-12 | [7 empty] | AC | [16 empty] | Kings | NY | ConEd |  | Greenwood-Bensonhurst and Farragut-Brownsville 138 kV feeders | 12-2028 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation II | [37 empty] | SRIS/SIS Pending | [33 empty] | 2023-04-30
NYISO | Massena Green Hydrogen | 1446 | 2022-10-05 | [7 empty] | Load | [16 empty] | St Lawrence | NY | NYPA |  | Haverstock - Adirondack 345 kV line 1 | 10-2025 | [9 empty] | Air Products and Chemicals Inc | [37 empty] | SRIS/SIS Approved | [30 empty] | 110 | 110 |  | 2023-12-31 |  |  |  |  | SIS
NYISO | Digihost load | 1465 | 2022-11-14 | [7 empty] | Load | [16 empty] | Niagara | NY | NM-NG |  | Walck Rd. 115kV | 04-2024 | [9 empty] | Digihost Technologies, Inc. | [37 empty] | SRIS/SIS Pending | [30 empty] | 50.2 | 50.2 |  | 2023-06-30
NYISO | 580 STAMP load increase | 1484 | 2022-12-02 | [7 empty] | Load | [16 empty] | Genesee | NY | NM-NG |  | 115 kv STAMP substation | 12-2025 | [9 empty] | GCEDC | [37 empty] | SRIS/SIS Approved | [30 empty] | 300 | 300 |  | 2023-12-31 |  |  |  |  | SIS
NYISO | Westchester Wind | 1530 | 2023-03-02 | [7 empty] | AC | [16 empty] | Westchester | NY | ConEd |  | Sprainbrook-Eastview 345kV #1N, #1S, and #2S. | 12-2028 | [9 empty] | New York Power Authority | [37 empty] | SRIS/SIS Pending | [33 empty] | 2023-05-31
NYISO | White Pine Phase 1 | 1536 | 2023-03-11 | [7 empty] | Load | [16 empty] | Onondaga | NY | NM-NG |  | Clay 345 kV Substation | 06-2026 | [9 empty] | Micron New York Semiconductor Manufacturing LLC | [37 empty] | SRIS/SIS in Progress | [30 empty] | 480 | 480 |  | 2024-02-29
NYISO | Liberty Green Line | 1555 | 2023-05-12 | [7 empty] | AC | [16 empty] | New York County | NY | ConEd, PJM |  | Con Edison W 49th St 345kV Substation | 01-2029 | [9 empty] | North Bergen Liberty Generating LLC | [37 empty] | FES Pending | [33 empty] | 2023-08-31
NYISO | Micron Fab 2 | 1627 | 2023-10-31 | [7 empty] | Load | [16 empty] | Onondaga | NY | NM-NG |  | National Grid Clay 345 kV Substation | 09-2030 | [9 empty] | Micron New York Semiconductor Manufacturing LLC | [37 empty] | SRIS/SIS in Progress | [30 empty] | 576 | 507 |  | 2024-06-30
NYISO | POWI Project | 1646 | 2023-11-30 | [7 empty] | Load | [16 empty] | Albany | NY | NM-NG |  | New Scotland to Knickerbocker 345kV line | 01-2027 | [9 empty] | P&M Brick LLC | [37 empty] | SRIS/SIS in Progress | [30 empty] | 50 | 50 |  | 2024-07-31
NYISO | Designated Public Policy Project Rainey Breaker Replacement | 1667 | 2024-01-12 | [7 empty] | AC | [16 empty] | New York | NY | ConEd |  | Rainey 345kV Substation | 05-2030 | [9 empty] | Consolidated Edison Company of New York | [37 empty] | FS Pending | [33 empty] | 2024-07-31
NYISO | Lake Mariner Data II | 1670 | 2024-01-23 | [7 empty] | Load | [16 empty] | Niagara | NY | NYSEG |  | Kintigh 345kV Substation | 04-2025 | [9 empty] | Lake Mariner Data LLC | [37 empty] | SRIS/SIS in Progress | [30 empty] | 250 | 250 |  | 2024-07-31
NYISO | Meyer Substation Rebuild and South Perry Substation Rebuild | 1671 | 2024-02-02 | [7 empty] | AC | [16 empty] | Wyoming/Livingston | NY | NYSEG |  | Meyer 115kV, 34.5, 230kV South Perry 115kV, 34.5kV, 69kV | 12-2030 | [9 empty] | NYSEG | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-03-31
NYISO | Ames Road Station | 1672 | 2024-02-05 | [7 empty] | AC | [16 empty] | Montgomery | NY | NM-NG, NYPA |  | 345kV Edic Princetown 351 345kV Edic Princetwon 352 115kV Saint Johnsville Mashville 11 115kV Clinton Marshville 12 | 01-2028 | [9 empty] | National Grid | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-02-29
NYISO | Niagara Digital Campus | 1681 | 2024-04-09 | [7 empty] | Load | [16 empty] | Niagara | NY | NM-NG |  | Adams to Packard 115kV lines 187 and 188 | 06-2026 | [9 empty] | Niagara Falls Redevelopment LLC | [37 empty] | SRIS/SIS Pending | [30 empty] | 140 | 140 |  | 2024-07-31
NYISO | Cayuga Compute | 1683 | 2024-04-24 | [7 empty] | Load | [16 empty] | Tompkins | NY | NYSEG |  | Milliken substation 115kV | 10-2025 | [9 empty] | Cayuga Operating Company, LLC | [37 empty] | SRIS/SIS in Progress | [30 empty] | 150 | 150 |  | 2024-06-30
NYISO | Clean Borough Power Link #1 | 1685 | 2024-05-30 | [7 empty] | DC | [16 empty] | Richmond,Kings,Queens,West Chester | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | 12-2032 | [9 empty] | energyRe Giga-Projects USA, LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Clean Borough Power Link #2 | 1686 | 2024-05-30 | [7 empty] | DC | [16 empty] | New York, Richmond, Kings | NY | CONED |  | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; West 49 St - East13 St 345kV lines; Goethals 345kV, | 12-2032 | [9 empty] | energyRe Giga-Projects USA, LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Clean Borough Power Link #3 | 1687 | 2024-05-30 | [7 empty] | DC | [16 empty] | Richmond, New York, Kings, Queens | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345kV; Mott Haven - Rainey 345kV lines; Rainey 345kV; Astoria West 138kV; Farragut 345kV; Astoria Annex 345kV, Goethals 345 kV | 12-2032 | [9 empty] | energyRe Giga-Projects USA, LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Liberty Link 1 | 1688 | 2024-05-31 | [7 empty] | DC | [16 empty] | Kings, Westchester, Richmond | NY | Con Edison |  | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | 12-2032 | [9 empty] | Viridon New York Inc. | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Liberty Link 2 | 1689 | 2024-05-31 | [7 empty] | DC | [16 empty] | Kings, Westchester, Richmond | NY | Con Edison |  | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, Sprain Brook 345kV, Goethals 345kV | 12-2032 | [9 empty] | Viridon New York Inc. | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Liberty Link 3 | 1690 | 2024-05-31 | [7 empty] | DC | [16 empty] | Kings, New York, Richmond | NY | Con Edison |  | Brooklyn Clean Energy Hub (BCEH) 345kV, Farragut 345kV, W49th Street 345kV - E13th Street 345 kV lines, Goethals 345kV | 12-2032 | [9 empty] | Viridon New York Inc. | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Energy Link New York Solution 1 | 1691 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings, Westchester, Queens, Richmond | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Energy Link New York Solution 2 | 1692 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings, Westchester, Queens, Richmond | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Energy Link New York Solution 3 | 1693 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings, Westchester, Queens, Richmond | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV, Gowanus- Goethals 345 kV lines | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Energy Link New York Solution 4 | 1694 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings, Westchester, Queens, Richmond | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Sprain Brook 345 kV, Astoria Annex 345 kV, Goethals 345 kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Energy Link New York Solution 5 | 1695 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings, Richmond, Queens, Westchester | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Goethals 345kV, Astoria Annex 345kV, Sprain Brook 345kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Energy Link New York Solution 6 | 1696 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings, Westchester, Queens, Richmond | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV; Astoria Annex 345kV; Sprain Brook 345kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Energy Link New York Solution 7 | 1697 | 2024-06-13 | [7 empty] | DC | [16 empty] | Brooklyn & Staten Island | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345kV; Farragut 345kV; Rainey 345kV; Astoria West 138kV; Mott Haven - Rainey 345kV lines; Goethals 345kV, Astoria Annex 345kV; Sprain Brook 345kV; Gowanus- Goethals 345kV lines | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Energy Link New York Solution 10 | 1698 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings, Westchester, Queens, Richmond | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Sprain Brook 345kV , Astoria Annex 345kV , Goethals 345kV , Mott Haven - Rainey 345kV substations, Gowanus - Goethals 345kV , Astoria West 345 kV, Rainey 345 kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Five Boro Energy Connect ? Mint | 1699 | 2024-06-13 | [7 empty] | DC | [16 empty] | Kings,Queens,NY,Bronx,Delaware, | NY | CONED, NYPA, NYSEG |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV | 10-2032 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Energy Link New York Solution 8 | 1700 | 2024-06-15 | [7 empty] | DC | [16 empty] | Kings,Bronx,Queens,Westchester,Richmond | NY | CONED |  | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV ; Goethals 345 kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Energy Link New York Solution 9 | 1701 | 2024-06-15 | [7 empty] | DC | [16 empty] | Kings,Bronx,Queens,Westchester,Richmond | NY | CONED |  | Brooklyn Clean Energy Hub 345kV; Mott Haven 345kV; Rainey 345kV; Gowanus 345kV; Sprain Brook 345kV, Goethals 345 kV | 01-2033 | [9 empty] | New York Transco LLC | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Five Boro Energy Connect ? Sage | 1702 | 2024-06-15 | [7 empty] | DC | [16 empty] | Kings, Queens, New York, Bronx | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Academy 345 kV, Astoria Annex 345 kV, Mott Haven 345 kV, Mott Haven - Rainey 345 kV Lines, | 09-2032 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Five Boro Energy Connect - Ruby | 1703 | 2024-06-15 | [7 empty] | DC | [16 empty] | Kings, Queens, New York, Bronx | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | 09-2032 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Five Boro Energy Connect - Rose | 1704 | 2024-06-15 | [7 empty] | DC | [16 empty] | Kings, Queens, New York, Bronx | NY | CONED, NYPA |  | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, West 49 Street 345 kV, Mott Haven 345 kV, Astoria Annex 345 kV, Mott Haven - Rainey 345kV Lines | 09-2032 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Five Boro Energy Connect ? Olive | 1705 | 2024-06-15 | [7 empty] | DC | [16 empty] | Kings/Queens/NY/Bronx/Delaware | NY | CONED, NYPA, NYSEG |  | Brooklyn Clean Energy Hub 345 kV, Farragut 345 kV, Rainey 345 kV, Academy 345 kV, Mott Haven 345 kV, Astoria Annex 345kV , Fraser, Mott Haven - Rainey 345kV Lines, | 06-2033 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Five Boro Energy Connect ? Kelly | 1706 | 2024-06-17 | [7 empty] | DC | [16 empty] | Kings, Queens, New York, Bronx | NY | Con Edison, NYPA |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345 kV, Astoria Annex 345kV, Tremont 345kV, Mott Haven - Rainey 345kV Lines, | 08-2033 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-07-31
NYISO | Five Boro Energy Connect ? Hazel | 1707 | 2024-06-17 | [7 empty] | DC | [16 empty] | Kings/Queens/NY/Bronx/Delaware | NY | Con Edison, NYPA, NYSEG |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Mott Haven 345kV, Astoria Annex 345kV, Fraser 345kV, Mott Haven - Rainey 345kV Lines, | 12-2033 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Five Boro Energy Connect ? Navy | 1708 | 2024-06-17 | [7 empty] | DC | [16 empty] | Kings,Queens,Bronx,Richmond,Westchester | NY | Con Edison, NYPA |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Astoria Annex 345kV, Mott Haven 345kV, Rainey 345kV, Dunwoodie 345kV, Sprain Brook 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | 09-2032 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Five Boro Energy Connect ? Royal | 1709 | 2024-06-17 | [7 empty] | DC | [16 empty] | Kings,Queens,Bronx,Richmond,Westchester, | NY | Con Edison, NYPA |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Astoria Annex 345kV, Mott Haven 345kV, Tremont 345kV, W49th St 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Gowanus 345 kV | 05-2033 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Five Boro Energy Connect ? Golden | 1710 | 2024-06-17 | [7 empty] | DC | [16 empty] | Kings,Queens,NY,Bronx,Westchester,Delawa | NY | Con Edison, NYPA, NYSEG, |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Dunwoodie 345kV, Fraser 345kV, Vernon 138kV, Mott Haven - Rainey 345kV Lines | 10-2033 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Five Boro Energy Connect ? Honey | 1711 | 2024-06-17 | [7 empty] | DC | [16 empty] | Kings,Queens,NY,Bronx,Delaware | NY | Con Edison, NYPA, NYSEG, |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Vernon 138kV, Fraser 345kV, | 10-2033 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Five Boro Energy Connect ? Cobalt | 1712 | 2024-06-17 | [7 empty] | DC | [16 empty] | Kings,Queens,NY,Bronx,Richmond,Delaware | NY | Con Edison, NYPA, NYSEG |  | Brooklyn Clean Energy Hub 345kV, Farragut 345kV, Rainey 345kV, Academy 345kV, Astoria Annex 345kV, Mott Haven 345kV, Gowanus - Goethals 345kV Lines, Mott Haven - Rainey 345kV Lines, Fraser 345kV, Gowanus 345 | 10-2033 | [9 empty] | New York Power Authority & LS Power Grid New York Corporation I | [37 empty] | SRIS/SIS Pending | [33 empty] | 2024-08-31
NYISO | Project Sycamore Orangeburg | 1713 | 2024-06-19 | [7 empty] | Load | [16 empty] | Rockland | NY | O&R |  | Oak Street 138kV | 01-2025 | [9 empty] | Project Sycamore - Orangeburg | [37 empty] | SRIS/SIS Pending | [30 empty] | 25.3 | 25.3 |  | 2024-08-31
NYISO | Hudson Valley Data Center | 1714 | 2024-07-02 | [7 empty] | Load | [16 empty] | Rockland | NY | O&R |  | Line 60 138KV - Ramp to Tallman | 02-2027 | [9 empty] | Robert Delcalzo | [37 empty] | SRIS/SIS Pending | [30 empty] | 25 | 25 |  | 2024-07-31
NYISO | 1547 CSR - Orangeburg LLC | 1715 | 2024-07-02 | [7 empty] | Load | [16 empty] | Rockland | NJ | O&R |  | 138kV Line 703 between Corporate Drive and Harings Corner | 01-2027 | [9 empty] | Jerry Martin | [37 empty] | SRIS/SIS Pending | [30 empty] | 60 | 60 |  | 2024-08-31
NYISO | Orangeburg Expansion Phase 2 | 1716 | 2024-08-05 | [7 empty] | Load | [16 empty] | Orange | NY | O&R |  | Oak St 38kV substation | 12-2027 | [9 empty] | DataBank Holdings, LLC | [37 empty] | SRIS/SIS Pending | [30 empty] | 60 | 60 |  | 2024-10-31
NYISO | Proposed Datacenters at 450 Broadway, Buchanan, NY, 10511 | 1717 | 2024-08-07 | [7 empty] | Load | [16 empty] | Westchester | NY | ConEd |  | Buchanan 138kV Substation | 09-2026 | [9 empty] | Holtec Decommissioning International (HDI) | [37 empty] | SRIS/SIS Pending | [30 empty] | 200 | 200 |  | 2024-09-30
NYISO | Erie East BESS | 1718 | 2024-09-10 | [7 empty] | AC | [16 empty] | Erie | PA | PJM |  | Erie East 230kV (First Energy, Erie PA) | 06-2027 | [9 empty] | Seven Creek Energy, LLC | [37 empty] | Scoping Meeting Pending | [33 empty] | 2024-12-31
NYISO | New York State Artificial Intelligence Data Center | 1719 | 2024-09-18 | [7 empty] | Load | [16 empty] | St. Lawrence | NY | NM-NG |  | Dennison 115kV substation | 12-2025 | [9 empty] | ZeroC Data Centers, LLC | [37 empty] | SRIS/SIS Pending | [30 empty] | 300 | 300 |  | 2024-09-30
NYISO | Elk Run Storage | 1720 | 2024-10-16 | [7 empty] | AC | [16 empty] | Tioga | PA | PJM |  | Mainesburg 115 kV Substation | 11-2027 | [9 empty] | Elk Run Storage LLC | [37 empty] | Scoping Meeting Pending | [33 empty] | 2024-10-31
NYISO | Brookhaven Logistics Center | 1721 | 2024-10-28 | [7 empty] | Load | [16 empty] | Suffolk | NY | LIPA |  | 138-872 Holbrook to Sills Rd or 138-873 West Bus to Sills Rd. | 01-2027 | [9 empty] | WF Industrial XII LLC | [37 empty] | SRIS/SIS Pending | [30 empty] | 176.6 | 176.6
NYISO | Treebeard BESS | 1722 | 2024-10-29 | [7 empty] | AC | [16 empty] | New Milford | CT | ISO-NE |  | 115 kV line 1555 between Rocky River and Bulls Bridge substations | 02-2027 | [9 empty] | Treebeard BESS Project Co LLC | [37 empty] | Scoping Meeting Pending | [33 empty] | 2024-11-30
NYISO | Olean Digital Data Center | 1723 | 2024-11-07 | [7 empty] | Load | [16 empty] | Cattaraugus | NY | NM-NG |  | Homer Hill Olean Substation | 06-2026 | [9 empty] | Olean Digital LLC | [37 empty] | Scoping Meeting Pending | [30 empty] | 150 | 150