## Sheet1
ISO | Project Name | Queue Position | Interconnection Request Receive Date | Queue Date | Application Status | Study Process | Technology | Technology-1 | Technology-2 | Technology-3 | Fuel | Fuel-1 | Fuel-2 | Fuel-3 | Capacity (MW) | Capacity-1 | Capacity-2 | Capacity-3 | Net MWs to Grid | Energy | Energy-1 | Energy-2 | Energy-3 | TPD Allocation Group | County | State | Utility | Nearest Town or County | Station or Transmission Line | Proposed On-line Date (as filed with IR) | Current On-line Date | POI Name | Proposed In-Service/Initial Backfeed Date | Projected COD | Facilities Study (FAS) or Phase II Cluster Study | Feasibility Study Status | System Impact Study Status
CAISO | MONTEZUMA (HIGH WINDS III) | 22 | 2003-11-18 | 2003-11-18 08:00 | ACTIVE | AMEND 39 |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 38 | 38 |  | 38 |  | Partial Capacity | 50 | Off-Peak Deliverability | Group D | SOLANO | CA | PGAE | Northern | Birds Landing 230 kV | 2005-06-30 07:00 | 2024-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | TULE WIND | 32 | 2004-05-12 | 2004-05-24 07:00 | ACTIVE | Serial LGIP |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 193.8 |  |  | 193.8 |  | Partial Capacity | 65.5 | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE | SDGE | Boulevard East Substation 138 kV | 2007-09-01 07:00 | 2027-12-31 08:00 |  | Waived | Complete | Complete |  | Executed
CAISO | MIDWAY PEAKING AGGREGATE | 54 | 2005-01-12 | 2005-01-12 08:00 | ACTIVE | Serial LGIP |  | Gas Turbine | Storage |  |  | Natural Gas | Battery |  |  | 119.9 | 119.9 |  | 119.9 |  | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE |  | Panoche Substation | 2008-06-01 07:00 | 2027-06-30 07:00 |  | Waived | Complete | Re-Study |  | Executed
CAISO | FRESNO COGENERATION EXPANSION PROJECT | 61 | 2005-03-28 | 2005-03-30 08:00 | ACTIVE | AMEND 39 |  | Steam Turbine | Storage |  |  | Natural Gas | Battery |  |  | 73.27 | 18.5 |  | 73.27 |  | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Helm-Kerman 70 kV Line | 2006-05-31 07:00 | 2023-02-28 08:00 |  |  | Complete | Complete |  | Executed
CAISO | LAKE ELSINORE ADVANCED PUMPED STORAGE PROJECT | 72 | 2005-04-26 | 2005-06-21 07:00 | ACTIVE | Serial LGIP |  | Storage |  |  |  | Pumped-Storage hydro |  |  |  | 500 |  |  | 500 |  | Full Capacity |  |  |  | RIVERSIDE | CA | SDGE | SDGE | Proposed Lee Lake Substation 500 kV | 2008-12-31 08:00 | 2028-12-31 08:00 |  | Waived | Complete | Re-Study |  | Executed
CAISO | BOTTLE ROCK POWER | 81 | 2005-09-13 | 2005-09-13 07:00 | ACTIVE | Serial LGIP |  | Steam Turbine | Storage |  |  | Geothermal | Battery |  |  | 9.435 | 47.4465 |  | 52.01 |  | Energy Only |  | Off-Peak Deliverability | Group A | LAKE | CA | PGAE | Kern | Geysers #17-Fulton 230 kV Line | 2006-09-01 07:00 | 2007-10-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CPC WEST | 96 | 2006-02-15 | 2006-03-01 08:00 | ACTIVE | Serial LGIP |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 600 | 300 |  | 600 |  | Partial Capacity | 59.76 | Off-Peak Deliverability | Group A | KERN | CA | SCE | Northern | Tehachapi Conceptual Substation #1 | 2009-12-31 08:00 | 2025-06-05 07:00 |  | Waived | Complete |  |  | Executed
CAISO | WINDSTAR I ALTERNATE | 100 | 2006-04-05 | 2006-04-05 07:00 | ACTIVE | Serial LGIP |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 120 | 120 |  | 120 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Vincent Substation 230kV | 2007-12-31 08:00 | 2025-08-01 07:00 |  | Waived | Complete |  |  | Executed
CAISO | SILVER RIDGE MOUNT SIGNAL | 124 | 2006-08-22 | 2006-08-22 07:00 | ACTIVE | Serial LGIP |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 600 | 150 |  | 600 |  | Partial Capacity | 19.36 | Off-Peak Deliverability |  | IMPERIAL | CA | SDGE |  | Imperial Valley Substation 230 kV | 2011-03-01 08:00 | 2027-06-01 07:00 |  | Waived | Complete | Complete |  | Executed
CAISO | SANDSTORM WIND POWER | 138 | 2006-10-23 | 2006-10-23 07:00 | ACTIVE | Serial LGIP |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 60 | 90 |  | 150 |  | Partial Capacity | 30.44 | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Devers Substation 220 kV | 2008-12-31 08:00 | 2030-02-01 08:00 |  | Waived | Complete | Complete |  | Executed
CAISO | MONTEZUMA II | 222 | 2007-05-23 | 2007-05-23 07:00 | ACTIVE | TC |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 78 | 54 |  | 78 |  | Partial Capacity | 59 | Off-Peak Deliverability | Group D | SOLANO | CA | PGAE | Northern | Birds Landing 230 kV | 2010-12-31 08:00 | 2012-01-29 08:00 |  |  | Complete | Complete |  | Executed
CAISO | TRACY COMBINED-CYCLE POWER PLANT | 268 | 2007-10-24 | 2007-10-24 07:00 | ACTIVE | Serial LGIP |  | Steam Turbine | Storage |  |  | Natural Gas | Battery |  |  | 145 | 40 |  | 145 |  | Full Capacity |  | Off-Peak Deliverability |  | SAN JOAQUIN | CA | PGAE |  | Tesla-Manteca 115kV line via Schulte Switchyard | 2012-06-01 07:00 | 2027-04-28 07:00 |  | Waived | Complete | Complete |  | Executed
CAISO | AMERICAN KINGS SOLAR | 272 | 2007-11-01 | 2007-11-01 07:00 | ACTIVE | TC |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 123 | 73.8 |  | 123 |  | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE | Fresno | Henrietta 70 kV | 2012-06-01 07:00 | 2025-12-30 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ALTA VISTA SUNTOWER GENERATING STATION | 297 | 2008-01-18 | 2008-01-18 08:00 | ACTIVE | TC |  | Steam Turbine | Storage |  |  | Solar | Battery |  |  | 66 | 66 |  | 66 |  | Partial Capacity | 35.42 | Off-Peak Deliverability | Group A | LOS ANGELES | CA | SCE | Northern | Neenach-Bailey 66kV line | 2009-12-01 08:00 | 2025-04-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LOS ESTEROS CRITICAL ENERGY FACILITY EXPANSION | 378 | 2008-05-28 | 2008-05-28 07:00 | ACTIVE | TC |  | Combined Cycle | Storage |  |  | Natural Gas | Battery |  |  | 120 | 3 |  | 120 |  | Full Capacity |  | Off-Peak Deliverability |  | SANTA CLARA | CA | PGAE | Northern | Los Esteros 115 kV | 2011-06-01 07:00 | 2023-09-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SILVER STATE SOUTH SOLAR PROJECT | 467 | 2008-05-30 | 2008-06-02 07:00 | ACTIVE | TC |  | Steam Turbine | Storage |  |  | Solar | Battery |  |  | 230 | 200 |  | 230 |  | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | SCE | EOP | Eldorado-Ivanpah 230kV line | 2012-08-01 07:00 | 2024-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ROSAMOND WEST SOLAR | 506 | 2009-07-30 | 2009-07-31 07:00 | ACTIVE | C01 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 299.6 | 147.7 |  | 299.6 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2015-07-31 07:00 | 2023-07-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CROW CREEK SOLAR 1 (FKA: FRONTIER SOLAR 1) (FKA AS SCATEC WESTSIDE SOLAR RANCH I AND STANISLAUS PV - PHASE 1) | 539 | 2009-12-18 | 2009-12-18 08:00 | ACTIVE | SGIP |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 20 | 20 |  | 20 |  | Energy Only |  | Off-Peak Deliverability |  | STANISLAUS | CA | PGAE |  | Salado-Newman #1 60kV Line | 2012-10-31 07:00 | 2016-06-30 07:00 |  |  | Facilities Study | SGIA |  | Executed
CAISO | KETTLEMAN SOLAR PROJECT (FKA KETTLEMAN SOLAR FARM) | 625 | 2010-05-14 | 2010-05-14 07:00 | ACTIVE | SGIP |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 20 | 20 |  | 20 |  | Energy Only |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | Fresno | Henrietta-Tulare Lake 70 kV | 2011-12-31 08:00 | 2025-04-01 07:00 |  |  | Facilities Study | SGIA |  | Executed
CAISO | PUMPJACK SOLAR I (AKA PIONEER SOLAR I) | 653B | 2010-09-29 | 2010-09-29 07:00 | ACTIVE | SGIP-TC |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 20 | 20 |  | 20 |  | Partial Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Belridge - Temblor 115 kV | 2013-05-01 07:00 | 2027-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | APPARENT FIRST HYBRID | 653F | 2010-10-07 | 2010-10-13 07:00 | ACTIVE | SGIP-TC |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 12 | 12.1 |  | 12 |  | Energy Only |  | Off-Peak Energy Only |  | YOLO | CA | PGAE | Northern | Woodland-Davis 115 kV Line | 2012-05-01 07:00 | 2022-05-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | EXCELSIOR SOLAR (FKA: BURFORD FIVE POINTS) | 678 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 60 | 60 |  | 60 |  | Partial Capacity | 10 | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Panoche-Schindler #1 and #2 115 kV Line | 2013-09-05 07:00 | 2024-12-20 08:00 |  |  | Complete | Complete |  | Executed
CAISO | COLUMBIA SOLAR ENERGY 2 FKA COLUMBIA SOLAR ENERGY II | 687 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 20 | 20 |  | 20 |  | Partial Capacity | 10 | Off-Peak Deliverability | Group D | CONTRA COSTA | CA | PGAE | Northern | Pittsburg-Kirker-Columbia Steel 115 kV Line | 2012-12-31 08:00 | 2025-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LASSEN LODGE HYDROELECTRIC | 720 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 |  | Hydro |  |  |  | Water |  |  |  | 4.5 |  |  | 4.5 |  | Energy Only |  |  |  | TEHAMA | CA | PGAE | Northern | Vota-South 60 kV | 2012-12-15 08:00 | 2027-10-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | REDWOOD SOLAR FARM | 744 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 |  | Photovoltaic |  |  |  | Solar |  |  |  | 90 |  |  | 90 |  | Partial Capacity | 87 | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Lamont 115 KV | 2014-07-01 07:00 | 2024-07-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BIG SKY SOLAR | 768 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 320 | 163.4 |  | 320 |  | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Substation 230kV bus | 2014-12-31 08:00 | 2023-01-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | WRIGHT SOLAR | 779 | 2011-03-31 | 2011-03-31 07:00 | ACTIVE | C04 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 200 | 80 |  | 200 |  | Partial Capacity | 49.35 | Off-Peak Deliverability |  | MERCED | CA | PGAE | Fresno | Los Banos-Panoche #1 230kV Line | 2014-01-06 08:00 | 2026-03-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | RUGGED SOLAR FARM | 789 | 2011-03-30 | 2011-03-31 07:00 | ACTIVE | C04 |  | Photovoltaic |  |  |  | Solar |  |  |  | 71.88 |  |  | 71.88 |  | Energy Only |  | Off-Peak Deliverability | Group B | SAN DIEGO | CA | SDGE | SDGE | Boulevard East Substation 69 kV | 2015-07-31 07:00 | 2025-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | STAGE COACH SOLAR | 897 | 2012-04-02 | 2012-04-02 07:00 | ACTIVE | C05 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 200 | 50 |  | 200 |  | Partial Capacity | 65 | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Calcite Substation 220kV bus | 2016-12-01 08:00 | 2026-08-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | RIO BRAVO SOLAR 1 | 900 | 2012-04-02 | 2012-04-02 07:00 | ACTIVE | C05 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 20 | 20 |  | 20 |  | Partial Capacity | 10 | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Midway Temblor 115 kV line | 2014-12-20 08:00 | 2027-06-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | NORTHERN ORCHARD SOLAR | 946 | 2013-04-23 | 2013-04-30 07:00 | ACTIVE | C06 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 100 | 92 |  | 100 |  | Partial Capacity | 60 | Off-Peak Deliverability |  | KERN | CA | PGAE | Kern | Midway-Wheeler Ridge #2 230 kV Line | 2015-12-01 08:00 | 2025-01-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | RIO BRAVO SOLAR 2 | 972 | 2013-04-30 | 2013-04-30 07:00 | ACTIVE | C06 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 20 | 20 |  | 20 |  | Partial Capacity | 10 | Off-Peak Deliverability |  | KERN | CA | PGAE |  | Midway-Temblor 115kV line | 2016-12-31 08:00 | 2027-07-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SUNSHINE VALLEY SOLAR 1 | 993 | 2013-04-30 | 2013-04-30 07:00 | ACTIVE | C06 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 50 | 40 |  | 50 |  | Full Capacity |  | Off-Peak Deliverability |  | NYE | NV | VEA | EOP | Valley Substation 138 kV | 2016-12-31 08:00 | 2026-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | LASSEN LODGE HYDROELECTRIC 2 | 1002 | 2013-05-01 | 2013-04-30 07:00 | ACTIVE | C06 |  | Hydro |  |  |  | Water |  |  |  | 0.5 |  |  | 0.5 |  | Energy Only |  |  |  | TEHAMA | CA | PGAE | Northern | Volta-South 60 kV Line | 2015-11-15 08:00 | 2024-10-16 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CHULA VISTA ENERGY CENTER 2 | 1045 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 |  | Storage |  |  |  | Battery |  |  |  | 50 |  |  | 50 |  | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | Otay Substation 69 kV | 2019-11-01 07:00 | 2025-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | NORTH JOHNSON ENERGY CENTER | 1047 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 |  | Storage |  |  |  | Battery |  |  |  | 50 |  |  | 50 |  | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | El Cajon Substation 69 kV | 2019-11-01 07:00 | 2026-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ESCONDIDO ENERGY CENTER 2 | 1048 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 |  | Storage |  |  |  | Battery |  |  |  | 33 |  |  | 33 |  | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | Escondido Substation 69 kV | 2019-11-01 07:00 | 2027-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | WHITE WING RANCH SOLAR | 1062 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 200 | 200 |  | 200 |  | Energy Only |  | Off-Peak Deliverability |  | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2018-12-31 08:00 | 2026-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ARES NEVADA | 1064 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 |  | Storage |  |  |  | Gravity via Rail |  |  |  | 44 |  |  | 44 |  | Energy Only |  |  |  | NYE | NV | GLW |  | Gamebird Substation 230 kV | 2017-01-01 08:00 | 2027-01-08 08:00 |  |  | Complete | Complete |  | Executed
CAISO | GASKELL WEST | 1074 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 125 | 61.62 |  | 128.07 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 220 kV | 2016-06-30 07:00 | 2026-12-02 08:00 |  |  | Complete | Complete |  | Executed
CAISO | WILLOW SPRINGS SOLAR 3 | 1076 | 2014-04-30 | 2014-04-30 07:00 | ACTIVE | C07 |  | Storage |  |  |  | Battery |  |  |  | 50 |  |  | 50 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230 kV | 2017-06-30 07:00 | 2026-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ALTAMONT MIDWAY LTD | 1096 | 2015-02-24 | 2015-04-13 07:00 | ACTIVE | FT |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 5 |  |  | 5 |  | Energy Only |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE | Northern | Altamont Midway 230 kV | 2015-08-31 07:00 | 2025-04-28 07:00 | [5 empty] | Executed
CAISO | FOUNTAIN WIND | 1106 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 206 |  |  | 200 |  | Full Capacity |  | Off-Peak Deliverability |  | SHASTA | CA | PGAE | Northern | Pit 1-Cottonwood 230 kV Line | 2020-10-15 07:00 | 2027-09-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ULTRAPOWER CHINESE STATION BESS | 1116 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 10 |  |  | 10 |  | Full Capacity |  |  |  | TUOLUMNE | CA | PGAE | Northern | Melones-Curtis 115 kV Line | 2017-03-31 07:00 | 2024-12-30 08:00 |  |  | Complete | Complete |  | Executed
CAISO | LUNA VALLEY SOLAR | 1129 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 204 | 168.5 |  | 200 |  | Partial Capacity | 84.3 | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2018-12-31 08:00 | 2028-12-29 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SCARLET | 1135 | 2015-04-29 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 400 | 400 |  | 400 |  | Full Capacity |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2018-12-31 08:00 | 2025-12-23 08:00 |  |  | Complete | Complete |  | Executed
CAISO | LAKE ALPAUGH BATTERY STORAGE | 1143 | 2015-04-29 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 10 |  |  | 10 |  | Full Capacity |  |  |  | TULARE | CA | PGAE | Kern | Corcoran-Olive 115 kV Line | 2017-12-31 08:00 | 2025-09-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BIG ROCK SOLAR FARM | 1166 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 200 |  |  | 200 |  | Partial Capacity | 50 | Off-Peak Deliverability | Group D | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2020-06-01 07:00 | 2025-04-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | FALLBROOK ENERGY STORAGE | 1169 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 69.6 |  |  | 69.6 |  | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Avocado Substation 69 kV | 2020-02-01 08:00 | 2024-12-10 08:00 |  |  | Complete | Complete |  | Executed
CAISO | GATEWAY ENERGY STORAGE | 1170 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 250 |  |  | 250 |  | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Otay Mesa Switchyard 230 kV | 2018-09-01 07:00 | 2024-08-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | MCFARLAND SOLAR | 1171 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 500 | 435 |  | 500 |  | Partial Capacity | 87 | Off-Peak Deliverability |  | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2018-12-31 08:00 | 2025-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LECONTE ENERGY STORAGE | 1175 | 2015-04-29 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 125 |  |  | 125 |  | Partial Capacity | 18 |  | Group B | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2018-09-01 07:00 | 2026-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | QUARTZITE SOLAR 8 | 1198 | 2015-04-28 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 150 | 75 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 220kV | 2020-12-01 08:00 | 2024-12-21 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ARATINA SOLAR CENTER 1 | 1204 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 200 | 200 |  | 200 |  | Partial Capacity | 19 | Off-Peak Deliverability | Group A | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2020-06-01 07:00 | 2025-11-27 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SIENNA SOLAR FARM | 1207 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 200 | 200 |  | 200 |  | Partial Capacity | 93 | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Calcite Substation 230kV | 2020-06-01 07:00 | 2027-01-28 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ANTELOPE SOLAR 2 | 1208 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 358.88 | 423 |  | 650 |  | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Antelope Substation 220kV | 2018-12-31 08:00 | 2025-11-27 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ROSAMOND SOUTH EAST | 1211 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 100 | 92 |  | 101.7 |  | Partial Capacity | 90.46 | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2018-06-30 07:00 | 2025-05-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | GOLDEN FIELDS SOLAR | 1212 | 2015-04-30 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 100 |  |  | 100 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2018-06-30 07:00 | 2026-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | RABBITBRUSH SOLAR | 1215 | 2015-04-28 | 2015-04-30 07:00 | ACTIVE | C08 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 100 | 70 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2019-12-31 08:00 | 2024-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | WILLOW SPRINGS SOLAR 4 | 1217 | 2015-04-28 | 2015-04-30 07:00 | ACTIVE | C08 |  | Storage |  |  |  | Battery |  |  |  | 75 |  |  | 75 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2019-12-31 08:00 | 2026-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | AGUA CALIENTE SOLAR 2 | 1222 | 2016-03-01 | 2016-03-08 08:00 | ACTIVE | ISP |  | Photovoltaic |  |  |  | Solar |  |  |  | 20 |  |  | 20 |  | Energy Only |  | Off-Peak Energy Only |  | MARICOPA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2016-12-01 08:00 | 2016-12-01 08:00 |  |  | Complete | Complete |  | In Progress
CAISO | DAYLIGHT | 1223 | 2016-04-22 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 310.707 | 300 |  | 300 |  | Partial Capacity | 60 | Off-Peak Deliverability | Group B | KINGS | CA | PGAE | Fresno | Mustang 230 kV | 2020-12-31 08:00 | 2028-01-19 08:00 |  |  | Complete | Complete |  | Executed
CAISO | PLUOT | 1242 | 2016-05-03 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 254 | 225 |  | 246.4 |  | Full Capacity |  | Off-Peak Deliverability | Group B | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2023-04-05 07:00 | 2026-06-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | POMEGRANATE | 1243 | 2016-05-03 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 254 | 225 |  | 249.7 |  | Full Capacity |  | Off-Peak Deliverability | Group A | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2022-04-06 07:00 | 2025-12-20 08:00 |  |  | Complete | Complete |  | Executed
CAISO | NORTHERN ORCHARD SOLAR 2 | 1259 | 2016-04-27 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic |  |  |  | Solar |  |  |  | 50 |  |  | 50 |  | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | PGAE | Kern | Midway-Wheeler Ridge #2 230 kV Line | 2020-12-16 08:00 | 2025-01-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | KYAN SOLAR | 1260 | 2016-04-27 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic |  |  |  | Solar |  |  |  | 102 |  |  | 100 |  | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | PGAE | Kern | Midway-Wheeler Ridge #2 230 kV Line | 2020-10-14 07:00 | 2027-09-03 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CORBY | 1270 | 2016-04-27 | 2016-05-02 07:00 | ACTIVE | C09 |  | Storage |  |  |  | Battery |  |  |  | 313.5 |  |  | 300 |  | Full Capacity |  |  |  | SOLANO | CA | PGAE | Northern | Vaca-Dixon 230 kV | 2020-12-01 08:00 | 2027-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | KOLA | 1275 | 2016-04-26 | 2016-05-02 07:00 | ACTIVE | C09 |  | Storage |  |  |  | Battery |  |  |  | 418 |  |  | 400 |  | Full Capacity |  |  |  | ALAMEDA | CA | PGAE | Northern | Tesla 230 kV | 2020-12-01 08:00 | 2025-06-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | MULQUEENEY RANCH WIND | 1277 | 2016-05-02 | 2016-05-02 07:00 | ACTIVE | C09 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 114 |  |  | 20 |  | Full Capacity |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE | Northern | Tesla 230 kV | 2020-03-01 08:00 | 2026-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | DAGGETT SOLAR 1 | 1312 | 2016-04-28 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 148.96 | 118.5 |  | 144 |  | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Coolwater Substation 115kV | 2020-06-30 07:00 | 2025-03-28 07:00 |  |  | Complete | Complete |  | Executed
CAISO | DAGGETT SOLAR 3 | 1314 | 2016-04-28 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 313.88 | 208 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2020-06-30 07:00 | 2023-08-06 07:00 |  |  | Complete | Complete |  | Executed
CAISO | WILLY 9 | 1319 | 2016-04-25 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 259.842 | 250 |  | 250 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2020-12-31 08:00 | 2024-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SOLAR STAR 3 | 1322 | 2016-04-25 | 2016-05-02 07:00 | ACTIVE | C09 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 24.95 | 25 |  | 24 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2021-12-31 08:00 | 2025-07-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SOLAR STAR 4 | 1323 | 2016-04-25 | 2016-05-02 07:00 | ACTIVE | C09 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 24.95 | 25.05 |  | 24 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2021-12-31 08:00 | 2025-08-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CYCLONE SOLAR | 1327 | 2016-04-29 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 40 | 25 |  | 40 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2019-07-01 07:00 | 2025-05-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | PASTORIA SOLAR | 1335 | 2016-05-02 | 2016-05-02 07:00 | ACTIVE | C09 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 106.875 | 80 |  | 105.2 |  | Partial Capacity | 77 | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Pastoria Substation 230kV | 2019-09-01 07:00 | 2026-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | TAHOE | 1339 | 2016-04-29 | 2016-05-02 07:00 | ACTIVE | C09 |  | Storage |  |  |  | Battery |  |  |  | 300 |  |  | 300 |  | Partial Capacity | 93 | Off-Peak Deliverability |  | CLARK | NV | SCE | EOP | SCE owned Eldorado Bus 230kV | 2019-07-31 07:00 | 2026-05-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ROCCASECCA BESS | 1347 | 2016-05-02 | 2016-05-02 07:00 | ACTIVE | C09 |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 310 | 95 |  | 303 |  | Partial Capacity | 41.78 | Off-Peak Deliverability |  | CLARK | NV | GLW |  | Sloan Canyon Switching Station 230kV | 2019-07-31 07:00 | 2026-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ARAMIS POWER PLANT | 1349 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 101.4 | 101.3 |  | 100 |  | Full Capacity |  | Off-Peak Deliverability | Group 2 | ALAMEDA | CA | PGAE | Northern | Cayetano 230 kV | 2020-12-31 08:00 | 2025-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SAND HILL C | 1363 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 84.25 |  |  | 80.8 |  | Full Capacity |  | Off-Peak Deliverability |  | ALAMEDA | CA | PGAE | Northern | Delta Switching Yard-Tesla 230 kV Line | 2019-12-31 08:00 | 2025-04-28 07:00 |  |  | Complete | Complete |  | Executed
CAISO | GONZAGA WIND FARM | 1378 | 2017-04-27 | 2017-05-01 07:00 | ACTIVE | C10 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 80 |  |  | 76.35 |  | Partial Capacity | 66.5 | Off-Peak Deliverability | Group 2 | MERCED | CA | PGAE | Fresno | Los Banos 70 kV | 2020-10-09 07:00 | 2026-03-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | HEARTLAND 1 | 1379 | 2017-04-26 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic |  |  |  | Solar |  |  |  | 156.04 |  |  | 150 |  | Energy Only |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2021-09-01 07:00 | 2028-06-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | HEARTLAND 2 | 1380 | 2017-04-26 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic |  |  |  | Solar |  |  |  | 156.05 |  |  | 150 |  | Energy Only |  | Off-Peak Deliverability |  | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2021-09-01 07:00 | 2028-06-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LAS CAMAS 1 | 1382 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 102.5 | 100 |  | 100 |  | Partial Capacity | 10 | Off-Peak Energy Only | Group D | MERCED | CA | PGAE | Fresno | Los Banos 230 kV | 2021-11-30 08:00 | 2025-05-07 07:00 |  |  | Complete | Complete |  | Executed
CAISO | REDUX SOLAR | 1389 | 2017-05-01 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 128.24 | 61.25 |  | 125 |  | Full Capacity |  | Off-Peak Deliverability | Group 2b | FRESNO | CA | PGAE | Fresno | Gates 230 kV | 2020-12-30 08:00 | 2024-12-15 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SONRISA | 1391 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 200 | 184 |  | 200 |  | Partial Capacity | 91 | Off-Peak Deliverability | Group 1 | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2021-11-30 08:00 | 2025-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | DRIFTWOOD STELLA | 1394 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 207.4 | 184 |  | 200 |  | Energy Only |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Midway 115 kV | 2021-11-30 08:00 | 2026-11-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SANDRINI SOL 1 | 1397 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 100 | 92 |  | 100 |  | Partial Capacity | 62 | Off-Peak Deliverability |  | KERN | CA | PGAE | Kern | Wheeler Ridge 70 kV | 2021-11-30 08:00 | 2025-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ATLAS COMPLEX | 1402 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 1920 | 3200 |  | 3200 |  | Partial Capacity | 66 | Off-Peak Deliverability | Group A | LA PAZ | AZ | DCRT | Eastern | Delaney-Colorado River 500 kV Line | 2020-12-31 08:00 | 2027-10-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ATHOS POWER PLANT | 1405 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 458 | 450 |  | 450 |  | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2020-12-31 08:00 | 2025-05-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BALDY MESA | 1413 | 2017-04-29 | 2017-05-01 07:00 | ACTIVE | C10 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 110.04 | 110.04 |  | 100 |  | Full Capacity |  | Off-Peak Deliverability |  | SAN BERNARDINO | CA | SCE | NOL | Roadway Substation 115kV bus | 2020-12-31 08:00 | 2025-02-03 08:00 |  |  | Complete | Complete |  | Executed
CAISO | CAMINO SOLAR | 1419 | 2017-04-27 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 44.88 | 13.4 |  | 54.28 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2020-08-15 07:00 | 2027-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | MOUNT LAGUNA WIND 2 | 1429 | 2017-04-28 | 2017-05-01 07:00 | ACTIVE | C10 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 400 |  |  | 400 |  | Energy Only |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE | SDGE | Suncrest - Ocotillo 500 kV Line | 2020-06-01 07:00 | 2031-02-05 08:00 |  |  | Complete | Complete |  | Executed
CAISO | STARLIGHT SOLAR | 1432 | 2017-05-01 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 20 | 17.4 |  | 20 |  | Partial Capacity | 87 | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE |  | Boulevard East Substation 69 kV | 2020-06-01 07:00 | 2026-05-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | VIKTORIA SOLAR | 1435 | 2017-04-24 | 2017-05-01 07:00 | ACTIVE | C10 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 250 | 250 |  | 250 |  | Energy Only |  | Off-Peak Deliverability |  | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2020-12-31 08:00 | 2026-03-06 08:00 |  |  | Complete | Complete |  | Executed
CAISO | AJO POWER BANK | 1442 | 2018-04-05 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 124.3 |  |  | 120 |  | Full Capacity |  |  |  | SANTA CLARA | CA | PGAE | Northern | Llagas-Gilroy Foods 115 kV line | 2020-12-01 08:00 | 2028-01-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ANGELA | 1443 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 40 | 20 |  | 40 |  | Partial Capacity | 65 | Off-Peak Deliverability | Group 2a | TULARE | CA | PGAE | Kern | Olive 115 kV | 2021-11-30 08:00 | 2025-12-15 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SALOON ENERGY STORAGE | 1444 | 2018-04-04 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 150 |  |  | 150 |  | Partial Capacity | 54 | Off-Peak Deliverability |  | COLUSA | CA | PGAE | Northern | Cortina 115 kV | 2022-12-01 08:00 | 2027-07-13 07:00 |  |  | Complete | Complete |  | Executed
CAISO | HUMMINGBIRD ENERGY STORAGE | 1454 | 2018-04-09 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 75 |  |  | 75 |  | Full Capacity |  |  | Group 1a | SANTA CLARA | CA | PGAE | Northern | Metcalf 115 kV | 2020-12-31 08:00 | 2025-05-23 07:00 |  |  | Complete | Complete |  | Executed
CAISO | JANUS | 1455 | 2018-04-12 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 80 | 83.54 |  | 80 |  | Full Capacity |  | Off-Peak Deliverability |  | COLUSA | CA | PGAE | Northern | Cortina 60 kV | 2021-12-31 08:00 | 2026-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LAS CAMAS 3 | 1456 | 2018-04-10 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 102.5 | 100 |  | 100 |  | Partial Capacity | 10 | Off-Peak Energy Only | Group D | MERCED | CA | PGAE | Fresno | Los Banos 230 kV | 2022-11-30 08:00 | 2025-08-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | MILPA POWER BANK | 1457 | 2018-04-09 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 3 |  |  | 3 |  | Full Capacity |  |  |  | SANTA CLARA | CA | PGAE | Northern | Los Esteros 115 kV | 2020-12-01 08:00 | 2025-04-29 07:00 |  |  | Complete | Complete
CAISO | MULQUEENEY RANCH WIND 2 | 1459 | 2018-04-12 | 2018-04-16 07:00 | ACTIVE | C11 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 62.5 |  |  | 60 |  | Full Capacity |  | Off-Peak Deliverability | Group 2b | ALAMEDA | CA | PGAE | Northern | Tesla 230 kV | 2021-12-15 08:00 | 2024-11-30 08:00 |  |  | Complete | Complete |  | Executed
CAISO | RECLAIMED WIND | 1461 | 2018-04-04 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 114.4 |  |  | 90.7 |  | Full Capacity |  | Off-Peak Deliverability | Group A | ALAMEDA | CA | PGAE | Northern | Kelso-Tesla Tap 230 kV | 2020-12-31 08:00 | 2025-04-04 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SOLANO 4 WIND | 1463 | 2018-04-04 | 2018-04-16 07:00 | ACTIVE | C11 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 92.354 |  |  | 90.8 |  | Full Capacity |  | Off-Peak Deliverability | Group 1 | SOLANO | CA | PGAE | Northern | Birds Landing 230 kV | 2023-03-31 07:00 | 2025-05-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CABALLERO STORAGE | 1470 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 106.2 |  |  | 99.7 |  | Full Capacity |  |  | Group 2a | SAN LUIS OBISPO | CA | PGAE | Kern | Mesa 230 kV | 2021-12-01 08:00 | 2024-11-15 08:00 |  |  | Complete | Complete |  | Executed
CAISO | KEY STORAGE 1 | 1479 | 2018-04-11 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 309.3 |  |  | 300.1 |  | Full Capacity |  |  | Group 3 | FRESNO | CA | PGAE | Fresno | Gates 500 kV | 2022-12-01 08:00 | 2026-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | TEPONA OFF-SHORE WIND | 1491 | 2018-04-14 | 2018-04-16 07:00 | ACTIVE | C11 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 161.925 |  |  | 156 |  | Energy Only |  | Off-Peak Energy Only | Group 3 | HUMBOLDT | CA | PGAE | Northern | Humboldt 115 kV | 2024-10-01 07:00 | 2034-10-01 07:00 |  |  | Complete | Complete
CAISO | AZALEA | 1493 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 61.3 | 38 |  | 60 |  | Partial Capacity | 70 | Off-Peak Deliverability |  | KERN | CA | PGAE | Kern | Arco 70 kV | 2022-11-01 07:00 | 2025-03-09 08:00 |  |  | Complete | Complete |  | Executed
CAISO | CHALAN SOLAR | 1495 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 25.2 | 66.6 |  | 64.9 |  | Partial Capacity | 48.5 | Off-Peak Deliverability | Group 1a | KERN | CA | PGAE | Kern | Arco 230 kV | 2021-12-01 08:00 | 2025-02-20 08:00 |  |  | Complete | Complete |  | Executed
CAISO | DESCENDANT RANCH 1 | 1496 | 2018-04-11 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 510 | 513.5 |  | 500 |  | Partial Capacity | 9.6 | Off-Peak Deliverability | Group 1b | COLUSA | CA | PGAE | Northern | Delevan 230 kV | 2023-12-01 08:00 | 2025-06-21 07:00 |  |  | Complete | Complete |  | Executed
CAISO | JASMINE | 1499 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 71.161 | 70 |  | 70 |  | Partial Capacity | 92 | Off-Peak Deliverability |  | KERN | CA | PGAE | Kern | Lakeview 70 kV | 2022-11-01 07:00 | 2026-08-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | PROSPECT ENERGY STORAGE | 1507 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 58.75 |  |  | 49.9 |  | Full Capacity |  |  | Group 1 | SACRAMENTO | CA | PGAE | Northern | Gold Hill 60 kV | 2022-06-01 07:00 | 2026-03-31 07:00 | Suspended |  | Complete | Complete |  | Executed
CAISO | BELLEFIELD SOLAR FARM | 1510 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 500 | 500 |  | 500 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2022-10-01 07:00 | 2025-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | REXFORD SOLAR FARM | 1516 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 300 | 240 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | TULARE | CA | SCE | Northern | Vestal Substation 230kV | 2022-10-01 07:00 | 2024-12-20 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SANBORN SOLAR 2 | 1518 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 334 | 372.5 |  | 500 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2022-12-31 08:00 | 2025-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BALDY MESA 2 | 1519 | 2018-04-15 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 110.88 | 49.9 |  | 100 |  | Full Capacity |  | Off-Peak Deliverability | Group 2 | SAN BERNARDINO | CA | SCE | NOL | Roadway Substation 115kV | 2021-12-15 08:00 | 2025-02-03 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ARIDA SOLAR FARM | 1522 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 370 | 370 |  | 370 |  | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | SCE | EOP | Mohave Substation 500kV | 2022-10-01 07:00 | 2027-09-15 07:00 |  |  | Complete | Complete
CAISO | WINDY WASH SOLAR | 1528 | 2018-04-13 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic |  |  |  | Solar |  |  |  | 79 |  |  | 79 |  | Energy Only |  | Off-Peak Deliverability |  | RIVERSIDE | CA | SCE | Eastern | Devers Substation 220kV | 2021-06-30 07:00 | 2022-12-31 08:00 |  |  | Complete | Complete
CAISO | CENTENNIAL FLATS | 1529 | 2018-04-17 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 500 | 250 |  | 500 |  | Partial Capacity | 83.46 | Off-Peak Deliverability |  | LA PAZ | AZ | DCRT | Eastern | Delaney-Colorado River 500 kV Line | 2022-12-15 08:00 | 2025-06-22 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BATERIA DEL SUR | 1531 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage |  |  |  | Battery |  |  |  | 350 |  |  | 350 |  | Full Capacity |  |  | Group A | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2022-05-01 07:00 | 2025-04-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | KETTLE SOLAR ONE | 1532 | 2018-04-16 | 2018-04-16 07:00 | ACTIVE | C11 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 90 | 90 |  | 90 |  | Full Capacity |  | Off-Peak Deliverability |  | SAN DIEGO | CA | SDGE | SDGE | Carrizo Gorge Switchyard 138 kV | 2020-12-01 08:00 | 2026-10-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | VULCAN | 1534 | 2018-04-11 | 2018-04-16 07:00 | ACTIVE | C11 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 28.8 | 225 |  | 250 |  | Energy Only |  | Off-Peak Deliverability | Group B | MARICOPA | AZ | SDGE | SDGE | Hassayampa Common Bus 500 kV | 2021-05-01 07:00 | 2027-12-31 08:00 |  |  | Complete | Complete
CAISO | IRVING STORAGE | 1539 | 2019-03-05 | 2019-05-07 07:00 | ACTIVE | ISP |  | Storage |  |  |  | Battery |  |  |  | 782.79 |  |  | 750 |  | Full Capacity |  |  |  | MONTEREY | CA | PGAE | Northern | Moss Landing 500 kV | 2022-12-01 08:00 | 2025-11-30 08:00 |  |  | Complete | Complete |  | Executed
CAISO | TANAGER STORAGE | 1550 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 200 |  |  | 200 |  | Full Capacity |  |  | Group 2 | SANTA CLARA | CA | PGAE | Northern | Los Esteros 230 kV | 2023-06-30 07:00 | 2025-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CORMORANT STORAGE | 1552 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 250 |  |  | 250 |  | Full Capacity |  |  | Group 2 | SAN FRANCISCO | CA | PGAE | Northern | Martin 115 kV | 2023-06-30 07:00 | 2025-03-14 07:00 |  |  | Complete | Complete |  | Executed
CAISO | JEWELFLOWER STORAGE | 1553 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 354.88 |  |  | 350 |  | Full Capacity |  |  | Group 3 | SANTA CLARA | CA | PGAE | Northern | Metcalf 230 kV | 2022-12-31 08:00 | 2025-03-27 07:00 |  |  | Complete | Complete
CAISO | NOOSA ENERGY STORAGE | 1557 | 2019-04-15 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 99 |  |  | 99 |  | Full Capacity |  |  | Group 3 | SAN JOAQUIN | CA | PGAE | Northern | Ripon 115 kV | 2022-12-16 08:00 | 2025-05-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | DYNAMO SOLAR | 1565 | 2019-04-08 | 2019-04-15 07:00 | ACTIVE | C12 |  | Photovoltaic |  |  |  | Solar |  |  |  | 24.5 |  |  | 24.5 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | NAPA | CA | PGAE | Northern | Tulucay 60 kV | 2023-06-30 07:00 | 2025-11-21 08:00 |  |  | Complete | Complete |  | Executed
CAISO | AIR STATION 1 | 1568 | 2019-04-16 | 2019-04-15 07:00 | ACTIVE | C12 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 21.05 | 21.05 |  | 40 |  | Energy Only |  | Off-Peak Energy Only | Other | KINGS | CA | PGAE | Fresno | Henrietta-Lemoore NAS 70 kV | 2021-12-31 08:00 | 2021-12-31 08:00 |  |  | Complete | Complete |  | In Progress
CAISO | ARCTURUS | 1586 | 2019-04-04 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 152.29 | 151.794 |  | 150 |  | Energy Only |  | Off-Peak Energy Only | Group 3 | KERN | CA | PGAE | Kern | Arco 230 kV | 2022-12-30 08:00 | 2026-11-03 08:00 |  |  | Complete | Complete |  | Executed
CAISO | KINGSROAD HYBRID SOLAR | 1587 | 2019-04-16 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 101.78 | 101.78 |  | 100 |  | Energy Only |  | Off-Peak Energy Only | Group 2a | KERN | CA | PGAE | Kern | Arco 230 kV | 2023-11-30 08:00 | 2026-01-15 08:00 |  |  | Complete | Complete |  | Executed
CAISO | PELICANS JAW HYBRID SOLAR | 1593 | 2019-04-09 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 500 | 500 |  | 500 |  | Partial Capacity | 47.8 | Off-Peak Energy Only | Group A | KINGS | CA | PGAE | Fresno | Gates-Midway 230 kV Line | 2022-11-30 08:00 | 2028-01-24 08:00 |  |  | Complete | Complete |  | Executed
CAISO | BUTTONBUSH SOLAR HYBRID ENERGY CENTER | 1596 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 818 | 818 |  | 800 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | PGAE | Kern | Midway 500 kV | 2025-11-01 07:00 | 2026-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ARATINA SOLAR CENTER 2 | 1604 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 200 | 200 |  | 200 |  | Partial Capacity | 56.5 | Off-Peak Deliverability | Group 1a | KERN | CA | SCE | NOL | Kramer Substation 230kV | 2022-06-01 07:00 | 2025-10-29 07:00 |  |  | Complete | Complete |  | Executed
CAISO | AVOCET STORAGE | 1608 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 200 |  |  | 200 |  | Full Capacity |  |  | Group 2 | LOS ANGELES | CA | SCE | Metro | Hinson Substation 230kV | 2023-06-30 07:00 | 2026-04-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | COMMERCE ENERGY STORAGE | 1611 | 2019-04-09 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 250 |  |  | 250 |  | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Metro | Laguna Bell Substation 230kV | 2023-01-01 08:00 | 2026-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | KESTREL STORAGE | 1615 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 200 |  |  | 200 |  | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Metro | Walnut Substation 220kV | 2023-06-30 07:00 | 2025-05-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LOCKHART SOLAR 2 | 1617 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 59.7 | 105 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability | Group B | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2022-12-01 08:00 | 2025-11-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | GOLDBACK SOLAR CENTER | 1619 | 2019-04-12 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 500 |  |  | 500 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | VENTURA | CA | SCE | Northern | Moorpark Substation 230 kV | 2023-06-01 07:00 | 2026-03-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ANGELENO SOLAR FARM | 1625 | 2019-03-31 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 1150 | 1150 |  | 1150 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | LOS ANGELES | CA | SCE | Northern | Vincent Substation 500kV | 2023-06-01 07:00 | 2026-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | HUMIDOR STORAGE 1 | 1629 | 2019-04-11 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 305 |  |  | 300 |  | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Northern | Vincent Substation 230 kV | 2021-12-01 08:00 | 2025-08-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BELLEFIELD 2 SOLAR FARM | 1631 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 500 | 500 |  | 500 |  | Full Capacity |  | Off-Peak Deliverability | Group 2a | KERN | CA | SCE | Northern | Windhub Substation 220kV | 2022-10-01 07:00 | 2024-09-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SANBORN HYBRID 3 | 1632 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 671.55 | 778.5456 |  | 1400 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Windhub Substation 500kV | 2023-12-01 08:00 | 2026-07-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CALYPSO SOLAR | 1636 | 2019-04-04 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 400 | 400 |  | 400 |  | Energy Only |  | Off-Peak Energy Only | Group D | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230kV | 2023-12-01 08:00 | 2031-10-28 07:00 |  |  | Complete | Complete |  | Executed
CAISO | OBERON | 1642 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 518.4 | 518.4 |  | 500 |  | Partial Capacity | 51.06 | Off-Peak Deliverability | Group 2a | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 500kV | 2022-12-31 08:00 | 2026-04-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LYCAN SOLAR | 1643 | 2019-04-04 | 2019-04-15 07:00 | ACTIVE | C12 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 400 | 400 |  | 400 |  | Full Capacity |  | Off-Peak Energy Only | Group B | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 500kV | 2023-12-01 08:00 | 2030-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | MENIFEE POWER BANK | 1645 | 2019-04-10 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 680 |  |  | 680 |  | Full Capacity |  |  | Other | RIVERSIDE | CA | SCE | Eastern | Valley Substation 500kV | 2022-12-01 08:00 | 2025-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | DOUBLE BUTTE STORAGE | 1646 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 507.6 |  |  | 500 |  | Full Capacity |  |  | Group A | RIVERSIDE | CA | SCE | Eastern | Valley Substation 500 kV | 2022-12-31 08:00 | 2030-07-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ARIDA 2 SOLAR FARM | 1647 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 700 | 700 |  | 700 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | CLARK | NV | SCE | EOP | Mohave Substation 500kV | 2022-10-01 07:00 | 2027-12-30 08:00 |  |  | Complete | Complete
CAISO | BONANZA SOLAR | 1649 | 2019-04-05 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 150 | 300 |  | 300 |  | Partial Capacity | 73.71 | Off-Peak Deliverability | Group B | CLARK/NYE | NV | GLW | EOP | Innovation Substation 230 kV | 2023-12-01 08:00 | 2028-09-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ROUGH HAT HYBRID SOLAR | 1650 | 2019-04-15 | 2019-04-15 07:00 | ACTIVE | C12 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 204 | 200 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group A | NYE | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2022-11-30 08:00 | 2028-07-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | YELLOW PINE 3 | 1654 | 2019-04-09 | 2019-04-15 07:00 | ACTIVE | C12 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 261.954 | 254.98 |  | 250 |  | Full Capacity |  | Off-Peak Deliverability | Group B | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2025-03-15 07:00 | 2027-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | BONANZA PEAK SOLAR FARM | 1655 | 2019-04-12 | 2019-04-12 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 200 | 441 |  | 400 |  | Full Capacity |  | Off-Peak Deliverability | Group D | CLARK/NYE | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2022-12-16 08:00 | 2027-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SANDPIPER STORAGE | 1657 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 200 |  |  | 200 |  | Partial Capacity | 50 |  | Group 2a | ORANGE | CA | SDGE | SDGE | Talega Substation 138 kV | 2023-06-30 07:00 | 2025-03-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CIMARRON WIND | 1660 | 2019-03-29 | 2019-04-15 07:00 | ACTIVE | C12 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 352.5 |  |  | 300 |  | Full Capacity |  | Off-Peak Deliverability | Group A | TECATE | MX | SDGE | SDGE | East County Substation 230 kV | 2023-12-31 08:00 | 2025-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | VENTASSO ENERGY STORAGE | 1662 | 2019-04-06 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 50.774 |  |  | 50 |  | Full Capacity |  |  | Group 3 | SAN DIEGO | CA | SDGE | SDGE | El Cajon Substation 69 kV | 2022-11-30 08:00 | 2025-09-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | HOODINI | 1663 | 2019-04-13 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 112.63 | 459.54 |  | 450 |  | Energy Only |  | Off-Peak Deliverability | Group 3 | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2023-05-31 07:00 | 2028-01-31 08:00 |  |  | Complete | Complete
CAISO | VOLTA DE MEXICALI | 1664 | 2019-03-29 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 500 |  |  | 500 |  | Energy Only |  |  | Group 3 | SONORA | MX | SDGE | SDGE | Imperial Valley Substation 230 kV | 2021-12-31 08:00 | 2035-03-10 08:00 |  |  | Complete | Complete
CAISO | KINGSLEY SOLAR FARM | 1665 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 360 | 360 |  | 360 |  | Partial Capacity | 20.6 | Off-Peak Deliverability | Group D | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2023-06-01 07:00 | 2030-01-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SUNRISE BUTTE | 1667 | 2019-04-12 | 2019-04-15 07:00 | ACTIVE | C12 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 0 | 150 |  | 150 |  | Energy Only |  | Off-Peak Deliverability | Group 3 | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2022-12-31 08:00 | 2029-11-18 08:00 |  |  | Complete | Complete |  | Executed
CAISO | POME BESS | 1669 | 2019-04-13 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 100 |  |  | 100 |  | Full Capacity |  |  | Group 3 | SAN DIEGO | CA | SDGE | SDGE | Pomerado Substation 69 kV | 2023-05-31 07:00 | 2025-03-24 07:00 |  |  | Complete | Complete |  | Executed
CAISO | PEREGRINE STORAGE | 1670 | 2019-04-01 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 200 |  |  | 200 |  | Partial Capacity | 50 |  | Group 2 | SAN DIEGO | CA | SDGE | SDGE | Silvergate Substation 230 kV | 2023-06-30 07:00 | 2025-01-30 08:00 |  |  | Complete | Complete |  | Executed
CAISO | MARINE DEPOT | 1671 | 2019-04-16 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 26.6 |  |  | 25 |  | Energy Only |  |  | Other | SAN DIEGO | CA | SDGE | SDGE | Point Loma Substation 69 kV | 2021-12-31 08:00 | 2026-10-20 07:00 |  |  | Complete | Complete
CAISO | NIGHTHAWK STORAGE | 1673 | 2019-04-02 | 2019-04-15 07:00 | ACTIVE | C12 |  | Storage |  |  |  | Battery |  |  |  | 300 |  |  | 300 |  | Full Capacity |  |  | Group 2 | SAN DIEGO | CA | SDGE | SDGE | Sycamore Canyon Substation 138 kV | 2023-06-30 07:00 | 2025-03-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | HARQUAHALA SUNRISE | 1678 | 2020-03-13 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 308.926 | 308.926 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability | Other | MARICOPA | AZ | DCRT | Eastern | Delaney Substation 500 kV | 2022-04-01 07:00 | 2030-04-01 07:00 |  |  | Complete | Complete
CAISO | AQUEDUCT ENERGY STORAGE | 1683 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 102.25 |  |  | 100 |  | Energy Only |  | Off-Peak Deliverability | Group D | CONTRA COSTA | CA | PGAE | Northern | Contra Costa-Delta 230 kV Line | 2023-12-31 08:00 | 2026-04-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CONAWAY HYBRID POWER PLANT | 1687 | 2020-04-08 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 84.8117 | 84.9957 |  | 80 |  | Energy Only |  | Off-Peak Deliverability | Other | YOLO | CA | PGAE | Northern | Woodland-Davis 115 kV Line | 2023-01-01 08:00 | 2023-01-01 08:00 |  |  | Complete | Complete
CAISO | DENALI ENERGY STORAGE | 1690 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 102 |  |  | 101.2 |  | Partial Capacity | 92 |  | Group B | SAN JOAQUIN | CA | PGAE | Northern | Vierra 115 kV | 2023-06-15 07:00 | 2028-09-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | FORTIS | 1691 | 2020-04-09 | 2020-04-15 07:00 | ACTIVE | C13 |  | Wind Turbine | Storage | Photovoltaic |  | Wind Turbine | Battery | Solar |  | 207.2 | 203.94 | 205.02 | 200 |  | Energy Only |  | Off-Peak Deliverability | Group D | SOLANO | CA | PGAE | Northern | Birds Landing 230 kV | 2024-12-15 08:00 | 2028-02-11 08:00 |  |  | Complete | Complete |  | Executed
CAISO | POTENTIA-VIRIDI | 1702 | 2020-04-13 | 2020-04-15 07:00 | ACTIVE | C13 |  | Wind Turbine | Photovoltaic | Storage |  | Wind Turbine | Solar | Battery |  | 408.8 | 410.04 | 405.9 | 400 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | SAN JOAQUIN | CA | PGAE | Northern | Tesla 500 kV | 2024-12-15 08:00 | 2028-05-11 07:00 |  |  | Complete | Complete |  | Executed
CAISO | STEEL CITY BATTERY STORAGE | 1705 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 675 |  |  | 220 |  | Energy Only |  |  | Group 3 | CONTRA COSTA | CA | PGAE | Northern | Pittsburg 230 kV | 2025-06-30 07:00 | 2029-03-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ROSEMARY | 1709 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 36.1746 | 36.1746 |  | 35 |  | Full Capacity |  | Off-Peak Deliverability | Group D | FRESNO | CA | PGAE | Northern | Crescent 70 kV | 2023-12-01 08:00 | 2028-04-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | LEAD | 1713 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 32.7 |  |  | 32 |  | Partial Capacity |  |  | Group B | KINGS | CA | PGAE | Fresno | GWF Hanford 115 kV | 2023-08-01 07:00 | 2024-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | GONZAGA HYBRID | 1718 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Wind Turbine |  |  | Battery | Wind Turbine |  |  | 54.94 | 60.45 |  | 103.65 |  | Full Capacity |  | Off-Peak Deliverability | Group B | MERCED | CA | PGAE | Fresno | Los Banos 70 kV | 2024-07-01 07:00 | 2026-03-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ZETA | 1728 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 77.4774 | 77.4774 |  | 75 |  | Full Capacity |  | Off-Peak Deliverability | Group B | MERCED | CA | PGAE | Fresno | Mercy Springs 70 kV | 2023-12-01 08:00 | 2027-05-26 07:00 |  |  | Complete | Complete |  | Executed
CAISO | HAWKINS SOLAR HYBRID | 1736 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 250 | 250 |  | 250 |  | Partial Capacity | 76.75 | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Arco 230 kV | 2024-04-01 07:00 | 2027-05-01 07:00 |  |  | Complete | Complete |  | In Progress
CAISO | PECHO ENERGY STORAGE | 1739 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Other |  |  | Battery | Other |  |  | 108 | 520 |  | 500 |  | Partial Capacity | 92.98 | Off-Peak Deliverability | Group B | SAN LUIS OBISPO | CA | PGAE | Kern | Morro Bay 230 kV | 2023-06-01 07:00 | 2031-01-24 08:00 |  |  | Complete | Complete |  | Executed
CAISO | PUFF HYBRID SOLAR | 1740 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 101.8 | 101.8 |  | 100 |  | Full Capacity |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Arco 230 kV | 2024-11-30 08:00 | 2024-11-30 08:00 |  |  | Complete | Complete
CAISO | CRYSTAL FLATS | 1744 | 2020-04-02 | 2020-04-15 07:00 | ACTIVE | C13 |  | Solar Thermal | Storage |  |  | Solar | Battery |  |  | 103.455 | 51.401 |  | 100 |  | Energy Only |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Lamont 115 kV | 2023-10-31 07:00 | 2030-12-26 08:00 |  |  | Complete | Complete |  | Executed
CAISO | SUNRISE POWER IMPROVEMENT | 1745 | 2020-04-06 | 2020-04-15 07:00 | ACTIVE | C13 |  | Combined Cycle |  |  |  | Natural Gas |  |  |  | 655.7 |  |  | 35 |  | Energy Only |  |  | Other | KERN | CA | PGAE | Kern | Midway 230 kV | 2023-06-01 07:00 | 2024-05-11 07:00 |  |  | Complete | Complete
CAISO | WHALE ROCK ENERGY | 1749 | 2020-04-13 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 75 |  |  | 299.65 |  | Energy Only |  | Off-Peak Deliverability | Group 3 | SAN LUIS OBISPO | CA | PGAE | Kern | Caliente 230 kV | 2024-12-31 08:00 | 2031-04-27 07:00 |  |  | Complete | Complete |  | In Progress
CAISO | WINDWALKER OFFSHORE | 1750 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 1028.94 |  |  | 1000 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | SAN LUIS OBISPO | CA | PGAE | Kern | Diablo Canyon 500 kV | 2027-03-31 07:00 | 2028-02-12 08:00 |  |  | Complete | Complete |  | Executed
CAISO | WINSTON HYBRID PV AND BESS | 1751 | 2020-04-08 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 102 | 204 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group A | KERN | CA | PGAE | Kern | Midway 115 kV | 2025-03-01 08:00 | 2028-12-10 08:00 |  |  | Complete | Complete |  | Executed
CAISO | COBALT | 1757 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 256.202 | 256.41 |  | 250 |  | Energy Only |  | Off-Peak Deliverability | Group 3 | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 220kV | 2023-10-31 07:00 | 2027-05-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | DESERT SANDS | 1758 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 300 |  |  | 300 |  | Full Capacity |  | Off-Peak Deliverability | Group B | RIVERSIDE | CA | SCE | Eastern | Devers Substation 230kV | 2024-11-30 08:00 | 2027-05-31 07:00 |  |  | Complete | Complete
CAISO | GRACE ENERGY CENTER | 1761 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 508.56 | 508.56 |  | 500 |  | Partial Capacity | 10 | Off-Peak Deliverability | Group B | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230kV | 2024-11-30 08:00 | 2027-05-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | PORTA | 1763 | 2020-04-09 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic | Wind Turbine |  | Battery | Solar | Wind Turbine |  | 204.16 | 203.76 | 207.2 | 200 |  | Energy Only |  | Off-Peak Deliverability | Group B | RIVERSIDE | CA | SCE | Eastern | DEVERS SUBSTATION 220kV | 2024-12-15 08:00 | 2029-01-31 08:00 |  |  | Complete | Complete
CAISO | SAPPHIRE SOLAR | 1764 | 2020-04-07 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 117 | 126.2907 |  | 117 |  | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230kV | 2024-12-01 08:00 | 2025-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | COMMERCE ENERGY STORAGE 2 | 1766 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 250 |  |  | 250 |  | Full Capacity |  |  | Group 3 | LOS ANGELES | CA | SCE | Metro | Laguna Bell Substation 230kV | 2023-12-01 08:00 | 2026-03-15 07:00 |  |  | Complete | Complete
CAISO | ROADHOUSE STORAGE | 1768 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 312.96 |  |  | 300 |  | Full Capacity |  |  | Group 3 | SAN BERNARDINO | CA | SCE | Metro | Mira Loma Substation 230kV | 2024-11-30 08:00 | 2027-06-12 07:00 |  |  | Complete | Complete |  | Executed
CAISO | OVERNIGHT SOLAR | 1774 | 2020-04-09 | 2020-04-15 07:00 | ACTIVE | C13 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 150 | 150 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability | Group A | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230kV | 2024-10-31 07:00 | 2027-05-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SEGS EXPANSION 2 HYBRID | 1775 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 45 | 100 |  | 100 |  | Energy Only |  | Off-Peak Deliverability | Group B | SAN BERNARDINO | CA | SCE | NOL | Kramer Junction Substation 230kV | 2023-12-15 08:00 | 2025-11-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | VENTOSO | 1776 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 |  | Wind Turbine | Photovoltaic | Storage |  | Wind Turbine | Solar | Battery |  | 212.18 | 206.59 | 204.16 | 200 |  | Energy Only |  | Off-Peak Deliverability | Group B | SAN BERNARDINO | CA | SCE | NOL | COOLWATER SUBSTATION 115kV | 2024-12-15 08:00 | 2027-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BELLEFIELD 3 SOLAR FARM | 1779 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 150 | 150 |  | 150 |  | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2023-04-01 07:00 | 2027-04-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | WILLOW ROCK ENERGY STORAGE | 1782 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Other |  |  | Battery | Other |  |  | 108 | 512 |  | 500 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2023-06-01 07:00 | 2028-03-31 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SHOALS ENERGY STORAGE | 1783 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 409 |  |  | 400 |  | Full Capacity |  |  | Other | VENTURA | CA | SCE | Northern | Mandalay Switchyard 220kV | 2023-07-01 07:00 | 2026-07-15 07:00 |  |  | Complete | Complete
CAISO | KEYHOLE WIND | 1784 | 2020-04-06 | 2020-04-15 07:00 | ACTIVE | C13 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 100 |  |  | 100 |  | Full Capacity |  | Off-Peak Deliverability | Group A | KERN | CA | SCE | Northern | Whirlwind Substation 230kV | 2024-12-01 08:00 | 2028-06-28 07:00 |  |  | Complete | Complete |  | Executed
CAISO | REXFORD 2 SOLAR FARM | 1789 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 200 | 200 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | TULARE | CA | SCE | Northern | Vestal Substation 230kV | 2023-04-01 07:00 | 2026-09-01 07:00 |  |  | Complete | Complete
CAISO | SANBORN HYBRID 4 | 1790 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 50 | 50 |  | 100 |  | Energy Only |  | Off-Peak Deliverability | Group B | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2022-12-15 08:00 | 2025-10-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SANBORN 5 HYBRID | 1791 | 2020-04-10 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 574.8854 |  |  | 550 |  | Energy Only |  |  | Group D | KERN | CA | SCE | Northern | Windhub Substation 230kV | 2024-12-15 08:00 | 2027-05-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SEQUOIA | 1792 | 2020-04-03 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 200 | 200 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | TULARE | CA | SCE | Northern | Vestal Substation 230 kV | 2023-10-31 07:00 | 2031-04-01 07:00 |  |  | Complete | Complete
CAISO | ARIDA 3 SOLAR FARM | 1795 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 450 | 450 |  | 450 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | CLARK | NV | SCE | EOP | Mohave Substation 500kV | 2025-04-01 07:00 | 2030-07-01 07:00 |  |  | Complete | Complete
CAISO | DELAMAR ENERGY STORAGE | 1796 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 256.29 |  |  | 250 |  | Full Capacity |  |  | Group D | CLARK | NV | SCE | EOP | Eldorado Substation 230kV | 2024-08-01 07:00 | 2027-06-01 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CALVADA SPRINGS SOLAR | 1798 | 2020-04-08 | 2020-04-15 07:00 | ACTIVE | C13 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 250 | 250 |  | 250 |  | Full Capacity |  | Off-Peak Deliverability | Group D | INYO | CA | GLW | EOP | Trout Canyon Substation 230 kV | 2022-12-16 08:00 | 2027-12-31 08:00 |  |  | Complete | Complete
CAISO | ROUGH HAT 2 | 1799 | 2020-04-02 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 203.8 | 203.8 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2024-09-30 07:00 | 2027-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | PURPLE SAGE ENERGY CENTER | 1800 | 2020-03-31 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 408.24 | 409.2 |  | 400 |  | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2024-12-31 08:00 | 2027-12-31 08:00 |  |  | Complete | Complete |  | Executed
CAISO | WATER ROCK SOLAR 1 | 1801 | 2020-04-02 | 2020-04-15 07:00 | ACTIVE | C13 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 200 | 200 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Gamebird Substation 230 kV | 2025-12-01 08:00 | 2027-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | CAPTIVA ENERGY STORAGE | 1806 | 2020-04-14 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 256.875 |  |  | 250 |  | Full Capacity |  |  | Group 3 | ORANGE | CA | SDGE | SDGE | Trabuco - Capistrano 138 kV Line | 2024-06-01 07:00 | 2025-07-02 07:00 |  |  | Complete | Complete |  | Executed
CAISO | EAST FIELD ENERGY STORAGE | 1810 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 312.96 |  |  | 300.01 |  | Energy Only |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | Otay Mesa Switchyard 230 kV | 2024-11-30 08:00 | 2027-06-25 07:00 |  |  | Complete | Complete |  | Executed
CAISO | DATELAND ENERGY COMPLEX | 1812 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 237.5 | 112.5 |  | 350 |  | Full Capacity |  | Off-Peak Deliverability | Group 3 | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2024-12-01 08:00 | 2026-12-01 08:00 |  |  | Complete | Complete |  | Executed
CAISO | HEDIONDA ENERGY STORAGE | 1814 | 2020-04-01 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 160 |  |  | 160 |  | Energy Only |  |  | Other | SAN DIEGO | CA | SDGE | SDGE | Encina Substation 138 kV | 2023-03-31 07:00 | 2024-02-08 08:00 |  |  | Complete | Complete
CAISO | SADDLE MOUNTAIN SOLAR | 1818 | 2020-04-06 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 62.1 | 126.9 |  | 125 |  | Energy Only |  | Off-Peak Deliverability | Group B | MARICOPA | AZ | SDGE | SDGE | Hassayampa Common Bus 500 kV | 2023-02-10 08:00 | 2025-12-31 08:00 |  |  | Complete | Complete
CAISO | SCAFELL STORAGE | 1820 | 2020-04-12 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 52 |  |  | 50 |  | Energy Only |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | Creelman Substation 69 kV | 2022-11-15 08:00 | 2033-06-20 07:00 |  |  | Complete | Complete
CAISO | SEGURO STORAGE | 1821 | 2020-04-15 | 2020-04-15 07:00 | ACTIVE | C13 |  | Storage |  |  |  | Battery |  |  |  | 407 |  |  | 400 |  | Partial Capacity | 80 |  | Group A | SAN DIEGO | CA | SDGE | SDGE | Escondido Substation 230 kV | 2025-10-30 07:00 | 2032-05-14 07:00 |  |  | Complete | Complete
CAISO | VIENTO FRONTERIZO | 1824 | 2020-04-11 | 2020-04-15 07:00 | ACTIVE | C13 |  | Wind Turbine |  |  |  | Wind Turbine |  |  |  | 1001 |  |  | 972.82 |  | Energy Only |  | Off-Peak Deliverability | Group D | MUNICIPALITY OF TECATE | MX | SDGE | SDGE | East County Substation 500 kV | 2024-09-30 07:00 | 2032-08-28 07:00 |  |  | Complete | Complete
CAISO | WELLHEAD POWER PANOCHE, LLC | 1828 | 2019-12-24 | 2020-07-14 07:00 | ACTIVE | FT |  | Storage |  |  |  | Battery |  |  |  | 5 |  |  | 5 |  | Energy Only |  |  |  | FRESNO | CA | PGAE | Northern | Panoche 115 kV | 2021-04-01 07:00 | 2021-04-01 07:00
CAISO | MIDLAND ES | 1831 | 2020-12-08 | 2021-02-26 08:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.4 |  |  | 400 |  | Full Capacity |  |  | Group D | SAN LUIS OBISPO | CA | PGAE | Northern | Morro Bay 230 kV | 2024-11-01 07:00 | 2032-03-01 08:00 |  |  | Complete | Complete
CAISO | CASCADE ENERGY STORAGE EXPANSION | 1835 | 2021-02-26 | 2021-05-03 07:00 | ACTIVE | ISP |  | Storage |  |  |  | Battery |  |  |  | 20.25 |  |  | 20 |  | Full Capacity |  |  |  | SAN JOAQUIN | CA | PGAE | Northern | Weber 60 kV | 2022-12-01 08:00 | 2024-10-02 07:00 |  |  | Complete | Complete
CAISO | TAMALPAIS ENERGY STORAGE | 1837 | 2021-04-03 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 313.7932 |  |  | 300 |  | Full Capacity |  |  |  | MARIN | CA | PGAE | NGBA | Ignacio 115 kV | 2025-06-01 07:00 | 2030-06-18 07:00 |  |  | Complete | Complete
CAISO | BOREALIS ENERGY STORAGE | 1838 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 313.7932 |  |  | 300 |  | Full Capacity |  |  | Group A | SONOMA | CA | PGAE | NGBA | Lakeville 115 kV | 2025-06-01 07:00 | 2030-06-18 07:00 |  |  | Complete | Complete
CAISO | GENOA ENERGY STORAGE | 1840 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 252 |  |  | 250 |  | Full Capacity |  |  | Group D | NAPA | CA | PGAE |  | Vaca-Lakeville #1 230 kV Line | 2024-08-01 07:00 | 2031-12-19 08:00 |  |  | Complete | Complete
CAISO | TOLENAS | 1842 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 417.3487 |  |  | 400 |  | Full Capacity |  |  | Group A | SOLANO | CA | PGAE | NGBA | Lambie 230 kV | 2026-06-01 07:00 | 2031-02-18 08:00 |  |  | Complete | Complete
CAISO | BRUSHY | 1843 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 400 |  |  | 400 |  | Full Capacity |  |  | Group D | SOLANO | CA | PGAE | NGBA | Lambie 230 kV | 2026-06-01 07:00 | 2031-02-18 08:00 |  |  | Complete | Complete
CAISO | WILDHORSE ENERGY CENTER | 1846 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 121.55 |  |  | 120 |  | Full Capacity |  | Off-Peak Deliverability |  | SONOMA | CA | PGAE | NGBA | Fulton 230 kV | 2025-04-01 07:00 | 2030-05-04 07:00 |  |  | Complete | Complete
CAISO | JUGLANS ENERGY STORAGE | 1847 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 710.6 |  |  | 700 |  | Full Capacity |  |  |  | SOLANO | CA | PGAE | NGBA | Vaca-Dixon 500 kV | 2024-06-30 07:00 | 2031-02-02 08:00 |  |  | Complete | Complete
CAISO | HIGH WINDS STORAGE | 1850 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 120.62 |  |  | 100 |  | Full Capacity |  |  | Group D | SOLANO | CA | PGAE | NGBA | Birds Landing 230 kV | 2024-03-30 07:00 | 2031-03-16 07:00 |  |  | Complete | Complete
CAISO | CORBY 2 | 1854 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 475.96 |  |  | 400 |  | Full Capacity |  |  | Group D | SOLANO | CA | PGAE | NGBA | Vaca-Dixon 230 kV | 2025-11-30 08:00 | 2031-03-16 07:00 |  |  | Complete | Complete
CAISO | ARGES BESS | 1856 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 102.15 |  |  | 100 |  | Full Capacity |  |  | Group B | SOLANO | CA | PGAE | NGBA | Vaca-Dixon 115 kV | 2024-06-01 07:00 | 2029-06-18 07:00 |  |  | Complete | Complete
CAISO | GRINDSTONE CREEK SOLAR | 1858 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic |  |  |  | Solar |  |  |  | 142.85 |  |  | 140 |  | Full Capacity |  | Off-Peak Deliverability |  | TEHAMA | CA | PGAE | NGBA | Cottonwood-Delevan #1 and #2 230 kV | 2024-08-31 07:00 | 2031-07-19 07:00 |  |  | Complete | Complete
CAISO | MAYACAMAS GEOTHERMAL | 1859 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Steam Turbine |  |  |  | Geothermal |  |  |  | 53 |  |  | 53 |  | Full Capacity |  |  | Group A | SONOMA | CA | PGAE | NGBA | Geysers #3-Cloverdale 115 kV Line | 2024-02-01 08:00 | 2030-10-19 07:00 |  |  | Complete | Complete
CAISO | VERBENA ENERGY STORAGE | 1862 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 50.5 |  |  | 49.2 |  | Full Capacity |  |  |  | SUTTER | CA | PGAE | NGBA | at Switch 125 outside Harter Sub | 2023-12-31 08:00 | 2028-03-01 08:00 |  |  | Complete | Complete
CAISO | STONY CREEK STORAGE | 1863 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 251.9 |  |  | 250 |  | Full Capacity |  | Off-Peak Deliverability |  | TEHAMA | CA | PGAE | NGBA | Cottonwood-Delevan #1 and #2 230 kV | 2024-08-31 07:00 | 2031-07-19 07:00 |  |  | Complete | Complete
CAISO | TOWNSHIP POWER BANK | 1864 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 50.5 |  |  | 49 |  | Energy Only |  |  |  | SUTTER | CA | PGAE | NGBA | Greenleaf #1 115 kV Tap | 2025-04-01 07:00 | 2028-03-01 08:00 |  |  | Complete | Complete
CAISO | SEAHAWK STORAGE | 1865 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 203.699 |  |  | 200 |  | Full Capacity |  |  | Group B | SANTA CRUZ | CA | PGAE | GBAY | Green Valley 115 kV | 2025-06-01 07:00 | 2029-09-18 07:00 |  |  | Complete | Complete |  | Executed
CAISO | TOKAY STORAGE | 1866 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 101.888 |  |  | 100 |  | Full Capacity |  |  | Group D | SANTA CLARA | CA | PGAE | GBAY | Santa Teresa 115 kV | 2025-06-01 07:00 | 2030-03-18 07:00 |  |  | Complete | Complete |  | In Progress
CAISO | VELAS | 1867 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 462.57 |  |  | 450 |  | Full Capacity |  |  | Group D | SAN JOAQUIN | CA | PGAE | GBAY | Schulte 115 kV | 2024-11-01 07:00 | 2031-08-18 07:00 |  |  | Complete | Complete
CAISO | STAGELINE ENERGY STORAGE | 1871 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 213.55 |  |  | 200 |  | Full Capacity |  |  |  | BUTTE | CA | PGAE | NGBA | Palermo 115 kV | 2024-06-01 07:00 | 2030-11-18 08:00 |  |  | Complete | Complete
CAISO | ALLEGHENY ENERGY STORAGE | 1872 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 353.2 |  |  | 325 |  | Full Capacity |  |  | Group D | CONTRA COSTA | CA | PGAE | GBAY | Pittsburg 115 kV | 2024-08-01 07:00 | 2032-09-20 07:00 |  |  | Complete | Complete
CAISO | COMMANDER ENERGY STORAGE | 1874 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 504 |  |  | 500 |  | Full Capacity |  |  | Group D | CONTRA COSTA | CA | PGAE | GBAY | Pittsburg 230 kV | 2024-08-01 07:00 | 2032-07-19 07:00 |  |  | Complete | Complete
CAISO | DELILAH ENERGY STORAGE | 1875 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 504 |  |  | 500 |  | Full Capacity |  |  | Group D | CONTRA COSTA | CA | PGAE | GBAY | Pittsburg-Tesla #1 230 kV Line | 2024-08-01 07:00 | 2032-07-19 07:00 |  |  | Complete | Complete
CAISO | DOUBLE SPRINGS ENERGY STORAGE | 1876 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 101 |  |  | 100 |  | Full Capacity |  |  | Group D | CALAVERAS | CA | PGAE | GBAY | Valley Springs 60 kV | 2024-11-29 08:00 | 2029-08-17 07:00 |  |  | Complete | Complete |  | In Progress
CAISO | JAGUAR ENERGY STORAGE | 1877 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 252 |  |  | 250 |  | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBAY | Grant-Eastshore #1 115 kV Line | 2024-08-01 07:00 | 2034-01-18 08:00 |  |  | Complete | Complete
CAISO | PALMETTO ENERGY STORAGE | 1880 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 75.6 |  |  | 75 |  | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBAY | Oakland C 115 kV | 2024-08-01 07:00 | 2030-07-22 07:00 |  |  | Complete | Complete
CAISO | SPECTRUM ENERGY STORAGE | 1881 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 504 |  |  | 500 |  | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBAY | Tesla-Newark #1 230 kV Line | 2024-08-01 07:00 | 2034-03-19 07:00 |  |  | Complete | Complete
CAISO | PRESIDIO | 1887 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 356.592 | 356.592 |  | 350 |  | Full Capacity |  | Off-Peak Deliverability | Group A | SAN JOAQUIN | CA | PGAE | NGBA | Rancho Seco-Bellota #1 230 kV Line | 2025-06-01 07:00 | 2030-12-16 08:00 |  |  | Complete | Complete |  | Executed
CAISO | HOLMAN | 1889 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Wind Turbine |  |  | Battery | Wind Turbine |  |  | 756.813 | 1525.172 |  | 1500 |  | Partial Capacity | 50 | Off-Peak Deliverability | Group B | MONTEREY | CA | PGAE | GBAY | Moss Landing 500 kV | 2028-04-01 07:00 | 2034-02-17 08:00 |  |  | Complete | Complete
CAISO | HARMONY STORAGE 2 | 1892 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 307.878 |  |  | 300 |  | Full Capacity |  |  | Group A | CONTRA COSTA | CA | PGAE | GBAY | Contra Costa PP 230 kV | 2025-10-30 07:00 | 2031-06-05 07:00 |  |  | Complete | Complete
CAISO | OAKDALE STORAGE | 1895 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 102.672 |  |  | 100 |  | Partial Capacity | 54 |  | Group A | STANISLAUS | CA | PGAE | GBAY | Cottle 230 kV | 2025-10-30 07:00 | 2029-09-18 07:00 |  |  | Complete | Complete
CAISO | PATHFINDER STORAGE | 1896 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 268.065 |  |  | 260 |  | Full Capacity |  |  | Group A | SAN JOAQUIN | CA | PGAE | GBAY | Weber 60 kV | 2025-10-30 07:00 | 2031-06-05 07:00 |  |  | Complete | Complete |  | Executed
CAISO | BAYLANDS BATTERY | 1900 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 250 |  |  | 250 |  | Full Capacity |  |  | Group D | SAN MATEO | CA | PGAE | GBAY | Martin 115 kV | 2025-07-27 07:00 | 2034-05-18 07:00 |  |  | Complete | Complete
CAISO | GOLDEN FLATS | 1903 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 365.12 |  |  | 300 |  | Full Capacity |  |  | Group D | STANISLAUS | CA | PGAE | Fresno | Westly-Quinto 230 kV | 2025-11-30 08:00 | 2031-09-01 07:00 |  |  | Complete | Complete
CAISO | NORTHEAST CENTRAL VALLEY | 1904 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 365.12 |  |  | 300 |  | Full Capacity |  |  | Group D | SAN JOAQUIN | CA | PGAE | GBAY | Bellota 115 kV | 2025-11-30 08:00 | 2031-02-16 08:00 |  |  | Complete | Complete
CAISO | ZORIN STORAGE | 1911 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 252 |  |  | 180 |  | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBAY | Newark 230 kV | 2024-10-31 07:00 | 2034-02-19 08:00 |  |  | Complete | Complete
CAISO | ESPRESSO (FKA KOLA 2) | 1912 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 365.12 |  |  | 300 |  | Full Capacity |  |  | Group D | ALAMEDA | CA | PGAE | GBAY | Tesla 230 kV | 2025-11-30 08:00 | 2031-08-18 07:00 |  |  | Complete | Complete
CAISO | BLACK DIAMOND ES2 | 1914 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 179.4 |  |  | 175 |  | Full Capacity |  |  | Group B | CONTRA COSTA | CA | PGAE | GBAY | Pittsburg 230 kV | 2024-06-01 07:00 | 2031-06-18 07:00 |  |  | Complete | Complete
CAISO | SHERMAN ENERGY STORAGE | 1915 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 256.29 |  |  | 250 |  | Full Capacity |  |  | Group D | CONTRA COSTA | CA | PGAE | GBAY | Contra Costa PP 230 kV | 2025-06-01 07:00 | 2031-06-18 07:00 |  |  | Complete | Complete
CAISO | KIFER BESS 1 | 1918 | 2021-04-13 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 50 |  |  | 50 |  | Full Capacity |  |  | Group A | SANTA CLARA | CA | PGAE | GBAY | KEN-OKJ 60 kV | 2023-10-01 07:00 | 2025-12-18 08:00 |  |  |  | Complete
CAISO | SUNBEAM STORAGE | 1919 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 100.9 |  |  | 65 |  | Full Capacity |  |  | Group D | SAN MATEO | CA | PGAE | GBAY | Cooley Landing 60 kV | 2024-10-31 07:00 | 2034-02-19 08:00 |  |  | Complete | Complete
CAISO | ZEUS BESS | 1920 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 213.55 |  |  | 200 |  | Partial Capacity | 45 |  | Group B | SAN JOAQUIN | CA | PGAE | GBAY | Schulte 115 kV | 2024-06-01 07:00 | 2031-06-18 07:00 |  |  | Complete | Complete |  | Executed
CAISO | ALLIUM HYBRID | 1921 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 112.386 | 112.491 |  | 110 |  | Full Capacity |  | Off-Peak Deliverability | Group B | SAN BENITO | CA | PGAE | GBAY | Crazy Horse Canyon-Hollister 115 kV Line | 2025-06-01 07:00 | 2030-12-15 08:00 |  |  | Complete | Complete
CAISO | ALTA CASA STORAGE | 1922 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 515.418 |  |  | 500 |  | Full Capacity |  |  | Group B | SAN JOAQUIN | CA | PGAE | GBAY | Tesla 500 kV | 2025-06-01 07:00 | 2031-10-21 07:00 |  |  | Complete | Complete |  | Executed
CAISO | EL REY POWER BANK | 1928 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 124.3 |  |  | 120 |  | Energy Only |  |  |  | MONTEREY | CA | PGAE | GBAY | Coburn-Basic Energy 60 kV Line | 2025-04-01 07:00 | 2029-01-02 08:00 |  |  | Complete | Complete
CAISO | CAZADORES STORAGE | 1929 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 151.3 |  |  | 150 |  | Full Capacity |  |  | Group D | SAN JOAQUIN | CA | PGAE | GBAY | Lammers 115 kV | 2024-10-31 07:00 | 2032-08-19 07:00 |  |  | Complete | Complete
CAISO | APACHE STORAGE | 1930 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 203.699 |  |  | 200 |  | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | Kern | Sanger 115 kV | 2025-06-01 07:00 | 2029-05-21 07:00 |  |  | Complete | Complete |  | Executed
CAISO | COUGAR STORAGE | 1932 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 203.699 |  |  | 200 |  | Full Capacity |  |  | Group D | MERCED | CA | PGAE | Fresno | Wilson 115 kV | 2025-06-01 07:00 | 2030-09-19 07:00 |  |  | Complete | Complete |  | Executed
CAISO | PUMA STORAGE | 1933 | 2021-03-24 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 203.699 |  |  | 200 |  | Full Capacity |  |  | Group D | MADERA | CA | PGAE | Fresno | Borden 230 kV | 2025-06-01 07:00 | 2030-11-18 08:00 |  |  | Complete | Complete
CAISO | LOTUS SOLAR 2 | 1934 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 203.2 | 203.2 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | MADERA | CA | PGAE | Fresno | Borden 230 kV | 2024-12-01 08:00 | 2030-11-17 08:00 |  |  | Complete | Complete
CAISO | ELYSIAN | 1935 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 206.091 | 206.091 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2024-11-01 07:00 | 2029-10-18 07:00 |  |  | Complete | Complete |  | Executed
CAISO | WHITE RABBIT | 1940 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 150 |  |  | 150 |  | Energy Only |  | Off-Peak Deliverability | Group D | FRESNO | CA | PGAE | Fresno | Mendota 115 kV | 2024-11-01 07:00 | 2030-07-18 07:00 |  |  | Complete | Complete |  | Executed
CAISO | WINGTIP SOLAR 1 | 1943 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 1176.1 | 1176.1 |  | 1150 |  | Full Capacity |  | Off-Peak Deliverability | Group D | MERCED | CA | PGAE | S500 | Los Banos 500 kV | 2027-06-01 07:00 | 2032-09-18 07:00 |  |  | Complete | Complete
CAISO | DARDEN | 1949 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 1182.384 | 1182.384 |  | 1150 |  | Full Capacity |  | Off-Peak Deliverability | Group D | FRESNO | CA | PGAE | S500 | Manning-Midway 500kV Line | 2026-12-31 08:00 | 2031-08-19 07:00 |  |  | Complete | Complete |  | Executed
CAISO | AUSTRALIS | 1952 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 307 | 307 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability | Group A | MERCED | CA | PGAE | Fresno | Los Banos 230 kV | 2025-06-01 07:00 | 2031-04-18 07:00 |  |  | Complete | Complete
CAISO | FLORES STORAGE | 1953 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 151.7416 |  |  | 150 |  | Full Capacity |  | Off-Peak Deliverability | Group D | MADERA | CA | PGAE | Fresno | Gregg 230 kV | 2025-10-01 07:00 | 2031-02-18 08:00 |  |  | Complete | Complete
CAISO | HUASO HYBRID | 1954 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 101.83 | 102.1 |  | 100 |  | Full Capacity |  | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Gates 230 kV | 2025-12-01 08:00 | 2026-12-03 08:00 |  |  | Complete | Complete
CAISO | CIERVO MOUNTAIN HYBRID | 1955 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 127.37 | 127.57 |  | 125 |  | Full Capacity |  | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Excelsior 115 kV | 2025-12-01 08:00 | 2029-08-03 07:00 |  |  | Complete | Complete |  | Executed
CAISO | CLARKSON | 1956 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 203.659 | 203.849 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group A | FRESNO | CA | PGAE | Fresno | Tranquility 230 kV | 2025-06-01 07:00 | 2029-09-30 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SPIKES PEAK SOLAR | 1958 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 158.9783 | 158.5678 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability | Group B | MERCED | CA | PGAE | Fresno | Quinto 230 kV | 2025-10-01 07:00 | 2029-10-18 07:00 |  |  | Complete | Complete
CAISO | CORNUCOPIA HYBRID | 1959 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 300.951 | 303.678 |  | 300 |  | Partial Capacity | 95 | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Gates-Templeton 230 kV Line | 2025-06-16 07:00 | 2030-11-16 08:00 |  |  | Complete | Complete |  | Executed
CAISO | LAS CAMAS 4 | 1960 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 100 |  |  | 100 |  | Full Capacity |  |  | Group D | MERCED | CA | PGAE | Fresno | Los Banos 230 kV | 2025-05-07 07:00 | 2028-04-01 07:00 |  |  | Complete | Complete
CAISO | LOCK STORAGE | 1962 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 508 |  |  | 500.01 |  | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | S500 | Gates 500 kV | 2025-11-30 08:00 | 2030-06-17 07:00 |  |  | Complete | Complete
CAISO | ALMANDE ENERGY STORAGE | 1963 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 256.29 |  |  | 250 |  | Full Capacity |  |  | Group D | MERCED | CA | PGAE | Fresno | Wilson 230 kV | 2025-06-01 07:00 | 2030-06-18 07:00 |  |  | Complete | Complete
CAISO | ORLEANS | 1966 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 25.54 | 25.54 |  | 25 |  | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | Fresno | Giffen 70 kV | 2024-12-31 08:00 | 2029-08-03 07:00 |  |  | Complete | Complete
CAISO | PLUM | 1968 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 1040 | 520 |  | 1000 |  | Full Capacity |  | Off-Peak Deliverability |  | KINGS | CA | PGAE | Fresno | Gates 230 kV | 2024-12-10 08:00 | 2031-03-19 07:00 |  |  | Complete | Complete
CAISO | BUTTERCUP HYBRID SOLAR | 1970 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 131.43 | 65.47 |  | 130 |  | Full Capacity |  | Off-Peak Deliverability | Group D | MERCED | CA | PGAE | Fresno | Le Grand 115 kV | 2024-11-30 08:00 | 2032-03-04 08:00 |  |  | Complete | Complete
CAISO | PEACEFUL HOLLOW BESS | 1973 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 100 |  |  | 75 |  | Full Capacity |  |  | Group D | FRESNO | CA | PGAE | Fresno | Tranquility 230kV | 2024-06-01 07:00 | 2028-06-18 07:00 |  |  | Complete | Complete |  | Executed
CAISO | TARRAGON HYBRID | 1975 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 35.979 | 35.951 |  | 35 |  | Full Capacity |  | Off-Peak Deliverability | Group B | FRESNO | CA | PGAE | Fresno | Crescent 70 kV | 2025-06-01 07:00 | 2028-06-01 07:00 |  |  | Complete | Complete
CAISO | VALETUDO ENERGY STORAGE | 1977 | 2021-09-30 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 79.5871 |  |  | 75 |  | Full Capacity |  |  | Group B | MADERA | CA | PGAE | Fresno | Chowchilla 115 kV | 2022-12-31 08:00 | 2028-11-01 07:00 |  |  | Complete | Complete
CAISO | ARTEMIS | 1980 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 412.336 | 412.336 |  | 400 |  | Partial Capacity | 24 | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Arco 230 kV | 2024-11-01 07:00 | 2029-10-18 07:00 |  |  | Complete | Complete
CAISO | PHAENON | 1983 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 102.254 | 101.7635 |  | 100 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | PGAE | Kern | Shafter 115 kV | 2024-12-31 08:00 | 2029-07-18 07:00 |  |  | Complete | Complete
CAISO | BUTTONBUSH SOLAR 2 | 1987 | 2021-04-03 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 358.2 | 358.2 |  | 350 |  | Full Capacity |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | S500 | Midway 500 kV | 2028-04-01 07:00 | 2032-03-17 07:00 |  |  | Complete | Complete
CAISO | CALLINAN SOLAR AND STORAGE | 1992 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 159.4008 | 160.3879 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability | Group D | KERN | CA | PGAE | Kern | Arco 230 kV | 2025-10-01 07:00 | 2031-02-18 08:00 |  |  | Complete | Complete
CAISO | EIGER ENERGY STORAGE | 1994 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 100.9 |  |  | 100 |  | Full Capacity |  |  | Group D | KERN | CA | PGAE | Kern | Lamont 115 kV | 2025-01-01 08:00 | 2032-02-16 08:00 |  |  | Complete | Complete
CAISO | EVEREST ENERGY STORAGE | 1995 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 201.8 |  |  | 200 |  | Partial Capacity | 78 |  | Group D | KERN | CA | PGAE | Kern | Kern PP 230 kV | 2025-01-01 08:00 | 2030-10-18 07:00 |  |  | Complete | Complete
CAISO | ISLAY | 1998 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Wind Turbine |  |  | Battery | Wind Turbine |  |  | 756.054 | 1518.472 |  | 1500 |  | Full Capacity |  | Off-Peak Deliverability | Group D | SAN LUIS OBISPO | CA | PGAE | S500 | Diablo Canyon 500 kV | 2028-04-01 07:00 | 2034-08-16 07:00 |  |  | Complete | Complete
CAISO | SERENA STORAGE | 2001 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 114.264 |  |  | 110 |  | Full Capacity |  |  | Group A | KERN | CA | PGAE | Kern | Kern PP 230 kV | 2025-10-30 07:00 | 2029-09-18 07:00 |  |  | Complete | Complete
CAISO | VALLEY SUNLIGHT REFINERY | 2004 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 410 | 411.3018 |  | 400 |  | Full Capacity |  | Off-Peak Deliverability | Group D | KINGS | CA | PGAE | Kern | Gates-Midway 230 kV Line | 2025-06-10 07:00 | 2032-02-18 08:00 |  |  | Complete | Complete
CAISO | SALINAN ENERGY | 2008 | 2021-04-11 | 2021-04-15 07:00 | ACTIVE | C14 |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 1190 | 319.35 |  | 1148.37 |  | Full Capacity |  | Off-Peak Deliverability |  | SAN LUIS OBISPO | CA | PGAE | S500 | Diablo-Gates 500 kV Line | 2028-04-11 07:00 | 2032-09-17 07:00 |  |  | Complete | Complete
CAISO | CANNAE | 2010 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 118.5 | 115 |  | 115 |  | Full Capacity |  |  | Group D | KERN | CA | PGAE | Kern | Midway 115 kV | 2024-12-31 08:00 | 2030-12-03 08:00 |  |  | Complete | Complete
CAISO | ANDROMEDA | 2013 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 172.835 | 172.835 |  | 160 |  | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | PGAE | Kern | Alpaugh 115 kV | 2026-12-31 08:00 | 2029-04-10 07:00 |  |  | Complete | Complete
CAISO | CHERRY LANE HYBRID | 2015 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 310.63 | 310.63 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability | Group B | KERN | CA | PGAE | Kern | Wheeler Ridge 230 kV | 2025-06-01 07:00 | 2031-06-19 07:00 |  |  | Complete | Complete
CAISO | ARIELLA SOLAR | 2017 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 163.268 | 163.268 |  | 160 |  | Full Capacity |  | Off-Peak Deliverability | Group D | TULARE | CA | PGAE | Kern | Olive 115 kV | 2023-12-31 08:00 | 2030-12-17 08:00 |  |  | Complete | Complete
CAISO | HIDDEN KNOLLS BESS | 2018 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 30.8 |  |  | 30 |  | Full Capacity |  |  | Group D | KERN | CA | PGAE | Kern | Arco-Carneras 70 kV Line | 2024-06-01 07:00 | 2028-10-18 07:00 |  |  | Complete | Complete
CAISO | SOCORRO PEAK SOLAR | 2022 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 379.7505 | 376.0403 |  | 350 |  | Full Capacity |  | Off-Peak Deliverability | Group B | LA PAZ | AZ | DCRT | Eastern | Cielo Azul Substation 500 kV | 2025-10-01 07:00 | 2029-03-26 07:00 |  |  | Complete | Complete
CAISO | JOVE SOLAR | 2023 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 2042.4 | 2090.2 |  | 2000 |  | Full Capacity |  | Off-Peak Deliverability | Group D | LA PAZ | AZ | DCRT | Eastern | Cielo Azul Substation 500 kV | 2024-12-31 08:00 | 2030-01-26 08:00 |  |  | Complete | Complete
CAISO | RANEGRAS PVS | 2025 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 718.81 | 718.81 |  | 700 |  | Full Capacity |  | Off-Peak Deliverability | Group B | LA PAZ | AZ | DCRT | Eastern | Colorado River-Delaney 500 kV line | 2025-06-01 07:00 | 2029-07-26 07:00 |  |  | Complete | Complete
CAISO | HARQUAHALA FLATS 2 | 2027 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 410.76 | 410.76 |  | 400 |  | Full Capacity |  | Off-Peak Deliverability | Group D | MARICOPA | AZ | DCRT | Eastern | Delaney Substation 500 kV | 2025-11-30 08:00 | 2028-04-15 07:00 |  |  | Complete | Complete
CAISO | HARQUAHALA SUNRISE 2 | 2029 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 169.2 | 160.98 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability | Group A | MARICOPA | AZ | DCRT | Eastern | Delaney Substation 500 kV | 2024-11-01 07:00 | 2026-09-01 07:00 |  |  | Complete | Complete
CAISO | MARLEY | 2031 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 206.091 |  |  | 200 |  | Full Capacity |  |  | Group D | RIVERSIDE | CA | SCE | Eastern | Wildlife Substation 230 kV | 2024-11-01 07:00 | 2032-06-26 07:00 |  |  | Complete | Complete
CAISO | TROLLEY | 2032 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.6634 |  |  | 400 |  | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | Eastern | Etiwanda Substation 230 kV | 2024-06-30 07:00 | 2031-02-26 08:00 |  |  | Complete | Complete
CAISO | CARMINE | 2033 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 360.296 |  |  | 350 |  | Full Capacity |  | Off-Peak Deliverability | Group D | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230 kV | 2024-11-01 07:00 | 2030-12-26 08:00 |  |  | Complete | Complete
CAISO | HUB CITY ENERGY STORAGE | 2034 | 2021-04-03 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 261 |  |  | 250 |  | Partial Capacity | 40 |  | Group D | SAN BERNARDINO | CA | SCE | Eastern | Devers 220kV | 2025-06-01 07:00 | 2031-01-01 08:00 |  |  | Complete | Complete
CAISO | REDONDA | 2036 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 273.0212 | 268.7138 |  | 250 |  | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 220 kV | 2024-12-01 08:00 | 2031-01-01 08:00 |  |  | Complete | Complete
CAISO | SARGASSO STORAGE | 2037 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 202.8 |  |  | 200 |  | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | Eastern | San Bernadino 230 kV | 2024-12-15 08:00 | 2032-05-26 07:00 |  |  | Complete | Complete
CAISO | SANDRIFT STORAGE 1 | 2039 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 254.77 |  |  | 250 |  | Partial Capacity | 88.43 |  | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230 kV | 2023-12-31 08:00 | 2030-12-26 08:00 |  |  | Complete | Complete
CAISO | SANDRIFT STORAGE 2 | 2041 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 254.77 |  |  | 250 |  | Partial Capacity | 88.43 |  | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 230 kV | 2023-12-31 08:00 | 2030-12-26 08:00 |  |  | Complete | Complete
CAISO | EASLEY | 2042 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 650 | 350 |  | 650 |  | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 500 kV | 2024-12-31 08:00 | 2028-03-06 08:00 |  |  | Complete | Complete |  | In Progress
CAISO | PICADOR ENERGY STORAGE | 2043 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 252 |  |  | 250 |  | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | Eastern | Etiwanda Substation 230 kV | 2024-08-01 07:00 | 2032-05-26 07:00 |  |  | Complete | Complete
CAISO | INVICTUS | 2045 | 2021-04-10 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 430.192 | 430.192 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability | Group B | RIVERSIDE | CA | SCE | Eastern | Colorado River 230 kV | 2025-12-15 08:00 | 2029-11-26 08:00 |  |  | Complete | Complete
CAISO | TWIN PALMS SOLAR | 2048 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 288.144 | 288 |  | 280 |  | Full Capacity |  | Off-Peak Deliverability | Group A | RIVERSIDE | CA | SCE | Eastern | Colorado River Substation 230 kV | 2025-10-30 07:00 | 2030-01-30 08:00 |  |  | Complete | Complete
CAISO | ARDILLA | 2049 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 410.76 |  |  | 400 |  | Full Capacity |  |  | Group D | RIVERSIDE | CA | SCE | Eastern | Devers Substation 230kV | 2025-11-30 08:00 | 2032-04-26 07:00 |  |  | Complete | Complete
CAISO | ETERNAL 2 | 2050 | 2021-04-13 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Storage |  |  | Pumped-Storage hydro | Battery |  |  | 1417 | 1434.4 |  | 1400 |  | Full Capacity |  | Off-Peak Deliverability | Group D | RIVERSIDE | CA | SCE | Eastern | Red Bluff Substation 500 kV | 2026-12-01 08:00 | 2031-11-26 08:00 |  |  | Complete | Complete
CAISO | SALVADOR | 2051 | 2021-04-13 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 65 | 404.8 |  | 400 |  | Full Capacity |  | Off-Peak Deliverability | Group D | RIVERSIDE | CA | SCE | Eastern | MIRAGE Substation 220 kV | 2025-12-15 08:00 | 2030-12-26 08:00 |  |  | Complete | Complete
CAISO | BOUSE SOLAR AND STORAGE PLANT | 2052 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 1009.9 | 1010.88 |  | 1000 |  | Full Capacity |  | Off-Peak Deliverability | Group D | LA PAZ | AZ | SCE | Eastern | Colorado River - Palo Verde 500kV | 2026-02-05 08:00 | 2033-12-26 08:00 |  |  | Complete | Complete
CAISO | EUISMOD | 2055 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 623.48 | 623.48 |  | 600 |  | Full Capacity |  | Off-Peak Deliverability | Group B | KERN | CA | SCE | Northern | WHIRLWIND Substation 230 kV | 2024-06-30 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete
CAISO | FOUR CREEKS ENERGY STORAGE | 2058 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 261 |  |  | 250 |  | Full Capacity |  |  | Group B | TULARE | CA | SCE | Northern | Rector Substation 230 kV | 2025-06-01 07:00 | 2030-07-01 07:00 |  |  | Complete | Complete
CAISO | J90 ENERGY STORAGE | 2059 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 261 |  |  | 250 |  | Full Capacity |  | Off-Peak Deliverability | Group B | LOS ANGELES | CA | SCE | Northern | Antelope Substation 230 kV | 2025-06-01 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete |  | In Progress
CAISO | SAGEBRUSH ENERGY STORAGE | 2060 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 528 |  |  | 500 |  | Partial Capacity | 50 |  | Group D | KERN | CA | SCE | Northern | Vincent Substation 230 kV | 2025-07-01 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete
CAISO | JUNIPER STORAGE | 2061 | 2021-04-05 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 153.5 | 153.5 |  | 150 |  | Full Capacity |  | Off-Peak Deliverability |  | LOS ANGELES | CA | SCE | Northern | Vincent - Pearblossom 230 kV line | 2024-06-30 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete
CAISO | DORIAN STORAGE | 2062 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 213.5926 |  |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | LOS ANGELES | CA | SCE | Northern | Antelope Substation 230 kV | 2025-10-01 07:00 | 2034-08-26 07:00 |  |  | Complete | Complete
CAISO | ELION ENERGY STORAGE | 2064 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 302.4 |  |  | 300 |  | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Northern | Antelope ValleySubstation 230 kV | 2024-08-01 07:00 | 2034-05-26 07:00 |  |  | Complete | Complete
CAISO | DRIFTER ENERGY STORAGE | 2066 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 504.8 |  |  | 500 |  | Full Capacity |  |  | Group B | VENTURA | CA | SCE | Northern | Moorpark Substation 230 kV | 2024-08-01 07:00 | 2033-03-26 07:00 |  |  | Complete | Complete
CAISO | BOBOR STORAGE | 2068 | 2021-04-07 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 152.1 |  |  | 150 |  | Full Capacity |  |  | Group D | TULARE | CA | SCE | Northern | Rector Substation 230 kV | 2025-12-15 08:00 | 2030-12-26 08:00 |  |  | Complete | Complete
CAISO | SOLEIL CANTIL | 2078 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 372.3 | 225 |  | 350 |  | Full Capacity |  | Off-Peak Deliverability |  | KERN | CA | SCE | Northern | Windhub Substation 500kV | 2024-06-01 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete
CAISO | RANGELAND SOLAR | 2080 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 113.832 | 102.672 |  | 210 |  | Full Capacity |  | Off-Peak Deliverability | Group A | LOS ANGELES | CA | SCE | Northern | Antelope- Magunden #2 230 kV line | 2024-10-30 07:00 | 2033-08-26 07:00 |  |  | Complete | Complete
CAISO | MINERAL KING SOLAR | 2081 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 215.4124 | 214.0983 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | SCE | Northern | Rector Substation 220 kV | 2026-12-31 08:00 | 2029-09-26 07:00 |  |  | Complete | Complete
CAISO | ELECTRON | 2082 | 2021-04-12 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 300 |  |  | 300 |  | Energy Only |  |  |  | LOS ANGELES | CA | SCE | Northern | ANTELOPE Substation 220 kV | 2024-06-01 07:00 | 2033-01-26 08:00 |  |  | Complete | Complete
CAISO | SOLSKEN | 2085 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 345 | 464.42 |  | 460 |  | Full Capacity |  | Off-Peak Deliverability |  | TULARE | CA | SCE | Northern | Springville Substation 230 kV | 2024-04-15 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete
CAISO | GREASEWOOD ENERGY STORAGE | 2089 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 513.2 |  |  | 500 |  | Full Capacity |  |  | Group D | KERN | CA | SCE | Northern | Whirlwind Substation 500 kV | 2025-06-01 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete
CAISO | GWENT STORAGE 2 | 2090 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 473 |  |  | 465 |  | Full Capacity |  |  | Group D | VENTURA | CA | SCE | Northern | Moorpark Substation 230 kV | 2023-12-15 08:00 | 2033-01-26 08:00 |  |  | Complete | Complete
CAISO | MAATHAI | 2091 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 256 |  |  | 250 |  | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Northern | Vincent Substation 230 kV | 2023-12-15 08:00 | 2033-01-26 08:00 |  |  | Complete | Complete |  | In Progress
CAISO | ROSA STORAGE | 2092 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 511.725 |  |  | 500 |  | Full Capacity |  |  | Group D | VENTURA | CA | SCE | Northern | Moorpark Substation 230 kV | 2025-06-01 07:00 | 2034-06-27 07:00 |  |  | Complete | Complete
CAISO | HIDALGO ENERGY STORAGE | 2096 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 408.12 |  |  | 400 |  | Partial Capacity | 70 |  | Group B | SAN BERNARDINO | CA | SCE | NOL | Kramer-Lugo #1 220 kV | 2024-06-01 07:00 | 2033-09-26 07:00 |  |  | Complete | Complete
CAISO | SIENNA SOLAR 2 | 2097 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 56 | 56 |  | 55 |  | Full Capacity |  | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Calcite Substation 230 kV | 2025-12-01 08:00 | 2029-03-26 07:00 |  |  | Complete | Complete |  | In Progress
CAISO | WESTON STORAGE | 2101 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 213.5957 |  |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Kramer Substation 230 kV | 2025-10-01 07:00 | 2031-03-26 07:00 |  |  | Complete | Complete
CAISO | CADY SOLAR | 2103 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 312.96 | 312.96 |  | 300 |  | Partial Capacity | 80 | Off-Peak Deliverability | Group D | SAN BERNARDINO | CA | SCE | NOL | Pisgah Substation 230 kV | 2025-11-30 08:00 | 2031-02-26 08:00 |  |  | Complete | Complete
CAISO | DOS PALMAS | 2104 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 410.76 |  |  | 400 |  | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | NOL | Victor Substation 230 kV | 2025-11-30 08:00 | 2031-04-26 07:00 |  |  | Complete | Complete
CAISO | CONDUIT ENERGY STORAGE | 2105 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 512.58 |  |  | 500 |  | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | NOL | Lugo Substation 500 kV | 2025-06-01 07:00 | 2031-02-26 08:00 |  |  | Complete | Complete
CAISO | ADAGIO | 2109 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.6634 |  |  | 400 |  | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | Hinson Substation 230 kV | 2024-06-30 07:00 | 2032-04-28 07:00 |  |  | Complete | Complete
CAISO | FLEETWOOD | 2111 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.5148 |  |  | 400 |  | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | Litehipe Substation 230 kV | 2024-06-30 07:00 | 2032-04-28 07:00 |  |  | Complete | Complete
CAISO | GABRIEL STORAGE | 2113 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.7509 |  |  | 400 |  | Full Capacity |  |  | Group B | LOS ANGELES | CA | SCE | Metro | Rio Hondo Substation 230 kV | 2024-06-30 07:00 | 2033-02-26 08:00 |  |  | Complete | Complete
CAISO | DIRAC | 2114 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 403.4 |  |  | 400 |  | Full Capacity |  |  | Group D | SAN BERNARDINO | CA | SCE | Metro | Chino Substation 230 kV | 2024-06-30 07:00 | 2031-02-26 08:00 |  |  | Complete | Complete
CAISO | SIMON | 2115 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.7509 |  |  | 400 |  | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | La Cienega Substation 230 kV | 2024-06-30 07:00 | 2032-04-26 07:00 |  |  | Complete | Complete
CAISO | MARICI | 2116 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.5148 |  |  | 400 |  | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Walnut Substation 230 kV | 2024-06-30 07:00 | 2031-02-26 08:00 |  |  | Complete | Complete
CAISO | CORAL REEF | 2117 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 405.6634 |  |  | 400 |  | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | El Nido Substation 230 kV | 2024-06-30 07:00 | 2032-04-26 07:00 |  |  | Complete | Complete
CAISO | GREENWOOD ENERGY STORAGE | 2121 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 252 |  |  | 250 |  | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Mesa Substation 500 kV | 2024-08-01 07:00 | 2032-05-26 07:00 |  |  | Complete | Complete
CAISO | TABLA ENERGY STORAGE | 2124 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 302.4 |  |  | 300 |  | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Rio Hondo Substation 230 kV | 2024-08-01 07:00 | 2032-05-26 07:00 |  |  | Complete | Complete
CAISO | TYRELL ENERGY STORAGE | 2125 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 302.4 |  |  | 300 |  | Full Capacity |  |  | Group D | ORANGE | CA | SCE | Metro | Viejo Substation 230kV | 2024-08-01 07:00 | 2032-05-26 07:00 |  |  | Complete | Complete
CAISO | OTROS ALAMITOS ENERGY STORAGE | 2127 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 241.5 |  |  | 236 |  | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Alamitos 220 kV | 2025-10-30 07:00 | 2031-08-26 07:00 |  |  | Complete | Complete
CAISO | LOS NIETOS | 2129 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 102.26 |  |  | 100 |  | Full Capacity |  |  | Group D | ORANGE | CA | SCE | Metro | Johanna Substation 230 kV | 2024-11-01 07:00 | 2031-04-26 07:00 |  |  | Complete | Complete
CAISO | MERLIN STORAGE | 2131 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 200 |  |  | 200 |  | Full Capacity |  |  |  | LOS ANGELES | CA | SCE | Metro | Hinson Substation 220 kV | 2023-06-01 07:00 | 2032-05-26 07:00 |  |  | Complete | Complete
CAISO | HAVEN STORAGE | 2136 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 312.96 |  |  | 300 |  | Full Capacity |  |  | Group D | LOS ANGELES | CA | SCE | Metro | Rio Hondo Substation 230 kV | 2025-11-30 08:00 | 2031-02-26 08:00 |  |  | Complete | Complete |  | Executed
CAISO | COMMERCE ENERGY STORAGE 3 | 2139 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 256.29 |  |  | 250 |  | Full Capacity |  |  | Group D | L.A | CA | SCE | Metro | Laguna Bell Substation 230 kV | 2025-06-01 07:00 | 2031-02-26 08:00 |  |  | Complete | Complete
CAISO | STERLING | 2140 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 250 | 250 |  | 250 |  | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | SCE | EOP | Mohave Substation 500 kV | 2024-12-01 08:00 | 2031-05-26 07:00 |  |  | Complete | Complete
CAISO | DELAMAR ENERGY STORAGE 2 | 2141 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 256.29 |  |  | 250 |  | Full Capacity |  |  | Group B | CLARK | NV | SCE | EOP | SCE portion of Eldorado Substation 230 kV | 2025-06-01 07:00 | 2027-06-26 07:00 |  |  | Complete | Complete
CAISO | SILVER STAR SOLAR | 2142 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 516.7638 | 516.7638 |  | 500 |  | Partial Capacity | 0 | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Lathrop Wells Substation 230 kV | 2028-03-31 07:00 | 2028-12-01 08:00 |  |  | Complete | Complete |  | In Progress
CAISO | ROCK VALLEY ENERGY CENTER | 2144 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 515.08 | 508.56 |  | 500 |  | Energy Only |  | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Beatty Substation 230 kV | 2025-11-30 08:00 | 2029-03-15 07:00 |  |  | Complete | Complete |  | Executed
CAISO | DANDELION HYBRID SOLAR | 2145 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 223.33 | 110.87 |  | 220 |  | Full Capacity |  | Off-Peak Deliverability | Group B | NYE | NV | GLW | EOP | Vista Substation 230 kV | 2024-11-30 08:00 | 2027-12-26 08:00 |  |  | Complete | Complete
CAISO | WATER ROCK SOLAR 2 | 2146 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 516.7638 | 516.7638 |  | 500 |  | Partial Capacity | 0 | Off-Peak Deliverability | Group D | NYE | NV | GLW | EOP | Gamebird Substation 230 kV | 2028-03-31 07:00 | 2028-12-01 08:00 |  |  | Complete | Complete
CAISO | KAWICH | 2147 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 350 | 350 |  | 350 |  | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Innovation-Desert View 230 kV Line | 2025-06-01 07:00 | 2029-07-27 07:00 |  |  | Complete | Complete |  | Executed
CAISO | MOSEY | 2148 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 537.0067 | 543.856 |  | 500 |  | Full Capacity |  | Off-Peak Deliverability | Group A | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2025-06-01 07:00 | 2029-06-27 07:00 |  |  | Complete | Complete |  | Executed
CAISO | SUNBAKED SOLAR | 2149 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 515.08 | 508.56 |  | 500 |  | Energy Only |  | Off-Peak Deliverability | Group B | INYO | CA | GLW | EOP | Trout Canyon Substation 230 kV | 2025-11-30 08:00 | 2029-02-26 08:00 |  |  | Complete | Complete |  | Executed
CAISO | ROUGH HAT 3 | 2150 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 307 | 307 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability |  | CLARK | NV | GLW | EOP | Trout Canyon Substation 230 kV | 2024-09-01 07:00 | 2028-09-15 07:00 |  |  | Complete | Complete
CAISO | FRIGATEBIRD STORAGE | 2153 | 2021-03-23 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 213.5487 |  |  | 200 |  | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Silvergate Substation 230 kV | 2023-06-30 07:00 | 2035-03-05 08:00 |  |  | Complete | Complete
CAISO | REMY | 2154 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 308.47 | 308 |  | 300 |  | Full Capacity |  | Off-Peak Deliverability |  | YUMA | AZ | SDGE | SDGE | Hoodoo Wash Switchyard 500 kV | 2025-12-01 08:00 | 2029-06-30 07:00 |  |  | Complete | Complete
CAISO | GNARLY OSAGE | 2157 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 304.3999 |  |  | 300 |  | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Encina Substation 138 kV | 2024-06-30 07:00 | 2027-08-07 07:00 |  |  | Complete | Complete
CAISO | ALISA SOLAR ENERGY COMPLEX | 2161 | 2021-04-01 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 208.494 | 208.494 |  | 200 |  | Full Capacity |  | Off-Peak Deliverability | Group D | YUMA | AZ | SDGE | SDGE | Hoodoo Wash - North Gila 500 kV | 2024-06-01 07:00 | 2028-06-01 07:00 |  |  | Complete | Complete
CAISO | SOLAR DE MEXICALI | 2162 | 2021-03-31 | 2021-04-15 07:00 | ACTIVE | C14 |  | Photovoltaic | Storage |  |  | Solar | Battery |  |  | 286.13 | 286.13 |  | 275 |  | Full Capacity |  | Off-Peak Deliverability | Group D | BAJA CALIFORNIA | MX | SDGE | SDGE | Imperial Valley Substation 230 kV | 2027-12-31 08:00 | 2030-03-16 07:00 |  |  | Complete | Complete
CAISO | TOWER 1 ENERGY STORAGE | 2165 | 2021-04-06 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 105 |  |  | 100 |  | Full Capacity |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | Ocean Ranch Substation 69 kV | 2025-06-01 07:00 | 2029-02-05 08:00 |  |  | Complete | Complete
CAISO | UMBRIEL | 2166 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage | Photovoltaic |  |  | Battery | Solar |  |  | 1182.38 | 1182.38 |  | 1150 |  | Full Capacity |  | Off-Peak Deliverability | Group A | IMPERIAL | CA | SDGE | SDGE | North Gila - Imperial Valley 500 kV Line | 2026-12-31 08:00 | 2035-06-05 07:00 |  |  | Complete | Complete
CAISO | HAMMERHEAD STORAGE | 2167 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 71.3 |  |  | 70 |  | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Scripps Substation 69 kV | 2024-12-15 08:00 | 2030-05-05 07:00 |  |  | Complete | Complete
CAISO | DESERT JEWEL STORAGE | 2173 | 2021-04-08 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 206.31 |  |  | 200 |  | Full Capacity |  |  | Group A | SAN DIEGO | CA | SDGE | SDGE | Boulevard East Substation 138 kV | 2025-10-30 07:00 | 2029-02-05 08:00 |  |  | Complete | Complete
CAISO | YUHA DESERT BATTERY STORAGE | 2176 | 2021-04-02 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 633.1 |  |  | 600 |  | Full Capacity |  |  | Group D | IMPERIAL | CA | SDGE | SDGE | Imperial Valley Substation 230 kV | 2024-12-31 08:00 | 2031-11-05 08:00 |  |  | Complete | Complete
CAISO | BOULDER BRUSH HYBRID | 2177 | 2021-04-13 | 2021-04-15 07:00 | ACTIVE | C14 |  | Wind Turbine | Storage |  |  | Wind Turbine | Battery |  |  | 105.8 | 313.9193 |  | 400 |  | Full Capacity |  | Off-Peak Deliverability | Group D | SAN DIEGO | CA | SDGE | SDGE | Suncrest - Ocotillo 500 kV Line | 2025-06-01 07:00 | 2031-02-05 08:00 |  |  | Complete | Complete
CAISO | BELL BLUFF STORAGE | 2178 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 312.96 |  |  | 300 |  | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Suncrest Substation 230 kV | 2025-11-30 08:00 | 2035-03-05 08:00 |  |  | Complete | Complete
CAISO | CARGO STORAGE | 2180 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 312.96 |  |  | 300 |  | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Otay Mesa Switchyard 230 kV | 2025-03-31 07:00 | 2036-05-05 07:00 |  |  | Complete | Complete
CAISO | TAYLOR STORAGE | 2182 | 2021-04-09 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 101.9 |  |  | 100 |  | Full Capacity |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | Chicarita Substation 138 kV | 2025-11-01 07:00 | 2029-02-05 08:00 |  |  | Complete | Complete
CAISO | AMBERJACK ENERGY STORAGE | 2184 | 2021-04-14 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 100.6499 |  |  | 100 |  | Full Capacity |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | Loveland - Alpine 69 kV Line | 2024-11-30 08:00 | 2034-02-05 08:00 |  |  | Complete | Complete
CAISO | GATEWAY ENERGY STORAGE 2 | 2185 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 256.29 |  |  | 250 |  | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Otay Mesa Switchyard 230 kV | 2024-06-01 07:00 | 2035-02-05 08:00 |  |  | Complete | Complete
CAISO | SANDBAR ENERGY STORAGE | 2186 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 256 |  |  | 250 |  | Full Capacity |  |  | Group B | SAN DIEGO | CA | SDGE | SDGE | San Luis Rey Substation 230 kV | 2025-06-01 07:00 | 2030-02-05 08:00 |  |  | Complete | Complete
CAISO | GERANIUM ENERGY STORAGE | 2188 | 2021-04-15 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 51.4 |  |  | 50 |  | Full Capacity |  |  | Group D | SAN DIEGO | CA | SDGE | SDGE | Miguel Substation 69 kV | 2023-12-31 08:00 | 2029-02-05 08:00 |  |  | Complete | Complete
CAISO | PAJARO VALLEY STORAGE | 2192 | 2021-04-13 | 2021-04-15 07:00 | ACTIVE | C14 |  | Storage |  |  |  | Battery |  |  |  | 102.04 |  |  | 100 |  | Full Capacity |  |  |  | SAN DIEGO | CA | SDGE | SDGE | Salt Creek Substation 69 kV | 2024-09-01 07:00 | 2030-03-05 08:00 |  |  | Complete | Complete
CAISO | TOWNSHIP EXPANSION | 2195 | 2022-07-07 | 2022-10-13 07:00 | ACTIVE | ISP |  | Gas Turbine | Storage |  |  | Battery |  |  |  | 11.3 | 11.3 |  | 11 |  | Full Capacity |  | Off-Peak Deliverability |  | SUTTER | CA | PGAE | Northern | Greenleaf #1 115 kV Tap | 2024-06-01 07:00 | 2024-06-01 07:00