## Queue
Interconnection Requests for New England Control Area | [5 empty] | As of: 1/23/2025 12:00:00 AM |  |  | ISO-NE Public
Generation, Elective Transmission Upgrade and Transmission Service Requests
Jurisdiction: | All | Status: | All
Position | Updated | Type | Requested | Alternative Name | Unit | Fuel Type | Net MW | Summer MW | Winter MW | County | State | Op Date | Sync Date | W/ D Date | Interconnection Location | Serv | SIS Complete | I39 | TO Report | Dev | Zone | FS | SIS | OS | FAC | IA | Project Status
1601 | 2025-01-17 13:31 | G | 2025-01-14 | BESS | OT | BAT | 4.99 | 4.99 | 4.99 | Essex | MA | 2027-02-03 | 2027-02-03 |  | NGRID KING ST T3 | NA | FALSE | FALSE |  |  | BOST
1600 | 2025-01-10 16:58 | G | 2024-12-12 | Chazy Lake BESS (NYISO-C24-308) | OT | BAT | 50 | 50 | 50 | Clinton | NY | 2028-08-01 | 2028-08-01 |  | NYISO Patnode 230 kV | CNR | FALSE | FALSE |  |  | N/A
1599 | 2025-01-10 16:55 | G | 2024-12-12 | Dover NY BESS (NYISO-C24-316) | OT | BAT | 1000 | 1000 | 1000 | Dutchess | NY | 2028-05-01 | 2028-05-01 |  | NYISO Pleasant Valley-Cricket Valley 345 kV | CNR | FALSE | FALSE |  |  | N/A
1598 | 2025-01-10 16:51 | G | 2024-12-12 | Zenobe Rotterdam LLC (NYISO-C24-191) | OT | BAT | 100 | 100 | 100 | Schenectady | NY | 2028-06-01 | 2028-06-01 |  | NYISO Rotterdam 115 kV | CNR | FALSE | FALSE |  |  | N/A
1597 | 2025-01-10 16:41 | G | 2024-12-12 | New Scotland BESS (NYISO-C24-045) | OT | BAT | 1350 | 1350 | 1350 | Albany | NY | 2027-09-01 | 2027-09-01 |  | NYISO New Scotland 345 kV | CNR | FALSE | FALSE |  |  | N/A
1596 | 2025-01-10 16:36 | G | 2024-12-12 | NY Chateaugay 0 Willis Rd Storage (NYISO-C24-304-004) | OT | BAT | 150 | 150 | 150 | Franklin | NY | 2028-02-01 | 2028-02-01 |  | NYISO Willis 230 kV Substation | CNR | FALSE | FALSE |  |  | N/A
1595 | 2025-01-10 14:23 | G | 2024-12-12 | Willard Storage (NYISO-C24-148) | OT | BAT | 300 | 300 | 300 | Rensselaer | NY | 2028-10-01 | 2028-10-01 |  | NYISO Eastover 115 kV | CNR | FALSE | FALSE |  |  | N/A
1594 | 2024-11-15 16:01 | G | 2024-11-15 | Woonsocket Substation – Tifft ST BESS | OT | BAT | 4.5 | 4.5 | 4.5 | Providence | RI | 2026-12-31 | 2026-12-31 |  | RIE feeder 26W7, Woonsocket Substation | NA | FALSE | FALSE |  |  | RI
1593 | 2024-11-15 16:02 | G | 2024-11-15 | Point St Substation – Aldrich St BESS | OT | BAT | 3 | 3 | 3 | Providence | RI | 2026-12-31 | 2026-12-31 |  | RIE feeder 76F6, Point St Substation | NA | FALSE | FALSE |  |  | RI
1592 | 2024-08-21 13:40 | G | 2024-08-21 | SHELD BESS | OT | BAT | 3 | 3 | 3 | Hampden | MA | 2025-09-01 | 2025-09-01 |  | South Hadley Electric Light Department 13.8KV | NA | FALSE | FALSE |  | PD | WMA
1591 | 2024-08-19 17:49 | G | 2024-08-19 | Chase Hill Substation - Western RI DER Study #3 | PV | SUN | 2.375 | 2.375 | 2.375 | Washington | RI | 2026-12-31 | 2026-12-01 |  | RIE Feeder 155F2, Chase Hill Substation | NA | FALSE | FALSE |  | PD | RI
1590 | 2024-08-19 17:46 | G | 2024-08-19 | Tower Hill Substation - Western RI DER Study #3 | PV | SUN | 3.06 | 3.06 | 3.06 | Washington | RI | 2026-12-31 | 2026-12-01 |  | RIE Feeder 88F7, Tower Hill Substation | NA | FALSE | FALSE |  | PD | RI
1589 | 2024-08-19 17:44 | G | 2024-08-19 | Kent County Substation - Western RI DER Study #3 | PV | SUN | 21.748 | 21.748 | 21.748 | Kent | RI | 2026-12-31 | 2026-12-01 |  | RIE feeder 3309 and 3311, Kent County Substation | NA | FALSE | FALSE |  | PD | RI
1588 | 2024-08-19 17:39 | G | 2024-08-19 | Wood River Substation - Western RI DER Study #3 | PV | SUN | 49 | 49 | 49 | Washington | RI | 2026-12-31 | 2026-12-01 |  | RIE feeder 85T2 and 85T3, Wood River Substation | NA | FALSE | FALSE |  | PD | RI
1587 | 2024-08-20 09:52 | G | 2024-08-15 | Battery Storage | OT | BAT | 3 | 3 | 3 | Worcester | MA | 2025-10-15 | 2025-09-15 |  | West Boylston Denton Lovell Substation T2 Transformer fed from the P142W. Distribution Feeder -F23 Hartwell Feeder | NA | FALSE | FALSE |  | PD | CMA
1586 | 2024-08-14 13:10 | G | 2024-08-14 | Battery Storage | OT | BAT | 16 | 16 | 16 | Chittenden | VT | 2026-04-01 | 2026-03-01 |  | Global Foundries 13.8 kV bus | NA | FALSE | FALSE |  | PD | VT
1585 | 2024-08-13 15:56 | G | 2024-08-13 | HGE Group Study | OT | BAT | 12.98 | 12.98 | 12.98 | Hampden | MA | 2026-01-01 | 2025-03-01 |  | Holyoke 52W via 52W6 Circuit or New Circuit | NA | FALSE | FALSE |  | PD | WMA
1584 | 2024-08-13 15:52 | G | 2024-08-13 | HGE Group Study | GT | NG | 4 | 4 | 4 | Hampden | MA | 2026-01-01 | 2026-01-01 |  | Holyoke 44P via New 34.5 kV Circuit | NA | FALSE | FALSE |  | PD | WMA
1583 | 2024-08-13 15:53 | G | 2024-08-13 | HGE Group Study | OT | BAT | 4.95 | 4.95 | 4.95 | Hampden | MA | 2025-02-15 | 2025-02-15 |  | Holyoke 17L via 17L16 Circuit | NA | FALSE | FALSE |  | PD | WMA
1582 | 2024-10-24 14:30 | G | 2024-07-29 | Paxton BESS | OT | BAT | 3 | 3 | 3 | Worcester | MA | 2024-12-02 | 2024-11-25 |  | Paxton Municipal Light Department 13.8KV | NA | TRUE | TRUE |  | PD | SEMA
1581 | 2024-07-31 17:03 | G | 2024-07-29 | TMLP Landfill Solar | PV | SUN | 2.99 | 2.99 | 2.99 | Bristol | MA | 2025-01-25 | 2025-01-24 |  | TMLP Dist Feeder 1841.32 Station 18 13.8kV/115kV | NA | FALSE | FALSE |  | PD | SEMA
1580 | 2024-07-31 16:51 | G | 2024-07-29 | RMLD DER Group Study | OT | BAT | 9.98 | 9.98 | 9.98 | Middlesex | MA | 2025-06-16 | 2025-06-15 |  | RMLD Station 3/NG S145 & T146 Lines | NA | FALSE | FALSE |  | PD | CMA
1579 | 2024-07-31 16:46 | G | 2024-07-29 | RMLD DER Group Study | OT | BAT | 4.996 | 4.996 | 4.996 | Middlesex | MA | 2025-02-16 | 2025-02-15 |  | RMLD Station 4/EE 211-503 & 211-504 Lines | NA | FALSE | FALSE |  | PD | CMA
1578 | 2024-08-12 18:17 | G | 2024-06-26 | Solar | PV | SUN | 20 | 20 | 20 | Oxford | ME | 2028-06-06 | 2028-05-20 | 2024-08-12 | CMP 115kV Woodstock Substation | CNR | FALSE | FALSE |  | PD | ME | [5 empty] | Under Study
1577 | 2024-08-12 18:15 | G | 2024-06-26 | Solar | PV | SUN | 20 | 20 | 20 | Knox | ME | 2028-06-06 | 2028-05-20 | 2024-08-12 | CMP 115KV SECTION 80 | CNR | FALSE | FALSE |  | PD | ME
1576 | 2024-08-12 18:14 | G | 2024-06-26 | Solar | PV | SUN | 20 | 20 | 20 | Cheshire | NH | 2028-06-06 | 2028-05-20 | 2024-08-12 | Eversource 115kV Section L-163, approximately 2.6 miles north of North Keene Substation. | CNR | FALSE | FALSE |  | PD | NH
1575 | 2024-08-12 18:12 | G | 2024-06-26 | Solar | PV | SUN | 20 | 20 | 20 | Oxford | ME | 2028-06-06 | 2028-05-20 | 2024-08-12 | CMP 115kV Woodstock Substation | CNR | FALSE | FALSE |  | PD | ME
1574 | 2024-08-12 18:11 | G | 2024-06-26 | Battery Storage | OT | BAT | 20 | 20 | 20 | Merrimack | NH | 2028-06-06 | 2028-05-20 | 2024-08-12 | EVERSOURCE 115KV SECTION C196, APPROXIMATELY 1.5 MILES SOUTH OF THE MERRIMACK SUBSTATION. | CNR | FALSE | FALSE |  | PD | NH
1573 | 2024-08-12 18:09 | G | 2024-06-26 | Solar | PV | SUN | 20 | 20 | 20 | York | ME | 2028-06-06 | 2028-05-20 | 2024-08-12 | CMP 34.5kV Line 182, located approximately 2.5 miles from the West Buxton Substation. | CNR | FALSE | FALSE |  | PD | ME
1572 | 2024-08-06 17:18 | G | 2024-06-24 | Solar | PV | SUN | 8.084 | 4.042 | 4.042 | Windham | VT | 2026-06-30 | 2026-06-23 | 2024-08-06 | Vernon #13 69kV | CNR | FALSE | FALSE |  | PD | VT
1571 | 2024-11-05 10:47 | G | 2024-06-13 | Battery Storage | OT | BAT | 19.73 | 19.73 | 19.73 | Worcester | MA | 2027-06-30 | 2027-02-28 |  | 42.066328, -71.864144 National Grid 69 kV Substation the East Webster 412 substation. | CNR | FALSE | FALSE |  | PD | CMA |  | Not Started |  |  |  | Under Study
1570 | 2024-09-27 12:52 | G | 2024-06-13 | Battery Storage | OT | BAT | 19.73 | 19.73 | 19.73 | Worcester | MA | 2027-06-30 | 2027-02-28 | 2024-09-27 | National Grid 69kV line tap on line A-1S Coordinates: 42.493823759032914, -71.77425691308422. Based off the ISO-NE system diagram, it is assumed that the eastern circuit is A-1S and is the preferred connection. however seeking this to be confirmed with ISO-NE" | CNR | FALSE | FALSE |  | PD | CMA
1569 | 2025-01-06 11:32 | ETU | 2024-06-13 | Non-controllable objective ETU to enable 2400 MW injection | NA | N/A | 2400 |  |  | New London | CT | 2031-06-30 | 2030-12-30 |  | N/A | N/A | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
1568 | 2024-12-01 10:15 | G | 2024-06-12 | Battery Storage | OT | BAT | 312.84 | 152.7552 | 152.7552 | Washington | RI | 2027-01-31 | 2026-11-30 |  | The Primary Point of Interconnection will be a direct interconnection to the 115-kV bus at Davisville Substation Expansion owned by RI_NGRID. | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
1567 | 2024-11-05 16:49 | G | 2024-06-11 | Battery Storage | OT | BAT | 514.8 | 509.184 | 509.184 | Middlesex | MA | 2027-01-31 | 2026-11-30 |  | The Primary Point of Interconnection will be a direct interconnection will be located on the IC’s property (Lat, long: 42°41'23.38"N, 71°26'20.43"W) by tapping the 345-kV Line 326-2 (Sandy Pond-Lawrence Rd), owned by RI_NGRID, at approx. 8.4 miles from the 345-kV Lawerence Rd Substation. | CNR | FALSE | FALSE |  | PD | SEMA |  | Not Started |  |  |  | Under Study
1566 | 2024-06-11 17:36 | G | 2024-06-11 | Wind | WT | WND | 197.4 | 197.4 | 197.4 | Aroostook | ME | 2028-10-01 | 2028-05-01 |  | Orrington – Albion Road 345kV | CNR | FALSE | FALSE |  | PD | BHE
1565 | 2024-09-11 17:06 | G | 2024-06-10 | Battery Storage | OT | BAT | 81 | 81 | 81 | Bristol | MA | 2027-01-31 | 2026-11-30 | 2024-09-11 | Interconnect at the 115kV Sykes Rd Substation owned by MA_NGRID. | CNR | FALSE | FALSE |  | PD | SEMA
1564 | 2024-11-05 10:57 | G | 2024-06-06 | Battery Storage | OT | BAT | 100.955 | 100.955 | 100.955 | Windham | VT | 2027-09-30 | 2027-03-30 |  | Vernon 115 kV (Line K-40) Coordinates: 42.78270705350802, -72.51706642321578 | CNR | FALSE | FALSE |  | PD | VT |  | Not Started |  |  |  | Under Study
1563 | 2024-11-05 10:51 | G | 2024-06-06 | Solar | PV | SUN | 165 | 165 | 165 | Somerset | ME | 2028-06-06 | 2028-06-06 |  | CMP 115kV Line 83 | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
1562 | 2024-08-28 16:38 | G | 2024-06-07 | Battery Storage | OT | BAT | 45.29 | 45.29 | 45.29 | Litchfield | CT | 2027-06-01 | 2026-12-01 | 2024-08-28 | Eversource 115 kV Line from Frost Bridge #8R to Carmel Hill #11S | CNR | FALSE | FALSE |  | PD | CT
1561 | 2024-11-22 12:39 | G | 2024-06-06 | Battery Storage | OT | BAT | 141.6 | 141.6 | 141.6 | Litchfield | CT | 2027-04-01 | 2027-03-01 |  | 115 kV line between Rocky River and Bulls Bridge substations | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1560 | 2024-11-05 15:33 | G | 2024-06-06 | Battery Storage | OT | BAT | 133.796 | 133.796 | 133.796 | Bristol | MA | 2027-04-01 | 2027-03-01 |  | Non-PTF 115KV lines ET and W owned by TMLP between Cleary Flood Substation and Substation #16 (W Water St), approximately 1.26 miles from Cleary Flood. Project will interconnect half of the new MW capability to each line. | CNR | FALSE | FALSE |  | PD | SEMA |  | Not Started |  |  |  | Under Study
1559 | 2024-11-05 14:51 | G | 2024-06-06 | Battery Storage | OT | BAT | 93.2 | 93.2 | 93.2 | New London | CT | 2027-05-01 | 2027-04-01 |  | 115 kV line 1070 between Ft Hill Farms and Stockhouse Substations, interconnected by a new three-breaker ring bus approximately 2.5 miles from Ft Hill Farms substation and 5.2 miles from Stockhouse Substations. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1558 | 2024-11-05 14:50 | G | 2024-06-06 | Battery Storage | OT | BAT | 141.5 | 141.5 | 141.5 | Bristol | MA | 2028-01-01 | 2027-12-01 |  | 115 kV line W4S between Grand Army Substation and Pottersville Substation. Approximately 0.43 miles from Grand Army - 115KV Substation and approximately 2.33 miles from Pottersville / Somerset substations | CNR | FALSE | FALSE |  | PD | SEMA |  | Not Started |  |  |  | Under Study
1557 | 2024-11-05 14:50 | G | 2024-06-06 | Battery Storage | OT | BAT | 240.1577 | 240.1577 | 240.1577 | Essex | MA | 2028-01-01 | 2027-12-01 |  | 115 kV Wakefield Junction Substation | CNR | FALSE | FALSE |  | PD | BOST |  | Not Started |  |  |  | Under Study
1556 | 2024-11-06 16:02 | G | 2024-06-06 | Battery Storage | OT | BAT | 204.818 | 204.818 | 204.818 | Worcester | MA | 2027-10-11 | 2027-09-27 |  | Eversource 345 kV Line 3361, approximately 3.2 miles from Sherman Road and 7.6 miles from Blackstone. | CNR | FALSE | FALSE |  | PD | CMA |  | Not Started |  |  |  | Under Study
1555 | 2024-11-05 14:48 | G | 2024-06-06 | Battery Storage | OT | BAT | 214.1568 | 214.1568 | 214.1568 | Essex | MA | 2028-01-01 | 2027-12-01 |  | 115KV Line Q-169 between Resco-Saugus Tap and Melrose #2 Tap. Approximately 2.4 miles from Melrose #2 Tap and approximately 2.35 miles from Resco-Saugus Tap | CNR | FALSE | FALSE |  | PD | BOST |  | Not Started |  |  |  | Under Study
1554 | 2024-11-07 12:08 | G | 2024-06-07 | Battery Storage | OT | BAT | 414.632 | 414.632 | 414.632 | Providence | RI | 2027-10-11 | 2027-09-27 | 2024-11-07 | NEP transmission line: 345 kV line 359, approximately 10.55 miles from West Farnum and 10.81 miles from Kent County substations. | CNR | FALSE | FALSE |  | PD | RI |  | Not Started |  |  |  | Under Study
1553 | 2024-12-01 10:13 | G | 2024-06-04 | Battery Storage | OT | BAT | 135.6 | 126.401 | 126.401 | Middlesex | MA | 2028-05-01 | 2028-04-15 |  | Primary Point of Interconnection - National Grid Tewksbury 115kV substation, Open position opposite the J-162 line | CNR | FALSE | FALSE |  | PD | BOST |  | Not Started |  |  |  | Under Study
1552 | 2024-11-22 12:47 | G | 2024-06-04 | Battery Storage | OT | BAT | 133.2 | 133.2 | 133.2 | Hartford | CT | 2028-04-01 | 2028-03-15 | 2024-11-22 | Eversource Energy Corporation owned 115 kV Line 1756 | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1551 | 2024-11-07 14:50 | G | 2024-05-31 | Battery Storage | OT | BAT | 190 | 181.78 | 181.78 | Worcester | MA | 2027-01-31 | 2026-11-30 |  | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 42°21'44.53"N, 72° 2'22.57"W) by tapping the 115-kV Line A127-4 (Barre-Paxton) at approx. 6km from Barre Substation owned by MA_NGRID. | CNR | FALSE | FALSE |  | PD | CMA |  | Not Started |  |  |  | Under Study
1550 | 2024-08-02 09:25 | G | 2024-05-31 | Battery Storage | OT | BAT | 76 | 76 | 76 | Plymouth | MA | 2027-01-31 | 2026-11-30 | 2024-08-02 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°58'7.22"N, 71° 1'18.59"W) by tapping the 115-kV Line U6-4 (Bridgewater-Raynham) at approx. 7,87 Km from Bridgewater Substation. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Bridgewater Substation owned by MA_NGRID. | CNR | FALSE | FALSE |  | PD | SEMA
1549 | 2024-10-18 17:11 | G | 2024-06-03 | Battery Storage | OT | BAT | 108 | 108 | 108 | Providence | RI | 2027-01-31 | 2026-11-30 | 2024-10-18 | The Primary Point of Interconnection will be a direct interconnection to the 115-kV bus at Highland Park Substation owned by RI_NGRID. The Alternative Point of Interconnection will be located on the IC’s property (Lat, long: 41°59'46.60"N, 71°28'16.01"W) by tapping the 115-kV Line J16 (Riverside-Highland Park) at approx. 0.27 km from Highland Park Substation. | CNR | FALSE | FALSE |  | PD | RI |  | Not Started |  |  |  | Under Study
1548 | 2024-10-17 12:46 | G | 2024-05-31 | Battery Storage | OT | BAT | 165.76 | 165.76 | 165.76 | Providence | RI | 2028-03-01 | 2028-01-01 | 2024-10-17 | Primary POI: 42.001693, -71.710650, Eversource Line 347, Sherman Road to Killingly 345kV Alternate POI: 42.001693, -71.710650, Eversource West Farnum to Lake Road 345kV | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
1547 | 2024-11-05 10:51 | G | 2024-05-31 | Solar | PV | SUN | 19.6 |  |  | Penobscot | ME | 2027-12-01 | 2027-11-01 |  | Clifton Switchyard in Clifton, Maine. | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
1546 | 2024-11-05 10:51 | G | 2024-05-30 | Battery Storage | OT | BAT | 202.07 | 202.07 | 202.07 | Berkshire | MA | 2030-06-06 | 2029-12-05 |  | MA_WMECO Partridge 115kV substation. | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1545 | 2024-11-05 10:51 | G | 2024-05-30 | Battery Storage | OT | BAT | 100.7521 | 100.7521 | 100.7521 | Franklin | MA | 2028-08-01 | 2028-04-01 |  | MA_WMECO 115 kV Erving Substation Bus No. 116107 | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1544 | 2024-07-03 15:02 | G | 2024-05-29 | Battery Storage | OT | BAT | 0 | 105 | 105 | Franklin | MA | 2029-12-30 | 2029-07-09 | 2024-07-03 | 115 kV B128 line; 18.88 miles from Barre B128 and 5.3 miles from French King | CNR | FALSE | FALSE |  | NA | WMA
1543 | 2024-11-05 10:50 | G | 2024-05-28 | Battery Storage | OT | BAT | 588.3 | 588.3 | 588.3 | Barnstable | MA | 2028-12-01 | 2028-09-15 |  | The project will tap the Bourne-Jordan Pond (342) 345kV line with a new three breaker ring bus to connect the project. | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
1542 | 2024-11-05 10:50 | G | 2024-05-28 | Battery Storage | OT | BAT | 202.07 | 202.07 | 202.07 | Hampden | MA | 2030-01-24 | 2029-12-23 |  | MA_WMECO Blandford 115kV substation | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1541 | 2024-12-01 10:11 | G | 2024-05-28 | Battery Storage | OT | BAT | 101 | 101 | 101 | Middlesex | MA | 2028-05-31 | 2028-05-01 |  | 42.385528, -71.490823 on Hudson-Sudbury 115kV line | CNR | FALSE | FALSE |  | PD | BOST |  | Not Started |  |  |  | Under Study
1540 | 2024-05-15 14:44 | G | 2024-05-15 | EE CT DER Group Study | OT | BAT | 19.999 | 19.999 | 19.999 | Hartford | CT | 2025-12-31 | 2025-12-31 |  | EE Enfield 12C | NA | FALSE | FALSE |  | PD | CT
1539 | 2024-05-15 14:42 | G | 2024-05-15 | EE CT DER Group Study | OT | BAT | 20 | 20 | 20 | Middlesex | CT | 2027-04-05 | 2027-04-05 |  | EE 30K DOOLEY | NA | FALSE | FALSE |  | PD | CT
1538 | 2024-05-15 14:39 | G | 2024-05-15 | EE CT DER Group Study | OT | BAT | 4.99 | 4.99 | 4.99 | New London | CT | 2025-12-31 | 2025-12-31 |  | EE Flanders 11Y | NA | FALSE | FALSE |  | PD | CT
1537 | 2024-05-15 14:36 | G | 2024-05-15 | EE CT DER Group Study | OT | BAT | 4.99 | 4.99 | 4.99 | New London | CT | 2025-12-31 | 2025-12-21 |  | EE 1Q UNCASVILLE | NA | FALSE | FALSE |  | PD | CT
1536 | 2024-05-29 11:46 | G | 2024-05-15 | EE CT DER Group Study | PV | SUN | 3.74 | 3.74 | 3.74 | Litchfield | CT | 2024-07-01 | 2024-07-01 | 2024-05-29 | EE WINSTED 33B/CAMPVILLE | NA | FALSE | FALSE |  | PD | CT
1535 | 2024-05-15 13:50 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 2.805 | 2.805 | 2.805 | Barnstable | MA | 2026-12-31 | 2026-12-31 |  | EE STA_946 Mashpee | NA | FALSE | FALSE |  | PD | SEMA
1534 | 2024-05-10 16:10 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 4.98 | 4.98 | 4.98 | Plymouth | MA | 2026-12-31 | 2026-12-31 |  | EE STA_646 Crystal Spring | NA | FALSE | FALSE |  | PD | SEMA
1533 | 2024-05-10 16:07 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 16.94 | 16.94 | 16.94 | Plymouth | MA | 2026-12-31 | 2026-12-31 |  | EE STA_713 Tremont | NA | FALSE | FALSE |  | PD | SEMA
1532 | 2024-05-10 16:03 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 4.999 | 4.999 | 4.999 | Plymouth | MA | 2026-12-31 | 2026-12-31 |  | EE STA_727 Brook Street | NA | FALSE | FALSE |  | PD | SEMA
1531 | 2024-05-15 13:49 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 4.98 | 4.98 | 4.98 | Plymouth | MA | 2024-12-31 | 2024-12-31 |  | EE STA_745 Rochester | NA | FALSE | FALSE |  | PD | SEMA
1530 | 2024-05-10 16:00 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 4.999 | 4.999 | 4.999 | Bristol | MA | 2026-12-31 | 2026-12-31 |  | EE STA_624 Wing Lane | NA | FALSE | FALSE |  | PD | SEMA
1529 | 2024-05-10 15:53 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | BAT | 4.99 | 4.99 | 4.99 | Plymouth | MA | 2024-12-31 | 2024-12-31 |  | EE STA_738 Duxbury | NA | FALSE | FALSE |  | PD | SEMA
1528 | 2024-05-10 15:53 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | BAT | 4.9992 | 4.9992 | 4.9992 | Plymouth | MA | 2026-12-31 | 2026-12-31 |  | EE TA_739 Marshfield | NA | FALSE | FALSE |  | PD | SEMA
1527 | 2024-05-10 15:50 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 2.5 | 2.5 | 2.5 | Barnstable | MA | 2026-12-31 |  |  | EE STA_933 Falmouth | NA | FALSE | FALSE |  | PD | SEMA
1526 | 2024-05-10 15:53 | G | 2024-05-08 | EE 2024 SEMA/Cape ASO Group Study | OT | SUN BAT | 4.98 | 4.98 | 4.98 | Bristol | MA | 2026-12-31 | 2026-12-31 |  | EE STA_636 Industrial Park | NA | FALSE | FALSE |  | PD | SEMA
1525 | 2024-06-25 16:30 | G | 2024-05-06 | Battery Storage | OT | BAT | 134.7 | 134.7 | 134.7 | New Haven | CT | 2027-01-31 | 2026-11-30 | 2024-06-25 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°28'9.40"N, 73° 7'52.44"W) by tapping the 115-kV Line 1619 (Towantic-Stevenson) at approx. 1.8 Km from Towantic Substation. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Oxford Substation owned by CT_CL&P. | CNR | FALSE | FALSE |  | PD | CT
1524 | 2024-11-05 10:50 | G | 2024-05-06 | Battery Storage | OT | BAT | 237.6 | 237.6 | 237.6 | Hartford | CT | 2027-01-31 | 2026-11-30 |  | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°49'19.50"N, 72°43'23.49"W) by tapping the 115-kV Line 1751 (Bloomfield_J-NW.Hartford) at approx. 0.98 km from Bloomfield Substation owned by CT_CL&P. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Bloomfield Substation owned by CT_CL&P. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1523 | 2024-10-22 10:59 | G | 2024-05-06 | Battery Storage | OT | BAT | 253.816 | 253.816 | 253.816 | Norfolk | MA | 2029-06-01 | 2029-04-01 |  | National Grid’s 115kV South Wrentham substation | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
1522 | 2024-08-16 11:33 | G | 2024-04-25 | Battery Storage | OT | BAT | 150 | 125.5 | 125.5 | Bristol | MA | 2028-05-01 | 2028-04-15 | 2024-08-16 | Primary POI will be National Grid Line C-181 (Brayton Point to Reynolds Ave, 115 kV). Primary POI is 10.6 miles from Brayton Point and 1.9 miles from Reynolds Ave. POI Coords: 41.856375, -71.193471 | CNR | FALSE | FALSE |  | PD | RI
1521 | 2024-05-06 14:56 | G | 2024-04-22 | Solar CNR only | PV | SUN | 0 | 50 | 50 | Addison | VT | 2026-05-31 | 2026-05-01 |  | Vergennes 115 kV Substation | CNR | FALSE | FALSE |  |  | VT
1520 | 2024-08-23 10:13 | G | 2024-04-16 | Battery Storage | OT | BAT | 125 | 125 | 125 | New Haven | CT | 2028-05-01 | 2028-03-01 |  | Primary POI: Eversource Owned 115kV Line # 1142 Alternate POI 1: 115kV Express Feeder to Oxford 26N Substation Alternate POI 2: Eversource Owned 115kV Line # 1403 | CNR | FALSE | FALSE |  | PD | CT |  | In Progress |  |  |  | Under Study
1519 | 2024-06-21 10:20 | G | 2024-04-12 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | RI | 2031-04-10 | 2030-07-01 |  | Kent County 345kV | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
1518 | 2024-08-22 16:00 | G | 2024-04-09 | Battery Storage | OT | BAT | 139.5 | 139.5 | 139.5 | Berkshire | MA | 2028-08-30 | 2028-05-31 |  | Eversource, Partridge 115kV Substation | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1517 | 2024-06-20 10:23 | G | 2024-04-09 | Battery Storage | OT | BAT | 365.8 | 365.8 | 365.8 | Franklin | MA | 2028-08-30 | 2028-05-31 |  | National Grid 69kV Line E-5D Deerfeild-Shutesbury | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1516 | 2024-06-06 09:24 | G | 2024-04-09 | Battery Storage | OT | BAT | 114.7 | 114.7 | 114.7 | Windsor | VT | 2028-08-30 | 2028-05-31 |  | Vermont Electric Power Company (VELCO) Ascutney 115 kV Substation | CNR | FALSE | FALSE |  | PD | VT | Not Started |  |  |  |  | Under Study
1515 | 2024-08-23 10:14 | G | 2024-04-09 | Battery Storage | OT | BAT | 508.4 | 508.4 | 508.4 | Berkshire | MA | 2028-08-30 | 2028-05-31 |  | Alps-Berkshire 345kV line | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1514 | 2024-08-23 10:13 | G | 2024-04-08 | Battery Storage | OT | BAT | 408.1 | 408.1 | 408.1 | Worcester | MA | 2028-08-30 | 2028-05-31 |  | National Grid Barre Tap-Wendell Depot Tap 115kV | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
1513 | 2024-08-23 10:14 | G | 2024-04-08 | Battery Storage | OT | BAT | 408.1 | 408.1 | 408.1 | Worcester | MA | 2028-08-30 | 2028-05-31 |  | Bear Swamp- Pratts Junction 230kV | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
1512 | 2024-05-29 11:05 | G | 2024-04-08 | Battery Storage + Solar | OT | SUN BAT | 100.4637 | 100.4637 | 100.4637 | Franklin | MA | 2027-12-31 | 2027-08-31 | 2024-05-29 | New England Power Co, 115 kV, 2.25 miles from E131 TAP 113010 and 3.29 miles from HARRIMAN 113146) (115 kV) | CNR | FALSE | FALSE |  | PD | WMA
1511 | 2024-05-15 08:54 | G | 2024-04-08 | Battery Storage | OT | BAT | 250.8939 | 250.8939 | 250.8939 | Hampden | MA | 2027-12-31 | 2027-08-01 | 2024-05-14 | Western Massachusetts Electric Company (Eversource Energy) 345kV Ludlow | CNR | FALSE | FALSE |  | PD | WMA
1510 | 2024-08-23 09:40 | G | 2024-04-03 | Battery Storage | OT | BAT | 152.7552 | 152.7552 | 152.7552 | Wocester | MA | 2027-12-31 | 2027-12-31 |  | Carpenter Hill substation, 115 kV bus, National Grid at open bay | CNR | FALSE | FALSE |  | PD | CMA | Not Started |  |  |  |  | Under Study
1509 | 2024-08-23 09:41 | G | 2024-04-03 | Battery Storage | OT | BAT | 152.7552 | 152.7552 | 152.7552 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | 3-breaker ring bus tapping the W175 line. ESA sub located approximately 0.23 miles from West Charlton 115 kV substation at current coordinates 42° 8'10.02"N 72° 1'30.37"W | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
1508 | 2024-09-26 13:16 | G | 2024-04-01 | Battery Storage | OT | BAT | 167.1 | 167.1 | 167.1 | Hartford | CT | 2028-04-01 | 2028-03-20 | 2024-09-26 | Primary POI: 345kV Line, Agawam to North Bloomfield Line, POI: 42.031254, -72.698516 Alternative POI: 115kV Line, Tap156253 to North Bloomfield, POI: 42.031274, -72.698830 | CNR | FALSE | FALSE |  | PD | CT
1507 | 2024-07-29 11:14 | G | 2024-03-27 | Solar Increase | PV | SUN | 25 | 177.4113 | 177.4113 | Hartford | CT | 2028-12-15 | 2028-10-15 |  | To interconnect at the POI of Gravel Pit Solar as an increase to (QP1030 + QP 1247 + QP 1357), the POI is the new Gravel Pit Solar substation at the new three-breaker ring bus on the 115 kV Connecticut Light & Power Company 1200 line between Barbour Hill and Windsor Locks. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1506 | 2024-04-18 16:38 | G | 2024-03-22 | Battery Storage | OT | BAT | 152.656 | 152.656 | 152.656 | Middlesex | MA | 2028-06-01 | 2028-05-01 | 2024-04-18 | The proposed POI is tapping Eversource’s 115kV transmission line from Hudson to Sudbury. | NR | FALSE | FALSE |  | PD | BOST
1505 | 2024-08-23 09:43 | G | 2024-03-14 | Offshore Wind | WT | WND | 1275 | 1275 | 1275 | NA | CT | 2031-09-01 | 2031-03-01 |  | Eversource 345kV Montville Substation | CNR | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
1504 | 2024-03-20 16:55 | G | 2024-03-13 | Solar | PV | SUN | 10 | 10 | 10 | Belknap | NH | 2025-12-31 | 2025-12-01 | 2024-03-20 | EE Laconia substation | NA | FALSE | FALSE |  | PD | NH
1503 | 2024-03-20 16:55 | G | 2024-03-13 | EE Lost Nation Group DG Study | PV | SUN | 9.98 | 9.98 | 9.98 | Coos | NH | 2025-12-31 | 2025-12-01 | 2024-03-20 | EE Lost Nation substation | NA | FALSE | FALSE |  | PD | NH
1502 | 2024-06-06 09:40 | G | 2024-03-28 | Battery Storage | OT | BAT | 19.3 |  |  | Franklin | VT | 2026-07-01 | 2026-06-01 |  | Direct connection to VELCO 115kV Highgate substation (44.943833, -73.058515) | CNR | FALSE | FALSE |  | PD | VT |  | Not Started |  |  |  | Under Study
1501 | 2024-12-11 11:57 | G | 2024-02-29 | Battery Storage | OT | BAT | 167.1 | 167.1 | 167.1 | New London | CT | 2028-04-01 | 2028-03-20 | 2024-12-11 | Primary POI: 115kV line 1080 (41.5515028, -72.1253556) , Alternate POI: 115kV line 1000 (41.551478, -72.125294) | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1500 | 2024-04-25 15:42 | G | 2024-02-20 | Offshore Wind CNR only | WT | WND | 0 | 1249.5 | 1249.5 | NA | MA | 2033-11-04 | 2033-03-27 |  | National Grid Brayton Point 345kV Substation | CNR | FALSE | FALSE |  |  | RI
1499 | 2024-08-23 10:15 | G | 2024-02-13 | Battery Storage | OT | BAT | 115.6 | 115.6 | 115.6 | Hampden | MA | 2026-10-31 | 2026-09-30 |  | Palmer 503 Substation new 115 kV line | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
1498 | 2024-05-09 11:34 | G | 2024-02-08 | Battery Storage | OT | BAT | 109.52 | 109.52 | 110.87 | Fairfield | CT | 2027-12-31 | 2027-12-15 |  | Direct tap into the Pequonnock 115kV substation in Bridgeport, CT | CNR | FALSE | FALSE |  | PD | SWCT |  | Not Started |  |  |  | Under Study
1497 | 2024-05-14 14:31 | G | 2024-02-07 | Solar | PV | SUN | 68 | 68 | 68 | Penobscot | ME | 2028-07-15 | 2028-04-15 | 2024-05-14 | Tap on Enfield ME – Passadumkeag 115kV line | CNR | FALSE | FALSE |  | PD | BHE
1496 | 2024-05-01 10:31 | G | 2024-02-07 | Battery Storage addition(QP1192) | OT | SUN BAT | 101.1158 | 202.2316 | 202.2316 | Hartford | CT | 2027-12-15 | 2027-10-15 |  | To interconnect at the POI of Broadleaf Storage, via a shared facility. It is connected as a tap at existing 345 kV line between N. Bloomfield to Agawam Line. POI is approximately 3.6 mi north of N. Bloomfield and 11.5 mi south of Agawam. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1495 | 2024-04-09 15:32 | G | 2024-02-22 | Battery Storage | OT | BAT | 19.3 | 19.3 | 19.3 | Windsor | VT | 2026-07-01 | 2026-06-01 |  | Direct connection to VELCO 115kV Windsor substation (43.48988, -72.40858) | CNR | FALSE | FALSE |  | PD | VT |  | Not Started |  |  |  | Under Study
1494 | 2024-01-26 11:29 | G | 2024-01-26 | Walpole 146 110A - 2023 EE GB ASO | OT | SUN BAT | 4.99 | 4.99 | 4.99 | Norfolk | MA | 2026-12-31 | 2026-12-31 |  | Eversource Walpole 146 110A | NA | FALSE | FALSE |  | PD | SEMA
1493 | 2024-01-26 11:26 | G | 2024-01-26 | Medway 65 110B - 2023 EE GB ASO | OT | SUN BAT | 3.9 | 3.9 | 3.9 | Middlesex | MA | 2026-12-31 | 2026-12-31 |  | Eversource Medway 65 110B | NA | FALSE | FALSE |  | PD | SEMA
1492 | 2024-01-26 11:23 | G | 2024-01-26 | Medway 65 110A - 2023 EE GB ASO | OT | BAT | 4.948 | 4.948 | 4.948 | Middlesex | MA | 2026-12-31 | 2026-12-31 |  | Eversource Medway 65 110A | NA | FALSE | FALSE |  | PD | SEMA
1491 | 2024-01-26 11:20 | G | 2024-01-26 | Canton 470 110A - 2023 EE GB ASO | OT | BAT | 4.99 | 4.99 | 4.99 | Norfolk | MA | 2026-12-31 | 2026-12-31 |  | Eversource Canton 470 110A | NA | FALSE | FALSE |  | PD | SEMA
1490 | 2024-01-23 16:46 | G | 2024-01-17 | EE Mansfield Center DG Cluster | PV | SUN | 19.975 | 19.975 | 19.975 | Tolland | CT | 2024-12-31 | 2024-06-30 |  | EE Card St 11F | NA | FALSE | FALSE |  | PD | CT
1489 | 2024-01-23 16:43 | G | 2024-01-17 | EE Mansfield Center DG Cluster | OT | SUN BAT | 10.799 | 10.799 | 10.799 | Tolland | CT | 2025-07-27 | 2024-12-29 |  | EE Mansfield 12J | NA | FALSE | FALSE |  | PD | CT
1488 | 2024-09-25 16:47 | G | 2024-01-11 | Offshore Wind | WT | WND | 1275 | 1275 | 1275 | NA | CT | 2031-09-01 | 2031-03-01 |  | Intersection of 345 kV transmission lines 364, 371, 383, 310, and 348 | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
1487 | 2024-01-10 13:38 | G | 2024-01-09 | EE CT DG Group Study | PV | SUN | 5 | 5 | 5 | New Haven | CT | 2024-12-31 | 2024-12-31 |  | EE Oxford 26N | NA | FALSE | FALSE |  | PD | CT
1486 | 2024-05-01 10:24 | G | 2024-01-02 | Battery Storage | OT | BAT | 300 | 300 | 300 | New Haven | CT | 2027-06-30 | 2027-04-30 |  | Bunker Hill 115kV substation | CNR | FALSE | FALSE |  | PD | SWCT | In Progress |  |  |  |  | Under Study
1485 | 2024-08-07 16:19 | G | 2024-01-02 | Offshore Wind CNR | WT | WND | 0 | 1200 | 1200 | NA | CT | 2031-05-31 | 2031-01-31 | 2024-08-07 | Eversource (CL&P) 345kV Montville Substation | CNR | FALSE | FALSE |  |  | CT
1484 | 2025-01-08 09:55 | G | 2023-12-29 | CMP Moshers/Prides Corner 115 kV SS - Greater Portland Area DG Study | OT | SUN WAT | 3.99 | 3.99 | 3.99 | Cumberland | ME | 2024-12-31 | 2024-12-31 |  | CMP Moshers/Prides Corner 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1483 | 2025-01-08 09:53 | G | 2023-12-29 | CMP Elm St 115 kV SS - Greater Portland Area DG Study | PV | SUN | 4.97 | 4.97 | 4.97 | Cumberland | ME | 2024-12-31 | 2024-12-31 |  | CMP Elm St 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1482 | 2025-01-08 09:53 | G | 2023-12-29 | CMP Spring St 115 kV SS - Greater Portland Area DG Study | PV | SUN | 4.98 | 4.98 | 4.98 | Cumberland | ME | 2024-12-31 | 2024-12-31 |  | CMP Spring St 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1481 | 2025-01-08 09:53 | G | 2023-12-29 | CMP Vallee Lane 115 kV SS - Louden-Biddeford Area DG Study | PV | SUN | 1.99 | 1.99 | 1.99 | Cumberland | ME | 2024-12-31 | 2024-12-31 |  | CMP Vallee Lane 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1480 | 2024-02-26 14:04 | G | 2023-12-29 | CMP Biddeford IP 115 kV SS - Louden-Biddeford Area DG Study | PV | SUN | 4.95 | 4.95 | 4.95 | York | ME | 2024-12-31 | 2024-12-31 |  | CMP Biddeford IP 115 kV Substation | NA | TRUE | TRUE | CMP |  | ME
1479 | 2025-01-08 09:52 | G | 2023-12-29 | CMP West Buxton 115 kV SS - Louden-Biddeford Area DG Study | PV | SUN | 4.5 | 4.5 | 4.5 | York | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP West Buxton 115 kV Substation | NA | TRUE | TRUE | CMP |  | ME
1478 | 2024-03-08 12:29 | G | 2023-12-28 | Battery Storage | OT | BAT | 50 | 50 | 50 | Hampden | MA | 2028-05-25 | 2028-02-24 |  | A new 115kV POI Station tie-in to the Pleasant-Blandford Line adjacent to the existing Eversource Blanford Substation | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
1477 | 2023-12-19 14:22 | G | 2023-12-19 | NG DG @ Sykes Road | OT | BAT | 9.998 | 9.998 | 9.998 | Bristol | MA | 2025-12-31 | 2025-12-31 |  | NG Sykes Rd 282TR (M13N) | NA | FALSE | FALSE |  | PD | SEMA
1476 | 2024-01-02 09:39 | G | 2023-12-18 | NG NEMA Group DER Study | OT | BAT | 5 | 5 | 5 | Middlesex | MA | 2025-12-31 | 2025-12-31 |  | NG East Tewksbury T1 | NA | FALSE | FALSE |  | PD | BOST
1475 | 2024-01-02 09:38 | G | 2023-12-18 | NG NEMA Group DER Study | OT | SUN BAT | 4.998 | 4.998 | 4.998 | Essex | MA | 2025-12-31 | 2025-12-31 |  | NG Newbury 60-4T | NA | FALSE | FALSE |  | PD | BOST
1474 | 2024-01-02 09:38 | G | 2023-12-18 | NG NEMA Group DER Study | OT | BAT | 9.982 | 9.982 | 9.982 | Essex | MA | 2025-12-31 | 2025-12-31 |  | NG King St T3 | NA | FALSE | FALSE |  | PD | BOST
1473 | 2024-01-26 10:25 | G | 2023-12-14 | Battery Storage | OT | BAT | 202.07 | 202.07 | 202.07 | Hampden | MA | 2028-04-04 | 2028-02-23 | 2024-01-22 | MA_WMECO Blandford 115kV substation | CNR | FALSE | FALSE |  | PD | WMA
1472 | 2024-01-26 08:54 | G | 2023-12-12 | Battery Storage | OT | BAT | 108 | 108 | 108 | Providence | RI | 2027-01-31 | 2026-11-30 | 2024-01-09 | The Primary Point of Interconnection will be a direct interconnection to the 115-kV bus at Highland Park Substation owned by RI_NGRID. The Alternative Point of Interconnection will be located on the IC’s property (Lat, long: 41°59'46.60"N, 71°28'16.01"W) by tapping the 115-kV Line J16 (Riverside-Highland Park) at approx. 0.27 km from Highland Park Substation. | CNR | FALSE | FALSE |  | PD | RI
1471 | 2024-02-01 17:24 | G | 2023-12-12 | Battery Storage | OT | BAT | 134.7 | 134.7 | 134.7 | New Haven | CT | 2027-01-31 | 2026-11-30 | 2024-02-01 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°28'9.40"N, 73° 7'52.44"W) by tapping the 115-kV Line 1619 (Towantic-Stevenson) at approx. 1.8 Km from Towantic Substation. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Oxford Substation owned by CT_CL&P. | CNR | FALSE | FALSE |  | PD | CT
1470 | 2024-02-01 17:17 | G | 2023-12-12 | Battery Storage | OT | BAT | 237.6 | 237.6 | 237.6 | Hartford | CT | 2027-01-31 | 2026-11-30 | 2024-02-01 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°49'19.50"N, 72°43'23.49"W) by tapping the 115-kV Line 1751 (Bloomfield_J-NW.Hartford) at approx. 0.98 km from Bloomfield Substation owned by CT_CL&P. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Bloomfield Substation owned by CT_CL&P. | CNR | FALSE | FALSE |  | PD | CT
1469 | 2024-02-15 10:30 | G | 2023-12-12 | Battery Storage | OT | BAT | 190 | 190 | 190 | Worcester | MA | 2027-01-31 | 2026-11-30 | 2024-02-15 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 42°21'44.53"N, 72° 2'22.57"W) by tapping the 115-kV Line A127-4 (Barre-Paxton) at approx. 6km from Barre Substation owned by MA_NGRID. | CNR | FALSE | FALSE |  | PD | CMA
1468 | 2024-01-26 17:05 | G | 2023-12-12 | Battery Storage | OT | BAT | 76 | 76 | 76 | Plymouth | MA | 2027-01-31 | 2026-11-30 | 2024-01-26 | The Primary Point of Interconnection will be located on the IC’s property (Lat, long: 41°58'7.22"N, 71° 1'18.59"W) by tapping the 115-kV Line U6-4 (Bridgewater-Raynham) at approx. 7,87 Km from Bridgewater Substation. The Alternative Point of Interconnection will be a direct interconnection to the 115-kV bus at Bridgewater Substation owned by MA_NGRID. | CNR | FALSE | FALSE |  | PD | SEMA
1467 | 2024-12-18 15:54 | G | 2023-12-12 | Battery Storage | OT | BAT | 69.4 | 69.4 | 69.4 | Worcester | MA | 2026-10-31 | 2026-09-30 |  | National Grid 69KV Meadow Street 552 Substation | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started |  |  |  | Under Study
1466 | 2025-01-08 09:51 | G | 2023-12-05 | Winslow-County Rd Lakewood 115 kV SS - Winslow-County Rd-Lakewood 2 DG Study | PV | SUN | 20.97 | 20.97 | 20.97 | Kennebec/Somerset | ME | 2024-12-31 | 2024-12-31 |  | CMP Winslow-County Rd Lakewood 115 kV substation | NA | TRUE | TRUE | CMP | PD | ME
1465 | 2025-01-08 09:50 | G | 2023-12-05 | Augusta E/Puddledock/Bowman St 115 kV SS - Midcoast Area DG Study | OT | SUN BAT | 20.6 | 20.6 | 20.6 | Kennebec | ME | 2024-12-31 | 2024-12-31 |  | CMP Augusta E/Puddledock/Bowman St 115 kV substation | NA | TRUE | TRUE | CMP | PD | ME
1464 | 2024-02-05 12:59 | G | 2023-12-05 | Wind Repower | WT | WND | 0 | 35.2 | 35.2 | Caledonia | VT | 2026-12-31 | 2026-11-16 |  | VELCO, 115kV, Sheffield Substation 44.663509, -72.123160 | CNR | FALSE | FALSE |  | PD | VT |  | In Progress |  |  |  | Under Study
1463 | 2023-11-27 14:33 | G | 2023-11-22 | EE Valley DG Group Study | PV | SUN | 8 | 8 | 8 | Plymouth | MA | 2026-12-31 | 2026-12-31 |  | EE Valley 715 substation | NA | FALSE | FALSE |  | PD | SEMA
1462 | 2024-02-20 09:44 | G | 2023-11-27 | Battery Storage | OT | BAT | 115 | 115 | 115 | Norfolk | MA | 2029-12-20 | 2029-11-25 | 2024-02-20 | Tap on Belmont 115 kV - Stoughton Tap 115 kV Line with three breaker ring bus scheme. POI is located at the 1.75 miles from Stoughton 115kV substation and the 2.8 miles from Belmont Substation. Latitude: 42.09564, Longitude: -71.08200 | CNR | FALSE | FALSE |  | PD | SEMA
1461 | 2024-05-01 10:19 | G | 2023-10-18 | Battery Addition | OT | KER BAT | 1.498 | 165.38 | 169.25 | Rockingham | NH | 2025-09-01 | 2025-08-01 |  | 400 Gosling Road, Portsmouth, New Hampshire. The project will interconnect to the 115kV Bus 1 & 2 at Schiller Substation, directly adjacent to the project’s proposed location on the former coal storage space directly to the southeast of Schiller Substation. | CNR | FALSE | FALSE |  | PD | NH | In Progress |  |  |  |  | Under Study
1460 | 2024-09-25 16:47 | G | 2023-10-12 | Battery Storage | OT | BAT | 706.3 | 706.3037 | 706.3037 | Bristol | MA | 2027-09-30 | 2027-09-15 |  | Primary POI: NG Brayton Point 345kV substation Alternate POI: Customer built substation with a tap into the west-most 345kV line exiting the NG 345kV Brayton Point substation | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
1459 | 2025-01-08 09:47 | G | 2023-10-02 | Bath 115 kV SS - Midcoast Area DG Study | PV | SUN | 3.43 | 3.43 | 3.43 | Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP Bath 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1458 | 2025-01-08 09:46 | G | 2023-10-02 | Lincolnville 115 kV SS - Midcoast Area DG Study | PV | SUN | 4.95 | 4.95 | 4.95 | Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP - Lincolnville 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1457 | 2025-01-08 09:45 | G | 2023-10-02 | Mason 115 kV SS - Midcoast Area DG Study | PV | SUN | 3.94 | 3.94 | 3.94 | Lincoln | ME | 2024-12-31 | 2024-12-31 |  | CMP Mason 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1456 | 2025-01-08 09:45 | G | 2023-10-02 | Topsham 115 kV SS - Midcoast Area DG Study | PV | SUN | 1.98 | 1.98 | 1.98 | Waldo/Sagadahoc | ME | 2024-12-31 | 2024-12-31 |  | CMP Topsham 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1455 | 2025-01-08 09:43 | G | 2023-10-02 | Highland/Park St 115 kV SS - Midcoast Area DG Study | PV | SUN | 2 | 2 | 2 | Knox | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP Highland/Park St 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1454 | 2025-01-08 09:42 | G | 2023-10-02 | Newcastle 115 kV SS - Midcoast Area DG Study | PV | SUN | 11.65 | 11.65 | 11.65 | Cumberland/Kennedbec/Sagadahoc/Lincoln | ME | 2024-12-31 | 2024-12-31 |  | CMP Newcastle 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1453 | 2025-01-08 09:40 | G | 2023-10-02 | Coopers Mills 115 kV SS - Midcoast Area DG Study | PV | SUN | 2.88 | 2.88 | 2.88 | Lincoln | ME | 2024-12-31 | 2024-12-31 | 2025-01-07 | CMP Coopers Mills 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
1452 | 2024-08-12 10:26 | G | 2023-10-05 | Battery Storage | OT | BAT | 151.286 | 151.286 | 151.286 | Worcester | MA | 2027-05-28 | 2027-03-26 | 2024-08-08 | The Primary Point of Interconnection will be a new 3-breaker-ring bus located on the IC’s property (Lat, long: 42.322909, -71.984654) which connects to T line A127-4 at 115 KV (Barre Substation to Paxton Substation). The POI distance following the T Line is approximately 7.66 miles from the Barre Substation and approximately 3.04 miles from the Paxton Substation. The Alternative Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property (Lat, long: 42.322909, -71.984654) which connects to T line B128-5 at 115 KV (Treasure Valley Substation to Barre Substation). The POI distance following the T Line is approximately 0.2 miles from the Treasure Valley Substation and 7.66 miles from the Barre Substation. | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
1451 | 2024-07-30 11:46 | G | 2023-10-05 | Offshore wind | WT | WND | 1309 | 1309 | 1309 | NA | MA | 2030-09-27 | 2029-12-27 | 2024-07-30 | Primary: Pottersville 115kV Substation, Secondary: Bridgewater 345kV Substation | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
1450 | 2025-01-08 09:39 | G | 2023-09-29 | Woodstock 115 kV SS - Roxbury-Rumford-Woodstock Area DG Study | PV | SUN | 1.623 | 1.623 | 1.623 | Oxford | ME | 2024-12-15 | 2024-12-15 | 2025-01-07 | CMP Woodstock 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
1449 | 2025-01-08 09:38 | G | 2023-09-29 | Sturtevant 115 kV SS - Sturtevant-Leeds-Livermore-Ludden-Riley Area Study | PV | SUN | 4.99 | 4.99 | 4.99 | Franklin | ME | 2024-12-30 | 2024-06-01 |  | CMP Sturtevant 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
1448 | 2025-01-08 09:36 | G | 2023-09-29 | Ludden Lane 115 kV SS - Sturtevant-Leeds-Livermore-Ludden-Riley Area DG Study | PV | SUN | 1.999 | 1.999 | 1.999 | Oxford | ME | 2024-06-01 | 2024-06-01 |  | CMP Ludden Lane 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
1447 | 2025-01-08 09:36 | G | 2023-09-29 | Leeds 115 kV SS - Sturtevant-Leeds-Livermore-Ludden-Riley Area DG Study | PV | SUN | 4.999 | 4.999 | 4.999 | Androscoggin | ME | 2024-09-01 | 2024-09-01 |  | CMP Leeds 115 kV Substation | NA | FALSE | TRUE | CMP | PD | ME
1446 | 2025-01-08 09:36 | G | 2023-09-29 | Raymond 115 kV SS - Raymond Area DG Study | PV | SUN | 25.07 | 25.07 | 25.07 | Cumberland | ME | 2025-06-20 | 2024-09-01 |  | CMP Raymond 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1445 | 2023-12-15 16:31 | G | 2023-09-21 | Solar | PV | SUN | 51.5 | 51.5 | 51.5 | Somerset | ME | 2027-12-15 | 2027-10-15 | 2023-12-15 | The CMP 115 kV Chase Pond substation being built on Section 222. | CNR | FALSE | FALSE |  |  | ME
1444 | 2023-11-06 13:51 | G | 2023-09-21 | Battery Storage | OT | BAT | 250 | 250 | 250 | Norfolk | MA | 2027-09-15 | 2027-07-15 | 2023-11-06 | National Grid’s 115kV South Wrentham substation | NR | FALSE | FALSE |  | PD | SEMA
1443 | 2023-11-20 11:57 | G | 2023-09-20 | Battery Storage | OT | BAT | 200 | 202.6914 | 202.6914 | Rockingham | NH | 2026-12-30 | 2026-12-01 | 2023-11-20 | Project will interconnect will be a shared facility at QP-1428's POI - via tap at existing 115 kV line between Eversource 115kV Scobie Pond - Pulpit Rock Line A184 115kV. | CNR | FALSE | FALSE |  | PD | NH
1442 | 2024-09-04 13:41 | G | 2023-09-18 | Battery Storage | OT | BAT | 151.576 | 151.576 | 151.576 | Bristol | MA | 2027-05-31 | 2027-03-31 | 2024-09-04 | Primary: Eversource 115 kV Cross Road Line 111, alternate: line 109 | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
1441 | 2023-11-02 12:17 | G | 2023-09-18 | Battery Storage | OT | BAT | 103 | 103 | 103 | Hampden | MA | 2027-05-31 | 2027-03-26 | 2023-11-02 | Eversource Southwick Substation (115 KV) | CNR | FALSE | FALSE |  | PD | WMA
1440 | 2024-04-22 17:11 | G | 2023-09-18 | Battery Storage | OT | BAT | 151.556 | 151.556 | 151.556 | Hampden | MA | 2027-05-31 | 2027-03-26 |  | The Primary Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property connecting to Eversource T line 1314 (Agawam to Chicopee) at 115 KV. The POI substation would be 3.39 miles from the Chicopee Substation and 3.66 miles from the Agawam substation. The electric line placement percentage from the Chicopee substation is 48%. Alternative POI: The Alternative Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property connecting to T line 1904 (Piper to Memorial Drive) at 115 KV | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
1439 | 2024-10-29 16:12 | G | 2023-09-18 | Battery Storage | OT | BAT | 151.306 | 151.306 | 151.306 | Hampshire | MA | 2027-05-31 | 2027-03-26 | 2024-10-29 | The Primary Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property which connects to Eversource T line 1113 (Fairmont to Tillson) at 115 KV. The break in the line will take place 4.52 miles from the Fairmont Substation and 10.55 miles from the Tillson substation. The distance from the line break to the 3-breaker ring bus located on the IC’s property will be approximately 0.22 miles. The approximate latitude/longitude coordinates of the 3-breaker ring bus is 42.249111, -72.533752. The Alternative Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property which connects to Eversource T line 1134 (Fairmont to Five Corners) at 115 KV. The break in the line will take place 4.52 miles from the Fairmont Substation and 0.11 miles from the Five Corners Substation. The distance from the line break to the 3-breaker ring bus located on the IC’s property will be approximately 0.22 miles. The approximate latitude/longitude coordinates of the 3-breaker ring bus is 42.249111, -72.533752. | CNR | FALSE | FALSE |  | BL | WMA | Document Posted |  |  |  |  | Under Study
1438 | 2023-12-12 09:15 | G | 2023-10-10 | Solar | PV | SUN | 15.58 | 15.58 | 15.58 | York | ME | 2024-12-31 | 2024-12-15 | 2023-12-11 | CMP 34.5 kV, Section 182 | CNR | FALSE | FALSE |  | PD | ME
1437 | 2024-01-02 13:47 | G | 2023-08-31 | Battery Storage | OT | BAT | 103.32 | 103.32 | 103.5 | New London | CT | 2029-02-01 | 2029-01-15 |  | Montville to Gales Ferry 115kV line 1787, approximately 0.5mi north of Montville Substation | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1436 | 2024-01-02 13:45 | G | 2023-08-29 | Battery Storage | OT | BAT | 300 | 300 | 300 | New London | CT | 2028-06-01 | 2028-04-01 |  | Line tap of the Eversource 1235 115 kV Line approximately 1200’ from Uncasville 115kV SS | CNR | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
1435 | 2024-11-13 11:57 | ETU | 2023-08-21 | Non-controllable objective ETU to enable additional 1200 MW (to QP1309) injection near Millstone sub | NA | N/A | 1200 |  |  | New London | CT | 2030-12-30 | 2030-05-01 | 2024-11-12 | N/A | N/A | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1434 | 2024-06-20 12:13 | G | 2023-08-15 | Battery Storage | OT | BAT | 160 | 160 | 160 | Franklin | MA | 2027-12-31 | 2027-10-31 | 2024-06-19 | Lat Long is 42.6254349775399, -72.56881378900127 The NG Harriman - Montague 115 kV line (Y-177) Distances: 3.35 miles to Montague and 20.67 miles to Harriman | CNR | FALSE | FALSE |  | PD | WMA | Not Started
1433 | 2024-06-20 12:12 | G | 2023-08-15 | Battery Storage | OT | BAT | 100 | 100 | 100 | Hampden | MA | 2027-12-31 | 2027-10-31 | 2024-06-19 | Lat Long is 42.13610456666797, -72.27784889556564 This is the National Grid's Little Red Road - Palmer 115 kV line (W-175). The POI is approximately 1.56 miles (23.9%) from the Palmer substation and 4.97 miles (76.1%) to the Little Rest Road substation | CNR | FALSE | FALSE |  | PD | WMA | Not Started
1432 | 2024-08-15 11:21 | G | 2023-08-11 | Battery Storage | OT | BAT | 256.53 | 256.53 | 256.98 | New London | CT | 2028-09-30 | 2028-09-15 | 2024-08-15 | Direct tap into the 115kV Uncasville Substation | CNR | FALSE | FALSE |  | PD | CT |  | In Progress
1431 | 2023-08-09 12:46 | G | 2023-08-09 | Battery Storage | OT | BAT | 7 | 7 | 7 | Hartford | CT | 2024-12-29 | 2024-12-01 |  | Eversource Northwest Hartford 2N | NA | FALSE | FALSE |  | PD | CT
1430 | 2024-04-25 15:43 | G | 2023-08-09 | Battery Storage | OT | BAT | 237.545 | 237.545 | 237.545 | Bristol | MA | 2027-10-17 | 2027-09-16 |  | 115 kV line C181N - Circuit 1. Alternate POI : 345 kV line 327 - Circuit 1 | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
1429 | 2023-08-11 12:42 | G | 2023-08-08 | Wind | WT | WND | 197.4 | 197.4 | 197.4 | Aroostook | ME | 2028-10-01 | 2028-05-01 |  | CMP Orrington - Albion Road 345kV line | CNR | FALSE | FALSE |  | PD | BHE
1428 | 2024-11-05 14:06 | G | 2023-07-25 | Solar | PV | SUN | 101.549 | 101.549 | 101.549 | Rockingham | NH | 2025-12-30 | 2025-12-01 |  | A tap at existing 115 kV line between Eversource 115kV Scobie Pond - Pulpit Rock Line A184 115kV. * The new tap will be located at approx. 42.9292184N, -71.2567898W and along a ~6 mile segment of Line A184 (approx. 4.9 miles northeast of Scobie Pond and approx. 1.1 miles southwest of Pulpit Rock). | CNR | FALSE | FALSE |  | PD | NH |  | Not Started |  |  |  | Under Study
1427 | 2024-11-05 14:03 | G | 2023-07-21 | Solar | PV | SUN | 253.61 | 253.6103 | 253.6103 | York | ME | 2027-10-01 | 2027-07-01 |  | Lebanon, Maine Line 391 Buxton Sub (CMP) to Scobie Pond (Eversource). GPS coordinates of the POI: 43°22'51.59"N, 70°55'57.74"W. ** This new tap is located approximately 27.8 miles southwest of Buxton substation and approx. 39.9 miles northeast of the Scobie Pond substation. | CNR | FALSE | FALSE |  | PD | ME | Document Posted | Not Started |  |  |  | Under Study
1426 | 2024-12-10 17:23 | G | 2023-07-14 | Battery Storage | OT | BAT | 528.75 | 528.75 | 529.61 | Bristol | MA | 2028-03-31 | 2028-03-15 | 2024-12-10 | Primary POI is a direct tap into the Pottersville substation in Somerset, MA utilizing shared interconnection facilities with QP1412. Secondary POI is a direct tap into the Pottersville substation. Tertiary POI is a customer substation with a tap into the "Bell Rock Road 118 to Pottersville Station 115 kV" line, 1/2 mile east of the Pottersville substation. | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
1425 | 2024-09-04 13:42 | G | 2023-07-10 | Battery Storage | OT | BAT | 151.596 | 151.596 | 151.596 | Hampden | MA | 2026-10-01 | 2026-07-01 | 2024-09-04 | Western Massachusetts Electric Co South Agawam Switching Station (115 kv) via a new breaker bay | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1424 | 2023-08-15 14:32 | G | 2023-07-10 | Battery Storage | OT | BAT | 41.2 | 41.2 | 41.2 | Worcester | MA | 2026-09-01 | 2026-06-01 | 2023-08-15 | New England Power Company Westminster Switching Station (69KV Line) | CNR | FALSE | FALSE |  | PD | CMA
1423 | 2024-09-25 16:46 | G | 2023-07-10 | Battery Storage | OT | BAT | 121.6 | 121.6 | 121.6 | Worcester | MA | 2026-09-01 | 2026-06-01 | 2024-09-04 | The Primary Point of Interconnection will be a new 3-breaker ring bus located on the IC’s property which will connect to National Grid T-Line H160 (Northboro Rd to Hudson) at 115 KV. The approximate line-break location will be 0.26 miles from Northboro Rd substation and 7.92 miles from Hudson Substation. The Alternative POI will be a new 3-breaker ring bus located on the IC’s property which connects to T-Line N166 (Northboro Rd to N.Marloboro) at 115 KV. | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
1422 | 2024-04-25 12:37 | G | 2023-07-07 | Battery Storage | OT | BAT | 326 | 326 | 326 | Hartford | CT | 2029-02-02 | 2028-12-01 |  | Barbour Hill Substation 115kV direct connection ( 41.854810, -72.528106) | CNR | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
1421 | 2024-01-26 16:59 | G | 2023-07-06 | Battery Storage | OT | BAT | 175.67 | 175.67 | 175.67 | Bristol | MA | 2024-09-08 | 2024-08-08 | 2024-01-26 | 41.987864, -71.265095 Tapping to National Grid 115kV line C181 | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
1420 | 2024-09-24 09:34 | G | 2023-06-29 | Battery Storage | OT | BAT | 175.097 | 175.097 | 175.097 | New London | CT | 2027-12-31 | 2027-09-30 |  | Existing Eversource 115kV structure on Line 1410, West of 39 Dock Road (41.430126, -72.103424). | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
1419 | 2024-03-06 12:41 | G | 2023-06-28 | Battery Storage | OT | BAT | 108.7 | 108.7 | 108.7 | Bristol | MA | 2027-04-01 | 2027-03-01 | 2024-03-06 | National Grid 115KV Bates Street Substation | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
1418 | 2023-12-05 08:47 | G | 2023-06-27 | Battery Storage | OT | BAT | 108.7 | 108.7 | 108.7 | Providence | RI | 2027-04-01 | 2027-03-01 | 2023-11-30 | 115KV Line Q143S-2 between Woonsocket and Franklin Square substations, approximately 10 miles from Woonsocket substation. | CNR | FALSE | FALSE |  | PD | RI | In Progress |  |  |  |  | Under Study
1417 | 2024-12-11 13:07 | G | 2023-06-26 | Battery Storage | OT | BAT | 300 | 300 | 300 | Windham | CT | 2028-06-01 | 2028-04-01 | 2024-12-11 | Eversource 115kV Killingly Substation | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
1416 | 2023-08-09 08:34 | G | 2023-06-26 | Battery Storage | OT | BAT | 196 | 196 | 196 | Hampshire | MA | 2027-05-19 | 2027-05-12 | 2023-08-08 | Eversource 115 KV Line Number 1447 | CNR | FALSE | FALSE |  | PD | WMA
1415 | 2024-09-26 13:15 | G | 2023-06-20 | Battery Storage | OT | BAT | 261.9 | 261.9 | 261.9 | Worcester | MA | 2024-08-12 | 2024-07-12 | 2024-09-26 | POI interconnection coordinates: 42.471953, -71.734165 Interconnecting to National Grid 345kV line (line ID: 343) via line tap (approx. 8.5 mi from Wachusett Substation and 14.9 mi from Sandy Pond Substation). | CNR | FALSE | FALSE |  | PD | CMA | Not Started |  |  |  |  | Under Study
1414 | 2023-06-20 16:24 | G | 2023-06-19 | Individual @ Piper | FC | FC | 4.1 | 4.1 | 4.1 | Hampden | MA | 2026-12-31 | 2026-12-31 |  | EE Piper 21N | NA | FALSE | FALSE |  | PD | WMA
1413 | 2023-06-20 16:21 | G | 2023-06-19 | Group @ Orchard | OT | SUN BAT | 4.04 | 4.04 | 4.04 | Hampden | MA | 2026-12-31 | 2026-12-31 |  | EE Orchard 27A | NA | FALSE | FALSE |  | PD | WMA
1412 | 2023-09-20 09:49 | G | 2023-06-20 | Battery Storage | OT | BAT | 179.47 | 179.47 | 179.84 | Bristol | MA | 2027-09-30 | 2027-09-15 |  | Direct tap into the Pottersville Substation in Somerset, MA | CNR | FALSE | FALSE |  | PD | SEMA | Not Started |  |  |  |  | Under Study
1411 | 2023-08-17 09:18 | ETU | 2023-06-20 | 1200 MW controllable ETU - unidirectional | NA | N/A | 1200 |  |  | Middlesex | MA | 2032-05-31 | 2031-12-31 | 2023-08-17 | Eversource Mystic 345 kV Substation | N/A | FALSE | FALSE |  | PD | BOST
1410 | 2023-06-16 16:40 | G | 2023-06-13 | Individual @ Amherst | OT | BAT | 2 | 2 | 2 | Hampshire | MA | 2024-12-31 | 2024-12-01 |  | EE Amherst 17K | NA | FALSE | FALSE |  | PD | WMA
1409 | 2023-06-16 16:37 | G | 2023-06-13 | Individual @ Montague | OT | BAT | 4.99 | 4.99 | 4.99 | Franklin | MA | 2024-12-31 | 2024-12-01 |  | EE MONTAGUE 21C | NA | FALSE | FALSE |  | PD | WMA
1408 | 2023-06-16 16:34 | G | 2023-06-13 | Individual @ Partridge | OT | SUN BAT | 4 | 4 | 4 | Berkshire | MA | 2024-12-31 | 2024-12-01 |  | EE Partridge 15E1 | NA | FALSE | FALSE |  | PD | WMA
1407 | 2023-06-16 16:31 | G | 2023-06-13 | EE Group @ Blandford | OT | SUN BAT | 28.936 | 28.926 | 28.936 | Hampshire | MA | 2024-12-31 | 2024-12-01 |  | EE BLANDFORD 19J | NA | FALSE | FALSE |  | PD | WMA
1406 | 2023-06-16 16:28 | G | 2023-06-13 | EE Group @ Doreen | OT | SUN BAT | 9.15 | 9.15 | 9.15 | Berkshire | MA | 2024-12-31 | 2024-12-01 |  | EE Doreen 19A | NA | FALSE | FALSE |  | PD | WMA
1405 | 2023-06-16 16:26 | G | 2023-06-13 | EE Group @ Southwick | OT | SUN BAT | 7 | 7 | 7 | Hampden | MA | 2024-12-31 | 2024-12-01 |  | EE SOUTHWICK 29A | NA | FALSE | FALSE |  | PD | WMA
1404 | 2023-06-16 16:23 | G | 2023-06-13 | Individual @ French King | OT | SUN BAT | 2.2 | 2.2 | 2.2 | Franklin | MA |  | 2024-12-01 |  | EE French King 21B | NA | FALSE | FALSE |  | PD | WMA
1403 | 2025-01-13 17:35 | G | 2023-06-09 | Battery Storage | OT | BAT | 304.72 | 304.72 | 304.72 | Middlesex | CT | 2026-11-20 | 2026-06-12 | 2025-01-13 | Scoville 345kV substation | CNR | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
1402 | 2023-09-08 14:31 | G | 2023-06-07 | Battery Storage | OT | BAT | 171.6 | 171.6 | 171.6 | Hampden | MA | 2027-06-01 | 2027-05-01 |  | POI interconnection coordinates: 42.068458, -72.462254 Interconnecting to the 115kV open bay at the NGRID West Hampden substation (connecting to T3's current position). | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1401 | 2023-09-08 14:30 | ETU | 2023-06-07 | controllable 345 kV ETU - Brayton Point to Pottersville | NA | N/A |  |  |  | Bristol | MA | 2029-12-31 | 2029-06-30 |  | N/A | N/A | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
1400 | 2023-09-08 14:29 | G | 2023-05-18 | Battery Storage | OT | BAT | 101.97 | 101.97 | 101.97 | Hartford | CT | 2026-12-31 | 2026-07-31 |  | 41.6317, -72.7289, Berlin 115 kV Substation | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
1399 | 2023-09-08 14:28 | G | 2023-05-18 | Battery Storage | OT | BAT | 92.438 | 92.438 | 92.438 | Hampden | MA | 2027-05-31 | 2027-03-31 |  | The proposed POI is Buck Pond 115 kV substation, share gen leadline with QP1117. | CNR | FALSE | FALSE |  | PD | WMA |  | Not Started |  |  |  | Under Study
1398 | 2024-12-04 09:51 | G | 2023-05-08 | Battery Storage | OT | BAT | 101.97 | 101.97 | 101.97 | Worcester | MA | 2026-12-31 | 2026-07-31 | 2024-12-03 | A newly constructed three-breaker ring bus that will sectionalize National Grid’s Fitzwilliam to Flagg Pond 115 kV transmission line I-135 at about 7.48 miles from the East Winchendon Substation and 6.34 miles from the Flagg Pond Substation | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started |  |  |  | Under Study
1397 | 2024-04-25 12:38 | G | 2023-05-05 | Battery Storage | OT | BAT | 100.24 | 100.2358 | 100.2358 | Worcester | MA | 2026-12-31 | 2026-07-31 |  | 42.31815556, -71.98500556, Treasure Valley 115 kV Substation | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | In Progress |  |  |  | Under Study
1396 | 2024-03-06 14:45 | G | 2023-05-05 | Battery Storage | OT | BAT | 101.97 | 101.97 | 101.97 | Providence | RI | 2026-12-31 | 2026-07-31 |  | 41.82919444, -71.52111667, Hartford 115 kV Substation | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1395 | 2023-10-13 16:05 | G | 2023-05-05 | Battery Storage | OT | BAT | 20 | 20 | 20 | Hampshire | MA | 2027-06-30 | 2027-06-30 | 2023-05-22 | National Grid 115 kV Line 1134 | CNR | FALSE | FALSE |  | PD | WMA
1394 | 2023-09-08 14:22 | G | 2023-05-04 | Battery Storage Addition | OT | BAT | 0 | 284.05 | 284.05 | Middlesex | CT | 2026-07-01 | 2026-05-01 |  | POI between 10F-2T-2 and 10F-1T-1 breakers on the 345 kV bus; Northeast Utilities 11631 Substation - Middletown. | CNR | FALSE | FALSE |  | PD | CT |  | In Progress |  |  |  | Under Study
1393 | 2023-09-13 11:41 | G | 2023-05-03 | Gas Turbine | GT | NG | 233 | 233 | 233 | Fairfield | CT | 2026-06-01 | 2026-05-04 | 2023-09-13 | Eversource Middleriver substation 115kv | CNR | FALSE | FALSE |  | PD | SWCT
1392 | 2024-02-02 10:14 | G | 2023-05-03 | Battery Storage | OT | BAT | 53.74 | 53.74 | 53.74 | New Haven | CT | 2026-09-15 | 2026-08-15 |  | Latitude: 41.492036°, Longitude: -72.762080° -Owner: Connecticut Light and Power Company, Voltage 115 kV, Substation Name: North Wallingford 115 kV Station. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1391 | 2023-04-28 14:59 | G | 2023-04-28 | Wind CNR | WT | WND | 0 | 26.01 | 26.01 | Washington | ME | 2023-11-01 | 2023-11-01 |  | Keene Rd Substation via through a 115kV Line 56 from Stetson Mountain115/34.5kV substation | CNR | FALSE | FALSE |  |  | BHE |  | Not Required |  |  | In Progress
1390 | 2023-04-28 14:58 | G | 2023-04-28 | Wind CNR | WT | WND | 0 | 34.485 | 34.485 | Hancock | ME | 2023-11-01 | 2023-11-01 |  | Bull Hill 115 kV Switching Station | CNR | FALSE | FALSE |  |  | BHE |  | Not Required |  |  | In Progress
1389 | 2023-04-28 14:57 | G | 2023-04-27 | Wind CNR | WT | WND | 0 | 58.14 | 58.14 | Washington | ME | 2023-11-01 | 2023-11-01 |  | Keene Rd Substation via through a 115kV Line 56 from Stetson Mountain115/34.5kV substation | CNR | FALSE | FALSE |  |  | BHE |  | Not Required |  |  | In Progress
1388 | 2023-04-28 14:57 | G | 2023-04-27 | Wind CNR | WT | WND | 0 | 61.2 | 61.2 | Penobscot | ME | 2023-11-01 | 2023-11-01 |  | Keene Rd Substation via through a 115kV Line 55 & Line 56 from Rollins Mountain115/34.5kV | CNR | FALSE | FALSE |  |  | BHE |  | Not Required |  |  | In Progress
1387 | 2024-11-13 11:56 | ETU | 2023-04-27 | Non-controllable objective ETU to enable 1200 MW offshore wind/300 MW solar at Crystal Springs sub | NA | N/A |  |  |  | Plymouth | MA | 2030-12-30 | 2029-12-31 | 2024-11-12 | N/A | N/A | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
1386 | 2024-10-04 10:15 | G | 2023-04-26 | Battery Storage | OT | BAT | 100 | 100 | 100 | Berkshire | MA | 2026-12-31 | 2026-10-31 | 2024-10-04 | National Grid Berkshire - Plainfield 115 kV line Lat/Long: 42.49627608454711, -73.01015449707741 | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
1385 | 2024-10-23 09:30 | G | 2023-04-26 | Battery Storage | OT | BAT | 200 | 233 | 233 | Worcester | MA | 2026-12-31 | 2026-09-01 | 2024-07-29 | National Grid's: Bellows Fall (37.18 mi) - E. Winchendon Tap (2.07 mi) 115kV line (J136N) | NR | FALSE | FALSE |  | PD | CMA | In Progress
1384 | 2024-10-23 09:31 | G | 2023-04-26 | Battery Storage | OT | BAT | 300 | 300 | 300 | Worcester | MA | 2026-12-31 | 2026-09-01 | 2024-07-29 | National Grid's Pratts Junction - Sandy Pond L138W-2 line (115 kV). 2.92 miles from Pratts Junction and 11.95 miles from Sandy Pond (on 115 kV line). Coordinates: 42.493249051839484, -71.7028083287439 | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started
1383 | 2023-12-15 16:34 | G | 2023-04-13 | Solar and Battery | PV | SUN BAT | 139 | 139 | 139 | Penoboscot | ME | 2028-12-31 | 2028-09-01 | 2023-12-15 | 44°46'22.13"N, 68°29'5.84"W new switching station to tie into Versant 115 kV line in Clifton | CNR | FALSE | FALSE | ISO-NE | NA | BHE | Document Posted | Not Started |  |  |  | Under Study
1382 | 2023-06-05 16:57 | G | 2023-04-11 | Vineyard Offshore Wind CNR | WT | WND | 0 | 843.2 | 843.2 | N/A | MA | 2025-05-26 | 2024-01-02 |  | Eversource (NSTAR) 115kV Barnstable Switch Station (958) | CNR | FALSE | FALSE | ISO-NE | NA | SEMA
1381 | 2023-09-08 14:14 | ETU | 2023-04-11 | 1200 MW (+/- 400 kV) HVDC External ETU | NA | N/A | 1200 |  |  | Grafton | NH | 2029-07-01 | 2029-01-01 |  | In New Hampshire, the point of interconnection is near the old Monroe yard (AC capacitors and reactors and Phase II filters presently reside in this yard). The project will tie into the currently existing Comerford 230 kV substation. The northern section of the project will connect with the Hydro-Quebec system at the US-Canada border near Canaan, Vermont. | NI | FALSE | FALSE | ISO-NE | NA | NH | In Progress |  |  |  |  | Under Study
1380 | 2025-01-14 09:18 | G | 2023-04-06 | Fuel Cell CNR | FC | FC | 0 | 20.1 | 20.1 | Hartford | CT | 2024-12-12 | 2024-05-28 |  | The electrical connection where Eversource's 69 kV 680 line span from pole 2742 connects to the Farmington River Power Company's 680 line at pole 2743's insulator. | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed | In Service
1379 | 2023-04-06 10:53 | G | 2023-04-03 | Solar | PV | SUN | 218.4 | 218.4 | 218.4 | Aroostook | ME | 2028-10-31 | 2028-09-30 |  | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near the town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
1378 | 2023-12-12 15:44 | G | 2023-04-03 | Battery Storage | OT | BAT | 105 | 105 | 105 | Windsor | VT | 2027-04-08 | 2027-03-08 | 2023-12-12 | Vermont Electric Power Company, Ascutney 115 kV. | CNR | FALSE | FALSE |  | PD | VT | In Progress |  |  |  |  | Under Study
1377 | 2023-12-12 15:43 | G | 2023-04-03 | Battery Storage | OT | BAT | 180 | 180 | 180 | Windsor | VT | 2027-04-08 | 2027-03-08 | 2023-12-12 | Vermont Electric Power Company, Coolidge 115 kV | CNR | FALSE | FALSE |  |  | VT | In Progress |  |  |  |  | Under Study
1376 | 2024-10-09 08:32 | G | 2023-03-29 | Battery Storage | OT | BAT | 325.7 | 325.7 | 325.7 | New Haven | CT | 2027-04-01 | 2027-03-01 | 2024-10-08 | 115KV Line #1640 between Devon 2 & Wallingford substations, approximately 2.15 circuit miles from Wallingford substation | CNR | FALSE | FALSE |  | PD | CT | Document Posted
1375 | 2023-03-29 12:42 | G | 2023-03-29 | Wind | WT | WND | 217 | 217 | 217 | Aroostook | ME | 2026-12-09 | 2026-10-08 |  | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near the town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
1374 | 2024-10-15 16:52 | G | 2023-03-28 | Battery Storage | OT | BAT | 226 | 226 | 226 | Merrimack | NH | 2027-04-07 | 2027-03-31 |  | Eversource 115 kV Line C196. | CNR | FALSE | FALSE |  | PD | NH | Document Posted | In Progress |  |  |  | Under Study
1373 | 2023-07-25 13:23 | G | 2023-03-15 | Battery Storage Increase (QP1362) | OT | BAT | 140.48 | 743 | 743 | Norfolk | MA | 2027-11-12 | 2027-06-25 |  | Eversource's West Medway 345kV station | CNR | FALSE | FALSE |  | PD | SEMA |  | Not Started |  |  |  | Under Study
1372 | 2023-05-03 09:10 | ETU | 2023-03-15 | Non-controllable ETU - bi-directional | NA | N/A |  |  |  | Lincoln | ME | 2028-06-01 | 2028-06-01 | 2023-05-03 | New 345 kV Transmission Line from Maine Yankee 345 Substation (existing) to Coopers Mills 345 Substation (existing) | N/A | FALSE | FALSE |  |  | ME
1371 | 2023-04-05 15:55 | ETU | 2023-03-10 | Non-controllable ETU - N to S flow only | NA | N/A |  |  |  | Somerset /Lincoln | ME | 2028-06-01 | 2028-06-01 |  | New Pittsfield Substation lat/long 44.795/-69.386 Existing Coopers Mills 345 kV Station lat/long 44.2966/-69.556771 | N/A | FALSE | FALSE |  |  | ME
1370 | 2023-03-15 13:32 | ETU | 2023-03-10 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Aroostook/Somerset | ME | 2028-06-01 | 2028-06-01 |  | Transmission line connects between the new Aroostook station and Pittsfield station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line in Somerset county at Lat/Long 44.795/-69.386. The Aroostook station will be located in Aroostook county at Lat/Long 45.7634/-68.0278 | N/A | FALSE | FALSE |  |  | ME
1369 | 2023-11-21 14:10 | G | 2023-03-08 | Athens 115 kV SS - CMP Wyman Area Study | PV | SUN | 1.992 | 1.992 | 1.992 | Somerset | ME | 2024-12-31 |  |  | CMP Athens substation, Circuit 827D2 | NA | TRUE | TRUE | CMP | PD | ME
1368 | 2023-04-12 08:12 | G | 2023-03-09 | Battery Storage | OT | BAT | 240.8 | 240.8 | 240.8 | Essex | MA | 2027-04-01 | 2027-03-01 | 2023-04-12 | National Grid 115KV Line Q169 - Approximately 0.5 Miles from Lynn Substation | CNR | FALSE | FALSE |  | PD | BOST
1367 | 2023-12-05 08:46 | G | 2023-03-09 | Battery Storage | OT | BAT | 271.4 | 271.4 | 271.4 | Bristol | MA | 2027-04-01 | 2027-03-01 | 2023-11-30 | National Grid 115KV Line U6 between Pottersville and Bridgewater substations - approximately 6.1 circuit miles from Bridgewater substation | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
1366 | 2024-08-19 12:42 | G | 2023-03-09 | Battery Storage | OT | BAT | 200.84 | 200.84 | 200.84 | Fairfield | CT | 2026-11-20 | 2026-06-12 | 2024-08-19 | Peaceable 115 kV station | CNR | FALSE | FALSE |  | PD | SWCT | Document Posted
1365 | 2023-07-07 13:08 | G | 2023-03-09 | Battery Storage | OT | BAT | 301.26 | 301.26 | 301.26 | Hampden | MA | 2026-11-20 | 2026-06-12 |  | Connect to South Agawam 115 kV switchyard | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
1364 | 2025-01-13 12:23 | G | 2023-03-01 | Battery Storage | OT | BAT | 401.68 | 401.68 | 401.68 | Rockingham | NH | 2026-11-20 | 2026-06-12 | 2025-01-13 | Timber Swamp Rd 345 kV station | CNR | FALSE | FALSE |  | PD | NH | Document Posted | Not Started |  |  |  | Under Study
1363 | 2024-11-05 14:07 | G | 2023-03-01 | Battery Storage | OT | BAT | 301.26 | 301.26 | 301.26 | Hampden | MA | 2026-11-20 | 2026-06-12 |  | Ludlaw 345 kV station | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
1362 | 2023-07-25 13:22 | G | 2023-02-24 | Battery Storage Increase (QP1238) | OT | BAT | 301.26 | 602.52 | 602.52 | Norfolk | MA | 2027-11-12 | 2027-06-25 |  | Eversource's West Medway 345kV station | CNR | FALSE | FALSE |  | PD | SEMA |  | Not Started |  |  |  | Under Study
1361 | 2023-09-08 13:05 | G | 2023-02-24 | Offshore Wind | WT | WND | 882 | 882 | 882 | NA | MA | 2030-02-15 | 2029-10-01 | 2023-09-08 | RIE, Jepson 115 kV Substation | CNR | FALSE | FALSE |  | PD | SEMA | In Progress
1360 | 2023-02-23 12:56 | G | 2023-02-22 | Battery Storage | OT | BAT | 10 | 10 | 10 | Middlesex | CT | 2024-06-15 | 2024-06-01 |  | CLP 11C Haddam, Circuit 11C13 | NA | FALSE | FALSE |  | PD | CT
1359 | 2023-03-09 15:08 | G | 2023-02-22 | Fuel Cell | FC | FC | 1.84 | 1.84 | 1.84 | Hartford | CT | 2024-12-31 | 2024-11-30 |  | CLP Northwest Hartford 2N, Circuit 2N14 | NA | FALSE | FALSE |  |  | CT
1358 | 2023-07-07 13:00 | G | 2023-02-21 | Battery Storage | OT | BAT | 100 | 100 | 100 | Hartford | CT | 2026-07-31 | 2026-06-30 |  | Tap on South Windsor to Manchester 115kV line. | CNR | FALSE | FALSE |  | PD | CT |  | In Progress |  |  |  | Under Study
1357 | 2024-10-01 14:11 | G | 2023-02-16 | Solar Increase | PV | SUN | 5 | 152.045 | 152.045 | Hartford | CT | 2026-06-15 | 2026-05-15 |  | To interconnect at the POI of Gravel Pit Solar (QP 1030 + QP 1247), as an increase to QP 1030 and QP1247, the POI is the new Gravel Pit Solar substation at the new three-breaker ring bus on the 115 kV Connecticut Light & Power Company 1200 line between Barbour Hill and Windsor Locks. | CNR | TRUE | TRUE |  | PD | CT |  | Document Posted |  |  | In Progress
1356 | 2024-10-15 09:46 | G | 2023-02-09 | (Offshore wind Increase (Q700 +Q1154) | WT | WND | 38.8 | 895 | 895 | NA | MA | 2026-10-30 | 2026-03-14 | 2024-10-14 | Eversource 345kV West Barnstable (921) | CNR | FALSE | FALSE |  | PD | SEMA
1355 | 2023-04-19 10:15 | G | 2023-02-06 | Battery Storage | OT | BAT | 136.32 | 136.32 | 136.32 | New Haven | CT | 2024-10-01 | 2024-09-01 |  | POI is the Devon 115 kV Bus 2 between 7R-19T2 and 7R-23T-2 breakers | NR | FALSE | FALSE |  | PD | SWCT |  | Not Started |  |  |  | Under Study
1354 | 2023-04-13 16:07 | G | 2023-02-06 | Battery Storage | OT | BAT | 289.29 | 289.29 | 289.29 | Middlesex | CT | 2024-10-01 | 2024-09-01 | 2023-04-13 | POI between 5A-5T-2 and 5A-6T-2; Northeast Utilities 11631 Substation - Middletown | CNR | FALSE | FALSE |  | PD | CT
1353 | 2023-04-19 13:45 | G | 2023-02-06 | Battery Storage | OT | BAT | 289.29 | 289.29 | 289.29 | New London | CT | 2024-10-01 | 2024-09-01 |  | Montville 4J between 4J-11T-2 and 4J-12T-2. Interconnected with Montville Unit 6. New Montville Unit 6 Generator breaker will be installed for sync control. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1352 | 2023-07-07 12:59 | G | 2023-02-06 | Battery Storage | OT | BAT | 262.68 | 262.68 | 262.68 | New Haven | CT | 2024-10-01 | 2024-09-01 |  | POI: East Shore Substation 115 kV | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1351 | 2023-07-07 12:58 | G | 2023-02-06 | Battery Storage | OT | BAT | 156.24 | 156.24 | 156.24 | Fairfield | CT | 2027-10-01 | 2027-08-01 |  | Owner: UI, Substation: Singer 345 kV | CNR | FALSE | FALSE |  | PD | SWCT |  | In Progress |  |  |  | Under Study
1350 | 2023-08-24 16:18 | ETU | 2023-01-31 | 1200 MW Controllable ETU | NA | N/A | 1200 |  |  |  | RI | 2029-12-31 | 2029-09-01 | 2023-08-24 | POI at Rhode Island Energy's Kent county Substations, See assocation reference drawings | N/A | FALSE | FALSE |  | PD | RI
1349 | 2023-01-27 09:24 | G | 2023-01-26 | Scitico DG Cluster | OT | SUN BAT | 5.2 | 5.2 | 5.2 | Hartford | CT | 2023-12-31 | 2023-07-01 |  | Eversource Scitico 27H/27H1 | NA | FALSE | FALSE |  | PD | CT
1348 | 2023-03-09 15:07 | G | 2023-01-26 | Battery Storage | OT | BAT | 5.057 | 5.057 | 5.057 | Middlesex | CT | 2025-07-27 | 2025-06-25 |  | Eversource Portland 21H | NA | FALSE | FALSE |  | PD | CT
1347 | 2023-01-27 09:14 | G | 2023-01-26 | Enfield DG Cluster | OT | SUN BAT | 18.77 | 18.77 | 18.77 | Hartford | CT | 2025-07-27 | 2023-12-31 |  | Eversource Enfield 12C/Windsor Locks 14K | NA | FALSE | FALSE |  | PD | CT
1346 | 2024-10-09 14:14 | G | 2023-01-12 | Battery Storage | OT | BAT | 196.468 | 196.468 | 196.468 | Hartford | CT | 2026-09-15 | 2026-09-08 | 2024-10-09 | Eversource, North Bloomfield Substation, 345kV BUS. | CNR | FALSE | FALSE |  | PD | CT | In Progress
1345 | 2024-12-18 12:23 | G | 2023-01-10 | Battery Storage | OT | BAT | 75 | 75 | 75 | New London | CT | 2028-06-01 | 2028-04-01 |  | Shunock 115kV Substation, Pendleton Hill Substation, North Stonington, CT 06359 | CNR | FALSE | FALSE |  | PD | CT |  | Not Started |  |  |  | Under Study
1344 | 2022-12-30 09:29 | G | 2022-12-28 | Offshore Wind CNR only | WT | WND | 0 | 827 | 827 | NA | MA | 2025-10-15 | 2025-08-15 |  | Eversource 345 kV West Barnstable Substation | CNR | FALSE | FALSE |  |  | SEMA
1343 | 2023-09-19 13:27 | G | 2022-12-19 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2029-12-15 | 2029-07-15 |  | National Grid 115 kV Pottersville | CNR | FALSE | FALSE |  |  | SEMA | Document Posted | Not Started |  |  |  | Under Study
1342 | 2023-02-06 08:36 | G | 2022-12-15 | Western Maine Wind CNR | WT | WND | 0 | 58.8 | 58.8 | Somerset | ME | 2024-12-20 | 2024-11-22 |  | CMP 115 kV Section 222 - coordinates 45° 9'30.90"N, 69°51'1.40"W | CNR | FALSE | FALSE |  |  | ME
1341 | 2023-01-30 15:17 | G | 2022-12-06 | Battery Storage | OT | BAT | 117.3 | 667.425 | 667.425 | Bristol | MA | 2027-06-30 | 2027-06-15 | 2023-01-30 | National Grid's Brayton Point 345kV Substation, Somerset MA. | CNR | FALSE | FALSE |  | PD | SEMA
1340 | 2023-01-30 15:17 | G | 2022-12-06 | Battery Storage | OT | BAT | 292.52 | 550.12 | 550.12 | Bristol | MA | 2027-06-30 | 2027-06-15 | 2023-01-30 | National Grid's Brayton Point 345kV Substation, Somerset MA. | CNR | FALSE | FALSE |  | PD | SEMA
1339 | 2023-01-30 15:17 | G | 2022-12-06 | Battery Storage | OT | BAT | 257.06 | 257.06 | 257.06 | Bristol | MA | 2027-06-30 | 2027-06-15 | 2023-01-30 | National Grid's Brayton Point 345kV Substation, Somerset MA. | CNR | FALSE | FALSE |  | PD | SEMA
1338 | 2024-07-30 17:23 | G | 2022-12-06 | Battery Storage | OT | BAT | 275.06 | 275.06 | 275.06 | Hampden | MA | 2027-06-30 | 2027-06-15 | 2024-07-30 | Agawam to Ludlow - 345kV line, 2.5 miles west of Ludlow substation | CNR | TRUE | FALSE | ISO-NE | PD | WMA |  | Document Posted |  |  | Not Started
1337 | 2023-11-17 10:07 | G | 2022-11-22 | Battery Storage | OT | BAT | 130 | 130 | 130 | Berkshire | MA | 2026-12-31 | 2026-07-01 | 2023-11-17 | 7,500' to Adams - NG Q117 VEL - 65,000' Bennington 115 kV line (42.72482385, -73.09931100). (The project site is on the western side of the transmission line off a gravel bank road and on the opposite side of the small solar array) | CNR | FALSE | FALSE |  | PD | WMA | Document Posted | Not Started |  |  |  | Under Study
1336 | 2024-01-05 12:11 | G | 2022-11-22 | Battery Storage | OT | BAT | 130 | 130 | 130 | Worcester | MA | 2026-12-31 | 2026-07-01 | 2024-01-05 | Carpenter Hill - North Oxford - Millbury #2 115 kV (V-174) line (2.57 miles from the N. Oxford substation and 6.92 miles from the Millbury #2 substation). | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started |  |  |  | Under Study
1335 | 2024-10-09 08:30 | G | 2022-11-10 | Battery Storage | OT | BAT | 205.8 | 205.8 | 205.8 | Bristol | MA | 2027-04-01 | 2027-03-01 | 2024-10-08 | Non-PTF 115KV lines ET and W owned by TMLP between Cleary Flood Substation and Substation #16 (W Water St), approximately 1.26 miles from Cleary Flood. Project would interconnect half of the net MW capability to each line. | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started
1334 | 2024-10-09 08:30 | G | 2022-11-10 | Battery Storage | OT | BAT | 93.2 | 93.2 | 93.2 | New London | CT | 2027-05-01 | 2027-04-01 | 2024-10-08 | 115 kV line 1070 between Ft Hill Farms and Stockhouse Substations, interconnected by a new three-breaker ring bus approximately 2.5 miles from Ft Hill Farms substation. | CNR | FALSE | FALSE |  | PD | CT |  | Not Started
1333 | 2024-01-30 15:32 | ETU | 2022-11-08 | 2400 controllable ETU - unidirectional | NA | N/A | 1100 |  |  |  | CT | 2028-05-31 | 2028-03-31 | 2024-01-30 | 1. Singer 345kV Substation existing available circuit breaker position and new circuit breaker position. 2. Offshore platform at the MA/RI BOEM Wind Energy Areas | N/A | FALSE | FALSE |  |  | SWCT | Not Started |  |  |  |  | Under Study
1332 | 2023-11-22 11:41 | ETU | 2022-11-08 | Enable 1200 MW injection at Mystic | NA | N/A | 1200 |  |  |  | MA | 2029-12-30 | 2029-05-01 | 2023-11-22 | N/A | N/A | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
1331 | 2023-12-19 09:00 | G | 2022-11-02 | Battery Storage | OT | BAT | 300 | 300 | 300 | Hampden | MA | 2025-12-23 | 2025-12-16 | 2023-12-19 | Interconnecting to POI coordinates (42.148537, -72.300019) on 115 kV Transmission line X-176, approximately 0.3 miles north of Palmer #503 substation and 5.76 miles from Thorndike #523 substation. | CNR | FALSE | FALSE |  | PD | WMA | Document Posted | Not Started |  |  |  | Under Study
1330 | 2022-12-19 08:10 | G | 2022-11-01 | Solar | PV | SUN | 46.5 | 46.5 | 46.5 | Sullivan | NH | 2023-12-20 | 2023-11-17 | 2022-12-16 | 43.177488°, -72.434553° - National Grid 115kV line | CNR | FALSE | FALSE |  |  | NH
1329 | 2023-05-19 07:57 | G | 2022-10-24 | Solar | PV | SUN | 54.4 | 54.4 | 54.4 | Grafton | NH | 2024-06-05 | 2024-05-15 | 2023-05-19 | POI: (44.321330°, -72.003124°), National Grid's PTF 230 kV bus at Comerford No. 18 station | CNR | FALSE | FALSE |  | PD | NH | Document Posted |  |  |  |  | Under Study
1328 | 2023-04-28 11:07 | G | 2022-10-24 | Solar | PV | SUN | 21.44 | 21.44 | 21.44 | Grafton | NH | 2024-06-05 | 2024-05-15 | 2023-04-27 | 44.336047°, -71.874785°, National Grid 230 kV Substation | CNR | FALSE | FALSE |  | PD | NH | In Progress |  |  |  |  | Under Study
1327 | 2023-02-14 11:19 | G | 2022-10-20 | Battery Storage | OT | BAT | 270 | 270 | 270 | Norfolk | MA | 2023-12-02 | 2023-11-02 | 2023-02-14 | West Walpole substation | CNR | FALSE | FALSE |  | PD | SEMA
1326 | 2023-10-13 16:23 | G | 2022-10-19 | Battery Storage | OT | BAT | 40 | 40 | 40 | Kent | RI | 2027-12-30 | 2027-12-15 | 2023-10-13 | Line tap on the S-171 South 115 kV transmission line, roughly 4 miles from West Cranston Substation and 1.5 miles from Drumrock Substation. | NR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1325 | 2024-06-04 08:16 | G | 2022-10-19 | Battery Storage | OT | BAT | 305 | 307.8 | 307.8 | Providence | RI | 2027-12-30 | 2027-12-15 | 2024-05-31 | NEP transmission line: 345 kV line 359, approximately 10.55 miles from West Farnum and 10.81 miles from Kent County substations. | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1324 | 2024-10-27 17:04 | G | 2022-10-18 | Battery Storage | OT | BAT | 55 | 55 | 55 | Providence | RI | 2027-12-30 | 2027-12-15 | 2024-10-23 | 115 kV Line T-172N approximately 1.38 mi from Farnum Pike and 1.09 mi from Putnam Pike Substations | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1323 | 2022-11-28 12:55 | ETU | 2022-10-11 | Non-controllable ETU from Line 3023 substation to Coopers Mills substation | NA | N/A |  |  |  |  | ME | 2027-12-31 | 2027-10-08 | 2022-11-02 | New substation on line 3023 (per QP1227 ) to Coopers Mills Substation, Windsor Kennebec, ME, 04363 | N/A | FALSE | FALSE |  | PD | ME
1322 | 2022-11-28 12:54 | ETU | 2022-10-11 | Non-controllable ETU from Line 388 substation to Coopers Mills substation | NA | N/A |  |  |  |  | ME | 2027-12-31 | 2027-10-08 | 2022-11-02 | New substation on line 388 (per QP1228 ) to Coopers Mills Substation, Windsor Kennebec, ME, 04363 | N/A | FALSE | FALSE |  | PD | ME
1321 | 2022-12-01 09:26 | TS | 2022-10-06 | NEP LNS | NA | N/A | 17.56 | 17.56 | 17.56 | Somerset | MA | 2024-12-01 | 2024-12-01 | 2022-11-30 | NEP 115 kV Brayton Point | N/A | FALSE | FALSE |  | PD | SEMA
1320 | 2025-01-03 13:22 | G | 2022-10-07 | Battery Storage | OT | BAT | 203.95 | 203.95 | 203.95 | Worcester | MA | 2027-11-16 | 2027-11-01 |  | National Grid 115KV Line R144 between Millbury No. 2 and Woonsocket substations - approximately 5.8 circuit miles from Woonsocket substation. | CNR | TRUE | TRUE |  | PD | SEMA |  | Document Posted |  |  | In Progress
1319 | 2025-01-03 13:22 | G | 2022-10-07 | Battery Storage | OT | BAT | 141.6 | 141.6 | 141.6 | Litchfield | CT | 2028-02-23 | 2028-01-04 |  | 115 kV line between Rocky River and Bulls Bridge substations | CNR | TRUE | TRUE |  |  | CT |  | Document Posted |  |  | In Progress
1318 | 2023-07-20 17:10 | TS | 2022-10-03 | GRID LNS | NA | N/A | 9 | 45 | 39 | Middlesex/Worcester | MA | 2023-10-03 | 2023-10-01 | 2023-07-03 | GRID 69 kV transmission lines U-21S and U-21E | N/A | FALSE | FALSE |  | PD | CMA
1317 | 2024-01-18 12:42 | ETU | 2022-09-30 | non-controllable objective ETU to enable 1200 MW injection near Norwalk substation | NA | N/A |  |  |  | Fairfield | CT | 2029-12-30 | 2029-05-01 | 2024-01-18 | N/A | N/A | FALSE | FALSE |  |  | SWCT | Document Posted | Not Started |  |  |  | Under Study
1316 | 2023-08-28 08:14 | G | 2022-09-30 | Solar plus Battery | OT | SUN BAT | 102 | 102 | 102 | Cheshire | NH | 2027-10-28 | 2027-10-28 | 2023-08-25 | Eversource 115kV line L163 | CNR | FALSE | FALSE |  |  | NH | In Progress |  |  |  |  | Under Study
1315 | 2024-10-02 13:00 | G | 2022-09-29 | Battery Storage | OT | BAT | 106.97 | 106.97 | 106.97 | Windham | CT | 2026-06-12 | 2026-06-09 | 2024-10-02 | Eversource Killingly Substation,115kV BUS, Tracy Rd, Killingly, CT 06241, 41.881384, -71.891162 | CNR | FALSE | FALSE |  | PD | CT | In Progress
1314 | 2024-10-15 09:45 | G | 2022-09-27 | Offshore Wind | WT | WND | 470 | 470 | 470 | NA | MA | 2029-11-01 | 2029-09-01 | 2024-10-14 | Eversource 115kV Acushnet, lines 112/114 | NR | FALSE | FALSE |  | PD | SEMA |  | Not Started |  |  |  | Under Study
1313 | 2022-09-26 13:28 | ETU | 2022-09-23 | NY ETU QP1125 | NA | N/A | 0 | 0 | 0 | St. Lawrence-Lewis | NY | 2025-12-31 | 2025-12-01 |  | Moses/Adirondack/Poter Path | N/A | FALSE | FALSE |  | PD | N/A
1312 | 2024-07-17 14:29 | ETU | 2022-09-26 | non-controllable ETU - inc the simultaneous injection capacity to 2400 MW at Brayton Pt 345 kV sub | NA | N/A |  |  |  | Somerset | MA | 2028-12-30 | 2028-09-29 |  | N/A | N/A | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1311 | 2024-10-01 12:23 | TS | 2022-09-23 | RNS - move load to new substation | NA | N/A | 20 | 85.32 | 50.6 | Plymouth | MA | 2026-07-01 | 2026-07-01 |  | Wareham Street to new South Middleborough Substation | N/A | TRUE | TRUE | ISO-NE | PD | SEMA
1310 | 2023-12-11 11:56 | G | 2022-09-23 | Battery Storage | OT | BAT | 118.75 | 118.75 | 118.75 | Berkshire | MA | 2025-10-31 | 2025-09-30 | 2023-12-08 | 115 kV Transmission line (1211 - Present between Doreen and Oswald substation) | CNR | FALSE | FALSE |  | PD | WMA | Document Posted | Not Started |  |  |  | Under Study
1309 | 2024-11-13 11:56 | ETU | 2022-09-23 | non-controllable objective ETU to enable 1200 MW injection near Millstone substation | NA | N/A | 1200 |  |  | New London | CT | 2029-12-30 | 2029-05-01 | 2024-11-12 | N/A | N/A | FALSE | FALSE |  | PD | CT | Document Posted | Not Started |  |  |  | Under Study
1308 | 2023-11-21 13:26 | G | 2022-09-09 | Uxbridge Substation – NG Hopedale West Group Study | OT | BAT | 6.994 | 6.994 | 6.994 | Worcester | MA | 2025-12-31 | 2025-11-15 |  | NG Feeder 321W6, Uxbridge T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
1307 | 2023-11-21 13:25 | G | 2022-09-09 | Whitins Pond Substation – NG Hopedale West Group Study | OT | BAT | 4.948 | 4.948 | 4.948 | Worcester | MA | 2025-12-31 | 2025-11-15 |  | NG Feeder 320W5, Whitins Pond T1 | NA | TRUE | FALSE | NGRID | PD | SEMA
1306 | 2023-11-21 13:25 | G | 2022-09-09 | Whitins Pond Substation – NG Hopedale West Group Study | OT | BAT | 4.948 | 4.948 | 4.948 | Worcester | MA | 2025-12-31 | 2025-11-15 |  | NG Feeder 320W4, Whitins Pond T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
1305 | 2023-11-21 13:24 | G | 2022-09-09 | Depot Street Substation – NG Hopedale West Group Study | OT | SUN BAT | 1.5 | 1.5 | 1.5 | Worcester | MA | 2025-12-31 | 2025-11-15 |  | NG Feeder 335W1 (7U), Depot Street T1 and T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
1304 | 2023-11-21 13:23 | G | 2022-09-09 | Uxbridge Substation – NG Hopedale West Group Study | OT | BAT | 4.99 | 4.99 | 4.99 | Worcester | MA | 2025-12-31 | 2025-11-15 |  | NG Feeder 321W6, Uxbridge T2 | NA | TRUE | FALSE | NGRID | PD | SEMA
1303 | 2023-05-25 13:22 | G | 2022-09-22 | Battery Storage | OT | BAT | 11.9 | 11.9 | 11.9 | Franklin | MA | 2027-05-28 | 2027-02-26 | 2023-05-25 | Eversource 21B8, 13.8 kV | CNR | FALSE | FALSE |  | PD | WMA
1302 | 2023-03-24 10:30 | G | 2022-09-22 | Battery Storage | OT | BAT | 9.11 | 8.5 | 8.5 | Franklin | MA | 2027-05-28 | 2027-02-26 | 2023-03-24 | Eversource 21C1, Montague Substation,13.8 kV | CNR | FALSE | FALSE |  | PD | WMA | Not Started |  |  |  |  | Under Study
1301 | 2022-12-09 19:22 | G | 2022-09-06 | Battery Storage | OT | BAT | 10 | 10 | 10 | Worcester | MA | 2025-05-15 | 2025-03-15 | 2022-12-09 | National Grid Feeder 01-21W1, Leicester Substation, 13.8 kV | CNR | FALSE | FALSE |  | PD | CMA
1300 | 2022-10-04 12:23 | G | 2022-08-19 | Solar plus Battery Increase (QP1129) | OT | SUN BAT | 0.04 | 2.5 | 2.5 | Bristol | MA | 2022-08-31 | 2021-08-31 | 2022-10-04 | The primary connection of the proposed project to Eversource Energy is located at the Wing Lane substation #624 Transformer #1 Line #240. The site is located approximately 0.26 circuit miles from Substation 624 near PSS/E node 111293(Wing Lane 13.2 KV) | CNR | FALSE | FALSE |  |  | SEMA
1299 | 2024-06-28 15:05 | G | 2022-08-18 | Solar Increase (QP1145) | PV | SUN | 54.1 | 74.8 | 74.8 | Hancock | ME | 2026-09-25 | 2026-09-11 |  | Versant 115kV Line 57 (new ring bus located 0.7 miles north of Versant's 115kV substation). | CNR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | In Progress
1298 | 2024-06-04 08:15 | G | 2022-08-16 | Battery Storage | OT | BAT | 157.92 | 157.92 | 157.92 | Worcester | MA | 2027-06-30 | 2027-06-15 | 2024-05-31 | Eversource 345 kV Line 3361, approximately 3.2 miles from Sherman Road and 7.6 miles from Blackstone. | CNR | FALSE | FALSE |  | PD | CMA | Document Posted | Not Started
1297 | 2022-09-13 13:59 | G | 2022-08-15 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2029-05-31 | 2029-01-31 | 2022-09-13 | National Grid Brayton Point 345 kV Substation | CNR | FALSE | FALSE |  | PD | SEMA
1296 | 2024-12-10 10:19 | G | 2022-08-10 | Battery Storage | OT | BAT | 125 | 125 | 125 | Hartford | CT | 2027-04-01 | 2027-03-15 | 2024-12-10 | Eversource Energy Corporation 115 kV line 1756 | CNR | TRUE | FALSE |  | PD | CT | Document Posted | Document Posted |  |  | Not Started
1295 | 2024-08-13 18:01 | G | 2022-08-09 | Solar plus Battery | OT | SUN BAT | 205 | 205 | 205 | Aroostook | ME | 2025-11-28 | 2025-09-03 | 2024-08-13 | Orrington-Albion Rd 345kV line (3023) near the town of Pittsfield (approximately 19 miles from Albion Rd Substation) | CNR | FALSE | FALSE |  | PD | ME
1294 | 2023-06-06 09:21 | G | 2022-07-27 | Solar | PV | SUN | 75.32 | 75.32 | 75.32 | Washington | ME | 2026-08-04 | 2026-07-21 | 2023-06-06 | Ring Bus constructed for QP760 on Versant 115kV Line 52 | CNR | FALSE | FALSE |  | PD | BHE | In Progress |  |  |  |  | Under Study
1293 | 2023-11-21 13:28 | TS | 2022-07-13 | GRID RNS | NA | N/A | 12 | 183.7 | 183.7 | Middlesex | MA | 2025-08-01 | 2025-08-01 |  | NGRID 115 kV T146 line | N/A | TRUE | TRUE | ISO-NE | PD | BOST
1292 | 2023-05-01 11:50 | G | 2022-07-12 | Battery Storage | OT | BAT | 95 | 95 | 95 | Worcester | MA | 2023-09-30 | 2023-08-30 | 2023-05-01 | National Grid 115 kV E-157W line three-breaker ring bus location: 0.32 miles north of Millbury 2 station along transmission line; 2.62 miles south of Wyman station along transmission line (the length of the Millbury 2 - Wyman Gordon line is 2.94 miles). Three-breaker ring bus will be located <0.01 miles east of POI. | CNR | FALSE | FALSE |  | PD | CMA | In Progress |  |  |  |  | Under Study
1291 | 2022-12-06 16:36 | G | 2022-06-09 | Turners Falls CNR | HD | WAT | 0 | 0.937 | 0.937 | Franklin | MA | 2022-11-15 | 2022-11-15 |  | The POI is at 13.8 kV where the conductors from WMECO's pole 70/460H1 attach to the Interconnection Customer's building on the other side of the canal. | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
1290 | 2023-03-30 14:18 | G | 2022-06-08 | Group @ Wing Lane 624 - EMA ASO | OT | SUN BAT | 14.979 | 14.979 | 14.979 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Wing Lane 624 | NA | FALSE | FALSE |  | PD | SEMA
1289 | 2023-03-30 14:17 | G | 2022-06-08 | Group @ West Pond 737 - EMA ASO | OT | SUN BAT | 6.982 | 6.982 | 6.982 | Middlesex | MA | 2023-11-30 | 2023-09-30 |  | Eversource West Pond 737 | NA | FALSE | FALSE |  | PD | SEMA
1288 | 2023-03-30 14:17 | G | 2022-06-08 | Wellfleet 976 - EMA ASO | OT | SUN BAT | 4.107 | 4.107 | 4.107 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Wellfleet 976 | NA | FALSE | FALSE |  | PD | SEMA
1287 | 2023-03-30 14:16 | G | 2022-06-08 | Valley 715 - EMA ASO | OT | SUN BAT | 3.7 | 3.7 | 3.7 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Valley 715 | NA | FALSE | FALSE |  | PD | SEMA
1286 | 2023-03-30 14:16 | G | 2022-06-08 | Tremont 713 - EMA ASO | OT | SUN BAT | 4.996 | 4.996 | 4.996 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Tremont 713 | NA | FALSE | FALSE |  | PD | SEMA
1285 | 2023-03-30 14:15 | G | 2022-06-08 | Sandwich 916 - EMA ASO | OT | SUN BAT | 4.6 | 4.6 | 4.6 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Sandwich 916 | NA | FALSE | FALSE |  | PD | SEMA
1284 | 2023-03-30 14:15 | G | 2022-06-08 | Group @ Orleans 975 - EMA ASO | OT | SUN BAT | 9.998 | 9.998 | 9.998 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Orleans 975 | NA | FALSE | FALSE |  | PD | SEMA
1283 | 2023-03-30 14:14 | G | 2022-06-08 | Mashpee 946 - EMA ASO | OT | SUN BAT | 1.49 | 1.49 | 1.49 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Mashpee 946 | NA | FALSE | FALSE |  | PD | SEMA
1282 | 2023-03-30 14:13 | G | 2022-06-08 | Marshfield 739 - EMA ASO | OT | SUN BAT | 4.6 | 4.6 | 4.6 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Marshfield 739 | NA | FALSE | FALSE |  | PD | SEMA
1281 | 2023-03-30 14:13 | G | 2022-06-08 | Group @ Industrial Park 636 - EMA ASO | OT | SUN BAT | 16.514 | 16.514 | 16.514 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Industrial Park 636 | NA | FALSE | FALSE |  | PD | SEMA
1280 | 2023-03-30 14:12 | G | 2022-06-08 | Hyannis 961 - EMA ASO | OT | SUN BAT | 4.993 | 4.993 | 4.993 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Hyannis 961 | NA | FALSE | FALSE |  | PD | SEMA
1279 | 2023-03-30 14:12 | G | 2022-06-08 | Group @ Hatchville 936 - EMA ASO | OT | SUN BAT | 18.486 | 18.486 | 18.486 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Hatchville 936 | NA | FALSE | FALSE |  | PD | SEMA
1278 | 2023-03-30 14:11 | G | 2022-06-08 | Harwich 968 - EMA ASO | OT | SUN BAT | 3.998 | 3.998 | 3.998 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Harwich 968 | NA | FALSE | FALSE |  | PD | SEMA
1277 | 2023-03-30 14:10 | G | 2022-06-08 | Fisher Road 657 - EMA ASO | OT | SUN BAT | 3 | 3 | 3 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Fisher Road 657 | NA | FALSE | FALSE |  | PD | SEMA
1276 | 2023-03-30 14:10 | G | 2022-06-08 | Falmouth 933 - EMA ASO | OT | SUN BAT | 3.5 | 3.5 | 3.5 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Falmouth 933 | NA | FALSE | FALSE |  | PD | SEMA
1275 | 2023-03-30 14:09 | G | 2022-06-08 | Group @ Duxbury 738 - EMA ASO | OT | SUN BAT | 6.782 | 6.782 | 6.782 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Duxbury 738 | NA | FALSE | FALSE |  | PD | SEMA
1274 | 2023-03-30 14:09 | G | 2022-06-08 | Crystal Spring 646 - EMA ASO | OT | SUN BAT | 1.7 | 1.7 | 1.7 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Crystal Spring 646 | NA | FALSE | FALSE |  | PD | SEMA
1273 | 2023-03-30 14:08 | G | 2022-06-08 | Canton 470 - EMA ASO | OT | SUN BAT | 4.999 | 4.999 | 4.999 | Norfolk | MA | 2023-11-30 | 2023-09-30 |  | Eversource Canton 470 | NA | FALSE | FALSE |  | PD | SEMA
1272 | 2025-01-03 13:24 | G | 2022-06-08 | West Springfield 45 MW BESS | OT | BAT | 45 | 45 | 45 | Hampden | MA | 2026-05-08 | 2025-12-01 |  | West Springfield Station, 115kV Bus (existing 8C-3X 140 MVA transformer; position WS#2). | CNR | TRUE | TRUE | ISO-NE | PD | WMA |  | Document Posted |  |  | Executed
1271 | 2022-09-01 09:33 | ETU | 2022-06-07 | Non-Controllable ETU - Pittsfield to Coopers Mills flow only | NA | N/A |  |  |  | Somerset/Lincoln | ME | 2027-12-01 | 2027-10-01 |  | New Pittsfield substation (per QP1230) Pittsfield Somerset ME 04967 Coopers Mills substation Windsor Kennebec ME 04363 | N/A | FALSE | FALSE |  | PD | ME
1270 | 2023-07-24 13:32 | G | 2022-05-31 | Nutmeg Solar CNR Only | PV | SUN | 0 | 19.9 | 19.9 | Hartford | CT | 2020-12-07 | 2020-11-15 |  | Scitico 115 kV | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed | In Service
1269 | 2023-08-10 15:06 | G | 2022-05-27 | Sanford Airport Solar CNR Only | PV | SUN | 0 | 50 | 50 | York | ME | 2023-08-02 | 2023-08-02 |  | Cyro Drive substation 115 kV | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
1268 | 2022-12-07 10:53 | G | 2022-05-24 | Coolidge Solar CNR Only | PV | SUN | 0 | 19.9 | 19.9 | Windsor | VT | 2018-12-20 | 2018-12-12 |  | 115 kV Coolidge Substation | CNR | FALSE | FALSE |  |  | VT |  |  |  |  | Executed
1267 | 2022-06-27 09:23 | G | 2022-05-20 | Battery Storage | OT | BAT | 51.73 | 51.73 | 51.73 | New London | CT | 2025-08-08 | 2025-07-25 | 2022-06-24 | Groton Utilities Buddington Substation, 69kV bus (future 115kV) Alternate POI: Groton Utilities Buddington Substation, 34.5kV bus | CNR | FALSE | FALSE |  | PD | CT
1266 | 2024-09-04 09:58 | G | 2022-05-23 | Battery Storage | OT | BAT | 100 | 100 | 100 | Hartford | CT | 2025-08-04 | 2025-07-03 | 2024-08-28 | 115kV Manchester Substation (Bus# 120074) Geographic coordinates: 41.76948781166102, -72.56130136574556 | CNR | FALSE | FALSE |  | PD | CT |  | Document Posted |  |  | Not Started
1265 | 2023-05-10 12:16 | G | 2022-05-23 | Revolution Offshore Wind CNR only | WT | WND | 0 | 750.75 | 750.75 | NA | RI | 2025-09-07 | 2025-09-07 |  | NG 115 kV Davisville Substation, Washington County | CNR | FALSE | FALSE |  |  | RI |  |  |  |  | Executed
1264 | 2023-01-12 13:58 | G | 2022-05-19 | Bear Swamp Pump Load increase | PS | WAT | 0 | 333 | 333 | Berkshire | MA | 2023-01-06 | 2023-01-04 |  | The existing POI of the Bear Swamp generating station. | NR | TRUE | FALSE | ISO-NE | PD | WMA |  | Document Posted |  |  | Executed
1263 | 2023-07-13 09:56 | G | 2022-07-01 | Battery Storage | OT | BAT | 18.87 |  |  | Hampshire | MA | 2023-10-27 | 2023-10-20 | 2023-07-13 | POI Coordinates: 42.42649, -72.53956, Feeder: 18G6, Express feeder, Owner of POI: WMECO (Eversource), Distribution Voltage Level: 13.8 kV, Substation Voltage Level: 115 kV - 13.8 kV | CNR | FALSE | FALSE |  | PD | WMA | In Progress |  |  |  |  | Under Study
1262 | 2024-08-29 16:57 | G | 2022-05-17 | Battery Storage | OT | BAT | 80.875 | 80.875 | 80.875 | Middlesex | CT | 2026-07-06 | 2026-06-18 | 2024-08-29 | Haddam 115kV BUS [HADDAM(120632)]; 41°27'38.74"N, 72°28'38.23"W | CNR | TRUE | FALSE |  | PD | CT | Document Posted | Document Posted |  |  | Not Started
1261 | 2024-08-12 12:41 | G | 2022-05-17 | Battery Storage Addition (to QP1086) | OT | SUN BAT | 0 | 160 | 160 | Knox | ME | 2026-11-30 | 2026-10-31 |  | CMP 115kV line Section 80 | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
1260 | 2022-08-31 09:26 | G | 2022-05-06 | Solar plus Battery | OT | SUN BAT | 2.772 | 2.6888 | 2.6888 | Hampden | MA | 2023-06-01 | 2023-06-01 | 2022-08-31 | Eversource 13.8 kV Line 19S1 | CNR | FALSE | FALSE |  |  | WMA
1259 | 2024-08-02 15:25 | G | 2022-06-15 | Battery Storage | OT | BAT | 20 | 20 | 20 | Berkshire | MA | 2027-06-28 | 2027-03-28 |  | Eversource 115 kV Line 1231 (Berkshire - Plainfield) | CNR | TRUE | FALSE | ISO-NE |  | WMA |  | Document Posted |  |  | Not Started
1258 | 2024-01-25 15:53 | G | 2022-05-03 | Battery Storage CNR Only | OT | BAT | 0 | 170 | 170 | Norfolk | MA | 2027-07-26 | 2027-06-26 |  | National Grid's South Wrentham 115kV Substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
1257 | 2022-05-03 16:13 | G | 2022-05-03 | Solar | PV | SUN | 319.2 | 319.2 | 319.2 | Aroostook | ME | 2026-12-09 | 2026-10-08 |  | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
1256 | 2022-05-03 16:12 | G | 2022-05-03 | Wind | WT | WND | 905 | 905 | 905 | Aroostook | ME | 2026-12-09 | 2026-10-08 |  | Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line (3023) near town of Pittsfield. | CNR | FALSE | FALSE |  | PD | BHE
1255 | 2025-01-08 09:33 | G | 2022-05-02 | Detroit/Guilford/Belfast DG Area Study | OT | SUN BAT | 59.72 | 59.72 | 59.72 | Piscataquis/Penobscot/Somerset/Waldo/Hancock | ME | 2027-12-31 | 2027-12-31 |  | CMP Detroit 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1254 | 2024-06-11 12:39 | G | 2022-05-02 | Kimball DG Area Study | OT | SUN BAT | 24.546 | 24.546 | 24.546 | York/Oxford/Cumberland | ME | 2028-06-30 | 2028-06-30 |  | CMP Kimball Road/Lovell 115 kV Substation | NA | TRUE | TRUE | CMP | PD | ME
1253 | 2023-11-14 16:22 | G | 2022-04-27 | Battery Storage CNR Only (see QP887) | OT | BAT | 0 | 150 | 150 | Norfolk | MA | 2026-05-31 | 2026-04-30 | 2023-11-14 | Wareham Substation 115kV, Eversource Line 113 | CNR | FALSE | FALSE |  |  | SEMA
1252 | 2024-10-01 14:11 | G | 2022-04-21 | Battery Storage | OT | BAT | 314.7 | 314.7 | 314.7 | Essex | MA | 2026-06-01 | 2026-02-15 |  | Ward Hill 345 kV Substation | CNR | TRUE | TRUE |  | PD | BOST | Document Posted | Document Posted | Not Required | Not Required | Not Started
1251 | 2022-08-26 10:43 | G | 2022-04-11 | Battery Storage | OT | BAT | 60 | 60 | 60 | Hartford | CT | 2024-12-31 | 2024-10-15 | 2022-08-26 | To interconnect at the POI of Gravel Pit Solar QP 1030, via a Shared Facility, QP 1030 is described as a line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
1250 | 2023-05-19 09:10 | G | 2022-04-14 | Battery Storage | OT | BAT | 50.7 | 50.7 | 50.7 | York | ME | 2024-11-01 | 2024-09-01 | 2023-05-18 | CMP Goosefare 115kV Substation 43 31 22 N 70 26 59 W | CNR | FALSE | FALSE |  |  | ME | Not Started |  |  |  |  | Under Study
1249 | 2023-03-28 10:14 | G | 2022-04-19 | Battery Storage Addition | OT | BAT | 0 | 16.02 | 16.02 | New London | CT | 2027-05-14 | 2027-03-12 | 2023-03-28 | Tunnel 23 kV Substation | CNR | FALSE | FALSE |  |  | CT | Document Posted | Not Started |  |  |  | Under Study
1248 | 2023-02-23 12:17 | G | 2022-04-06 | Battery Storage | OT | BAT | 154.656 | 154.656 | 154.656 | Bristol | MA | 2026-05-31 | 2026-03-01 |  | NGRID 115kV Robinson Ave substation | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1247 | 2025-01-06 11:30 | G | 2022-04-05 | Solar | PV | SUN | 25 | 25 | 25 | Hartford | CT | 2025-11-01 | 2025-10-01 |  | To interconnect at the POI of Gravel Pit Solar QP 1030, via a Shared Facility, QP 1030 is described as a line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress
1246 | 2023-07-25 15:47 | G | 2022-03-31 | Solar | PV | SUN | 150 | 150 | 150 | Grafton | NH | 2025-11-01 | 2025-10-01 | 2023-07-25 | 230 kV Comerford to North Litchfield A201Line; alternative POI is B-202. | NR | FALSE | FALSE |  | PD | NH | In Progress |  |  |  |  | Under Study
1245 | 2024-10-01 14:11 | G | 2022-03-31 | Solar | PV | SUN | 150 | 150 | 150 | Hartford | CT | 2028-11-01 | 2028-10-01 |  | 345kV Line 3419 Tap between Meekville Junction/Barbour Hill (PSSE Bus Number: 119103) To LudlowPSSE Bus Number: 116045) | NR | TRUE | TRUE |  | PD | CT | Document Posted | Document Posted |  |  | In Progress
1244 | 2023-01-10 16:36 | G | 2022-03-31 | Solar | PV | SUN | 75 | 75 | 75 | Franklin | ME | 2025-11-01 | 2025-10-01 | 2022-11-14 | 115 kV New Sturtevant Substation (PSSE Bus Number: 100116) | NR | FALSE | FALSE |  | PD | ME | In Progress |  |  |  |  | Under Study
1243 | 2022-03-31 17:37 | G | 2022-03-31 | Solar | PV | SUN | 300 | 300 | 300 | Aroostook | ME | 2026-11-01 | 2026-10-01 |  | 345kV line between Orrington(PSSE Bus Number: 100002) -Albion Rd (PSSE Bus Number: 100092) near the town of Pittsfield | NR | FALSE | FALSE |  | PD | ME
1242 | 2025-01-08 14:35 | G | 2022-03-28 | Lewiston CMP Cluster 5 | OT | SUN BAT | 52.464 | 52.464 | 52.464 | Oxford/Androscoggin | ME | 2028-06-30 | 2028-06-30 |  | CMP Lewiston | NA | TRUE | TRUE | CMP | PD | ME
1241 | 2025-01-08 14:34 | G | 2022-03-28 | Sanford/Quaker Hill CMP Cluster 4 | OT | SUN BAT | 21.184 | 21.184 | 21.184 | York | ME | 2028-06-30 | 2026-06-30 |  | CMP Sandford/Quaker Hill | NA | TRUE | TRUE | CMP | PD | ME
1240 | 2024-10-27 17:03 | G | 2022-03-25 | Battery Storage | OT | BAT | 62.84 | 62.84 | 62.84 | Kent | RI | 2025-12-31 | 2025-12-15 | 2024-10-23 | National Grid Kent County Substation - 115kV open line position between 4T3T and 3T10 breakers. | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1239 | 2024-10-16 10:28 | G | 2022-03-25 | Solar plus Battery | OT | SUN BAT | 129 | 183.6 | 183.6 | Oxford | ME | 2026-04-21 | 2026-04-07 |  | CMP 115kV Woodstock S/S | CNR | TRUE | FALSE |  | PD | ME | Document Posted | Document Posted |  |  | In Progress
1238 | 2023-06-08 16:28 | G | 2022-03-22 | Battery Storage | OT | BAT | 301.26 | 301.26 | 301.26 | Norfolk | MA | 2026-11-23 | 2026-06-15 |  | Primary: West Medway 345kV station | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | In Progress |  |  |  | Under Study
1237 | 2022-08-31 12:41 | G | 2022-03-21 | Battery Storage CNR only | OT | BAT | 0 | 205 | 205 | Washinton | RI | 2026-06-01 | 2026-06-01 |  | Primary - NEP L190-2, Alt NEP G185S | CNR | FALSE | FALSE |  |  | RI
1236 | 2022-05-23 16:15 | ETU | 2022-03-15 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Aroostook/Somerset | ME | 2028-06-01 | 2028-06-01 |  | Transmission Line connects between the new Aroostook station and Pittsfield Station. Pittsfield 345 kV substation is located between the existing Orrington - Albion Road line in Somerset County at lat/long 44.795/-69.386. The Aroostook station will be located in Aroostook county at lat/long 45.7634/-68.0278. | N/A | FALSE | FALSE |  | PD | ME
1235 | 2022-08-12 08:54 | G | 2022-03-14 | Battery Storage | OT | BAT | 20 | 20 | 20 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2022-08-11 | Eversource's Cross Road 13.2kV Circuit 532 | CNR | FALSE | FALSE |  | PD | SEMA
1234 | 2022-08-12 08:53 | G | 2022-03-14 | Battery Storage | OT | BAT | 20 | 20 | 20 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2022-08-11 | Eversource's Cross Road 13.2kV Circuit 533 | CNR | FALSE | FALSE |  | PD | SEMA
1233 | 2022-08-12 08:53 | G | 2022-03-14 | Battery Storage | OT | BAT | 20 | 20 | 20 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2022-08-11 | Eversource's Cross Road 13.2kV Circuit 541 | CNR | FALSE | FALSE |  | PD | SEMA
1232 | 2024-10-27 17:03 | G | 2022-03-04 | Battery Storage | OT | BAT | 27.44 | 27.44 | 27.44 | Providence | RI | 2025-12-31 | 2025-12-15 | 2024-10-23 | NEC 115/34.5kV Iron Mine Hill Substation #1203 spare buss position #2 | CNR | FALSE | FALSE |  | PD | RI |  | Not Started |  |  |  | Under Study
1231 | 2022-04-22 13:35 | G | 2022-03-04 | Battery Storage CNR Only | OT | BAT | 0 | 204.64 | 204.64 | Windham | CT | 2025-05-01 | 2025-02-15 | 2022-04-22 | Eversource Killingly 345kV Substation | CNR | FALSE | FALSE |  |  | CT
1230 | 2022-03-04 14:13 | ETU | 2022-03-03 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Somerset/Aroostook | ME | 2027-12-01 | 2027-10-01 |  | The Point of Interconnection will be a new station about 30 miles from Orrington that taps the existing segment 3023 between Orrington and Albion Rd. Hammond, ME to Pittsfield ME (see map) | N/A | FALSE | FALSE |  | PD | ME
1229 | 2022-09-14 10:55 | G | 2022-02-22 | Solar plus Battery | OT | SUN BAT | 3 | 3 | 3 | Hampshire | MA | 2022-12-31 | 2022-09-30 | 2022-09-14 | Eversource 13.8kV Circuit 18G4 | CNR | FALSE | FALSE |  |  | WMA |  | In Progress |  |  |  | Under Study
1228 | 2024-09-04 16:32 | ETU | 2022-02-16 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Hancock/Aroostook | ME | 2026-12-09 | 2026-10-08 | 2024-09-04 | New substation on Line 388 | N/A | FALSE | FALSE |  | PD | ME
1227 | 2024-09-04 16:32 | ETU | 2022-02-16 | 1200 MW non-controllable ETU - N to S flow only | NA | N/A | 1200 |  |  | Somerset/Aroostook | ME | 2026-12-09 | 2026-10-08 | 2024-09-04 | New substation on Line 3023 near the Detroit Substation near Pittsfield, Maine. | N/A | FALSE | FALSE |  | PD | ME
1226 | 2025-01-22 13:59 | G | 2022-03-04 | Grissom Solar | PV | SUN | 4.99 | 4.99 | 4.99 | Sullivan | NH | 2025-05-15 | 2025-05-01 |  | 46 kV subtransmission line between GMP Maple Avenue B-42 and the 4402 breaker at the GMP/NGRID demarc considered at Bellows Falls | NR | TRUE | FALSE | ISO-NE | NA | NH |  | Document Posted |  |  | Executed
1225 | 2024-01-02 11:28 | G | 2022-02-03 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2029-01-31 | 2028-09-30 |  | Bourne 345 kV Switching Station | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
1224 | 2022-09-14 10:54 | G | 2022-01-25 | Solar plus Battery | OT | SUN BAT | 1 | 1 | 1 | Worcester | MA | 2022-04-29 | 2022-04-29 | 2022-09-14 | National Grid MA 13.8 kV, Whitins Pond 320W5 | CNR | FALSE | FALSE |  |  | CMA |  |  |  |  | In Progress
1223 | 2022-03-15 15:52 | G | 2022-01-18 | Battery Storage | OT | BAT | 9.99 | 9.99 | 9.992 | Worcester | MA | 2022-04-29 | 2022-03-31 | 2022-03-15 | ZP Battery DevCo, LLC, 13.2kV, National Grid Feeder #413L3 | CNR | FALSE | FALSE |  |  | CMA
1222 | 2023-03-30 13:42 | G | 2022-01-14 | Group @ Berkshire 18C | OT | SUN BAT | 7.65 | 7.65 | 7.65 | Hampden | MA | 2023-11-30 | 2023-09-30 |  | Eversource Berkshire 18C | NA | FALSE | FALSE |  | PD | WMA
1221 | 2023-03-30 13:38 | G | 2022-01-14 | Cumberland 22B - WMA ASO | OT | SUN BAT | 4.99 | 4.99 | 4.99 | Hampden | MA | 2023-11-30 | 2023-09-30 |  | Eversource Cumberland 22B | NA | FALSE | FALSE |  | PD | WMA
1220 | 2023-03-30 13:36 | G | 2022-01-14 | Group @ Blandford 19J - WMA ASO | OT | SUN BAT | 6.99 | 6.99 | 6.99 | Berkshire | MA | 2023-11-30 | 2023-09-30 |  | Eversource Blandford 19J | NA | FALSE | FALSE |  | PD | WMA
1219 | 2023-03-30 13:32 | G | 2022-01-14 | Group @ French King - WMA ASO | OT | SUN BAT | 8.9 | 8.9 | 8.9 | Franklin/Hampshire | MA | 2023-11-30 | 2023-09-30 |  | Eversource French King | NA | FALSE | FALSE |  | PD | WMA
1218 | 2023-05-31 09:30 | G | 2022-01-14 | Group @ Montigue - WMA ASO | OT | SUN BAT | 9.86 | 9.86 | 9.86 | Franklin | MA | 2023-11-30 | 2023-09-30 |  | Eversource Montigue | NA | TRUE | TRUE | NU | PD | WMA
1217 | 2023-03-30 13:30 | G | 2022-01-14 | Oswald - WMA ASO | OT | SUN BAT | 2.49 | 2.49 | 2.49 | Franklin | MA | 2023-11-30 | 2023-09-30 |  | Eversource Oswald | NA | FALSE | FALSE |  | PD | WMA
1216 | 2023-03-30 13:29 | G | 2022-01-14 | Group @ Podick - WMA ASO | OT | SUN BAT | 7.7 | 7.7 | 7.7 | Hampden/Franklin | MA | 2023-11-30 | 2023-09-30 |  | Eversource Podick | NA | FALSE | FALSE |  | PD | WMA
1215 | 2023-03-30 13:29 | G | 2022-01-14 | Group @ Maynard 416 - EMA ASO | OT | SUN BAT | 8.476 | 8.476 | 8.476 | Middlesex | MA | 2023-11-30 | 2023-09-30 |  | Eversource Maynard 416 | NA | TRUE | FALSE | NU | PD | BOST
1214 | 2023-03-30 13:28 | G | 2022-01-14 | Group @ Medway 65 - EMA ASO | OT | SUN BAT | 17.497 | 17.497 | 17.497 | Middlesex/Norfolk | MA | 2023-11-30 | 2023-09-30 |  | Eversource Medway 65 | NA | TRUE | FALSE | NU | PD | BOST
1213 | 2023-03-30 13:27 | G | 2022-01-14 | Holliston 130 - EMA ASO | OT | BAT | 4.99 | 4.99 | 4.99 | Middlesex | MA | 2023-11-30 | 2023-09-30 |  | Eversource Holliston 130 | NA | TRUE | FALSE | NU | PD | BOST
1212 | 2024-01-26 11:10 | G | 2022-01-14 | Hopkinton 126 - EMA ASO | OT | SUN BAT | 3.9 | 3.9 | 3.9 | Middlesex | MA | 2023-11-30 | 2023-09-30 | 2024-01-25 | Eversource Hopkinton 126 | NA | TRUE | FALSE | NU | PD | BOST
1211 | 2022-12-13 13:30 | G | 2022-01-10 | Wind | WT | WND | 500 | 527 | 527 | Aroostook | ME | 2026-11-27 | 2026-09-03 |  | Orrington-Albion Rd 345kV line (3023) near the town of Pittsfield (approximately 19 miles from Albion Rd Substation) | CNR | FALSE | FALSE |  | PD | ME
1210 | 2022-12-13 13:29 | G | 2022-01-07 | Wind | WT | WND | 500 | 572 | 572 | Aroostook | ME | 2025-11-28 | 2025-09-03 |  | Orrington-Albion Rd 345kV line (3023) near the town of Pittsfield (approximately 19 miles from Albion Rd Substation) | CNR | FALSE | FALSE |  | PD | ME
1209 | 2022-03-08 12:42 | G | 2021-12-30 | Battery Storage | OT | BAT | 170 | 170 | 170 | Providence | RI | 2024-12-31 | 2024-12-01 | 2022-03-08 | RI_NGRID Hartford 115kV substation/ Bus ID: 117351 | NR | FALSE | FALSE |  | PD | RI
1208 | 2022-03-08 12:57 | G | 2021-12-30 | Battery Storage | OT | BAT | 160 | 160 | 160 | New Haven | CT | 2024-12-31 | 2024-12-01 | 2022-03-08 | CT_UI June Street 115KV substation/ Bus ID: 123416 | NR | FALSE | FALSE |  | PD | CT
1207 | 2022-01-28 07:47 | G | 2021-12-30 | Battery Storage | OT | BAT | 200 | 200 | 200 | Barnstable | MA | 2024-12-31 | 2024-12-01 | 2022-01-28 | MA_NSTAR_CE Canal 115KV substation | NR | FALSE | FALSE |  | PD | SEMA
1206 | 2022-03-08 12:44 | G | 2021-12-30 | Battery Storage | OT | BAT | 200 | 200 | 200 | Berkshire | MA | 2024-12-31 | 2024-12-01 | 2022-03-08 | MA_NGRID Adams 115kV substation Bus ID: 113005 | NR | FALSE | FALSE |  | PD | WMA
1205 | 2022-10-31 12:24 | G | 2021-12-30 | Hamilton Sunstrand | OT | SUN | 2 | 2 | 2 | Hartford | CT | 2023-04-01 | 2023-04-01 |  | Windsor Locks 14K | NA | TRUE | TRUE | NU |  | CT
1204 | 2023-03-09 15:06 | G | 2021-12-28 | LSE Scorpuis | OT | SUN | 1.82 | 1.82 | 1.82 | Putnam | CT | 2023-12-31 | 2023-10-31 |  | Tracy 14M | NA | TRUE | TRUE | NU |  | CT
1203 | 2022-01-04 14:40 | G | 2021-12-28 | CTEC Solar 186 Foster St, South Windsor | OT | SUN | 1.875 | 1.875 | 1.875 | Hartford | CT | 2023-07-01 | 2023-07-01 |  | Barbour Hill 23J | NA | FALSE | FALSE |  |  | CT
1202 | 2022-01-03 08:22 | G | 2021-12-28 | Community Power Group, 24 Middle Road, Ellington, CT | OT | SUN | 4 | 4 | 4 | Tolland | CT | 2023-07-01 | 2023-07-01 |  | Rockville 14W | NA | FALSE | FALSE |  |  | CT
1201 | 2022-01-03 08:21 | G | 2021-12-28 | Verogy - Tripp RD | OT | SUN | 2 | 2 | 2 | Hartford | CT | 2023-07-01 | 2023-07-01 |  | Rockville 14W | NA | FALSE | FALSE |  |  | CT
1200 | 2022-01-03 08:21 | G | 2021-12-28 | Verogy - Thrall Rd, East Windsor | OT | SUN | 4 | 4 | 4 | Hartford | CT | 2023-07-01 | 2023-07-01 |  | Rockville 14W or Barbour Hill 23J | NA | FALSE | FALSE |  |  | CT
1199 | 2022-01-03 08:20 | G | 2021-12-28 | USS Vineyard Solar, Somers Rd | PV | SUN | 4 | 4 | 4 | Tolland | CT | 2022-09-30 | 2022-09-30 |  | Scitico 27H | NA | FALSE | FALSE |  | PD | CT
1198 | 2023-02-23 12:01 | G | 2021-12-30 | Storage | OT | BAT | 241.8 | 241.8 | 241.8 | Bristol | MA | 2028-05-12 | 2028-02-14 |  | Looping the D-182S line adjacent to National Grid’s 115 kV Reynold’s Ave Substation | CNR | FALSE | FALSE |  |  | RI | Document Posted | Not Started |  |  |  | Under Study
1197 | 2023-03-30 18:48 | G | 2021-12-20 | Battery Storage | OT | BAT | 150 | 150 | 150 | Bristol | MA | 2027-12-31 | 2027-10-28 |  | Eversource 115kV Cross Road Line 111 | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
1196 | 2022-03-08 13:31 | G | 2021-12-14 | Energy Storage | OT | BAT | 99.9 | 99.9 | 99.9 | Hampden | MA | 2024-10-01 | 2024-08-01 | 2022-03-08 | National Grid Hampden Substation, 115 kV. Secondary is 115 kV Line 1976. | CNR | FALSE | FALSE |  | PD | WMA
1195 | 2024-09-30 16:22 | TS | 2021-11-23 | Regional Network Service | NA | N/A | 6.3 | 6.3 | 6.3 | Middlesex | MA | 2024-11-15 | 2024-10-07 |  | NSTAR 115 kV Line 875-539 | N/A | TRUE | FALSE | ISO-NE |  | BOST
1194 | 2021-12-06 15:07 | G | 2021-11-09 | Bear Swamp Pumping Load Increase | PS | WAT | 0 | 333 | 333 | Berkshire | MA | 2021-11-09 | 2021-11-09 |  | The existing POI of the Bear Swamp generating station | NR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
1193 | 2025-01-10 10:04 | G | 2021-11-09 | Battery Storage | OT | BAT | 325 | 325 | 325 | Windham | CT | 2026-01-01 | 2025-01-08 |  | CL&P 345 kV 3271 Line | CNR | TRUE | TRUE |  | PD | CT | Document Posted | Document Posted |  |  | In Progress
1192 | 2024-05-29 10:09 | G | 2021-11-04 | Solar | PV | SUN | 101.128 | 101.128 | 101.128 | Hartford | CT | 2027-10-15 | 2027-09-24 |  | N. Bloomfield to Agawam 345kV Line. POI is approximately 3.6 mi north of N. Bloomfield (345kV) and 11.5 mi south of Agawam (345kV). | CNR | TRUE | TRUE | ISO-NE |  | CT | Document Posted | Document Posted |  |  | In Progress
1191 | 2021-11-09 13:11 | G | 2021-11-03 | Increase to Pumping load | PS | WAT | 0 | 333 | 333 | Berkshire | MA | 2021-11-03 | 2021-11-03 | 2021-11-09 | The current Bear Swamp interconnection points | NR | FALSE | FALSE |  |  | WMA
1190 | 2024-08-12 12:42 | G | 2021-10-28 | Solar Knox | PV | SUN | 33.5 | 33.5 | 33.5 | Knox | ME | 2027-03-31 | 2027-02-28 |  | CMP 115kV Line 80 | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
1189 | 2023-03-30 17:02 | G | 2021-10-27 | Wendall Depot Substation - NG WMA Group 3 | OT | SUN BAT | 27.981 | 27.981 | 27.981 | Franklin | MA | 2027-12-31 | 2027-12-31 |  | NG Wendall Depot Substation | NA | FALSE | FALSE |  | PD | WMA
1188 | 2023-03-30 17:01 | G | 2021-10-27 | Ware Substation - NG WMA Group 3 | OT | SUN BAT | 11 | 11 | 11 | Hampshire | MA | 2027-12-31 | 2027-12-31 |  | NG Ware Substation | NA | FALSE | FALSE |  | PD | WMA
1187 | 2023-03-30 17:01 | G | 2021-10-27 | W. Charlton Substation - NG WMA Group 3 | OT | BAT | 19.984 | 19.984 | 19.984 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG W. Charlton Substation | NA | FALSE | FALSE |  | PD | WMA
1186 | 2023-03-30 17:00 | G | 2021-10-27 | Treasure Valley Substation - NG WMA Group 3 | OT | BAT | 9.992 | 9.992 | 9.992 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG treasure Valley Substation | NA | FALSE | FALSE |  | PD | WMA
1185 | 2023-03-30 17:00 | G | 2021-10-27 | Stafford St. Substation - NG WMA Group 3 | OT | SUN BAT | 22.448 | 22.448 | 22.448 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Stafford St. Substation | NA | FALSE | FALSE |  | PD | WMA
1184 | 2023-03-30 16:59 | G | 2021-10-27 | Snow St. Substation - NG WMA Group 3 | OT | SUN BAT | 27.836 | 27.836 | 27.836 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Snow St. Substation | NA | FALSE | FALSE |  | PD | WMA
1183 | 2023-03-30 16:59 | G | 2021-10-27 | Royalston Substation - NG WMA Group 3 | OT | SUN BAT | 5 | 5 | 5 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Royalston Substation | NA | FALSE | FALSE |  | PD | WMA
1182 | 2023-03-30 16:58 | G | 2021-10-27 | Pratts Junc. Substation - NG WMA Group 3 | OT | BAT | 14.94 | 14.94 | 14.94 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Pratts Junc. Substation | NA | FALSE | FALSE |  | PD | WMA
1181 | 2023-03-30 16:58 | G | 2021-10-27 | N. Oxford Substation - NG WMA Group 3 | OT | SUN BAT | 20.396 | 20.396 | 20.396 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG N. Oxford Substation | NA | FALSE | FALSE |  | PD | WMA
1180 | 2023-03-30 16:57 | G | 2021-10-27 | Millbury Substation - NG WMA Group 3 | OT | SUN BAT | 11.742 | 11.742 | 11.742 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Millbury Substation | NA | FALSE | FALSE |  | PD | WMA
1179 | 2023-03-30 16:57 | G | 2021-10-27 | Meadow Street 552 Substation - NG WMA Group 3 | OT | SUN BAT | 13.799 | 13.799 | 13.799 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Meadow Street 552 Substation | NA | FALSE | FALSE |  | PD | WMA
1178 | 2023-03-30 16:56 | G | 2021-10-27 | Little Rest Rd Substation - NG WMA Group 3 | OT | SUN BAT | 5.8 | 5.8 | 5.8 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Little Rest Rd Substation | NA | FALSE | FALSE |  | PD | WMA
1177 | 2023-03-30 16:56 | G | 2021-10-27 | Lashaway Substation - NG WMA Group 3 | OT | BAT | 14.94 | 14.94 | 14.94 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Lashaway Substation | NA | FALSE | FALSE |  | PD | WMA
1176 | 2023-03-30 16:55 | G | 2021-10-27 | E. Winchendon Substation - NG WMA Group 3 | OT | SUN BAT | 34.975 | 34.975 | 34.975 | Worcester | MA | 2026-12-31 | 2026-12-31 |  | NG E. Winchendon Substation | NA | FALSE | FALSE |  | PD | WMA
1175 | 2023-03-30 16:54 | G | 2021-10-27 | E. Westminster Substation - NG WMA Group 3 | OT | SUN BAT | 4.99 | 4.99 | 4.99 | Worcester | MA | 2026-12-31 | 2026-12-31 |  | NG E. Westminster Substation | NA | FALSE | FALSE |  | PD | WMA
1174 | 2023-03-30 16:54 | G | 2021-10-27 | Crystal Lake Substation - NG WMA Group 3 | OT | BAT | 7.998 | 7.998 | 7.998 | Worcester | MA | 2026-12-31 | 2026-12-31 |  | NG Crystal Lake Substation | NA | FALSE | FALSE |  | PD | WMA
1173 | 2023-03-30 16:53 | G | 2021-10-27 | Barre Substation - NG WMA Group 3 | OT | SUN BAT | 12.398 | 12.398 | 12.398 | Worcester | MA | 2027-12-31 | 2027-12-31 |  | NG Barre Substation | NA | FALSE | FALSE |  | PD | WMA
1172 | 2024-10-02 14:39 | G | 2021-10-27 | Solar plus Battery | OT | SUN BAT | 53.07 | 53.07 | 53.07 | Merrimack | NH | 2025-07-31 | 2025-05-31 | 2024-10-02 | Eversource 115kV F139 line | CNR | TRUE | FALSE |  |  | NH | Document Posted | Document Posted |  |  | Not Started
1171 | 2024-10-30 13:39 | G | 2021-10-25 | Twin Energy Wind | WT | WND | 18.3 | 20 | 20 | Oxford | ME | 2025-10-17 | 2025-09-18 |  | Roxbury Substation | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
1170 | 2023-10-11 14:38 | G | 2021-10-22 | Battery Storage | OT | BAT | 100 | 100 | 100 | Franklin | MA | 2023-01-11 | 2022-12-14 | 2023-10-11 | National Grid's PTF (115kV Y-177 line), located at 42.730250 degrees north latitude, -72.931858 degrees west longitude. | CNR | FALSE | FALSE |  | PD | WMA | Document Posted |  |  |  |  | Under Study
1169 | 2023-10-11 10:23 | G | 2021-10-22 | Roxbury Solar | PV | SUN | 1.999 | 1.999 | 1.999 | Oxford | ME | 2025-02-07 | 2025-01-10 |  | CMP 12.47 kV distribution circuit 447D1 out of CMP Rumford Substation | NR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed
1168 | 2022-10-31 12:22 | G | 2021-10-04 | Fuel Cell | FC | NG | 8.7 | 8.7 | 8.7 | Hartford | CT | 2023-10-15 | 2023-10-01 |  | Eversource Northwest Hartford 2N substation circuit 2N17 | NA | TRUE | TRUE | NU | PD | CT
1167 | 2023-01-31 10:35 | G | 2021-10-04 | Solar | PV | SUN | 4 | 4 | 4 | Windham | CT | 2023-01-31 | 2022-12-31 | 2023-01-30 | Eversource Tracy 14M substation circuit 14M9 | NA | TRUE | TRUE | NU | PD | CT
1166 | 2023-01-31 10:34 | G | 2021-10-04 | Battery Storage | OT | BAT | 20 | 20 | 20 | New Haven | CT | 2024-09-01 | 2024-08-01 |  | Eversource Oxford 26N Substation | NA | FALSE | FALSE |  | PD | CT
1165 | 2024-03-06 11:46 | G | 2021-10-22 | Solar | PV | SUN | 1.999 |  |  | Hancock | ME | 2023-07-15 | 2023-07-15 |  | 34.5kV Line on Bar Harbor Road. The 34.5 kV line from Ellsworth to Trenton is not explicitly modeled in the power flow. We added a model for this line and then tapped it at tap 30% of the total line length from Trenton for the POI. | CNR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted |  |  | In Progress
1164 | 2022-12-07 13:11 | G | 2021-09-23 | Solar | PV | SUN | 20 | 20 | 20 | Coos | NH | 2023-11-01 | 2023-11-01 | 2022-12-07 | Eversource 34.5 kV Line 384, Pole 4 | CNR | FALSE | FALSE |  | PD | NH | In Progress |  |  |  |  | Under Study
1163 | 2024-12-13 15:33 | G | 2021-09-22 | Battery Storage | OT | BAT | 205 | 201.43 | 201.43 | Washington | RI | 2026-06-01 | 2026-06-01 |  | RIE L190-2 (0.615 miles from Davisville and 1.935 miles from Old Baptist substations). | NR | FALSE | FALSE |  |  | RI | Document Posted | Document Posted |  |  | Not Started
1162 | 2023-06-01 16:38 | G | 2021-09-21 | Solar with Battery | OT | SUN BAT | 87 | 95.6 | 95.6 | Windham | CT | 2023-12-31 | 2023-11-30 | 2023-06-01 | POI will be the three breaker ring bus at the 1607 Line. Approximate Coordinates 41.7119, -71.9379. | CNR | FALSE | FALSE |  | PD | CT | Document Posted | Not Started |  |  |  | Under Study
1161 | 2022-09-13 09:53 | G | 2021-09-08 | Solar plus Battery | OT | SUN BAT | 3.6 | 3.6 | 3.6 | Berkshire | MA | 2022-07-01 | 2022-06-15 | 2022-09-12 | Eversource 22.8Kv feeder 15E1 Name of the substation = Partridge 15E substation | CNR | TRUE | FALSE | ISO-NE | PD | WMA | Not Required | Document Posted |  |  |  | Under Study
1160 | 2022-09-13 09:52 | G | 2021-08-31 | Solar plus Battery | OT | SUN BAT | 4.536 | 4.536 | 4.536 | Berkshire | MA | 2022-07-01 | 2022-06-15 | 2022-09-12 | Eversource 22.8Kv feeder 15E1 Name of the substation = Partridge 15E substation | CNR | TRUE | FALSE | ISO-NE | PD | WMA | Not Required | Document Posted |  |  |  | Under Study
1159 | 2023-08-18 16:10 | G | 2021-08-27 | Battery Storage | OT | BAT | 276 | 276 | 276 | Suffolk | MA | 2023-12-30 | 2023-12-05 | 2023-08-18 | Primary POI - Mystic 115 kV Station, Alternative POI - Mystic 345 kV Station | NR | FALSE | FALSE |  | PD | BOST | In Progress |  |  |  |  | Under Study
1158 | 2023-06-21 16:46 | ETU | 2021-08-19 | 1200 MW DC Transmission Line | NA | N/A | 1200 |  |  |  | MA | 2028-05-31 | 2028-02-29 | 2023-06-21 | Mystic 345 kV Substation | N/A | FALSE | FALSE |  |  | BOST | In Progress |  |  |  |  | Under Study
1157 | 2022-12-19 09:18 | ETU | 2021-08-19 | 1200 MW DC Transmission Line | NA | N/A | 1200 |  |  |  | MA | 2028-05-31 | 2028-02-29 | 2022-12-19 | Mystic 345 kV Substation | N/A | FALSE | FALSE |  |  | BOST | Not Started |  |  |  |  | Under Study
1156 | 2021-09-21 12:10 | G | 2021-08-16 | Solar | PV | SUN | 101.164 | 101.164 | 101.164 | Hartford | CT | 2024-10-15 | 2024-09-15 | 2021-09-21 | N. Bloomfield to NE Simsbury 115kV Line. POI is 200 feet east of the NE Simsbury Substation(115kV) and 2.25 miles west of N.Bloomfield(115kV). | CNR | FALSE | FALSE |  | PD | CT
1155 | 2021-09-21 12:10 | G | 2021-08-16 | Solar | PV | SUN | 101.09 | 101.09 | 101.09 | Hartford | CT | 2024-10-15 | 2024-09-15 | 2021-09-21 | N. Bloomfield to Agawam 345kV Line. POI is approximately 3.6 mi north of N. Bloomfield (345kV) and 11.5 mi south of Agawam (345kV). | CNR | FALSE | FALSE |  | PD | CT
1154 | 2024-10-02 16:49 | G | 2021-08-13 | Offshore wind Inc (QP700) | WT | WND | 18 | 856.2 | 856.2 | NA | MA | 2026-10-30 | 2026-03-14 |  | Eversource 345kV West Barnstable (921) | CNR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  | In Progress |  | Under Study
1153 | 2022-09-28 11:50 | G | 2021-08-11 | Offshore wind | WT | WND | 440 | 440 | 440 | NA | MA | 2026-11-01 | 2026-09-01 | 2022-09-28 | Eversource 115kV Acushnet, lines 112/114, Alternative Eversource Pine Street 115kV | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
1152 | 2022-09-08 10:21 | G | 2021-08-04 | Solar + Battery Storage | OT | SUN BAT | 9.998 | 9.998 | 9.998 | Hampshire | MA | 2022-09-01 | 2022-09-01 | 2022-09-08 | National Grid 13.8 kV 909W4 | CNR | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | Not Started
1151 | 2023-06-26 10:37 | G | 2021-08-04 | 13665 Felt Road Solar | OT | SUN BAT | 1.968 |  |  | Oxford | ME | 2024-11-15 | 2024-11-15 |  | CMP 34.5 kV Feeder 452K1, Woodstock Substation | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
1150 | 2023-05-22 13:35 | G | 2021-07-29 | Offshore Wind | WT | WND | 11.55 | 11.55 | 11.55 | NA | ME | 2023-09-01 | 2023-08-01 | 2023-05-22 | CMP Boothbay Harbor 34.5kV substation | CNR | FALSE | FALSE |  |  | ME |  | In Progress |  |  |  | Under Study
1149 | 2025-01-01 11:47 | G | 2021-08-06 | Battery addition | OT | WAT BAT | 6.7 |  |  | Franklin | MA | 2025-08-17 | 2025-08-13 |  | National Grid's PTF (E-5B, F-6 West PTF transmission lines) | CNR | TRUE | FALSE |  |  | WMA | Document Posted | Document Posted |  |  | In Progress
1148 | 2025-01-07 13:53 | G | 2021-07-13 | Lite Brite Battery Storage | OT | BAT | 305.624 | 305.624 | 305.624 | Suffolk | MA | 2028-05-26 | 2028-04-30 |  | Electric Avenue 115 kV substation (bus number 110926), Zone MA_NST | CNR | TRUE | TRUE | ISO-NE |  | BOST | Document Posted | Document Posted |  |  | Executed
1147 | 2021-07-12 10:51 | G | 2021-07-08 | Solar | PV | SUN | 20 | 20 | 20 | Rensselaer | NY | 2022-12-30 | 2022-11-30 |  | National Grid’s North Troy – Hoosick 115kV Line #5 | NA | FALSE | FALSE |  | PD | N/A
1146 | 2024-11-12 17:11 | G | 2021-07-07 | Swain Solar | PV | SUN | 40.355 | 40.91 | 40.91 | Oxford | ME | 2027-07-09 | 2027-06-25 | 2024-10-30 | CMP 115kV Line 270 | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
1145 | 2023-08-31 09:47 | G | 2021-07-07 | Solar | PV | SUN | 20.7 | 20.7 | 20.7 | Hancock | ME | 2024-07-08 | 2024-06-24 |  | Versant 115 kV Trenton substation bus; Alternate POI - Versant 115kV Line 57 | CNR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | In Progress
1144 | 2021-10-27 10:27 | G | 2021-06-17 | Solar | OT | SUN BAT | 1 | 1 | 1 | Dukes | MA | 2022-11-01 | 2022-10-01 | 2021-10-26 | Eversource 23 kV Line 4-99-99 | CNR | FALSE | FALSE |  |  | SEMA
1143 | 2024-04-11 11:53 | G | 2021-06-15 | Battery Storage | OT | BAT | 508.248 | 508.248 | 508.248 | Middlesex | MA | 2028-05-31 | 2027-12-01 |  | Mystic 345 kV between breaker 101, 106 and 107 | CNR | TRUE | TRUE | ISO-NE | NA | BOST | Document Posted | Document Posted |  |  | Executed
1142 | 2022-12-19 09:18 | ETU | 2021-06-07 | 1200 MW DC Bidirectional Transmission line | NA | N/A |  |  |  | Suffolk/Barnstable | MA | 2027-09-30 | 2027-07-31 | 2022-12-19 | K Street 345 kV Substation associated terminals Boston, MA Bourne 345 kV Substation associated terminals Sandwich, MA | N/A | FALSE | FALSE |  | NA | BOST
1141 | 2021-09-03 11:20 | ETU | 2021-06-07 | 1200 MW DC Bidirectional Transmission line | NA | N/A |  |  |  | Suffolk/Barnstable | MA | 2027-09-30 | 2027-07-31 | 2021-09-02 | Mystic 345 kV Substation associated terminals Everett, MA Bourne 345 kV Substation associated terminals Sandwich, MA |  | FALSE | FALSE |  | NA | BOST
1140 | 2022-01-11 15:10 | TS | 2021-06-03 | Regional Network Service Request | NA | N/A | 395 | 395 | 316 | Hampden | MA | 2023-10-01 | 2023-10-01 | 2022-01-11 | Eversource 115 kV Lines 1293 & 1302 | N/A | FALSE | FALSE |  | NA | WMA
1139 | 2024-08-12 12:44 | G | 2021-06-04 | Turner Meadow Solar | PV | SUN | 20 | 20 | 20 | Androscoggin | ME | 2026-11-20 | 2026-11-15 |  | CMP 34.5kV Line 50 | CNR | TRUE | TRUE | ISO-NE | NA | ME |  | Document Posted |  |  | Executed
1138 | 2024-10-08 13:39 | G | 2021-06-03 | Husky Solar | PV | SUN | 50.159 | 50.159 | 50.159 | Windham | CT | 2028-05-10 | 2028-05-01 |  | The POI will be located about 6.9 miles from the 1607/1505 line ROW (Exeter Tap) and about 1.1 miles from the Exeter Sub 54N along the 115 kV underground line to the Exeter Sub 54N. | CNR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted | Not Required | Not Required | Executed
1137 | 2021-05-26 12:35 | G | 2021-05-25 | Nasonville Substation – NG RI-Nasonville-21-Comp-1 Study | PV | SUN | 9.5 | 9.5 | 9.5 | Providence | RI | 2023-03-15 | 2023-03-15 |  | NG feeder 127W43, Nasonville Substation | NA | FALSE | FALSE |  | PD | RI
1136 | 2025-01-22 13:58 | G | 2021-05-20 | Nutes Solar | PV | SUN | 20 | 20 | 20 | Strafford | NH | 2026-05-15 | 2026-04-15 |  | 43°23'7.50"N, 71° 1'23.45"W, Direct Tap, Circuit #3174 34.5 kV | CNR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | Executed
1135 | 2023-02-02 14:30 | G | 2021-05-13 | Solar + Battery Storage | OT | SUN BAT | 113.01 | 113.01 | 113.01 | Coos | NH | 2025-05-15 | 2025-02-15 | 2023-02-02 | Eversource W179-1 115 kV Line between Berlin and Pontook Hydro Substations, 11.5 miles from the Berlin Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted | In Progress |  |  |  | Under Study
1134 | 2023-03-09 14:36 | G | 2021-05-06 | Noresco Navy | IC | NG | 10.8 | 10.8 | 10.8 | New London | CT | 2023-04-15 | 2023-03-01 |  | GU 323 | NA | TRUE | FALSE |  |  | CT
1133 | 2024-09-10 11:29 | G | 2021-04-27 | Stored Solar Fitchburg CNR Only | ST | WDS | 0 | 17 | 17 | Worcester | MA | 2024-08-08 | 2024-08-08 |  | Flagg Pond 69kv | CNR | FALSE | FALSE |  |  | CMA |  |  |  |  | Executed
1132 | 2022-09-14 10:52 | G | 2021-04-23 | Solar + Battery Storage | OT | SUN BAT | 3 | 3 | 3 | Hampshire | MA | 2021-12-28 | 2021-12-28 | 2022-09-14 | 13.2 Kv, Circuit #527L1, POI Pole# 52/42-2-3-1 | CNR | FALSE | FALSE |  |  | WMA |  | In Progress |  |  |  | Under Study
1131 | 2022-09-21 08:31 | G | 2021-04-23 | Solar + Battery Storage | OT | SUN BAT | 4.95 | 9.9 | 9.9 | Barnstable | MA | 2021-12-31 | 2021-12-31 | 2022-09-20 | Falmouth Station #933 Line #98 Pole# 9105/16 | CNR | TRUE | FALSE | ISO-NE |  | SEMA |  | Document Posted |  |  |  | Under Study
1130 | 2022-09-14 10:51 | G | 2021-04-23 | Solar + Battery Storage | OT | SUN BAT | 2 | 2 | 2 | Franklin | MA | 2022-04-30 | 2022-04-30 | 2022-09-14 | Eversource 13.8kV 22B3 feeder | CNR | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | Not Started | Under Study
1129 | 2022-10-04 12:23 | G | 2021-04-22 | Solar + Battery Storage | OT | SUN BAT | 2.456 | 2.456 | 2.456 | Bristol | MA | 2021-12-31 | 2021-10-31 | 2022-10-04 | The primary connection of the proposed project to Eversource Energy is located at the Wing Lane substation #624 Transformer #1 Line #240. The site is located approximately 0.26 circuit miles from Substation 624 near PSS/E node 111293(Wing Lane 13.2 KV) | CNR | FALSE | FALSE |  |  | SEMA |  | Document Posted |  |  | Not Started
1128 | 2022-09-13 09:51 | G | 2021-04-21 | Solar + Battery Storage | OT | SUN BAT | 4.536 | 4.536 | 4.536 | Berkshire | MA | 2022-07-15 | 2022-07-08 | 2022-09-12 | Eversource 22.8Kv feeder 15E2 Name of substation = Partridge 15E substation | CNR | FALSE | FALSE |  | PD | WMA |  | Document Posted |  |  | In Progress | Under Study
1127 | 2022-09-16 13:48 | G | 2021-04-21 | Solar + Battery Storage | OT | SUN BAT | 0.999 | 0.999 | 0.999 | Barnstable | MA | 2022-02-28 | 2022-02-17 | 2022-09-16 | Eversource East 22.8kV CKT #4-77-450 (Pole# 429/5) | NR | FALSE | FALSE |  |  | SEMA |  | Document Posted |  |  | In Progress | Under Study
1126 | 2022-09-16 13:47 | G | 2021-04-21 | Solar + Battery Storage | OT | SUN BAT | 4 | 4 | 4 | Barnstable | MA | 2022-02-28 | 2022-02-17 | 2022-09-16 | Eversource West 22.8kV CKT #4-77-450 (POLE#429/8) | CNR | FALSE | FALSE |  |  | SEMA |  | Document Posted |  |  | In Progress | Under Study
1125 | 2023-09-28 15:43 | G | 2021-04-21 | Solar | PV | SUN | 72 | 72 | 72 | Somerset | ME | 2024-01-31 | 2023-12-01 | 2023-09-28 | 44°36'30.65"N 69°38'23.26"W. CMP Line 241, new substation on 115kV line between Heywood Road Substation and County Road Substation. | CNR | FALSE | FALSE |  | PD | ME | Document Posted | In Progress |  |  |  | Under Study
1124 | 2023-06-26 08:46 | G | 2021-04-21 | Battery Storage | OT | BAT | 107.5 | 107.5 | 107.5 | Hampden | MA | 2025-01-01 | 2024-10-01 | 2023-06-26 | Eversource 345kV Ludlow substation via the 115kV Stony Brook Substation | CNR | FALSE | FALSE |  |  | WMA | Document Posted | In Progress |  |  |  | Under Study
1123 | 2024-08-14 10:45 | G | 2021-04-21 | Naugatuck Avenue Battery Storage CNR Only (see QP1089) | OT | BAT | 0 | 205.32 | 205.32 | New Haven | CT | 2026-12-01 | 2026-10-15 |  | devon 115kV substation | CNR | FALSE | FALSE |  | PD | SWCT
1122 | 2021-06-16 13:46 | G | 2021-04-19 | Battery Storage | OT | BAT | 20 | 20 | 20 | Addison | VT | 2022-12-31 | 2022-08-31 | 2021-06-16 | VELCO Middlebury Substation @ 46kV bus | CNR | FALSE | FALSE |  |  | VT
1121 | 2022-10-19 16:40 | G | 2021-04-16 | Offshore wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2033-05-31 | 2032-12-01 |  | Brayton Point 345 kV | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | In Progress |  |  |  | Under Study
1120 | 2022-04-22 13:27 | G | 2021-04-14 | Battery Storage | OT | BAT | 204.64 | 204.64 | 204.64 | Windham | CT | 2025-05-01 | 2025-02-15 | 2022-04-22 | Eversource Killingly 345kV Substation | NR | TRUE | FALSE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress | Under Study
1119 | 2022-04-25 16:29 | G | 2021-04-14 | Offshore wind | WT | WND | 1320 | 1320 | 1320 | NA | MA | 2027-09-01 | 2027-03-01 | 2022-04-25 | Primary National Grid Brayton Point 345kV, Alt Kent County 345 kV | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Under Study
1118 | 2024-02-13 08:50 | G | 2021-04-15 | Offshore wind Increase (QP909) | WT | WND | 386 | 1200 | 1200 | NA | MA | 2027-09-30 | 2027-03-31 | 2024-02-13 | National Grid 115kV Bell Rock, | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
1117 | 2024-02-14 16:06 | G | 2021-04-15 | Streamfield | OT | BAT | 202.4 | 202.4 | 202.4 | Hampden | MA | 2027-05-31 | 2027-04-15 |  | The proposed POI is Buck Pond 115 kV substation, the alternative POI is to build a new substation next to Buck pond 115 kV in the north side by breaking Line 1657 | CNR | TRUE | TRUE | ISO-NE |  | WMA | Document Posted | Document Posted |  |  | Executed
1116 | 2024-07-17 14:19 | G | 2021-04-13 | SouthCoast Wind 1 | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2031-12-31 | 2030-05-01 |  | Brayton Point making use of QP 837 to connect | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | Executed
1115 | 2023-09-15 08:43 | G | 2021-04-08 | Hecate Energy Eastern Ave Energy Center | OT | BAT | 250 | 250 | 250 | Suffolk | MA | 2026-11-09 | 2026-08-14 |  | Sta 488 Chelsea 115 kV substation | CNR | TRUE | TRUE | ISO-NE | PD | BOST | Document Posted | Document Posted |  |  | Executed
1114 | 2021-04-21 09:12 | G | 2021-04-01 | Solar | PV | SUN | 103 | 103 | 103 | Somerset | ME | 2024-01-31 | 2023-11-30 | 2021-04-20 | New Substation Tapping CMP 115 kV Circuit, Section 241 | CNR | FALSE | FALSE |  | PD | ME
1113 | 2023-05-05 15:22 | G | 2021-03-24 | Rumford Uprate and Battery addition | OT | WAT BAT | 8.5 | 52.5 | 52.5 | Oxford | ME | 2023-05-05 | 2023-03-24 |  | 11.5kV bus at Brookfield owned existing Rumford Falls Substation which is connected to the CMP 115kV 218 Line. | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
1112 | 2024-07-03 15:02 | G | 2021-03-24 | Battery Storage | OT | BAT | 105 | 105 | 105 | Franklin | MA | 2029-12-30 | 2029-07-09 | 2024-07-03 | 115 kV B128 line; 18.88 miles from Barre B128 and 5.3 miles from French King | NR | TRUE | TRUE | ISO-NE | PD | WMA | Document Posted | Document Posted |  | Document Posted | In Progress
1111 | 2023-09-21 17:44 | G | 2021-03-22 | Battery Storage | OT | BAT | 20 | 20 | 20 | Norfolk | MA | 2026-03-01 | 2026-02-15 | 2023-09-21 | Ever Source 115kV Ring Station 150 (@ spare bay in breaker and-a-half switchyard) | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Not Started
1110 | 2023-10-25 08:54 | G | 2021-03-18 | Norman Street Battery Storage | OT | BAT | 204 | 204 | 204 | Middlesex | MA | 2028-03-18 | 2028-02-15 |  | Mystic 115kV | CNR | TRUE | TRUE | ISO-NE | PD | BOST | Document Posted | Document Posted |  |  | Executed
1109 | 2024-10-02 16:50 | G | 2021-03-17 | Offshore Wind Inc. (Q806) | WT | WND | 487 | 1314 | 1314 | NA | MA | 2026-12-31 | 2026-04-01 |  | Eversource 345kV West Barnstable (921) | CNR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  | In Progress |  | Under Study
1108 | 2024-11-15 08:53 | G | 2021-03-16 | Battery Storage | OT | BAT | 188.96 | 188.96 | 188.96 | Plymouth | MA | 2027-05-14 | 2027-02-12 | 2024-11-15 | Eversource (NSTAR - South) 115 kV Line 116, 0.31 miles from Brook St 115 kV substation and 4.55 miles from Carver 115 kV substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
1107 | 2025-01-08 16:48 | G | 2021-03-16 | Battery Storage | OT | BAT | 189 | 182.23 | 182.23 | Plymouth | MA | 2027-05-14 | 2027-02-14 | 2025-01-08 | Eversource (NSTAR - South) 115 kV Wareham Line 108 | CNR | TRUE | FALSE |  | PD | SEMA | Document Posted | Document Posted |  |  | Not Started
1106 | 2021-04-23 08:38 | G | 2021-03-15 | Battery Storage | OT | BAT | 55.05 | 55.05 | 55.05 | Franklin | MA | 2025-05-15 | 2025-02-15 | 2021-04-22 | Eversource 115 kv Ashfield substation | CNR | FALSE | FALSE |  |  | WMA
1105 | 2021-10-21 11:29 | G | 2021-03-15 | Battery Storage | OT | BAT | 104.5 | 104.5 | 104.5 | Worcester | MA | 2025-05-15 | 2025-02-15 | 2021-10-20 | National Grid 115 kV Paxton Line A127-4 | CNR | FALSE | FALSE |  |  | CMA | Document Posted | Not Started |  |  |  | Under Study
1104 | 2023-04-20 12:40 | G | 2021-03-11 | Bonny Eagle Energy Storage - Uprate | OT | WAT BAT | 8 | 25.5 | 25.5 | York | ME | 2023-04-20 | 2023-03-13 |  | The battery will connect to Brookfield owned 34.5kV bus inside the Bonny Eagle Power station. The Bonny Eagle Power Station 34.5kV bus ties in to the CMP owned Bonny Eagle substation. | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
1103 | 2024-01-02 14:12 | G | 2021-03-10 | Berlin Energy Uprate and Battery Addition | OT | WAT BAT | 15 | 44.2 | 44.2 | Coos | NH | 2023-12-19 | 2023-09-25 |  | 22kV bus at Brookfield owned Goebel St Substation connected to the Eversource Berlin 115kV substation. | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed | In Service
1102 | 2021-11-26 10:39 | G | 2021-03-01 | Battery Storage | OT | BAT | 200 | 200 | 200 | Kent | RI | 2023-03-01 | 2023-03-01 | 2021-11-26 | NEC 115 kV G-185S-2 | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1101 | 2022-10-19 16:36 | ETU | 2021-02-25 | Objective ETU - upgrade alternative | NA | N/A |  |  |  | NA | NH | 2025-09-14 | 2025-09-14 |  | N/A | N/A | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | In Progress
1100 | 2024-02-26 13:52 | G | 2021-02-19 | Solar | PV | SUN | 164.56 | 164.56 | 164.56 | Somerset | ME | 2028-03-31 | 2028-01-29 |  | The proposed POI is on Central Maine Power 115 kV line Section 82 (Athens – Hartland), approximately 7.5 circuit miles to Athens Substation and approximately 4.3 circuit miles to Hartland station. Approximate POI coordinates: 44.8759° N, 69.5423° W | CNR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Not Started
1099 | 2022-12-15 11:44 | G | 2021-02-19 | Solar | PV | SUN | 31.4 | 31.4 | 31.4 | Knox | ME | 2024-12-31 | 2024-12-15 | 2022-12-15 | Central Maine Power 34.5 kV Line Section 51A (S51A Tap – Highland) @ 44°07'59.3"N, 69°11'43.5"W | CNR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | In Progress |  |  |  | Under Study
1098 | 2024-04-01 08:55 | G | 2021-02-19 | Solar | PV | SUN | 51.4 | 51.4 | 51.4 | Hancock | ME | 2024-12-31 | 2024-12-15 | 2024-04-01 | 34.5 kV bus at Versant Power Trenton substation at 44°26'19.81"N, 68°22'29.11"W | CNR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | Not Started
1097 | 2024-08-08 11:24 | G | 2021-02-15 | Green Apple Solar | PV | SUN | 178.59 | 178.59 | 178.59 | Androscoggin | ME | 2027-11-01 | 2027-05-15 |  | 44.172365, -70.104225 CMP 115kv Line 212 | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  | Document Posted | Executed
1096 | 2025-01-08 13:31 | G | 2021-02-04 | CMP Winslow 115 kV SS - Winslow-Lakewood Areas Study | OT | SUN BAT | 18.728 | 18.728 | 18.728 | Somerset/Kennebec | ME | 2024-04-30 | 2024-04-30 |  | CMP Winslow 115 kV SS | NA | TRUE | TRUE | CMP | PD | ME
1095 | 2025-01-08 13:29 | G | 2021-02-04 | CMP Lakewood 115 kV SS - Winslow-Lakewood Areas Study | PV | SUN | 28.72 | 28.72 | 28.72 | Somerset | ME | 2024-04-30 | 2024-04-30 |  | CMP Lakewood 115 kV SS | NA | TRUE | TRUE | CMP | PD | ME
1094 | 2025-01-08 13:28 | G | 2021-02-04 | CMP County Road 115 kV SS - Winslow-Lakewood Areas Study | OT | SUN BAT | 12.75 | 12.75 | 12.75 | Kennebec | ME | 2024-04-30 | 2024-04-30 |  | CMP County Road 115 kV SS | NA | TRUE | TRUE | CMP | PD | ME
1093 | 2023-12-12 09:03 | ETU | 2021-02-05 | NB TA#1365950 HVDC | OT | N/A | 0 | 0 | 0 | Salisbury, New Brunswick | NB | 2030-01-01 | 2030-01-01 | 2023-12-12 | Salisbury, New Brunswick | N/A | FALSE | FALSE |  | NA | N/A
1092 | 2023-01-31 10:30 | G | 2021-01-20 | Solar | PV | SUN | 26 | 26 | 26 | Hartford | CT | 2024-09-01 | 2024-08-01 |  | Eversource North Bloomfield 2A | NA | FALSE | FALSE |  |  | CT
1091 | 2021-11-01 08:28 | G | 2021-01-14 | Battery Storage | OT | BAT | 50.4 | 50.4 | 50.4 | Providence | RI | 2022-05-02 | 2022-05-02 | 2021-11-01 | The proposed POI is off the 115kV H17 transmission line owned by NEP via a spare buss position located in the Iron Mine HIll Substation owned by NEC. | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
1090 | 2022-09-16 09:43 | G | 2021-01-13 | Park City Offshore Wind CNR | WT | WND | 0 | 838.2 | 838.2 | NA | MA | 2029-12-31 | 2029-05-01 |  | Eversource (NSTAR) 345kV West Barnstable | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
1089 | 2023-10-20 12:54 | G | 2021-01-08 | Naugatuck Avenue Battery Storage | OT | BAT | 205.32 | 205.32 | 205.32 | New Haven | CT | 2026-12-01 | 2026-10-15 |  | Devon 115 kV open position between 4T and 5T | NR | TRUE | TRUE | ISO-NE | PD | SWCT | Document Posted | Document Posted |  |  | Executed
1088 | 2023-03-09 15:05 | G | 2020-12-07 | Solar | PV | SUN | 27 | 27 | 27 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2023-03-09 | Littleton W&L Section 30 34.5 kv line or 12.47 kv distrivution line | NA | FALSE | FALSE |  |  | NH
1087 | 2024-08-12 12:45 | G | 2020-12-17 | SolarFairfield | PV | SUN | 18.14 | 18.14 | 18.14 | Somerset | ME | 2027-06-30 | 2027-01-01 |  | New Rice Rips 34.5 kV Substation in Oakland Maine | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
1086 | 2024-08-12 12:40 | G | 2020-11-30 | Warren Meadow Solar | PV | SUN | 74.5 | 74.5 | 74.5 | Knox | ME | 2026-11-30 | 2026-09-30 |  | CMP 115kV line Section 80 | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
1085 | 2021-01-21 17:48 | G | 2020-11-17 | Solar | PV | SUN | 100 | 100 | 100 | Penobscot | ME | 2024-12-30 | 2024-11-30 | 2021-01-21 | BHE 115kV Line 64 | CNR | FALSE | FALSE |  | PD | BHE
1084 | 2021-02-08 14:50 | G | 2020-11-04 | Battery Storage | OT | BAT | 102 | 102 | 102 | Kennebec | ME | 2023-12-01 | 2023-09-01 | 2021-01-27 | Bowman st 115kV | CNR | FALSE | FALSE |  | PD | ME
1083 | 2020-11-30 14:09 | G | 2020-10-29 | Battery Storage | OT | BAT | 200 | 204 | 204 | Middlesex | MA | 2023-12-01 | 2023-10-01 | 2020-11-30 | Mystic 115kV | NR | FALSE | FALSE |  | PD | BOST
1082 | 2021-05-07 15:50 | G | 2020-10-29 | Battery Storage | OT | BAT | 204 | 204 | 204 | Middlesex | MA | 2025-06-01 | 2025-02-01 | 2021-05-07 | Mystic 115kV | NR | FALSE | FALSE |  | PD | BOST | In Progress |  |  |  |  | Under Study
1081 | 2020-10-21 14:09 | G | 2020-10-09 | Solar | PV | SUN | 100 | 100 | 100 | Penobscot | ME | 2024-12-30 | 2024-11-30 | 2020-10-21 | BHE 115kV Line 97 | CNR | FALSE | FALSE |  | PD | BHE
1080 | 2024-10-18 16:29 | G | 2020-10-08 | Solar | PV | SUN | 65 | 66.5 | 66.5 | Oxford | ME | 2024-10-24 | 2024-10-03 | 2024-10-18 | Ludden Lane 115 kV substation (Riley 115 kV line) | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  | Document Posted | In Progress
1079 | 2023-03-14 16:25 | G | 2020-10-02 | Puddledock Road 115 kV SS - Augusta Area Study | PV | SUN | 2.5 | 2.5 | 2.5 | Kennebec | ME | 2023-05-23 | 2023-05-23 |  | CMP WINTHROP Substation, Circuit 256D3 | NA | TRUE | TRUE | CMP | PD | ME
1078 | 2023-03-14 16:23 | G | 2020-10-02 | Puddledock Road 115 kV SS - Augusta Area Study | PV | SUN | 4.95 | 4.95 | 4.95 | Kennebec | ME | 2023-05-16 | 2023-05-16 |  | CMP PUDDLEDOCK ROAD Substation, Circuit 262D1 | NA | TRUE | TRUE | CMP |  | ME
1077 | 2023-03-14 16:22 | G | 2020-10-02 | Puddledock Road 115 kV SS - Augusta Area Study | PV | SUN | 4.875 | 4.875 | 4.875 | Kennebec | ME | 2024-01-04 | 2024-01-04 |  | CMP BOND BROOK Substation, Circuit 208D1 | NA | TRUE | TRUE | CMP | PD | ME
1076 | 2023-03-14 16:21 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | OT | SUN BAT | 4.975 | 4.975 | 4.975 | Kennebec | ME | 2023-06-27 | 2023-06-27 |  | CMP WEST STREET Substation, Circuit 255D1 | NA | TRUE | TRUE | CMP | PD | ME
1075 | 2023-03-14 16:20 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | PV | SUN | 1.75 | 1.75 | 1.75 | Sagadahoc | ME | 2023-09-12 | 2023-09-12 |  | CMP RICHMOND Substation, Circuit 240D1 | NA | TRUE | TRUE | CMP | PD | ME
1074 | 2023-04-18 10:58 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | OT | SUN BAT | 9.475 | 9.475 | 9.475 | Kennebec | ME | 2023-03-28 | 2023-03-01 |  | CMP MANCHESTER Substation, Circuit 233D1 and 233D2 | NA | TRUE | TRUE | CMP | PD | ME
1073 | 2023-03-14 16:17 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | PV | SUN | 3.25 | 3.25 | 3.25 | Kennebec | ME | 2022-06-28 | 2022-06-28 |  | CMP GARDINER Substation, Circuit 226D2 | NA | TRUE | TRUE | CMP |  | ME
1072 | 2023-03-14 16:16 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | PV | SUN | 1.703 | 1.703 | 1.703 | Kennebec | ME | 2023-06-15 | 2023-06-15 |  | CMP CAPITOL STREET Substation, Circuit 215D3 | NA | TRUE | TRUE | CMP | PD | ME
1071 | 2023-03-14 16:14 | G | 2020-10-02 | Bowman Street 115 kV SS - Augusta Area Study | OT | SUN BAT | 9.94 | 9.94 | 9.94 | Kennebec | ME | 2022-12-30 | 2022-09-30 |  | CMP BOWMAN STREET Substation, Circuit 263D1 | NA | TRUE | TRUE | CMP | PD | ME
1070 | 2023-03-14 16:13 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | OT | SUN BAT | 4.25 | 4.25 | 4.25 | Kennebec | ME | 2022-12-13 | 2022-12-13 |  | CMP SOUTH CHINA Substation, Circuit 244D2 | NA | TRUE | TRUE | CMP | PD | ME
1069 | 2023-03-14 16:12 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | PV | SUN | 4 | 4 | 4 | Kennebec | ME | 2022-03-25 | 2022-03-25 |  | CMP SIDNEY Substation, Circuit 242D1 | NA | TRUE | TRUE | CMP | PD | ME
1068 | 2023-03-14 16:10 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | PV | SUN | 9.998 | 9.998 | 9.998 | Kennebec | ME | 2024-10-21 | 2024-10-21 |  | CMP CONY ROAD Substation, Circuit 216D1 and 216D2 | NA | TRUE | TRUE | CMP | PD | ME
1067 | 2023-03-14 16:09 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | OT | SUN BAT | 3.75 | 3.75 | 3.75 | Kennebec | ME | 2022-05-03 | 2022-05-03 |  | CMP BLAIR ROAD Substation, Circuit 207D2 | NA | TRUE | TRUE | CMP | PD | ME
1066 | 2023-03-14 16:08 | G | 2020-10-02 | Augusta E. Side 115 kV SS - Augusta Area Study | PV | SUN | 2 | 2 | 2 | Kennebec | ME | 2024-03-01 | 2024-03-01 |  | CMP AUGUSTA K5 Substation, Circuit 200D2 | NA | TRUE | TRUE | CMP | PD | ME
1065 | 2020-10-09 17:58 | G | 2020-09-25 | Solar | PV | SUN | 100 | 100 | 100 | Penobscot | ME | 2024-11-30 | 2024-11-30 | 2020-10-09 | BHE 115kV Line 97 | NR | FALSE | FALSE |  | PD | BHE
1064 | 2020-12-01 11:15 | G | 2020-09-17 | Solar | PV | SUN | 11.8 | 11.8 | 11.8 | Washington | ME | 2023-09-15 | 2023-08-20 | 2020-12-01 | Emera Maine 34.5 kV Line 19, connecting Scott’s Hill Substation and Pembroke Substation Latitude: 44.873 Longitude: -67.356 | CNR | FALSE | FALSE |  | PD | BHE
1063 | 2021-12-23 11:16 | G | 2020-09-15 | Syncarpha Blandford Solar plus battery storage | OT | SUN BAT | 4.99 | 9.998 | 9.998 | Berkshire | MA | 2021-12-14 | 2021-12-09 |  | Eversource 23 kv 19J2 | CNR | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | Executed | In Service
1062 | 2020-12-03 11:06 | G | 2020-09-10 | Battery Storage | OT | BAT | 100 | 100 | 100 | Fairfield | CT | 2023-06-01 | 2023-03-01 | 2020-12-03 | Baird substation | CNR | FALSE | FALSE |  | PD | SWCT
1061 | 2021-07-19 16:22 | G | 2020-09-10 | Solar | PV | SUN | 135 | 135 | 135 | Hartford | CT | 2022-10-31 | 2022-09-30 | 2021-07-19 | The project will connect at North East Simsbury Substation (115 kV), with an alternate POI at the North East Simsbury to North Bloomfield 115 kV line in close proximity to the N.E. Simsbury substation. | NR | FALSE | FALSE |  | PD | CT | Document Posted |  |  |  |  | Under Study
1060 | 2023-10-26 16:42 | G | 2020-09-09 | Offshore Wind Increase | WT | WND | 0 | 1200 | 1200 | NA | CT | 2027-11-30 | 2027-03-31 |  | Eversource (CL&P) Millstone 345 kV substation | CNR | TRUE | FALSE | ISO-NE | PD | CT | Document Posted | In Progress |  |  |  | Under Study
1059 | 2022-12-14 09:48 | G | 2020-09-09 | Offshore Wind | WT | WND | 1200 | 1278.9 | 1278.9 | NA | MA | 2027-11-30 | 2027-03-31 | 2022-12-13 | Eversource NSTAR Pilgrim 345 kV substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
1058 | 2023-08-28 07:13 | G | 2020-09-09 | Offshore Wind | WT | WND | 1200 | 1266.72 | 1266.72 | NA | CT | 2027-11-30 | 2027-03-31 |  | Eversource (CL&P) Millstone 345 kV substation | CNR | TRUE | FALSE | ISO-NE | PD | CT | Document Posted | Document Posted |  |  | Not Started
1057 | 2021-04-22 14:30 | G | 2020-08-28 | Battery Storage | OT | BAT | 500 | 500 | 500 | Middlesex | MA | 2025-06-01 | 2025-03-01 | 2021-04-22 | Mystic 345 kV | NR | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
1056 | 2021-03-04 08:05 | G | 2020-08-28 | Battery Storage | OT | BAT | 50 | 50 | 50 | New Haven | CT | 2022-06-01 | 2022-03-01 | 2021-03-03 | June Street substation | CNR | FALSE | FALSE |  |  | SWCT | Document Posted | Not Started |  |  |  | Under Study
1055 | 2024-04-29 10:39 | G | 2020-08-26 | Fuel Cell | FC | NG | 14.4 | 14.4 | 14.4 | New Haven | CT | 2024-03-21 | 2023-10-12 |  | UI 13.8kV Indian Well Substation | NA | TRUE | TRUE | UI | PD | SWCT
1054 | 2024-10-08 15:51 | G | 2020-08-19 | Wood River - NG WRI DG Area Study #2 <5 MW | PV | SUN | 9.75 | 9.75 | 9.75 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Wood River Substation, feeder 85T2 | NA | TRUE | TRUE | NGRID | PD | RI
1053 | 2021-09-15 12:24 | G | 2020-08-19 | Westerly - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.875 | 4.875 | 4.875 | Washington | RI | 2025-06-30 | 2025-06-15 | 2021-09-14 | NR Westerly substation, feeder 16F2 | NA | TRUE | TRUE | NGRID | PD | RI
1052 | 2021-09-15 12:23 | G | 2020-08-19 | West Cranston - NG WRI DG Area Study #2 <5 MW | PV | SUN | 1.56 | 1.56 | 1.56 | Washington | RI | 2022-04-01 | 2022-03-15 | 2021-09-14 | NG West Cranston substation, feeder 21F2 | NA | TRUE | TRUE | NGRID | PD | RI
1051 | 2024-10-08 15:50 | G | 2020-08-19 | Tower Hill - NG WRI DG Area Study #2 <5 MW | PV | SUN | 3.06 | 3.06 | 3.06 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Tower Hill substation, feeder 88F7 | NA | TRUE | TRUE | NGRID | PD | RI
1050 | 2020-08-27 09:44 | G | 2020-08-19 | Putnam Pike - NG WRI DG Area Study #2 <5 MW | PV | SUN | 3 | 3 | 3 | Providence | RI | 2021-08-31 | 2021-08-15 |  | NG Putnam Pike substation, feeder 38F3 | NA | FALSE | FALSE |  | PD | RI
1049 | 2021-09-15 12:29 | G | 2020-08-19 | Old Baptist Road - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4 | 4 | 4 | Washington | RI | 2022-04-01 | 2022-03-15 | 2021-09-14 | NG Old Baptisst Road substation, feeder 46F3 | NA | TRUE | TRUE | NGRID | PD | RI
1048 | 2021-09-15 12:28 | G | 2020-08-19 | New London - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.875 | 4.875 | 4.875 | Kent | RI | 2022-04-01 | 2022-03-15 | 2021-09-14 | NG New London substation, feeder 150F4 | NA | TRUE | TRUE | NGRID | PD | RI
1047 | 2021-09-15 12:27 | G | 2020-08-19 | Kent County - NG WRI DG Area Study #2 <5 MW | PV | SUN | 13.525 | 13.525 | 13.525 | Kent | RI | 2022-04-01 | 2022-03-15 |  | NG Kent County Substation, feeders 3309, 22F1 and 3311 | NA | TRUE | TRUE | NGRID | PD | RI
1046 | 2021-03-03 13:33 | G | 2020-08-19 | Johnston - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.875 | 4.875 | 4.875 | Povidence | RI | 2022-04-01 | 2022-03-15 |  | NG Johnston substation | NA | TRUE | TRUE | NGRID | PD | RI
1045 | 2021-09-15 12:26 | G | 2020-08-19 | Hopkins Hill - NG WRI DG Area Study #2 <5 MW | PV | SUN | 3.5 | 3.5 | 3.5 | Kent | RI | 2022-04-01 | 2022-03-15 |  | NG Hopkins Hill substation, feeder 63F3 | NA | TRUE | TRUE | NGRID | PD | RI
1044 | 2021-03-03 13:18 | G | 2020-08-19 | Drumrock - NG WRI DG Area Study #2 <5 MW | PV | SUN | 4.975 | 4.975 | 4.975 | Kent | RI | 2022-04-01 | 2022-03-15 |  | NG Drumrock sustation, feeder 14F4 | NA | TRUE | TRUE | NGRID | PD | RI
1043 | 2024-10-08 15:49 | G | 2020-08-19 | Chase Hill - NG WRI DG Area Study #2 <5 MW | PV | SUN | 7.325 | 7.325 | 7.325 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Chase Hillk substation | NA | TRUE | TRUE | NGRID | PD | RI
1042 | 2024-10-08 15:49 | G | 2020-08-19 | Wood River - NG WRI DG Area Study #2 >5 MW | PV | SUN | 34.375 | 34.375 | 34.375 | Washington | RI | 2025-06-30 | 2025-06-15 | 2024-10-08 | NG Wood River Substation, feeder 85T2 | NA | TRUE | TRUE | NGRID | PD | RI
1041 | 2025-01-08 10:08 | G | 2020-08-19 | Kent County - NG WRI DG Area Study #2 >5 MW | PV | SUN | 49.75 | 49.75 | 49.75 | Kent | RI | 2025-07-07 | 2024-04-14 |  | NG Kent County Substation, feeders 3309 and 3310 | NA | TRUE | TRUE | NGRID | PD | RI
1040 | 2022-06-22 09:48 | G | 2020-08-19 | Farnum Pike - NG WRI DG Area Study #2 >5 MW | PV | SUN | 8 | 8 | 8 | Providence | RI | 2022-12-29 | 2022-12-15 |  | NG Drumrock sustation, feeder 23F3 | NA | TRUE | TRUE | NGRID | PD | RI
1039 | 2024-07-23 15:14 | G | 2020-08-19 | Warren Substation – NG RI-Warren-20-Comp-1 Study | PV | SUN | 6.93 | 6.93 | 6.93 | Kent | RI | 2024-08-02 | 2024-06-28 |  | NG feeder 5F2, Warren Substation | NA | TRUE | TRUE | NGRID | PD | RI
1038 | 2024-03-06 13:35 | G | 2020-08-07 | Solar | PV | SUN | 76.25 | 76.25 | 76.25 | Merrimack | NH | 2025-10-31 | 2025-10-05 |  | 3-breaker ring bus tap of the existing Comerford - Dunbarton Tap 230 kV line. This line is owned by National Grid and has the designation of Line B202 N. Latitude/ Longitude : 43.268, -71.66 | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Not Started
1037 | 2021-04-22 14:29 | G | 2020-08-04 | Battery Storage | OT | BAT | 700 | 700 | 700 | Suffolk | MA | 2024-06-01 | 2024-03-01 | 2021-04-22 | The Mystic 345 kV substation. | NR | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
1036 | 2020-08-28 08:07 | G | 2020-07-20 | Solar plus battery storage | OT | SUN BAT | 85 | 85 | 85 | Carroll | NH | 2023-10-31 | 2023-10-02 | 2020-08-27 | 115 kV bus at Eversource's White Lake Substation in Tamworth, New Hampshire (43.848851, -71.2444465) | CNR | FALSE | FALSE |  | PD | NH
1035 | 2020-09-23 09:29 | G | 2020-06-29 | Solar | PV | SUN | 60 | 60 | 60 | Coos | NH | 2023-12-30 | 2023-11-30 | 2020-09-22 | Eversource Berlin to Lost Nation 115 kV Line W179; 44.564565, -71.19104; 9.69 miles from Berlin substation, 18.27 miles from Lost Nation substation | CNR | FALSE | FALSE |  | PD | NH
1034 | 2021-05-03 10:09 | G | 2020-06-29 | Solar | PV | SUN | 60 | 60 | 60 | Coos | NH | 2023-12-30 | 2023-11-30 | 2021-04-30 | Eversource Whitefield to Berlin 115 kV S136 line (44.36675, -71.52688) 4.3 miles from Whitefield Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted | Not Started
1033 | 2023-01-31 10:21 | G | 2020-06-24 | Solar | PV | SUN | 6 | 6 | 6 | Ellington | CT | 2024-09-01 | 2024-08-01 |  | Eversource Scitico #27H9 | NA | TRUE | TRUE | NU |  | CT
1032 | 2023-03-30 13:12 | G | 2020-06-23 | Eversource Group @ Bell Rock #661 | OT | SUN BAT | 11.992 | 11.992 | 11.992 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Bell Rock #661 | NA | FALSE | FALSE |  |  | SEMA
1031 | 2022-10-19 15:48 | G | 2020-06-18 | Solar | PV | SUN | 40 | 40 | 40 | Hampshire | MA | 2023-10-01 | 2023-08-08 | 2022-10-19 | NATIONAL GRID 69 kV LINE F-6W, WARE - DEERFIELD Latitude: 42.287024° Longitude: -72.289276° | CNR | TRUE | FALSE | ISO-NE |  | WMA | Document Posted | Document Posted |  |  | In Progress | Under Study
1030 | 2023-01-11 08:33 | G | 2020-06-02 | Gravel Pit Solar Increase | PV | SUN | 45 | 120 | 120 | Hartford | CT | 2025-02-07 | 2024-10-28 |  | Line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed
1029 | 2024-02-06 09:48 | G | 2020-05-29 | Solar | PV | SUN | 120 | 120 | 120 | Penobscot | ME | 2023-12-01 | 2023-10-02 | 2024-02-06 | Emera Maine 115 kV Line 97 BHE, (Passadumkeag to Graham) | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | In Progress
1028 | 2024-03-06 13:34 | G | 2020-05-28 | Western Maine Wind Project | WT | WND | 58.8 | 58.8 | 58.8 | Somerset | ME | 2025-01-29 | 2025-01-20 |  | CMP 115 kV Section 222 - coordinates 45° 9'30.90"N, 69°51'1.40"W | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
1027 | 2022-09-13 09:49 | G | 2020-05-14 | Solar + Battery Storage | OT | SUN BAT | 2 | 2 | 2 | Berkshire | MA | 2022-12-15 | 2022-12-01 | 2022-09-13 | National Grid, 13.8kV, DISTRIBUTION CIRCUIT #09-1102W1 | CNR | TRUE | TRUE | ISO-NE |  | WMA |  |  |  |  | In Progress
1026 | 2020-06-23 17:10 | G | 2020-05-08 | Solar | PV | SUN | 90 | 90 | 90 | Oxford | ME | 2021-11-22 | 2021-10-25 | 2020-06-23 | CMP Rumford substation 115 kV | NR | FALSE | FALSE |  | PD | ME
1025 | 2020-08-25 10:27 | G | 2020-04-27 | Solar Increase | PV | SUN | 5 | 20 | 20 | Androscoggin | ME | 2021-11-01 | 2021-10-01 | 2020-08-25 | 34.5 kV line from Gulf island to Crowleys substation. 102159-97000-101460 | CNR | FALSE | FALSE |  | PD | ME
1024 | 2024-09-25 10:36 | G | 2020-04-28 | ENA Old Falmouth Road PV + Storage | OT | SUN BAT | 4.85 | 4.85 | 4.85 | Barnstable | MA | 2024-08-08 | 2024-07-05 |  | The facility is located approximately 5.5 miles from MASHPEE Substation, via the 23 kV#88 circuit. | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
1023 | 2022-03-04 09:19 | G | 2020-04-24 | Solar + Battery Storage | OT | SUN BAT | 2.425 | 2.425 | 2.425 | Bristol | MA | 2021-10-20 | 2021-10-20 | 2022-03-04 | Eversource 13.2 kV Circuit #522 approximately 5.95 miles from Fisher Road substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Not Started
1022 | 2022-02-22 13:52 | G | 2020-04-24 | Cranberry Highway Solar + Battery Storage | OT | SUN BAT | 2.2 |  |  | Plymouth | MA | 2022-02-15 | 2022-02-05 |  | The primary connection of the proposed project to Eversource Energy is located on Tremont Station 713 Transformer #1 Line #86. The site is located approximately 2.29 circuit miles from Substation 713 near CYME® node 1200910-295. Circuit 3-86-966 | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
1021 | 2024-07-11 13:31 | G | 2020-04-27 | Emery Meadow Solar | PV | SUN | 16.425 | 16.425 | 16.425 | York | ME | 2026-09-30 | 2026-09-15 |  | CMP 34.5 kV, Section 182 | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
1020 | 2022-12-14 09:12 | G | 2020-04-24 | Silver Maple Wind CNR | WT | WND | 0 | 20 | 20 | Penobscot | ME | 2022-12-14 | 2022-09-24 |  | Emera Maine 115kV Transmission Line 66, between Graham Substation and Rebel Hill substation, adjacent to Pisgah Mountain Wind Farm. | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
1019 | 2023-09-19 09:19 | G | 2020-04-24 | Battery Storage | OT | BAT | 20 | 20 | 20 | Penobscot | ME | 2024-04-01 | 2024-01-01 | 2023-09-19 | Chester 46 kV | NR | TRUE | FALSE | ISO-NE | PD | BHE |  | Document Posted |  |  | In Progress | Under Study
1018 | 2024-08-29 14:17 | G | 2020-04-24 | Passadumkeag Wind CNR | WT | WND | 0 | 39.97 | 39.97 | Peneobscot | ME | 2021-11-15 | 2021-11-15 |  | Interconnection shall be at the point where the leads from the switch located on the high side of the 115 kV/34.5 kV transformer connect into the 115 kV ring bus at the Passadumkeag Substation in Greenbush, Maine | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed
1017 | 2023-08-31 14:44 | G | 2020-04-24 | Battery Storage | OT | BAT | 200 | 200 | 200 | New Haven | CT | 2026-10-01 | 2026-07-01 |  | Eversource East Devon 345 kV Substation | NR | TRUE | TRUE | ISO-NE |  | SWCT | Document Posted | Document Posted |  |  | In Progress
1016 | 2024-05-01 10:52 | G | 2020-04-24 | Solar | PV | SUN | 16 | 16 | 16 | Hillsborough | NH | 2024-11-25 | 2024-10-31 | 2024-05-01 | At the Eversource NH 314 line (34.5kV) out of the South Milford substation. | NR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | In Progress
1015 | 2023-10-03 15:01 | G | 2020-04-22 | Battery Storage | OT | BAT | 112.2 | 112.2 | 112.2 | Penobscot | ME | 2024-12-01 | 2024-09-01 | 2023-08-22 | Orrington 115kV | CNR | TRUE | FALSE | ISO-NE | PD | BHE |  | Document Posted |  | Not Required
1014 | 2023-10-03 15:01 | G | 2020-04-22 | Battery Storage | OT | BAT | 112.2 | 112.2 | 112.2 | Penobscot | ME | 2024-06-01 | 2024-03-01 | 2023-08-22 | EMERA Keene Rd 115 kV substation | CNR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted
1013 | 2023-08-31 14:43 | G | 2020-04-22 | Solar | PV | SUN | 17.2 | 17.2 | 17.2 | Sagadahoc | ME | 2025-09-30 | 2025-08-31 |  | CMP 34.5kV line 43, pole 278 | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress
1012 | 2020-08-28 11:12 | G | 2020-04-20 | Combined Cycle | CC | NG | 800 | 800 | 850 | Suffolk | MA | 2024-06-01 | 2024-05-31 | 2020-08-28 | Eversource Mystic 115 kV station | CNR | FALSE | FALSE |  | PD | BOST |  | Not Started
1011 | 2020-08-28 11:12 | G | 2020-04-20 | Combined Cycle | CC | NG | 800 | 800 | 850 | Suffolk | MA | 2024-06-01 | 2024-05-31 | 2020-08-28 | Eversource Mystic 345 kV station | CNR | FALSE | FALSE |  | PD | BOST |  | In Progress |  |  |  | Under Study
1010 | 2021-12-01 09:14 | G | 2020-04-10 | Berkshire Wind CNR | WT | WND | 0 | 19.6 | 19.6 | Berkshire | MA | 2021-09-13 | 2021-09-13 |  | Eversource 15-E 4 circuit. Interconnection Circuit connects to 115 KV transmission system at Partridge Substation in Pittsfield MA | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
1009 | 2023-03-30 13:11 | G | 2020-04-09 | Eversource Group @ Wing Lane 624 | OT | SUN BAT | 18.989 | 18.989 | 18.989 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Wing Lane #624 | NA | FALSE | FALSE |  |  | SEMA
1008 | 2023-03-30 13:11 | G | 2020-04-09 | Eversource Group @ West Pond 737 | OT | SUN BAT | 44.12 | 44.12 | 44.12 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource West Pond #737 | NA | FALSE | FALSE |  |  | SEMA
1007 | 2023-03-30 13:10 | G | 2020-04-09 | Eversource Group @ Wareham 714 | OT | SUN BAT | 48.019 | 48.019 | 48.019 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Wareham #714 | NA | FALSE | FALSE |  |  | SEMA
1006 | 2023-03-30 13:09 | G | 2020-04-09 | Eversource Group @ Valley 715 | OT | SUN BAT | 9.98 | 9.98 | 9.98 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Valley 715 | NA | FALSE | FALSE |  |  | SEMA
1005 | 2023-03-30 13:08 | G | 2020-04-09 | Eversource Group @ Tremont Substation 713 | OT | SUN BAT | 33.735 | 33.735 | 33.735 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Tremont 713 | NA | FALSE | FALSE |  |  | SEMA
1004 | 2023-03-30 13:07 | G | 2020-04-09 | Eversource Group @ Sandwich 916 | OT | SUN BAT | 11.75 | 11.75 | 11.75 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Sandwich 916 | NA | FALSE | FALSE |  |  | SEMA
1003 | 2023-03-30 13:06 | G | 2020-04-09 | Eversource Group @ Rochester #745 | OT | SUN BAT | 24.618 | 24.618 | 24.618 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Rochester #745 | NA | FALSE | FALSE |  |  | SEMA
1002 | 2023-03-30 13:06 | G | 2020-04-09 | Solar | PV | SUN | 2.76 | 2.76 | 2.76 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Kingston 735 | NA | FALSE | FALSE |  |  | SEMA
1001 | 2023-03-30 13:05 | G | 2020-04-09 | Eversource Group @ Industrial Park 636 | OT | SUN BAT | 29.11 | 29.11 | 29.11 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Industrial Park 636 | NA | FALSE | FALSE |  |  | SEMA
1000 | 2023-03-30 13:04 | G | 2020-04-09 | Solar + battery | OT | SUN BAT | 3.15 | 3.15 | 3.15 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Harwich 968 | NA | FALSE | FALSE |  |  | SEMA
999 | 2023-03-30 13:03 | G | 2020-04-09 | Eversource Group @ Fisher Rd Substation 657 | OT | SUN BAT | 27.948 | 27.948 | 27.948 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Fisher Rd 657 | NA | FALSE | FALSE |  |  | SEMA
998 | 2023-03-30 13:03 | G | 2020-04-09 | Eversource Group @ Falmouth 993 | OT | SUN BAT | 7.99 | 7.99 | 7.99 | Barnstable | MA | 2023-11-30 | 2023-09-30 |  | Eversource Falmouth 933 | NA | FALSE | FALSE |  |  | SEMA
997 | 2023-03-30 13:02 | G | 2020-04-09 | Eversource Group @ Crystal Spring 646 | OT | SUN BAT | 7.499 | 7.499 | 7.499 | Middlesex | MA | 2023-11-30 | 2023-09-30 |  | Eversource Crystal Spring 646 | NA | FALSE | FALSE |  |  | SEMA
996 | 2023-03-30 13:01 | G | 2020-04-09 | Eversource Group @ Cross Rd 651 | OT | SUN BAT | 9.5 | 9.5 | 9.5 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Cross Rd #651 | NA | FALSE | FALSE |  |  | SEMA
995 | 2023-03-30 12:59 | G | 2020-04-09 | Solar + Battery | OT | SUN BAT | 5 | 5 | 5 | Norfolk | MA | 2023-11-30 | 2023-09-30 |  | Eversource Canton #470 | NA | FALSE | FALSE |  |  | SEMA
994 | 2023-03-30 12:58 | G | 2020-04-09 | Solar + battery | OT | SUN BAT | 5.5 | 5.5 | 5.5 | Middlesex | MA | 2023-11-30 | 2023-09-30 |  | Eversource Burlington #391 | NA | FALSE | FALSE |  |  | SEMA
993 | 2023-03-30 12:58 | G | 2020-04-09 | Solar + Battery | OT | SUN BAT | 2 | 2 | 2 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Brook St 727 | NA | FALSE | FALSE |  |  | SEMA
992 | 2023-03-30 12:57 | G | 2020-04-09 | Eversource Group @ Arsene St 654 | OT | SUN BAT | 7 | 7 | 7 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Arsene Street #654 | NA | FALSE | FALSE |  | PD | SEMA
991 | 2023-03-30 12:56 | G | 2020-04-09 | Solar | PV | SUN | 2.5 | 2.5 | 2.5 | Franklin | MA | 2023-11-30 | 2023-09-30 |  | Eversource Cumberland station | NA | TRUE | TRUE | NU |  | WMA
990 | 2023-03-30 12:55 | G | 2020-04-09 | Solar | PV | SUN | 4.89 | 4.89 | 4.89 | Berkshire | MA | 2023-11-30 | 2023-09-30 |  | Eversource Partidge station | NA | TRUE | TRUE | NU |  | WMA
989 | 2023-03-30 12:54 | G | 2020-04-09 | Eversource Group Study @ Blandford | PV | SUN | 12.48 | 12.48 | 12.48 | Hampden | MA | 2023-11-30 | 2023-09-30 |  | Eersource Blandford station | NA | TRUE | TRUE | NU |  | WMA
988 | 2021-11-01 08:14 | G | 2020-04-07 | Solar CNR only | PV | SUN | 0 | 30 | 30 | Cheshire | NH | 2024-07-30 | 2024-06-30 | 2021-10-31 | The Project will interconnect at National Grid’s 115 kV line I-135 via a new three circuit breaker ring bus switching station located at 2.9 miles from Eversource’s Fitzwilliam Substation and 20.5 miles from Fitchburg Gas & Electric Light Company’s Flagg Pond Substation. | CNR | FALSE | FALSE |  |  | NH |  |  |  |  | In Progress
987 | 2025-01-13 17:41 | G | 2020-04-10 | Chariot Solar CNR only | PV | SUN | 0 | 49.5 | 49.5 | Cheshire | NH | 2024-12-15 | 2024-11-15 | 2025-01-13 | NGrid 115 kV Vernon Road tap to Vernon Road Substation, 2.5 mi from Vernon Road Substation | NR | FALSE | FALSE |  |  | NH |  |  |  |  | Executed
986 | 2023-08-31 14:40 | G | 2020-04-07 | Solar | PV | SUN | 19.99 | 19.99 | 19.99 | Penobscot | ME | 2027-09-30 | 2027-08-31 |  | Graham Substation – 46 kV open bus tie/breaker -via a tapped existing line approximately 5.1 miles to the substation. (44 51 39.25 N 68 39 28.19 W) | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Not Started | In Progress
985 | 2021-07-20 11:03 | G | 2020-04-02 | Solar | PV | SUN | 4 | 4 | 4 | Washington | ME | 2021-07-29 | 2021-07-15 | 2021-07-20 | Emera Maine 34.5kV Line 3 approximately 1.8 miles from Washington County Substation (WCS) | CNR | FALSE | FALSE |  |  | BHE |  | In Progress |  |  |  | Under Study
984 | 2023-05-31 13:54 | G | 2020-04-01 | Storage | OT | BAT | 150 | 150 | 150 | Middlesex | MA | 2023-09-20 | 2023-05-31 | 2023-05-31 | National Grid 115kV line 1/2 mile to the East of Billerica 70 substation | CNR | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted |  |  | In Progress
983 | 2020-06-18 16:52 | G | 2020-03-31 | Solar | PV | SUN | 40 | 40 | 40 | Androscoggin | ME | 2022-11-15 | 2022-10-16 | 2020-06-18 | The project will connect at Central Maine Power 200A at Switch 200A-2 (115 kV) | CNR | FALSE | FALSE |  | PD | ME
982 | 2023-08-10 16:31 | G | 2020-03-30 | Wind | WT | WND | 3.8 | 3.8 | 3.8 | Litchfield | CT | 2024-09-01 | 2024-07-01 |  | Eversource Canton 5R | NA | FALSE | FALSE |  | PD | CT
981 | 2022-03-24 09:58 | G | 2020-03-27 | Bridgeport Harbor Unit #5 Uprate | CC | DFO NG | 0.4 | 509.6 | 532.6 | Fairfield | CT | 2021-12-22 | 2021-12-22 |  | UI Singer Substation 345kv | CNR | FALSE | FALSE |  | PD | SWCT |  |  |  |  | Executed
980 | 2021-03-05 16:21 | G | 2020-03-26 | Solar addition | PV | SUN | 10 | 20 | 20 | Sullivan | NH | 2022-11-15 | 2022-10-30 | 2021-03-05 | River Road 46 kV (Bus No 108291) is same as the previous interconnection QP799 | CNR | FALSE | FALSE |  | PD | NH |  | In Progress |  |  |  | Under Study
979 | 2024-08-26 12:47 | ETU | 2020-03-26 | NECEC 1200 MW HVDC (controllable - import only) CNR | NA | N/A | 0 |  |  | Androscoggin | ME | 2026-01-07 | 2024-09-01 |  | N/A | NI | FALSE | FALSE |  |  | ME |  |  |  |  | Executed
978 | 2023-03-30 12:53 | G | 2020-03-25 | Eversource Group Study @ Wing Lane | PV | SUN | 5.08 | 5.08 | 5.08 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Wing Lane 624 | NA | TRUE | TRUE | NSTAR | PD | SEMA
977 | 2023-03-30 12:52 | G | 2020-03-25 | Eversource Group Study @ Wareham | OT | SUN BAT | 55.14 | 55.14 | 55.14 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Wareham 714 | NA | TRUE | TRUE | NSTAR | PD | SEMA
976 | 2023-03-30 12:51 | G | 2020-03-25 | Eversource Group Study @ Industrial Park | OT | SUN BAT | 11.338 | 11.338 | 11.338 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Industrial Park 636 | NA | TRUE | TRUE | NSTAR | PD | SEMA
975 | 2023-03-30 12:50 | G | 2020-03-25 | Eversource Group Study @ Crystal Spring | OT | SUN BAT | 20.46 | 20.46 | 20.46 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Crystal Spring 646 | NA | TRUE | TRUE | NSTAR | PD | SEMA
974 | 2023-03-30 12:35 | G | 2020-03-25 | Solar plus Battery | OT | SUN BAT | 4.999 | 4.999 | 4.999 | Bristol | MA | 2023-11-30 | 2023-09-30 |  | Eversource Cross Road 651 | NA | TRUE | TRUE | NSTAR | PD | SEMA
973 | 2023-03-30 12:49 | G | 2020-03-25 | Eversource Group Study @ Brook St | OT | SUN BAT | 9.778 | 9.778 | 9.778 | Plymouth | MA | 2023-11-30 | 2023-09-30 |  | Eversource Brook St | NA | TRUE | TRUE | NSTAR | PD | SEMA
972 | 2022-05-16 12:59 | G | 2020-03-25 | Rumford Power Repair for Performance Upgrade | CC | NG | 0.205 | 271 | 280 | Oxford | ME | 2021-11-15 | 2021-11-15 |  | Interconnection of Rumford Power’s 115 kV Bus to CMP’s 115kV bus, located on Rumford Power's support structure, extending to CMP’s 115kV Rumford Industrial Park Substation | CNR | FALSE | FALSE |  | PD | ME |  |  |  |  | Executed
971 | 2024-08-02 11:07 | G | 2020-03-26 | Combined Cycle Upgrade | CC | NG | 4 | 564 | 588 | Fairfield | CT | 2021-07-12 | 2021-07-12 |  | UI Singer Substation | CNR | FALSE | FALSE |  | PD | SWCT |  |  |  |  | Executed | In Service
970 | 2020-07-09 17:02 | G | 2020-03-18 | Wood River Substation - NG Western RI DG Area Study | PV | SUN | 7.84 | 7.84 | 7.84 | Washington | RI | 2021-08-15 | 2021-08-01 |  | NG Wood River Substation | NA | TRUE | TRUE | NGRID | PD | RI
969 | 2020-07-09 17:02 | G | 2020-03-18 | Tower Hill Substation - NG Western RI DG Area Study | PV | SUN | 2 | 2 | 2 | Washington | RI | 2021-08-15 | 2021-08-01 |  | NG Tower Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
968 | 2020-07-09 17:01 | G | 2020-03-18 | Putnam Pike Substation - NG Western RI DG Area Study | PV | SUN | 5.62 | 5.62 | 5.62 | Providence | RI | 2021-08-15 | 2021-08-01 |  | NG Putnam Pike Substation | NA | TRUE | TRUE | NGRID | PD | RI
967 | 2020-07-09 17:01 | G | 2020-03-18 | Old Baptist Road Substation - NG Western RI DG Area Study | PV | SUN | 4.422 | 4.422 | 4.422 | Washington | RI | 2021-08-15 | 2021-08-01 |  | NG Old Baptist Road Substation | NA | TRUE | TRUE | NGRID | PD | RI
966 | 2020-03-19 12:49 | G | 2020-03-18 | New London Substation - NG Western RI DG Area Study | PV | SUN | 3 | 3 | 3 | Kent | RI | 2021-08-15 | 2021-08-01 |  | NG New London Substation | NA | FALSE | FALSE |  | PD | RI
965 | 2020-07-09 17:00 | G | 2020-03-18 | Kent County Substation - NG Western RI DG Area Study | PV | SUN | 10.368 | 10.368 | 10.368 | Kent | RI | 2021-08-15 | 2021-08-01 |  | NG Lafayette No. 30 (supplied by Kent County Substation) | NA | TRUE | TRUE | NGRID | PD | RI
964 | 2020-07-09 16:59 | G | 2020-03-18 | Kenyon Substation - NG Western RI DG Area Study | PV | SUN | 3.5 | 3.5 | 3.5 | Washington | RI | 2021-08-15 | 2021-08-01 |  | NG Kenyon Substation | NA | TRUE | TRUE | NGRID | PD | RI
963 | 2020-07-09 16:59 | G | 2020-03-18 | Johnston Substation - NG Western RI DG Area Study | PV | SUN | 4.25 | 4.25 | 4.25 | Providence | RI | 2021-08-15 | 2021-08-01 |  | NG Johnston Substation | NA | TRUE | TRUE | NGRID | PD | RI
962 | 2020-07-09 16:58 | G | 2020-03-18 | Drumrock - NG Western RI DG Area Study | PV | SUN | 3.85 | 3.85 | 3.85 | Kent | RI | 2021-08-15 | 2021-08-01 |  | NG Drumrock | NA | TRUE | TRUE | NGRID | PD | RI
961 | 2020-07-09 16:58 | G | 2020-03-18 | Wolf Hill substation - NG Western RI DG Area Study | PV | SUN | 2.2 | 2.2 | 2.2 | Providence | RI | 2021-08-15 | 2021-08-01 |  | NG Wolf Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
960 | 2020-07-09 16:57 | G | 2020-03-18 | Chase Hill Substation - NG Western RI DG Area Study | PV | SUN | 6.339 | 6.339 | 6.339 | Washington | RI | 2021-08-15 | 2021-08-01 |  | NG Chase Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
959 | 2025-01-13 10:53 | G | 2020-03-18 | Chase Hill Substation - NG Western RI DG Area Study | PV | SUN | 6.75 | 6.75 | 6.75 | Washington | RI | 2021-08-15 | 2021-08-01 |  | NG feeder 88F1, Chase Hill Substation | NA | TRUE | TRUE | NGRID | PD | RI
958 | 2021-08-04 11:35 | G | 2020-03-18 | Wood River - NG Western RI DG Area Study | PV | SUN | 6.474 | 6.474 | 6.474 | Washington | RI | 2022-01-24 | 2022-01-17 |  | NG feeder 85T2, Wood River Substation | NA | TRUE | TRUE | NGRID | PD | RI
957 | 2022-05-26 10:55 | G | 2020-03-18 | Tower Hill - NG Western RI DG Area Study | PV | SUN | 6.75 | 6.75 | 6.75 | Washington | RI | 2023-01-15 | 2022-12-15 |  | NG feeder 88F1, Tower Hill substation | NA | TRUE | TRUE | NGRID | PD | RI
956 | 2024-05-01 10:53 | G | 2020-03-16 | Solar | PV | SUN | 10 | 10 | 10 | Rockingham | NH | 2024-10-28 | 2024-10-04 | 2024-05-01 | Eversource NH 3103 Line (34.5 kV) out of Brentwood substation extended along Exeter Rd | NR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | In Progress
955 | 2020-08-26 16:03 | G | 2020-03-12 | Vineyard Offshore Wind CNR Only | WT | WND | 0 | 800 | 800 | NA | MA | 2025-05-26 | 2024-01-02 |  | Eversource 115kV Barnstable Switch Station | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
954 | 2023-03-21 09:07 | G | 2020-03-05 | Tiverton Uprate | CC | NG | 0 | 287.5 | 305.5 | Newport | RI | 2021-05-31 | 2021-05-31 |  | Interconnection with Narragansett Electric Company's M13 and L14 115kV line taps to NEC's Tiverton substation. | CNR | FALSE | FALSE |  | PD | SEMA |  |  |  |  | Executed | In Service
953 | 2024-02-14 15:59 | G | 2020-02-19 | BD Solar Church Hill | PV | SUN | 20 | 20 | 20 | Androscoggin | ME | 2026-12-31 | 2026-11-30 |  | 101105 Augusta East w New Breaker | NR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed
952 | 2020-04-08 12:16 | G | 2020-02-18 | Solar | PV | SUN | 4.99 | 4.99 | 4.99 | Androscoggin | ME | 2021-09-30 | 2021-08-31 | 2020-04-08 | CMP 34.5kV line. 44.074807, -70.280400 | NR | FALSE | FALSE |  |  | ME
951 | 2024-11-04 08:21 | G | 2020-02-03 | Riley-Jay-Otis-Livermore | HD | WAT | 28.325 | 28.325 | 28.325 | Androscoggin/Franklin | ME | 2024-11-01 | 2024-02-27 |  | CMP 115 kV Section 230 | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed | Under Construction
950 | 2022-08-23 14:28 | G | 2020-01-20 | Solar | PV | SUN | 17 | 17 | 17 | Oxford | ME | 2024-06-20 | 2024-06-15 | 2022-08-23 | New substation on CMP 34.5 kV circuit Section #97 as shown on one-line | CNR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | In Progress |  |  |  | Under Study
949 | 2023-03-09 14:40 | G | 2020-01-23 | Fuel Cell | FC | NG | 9.66 | 9.66 | 9.66 | Fairfield | CT | 2024-12-01 | 2024-12-01 |  | UI 13.8kV Congress I Substation | NA | TRUE | TRUE | UI |  | SWCT
948 | 2020-11-03 16:20 | G | 2020-01-10 | Solar | PV | SUN | 51.02 | 51.02 | 51.02 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2020-11-03 | Eversource 115kV B-112 transmission line just east of Beebe River Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted |  |  |  |  | Under Study
947 | 2020-03-12 16:38 | G | 2020-01-07 | Battery Storage | OT | BAT | 200 | 200 | 200 | Androscoggin | ME | 2022-12-07 | 2022-12-07 | 2020-03-12 | Sec 377, Approx. 2.71 miles east of Surowiec 345kV bus | CNR | FALSE | FALSE |  | PD | ME
946 | 2020-04-01 10:54 | G | 2019-12-27 | Solar | PV | SUN | 18.4 | 18.4 | 18.4 | York | ME | 2021-08-31 | 2021-08-15 | 2020-04-01 | CMP 34.5 kv, Section 182 | CNR | FALSE | FALSE | CMP | PD | ME
945 | 2021-06-09 09:40 | G | 2019-12-18 | ND OTM LLC Generator Reactivation | ST | BLQ WDS | 8 | 8 | 8 | Penobscot | ME | 2021-06-05 | 2021-06-05 |  | Emera Maine 46 kv Line 5/7 / Old Town Maine @ Penobscot River | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
944 | 2024-08-08 11:23 | G | 2019-12-18 | Bay State Wind 4 Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | MA | 2033-11-04 | 2033-03-27 |  | National Grid Brayton Point 345kV | NR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  | Document Posted | Executed
943 | 2021-11-12 15:03 | G | 2019-12-12 | Solar | PV | SUN | 15 | 15 | 15 | Androscoggin | ME | 2021-11-01 | 2021-10-01 | 2021-11-12 | Interconnecting to the existing CMP 34.5 kV line Section 72 between Gulf Island and Crowleys (about 3.85 miles from Crowleys). | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress | Under Study
942 | 2024-04-29 10:37 | G | 2019-12-10 | Brayton Road Solar | PV | SUN | 8.423 | 8.423 | 8.423 | Newport | RI | 2024-02-15 | 2024-01-09 |  | GRID 33F4 Feeder Connecting to Tiverton No. 2 substation | NA | TRUE | TRUE | NGRID | PD | SEMA
941 | 2024-04-29 10:37 | G | 2019-12-10 | Brayton Road Solar | PV | SUN | 3.368 | 3.368 | 3.368 | Newport | RI | 2024-02-15 | 2024-01-09 |  | GRID 33F4 Feeder Connecting to Tiverton No. 2 substation | NA | TRUE | TRUE | NGRID | PD | SEMA
940 | 2024-11-05 14:17 | G | 2019-12-04 | Gravel Pit Solar increase | PV | SUN | 25 | 75 | 75 | Hartford | CT | 2025-02-07 | 2024-10-28 |  | Line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks. | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed
939 | 2025-01-13 12:00 | G | 2019-11-25 | NB Fuel Cell | FC | NG | 20 | 20 | 20 | Hartford | CT | 2024-12-12 | 2024-05-28 |  | Black Rock Substation (Eversource) via the Farmington River Power Company owned Burritt St substation 69kv line 680 | NR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed | In Service
938 | 2020-09-21 17:03 | G | 2019-11-21 | Solar | PV | SUN | 35 | 35 | 35 | Merrimack | NH | 2022-10-03 | 2022-09-25 | 2020-09-21 | POI is Eversource NH pole 317/153 of the 317 line out of the Oak Hill Substation. | CNR | FALSE | FALSE |  |  | NH | Document Posted |  |  |  |  | Under Study
937 | 2021-08-12 15:32 | G | 2019-11-14 | Solar CNR only | PV | SUN | 0 | 150 | 150 | York | ME | 2022-12-31 | 2022-12-15 | 2021-08-12 | CMP/Eversource 345 kV Line 391 from Buxton substation to Scobie Pond substation (approx. 27.7 miles from Buxton substation) | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed
936 | 2023-12-06 13:53 | G | 2019-10-30 | Solar | PV | SUN | 45 | 45 | 45 | Coos | NH | 2024-10-01 | 2024-09-10 | 2023-12-06 | 115 kV bus of Eversource Paris Substation. | NR | TRUE | TRUE | ISO-NE | NA | NH |  | Document Posted |  |  | In Progress
935 | 2024-08-12 12:36 | G | 2019-10-30 | West Baldwin Solar | PV | SUN | 17.1 | 17.1 | 17.1 | Cumberland | ME | 2029-09-30 | 2029-08-31 |  | CMP 34.5 kv Line, Section 91 | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
934 | 2025-01-06 15:15 | G | 2019-10-25 | Pembroke Solar | PV | SUN | 17.5 | 17.5 | 17.5 | Merrimack | NH | 2024-09-01 | 2024-08-05 | 2025-01-06 | Eversource Pole 334/201 of the 334G Line looped between Garvins & Rimmon, roughly 3.5 miles from Garvins | NR | TRUE | TRUE | ISO-NE | NA | NH |  | Document Posted |  |  | Executed
933 | 2020-12-01 14:45 | G | 2019-10-22 | Coolidge Solar CNR Only | PV | SUN | 0 | 19.9 | 19.9 | Windsor | VT | 2020-11-13 | 2018-12-12 |  | 115 kV Coolidge Substation | CNR | FALSE | FALSE |  | NA | VT |  |  |  |  | Executed
932 | 2023-01-03 11:58 | G | 2019-10-22 | Solar | PV | SUN | 110 | 110 | 110 | Carroll | NH | 2025-10-03 | 2025-09-12 | 2022-11-23 | 115 kV Eversource K1214 line between Saco Valley and Lovell, approximately 3.46 miles from Saco Valley. | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress |  |  |  | Under Study
931 | 2024-10-18 17:16 | G | 2019-10-22 | Roxbury Solar | PV | SUN | 55 | 55 | 55 | Oxford | ME | 2024-10-24 | 2024-10-03 | 2024-10-18 | CMP Roxbury substation 115 kV bus | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
930 | 2022-10-24 14:42 | G | 2019-10-17 | Millstone Increase | ST | NUC | 37 | 1262 | 1262 | New London | CT | 2022-05-26 | 2022-05-26 |  | Eversource's Millstone 345 KV switchyard (15G) - no change to existing connection | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed | In Service
929 | 2023-08-31 14:28 | G | 2019-10-15 | GDC Saco Solar | PV | SUN | 20 | 20 | 20 | York | ME | 2025-04-30 | 2025-03-15 |  | CMP Louden 34.5kV substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
928 | 2023-11-27 09:52 | G | 2019-10-09 | Solar | PV | SUN | 20 | 20 | 20 | Somerset | ME | 2027-04-01 | 2027-03-15 | 2023-11-27 | 34.5 kV bus at CMP's Lakewood Substation in Madison, Maine | CNR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | In Progress
927 | 2024-08-07 16:18 | G | 2019-09-16 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | CT | 2031-05-31 | 2031-01-31 | 2024-08-07 | Primary: Eversource (CL&P) 345kV Montville, Alternatively Eversource (CL&P) 345kV Millstone. | NR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted |  |  | In Progress
926 | 2020-11-06 13:00 | G | 2019-09-11 | Offshore Wind Increase (Q781) | WT | WND | 167 | 871 | 871 | NA | RI | 2023-12-01 | 2023-04-30 | 2020-11-06 | National Grid's 115kV Davisville Substation | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
925 | 2023-05-31 14:50 | ETU | 2019-09-06 | NY QP556 AC | NA | N/A | 0 | 0 | 0 | Onieda/Albany | NY | 2023-12-31 | 2023-12-31 |  | NY Edic - New Scotland 345 kV | N/A | FALSE | FALSE |  | PD | N/A
924 | 2023-05-31 14:49 | ETU | 2019-09-06 | NY QP543 AC | NA | N/A | 0 | 0 | 0 | Albany/Dutchess | NY | 2023-12-31 | 2023-12-31 |  | NY Greenbush PV 345 kV | N/A | FALSE | FALSE |  | PD
923 | 2024-12-30 16:01 | G | 2019-09-03 | Solar | PV | SUN | 20 | 20 | 20 | Androscoggin | ME | 2025-01-15 | 2024-12-14 |  | CMP 34.5 kV Leeds substation | NA | TRUE | TRUE | CMP | PD | ME
922 | 2022-05-24 14:05 | G | 2019-09-03 | Offshore wind Increase (Q829) | WT | WND | 200 | 600 | 600 | NA | MA | 2025-07-01 | 2025-04-01 | 2022-05-24 | NSTAR Electric Company 345 kV lines 322 and 342 | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
921 | 2019-10-21 16:00 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 9.35 | 9.35 | 9.35 | York | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Bonney Easgle substation - Circuit 610D2 | NA | FALSE | FALSE |  | PD | ME
920 | 2019-10-21 15:59 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 11.68 | 11.68 | 11.68 | York | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Biddleford Pump station - Circuit 605D1 | NA | FALSE | FALSE |  | PD | ME
919 | 2019-10-21 15:59 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Knox | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Thomaston Creek substation - Circuit 246D1 | NA | FALSE | FALSE |  | PD | ME
918 | 2019-10-21 15:58 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Howard | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Trap Corner substation, Circuit 453D1 | NA | FALSE | FALSE |  | PD | ME
917 | 2019-10-21 15:57 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 7.5 | 7.5 | 7.5 | Androscoggin | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Great Falls substation, Circuit 436D6 | NA | FALSE | FALSE |  | PD | ME
916 | 2019-10-21 15:56 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Cumberland | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Fort Hill substation, Circuit 624D1 | NA | FALSE | FALSE |  | PD | ME
915 | 2019-10-21 15:56 | G | 2019-08-29 | Solar and Battery | OT | SUN BAT | 5 | 5 | 5 | Oxford | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Rumford substation, Curcuit 447D2 | NA | FALSE | FALSE |  | PD | ME
914 | 2019-10-21 15:55 | G | 2019-08-29 | Solar | PV | SUN | 5 | 5 | 5 | Androscoggin | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Deer Rips substation, curcuit 412D4 | NA | FALSE | FALSE |  | PD | ME
913 | 2019-10-21 15:54 | G | 2019-08-29 | Solar | PV | SUN | 9.98 | 9.98 | 9.98 | Androscoggin | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Hotel Road substation, Curcuit 420D4 | NA | FALSE | FALSE |  | PD | ME
912 | 2021-10-22 08:55 | G | 2019-08-23 | Bloom Energy Fuel Cell | FC | FC | 10.2 | 10.2 | 10.2 | New London | CT | 2021-10-20 | 2021-10-07 |  | Eversource Willimantic 14S | NA | TRUE | TRUE | NU | PD | CT
911 | 2022-07-05 10:36 | G | 2019-08-22 | Solar | PV | SUN | 35 | 35 | 35 | Oxford | ME | 2024-12-30 | 2024-12-14 | 2022-07-05 | 34.5 kV bus at CMP's Lovell Substation. Lat/Lon 44° 7.315'N, 70° 53.332'W | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress
910 | 2022-08-11 16:38 | G | 2019-08-15 | Mousam River Solar | PV | SUN | 20 | 20 | 20 | York | ME | 2025-09-30 | 2025-09-15 |  | 34.5 kV bus at CMP Sanford Substation ( 43° 25.746'N, 70° 44.085'W) | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
909 | 2024-02-13 08:50 | G | 2019-08-01 | Offshore Wind | WT | WND | 814 | 814 | 814 | NA | MA | 2026-05-31 | 2026-04-01 | 2024-02-13 | Primary National Grid 115kV Bell Rock, alt: Eversource 115kV Wings Lane, National Grid 115kV Somerset | NR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
908 | 2019-10-21 15:53 | G | 2019-08-01 | Solar | PV | SUN | 8.999 | 8.999 | 8.999 | Somerset | ME | 2020-12-31 | 2020-12-01 | 2019-10-17 | CMP Skowhegan North Side substation, Circuit 853D1 and 853D2 | NA | FALSE | FALSE |  |  | ME
907 | 2019-10-21 15:52 | G | 2019-08-01 | Solar | PV | SUN | 5 | 5 | 5 | Androscoggin | ME | 2020-08-31 | 2020-08-01 | 2019-10-17 | CMP Hotel Road substation, Circuit 420D4 | NA | FALSE | FALSE |  |  | ME
906 | 2023-03-14 16:05 | G | 2019-08-01 | Solar | PV | SUN | 4.8 | 4.8 | 4.8 | York | ME | 2022-07-14 | 2022-07-01 |  | CMP Pratt & Whitney substation, Circuit 661D2 | NA | TRUE | TRUE | CMP |  | ME
905 | 2025-01-08 11:45 | G | 2019-08-01 | Battery Storage | OT | BAT | 10 | 10 | 10 | Cumberland | ME | 2024-08-01 | 2024-08-01 | 2025-01-08 | CMP Mussey Road substation, Circuit 636D2 | NA | TRUE | TRUE | CMP |  | ME
904 | 2025-01-08 11:44 | G | 2019-08-01 | Battery Storage | OT | BAT | 14 | 14 | 14 | Kennebec | ME | 2024-01-25 | 2024-01-01 | 2025-01-08 | CMP Puddledock substation, circuit 262D1 | NA | TRUE | TRUE | CMP |  | ME
903 | 2022-07-14 09:09 | G | 2019-08-01 | Solar | PV | SUN | 6.999 | 6.999 | 6.999 | Kennebec | ME | 2022-07-13 | 2022-05-24 |  | CMP Winslow substation, Circuit 870D2 | NA | TRUE | TRUE | CMP |  | ME | [5 empty] | Partially In Service
902 | 2021-07-02 11:07 | G | 2019-08-01 | Solar | PV | SUN | 7.2 | 7.2 | 7.2 | Kennebec | ME | 2021-07-02 | 2021-06-22 |  | CMP Blair Road substation, Circuit207D2 | NA | TRUE | TRUE | CMP |  | ME
901 | 2021-06-28 13:11 | G | 2019-08-01 | Solar | PV | SUN | 4.6 | 4.6 | 4.6 | Oxford | ME | 2021-06-14 | 2021-06-04 |  | CMP Oxford substation, Circuit 437D2 | NA | TRUE | TRUE | CMP |  | ME
900 | 2021-06-28 13:10 | G | 2019-08-01 | Solar | PV | SUN | 4.6 | 4.6 | 4.6 | Oxford | ME | 2021-06-14 | 2021-06-04 |  | CMP Oxford subsation, Circuit 437D1 | NA | TRUE | TRUE | CMP |  | ME
899 | 2020-07-31 10:55 | ETU | 2019-07-29 | 1200 MW HVDC Line into Singer (Controllable) | NA | N/A | 1200 |  |  | Fairfield | CT | 2024-09-01 | 2024-07-01 | 2020-07-31 | The proposed point of interconnection is 345kV Singer substation in Bridgeport, CT. | N/A | FALSE | FALSE |  | PD | SWCT | Document Posted | Not Started |  |  |  | Under Study
898 | 2019-08-28 12:43 | G | 2019-07-26 | Solar | PV | SUN | 33.1 | 33.1 | 33.1 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2019-08-28 | NGRID 34.5kV transmission/distribution line 3318 in Monroe, NH | CNR | FALSE | FALSE |  |  | NH
897 | 2019-08-28 12:43 | G | 2019-07-26 | Solar | PV | SUN | 60 | 60 | 60 | Grafton | NH | 2022-06-01 | 2022-05-01 | 2019-08-28 | Eversource 34.5kV bus at the Beebe River Substation | CNR | FALSE | FALSE |  |  | NH
896 | 2024-08-09 09:08 | G | 2019-07-17 | Saco Solar | PV | SUN | 19.6 | 19.6 | 19.6 | York | ME | 2026-07-01 | 2026-06-01 |  | CMPCO 34.5kV Louden Substation Saco, Maine | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  | Document Posted | Executed
895 | 2019-08-09 13:01 | G | 2019-06-27 | CT additional | GT | NG WO | 10 | 37.05 | 43.25 | Tolland | CT | 2021-02-01 | 2021-02-01 | 2019-08-09 | Connecticut Light and Power Company d/b/a Eversource Connecticut (ES CT) Card-Mansfield 900 Line operating at 69 kV at the North Eagleville / King Hill Road intersection | CNR | FALSE | FALSE |  |  | CT
894 | 2021-12-02 09:23 | G | 2019-06-10 | Gas turbine repowering (Alt. to Q647) | GT | DFO NG | 23 | 376 | 378 | Middlesex | CT | 2025-05-31 | 2025-01-16 | 2021-12-02 | Middletown 115 kV substation, Bus A, between breakers 1T and 2T | CNR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Not Started
893 | 2021-10-20 10:01 | G | 2019-06-07 | Offshore Wind | WT | WND | 1200 | 1200 | 1200 | NA | CT | 2025-05-31 | 2024-06-01 | 2021-10-20 | Millstone 345kV alternate: lines 348 and 310 | CNR | FALSE | FALSE |  | PD | CT | Document Posted | In Progress |  |  |  | Under Study
892 | 2021-04-20 12:15 | G | 2019-06-05 | Gravel Pit Solar | PV | SUN | 50 | 50 | 50 | Hartford | CT | 2025-02-07 | 2024-10-28 |  | Line cut and three-breaker ring bus of the 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks | CNR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed
891 | 2020-01-16 13:31 | ETU | 2019-05-29 | 1400 MW HVDC Line into Millstone | NA | N/A | 1400 |  |  | New London | CT | 2024-03-01 | 2024-01-01 | 2020-01-16 | The proposed point of Interconnection is the Eversource Millstone 345kV substation in Waterford, CT - Alternate is Haddam 345 kV Substation | N/A | FALSE | FALSE |  | PD | CT | Not Started |  |  |  |  | Under Study
890 | 2020-06-26 17:07 | ETU | 2019-05-13 | Increase transfer capability for N to S flows (Norwalk Harbor substation to Northport substation) | NA | N/A |  |  |  | NA | CT | 2023-07-01 | 2023-06-02 | 2020-06-26 | N/A | N/A | FALSE | FALSE |  |  | SWCT | In Progress |  |  |  |  | Under Study
889 | 2023-06-05 16:50 | ETU | 2019-05-01 | NECEC Elective Transmission Deliverability Upgrades | NA | N/A |  |  |  | Androscoggin | ME | 2025-08-28 | 2025-08-28 |  | N/A | N/A | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
888 | 2021-03-04 11:56 | G | 2019-04-26 | Millinocket Battery additon | OT | WAT BAT | 0 | 126 | 126 | Penobscot | ME | 2020-12-30 | 2020-12-07 |  | 115/34.5 kV Powersville Rd Substation and Millinocket Sub 4, 34.5 kV Bus | CNR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | Under Construction
887 | 2023-11-14 16:22 | G | 2019-04-26 | Battery Storage | OT | BAT | 150 | 150 | 150 | Plymouth | MA | 2026-05-31 | 2026-04-30 | 2023-11-14 | Eversource Line 113 at Wareham 115 kV substation | NR | TRUE | FALSE | ISO-NE | PD | SEMA | Document Posted | In Progress |  |  |  | Under Study
886 | 2020-03-09 08:27 | G | 2019-04-26 | Battery Storage | OT | BAT | 200 | 200 | 200 | Norfolk | MA | 2023-05-31 | 2023-04-30 | 2020-03-06 | Eversource 345 kV Holbrook | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Under Study
885 | 2019-09-03 11:24 | G | 2019-04-25 | Fuel Cell | FC | NG | 20.24 | 20.24 | 20.24 | Hartford | CT | 2020-06-30 | 2020-05-01 | 2019-09-03 | Black Rock Substation (Eversource) via the Farmington River Power Company owned Burritt St substation 69kv line 680 | CNR | FALSE | FALSE |  |  | CT
884 | 2021-01-12 09:46 | G | 2019-04-24 | Nutmeg Solar CNR only | PV | SUN | 0 | 19.9 | 19.9 | Hartford | CT | 2020-12-07 | 2020-11-15 |  | 115kV Sitico Sub | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
883 | 2022-06-17 14:17 | G | 2019-04-24 | Kendall Combined Cycle increase | CC | DFO NG | 16.449 | 264.953 | 268.523 | Middlesex | MA | 2025-06-01 | 2025-06-01 |  | Kendall CT and Kendall Steam 3: point where Eversource Line 875-539 connects to Eversource 115 kV bus at Station 875. Kendall Jet: point where Eversource breaker J1242 connects to A bus at Kendall Station. | CNR | TRUE | TRUE | ISO-NE | PD | BOST |  | Document Posted |  |  | Executed
882 | 2021-12-14 13:04 | G | 2019-04-24 | Kendall CNR Restoration | CC | DFO NG | 13.551 | 248.504 | 252.074 | Middlesex | MA | 2021-11-04 | 2021-11-04 |  | Kendall CT and Kendall Steam 3: point where Eversource Line 875-539 connects to Eversource 115 kV bus at Station 875. Kendall Jet: point where Eversource breaker J1242 connects to A bus at Kendall Station. | CNR | TRUE | TRUE |  |  | BOST |  | Document Posted |  |  | Executed
881 | 2020-06-02 13:02 | G | 2019-04-18 | Fore River CNR Uprate | CC | DFO NG | 0 | 800 | 843 | Norfolk | MA | 2020-06-01 | 2020-06-01 |  | NSTAR Edgar 115kv substation. | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
880 | 2019-05-15 14:10 | G | 2019-04-17 | Generator reactivation | ST | BLQ WDS | 24 | 24 | 24 | Penobscot | ME | 2020-10-30 | 2020-09-30 | 2019-05-15 | Emera Maine 46kv Line 5/7 / Old Town Maine @ Penobscot River | CNR | FALSE | FALSE |  |  | BHE
879 | 2019-05-28 17:05 | G | 2019-04-15 | Simple Cycle Combustion Turbine Repowering (alternative to Q647) | GT | DFO NG | 0 | 376 | 378 | Middlesex | CT | 2023-05-31 | 2023-01-16 | 2019-05-28 | Middletown 115 kV substation, Bus A, between breakers 1T and 2T | CNR | FALSE | FALSE |  |  | CT
878 | 2019-05-02 16:10 | G | 2019-04-15 | Solar | PV | SUN | 19.8 | 19.8 | 19.8 | Sullivan | NH | 2020-11-05 | 2020-03-05 | 2019-05-01 | Eversource Lost Nation Substation (34.5 kV) | NR | FALSE | FALSE |  | PD | NH
877 | 2024-01-25 15:54 | G | 2019-04-11 | Energy Storage | OT | BAT | 170 | 170 | 170 | Norfolk | MA | 2027-07-26 | 2027-06-26 |  | National Grid's South Wrentham 115kV substation | NR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed
876 | 2021-12-21 09:46 | G | 2019-04-11 | Energy Storage | OT | BAT | 246 | 246 | 246 | Bristol | MA | 2024-12-31 | 2024-10-28 | 2021-12-20 | Eversource 115kV Cross Road Substation Line 109 | CNR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  | In Progress |  | Under Study
875 | 2021-10-27 10:39 | G | 2019-04-08 | Farmington Solar CNR only | PV | SUN | 0 | 78.4 | 78.4 | Franklin | ME | 2021-10-27 | 2021-09-09 |  | CMP's Sturtevant - Livermoore Fall 115 kV line | CNR | FALSE | FALSE |  | NA | ME |  |  |  |  | Executed
874 | 2021-11-29 14:50 | G | 2019-04-08 | Cross Town Battery Storage | OT | BAT | 175 | 175 | 175 | Cumberland | ME | 2025-08-29 | 2025-05-30 |  | CMP Mosher 115kV Substation - Lat: 43°41'2.39"N Long: 70°23'56.24"W | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
873 | 2020-07-02 11:34 | ETU | 2019-04-04 | 1200 MW HVDC Line (controllable) Into Mystic | NA | N/A | 1200 |  |  | Middlesex | MA | 2024-08-01 | 2024-05-01 | 2020-07-02 | The proposed point of Interconnection is: NSTAR Mystic 345kV Substation | N/A | FALSE | FALSE |  | PD | BOST | Document Posted | Not Started |  |  |  | Under Study
872 | 2020-02-10 08:26 | G | 2019-04-01 | Battery Storage | OT | BAT | 180 | 180 | 180 | Washington | RI | 2023-03-01 | 2022-11-15 | 2020-02-08 | National Grid 115kV Kent County- West Kingston line Approx: Latitude: 41°28'50.34"N, Longitude: 71°34'24.82"W | CNR | FALSE | FALSE |  | PD | RI |  | In Progress |  |  |  | Under Study
871 | 2020-01-17 10:27 | G | 2019-03-28 | Energy Storage | OT | BAT | 100 | 100 | 100 | Grafton | NH | 2023-05-31 | 2022-03-01 | 2020-01-17 | PSNH 115kV Littleton substation | CNR | FALSE | FALSE |  | PD | NH |  | In Progress |  |  |  | Under Study
870 | 2024-12-30 16:31 | G | 2019-03-26 | Solar | PV | SUN | 6.22 | 6.22 | 6.22 | Providence | RI | 2025-01-13 | 2022-04-01 |  | NG feeder 26W7, Woonsocket substation | NA | TRUE | TRUE | NGRID | PD | RI
869 | 2024-12-30 16:00 | G | 2019-03-26 | Solar | PV | SUN | 6.22 | 6.22 | 6.22 | Providence | RI | 2025-02-13 | 2022-04-01 |  | NG feeder 26W1, Woonsocket substation | NA | TRUE | TRUE | NGRID | PD | RI
868 | 2024-10-18 17:15 | G | 2019-04-10 | Nellie Solar | PV | SUN | 15 | 15 | 15 | Sullivan | NH | 2024-10-01 | 2024-09-04 | 2024-10-18 | Eversource 34.5 kV line 3410 out of the North Road substation, extended along Maple Street, Newport NH. | NR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  | Executed
867 | 2021-10-27 12:10 | G | 2019-03-21 | Wilbraham substation - NG Western MA Area Cluster Study | PV | SUN | 4 | 4 | 4 | Hampden | MA | 2020-12-03 | 2020-12-03 |  | NG Wilbraham substation | NA | TRUE | TRUE | NGRID |  | WMA
866 | 2021-03-04 09:07 | G | 2019-03-21 | Whitmanville substation - NG Western MA Area Cluster Study | PV | SUN | 26.612 | 26.612 | 26.612 | Worcester | MA | 2020-08-01 | 2020-08-01 |  | NG Whitmanville substation | NA | TRUE | TRUE | NGRID |  | WMA
865 | 2021-10-27 12:09 | G | 2019-03-21 | West Hampden 139 substation - NG Western MA Area Cluster Study | PV | SUN | 13.173 | 13.173 | 13.173 | Hampden | MA | 2023-03-10 | 2019-07-05 |  | NG West Hampden substation | NA | TRUE | TRUE | NGRID |  | WMA
864 | 2021-10-27 12:07 | G | 2019-03-21 | W. Charlton substation - NG Western MA Area Cluster Study | PV | SUN | 17.032 | 17.032 | 17.032 | Worcester | MA | 2022-10-10 | 2020-08-29 |  | NG W. Charlton substation | NA | TRUE | TRUE | NGRID |  | WMA
863 | 2021-10-27 12:05 | G | 2019-03-21 | Treasure Valley substation - NG Western MA Area Cluster Study | PV | SUN | 2.23 | 2.23 | 2.23 | Worcester | MA | 2019-09-19 | 2019-09-19 |  | NG Treasure Valley substation | NA | TRUE | TRUE | NGRID |  | WMA
862 | 2021-10-27 12:03 | G | 2019-03-21 | Stafford Street substation - NG Western MA Area Cluster Study | PV | SUN | 20.38 | 20.38 | 20.38 | Worcester | MA | 2022-10-01 | 2020-08-01 | 2021-10-20 | NG Stafford Street substation | NA | TRUE | TRUE | NGRID |  | WMA
861 | 2021-10-27 12:03 | G | 2019-03-21 | Snow Street substation - NG Western MA Area Cluster Study | PV | SUN | 24.652 | 24.652 | 24.652 | Worcester | MA | 2023-04-05 | 2020-12-31 |  | NG Snow Street substation | NA | TRUE | TRUE | NGRID |  | WMA
860 | 2021-10-27 12:01 | G | 2019-03-21 | Shutesbury substation - NG Western MA Area Cluster Study | PV | SUN | 19.992 | 19.992 | 19.992 | Hampshire | MA | 2023-12-31 | 2021-12-31 |  | NG Shutesbury substation | NA | TRUE | TRUE | NGRID |  | WMA
859 | 2020-02-26 15:36 | G | 2019-03-21 | Prospect Street substation - NG Western MA Area Cluster Study | PV | SUN | 2 | 2 | 2 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2020-02-18 | NG Prospect Street Substation | NA | FALSE | FALSE |  |  | WMA
858 | 2020-02-26 15:38 | G | 2019-03-21 | Pratts Junction substation - NG Western MA Area Cluster Study | PV | SUN | 2 | 2 | 2 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2020-02-18 | NG Pratts Junction substation | NA | FALSE | FALSE |  |  | WMA
857 | 2021-03-04 09:15 | G | 2019-03-21 | Powder Mill substation - NG Western MA Area Cluster Study | PV | SUN | 70.664 | 70.664 | 70.664 | Worcester | MA | 2020-08-01 | 2020-08-01 |  | NG Powder Mill substation | NA | TRUE | TRUE | NGRID |  | WMA
856 | 2021-03-04 08:54 | G | 2019-03-21 | New Salem substation - NG Western MA Area Cluster Study | PV | SUN | 21.272 | 21.272 | 21.272 | Worcester | MA | 2020-08-01 | 2020-08-01 |  | NG New Salem substation | NA | TRUE | TRUE | NGRID |  | WMA
855 | 2021-10-27 12:00 | G | 2019-03-21 | Millbury substation - NG Western MA Area Cluster Study | PV | SUN | 14.44 | 14.44 | 14.44 | Worcester | MA | 2023-11-01 | 2022-05-21 |  | NG Millbury substation | NA | TRUE | TRUE | NGRID |  | WMA
854 | 2021-10-27 11:58 | G | 2019-03-21 | Litchfield substation - NG Western MA Area Cluster Study | PV | SUN | 9.49 | 9.49 | 9.49 | Worcester | MA | 2021-04-30 | 2021-04-30 |  | NG Litchfield substation | NA | TRUE | TRUE | NGRID |  | WMA
853 | 2021-10-27 11:57 | G | 2019-03-21 | East Longmeadow substation - NG Western MA Area Cluster Study | PV | SUN | 8.99 | 8.99 | 8.99 | Hampden | MA | 2022-08-07 | 2019-11-15 |  | NG East Longmeadow | NA | TRUE | TRUE | NGRID |  | WMA
852 | 2021-10-27 11:56 | G | 2019-03-21 | E. Webster substation - NG Western MA Area Cluster Study | PV | SUN | 4.88 | 4.88 | 4.88 | Worcester | MA | 2023-10-01 | 2022-08-09 |  | NG E.. Webster substation | NA | TRUE | TRUE | NGRID |  | WMA
851 | 2020-02-26 15:35 | G | 2019-03-21 | Brookfield substation - NG Western MA Area Cluster Study | PV | SUN | 24 | 24 | 24 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2020-02-18 | NG Brookfield substation | NA | FALSE | FALSE |  |  | WMA
850 | 2021-10-27 11:08 | G | 2019-03-21 | Bear Swamp Upper Yard substation - NG Western MA Area Cluster Study | PV | SUN | 2.5 | 2.5 | 2.5 | Berkshire | MA | 2021-09-08 | 2021-09-08 |  | NG Bear Swamp Upper Yard substation | NA | TRUE | TRUE | NGRID |  | WMA
849 | 2021-10-27 11:10 | G | 2019-03-21 | Ashburnham substation - NG Western MA Area Cluster Study | PV | SUN | 4.98 | 4.98 | 4.98 | Worcester | MA | 2023-01-12 | 2023-01-12 |  | NG Ashburnham substation | NA | FALSE | FALSE |  |  | WMA
848 | 2021-10-27 11:07 | G | 2019-03-21 | Adams substation - NG Western MA Area Cluster Study | PV | SUN | 10.978 | 10.978 | 10.978 | Berkshire | MA | 2021-12-31 | 2021-12-02 |  | NG Adams substation | NA | TRUE | TRUE | NGRID |  | WMA
847 | 2020-03-09 08:26 | G | 2019-03-19 | Battery Storage | OT | BAT | 150 | 150 | 150 | Essex | MA | 2023-05-31 | 2023-04-30 | 2020-03-06 | Primary POI: Expand NGRID S.Danvers 115 kV substation by connecting to B-154N line Alternative POI: Tap B-154N line two spans west of the S. Danvers substation to construct a new three-breaker ring bus | CNR | FALSE | FALSE |  | PD | BOST | Document Posted |  |  |  |  | Under Study
846 | 2022-08-10 13:00 | G | 2019-03-19 | Offshore Wind Increase | WT | WND | 40 | 840 | 840 | NA | MA | 2026-05-31 | 2025-09-21 | 2022-08-10 | National Grid, 345 kV Brayton Point Substation, Somerset, MA | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | Not Started
845 | 2019-11-12 09:31 | G | 2019-03-18 | Solar | PV | SUN | 20 | 20 | 20 | Windham | CT | 2020-07-01 | 2020-06-01 | 2019-11-08 | 3 Breaker Ring Bus on the Eversource 1607 Line (modeling based on same point as Exeter Tap for practical purposes) | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
844 | 2023-10-19 13:46 | G | 2019-03-13 | Medway Grid Battery Storage | OT | BAT | 250 | 250 | 250 | Norfolk | MA | 2025-12-01 | 2025-09-01 |  | Eversource 345 kV West Medway substation | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed | Under Study
843 | 2019-04-18 09:07 | G | 2019-03-07 | Solar | PV | SUN | 12 | 12 | 12 | Essex | VT | 2020-07-01 | 2020-06-01 | 2019-04-18 | POI location: 44.777214,-71.633269 New 34.5 kV Line Tap at VEC Pole 84-872 | CNR | FALSE | FALSE |  |  | VT
842 | 2021-09-27 13:02 | G | 2019-03-05 | Milo Solar | PV | SUN | 20 | 20 | 20 | Pisataquis | ME | 2021-09-25 | 2021-06-02 |  | EMERA 46kV 28 ME-16 Milo, Maine | CNR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted |  |  | Executed | In Service
841 | 2021-12-27 14:19 | G | 2019-03-05 | Quinebaug Solar CNR only | PV | SUN | 0.9 | 49.9 | 49.9 | Windham | CT | 2021-12-18 | 2021-12-11 |  | Killingly to Tunnel 115 kV line (approx 5.5 miles south of Brooklyn Substation) - New Eversource Canterbury switching station. GPS Coordinates: - 71 55’ 27.9” W - 41 44’ 14.21” N | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed | In Service
840 | 2020-11-09 16:13 | G | 2019-03-01 | Sanford Airport Solar CNR only | PV | SUN | 0 | 50 | 50 | York | ME | 2020-11-07 | 2020-10-06 |  | CMP's Sanford - Maguire 115 kV line, section 237 | CNR | FALSE | FALSE |  | NA | ME |  |  |  |  | Executed | In Service
839 | 2023-03-30 17:18 | G | 2019-02-25 | Solar | PV | SUN | 20 | 20 | 20 | Kent | RI | 2023-03-17 | 2023-01-20 |  | GRID 3310 Feeder 34.5 kV to Kent County substation | NA | TRUE | TRUE | NGRID | PD | RI
838 | 2020-08-14 11:31 | G | 2019-02-25 | Solar | PV | SUN | 9.8 | 9.8 | 9.8 | Kent | RI | 2021-09-30 | 2021-09-01 |  | GRID 3310 Feeder 34.5 kV to Kent County substation | NA | TRUE | TRUE | NGRID | PD | RI
837 | 2024-07-17 14:18 | ETU | 2019-02-22 | Somerset Wind Link - 1200 MW HVDC Line (Controllable) into Brayton Point | NA | N/A | 1200 |  |  | Bristol | MA | 2031-12-01 | 2030-05-01 |  | The proposed point of interconnection is: GRID Brayton PT 345kV | N/A | TRUE | TRUE | ISO-NE | PD | RI |  | Document Posted |  | Document Posted | Executed
836 | 2022-01-11 15:24 | G | 2019-01-31 | Solar | PV | SUN | 6.25 | 6.25 | 6.25 | Cranston | RI | 2023-03-01 | 2023-01-01 |  | GRID Feeder 21F1 connected to West Cranston No. 21 substation | NA | TRUE | TRUE | NGRID |  | RI
835 | 2020-06-09 09:30 | G | 2019-01-22 | Solar | PV | SUN | 5 | 5 | 5 | Norfolk | MA | 2021-09-03 | 2021-08-15 |  | GRID 348W7, Pole P53 on Washington St, Franklin | NA | FALSE | FALSE |  | NA | SEMA
834 | 2022-05-16 12:56 | G | 2019-01-17 | GD 1-9 Iron Mine Solar | PV | SUN | 38.4 | 38.4 | 38.4 | N. Smithfield | RI | 2022-05-13 | 2021-12-30 |  | GRID 115 kV H17 Line (via 34.5 kV feeders from new 115/34.5 kV station) | NA | TRUE | TRUE | NGRID | PD | RI
833 | 2023-10-26 14:52 | G | 2019-01-09 | Three Rivers Solar | PV | SUN | 100 | 100 | 100 | Hancock | ME | 2026-12-31 | 2025-12-03 |  | New 115 kV breaker Ring bus, tapping 115 kV Line 93 (Emera Maine) between Bull Hill & Deblois | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | Executed
832 | 2019-09-05 11:40 | G | 2019-01-04 | Battery Storage | OT | BAT | 150 | 150 | 150 | Plymouth | MA | 2021-12-01 | 2021-11-01 | 2019-09-05 | National Grid East Bridgewater 115kV substation, Lat: 42.023890°, Long: -70.966356° | CNR | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
831 | 2021-03-16 08:08 | G | 2018-12-21 | Battery Storage | OT | BAT | 200 | 200 | 200 | Windham | CT | 2024-05-01 | 2024-04-01 | 2021-03-16 | Eversource Killingly 345kV substation, Lat: 41.881266°, Long: -71.891253° | CNR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress
830 | 2022-05-24 14:04 | G | 2018-12-19 | Offshore Wind | WT | WND | 860 | 860 | 860 | NA | MA | 2025-07-01 | 2025-04-01 | 2022-05-24 | NSTAR Electric Company West Barnstable 345 kV. | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
829 | 2022-05-24 14:03 | G | 2018-12-19 | Offshore Wind | WT | WND | 400 | 400 | 400 | NA | MA | 2025-07-02 | 2025-04-01 | 2022-05-24 | NSTAR Electric Company 345 kV lines 322 and 342 | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | In Progress |  |  |  | Under Study
828 | 2021-08-31 10:52 | ETU | 2018-12-14 | ETU for simultaneous delivery of specific Queued projects | NA | N/A |  |  |  | NA | MA | 2025-05-31 | 2025-03-31 | 2021-08-26 | N/A | N/A | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started |  |  |  | Under Study
827 | 2021-10-27 11:14 | G | 2018-12-14 | Westminster - NG Western MA Area Cluster Study | PV | SUN | 4.875 | 4.875 | 4.875 | Worcester | MA | 2021-06-07 | 2021-06-07 |  | NG Westminster | NA | TRUE | TRUE |  | PD | WMA
826 | 2021-10-27 11:05 | G | 2018-12-14 | Wendell Depot Substation - NG Western MA Area Cluster Study | PV | SUN | 14.97 | 14.97 | 14.97 | Franklin | MA | 2021-10-16 | 2021-06-01 |  | NG Wendell Depot Substation | NA | TRUE | TRUE | NGRID | PD | WMA
825 | 2019-05-03 07:56 | G | 2018-12-14 | Webster St - NG Western MA Area Cluster Study | PV | SUN | 9 | 9 | 9 | Worcester | MA | 2020-08-01 | 2020-08-01 | 2019-03-15 | NG Webster St | NA | FALSE | FALSE |  | PD | WMA
824 | 2021-10-27 11:03 | G | 2018-12-14 | Ware Substation - NG Western MA Area Cluster Study | PV | SUN | 13.272 | 13.272 | 13.272 | Hampshire | MA | 2023-12-31 | 2021-07-08 |  | NG Ware Substation | NA | TRUE | TRUE | NGRID | PD | WMA
823 | 2021-10-27 11:02 | G | 2018-12-14 | Thorndike Substation - NG Western MA Area Cluster Study | PV | SUN | 12.448 | 12.448 | 12.448 | Hampden | MA | 2023-12-31 | 2019-10-01 |  | NG Thorndike Substation | NA | TRUE | TRUE | NGRID | PD | WMA
822 | 2021-10-27 11:00 | G | 2018-12-14 | Royalston - NG Western MA Area Cluster Study | PV | SUN | 2.5 | 2.5 | 2.5 | Worcester | MA | 2022-04-26 | 2022-04-26 | 2021-10-20 | NG Royalston | NA | TRUE | TRUE | NGRID | PD | WMA
821 | 2021-10-27 11:13 | G | 2000-12-14 | Pondville - NG Western MA Area Cluster Study | PV | SUN | 4.875 | 4.875 | 4.875 | Worcester | MA | 2022-05-22 | 2022-05-22 |  | NG Pondville | NA | FALSE | FALSE |  | PD | WMA
820 | 2021-10-27 10:59 | G | 2018-12-14 | Palmer Substation - NG Western MA Area Cluster Study | PV | SUN | 18.095 | 18.095 | 18.095 | Hampden | MA | 2022-01-20 | 2019-02-28 |  | NG Palmer Substation | NA | TRUE | TRUE | NGRID | PD | WMA
819 | 2021-10-27 10:57 | G | 2018-12-14 | N. Oxford Substation - NG Western MA Area Cluster Study | PV | SUN | 8.7 | 8.7 | 8.7 | Worcester | MA | 2020-12-30 | 2020-01-31 |  | NG N. Oxford Substation | NA | TRUE | TRUE | NGRID | PD | WMA
818 | 2021-10-27 10:56 | G | 2018-12-14 | Meadow Street 552 Substation - NG Western MA Area Cluster Study | PV | SUN | 13.38 | 13.38 | 13.38 | Worcester | MA | 2022-11-08 | 2020-06-20 |  | NG Meadow Street 552 Substation | NA | TRUE | TRUE | NGRID | PD | WMA
817 | 2021-10-27 10:55 | G | 2018-12-14 | Little Rest Rd Substation - NG Western MA Area Cluster Study | PV | SUN | 6 | 6 | 6 | Worcester | MA | 2022-08-20 | 2020-08-14 |  | NG Little Rest Rd Substation | NA | TRUE | TRUE | NGRID | PD | WMA
816 | 2021-10-27 11:11 | G | 2018-12-14 | Leicester - NG Western MA Area Cluster Study | PV | SUN | 2.592 | 2.592 | 2.592 | Worcester | MA | 2021-05-31 | 2021-05-31 |  | NG Lecester | NA | FALSE | FALSE |  | PD | WMA
815 | 2021-10-27 10:53 | G | 2018-12-14 | Lashaway Substation - NG Western MA Area Cluster Study | PV | SUN | 13.675 | 13.675 | 13.675 | Worcester | MA | 2022-04-15 | 2020-07-20 |  | NG Lashaway Substation | NA | TRUE | TRUE | NGRID | PD | WMA
814 | 2021-10-27 10:52 | G | 2018-12-14 | Five Corners Substation - NG Western MA Area Cluster Study | PV | SUN | 3 | 3 | 3 | Hampshire | MA | 2021-07-29 | 2021-07-29 |  | NG Five Corners Substation | NA | TRUE | TRUE | NGRID | PD | WMA
813 | 2021-10-27 10:51 | G | 2018-12-14 | E. Winchendon Substation - NG Western MA Area Cluster Study | PV | SUN | 3.9 | 3.9 | 3.9 | Worcester | MA | 2022-06-26 | 2022-06-26 |  | NG E. Winchendon Substation | NA | TRUE | TRUE | NGRID | PD | WMA
812 | 2021-10-27 10:49 | G | 2018-12-14 | E. Westminster Substation - NG Western MA Area Cluster Study | PV | SUN | 7.98 | 7.98 | 7.98 | Worcester | MA | 2022-08-01 | 2021-03-28 |  | NG E. Westminster Substation | NA | TRUE | TRUE | NGRID | PD | WMA
811 | 2021-10-27 10:48 | G | 2018-12-14 | Crystal Lake Substation - NG Western MA Area Cluster Study | PV | SUN | 24.73 | 24.73 | 24.73 | Worcester | MA | 2020-12-31 | 2019-04-19 |  | NG Crystal Lake Substation | NA | TRUE | TRUE | NGRID | PD | WMA
810 | 2021-10-27 10:46 | G | 2018-12-14 | Chestnut Hill 702 Substation - NG Western MA Area Cluster Study | PV | SUN | 3.276 | 3.276 | 3.276 | Worcester | MA | 2020-03-05 | 2020-03-05 |  | NG Chestnut Hill 702 Substation | NA | TRUE | TRUE | NGRID | PD | WMA
809 | 2021-10-27 10:45 | G | 2018-12-14 | Belchertown Substation - NG Western MA Area Cluster Study | PV | SUN | 8 | 8 | 8 | Hampden | MA | 2021-08-08 | 2021-06-21 |  | NG Belchertown Substation | NA | TRUE | TRUE | NGRID | PD | WMA
808 | 2021-10-27 10:43 | G | 2018-12-14 | Barre substation - NG Western MA Area Cluster Study | PV | SUN | 12.398 | 12.398 | 12.398 | Worcester | MA | 2022-12-30 | 2021-04-20 |  | NG Barre substation | NA | TRUE | TRUE | NGRID | PD | WMA
807 | 2022-07-13 10:46 | G | 2018-12-13 | FPS Panton Solar | PV | SUN | 50 | 50 | 50 | Addison | VT | 2026-05-31 | 2026-05-01 |  | Vergennes 115 kV Substation | NR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | Executed
806 | 2024-10-02 16:31 | G | 2018-12-12 | Offshore Wind | WT | WND | 827 | 827 | 827 | NA | MA | 2025-10-15 | 2025-08-15 |  | Eversource 345 kV West Barnstable Substation | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  | In Progress |  | Under Study
805 | 2024-12-30 16:00 | G | 2018-12-10 | Solar | PV | SUN | 10.99 | 10.99 | 10.99 | Middletown | RI | 2025-01-15 | 2025-01-15 |  | GRID Jepson 37K33 | NA | TRUE | TRUE | NGRID | PD | RI
804 | 2019-02-04 15:37 | G | 2018-12-10 | Solar | PV | SUN | 5 | 5 | 5 | Windham | CT | 2020-07-01 | 2020-07-01 | 2019-02-04 | Eversource, 23kV, Line 14MX29, POI is ~3.6 miles from Tracy Substation, POI Lat/Long = 41.907528, -71.914968 | CNR | FALSE | FALSE |  |  | CT | Not Started
803 | 2021-08-04 16:45 | G | 2018-12-06 | Solar | PV | SUN | 50 | 50 | 50 | York | ME | 2021-07-01 | 2021-06-01 | 2021-08-04 | Tap CMP existing 115 kV line section 225 approximately 2.25 miles from Sanford 115 kV Substation | CNR | TRUE | FALSE | ISO-NE | PD | ME |  | Document Posted |  |  | In Progress
802 | 2019-08-06 09:41 | G | 2018-12-04 | Generator Increase | ST | MSW | 2.08 | 15.6 | 15.6 | Hartford | CT | 2019-09-03 | 2019-09-03 | 2019-08-06 | Connecticut Light and Powers 13.8 kv Forestville 12A Substation | CNR | TRUE | FALSE | ISO-NE |  | CT |  | In Progress
801 | 2019-02-15 11:44 | G | 2018-11-30 | Solar | PV | SUN | 14 | 14 | 14 | Cheshire | NH | 2022-04-01 | 2022-03-01 | 2019-02-15 | Eversource 34.5 kV distribution circuit #3178, near pole 2/97 on Brattleboro Rd (Rt 119) in Hinsdale, NH Chestnut Hill SS, approx. 3.8 miles away) | NR | FALSE | FALSE |  | PD | NH
800 | 2019-02-14 09:54 | G | 2018-11-30 | Solar | PV | SUN | 19.8 | 19.8 | 19.8 | Somerset | ME | 2022-04-01 | 2022-03-01 | 2019-02-13 | CMP 34.5 kV express feeder at project site (Approx. 2.12 mile feeder originating from CMP North Anson substation) | NR | FALSE | FALSE |  | PD | ME
799 | 2021-03-15 17:58 | G | 2018-11-16 | Solar | PV | SUN | 10 | 10 | 10 | Sullivan | NH | 2021-11-01 | 2021-10-01 | 2021-03-05 | Primary POI - PSNH 46 kV River Road substation; Alternate POI - GMP 46 kV Line 102 | CNR | TRUE | FALSE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  |  | Under Study
798 | 2019-08-02 13:42 | G | 2018-11-08 | Solar | PV | SUN | 15 | 15 | 15 | Androscoggin | ME | 2021-11-01 | 2021-10-01 | 2019-08-02 | Interconnecting to existing CMP 34.5 kV Sabattus substation | CNR | FALSE | FALSE |  | PD | ME | In Progress |  |  |  |  | Under Study
797 | 2020-06-09 09:28 | G | 2018-11-05 | Solar | PV | SUN | 8.125 | 8.125 | 8.125 | Worcester | MA | 2020-12-30 | 2020-12-01 |  | GRID P7 and P8 McCormick Rd/Meadow St 552L5 (Spencer, MA) | NA | TRUE | TRUE | NGRID | PD | WMA
796 | 2018-12-06 15:35 | G | 2018-10-26 | Solar | PV | SUN | 50 | 50 | 50 | Hartford | CT | 2022-11-01 | 2022-10-15 | 2018-12-06 | Tap of existing 115 kV Connecticut Light & Power Company line between Barbour Hill and Windsor Locks | CNR | FALSE | FALSE |  |  | CT
795 | 2022-06-15 15:53 | G | 2018-10-26 | Solar (QF) | PV | SUN | 56.496 | 56.496 | 56.496 | North Kingstown | RI | 2021-06-01 | 2021-05-15 | 2022-04-04 | GRID L-190 line via new station | NA | TRUE | TRUE | NGRID | PD | RI
794 | 2024-12-30 15:59 | G | 2018-10-26 | Solar (QF) | PV | SUN | 10 | 10 | 10 | North Kingstown | RI | 2025-02-01 | 2024-12-31 |  | GRID L-190 line via new station | NA | TRUE | TRUE | NGRID | PD | RI
793 | 2024-12-30 15:57 | G | 2018-10-26 | Solar (QF) | PV | SUN | 40 | 40 | 40 | North Kingstown | RI | 2025-01-30 | 2023-09-29 |  | GRID L-190 line via new station | NA | TRUE | TRUE | NGRID | PD | RI
792 | 2022-01-13 14:44 | G | 2018-10-19 | Offshore Wind | WT | WND | 805 | 805 | 805 | NA | CT | 2023-05-31 | 2023-04-01 | 2022-01-13 | Eversource (CL&P) 345kV Montville, alternatively Eversource (CL&P) 345kV Millstone | CNR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted |  |  | Not Started
791 | 2020-03-06 08:37 | G | 2018-10-19 | Offshore Wind | WT | WND | 805 | 805 | 805 | NA | CT | 2023-05-31 | 2023-04-01 | 2020-03-05 | Eversource (CL&P) 345kV Montville, alternatively Eversource (CL&P) 345kV Millstone | CNR | FALSE | FALSE |  | PD | CT | Document Posted | ISA Not Executed |  |  |  | Under Study
790 | 2019-02-13 09:10 | G | 2018-10-11 | Solar | PV | SUN | 15 | 15 | 15 | Coos | NH | 2020-07-01 | 2020-07-01 | 2019-02-13 | Eversource, 115kV, Line X178-3, POI ~2.2 miles from Whitefield Substation, POI Lat/Long = 44.368066, -71.640429 | CNR | FALSE | FALSE |  | PD | NH | Not Started
789 | 2020-05-19 15:04 | G | 2018-09-28 | CHP | GT | NG | 6.268 | 6.268 | 9.091 | Newport | RI | 2021-06-30 | 2021-06-01 |  | GRID 13.8 kV supplied by 69/13.8 KV Navy Substion in RI | NA | TRUE | TRUE | NGRID | PD | RI
788 | 2022-09-09 14:06 | G | 2018-09-28 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | New London | CT | 2023-12-31 | 2023-07-31 | 2022-09-09 | Primary POI - Eversource Montville Plant 69 kV switchyard via new breaker position. Alternate POI - New 34.5 kV breaker position at Mohegan Tribal Utility Authority (MTUA) Fort Hill Substation. | NR | TRUE | TRUE | ISO-NE |  | CT | Document Posted | Document Posted |  |  | In Progress
787 | 2024-11-27 14:37 | G | 2018-09-26 | Black Hill Point Energy Center | PV | SUN | 19.9 | 19.9 | 19.9 | Windham | CT | 2025-09-25 | 2025-07-31 | 2024-11-27 | New 3 breaker ring bus switching station on Eversource (CL&P) Killingly to Tunnel 115 kV line L-1607. | NR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed | Under Study
786 | 2024-11-27 14:36 | G | 2018-09-26 | Keay Brook Energy Solar | PV | SUN | 19.9 | 19.9 | 19.9 | York | ME | 2025-09-25 | 2025-07-31 | 2024-11-27 | Tap of CMP 34.5 kV Section 185 A TA approximately 3.5 miles north of Lebanon substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
785 | 2024-11-27 14:36 | G | 2018-09-26 | Tilton Heights Energy Center | PV | SUN | 19.9 | 19.9 | 19.9 | Belknap | NH | 2025-09-25 | 2025-07-31 | 2024-11-27 | POI at Eversource 34.5 kV circuit #3216 (sourced from Webster SS) near pole #3798/1. | NR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed
784 | 2020-04-13 12:51 | G | 2018-09-18 | CPV Towantic incremental | CC | DFO NG | 45 | 845.5 | 876.5 | New Haven | CT | 2020-03-01 | 2020-03-01 |  | Eversource 115 KV lines 1575, 1585 and 1990 | CNR | TRUE | TRUE | ISO-NE |  | SWCT |  | Document Posted |  |  | Executed | In Service
783 | 2019-04-17 11:23 | ETU | 2018-09-18 | controllable 150 kV HVDC Tie - Import Only | NA | N/A | 400 |  |  | Addison | VT | 2023-12-31 | 2023-10-31 | 2019-04-17 | a new ~60-mile, 400 MW, ±150 kV, VSC-controlled HVDC transmission line originating from New York Power Authority’s (NYPA) Plattsburgh 230 kV Substation in Plattsburgh, NY and terminating at VELCO’s 345 kV Substation at New Haven, Vermont. The project will deliver a maximum of 400 MW from New York to New England. VGL is an elective transmission upgrade project that will begin in Clinton County, NY, and terminate in Addison County, VT. | CNI | FALSE | FALSE |  | PD | VT |  | In Progress
782 | 2019-09-27 11:00 | G | 2018-09-13 | Offshore Wind | WT | WND | 352 | 352 | 352 | NA | RI | 2024-12-01 | 2024-04-30 | 2019-09-27 | NG 115 kV Kent County substation, RI or alternatively NG 345 kV Kent County Substation, RI | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
781 | 2022-04-27 13:33 | G | 2018-09-13 | Revoultion Offshore wind | WT | WND | 704 | 704 | 704 | NA | RI | 2025-09-07 | 2025-09-07 |  | NG 115 kV Davisville substation, Washington County | NR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | Executed
780 | 2021-10-04 10:07 | G | 2018-09-11 | Combined Reciprocating, Solar and Battery modification | OT | NG SUN BAT | 0 | 7.81 | 7.81 | Middlesex | MA | 2022-05-31 | 2022-05-01 |  | GRID Hendersonville 593 substation (593W1 and 593W4) | NA | TRUE | TRUE | NGRID | PD | BOST
779 | 2021-09-17 16:23 | G | 2018-09-04 | Solar with Battery | OT | SUN BAT | 9.98 | 9.98 | 9.98 | Worcester | MA | 2021-08-03 | 2021-03-31 |  | GRID Circuit 320W1, Pole 9, Puddon Street, Northbridge | NA | TRUE | TRUE | NGRID | PD | WMA
778 | 2021-12-23 11:04 | G | 2018-08-31 | Kearsarge Solar with battery | OT | SUN BAT | 5.4 | 5.4 | 5.4 | Norfolk | MA | 2021-12-21 | 2021-12-06 |  | GRID circuit 335W1, Pole 11 on Williams Way, Bellingham | NA | TRUE | TRUE | NGRID | PD | SEMA
777 | 2019-05-03 07:54 | G | 2018-08-29 | Solar | PV | SUN | 30 | 40 | 40 | North Kingstown | RI | 2020-08-01 | 2020-08-01 | 2019-10-17 | GRID L-190 line | NA | FALSE | FALSE |  | PD | SEMA
776 | 2018-10-22 14:51 | G | 2018-08-29 | Solar | PV | SUN | 10 | 10 | 10 | North Kingstown | RI | 2019-10-01 | 2019-10-01 | 2018-10-17 | GRID 84T3 feeder to Davisville Substation | NA | FALSE | FALSE |  |  | SEMA
775 | 2020-08-21 09:46 | G | 2018-08-20 | Solar | PV | SUN | 20 | 20 | 20 | Kennebec | ME | 2021-11-01 | 2021-10-15 | 2020-08-21 | CMP Albion to Detroit 115 kV line approximately 2.5 miles from Albion | NR | FALSE | FALSE |  | PD | ME | Not Required | In Progress |  |  |  | Under Study
774 | 2020-11-10 15:54 | G | 2018-08-13 | Solar | PV | SUN | 8 | 8 | 8 | Washington | RI | 2021-07-15 | 2021-07-01 |  | GRID 85T1 Woodville Road | NA | TRUE | TRUE | NGRID |  | SEMA
773 | 2020-06-16 11:53 | G | 2018-08-13 | Solar | PV | SUN | 4.95 | 4.95 | 4.95 | Plymouth | MA | 2019-12-18 | 2019-12-01 |  | GRID Circuit 912W75 River Street | NA | TRUE | TRUE | NGRID |  | SEMA
772 | 2019-06-06 11:29 | G | 2018-08-07 | Combined Reciprocating, Solar and Battery | OT | NG SUN BAT | 7.81 | 7.81 | 7.81 | Middlesex | MA | 2019-06-03 | 2019-05-01 |  | GRID Norman Street D substation (8W1) | NA | TRUE | TRUE | NGRID |  | BOST
771 | 2018-08-28 08:49 | G | 2018-07-26 | Battery Storage | OT | BAT | 19.01 | 19.01 | 19.01 | Penobscot | ME | 2019-06-01 | 2019-05-01 | 2018-08-28 | Lincoln (Maine) - 46 kv - bus #103039 | CNR | FALSE | FALSE |  | PD | BHE
770 | 2018-07-27 12:08 | G | 2018-06-20 | Solar | PV | SUN | 10 | 10 | 10 | Rockingham | NH | 2019-06-01 | 2019-05-31 | 2018-07-27 | Eversource 34.5 kV feeder (3184 circuit), Mammoth Rd substation | NA | FALSE | FALSE |  |  | NH
769 | 2018-08-21 15:59 | G | 2018-06-13 | Wind | WT | WND | 7.5 | 7.5 | 7.5 | Berkshire | MA | 2020-03-01 | 2020-02-01 | 2018-08-21 | Eversource 23 kV Feeder Berkshire Substation | NA | FALSE | FALSE |  |  | WMA
768 | 2019-09-30 10:08 | G | 2018-06-13 | Solar with battery addition | OT | SUN BAT | 1.32 | 6.138 | 6.138 | Hampshire | MA | 2019-09-03 | 2019-06-01 |  | Eversource Tillson Substation | NA | TRUE | TRUE |  |  | WMA
767 | 2019-06-03 12:26 | G | 2018-06-13 | Solar | PV | SUN | 20 | 20 | 20 | Fairfield | ME | 2020-11-30 | 2020-09-14 | 2019-06-03 | Tap point on 34.5kV CMP Section 9 approximately 2.2mi west of Shawmut Hydro S/S in the direction of Skowhegan South Side S/S. | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
766 | 2024-04-29 10:34 | G | 2018-05-22 | Solar | PV | SUN | 5.2 | 5.2 | 5.2 | Washington | RI | 2024-11-24 | 2024-11-15 |  | GRID 68F1 feeder (Richmond, RI) | NA | TRUE | TRUE | NGRID |  | RI
765 | 2021-01-25 17:25 | G | 2018-05-09 | Solar | PV | SUN | 10 | 10 | 10 | Providence | RI | 2021-07-15 | 2021-06-30 | 2021-01-25 | GRID 228 circuit 23 kV feeder (7 Mile Rd, Scituate) | NA | TRUE | TRUE | NGRID |  | RI
764 | 2019-09-30 08:51 | G | 2018-05-09 | Solar | PV | SUN | 10 | 10 | 10 | Providence | RI | 2019-09-30 | 2019-08-30 |  | GRID 2228 circuit 23 kV feeder (Hope Rd, Cranston) | NA | TRUE | TRUE | NGRID |  | RI
763 | 2022-06-22 09:50 | G | 2018-04-27 | Davenport Solar | PV | SUN | 15 | 15 | 15 | Rutland | VT | 2021-12-01 | 2021-11-01 | 2022-06-14 | Florence - S. Middlebury Jct. 46 kV line, approx. 4 miles from Florence | NR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | Executed | Under Study
762 | 2018-05-21 11:13 | G | 2018-04-27 | Solar | PV | SUN | 22.5 | 22.5 | 22.5 | Rutland | VT | 2020-08-01 | 2020-05-15 | 2018-05-18 | POI tap of GMP Florence - S. Middlebury Jct. 46 kV line, approx. 4 miles from Florence. Site is 13 acres on Carver Street/Syndicate Road, Brandon, VT 05733 | CNR | FALSE | FALSE |  | PD | VT
761 | 2020-03-26 09:16 | G | 2018-04-27 | Storage | OT | BAT | 150 | 150 | 150 | Middlesex | MA | 2021-05-31 | 2021-04-30 | 2020-03-26 | National Grid 115 kV line M139 | CNR | FALSE | FALSE |  | PD | BOST | Document Posted | In Progress |  |  |  | Under Study
760 | 2023-05-17 16:59 | G | 2018-04-26 | Downeast Wind | WT | WND | 126 | 126 | 126 | Washington | ME | 2025-01-31 | 2024-12-02 |  | Primary POI: Emera Maine 115 line 52 near Epping switching station Alternate POI: Epping station | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | Executed
759 | 2022-08-12 14:12 | G | 2018-04-26 | Wallingford GT Uprate | GT | NG | 0 | 350 | 350 | New Haven | CT | 2022-05-31 | 2022-05-31 |  | WED 115kV Lines 1305 and 1406 | CNR | FALSE | FALSE |  |  | SWCT |  |  |  |  | Executed | In Service
758 | 2023-05-17 16:58 | G | 2018-04-26 | Ocean State Power uprate | CC | DFO NG | 73.204 | 631.2 | 652.342 | Providence | RI | 2025-11-30 | 2025-11-30 |  | NGRID 345kV Sherman Road (existing OSP I and II switchyard) | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted | Document Posted |  | Executed
757 | 2020-08-12 16:44 | G | 2018-04-26 | Solar | PV | SUN | 20 | 20 | 20 | Somerset | ME | 2021-11-01 | 2021-10-15 | 2020-08-12 | Approximately at 44°42'47.78"N, 69°39'15.37"W at proposed interconnection substation to tap CMP Section 83 line and SAPI Somerset generator tap line. Substation to have short gen tie line to project site located between Kendall Annex Road and Middle Road in Fairfield, Maine | CNR | FALSE | FALSE |  | PD | ME | Document Posted | In Progress |  |  |  | Under Study
756 | 2020-08-12 16:43 | G | 2018-04-26 | Solar | PV | SUN | 20 | 20 | 20 | Kennebec | ME | 2021-11-01 | 2021-10-15 | 2020-08-12 | CMP Albion to Detroit 115 kV line approximately 2.5 miles from Albion. | CNR | FALSE | FALSE |  | PD | ME | Document Posted | In Progress |  |  |  | Under Study
755 | 2018-12-27 11:54 | G | 2018-04-25 | Bingham Wind CNR Only | WT | WND | 0 | 184.8 | 184.8 | Somerset | ME | 2016-12-13 | 2016-08-15 |  | CMP 115kV Guilford Substation | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
754 | 2021-11-01 08:14 | G | 2018-04-25 | Solar | PV | SUN | 30 | 30 | 30 | Cheshire | NH | 2024-07-30 | 2024-06-30 | 2021-10-31 | Primary: NGRID 115 KV Line I-135 between Fitzwilliam Sub and Flagg Pond Sub Alternate 1: NGRID 115 KV Line J-136 between Bellows Falls Sub and Flagg Pond Sub Alternate 2: Eversource 115 KV Bus at Monadnock Substation via short 115 KV gentie line from project site | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  | In Progress | Under Study
753 | 2019-08-06 09:28 | G | 2018-04-20 | Solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2021-11-01 | 2021-10-15 | 2019-08-06 | VEC Sheldon Substation - 46 kV | CNR | FALSE | FALSE |  | PD | VT | In Progress |  |  |  |  | Under Study
752 | 2019-05-14 08:10 | G | 2018-04-19 | Energy Storage | OT | BAT | 102.85 | 102.85 | 102.85 | Bristol | MA | 2022-05-02 | 2022-03-02 | 2019-05-13 | Eversource 115kV Cross Road Substation [both buses at Cross Road Substation (bus/line 111 = primary; bus/line 109 = alternate)] | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Under Study
751 | 2020-08-12 16:42 | G | 2018-04-12 | Solar | PV | SUN | 20 | 20 | 20 | Orange | VT | 2021-11-01 | 2021-10-15 | 2020-08-12 | GMP's Randolph Center substation 46 kV | CNR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | In Progress | Under Study
750 | 2019-08-06 09:27 | G | 2018-04-12 | Solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2021-11-01 | 2021-10-15 | 2019-08-06 | VEC's Highgate - Enosburg 46 kV line, 700 feet from Highgate | CNR | FALSE | FALSE |  |  | VT | Document Posted | Not Started |  |  |  | Under Study
749 | 2019-08-28 08:16 | G | 2018-04-12 | Solar | PV | SUN | 150 | 150 | 150 | Franklin | ME | 2021-10-31 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road 345 kV | CNR | FALSE | FALSE |  | PD | ME
748 | 2019-08-28 08:15 | G | 2018-04-12 | Battery storage addition (see Q746) | OT | WND BAT | 24.3 | 238.6 | 238.6 | Franklin | ME | 2021-10-31 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME
747 | 2019-08-28 08:14 | G | 2018-04-12 | Battery storage addition (see Q745) | OT | WND BAT | 24.4 | 265.6 | 265.6 | Franklin | ME | 2021-10-31 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road Station,345 kV | CNR | FALSE | FALSE |  | PD | ME
746 | 2019-08-28 08:13 | G | 2018-04-12 | Wind | WT | WND | 214.3 | 214.3 | 214.3 | Franklin | ME | 2021-12-15 | 2021-10-29 | 2019-08-27 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME
745 | 2019-08-28 08:09 | G | 2018-04-12 | Wind | WT | WND | 241.2 | 241.2 | 241.2 | Franklin | ME | 2021-10-29 | 2021-08-01 | 2019-08-27 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME
744 | 2019-02-07 18:47 | G | 2018-04-12 | Wind | WT | WND | 150 | 150 | 150 | Franklin | ME | 2022-12-01 | 2022-09-01 | 2019-02-07 | Approximate location of the proposed Point of Interconnection is the CMP Avangrid Larrabee Road 345 kV Substation | CNR | FALSE | FALSE |  | PD | ME
743 | 2019-02-07 18:46 | ETU | 2018-04-12 | noncontrollable ETU from Quebec to ME | NA | N/A | 450 |  |  | Franklin | ME | 2022-12-01 | 2022-09-01 | 2019-02-07 | CMP/Avangrid 345 kV Larabee Road | N/A | FALSE | FALSE |  | PD | ME
742 | 2020-12-01 13:10 | ETU | 2018-04-12 | Internal noncontrollable ETU to Larabee Road - increase (see Q740 and Q741) | NA | N/A | 540 |  |  | Lewiston | ME | 2021-12-31 | 2021-11-30 | 2020-11-29 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | N/A | FALSE | FALSE |  | PD | ME
741 | 2020-12-01 13:10 | ETU | 2018-04-12 | Internal noncontrollable ETU to Larabee Road - increase (see Q740) | NA | N/A | 200 |  |  | Lewiston | ME | 2021-12-31 | 2021-11-30 | 2020-11-29 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | N/A | FALSE | FALSE |  | PD | ME
740 | 2020-12-01 13:12 | ETU | 2018-04-12 | Internal noncontrollable ETU to Larabee Road | NA | N/A | 460 |  |  | Lewiston | ME | 2021-12-31 | 2021-11-30 | 2020-11-29 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240 | N/A | FALSE | FALSE |  | PD | ME
739 | 2019-01-17 09:10 | G | 2018-04-12 | Wind | WT | WND | 89.7 | 89.7 | 89.7 | Somerset | ME | 2020-01-30 | 2020-01-15 | 2019-01-16 | CMP Section 3023 345kV line (via Johnson Mountain Substation) | CNR | FALSE | FALSE |  | PD | ME
738 | 2020-12-01 13:09 | ETU | 2018-04-12 | Internal noncontrollable ETU - interface upgrade | NA | N/A | 400 |  |  | Cumberland | ME | 2019-11-30 | 2019-10-31 | 2020-11-30 | N/A | N/A | FALSE | FALSE |  | PD | ME
737 | 2019-02-07 18:45 | ETU | 2018-04-12 | Internal noncontrollable ETU from NMISA to Pittsfield ME | NA | N/A | 1200 |  |  | Somerset and Penobscot | ME | 2021-12-31 | 2021-11-30 | 2019-02-07 | Emera Keene Rd substation and CMP Section 3023 345 kV Line | N/A | FALSE | FALSE |  | PD | ME
736 | 2019-02-07 18:45 | ETU | 2018-04-12 | Internal noncontrollable ETU to Pittsfield ME | NA | N/A | 550 |  |  | Somerset | ME | 2021-12-31 | 2021-11-30 | 2019-02-07 | CMP Section 3023 345 kV | N/A | FALSE | FALSE |  | PD | ME
735 | 2019-02-07 18:44 | G | 2018-04-12 | Wind | WT | WND | 600.6 | 600.599 | 600.599 | Aroostook | ME | 2021-12-01 | 2021-11-01 | 2019-02-07 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE
734 | 2019-02-07 18:44 | G | 2018-04-12 | Wind | WT | WND | 600.6 | 600.5999 | 600.5999 | Aroostook | ME | 2021-12-01 | 2021-11-01 | 2019-02-07 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE
733 | 2020-12-01 14:24 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
732 | 2020-12-01 14:24 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
731 | 2020-12-01 14:23 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
730 | 2020-12-01 14:22 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
729 | 2020-12-01 14:22 | G | 2018-04-12 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Aroostook | ME | 2022-11-20 | 2022-09-03 | 2020-12-01 | PITTSFIELD 345KV on line 3023 | CNR | FALSE | FALSE |  | PD | BHE
728 | 2019-06-28 16:52 | G | 2018-04-02 | Vernon Station Incremental Capacity Increase | HD | WAT | 2.9 | 34.9 | 34.9 | Windham | VT | 2019-03-31 | 2019-03-31 |  | (Same as Existing POI Vernon Substation No.13 69 KV Bus) Street Address: 152 Governor Hunt Road | CNR | FALSE | FALSE |  |  | VT |  |  |  |  | Executed | In Service
727 | 2025-01-13 17:41 | G | 2018-04-10 | Chariot Solar | PV | SUN | 49.5 | 49.5 | 49.5 | Cheshire | NH | 2024-12-15 | 2024-11-15 | 2025-01-13 | NGrid 115 kV Vernon Road tap to Vernon Road Substation, 2.5 mi from Vernon Road Substation | NR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | Executed
726 | 2022-11-07 11:33 | G | 2018-03-21 | Cranberry Point Energy Storage | OT | BAT | 150 | 150 | 150 | Plymouth | MA | 2025-05-30 | 2025-03-14 |  | Carver 115 kV Primary POI – Loop-in station with 3-breaker ring bus interconnecting to line 127 located just south of Carver substation Alternate POI – Expand the existing station to add a 4th bay with 2 breakers to interconnect the project. | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed
725 | 2021-01-21 12:10 | G | 2018-03-20 | Wallingford Solar | PV | SUN | 14.97 | 14.97 | 14.97 | New Haven | CT | 2020-12-18 | 2020-10-30 |  | WED Wallingford 13.8 KV substation | NA | TRUE | TRUE | ISO-NE |  | SWCT
724 | 2023-08-31 17:03 | G | 2018-03-07 | NTE Connecticut | CC | DFO NG | 672 | 671 | 692 | Windham | CT | 2025-02-28 | 2024-11-15 | 2023-07-12 | Lake Road 345 kV | CNR | TRUE | TRUE | ISO-NE |  | CT |  | In Progress |  |  | Executed
723 | 2019-05-06 12:43 | G | 2018-03-01 | Battery Storage | OT | BAT | 142.8 | 142.8 | 142.8 | Barnstable | MA | 2021-05-31 | 2021-04-30 | 2019-03-27 | Primary POI: Eversource 115 kV W. Barnstable Alternative POI 1: Eversource 115 kV Barnstable Alternative POI 2: New Eversource W. Barnstable – Bourne 115 kV line (RSP #1725) tapped at 51% (7.2 miles) from W. Barnstable substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted | Not Started
722 | 2018-04-25 12:44 | G | 2018-02-21 | Solar | PV | SUN | 24.6 | 24.6 | 24.6 | Hartford | CT | 2020-01-01 | 2019-12-31 | 2018-04-25 | Eversource North Simsbury | NA | FALSE | FALSE |  |  | CT
721 | 2018-04-25 12:43 | G | 2018-02-21 | Solar | PV | SUN | 26.4 | 26.4 | 26.4 | Hartford | CT | 2020-01-01 | 2019-12-31 | 2018-04-25 | Eversource North Simsbury | NA | FALSE | FALSE |  |  | CT
720 | 2022-10-03 10:49 | G | 2018-02-21 | Solar | PV | SUN | 15 | 15 | 15 | New London | CT | 2022-10-01 | 2022-08-29 |  | Eversource Shunock 32P | NA | TRUE | TRUE | NU |  | CT
719 | 2018-04-25 12:43 | G | 2018-02-21 | Solar | PV | SUN | 19.92 | 19.92 | 19.92 | Hartford | CT | 2021-01-01 | 2020-12-31 | 2018-04-25 | Eversource Barber Hill 23J | NA | FALSE | FALSE |  |  | CT
718 | 2018-03-05 09:37 | G | 2018-02-21 | Solar | PV | SUN | 6 | 6 | 6 | New London | CT | 2019-04-02 | 2019-04-01 | 2018-03-02 | Eversource 13B25 Feeder | NA | FALSE | FALSE |  |  | CT
717 | 2022-05-26 09:12 | G | 2018-02-21 | Battery Storage | OT | BAT | 20 | 20 | 20 | Hartford | CT | 2022-02-01 | 2021-12-01 | 2022-05-26 | Eversource North Bloomfield 2A | NA | FALSE | FALSE |  |  | CT
716 | 2023-09-19 08:40 | G | 2018-02-21 | Solar | PV | SUN | 17.73 | 17.73 | 17.73 | New London | CT | 2023-08-18 | 2023-04-26 |  | Eversource Waterford 36F2 | NA | TRUE | TRUE | NU |  | CT
715 | 2018-10-03 14:32 | G | 2018-02-21 | Fusion Solar Center | PV | SUN | 20 | 20 | 20 | New London | CT | 2018-04-18 | 2018-04-12 |  | Eversource Tunnel 12S | NA | TRUE | TRUE | NU |  | CT
714 | 2023-03-09 15:00 | G | 2018-02-21 | Solar | PV | SUN | 20 | 20 | 20 | Windham | CT | 2023-06-01 | 2023-03-01 | 2023-03-09 | Eversource Frybrook 13B | NA | TRUE | TRUE | NU |  | CT
713 | 2019-12-17 11:53 | G | 2018-02-21 | Solar | PV | SUN | 26.4 | 26.4 | 26.4 | Hartford | CT | 2019-12-10 | 2019-10-01 |  | Eversource North Simsbury | NA | TRUE | TRUE | NU |  | CT
712 | 2023-02-15 13:50 | G | 2018-02-21 | Solar | PV | SUN | 20 | 20 | 20 | Windham | CT | 2025-06-30 | 2025-06-15 | 2023-02-15 | Eversource Frybrook 13B | NA | TRUE | TRUE | NU |  | CT
711 | 2024-04-10 15:46 | G | 2018-02-21 | Solar | PV | SUN | 9.99 | 9.99 | 9.99 | New London | CT | 2024-03-30 | 2024-02-29 |  | Eversource Shunock 32P | NA | TRUE | TRUE | NU |  | CT
710 | 2024-12-30 15:56 | G | 2018-02-21 | Solar | PV | SUN | 19.8 | 19.8 | 19.8 | Litchfield | CT | 2025-01-07 | 2024-11-13 |  | Eversource 14R31 Feeder | NA | TRUE | TRUE | NU |  | CT
709 | 2020-10-08 14:08 | G | 2018-02-21 | Fuel Cell | FC | FC | 14.8 | 14.8 | 14.8 | Hartford | CT | 2021-01-01 | 2020-12-31 | 2020-10-01 | Eversource 12A Forestville | NA | FALSE | FALSE |  |  | CT
708 | 2024-05-10 15:23 | G | 2018-02-21 | Solar | PV | SUN | 20 | 20 | 20 | Litchfield | CT | 2024-02-01 | 2023-12-01 | 2024-05-10 | Eversource Rocky river 12Y | NA | TRUE | TRUE | NU |  | CT
707 | 2019-04-03 08:50 | G | 2018-02-21 | Solar | PV | SUN | 7.5 | 7.5 | 7.5 | Windham | CT | 2019-04-01 | 2019-03-31 | 2019-04-03 | Eversource 11F10 Feeder | NA | FALSE | FALSE |  |  | CT
706 | 2020-02-04 15:34 | G | 2018-02-21 | Beacon Falls Energy Park CNR only | FC | FC | 0 | 62.9 | 62.9 | New Haven | CT | 2022-04-01 | 2022-02-01 | 2020-01-30 | Eversource, Beacon Falls Substation, 180 Cold Spring Rd, Beacon Falls, Junction of the 115 kV lines 1570-1 and 1319 | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
705 | 2019-11-26 15:27 | G | 2018-01-26 | Combined Cycle CNR | CC | NG | 0 | 1030 | 1080 | Providence | RI | 2023-05-31 | 2023-02-01 | 2019-11-26 | Sherman Road 345kV substation | CNR | FALSE | FALSE |  |  | RI |  |  |  |  | In Progress
704 | 2020-10-08 14:09 | G | 2018-01-24 | Solar | PV | SUN | 1.904 | 1.904 | 1.904 | Bristol | MA | 2020-02-21 | 2020-02-21 |  | NSTAR Wing Lane Substation, #1 bank | NA | FALSE | FALSE |  |  | SEMA
703 | 2020-01-10 13:39 | G | 2018-01-24 | Solar | PV | SUN | 6.75 | 6.75 | 6.75 | Plymouth | MA | 2019-04-23 | 2019-04-15 |  | NSTAR Crystal Spring Substation 13.2 kV bus | NA | TRUE | TRUE | NSTAR |  | SEMA | [5 empty] | Partially In Service
702 | 2019-07-11 12:31 | G | 2018-01-24 | Solar | PV | SUN | 9.5 | 9.5 | 9.5 | Plymouth | MA | 2019-07-10 | 2019-06-28 |  | NSTAR Wareham Substation 23 kV bus | NA | TRUE | TRUE | NSTAR |  | SEMA
701 | 2019-02-14 15:32 | G | 2017-12-15 | Offshore Wind | WT | WND | 400 | 400 | 400 | NA | MA | 2023-12-01 | 2023-08-01 | 2019-02-14 | Brayton Point Substation in the Town of Somerset, Massachusetts or alternatively at Davisville Substation in the Town of North Kingstown, Rhode Island | CNR | FALSE | FALSE |  | PD | RI | In Progress |  |  |  |  | Under Study
700 | 2022-09-16 09:41 | G | 2017-12-15 | Park City Offshore Wind | WT | WND | 791 | 791 | 791 | NA | MA | 2029-12-31 | 2029-05-01 |  | Eversource 345 kV West Barnstable Substation | NR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed
699 | 2019-02-14 11:40 | G | 2017-12-13 | Offshore Wind with battery addition | OT | WND BAT | 75 | 875 | 875 | NA | MA | 2023-05-31 | 2022-04-30 | 2019-02-14 | National Grid 345 kV Brayton Point Substation, Somerset, MA | CNR | FALSE | FALSE |  |  | RI | Document Posted
698 | 2020-03-06 11:37 | G | 2017-12-07 | Solar | PV | SUN | 8.04 | 8.04 | 8.04 | Worcester | MA | 2020-02-05 | 2020-02-03 |  | GRID 13.8 kV 612W3 Feeder (Pole 53) | NA | TRUE | TRUE | NGRID | PD | CMA
697 | 2020-03-06 11:37 | G | 2017-12-07 | Solar | PV | SUN | 5.97 | 5.97 | 5.97 | Worcester | MA | 2020-02-05 | 2020-02-03 |  | GRID 13.8 kV 612W1 Feeder (Pole 53) | NA | TRUE | TRUE | NGRID | PD | CMA
696 | 2019-04-22 15:18 | G | 2017-11-27 | Johnston Landfill Wind | WT | WND | 21 | 21 | 21 | Providence | RI | 2018-12-20 | 2018-12-10 |  | GRID Johnston substation, Circuit 2227 | NA | TRUE | TRUE | NGRID | NA | RI
695 | 2020-08-14 09:50 | G | 2017-11-20 | Solar | PV | SUN | 6.12 | 6.12 | 6.12 | Washington | RI | 2020-09-01 | 2020-05-01 | 2020-08-14 | GRID circuit 88F3 | NA | TRUE | TRUE | NGRID | NA | RI
694 | 2020-08-14 09:49 | G | 2017-11-20 | Solar | PV | SUN | 7 | 7 | 7 | Washington | RI | 2020-09-01 | 2020-05-01 | 2020-08-14 | GRID circuit 88F3 | NA | TRUE | TRUE | NGRID | NA | RI
693 | 2020-07-09 15:53 | G | 2017-11-20 | Alton Solar | PV | SUN | 13.875 | 13.875 | 13.875 | Washington | RI | 2020-04-30 | 2020-04-24 |  | Grid 85T3 circuit | NA | TRUE | TRUE | NGRID | NA | RI
692 | 2019-05-24 09:08 | G | 2017-11-20 | Solar | PV | SUN | 16.25 | 16.25 | 16.25 | Providence | RI | 2019-05-24 | 2019-05-22 |  | GRID 23 kV 2228 circuit/Grid 12.47 kV 21F1 circuit | NA | TRUE | TRUE | NGRID | NA | RI
691 | 2020-11-10 15:27 | G | 2017-11-20 | University Solar | PV | SUN | 31.34 | 31.34 | 31.34 | Kent | RI | 2020-09-15 | 2020-05-07 |  | GRID 3311 circuit in West Greenwich | NA | TRUE | TRUE | NGRID | NA | RI
690 | 2018-02-09 13:51 | G | 2017-11-21 | Energy Storage | OT | BAT | 100 | 100 | 100 | Bristol | MA | 2021-12-31 | 2021-09-01 | 2018-02-09 | Wing Lane 624 Eversource Energy 115KV | CNR | FALSE | FALSE |  | PD | SEMA
689 | 2020-02-16 13:11 | G | 2017-11-21 | Energy Storage | OT | BAT | 100 | 100 | 100 | Middlesex | MA | 2023-05-31 | 2023-02-01 | 2020-02-14 | Wakefield 115 kV Substation Bus (Bus #114433) | CNR | TRUE | FALSE | ISO-NE | PD | BOST | Document Posted | Document Posted |  |  | In Progress | Under Study
688 | 2020-06-09 08:15 | G | 2017-11-21 | Energy Storage | OT | BAT | 50 | 50 | 50 | Worcester | MA | 2021-12-31 | 2021-09-01 | 2018-02-09 | Little Rest Road 516 New England Power Co 115KV | CNR | FALSE | FALSE |  | NA | CMA
687 | 2019-02-06 16:13 | G | 2017-11-21 | Energy Storage | OT | BAT | 150 | 150 | 150 | Barnstable | MA | 2021-12-31 | 2021-09-09 | 2019-02-06 | Falmouth 533 Eversource Energy 115KV | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted |  |  |  |  | Suspended
686 | 2020-03-12 11:59 | G | 2017-10-24 | Solar | PV | SUN | 19.98 | 19.98 | 19.98 | Berkshire | MA | 2021-12-15 | 2021-09-15 | 2020-03-12 | National Grid 115kV line F132-2 | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | In Progress
685 | 2019-11-26 15:26 | G | 2017-10-20 | Solar | PV | SUN | 20 | 20 | 20 | Coos | NH | 2022-07-01 | 2022-06-01 | 2019-11-26 | 34.5 kV Express Feeder to Berlin substation | CNR | FALSE | FALSE |  |  | NH | Document Posted | In Progress |  |  |  | Under Study
684 | 2019-05-14 08:34 | G | 2017-10-20 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2020-07-01 | 2020-06-01 | 2019-05-10 | 34.5 kV bus at Eversource NH Beebe Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted |  |  |  |  | Under Study
683 | 2019-05-21 14:37 | G | 2017-10-20 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2020-07-01 | 2020-06-01 | 2019-05-21 | 34.5 kV bus at Eversource NH Beebe Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted | Not Started |  |  |  | Under Study
682 | 2018-07-25 08:29 | G | 2017-09-18 | solar with battery | OT | SUN BAT | 20.005 | 20 | 20 | Worcester | MA | 2020-12-01 | 2020-11-17 | 2018-07-24 | National Grid 13.8kV circuit (E.-Winchendon Substation) on Winchendon Road (near Depot Road), Winchendon, MA | CNR | FALSE | FALSE |  |  | CMA | Document Posted | Not Started
681 | 2021-01-26 14:57 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2022-07-01 | 2022-06-01 | 2021-01-26 | Eversource 34.5 kV between Thornton and Beebe River | CNR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | In Progress
680 | 2021-05-20 11:23 | G | 2017-08-03 | Fair Haven Solar | PV | SUN | 20 | 20 | 20 | Rutland | VT | 2026-01-01 | 2025-12-01 |  | GMP 46 kV between Carver Falls and Fair Haven Tap | NR | TRUE | TRUE | ISO-NE | NA | VT |  | Document Posted |  |  | Executed
679 | 2021-01-26 14:56 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Hillsborough | NH | 2022-07-01 | 2022-06-01 | 2021-01-26 | Eversource NH 34.5 kV line 313, between South Peterborough and Monadnock substations. The Project will tap this line at about 0.1-0.5 miles south of the South Peterborough substation. | CNR | TRUE | TRUE | ISO-NE | NA | VT | Document Posted | Document Posted |  |  | In Progress
678 | 2017-10-25 08:15 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2019-07-01 | 2019-06-01 | 2017-10-24 | Eversource 34.5 kV Beebe River substation | CNR | FALSE | FALSE |  |  | NH
677 | 2017-10-25 08:14 | G | 2017-08-03 | Solar | PV | SUN | 20 | 20 | 20 | Grafton | NH | 2019-07-01 | 2019-06-01 | 2017-10-24 | Eversource 34.5 kV Beebe River Substation | CNR | FALSE | FALSE |  |  | NH
676 | 2021-10-05 16:22 | G | 2017-08-03 | Claremont Solar | PV | SUN | 20 | 20 | 20 | Sullivan | NH | 2023-07-01 | 2023-06-01 | 2021-10-05 | GMP 46 kV line 107 between High Bridge and Windsor | NR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | Executed
675 | 2017-12-07 09:42 | G | 2017-07-28 | Solar | PV | SUN | 22 | 22 | 22 | New London | CT | 2019-12-31 | 2019-11-01 | 2017-09-27 | Eversource Bean Hill - Tunnel 115 kV | CNR | FALSE | FALSE |  |  | CT
674 | 2021-05-20 11:24 | G | 2017-07-28 | Shaftsbury Solar | PV | SUN | 20 | 20 | 20 | Bennington | VT | 2026-01-01 | 2025-12-01 |  | GMP 46 kV between East Arlington and S. Shaftsbury Tap | NR | TRUE | TRUE | ISO-NE | NA | VT | Document Posted | Document Posted |  |  | Executed
673 | 2017-11-27 15:08 | G | 2017-07-26 | wind | WT | WND | 20 | 20 | 20 | Franklin | VT | 2020-12-31 | 2020-10-01 | 2017-11-27 | Green Mountain Power 34.5kV TL 137 Line between North St. Albans and Sheldon Springs Substations along State Route 105 in Swanton Vermont (approximately at pole 44) | CNR | FALSE | FALSE |  |  | VT | In Progress |  |  |  |  | Under Study
672 | 2019-10-22 08:38 | G | 2017-07-26 | Wind | WT | WND | 630 | 630 | 630 | Aroostook | ME | 2022-12-31 | 2022-11-30 | 2019-10-22 | NSTAR 345 kV K Street substation. | CNR | FALSE | FALSE |  | CD | BHE |  | In Progress |  |  |  | Under Study
671 | 2017-10-25 11:23 | G | 2017-07-26 | Solar | PV | SUN | 26 | 26 | 26 | Hartford | CT | 2019-12-01 | 2019-10-01 | 2017-10-25 | Interconnection to existing 115 kV transmission line running across the property between Eversources's Barbour Hill Substation and Endfield Substation. | CNR | FALSE | FALSE |  |  | CT
670 | 2024-07-26 12:56 | G | 2017-07-25 | Three Corners Solar | PV | SUN | 110 | 113.4 | 113.4 | Somerset | ME | 2024-07-27 | 2024-07-26 |  | CMP Albion Rd 115kV substation | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed
669 | 2019-02-14 15:31 | G | 2017-07-25 | Offshore Wind | WT | WND | 288 | 288 | 288 | NA | MA | 2023-12-01 | 2023-09-01 | 2019-02-14 | 115 kV Brayton Point Station (Primary) or 115 kV Davisville Substation (alternative) | CNR | FALSE | FALSE |  | PD | RI | Document Posted | Not Started |  |  |  | Under Study
668 | 2021-02-23 08:58 | ETU | 2017-07-24 | NE Clean Power Link - controllable HVDC Tie - CNI only | NA | N/A |  |  |  | Windsor | VT | 2027-12-31 | 2027-10-28 |  | Coolidge Substation | NI | FALSE | FALSE |  |  | VT |  |  |  |  | Executed
667 | 2018-04-12 11:19 | G | 2017-07-21 | Solar | PV | SUN | 0 | 150 | 150 | Somerset | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
666 | 2018-04-12 11:15 | G | 2017-07-21 | battery storage additional (see Q664) | OT | WND BAT | 0 | 238.6 | 238.6 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
665 | 2018-04-12 11:10 | G | 2017-07-21 | Battery storage addition (see Q663) | OT | WND BAT | 0 | 265.6 | 265.6 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station,345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
664 | 2018-04-12 11:07 | G | 2017-07-21 | Wind | WT | WND | 0 | 214.3 | 214.3 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
663 | 2018-04-12 11:03 | G | 2017-07-21 | Wind | WT | WND | 0 | 241.2 | 241.2 | Franklin | ME | 2020-10-31 | 2020-08-01 | 2018-04-12 | CMP Larrabee Road Station 345 kV | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
662 | 2018-04-12 10:40 | G | 2017-07-20 | Wind | WT | WND | 150 | 150 | 150 | Franklin | ME | 2022-12-01 | 2022-09-01 | 2018-04-12 | CMP Avangrid Larrabee Road 345 kV Substation | CNR | FALSE | FALSE |  | PD | ME
661 | 2018-04-12 10:19 | ETU | 2017-07-20 | 345 kV AC line from Quebec to ME | NA | N/A | 450 |  |  | Franklin | ME | 2022-12-01 | 2022-09-01 | 2018-04-12 | CMP/Avangrid 345 kV Larabee Road | N/A | FALSE | FALSE |  | PD | ME
660 | 2020-09-10 10:01 | G | 2017-07-20 | Solar | PV | SUN | 20 | 20 | 20 | Windham | VT | 2022-07-01 | 2022-06-01 | 2020-09-10 | National Grid line tap 69 kV transmission line (D-4), feeding the Vernon Station No. 13 | CNR | TRUE | TRUE | ISO-NE | NA | NH | Document Posted | Document Posted |  |  | In Progress
659 | 2018-04-12 10:16 | ETU | 2017-07-18 | AC to Larabee Road increase (See Q652 and 658) | NA | N/A | 540 |  |  | Lewiston | ME | 2020-12-31 | 2020-11-30 | 2018-04-12 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | NI | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
658 | 2018-04-12 10:12 | ETU | 2017-07-14 | AC to Larabee Road increase (see Q652) | NA | N/A | 200 |  |  | Lewiston | ME | 2020-12-31 | 2020-11-30 | 2018-04-12 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | NI | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
657 | 2019-09-12 09:46 | ETU | 2017-06-29 | ETU to increase Downeast Loop transfer | NA | N/A |  |  |  | Hancock | ME | 2020-12-31 | 2020-11-30 | 2019-09-12 | N/A | N/A | FALSE | FALSE |  | PD | BHE | Document Posted | Not Started |  |  |  | Under Study
656 | 2021-02-23 14:19 | G | 2017-06-28 | Weaver Wind CNR (see Q420) | WT | WND | 0 | 72.6 | 72.6 | Hancock | ME | 2020-12-12 | 2020-10-13 |  | EMERA Maine 115kV Bull Hill switching station | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
655 | 2021-11-30 09:56 | G | 2017-06-15 | RoxWind | WT | WND | 15.3 | 15.3 | 15.3 | Oxford | ME | 2021-11-30 | 2021-11-09 |  | 34.5 kV Bus at Roxbury Substation, Roxbury, Maine | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
654 | 2018-04-16 12:27 | G | 2017-06-09 | Wind CNR only (see Q460, 461, 462) | WT | WND | 0 | 312 | 312 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | CNR | FALSE | FALSE |  |  | BHE
653 | 2019-05-14 10:55 | G | 2017-06-09 | Number Nine Wind CNR only (Q417) | WT | WND | 0 | 250 | 250 | Aroostook | ME | 2021-10-31 | 2021-04-05 | 2019-05-13 | Pittsfield 345KV | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed
652 | 2018-04-12 10:08 | ETU | 2017-06-01 | AC to Larabee Road | NA | N/A | 460 |  |  | Lewiston | ME | 2020-12-31 | 2020-11-30 | 2018-04-12 | Larrabee Road 345 kV Substation in Lewiston, Androscoggin county Maine 04240. | NI | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
651 | 2019-07-29 14:47 | ETU | 2017-05-11 | AC tie line (import only) | NA | N/A | 600 |  |  | Berkshire | MA | 2023-12-31 | 2023-09-15 | 2019-07-29 | NY Alps 345kV substation and Eversource Berkshire 345 kV substation | CNI | TRUE | FALSE | ISO-NE |  | WMA |  | Document Posted |  | Not Started |  | Under Study
650 | 2018-02-05 16:17 | ETU | 2017-05-08 | ETU CNI only (see Q498) | NA | N/A | 0 |  |  | Colchester | VT | 2021-12-31 | 2021-10-01 | 2018-02-02 | N/A | CNI | FALSE | FALSE |  |  | VT
649 | 2022-12-14 09:08 | G | 2017-05-04 | Silver Maple Wind | WT | WND | 20 | 20 | 20 | Penobscot | ME | 2022-12-14 | 2022-09-24 |  | Pisgah Mountain Substation, Clifton, ME. 115 kv Bus. | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
648 | 2017-06-01 08:11 | G | 2017-04-28 | Gas Turbine Repowering | GT | DFO NG | 0 | 376 | 378 | Middlesex | CT | 2021-05-31 | 2021-03-01 | 2017-06-01 | Middletown Station 345KV Substation | CNR | FALSE | FALSE |  |  | CT
647 | 2020-06-11 07:06 | G | 2017-04-28 | Gas turbine repowering | GT | DFO NG | 23 | 376 | 378 | Middlesex | CT | 2022-05-31 | 2022-02-01 | 2020-06-11 | Middletown Substation at 115KV, MD#2 breaker position | CNR | TRUE | TRUE | ISO-NE |  | CT | Document Posted | Document Posted |  |  | In Progress
646 | 2017-07-24 11:02 | G | 2017-04-28 | Solar | PV | SUN | 20.1 | 20.1 | 20.1 | Franklin | VT | 2019-09-01 | 2019-08-01 | 2017-07-24 | VEC Highgate - Enosburg 46 kV line, 700 feet from Highgate | CNR | FALSE | FALSE |  |  | VT
645 | 2017-07-24 11:02 | G | 2017-04-28 | Solar | PV | SUN | 20.1 | 20.1 | 20.1 | Orange | VT | 2019-12-15 | 2019-11-15 | 2017-07-24 | GMP Randolph Center Substation 46 kV | CNR | FALSE | FALSE |  |  | VT
644 | 2017-07-24 11:01 | G | 2017-04-28 | Solar | PV | SUN | 20.1 | 20.1 | 20.1 | Franklin | VT | 2018-10-31 | 2018-10-15 | 2017-07-24 | VEC Sheldon - Rocktenn 46 kV line | CNR | FALSE | FALSE |  |  | VT
643 | 2017-05-24 09:27 | G | 2017-04-27 | Solar CNR only | PV | SUN | 0 | 20 | 20 | New Haven | CT | 2018-12-31 | 2018-11-15 | 2017-05-23 | CT_NU 115 kV Line from Wallingford to NU_1208_WAL. Proposed POI is located at 41° 26’ 27.9” N , 72° 50’36.6” W (see the attached site layout drawing). | CNR | FALSE | FALSE |  |  | CT
642 | 2017-05-31 14:58 | G | 2017-04-26 | Repowering Increase | GT | DFO NG | 34.85 | 98.12 | 98.16 | Norfolk | MA | 2021-05-22 | 2021-02-22 | 2017-05-31 | BELD station 16 switchyard | CNR | FALSE | FALSE |  |  | SEMA
641 | 2018-08-13 13:49 | G | 2017-04-24 | Wind | WT | WND | 65.55 | 54.6 | 54.6 | Oxford | ME | 2020-12-31 | 2020-09-15 | 2018-08-13 | CMP 115 kV Line 210 | CNR | FALSE | FALSE |  | PD | ME | Document Posted | Not Started |  |  |  | Under Study
640 | 2020-12-01 13:04 | ETU | 2017-04-21 | 1000 MW HVDC (import only) | NA | N/A | 1000 |  |  | Plymouth | MA | 2022-12-31 | 2022-11-30 | 2020-11-30 | Northern Interconnection: Coleson Cove 345kV Substation, New Brunswick Southern Interconnection: 345kV lines from Pilgrim Substation, Plymouth, Massachusetts | NI | FALSE | FALSE |  | PD | SEMA | In Progress |  |  |  |  | Under Study
639 | 2020-11-02 15:01 | ETU | 2017-04-19 | NECEC 1200 MW HVDC (import only) - controllable | NA | N/A | 1200 |  |  | Androscoggin | ME | 2026-01-07 | 2025-09-01 |  | CMP Larrabee Rd 345 kV Substation | NI | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
638 | 2019-08-08 11:26 | G | 2017-04-13 | Solar CNR only (see Q578) | PV | SUN | 0 | 152 | 152 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road 345 kV. | CNR | FALSE | FALSE |  | PD | ME
637 | 2019-08-08 11:25 | G | 2017-04-13 | BSS CNR only (see Q577) | OT | WND BAT | 0 | 270.46 | 270.46 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station,345 kV | CNR | FALSE | FALSE |  | PD | ME
636 | 2019-08-08 11:25 | G | 2017-04-13 | BSS CNR only (see Q576) | OT | WND BAT | 0 | 241.49 | 241.49 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road station 345 kV | CNR | FALSE | FALSE |  | PD | ME
635 | 2019-08-08 11:23 | G | 2017-04-13 | Wind CNR (see Q574) | WT | WND | 0 | 216.41 | 216.41 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larabee Road 345 kV station | CNR | FALSE | FALSE |  | PD | ME
634 | 2019-08-08 11:23 | G | 2017-04-11 | Wind CNR (see Q573) | WT | WND | 0 | 245.38 | 245.38 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larabee Road 345 kV station | CNR | FALSE | FALSE |  |  | ME
633 | 2020-02-24 16:08 | G | 2017-04-06 | Passadumkeag Wind CNR only | WT | WND | 0 | 39.97 | 39.97 | Penobscot | ME | 2019-06-28 | 2019-06-28 |  | Existing connection between Emera Maine 115kV lines 64 and 97 | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | In Progress
632 | 2020-01-23 12:49 | G | 2017-04-05 | Offshore Wind w/ battery storage | OT | WND BAT | 880 | 880 | 880 | NA | MA | 2024-12-06 | 2024-04-05 | 2020-01-23 | Eversource, 115kV Bourne Substation, Barnstable County, Massachusetts | CNR | TRUE | FALSE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  | Not Started |  | Under Study
631 | 2017-07-26 14:49 | G | 2017-04-05 | CHP | IC | NG | 8 | 8.64 | 8.64 | Coos | NH | 2018-07-15 | 2018-06-15 | 2017-07-26 | PSNH 34.5 kV Line, Berlin, NH | CNR | FALSE | FALSE |  |  | NH
630 | 2017-11-29 13:51 | G | 2017-04-05 | Project Increase | ST | MSW | 2.153 | 15.67 | 15.67 | Hartford | CT | 2017-09-01 | 2017-09-01 | 2017-11-21 | Connecticut Light and Powers 13.8 kv Forestville 12A Substation | CNR | FALSE | FALSE |  |  | CT |  | In Progress
629 | 2017-05-24 09:27 | G | 2017-03-07 | Solar | PV | SUN | 20 | 20 | 20 | New Haven | CT | 2018-12-31 | 2018-11-15 | 2017-05-23 | CT_NU 115 kV Line from Wallingford to NU_1208_WAL. Proposed POI is located at 41° 26’ 27.9” N , 72° 50’36.6” W (see the drawing with file name "Project Facility Layout - 22NOV16.pdf" for a map of proposed POI location). | NR | FALSE | FALSE |  |  | CT
628 | 2017-09-15 09:52 | G | 2017-03-07 | Solar | PV | SUN | 30 | 30 | 30 | Cheshire | NH | 2018-12-31 | 2018-09-30 | 2017-08-09 | Eversource 34.5 kV Monadnock SS (3120 line) | NA | FALSE | FALSE |  |  | NH
627 | 2019-07-16 12:29 | ETU | 2016-12-27 | 400 kV HVDC Tie - Import Only | NA | N/A | 1200 | 1200 | 1200 | Grafton | NH | 2022-12-31 | 2022-10-01 | 2019-07-16 | GRID 230 kV Comerford Substation | CNI | FALSE | FALSE |  |  | NH | Document Posted | In Progress |  |  |  | Under Study
626 | 2018-04-03 09:37 | G | 2016-12-14 | Wind | WT | WND | 376.2 | 376.2 | 376.2 | Aroostook | ME | 2019-12-01 | 2019-10-01 | 2018-04-02 | MEPCO 396 line | CNR | FALSE | FALSE |  | PD | BHE | Not Started |  |  |  |  | Under Study
625 | 2019-04-11 16:49 | ETU | 2016-11-10 | 345 kV AC line | NA | N/A | 1600 | 1600 | 1600 | Bristol | MA | 2023-12-31 | 2023-08-31 | 2019-04-11 | 345 kV Brayton point substation | N/A | FALSE | FALSE |  | PD | RI |  | In Progress |  |  |  | Under Study
624 | 2020-08-26 15:59 | G | 2016-11-08 | Vineyard Offshore Wind | WT | WND | 800 | 800 | 800 | NA | MA | 2025-05-26 | 2024-01-02 |  | 115 kV Barnstable Substation | CNR | TRUE | TRUE | ISO-NE | PD | SEMA | Document Posted | Document Posted |  |  | Executed | Under Construction
623 | 2021-08-12 15:31 | G | 2016-10-31 | Solar | PV | SUN | 150 | 150 | 150 | York | ME | 2022-12-31 | 2022-12-15 | 2021-08-12 | CMP/Eversource 345 kV Line 391 from Buxton substation to Scobie Pond substation (approx. 27.7 miles from Buxton substation) | NR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed | Under Study
622 | 2022-04-29 12:24 | G | 2016-10-17 | Cogen DG | GT | NG | 43 | 43 | 43 | Middlesex | MA | 2021-09-30 | 2020-08-31 |  | Putnum Station 831 | NA | TRUE | TRUE | NU |  | CMA
621 | 2018-04-12 10:01 | G | 2016-10-17 | Wind | WT | WND | 93.6 | 93.6 | 93.6 | Somerset | ME | 2020-01-15 | 2019-12-30 | 2018-04-12 | CMP Section 3023 345 kV line (via Johnson Mountain substation) | CNR | FALSE | FALSE |  | PD | ME | Not Started |  |  |  |  | Under Study
620 | 2020-08-13 07:49 | G | 2016-10-07 | Solar | PV | SUN | 75 | 75 | 75 | Washington | ME | 2022-05-31 | 2022-05-15 | 2020-08-12 | Emera 115 kV Deblois substation | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | In Progress
619 | 2017-01-25 15:01 | ETU | 2016-09-16 | Bi-directional AC LIne | NA | N/A |  |  |  | Berkshire | MA | 2021-12-31 | 2021-11-30 | 2017-01-25 | NY Alps 345 kV Substation to WMECO Berkshire 345 kV substation | N/A | FALSE | FALSE |  | PD | WMA
618 | 2022-08-10 12:59 | G | 2016-08-01 | Bay State Offshore Wind 1 | WT | WND | 800 | 800 | 800 | NA | MA | 2026-05-31 | 2025-09-21 | 2022-08-10 | National Grid, 345 kV Brayton Point Substation, Somerset, MA | NR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  | Document Posted | Executed
617 | 2024-07-23 11:46 | G | 2016-07-22 | Simple Cycle Gas Turbine | GT | DFO NG | 61.851 | 61.851 | 67.851 | Essex | MA | 2024-06-29 | 2024-01-11 |  | Peabody Waters River Substation | NA | TRUE | TRUE | NGRID |  | BOST
616 | 2016-07-14 07:58 | G | 2016-07-01 | Solar | PV | SUN | 19.9 |  |  | Windsor | VT | 2017-07-01 | 2017-06-15 | 2016-07-13 | 115 kV Cooolidge Substation | CNR | FALSE | FALSE |  | PD | VT
615 | 2016-07-14 07:58 | G | 2016-06-28 | Solar | PV | SUN | 78.4 | 78.4 | 78.4 | Cheshire | NH | 2018-07-01 | 2018-06-15 | 2016-07-13 | Mondanock to Ashburnham Eversource 115 kV line | CNR | FALSE | FALSE |  | PD | VT
614 | 2016-07-14 07:59 | G | 2016-06-28 | Solar | PV | SUN | 78.4 | 78.4 | 78.4 | Franklin | ME | 2018-07-01 | 2018-06-15 | 2016-07-13 | CMP Sturtevant Substation - 115 kV | CNR | FALSE | FALSE |  | PD | ME
613 | 2016-07-14 07:59 | G | 2016-06-28 | Solar | PV | SUN | 63 | 63 | 63 | Windham | CT | 2018-07-01 | 2018-06-15 | 2016-07-13 | Killingly to Tunnel 115 kV line | CNR | FALSE | FALSE |  | PD | CT
612 | 2017-09-25 15:30 | G | 2016-04-26 | Medway Hydro - CNR only | HD | WAT | 0 | 4.003 | 4.003 | Penobscot | ME | 2017-08-14 | 2017-08-14 |  | Medway Substation | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
611 | 2018-01-04 09:19 | G | 2016-04-25 | Combustion Turbine | GT | NG | 102 | 102 | 102 | Fairfield | CT | 2019-06-01 | 2019-01-01 | 2018-01-04 | Eversource Energy 115kV MiddleRiver Substation Danbury, CT | CNR | TRUE | FALSE | ISO-NE | PD | SWCT |  | Document Posted |  |  | In Progress
610 | 2017-03-27 09:14 | G | 2016-04-22 | Steam Turbines | ST | BLQ DFO KER WDS | 75 | 75 | 80 | Franklin | ME | 2018-05-31 | 2018-05-30 | 2017-03-24 | Central Maine Power (CMP) Riley 115kV Section 230 (K230-2) | CNR | FALSE | FALSE |  | PD | ME | Document Posted
609 | 2016-06-03 15:37 | G | 2016-04-22 | Gas Turbine Upgrade | GT | DFO | 23.52 | 162 | 162 | New Haven | CT | 2020-05-31 | 2020-04-21 | 2016-06-03 | POI is the CL&amp;P Devon 115kv Substation | CNR | FALSE | FALSE |  | PD | CT
608 | 2016-05-24 15:02 | G | 2016-04-22 | Combined Cycle GT | CC | NG WO | 68.01 | 68.01 | 69.5 | Bristol | MA | 2020-05-01 | 2019-12-31 | 2016-05-24 | Located at current Cleary node 375,376 interconnected with National Grid s-8 and v-5 line, SEMA load zone. | CNR | FALSE | FALSE |  | PD | SEMA
607 | 2017-11-29 08:44 | G | 2016-04-21 | Canton Mountain Wind CNR Only | WT | WND | 0 | 22.8 | 22.8 | Oxford | ME | 2017-12-01 | 2017-10-18 |  | CMP Ludden Lane Substation, Canton, Maine | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
606 | 2017-06-08 09:32 | G | 2016-04-21 | Huntington Falls 2017 Upgrades | HD | WAT | 1.59 | 1.24 | 1.24 | Chittenden | VT | 2017-04-12 | 2017-03-13 |  | GMP Huntington Falls Substation 46 kV Circuit Breaker BB-10 | CNR | TRUE | TRUE |  | PD | VT |  |  |  |  | Executed | In Service
605 | 2020-11-09 16:12 | G | 2016-04-21 | Sanford Airport Solar CNR only | PV | SUN | 0 | 50 | 50 | York | ME | 2020-11-07 | 2020-10-06 |  | CMP Sanford 115kV substation | NR | FALSE | FALSE |  | PD | ME |  |  |  |  | Executed | In Service
604 | 2018-08-01 15:58 | G | 2016-04-20 | Lake Road CNR Only (see Q534) | CC | NG | 0 | 882 | 951 | Windham | CT | 2018-05-20 | 2017-11-26 |  | 345kV Lake Road 27E Substation | CNR | FALSE | FALSE |  | PD | RI |  |  |  |  | Executed
603 | 2022-06-15 12:49 | G | 2016-04-15 | Essential Power Newington - CNRC Increase | CC | DFO NG | 0 | 596.1 | 634.9 | Rockingham | NH | 2016-10-28 | 2016-10-28 |  | Public Service New Hampshire Newington Switchyard - Gosling Road, Newington, NH | CNR | FALSE | FALSE |  |  | NH
602 | 2023-10-25 10:59 | G | 2016-04-14 | Moore Station Uprate | HW | WAT | 4.6 | 195.9 | 195.9 | Grafton | NH | 2023-10-18 | 2023-09-22 |  | NGRID at Moore power station switchyard 230kV | CNR | TRUE | TRUE | ISO-NE |  | NH | Document Posted | Document Posted |  |  | Executed | In Service
601 | 2017-08-28 16:19 | G | 2016-04-14 | Combined Cycle Upgrade | CC | DFO NG | 40 | 655.873 | 689.794 | Providence | RI | 2020-05-31 | 2020-03-01 | 2017-08-28 | NGRID 345kV Sherman Road (existing OSP I and II switchyard) | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
600 | 2017-08-28 16:18 | G | 2016-04-14 | Combined Cycle Uprate | CC | DFO NG | 21.077 | 615.873 | 649.794 | Providence | RI | 2016-07-31 | 2016-07-15 | 2017-08-28 | NGRID 345kV Sherman Road (existing OSP I and II switchyard) | CNR | FALSE | FALSE |  | PD | RI | Not Started |  |  |  |  | Under Study
599 | 2018-01-23 16:25 | G | 2016-04-05 | Solar | PV | SUN | 65 | 65 | 65 | Cheshire | NH | 2018-04-18 | 2018-04-15 | 2018-01-23 | NGrid 115kV line from Vernon road tap to the Vernon Road Substation | CNR | FALSE | FALSE |  | PD | VT |  | In Progress |  |  |  | Under Study
598 | 2018-03-28 16:13 | G | 2016-03-07 | Combined Cycle | CC | DFO NG | 563 | 563 | 576 | Windham | CT | 2022-03-01 | 2021-09-01 | 2018-03-28 | Killingly/Lake Road 345 kV | CNR | TRUE | FALSE | ISO-NE | PD | CT |  | Document Posted |  |  | In Progress
597 | 2018-04-20 08:37 | G | 2016-02-24 | Hydro | HD | WAT | 28.325 | 28.325 | 28.325 | Oxford/Franklin/Androscoggin | ME | 2019-06-01 | 2019-05-31 | 2018-04-20 | CMP Section 230 (115 kV) at southeast end, high side of Verso Androscoggin substation | CNR | FALSE | FALSE |  | PD | ME | Document Posted | Not Started |  |  |  | Under Study
596 | 2017-05-19 13:39 | G | 2016-02-08 | Combined Cycle | CC | DFO NG | 1120 | 1120 | 1170 | Windham | CT | 2020-06-01 | 2019-10-01 | 2017-05-19 | Killingly or Lake Road 345 kV | CNR | FALSE | FALSE |  | PD | CT | In Progress |  |  |  |  | Under Study
595 | 2017-06-26 14:07 | G | 2016-02-08 | Bridgeport Energy PSS Tuning | GT | NG | 0 | 578 | 588 | Fairfield | CT | 2016-10-28 | 2016-10-28 |  | UI Singer Substation | CNR | TRUE | TRUE | ISO-NE |  | SWCT |  | Document Posted |  |  | Executed | In Service
594 | 2018-04-09 10:28 | G | 2016-01-27 | Wind | WT | WND | 0 | 245.48 | 245.48 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2018-04-09 | CMP&#39;&#39;s existing Orrington - Albion Road 345 kV line section 3023 | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
593 | 2018-04-09 10:27 | G | 2016-01-27 | Wind | WT | WND | 0 | 216.41 | 216.41 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2018-04-09 | CMP&#39;&#39;s Orrington - Albion Road 345 kV line, section 3023 | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
592 | 2023-01-09 10:03 | G | 2016-01-21 | Bear Swamp Unit 1 and 2 Upgrade | PS | WAT | 66 | 663 | 663 | Berkshire | MA | 2023-01-06 | 2022-12-01 |  | GRID 230 kV Bear Swamp substation | CNR | TRUE | TRUE | ISO-NE | PD | WMA |  | Document Posted |  |  | Executed | Partially In Service
591 | 2018-04-12 09:53 | ETU | 2016-01-20 | AC Line | NA | N/A | 400 | 400 | 400 | Cumberland | ME | 2019-11-30 | 2019-10-31 | 2018-04-12 | CMP Surowiec Area | N/A | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
590 | 2018-04-12 09:49 | ETU | 2016-01-11 | AC Line from NMISA to Chester and Pittsfield, ME | NA | N/A | 1200 | 1200 | 1200 | Somerset and Penobscot | ME | 2019-12-31 | 2019-11-30 | 2018-04-12 | Emera Keene Rd substation and CMP Section 3023 345 kV Line | N/A | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
589 | 2018-04-12 09:43 | ETU | 2016-01-11 | AC Line to Pittsfield, ME | NA | N/A | 550 | 550 | 550 | Somerset | ME | 2019-12-31 | 2019-11-30 | 2018-04-12 | CMP Section 3023 345 kV Line | N/A | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
588 | 2021-12-27 14:16 | G | 2016-01-07 | Quinebaug Solar | PV | SUN | 49 | 49 | 49 | Windham | CT | 2021-12-18 | 2021-12-11 |  | Killingly to Tunnel 115 kV line (approx 5.5 miles south of Brooklyn Substation) GPS Coordinates: - 71 55’ 27.9” W - 41 44’ 14.21” N | NR | TRUE | TRUE | ISO-NE | PD | CT |  | Document Posted |  |  | Executed | In Service
587 | 2016-09-29 07:52 | G | 2016-01-07 | Solar | PV | SUN | 98 | 98 | 98 | Cheshire | NH | 2018-07-01 | 2018-06-15 | 2016-09-28 | 115 kV Eversource Fitzwilliam Substation | CNR | FALSE | FALSE |  | PD | VT |  | Not Started
586 | 2016-10-28 14:15 | G | 2016-01-04 | Hemphill Increase | ST | WDS | 3.363 | 17.5 | 17.5 | Sullivan | NH | 2016-10-28 | 2016-10-28 |  | 34.5 Kv PSNH 316 Utility Line | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Not Required |  |  | Executed | In Service
585 | 2018-03-05 15:26 | ETU | 2015-12-14 | HVDC Tie NB to Mystic | NA | N/A | 900 | 900 | 900 | Middlesex | MA | 2020-12-30 | 2020-11-30 | 2018-03-05 | NB 345 kV Coleson Cove substation to NSTAR 345 kV Mystic substation | CNI | FALSE | FALSE |  | PD | BOST | Not Started
584 | 2018-10-31 15:31 | ETU | 2015-12-10 | ETU CNI only (see Q508) | NA | N/A | 0 | 0 | 0 | Berkshire | MA | 2019-08-31 | 2019-07-31 | 2018-10-31 | NY Alps substation to WMECO Berkshire substation | CNI | FALSE | FALSE |  |  | WMA |  | Document Posted |  |  | In Progress
583 | 2020-11-09 16:11 | G | 2015-12-04 | Sanford Airport Solar | PV | SUN | 50 | 50 | 50 | York | ME | 2020-11-07 | 2020-10-06 |  | CMP Sanford 115kV Substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
582 | 2018-02-05 08:41 | G | 2015-12-02 | Solar | PV | SUN | 3.11 | 3.105 | 3.105 | Worcester | MA | 2017-12-01 | 2017-11-01 | 2018-02-05 | POI is the GRID 69KV switchyard at the Harrington Street Facility. 229 Harrington Street, East Brookfield, MA. National Grid has this information. | CNR | TRUE | FALSE |  |  | CMA |  | Document Posted |  |  | In Progress
581 | 2018-02-05 08:40 | G | 2015-12-02 | Solar | PV | SUN | 2.66 | 2.66 | 2.66 | Worcester | MA | 2017-12-01 | 2017-11-01 | 2018-02-05 | POI is the GRID 69KV switchyard at the Harrington Street Facility. 229 Harrington Street, East Brookfield, MA. National Grid has this information. | CNR | TRUE | FALSE |  |  | CMA |  | Document Posted |  |  | In Progress
580 | 2016-05-18 08:28 | G | 2015-11-30 | Combined Cycle | CC | DFO NG | 1020 | 1020 | 1030 | Worcester | MA | 2020-05-31 | 2020-01-15 | 2016-05-17 | Anticipated interconnection is the National Grid 345kV line 366 between the West Farnum and Millbury substations, and/or the Eversource 345kV line 3361 between Sherman Rd and Blackstone. | CNR | FALSE | FALSE |  | PD | CMA |  | Not Started
579 | 2016-04-21 14:52 | G | 2015-11-25 | Energy Center | OT | NG OTH | 570.1 | 570.1 | 569.6 | Cheshire | NH | 2020-06-01 | 2020-03-01 | 2016-04-21 | Eversource (PSNH) 379 line crossing Forest Lake Road (POI will be south of Forest Lake Road), which is in close proximity to the Project site. | CNR | FALSE | FALSE |  | PD | VT | Not Started |  |  |  |  | Under Study
578 | 2019-08-08 11:21 | G | 2015-11-20 | Solar | PV | SUN | 152 | 152 | 152 | Somerset | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road 345 kV. | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
577 | 2019-08-08 11:20 | G | 2015-11-12 | Battery Storage | OT | WND BAT | 25.08 | 270.46 | 270.46 | Frqanklin | ME | 2019-11-09 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station,345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
576 | 2019-08-08 11:20 | G | 2015-11-12 | Battery Storage | OT | WND BAT | 52.26 | 241.49 | 241.49 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road station 345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
575 | 2017-08-25 10:39 | G | 2015-11-03 | Casco Bay Energy Storage | OT | BAT | 16.2 | 16.2 | 16.2 | Cumberland | ME | 2016-12-31 | 2016-12-02 |  | CMP&#39;&#39;s PTF 115kV Upper Bus at William F Wyman Station | NR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed | In Service
574 | 2019-08-08 11:19 | G | 2015-11-03 | Wind | WT | WND | 216.41 | 216.41 | 216.41 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station 345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
573 | 2019-08-08 11:18 | G | 2015-11-03 | Wind | WT | WND | 245.38 | 245.38 | 245.38 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2019-08-08 | CMP Larrabee Road Station 345 kV | NR | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
572 | 2018-04-09 09:22 | G | 2015-11-03 | Wind | WT | WND | 113 | 113 | 113 | Franklin | ME | 2019-10-31 | 2019-08-01 | 2018-04-09 | CMP Larrabee Road 345 kV station | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
571 | 2019-08-08 11:18 | ETU | 2015-11-02 | Wyman Area to Larabee Rd Line | NA | N/A | 850 | 850 | 850 | Somerset/Androscoggin | ME | 2019-11-30 | 2019-10-31 | 2019-08-08 | Wyman Area to CMP Larabee Rd 345 kV sub | N/A | TRUE | FALSE | ISO-NE | PD | ME |  | In Progress
570 | 2016-05-31 12:28 | G | 2015-10-21 | Kendall Revised Reconfiguration Project | CC | DFO NG | 0 | 250 | 250 | Middlesex | MA | 2016-05-31 | 2016-05-31 |  | Where line 875-539 interconnects with TO&#39;&#39;s 115KV bus at station | CNR | FALSE | FALSE |  |  | BOST |  |  |  |  | Executed | In Service
569 | 2018-06-25 10:46 | ETU | 2015-10-16 | HVDC from ME to MA (MA import only) | NA | N/A | 1200 | 1200 | 1200 | Plymouth | MA | 2021-12-31 | 2021-11-30 | 2018-06-25 | Emera Orrington 345 kV substation to Eversource Jordan Rd | N/A | FALSE | FALSE |  | PD | SEMA | Document Posted
568 | 2021-03-11 15:12 | G | 2015-09-25 | Solar | PV | SUN | 10 | 10 | 10 | Rockingham | NH | 2021-11-01 | 2021-10-15 | 2021-03-11 | Unitil 34.5 kV W. Port. St. sub | NA | TRUE | TRUE |  |  | NH
567 | 2015-09-21 14:17 | G | 2015-09-11 | Solar | PV | SUN | 196 | 196 | 196 | Franklin | VT | 2017-07-01 | 2017-06-15 | 2015-09-21 | VELCO Highgate Substation - 345 kV Bus | CNR | FALSE | FALSE |  |  | VT
566 | 2016-04-18 08:18 | G | 2015-09-09 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Rutland | VT | 2016-12-01 | 2016-11-01 | 2016-04-15 | VELCO Florence Substation - 46 kV | CNR | FALSE | FALSE |  | PD | VT |  | Not Started |  |  |  | Under Study
565 | 2018-12-20 10:25 | G | 2015-09-08 | Coolidge Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Windsor | VT | 2018-12-20 | 2018-12-12 |  | 115 kV Coolidge Substation | CNR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | Executed | In Service
564 | 2016-02-24 14:11 | G | 2015-09-04 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Franklin | VT | 2016-12-01 | 2016-11-15 | 2016-02-24 | 115 kV Highgate Substation | CNR | FALSE | FALSE |  | PD | VT
563 | 2015-09-08 12:23 | G | 2015-09-01 | Solar | PV | SUN | 20 | 20 | 20 | Rutland | VT | 2016-11-01 | 2016-10-01 | 2015-09-03 | VELCO 46 kV bus at Florence Substation | NA | FALSE | FALSE |  |  | VT
562 | 2017-05-24 15:44 | G | 2015-08-27 | Solar | PV | SUN | 20 | 20 | 20 | Orleans | VT | 2017-08-31 | 2017-07-31 | 2017-05-24 | VEC Irasburg H16 46 kV line | NA | FALSE | FALSE |  |  | VT
561 | 2017-01-26 09:49 | G | 2015-08-27 | Solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2017-08-31 | 2017-07-31 | 2017-01-25 | VEC Highgate to Rock Tenn 46 kV line | NA | FALSE | FALSE |  |  | VT
560 | 2015-10-30 09:54 | G | 2015-08-27 | Solar | PV | SUN | 20 | 20 | 20 | Orange | VT | 2016-12-01 | 2016-11-01 | 2015-10-29 | GMP 46 kV Randolph Center Substation | NA | FALSE | FALSE |  |  | VT
559 | 2015-09-08 12:22 | G | 2015-08-12 | solar | PV | SUN | 20 | 20 | 20 | Windsor | VT | 2016-12-01 | 2016-11-15 | 2015-09-03 | 115 kV Coolidge substation | NA | FALSE | FALSE |  |  | VT
558 | 2015-09-08 12:21 | G | 2015-08-12 | solar | PV | SUN | 20 | 20 | 20 | Franklin | VT | 2016-12-01 | 2016-11-15 | 2015-09-03 | 115 kV Highgate Substation | NA | FALSE | FALSE |  |  | VT
557 | 2021-10-27 10:38 | G | 2015-08-10 | Farminton Solar | PV | SUN | 78.4 | 78.4 | 78.4 | Franklin | ME | 2021-10-27 | 2021-09-09 |  | CMP Sturtevant Substation - 115 kV | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | Under Construction
556 | 2017-04-27 13:38 | G | 2015-08-07 | Wind Farm | WT | WND | 79.2 | 79.2 | 79.2 | Somerset | ME | 2019-12-01 | 2019-09-01 | 2017-04-27 | CMP Wyman - Harris 115 kV | CNR | FALSE | FALSE |  | PD | ME | Not Started |  |  |  |  | Under Study
555 | 2019-01-18 12:08 | G | 2015-08-07 | Wind farm | WT | WND | 39.6 | 39.6 | 39.6 | Oxford | ME | 2019-12-01 | 2019-09-01 | 2019-01-18 | CMP Rumford-Kimball Road 115 kV | CNR | TRUE | FALSE |  | PD | ME | Document Posted | Document Posted |  | Not Started
554 | 2017-07-05 12:55 | G | 2015-06-18 | Southbridge LFGTE Engine 2 | IC | LFG | 1.6 | 3.2 | 3.2 | Worcester | MA | 2018-08-18 | 2018-07-25 | 2017-07-05 | National Grid 413L4 (Existing facility POI) | CNR | TRUE | FALSE | NGRID |  | CMA |  | Document Posted |  |  | Executed
553 | 2015-08-28 14:06 | G | 2015-06-12 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Franklin | ME | 2016-12-01 | 2016-11-15 | 2015-08-28 | 115 kV Sturtevant sub | CNR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
552 | 2020-12-08 11:02 | G | 2015-06-12 | Nutmeg Solar, LLC | PV | SUN | 19.9 | 19.9 | 19.9 | Hartford | CT | 2020-12-07 | 2020-11-15 |  | 115kV Sitico Sub | NR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed | In Service
551 | 2015-08-04 13:34 | G | 2015-06-12 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Windsor | VT | 2016-12-01 | 2016-11-15 | 2015-08-04 | 115kV Coolidge sub | CNR | FALSE | FALSE |  |  | VT
550 | 2015-08-04 13:34 | G | 2015-06-12 | Solar | PV | SUN | 19.9 | 19.9 | 19.9 | Franklin | VT | 2016-12-01 | 2016-11-15 | 2015-08-04 | 115 kV Highgate Sub | CNR | FALSE | FALSE |  |  | VT
549 | 2015-07-13 08:29 | G | 2015-05-28 | Combined Cycle | CC | DFO NG | 870 | 870 | 893 | Newport | RI | 2020-05-01 | 2020-01-02 | 2015-07-09 | interconnection on NGRID 115kV M13 &amp; L14 lines connecting to Somerset and Bell Rock substations | CNR | FALSE | FALSE |  | PD | RI
548 | 2016-05-20 08:11 | G | 2015-05-28 | Combined Cycle | CC | DFO NG | 870 | 870 | 893 | Plymouth | MA | 2020-05-01 | 2020-01-02 | 2016-05-19 | interconnection between Carver and Tremont substations (NSTAR 115kV Lines 127/128 and 134): ALT connection 345kV Carver substation | CNR | FALSE | FALSE |  | BL | SEMA | Document Posted
547 | 2018-05-31 14:50 | G | 2015-04-28 | Wind uprate | WT | WND | 2.93 | 42.9 | 42.9 | Penobscot | ME | 2018-12-31 | 2018-12-01 | 2018-05-31 | Existing connection between Emera Maine 115kV lines 64 and 97 | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
546 | 2019-05-21 11:03 | G | 2015-03-04 | NEA Bell. Uprate (Northeast Energy Associates, LP) | CC | DFO NG | 1.393 | 314.7 | 340.241 | Norfolk | MA | 2018-07-31 | 2018-07-15 |  | 345 kV NEA Bellingham substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed | Under Construction
545 | 2015-06-29 14:44 | G | 2015-03-03 | Proctor Hydroelectric Station Uprate | HD | WAT | 3.241 | 2 | 2 | Rutland | VT | 2015-06-25 | 2015-05-02 |  | GMP Proctor Substation 46kV Circuit Breaker BB8 | CNR | FALSE | TRUE |  |  | VT |  |  |  |  | Executed | In Service
544 | 2015-08-18 16:01 | G | 2015-03-03 | Increase RISEC Winter CNR | CC | NG | 0 | 613 | 625 | Providence | RI | 2015-08-17 | 2015-08-17 |  | 115 kV RISE substation | CNR | FALSE | FALSE |  |  | RI |  |  |  |  | Executed | In Service
543 | 2019-12-30 13:33 | G | 2015-03-02 | Antrim Wind | WT | WND | 28.4 | 28.4 | 28.4 | Hillsborough | NH | 2019-12-24 | 2019-08-16 |  | Proposed POI is to PSNH 115 kV line L163. | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed | Under Construction
542 | 2016-04-18 12:22 | G | 2015-03-02 | combustion turbine | GT | DFO NG | 97 | 97 | 97 | Norfolk | MA | 2018-02-01 | 2017-12-01 | 2016-04-18 | NSTAR 115kV Edgar substation | CNR | FALSE | FALSE |  | PD | SEMA | Document Posted
541 | 2016-02-17 07:58 | G | 2015-03-02 | Combined cycle (alt to Q442/472) | CC | DFO NG | 431 | 431 | 452 | Hampden | MA | 2019-03-01 | 2018-06-01 | 2016-02-16 | 115kV Line 1302 between Buck Pond and Pochassic substations, approximately 1 mile south of Buck Pond | CNR | FALSE | FALSE |  |  | WMA | In Progress |  |  |  |  | Under Study
540 | 2018-05-21 09:53 | G | 2015-03-02 | CPV Towantic Increase | CC | DFO NG | 55.5 | 800.5 | 830.5 | New Haven | CT | 2018-05-21 | 2018-01-24 |  | CL&amp;P 115kV Lines 1575, 1585 &amp; 1990 | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed | In Service
539 | 2016-01-29 15:40 | G | 2015-03-02 | Hoosac Wind Project CNR Only | WT | WND | 0 | 28.5 | 28.5 | Franklin | MA | 2016-01-19 | 2016-01-19 |  | Hoosac 69 kV Substation | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed | In Service
538 | 2016-04-27 10:49 | G | 2015-03-02 | Internal Combustion | IC | NG | 119.4 | 119.4 | 119.4 | Newport | RI | 2019-05-31 | 2019-04-30 | 2016-04-27 | Near Bell Rock and Somerset on NGRID 115kV lines L14 and M13. Adjacent to existing Tiverton combined cycle generator, possibly associated with existing tap. | CNR | FALSE | FALSE |  | PD | RI | Document Posted
537 | 2015-05-22 08:01 | G | 2015-02-28 | Combustion Turbine | GT | NG | 11.965 | 11.965 | 14.097 | Middlesex | MA | 2016-11-30 | 2016-08-31 | 2015-05-21 | MECO 23KV Behen St feeder load side of MTR 04034085 | CNR | FALSE | FALSE |  |  | BOST
536 | 2015-12-10 11:22 | G | 2015-02-27 | Wind | WT | WND | 4.98 | 4.98 | 4.98 | Orleans | VT | 2016-09-13 | 2016-09-01 | 2015-12-10 | GMP Line 14 between Irasburg and Lowell Substations approximately 3.6 miles from Irasburg Substation adjacent to Kidder Hill Road | CNR | FALSE | FALSE |  |  | VT |  | Not Started
535 | 2020-01-07 15:52 | G | 2015-02-27 | Holiday Hill Community Wind | WT | WND | 4.98 | 4.98 | 4.98 | Hampden | MA | 2020-01-07 | 2019-11-26 |  | WMECo 23 kV line 19J1 adjacent to Pine Hill Road in the town of Russell, Massachusetts | CNR | TRUE | TRUE | NU |  | WMA |  | Document Posted |  |  | Executed | Under Construction
534 | 2018-08-01 15:53 | G | 2015-02-27 | Lake Road Upgrades | CC | NG | 49.836 | 882 | 951 | Windham | CT | 2018-05-20 | 2017-11-26 |  | 345kV Lake Road 27E Substation | CNR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted | Document Posted |  |  | Executed | In Service
533 | 2017-08-01 08:26 | G | 2015-02-27 | Milford Upgrades - Phase I | CC | NG | 16.606 | 293 | 318.5 | New Haven | CT | 2017-06-05 | 2017-05-22 |  | 115kV East Devon Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT | Document Posted | Document Posted |  |  | Executed | In Service
533 | 2017-08-01 08:27 | G | 2015-02-27 | Milford Upgrades - Phase II | CC | NG | 16.606 | 293 | 318.5 | New Haven | CT | 2017-05-22 | 2017-04-12 |  | 115kV East Devon Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT | Document Posted | Document Posted |  |  | In Progress
532 | 2016-06-02 11:00 | G | 2015-02-27 | wind | WT | WND | 17.4 | 17.4 | 17.4 | Franklin | VT | 2016-09-15 | 2016-09-01 | 2016-06-01 | GMP 34.5 kV Line between North St. Albans and Sheldon Springs Substations. State Route 105, Swanton, Vermont | CNR | FALSE | FALSE |  |  | VT |  | In Progress |  |  |  | Under Study
531 | 2018-04-05 11:02 | G | 2015-02-27 | Combined Cycle Uprate | CC | NG | 29.999 | 546.8459 | 582.5609 | Penobscot | ME | 2018-08-01 | 2018-07-16 | 2018-04-05 | EMERA Maine-Graham Station via 115kv | CNR | FALSE | FALSE |  | PD | BHE |  | In Progress |  |  |  | Under Study
530 | 2017-11-21 15:18 | G | 2015-02-26 | Bridgeport Energy Wet Compression Upgrade | CC | NG | 18 | 578 | 588 | Fairfield | CT | 2018-06-01 | 2018-05-16 | 2017-09-14 | UI Singer Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed
529 | 2017-06-26 13:46 | G | 2015-02-26 | Combined Cycle CNR Only | CC | NG | 0 | 585.648 | 615 | Worcester | MA | 2017-11-03 | 2017-10-20 | 2017-06-26 | ANP Blackstone 345kV Bus 110785 Station BLK_336 | CNR | FALSE | FALSE |  |  | CMA |  |  |  |  | In Progress
528 | 2016-09-29 08:26 | G | 2015-02-26 | Combined Cycle Upgrate #3 | CC | NG | 30 | 249.583 | 260.73 | Worcester | MA | 2018-10-08 | 2018-09-24 | 2016-09-28 | Milford Power Switch DS-F3 115kV (Nat Grid # D-130-3) and Milford Power Switch DS-A3 115kV (Nat Grid # C-129-3) | CNR | TRUE | FALSE | ISO-NE | PD | CMA |  | Document Posted
527 | 2018-12-20 11:25 | G | 2015-02-26 | Combined Cycle Uprate #2 | CC | NG | 30 | 219.583 | 230.73 | Worcester | MA | 2018-12-14 | 2018-12-13 |  | Milford Power Switch DS-F3 115kV (Nat Grid #D-130-3) and Milford Power Switch DS-A3 115kV (Nat Grid #C-129-3). | CNR | TRUE | TRUE | ISO-NE | PD | CMA |  | Document Posted |  | Document Posted | Executed | In Service
526 | 2016-09-29 08:24 | G | 2015-02-26 | Combined Cycle Upgrade #1 | CC | NG | 40.583 | 189.583 | 200.73 | Worcester | MA | 2018-10-08 | 2018-09-24 | 2016-09-28 | Milford Power Switch DS-F3 115kV (Nat Grid # D-130-3) and Milford Power Switch DS-A3 115kV (Nat Grid # C-129-3) | CNR | TRUE | FALSE | ISO-NE | PD | CMA |  | Document Posted
525 | 2016-11-08 16:02 | G | 2015-02-25 | Tiverton Power LLC Upgrade | CC | NG | 21.5 | 287.5 | 305.5 | Newport | RI | 2016-11-04 | 2016-11-02 |  | near Bell Rock and Somerset on NGRID 115kV lines L14 and M13. | CNR | TRUE | TRUE | ISO-NE |  | RI |  | Document Posted |  |  | Executed | In Service
524 | 2015-03-31 14:41 | G | 2015-02-23 | Combustion Turbine (Alt to Q523) | GT | DFO NG | 0 | 226.5 | 233.5 | Providence | RI | 2019-05-01 | 2019-01-01 | 2015-03-31 | Both National Grid 115kV lines S171 and T172 south of the Rhode Island State Energy tap. | CNR | FALSE | FALSE |  |  | RI
523 | 2015-09-14 08:05 | G | 2015-02-23 | Combustion Turbine | GT | DFO NG | 226.5 | 226.5 | 233.5 | Providence | RI | 2019-05-01 | 2019-01-01 | 2015-09-11 | Both National Grid 345kV lines 328 and 332 south of the Rhode Island State Energy project | CNR | FALSE | FALSE |  | PD | RI |  | Not Started
522 | 2015-07-09 10:10 | G | 2015-02-20 | Plainfield 2.3 MW Capacity Restoration (CNR Only) | ST | WDS | 0 | 38.5 | 38.5 | Windham | CT | 2015-07-01 | 2015-07-01 |  | Frybrook substation, 115 KV | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
521 | 2016-03-10 15:06 | G | 2015-02-17 | Combustion Turbine | GT | DFO NG | 109.799 | 109.799 | 109.799 | Fairfield | CT | 2018-05-02 | 2018-04-04 | 2016-03-10 | CL&amp;P (Eversource) 115 kV Middle River Substation | CNR | FALSE | FALSE |  | PD | SWCT | Not Started |  |  |  |  | Under Study
520 | 2016-03-10 15:06 | G | 2015-02-17 | Simple Cycle gas turbine | GT | DFO NG | 109.799 | 109.799 | 109.799 | Fairfield | CT | 2018-05-02 | 2018-04-04 | 2016-03-10 | Eversource Energy 115 kv Line Middle River Substation 28M | CNR | FALSE | FALSE |  | PD | SWCT | Document Posted |  |  |  |  | Under Study
519 | 2015-08-18 15:23 | ETU | 2015-02-16 | HVDC/AC Tie - Import only | NA | N/A | 1200 | 1200 | 1200 | Rockingham | NH | 2019-04-30 | 2019-03-30 | 2015-08-18 | HQ Des Cantons substation to PSNH Deerfield substation | CNI | FALSE | FALSE |  | PD | NH
518 | 2015-07-09 11:25 | ETU | 2015-02-16 | HVDC from S. Maine to K Street - bidirectional fl | NA | N/A | 1000 | 1000 | 1000 | Suffolk | MA | 2018-12-01 | 2018-11-01 | 2015-07-09 | CMP 345 kV ME Yankee substation to NSTAR 115 kV K Street substation | N/A | FALSE | FALSE |  | PD | BOST
517 | 2015-07-09 11:24 | ETU | 2015-02-16 | HVDC from S. Maine to Mystic - bidirectional flow | NA | N/A | 1000 | 1000 | 1000 | Middlesex | MA | 2018-12-31 | 2018-11-01 | 2015-07-09 | CMP 345 kV ME Yankee substation to NSTAR 345 kV Mystic substation | N/A | FALSE | FALSE |  | PD | BOST
516 | 2015-04-15 09:12 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 425 | 425 | 425 | Addison | VT | 2018-06-30 | 2018-01-30 | 2015-04-15 | HQ to VELCO 345 kV New Haven substation | CNI | FALSE | FALSE |  |  | VT
515 | 2015-04-15 09:11 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 425 | 425 | 425 | Franklin | VT | 2018-06-30 | 2018-01-30 | 2015-04-15 | HQ to VELCO Williston 115 kV substation | CNI | FALSE | FALSE |  |  | VT
514 | 2015-04-17 11:14 | ETU | 2015-02-16 | Expand NB/NE Interface | NA | N/A | 350 | 350 | 350 | Aroostook | ME | 2017-11-01 | 2017-09-01 | 2015-04-17 | NB to ME interface | CNI | FALSE | FALSE |  |  | BHE
513 | 2015-04-17 16:19 | ETU | 2015-02-16 | Coos ETU | NA | N/A |  |  |  | Coos | NH | 2016-07-01 | 2016-07-01 | 2015-04-17 | PSNH Coos area transmission | N/A | FALSE | FALSE |  |  | NH
512 | 2015-04-17 16:19 | ETU | 2015-02-16 | AC to HVDC Tie | NA | N/A | 1200 | 1200 | 1200 | Middlesex | MA | 2019-03-31 | 2019-01-01 | 2015-04-17 | NB 345 kV Keswick or St. Andre substation to NGRID 345 kV Wakefield substation | CNI | FALSE | FALSE |  |  | BOST
511 | 2015-04-15 09:10 | ETU | 2015-02-16 | HVDC Line | NA | N/A | 1000 | 1000 | 1000 | Barnstable | MA | 2020-06-01 | 2020-06-01 | 2015-04-15 | NSTAR 345 kV Barnstable substation | N/A | FALSE | FALSE |  |  | SEMA
510 | 2015-04-15 09:10 | ETU | 2015-02-16 | HVDC Line | NA | N/A | 1000 | 1000 | 1000 | Plymouth | MA | 2020-06-01 | 2020-06-01 | 2015-04-15 | NSTAR 345 kV Carver substation | N/A | FALSE | FALSE |  |  | SEMA
509 | 2015-04-17 14:50 | ETU | 2015-02-16 | HVDC Line | NA | N/A | 1100 | 1100 | 1100 | Middlesex | MA | 2017-06-30 | 2017-03-30 | 2015-04-17 | Orrington substation to NGRID Tewksbury substation | N/A | FALSE | FALSE |  |  | BOST
508 | 2018-10-31 15:30 | ETU | 2015-02-16 | HVDC from NY to WMA - bidirectional | NA | N/A | 600 | 600 | 600 | Berkshire | MA | 2019-08-30 | 2019-07-30 | 2018-10-31 | NY Alps substation to WMECO Berkshire substation | NI | TRUE | TRUE | ISO-NE | PD | WMA |  | Document Posted |  |  | In Progress
507 | 2018-01-30 11:37 | ETU | 2015-02-16 | AC Tie - bidirectional flows | NA | N/A | 75 | 75 | 75 | Aroostook | ME | 2017-07-31 | 2017-07-25 | 2018-01-30 | NMISA Mullen substation to Emera Keene Road substation | NI | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
506 | 2020-02-10 11:06 | ETU | 2015-02-16 | Internal HVDC - North to South flow | NA | N/A | 1000 | 1000 | 1000 | Suffolk | MA | 2027-10-01 | 2027-09-01 | 2020-02-10 | NMISA to NSTAR 345 kV K Street substation | N/A | TRUE | TRUE | ISO-NE | PD | BOST |  | Document Posted |  | Document Posted | In Progress | Under Study
505 | 2015-04-17 16:17 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Windsor | VT | 2017-12-31 | 2017-12-31 | 2015-04-17 | HQ to VELCO 345 kV Coolidge substation | CNI | FALSE | FALSE |  |  | VT
504 | 2015-04-15 08:05 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Addison | VT | 2018-12-31 | 2018-10-31 | 2015-04-15 | HQ 735 kV substation to VELCO 345 kV New Haven substation | CNI | FALSE | FALSE |  |  | VT
503 | 2015-04-15 08:05 | ETU | 2015-02-16 | HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Rutland | VT | 2018-12-31 | 2018-10-31 | 2015-04-15 | HQ 735 kV substation to VELCO 345 kV W. Rutland substation | CNI | FALSE | FALSE |  |  | VT
502 | 2015-04-17 15:25 | ETU | 2015-02-16 | 345 kV Tie - Phase 1 | NA | N/A | 200 | 200 | 200 | Aroostook | ME | 2016-12-01 | 2016-12-01 | 2015-04-17 | Houlton, ME to MEPCO 396 Line | N/A | FALSE | FALSE |  |  | BHE
502 | 2015-04-17 15:26 | ETU | 2015-02-16 | 345 kV Tie - Phase 2 | NA | N/A | 0 | 0 | 0 | Aroostook | ME | 2016-12-01 | 2016-12-01 | 2015-04-17 | Bridgewater, ME to MEPCO 396 Line | N/A | FALSE | FALSE |  |  | BHE
501 | 2021-03-26 12:10 | ETU | 2015-02-16 | NE Clean Power Link - controllable HVDC Tie - Import only | NA | N/A | 1000 | 1000 | 1000 | Windsor | VT | 2027-12-31 | 2027-10-28 |  | HQ 735 kV substation to VELCO 345 kV Coolidge substation | NI | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted | Document Posted |  | Executed
500 | 2019-07-08 13:57 | ETU | 2015-02-16 | Keene Road ETU | NA | N/A |  |  |  | Penobscot | ME | 2018-12-01 | 2018-12-15 | 2018-06-15 | Emera Keene Road substation | N/A | TRUE | FALSE |  | PD | BHE |  | Document Posted
499 | 2019-08-14 14:48 | ETU | 2015-02-16 | Northern Pass Transmission Project (300 kV HVDC/AC Tie) - Import Only | NA | N/A | 1090 | 1090 | 1090 | Rockingham | NH | 2022-12-29 | 2022-11-04 | 2019-08-14 | HQ Des Cantes substation to PSNH Deerfield substation | NI | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed
498 | 2018-02-05 16:16 | ETU | 2015-02-16 | 150 kV HVDC Tie - Import Only | NA | N/A | 400 | 400 | 400 | Colchester | VT | 2020-12-31 | 2020-12-01 | 2018-02-02 | NYPA 230/115 kV substation to VELCO 345 kV New Haven Substation | NI | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | In Progress
497 | 2020-02-04 15:33 | G | 2015-02-13 | Beacon Falls Energy Park | FC | NG | 62.9 | 62.9 | 62.9 | New Haven | CT | 2022-04-01 | 2022-02-01 | 2020-01-30 | Beacon Falls Substation, 180 Cold Spring Rd, Beacon Falls, CT Junction of 115kV lines 1570-1 and 1319 | NR | TRUE | TRUE | ISO-NE |  | SWCT | Document Posted | Document Posted |  |  | Executed
496 | 2019-07-22 09:37 | G | 2015-02-13 | Millinocket Frequency Conversion | HW | WAT | 0 | 126 | 126 | Penobscot | ME | 2019-06-15 | 2019-02-13 |  | Powersville Substation, Emera, 115kV, Line62, existing node424. | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted | Not Required | Not Required | Executed | In Service
495 | 2015-02-17 08:31 | ETU | 2015-02-13 | 1200 MW HVDC Tie - Import Only | NA | N/A |  |  |  | Rockingham | NH | 2018-12-01 | 2018-09-01 | 2015-02-16 | HQ Des Cantons substation to PSNH Deerfield Substation | N/A | FALSE | FALSE |  |  | NH
494 | 2015-02-17 08:31 | ETU | 2015-02-12 | 1000 MW HVDC - bidirectional | NA | N/A |  |  |  | Suffolk | MA | 2018-12-01 | 2018-09-01 | 2015-02-16 | CMP 345 kV ME Yankee to NSTAR 115 kV K Street | N/A | FALSE | FALSE |  |  | BOST
493 | 2015-02-17 08:30 | ETU | 2015-02-12 | 1000 MW HVDC - bidirectional | NA | N/A |  |  |  | Middlesex | MA | 2018-12-31 | 2018-09-01 | 2015-02-16 | CMP 345 kV ME Yankee to NSTAR 345 kV Mystic | N/A | FALSE | FALSE |  |  | BOST
492 | 2017-11-03 08:21 | G | 2015-02-05 | Combustion Turbine Generator | GT | DFO NG | 238 | 238 | 238 | Providence | RI | 2020-05-31 | 2020-03-01 | 2017-10-03 | NGRID 345 kV Sherman Road (via OSP Switchyard) | CNR | TRUE | TRUE | ISO-NE | PD | RI | Document Posted | Document Posted |  |  | In Progress
491 | 2016-01-26 14:19 | G | 2015-01-16 | Fore River CNR Increase | CC | DFO NG | 0 | 800 | 843 | Norfolk | MA | 2016-01-20 | 2016-01-20 |  | NSTAR Edgar 115kv substation | CNR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed | In Service
490 | 2016-05-31 12:28 | G | 2015-01-15 | Kendall Reconfiguration Project | CC | DFO NG | 1.88 | 75 | 75 | Middlesex | MA | 2016-05-31 | 2016-05-31 |  | Where line 875-539 interconnects with TO&#39;&#39;s 115 kv bus at station 875 | CNR | FALSE | FALSE |  |  | BOST |  |  |  |  | Executed | In Service
489 | 2019-11-26 15:26 | G | 2015-01-08 | Clear River | CC | NG | 1030 | 1030 | 1080 | Providence | RI | 2022-05-31 | 2022-01-15 | 2019-11-26 | Sherman Road 345kV Station | NR | TRUE | TRUE | ISO-NE |  | RI | Document Posted | Document Posted |  | Document Posted | IA Filed Unexecuted
488 | 2015-10-16 11:26 | G | 2014-12-22 | Wind | WT | WND | 73.5 | 73.5 | 73.5 | Windham | VT | 2019-12-31 | 2019-10-01 | 2015-10-16 | VELCO Coolidge - Vermont Yankee 345 kV line | CNR | FALSE | FALSE |  |  | VT | Document Posted | In Progress
487 | 2020-04-21 15:23 | G | 2014-12-18 | Cricket Valley Project (QP444 in NYISO Queue) | CC | NG | 1020 | 1020 | 1132 | Dutchess | NY | 2020-04-18 | 2019-07-01 |  | Pleasant Valley - Long Mtn 345 kV | NA | TRUE | FALSE
486 | 2018-06-08 14:28 | G | 2014-12-19 | Wind | WT | WND | 250 | 250 | 250 | Hancock | ME | 2021-12-01 | 2021-10-01 | 2018-06-08 | Rebel Hill 115 kV | NR | FALSE | FALSE |  | PD | BHE | Document Posted |  |  |  |  | Under Study
485 | 2015-04-27 07:58 | G | 2014-12-10 | Combined Cycle | CC | DFO NG | 837 | 837 | 844 | Hampden | MA | 2019-06-01 | 2018-09-01 | 2015-04-23 | Ludlow 19S Substation, Ludlow, MA | CNR | FALSE | FALSE |  |  | WMA |  | In Progress |  |  |  | Under Study
484 | 2015-11-16 09:24 | G | 2014-12-04 | Newington Gas Turbine Uprate | CC | NG | 27.9 | 596.1 | 634.8 | Rockingham | NH | 2015-10-30 | 2015-10-30 |  | Public Service New Hampshire Newington Switchyard - Gosling Road, Newington, NH | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
483 | 2016-03-30 07:56 | G | 2014-11-21 | Wyman Hydro CNR only | HW | WAT | 0 | 89.9 | 89.9 | Somerset | ME | 2016-03-30 | 2016-03-24 |  | Interconnection of Buyer’s 115 kV gang operated disconnect switch BS &#189; to CMP’s 115 kV Bus No. 2 located in the 115 kV switchyard | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed
482 | 2015-01-08 13:53 | G | 2014-11-18 | Hydro | HD | WAT | 1.318 | 0.325 | 0.325 | Rutland | VT | 2014-12-12 | 2014-12-11 | 2015-01-08 | GMP Power Circuit 85G2 from Ryegate Paper Substation No. 85. | CNR | FALSE | FALSE |  |  | VT
481 | 2022-06-15 12:49 | G | 2014-11-18 | GRE Capacity Uprate | CC | NG | 41 | 762 | 812 | Rockingham | NH | 2017-06-29 | 2015-09-01 |  | Watts Brook, North Litchfield | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
480 | 2015-02-23 10:56 | ETU | 2014-11-13 | 1000 MW HVDC Tie | NA | N/A |  |  |  | Suffolk | MA | 2017-12-31 | 2017-10-31 | 2015-02-12 | HQ to NSTAR K Street 115 kV substation | N/A | FALSE | FALSE |  |  | BOST
479 | 2014-11-19 08:16 | G | 2014-10-17 | Combined Cycle Increase | CC | NG | 33 | 754 | 838 | Rockingham | NH | 2015-03-08 | 2015-03-07 | 2014-11-18 | Watts Brook, North Litchfield | CNR | FALSE | FALSE |  |  | NH
478 | 2016-08-17 10:41 | G | 2014-10-01 | Wind | WT | WND | 9.6 | 9.6 | 9.6 | Washington | ME | 2016-06-01 | 2016-05-01 | 2016-08-17 | Emera 34.5kV Line 16 | NA | FALSE | FALSE |  |  | BHE
477 | 2019-06-03 08:24 | G | 2014-09-19 | Deerfield Wind Project | WT | WND | 30 | 30 | 30 | Bennington | VT | 2019-06-01 | 2017-12-08 |  | Future GMP Putnam Road 69 kV Substation on Y-25N Line | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
476 | 2016-06-21 16:47 | G | 2014-08-29 | Wind | WT | WND | 52.8 | 52.8 | 52.8 | Penobscot/Washington | ME | 2017-10-01 | 2017-09-01 | 2016-06-17 | Emera Maine (Bangor Hydro) Keene Road Substation (Connecting through Evergreen Gen Lead, LLC Line 56) | CNR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
475 | 2015-02-17 08:30 | ETU | 2014-08-14 | 600 MW HVDC Tie | NA | N/A |  |  |  | Berkshire | MA | 2019-12-30 | 2019-09-30 | 2015-02-16 | Alps Sub in NY to WMECO Berkshire Sub in MA | N/A | FALSE | FALSE |  |  | WMA
474 | 2015-04-10 08:30 | G | 2014-08-01 | CNR Increase | CC | NG | 0 | 1600 | 1700 | Middlesex | MA | 2016-05-31 | 2016-05-30 | 2015-04-09 | Mystic 115 and 345 kV Stations | CNR | FALSE | FALSE |  |  | BOST
473 | 2014-07-21 11:38 | TS | 2014-06-30 | RNS Application | NA | N/A | 0 | 0 | 0 | Norfolk | MA | 2017-01-01 | 2017-01-01 | 2014-07-21 | NU 115 kV | N/A | FALSE | FALSE |  |  | BOST
472 | 2015-12-29 11:21 | G | 2014-06-20 | Combined Cycle Increase | CC | DFO NG | 22 | 409.9 | 441.1 | Hampden | MA | 2019-03-01 | 2018-06-01 | 2015-12-28 | 115kV Line 1302 between Buck Pond and Pochassic substations, approximately 1 mile south of Buck Pond | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | In Progress
471 | 2018-04-12 09:41 | G | 2014-06-19 | Wind | WT | WND | 600.6 | 600.6 | 600.6 | Aroostook | ME | 2019-12-30 | 2019-11-30 | 2018-04-12 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE | Not Started |  |  |  |  | Under Study
470 | 2018-04-12 09:37 | G | 2014-06-19 | Wind | WT | WND | 600.6 | 600.6 | 600.6 | Aroostook | ME | 2018-12-30 | 2018-11-30 | 2018-04-12 | Primary: Orrington Substations 345kV with two alternatives: Keene Rd. Substation 345kV and the Orrington-Albion Rd 345kV line | NR | FALSE | FALSE |  | PD | BHE | Not Started |  |  |  |  | Under Study
469 | 2015-06-23 12:15 | G | 2014-06-16 | Bridgeport Energy Uprate | CC | NG | 84 | 560 | 588 | Fairfield | CT | 2015-06-05 | 2015-03-31 |  | UI Singer Substation | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed | In Service
468 | 2015-03-16 12:38 | G | 2014-06-02 | Manchester Street Station Increase and CNR | CC | NG | 27 | 510 | 510 | Providence | RI | 2015-03-12 | 2015-03-02 |  | CTGs NGrid 115 kV Franklin Square Substation. STGs NGrid 11.5 kV distribution substation | CNR | TRUE | TRUE | ISO-NE | PD | RI |  | Document Posted |  |  | Executed | In Service
467 | 2020-06-09 08:14 | G | 2014-05-29 | MASSPOWER CNR Recovery | CC | NG | 0 | 256.1 | 279.9 | Hampden | MA | 2014-11-10 | 2014-11-10 |  | 115kV Shawinigan Substation | CNR | FALSE | FALSE |  |  | WMA |  |  |  |  | Executed
466 | 2015-02-17 08:29 | ETU | 2014-05-14 | AC Tie | NA | N/A |  |  |  | Aroostook | ME | 2016-07-31 | 2016-02-28 | 2015-02-16 | NMISA to Emera Keene Rd Substation | N/A | FALSE | FALSE |  |  | BHE
465 | 2015-02-17 08:28 | ETU | 2014-05-13 | 425 MW HVDC Tie | NA | N/A |  |  |  | Addison | VT | 2018-06-30 | 2018-01-30 | 2015-02-16 | VELCO 345 kV New Haven substation | N/A | FALSE | FALSE |  |  | VT
464 | 2015-02-17 08:28 | ETU | 2014-05-12 | 1000 MW HVDC | NA | N/A |  |  |  | Suffolk | MA | 2019-06-30 | 2019-01-30 | 2015-02-16 | NMISA to NSTAR K Street 345 kV substation | N/A | FALSE | FALSE |  |  | BOST
463 | 2015-02-17 08:27 | ETU | 2014-04-30 | 425 MW HVDC Tie | NA | N/A |  |  |  | Franklin | VT | 2018-06-30 | 2018-01-30 | 2015-02-16 | HQ to VELCO Williston 115 kV substation | N/A | FALSE | FALSE |  |  | VT
462 | 2018-04-12 09:35 | G | 2014-04-30 | wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
461 | 2018-04-12 09:32 | G | 2014-04-30 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2018-12-30 | 2018-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
460 | 2018-04-12 09:29 | G | 2014-04-29 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
459 | 2018-04-12 09:26 | G | 2014-04-29 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | Not Started |  |  |  | Under Study
458 | 2018-04-12 09:21 | G | 2014-04-28 | Wind | WT | WND | 104 | 104 | 104 | Aroostook | ME | 2020-12-30 | 2020-09-15 | 2018-04-12 | Pittsfield 345KV | NR | FALSE | FALSE |  | PD | BHE |  | In Progress |  |  |  | Under Study
457 | 2014-11-19 08:15 | ETU | 2014-04-17 | 500 MW HVDC Tie | NA | N/A |  |  |  | Chittenden | VT | 2017-12-31 | 2017-12-31 | 2014-11-18 | HQ to VELCO 115 kV Essex substation | N/A | FALSE | FALSE |  |  | VT
456 | 2015-02-13 07:53 | ETU | 2014-04-17 | 1200 MW HVDC Tie | NA | N/A |  |  |  | Middlesex | MA | 2017-12-31 | 2017-12-31 | 2015-02-12 | HQ to NSTAR 345 kV Mystic substation | N/A | FALSE | FALSE |  |  | BOST
455 | 2015-02-17 08:26 | ETU | 2014-04-17 | 1000 MW HVDC Tie | NA | N/A |  |  |  | Windsor | VT | 2017-12-31 | 2017-12-31 | 2015-02-16 | HQ to VELCO 345 kv Coolidge substation | N/A | FALSE | FALSE |  |  | VT
454 | 2016-06-21 16:47 | G | 2014-04-07 | Wind Increase (see Q452) | WT | WND | 0.8 | 85.8 | 85.8 | Somerset | ME | 2018-12-30 | 2018-11-30 | 2016-06-17 | Harris substation near the Town of Jackman and Misery Township Somerset County, Maine | NR | FALSE | FALSE |  | PD | ME
453 | 2014-06-11 13:51 | G | 2014-03-31 | Offshore Wind | WT | WND | 10 | 10 | 10 | Lincoln | ME | 2017-11-13 | 2017-09-11 | 2014-06-11 | CMP Bristol Substation, Bristol Maine | NR | FALSE | FALSE |  |  | ME
452 | 2016-06-21 16:46 | G | 2014-03-04 | Wind | WT | WND | 85 | 85 | 85 | Somerset | ME | 2018-12-30 | 2018-11-30 | 2016-06-17 | Harris substation near the Town of Jackman and Misery Township Somerset County, Maine | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
451 | 2014-05-21 16:42 | G | 2014-03-04 | Combined Cycle | CC | DFO NG | 100 | 345 | 345 | Fairfield | CT | 2018-05-31 | 2018-05-01 | 2014-05-21 | NU/CL&amp;P Norwalk Harbor 115kV substation | CNR | FALSE | FALSE |  |  | NOR
450 | 2014-05-21 16:41 | G | 2014-03-04 | Combustion Turbine | GT | DFO | 245 | 245 | 245 | Fairfield | CT | 2018-05-31 | 2018-05-01 | 2014-05-21 | NU/CL&amp;P Norwalk Harbor 115kV Substation | CNR | FALSE | FALSE |  |  | NOR
449 | 2019-06-17 08:00 | G | 2014-03-04 | Canal 3 | GT | DFO NG | 333 | 333 | 336.2 | Barnstable | MA | 2019-06-15 | 2019-04-01 |  | NU/NStar 345kV Canal Substation | CNR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted |  |  | Executed | In Service
448 | 2014-06-11 16:03 | G | 2014-03-04 | Fuel Cell | FC | NG | 5.6 | 5.6 | 5.6 | New London | CT | 2018-05-31 | 2018-05-01 | 2014-06-11 | NU/CL&amp;P Montville substation, 4160V station service bus | CNR | FALSE | FALSE |  |  | CT
447 | 2024-08-29 14:17 | G | 2014-03-04 | Passadumkeag Windpark CNR Only | WT | WND | 0 | 39.975 | 39.975 | Penobscot | ME | 2016-07-01 | 2016-04-12 |  | 115kV line between James River and Enfield substations on Line 64 | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
446 | 2014-04-01 09:59 | G | 2014-03-04 | Gas Turbine | GT | DFO NG | 47.5 | 59.5 | 59.5 | Chittenden | VT | 2018-05-31 | 2018-03-31 | 2014-03-31 | Gorge substation, No. 16, Breaker 3320. | CNR | FALSE | FALSE |  |  | VT
445 | 2015-03-02 11:50 | G | 2014-03-04 | Gas Turbine | GT | DFO NG | 103.5 | 103.5 | 103.5 | Norfolk | MA | 2018-05-31 | 2018-02-01 | 2015-03-02 | Edgar 115 kV Station | CNR | FALSE | FALSE |  | PD | SEMA |  | In Progress |  |  |  | Under Study
444 | 2019-05-02 14:12 | G | 2014-05-02 | Medway Peaker - SEMARI | GT | DFO NG | 207.7 | 207.7 | 207.7 | Norfolk | MA | 2019-03-14 | 2019-02-08 |  | Medway 115 kV station | CNR | TRUE | TRUE | ISO-NE | PD | SEMA |  | Document Posted |  |  | Executed | In Service
443 | 2017-05-25 09:43 | G | 2014-03-03 | Brockton Combined Cycle CNR Increase | CC | NG | 0 | 354.9 | 383.9 | Plymouth | MA | 2019-05-31 | 2019-01-25 | 2017-05-25 | Grid 115 kV E20 and F19 Lines | NR | FALSE | FALSE |  |  | SEMA |  |  |  |  | Executed
442 | 2015-12-29 11:20 | G | 2014-02-26 | Combined Cycle | CC | DFO NG | 387.9 | 387.9 | 422.1 | Hampden | MA | 2019-03-01 | 2018-06-01 | 2015-12-28 | 115kV Line 1302 between Buck Pond and Pochassic substations, approximately 1 mile south of Buck Pond. | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | In Progress
441 | 2018-11-26 08:21 | G | 2014-02-25 | Glendale Hydroelectric Expansion Project | HD | WAT | 0.2 | 0.1856 | 0.1856 | Berkshire | MA | 2018-11-13 | 2018-11-07 |  | GRID 13.8 kV | CNR | TRUE | FALSE | NGRID |  | WMA |  | Document Posted |  |  | Executed | In Service
440 | 2018-05-08 08:05 | G | 2014-02-24 | Wallingford Energy Center | GT | NG | 100 | 350 | 350 | New Haven | CT | 2018-05-09 | 2017-12-07 |  | CMEEC 115 kV Wallingford Substation Generating facility. | CNR | TRUE | TRUE | ISO-NE |  | SWCT | Document Posted | Document Posted |  |  | Executed | In Service
439 | 2015-02-12 16:41 | G | 2014-02-24 | Simple Cycle | GT | NG | 478 | 478 | 483 | Essex | MA | 2018-05-01 | 2018-01-01 | 2015-02-12 | GRID Ward Hill – Tewksbury 345 kV line, approximately 1.8 miles from the Ward Hill | CNR | FALSE | FALSE |  |  | CMA | Document Posted | In Progress
438 | 2017-05-31 14:58 | G | 2014-02-24 | Potter Repowering | GT | NG | -21.2 | 63.27 | 65.25 | Norfolk | MA | 2019-05-22 | 2019-02-22 | 2017-05-31 | BELD Station 16 Switchyard | NR | TRUE | TRUE | ISO-NE |  | SEMA |  | Document Posted |  |  | Executed
437 | 2022-06-15 12:48 | G | 2014-02-10 | Jericho Wind expansion | WT | WND | 3.5 |  |  | Coos | NH | 2016-01-23 | 2015-10-16 |  | PSNH Berlin Substation Bus 1 Breaker 3521. | CNR | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
436 | 2014-11-07 08:52 | G | 2014-02-05 | Gas Turbine (alt. to QP412) | GT | DFO NG | 0 | 335 | 335 | Fairfield | CT | 2018-05-31 | 2018-02-01 | 2014-11-07 | 345 kV generator side connection to the transmission grid. | CNR | TRUE | FALSE | ISO-NE | PD | SWCT |  | Document Posted
435 | 2018-01-19 16:33 | G | 2014-01-31 | Wind | WT | WND | 103.5 | 103.5 | 103.5 | Washington | ME | 2018-12-31 | 2018-09-30 | 2018-01-19 | Bangor Hydro Epping Substation, Columbia, Washington County, ME | NR | FALSE | FALSE |  | PD | BHE | Document Posted | In Progress |  |  |  | Under Study
434 | 2015-02-17 08:26 | ETU | 2014-01-29 | Expand Interface | NA | N/A |  |  |  | Aroostook | ME | 2017-11-01 | 2017-09-01 | 2015-02-16 | TBD | N/A | FALSE | FALSE |  |  | BHE
433 | 2014-04-30 14:17 | G | 2014-01-24 | MATEP (Combined Cycle) Increase | CC | DFO NG | 1.7 | 62.083 | 66 | Suffolk | MA | 2014-04-21 | 2014-03-21 |  | At existing point of interconnection for MATEP (Combined Cycle) | CNR | FALSE | FALSE |  |  | BOST |  |  |  |  | Executed | In Service
432 | 2017-03-28 15:56 | ETU | 2014-01-21 | 115 KV ETU | NA | N/A |  |  |  | Aroostook | ME | 2017-07-31 | 2017-07-31 | 2014-05-14 | MPS 69 kV Mullen substation to ME Gen Lead 115 kV line | N/A | FALSE | FALSE |  |  | BHE
431 | 2014-01-29 08:07 | TS | 2014-01-14 | Local Transmission Service - 99 MW | NA | N/A | 0 | 0 | 0 | Coos | NH | 2015-01-01 | 2015-01-01 | 2014-01-28 | NA | N/A | FALSE | FALSE |  |  | NH
430 | 2015-02-17 08:25 | ETU | 2014-01-13 | Coos ETU | NA | N/A |  |  |  | Coos | NH | 2016-07-01 | 2016-07-01 | 2015-02-16 | TBD | N/A | FALSE | FALSE |  |  | NH
429 | 2014-01-10 13:54 | G | 2013-12-02 | Offshore Wind | WT | WND | 12 | 12 | 12 | Lincoln | ME | 2017-11-06 | 2017-10-02 | 2014-01-10 | Central Maine Power, Bristol Substation, Bristol Maine | NR | FALSE | FALSE |  |  | ME
428 | 2015-02-17 08:24 | ETU | 2013-11-15 | 1200 MW AC to HVDC Tie | NA | N/A |  |  |  | Middlesex | MA | 2019-03-31 | 2019-01-01 | 2015-02-16 | NB 345 Keswick or St. Andre substation to GRID 345 kV Wakefield substation | N/A | FALSE | FALSE |  |  | BOST
427 | 2015-02-17 08:23 | ETU | 2013-10-15 | 1000 MW HVDC Tie V3 (See Q425) | NA | N/A |  |  |  | Addison | VT | 2018-12-31 | 2018-10-31 | 2015-02-16 | HQ 735 kV substation to Velco 345 kV New Haven substation | N/A | FALSE | FALSE |  |  | VT
426 | 2015-02-17 08:23 | ETU | 2013-10-15 | 1000 MW HVDC Tie V2 (See Q425) | NA | N/A |  |  |  | Rutland | VT | 2018-12-31 | 2018-10-31 | 2015-02-16 | HQ 735 kV substation to Velco 345 kV W. Rutland Substation | N/A | FALSE | FALSE |  |  | VT
425 | 2015-02-17 08:22 | ETU | 2013-09-23 | 1000 MW HVDC Tie V1 | NA | N/A |  |  |  | Windsor | VT | 2018-12-31 | 2018-10-31 | 2015-02-16 | HQ 735 kV substation to Velco 345 kV Coolidge substation | N/A | FALSE | FALSE |  |  | VT |  | In Progress |  |  |  | Under Study
424 | 2013-11-06 08:12 | G | 2013-09-11 | Hydro Increase | HW | WAT | 0.1 | 0.65 | 0.65 | Hampden | MA | 2014-01-01 | 2014-01-01 | 2013-11-05 | HGE 115 kV North Canal substation | CNR | FALSE | FALSE |  |  | WMA
423 | 2014-03-12 12:26 | G | 2013-09-10 | Wind | WT | WND | 74.29 | 74.29 | 74.29 | Merrimack/Grafton | NH | 2016-12-31 | 2016-10-01 | 2014-03-12 | A201 Comerford - North Litchfield 230 kV line | CNR | FALSE | FALSE |  |  | NH |  | In Progress |  |  |  | Under Study
422 | 2019-05-14 10:56 | G | 2013-07-26 | Number Nine Wind Farm CNR | WT | WND | 0 | 250 | 250 | Aroostook | ME | 2021-10-31 | 2021-04-05 | 2019-05-13 | MEPCO line in Haynesville, ME | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed
421 | 2017-04-11 10:12 | G | 2013-07-18 | Spruce Ridge Wind CNR (see Q390) | WT | WND | 0 | 50.82 | 50.82 | Grafton | NH | 2017-10-31 | 2017-08-18 | 2017-04-10 | NGRID 230 kV Comerford/Dunbarton Line | NR | FALSE | FALSE |  |  | NH |  |  |  |  | Executed
420 | 2020-12-14 08:27 | G | 2013-07-15 | Weaver Wind | WT | WND | 72.6 | 72.6 | 72.6 | Hancock | ME | 2020-12-12 | 2020-10-13 |  | Bull Hill Switching Station | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  | Document Posted | Executed | In Service
419 | 2014-07-03 10:45 | G | 2013-05-02 | Wind | WT | WND | 33 | 33 | 33 | Franklin | ME | 2016-11-01 | 2016-10-01 | 2014-07-02 | CMP 115 kV Bigalow Substation | NR | FALSE | FALSE |  | PD | ME |  | Not Started |  |  |  | Under Study
418 | 2014-02-14 16:36 | G | 2013-05-01 | Biomass | ST | DFO WDS | 37 | 37 | 37 | Windsor | VT | 2015-08-30 | 2015-06-30 | 2014-02-14 | GMP L97 Line | CNR | FALSE | FALSE |  | BL | VT |  | In Progress |  |  |  | Under Study
417 | 2019-05-14 10:57 | G | 2013-04-25 | Number Nine Wind Farm | WT | WND | 250 | 250 | 250 | Aroostook | ME | 2021-10-31 | 2021-04-05 | 2019-05-13 | Pittsfield 345KV | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed
416 | 2013-11-12 13:49 | G | 2013-04-23 | Wind | WT | WND | 18 | 18 | 18 | Coos | NH | 2017-04-30 | 2017-04-12 | 2013-07-17 | Pontook Hydro | CNR | FALSE | FALSE |  |  | NH
415 | 2016-01-25 11:19 | G | 2013-04-12 | Jericho Wind | WT | WND | 8.55 | 8.55 | 8.55 | Coos | NH | 2016-01-23 | 2015-10-16 |  | PSNH Berlin Substation | CNR | TRUE | TRUE | ISO-NE | BL | NH |  | Document Posted |  |  | Executed | In Service
414 | 2014-06-24 08:27 | G | 2013-03-26 | EP Newington Energy Capacity Increase | CC | NG | 21.2 | 568.2 | 594.8 | Rockingham | NH | 2014-06-17 | 2014-05-31 |  | PSNH Newington 345 kV substation | CNR | TRUE | TRUE | ISO-NE | BL | NH |  | Document Posted |  |  | Executed | In Service
413 | 2015-02-17 08:21 | ETU | 2013-03-04 | Keene Rd ETU | NA | N/A |  | 0 | 0 | Penobscot | ME | 2016-03-01 | 2015-11-01 | 2015-02-16 | BHE Keene Road Substation | N/A | FALSE | FALSE |  |  | BHE |  | In Progress |  |  |  | Under Study
412 | 2019-06-10 07:58 | G | 2013-02-28 | PSEG Bridgeport Harbor CCGT Expansion | CC | DFO NG | 509.6 | 509.6 | 532.6 | Fairfield | CT | 2019-06-10 | 2019-05-11 |  | UI 345 kV Singer | CNR | TRUE | TRUE | ISO-NE | BL | SWCT | Document Posted | Document Posted |  |  | Executed | In Service
411 | 2014-07-16 16:12 | G | 2013-02-28 | Gas Turbine Increase | GT | DFO NG | 10.9 | 39.4 | 45.8 | Essex | MA | 2013-12-31 | 2013-12-31 |  | Peabody B-154S line | NA | FALSE | TRUE |  |  | BOST | [5 empty] | In Service
410 | 2014-09-02 10:55 | G | 2013-02-28 | Wind CNR | WT | WND | 0 | 48 | 48 | Peneobscot/Washington | ME | 2016-08-01 | 2016-06-01 | 2014-08-25 | BHE Keene Rd | CNR | FALSE | FALSE |  |  | BHE |  |  |  |  | In Progress
409 | 2015-03-02 11:49 | G | 2013-02-28 | Gas Turbine | GT | DFO NG | 207.7 | 207.7 | 204.4 | Norfolk | MA | 2018-05-31 | 2018-02-01 | 2015-03-02 | NSTAR 230 kV W. Medway Station | CNR | FALSE | FALSE |  | BL | BOST |  | In Progress |  |  |  | Under Study
408 | 2016-03-23 15:12 | G | 2013-02-28 | Gas Turbine | GT | DFO NG | 207.7 | 207.7 | 204.4 | Middlesex | MA | 2018-05-31 | 2018-02-01 | 2016-03-17 | NSTAR 345 kV Mystic Station | NR | TRUE | FALSE |  | PD | BOST |  | Document Posted
407 | 2015-09-16 16:50 | G | 2013-02-27 | Saddleback Increase and CNR (see Q287) | WT | WND | 1.2 | 34.2 | 34.2 | Franklin | ME | 2015-09-15 | 2015-08-15 |  | CMP Ludden Lane Substation | CNR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
406 | 2017-11-29 08:43 | G | 2013-02-22 | Canton Increase and CNR (see Q300) | WT | WND | 3.55 | 22.8 | 22.8 | Oxford | ME | 2017-11-29 | 2017-10-18 |  | CMP Ludden Lane Substation | NR | FALSE | FALSE |  |  | ME |  |  |  |  | Executed | In Service
405 | 2016-12-09 11:05 | G | 2013-01-18 | Block Island Wind Farm | WT | WND | 29 | 29 | 29 | Washington | RI | 2016-12-09 | 2016-11-04 |  | Grid 34.5 kV | NA | TRUE | TRUE | NGRID |  | RI | [5 empty] | In Service
404 | 2017-06-30 10:37 | G | 2013-01-08 | MATEP -3rd CTG | GT | DFO NG | 14.15 | 100 | 105.6 | Suffolk | MA | 2017-06-28 | 2016-12-01 |  | NSTAR Brighton substation | CNR | TRUE | TRUE | ISO-NE | BL | BOST |  | Document Posted |  |  | Executed | In Service
403 | 2016-12-16 13:15 | G | 2012-12-06 | Pisgah Mountain Increase (see Q349) | WT | WND | 0.075 | 9.075 | 9.075 | Penobscot | ME | 2016-12-16 | 2016-11-01 |  | BHE Line 66 | NR | FALSE | FALSE |  |  | BHE |  |  |  |  | Executed | In Service
402 | 2014-01-17 14:03 | G | 2012-10-16 | Mechanicsville Hydro Increase | HD | WAT | 0.31 | 0.31 | 0.31 | Windham | CT | 2013-03-01 | 2013-03-01 |  | CL&amp;P 23 kV at Mechanicsville | CNR | FALSE | FALSE |  |  | CT |  |  |  |  | Executed
401 | 2014-12-11 13:50 | G | 2012-10-05 | Wind | WT | WND | 19.8 | 19.8 | 19.8 | Washington | ME | 2014-12-31 | 2014-11-30 | 2014-08-14 | BHE Epping 115 kV substation or BHE 34.5 kV | CNR | FALSE | FALSE |  | PD | BHE | In Progress |  |  |  |  | Under Study
400 | 2018-04-19 13:22 | G | 2012-10-03 | Downeast Wind | WT | WND | 90 | 90 | 90 | Washington | ME | 2019-10-03 | 2019-07-18 | 2018-04-19 | BHE Epping Substation | NR | TRUE | TRUE | ISO-NE | PD | BHE | Document Posted | Document Posted |  |  | Executed
399 | 2013-02-27 | G | 2012-10-01 | Wind Increase | WT | WND | 1.2 | 34.2 | 34.2 | Franklin | ME | 2014-08-15 | 2014-06-02 | 2013-02-27 | CMP Ludden Lane Substation | CNR | FALSE | FALSE |  |  | ME
398 | 2013-11-15 16:35 | G | 2012-09-04 | Dighton Power Uprate | CC | NG | 5 | 180 | 197 | Bristol | MA | 2013-12-05 | 2013-12-05 |  | GRID 115 kV U6 Line | CNR | TRUE | TRUE | ISO-NE | CD | SEMA |  | Document Posted |  |  | Executed | In Service
397 | 2016-12-14 15:47 | G | 2012-08-30 | Hancock Wind Project | WT | WND | 51 | 51 | 51 | Hancock | ME | 2016-12-14 | 2016-10-01 |  | BHE Line 66 - Bull Hill substation | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
396 | 2020-01-07 13:43 | G | 2012-08-28 | Berkshire Wind Increase | WT | WND | 4.6 | 19.6 | 19.6 | Berkshire | MA | 2019-11-19 | 2019-09-25 |  | WMECO 23 kV from Partridge substation | NR | TRUE | FALSE | NU | BL | WMA |  | Document Posted |  |  | Executed | Under Construction
395 | 2012-10-24 | G | 2012-07-30 | Solar | PV | SUN | 2.18 | 2.18 | 2.18 | Windham | VT | 2013-06-01 | 2013-05-15 | 2012-10-24 | CVPS 46 kV | CNR | FALSE | FALSE |  |  | VT
394 | 2013-12-23 10:12 | G | 2012-07-25 | Bridgeport Fuel Cell I | FC | NG | 5.6 | 5.6 | 5.6 | Fairfield | CT | 2013-12-22 | 2013-11-24 |  | UI 13.8 kV Ash Creek substation | NA | TRUE | TRUE | UI |  | SWCT |  | Document Posted |  |  | Executed | In Service
394 | 2013-12-23 10:12 | G | 2012-07-25 | Bridgeport Fuel Cell 2 | FC | NG | 5.6 | 5.6 | 5.6 | Fairfield | CT | 2013-12-22 | 2013-11-24 |  | UI 13.8 kV New Congress I substation | NA | TRUE | TRUE | UI |  | SWCT |  |  |  |  | Executed | In Service
394 | 2013-12-23 10:13 | G | 2012-07-25 | Bridgeport Fuel Cell 3 | FC | NG | 4.15 | 4.15 | 4.15 | Fairfield | CT | 2013-12-22 | 2013-11-24 |  | UI 13.8 kV New Congress II Substation | NA | TRUE | TRUE | UI |  | SWCT |  |  |  |  | Executed | In Service
393 | 2015-10-28 13:52 | G | 2012-05-07 | Wind | WT | WND | 84 | 84 | 84 | Somerset | ME | 2016-11-01 | 2016-10-01 | 2015-10-28 | CMP 115 kV W. S. Wyman Hydro Substation | NR | FALSE | FALSE |  | PD | ME | Document Posted
392 | 2012-07-23 | G | 2012-03-28 | Wind | WT | WND | 2.7 | 2.7 | 2.7 | Coos | NH | 2012-10-29 | 2012-10-15 | 2012-07-11 | PSNH 12.47 kV | CNR | FALSE | FALSE |  |  | NH
391 | 2015-10-09 14:25 | G | 2012-02-02 | Weston Station Uprate U4 | HD | WAT | 1.6 | 14.806 | 14.806 | Somerset | ME | 2015-07-31 | 2015-07-30 |  | CMP 34.5 kV Weston Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  |  |  |  | Executed | In Service
391 | 2013-12-17 12:33 | G | 2012-02-02 | Weston Station GSU/AVR Replacement U1 | HD | WAT | 0 | 14.806 | 14.806 | Somerset | ME | 2013-12-14 | 2013-12-14 |  | CMP 34.5 kV Weston Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
391 | 2015-10-09 14:26 | G | 2012-02-02 | Weston Station AVR Replacement U2-4 | HD | WAT | 0 | 14.806 | 14.806 | Somerset | ME | 2015-07-31 | 2015-07-30 |  | CMP 34.5 kV Weston Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  |  |  |  | Executed | In Service
390 | 2017-04-11 10:11 | G | 2012-01-30 | Spruce Ridge Wind Farm | WT | WND | 50.82 | 50.82 | 50.82 | Grafton | NH | 2017-10-31 | 2017-09-18 | 2017-04-10 | NGRID 230 kV Comerford/Dunbarton Line | NR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed
389 | 2012-03-23 | G | 2012-01-17 | Solar | PV | SUN | 5.04 | 5.04 | 5.04 | Fairfield | CT | 2013-05-31 | 2013-03-31 | 2012-03-23 | CL&P 115 kV Norwalk Harbor Substation | CNR | FALSE | FALSE |  |  | NOR
388 | 2013-03-26 12:28 | G | 2012-01-13 | Combined Cycle | CC | NG | 680 | 680 | 700 | Fairfield | CT | 2016-05-31 | 2016-03-01 | 2013-03-19 | UI 115 kV or 345 kV |  | FALSE | FALSE |  | PD | SWCT
387 | 2013-03-26 12:27 | G | 2012-01-13 | Gas Turbine Increase | GT | NG | 13.5 | 250 | 250 | New Haven | CT | 2013-02-28 | 2013-02-28 | 2013-03-22 | CMEEC 115kV Wallingford Substation |  | FALSE | TRUE |  |  | SWCT |  | Document Posted |  |  | Executed | Under Construction
387 | 2018-05-31 09:57 | G | 2012-01-13 | Footprint Combined Cycle Unit | CC | NG | 715.6 | 715.6 | 715.6 | Essex | MA | 2018-05-31 | 2017-12-22 |  | NGRID 115 kV Salem Harbor Substation | CNR | TRUE | TRUE | NGRID | BL | BOST |  | Document Posted |  |  | Executed | In Service
386 | 2013-02-05 | G | 2012-01-12 | Westbrook Energy Center Expansion | CC | NG | 9.5 | 538 | 597 | York | ME | 2013-01-31 | 2013-01-31 |  | CMP 115 kV Westbrook Substation | CNR | TRUE | TRUE | ISO-NE | CD | SME |  |  |  |  | Executed
385 | 2014-05-21 10:15 | G | 2012-01-06 | Wind | WT | WND | 60 | 60 | 60 | Calendonia and Essex | VT | 2015-12-01 | 2015-09-01 | 2014-05-21 | VELCO 115 kV Lyndonville substation | CNR | FALSE | FALSE |  | PD | VT | Document Posted | In Progress
384 | 2018-05-21 09:52 | G | 2011-12-29 | CPV Towantic Energy Center | CC | DFO NG | 745 | 745 | 775 | New Haven | CT | 2018-05-21 | 2018-01-24 |  | CL&amp;P 115 kV | CNR | TRUE | TRUE | ISO-NE | PD | SWCT |  | Document Posted |  |  | Executed | In Service
383 | 2013-07-26 09:50 | G | 2011-12-22 | Wind | WT | WND | 198 | 198 | 198 | Franklin | ME | 2016-10-31 | 2015-10-31 | 2013-07-26 | CMP Roxbury substation | CNR | FALSE | FALSE |  | PD | ME | Document Posted
382 | 2012-11-20 | G | 2011-12-05 | Wind | WT | WND | 79.86 | 79.86 | 79.86 | Oxford | ME | 2014-10-31 | 2014-07-31 | 2012-11-20 | CMP 115 kV Rumford to Livermore Line | CNR | FALSE | FALSE |  | PD | ME
381 | 2013-10-21 13:53 | G | 2011-11-14 | Wind | WT | WND | 11.9 | 11.9 | 11.9 | Lincoln | ME | 2017-09-15 | 2017-09-01 | 2013-10-21 | CMP 34.5 kV Boothbay Substation | CNR | TRUE | FALSE | CMP | BL | ME |  | Document Posted
380 | 2015-02-17 08:20 | ETU | 2011-11-10 | 1000 MW HVDC Line | NA | N/A |  |  |  | N/A | MA | 2020-06-01 | 2020-01-01 | 2015-02-16 | NSTAR Carver 345 kV | N/A | FALSE | FALSE |  |  | SEMA |  | Not Started
380 | 2015-02-17 08:21 | ETU | 2011-11-10 | 1000 MW HVDC Line | NA | N/A |  |  |  | N/A | MA | 2020-06-01 | 2020-01-01 | 2015-02-16 | NSTAR Barnstable 345 kV | N/A | FALSE | FALSE |  |  | SEMA |  | Not Started
379 | 2014-09-02 10:58 | G | 2011-10-19 | CornerStone Power Monson 2 | PV | SUN | 4.92 | 4.92 | 4.92 | Hampden | MA | 2014-11-01 | 2014-10-15 | 2014-08-12 | GRID 69 kV N14 Line | NR | TRUE | TRUE | ISO-NE | BL | WMA |  | Document Posted |  |  | Executed | Under Construction
379 | 2014-09-02 10:58 | G | 2011-10-19 | CornerStone Power Monson 3 | PV | SUN | 4.92 | 4.92 | 4.92 | Hampden | MA | 2014-11-01 | 2014-10-15 | 2014-08-12 | GRID 69 kV N14 Line | NR | TRUE | TRUE | ISO-NE | BL | WMA |  | Document Posted |  |  | Executed | Under Construction
378 | 2013-11-15 11:53 | ETU | 2011-10-18 | HVDC Line | NA | N/A | 0 |  |  | N/A | MA | 2015-12-31 | 2015-12-31 | 2013-11-15 | MEPCO 345 kV at Haynesville or MPC 345 KV/GRID 115 | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
377 | 2016-12-23 09:03 | G | 2011-09-14 | Harrington Street PV Project (QF) | PV | SUN | 9.75 | 9.75 | 9.75 | Worcester | MA | 2016-12-23 | 2016-02-08 |  | GRID 69 kV | NA | TRUE | TRUE | NGRID |  | WMA | [5 empty] | In Service
376 | 2012-07-30 | G | 2011-09-08 | Algonquin Power Windsor Locks CNR Increase | IC | NG | 0 | 0 | 0 | Hartford | CT | 2012-07-20 | 2012-06-28 |  | CL&P Windsor Locks 23 kV Substation | CNR | TRUE | TRUE | ISO-NE | BL | CT
375 | 2013-09-27 15:59 | G | 2011-09-07 | Wind | WT | WND | 80 | 80 | 80 | Merrimack/Grafton | NH | 2014-12-31 | 2014-09-30 | 2013-09-27 | GRID Comerford/Merrimack 230 kV Line | CNR | FALSE | FALSE |  | BL | NH
374 | 2012-06-07 | G | 2011-08-24 | Brayton Pt. 1 Exciter Replacement | ST | BIT | 0 | 0 | 0 | Bristol | MA | 2012-05-20 | 2012-05-12 |  | GRID 345 kV Brayton Pt Switchyard | CNR | TRUE | TRUE | ISO-NE |  | RI |  | Document Posted |  |  | Executed | In Service
374 | 2014-01-28 08:10 | G | 2011-08-24 | Brayton Pt. 2 Exciter Replacement | ST | BIT | 0 | 0 | 0 | Bristol | MA | 2014-05-30 | 2014-05-22 | 2013-12-04 | GRID 345 kV Brayton Pt Switchyard | CNR | TRUE | TRUE | ISO-NE | BL | RI |  | Document Posted |  |  | Executed
373 | 2012-09-21 | G | 2011-08-12 | CC Administrative Increase | CC | DFO NG | 0 | 478 | 550 | Hampden | MA |  |  | 2012-09-21 | WMECO Ludlow 19S substation | CNR | FALSE | FALSE |  |  | WMA
372 | 2014-01-07 15:52 | G | 2011-08-03 | Skelton Station Modernization Phase 1 | HD | WAT | 1.083 | 21.083 | 21.083 | York | ME | 2013-12-28 | 2013-12-19 |  | CMP 34.5 kV Louden substation | CNR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted |  |  | Executed | In Service
372 | 2014-01-07 15:52 | G | 2011-08-03 | Skelton Station Modernization Phase 2 | HD | WAT | 1.083 | 22.2 | 22.2 | York | ME | 2013-12-28 | 2013-12-14 |  | CMP 34.5 kV Louden substation | CNR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
371 | 2013-08-06 10:24 | G | 2011-08-01 | Wind | WT | WND | 33 | 33 | 33 | Hillsborough | NH | 2015-07-31 | 2015-06-30 | 2013-08-06 | PSNH L163 115 kV | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted
370 | 2012-10-15 | G | 2011-07-01 | Shepaug AVR Upgrade | HW | WAT | 0 | 0 | 0 | New Haven | CT | 2012-10-16 | 2012-09-23 |  | CL&P 69 kV bus at Shepaug | CNR | TRUE | TRUE | ISO-NE |  | SWCT
369 | 2011-11-29 | G | 2011-06-08 | Combined Cycle | CC | NG | 745 | 745 | 775 | Fairfield | CT | 2016-06-01 | 2016-01-01 | 2011-11-28 | NU 345 kV Line | CNR | FALSE | FALSE |  |  | NOR
368 | 2014-06-10 14:22 | G | 2011-05-27 | Wind | WT | WND | 10 | 10 | 10 | Hillsborough | NH | 2012-09-30 | 2012-09-01 | 2011-08-23 | PSNH 7.2 kV to Milford Substation | CNR | FALSE | FALSE |  |  | NH |  | Document Posted |  |  |  | Under Study
368 | 2013-07-25 16:24 | G | 2011-05-27 | Wind | WT | WND | 16.1 | 16.1 | 16.1 | Hillsborough | NH | 2014-10-31 | 2014-10-01 | 2013-07-25 | PSNH 34.5 kV to Monadnock substation | CNR | TRUE | TRUE | ISO-NE | CD | NH |  | Document Posted
367 | 2012-11-19 | G | 2011-05-26 | Kingdom Community Wind Increase (see Q311) | WT | WND | 3.075 | 64.575 | 64.575 | Orleans | VT | 2012-12-16 | 2012-08-29 |  | VEC Lowell 46 kV station | CNR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted |  |  | Executed
366 | 2016-03-30 07:54 | G | 2011-05-23 | Wyman Hydro Uprate U1 | HW | WAT | 2.5 | 30 | 30 | Somerset | ME | 2016-03-30 | 2016-03-24 |  | CMP 115 kv Wyman | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
366 | 2015-03-25 15:11 | G | 2011-05-23 | Wyman Hydro Uprate U2 | HW | WAT | 0 | 29.9 | 29.9 | Somerset | ME | 2015-03-23 | 2015-03-23 |  | CMP 115 kV Wyman | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
366 | 2016-03-30 07:55 | G | 2011-05-23 | Wyman Hydro Uprate U3 | HW | WAT | 4.3 | 30 | 30 | Somerset | ME | 2016-03-30 | 2016-03-24 |  | CMP 115 kV Wyman | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
365 | 2011-11-14 | G | 2011-04-27 | Bridgeport Harbor #3 CNR Increase | ST | DFO SUB | 5 | 385 | 385 | Fairfield | CT | 2011-10-31 |  |  | UI Pequonnock 115 kV substation | CNR | FALSE | TRUE |  |  | SWCT
364 | 2011-05-26 | G | 2011-04-07 | Solar | PV | SUN | 4.92 | 4.92 | 4.92 | Hampden | MA | 2012-03-31 | 2012-03-01 | 2011-05-18 | GRID 69kV N-14 Line | CNR | FALSE | FALSE |  |  | WMA
363 | 2011-07-29 | G | 2011-03-31 | Solar | PV | SUN | 6 | 6 | 6 | Bristol | MA | 2012-12-31 | 2012-09-30 | 2011-07-29 | NSTAR 115 kV or 13.2 kV | CNR | FALSE | FALSE |  |  | SEMA
362 | 2011-11-17 | G | 2011-03-22 | Milford Hydro Expansion Increase (Q358) | HD | WAT | 0.183 | 9.083 | 9.083 | Penobscot | ME | 2011-11-04 | 2011-11-01 |  | BHE Milford substation | CNR | TRUE | TRUE | BHE |  | BHE |  | Document Posted
361 | 2014-05-19 15:34 | G | 2011-03-14 | Grandpas Knob Wind | WT | WND | 20 | 20 | 20 | West Rutland | VT | 2016-12-31 | 2016-09-30 | 2014-05-19 | VELCO W Rutland 115 kV Substation | NR | TRUE | TRUE | ISO-NE | BL | VT |  | Document Posted |  |  | Executed
360 | 2011-08-03 | G | 2011-03-14 | Indian River Power Supply CNR | HD | WAT | 0 | 1.3 | 1.3 | Hampden | MA | 2011-08-02 |  |  | WMECO 23 kV circuit | CNR | FALSE | FALSE |  |  | WMA
360 | 2015-01-13 12:47 | G | 2011-03-14 | Turners Falls Hydro CNR | HD | WAT | 0 | 0.95 | 0.95 | Franklin | MA | 2012-05-29 | 2012-05-29 |  | WMECO 13.8 kV | NR | FALSE | FALSE |  | BL | WMA
360 | 2012-01-11 | G | 2011-03-14 | Woronoco Hydro CNR | HD | WAT | 0 | 2.7 | 2.7 | Hampden | MA | 2012-01-06 |  |  | WMECO 23 kV | CNR | FALSE | FALSE |  |  | WMA
359 | 2020-06-09 08:12 | G | 2011-03-07 | Bear Swamp AVR/PSS Unit 2 | PS | WAT | 0 | 0 | 0 | Franklin and Berkshire | MA | 2011-07-13 | 2011-06-30 |  | GRID Bear Swamp 230 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
359 | 2012-03-09 | G | 2011-03-07 | Bear Swamp AVR/PSS Unit 1 | PS | WAT | 0 | 0 | 0 | Franklin and Bershire | MA | 2012-03-08 | 2012-03-06 |  | Bear Swamp 230 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
358 | 2011-11-17 | G | 2011-03-04 | Milford Hydro Expansion | HD | WAT | 2.5 | 8.9 | 8.9 | Penobscot | ME | 2011-11-04 | 2011-11-01 |  | BHE Milford Substation | CNR | TRUE | TRUE | BHE |  | BHE |  | Document Posted |  |  | Executed | In Service
358 | 2016-10-26 10:11 | G | 2011-03-04 | Medway Hydro Expansion | HD | WAT | 0.6 | 4.003 | 4.003 | Penobscot | ME | 2012-04-04 | 2012-04-04 |  | BHE Medway substation | CNR | TRUE | TRUE | BHE |  | BHE |  | Document Posted |  |  | Executed
358 | 2011-10-06 | G | 2011-03-04 | Hydro | HD | WAT | 2.274 | 2.274 | 2.274 | Penobscot | ME | 2012-08-15 | 2012-08-01 | 2011-10-05 | BHE Stillwater 12.5 kV substation | CNR | FALSE | FALSE |  |  | BHE |  | Document Posted
358 | 2011-04-12 | G | 2011-03-04 | Hydro | HD | WAT | 3.858 | 3.858 | 3.858 | Penobscot | ME | 2012-08-15 | 2012-08-01 | 2011-04-11 | BHE Orono 12.5 kV substation | CNR | FALSE | FALSE |  |  | BHE
357 | 2016-07-01 08:41 | G | 2011-02-24 | Passadumkeag Windpark | WT | WND | 39.975 | 39.975 | 39.975 | Penobscot | ME | 2016-05-23 | 2016-04-12 |  | BHE 115 kV between Enfield and James River Substat | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
356 | 2012-06-26 | G | 2011-02-04 | Altresco Increase (winter) | CC | DFO NG | 0 | 160 | 192.5 | Berkshire | MA | 2012-06-29 |  |  | WMECO Doreen 19A substation | CNR | TRUE | TRUE | ISO-NE | BL | WMA
355 | 2012-12-04 | ETU | 2011-01-27 | HVDC Tie | NA | N/A |  |  |  | N/A |  | 2016-06-30 |  | 2012-12-04 | UI Singer 345 kV substation to LIPA Pt Jefferson 1 | N/A | FALSE | FALSE
354 | 2011-02-07 | G | 2011-01-12 | Combined Cycle Increase | CC | DFO NG | 20.2 | 157.3 | 185.2 | Berkshire | MA | 2011-04-01 |  | 2011-02-04 | WMECO Doreen 19A Substation | CNR | FALSE | FALSE |  |  | WMA
353 | 2012-08-08 | G | 2010-12-21 | Wind | WT | WND | 9.9 | 9.9 | 9.9 | Plymouth | MA | 2013-12-31 | 2013-11-30 | 2012-08-08 | NSTAR 115 kV Valley substation | CNR | TRUE | FALSE | ISO-NE | BL | SEMA
353 | 2011-06-09 | G | 2010-12-21 | Wind | WT | WND | 14.9 | 14.9 | 14.9 | Barnstable | MA | 2012-11-30 | 2012-10-31 | 2011-06-07 | NSTAR 115 kV Valley substation | CNR | FALSE | FALSE |  |  | SEMA
352 | 2011-05-26 | G | 2010-12-14 | Salem Harbor Station Increase | ST | BIT RFO | 8 | 750.58 | 753.07 | Essex | MA |  |  |  | Salem Switchyard | CNR | FALSE | FALSE |  |  | BOST
351 | 2012-01-11 | G | 2010-12-03 | Gulf Island Unit 2 Increase | HW | WAT | 4.4 | 38.915 | 38.915 | Androscoggin | ME | 2011-04-26 | 2011-04-26 |  | CMP Gulf Island 115 kV | CNR | FALSE | TRUE |  |  | SME
350 | 2015-10-01 10:54 | G | 2010-11-10 | Wind | WT | WND | 92.25 | 92.25 | 92.25 | Washington | ME | 2015-12-31 | 2015-10-01 | 2013-11-15 | BHE Washington County 115 kV substation | NR | FALSE | FALSE |  | PD | BHE | Document Posted | In Progress
350 | 2015-10-05 11:38 | G | 2010-11-10 | Wind | WT | WND | 96.9 | 96.9 | 96.9 | Somerset | ME | 2016-12-31 | 2016-10-01 | 2015-10-05 | CMP Wyman substation | NR | TRUE | FALSE | ISO-NE | PD | ME | Document Posted | In Progress |  |  |  | Under Study
349 | 2016-12-16 13:14 | G | 2010-10-20 | Pisgah Mountain | WT | WND | 9 | 9 | 9 | Penobscot | ME | 2016-12-16 | 2016-11-01 |  | BHE Line 66 | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
348 | 2015-02-17 08:19 | ETU | 2010-10-13 | 1090 MW HVDC Tie - Import Only | NA | N/A |  |  |  | N/A | NH | 2018-06-01 | 2018-05-01 | 2015-02-16 | HQ Des Cantons substation to PSNH Deerfield substa | N/A | TRUE | TRUE | NU |  | NH |  | Document Posted
347 | 2014-02-13 13:37 | G | 2010-10-07 | Bucksport G5 | ST | WDS | 25 | 25 | 25 | Hancock | ME | 2012-11-15 | 2012-10-25 |  | CMP 115 kV | NR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
346 | 2015-04-07 09:45 | G | 2010-10-01 | Burgess BioPower Increase | ST | WDS | 9 | 67.5 | 67.5 | Coos | NH | 2014-06-17 | 2013-10-25 |  | PSNH Eastside (Berlin) Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH |  | Document Posted |  |  | Executed | In Service
345 | 2012-12-27 | G | 2010-09-08 | Groton Wind Farm | WT | WND | 48 | 48 | 48 | Grafton | NH | 2012-12-28 | 2012-10-31 |  | PSNH Beebe River 115 kV Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted
344 | 2011-09-30 | G | 2010-09-07 | Mass Power Increase | CC | NG | 5 | 256.3 | 279.89 | Hampden | MA | 2011-09-30 | 2011-09-30 |  | NU 115 kV Shawanigan | CNR | FALSE | TRUE |  |  | WMA
343 | 2012-03-21 | G | 2010-08-10 | Operating change | ST | NUC | 0 | 0 | 0 | Plymouth | MA |  |  | 2012-03-21 | NSTAR 342 & 355 Line/345 switchyard | NA | FALSE | FALSE |  | BL | SEMA
342 | 2011-06-09 | G | 2010-07-21 | Manchester Street Station Exciter Upgrades & incre | CC | NG | 12 | 483 | 510 | Providence | RI | 2011-06-14 | 2011-02-13 |  | GRID 115 kV Franklin substation | CNR | TRUE | TRUE | ISO-NE | CD | RI
341 | 2013-11-15 11:53 | ETU | 2010-07-19 | HVDC Line | NA | N/A | 0 |  |  | N/A | MA | 2014-12-31 | 2014-12-31 | 2013-11-15 | MEPCO 345kV at Haynesville or MPC 345 kV/NSTAR 345 | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
340 | 2011-03-31 | G | 2010-06-24 | Biomass | ST | WDS | 33 | 33 | 33.3 | Bennington | VT | 2013-03-31 | 2012-12-31 | 2011-03-28 | CVPS East Pownal to Bennington 46 KV line | CNR | FALSE | FALSE |  | BL | VT
339 | 2010-07-22 | G | 2010-06-09 | Exciter Upgrades | CC | NG | 0 | 441 | 492 | Providence | RI | 2011-03-07 | 2011-02-13 | 2010-07-21 | GRID 115 kV Franklin substation | NA | FALSE | FALSE |  |  | RI
338 | 2012-11-19 | G | 2010-05-14 | Wind | WT | WND | 0 | 18 | 18 | Hillsborough | NH | 2013-12-03 | 2013-11-02 | 2012-11-19 | PSNH 34.5 kV 3140 Circuit | NA | FALSE | FALSE |  |  | NH
337 | 2012-01-20 | G | 2010-05-14 | Verso Androscoggin Energy Cogen 1, 2, & 3 Increase | CC | KER NG | 26 | 147 | 180 | Franklin | ME | 2012-01-13 |  |  | CMP Section 227 | CNR | TRUE | TRUE | ISO-NE | BL | ME
336 | 2010-08-04 | G | 2010-05-14 | Manchester Street Station increase | CC | NG | 0 | 471 | 492 | Providence | RI | 2010-08-02 |  |  | GRID 115 kV Franklin substation | CNR | FALSE | FALSE |  |  | RI
335 | 2011-06-30 | G | 2010-05-14 | Biomass | ST | WDS | 18.1 | 18.1 | 18.1 | Hancock | ME | 2012-03-01 | 2012-02-01 | 2011-06-30 | CMP 115 kV | CNR | TRUE | FALSE |  | CD | ME
334 | 2011-03-21 | G | 2010-05-14 | Wind | WT | WND | 30 | 30 | 30 | Hampden | MA | 2012-12-31 | 2012-10-01 | 2011-03-17 | Section #175 115kV line from Palmer to Little Rest | CNR | FALSE | FALSE |  | BL | WMA
333 | 2016-12-13 14:28 | G | 2010-05-14 | Bingham Wind | WT | WND | 184.8 | 184.8 | 184.8 | Somerset | ME | 2016-12-13 | 2016-08-15 |  | CMP Guilford Substation | CNR | TRUE | TRUE | ISO-NE | PD | ME | Document Posted | Document Posted |  |  | Executed | In Service
332 | 2013-02-19 | G | 2010-05-13 | RISEP Increase | CC | NG | 66 | 613 | 625 | Providence | RI | 2012-11-12 | 2011-11-15 |  | 115 kV RISE substation | NR | TRUE | TRUE | ISO-NE | BL | RI |  | Document Posted |  |  | Executed | In Service
331 | 2011-01-10 | G | 2010-05-13 | Waterbury Generation Increase | GT | NG | 7.5 | 103.6 | 103 | New Haven | CT | 2010-10-12 | 2010-09-30 |  | CL&P Baldwin 115 kV substation | CNR | FALSE | TRUE |  |  | SWCT |  |  |  |  | Executed
331 | 2016-05-31 12:21 | G | 2010-05-13 | Kendall #3 Back Pressure Steam Turbine | ST | DFO NG | 7.5 | 28.5 | 28.4 | Middlesex | MA | 2016-05-31 | 2016-05-31 |  | 115 kV Line 875-539 to NSTAR 875 substation | CNR | FALSE | TRUE |  |  | BOST |  |  |  |  | Executed | In Service
330 | 2015-06-09 12:17 | G | 2010-05-10 | Fair Haven Biomass | ST | WDS | 33 | 33 | 33.3 | Rutland | VT | 2016-03-30 | 2016-01-29 | 2015-06-09 | CVPS 46 kV Castleton - Fair Haven | NR | TRUE | TRUE | ISO-NE | BL | VT |  | Document Posted |  |  | Executed
329 | 2012-12-27 | G | 2010-05-07 | Georgia Mountain Community Wind | WT | WND | 10 | 10 | 10 | Chittenden | VT | 2012-12-31 | 2012-12-20 |  | CVPS 34.5 kV Fairfax - Milton Line | CNR | TRUE | TRUE | ISO-NE | BL | VT |  |  |  |  | Executed
328 | 2020-06-09 08:16 | G | 2010-05-06 | Douglas Woods Wind Units 1-11 | WT | WND | 27.5 | 27.5 | 27.5 | Worcester | MA | 2014-10-01 | 2014-08-01 | 2013-09-05 | GRID 69 kV S19 at E. Webster Substation | NR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
328 | 2020-06-09 08:17 | G | 2010-05-06 | Douglas Woods Wind Unit 12 | WT | WND | 2.5 | 30 | 30 | Worcester | MA | 2014-10-01 | 2014-08-01 | 2013-09-05 | GRID 69 kV S19 at E. Webster Substation | NR | TRUE | TRUE | ISO-NE |  | WMA
327 | 2014-08-26 11:52 | G | 2010-05-04 | Wind | WT | WND | 48 | 48 | 48 | Penobscot/Washington | ME | 2016-09-01 | 2016-06-01 | 2014-08-25 | BHE Keene Rd Substation | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | In Progress
326 | 2010-07-19 | G | 2010-04-08 | Solar | PV | SUN | 19.92 | 19.92 | 19.92 | Hampden | MA | 2012-06-01 | 2012-04-01 | 2010-07-26 | GRID 69 kV N-14 Line | CNR | FALSE | FALSE |  |  | WMA
325 | 2011-09-19 | G | 2010-02-10 | Wind | WT | WND | 535.5 | 535.5 | 535.5 | Washington | RI | 2015-12-31 | 2014-09-30 | 2011-09-19 | GRID Brayton Point 345 kV substation | NR | FALSE | FALSE |  | BL | RI
324 | 2015-02-17 08:18 | ETU | 2010-01-22 | 345kV Tie Line - Part 1 | NA | N/A |  |  |  | N/A | ME | 2016-12-01 | 2016-09-01 | 2015-02-16 | Houlton, ME to MEPCO Line | N/A | FALSE | FALSE |  |  | BHE
324 | 2015-02-17 08:19 | ETU | 2010-01-22 | 345 kV Tie Line - Part 2 | NA | N/A |  |  |  | N/A | ME | 2016-12-31 | 2016-09-01 | 2015-02-16 | MEPCO to Bridgewater, ME | N/A | FALSE | FALSE |  |  | BHE
323 | 2010-07-30 | G | 2010-01-21 | Wind Increase (see QP290) | WT | WND | 2 | 20 | 20 | Oxford | ME | 2010-12-30 | 2010-09-30 | 2010-07-29 | CMP Woodstock Substation | CNR | FALSE | FALSE |  |  | ME
323 | 2011-12-21 | G | 2010-01-21 | Spruce Mountain Wind Increase | WT | WND | 2 | 20 | 20 | Oxford | ME | 2011-12-21 | 2011-11-30 |  | CMP Woodstock substation | NA | FALSE | TRUE |  |  | ME
322 | 2011-06-29 | ETU | 2009-12-28 | 345 kV Tie Line | NA | N/A |  |  |  | N/A | ME | 2012-07-01 |  | 2011-06-29 | Houlton to MEPCO Line | N/A | FALSE | FALSE |  |  | BHE
321 | 2014-05-07 13:15 | G | 2009-12-24 | Rumford Falls Unit #3 increase | HD | WAT | 1.3 | 44.1 | 44.1 | Oxford | ME | 2010-06-01 | 2010-06-01 |  | CMP 115 kV Rumford Substation | CNR | FALSE | FALSE |  |  | ME
320 | 2011-11-01 | G | 2009-12-15 | Combined Cycle Repowering | CC | DFO NG | 0 | 0 | 0 | Fairfield | CT | 2014-06-01 | 2014-01-01 | 2011-10-31 | Norwalk Harbor 115 kV station | CNR | FALSE | FALSE |  | CD | NOR
319 | 2011-06-09 | G | 2009-12-14 | Power Station Increase | ST | NUC | 29 | 1253 | 1260 | New London | CT | 2011-11-30 | 2011-11-20 | 2011-06-09 | CL&P Millstone 345 kV substation | CNR | FALSE | FALSE |  | BL | CT
318 | 2010-05-13 | G | 2009-11-24 | Algonquin Power Windsor Locks Cogeneration Facilit | GT | DFO NG | 0 | 47.5 | 47.5 | Hartford | CT | 2010-04-14 | 2010-04-14 |  | CL&P Windsor Locks Substation | CNR | FALSE | FALSE |  |  | CT
317 | 2013-02-05 | G | 2009-11-04 | Bull Hill Wind Phase I | WT | WND | 34.485 | 34.485 | 34.485 | Hancock | ME | 2012-10-31 | 2012-10-04 |  | BHE Line 66 | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed
317 | 2011-08-22 | G | 2009-11-04 | Wind | WT | WND | 46.8 | 81 | 81 | Hancock | ME | 2013-12-31 | 2013-10-01 | 2011-08-22 | BHE Line 66 | CNR | FALSE | FALSE |  | PD | BHE |  | Document Posted
316 | 2011-01-10 | G | 2009-11-02 | Red Shield Acquisition #5 | GT | NG WDS | 9.5 | 26.15 | 27.25 | Penobscot | ME | 2010-10-04 | 2010-09-15 |  | BHE Line 5 - 46 kV | CNR | TRUE | TRUE | BHE |  | ME
315 | 2012-06-15 | G | 2009-10-20 | Cresent Hydroelectric Project Uprate | HD | WAT | 0.667 | 1.667 | 1.667 | Hampden | MA | 2012-06-08 |  |  | WMECO 19J1 23 kV line | CNR | FALSE | FALSE |  | BL | WMA |  |  |  |  | Executed
314 | 2015-02-17 08:17 | ETU | 2009-10-16 | 400 MW 150 kV HVDC Line | NA | N/A |  |  |  | Colchester | VT | 2018-06-01 | 2018-06-01 | 2015-02-16 | NYPA 230.115 kV substation in Plattsburg, NY to near VELCO 345 kV New Haven Substation | N/A | FALSE | FALSE |  |  | VT |  | In Progress
314 | 2009-12-03 | G | 2009-10-16 | Combined Cycle | CC | NG | 410 | 410 | 455 | Plymouth | MA | 2015-05-01 | 2014-12-01 | 2009-12-02 | NSTAR 127 and 128 Lines or new 115 kV | CNR | FALSE | FALSE |  |  | SEMA
314 | 2010-01-27 | TS | 2009-10-16 | RNS Application | NA | N/A |  |  |  | Aroostook | ME | 2011-12-01 |  |  | N/A | N/A | FALSE | FALSE |  |  | BHE
313 | 2012-09-12 | G | 2009-10-08 | Gulf Island Unit 1 Increase | HW | WAT | 0.975 | 33.945 | 34.175 | Androscoggin | ME | 2012-08-24 | 2012-08-23 |  | CMP Gulf Island 115 kV | CNR | FALSE | TRUE |  |  | SME
313 | 2011-05-10 | G | 2009-10-08 | Gulf Island Unit 3 Increase | HW | WAT | 0.569 | 34.514 | 34.744 | Androscoggin | ME | 2011-04-26 | 2010-12-18 |  | CMP Gulf Island 115 kV | CNR | FALSE | TRUE |  |  | SME
312 | 2011-10-19 | G | 2009-09-18 | Biomass | ST | WDS | 20 | 20 | 20 | Cheshire | NH | 2013-10-30 | 2013-06-30 | 2011-10-18 | PSNH 34.5 kV to Winchester substation | CNR | FALSE | FALSE |  | CD | NH
311 | 2012-11-19 | G | 2009-09-15 | Kingdom Community Wind | WT | WND | 61.5 | 61.5 | 61.5 | Orleans | VT | 2012-11-16 | 2012-08-29 |  | VEC Lowell 46 kV station | CNR | TRUE | TRUE | ISO-NE | PD | VT |  | Document Posted |  |  | IA Filed Unexecuted
310 | 2012-11-15 | G | 2009-09-10 | Kibby Wind Expansion | WT | WND | 33 | 33 | 33 | Franklin | ME | 2014-10-15 | 2014-09-01 | 2012-11-15 | Section 267 to CMP Bigalow | CNR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed
309 | 2009-09-28 | G | 2009-09-01 | Hydro Uprate | HD | WAT | 0.975 | 34.038 | 34.038 | Lewiston | ME | 2009-12-01 | 2009-11-01 | 2009-09-28 | CMP Gulf Island 115 kV | CNR | FALSE | FALSE |  |  | ME
308 | 2011-08-08 | G | 2009-08-28 | Wind | WT | WND | 28.8 | 28.8 | 28.8 | Washington | RI | 2012-12-31 | 2012-09-30 | 2011-08-08 | NGRID 3302 Feeder | NR | FALSE | FALSE |  | CD | RI |  | Document Posted
307 | 2012-05-30 | G | 2009-07-14 | Diesel | IC | DFO | 9.125 | 9.125 | 9.125 | Essex | VT | 2013-05-30 | 2013-04-01 | 2012-05-30 | NGRID 34.5 kV Moore/Gilman Line | CNR | TRUE | FALSE | ISO-NE | CD | VT |  | Document Posted
307 | 2009-09-28 | G | 2009-07-14 | Wind Expansion | WT | WND | 45 | 45 | 45 | Franklin | ME | 2011-10-31 | 2011-09-01 | 2009-09-10 | Section 267 | NR | FALSE | FALSE |  |  | ME
306 | 2010-08-04 | G | 2009-07-13 | Hydro | HD | WAT | 3.35 | 3.35 | 3.35 | Hampden | MA | 2014-04-01 | 2014-01-01 | 2010-08-04 | HG&E Prospect 24B substation | CNR | FALSE | FALSE |  |  | WMA
306 | 2013-01-18 | G | 2009-07-13 | Overflow #3 | HD | WAT | 0.5 | 0.5 | 0.5 | Hampden | MA | 2013-11-30 | 2013-10-31 |  | HG&E Holyoke Substation | CNR | FALSE | FALSE |  |  | WMA
305 | 2015-11-19 13:51 | G | 2009-07-10 | Internal Combustion | IC | DFO | 10 | 15.5 | 15.5 | Dukes | MA | 2013-05-31 | 2013-04-30 | 2009-10-20 | NSTAR 23 kV Edgartown0Vineyard Haven Rd Line | CNR | FALSE | FALSE |  |  | SEMA
305 | 2011-07-29 | G | 2009-07-10 | Wind | WT | WND | 66 | 66 | 66 | Grafton/Merrimack | NH | 2012-12-31 | 2012-10-01 | 2011-07-29 | Pemigewassett 115 kV Substation | CNR | FALSE | FALSE |  | PD | NH | Document Posted
305 | 2011-07-29 | G | 2009-07-10 | Wind (non-FERC alternative) | WT | WND | 0 | 66 | 66 | Grafton/Merrimack | NH | 2012-12-31 | 2012-10-01 |  | Pemigewassett 34.5 kV Substation | NA | FALSE | FALSE |  |  | NH
304 | 2009-09-28 | G | 2009-07-06 | Biomass | IC | WDS | 4.9 | 4.9 | 4.9 | Cumberland | ME | 2012-04-30 | 2012-01-30 | 2009-09-16 | CMP Moshers 34.5 kV | CNR | FALSE | FALSE |  |  | SME
303 | 2009-08-20 | G | 2009-06-23 | Biomass | ST | WDS | 7.6 | 7.6 | 7.6 | Cumberland | ME | 2010-03-01 | 2010-02-16 | 2009-08-18 | Rigby/Pleasant Hill 34.5 kV Line | NR | FALSE | FALSE |  |  | SME
303 | 2009-09-28 | G | 2009-06-24 | Biomass | ST |  | 9.5 | 9.5 | 9.5 | Androscoggin | ME |  |  | 2009-07-10 | TBD | NR | FALSE | FALSE |  |  | ME
302 | 2011-04-26 | G | 2009-06-16 | Wind Alternative (see 272) | WT | WND | 0 | 150 | 150 | Aroostook | ME | 2012-12-31 | 2012-09-01 | 2011-04-26 | BHE/MEPCO Line | CNR | FALSE | FALSE |  | PD | BHE
301 | 2015-11-19 13:49 | G | 2009-05-28 | Dundee Wind Increase | WT | WND | 3.9 | 3.9 | 3.9 | Penobscot | ME | 2011-07-26 | 2011-05-01 |  | BHE Keene Rd Substation | NR | TRUE | TRUE | ISO-NE |  | BHE
300 | 2017-11-29 08:42 | G | 2009-05-14 | Canton Mountain Winds | WT | WND | 19.25 | 19.25 | 19.25 | Oxford | ME | 2017-11-29 | 2017-10-18 |  | 229 Line near Riley Substation | NR | TRUE | TRUE | ISO-NE | PD | ME |  | Document Posted |  |  | Executed | In Service
299 | 2012-04-10 | G | 2009-05-11 | Seabrook PSS Enabling | ST | NUC | 0 | 0 | 0 | Rockingham | NH | 2009-11-01 | 2009-11-01 |  | 345 kV Seabrook substation | CNR | TRUE | TRUE | ISO-NE | BL | NH |  |  |  |  | Executed
298 | 2009-05-12 | G | 2009-04-15 | Wind Uprate (see QP290) | WT |  | 1.5 | 1.5 | 1.5 | Oxford | ME | 2010-11-30 | 2010-09-30 | 2009-05-12 | CMP Woodstock Station | NR | FALSE | FALSE |  |  | ME
297 | 2012-01-11 | G | 2009-03-25 | Wind | WT | WND | 201.6 | 201.6 | 201.6 | Aroostook | ME | 2013-10-01 | 2013-07-01 | 2012-01-09 | MEPCO Line at Haynesville, ME | CNR | FALSE | FALSE |  | PD | BHE
296 | 2009-07-31 | G | 2009-02-20 | Biomass | ST | WDS | 30 | 30 | 30 | Windsor | VT | 2011-05-01 | 2011-03-01 | 2009-07-30 | CVPS 46 kV circuit in Springfield Area | MIS | FALSE | FALSE |  |  | VT
296 | 2010-05-19 | G | 2009-02-23 | Wind Farm | WT | WND | 12 | 12 | 12 | Chittenden | VT | 2010-12-31 | 2010-12-31 |  | CVPS 34.5 kV Fairfax - Milton line | NA | FALSE | FALSE |  |  | VT
296 | 2013-03-20 13:58 | G | 2009-03-20 | Salem Harbor 2 Exciter Replacement | ST | BIT | 0 | 0 | 0 | Essex | MA | 2009-11-15 | 2009-11-15 |  | Salem Switchyard | NA | TRUE | TRUE | ISO-NE |  | BOST |  |  |  |  | Executed
295 | 2015-07-29 15:39 | G | 2009-02-09 | Combined Cycle | CC | NG | 898 | 898 | 1012 | Plymouth | MA | 2015-03-01 | 2014-09-01 | 2009-05-08 | 345 kV 322 Line | CNR | FALSE | FALSE |  |  | SEMA
294 | 2015-07-29 15:38 | G | 2009-02-05 | Wind | WT | WND | 20 | 20 | 20 | Washington | RI | 2012-06-30 | 2012-04-30 | 2009-05-07 | NGRID 34.5 kV 3302 line | NS | FALSE | FALSE |  |  | RI
293 | 2010-05-19 | G | 2009-01-30 | Red Shield Acquisition - Hydro | HD | WAT | 0 | 5 | 5 | Penobscot | ME | 2009-07-20 |  |  | BHE's Line 5 - 46 kV | CNR | FALSE | FALSE |  |  | ME
293 | 2010-05-19 | G | 2009-01-30 | Red Shield Acquisition - Biomass | ST | WDS | 0 | 13 | 16 | Penobscot | ME | 2009-07-20 |  |  | BHE's Line 5 - 46 kV | CNR | FALSE | FALSE |  |  | ME
292 | 2010-02-01 | G | 2009-01-30 | Biomass Project | ST | WDS | 49.7 | 49.7 | 51.5 | Berkshire | MA | 2013-10-01 | 2013-07-01 | 2010-01-26 | Doreen 115 kV substation of F132 115 kV line | CNR | FALSE | FALSE |  | BL | WMA
291 | 2010-06-24 | G | 2009-01-21 | Merrimack Unit 2 Second Uprate | ST | BIT | 17.175 | 340 | 353.5 | Merrimack | NH | 2010-06-17 | 2010-06-01 |  | PSNH Merrimack Substation | CNR | TRUE | TRUE | ISO-NE | BL | NH
290 | 2010-07-29 | G | 2009-01-15 | Wind | WT | WND | 18 | 18 | 18 | Oxford | ME | 2010-12-30 | 2010-09-30 | 2010-07-29 | CMP Woodstock Substation | CNR | TRUE | TRUE | ISO-NE | BL | ME
290 | 2011-12-21 | G | 2009-01-15 | Spruce Mountain Wind | WT | WND | 18 | 18 | 18 | Oxford | ME | 2011-12-21 | 2011-11-30 |  | CMP Woodstock substation | NA | TRUE | TRUE | ISO-NE |  | ME
289 | 2013-08-05 15:02 | G | 2009-01-08 | Fuel Cell | FC | NG | 9 | 9 | 9 | New Haven | CT | 2012-06-15 | 2012-05-15 | 2013-08-05 | UI&#39;&#39;s Milvon substation | NA | TRUE | TRUE | UI |  | SWCT
289 | 2011-11-10 | G | 2009-01-08 | Sikorsky Aircraft | GT | NG | 10.265 | 10.265 | 10.265 | Fairfield | CT | 2011-10-05 | 2011-07-24 |  | UI's Trap Falls substation | NA | TRUE | TRUE | UI |  | SWCT
289 | 2010-06-02 | G | 2009-01-08 | Yale University - Sterling Power Plant | GT | NG | 17.6 | 17.6 | 17.6 | New Haven | CT | 2010-05-26 | 2010-05-01 |  | UI's Water Street substation | NA | TRUE | TRUE | UI |  | SWCT
288 | 2009-09-25 | TS | 2008-12-18 | Local Service Application - 87 MW |  |  | 0 |  |  | Somerset | ME | 2009-09-01 |  |  | N/A | N/A | TRUE | FALSE | ISO-NE |  | ME |  | Document Posted
287 | 2015-09-16 16:49 | G | 2008-12-18 | Saddleback Ridge Wind Project | WT | WND | 33 | 33 | 33 | Franklin | ME | 2015-09-15 | 2015-08-15 |  | 115kV Line 229 | NR | TRUE | TRUE | ISO-NE | BL | ME |  | Document Posted |  |  | Executed | In Service
286 | 2009-09-30 | G | 2008-12-05 | Gas Turbine | GT | NG | 187.5 | 187.5 | 199 | Worcester | MA | 2012-06-01 | 2012-02-01 | 2009-09-30 | 115 kV bus at Millbury substation | MIS | FALSE | FALSE |  |  | CMA
285 | 2012-08-29 | G | 2008-10-24 | Gas Turbine | GT | NG | 35 | 35 | 35 | Penobscot | ME | 2014-07-31 | 2014-06-30 | 2012-08-29 | BHE Powersville substation | CNR | TRUE | FALSE | ISO-NE | PD | BHE
284 | 2012-04-10 | G | 2008-10-22 | Seabrook LP Turbine Blade replacement | ST | NUC | 13 | 1257 | 1257 | Rockingham | NH | 2012-04-05 | 2010-12-31 |  | 345 kV Seabrook Substation | CNR | TRUE | TRUE | ISO-NE |  | NH |  |  |  |  | Executed
283 | 2015-02-17 08:16 | ETU | 2008-10-20 | 1100 MW HVDC Line | NA | N/A | 0 |  |  | N/A | MA | 2017-06-30 | 2017-03-30 | 2015-02-16 | Orrington ME and BostonMA | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
282 | 2011-06-29 | G | 2008-10-15 | Biomass Project | ST | WDS | 49.7 | 49.7 | 51.5 | Franklin | MA | 2014-02-01 | 2013-11-01 | 2011-06-28 | 115 kV line near Montage or Fench King substations | CNR | FALSE | FALSE |  | BL | WMA
281 | 2010-03-31 | G | 2008-10-06 | Wind | WT | WND | 85 | 85 | 85 | Rutland | VT | 2011-09-01 | 2011-07-01 | 2010-03-30 | VELCO 115 kV K34 line | CNR | FALSE | FALSE |  | BL | VT | Document Posted
281 | 2009-02-12 | G | 2008-10-07 | Equipment Addition | CC | NG | 45 |  |  | Windham | CT | 2009-01-30 | 2008-06-01 |  | CL&P 345 kV Lake Road substation | MIS | FALSE | FALSE |  |  | RI
280 | 2010-09-24 | G | 2008-10-02 | Wind | WT | WND | 180 | 180 | 180 | Coos | NH | 2011-09-01 | 2011-07-01 | 2010-09-24 | PSNH W-179 115 kV | CNR | FALSE | FALSE |  | PD | NH | Document Posted
279 | 2009-03-19 | G | 2008-09-30 | Biomass | ST | WDS | 30 | 30 | 30 | Windsor | VT | 2011-05-01 | 2011-03-01 | 2009-02-20 | CVPS 46kV circuit in Springfield area | MIS | FALSE | FALSE |  |  | VT
278 | 2014-06-13 12:52 | ETU | 2008-09-26 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A | MA | 2017-03-31 | 2017-03-31 | 2014-06-13 | Maine Yankee Substation, South Boston Substation | N/A | FALSE | FALSE |  |  | BOST |  | Not Started
277 | 2009-03-19 | G | 2008-09-12 | Combined Cycle | CC | DFO NG | 695 | 695 | 695 | Fairfield | CT | 2013-06-01 | 2013-01-15 | 2009-02-13 | CL&P 345 KV 321 line | MIS | FALSE | FALSE |  |  | SWCT
277 | 2014-12-22 13:16 | G | 2008-09-22 | Combined Cycle (QP310 in NYISO Queue) | CC | NG | 1002 | 1002 | 1115 | Dutchess | NY | 2018-01-31 | 2017-07-01 | 2014-12-18 | Pleasant Valley - Long Mtn 345 kV | NA | FALSE | FALSE
276 | 2014-09-19 13:18 | G | 2008-09-02 | Deerfield Wind | WT | WND | 30 | 30 | 30 | Bennington | VT | 2013-12-31 | 2013-10-01 | 2014-09-11 | Y-25 North, 69 kV line between Searsburg and Benni | NR | TRUE | TRUE | ISO-NE | BL | WMA | Document Posted | Document Posted |  |  | Executed
275 | 2017-04-21 06:54 | ETU | 2008-08-27 | Two terminal, 2000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  | 2008-09-15 | Maine Yankee Substation, South Boston Substation | N/A | FALSE | FALSE
274 | 2012-10-04 | G | 2008-08-07 | GMP Generator Replacement | GT | DFO NG | 29.5 | 41.5 | 48.7 | Chittenden | VT | 2014-06-01 | 2014-05-01 | 2012-10-14 | GMP Gorge Substation | CNR | TRUE | TRUE | ISO-NE |  | VT |  | Document Posted
274 | 2009-03-19 | TS | 2008-08-25 | Wind project point-to-point application | NA | N/A | 0 | 100 | 100 | Aroostoock | ME | 2011-10-01 |  |  | N/A | N/A | FALSE | FALSE |  |  | BHE
273 | 2019-11-01 08:56 | G | 2008-08-03 | Palmer Renewable Energy | ST | WDS | 36.7 | 36.7 | 37 | Hampden | MA | 2020-07-15 | 2020-06-15 | 2019-10-16 | 115 kV line near E. Springfield substation | NR | TRUE | TRUE | ISO-NE | BL | WMA | Document Posted | Document Posted |  |  | Executed | Under Construction
272 | 2009-06-17 | G | 2008-08-01 | Wind | WT | WND | 64 | 64 | 64 | Franklin | ME | 2012-08-01 | 2012-06-01 | 2009-06-15 | CMP Rumford or Bigelow Substation | MIS | FALSE | FALSE |  |  | ME | Document Posted | Document Posted |  |  | IA Filed Unexecuted
272 | 2008-10-03 | G | 2008-08-01 | Wind | WT | WND | 0 | 150 | 150 | Aroostoock | ME | 2011-08-01 | 2011-05-01 | 2008-10-03 | BHE Millinocket Substation | MIS | FALSE | FALSE |  |  | BHE
272 | 2009-04-15 | G | 2008-08-01 | Wind | WT | WND | 0 | 150 | 150 | Aroostoock | ME | 2011-08-01 | 2011-05-01 | 2009-03-10 | BHE Powersville Substation | MIS | FALSE | FALSE |  |  | BHE
272 | 2010-02-16 | G | 2008-08-01 | Wind | WT | WND | 85 | 85 | 85 | Somerset | ME | 2012-08-01 | 2012-06-01 | 2010-02-03 | CMP 115 KV LINE 222 | CNR | FALSE | FALSE |  | PD | ME | Document Posted
272 | 2009-05-01 | G | 2008-08-01 | Wind | WT | WND | 128 | 128 | 128 | Aroostoock | ME | 2013-12-31 | 2013-10-31 | 2009-04-21 | BHE 345 kV 396 line | MIS | FALSE | FALSE |  |  | BHE
272 | 2015-10-29 08:43 | G | 2008-08-01 | Oakfield II Wind - Keene Road | WT | WND | 135.5 | 135.5 | 135.5 | Aroostoock | ME | 2015-10-29 | 2015-07-29 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE | PD | BHE |  | Document Posted |  |  | Executed | In Service
271 | 2017-04-21 06:53 | ETU | 2008-07-30 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  | 2009-05-12 | Hertel S/S in Quebec or Clay S/S in NY and Norwalk | N/A | FALSE | FALSE
271 | 2010-01-29 | ETU | 2008-07-30 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  |  | Hertel S/S in Quebec or Clay S/S in NY and Glenbro | N/A | FALSE | FALSE
271 | 2010-07-16 | ETU | 2008-07-30 | Two terminal, 1000 MW , 500 kV, dc line | NA | N/A | 0 |  |  | N/A |  | 2014-03-31 |  |  | Hertel S/S in Quebec or Clay S/S in NY and Singer | N/A | FALSE | FALSE
271 | 2009-10-22 | TS | 2008-08-01 | MPS RNS Application | NA | N/A | 0 |  |  | Aroostoock | ME | 2010-10-01 |  |  | N/A | N/A | FALSE | FALSE |  |  | BHE
270 | 2011-03-31 | G | 2008-07-17 | Pumped Storage Project | PS | WAT | 1000 | 1000 | 1000 | Wiscasset | ME | 2014-06-01 | 2014-06-01 | 2011-03-31 | Maine Yankee 345 kV substation | NR | FALSE | FALSE |  | BL | ME | Document Posted
269 | 2011-08-03 | G | 2008-07-14 | Indian River Power | HD | WAT | 1.28 | 1.28 | 1.28 | Hampden | MA | 2011-08-02 | 2011-03-31 |  | WMELCO 23 kV circuit | NR | TRUE | TRUE | NU |  | WMA |  | Document Posted
268 | 2009-05-01 | G | 2008-07-08 | Wind ( increase in queue position 266) | WT | WND | 8.5 | 8.5 | 8.5 | Orleans | VT | 2011-12-31 | 2011-09-15 | 2009-04-13 | CVPS Lowell Substation | MIS | FALSE | FALSE |  |  | VT
267 | 2009-03-19 | G | 2008-06-24 | Gas Turbine Capacity Increase ( See queue position | GT | DFO NG | 175 | 175 | 222 | Fairfield | CT | 2011-06-01 | 2011-02-01 | 2009-03-09 | 345 kV line # 321 | MIS | FALSE | FALSE |  |  | SWCT
266 | 2009-05-01 | G | 2008-06-19 | Wind | WT | WND | 34 | 34 | 34 | Orleans | VT | 2011-12-31 | 2011-09-15 | 2009-04-13 | CVPS Lowell Substation | MIS | FALSE | FALSE |  |  | VT
265 | 2013-12-05 09:09 | G | 2008-06-16 | MATEP - Third CTG | GT | DFO NG | 12.5 | 12.5 | 14 | Suffolk | MA | 2014-06-01 | 2014-05-01 | 2013-01-07 | NSTAR Brighton Substation | CNR | TRUE | TRUE | NSTAR |  | BOST
264 | 2008-07-10 | G | 2008-06-04 | Landfill Gas | IC | LFG | 0.8 | 0.8 | 0.8 |  | NH | 2008-11-30 | 2008-11-01 | 2008-07-10 | NHEC 12.5 kV circuit | MIS | FALSE | FALSE |  |  | NH
264 | 2009-09-28 | G | 2008-06-11 | Biomass Project | ST | WDS | 10 | 10 | 10 | Grafton | NH | 2010-06-01 | 2010-06-01 | 2009-09-28 | PSNH 34.5 kV circuit #343 | NA | FALSE | FALSE |  |  | NH
263 | 2010-03-25 | G | 2008-05-27 | Wind | WT | WND | 385 | 385 | 385 | Washington | RI | 2012-12-01 | 2011-06-01 | 2010-03-24 | West Kingston Substation | CNR | FALSE | FALSE |  | BL | RI
262 | 2011-11-10 | G | 2008-05-23 | Rhode Island Landfill Gas Genco Increase (see QP # | CC | LFG | 6 | 45.9 | 50.1 | Providence | RI | 2013-09-01 | 2013-09-01 | 2011-11-09 | NGRID 115 kV S171 line | CNR | TRUE | TRUE | NGRID |  | RI |  | Document Posted
261 | 2008-11-07 | G | 2008-05-19 | Combined Cycle | CC | NG | 221.6 | 440 | 497 |  | ME | 2013-12-31 | 2013-06-30 | 2008-11-07 | Yarmouth Substation 115 kV bus | MIS | FALSE | FALSE |  |  | ME
260 | 2009-03-19 | G | 2008-05-08 | Wind | WT | WND | 450 | 450 | 450 | N/A | RI | 2013-12-31 | 2012-06-30 | 2009-02-27 | Brayton Point 115 kV bus or Dexter 115 kV bus | MIS | FALSE | FALSE |  |  | RI
260 | 2009-03-19 | G | 2008-05-08 | Wind | WT | WND | 0 | 450 | 450 | N/A | RI | 2013-12-31 | 2012-06-30 | 2009-02-27 | Kent County 115 kV bus or Davisville 115 kV bus | MIS | FALSE | FALSE |  |  | RI
259 | 2010-08-19 | G | 2008-05-07 | Combined Cycle | CC | NG | 27 | 551 | 616.3 | Providence | RI | 2012-06-01 | 2012-06-01 | 2010-08-11 | 115 kV RISE Substation | CNR | FALSE | FALSE |  | PD | RI
259 | 2009-02-12 | G | 2008-05-07 | Combined Cycle | CC | DFO NG | 27 | 303.3 | 340.2 | Norfolk | MA | 2010-06-01 | 2010-06-01 | 2009-01-28 | 345 kV NEA Bellingham Substation | MIS | FALSE | FALSE |  |  | RI
258 | 2015-11-19 13:47 | G | 2008-04-15 | Merrimack Unit 2 Uprate | ST | BIT | 4.65 | 327.5 | 337 | Merrimack | NH | 2008-05-26 |  |  | PSNH Merrimack Substation | MIS | FALSE | FALSE |  |  | NH
257 | 2013-09-16 10:20 | G | 2008-04-14 | Wind Project-Phase 4( MPS Queue # 8) | WT | WND | 250 | 250 | 250 | N/A | ME | 2013-09-01 |  | 2013-09-03 | Maine Public Service System, upgrades include tap | NA | FALSE | FALSE | MPS |  | BHE
257 | 2013-09-16 10:21 | G | 2008-04-14 | Wind Project-Phase 5( MPS Queue # 9) | WT | WND | 150 | 150 | 150 | N/A | ME | 2013-09-01 | 2013-09-03 | 2013-09-03 | Maine Public Service System, upgrades include tap | NA | FALSE | FALSE | MPS |  | BHE
256 | 2013-03-26 12:53 | G | 2008-04-04 | Steam Turbine | ST | WDS | 20 | 20 | 20 | Merrimack | NH | 2013-03-31 | 2012-12-30 | 2013-03-02 | Unitil 34.5kV line from PSNH Garvins station to UE | NA | FALSE | FALSE |  |  | NH
255 | 2009-12-03 | G | 2008-03-31 | Wind | WT | WND | 50 | 50 | 50 | Grafton | NH | 2010-12-31 | 2010-10-01 | 2009-09-30 | 115 kV Plymouth substation | CNR | FALSE | FALSE |  |  | NH
255 | 2012-11-13 | G | 2008-03-31 | Distribution Wind Alternative | WT | WND | 2 | 50 | 50 | Grafton | NH | 2012-12-31 | 2012-10-01 |  | PSNH Ashland 34.5 kV | NA | FALSE | FALSE |  |  | NH
254 | 2009-08-31 | G | 2008-03-10 | Wind | WT | WND | 19.5 | 19.5 | 19.5 | Penobscot | ME | 2010-11-01 | 2010-11-01 | 2009-08-25 | CMP 115 kV line # 203 | CNR | FALSE | FALSE |  |  | ME
254 | 2015-09-03 08:36 | G | 2008-03-25 | Wind Project | WT | WND | 12.5 | 12.5 | 12.5 | Berkshire | MA | 2016-11-30 | 2016-10-31 | 2015-09-02 | WMECO Berkshire substation 23 kV circuit | NA | FALSE | FALSE |  |  | WMA
253 | 2009-06-17 | G | 2008-03-11 | Combined Cycle | CC | DFO | 269 | 269 | 310 | Fairfield | CT | 2011-06-01 | 2011-02-01 | 2009-06-01 | CL&P 115 kV 1876 line | MIS | FALSE | FALSE |  |  | SWCT
252 | 2010-07-30 | G | 2008-02-13 | Foxwoods Central Plant | GT | NG | 13.2 | 13.2 | 17.6 | New London | CT | 2010-07-15 | 2010-04-30 |  | CL&P 23 kV feeders from Tunnel and Mystic Substati | NA | TRUE | TRUE | NU |  | CT
251 | 2014-06-18 10:37 | G | 2008-02-15 | Burgess BioPower | ST | WDS | 58.7 | 58.7 | 58.7 | Coos | NH | 2014-06-17 | 2013-10-25 |  | PSNH Eastside(Berlin) Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  |  | Executed | In Service
250 | 2011-11-30 | G | 2008-02-13 | Hamilton Sundstrand | GT | NG | 5 | 4.9 | 6.1 | Hartford | CT | 2011-10-01 | 2011-09-30 |  | CL&P Windsor Locks Substation | NA | FALSE | TRUE |  |  | CT
249 | 2013-02-05 | G | 2008-02-04 | Stetson Wind II(Jimmey & Owl Mt.-UPC) | WT | WND | 2.2 | 26.2 | 26.2 | Washington | ME | 2010-03-12 | 2010-01-15 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE |  | BHE
248 | 2015-11-19 13:05 | G | 2008-02-07 | New Haven Harbor 2-4 | GT | DFO NG | 129.6 | 129.6 | 145.8 | New Haven | CT | 2012-05-23 | 2012-04-11 |  | UI East shore Substation 115 kV bus | CNR | TRUE | TRUE | ISO-NE | PD | CT | Document Posted
247 | 2009-04-17 | G | 2008-01-31 | Reconnect Existing Hydro | HD | WAT | 0 | 4.1 | 4.1 | Orleans | VT | 2010-05-31 | 2010-05-01 | 2009-04-02 | VELCO Newport Substation 46 kV bus | MIS | FALSE | FALSE |  |  | VT
247 | 2009-04-17 | G | 2008-01-31 | Diesel generation | IC | DFO | 10.3 | 10.3 | 10.3 | Orleans | VT | 2009-05-01 | 2009-05-01 | 2009-04-02 | VELCO Newport Substation 46 kV bus | MIS | FALSE | FALSE |  |  | VT
246 | 2008-12-31 | G | 2008-01-29 | Gas Turbine | GT | NG | 77 | 77 | 87 | Worcester | MA | 2011-06-01 | 2011-03-01 | 2008-12-31 | 115 kV bus at Millbury substation | MIS | FALSE | FALSE |  |  | CMA
245 | 2013-02-05 | G | 2008-01-11 | Stetson Wind II(Jimmey & Owl Mt.-UPC) See # 249 | WT | WND | 24 | 24 | 24 | Washington | ME | 2010-03-12 | 2010-01-15 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE |  | BHE
244 | 2012-03-23 | G | 2008-01-03 | Wind | WT | WND | 117 | 117 | 117 | Somerset | ME | 2013-12-30 | 2013-10-01 | 2012-03-21 | CMP 115 kV Wyman substation | CNR | TRUE | TRUE | ISO-NE | BL | ME | Document Posted | Document Posted
243 | 2011-12-14 | G | 2008-01-04 | Increase to Steam Turbine Capacity Uprate (See QP | ST | BIT | 6 | 648 | 669 | Bristol | MA | 2011-12-12 | 2011-12-11 |  | Brayton Point 345 kV Switchyard | NR | TRUE | TRUE | ISO-NE |  | RI
242 | 2009-09-25 | G | 2008-01-03 | Biomass Project | ST | WDS | 20 | 20 | 20 | Cheshire | NH | 2013-10-30 | 2013-06-30 | 2009-09-18 | PSNH 115 kV N186 circuit | CNR | FALSE | FALSE |  |  | NH
241 | 2012-01-30 | G | 2007-12-31 | Towantic Energy increase | CC | DFO NG | 38 | 489 | 557 | New Haven | CT | 2014-12-31 | 2014-06-30 | 2012-01-27 | CL&P 115 kV lines between Baldwin Junction and Bea | CNR | TRUE | TRUE | ISO-NE |  | SWCT
240 | 2010-10-27 | G | 2007-12-18 | Gas Turbine | GT | KER NG | 94 | 94 | 98 | New London | CT | 2013-06-01 | 2013-01-01 | 2010-10-27 | Montville Substation | CNR | FALSE | FALSE |  | BL | CT | Document Posted
239 | 2008-11-12 | G | 2007-12-12 | Gas Turbine Capacity Increase ( See queue position | GT | DFO NG | 35 | 360 | 436 | Fairfield | CT | 2010-09-30 | 2010-06-30 | 2008-10-22 | UI 345 kV Singer Substation | MIS | FALSE | FALSE |  |  | SWCT
238 | 2010-06-24 | G | 2007-12-07 | Barre Mass Landfill Gas | IC | LFG | 1.6 | 1.6 | 2 | Worcester | MA | 2011-03-11 | 2011-02-11 | 2010-06-17 | 13.8 kV distribution circuit | NR | TRUE | TRUE | ISO-NE |  | WMA
237 | 2010-01-14 | G | 2007-12-05 | Combined Cycle | CC | NG | 285 | 285 | 300 | Newport | RI | 2014-12-01 | 2014-08-01 | 2010-01-14 | 115 kV Tiverton Substation | CNR | FALSE | FALSE |  | PD | RI |  | Document Posted
236 | 2012-11-13 | G | 2007-11-30 | Pioneer Valley Energy Center | CC | DFO NG | 353 | 353 | 421 | Hampden | MA | 2015-09-28 | 2015-04-29 | 2012-11-01 | 115 kV line between Buck Pond and Pochassic substa | CNR | TRUE | TRUE | ISO-NE | BL | WMA |  | Document Posted |  |  | Executed
235 | 2008-03-15 | G | 2007-11-15 | Gas Turbine | GT | NG |  | 58 | 65 | New Haven | CT | 2010-01-31 | 2010-01-01 | 2008-02-27 | CL&P 46 kV circuit from Baldwin Substation | MIS | FALSE | FALSE |  |  | SWCT
235 | 2008-06-30 | G | 2007-11-15 | Gas Turbine | GT | DFO NG |  | 170 | 196 | New London | CT | 2010-05-31 | 2010-05-01 | 2008-06-30 | CL&P Card Street substation | MIS | FALSE | FALSE |  |  | CT
234 | 2009-05-22 | G | 2007-11-07 | Moretown Landfill | IC | LFG | 4.8 | 4.8 | 4.8 | Washington | VT | 2008-09-04 | 2008-09-04 |  | Green Mountain Power 34 kV feeder | MIS | FALSE | FALSE |  |  | VT
233 | 2013-05-30 14:18 | G | 2007-11-02 | Rhode Island Landfill Gas Genco | CC | LFG | 27.9 | 32.6 | 36.8 | Providence | RI | 2013-05-25 | 2012-12-10 |  | NGRID 115 kV S171 line | CNR | TRUE | TRUE | NGRID |  | RI
232 | 2008-01-29 | G | 2007-11-01 | Gas Turbine | GT | DFO NG |  | 250 | 275 | Hartford | CT | 2010-06-01 | 2010-04-01 | 2008-01-29 | CL&P 329 345 kV line or 1895 115 kV line | MIS | FALSE | FALSE |  |  | CT
231 | 2011-12-14 | G | 2007-10-25 | Brayton Point 3 Uprate( see 243) | ST | BIT | 30 | 642 | 663 | Bristol | MA | 2011-12-12 | 2011-12-11 |  | Brayton Point 345 kV Switchyard | NR | TRUE | TRUE | ISO-NE |  | RI
230 | 2009-08-20 | G | 2007-10-15 | GMP Essex Diesel | IC | DFO |  | 8 | 8 | Colchester | VT | 2007-10-30 |  |  | GMP Essex Substation | MIS | FALSE | TRUE | N/A |  | VT
229 | 2008-09-08 | G | 2007-10-15 | Biomass Project | ST | WDS |  | 41 | 41 | Coos | NH | 2013-12-31 | 2013-12-31 | 2008-09-08 | PSNH 34.5 kV circuit from Lost Nation or Whitefiel | MIS | FALSE | FALSE |  |  | NH
229 | 2011-10-19 | G | 2007-10-15 | CPD Berlin | ST | WDS | 29.5 | 29.5 | 29.5 | Coos | NH | 2013-08-31 | 2013-07-31 | 2011-10-11 | PSNH 115 kV Berlin Substation | CNR | TRUE | TRUE | ISO-NE | PD | NH | Document Posted | Document Posted |  | Document Posted
228 | 2013-02-05 | G | 2007-10-09 | Dundee Wind | WT | WND | 27 | 27 | 30 | Penobscot | ME | 2011-07-26 | 2011-05-01 |  | BHE Keene Road Substation | NR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted
227 | 2010-09-23 | G | 2007-09-26 | Bear Swamp Uprate - First Unit | PS | WAT | 43 | 333 | 333 | Berkshire | MA | 2012-03-31 | 2012-03-17 | 2010-09-23 | Bear Swamp 230 kV Substation | NR | TRUE | TRUE | ISO-NE |  | WMA
227 | 2010-09-23 | G | 2007-09-26 | Pump Storage Capacity Upgrade | PS | WAT | 43 | 333 | 333 | Berkshire | MA | 2013-03-30 | 2013-03-16 | 2010-09-23 | Bear Swamp 230 kV Substation | NR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted
227 | 2008-03-14 | ETU | 2007-09-28 | Increase Transfer South From Wyman Hydro | NA | N/A |  |  |  | N/A | ME |  |  |  | N/A | MIS | FALSE | FALSE |  |  | ME
226 | 2009-07-23 | G | 2007-09-05 | Combined Cycle Capacity Increase/ Generator Change | CC | NG | 904 | 904 | 1010 | Rockingham | NH | 2013-06-30 | 2012-12-31 | 2009-07-14 | 345 kV Seabrook Substation | MIS | FALSE | FALSE |  |  | NH
225 | 2010-10-22 | G | 2007-08-13 | Combined Cycle Capacity Increase (See QP #202) | CC | NG | 161 | 411 | 412 | Windham | CT | 2013-05-31 | 2013-01-31 | 2010-10-22 | CL&P 345 kV Lake Road substation | CNR | FALSE | FALSE |  | PD | RI
225 | 2010-08-20 | G | 2007-09-04 | Wind Project-Phase 1( MPS Queue # 6) | WT | WND | 53.4 | 255 | 255 | N/A |  | 2010-09-01 |  |  | Maine Public Service System, upgrades include tap | NA | FALSE | FALSE | N/A
224 | 2010-02-17 | G | 2007-08-10 | VPPSA Swanton Gas Turbine #1 | GT | DFO NG | 21 | 21.2 | 27.6 | Franklin | VT | 2010-02-12 | 2009-12-16 |  | Swanson Village 46 kV System | NA | TRUE | TRUE | ISO-NE |  | VT
224 | 2010-05-24 | G | 2007-08-10 | VPPSA Swanton Gas Turbine #2 | GT | DFO NG | 21 | 21.2 | 27.6 | Franklin | VT | 2010-05-24 | 2010-05-01 |  | Swanton Village 46 kV System | NA | TRUE | TRUE | ISO-NE |  | VT
223 | 2015-11-19 13:44 | G | 2007-07-25 | Increase to biomass project in queue position 218 | ST | WDS | 0 | 20.5 | 24 | Berkshire | MA | 2010-12-01 | 2010-09-01 | 2009-01-30 | Doreen 115 kV substation or F132 115 kV line | MIS | FALSE | FALSE |  |  | WMA
223 | 2007-11-07 | G | 2007-07-25 | Gas Turbine | GT | NG |  | 159 | 185 | New Haven | CT | 2010-05-06 | 2010-03-24 | 2007-11-07 | East Shore-Grand Ave 115 kV line | MIS | FALSE | FALSE |  |  | SWCT
222 | 2012-05-30 | G | 2007-07-16 | Meriden Gas Turbines | CC | DFO NG | 510 | 510 | 560 | New Haven | CT | 2015-06-01 | 2014-12-01 | 2012-05-30 | Haddam Neck-Southington 345 kV line | CNR | TRUE | TRUE | ISO-NE | BL | CT | Document Posted
221 | 2011-02-04 | G | 2007-07-18 | Wind Project | WT | WND | 34.9 | 34.9 | 34.9 | Penobscot | ME | 2012-12-30 | 2012-10-30 | 2011-02-04 | 115 kV line between Enfield and James River substa | NR | TRUE | TRUE | ISO-NE |  | BHE |  | Document Posted
220 | 2009-05-22 | G | 2007-07-10 | Indeck Energy Alexandria | ST | WDS | 16.5 | 16.5 | 16.5 | Grafton | NH | 2009-01-31 | 2008-09-07 |  | 34.5 kV circuit from PSNH Peniwagewassett substat | MIS | TRUE | TRUE | NU |  | NH
219 | 2010-10-01 | G | 2007-07-06 | L'Energia | CC | DFO NG | 74 | 74 | 77 | Middlesex | MA | 2009-01-01 | 2008-11-15 |  | J162 115kV line between Tewksbury and Perry Street | MIS | TRUE | TRUE | ISO-NE |  | CMA
218 | 2009-02-12 | G | 2007-06-27 | Biomass Project ( Also see queue position #223) | ST | WDS | 62 | 41 | 48 | Berkshire | MA | 2010-12-01 | 2010-09-01 | 2009-01-30 | Doreen 115 kV substation or F132 115 kV line | MIS | FALSE | FALSE |  |  | WMA
217 | 2010-04-09 | G | 2007-06-13 | Northfield Mt. Equipment Replacement | PS | WAT | 0 | 1180 | 1180 | Franklin | MA | 2008-10-20 | 2008-10-20 |  | W. Mass Northfield 345 kV substation | NA | TRUE | TRUE | ISO-NE |  | WMA
216 | 2010-06-02 | G | 2007-06-08 | Combined Cycle | CC | DFO NG | 244 | 244 | 294 | Bristol | MA | 2013-12-31 | 2013-11-01 | 2010-05-28 | Cleary 115 kV substation | NR | TRUE | TRUE | ISO-NE | BL | SEMA |  | Document Posted
215 | 2008-10-15 | G | 2007-05-30 | Combined Cycle | CC | DFO NG | 578 | 578 | 558 | Norfolk | MA | 2013-06-01 | 2013-02-01 | 2008-10-27 | NGRID 345 kV 344 Line | MIS | FALSE | FALSE |  |  | SEMA
215 | 2011-12-19 | G | 2007-05-24 | Longfellow Wind | WT | WND | 50 | 50 | 50 | Oxford | ME | 2013-12-01 | 2013-10-01 | 2011-12-14 | CMP 115 kV Rumford Substation | CNR | TRUE | TRUE | ISO-NE | PD | ME
214 | 2007-10-15 | G | 2007-05-21 | Biomass Project | ST | WDS |  | 41 | 41 | Coos | NH | 2010-08-31 | 2010-06-30 | 2007-10-27 | PSNH 34.5 kV circuit from Lost Nation or Whitefiel | MIS | FALSE | FALSE |  |  | NH
214 | 2007-10-15 | G | 2007-05-21 | Biomass Project | ST | WDS |  | 41 | 41 | Coos | NH | 2010-08-31 | 2010-06-30 | 2007-10-15 | PSNH 115 kV S136 line | MIS | FALSE | FALSE |  |  | NH
213 | 2010-03-03 | G | 2007-05-15 | Gas Turbine | GT | NG | 159 | 158.5 | 184.7 | Worcester | MA | 2013-06-01 | 2013-02-01 | 2010-03-03 | ANP Blackstone 345 kV substation | CNR | FALSE | FALSE |  | PD | RI
213 | 2008-11-20 | G | 2007-05-15 | Gas Turbine | GT | NG | 159 | 158.5 | 184.7 | Worcester | MA | 2010-06-01 | 2010-02-01 | 2008-10-21 | ANP Milford 115 kV substation | MIS | FALSE | FALSE |  |  | RI
212 | 2020-06-09 08:18 | G | 2007-05-15 | Biomass Project | ST | WDS | 45 | 45 | 45 | Hillsborough | NH | 2010-02-28 | 2009-12-31 | 2009-05-28 | PSNH K-165 115 kV line | MIS | FALSE | FALSE |  |  | NH
211 | 2007-11-20 | G | 2007-05-08 | Combined Cycle | CC | DFO NG |  | 496 | 550 | Bristol | MA | 2010-06-01 | 2010-02-01 | 2007-11-20 | NSTAR 115 kV line #111 | MIS | FALSE | FALSE |  |  | SEMA
210 | 2009-05-22 | G | 2007-04-30 | MATEP (Medical Area Total Energy Project)-modify i | OT | DFO NG |  |  |  | Suffolk | MA | 2007-12-11 |  |  | NSTAR Coburn Substation | MIS | FALSE | TRUE | NSTAR |  | BOST
209 | 2009-05-22 | G | 2007-04-18 | Mount Tom Voltage Regulator Replacement | ST | BIT |  |  |  | Hampden | MA | 2007-06-30 |  |  | W Mass. Mt. Tom 115 kV Substation | MIS | FALSE | FALSE |  |  | WMA
208 | 2007-12-12 | G | 2007-04-13 | Gas Turbine | GT | NG |  | 100 | 100 | Norfolk | MA | 2011-06-01 | 2010-12-31 | 2008-08-21 | 345 kV NEA Bellingham substation | MIS | FALSE | FALSE |  |  | RI
207 | 2012-01-30 | G | 2007-04-03 | Towantic Energy | CC | DFO NG | 452 | 452 | 540 | New Haven | CT | 2014-12-31 | 2014-06-30 | 2012-01-27 | CL&P 115 kV lines between Baldwin Junction and Bea | CNR | TRUE | TRUE | ISO-NE |  | SWCT
206 | 2009-05-22 | G | 2007-04-03 | Kimberly Clark-Unit 1 |  | NG |  | 28 | 28 | Litchfield | CT | 2008-05-05 |  |  | CL&P Rocky River Substation | MIS | TRUE | TRUE | NU |  | SWCT
206 | 2009-05-22 | G | 2007-04-03 | Kimberly Clark-Unit 2 |  | NG |  | 10.8 | 10.8 | Litchfield | CT | 2008-10-01 |  |  | CL&P Rocky River Substation | MIS | TRUE | TRUE | NU |  | SWCT
206 | 2009-05-22 | G | 2007-04-03 | Kimberly Clark-Unit 3 |  | NG | 4 | 4 | 4 | Litchfield | CT | 2009-01-05 | 2008-11-15 |  | CL&P Rocky River Substation | MIS | TRUE | TRUE | NU |  | SWCT
205 | 2007-10-03 | G | 2007-04-02 | Gas Turbine | GT | NG |  | 8.1 | 9.1 | Penobscot | ME | 2007-06-01 | 2007-06-01 | 2007-10-03 | BHE's Line 5 - 46 kV | MIS | FALSE | FALSE |  |  | ME
204 | 2007-04-24 | G | 2007-03-30 | Gas Turbine | GT | DFO NG |  | 40 | 48 | Hartford | CT | 2009-12-31 | 2009-12-31 | 2007-04-27 | CL&P Windsor locks substation | MIS | FALSE | FALSE |  |  | CT
203 | 2009-07-01 | G | 2007-03-20 | Landfill Gas | IC | LFG | 6.3 | 6.3 | 6.3 | Coos | NH | 2008-12-31 | 2008-12-31 | 2009-07-01 | 34.5 kV feeder from Littleton | MIS | FALSE | FALSE |  |  | NH
202 | 2010-10-22 | G | 2007-02-27 | Combined Cycle | CC | NG | 250 | 250 | 285 | Windham | CT | 2013-05-31 | 2013-01-31 | 2010-10-22 | CL&P 345 kV Lake Road substation | CNR | FALSE | FALSE |  | PD | RI
201 | 2009-12-15 | G | 2007-02-26 | Converts QP 164 to combined cycle facility and inc | CC | NG | 0 | 162 | 162 | Providence | RI | 2014-02-26 | 2013-12-31 | 2009-12-14 | 345 kV RISE Substation | CNR | FALSE | FALSE |  |  | RI
200 | 2013-08-12 09:00 | G | 2007-02-21 | Wind Project | WT | WND | 34 | 34 | 34 | Coos | NH | 2014-11-01 | 2014-08-01 | 2013-08-07 | New Hampshire Electric Coop 34.5 kV line | NA | FALSE | FALSE |  |  | NH
199 | 2010-03-19 | G | 2007-02-21 | Waterbury Generating Facility | GT | NG | 95.7 | 95.7 | 98.1 | New Haven | CT | 2009-06-26 | 2009-05-01 |  | CL&P Baldwin 115 kV substations | CNR | TRUE | TRUE | ISO-NE |  | SWCT
198 | 2008-05-07 | G | 2007-02-08 | Biomass Project | ST | WDS |  | 56.4 | 67.5 | Coos | NH | 2009-06-01 | 2009-04-01 | 2008-05-07 | Near PSNH Lost Nation substation | MIS | FALSE | FALSE |  |  | NH
197 | 2012-01-31 | G | 2007-01-31 | Record Hill Wind | WT | WND | 50.6 | 50.6 | 50.6 | Oxford | ME | 2012-01-31 | 2011-11-28 |  | 115kV Rumford Substation | CNR | TRUE | TRUE | ISO-NE |  | ME |  | Document Posted
196 | 2011-06-29 | G | 2007-01-16 | Northfield Mt Upgrade #3 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2011-06-17 | 2011-06-01 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
196 | 2012-06-06 | G | 2007-01-16 | Northfield Mt. Upgrade #2 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2012-05-25 | 2012-06-01 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
196 | 2014-05-21 10:18 | G | 2007-01-16 | Northfield Mt. Upgrade #4 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2014-05-21 | 2014-05-21 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
196 | 2016-02-22 09:43 | G | 2007-01-16 | Northfield Mt Upgrade #1 | PS | WAT | 25 | 295 | 295 | Franklin | MA | 2016-02-18 | 2015-08-31 |  | W. Mass Northfield 345 kV substation | CNR | TRUE | TRUE | ISO-NE |  | WMA |  | Document Posted |  |  | Executed | In Service
196 | 2009-05-22 | G | 2007-01-26 | UMass Gas Turbine | GT | NG | 10.4 | 8.5 | 11.4 | Hampshire | MA | 2009-01-29 | 2008-05-06 |  | WMECO Podick substation 13.8 kV feeders | MIS | TRUE | TRUE | NU |  | WMA
195 | 2009-09-25 | G | 2007-01-09 | Dartmouth Power Expansion | GT | KER NG | 24 | 24 | 24 | Bristol | MA | 2009-09-24 | 2009-08-14 |  | NSTAR 115 kV line #111 | CNR | TRUE | TRUE | ISO-NE |  | SEMA |  | Document Posted
194 | 2007-05-01 | G | 2007-01-08 | Gas Turbine | GT | NG |  | 177.1 | 189.3 | New Haven | CT | 2010-03-31 | 2010-01-15 | 2007-05-01 | UI 115 kV line # 8200 | MIS | FALSE | FALSE |  |  | SWCT
193 | 2012-03-13 | G | 2007-01-05 | Ansonia Generation | CC | NG | 60 | 60 | 67 | New Haven | CT | 2013-09-09 | 2013-07-10 | 2012-03-13 | UI Ansonia 115 kV substation | CNR | TRUE | TRUE | ISO-NE |  | SWCT
192 | 2007-03-26 | G | 2006-12-28 | Combined Cycle | CC | DFO NG |  | 496 | 550 | Litchfield | CT | 2010-06-01 | 2010-04-01 | 2007-03-26 | CL&P Frostbridge Substation | MIS | FALSE | FALSE
192 | 2008-06-30 | G | 2006-12-28 | Combined Cycle | CC | DFO NG |  | 496 | 550 | Fairfield | CT | 2013-06-01 | 2013-04-01 | 2008-07-30 | CL&P Plumtree Substation | MIS | FALSE | FALSE |  |  | SWCT
192 | 2011-05-26 | G | 2007-01-03 | Salem Harbor Unit 3 Exciter Replacement | ST | BIT |  |  |  | Essex | MA | 2007-05-04 |  |  | Salem Switchyard | MIS | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted
191 | 2007-05-14 | G | 2006-12-22 | Gas Turbine | GT | NG |  | 100 | 100 | Fairfield | CT | 2010-05-31 | 2010-03-31 | 2007-05-14 | UI 115 kV line #8909 | MIS | FALSE | FALSE |  |  | SWCT
191 | 2010-09-14 | G | 2006-12-22 | Biomass Project | ST | WDS | 26 | 26.25 | 26.75 | Litchfield | CT | 2013-03-01 | 2012-12-14 | 2010-09-13 | CL&P 115 kV line #1238 | CNR | TRUE | TRUE | ISO-NE |  | SWCT
190 | 2009-05-15 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 156 | 156 | 200 | Hampden | MA | 2010-01-31 | 2009-10-30 | 2009-05-28 | W Mass. Mt. Tom 115 kV Substation | MIS | FALSE | FALSE |  |  | WMA
190 | 2009-05-12 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 39 | 39 | 50 | New London | CT | 2010-01-31 | 2009-10-30 | 2009-05-07 | CL&P Tunnel 115 kV Substation | MIS | TRUE | FALSE | ISO-NE |  | CT | Document Posted | Document Posted
190 | 2009-05-15 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 39 | 39 | 50 | Litchfield | CT | 2010-01-31 | 2009-10-30 | 2009-05-11 | CL&P Falls Village 69 kV Substation | MIS | TRUE | FALSE | ISO-NE |  | CT
190 | 2009-05-15 | G | 2006-12-22 | Gas Turbine | GT | DFO KER NG | 39 | 39 | 50 | New Haven | CT | 2010-01-31 | 2009-10-30 | 2009-05-07 | CL&P Stevenson 115 kV Substation | MIS | TRUE | FALSE | ISO-NE |  | SWCT |  | Document Posted
189 | 2009-11-25 | G | 2006-12-15 | Covanta Haverhill Landfill Gas | IC | LFG |  | 1.6 | 1.6 | Essex | MA | 2007-12-05 |  |  | NGRID 23 kV circuit # 2371 from Ward Hill substati | MIS | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted |  |  |  | In Service
188 | 2007-02-01 | G | 2006-12-07 | Gas Turbine Capacity Increase( #178) | CC | DFO NG |  | 69 | 0 | Plymouth | MA | 2010-06-01 | 2010-04-01 | 2007-02-01 | 115 kV F19 and/or E20 lines | MIS | FALSE | FALSE |  |  | SEMA
187 | 2009-02-11 | G | 2006-12-05 | Fuel Cell | FC | NG | 28.9 | 28.9 | 28.9 | Fairfield | CT | 2009-06-01 | 2009-06-01 | 2009-01-27 | UI Congress substation | MIS | FALSE | FALSE |  |  | SWCT
186 | 2009-06-01 | G | 2006-12-01 | Gas Turbine | GT | DFO KER | 78 | 78 | 93 | New Haven | CT | 2011-12-31 | 2011-10-30 | 2009-05-29 | CL&P Shepaug 115 kV substation | MIS | FALSE | FALSE | ISO-NE |  | SWCT |  | Document Posted
186 | 2009-06-01 | G | 2006-12-01 | Hydro | HD | WAT | 6.5 | 48 | 48 | New Haven | CT | 2011-12-31 | 2011-10-30 | 2009-05-29 | CL&P Shepaug 115 kV substation | MIS | FALSE | FALSE | ISO-NE |  | SWCT
185 | 2013-02-21 | G | 2006-11-22 | Stetson Wind Phase I | WT | WND | 60 | 58.7 | 58.7 | Penobscot | ME | 2009-01-22 | 2008-12-01 |  | BHE Keene Road 115 kV substation | NR | TRUE | TRUE | ISO-NE |  | BHE
185 | 2013-02-05 | G | 2006-11-22 | Rollins Wind (Stetson Wind Phase II) | WT | WND | 27.8 | 27.8 | 27.8 | Penobscot | ME | 2011-07-26 | 2011-05-01 |  | BHE Keene Road 115 kV substation | NR | TRUE | TRUE | ISO-NE |  | BHE
184 | 2007-05-23 | G | 2006-11-17 | Gas Turbine Capacity Increase( #157) | GT | DFO NG |  | 140 | 140 | Middlesex | MA | 2008-12-01 | 2008-09-01 | 2007-05-23 | 337 Sandy Pond - Tewksbury 345 kV Line | MIS | FALSE | FALSE | ISO-NE |  | CMA
183 | 2010-10-01 | G | 2006-11-17 | Increase Existing Capacity | ST | NUC | 70 | 1225 | 1245 | New London | CT | 2008-11-01 | 2008-11-01 |  | CL&P Millstone 345 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | CT
182 | 2009-05-15 | G | 2006-10-20 | Gas Turbine Capacity Increase ( See queue position | GT | DFO NG | 0 | 0 | 18.4 | Fairfield | CT | 2010-06-01 | 2010-02-01 | 2009-05-13 | 345 kV line # 321 | MIS | FALSE | FALSE | ISO-NE |  | SWCT
181 | 2017-04-21 06:49 | ETU | 2006-11-09 | Transmission Expansion | NA | N/A | 0 |  |  | N/A | CT |  |  | 2009-09-02 | Lake Road 345 kV Substation | N/A | TRUE | FALSE | ISO-NE |  | CT
180 | 2017-04-21 06:49 | ETU | 2006-11-08 | Transmission Expansion | NA | N/A |  |  |  | N/A | CT |  |  | 2007-05-31 | CL&P Killingly 115 kV Substation | N/A | FALSE | FALSE |  |  | CT
180 | 2007-02-16 | ETU | 2006-11-08 | Transmission Expansion | NA | N/A |  |  |  | N/A | CT |  |  |  | CL&P Card 345 kV Substation | N/A | FALSE | FALSE |  |  | CT
179 | 2009-05-22 | G | 2006-11-06 | Red Shield( Georgia Pacific/Old Town) | ST | WDS |  | 16 | 16 | Penobscot | ME | 2006-11-01 |  |  | BHE's Line 5 - 46 kV | MIS | FALSE | FALSE | ISO-NE |  | BHE
178 | 2017-05-25 09:42 | G | 2006-11-02 | Brockton Combined Cycle | CC | DFO NG | 332 | 332 | 371 | Plymouth | MA | 2019-05-31 | 2019-01-25 | 2017-05-25 | 115 kV F19 and E20 lines | NR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted |  | Document Posted
177 | 2008-12-31 | G | 2006-10-23 | Gas Turbine | GT | DFO NG | 190 | 190 | 190 | Worcester | MA | 2011-06-01 | 2011-03-01 | 2008-12-23 | 115 kV bus at Millbury substation | MIS | FALSE | FALSE | ISO-NE |  | CMA |  | Document Posted
176 | 2008-12-31 | G | 2006-10-20 | Wind | WT | WND | 145.5 | 145.5 | 145.5 | Coos | NH | 2008-12-30 | 2008-11-30 | 2008-12-29 | PSNH 115 kV Whitefield substation | MIS | FALSE | FALSE | ISO-NE |  | NH
175 | 2009-05-15 | G | 2006-10-20 | Gas Turbine | GT | DFO NG | 175 | 175 | 203.6 | Fairfield | CT | 2010-06-01 | 2010-02-01 | 2009-05-13 | 345 kV line # 321 | MIS | FALSE | FALSE | ISO-NE |  | SWCT
174 | 2012-08-09 | G | 2006-10-13 | Combined Cycle | CC | DFO NG | 280 | 280 | 280 | Hampden | MA | 2015-07-01 | 2015-05-01 | 2012-08-10 | 345 kV Stony Brook Substation | CNR | TRUE | TRUE | ISO-NE | BL | WMA
173 | 2009-02-11 | G | 2006-09-21 | Wind Project | WT | WND | 60 | 60 | 60 | Rutland | VT | 2010-10-30 | 2010-09-15 | 2009-01-21 | 115 kV West Rutland substation | MIS | FALSE | FALSE |  |  | VT
172 | 2011-10-19 | G | 2006-08-29 | Sheffield Wind Project | WT | WND | 40 | 40 | 40 | Caledonia | VT | 2011-10-19 | 2011-09-19 |  | Irasburg - St. Johnsbury 115 kV | CNR | TRUE | TRUE | ISO-NE |  | VT
171 | 2009-06-30 | G | 2006-08-29 | Thomas A. Watson Generating Station | GT | DFO NG | 108 | 108 | 115 | Norfolk | MA | 2009-06-23 | 2009-03-01 |  | 115 kV Potter Substation | CNR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted |  |  |  | In Service
170 | 2009-04-16 | G | 2006-08-25 | Gas Turbine Capacity Increase (see #155) |  | DFO NG | 0 | 40 | 55 | Middlesex | MA | 2011-05-01 | 2011-03-01 | 2009-04-09 | NSTAR Mystic Substation | MIS | FALSE | FALSE | ISO-NE |  | BOST
169 |  | ETU | 2006-08-15 | Transmission Expansion | NA | N/A |  |  |  | N/A | VT | 2009-06-30 |  |  | VELCO Coolidge Substation | N/A | FALSE | FALSE |  |  | VT
169 |  | G | 2006-08-15 | Biomass | ST | WDS |  | 25 | 27.5 | Windsor | VT | 2009-06-30 | 2009-04-30 | 2006-11-02 | New Ludlow 115 kV Substation | MIS | FALSE | FALSE |  |  | VT
168 | 2009-10-01 | G | 2006-08-11 | Wind Project-Phase 2( MPS Queue # 2&3) | WT | WND |  | 250 | 250 | N/A |  | 2012-09-30 |  | 2009-09-16 | Maine Public Service System, upgrades include tap | MIS | FALSE | FALSE | MPS
168 | 2009-10-01 | G | 2006-08-11 | Wind Project-Phase 3( MPS Queue # 4) | WT | WND |  | 250 | 250 | N/A |  | 2011-09-30 |  | 2009-09-16 | Maine Public Service System, upgrades include tap |  | FALSE | FALSE | MPS
167 | 2009-02-11 | G | 2006-08-10 | Fuel Cell | FC | NG | 16 | 16 | 16 | New Haven | CT | 2009-12-31 | 2009-12-31 |  | CL&P Cherry Street 13 kV substation | MIS | FALSE | FALSE |  |  | SWCT
166 | 2015-06-15 15:07 | G | 2006-08-09 | Granite Reliable Power | WT | WND | 94.5 | 94.5 | 94.5 | Coos | NH | 2012-02-15 | 2011-10-24 |  | PSNH W-179 115 kV line | CNR | TRUE | TRUE | ISO-NE |  | NH | Document Posted | Document Posted
165 | 2009-04-17 | G | 2006-08-03 | Combined Cycle( See # 226) | CC | NG | 563 | 563 | 616 | Rockingham | NH | 2013-06-30 | 2012-12-31 | 2009-04-10 | 345 kV Seabrook Substation | MIS | FALSE | FALSE | ISO-NE |  | NH
164 | 2009-12-15 | G | 2006-08-01 | Combined Cycle( see # 201) | GT | NG | 320 | 158 | 196 | Providence | RI | 2012-06-01 | 2011-12-31 | 2009-12-14 | 345 kV RISE Substation | CNR | FALSE | FALSE |  | BL | RI
163 | 2009-07-16 | G | 2006-07-24 | Mirant Kendall Jet 2 | GT | JF | 18 | 18 | 22 | Middlesex | MA | 2010-01-31 | 2010-01-15 | 2009-07-14 | Kendall Station in Cambridge | MIS | TRUE | TRUE | NSTAR |  | BOST | Document Posted | Document Posted
162 | 2009-05-22 | G | 2006-07-18 | Vernon Repowering | HD | WAT |  | 32 | 32 | Windham | VT | 2008-03-13 |  |  |  | MIS | TRUE | TRUE | ISO-NE |  | VT
161 | 2010-07-16 | G | 2006-07-05 | Devon Units 15, 16, 17, 18 | GT | KER NG | 196.8 | 196.8 | 196.8 | New Haven | CT | 2010-06-09 | 2010-04-01 |  | Devon Substation | CNR | TRUE | TRUE | ISO-NE |  | SWCT
161 | 2011-06-27 | G | 2006-07-05 | Middletown 12, 13, 14 and 15 | GT | JF KER NG | 215 | 215 | 211 | Middlesex | CT | 2011-06-24 | 2011-04-05 |  | CL&P Middletown Substation or CL&P Scovill Rock Su | CNR | TRUE | TRUE | ISO-NE |  | CT
161 | 2011-02-15 | G | 2006-07-05 | Middletown 11 | GT | JF KER NG | 107.5 | 107.5 | 110 | Middlesex | CT | 2011-06-01 | 2011-04-01 | 2011-02-10 | CL&P Middletown Substation | CNR | TRUE | TRUE | ISO-NE |  | CT
161 | 2009-04-15 | G | 2006-07-05 | Combined Cycle | CC | NG | 223 | 630 | 690 | New London | CT | 2013-05-31 | 2013-02-01 | 2009-04-07 | Montville Substation | MIS | FALSE | FALSE | ISO-NE |  | CT
161 | 2007-03-28 | G | 2006-07-17 | Combustion Turbine |  | NG |  |  |  |  | CT | 2008-04-30 |  |  | CL&P Rocky River Substation | MIS | FALSE | FALSE |  |  | SWCT
160 | 2008-11-26 | G | 2006-06-30 | Gas Turbine | GT | DFO NG | 82.2 | 82.2 | 94.8 | Middlesex | CT | 2011-05-31 | 2011-04-30 | 2008-11-26 | CL&P Middletown Substation | MIS | TRUE | FALSE | ISO-NE |  | CT
159 | 2008-11-12 | G | 2006-06-30 | Gas Turbine | GT | NG | 325 | 325 | 375 | Fairfield | CT | 2010-09-30 | 2010-06-30 | 2008-10-22 | UI 345 kV Singer Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
159 |  | G | 2006-06-30 | Fuel Cell | FC | NG |  | 30 | 30 | Fairfield | CT | 2008-12-31 | 2008-03-31 | 2006-10-25 | NU Triangle Substation 11A | MIS | FALSE | FALSE |  |  | SWCT
159 |  | G | 2006-06-30 | Fuel Cell | FC | NG |  | 30 | 30 | Fairfield | CT | 2008-12-31 | 2008-03-31 | 2006-10-25 | UI Congress Street Substation 2C | MIS | FALSE | FALSE |  |  | SWCT
158 | 2009-05-22 | G | 2006-06-21 | UTC - P&WA |  | NG |  | 7.5 | 7.5 | Middlesex | CT | 2007-12-21 |  |  | CL&P P&WA Substation | MIS | TRUE | TRUE | NU |  | CT
157 | 2009-12-29 | G | 2006-06-21 | Billerica Power | GT | NG WO | 311 | 311 | 341 | Middlesex | MA | 2011-06-15 | 2011-05-15 | 2009-12-29 | J-162 line to Tewksbury Substation | CNR | TRUE | TRUE | ISO-NE |  | CMA |  | Document Posted
156 | 2011-05-26 | G | 2006-06-13 | Salem Harbor Unit 1 Exciter Replacement | ST | BIT |  |  |  | Essex | MA | 2006-11-26 |  |  | Salem Switchyard | MIS | TRUE | TRUE | ISO-NE |  | BOST |  | Document Posted
156 |  | G | 2006-06-13 | Brayton Point Unit 3 Voltage Regulator Replacement | ST | BIT |  |  |  | Bristol | MA | 2006-05-26 |  |  | Brayton Switchyard | MIS | FALSE | FALSE |  |  | RI
155 | 2009-04-16 | G | 2006-06-02 | Gas Turbine |  | DFO NG | 160 | 120 | 130 | Middlesex | MA | 2011-05-01 | 2011-03-01 |  | NSTAR Mystic Substation | MIS | FALSE | FALSE | ISO-NE |  | BOST
155 | 2009-05-22 | G | 2006-06-02 | Fairfield University |  | NG |  | 5 | 5 | Fairfield | CT | 2007-12-11 |  |  | UI Ash Creek Substation | MIS | FALSE | FALSE |  |  | SWCT
155 | 2009-02-11 | G | 2006-06-16 | Fuel Cell | FC | NG | 14.4 | 14.4 | 14.4 | Fairfield | CT | 2009-06-01 | 2009-06-01 |  | UI Pequonnock Substation | MIS | FALSE | FALSE |  |  | SWCT
154 |  | G | 2006-05-31 | Gas Turbine (Additional Capacity) | GT | DFO |  | 29 | 0 | Suffolk | MA | 2008-08-01 | 2008-06-01 |  | NSTAR Chelsea Substation | MIS | FALSE | FALSE |  |  | BOST
153 | 2007-10-08 | G | 2006-05-30 | Fuel Cell | FC | NG |  | 8 | 8 | Fairfield | CT | 2007-05-31 | 2007-05-31 |  | CL&P Cedar Heights Substation | MIS | FALSE | FALSE |  |  | SWCT
152 |  | G | 2006-05-30 | MATEP (Medical Area Total Energy Project) | OT | DFO NG |  | 42 | 42 | Suffolk | MA |  |  |  | NSTAR Brighton Substation | MIS | FALSE | TRUE | NSTAR |  | BOST
151 |  | G | 2006-05-30 | Fitchburg Renewable Energy | IC | LFG |  | 7.2 | 7.2 | Worcester | MA | 2007-08-29 |  |  | NGRID E. Westminster Substation 13.8 kV | MIS | TRUE | TRUE | NGRID |  | CMA
150 | 2013-12-12 09:30 | G | 2006-05-25 | Plainfield Renewable Energy Project | ST | WDS | 37.5 | 37.5 | 38.5 | Windham | CT | 2013-12-12 | 2013-11-07 |  | CLP Fry Brook Substation | CNR | TRUE | TRUE | ISO-NE |  | CT |  | Document Posted |  |  | Executed | In Service
149 | 2017-04-21 06:48 | ETU | 2006-03-10 | Transmission Expansion | NA | N/A |  |  |  | N/A | CT | 2006-11-01 |  | 2007-12-04 | N/A | N/A | FALSE | FALSE | ISO-NE |  | CT
148 | 2013-04-16 14:35 | G | 2006-03-06 | Comerford Unit #1 | HD | WAT | -17 | 24.3 | 24.5 | Grafton | NH | 2009-11-30 | 2009-11-30 |  | NGRID Comerford Substation | CNR | TRUE | TRUE | ISO-NE |  | NH
148 | 2011-03-21 | G | 2006-03-06 | Comerford Unit #3 | HD | WAT | 8.3 | 48.2 | 38.5 | Grafton | NH | 2011-03-25 | 2011-02-15 |  | NGRID Comerford Substation | CNR | TRUE | TRUE | ISO-NE |  | NH
148 | 2012-03-28 | G | 2006-03-06 | Comerford Unit #2 | HD | WAT | 8.4 | 48.3 | 48.5 | Grafton | NH | 2012-03-12 | 2012-02-27 |  | NGRID Comerford Substation | CNR | TRUE | TRUE | ISO-NE |  | NH
148 | 2013-03-26 12:23 | G | 2006-03-06 | Comerford Unit #4 | HD | WAT | 8.3 | 48.2 | 48.5 | Grafton | NH | 2013-03-22 | 2012-12-25 |  | NGRID Comerford Substation |  | TRUE | TRUE | ISO-NE |  | NH |  | Document Posted |  |  | Executed | In Service
147 | 2007-08-31 | G | 2006-02-28 | Gas Turbine | GT | DFO |  | 168.2 | 168.2 | Suffolk | MA | 2010-06-01 | 2010-04-01 | 2007-11-02 | NSTAR Chelsea Substation | MIS | FALSE | FALSE | ISO-NE |  | BOST
146 |  | G | 2006-02-21 | Devon 10 | GT | JF KER |  | 17 | 20 | New Haven | CT | 2006-06-29 |  |  | CL&P Devon Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
145 | 2007-08-31 | G | 2006-02-13 | Wind Project | WT | WND |  | 51 | 51 | Windham | CT | 2009-12-31 | 2009-12-01 | 2008-06-20 | CL&P 115 kV 1607 line | MIS | FALSE | FALSE | ISO-NE |  | CT
144 |  | G | 2006-02-06 | Biomass | ST | WDS |  | 25 | 27.5 | Windsor | VT | 2009-04-30 | 2009-02-28 |  | VELCO Coolidge Substation | MIS | FALSE | FALSE |  |  | VT
143 |  | G | 2006-01-16 | Land Fill Gas | IC | LFG |  | 25 | 25 | Providence | RI | 2007-06-30 | 2007-06-01 | 2006-04-25 | Johnston Substation Distribution System | MIS | FALSE | FALSE |  |  | RI
142 |  | G | 2005-12-21 | Wind Project | WT | WND |  | 48 | 48 | Windham | VT | 2008-05-31 | 2008-03-31 | 2006-04-13 | CVPS Londonderry Substation 46 kV | MIS | FALSE | FALSE |  |  | VT
141 | 2007-02-07 | G | 2005-12-14 | Gas Turbine | GT | DFO NG |  | 200 | 200 | Middlesex | MA | 2009-09-30 | 2009-08-31 | 2007-02-07 | 115 kV O 167 line between Everett and Mystic Subst | MIS | FALSE | FALSE | ISO-NE |  | BOST |  | Document Posted
140 | 2007-09-30 | G | 2005-12-13 | A. L. Pierce | GT | DFO NG |  | 89.35 | 99.56 | New Haven | CT | 2007-10-01 |  |  | Wallingford Electrical Division, East Street Subst | MIS | TRUE | TRUE | ISO-NE |  | SWCT
139 | 2009-05-15 | G | 2005-10-14 | Lowell Power Generators | GT | NG | 99 | 99 | 99 | Middlesex | MA | 2010-06-01 | 2010-04-01 | 2009-04-29 | J162 115kV line between Tewksbury and Perry Street | MIS | TRUE | TRUE | ISO-NE |  | CMA |  | Document Posted
138 | 2009-11-02 | G | 2005-09-26 | Kibby Wind Project | WT | WND | 65 | 65 | 65 | Franklin | ME | 2009-10-30 | 2009-09-30 |  | Bigelow Substation | CNR | TRUE | TRUE | ISO-NE |  | ME
138 | 2010-10-26 | G | 2005-09-26 | Kibby Wind Project | WT | WND | 65.5 | 65.5 | 65.5 | Franklin | ME | 2010-10-26 | 2010-09-15 |  | Bigelow Substation | CNR | TRUE | TRUE | ISO-NE |  | ME
137 | 2011-07-07 | G | 2005-09-23 | Rumford Hydro Configuration Modification | HD | WAT | 0 |  |  | Oxford | ME | 2011-06-21 | 2011-05-20 |  | CMP 115 kV Line 218 | NA | TRUE | TRUE | ISO-NE |  | ME |  |  |  | Document Posted
136 | 2007-04-03 | G | 2005-08-19 | Biomass | ST | WDS |  | 39 | 40 | Somerset | ME | 2008-12-31 | 2008-09-30 | 2007-04-03 | Gorbell Tap of CMP's Detroit-Wyman Hydro 66 - 115 | MIS | FALSE | FALSE | ISO-NE |  | ME
135 | 2012-04-24 | G | 2005-08-19 | Russell Biomass | ST | WDS | 55 | 55 | 55 | Hampden | MA | 2015-08-01 | 2015-03-01 | 2012-03-15 | Blanford - Southwick - Elm 115 kV line | CNR | TRUE | TRUE | ISO-NE |  | WMA | Document Posted
134 | 2008-02-18 | G | 2005-08-03 | Wind Project | WT | WND |  | 45 | 45 | Bennington | VT | 2010-12-30 | 2010-09-29 | 2008-08-19 | Y-25 North, 69 kV line between Searsburg and Benni | MIS | FALSE | FALSE | ISO-NE |  | VT
133 |  | G | 2005-08-01 | Combined Cycle | CC | DFO |  | 115 | 124 | Orleans | VT | 2010-01-31 | 2009-12-31 |  | Newport 115 kV Substation | MIS | FALSE | FALSE |  |  | VT
132 | 2008-06-30 | G | 2005-07-21 | Wind Project | WT | WND |  | 9 | 9 | Bennington | VT | 2007-12-31 | 2007-06-01 | 2008-06-30 | Bennington - Brattleboro 46 kV | MIS | FALSE | FALSE |  |  | VT
131 | 2008-02-18 | G | 2005-06-21 | Wind Project | WT | WND |  | 90 | 90 | Franklin | ME | 2010-12-31 | 2010-06-01 | 2008-09-25 | Bigelow Substation | MIS | TRUE | TRUE | ISO-NE |  | ME
130 |  | G | 2005-05-24 | Wind Project | WT | WND |  | 53 | 53 | Caledonia | VT | 2007-09-01 | 2007-08-01 | 2006-09-22 | Irasburg - St. Johnsbury 115 kV | MIS | FALSE | FALSE |  |  | VT
129 |  | G | 2005-02-28 | Georgia Pacific | ST | WDS |  | 16 | 16 | Penobscot | ME | 2005-04-04 |  |  | BHE's Line 5 - 46kV | MIS | TRUE | TRUE | ISO-NE |  | BHE
128 |  | G | 2005-02-11 | Biomass | ST | WDS |  | 39 | 42 | Litchfield | CT | 2007-07-31 | 2007-05-31 |  | TBD | MIS | FALSE | FALSE
127 | 2009-05-22 | G | 2004-11-15 | Lempster | WT | WND | 24 | 24 | 24 | Sullivan | NH | 2008-11-10 | 2008-09-04 |  | PSNH 34.5 kV circuit from Newport Substation | MIS | TRUE | TRUE | NU |  | NH
126 |  | G | 2004-11-09 | Biomass | ST | WDS |  | 40 |  | Cheshire | NH | 2007-07-01 |  |  | N-186, 115kV line between Vernon Road Tap and bor | MIS | FALSE | FALSE |  |  | NH
125 | 2008-02-18 | G | 2004-11-02 | Cos Cob Redevelopment | GT | KER |  | 36 | 45.8 | Fairfield | CT | 2008-05-31 |  |  | Cos Cob 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | NOR
125 | 2010-02-16 | G | 2004-11-02 | Norwalk Harbor Station Redevelopment | GT | KER | 322.5 | 322.5 | 330 | Fairfield | CT | 2013-02-28 | 2012-12-31 | 2010-02-16 | Norwalk 345 kV Station | CNR | TRUE | FALSE | ISO-NE | BL | NOR
125 |  | G | 2004-11-02 | Devon Station Redevelopment | [5 empty] | New Haven | CT | 2010-07-15 |  |  | Devon 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
124 |  | G | 2004-10-27 | Hardscrabble Mountain Project | [5 empty] | Caledonia | VT | 2006-03-31 |  |  | St. Johnsbury- Irasburg 115 kV Line | MIS | FALSE | FALSE |  |  | VT
123 |  | G | 2004-10-04 | GenPower Athens | [5 empty] | Somerset | ME | 2006-06-01 |  |  | Gorbell Tap of CMP's Detroit-Wyman Hydro 66 - 115 | MIS | FALSE | FALSE |  |  | ME
122 |  | G | 2004-07-20 | Rand-Whitney Co-Gen |  | DFO NG |  | 11.866 | 14.858 | New London | CT | 2005-01-03 |  |  | CL&P Distribution System/Montville 115 kV | MIS | TRUE | TRUE | ISO-NE |  | CT
121 |  | G | 2004-06-22 | Third Taxing District Units 1, 2 & 3 |  | DFO |  | 6 | 6 | Fairfield | CT | 2005-03-28 |  |  | CL&P 27.6 kV Distribution System/Norwalk 115kV | MIS | FALSE | TRUE | N/A |  | NOR
120 |  | G | 2004-05-10 | Univ. of NH - CHP | [5 empty] | Strafford | NH |  |  |  | PSNH Dist. Sys./Madbury 115 kV | MIS | FALSE | FALSE |  |  | NH
119 | 2007-10-19 | G | 2004-01-16 | Ridgebury Power | [5 empty] | Fairfield | CT | 2004-06-01 |  | 2007-10-19 | CL&P Distribution System | MIS | FALSE | FALSE |  |  | SWCT
118 |  | G | 2003-12-29 | Bridgeport Harbor Units 5 & 6 | [5 empty] | Fairfield | CT | 2005-05-01 |  |  | Paquonnock 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
118 |  | G | 2003-12-29 | New Haven Harbor Units 2 & 3 | [5 empty] | New Haven | CT | 2005-05-01 |  |  | East Shore 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
117 |  | G | 2003-12-08 | Waterside Power - 23 MW | [5 empty] | Fairfield | CT | 2004-06-01 |  |  | Waterside 115 kV - Norwalk/Stamford | MIS | FALSE | FALSE |  |  | NOR
116 | 2012-06-11 | G | 2003-11-10 | East Haven Wind Farm | WT | WND | 6 |  |  | Essex | VT | 2012-10-30 |  |  | Village of Lyndonville Elec. Dept. Distribution Sy | NA | FALSE | FALSE |  |  | VT
115 | 2008-12-31 | G | 2003-10-27 | SNEW Summer '04 Temporary Generator | GT | DFO | 0 | 23.8 |  | Fairfield | CT | 2004-06-01 |  | 2008-12-31 | Norwalk 27.6 kV | MIS | FALSE | FALSE |  |  | NOR
114 |  | G | 2003-10-02 | Waterside Power, LLC | GT | DFO |  | 69.3 | 74.1 | Fairfield | CT | 2004-06-01 |  |  | Waterside 115 kV | MIS | TRUE | TRUE | ISO-NE |  | NOR
113 |  | G | 2003-09-29 | Sheffield Wind Power Project | [5 empty] | Caledonia | VT | 2005-12-31 |  |  | TBD | MIS | FALSE | FALSE |  |  | VT
112 |  | G | 2003-09-15 | NECCO Cogen | IC | DFO |  |  |  | Suffolk | MA | 2003-10-01 |  |  | Everett 23 kV | MIS | TRUE | FALSE | NGRID |  | BOST
111 |  | G | 2003-07-21 | GLHA James River/Fraser Paper7 |  | WAT |  | 25 | 25 | Coos | NH | 2004-06-22 |  |  | Berlin 115 kV | MIS | TRUE | TRUE | ISO-NE |  | NH
110 |  | G | 2003-07-07 | UCONN COGEN Facility |  | NG |  | 24.9 | 24.9 | Tolland | CT | 2005-10-19 |  |  | Mansfield 69 kV | MIS | TRUE | TRUE | ISO-NE |  | CT
109 | 2008-12-31 | G | 2003-06-12 | AWT Fitchburg Wind Project | WT | WND | 12 |  |  | Worcester | MA | 2004-10-01 |  | 2008-12-31 | Ashburnham No. 610 - 13.8 kV | MIS | FALSE | FALSE |  |  | WMA
108 | 2012-12-27 | G | 2003-05-12 | Hoosac Wind Project | WT | WND | 28.5 | 28.5 | 28.5 | Berkshire & Franklin | MA | 2012-12-27 | 2012-12-05 |  | Line Y25S | NR | TRUE | TRUE | NGRID |  | WMA
107 |  | G | 2003-04-07 | SNEW Summer '03 Temporary Generator | GT | NG |  | 19.445 |  | Fairfield | CT | 2003-06-01 |  |  | Norwalk 27.6 kV | MIS | TRUE | TRUE | ISO-NE |  | NOR
106 | 2009-10-02 | G | 2003-03-18 | Ridgewood RI Generation Phase I | IC | LFG |  | 4.2 | 4.2 | Providence | RI | 2004-02-18 |  |  | Johnston Substation Distribution System | MIS | TRUE | TRUE | NGRID |  | RI
106 | 2009-10-02 | G | 2003-03-18 | Ridgewood RI Generation Phase II | IC | LFG |  | 4.2 | 4.2 | Providence | RI | 2005-11-20 |  |  | Johnston Substation Distribution System | MIS | TRUE | TRUE | NGRID |  | RI
105 |  | G | 2003-03-10 | Evergreen Wind Power - Bagley Mountain | [5 empty] | Penobscot | ME | 2004-07-01 |  |  | Chester 115 kV | MIS | FALSE | FALSE |  |  | BHE
105 |  | G | 2003-03-10 | Evergreen Wind Power - Blueberry Barrens | [5 empty] | Washington | ME | 2004-10-01 |  |  | Deblois 115 kV | MIS | FALSE | FALSE |  |  | BHE
104 | 2010-07-16 | G | 2003-03-06 | Waterside Power - 180 MW | GT | DFO NG | 203.9 | 203.9 | 207.2 | Fairfield | CT | 2011-12-31 | 2011-09-30 | 2010-07-12 | Waterside 115 kV | CNR | TRUE | TRUE | ISO-NE | PD | NOR |  |  |  | Document Posted
103 |  | G | 2003-03-04 | Waterside Power | GT |  |  |  |  | Fairfield | CT | 2003-06-01 |  |  | Waterside 115 kV | MIS | TRUE | TRUE | ISO-NE |  | NOR
102 | 2008-10-14 | G | 2003-02-04 | Peabody Power | GT | DFO NG |  | 97.2 | 97.2 | Essex | MA | 2008-05-01 | 2008-02-01 | 2008-10-14 | C155 & B154 - 115 kV Lines | MIS | TRUE | TRUE | NGRID |  | BOST
101 |  | G | 2003-01-15 | Seabrook Power Uprate7 | ST | NUC |  | 1265 | 1265 | Rockingham | NH | 2006-10-31 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | NH
100 |  | G | 2002-12-12 | VT Yankee Nuclear Power Station Upgrade7 | ST | NUC |  | 634.5 | 641.5 | Windham | VT | 2006-05-08 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | VT
99 |  | G | 2002-08-08 | Millstone 2 Upgrade7 | ST | NUC |  | 897.5 | 905.7 | New London | CT | 2004-03-10 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | CT
99 |  | G | 2002-08-08 | Millstone 3 Upgrade7 | ST | NUC |  | 1195 | 1207.4 | New London | CT | 2006-05-08 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | ISO-NE |  | CT
98 |  | G | 2002-06-03 | Redington Wind Farm Phase II | [5 empty] | Franklin | ME | 2005-12-01 |  |  | Bigelow 115 kV Substation | MIS | FALSE | FALSE |  |  | ME
97 |  | ETU | 2001-12-26 | Western Maine Area Export Enhancement | [5 empty] | N/A |  |  |  |  | Increase Export Capability from Rumford Power Asso | MIS | FALSE | FALSE |  |  | ME
96 |  | G | 2001-12-12 | Great Northern - Millinocket | HW | WAT |  | 126 | 126 | Penobscot | ME | 2003-05-20 |  |  | 115 kV connection to Chester 115 kV Substation | MIS | TRUE | TRUE | BHE |  | BHE
95 | 2011-07-12 | G | 2001-11-21 | Kleen Energy Project | CC | DFO NG | 619.8 | 619.8 | 620 | Middlesex | CT | 2011-07-12 | 2011-05-03 |  | Sectionalize 353 Line | CNR | TRUE | TRUE | ISO-NE |  | CT
94 |  | G | 2001-07-17 | CPV New Britain LLC | [5 empty] | Hartford | CT | 2005-07-01 |  |  | Interconnection South New Britain CT 115 kV Corrid | MIS | FALSE | FALSE |  |  | CT
93 |  | ETU | 2001-07-06 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
93 |  | ETU | 2001-07-06 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
93 |  | ETU | 2001-07-06 | HVDC Interconn. betw. Norwalk Stat, CT & Shore Rd | [5 empty] | N/A | CT | 2004-05-01 |  |  | Interconnection between Norwalk Stat, CT & Shore R | MIS | FALSE | FALSE |  |  | NOR
93 |  | ETU | 2001-07-06 | HVDC Interconn. betw. Norwalk Stat, CT & Shore Rd | [5 empty] | N/A | CT | 2004-05-01 |  |  | Interconnection between Norwalk Stat, CT & Shore R | MIS | FALSE | FALSE |  |  | NOR
92 |  | ETU | 2001-06-26 | Sithe Mystic 4,5,6 Reconfiguration of Interconnect | [5 empty] | Middlesex | MA | 2003-03-31 |  |  | Reconfigure Mystic 4,5,6 Interconnection from Myst | MIS | FALSE | FALSE |  |  | BOST
91 |  | ETU | 2001-06-12 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-06-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
91 |  | ETU | 2001-06-12 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2003-06-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
90 |  | G | 2001-06-08 | Cabot Station CUO Uprate | HD | WAT |  |  |  | Franklin | MA | 2004-05-01 |  |  | Increase generating capacity from 53.0 MW to 61.8 | MIS | TRUE | TRUE | NU |  | WMA
89 | 2017-01-13 08:33 | G | 2001-06-06 | Cape Wind Turbine Generators | WT | WND | 454 | 454 | 454 | N/A | MA | 2018-12-31 | 2018-10-01 | 2017-01-12 | Near Barnstable 115 kV Substation | NR | TRUE | TRUE | ISO-NE |  | SEMA | Document Posted | Document Posted | Document Posted |  | Executed
88 | 2017-04-21 06:48 | ETU | 2001-06-01 | Increase Orrington South Transfer Limit | NA | N/A |  |  |  | N/A |  | 2007-12-01 |  | 2008-01-02 | N/A | MIS | TRUE | TRUE | BHE |  | ME
87 |  | ETU | 2001-05-24 | Stage II Cross Sound Cable HVDC Interconnection | [5 empty] | New Haven | CT | 2003-07-01 |  |  | HVDC terminal adjacent to East Shore 345kV Substat | MIS | FALSE | FALSE |  |  | CT
86 |  | ETU | 2001-05-21 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2002-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
85 |  | G | 2001-04-04 | Pilgrim Power Uprate | ST | NUC |  |  |  | Plymouth | MA | 2003-08-01 |  |  | Increase Existing Unit Capacity | MIS | TRUE | TRUE | NSTAR |  | SEMA
84 |  | G | 2001-03-13 | Phase 1 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2007-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
84 |  | G | 2001-03-13 | Phase 2 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2008-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
84 |  | G | 2001-03-13 | Phase 3 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2009-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
84 |  | G | 2001-03-13 | Phase 4 - Nantucket Shouls Wind | [5 empty] | Barnstable | MA | 2010-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
84 |  | G | 2001-03-13 | Phase I - Nantucket Sound Wind Project | [5 empty] | Barnstable | MA | 2004-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
84 |  | G | 2001-03-13 | Phase 2 - Nantucket Sound Wind | [5 empty] | Barnstable | MA | 2005-12-31 |  |  | Near Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
83 |  | ETU | 2001-03-12 | Neptune Phase3 Boston Import from NB or NS | [5 empty] | Suffolk | MA | 2004-03-31 |  |  | Kingston St. 115/345 kV and K St. 115 kV Substatio | MIS | FALSE | FALSE |  |  | BOST
83 |  | ETU | 2001-03-12 | Neptune Phase4 CT Import from NB or NS | [5 empty] | Fairfield & New Haven | CT | 2004-03-31 |  |  | Glenbrook 115 kV and E. Shore St. 115/345 kV (sep. | MIS | FALSE | FALSE |  |  | NOR
83 |  | ETU | 2001-03-12 | Neptune Phase5 ME Yankee Export to Boston, CT or N | [5 empty] | Lincoln | ME | 2004-03-31 |  |  | Maine Yankee 345 kV (Bi-Polar HVDC Terminal) | MIS | FALSE | FALSE |  |  | ME
83 |  | ETU | 2001-03-12 | Neptune Phase7 Wyman Export to Boston, CT, NYC or | [5 empty] | Cumberland | ME | 2004-03-31 |  |  | Wyman 345 kV (Bi-Polar HVDC Terminal) | MIS | FALSE | FALSE |  |  | SEMA
82 |  | G | 2001-02-14 | Cape Cod Offshore Wind Project | [5 empty] | Barnstable | MA | 2004-12-31 |  |  | South of Barnstable 115kV Substation | MIS | FALSE | FALSE |  |  | SEMA
81 |  | G | 2001-01-02 | Berwick Energy Center | [5 empty] | York | ME | 2002-01-01 |  |  | Dover 115 kV Substation | MIS | FALSE | FALSE |  |  | NH
80 |  | G | 2000-12-27 | Berlin Energy Project | [5 empty] | Coos | NH | 2002-01-01 |  |  | Berlin 115 kV Substation (PSNH) | MIS | FALSE | FALSE |  |  | NH
79 |  | ETU | 2000-12-18 | Milford CT - New York HVDC | [5 empty] | New Haven | CT | 2003-06-30 |  |  | HVDC Devon CT 115 kV | MIS | FALSE | FALSE |  |  | SWCT
78 |  | ETU | 2000-12-13 | Norwalk-Northport HVDC | [5 empty] | Fairfield | CT | 2003-06-30 |  |  | HVDC Norwalk CT and Northport NY | MIS | FALSE | FALSE |  |  | NOR
77 | 2011-05-31 | G | 2000-10-02 | Berkshire Wind Power Project | WT | WND | 15 | 15 | 15 | Berkshire | MA | 2011-05-28 | 2011-05-06 |  | WMECO at Brodie Mt. In Lanesboro MA | NA | TRUE | TRUE | NU |  | WMA
76 |  | ETU | 2000-08-31 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2001-01-01 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
75 |  | ETU | 2000-08-16 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2001-01-01 |  |  | Increase Export Capability to New York | MIS | TRUE | TRUE | ISO-NE
74 | 2011-02-22 | G | 2000-07-24 | South Norwalk Repowering | IC | DFO NG | 48.9 | 48.9 | 48.9 | Fairfield | CT | 2011-06-01 | 2011-04-15 | 2011-02-22 | Norwalk 115 kV Substation | NA | TRUE | TRUE | ISO-NE |  | NOR
73 |  | G | 2000-07-07 | Norwalk Harbor A | [5 empty] | Fairfield | CT | 2003-12-31 |  |  | Norwalk 115 kV Station | MIS | FALSE | FALSE |  |  | NOR
73 |  | G | 2000-07-07 | Norwalk Harbor B | [5 empty] | Fairfield | CT | 2004-06-30 |  |  | Norwalk 115 kV Station | MIS | FALSE | FALSE |  |  | NOR
73 |  | G | 2000-07-07 | Devon A | [5 empty] | New Haven | CT | 2003-12-31 |  |  | Devon 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
73 |  | G | 2000-07-07 | Middletown A | [5 empty] | Middlesex | CT | 2003-12-31 |  |  | Middletown Station | MIS | FALSE | FALSE |  |  | CT
73 |  | G | 2000-07-07 | Middletown B | [5 empty] | Middlesex | CT | 2005-12-31 |  |  | Middletown Station | MIS | FALSE | FALSE |  |  | CT
73 |  | G | 2000-07-07 | Montville A | [5 empty] | New London | CT | 2004-09-30 |  |  | Montville Station | MIS | FALSE | FALSE |  |  | CT
73 |  | G | 2000-07-07 | Somerset Diversity | [5 empty] | Bristol | MA | 2004-03-31 |  |  | Somerset 115 kV Station | MIS | FALSE | FALSE |  |  | SEMA
73 |  | G | 2000-07-07 | Somerset A | [5 empty] | Bristol | MA | 2003-12-31 |  |  | Somerset 115 kV Station | MIS | FALSE | FALSE |  |  | SEMA
72 |  | G | 2000-06-28 | Tewksbury Power | [5 empty] | Middlesex | MA | 2004-06-30 |  |  | Tewksbury 345 kV Station | MIS | FALSE | FALSE |  |  | CMA
71 |  | G | 2000-05-22 | New Haven Harbor | [5 empty] | New Haven | CT | 2003-06-01 |  |  | East Shore Substation | MIS | FALSE | FALSE |  |  | CT
71 |  | G | 2000-05-22 | Bridgeport Harbor Station | [5 empty] | Fairfield | CT | 2003-06-01 |  |  | Pequonnock 115 kV Substation | MIS | FALSE | FALSE |  |  | SWCT
70 |  | ETU | 2000-04-25 | New York Interface LTF PtP Out Service | [5 empty] | N/A |  | 2003-07-31 |  |  | Increase Export Capability to New York | MIS | FALSE | FALSE
69 |  | ETU | 2000-04-20 | Neptune HVDC Cable Project | [5 empty] | N/A |  | 2004-03-31 |  |  | HVDC from Maine/ Maritimes to Boston Area and CT S | MIS | FALSE | FALSE
68 |  | ETU | 2000-03-09 | Bridgeport Long Island HVDC | [5 empty] | Fairfield | CT | 2003-05-01 |  |  | HVDC to Long Island, NY from Bridgeport, CT | MIS | FALSE | FALSE |  |  | SWCT
67 |  | G | 2000-02-25 | Lowell Power Expansion | [5 empty] | Middlesex | MA | 2001-05-01 |  |  | Lowell Power 115 kV Station | MIS | TRUE | TRUE | NGRID |  | CMA
66 |  | G | 1999-12-20 | AEC Expansion | [5 empty] | Franklin | ME | 2001-06-30 |  |  | Riley Road 115 kV Substation | MIS | FALSE | FALSE |  |  | ME
65 |  | ETU | 1999-12-02 | EPMI LTF Pt to Pt In Svce. | [5 empty] | N/A |  | 2002-01-01 |  |  |  |  | FALSE | FALSE
64 |  | G | 1999-11-08 | West Springfield Station | ST | NG RFO |  |  |  | Hampden | MA | 2002-06-07 |  |  | West Springfield 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | WMA
64 |  | G | 1999-11-08 | Seabrook Unit One Uprate | [5 empty] | Rockingham | NH | 2002-05-01 |  |  | Increase Existing Unit Capacity | MIS | FALSE | FALSE |  |  | NH
63 |  | ETU | 1999-11-04 | WESC LTF Pt to Pt In Svce | [5 empty] | N/A |  | 2000-02-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
62 |  | ETU | 1999-10-05 | New York Interface Import Expansion | [5 empty] | N/A |  | 2000-01-01 |  |  | Increase Import Capability from NY | MIS | FALSE | FALSE
61 |  | ETU | 1999-09-15 | New York Interface Import Expansion | [5 empty] | N/A |  | 1999-12-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
60 |  | ETU | 1999-09-01 | Sithe LTF Pt to Pt In Svce. | [5 empty] | N/A |  | 2000-03-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
59 |  | G | 1999-08-18 | Milford Power Uprate | [5 empty] | New Haven | CT | 2001-06-30 |  |  | Increase Existing Unit Capacity | MIS | FALSE | FALSE |  |  | SWCT
59 |  | G | 1999-08-18 | Berkshire Power Uprate | [5 empty] | Hampden | MA | 2001-06-30 |  |  | Increase Existing Unit Capacity | MIS | FALSE | FALSE |  |  | WMA
58 |  | ETU | 1999-08-05 | CPS LTF Pt to Pt In Svc. | [5 empty] | N/A |  | 1999-11-01 |  |  | Increase Import Capability from NY |  | FALSE | FALSE
57 |  | G | 1999-06-04 | Norwich Power Station | [5 empty] | New London | CT | 2002-01-01 |  |  | Bean Hill Substation | MIS | FALSE | FALSE |  |  | CT
56 |  | ETU | 1999-02-25 | New York Interface Import Expansion | [5 empty] | N/A |  | 1999-05-01 |  |  | Increase Import Capability from New York |  | FALSE | FALSE
55 |  | ETU | 1999-01-21 | Cross Sound Cable | NA | N/A |  |  |  | New Haven | CT | 2003-09-01 |  |  | HVDC terminal adjacent to East Shore 345kV Substat | MIS | TRUE | TRUE | TEUS |  | CT
54 |  | G | 1999-01-05 | Redington Mountain Wind Farm | [5 empty] | Franklin | ME | 2002-12-31 |  |  | Bigelow 115 kV Substation | MIS | FALSE | FALSE |  |  | ME
53 |  | ETU | 1998-11-30 | Tractebel LTF Int + Internal PtP | [5 empty] | N/A |  | 2002-05-01 |  |  | Import from the New Brunswick System | ES | FALSE | FALSE
52 |  | G | 1998-11-13 | Haddam Station | [5 empty] | Middlesex | CT | 2002-12-31 |  |  | Site of the Former CT Yankee Plant | MIS | FALSE | FALSE |  |  | CT
52 |  | G | 1998-11-13 | Haddam Station Phase II | [5 empty] | Middlesex | CT | 2002-12-31 |  |  | Site of the Former CT Yankee Plant |  | FALSE | FALSE |  |  | CT
51 |  | ETU | 1998-10-30 | MEPCO-New England Interface Expansion | [5 empty] | N/A |  | 2000-01-01 |  |  | Import Capability from MEPCO | MIS | FALSE | FALSE |  |  | ME
50 |  | G | 1998-10-29 | Patriot Cabot Street Station | [5 empty] | Hampden | MA | 2001-12-31 |  |  | Holyoke Substation |  | FALSE | FALSE |  |  | WMA
49 |  | ETU | 1998-09-14 | Irving Oil LTF PtP | [5 empty] | N/A |  | 2001-04-01 |  |  | Import from NB Via MEPCO | ES | FALSE | FALSE
48 |  | G | 1998-09-09 | Bennington Energy Park | [5 empty] | Bennington | VT | 2001-11-30 |  |  | TBD |  | FALSE | FALSE |  |  | VT
48 |  | G | 1998-09-09 | Rutland Energy Park | [5 empty] | Rutland | VT | 2001-11-30 |  |  | TBD |  | FALSE | FALSE |  |  | VT
47 |  | G | 1998-08-26 | Nickel Hill Energy Project | [5 empty] | Middlesex | MA | 2001-06-30 |  |  | Tewksbury 230 kV Substation | MIS | FALSE | FALSE |  |  | BOST
46 |  | G | 1998-08-18 | Campello Power Co. | [5 empty] | Plymouth | MA | 2002-06-30 |  |  |  | MIS | FALSE | FALSE |  |  | SEMA
45 |  | G | 1998-07-17 | Kendall Repowering Project | CC | NG |  |  |  | Suffolk | MA | 2002-12-18 |  |  | Kendall Station in Cambridge | MIS | TRUE | TRUE | NSTAR |  | BOST
44 |  | G | 1998-07-10 | Brockton Power Project | [5 empty] | Plymouth | MA | 2001-01-31 |  |  | Industrial Blvd. | MIS | TRUE | TRUE | NGRID |  | SEMA
43 |  | ETU | 1998-06-08 | Tractebel LTF PtP | [5 empty] | N/A |  | 2002-12-31 |  |  | Import from the New Brunswick System |  | FALSE | FALSE
42 |  | G | 1998-06-05 | Wiscassett | [5 empty] | Lincoln | ME | 2001-10-01 |  |  | Maine Yankee 345 KV | MIS | FALSE | FALSE |  |  | ME
41 |  | G | 1998-06-04 | Canal 2 Repowering | [5 empty] | Barnstable | MA | 2001-06-30 |  |  | Canal 345 kV Station | MIS | FALSE | FALSE |  |  | SEMA
40 |  | G | 1998-06-01 | Glen Charlie Unit One | [5 empty] | Plymouth | MA | 2001-03-31 |  |  | Wareham 115 kV Substation |  | FALSE | FALSE |  |  | SEMA
39 |  | ETU | 1998-05-28 | CVPS/GMP LTF PtP | [5 empty] | Clinton | NY | 2001-12-31 |  |  | Import from NY via PV20 | MIS | FALSE | FALSE |  |  | VT
39 |  | ETU | 1998-05-28 | HQ Highgate2 HVDC | [5 empty] | Franklin | VT | 2001-12-31 |  |  | Located on the Hydro Quebec sys. N. near Highgate, | MIS | FALSE | FALSE |  |  | VT
38 |  | G | 1998-05-08 | Rocky River Power | [5 empty] | Litchfield | CT | 2001-07-31 |  |  | Long Mountain 345 kV Station | MIS | FALSE | FALSE |  |  | CT
37 |  | G | 1998-04-29 | FPLE RISE, LLC (R.I. Hope Energy) | CC | NG |  |  |  | Providence | RI | 2002-11-05 |  |  | S 171 and S 172 Lines | MIS | TRUE | TRUE | NGRID |  | RI
36 |  | G | 1998-04-14 | FPL Energy (Bedford) | [5 empty] | Bristol | MA | 2000-11-30 |  |  | Industrial Park 115 kV Substation | MIS | FALSE | FALSE |  |  | SEMA
35 |  | G | 1998-04-02 | Mason | [5 empty] | Lincoln | ME | 2000-12-31 |  |  | Mason 345 kV Substation | MIS | FALSE | FALSE |  |  | ME
35 |  | G | 1998-04-02 | Wyman A | [5 empty] | Cumberland | ME | 2000-01-02 |  |  | Wyman 115 kV Station | MIS | FALSE | FALSE |  |  | SME
35 |  | G | 1998-04-02 | Wyman B | [5 empty] | Cumberland | ME | 2000-01-03 |  |  | Wyman 115 kV Station |  | FALSE | FALSE |  |  | SME
34 |  | G | 1998-04-01 | WEG-Norwich | [5 empty] | New London | CT | 2005-06-30 |  |  | Montville 115 kV Substation |  | FALSE | FALSE |  |  | CT
33 |  | G | 1998-03-31 | Sithe Framingham Station Expansion | [5 empty] | Middlesex | MA | 2001-12-31 |  |  | Framingham 230 kV |  | FALSE | FALSE |  |  | BOST
33 |  | G | 1998-03-31 | Sithe Medway | [5 empty] | Norfolk | MA | 2001-12-31 |  |  | Existing Medway Station 345 kV | MIS | TRUE | TRUE | NSTAR |  | RI
33 |  | G | 1998-03-31 | Westbrook Power | CC | NG |  |  |  | Cumberland | ME | 2001-04-13 |  |  | Spring St. 115 kV Substation | MIS | TRUE | TRUE | CMP |  | SME
33 |  | G | 1998-03-31 | Sithe Edgar Station Expansion (Fore River) | CC | NG |  |  |  | Norfolk | MA | 2003-08-04 |  |  | Holbrook 345 kV | MIS | TRUE | TRUE | NSTAR |  | SEMA
33 | 2009-10-02 | G | 1998-03-31 | Sithe Mystic Station Expansion Unit 8 | CC | NG |  |  |  | Suffolk | MA | 2003-04-13 |  |  | Mystic 345 kV | ES | TRUE | TRUE | NSTAR |  | BOST
33 | 2009-10-02 | G | 1998-03-31 | Sithe Mystic Station Expansion Unit 9 | CC | NG |  |  |  | Suffolk | MA | 2003-06-11 |  |  | Mystic 345 kV | ES | TRUE | TRUE | NSTAR |  | BOST
32 |  | G | 1998-03-30 | Towantic Energy | [5 empty] | New Haven | CT | 2002-12-31 |  |  | Beacon Falls 115 kV | MIS | TRUE | TRUE | ISO-NE |  | CT
31 |  | G | 1998-03-26 | North Smithfield | [5 empty] | Providence | RI | 2002-06-30 |  |  | W. Farnum 345 kV | MIS | TRUE | FALSE | NGRID |  | RI
30 |  | G | 1998-03-25 | Norwich Power Station | [5 empty] | New London | CT | 2000-12-31 |  |  | Bean Hill Substation |  | TRUE | FALSE | NU |  | CT
30 |  | ETU | 1998-03-25 | Engage Energy LTF PtP | [5 empty] | N/A |  | 2000-12-31 |  |  | Import from New Brunswick via MEPCO | ES | TRUE | FALSE | CMP
29 |  | G | 1998-03-24 | Bucksport Energy, L.P. | CC | DFO NG |  |  |  | Hancock | ME | 2001-01-01 |  |  | Belfast 115 kV bus | MIS | TRUE | TRUE | CMP |  | BHE
28 |  | G | 1998-03-18 | Newington Energy Center | [5 empty] | Rockingham | NH | 2001-03-31 |  |  | Newington 345 kV Station |  | FALSE | FALSE |  |  | NH
27 |  | G | 1998-03-13 | AES Carpenter | [5 empty] | Hartford | CT | 2001-12-31 |  |  | Southington 345 kV Substation | MIS | FALSE | FALSE |  |  | CT
26 |  | G | 1998-03-06 | S&P Cogeneration | [5 empty] | Essex | MA | 2001-12-31 |  |  | Lynn 115 kV |  | TRUE | FALSE |  |  | BOST
25 |  | G | 1998-02-27 | Patriot Power | [5 empty] | Bristol | MA | 2001-03-31 |  |  | Bridgewater 345 kV Line |  | FALSE | FALSE |  |  | SEMA
24 |  | G | 1998-02-25 | Orrington Generation | [5 empty] | Penobscot | ME | 2001-06-30 |  |  | Orrington 345 kV Station |  | FALSE | FALSE |  |  | ME
23 |  | ETU | 1998-02-19 | HQ-Surowiec | [5 empty] | Cumberland | ME | 2002-12-31 |  |  | Surowiec 345 kV or MEPCO | MIS | TRUE | FALSE | CMP |  | ME
22 |  | G | 1998-02-16 | Meriden Power | [5 empty] | New Haven | CT | 2003-06-30 |  |  | Sectionalize 362 Line | MIS | TRUE | TRUE | ISO-NE |  | CT
21 | 2009-10-02 | G | 1998-02-11 | Wallingford Power Units 1&3 | GT | NG |  |  |  | New Haven | CT | 2001-12-31 |  |  | Wallingford 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
21 | 2009-10-02 | G | 1998-02-11 | Wallingford Power Unit 4 | GT | NG |  |  |  | New Haven | CT | 2002-01-23 |  |  | Wallingford 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
21 | 2009-10-02 | G | 1998-02-11 | Wallingford Power Units 2&5 | GT | NG |  |  |  | New Haven | CT | 2002-02-07 |  |  | Wallingford 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
21 |  | G | 1998-02-11 | AES Londonderry (Granite Ridge) | CC | DFO NG |  |  |  | Rockingham | NH | 2003-04-01 |  |  | N. Litchfield 230 kV Station and Watts Brook 115 k | MIS | TRUE | TRUE | ISO-NE |  | NH
20 |  | G | 1998-01-20 | Housatonic Power | [5 empty] | Fairfield | CT | 2001-01-01 |  |  | 398 Line |  | FALSE | FALSE |  |  | CT
19 |  | G | 1998-01-14 | Livermore Falls | [5 empty] | Androscoggin | ME | 2000-12-01 |  |  | Livermore Falls 115 kV Substation |  | FALSE | FALSE |  |  | ME
18 |  | G | 1998-01-13 | Versaille Energy Center | [5 empty] | New London | CT | 2000-12-31 |  |  | Tunnel 115 kV Substation |  | FALSE | FALSE |  |  | CT
18 |  | G | 1998-01-13 | White Mountain Cogen.Center | [5 empty] | Coos | NH | 2000-12-31 |  |  | Lost Nation 115 kV Substation |  | FALSE | FALSE |  |  | NH
18 |  | G | 1998-01-13 | Sprague Newington (Piscataqua Power) | [5 empty] | Rockingham | NH | 2000-01-01 |  |  | Newington 345 kV Station | MIS | FALSE | FALSE |  |  | NH
17 |  | G | 1997-12-12 | SEI Newington (ConEd) | CC | JF NG |  |  |  | Rockingham | NH | 2002-09-18 |  |  | Newington 345 kV Station | MIS | TRUE | TRUE | NU |  | NH
17 | 2009-10-02 | G | 1997-12-12 | Lake Road Generating Units 1&2 | CC | DFO NG |  |  |  | Windham | CT | 2002-03-15 |  |  | Line 347 | MIS | TRUE | TRUE | ISO-NE |  | RI
17 | 2009-10-02 | G | 1997-12-12 | Lake Road Generating Unit 3 | CC | DFO NG |  |  |  | Windham | CT | 2002-05-22 |  |  | Line 347 | MIS | TRUE | TRUE | ISO-NE |  | RI
16 |  | G | 1997-10-24 | ANP Gorham | [5 empty] | Cumberland | ME | 2000-07-01 |  |  | S. Gorham 345 kV Substation | MIS | TRUE | TRUE | CMP |  | ME
15 |  | G | 1997-10-09 | South Norwalk | [5 empty] | Fairfield | CT | 2000-01-01 |  |  | Norwalk 115 kV Substation |  | TRUE | FALSE | ISO-NE |  | NOR
14 |  | G | 1997-09-30 | Cabot Power | [5 empty] | Middlesex | MA | 2000-06-30 |  |  | Mystic 345 kV Station | ES | TRUE | TRUE | NSTAR |  | BOST
13 |  | G | 1997-08-22 | Summit Power | [5 empty] | Hampden | MA | 2001-03-31 |  |  | 1302 Line |  | FALSE | FALSE |  |  | WMA
13 | 2009-10-02 | G | 1997-08-22 | Milford Power Unit 1 | CC | DFO NG |  |  |  | New Haven | CT | 2004-02-12 |  |  | Devon 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
13 | 2009-10-02 | G | 1997-08-22 | Milford Power Unit 2 | CC | DFO NG |  |  |  | New Haven | CT | 2004-05-03 |  |  | Devon 115 kV Substation | MIS | TRUE | TRUE | ISO-NE |  | SWCT
12 |  | G | 1997-08-15 | Berkshire Power | CC | NG |  |  |  | Hampden | MA | 2000-06-19 |  |  | South Agawam Jct. 115 kV Station | ES | TRUE | TRUE | NU |  | WMA
11 |  | G | 1997-08-05 | Wareham | [5 empty] | Plymouth | MA | 2001-02-28 |  |  | Adjacent to the Tremont Substation |  | FALSE | FALSE |  |  | SEMA
10 |  | G | 1997-07-24 | Maine Independence | CC | NG |  |  |  | Penobscot | ME | 2000-05-01 |  |  | Located at Graham Station in Veazie, ME |  | TRUE | TRUE | CMP |  | BHE
9 |  | G | 1997-07-22 | IDC Bellingham | [5 empty] | Norfolk | MA | 2002-12-31 |  |  | Sectionalize 336 Line | MIS | TRUE | TRUE | NSTAR |  | RI
8 | 2009-10-02 | G | 1997-07-15 | ANP Bellingham Energy Project Unit 1 | CC | NG |  |  |  | Norfolk | MA | 2002-10-24 |  |  | Sectionalize Line 303 | MIS | TRUE | TRUE | NGRID |  | RI
8 | 2009-10-02 | G | 1997-07-15 | ANP Bellingham Energy Project Unit 2 | CC | NG |  |  |  | Norfolk | MA | 2002-12-28 |  |  | Sectionalize Line 303 | MIS | TRUE | TRUE | NGRID |  | RI
8 | 2009-10-02 | G | 1997-07-15 | ANP Blackstone Energy Project Unit 1 | CC | NG |  |  |  | Worcester | MA | 2001-06-07 |  |  | Sectionalize 336 Line | MIS | TRUE | TRUE | NGRID |  | RI
8 | 2009-10-02 | G | 1997-07-15 | ANP Blackstone Energy Project Unit 2 | CC | NG |  |  |  | Worcester | MA | 2001-07-13 |  |  | Sectionalize 336 Line | MIS | TRUE | TRUE | NGRID |  | RI
7 |  | G | 1997-06-25 | Bridgeport Harbor Station | CC | NG |  |  |  | Fairfield | CT | 1999-07-24 |  |  | Pequonnock 115 kV Substation |  | TRUE | TRUE | UI |  | SWCT
6 |  | G | 1997-06-12 | Rumford Power Associates | CC | NG |  |  |  | Oxford | ME | 2000-10-16 |  |  | Rumford 115 kV Substation |  | TRUE | TRUE | CMP |  | ME
5 |  | G | 1997-05-09 | Brayton Pt | [5 empty] | Bristol | MA | 2001-12-31 |  |  | Brayton Point 345 kV Station | MIS | TRUE | TRUE | NGRID |  | RI
4 |  | G | 1997-04-10 | EMI Dighton Power Project | CC | NG |  |  |  | Bristol | MA | 1999-08-01 |  |  | U6 Line | ES | TRUE | TRUE | NGRID |  | SEMA
3 |  | G | 1997-02-13 | Androscoggin Energy Center | CC | DFO NG |  |  |  | Franklin | ME | 2000-12-28 |  |  | Jay 115 kV Substation | ES | TRUE | TRUE | CMP |  | ME
2 |  | G | 1996-11-08 | EMI-Tiverton | CC | NG |  |  |  | Newport | RI | 2000-08-18 |  |  | Near Tiverton 115 kV Substation | ES | TRUE | TRUE | NGRID |  | SEMA
1 |  | G | 35223 | Millennium+K117 | CC | DFO NG |  |  |  | Worcester | MA | 36987 |  |  | W 123 Line | ES | TRUE | TRUE | NGRID |  | WMA