## SPP GI_ActiveRequest
Last Updated On | 2025-01-22
Generation Interconnection Number | IFS Queue Number | Current Cluster | Cluster Group | Nearest Town or County | State | TO at POI | In-Service Date | Commercial Operation Date | Cessation Date | Replacement Generator Commercial Op Date | Capacity | MAX Summer MW | MAX Winter MW | Service Type | Generation Type | Fuel Type | Substation or Line | Request Received | Date Withdrawn | Status | Cause of Delay
GEN-2024-SR9 |  | Surplus | 05 SOUTHWEST | Beaver County | OK | OG&E |  | 2027-01-01 |  |  | 150 | 150 | 150 | ER | Battery/Storage |  | Beaver County Substation 345 kV | 2024-01-26 |  | IA PENDING
GEN-2024-SR8 |  | Surplus | 02 NEBRASKA | Greely County | NE | NPPD |  | 2026-12-31 |  |  | 70 | 70 | 70 | ER | Battery/Storage |  | Spalding to North Loup 115kV | 2024-04-03 |  | FACILITY STUDY STAGE
GEN-2024-SR7 |  | Surplus | 05 SOUTHWEST | Beaver County | OK | OG&E |  | 2027-06-01 |  |  | 200 | 200 | 200 | ER | Solar |  | Beaver County Substation 345 kV | 2024-01-26 |  | IA PENDING
GEN-2024-SR6 |  | Surplus | 04 SOUTHEAST | Johnston County | OK | OG&E |  |  |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Interconnecting at Hugo - Sunnyside 345 kV transmission line | 2024-02-20 |  | IA PENDING | EGF: GEN-2017-075 rc Ownership Transfer from Sunchase to Leeward Energy. Contact Gary Braun. 11/13/24 RC
GEN-2024-SR5 |  | Surplus | 04 SOUTHEAST | Drumright | OK | OG&E |  | 2025-06-01 |  |  | 176.9 | 176.9 | 176.9 | ER | Battery/Storage |  | 138 kV Greenwood Station | 2024-02-07 |  | IA PENDING
GEN-2024-SR3 |  | Surplus | 04 SOUTHEAST | Lincoln County | OK | OG&E |  | 2026-05-01 |  |  | 72.5 | 72.5 | 72.5 | ER/NR | Battery/Storage |  | 138 kV TRYON 3 (Bus # 515675 | 2024-02-01 |  | IA PENDING
GEN-2024-SR2 |  | Surplus | 04 SOUTHEAST | Franklin County | AR | OG&E |  | 2026-06-01 |  |  | 72.5 | 72.5 | 72.5 | ER/NR | Battery/Storage |  | 161 kV BRANCH 5 (Bus # 515316) | 2024-02-06 |  | IA PENDING
GEN-2024-SR16 |  | Surplus | 04 SOUTHEAST | Oologah | OK | AEP |  | 2026-12-31 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Northeastern 138kV | 2024-12-03 |  | None
GEN-2024-SR15 |  | Surplus | 05 SOUTHWEST | Yoakum | TX | SPS |  | 2026-05-01 |  |  | 300 | 300 | 300 | ER | Battery/Storage |  | Mahoney 230kV Substation | 2024-10-24 |  | None
GEN-2024-SR14 |  | Surplus | 05 SOUTHWEST | Lea County | NM | Xcel/SPS |  | 2026-04-01 |  |  | 36 | 36 | 36 | ER | Battery/Storage |  | Cunningham 115kV | 2024-07-08 |  | None
GEN-2024-SR13 |  | Surplus | 04 SOUTHEAST | Bryan County | OK | OG&E |  | 2026-06-01 |  |  | 52.2 | 52.2 | 52.2 | ER/NR | Battery/Storage |  | Brown 138kV Substation | 2024-05-01 |  | IA PENDING
GEN-2024-SR12 |  | Surplus | 01 NORTH | La Moure County | ND | WAPA |  | 2026-10-01 |  |  | 20 | 20 | 20 | ER | Battery/Storage |  | Edgeley 115 kV Substation | 2024-05-21 |  | IA PENDING
GEN-2024-SR11 |  | Surplus | 04 SOUTHEAST | Garfield | OK | OGE |  | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Woodring 345kV Substation | 2024-05-07 |  | IA PENDING
GEN-2024-SR10 |  | Surplus | 02 NEBRASKA | Lancaster | NE | NPPD |  | 2026-12-31 |  |  | 80 | 80 | 80 | ER/NR | Battery/Storage |  | Monolith 115kV | 2024-04-22 |  | FACILITY STUDY STAGE
GEN-2024-SR1 |  | Surplus | 04 SOUTHEAST | Chouteau | OK | GRDA |  | 2025-12-31 |  |  | 84 | 84 | 84 | ER | Solar |  | 345 kV bus of GRDA GREC 1 & 2 Substation | 2023-11-29 |  | IA PENDING
GEN-2024-GR6 |  | Replacement | 04 SOUTHEAST | Newkirk | OK | OG&E |  | 2027-05-01 | 2026-12-01 |  | 300 | 300 | 300 | ER | Wind |  | Open Sky 345kV Substation | 2024-07-25 |  | None
GEN-2024-GR5 |  | Replacement | 04 SOUTHEAST | Chouteau | OK | GRDA |  | 2027-06-01 | 2026-10-01 |  | 582 | 542 | 582 | ER | Hybrid |  | GREC #2 Interconnect Substation â€“ 345kV | 2024-08-02 |  | None
GEN-2024-GR4 |  | Replacement | 03 CENTRAL | Riverton | KS | EDE |  | 2026-06-30 | 2026-03-15 |  | 31 | 31 | 31 | ER | Thermal |  | Riverton 452 | 2024-07-25 |  | None
GEN-2024-GR3 |  | Replacement | 05 SOUTHWEST | Lea County | NM | Xcel/SPS |  | 2027-04-01 | 2027-04-01 |  | 196 | 196 | 196 | ER | Solar |  | 230kV Cunningham Substation | 2024-06-07 |  | None
GEN-2024-GR1 |  | Replacement | 04 SOUTHEAST | Harrah | OK | OG&E |  | 2026-12-31 | 2026-12-31 |  | 492 | 492 | 492 | ER | Thermal | CTG | Horseshoe Lake 138kV | 2024-01-08 |  | FACILITY STUDY STAGE
GEN-2024-084 |  | DISIS-2024-001 | 03 CENTRAL | Lawrence | MO | AEP | 2028-09-25 | 2028-11-25 |  |  | 167 | 167 | 167 | ER/NR | Battery/Storage |  | Reeds Spring - Aurora 161 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-083 |  | DISIS-2024-001 | 04 SOUTHEAST | Choctaw | OK | WFEC | 2029-09-30 | 2029-12-31 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Hugo 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-082 |  | DISIS-2024-001 | 01 NORTH | Williams | ND | BEPC | 2029-05-01 | 2030-03-01 |  |  | 745 | 745 | 745 | ER | Thermal | Gas | Springbrook - Tande 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-081 |  | DISIS-2024-001 | 01 NORTH | Williams | ND | BEPC | 2028-04-01 | 2029-02-01 |  |  | 745 | 745 | 745 | ER | Thermal | Gas | Springbrook - Tande 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-080 |  | DISIS-2024-001 | 05 SOUTHWEST | Clovis | NM | SPS | 2029-10-01 | 2029-12-01 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | San Juan 230 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-079 |  | DISIS-2024-001 | 05 SOUTHWEST | Clovis | NM | SPS | 2029-10-01 | 2029-12-01 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | San Juan 230 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-078 |  | DISIS-2024-001 | 05 SOUTHWEST | Stinnett | TX | SPS | 2029-10-01 | 2029-12-01 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Pringle 230 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-077 |  | DISIS-2024-001 | 05 SOUTHWEST | Stinnett | TX | SPS | 2029-10-01 | 2029-12-01 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Pringle 230 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-076 |  | DISIS-2024-001 | 03 CENTRAL | Burbon | KS | Evergy | 2029-10-01 | 2029-12-01 |  |  | 130 | 130 | 130 | ER/NR | Solar |  | Neosho - LaCygne 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-075 |  | DISIS-2024-001 | 04 SOUTHEAST | Sharon | OK | OGE | 2029-10-01 | 2029-12-01 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Woodward 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-074 |  | DISIS-2024-001 | 03 CENTRAL | Jackson | MO | Evergy | 2028-11-01 | 2028-12-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Duncan Road 161 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-073 |  | DISIS-2024-001 | 05 SOUTHWEST | Lea | NM | SPS | 2028-09-01 | 2028-12-01 |  |  | 500 | 500 | 500 | ER/NR | Hybrid | Solar/Storage | Crossroads - Hobbs 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-072 |  | DISIS-2024-001 | 03 CENTRAL | Mitchell | KS | SUNC | 2029-02-01 | 2029-04-01 |  |  | 160 | 160 | 160 | ER/NR | Solar |  | Beloit 115 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-071 |  | DISIS-2024-001 | 05 SOUTHWEST | Cass | TX | AEP | 2027-05-15 | 2027-07-01 |  |  | 28 | 28 | 28 | ER/NR | Solar |  | West Atlanta - Atlanta 69 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-070 |  | DISIS-2024-001 | 04 SOUTHEAST | Okfuskee | OK | WFEC | 2028-10-02 | 2028-12-29 |  |  | 184.5 | 184.5 | 184.5 | ER/NR | Wind |  | Pharoah 138 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-069 |  | DISIS-2024-001 | 03 CENTRAL | Crawford | KS | Evergy | 2028-09-30 | 2028-12-31 |  |  | 228 | 228 | 228 | ER/NR | Hybrid | Solar/Storage | Franklin 69 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-068 |  | DISIS-2024-001 | 05 SOUTHWEST | Morris | TX | AEP | 2028-10-02 | 2028-12-29 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Lydia - Welsh 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-067 |  | DISIS-2024-001 | 03 CENTRAL | Cloud | KS | SUNC | 2029-05-01 | 2029-07-01 |  |  | 380 | 380 | 380 | ER/NR | Solar |  | Meridian Way 230 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-066 |  | DISIS-2024-001 | 03 CENTRAL | Lawrence | MO | EDE | 2029-08-31 | 2029-12-31 |  |  | 199 | 199 | 199 | ER/NR | Battery/Storage |  | CPK446 5 161 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-065 |  | DISIS-2024-001 | 02 NEBRASKA | Dodge | NE | NPPD | 2029-08-31 | 2029-12-31 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | FREMONT7 115 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-064 |  | DISIS-2024-001 | 03 CENTRAL | Dade | MO | EDE | 2029-08-31 | 2029-12-31 |  |  | 185 | 185 | 185 | ER/NR | Hybrid | Solar/Storage | CPK446 5 161 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-063 |  | DISIS-2024-001 | 05 SOUTHWEST | Lamb | TX | SPS | 2027-10-31 | 2027-12-31 |  |  | 256 | 256 | 256 | ER/NR | Solar |  | Plant X 230 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-062 |  | DISIS-2024-001 | 04 SOUTHEAST | Kingfisher | OK | WFEC | 2028-11-01 | 2028-12-31 |  |  | 230 | 230 | 230 | ER/NR | Battery/Storage |  | Dover SW 138 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-061 |  | DISIS-2024-001 | 03 CENTRAL | Cowley | KS | WERE | 2028-11-01 | 2028-12-31 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Creswell 138 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-060 |  | DISIS-2024-001 | 04 SOUTHEAST | Nowata | OK | OGE | 2027-12-15 | 2029-03-15 |  |  | 250 | 250 | 250 | ER | Wind |  | Northeastern - Delaware 345kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-059 |  | DISIS-2024-001 | 01 NORTH | Stanley | SD | WAPA | 2028-10-02 | 2028-12-29 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Oahe - Philip Tap 230 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-058 |  | DISIS-2024-001 | 04 SOUTHEAST | Nowata | OK | OGE | 2028-10-02 | 2028-12-29 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Farmland - Delaware 138 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-057 |  | DISIS-2024-001 | 05 SOUTHWEST | Cass | TX | AEP | 2029-08-31 | 2029-12-31 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | NWTXARK7 - WELSH 7 345 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-056 |  | DISIS-2024-001 | 04 SOUTHEAST | Noble | OK | OGE | 2029-08-31 | 2029-12-31 |  |  | 120 | 120 | 120 | ER/NR | Solar |  | Cow Creek - Morrison 138 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-055 |  | DISIS-2024-001 | 03 CENTRAL | Vernon | MO | WERE | 2029-08-31 | 2029-12-31 |  |  | 175 | 175 | 175 | ER/NR | Solar |  | Butler - Nevada 161 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-054 |  | DISIS-2024-001 | 03 CENTRAL | Cooper | MO | WERE | 2029-08-31 | 2029-12-31 |  |  | 120 | 120 | 120 | ER/NR | Solar |  | Overton - Sedalia East 161 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-053 |  | DISIS-2024-001 | 03 CENTRAL | Nodaway | MO | WERE | 2031-06-01 | 2032-01-01 |  |  | 450.6 | 425.1 | 450.6 | ER/NR | Thermal | Gas | Mullin Creek 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-052 |  | DISIS-2024-001 | 04 SOUTHEAST | Choctaw | OK | WFEC | 2027-05-15 | 2027-07-01 |  |  | 42 | 42 | 42 | ER/NR | Solar |  | Unger - West Bank Tap 138 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-050 |  | DISIS-2024-001 | 05 SOUTHWEST | Castro | TX | SPS | 2028-11-30 | 2028-12-31 |  |  | 300 | 300 | 300 | ER/NR | Hybrid | Solar/Storage | Deaf Smith - Plant X 230 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-049 |  | DISIS-2024-001 | 03 CENTRAL | Ford | KS | SUNC | 2028-10-01 | 2028-12-01 |  |  | 199 | 199 | 199 | ER/NR | Battery/Storage |  | Holcomb - Spearville 345 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-048 |  | DISIS-2024-001 | 03 CENTRAL | Ford | KS | SUNC | 2028-10-01 | 2028-12-01 |  |  | 199 | 199 | 199 | ER/NR | Battery/Storage |  | Holcomb - Spearville 345 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-047 |  | DISIS-2024-001 | 03 CENTRAL | McPherson | KS | Evergy | 2031-01-01 | 2031-06-01 |  |  | 114.9 | 58.79 | 123.73 | ER/NR | Thermal | Gas | Johns-Manville 115 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-046 |  | DISIS-2024-001 | 05 SOUTHWEST | Hansford | TX | SPS | 2029-10-01 | 2029-12-01 |  |  | 345 | 345 | 345 | ER/NR | Solar |  | Hitchland-Moore 230 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-045 |  | DISIS-2024-001 | 05 SOUTHWEST | Hansford | TX | SPS | 2029-10-01 | 2029-12-01 |  |  | 345 | 345 | 345 | ER/NR | Solar |  | Hitchland - Moore 230kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-044 |  | DISIS-2024-001 | 04 SOUTHEAST | Parish Caddo | LA | AEP | 2027-05-15 | 2027-07-01 |  |  | 36 | 36 | 36 | ER/NR | Solar |  | Hosston - Plain Dealing 69 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-043 |  | DISIS-2024-001 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2029-10-01 | 2029-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Crossroads - Tolk 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-042 |  | DISIS-2024-001 | 05 SOUTHWEST | Floyd | TX | SPS | 2029-10-01 | 2029-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Tuco - Oklaunion 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-041 |  | DISIS-2024-001 | 05 SOUTHWEST | Floyd | TX | SPS | 2029-10-01 | 2029-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Tuco - Oklaunion 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-040 |  | DISIS-2024-001 | 02 NEBRASKA | Nemaha | NE | OPPD | 2029-10-01 | 2029-12-31 |  |  | 174 | 174 | 174 | ER/NR | Solar |  | Cooper - Nebraska City 345 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-039 |  | DISIS-2024-001 | 02 NEBRASKA | Nemaha | NE | OPPD | 2029-10-01 | 2029-12-31 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Humboldt - Auburn 161 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-038 |  | DISIS-2024-001 | 02 NEBRASKA | Nemaha | NE | OPPD | 2029-10-01 | 2029-12-31 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Cooper - Monolith 345 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-037 |  | DISIS-2024-001 | 03 CENTRAL | Newton | MO | AEP | 2029-10-01 | 2029-12-31 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Flint Creek - Brookline 345 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-036 |  | DISIS-2024-001 | 02 NEBRASKA | Colfax | NE | NPPD | 2029-10-01 | 2029-12-31 |  |  | 150 | 150 | 150 | ER/NR | Wind |  | Schuyler- North Bend 115 kV line | 2024-10-30 |  | DISIS STAGE
GEN-2024-035 |  | DISIS-2024-001 | 01 NORTH | Brown | SD | BEPC | 2027-09-01 | 2027-12-30 |  |  | 270 | 270 | 270 | ER/NR | Hybrid | Solar/Storage | Groton 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-034 |  | DISIS-2024-001 | 01 NORTH | Sargent | ND | WAPA | 2029-03-01 | 2029-07-01 |  |  | 175 | 175 | 175 | ER/NR | Battery/Storage |  | Forman 115 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-033 |  | DISIS-2024-001 | 03 CENTRAL | Vernon | MO | Evergy | 2028-11-30 | 2028-12-31 |  |  | 225 | 225 | 225 | ER/NR | Solar |  | Nevada-Butler 161 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-032 |  | DISIS-2024-001 | 03 CENTRAL | Stevens | KS | SUNC | 2028-11-01 | 2028-12-31 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Hugoton 115 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-031 |  | DISIS-2024-001 | 04 SOUTHEAST | Marshall | OK | OGE | 2028-11-01 | 2028-12-31 |  |  | 220 | 220 | 220 | ER/NR | Solar |  | Russett-S.Brown 138 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-030 |  | DISIS-2024-001 | 03 CENTRAL | Gray | KS | SUNC | 2028-11-01 | 2028-12-31 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Santa Fe 115 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-029 |  | DISIS-2024-001 | 04 SOUTHEAST | Logan | OK | OGE | 2028-11-01 | 2028-12-31 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Crescent 138 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-028 |  | DISIS-2024-001 | 03 CENTRAL | Nodaway | MO | WERE | 2029-06-01 | 2030-01-01 |  |  | 450.6 | 425.1 | 450.6 | ER/NR | Thermal | Gas | Mullin Creek 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-027 |  | DISIS-2024-001 | 03 CENTRAL | Reno | KS | WERE | 2029-06-01 | 2030-01-01 |  |  | 717.8 | 690.4 | 717.8 | ER/NR | Thermal | Gas | Reno County 345 kV Substation #1443 | 2024-10-30 |  | DISIS STAGE
GEN-2024-026 |  | DISIS-2024-001 | 03 CENTRAL | Sumner | KS | WERE | 2028-01-06 | 2029-01-01 |  |  | 721.1 | 693.2 | 721.1 | ER/NR | Thermal | Gas | Viola 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-025 |  | DISIS-2024-001 | 05 SOUTHWEST | Bowie | TX | AEP | 2030-06-01 | 2030-12-31 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Lydia 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-024 |  | DISIS-2024-001 | 04 SOUTHEAST | Woodward | OK | WFEC | 2028-05-01 | 2028-07-01 |  |  | 145 | 145 | 145 | ER/NR | Solar |  | Iodine - Mooreland Switchyard 138 kV | 2024-10-30 |  | DISIS STAGE
GEN-2024-023 |  | DISIS-2024-001 | 02 NEBRASKA | Gage | NE | NPPD | 2030-09-30 | 2030-12-31 |  |  | 270 | 270 | 270 | ER/NR | Thermal | Gas | New Beatrice Power Station 345 kV | 2024-10-30 |  | DISIS STAGE
GEN-2024-022 |  | DISIS-2024-001 | 02 NEBRASKA | Gage | NE | NPPD | 2030-09-30 | 2030-12-31 |  |  | 390 | 390 | 390 | ER/NR | Thermal | Gas | New Beatrice Power Station 345 kV | 2024-10-30 |  | DISIS STAGE
GEN-2024-021 |  | DISIS-2024-001 | 02 NEBRASKA | Lancaster | NE | NPPD | 2030-09-30 | 2030-12-31 |  |  | 540 | 540 | 540 | ER/NR | Thermal | Gas | Olive Creek 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-020 |  | DISIS-2024-001 | 02 NEBRASKA | Lancaster | NE | NPPD | 2030-09-30 | 2030-12-31 |  |  | 390 | 390 | 390 | ER/NR | Thermal | Gas | Olive Creek 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-019 |  | DISIS-2024-001 | 02 NEBRASKA | Gage | NE | NPPD | 2030-09-30 | 2030-12-31 |  |  | 62 | 62 | 62 | ER/NR | Thermal | Gas | New Beatrice Power Station 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-018 |  | DISIS-2024-001 | 02 NEBRASKA | Gage | NE | NPPD | 2030-09-30 | 2030-12-31 |  |  | 31 | 31 | 31 | ER/NR | Thermal | Gas | New Beatrice Power Station 345 kV | 2024-10-30 |  | DISIS STAGE
GEN-2024-017 |  | DISIS-2024-001 | 02 NEBRASKA | Lancaster | NE | NPPD | 2030-09-30 | 2030-12-31 |  |  | 62 | 62 | 62 | ER/NR | Thermal | Gas | Olive Creek 345 kV Substation | 2024-10-30 |  | DISIS STAGE
GEN-2024-016 |  | DISIS-2024-001 | 03 CENTRAL | Smith | KS | ITCGP | 2028-10-02 | 2028-12-29 |  |  | 300 | 300 | 300 | ER/NR | Wind |  | Post Rock - Axtell 345 kV Line | 2024-10-30 |  | DISIS STAGE
GEN-2024-015 |  | DISIS-2024-001 | 05 SOUTHWEST | Yoakum | TX | SPS | 2028-09-01 | 2028-12-01 |  |  | 280 | 280 | 280 | ER/NR | Hybrid | Solar/Storage | Sundown-Amaco-Yoakum 230 kV Substation | 2024-10-04 |  | DISIS STAGE
GEN-2024-013 |  | DISIS-2024-001 | 04 SOUTHEAST | McClain | OK | OG&E | 2029-04-01 | 2030-01-01 |  |  | 495.6 | 474.4 | 495.6 | ER/NR | Thermal | CT | Norman Hills 345 kV | 2024-08-02 |  | DISIS STAGE
GEN-2024-012 |  | DISIS-2024-001 | 04 SOUTHEAST | Oklahoma | OK | OG&E | 2028-04-01 | 2029-01-01 |  |  | 495.6 | 474.4 | 495.6 | ER/NR | Thermal | Gas | Horseshoe Lake 138 kV | 2024-08-02 |  | DISIS STAGE
GEN-2024-011 |  | DISIS-2024-001 | 05 SOUTHWEST | Lea | NM | WFEC | 2026-02-01 | 2026-12-29 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Lea County 115 kV Substation | 2023-12-29 |  | DISIS STAGE
GEN-2024-010 |  | DISIS-2024-001 | 05 SOUTHWEST | Lea | NM | SPS | 2026-02-01 | 2026-12-28 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Cunningham 230 kV Substation | 2023-12-29 |  | DISIS STAGE
GEN-2024-009 |  | DISIS-2024-001 | 05 SOUTHWEST | Lea | NM | SPS | 2026-02-26 | 2026-12-30 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Hobbs 230 kV Substation | 2024-01-02 |  | DISIS STAGE
GEN-2024-008 |  | DISIS-2024-001 | 05 SOUTHWEST | Lea | NM | SPS | 2026-02-01 | 2026-12-28 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Ward 115 kV Substation | 2023-12-29 |  | DISIS STAGE
GEN-2024-007 |  | DISIS-2024-001 | 03 CENTRAL | Stafford | KS | Evergy | 2028-01-30 | 2028-12-31 |  |  | 80 | 80 | 80 | ER/NR | Hybrid | Solar/Storage | Seward 115 kV Substation | 2024-04-30 |  | DISIS STAGE
GEN-2024-006 |  | DISIS-2024-001 | 04 SOUTHEAST | Lawrence | AR | SWPA | 2026-10-01 | 2028-02-01 |  |  | 100 | 100 | 100 | ER/NR | Solar |  | Jonesboro - Water Valley 161 kV | 2024-04-25 |  | DISIS STAGE
GEN-2024-005 |  | DISIS-2024-001 | 03 CENTRAL | Andrew and Nodaway | MO | Evergy | 2026-11-01 | 2028-03-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Midway - Avenue City 161 kV | 2024-04-25 |  | DISIS STAGE
GEN-2024-003 |  | DISIS-2024-001 | 04 SOUTHEAST | Franklin | AR | AECC | 2025-09-12 | 2025-11-07 |  |  | 102.2 | 102.2 | 102.2 | ER | Thermal | CT | Fitzhugh 161kV | 2024-04-25 |  | DISIS STAGE
GEN-2024-002 |  | DISIS-2024-001 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2029-05-27 | 2029-09-30 |  |  | 90 | 90 | 90 | ER/NR | Solar |  | Roosevelt - Portales 115 kV Line | 2024-02-02 |  | DISIS STAGE
GEN-2024-001 |  | DISIS-2024-001 | 05 SOUTHWEST | Curry | NM | SPS | 2029-05-27 | 2029-09-30 |  |  | 100 | 100 | 100 | ER/NR | Solar |  | Curry County 115 kV Substation | 2024-02-02 |  | DISIS STAGE
GEN-2023-SR9 |  | Surplus | 05 SOUTHWEST | Lorenzo | TX | Xcel |  | 2026-06-01 |  |  | 50 | 50 | 50 | ER | Battery/Storage |  | Tap Floyd County Interchange and Crosby County Interchange 115kV Line | 2023-02-13 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR8 |  | Surplus | 05 SOUTHWEST | Gruver | TX | Xcel |  | 2026-06-01 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Hitchland 345 kV Substation | 2023-02-13 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR7 |  | Surplus | 02 NEBRASKA | Wayne Co | NE | NPPD |  | 2024-12-31 |  |  | 135 | 135 | 135 | ER | Battery/Storage |  | Hoskins 345 kV Substation | 2022-12-16 |  | FACILITY STUDY STAGE
GEN-2023-SR5 |  | Surplus | 04 SOUTHEAST | Seiling | OK | OGE |  | 2026-06-01 |  |  | 85 | 85 | 85 | ER | Battery/Storage |  | Tatonga 345 kV Substation | 2022-12-15 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR4 |  | Surplus | 01 NORTH | Burke | ND | BEPC |  | 2026-06-01 |  |  | 170 | 170 | 170 | ER | Battery/Storage |  | Tande 345 kV Substation | 2022-12-15 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR28 |  | Surplus | 03 CENTRAL | Ford | KS | SUNC |  | 2025-12-31 |  |  | 150 | 150 | 150 | ER | Solar |  | 115 kV Fort Dodge Substation | 2023-10-06 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR27 |  | Surplus | 04 SOUTHEAST | Mayes County | OK | GRDA | 2021-12-01 | 2024-08-01 |  |  | 101.5 | 101.5 | 101.5 | ER | Battery/Storage |  | GRDA1 to CLARMR 5 161kV line | 2023-07-12 |  | IA PENDING
GEN-2023-SR26 |  | Surplus | 04 SOUTHEAST | Mayes County | OK | AEP | 2021-12-01 | 2024-12-09 |  |  | 72.5 | 72.5 | 72.5 | ER | Battery/Storage |  | Pryor Junction 138kV sub | 2023-07-12 |  | IA PENDING
GEN-2023-SR25 |  | Surplus | 04 SOUTHEAST | Mayes County | OK | GRDA | 2021-12-01 | 2024-08-01 |  |  | 72.5 | 72.5 | 72.5 | ER | Battery/Storage |  | Dry Gulch 161kV sub | 2023-07-12 |  | IA PENDING
GEN-2023-SR23 |  | Surplus | 04 SOUTHEAST | Caddo Parrish | LA | AEP |  | 2025-12-01 |  |  | 73.5 | 73.5 | 73.5 | ER/NR | Battery/Storage |  | 138 kV G16-167-TAP Station (Bus# 588404); Tapping North Benton (Bus# 508811) to Lieberman (bus# 508806) Transmission Line | 2023-06-20 |  | IA PENDING
GEN-2023-SR22 |  | Surplus | 04 SOUTHEAST | Mayes County | OK | AEP |  | 2024-12-06 |  |  | 124.7 | 124.7 | 124.7 | ER | Battery/Storage |  | 138 kV Exclart Bus (Bus# 510401) | 2023-06-20 |  | IA PENDING
GEN-2023-SR20 |  | Surplus | 04 SOUTHEAST | Custer/Wasita | OK | AEP |  | 2025-06-01 |  |  | 120 | 120 | 120 | ER | Battery/Storage |  | Weatherford 138 kV Substation | 2023-06-21 |  | IA PENDING
GEN-2023-SR19 |  | Surplus | 02 NEBRASKA | Jefferson County | NE | NPPD |  | 2025-06-01 |  |  | 60 | 60 | 60 | ER | Battery/Storage |  | Steele City 115 kV | 2023-06-21 |  | FACILITY STUDY STAGE
GEN-2023-SR18 |  | Surplus | 04 SOUTHEAST | Grady County | OK | OGE |  | 2025-05-15 |  |  | 80 | 80 | 80 | ER | Battery/Storage |  | Minco 345 kV | 2023-06-20 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR16 |  | Surplus | 04 SOUTHEAST | Woodward and Harper Counties | OK | OG&E |  | 2025-06-01 |  |  | 70 | 70 | 70 | ER | Battery/Storage |  | Tap Mooreland to Woodward 138 kV Line (FPLSwitch 138 kV Substation) | 2023-04-26 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR15 |  | Surplus | 04 SOUTHEAST | Choctaw County | OK | WFEC |  | 2026-06-01 |  |  | 50 | 50 | 50 | ER/NR | Battery/Storage |  | Hugo Power Plant 138 kV Substation | 2023-03-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR13 |  | Surplus | 04 SOUTHEAST | Garfield County | OK | OG&E |  | 2025-06-01 |  |  | 70 | 70 | 70 | ER | Battery/Storage |  | Breckinridge 138 kV Substation | 2023-01-26 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR12 |  | Surplus | 05 SOUTHWEST | Whiteface | TX | Xcel |  | 2025-09-30 |  |  | 120 | 120 | 120 | ER | Battery/Storage |  | Tap Cochran to Lehman 115 kV Line | 2023-02-13 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-SR1 |  | Surplus | 02 NEBRASKA | Brown | NE | NPPD | 2005-10-01 | 2024-06-21 |  |  | 21.9 | 21.9 | 21.9 | ER/NR | Thermal |  | Ainsworth Wind 115 kV | 2022-12-05 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-GR5 |  | Replacement | 05 SOUTHWEST | Lamb County | TX | Xcel/SPS |  | 2026-04-01 | 2022-08-11 |  | 150 | 150 | 150 | ER | Solar |  | Plant X 115 kV Substation | 2023-07-18 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-GR4 |  | Replacement | 05 SOUTHWEST | Lea County | NM | Xcel/SPS |  | 2026-05-01 | 2022-07-13 |  | 72 | 72 | 72 | ER | Solar |  | Cunningham 115kV | 2023-07-05 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-GR3 |  | Replacement | 05 SOUTHWEST | Quay County | NM | Xcel/SPS | 2004-12-01 | 2024-12-27 | 2024-09-16 | 2004-12-31 | 80 | 80 | 80 | ER/NR | Wind |  | Norton 115 kV | 2023-06-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2023-GR2 |  | Replacement | 04 SOUTHEAST | Oklahoma City | OK | OG&E |  | 2026-05-01 | 2026-04-01 |  | 94.242 | 84.926 | 94.242 | ER | Thermal | Gas | Tinker Air Force Base 138kV | 2023-02-17 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-GR1 |  | Replacement | 04 SOUTHEAST | Anadarko | OK | WFEC |  | 2025-12-01 | 2025-11-30 |  | 97.488 | 97.488 | 95.64 | ER | Thermal | Gas | Anadarko Power Plant 69 kV | 2023-01-09 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2023-241 |  | DISIS-2023-001 | 04 SOUTHEAST | Franklin & Wood | TX | AEP | 2027-08-28 | 2028-01-05 |  |  | 93 | 93 | 93 | ER | Solar |  | Winnsboro 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-237 |  | DISIS-2023-001 | 05 SOUTHWEST | Hale | TX | SPS | 2030-01-15 | 2030-12-31 |  |  | 500 | 500 | 500 | ER/NR | Wind |  | Crawfish Draw 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-236 |  | DISIS-2023-001 | 05 SOUTHWEST | Lea | NM | SPS | 2030-01-15 | 2030-12-31 |  |  | 400 | 400 | 400 | ER/NR | Solar |  | Hobbs - Yoakum 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-231 |  | DISIS-2023-001 | 03 CENTRAL | Crawford | KS | Evergy | 2028-05-01 | 2028-12-01 |  |  | 310 | 310 | 310 | ER | Hybrid | Wind/Storage | Neosho - LaCynge 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-230 |  | DISIS-2023-001 | 04 SOUTHEAST | Bossier | LA | AEP | 2028-02-04 | 2028-11-19 |  |  | 150 | 150 | 150 | ER/NR | Hybrid | Solar/Storage | Red Pointe 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-229 |  | DISIS-2023-001 | 04 SOUTHEAST | Caddo | OK | AEP | 2028-04-01 | 2028-10-31 |  |  | 230 | 230 | 230 | ER/NR | Wind |  | Southwestern Power Station 138 kV Substation (SWS4) | 2023-10-02 |  | DISIS STAGE
GEN-2023-228 |  | DISIS-2023-001 | 05 SOUTHWEST | Cottle | TX | SPS | 2026-08-15 | 2026-12-01 |  |  | 250 | 250 | 250 | ER/NR | Battery/Storage |  | Tuco-Okalunion 345 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-227 |  | DISIS-2023-001 | 04 SOUTHEAST | Titus | TX | AEP | 2026-05-01 | 2026-09-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Petty to Chapel 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-225 |  | DISIS-2023-001 | 02 NEBRASKA | Lancaster | NE | NPPD | 2027-03-01 | 2027-06-01 |  |  | 217 | 217 | 217 | ER | Thermal | RICE | Olive Creek 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-224 |  | DISIS-2023-001 | 02 NEBRASKA | Lancaster | NE | NPPD | 2027-03-01 | 2027-06-01 |  |  | 478 | 478 | 478 | ER | Thermal | CTG | Olive Creek 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-223 |  | DISIS-2023-001 | 02 NEBRASKA | Gage | NE | NPPD | 2027-03-01 | 2027-06-01 |  |  | 239 | 239 | 239 | ER/NR | Thermal | CTG | New Beatrice Power Station 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-222 |  | DISIS-2023-001 | 02 NEBRASKA | Gage | NE | NPPD | 2027-03-01 | 2027-06-01 |  |  | 478 | 478 | 478 | ER/NR | Thermal | CTG | New Beatrice Power Station 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-221 |  | DISIS-2023-001 | 03 CENTRAL | Osage | KS | Evergy | 2029-09-01 | 2029-12-01 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Emporia Energy Center - Swissvale 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-220 |  | DISIS-2023-001 | 03 CENTRAL | Osage | KS | Evergy | 2029-08-01 | 2029-12-01 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Emporia Energy Center - Swissvale 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-219 |  | DISIS-2023-001 | 03 CENTRAL | Osage | KS | Evergy | 2029-08-01 | 2029-12-01 |  |  | 125 | 125 | 125 | ER/NR | Solar |  | Reading - Osage Jct 115 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-218 |  | DISIS-2023-001 | 02 NEBRASKA | Knox and Cedar | NE | NPPD | 2026-09-30 | 2026-12-31 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Turtle Creek 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-217 |  | DISIS-2023-001 | 02 NEBRASKA | Knox and Cedar | NE | NPPD | 2026-09-30 | 2026-12-31 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Turtle Creek 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-216 |  | DISIS-2023-001 | 02 NEBRASKA | Knox and Cedar | NE | NPPD | 2026-09-30 | 2026-12-31 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Turtle Creek 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-213 |  | DISIS-2023-001 | 04 SOUTHEAST | Benton | AR | AEP | 2028-04-15 | 2028-09-01 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Chamber Springs 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-212 |  | DISIS-2023-001 | 04 SOUTHEAST | Bowie | TX/OK | AEP | 2027-03-01 | 2027-12-01 |  |  | 400 | 400 | 400 | ER/NR | Hybrid | Solar/Storage | Northwest Texarkana - Valliant 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-211 |  | DISIS-2023-001 | 04 SOUTHEAST | Kay | OK | OGE | 2028-03-01 | 2028-11-01 |  |  | 250 | 250 | 250 | ER/NR | Hybrid | Solar/Battery/Wind | Ranch Road 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-210 |  | DISIS-2023-001 | 04 SOUTHEAST | Lincoln | OK | WFEC | 2026-05-04 | 2026-09-01 |  |  | 191 | 191 | 191 | ER/NR | Solar |  | Prague - Chernicky 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-209 |  | DISIS-2023-001 | 05 SOUTHWEST | Randall | TX | SPS | 2027-04-01 | 2027-06-01 |  |  | 125 | 125 | 125 | ER/NR | Battery/Storage |  | Amarillo South 115 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-208 |  | DISIS-2023-001 | 05 SOUTHWEST | Potter | TX | SPS |  | 2029-12-31 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Rolling Hills 115 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-206 |  | DISIS-2023-001 | 04 SOUTHEAST | Sebastian | AR | OGE | 2029-01-01 | 2029-12-31 |  |  | 50 | 50 | 50 | ER/NR | Battery/Storage |  | Battlefield BESS 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-205 |  | DISIS-2023-001 | 04 SOUTHEAST | Hughes | OK | AEP | 2026-07-01 | 2026-12-31 |  |  | 180 | 180 | 180 | ER/NR | Solar |  | McAlester City - Weleetka 138 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-204 |  | DISIS-2023-001 | 04 SOUTHEAST | Morris | TX | AEP | 2028-04-01 | 2028-12-01 |  |  | 953 | 953 | 953 | ER | Thermal | CTG | Welsh-Lydia 345kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-203 |  | DISIS-2023-001 | 05 SOUTHWEST | Lea | NM | SPS | 2028-07-31 | 2028-12-31 |  |  | 300 | 300 | 300 | ER/NR | Hybrid | Solar/Storage | Hobbs - Ink Basin 230 kV Transmission Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-201 |  | DISIS-2023-001 | 05 SOUTHWEST | Lea | NM | NEET | 2028-07-31 | 2028-12-31 |  |  | 300 | 300 | 300 | ER/NR | Hybrid | Solar/Storage | Crossroads - Hobbs 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-199 |  | DISIS-2023-001 | 02 NEBRASKA | Dakota | NE | NPPD | 2030-03-01 | 2027-03-28 |  |  | 250 | 250 | 250 | ER/NR | Hybrid | Solar/Storage | Twin Church 230 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-195 |  | DISIS-2023-001 | 05 SOUTHWEST | Bailey | TX | SPS | 2028-02-01 | 2028-06-01 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Roosevelt - Tolk 230 kV line tap | 2023-10-02 |  | DISIS STAGE
GEN-2023-194 |  | DISIS-2023-001 | 03 CENTRAL | Cherokee | KS | EDE | 2028-06-01 | 2028-12-31 |  |  | 225 | 225 | 225 | ER/NR | Solar |  | Riverton - Neosho 161 kV Line Tap | 2023-10-02 |  | DISIS STAGE
GEN-2023-193 |  | DISIS-2023-001 | 04 SOUTHEAST | Harrison | TX | AEP | 2028-01-15 | 2028-03-31 |  |  | 175 | 175 | 175 | ER/NR | Hybrid | Solar/Storage | Pirkey - Whitney 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-189 |  | DISIS-2023-001 | 02 NEBRASKA | Lancaster | NE | LES | 2030-08-30 | 2030-12-31 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | NW 68th - Holdrege 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-188 |  | DISIS-2023-001 | 05 SOUTHWEST | Cotton | OK | AEP | 2027-02-15 | 2027-09-01 |  |  | 160 | 160 | 160 | ER/NR | Hybrid | Solar/Storage | Oklaunion - Lawton 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-184 |  | DISIS-2023-001 | 05 SOUTHWEST | Eddy | NM | SPS | 2030-08-30 | 2030-12-31 |  |  | 200 | 200 | 200 | ER | Solar |  | Phantom 115 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-183 |  | DISIS-2023-001 | 05 SOUTHWEST | Hale | TX | SPS | 2027-03-31 | 2027-02-28 |  |  | 217 | 217 | 217 | ER | Thermal | CTG | Tuco 345kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-182 |  | DISIS-2023-001 | 01 NORTH | Logan & McIntosh | ND | BEPC | 2026-08-15 | 2026-12-01 |  |  | 300 | 300 | 300 | ER | Wind |  | Groton - Leland Olds 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-180 |  | DISIS-2023-001 | 04 SOUTHEAST | Sebastian | AR | AEP | 2028-02-01 | 2028-06-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Hackett - N Huntington 161 kV Line Tap | 2023-10-02 |  | DISIS STAGE
GEN-2023-178 |  | DISIS-2023-001 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2026-08-15 | 2026-12-01 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Roosevelt 230kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-177 |  | DISIS-2023-001 | 04 SOUTHEAST | Garvin | OK | OGE | 2028-02-01 | 2028-06-01 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Paoli - Seminole 138 kV line tap | 2023-10-02 |  | DISIS STAGE
GEN-2023-176 |  | DISIS-2023-001 | 05 SOUTHWEST | Lamb | TX | SPS | 2030-08-30 | 2030-12-31 |  |  | 300 | 300 | 300 | ER | Wind |  | Plant X 230 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-174 |  | DISIS-2023-001 | 04 SOUTHEAST | Garvin | OK | WFEC | 2028-02-01 | 2028-06-01 |  |  | 150 | 150 | 150 | ER | Battery/Storage |  | Paoli West 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-173 |  | DISIS-2023-001 | 03 CENTRAL | Kearny | KS | SUNC | 2027-09-01 | 2027-12-31 |  |  | 100 | 100 | 100 | ER/NR | Wind |  | Holcomb 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-172 |  | DISIS-2023-001 | 03 CENTRAL | Kearny | KS | SUNC | 2027-09-01 | 2027-12-31 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Holcomb 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-171 |  | DISIS-2023-001 | 03 CENTRAL | Jackson | MO | INDN | 2028-02-01 | 2028-06-01 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Sub M 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-170 |  | DISIS-2023-001 | 03 CENTRAL | Chariton | MO | Evergy | 2028-02-01 | 2028-06-01 |  |  | 150 | 150 | 150 | ER | Battery/Storage |  | Salisbury 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-169 |  | DISIS-2023-001 | 03 CENTRAL | Clay | MO | Evergy | 2028-02-01 | 2028-06-01 |  |  | 125 | 125 | 125 | ER/NR | Battery/Storage |  | Missouri City - Liberty South 161 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-168 |  | DISIS-2023-001 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2028-02-01 | 2028-06-01 |  |  | 175 | 175 | 175 | ER/NR | Battery/Storage |  | Classen 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-167 |  | DISIS-2023-001 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2028-02-01 | 2028-06-01 |  |  | 250 | 250 | 250 | ER/NR | Battery/Storage |  | Washington Park 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-166 |  | DISIS-2023-001 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2028-02-01 | 2028-06-01 |  |  | 150 | 150 | 150 | ER | Battery/Storage |  | 84th Street - Tennessee Tap 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-165 |  | DISIS-2023-001 | 04 SOUTHEAST | Caddo | OK | OGE | 2028-03-01 | 2028-05-01 |  |  | 210 | 210 | 210 | ER/NR | Battery/Storage |  | Gracemont 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-164 |  | DISIS-2023-001 | 04 SOUTHEAST | Caddo | OK | OGE | 2028-03-01 | 2028-05-01 |  |  | 210 | 210 | 210 | ER/NR | Battery/Storage |  | Gracemont 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-161 |  | DISIS-2023-001 | 04 SOUTHEAST | Blaine | OK | OGE | 2026-09-03 | 2026-11-04 |  |  | 74.9 | 74.9 | 74.9 | ER/NR | Battery/Storage |  | Roman Nose 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-159 |  | DISIS-2023-001 | 05 SOUTHWEST | Bailey and Lamb | TX | SPS | 2029-03-01 | 2029-09-15 |  |  | 170 | 170 | 170 | ER/NR | Battery/Storage |  | Needmore - Yoakum 230 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-158 |  | DISIS-2023-001 | 05 SOUTHWEST | Bailey and Lamb | TX | SPS | 2029-03-01 | 2029-09-15 |  |  | 335 | 335 | 335 | ER/NR | Solar |  | Needmore - Yoakum 230 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-154 |  | DISIS-2023-001 | 01 NORTH | Hand | SD | WAPA | 2029-03-01 | 2029-09-30 |  |  | 175 | 175 | 175 | ER | Solar |  | Fort Thompson - Huron 230 kV Tap | 2023-10-02 |  | DISIS STAGE
GEN-2023-153 |  | DISIS-2023-001 | 02 NEBRASKA | Perkins | NE | Tri-State | 2028-06-30 | 2028-08-31 |  |  | 120 | 120 | 120 | ER/NR | Hybrid | Solar/Storage | Grant 115 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-151 |  | DISIS-2023-001 | 04 SOUTHEAST | Hempstead | AR | AEP | 2028-04-01 | 2028-08-01 |  |  | 100 | 100 | 100 | ER/NR | Hybrid | Solar/Storage | South Nashville - South Murfreesboro 138kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-150 |  | DISIS-2023-001 | 04 SOUTHEAST | Caddo | OK | OGE | 2027-09-01 | 2027-12-31 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Gracemont 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-149 |  | DISIS-2023-001 | 03 CENTRAL | Lin | KS | Evergy | 2029-02-15 | 2029-07-01 |  |  | 300 | 300 | 300 | ER/NR | Battery/Storage |  | LaCygne - Stilwell 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-143 |  | DISIS-2023-001 | 05 SOUTHWEST | Lamb | TX | SPS | 2029-03-01 | 2029-09-15 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Plant X 230 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-142 |  | DISIS-2023-001 | 05 SOUTHWEST | Lamb | TX | SPS | 2029-03-01 | 2029-09-15 |  |  | 275 | 275 | 275 | ER | Solar |  | Plant X 230 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-138 |  | DISIS-2023-001 | 04 SOUTHEAST | Deleware | OK | GRDA | 2028-07-15 | 2028-11-30 |  |  | 250 | 250 | 250 | ER | Wind |  | GRDA1 - Tonece7 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-135 |  | DISIS-2023-001 | 04 SOUTHEAST | Bowie | TX | AEP | 2026-09-15 | 2026-12-31 |  |  | 52 | 52 | 52 | ER/NR | Solar |  | Lydia 345kV substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-134 |  | DISIS-2023-001 | 04 SOUTHEAST | Hughes/Okfuskee | OK | AEP | 2026-09-15 | 2026-12-31 |  |  | 252 | 252 | 252 | ER/NR | Wind |  | Fixico Tap to Weleetka 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-133 |  | DISIS-2023-001 | 02 NEBRASKA | Custer | NE | NPPD | 2030-05-01 | 2030-12-30 |  |  | 250 | 250 | 250 | ER | Wind |  | Sweetwater 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-132 |  | DISIS-2023-001 | 04 SOUTHEAST | Craighead | AR | SWPA | 2026-06-30 | 2026-12-31 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Jonesboro - Independence 161 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-123 |  | DISIS-2023-001 | 05 SOUTHWEST | Ochiltree/Handsford | TX | SPS | 2030-08-30 | 2030-12-31 |  |  | 285 | 285 | 285 | ER | Wind |  | Pringle Interchange 230 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-120 |  | DISIS-2023-001 | 05 SOUTHWEST | Swisher | TX | SPS | 2030-08-30 | 2030-12-31 |  |  | 130 | 130 | 130 | ER | Solar |  | Kress 115 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-117 |  | DISIS-2023-001 | 02 NEBRASKA | Keith, Deuel, Garden | NE | NPPD | 2030-08-30 | 2030-12-30 |  |  | 300 | 300 | 300 | ER | Wind |  | Keystone 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-116 |  | DISIS-2023-001 | 02 NEBRASKA | Keith, Deuel, Garden | NE | NPPD | 2030-08-30 | 2030-12-30 |  |  | 500 | 500 | 500 | ER | Wind |  | Keystone 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-110 |  | DISIS-2023-001 | 05 SOUTHWEST | Hall | TX | SPS | 2030-08-30 | 2030-12-31 |  |  | 250 | 250 | 250 | ER | Solar |  | Tap Border to Tuco 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-107 |  | DISIS-2023-001 | 03 CENTRAL | Finney/Kearny | KS | SUNC | 2030-05-01 | 2030-12-31 |  |  | 300 | 300 | 300 | ER | Wind |  | Setab 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-105 |  | DISIS-2023-001 | 01 NORTH | Hyde | SD | BEPC | 2028-09-01 | 2028-12-01 |  |  | 249 | 249 | 249 | ER/NR | Wind |  | Chappelle Creek 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-104 |  | DISIS-2023-001 | 04 SOUTHEAST | Woods | OK | WFEC | 2027-08-30 | 2027-12-17 |  |  | 100 | 100 | 100 | ER/NR | Hybrid | Solar/Storage | Mooreland - Noel 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-102 |  | DISIS-2023-001 | 04 SOUTHEAST | Woods | OK | OGE | 2027-08-30 | 2027-12-17 |  |  | 475 | 475 | 475 | ER/NR | Hybrid | Solar/Storage | Degrasse 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-101 |  | DISIS-2023-001 | 04 SOUTHEAST | Wheeler | TX | SPS | 2027-10-01 | 2027-12-31 |  |  | 150 | 150 | 150 | ER/NR | Hybrid | Solar/Storage | Tap Stateline Demarc - Wheeler 230 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-100 |  | DISIS-2023-001 | 04 SOUTHEAST | Woods | OK | OGE | 2027-08-30 | 2027-12-17 |  |  | 300 | 300 | 300 | ER/NR | Hybrid | Solar/Storage | Degrasse 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-099 |  | DISIS-2023-001 | 03 CENTRAL | Jackson | KS | Evergy | 2030-08-30 | 2030-12-31 |  |  | 300 | 300 | 300 | ER | Solar |  | Jeffery Energy Center 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-097 |  | DISIS-2023-001 | 01 NORTH | Williams | ND | BEPC | 2029-02-15 | 2029-07-01 |  |  | 250 | 250 | 250 | ER/NR | Battery/Storage |  | Judson 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-092 |  | DISIS-2023-001 | 04 SOUTHEAST | Choctaw | OK | WFEC | 2027-08-30 | 2027-12-17 |  |  | 125 | 125 | 125 | ER/NR | Hybrid | Solar/Storage | Unger - Frogville 138 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-088 |  | DISIS-2023-001 | 04 SOUTHEAST | Okfuskee/Okmulgee | OK | WFEC | 2028-09-15 | 2028-12-31 |  |  | 117 | 117 | 117 | ER/NR | Wind |  | Pharaoh 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-087 |  | DISIS-2023-001 | 03 CENTRAL | Cass | MO | Evergy | 2030-08-30 | 2030-12-31 |  |  | 200 | 200 | 200 | ER | Solar |  | Archie 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-086 |  | DISIS-2023-001 | 05 SOUTHWEST | Randall | TX | SPS | 2028-10-01 | 2029-05-01 |  |  | 300 | 300 | 300 | ER/NR | Hybrid | Solar/Storage | Potter - Newhart 230 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-085 |  | DISIS-2023-001 | 03 CENTRAL | Douglas/Wright | MO | SWPA | 2026-09-15 | 2026-12-31 |  |  | 150 | 150 | 150 | ER/NR | Wind |  | Mansfield - Logan 161 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-082 |  | DISIS-2023-001 | 01 NORTH | Brookings | SD | WAPA | 2029-02-15 | 2029-07-01 |  |  | 175 | 175 | 175 | ER/NR | Battery/Storage |  | White 115 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-081 |  | DISIS-2023-001 | 05 SOUTHWEST | Lea | NM | NEET | 2028-08-01 | 2028-10-01 |  |  | 625 | 625 | 625 | ER/NR | Hybrid | Solar/Storage | Crossroads - Hobbs 345 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-079 |  | DISIS-2023-001 | 02 NEBRASKA | Cass | NE | OPPD | 2028-07-01 | 2029-02-01 |  |  | 303 | 303 | 303 | ER | Thermal | Gas Turbine | Substation 3740 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-078 |  | DISIS-2023-001 | 02 NEBRASKA | Cass | NE | OPPD | 2027-07-01 | 2028-02-01 |  |  | 255 | 255 | 255 | ER | Thermal | Gas Turbine | Substation 3740 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-077 |  | DISIS-2023-001 | 02 NEBRASKA | Cass | NE | OPPD | 2027-07-01 | 2028-02-01 |  |  | 255 | 255 | 255 | ER | Thermal | Gas Turbine | Substation 3740 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-076 |  | DISIS-2023-001 | 04 SOUTHEAST | Nowata/Craig | OK | Evergy | 2027-09-01 | 2027-12-31 |  |  | 100 | 100 | 100 | ER/NR | Wind |  | Delaware - Neosho 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-075 |  | DISIS-2023-001 | 04 SOUTHEAST | Nowata/Craig | OK | Evergy | 2027-10-01 | 2027-12-01 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Delaware to Neosho 345 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-073 |  | DISIS-2023-001 | 03 CENTRAL | Butler | KS | Evergy | 2027-08-30 | 2027-12-27 |  |  | 250 | 250 | 250 | ER/NR | Battery/Storage |  | Rose Hill 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-069 |  | DISIS-2023-001 | 04 SOUTHEAST | Atoka | OK | WFEC | 2027-08-30 | 2027-12-17 |  |  | 100 | 100 | 100 | ER/NR | Hybrid | Solar/Storage | Tupelo - Atoka 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-065 |  | DISIS-2023-001 | 03 CENTRAL | Harvey | KS | Evergy | 2026-05-01 | 2026-09-01 |  |  | 140 | 140 | 140 | ER/NR | Battery/Storage |  | Halstead 69 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-064 |  | DISIS-2023-001 | 04 SOUTHEAST | LeFlore | OK | SWPA | 2028-08-01 | 2028-12-01 |  |  | 200 | 200 | 200 | ER/NR | Hybrid | Solar/Storage | RS Kerr-Stigler 161 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-063 |  | DISIS-2023-001 | 04 SOUTHEAST | Rogers | OK | AEP | 2028-08-01 | 2028-12-01 |  |  | 135 | 135 | 135 | ER/NR | Hybrid | Solar/Storage | Catoosa - Owasso 88th 138 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-062 |  | DISIS-2023-001 | 01 NORTH | Williams | ND | LYREC | 2028-04-30 | 2028-07-31 |  |  | 98 | 98 | 98 | ER | Thermal | Steam | REN 115 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-061 |  | DISIS-2023-001 | 03 CENTRAL | Jasper | MO | SWPA | 2027-09-30 | 2027-12-31 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Carthage 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-060 |  | DISIS-2023-001 | 05 SOUTHWEST | Lamb | TX | SPS | 2026-09-30 | 2026-12-31 |  |  | 256 | 256 | 256 | ER/NR | Solar |  | Plant X 230kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-059 |  | DISIS-2023-001 | 04 SOUTHEAST | Harrison and Panola | TX | AEP | 2026-09-30 | 2026-12-31 |  |  | 200 | 200 | 200 | ER/NR | Hybrid | Solar\RECIP Gas | Tap Rockhill to South Shreveport 138 kV line | 2023-09-11 |  | DISIS STAGE
GEN-2023-057 |  | DISIS-2023-001 | 04 SOUTHEAST | Pawnee | OK | GRDA | 2027-12-28 | 2028-05-31 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Pawnee Switch 138 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-056 |  | DISIS-2023-001 | 04 SOUTHEAST | Van Buren County | AR | SWPA | 2027-12-28 | 2028-05-31 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Van Buren 161 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-055 |  | DISIS-2023-001 | 04 SOUTHEAST | Mayes County | OK | GRDA | 2027-12-28 | 2028-05-31 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Kerr Grove 161 kV | 2023-10-02 |  | DISIS STAGE
GEN-2023-050 |  | DISIS-2023-001 | 03 CENTRAL | Labette | KS | Evergy | 2028-06-30 | 2028-12-31 |  |  | 400 | 400 | 400 | ER/NR | Hybrid | Solar/Storage | Neosho 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-049 |  | DISIS-2023-001 | 04 SOUTHEAST | Mayes | OK | GRDA | 2028-06-30 | 2028-12-31 |  |  | 150 | 150 | 150 | ER/NR | Hybrid | Solar/Storage | Dry Gulch - Pensacola 161 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-038 |  | DISIS-2023-001 | 04 SOUTHEAST | Coal | OK | OGE | 2026-05-24 | 2026-09-01 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Lula 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-037 |  | DISIS-2023-001 | 03 CENTRAL | Wyandotte | KS | KACY | 2028-04-15 | 2028-07-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Nearman 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-036 |  | DISIS-2023-001 | 03 CENTRAL | Jackson | MO | INDN | 2026-08-30 | 2026-12-31 |  |  | 165 | 165 | 165 | ER/NR | Battery/Storage |  | Eckles Road 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-035 |  | DISIS-2023-001 | 04 SOUTHEAST | Grady | OK | WFEC | 2026-05-04 | 2026-09-01 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Cleveland - Amber Tap 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-034 |  | DISIS-2023-001 | 03 CENTRAL | Sedgwick | KS | Evergy | 2026-05-24 | 2026-09-01 |  |  | 130 | 130 | 130 | ER/NR | Solar |  | Clear Water - Waco 138 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-033 |  | DISIS-2023-001 | 03 CENTRAL | Clay | MO | Evergy | 2028-04-15 | 2028-07-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Liberty South 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-032 |  | DISIS-2023-001 | 03 CENTRAL | Lafayette | MO | Evergy | 2028-01-01 | 2028-06-01 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Odessa and Lexington 161 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-030 |  | DISIS-2023-001 | 04 SOUTHEAST | DeSoto Parish | LA | AEP | 2027-09-01 | 2027-12-31 |  |  | 25 | 25 | 25 | ER/NR | Solar |  | Tap between 345 kV SW Shreveport to Dolet Hills Substations | 2023-10-02 |  | DISIS STAGE
GEN-2023-028 |  | DISIS-2023-001 | 04 SOUTHEAST | Mayes | OK | GRDA | 2028-04-30 | 2028-10-31 |  |  | 230 | 230 | 230 | ER/NR | Hybrid | Solar/Battery | Dry Gulch - Pensacola 161 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-027 |  | DISIS-2023-001 | 04 SOUTHEAST | Mayes | OK | AEP | 2028-04-30 | 2027-11-30 |  |  | 150 | 150 | 150 | ER/NR | Hybrid | Solar/Battery | Bird Hollow (Langley) - Pryor Junction 138 kV Line | 2023-10-02 |  | DISIS STAGE
GEN-2023-023 |  | DISIS-2023-001 | 03 CENTRAL | Wyandotte | KS | KACY | 2028-04-15 | 2028-07-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Center City 161 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-022 |  | DISIS-2023-001 | 04 SOUTHEAST | McIntosh | OK | OGE | 2027-09-01 | 2027-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Canadian River 345 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-015 |  | DISIS-2023-001 | 03 CENTRAL | Finney County | KS | SPS | 2026-05-04 | 2026-09-01 |  |  | 330 | 330 | 330 | ER/NR | Solar |  | Finney-Carpenter 345 KV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-012 |  | DISIS-2023-001 | 01 NORTH | Lake Preston | SD | EREC | 2026-06-15 | 2026-10-31 |  |  | 98.6 | 98.6 | 98.6 | ER/NR | Wind |  | Kingsbury County 115kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-011 |  | DISIS-2023-001 | 02 NEBRASKA | Jefferson | NE | NPPD | 2030-08-30 | 2030-12-31 |  |  | 190 | 190 | 190 | ER | Wind |  | Harbine 115 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-010 |  | DISIS-2023-001 | 05 SOUTHWEST | Sherman | TX | SPS | 2030-08-30 | 2030-12-31 |  |  | 280 | 280 | 280 | ER | Wind |  | Moore Co 230 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-009 |  | DISIS-2023-001 | 04 SOUTHEAST | Sawyer | OK | WFEC | 2028-06-01 | 2028-12-01 |  |  | 250 | 250 | 250 | ER/NR | Battery/Storage |  | Hugo 138 kV Substation | 2023-10-02 |  | DISIS STAGE
GEN-2023-008 |  | DISIS-2023-001 | 05 SOUTHWEST | Hale | TX | SPS | 2030-08-08 | 2030-12-31 |  |  | 75 | 75 | 75 | ER | Solar |  | Tuco - Carlisle 230 kV line | 2023-10-02 |  | DISIS STAGE
GEN-2023-006 |  | DISIS-2023-001 | 03 CENTRAL | Barton, Vernon | MO | NEET | 2029-05-01 | 2029-12-31 |  |  | 202 | 202 | 202 | ER | Wind |  | Wolf Creek- Blackberry 345 kV Line Break | 2023-10-02 |  | DISIS STAGE
GEN-2023-005 |  | DISIS-2023-001 | 05 SOUTHWEST | Lamb | TX | SPS | 2026-09-30 | 2026-12-31 |  |  | 256 | 256 | 256 | ER/NR | Solar |  | Plant X 230kV Substation | 2023-09-25 |  | DISIS STAGE
GEN-2023-001 |  | DISIS-2023-001 | 05 SOUTHWEST | Lea | NM | SPS | 2025-07-15 | 2025-12-31 |  |  | 230 | 230 | 230 | ER/NR | Solar |  | T14 Circuit 115 V Line | 2023-05-26 |  | DISIS STAGE | 10/3/2023 Updated TO from XCEL to SPS. kr
GEN-2022-GR1 |  | Replacement | 04 SOUTHEAST | Hallsville | TX | AEP |  | 2026-03-30 | 2023-03-31 |  | 580 | 580 | 580 | ER | Solar |  | Pirkey 138 kV | 2022-03-23 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2022-241 |  | DISIS-2022-001 | 04 SOUTHEAST | Hempstead | AR | AEP | 2028-03-01 | 2028-09-15 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | John W Turk Jr Power Plant 345 kV sub | 2023-02-28 |  | DISIS STAGE
GEN-2022-240 |  | DISIS-2022-001 | 04 SOUTHEAST | Hempstead | AR | AEP | 2028-03-01 | 2028-09-15 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | John W Turk Jr Power Plant 345 kV sub | 2023-02-28 |  | DISIS STAGE
GEN-2022-239 |  | DISIS-2022-001 | 04 SOUTHEAST | Hempstead | AR | AEP | 2028-03-01 | 2028-09-15 |  |  | 350 | 350 | 350 | ER/NR | Solar |  | John W Turk Jr Power Plant 345 kV sub | 2023-02-28 |  | DISIS STAGE
GEN-2022-238 |  | DISIS-2022-001 | 04 SOUTHEAST | Pottawatomie | OK | OGE | 2028-03-01 | 2028-09-15 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Maud 138 kV substation | 2023-02-28 |  | DISIS STAGE
GEN-2022-237 |  | DISIS-2022-001 | 04 SOUTHEAST | Pottawatomie | OK | OGE | 2028-03-01 | 2028-09-15 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Maud 138 kV substation | 2023-02-28 |  | DISIS STAGE
GEN-2022-235 |  | DISIS-2022-001 | 04 SOUTHEAST | Canadian | OK | WFEC | 2028-03-01 | 2028-09-15 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | El Reno SW 138 kV | 2023-02-28 |  | DISIS STAGE
GEN-2022-234 |  | DISIS-2022-001 | 04 SOUTHEAST | Rogers | OK | AEP | 2028-03-01 | 2028-09-15 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Alluwe Tap â€“ Chelsea 138 kV line | 2023-02-28 |  | DISIS STAGE
GEN-2022-231 |  | DISIS-2022-001 | 04 SOUTHEAST | Logan | OK | OGE | 2028-03-01 | 2028-09-15 |  |  | 166 | 166 | 166 | ER/NR | Solar |  | Crescent to Cottonwood Creek 138 kV Line | 2023-02-28 |  | DISIS STAGE
GEN-2022-219 |  | DISIS-2022-001 | 01 NORTH | Dawson | MT | WAPA | 2026-10-06 | 2026-12-31 |  |  | 350 | 350 | 350 | ER/NR | Solar |  | Belfield 230 kV Substation | 2023-03-02 |  | DISIS STAGE
GEN-2022-214 |  | DISIS-2022-001 | 03 CENTRAL | Sumner | KS | WERE | 2027-05-01 | 2028-12-15 |  |  | 239 | 239 | 239 | ER | Solar |  | Gill - Viola 138 kV Line Break | 2023-03-02 |  | DISIS STAGE
GEN-2022-209 |  | DISIS-2022-001 | 03 CENTRAL | Andrew/Gentry/Dekalb | MO | KCPL | 2027-07-01 | 2027-12-01 |  |  | 600 | 600 | 600 | ER/NR | Hybrid | Solar/Storage | Tap on the Mullen Creek to Ketchum 345 kV Line | 2023-03-01 |  | DISIS STAGE
GEN-2022-208 |  | DISIS-2022-001 | 03 CENTRAL | Andrew/Gentry/Dekalb | MO | KCPL | 2027-07-01 | 2027-12-01 |  |  | 400 | 400 | 400 | ER/NR | Wind |  | Tap on the Mullen Creek to Ketchum 345 kV Line | 2023-03-01 |  | DISIS STAGE
GEN-2022-206 |  | DISIS-2022-001 | 03 CENTRAL | Edwards/Hodgeman | KS | ITCGP | 2027-07-01 | 2027-11-01 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Post Rock - Spearville 345 kV | 2023-03-01 |  | DISIS STAGE
GEN-2022-205 |  | DISIS-2022-001 | 03 CENTRAL | Edwards/Hodgeman | KS | ITCGP | 2027-07-01 | 2027-11-01 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Post Rock - Spearville 345 kV | 2023-03-01 |  | DISIS STAGE
GEN-2022-204 |  | DISIS-2022-001 | 03 CENTRAL | Edwards/Hodgeman | KS | ITCGP | 2027-07-01 | 2027-11-01 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Post Rock - Spearville 345 kV | 2023-03-01 |  | DISIS STAGE
GEN-2022-196 |  | DISIS-2022-001 | 04 SOUTHEAST | Pittsburg | OK | AEP | 2027-05-01 | 2027-12-15 |  |  | 215 | 215 | 215 | ER | Wind |  | Pittsburg 345kV Substation | 2023-02-28 |  | DISIS STAGE
GEN-2022-186 |  | DISIS-2022-001 | 03 CENTRAL | Coffey | KS | WERE | 2026-05-06 | 2026-05-30 |  |  | 684 | 684 | 684 | ER/NR | Solar |  | Wolf Creek - Benton 345 kV Substation | 2023-02-28 |  | DISIS STAGE
GEN-2022-176 |  | DISIS-2022-001 | 04 SOUTHEAST | Nowata | OK | AEP | 2026-04-01 | 2026-10-31 |  |  | 215 | 215 | 215 | ER/NR | Wind |  | Northeastern - Delaware 345 kV transmission line | 2023-02-17 |  | DISIS STAGE
GEN-2022-171 |  | DISIS-2022-001 | 05 SOUTHWEST | Curry | NM | SPS | 2026-08-01 | 2026-12-01 |  |  | 200 | 200 | 200 | ER | Wind |  | Pleasant Hill 230 kV Substation | 2023-02-26 |  | DISIS STAGE
GEN-2022-168 |  | DISIS-2022-001 | 03 CENTRAL | Henry | MO | KCPL | 2027-07-31 | 2027-12-31 |  |  | 380 | 380 | 380 | ER/NR | Solar |  | Silwell - Clinton 161 kV Line | 2023-02-26 |  | DISIS STAGE
GEN-2022-167 |  | DISIS-2022-001 | 04 SOUTHEAST | Tulsa | OK | AEP | 2028-06-30 | 2028-10-01 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Tulsa North - Northeastern 345 kV Line | 2023-02-26 |  | DISIS STAGE
GEN-2022-163 |  | DISIS-2022-001 | 04 SOUTHEAST | Canadian | OK | OGE | 2026-03-15 | 2026-06-15 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Cimarron 345kV Substation | 2023-02-26 |  | DISIS STAGE
GEN-2022-162 |  | DISIS-2022-001 | 02 NEBRASKA | Saline | NE | NPPD | 2025-05-01 | 2025-12-31 |  |  | 118 | 118 | 118 | ER/NR | Wind |  | Friend 115 kV Substation | 2023-02-24 |  | DISIS STAGE
GEN-2022-161 |  | DISIS-2022-001 | 03 CENTRAL | Butler | KS | WERE | 2026-12-31 | 2027-03-01 |  |  | 400 | 400 | 400 | ER | Wind |  | Burns 345kV Substation | 2023-02-24 |  | DISIS STAGE
GEN-2022-160 |  | DISIS-2022-001 | 05 SOUTHWEST | Chaves and Lea | NM | NEET | 2028-05-01 | 2028-12-01 |  |  | 280 | 280 | 280 | ER/NR | Wind |  | Crossroads - Hobbs 345 kV Line | 2023-02-24 |  | DISIS STAGE
GEN-2022-159 |  | DISIS-2022-001 | 05 SOUTHWEST | Chaves and Lea | NM | NEET | 2028-05-01 | 2027-12-01 |  |  | 280 | 280 | 280 | ER/NR | Wind |  | Crossroads - Hobbs 345 kV Line | 2023-02-24 |  | DISIS STAGE
GEN-2022-156 |  | DISIS-2022-001 | 04 SOUTHEAST | Creek | OK | GRDA | 2026-09-15 | 2026-12-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Silver City 138 kV Substation | 2023-02-24 |  | DISIS STAGE
GEN-2022-155 |  | DISIS-2022-001 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2026-09-15 | 2026-12-31 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Horseshoe Lake 138 kV Substation | 2023-02-24 |  | DISIS STAGE
GEN-2022-154 |  | DISIS-2022-001 | 04 SOUTHEAST | Cleveland | OK | WFEC | 2026-09-15 | 2026-12-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Canadian Switch 138 kV Substation | 2023-02-24 |  | DISIS STAGE
GEN-2022-152 |  | DISIS-2022-001 | 02 NEBRASKA | Richardson | NE | NPPD | 2026-05-10 | 2026-08-21 |  |  | 80 | 80 | 80 | ER/NR | Battery/Storage |  | Humboldt 161 kV Substation | 2023-02-23 |  | DISIS STAGE
GEN-2022-150 |  | DISIS-2022-001 | 05 SOUTHWEST | Randall | TX | SPS | 2026-05-10 | 2026-08-21 |  |  | 150 | 171 | 171 | ER/NR | Battery/Storage |  | Randall 115 kV Substation | 2023-02-23 |  | DISIS STAGE
GEN-2022-147 |  | DISIS-2022-001 | 05 SOUTHWEST | Hale | TX | SPS | 2024-02-27 | 2025-04-15 |  |  | 203 | 196 | 203 | ER | Thermal | CTG | Tuco 345kV | 2023-02-21 |  | DISIS STAGE
GEN-2022-145 |  | DISIS-2022-001 | 04 SOUTHEAST | Cluster | OK | AEP | 2027-09-15 | 2027-12-31 |  |  | 195 | 195 | 195 | ER | Battery/Storage |  | Weatherford Jct. to Hinton 138 kV line | 2023-02-21 |  | DISIS STAGE
GEN-2022-144 |  | DISIS-2022-001 | 03 CENTRAL | Jackson | MO | KCPL | 2027-09-15 | 2027-12-31 |  |  | 200 | 210.4 | 210.4 | ER/NR | Battery/Storage |  | Blue Mills BESS 161kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-143 |  | DISIS-2022-001 | 04 SOUTHEAST | Marshall | OK | OGE | 2027-09-15 | 2027-12-31 |  |  | 200 | 210.4 | 210.4 | ER/NR | Battery/Storage |  | Caney Creek 138 kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-142 |  | DISIS-2022-001 | 03 CENTRAL | Clay | MO | KCPL | 2027-09-15 | 2027-12-31 |  |  | 200 | 210.4 | 210.4 | ER/NR | Battery/Storage |  | Shoal Creek 161 kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-139 |  | DISIS-2022-001 | 04 SOUTHEAST | Harrison | TX | AEP | 2027-09-15 | 2027-12-31 |  |  | 300 | 315.7 | 315.7 | ER/NR | Battery/Storage |  | Pirkey 345kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-138 |  | DISIS-2022-001 | 04 SOUTHEAST | Roger | OK | AEP | 2027-09-15 | 2027-12-31 |  |  | 300 | 316.6 | 316.6 | ER/NR | Battery/Storage |  | Tulsa North - Northeast Station 345 kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-137 |  | DISIS-2022-001 | 04 SOUTHEAST | Cleveland | OK | WFEC | 2027-09-15 | 2027-12-31 |  |  | 200 | 210.4 | 210.4 | ER/NR | Battery/Storage |  | Canadian Switchyard 138kV | 2023-02-21 |  | DISIS STAGE
GEN-2022-136 |  | DISIS-2022-001 | 04 SOUTHEAST | Bryan | OK | WFEC | 2027-09-15 | 2027-12-31 |  |  | 200 | 210.5 | 210.5 | ER/NR | Battery/Storage |  | Colbert 138 kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-135 |  | DISIS-2022-001 | 05 SOUTHWEST | Lea | NM | SPS | 2027-09-15 | 2027-12-31 |  |  | 150 | 155.1 | 155.1 | ER/NR | Battery/Storage |  | Taylor Switching Station 115kV | 2023-02-21 |  | DISIS STAGE
GEN-2022-132 |  | DISIS-2022-001 | 04 SOUTHEAST | Caddo | OK | WFEC | 2027-09-15 | 2027-12-31 |  |  | 300 | 315.8 | 315.8 | ER/NR | Battery/Storage |  | Anadarko 138kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-131 |  | DISIS-2022-001 | 03 CENTRAL | Johnson | MO | KCPL | 2027-09-15 | 2027-12-31 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Warrensburg East - Odessa161kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-130 |  | DISIS-2022-001 | 04 SOUTHEAST | Sebastian | AR | OGE | 2027-09-15 | 2027-12-31 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Battlefield BESS 161kV | 2023-02-21 |  | DISIS STAGE
GEN-2022-129 |  | DISIS-2022-001 | 04 SOUTHEAST | Osage | OK | AEP | 2027-09-15 | 2027-12-31 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Webb City Tap - Shidler 138 kV line | 2023-02-21 |  | DISIS STAGE
GEN-2022-128 |  | DISIS-2022-001 | 05 SOUTHWEST | Eddy | NM | SPS | 2027-09-15 | 2027-12-31 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Pecos Interchange 115 kV Substation | 2023-02-21 |  | DISIS STAGE
GEN-2022-114 |  | DISIS-2022-001 | 05 SOUTHWEST | Tillman | OK | AEP | 2027-12-01 | 2027-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Lawton to Oklaunion 345kV Line | 2023-02-16 |  | DISIS STAGE
GEN-2022-113 |  | DISIS-2022-001 | 03 CENTRAL | Newton | MO | EDE | 2026-04-01 | 2027-12-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Tipton Station 161 kV Substation | 2023-02-16 |  | DISIS STAGE
GEN-2022-111 |  | DISIS-2022-001 | 04 SOUTHEAST | Marion | TX | AEP | 2026-06-30 | 2026-09-30 |  |  | 150 | 150 | 150 | ER/NR | Hybrid | Solar/Storage | Wilkes 345 kV Substation | 2023-02-10 |  | DISIS STAGE
GEN-2022-110 |  | DISIS-2022-001 | 04 SOUTHEAST | Coal | OK | AEP | 2026-01-30 | 2026-04-30 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Lehigh 138kV Station | 2023-02-10 |  | DISIS STAGE
GEN-2022-109 |  | DISIS-2022-001 | 05 SOUTHWEST | Lea | NM | SPS | 2026-05-01 | 2026-10-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Hobbs - Yoakum 345 kV transmission line | 2023-01-06 |  | DISIS STAGE
GEN-2022-108 |  | DISIS-2022-001 | 04 SOUTHEAST | DeSoto Parish | LA | AEP | 2027-09-01 | 2027-12-31 |  |  | 100 | 100 | 100 | ER/NR | Solar |  | Tap between 345kV SW Shreveport to Dolet Hills Substations | 2023-01-08 |  | DISIS STAGE
GEN-2022-107 |  | DISIS-2022-001 | 05 SOUTHWEST | Tillman | OK | AEP | 2026-03-01 | 2026-07-31 |  |  | 400 | 400 | 400 | ER/NR | Solar |  | Tap of Oklaunion to Lawton Eastside 345 kV Transmission Line | 2023-01-09 |  | DISIS STAGE
GEN-2022-106 |  | DISIS-2022-001 | 05 SOUTHWEST | Tillman | OK | AEP | 2026-03-01 | 2026-07-31 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Tap of Oklaunion to Lawton Eastside 345 kV Transmission Line | 2023-01-09 |  | DISIS STAGE
GEN-2022-105 |  | DISIS-2022-001 | 05 SOUTHWEST | Tillman | OK | AEP | 2026-03-01 | 2026-07-31 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Tap of Oklaunion to Lawton Eastside 345 kV Transmission Line | 2023-01-09 |  | DISIS STAGE
GEN-2022-104 |  | DISIS-2022-001 | 04 SOUTHEAST | Bryan | OK | WFEC | 2025-11-03 | 2026-02-02 |  |  | 113.078 | 113.078 | 113.078 | ER/NR | Solar |  | Brown - South Coleman Junction 138kV line | 2023-01-26 |  | DISIS STAGE
GEN-2022-103 |  | DISIS-2022-001 | 03 CENTRAL | Christian | MO | EDE | 2026-10-01 | 2027-01-01 |  |  | 74.99 | 74.99 | 74.99 | ER/NR | Battery/Storage |  | Ozark South 161kV | 2023-01-30 |  | DISIS STAGE
GEN-2022-102 |  | DISIS-2022-001 | 03 CENTRAL | Clay | MO | KCPL | 2026-10-01 | 2027-01-01 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Liberty West 161 kV | 2023-01-06 |  | DISIS STAGE
GEN-2022-100 |  | DISIS-2022-001 | 03 CENTRAL | Cooper | MO | KCPL | 2025-08-01 | 2026-10-01 |  |  | 80 | 80 | 80 | ER/NR | Hybrid | Solar/Storage | Overton - Sedalia East 161 kV Substation | 2023-03-24 |  | DISIS STAGE
GEN-2022-098 |  | DISIS-2022-001 | 04 SOUTHEAST | Johnston | OK | OGE | 2024-03-01 | 2024-12-01 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Bison 345kV Substation | 2022-12-06 |  | DISIS STAGE
GEN-2022-094 |  | DISIS-2022-001 | 03 CENTRAL | Osborne | KS | ITCGP | 2028-05-27 | 2028-12-31 |  |  | 250 | 250 | 250 | ER | Wind |  | Postrock to Axtell 345 kV line | 2022-11-15 |  | DISIS STAGE
GEN-2022-093 |  | DISIS-2022-001 | 04 SOUTHEAST | Hempstead | AR | AEP | 2026-10-01 | 2027-04-01 |  |  | 83 | 83 | 83 | ER/NR | Solar |  | Turk - Hope 115 kV line | 2022-11-15 |  | DISIS STAGE
GEN-2022-092 |  | DISIS-2022-001 | 04 SOUTHEAST | Nowata and Craig | OK | AEP | 2026-09-01 | 2026-12-15 |  |  | 299.2 | 299.2 | 299.2 | ER/NR | Wind |  | Neosho-Delaware 345 kV | 2022-11-15 |  | DISIS STAGE
GEN-2022-091 |  | DISIS-2022-001 | 04 SOUTHEAST | McCurtain | OK | AEP | 2026-09-30 | 2026-09-30 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Valiant Substation 138kV | 2022-11-15 |  | DISIS STAGE
GEN-2022-090 |  | DISIS-2022-001 | 04 SOUTHEAST | McCurtain | OK | AEP | 2026-09-30 | 2026-09-30 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Valiant Substation 138kV | 2022-11-15 |  | DISIS STAGE
GEN-2022-089 |  | DISIS-2022-001 | 04 SOUTHEAST | Little River | AR | AEP | 2026-09-30 | 2026-09-30 |  |  | 74.99 | 74.99 | 74.99 | ER/NR | Battery/Storage |  | South Foreman 138 kV Substation | 2022-11-15 |  | DISIS STAGE
GEN-2022-088 |  | DISIS-2022-001 | 04 SOUTHEAST | Little River | AR | AEP | 2026-09-30 | 2026-09-30 |  |  | 74.99 | 74.99 | 74.99 | ER/NR | Solar |  | South Foreman 138 kV Substation | 2022-11-15 |  | DISIS STAGE
GEN-2022-085 |  | DISIS-2022-001 | 04 SOUTHEAST | Ofuskee and Hughes | OK | OGE | 2025-09-01 | 2025-12-31 |  |  | 241.4 | 241.4 | 241.4 | ER/NR | Wind |  | Seminole to Muskogee 345kV Substation | 2022-11-05 |  | DISIS STAGE
GEN-2022-083 |  | DISIS-2022-001 | 01 NORTH | Williams | ND | BEPC | 2025-06-01 | 2025-02-01 |  |  | 250 | 250 | 265 | ER | Thermal | CTG | Judson Substation 345 kV | 2022-10-21 |  | DISIS STAGE
GEN-2022-082 |  | DISIS-2022-001 | 05 SOUTHWEST | Hale | TX | SPS | 2025-04-01 | 2028-12-31 |  |  | 180 | 180 | 180 | ER/NR | Solar |  | Tuco - Carlisle 230 kV line | 2022-09-22 |  | DISIS STAGE
GEN-2022-081 |  | DISIS-2022-001 | 03 CENTRAL | Washington | KS | SUNC | 2025-04-01 | 2027-11-29 |  |  | 218 | 218 | 218 | ER/NR | Battery/Storage |  | Clifton 115kV Substation | 2022-09-22 |  | DISIS STAGE
GEN-2022-080 |  | DISIS-2022-001 | 03 CENTRAL | Cedar | MO | EDE | 2026-01-01 | 2027-10-31 |  |  | 96 | 96 | 96 | ER | Battery/Storage |  | Dadeville East - Bolivar South 161kV | 2022-09-22 |  | DISIS STAGE
GEN-2022-079 |  | DISIS-2022-001 | 03 CENTRAL | Cedar | MO | EDE | 2026-01-01 | 2027-10-31 |  |  | 192 | 192 | 192 | ER | Solar |  | Dadeville East - Bolivar South 161kV | 2022-09-22 |  | DISIS STAGE
GEN-2022-077 |  | DISIS-2022-001 | 02 NEBRASKA | Chase | NE | NPPD | 2026-01-01 | 2026-12-01 |  |  | 255 | 255 | 255 | ER/NR | Solar |  | Enders 115 kV Substation | 2022-09-21 |  | DISIS STAGE
GEN-2022-076 |  | DISIS-2022-001 | 03 CENTRAL | Stevens | KS | SPS | 2026-03-15 | 2026-11-15 |  |  | 500 | 500 | 500 | ER/NR | Solar |  | Carpenter 345 kV Substation | 2022-09-07 |  | DISIS STAGE
GEN-2022-075 |  | DISIS-2022-001 | 03 CENTRAL | Ellis | KS | ITCGP | 2027-09-03 | 2027-11-19 |  |  | 175 | 175 | 175 | ER/NR | Solar |  | Tap on the Spearville - Post Rock 345kV line | 2022-09-02 |  | DISIS STAGE
GEN-2022-074 |  | DISIS-2022-001 | 04 SOUTHEAST | Eufaula, McIntosh | OK | WFEC | 2025-03-01 | 2025-10-31 |  |  | 220.86 | 220.86 | 220.86 | ER/NR | Wind |  | Hanna 138kV Substation | 2022-09-06 |  | DISIS STAGE
GEN-2022-073 |  | DISIS-2022-001 | 03 CENTRAL | Kay | MO | KCPL | 2025-04-01 | 2027-12-31 |  |  | 300 | 300 | 300 | ER/NR | Battery/Storage |  | Nashua 161 kV Substation | 2022-09-02 |  | DISIS STAGE
GEN-2022-072 |  | DISIS-2022-001 | 04 SOUTHEAST | Mayes | OK | GRDA | 2025-07-01 | 2028-12-31 |  |  | 181 | 181 | 181 | ER/NR | Solar |  | Grand River Dam - Claremore 161 kV Line | 2022-08-12 |  | DISIS STAGE
GEN-2022-071 |  | DISIS-2022-001 | 04 SOUTHEAST | Pittsburg | OK | AEP | 2025-11-03 | 2026-02-02 |  |  | 90.824 | 90.824 | 90.824 | ER/NR | Solar |  | Talawanda to Canadian River 138 kV Line Tap | 2022-08-12 |  | DISIS STAGE
GEN-2022-068 |  | DISIS-2022-001 | 01 NORTH | Hyde | SD | BEPC | 2026-07-01 | 2026-11-01 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Chappelle Creek 345 kV | 2022-08-11 |  | DISIS STAGE
GEN-2022-065 |  | DISIS-2022-001 | 03 CENTRAL | Edwards | KS | SUNC | 2027-09-04 | 2027-11-19 |  |  | 145 | 145 | 145 | ER/NR | Solar |  | tap on Arthur Mullergreen-Spearville 230 kV line | 2022-07-25 |  | DISIS STAGE
GEN-2022-062 |  | DISIS-2022-001 | 03 CENTRAL | Bourbon | KS | NEET | 2025-04-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Wolf Creek- Blackberry 345 kV | 2022-07-08 |  | DISIS STAGE
GEN-2022-058 |  | DISIS-2022-001 | 03 CENTRAL | Benton | AR | EDE | 2028-07-01 | 2028-12-31 |  |  | 180 | 180 | 180 | ER/NR | Solar |  | Noel Southwest - Decatur 161 kV line tap | 2022-06-23 |  | DISIS STAGE
GEN-2022-055 |  | DISIS-2022-001 | 04 SOUTHEAST | Grady | OK | WFEC | 2025-04-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Sunshine North to Anadarko 138 kV | 2022-06-23 |  | DISIS STAGE
GEN-2022-054 |  | DISIS-2022-001 | 03 CENTRAL | Bourbon | KS | NEET | 2025-04-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Wolf Creek - Blackberry 345 kV Tap | 2022-06-23 |  | DISIS STAGE
GEN-2022-048 |  | DISIS-2022-001 | 04 SOUTHEAST | Woodward | OK | WFEC | 2025-04-01 | 2025-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Mooreland 138 kV | 2022-06-23 |  | DISIS STAGE
GEN-2022-042 |  | DISIS-2022-001 | 04 SOUTHEAST | Carter | OK | OGE | 2025-04-01 | 2025-12-31 |  |  | 174 | 174 | 174 | ER/NR | Solar |  | Sunnyside to Pooleville 138 kV line | 2022-06-23 |  | DISIS STAGE
GEN-2022-041 |  | DISIS-2022-001 | 03 CENTRAL | Cowley | KS | GHP | 2025-04-01 | 2025-12-31 |  |  | 100 | 100 | 100 | ER/NR | Solar |  | Tie Substation 69 kV | 2022-06-29 |  | DISIS STAGE
GEN-2022-038 |  | DISIS-2022-001 | 04 SOUTHEAST | Harrison | TX | AEP | 2025-04-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Longwood to Scottville 138 kV line | 2022-06-23 |  | DISIS STAGE
GEN-2022-026 |  | DISIS-2022-001 | 03 CENTRAL | Decatur | KS | SUNC | 2024-06-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Tap of Mingo--Red Willow 345kV line | 2022-06-08 |  | DISIS STAGE
GEN-2022-025 |  | DISIS-2022-001 | 03 CENTRAL | Decatur | KS | SUNC | 2024-06-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Tap of Mingo--Red Willow 345kV line | 2022-06-08 |  | DISIS STAGE
GEN-2022-024 |  | DISIS-2022-001 | 03 CENTRAL | Bourbon | KS | WERE | 2024-06-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Tap of Neosho - LaCygne 345 kV Line | 2022-06-10 |  | DISIS STAGE
GEN-2022-021 |  | DISIS-2022-001 | 05 SOUTHWEST | Tillman | OK | AEP | 2024-06-01 | 2025-12-31 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Tap of Oklaunion - Lawton Eastside 345 kV line | 2022-06-08 |  | DISIS STAGE
GEN-2022-019 |  | DISIS-2022-001 | 05 SOUTHWEST | Tillman | OK | AEP | 2024-06-01 | 2025-12-31 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Tap of Oklaunion - Lawton Eastside 345 kV line | 2022-06-08 |  | DISIS STAGE
GEN-2022-017 |  | DISIS-2022-001 | 04 SOUTHEAST | Woodward | OK | OGE | 2024-06-06 | 2025-12-31 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Woodward 345kV Substation | 2022-06-08 |  | DISIS STAGE
GEN-2022-016 |  | DISIS-2022-001 | 04 SOUTHEAST | Woodward | OK | OGE | 2024-06-01 | 2025-12-31 |  |  | 288 | 288 | 288 | ER/NR | Solar |  | Woodward 345kV Substation | 2022-06-08 |  | DISIS STAGE
GEN-2022-015 |  | DISIS-2022-001 | 03 CENTRAL | Decatur | KS | SUNC | 2024-06-01 | 2025-12-31 |  |  | 270 | 270 | 270 | ER/NR | Solar |  | Tap of Mingo - Red Willow 345 kV Line | 2022-06-08 |  | DISIS STAGE
GEN-2022-013 |  | DISIS-2022-001 | 03 CENTRAL | Bourbon | KS | WERE | 2024-06-01 | 2025-12-31 |  |  | 300 | 300 | 300 | ER/NR | Solar |  | Tap of Neosho - LaCygne 345 kV Line | 2022-06-08 |  | DISIS STAGE
GEN-2022-012 |  | DISIS-2022-001 | 04 SOUTHEAST | Woodward | OK | OGE | 2024-06-01 | 2025-12-31 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Woodward 345 kV Substation | 2022-06-08 |  | DISIS STAGE
GEN-2022-011 |  | DISIS-2022-001 | 05 SOUTHWEST | Tillman | OK | AEP | 2024-06-01 | 2025-12-31 |  |  | 374 | 374 | 374 | ER/NR | Solar |  | Tap of Oklaunion - Lawton Eastside 345 kV line | 2022-06-03 |  | DISIS STAGE
GEN-2022-010 |  | DISIS-2022-001 | 01 NORTH | Williams | ND | BEPC | 2023-07-01 | 2025-02-01 |  |  | 250 | 250 | 250 | ER | Thermal |  | Judson Substation 345 kV | 2022-05-26 |  | DISIS STAGE
GEN-2022-009 |  | DISIS-2022-001 | 01 NORTH | Williams | ND | BEPC | 2023-07-01 | 2025-02-01 |  |  | 125 | 125 | 125 | ER | Thermal |  | Judson Substation 345 kV | 2022-05-26 |  | DISIS STAGE
GEN-2022-007 |  | DISIS-2022-001 | 03 CENTRAL | Lyon | KS | WERE | 2025-05-01 | 2026-10-31 |  |  | 135 | 135 | 135 | ER/NR | Solar |  | Lang - Reading 115 kV Transmission Line | 2022-05-26 |  | DISIS STAGE
GEN-2022-006 |  | DISIS-2022-001 | 03 CENTRAL | Labette | KS | WERE | 2025-04-01 | 2026-10-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Neosho - N345 161 kV Substation | 2022-05-25 |  | DISIS STAGE
GEN-2022-005 |  | DISIS-2022-001 | 03 CENTRAL | Labette | KS | WERE | 2025-04-01 | 2026-10-31 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | Northeast Parsons 138kV Substation | 2022-05-25 |  | DISIS STAGE
GEN-2022-004 |  | DISIS-2022-001 | 03 CENTRAL | Sedgwick | KS | WERE | 2025-08-01 | 2026-10-31 |  |  | 33 | 33 | 33 | ER/NR | Solar |  | Murray Gill 138 kV Substation | 2022-05-26 |  | DISIS STAGE
GEN-2022-001 |  | DISIS-2022-001 | 04 SOUTHEAST | Rogers | OK | AEP | 2026-09-26 | 2027-01-07 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Catoosa 138 kV Substation | 2021-12-30 |  | DISIS STAGE
GEN-2021-SR9 |  | Surplus |  | Kansas City | MO | KCPL |  | 2023-01-11 |  |  | 10 | 10 | 10 | ER/NR | Solar |  | Hawthorn Power Plant | 2021-08-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2021-SR8 |  | Surplus | 03 CENTRAL | Harper | KS | WERE | 2023-11-01 | 2023-11-01 |  |  | 42 | 42 | 42 | ER | Solar |  | Viola 345kV | 2021-05-13 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2021-108 |  | DISIS-2021-001 | 02 NEBRASKA | Cass | NE | OPPD | 2025-05-27 | 2025-05-14 |  |  | 182.25 | 182.25 | 182.25 | ER/NR | Solar |  | OPPD 345KV Cass County Substation | 2021-05-20 |  | DISIS STAGE
GEN-2021-107 |  | DISIS-2021-001 | 03 CENTRAL | Pottawatomie | KS | WERE | 2026-10-01 | 2026-12-01 |  |  | 201.6 | 201.6 | 201.6 | ER | Solar |  | Evergy 345kV Jeffrey Energy Center | 2021-05-20 |  | DISIS STAGE
GEN-2021-103 |  | DISIS-2021-001 | 03 CENTRAL | Johnson | KS | WERE | 2025-08-01 | 2026-09-01 |  |  | 150 | 150 | 150 | ER/NR | Battery/Storage |  | Evergy's Atlantic Substation115kV bus | 2021-05-25 |  | DISIS STAGE
GEN-2021-101 |  | DISIS-2021-001 | 03 CENTRAL | Douglas | KS | WERE | 2025-08-01 | 2025-09-01 |  |  | 159 | 159 | 159 | ER/NR | Solar |  | Evergy's Midland Substation 115kV bus | 2021-05-25 |  | DISIS STAGE
GEN-2021-098 |  | DISIS-2021-001 | 04 SOUTHEAST | Dewey | OK | OGE | 2026-07-01 | 2026-12-31 |  |  | 160 | 160 | 160 | ER/NR | Hybrid | Wind/Storage | Dewey District 138 kV Substation | 2021-05-24 |  | DISIS STAGE
GEN-2021-096 |  | DISIS-2021-001 | 03 CENTRAL | Coffey | KS | WERE | 2026-05-01 | 2027-12-01 |  |  | 500 | 500 | 500 | ER/NR | Solar |  | Wolf Creek - Benton 345 kV | 2021-04-29 |  | DISIS STAGE
GEN-2021-090 |  | DISIS-2021-001 | 05 SOUTHWEST | Yoakum | TX | SPS | 2022-06-15 | 2028-06-30 |  |  | 400 | 400 | 400 | ER/NR | Hybrid | Solar/Storage | Yoakum 345kV Substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-088 |  | DISIS-2021-001 | 04 SOUTHEAST | Cleveland | OK | OGE | 2025-12-21 | 2027-01-07 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Cedar Lane - Canadian 138 kV Transmission Line | 2021-04-29 |  | DISIS STAGE
GEN-2021-077 |  | DISIS-2021-001 | 03 CENTRAL | Pettis | MO | GMO | 2025-07-01 | 2027-12-31 |  |  | 95 | 95 | 95 | ER/NR | Hybrid | Solar/Storage | Windsor to AEC Sedalia 161 kV | 2021-04-30 |  | DISIS STAGE
GEN-2021-076 |  | DISIS-2021-001 | 03 CENTRAL | Ellis | KS | ITCGP | 2026-07-01 | 2026-12-31 |  |  | 113 | 113 | 113 | ER/NR | Solar |  | ITC Post Rock 345 kV Substation | 2021-05-13 |  | DISIS STAGE
GEN-2021-075 |  | DISIS-2021-001 | 04 SOUTHEAST | Camp | TX | AEP | 2026-07-01 | 2027-12-31 |  |  | 300 | 300 | 300 | ER/NR | Hybrid | Solar/Storage | CAMPCOR4 138kV Substation | 2021-05-19 |  | DISIS STAGE
GEN-2021-070 |  | DISIS-2021-001 | 03 CENTRAL | Hodgeman and Ford | KS | SUNC | 2027-08-01 | 2027-12-01 |  |  | 504 | 504 | 504 | ER | Wind |  | SUNC Spearville - Holcomb 345kV | 2021-04-26 |  | DISIS STAGE
GEN-2021-069 |  | DISIS-2021-001 | 03 CENTRAL | Hodgeman and Ford | KS | SUNC | 2027-08-01 | 2027-12-01 |  |  | 249.6 | 249.6 | 249.6 | ER | Wind |  | SUNC Spearville - Holcomb 345kV | 2021-04-26 |  | DISIS STAGE
GEN-2021-068 |  | DISIS-2021-001 | 03 CENTRAL | Hodgeman and Ford | KS | SUNC | 2025-09-01 | 2027-12-01 |  |  | 249.6 | 249.6 | 249.6 | ER | Wind |  | SUNC Spearville - Holcomb 345kV | 2021-04-26 |  | DISIS STAGE
GEN-2021-064 |  | DISIS-2021-001 | 04 SOUTHEAST | Caddo | OK | AEP | 2025-10-25 | 2027-12-31 |  |  | 100 | 100 | 100 | ER/NR | Hybrid | Solar/Storage | Carnegie South 138kV | 2021-04-28 |  | DISIS STAGE
GEN-2021-063 |  | DISIS-2021-001 | 04 SOUTHEAST | McCurtain | OK | AEP | 2025-10-25 | 2027-12-31 |  |  | 155 | 155 | 155 | ER/NR | Hybrid | Solar/Storage | Craig JCT 138kV | 2021-04-28 |  | DISIS STAGE
GEN-2021-057 |  | DISIS-2021-001 | 02 NEBRASKA | Antelope | NE | NPPD |  | 2027-12-31 |  |  | 300 | 300 | 300 | ER | Wind |  | Antelope 345kV substation | 2021-04-29 |  | DISIS STAGE
GEN-2021-056 |  | DISIS-2021-001 | 03 CENTRAL | Harper and Kingman | KS | WERE |  | 2028-12-31 |  |  | 300 | 300 | 300 | ER | Wind |  | Viola 345kV Substation | 2021-04-29 |  | DISIS STAGE
GEN-2021-053 |  | DISIS-2021-001 | 04 SOUTHEAST | Muskogee | OK | OGE |  | 2026-05-30 |  |  | 300 | 300 | 300 | ER | Solar |  | Pecan Creek 345 kV Substation | 2021-04-29 |  | DISIS STAGE
GEN-2021-052 |  | DISIS-2021-001 | 04 SOUTHEAST | Muskogee | OK | OGE |  | 2026-05-30 |  |  | 75 | 75 | 75 | ER | Battery/Storage |  | Pecan Creek 345kV substation | 2021-04-29 |  | DISIS STAGE
GEN-2021-051 |  | DISIS-2021-001 | 03 CENTRAL | Henry | MO | KCPL | 2025-07-31 | 2027-09-01 |  |  | 75 | 75 | 75 | ER/NR | Battery/Storage |  | 161kV Stilwell-Clinton Line | 2021-04-30 |  | DISIS STAGE
GEN-2021-050 |  | DISIS-2021-001 | 03 CENTRAL | Henry | MO | KCPL | 2025-07-31 | 2028-09-01 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | 161kV Stilwell-Clinton Line | 2021-04-30 |  | DISIS STAGE
GEN-2021-049 |  | DISIS-2021-001 | 02 NEBRASKA | Lancaster | NE | LES | 2025-07-31 | 2027-09-01 |  |  | 225 | 225 | 225 | ER/NR | Solar |  | Wagener 115kV Substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-048 |  | DISIS-2021-001 | 02 NEBRASKA | Lancaster | NE | LES | 2025-07-31 | 2027-09-01 |  |  | 75 | 75 | 75 | ER/NR | Battery/Storage |  | Wagener 115kV Substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-047 |  | DISIS-2021-001 | 04 SOUTHEAST | Mayes | OK | GRDA | 2026-03-01 | 2029-09-30 |  |  | 250 | 250 | 250 | ER | Solar |  | Tulsa (Bus #509852) - Igloo (Bus #513596) 345kV line | 2021-04-29 |  | DISIS STAGE
GEN-2021-043 |  | DISIS-2021-001 | 02 NEBRASKA | Lancaster | NE | LES | 2026-02-01 | 2028-05-31 |  |  | 250 | 250 | 250 | ER | Battery/Storage |  | 8000 SW 12th (Rokeby) Station, 115kV Bus | 2021-04-30 |  | DISIS STAGE
GEN-2021-042 |  | DISIS-2021-001 | 03 CENTRAL | Jackson | MO | INDN | 2025-02-01 | 2028-06-01 |  |  | 50 | 100 | 100 | ER/NR | Battery/Storage |  | Independence Power & Light, Blue Valley Substation, 161kV Bus | 2021-04-30 |  | DISIS STAGE
GEN-2021-041 |  | DISIS-2021-001 | 04 SOUTHEAST | Canadian | OK | OGE | 2025-02-01 | 2026-06-01 |  |  | 100 | 100.657 | 100.657 | ER/NR | Battery/Storage |  | Mustang 138kV Substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-040 |  | DISIS-2021-001 | 02 NEBRASKA | Cass | NE | OPPD | 2025-02-01 | 2029-11-30 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | OPPD District, Cass County Power Plant Substation, 345kV Bus | 2021-04-30 |  | DISIS STAGE
GEN-2021-039 |  | DISIS-2021-001 | 02 NEBRASKA | Douglas | NE | OPPD | 2025-02-01 | 2030-05-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | New 161kV substation looping in OPPD 161kV lines S1211 to S1220 and S1211 to S1299 | 2021-04-30 |  | DISIS STAGE
GEN-2021-038 |  | DISIS-2021-001 | 04 SOUTHEAST | Titus | TX | AEP | 2026-02-01 | 2028-05-31 |  |  | 200 | 201.32 | 201.32 | ER/NR | Battery/Storage |  | Welsh 345kV Substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-036 |  | DISIS-2021-001 | 04 SOUTHEAST | Little River | AR | AEP | 2025-10-29 | 2027-12-31 |  |  | 204.12 | 204.12 | 204.12 | ER/NR | Solar |  | Craig to Patterson 138 kV Transmission Line | 2021-05-14 |  | DISIS STAGE
GEN-2021-035 |  | DISIS-2021-001 | 03 CENTRAL | Grant | KS | SUNC | 2025-10-29 | 2026-12-31 |  |  | 113 | 113 | 113 | ER | Solar |  | Tap Sunflower Santana 115kV Transmission Line | 2021-05-14 |  | DISIS STAGE
GEN-2021-034 |  | DISIS-2021-001 | 02 NEBRASKA | Lancaster | NE | LES | 2027-10-31 | 2027-12-31 |  |  | 113 | 113 | 113 | ER | Solar |  | Rokeby 115 kV Substation | 2021-05-13 |  | DISIS STAGE
GEN-2021-033 |  | DISIS-2021-001 | 04 SOUTHEAST | Franklin | AR | OGE | 2027-07-01 | 2027-12-31 |  |  | 204.12 | 204.12 | 204.12 | ER | Solar |  | Branch 161kV Substation | 2021-05-14 |  | DISIS STAGE
GEN-2021-030 |  | DISIS-2021-001 | 03 CENTRAL | Linn KS and Bates MO | KS | KCPL | 2026-09-28 | 2026-12-31 |  |  | 510.3 | 510.3 | 510.3 | ER | Solar |  | Evergy Tap the La Cygne to Stillwel 345 kV Line | 2021-05-14 |  | DISIS STAGE
GEN-2021-029 |  | DISIS-2021-001 | 03 CENTRAL | Linn KS and Bates MO | KS | KCPL | 2026-07-01 | 2026-12-31 |  |  | 253.8 | 253.8 | 253.8 | ER | Battery/Storage |  | Evergy Tap the La Cygne to Stillwel 345 kV Line | 2021-05-14 |  | DISIS STAGE
GEN-2021-027 |  | DISIS-2021-001 | 02 NEBRASKA | Lancaster | NE | NPPD | 2026-07-01 | 2026-12-31 |  |  | 102.06 | 102.06 | 102.06 | ER | Solar |  | Olive Creek 115 kV Substation | 2021-05-14 |  | DISIS STAGE
GEN-2021-025 |  | DISIS-2021-001 | 04 SOUTHEAST | Woodward | OK | WFEC | 2025-10-31 | 2026-12-01 |  |  | 203.04 | 203.04 | 203.04 | ER | Wind |  | Western Farmers 138kV Mooreland Substation | 2021-05-14 |  | DISIS STAGE
GEN-2021-023 |  | DISIS-2021-001 | 03 CENTRAL | Grant | KS | WERE | 2026-09-30 | 2026-11-30 |  |  | 306.18 | 306.18 | 306.18 | ER | Solar |  | Wild Plains 345kV Substation | 2021-05-14 |  | DISIS STAGE
GEN-2021-021 |  | DISIS-2021-001 | 03 CENTRAL | Stevens | KS | SPS | 2026-09-01 | 2027-12-31 |  |  | 150 | 150 | 150 | ER | Wind |  | Carpenter 345 kV Substation | 2021-04-20 |  | DISIS STAGE
GEN-2021-019 |  | DISIS-2021-001 | 04 SOUTHEAST | Noble | OK | OGE | 2027-04-01 | 2028-12-31 |  |  | 74.9 | 75.89 | 75.89 | ER/NR | Battery/Storage |  | Sooner 345 kV | 2021-04-30 |  | DISIS STAGE
GEN-2021-018 |  | DISIS-2021-001 | 04 SOUTHEAST | Noble | OK | OGE | 2027-04-01 | 2028-12-31 |  |  | 231 | 235.35 | 235.35 | ER | Solar |  | Sooner 345 kV | 2021-04-30 |  | DISIS STAGE
GEN-2021-017 |  | DISIS-2021-001 | 03 CENTRAL | Cloud and Mitchell | KS | ITCGP | 2025-04-01 | 2027-12-31 |  |  | 37.5 | 37.5 | 37.5 | ER | Wind |  | Elm Creek 345 kV interconnection substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-016 |  | DISIS-2021-001 | 04 SOUTHEAST | Johnston and Murray | OK | AEP | 2025-04-01 | 2029-12-31 |  |  | 250 | 250 | 250 | ER | Wind |  | Sunnyside-Johnston 345 kV | 2021-04-30 |  | DISIS STAGE
GEN-2021-015 |  | DISIS-2021-001 | 04 SOUTHEAST | Ellis | OK | OGE | 2027-04-01 | 2028-12-01 |  |  | 74.9 | 75.91 | 75.91 | ER | Solar |  | Bobcat 345 kV interconnection substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-014 |  | DISIS-2021-001 | 04 SOUTHEAST | Beckham | OK | OGE | 2027-04-01 | 2029-12-31 |  |  | 208 | 233.98 | 233.98 | ER | Solar |  | Border 345 kV interconnection substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-012 |  | DISIS-2021-001 | 04 SOUTHEAST | Beckham | OK | OGE | 2023-11-15 | 2029-12-31 |  |  | 203 | 227 | 227 | ER | Battery/Storage |  | Border 345 kV interconnection substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-010 |  | DISIS-2021-001 | 04 SOUTHEAST | Beckham | OK | OGE | 2027-04-01 | 2029-12-31 |  |  | 208 | 233.98 | 233.98 | ER | Solar |  | Border 345 kV interconnection substation | 2021-04-30 |  | DISIS STAGE
GEN-2021-008 |  | DISIS-2021-001 | 01 NORTH | McKenzie | ND | BEPC | 2026-05-09 | 2030-10-19 |  |  | 200 | 200 | 200 | ER/NR | Solar |  | 345kV Bus at BEPC Patent Gate Substation, McKenzie County, ND | 2021-05-10 |  | DISIS STAGE
GEN-2021-006 |  | DISIS-2021-001 | 03 CENTRAL | Labette | KS | WERE | 2025-10-01 | 2026-02-01 |  |  | 300 | 300 | 300 | ER/NR | Battery/Storage |  | Neosho 345kV substation in Labette County, KS | 2021-05-07 |  | DISIS STAGE
GEN-2021-005 |  | DISIS-2021-001 | 03 CENTRAL | Saline | KS | WERE | 2024-11-01 | 2025-03-01 |  |  | 350 | 350 | 350 | ER/NR | Battery/Storage |  | Summit 345 kV substation in Saline County, KS | 2021-05-07 |  | DISIS STAGE
GEN-2021-001 |  | DISIS-2021-001 | 04 SOUTHEAST | Bryan | OK | OGE | 2024-09-25 | 2027-12-24 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | 138kV Brown Substation | 2020-12-29 |  | DISIS STAGE
GEN-2020-SR2 |  | Surplus | 04 SOUTHEAST | Johnston | OK | OGE | 2021-12-01 | 2026-03-31 |  |  | 100 | 100 | 100 | ER/NR | Battery/Storage |  | Brown 138kV | 2020-08-04 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2020-094 |  | DISIS-2020-001 | 02 NEBRASKA | Syracuse | NE | OPPD | 2023-04-02 | 2026-12-24 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Neb. City - 103rd & Rokeby 345 kV | 2020-04-30 |  | DISIS STAGE
GEN-2020-092 |  | DISIS-2020-001 | 04 SOUTHEAST | Mayes County | OK | AEP | 2025-11-02 | 2026-11-19 |  |  | 100 | 100 | 100 | ER/NR | Solar |  | Pryor Junction - Midwest Carbide 138kV line | 2020-04-30 |  | DISIS STAGE
GEN-2020-091 |  | DISIS-2020-001 | 01 NORTH | McKenzie | ND | BEPC | 2025-11-02 | 2026-11-19 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Patent Gate Substation 345 kV | 2020-04-30 |  | DISIS STAGE
GEN-2020-090 |  | DISIS-2020-001 | 03 CENTRAL | Bourbon | KS | WERE | 2026-04-01 | 2026-12-01 |  |  | 204.3 | 204.3 | 204.3 | ER/NR | Battery/Storage |  | Wolf Creek - Blackberry 345 kV Substation | 2020-04-27 |  | DISIS STAGE
GEN-2020-088 |  | DISIS-2020-001 | 03 CENTRAL | Jasper | MO | EDE | 2022-11-30 | 2025-12-31 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | La Russell 161 kV Substation | 2020-04-30 |  | DISIS STAGE
GEN-2020-087 |  | DISIS-2020-001 | 04 SOUTHEAST | Comanche | OK | AEP | 2023-05-01 | 2026-10-01 |  |  | 500 | 500 | 500 | ER/NR | Solar |  | Cimmarron to Lawton 345 kV Line | 2020-04-23 |  | DISIS STAGE
GEN-2020-085 |  | DISIS-2020-001 | 04 SOUTHEAST | Carter | OK | AEP | 2023-04-02 | 2026-10-01 |  |  | 500 | 500 | 500 | ER/NR | Solar |  | Lawton to Sunnyside 345 kV Line | 2020-04-23 |  | DISIS STAGE
GEN-2020-084 |  | DISIS-2020-001 | 02 NEBRASKA | Burt | NE | OPPD | 2022-04-01 | 2026-10-31 |  |  | 350 | 350 | 350 | ER/NR | Solar |  | Raun - Fort Calhoun 345 kV | 2020-04-30 |  | DISIS STAGE
GEN-2020-083 |  | DISIS-2020-001 | 01 NORTH | Fairview | MT | WAPA | 2024-10-01 | 2026-12-01 |  |  | 74.5 | 74.5 | 74.5 | ER/NR | Hybrid | Solar/Storage | Fairview 115kV Substation | 2020-04-30 |  | DISIS STAGE
GEN-2020-081 |  | DISIS-2020-001 | 04 SOUTHEAST | Rusk | TX | AEP | 2022-05-01 | 2028-06-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Tenaska Switching Substation 345kV | 2020-04-30 |  | DISIS STAGE
GEN-2020-079 |  | DISIS-2020-001 | 03 CENTRAL | Cherokee | KS | EDE | 2025-07-01 | 2025-12-31 |  |  | 225 | 225 | 225 | ER/NR | Hybrid | Solar/Storage | Riverton-Neosho 161kV line | 2020-04-30 |  | DISIS STAGE
GEN-2020-078 |  | DISIS-2020-001 | 02 NEBRASKA | Washington | NE | OPPD | 2022-11-30 | 2025-12-31 |  |  | 100 | 100 | 100 | ER/NR | Solar |  | Substation 1226 to Substation 1237, 161kV Tap | 2020-04-30 |  | DISIS STAGE
GEN-2020-075 |  | DISIS-2020-001 | 04 SOUTHEAST | Comanche | OK | AEP | 2023-05-01 | 2026-10-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Cimmarron to Lawton 345 kV Line | 2020-04-28 |  | DISIS STAGE
GEN-2020-074 |  | DISIS-2020-001 | 04 SOUTHEAST | Carter | OK | AEP | 2023-03-31 | 2026-10-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Lawton to Sunnyside 345 kV Substation | 2020-04-28 |  | DISIS STAGE
GEN-2020-073 |  | DISIS-2020-001 | 03 CENTRAL | Franklin | KS | KCPL | 2025-07-01 | 2027-12-01 |  |  | 150 | 150 | 150 | ER/NR | Hybrid | Solar/Storage | SE Ottawa to Pleasant Valley 161kV | 2020-04-30 |  | DISIS STAGE
GEN-2020-072 |  | DISIS-2020-001 | 03 CENTRAL | Windsor | MO | GMO | 2025-07-01 | 2027-12-01 |  |  | 150 | 150 | 150 | ER/NR | Hybrid | Solar/Storage | Windsor to AEC Sedalia 161 kV line | 2020-04-30 |  | DISIS STAGE
GEN-2020-069 |  | DISIS-2020-001 | 02 NEBRASKA | Cherry | NE | NPPD | 2023-11-30 | 2025-11-30 |  |  | 52.85 | 52.85 | 52.85 | ER/NR | Wind |  | Cody to Valentine 115kV line | 2020-04-24 |  | DISIS STAGE
GEN-2020-068 |  | DISIS-2020-001 | 05 SOUTHWEST | Terry & Hockley | TX | SPS | 2024-11-01 | 2026-12-01 |  |  | 400 | 400 | 400 | ER | Solar |  | Tuco to Yoakum 345kV line | 2020-04-29 |  | DISIS STAGE
GEN-2020-067 |  | DISIS-2020-001 | 05 SOUTHWEST | Terry & Hockley | TX | SPS | 2024-11-01 | 2026-12-01 |  |  | 352.5 | 352.5 | 352.5 | ER | Wind |  | Tuco to Yoakum 345kV line | 2020-04-24 |  | DISIS STAGE
GEN-2020-065 |  | DISIS-2020-001 | 05 SOUTHWEST | Gaines | NM | SPS | 2025-12-01 | 2028-05-15 |  |  | 1003 | 912.3 | 1003 | ER | Thermal | Combined Cycle | Hobbs-Andrews 345 kV Line | 2020-04-30 |  | DISIS STAGE
GEN-2020-064 |  | DISIS-2020-001 | 03 CENTRAL | Joplin | MO | EDE | 2020-10-01 | 2021-05-17 |  |  | 64 | 36 | 64 | ER/NR | Thermal | CT | 4544 Stateline CC 161kV Substation | 2020-04-22 |  | DISIS STAGE
GEN-2020-062 |  | DISIS-2020-001 | 05 SOUTHWEST | Curry | NM | SPS | 2023-11-01 | 2028-04-01 |  |  | 256 | 256 | 256 | ER | Solar |  | OASIS 230kV Substation | 2020-04-29 |  | DISIS STAGE
GEN-2020-061 |  | DISIS-2020-001 | 03 CENTRAL | Pleasant Hill | MO | GMO | 2021-05-01 | 2022-05-01 |  |  | 29 | 29 | 21 | ER/NR | Thermal | Gas | Pleasant Hill 345/161/69 kV Substation | 2020-04-28 |  | DISIS STAGE
GEN-2020-060 |  | DISIS-2020-001 | 05 SOUTHWEST | Lubbock | TX | SPS | 2026-05-01 | 2027-06-01 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Lubbock East Substation 230 kV | 2020-04-30 |  | DISIS STAGE
GEN-2020-059 |  | DISIS-2020-001 | 05 SOUTHWEST | Lovington | NM | SPS | 2025-03-02 | 2027-06-01 |  |  | 250 | 250 | 250 | ER | Hybrid | Solar/Storage | Tuco-Yoakum-Hobbs 345 kV | 2020-04-29 |  | DISIS STAGE
GEN-2020-058 |  | DISIS-2020-001 | 03 CENTRAL | Garner | KS | WERE | 2026-11-01 | 2028-06-01 |  |  | 424.5 | 424.5 | 424.5 | ER/NR | Solar |  | Atlantic 345 kV Substation | 2020-04-30 |  | DISIS STAGE
GEN-2020-057 |  | DISIS-2020-001 | 03 CENTRAL | Garner | KS | WERE | 2026-11-01 | 2028-06-01 |  |  | 424.5 | 424.5 | 424.5 | ER/NR | Battery/Storage |  | Atlantic 345 kV Substation | 2020-04-30 |  | DISIS STAGE
GEN-2020-056 |  | DISIS-2020-001 | 03 CENTRAL | Russell County | KS | SUNC | 2023-03-30 | 2025-01-03 |  |  | 20 | 20 | 20 | ER/NR | Solar |  | Russell 115 kV Substation | 2020-04-30 |  | DISIS STAGE
GEN-2020-054 |  | DISIS-2020-001 | 04 SOUTHEAST | Bowie County | TX | AEP | 2023-08-01 | 2026-09-01 |  |  | 298 | 298 | 298 | ER/NR | Solar |  | Lydia 345 kV Station | 2020-04-27 |  | DISIS STAGE
GEN-2020-045 |  | DISIS-2020-001 | 02 NEBRASKA | Douglas County | NE | OPPD | 2023-04-30 | 2024-08-01 |  |  | 56.52 | 56.52 | 56.52 | ER | Thermal | Reciprocating Engine | Between Substation 1209 and 1252; 161kV | 2020-04-29 |  | DISIS STAGE
GEN-2020-044 |  | DISIS-2020-001 | 02 NEBRASKA | Douglas County | NE | OPPD | 2023-04-30 | 2024-08-01 |  |  | 56.52 | 56.52 | 56.52 | ER | Thermal | Reciprocating Engine | Between Substation 1209 and 1252; 161kV | 2020-04-29 |  | DISIS STAGE
GEN-2020-043 |  | DISIS-2020-001 | 02 NEBRASKA | Douglas County | NE | OPPD | 2023-04-30 | 2024-08-01 |  |  | 56.52 | 56.52 | 56.52 | ER | Thermal | Reciprocating Engine | Between Substation 1209 and 1252; 161kV | 2020-04-29 |  | DISIS STAGE
GEN-2020-038 |  | DISIS-2020-001 | 02 NEBRASKA | Plattsmouth | NE | OPPD | 2023-04-30 | 2028-04-21 |  |  | 272.7 | 258 | 303 | ER | Thermal | CT | Substation 3740; 345kV | 2020-04-29 |  | DISIS STAGE
GEN-2020-031 |  | DISIS-2020-001 | 02 NEBRASKA | Sarpy County | NE | OPPD | 2023-04-30 | 2028-04-21 |  |  | 272.7 | 258 | 303 | ER | Thermal | CT | Substation 1363; 161kV Substation | 2020-04-29 |  | DISIS STAGE
GEN-2020-028 |  | DISIS-2020-001 | 02 NEBRASKA | Sarpy County | NE | OPPD | 2023-04-30 | 2024-08-01 |  |  | 255 | 235 | 255 | ER | Thermal | CT | Substation 1363; 161kV Substation | 2020-04-29 |  | DISIS STAGE
GEN-2020-025 |  | DISIS-2020-001 | 02 NEBRASKA | Sarpy County | NE | OPPD | 2023-04-30 | 2024-08-01 |  |  | 255 | 235 | 255 | ER | Thermal | CT | Substation 1363; 161kV Substation | 2020-04-29 |  | DISIS STAGE
GEN-2020-021 |  | DISIS-2020-001 | 01 NORTH | Sioux County | ND | BEPC | 2023-11-30 | 2026-12-31 |  |  | 235 | 235 | 235 | ER/NR | Wind |  | LeLand Olds-Chapelle Creek 345kV line | 2020-04-24 |  | DISIS STAGE
GEN-2020-020 |  | DISIS-2020-001 | 04 SOUTHEAST | McCurtain | OK | AEP | 2025-05-15 | 2025-12-15 |  |  | 201.6 | 201.6 | 201.6 | ER/NR | Hybrid | Solar/Storage | Tap the 345 kV Northwest Texarkana - Valliant line | 2020-04-28 |  | DISIS STAGE
GEN-2020-017 |  | DISIS-2020-001 | 05 SOUTHWEST | Lamb County | TX | SPS | 2025-10-01 | 2025-12-31 |  |  | 74.88 | 74.88 | 74.88 | ER/NR | Solar |  | 230kV Lamb County Interchange | 2020-04-24 |  | DISIS STAGE
GEN-2020-014 |  | DISIS-2020-001 | 01 NORTH | Alexander | ND | BEPC | 2021-06-17 | 2021-10-18 |  |  | 45 | 45 | 45 | ER/NR | Thermal | Gas | Lonesome Creek 115kV | 2020-04-20 |  | DISIS STAGE
GEN-2020-013 |  | DISIS-2020-001 | 02 NEBRASKA | Orleans | NE | NPPD | 2026-10-15 | 2027-06-01 |  |  | 215 | 215 | 215 | ER/NR | Hybrid | Solar/Storage | Orleans-Holdrege Substation 115kV | 2020-04-10 |  | DISIS STAGE
GEN-2020-012 |  | DISIS-2020-001 | 04 SOUTHEAST | Headrick | OK | AEP | 2026-10-15 | 2027-06-01 |  |  | 113 | 113 | 113 | ER/NR | Hybrid | Solar/Storage | Snyder â€“ Altus Jct. 138kV | 2020-04-10 |  | DISIS STAGE
GEN-2020-011 |  | DISIS-2020-001 | 02 NEBRASKA | Funk | NE | NPPD | 2026-10-15 | 2027-06-01 |  |  | 320 | 320 | 320 | ER/NR | Hybrid | Solar/Storage | Axtell-Sweetwater Substation 345kV | 2020-04-08 |  | DISIS STAGE
GEN-2020-010 |  | DISIS-2020-001 | 04 SOUTHEAST | Mutual | OK | WFEC | 2026-10-15 | 2027-06-01 |  |  | 140 | 140 | 140 | ER/NR | Hybrid | Solar/Storage | Seiling-Taloga Substations 138kV | 2020-04-08 |  | DISIS STAGE
GEN-2020-009 |  | DISIS-2020-001 | 05 SOUTHWEST | Cotton | OK | AEP | 2026-10-15 | 2025-12-31 |  |  | 300 | 300 | 300 | ER/NR | Hybrid | Solar/Storage | Lawton East Side to Oklaunion 345kV | 2020-04-08 |  | DISIS STAGE
GEN-2020-008 |  | DISIS-2020-001 | 03 CENTRAL | Stevens County | KS | SPS | 2023-09-01 | 2026-12-31 |  |  | 250 | 250 | 250 | ER | Hybrid | Solar/Storage | Corporation Carpenter 345kV Substation | 2020-04-22 |  | DISIS STAGE
GEN-2020-007 |  | DISIS-2020-001 | 03 CENTRAL | Linn & Bates | KS | KCPL | 2023-07-01 | 2025-12-31 |  |  | 650 | 650 | 650 | ER/NR | Hybrid | Solar/Storage | Evergy La Cygne to Wolf Creek 345kV Substation | 2020-04-22 |  | DISIS STAGE
GEN-2020-003 |  | DISIS-2020-001 | 03 CENTRAL | Winfield | KS | KPP | 2023-03-01 | 2025-06-01 |  |  | 58 | 58 | 58 | ER/NR | Thermal | Diesel/Gas | East Substation 69 kV | 2020-04-01 |  | DISIS STAGE
GEN-2020-002 |  | DISIS-2020-001 | 02 NEBRASKA | Yutan | NE | OPPD | 2022-11-15 | 2024-05-01 |  |  | 81 | 81 | 81 | ER | Solar |  | 6846 Substation 69 kV | 2020-04-06 |  | DISIS STAGE
GEN-2019-073 |  | DISIS-2019-001 | 02 NEBRASKA | Madison | NE | NPPD | 2023-12-31 | 2027-12-31 |  |  | 100 | 100 | 100 | ER | Solar |  | Shell Creek-Hoskins 345kv Line | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-070 |  | DISIS-2019-001 | 02 NEBRASKA | Madison | NE | NPPD | 2023-12-31 | 2027-12-31 |  |  | 50 | 50 | 50 | ER | Solar |  | Shell Creek-Hoskins 345kv Line | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-069 |  | DISIS-2019-001 | 02 NEBRASKA | Madison | NE | NPPD | 2023-12-31 | 2027-12-31 |  |  | 100 | 100 | 100 | ER | Solar |  | Shell Creek-Hoskins 345kV Line | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-068 |  | DISIS-2019-001 | 03 CENTRAL | Barton | KS | SUNC | 2023-06-01 | 2026-05-01 |  |  | 50 | 50 | 50 | ER/NR | Battery/Storage |  | Great Bend - Circle 230kV line | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-065 |  | DISIS-2019-001 | 04 SOUTHEAST | Smith | TX | AEP | 2024-06-01 | 2026-12-01 |  |  | 180 | 180 | 180 | ER | Battery/Storage |  | Overton-Northwest Henderson 138kV | 2019-05-23 |  | FACILITY STUDY STAGE
GEN-2019-063 |  | DISIS-2019-001 | 03 CENTRAL | Ford, Clark | KS | ITCGP | 2023-06-01 | 2026-05-01 |  |  | 50 | 50 | 50 | ER/NR | Battery/Storage |  | Clark County 345kV substation | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-058 |  | DISIS-2019-001 | 03 CENTRAL | Ford, Clark | KS | ITCGP | 2023-06-01 | 2026-05-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Clark County 345kV substation | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-055 |  | DISIS-2019-001 | 03 CENTRAL | Edwards, Pawnee | KS | SUNC | 2023-06-01 | 2026-05-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Great Bend-Spearville 230kV line | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-054 |  | DISIS-2019-001 | 03 CENTRAL | Barton | KS | SUNC | 2023-06-01 | 2026-05-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Great Bend- Circle 230kV line | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-053 |  | DISIS-2019-001 | 03 CENTRAL | Edwards/Pawnee | KS | SUNC | 2023-06-01 | 2026-05-01 |  |  | 50 | 50 | 50 | ER/NR | Battery/Storage |  | Great Bend-Spearville 230kV line | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-051 |  | DISIS-2019-001 | 03 CENTRAL | Barton | KS | SUNC | 2023-06-01 | 2026-05-01 |  |  | 40 | 40 | 40 | ER/NR | Battery/Storage |  | Frey St 115kV bus | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-045 |  | DISIS-2019-001 | 04 SOUTHEAST | Woods | OK | OGE | 2022-12-31 | 2027-12-31 |  |  | 155 | 155 | 155 | ER | Solar |  | DeGrasse 138kV Substation | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-044 |  | DISIS-2019-001 | 03 CENTRAL | Ford | KS | SUNC | 2023-12-31 | 2027-12-15 |  |  | 100 | 100 | 100 | ER | Solar |  | North Fort Dodge 115kV Substation | 2019-05-24 |  | FACILITY STUDY STAGE
GEN-2019-041 |  | DISIS-2019-001 | 02 NEBRASKA | Lancaster | NE | NPPD | 2020-12-01 | 2026-12-31 |  |  | 78 | 78 | 78 | ER/NR | Solar |  | 115kV Monolith Substation | 2019-05-23 |  | FACILITY STUDY STAGE
GEN-2019-039 |  | DISIS-2019-001 | 02 NEBRASKA | Butler | NE | NPPD | 2022-05-16 | 2025-05-01 |  |  | 174.5 | 174.5 | 174.5 | ER/NR | Solar |  | Columbus Southeast-Rising City 115kV | 2019-05-21 |  | FACILITY STUDY STAGE
GEN-2019-037 |  | DISIS-2019-001 | 01 NORTH | Mercer | ND | BEPC | 2023-12-01 | 2027-12-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Leland Olds 345kV substation | 2019-05-17 |  | FACILITY STUDY STAGE
GEN-2019-035 |  | DISIS-2019-001 | 03 CENTRAL | Barry | MO | EDE | 2022-12-31 | 2025-12-31 |  |  | 80 | 80 | 80 | ER/NR | Solar |  | Reeds Spring-Aurora 161kV Line | 2019-05-02 |  | FACILITY STUDY STAGE
GEN-2019-030 |  | DISIS-2019-001 | 03 CENTRAL | Ford | KS | ITCGP | 2021-12-01 | 2027-03-31 |  |  | 252 | 252 | 252 | ER/NR | Wind |  | Spearville to Clark County 345 kV line | 2019-04-25 |  | FACILITY STUDY STAGE
GEN-2019-023 |  | DISIS-2019-001 | 01 NORTH | Wibaux | MT | WAPA | 2023-12-31 | 2025-06-01 |  |  | 110 | 110 | 110 | ER/NR | Hybrid | Wind/Storage | WAPA-UGP Mingusville 230kV | 2019-05-08 |  | FACILITY STUDY STAGE
GEN-2019-021 |  | DISIS-2019-001 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2022-12-01 | 2025-06-01 |  |  | 50 | 50 | 50 | ER/NR | Solar |  | Roosevelt 230kV Substation | 2019-04-29 |  | FACILITY STUDY STAGE
GEN-2019-019 |  | DISIS-2019-001 | 01 NORTH | Sioux | IA | NIPCO | 2020-02-01 | 2023-02-16 |  |  | 15.15 | 15.15 | 15.15 | ER/NR | Thermal | Gas Turbine | Siouxland 69kV | 2019-04-24 |  | FACILITY STUDY STAGE
GEN-2019-018 |  | DISIS-2019-001 | 03 CENTRAL | Rice | KS | MIDW | 2020-03-01 | 2021-06-01 |  |  | 15.56 | 11.97 | 15.56 | ER/NR | Thermal | Gas Turbine | Saxman 115kV substation | 2019-04-24 |  | FACILITY STUDY STAGE
GEN-2019-016 |  | DISIS-2019-001 | 03 CENTRAL | Polk and Dade | MO | EDE | 2022-11-30 | 2026-12-31 |  |  | 200 | 200 | 200 | ER | Solar |  | Dadeville 161kV Substation | 2019-04-30 |  | FACILITY STUDY STAGE
GEN-2019-012 |  | DISIS-2019-001 | 04 SOUTHEAST | Woodward | OK | OGE | 2023-05-01 | 2027-05-01 |  |  | 200 | 200 | 200 | ER/NR | Battery/Storage |  | Woodward 345kV substation | 2019-05-22 |  | FACILITY STUDY STAGE
GEN-2019-011 |  | DISIS-2019-001 | 05 SOUTHWEST | Yoakum | TX | SPS | 2023-05-01 | 2025-05-01 |  |  | 207 | 207 | 207 | ER/NR | Battery/Storage |  | Yoakum 345kV Substation | 2019-04-22 |  | FACILITY STUDY STAGE
GEN-2019-009 |  | DISIS-2019-001 | 02 NEBRASKA | Nemaha | NE | OPPD | 2022-10-31 | 2026-11-30 |  |  | 100 | 100 | 100 | ER | Solar |  | S1263 Brock 161kV substation | 2019-04-24 |  | FACILITY STUDY STAGE
GEN-2019-003 |  | DISIS-2019-001 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2022-12-01 | 2025-06-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Roosevelt 230kV Substation | 2019-04-19 |  | FACILITY STUDY STAGE
GEN-2019-002 |  | DISIS-2019-001 | 04 SOUTHEAST | Mayes | OK | GRDA | 2020-12-01 | 2025-06-01 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Maid 161kV substation | 2018-11-26 |  | FACILITY STUDY STAGE
GEN-2019-001 |  | DISIS-2019-001 | 03 CENTRAL | Pratt | KS | WERE | 2018-12-31 | 2026-12-31 |  |  | 25 | 25 | 25 | ER | Wind |  | Thistle-Wichita Dbl Ckt (Buffalo Flats) 345kV | 2018-11-27 |  | FACILITY STUDY STAGE
GEN-2018-132 |  | DISIS-2018-002 | 02 NEBRASKA | Pierce | NE | NPPD | 2020-12-31 | 2026-12-31 |  |  | 201.6 | 201.6 | 201.6 | ER/NR | Solar |  | Antelope - Hoskins 345 kV | 2018-11-21 |  | FACILITY STUDY STAGE
GEN-2018-131 |  | DISIS-2018-002 | 02 NEBRASKA | Pierce | NE | NPPD | 2020-12-31 | 2026-12-31 |  |  | 221.4 | 221.4 | 221.4 | ER/NR | Solar |  | Antelope - Hoskins 345 kV | 2018-11-21 |  | FACILITY STUDY STAGE
GEN-2018-128 |  | DISIS-2018-002 | 03 CENTRAL | Sumner | KS | WERE | 2021-09-01 | 2027-10-01 |  |  | 200.22 | 200.22 | 200.22 | ER/NR | Wind |  | Renfrow-Viola 345 kV | 2018-11-19 |  | FACILITY STUDY STAGE
GEN-2018-125 |  | DISIS-2018-002 | 02 NEBRASKA | Lincoln | NE | NPPD | 2022-12-15 | 2027-12-01 |  |  | 231 | 231 | 231 | ER/NR | Wind |  | New switching station on Gentleman to Sweetwater 345kV line | 2018-11-19 |  | FACILITY STUDY STAGE
GEN-2018-116 |  | DISIS-2018-002 | 03 CENTRAL | Barton | KS | SUNC | 2022-12-31 | 2026-05-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Frey Street 115kV bus | 2018-11-20 |  | FACILITY STUDY STAGE
GEN-2018-115 |  | DISIS-2018-002 | 04 SOUTHEAST | Lawton | OK | AEP | 2021-12-01 | 2027-12-01 |  |  | 250 | 250 | 250 | ER/NR | Hybrid | Solar/Storage | Lawton East Side 345kV/138kv Substation | 2018-11-21 |  | FACILITY STUDY STAGE
GEN-2018-108 |  | DISIS-2018-002 | 03 CENTRAL | Barber | KS | ITCGP | 2027-12-31 | 2027-12-31 |  |  | 95 | 95 | 95 | ER | Battery/Storage |  | Thistle 345kV substation | 2018-11-21 |  | FACILITY STUDY STAGE
GEN-2018-106 |  | DISIS-2018-002 | 04 SOUTHEAST | Caddo | LA | AEP | 2023-12-31 | 2027-12-31 |  |  | 165 | 165 | 165 | ER | Solar |  | Longwood 345kV substation | 2018-11-02 |  | FACILITY STUDY STAGE
GEN-2018-099 |  | DISIS-2018-002 | 05 SOUTHWEST | Parmer | TX | SPS | 2023-12-31 | 2027-12-31 |  |  | 300 | 300 | 300 | ER | Wind |  | Tolk 230kV Substation | 2018-11-21 |  | FACILITY STUDY STAGE
GEN-2018-089 |  | DISIS-2018-002 | 05 SOUTHWEST | Castro | TX | SPS | 2023-12-31 | 2027-12-31 |  |  | 196 | 196 | 196 | ER | Wind |  | Newhart 230kV Substation | 2018-11-21 |  | FACILITY STUDY STAGE
GEN-2018-083 |  | DISIS-2018-002 | 02 NEBRASKA | Madison | NE | NPPD | 2023-12-31 | 2027-12-31 |  |  | 250 | 250 | 250 | ER | Wind |  | Shell Creek-Hoskins 345kv Line Break | 2018-11-16 |  | FACILITY STUDY STAGE
GEN-2018-082 |  | DISIS-2018-002 | 04 SOUTHEAST | Pittsburg | OK | AEP | 2023-12-31 | 2027-12-31 |  |  | 215 | 215 | 215 | ER | Wind |  | Pittsburg 345kV Substation | 2018-11-18 |  | FACILITY STUDY STAGE
GEN-2018-079 |  | DISIS-2018-002 | 04 SOUTHEAST | Craig/Novata | OK | AEP | 2023-12-31 | 2027-12-31 |  |  | 148 | 148 | 148 | ER | Solar |  | Farmland-Delaware 138kV line | 2018-11-18 |  | FACILITY STUDY STAGE
GEN-2018-074 |  | DISIS-2018-002 | 01 NORTH | Crawford and Carrol | IA | WAPA | 2022-05-10 | 2026-10-31 |  |  | 72 | 72 | 72 | ER | Wind |  | Denison 230kV Substation | 2018-10-31 |  | FACILITY STUDY STAGE
GEN-2018-072 |  | DISIS-2018-002 | 04 SOUTHEAST | Kay | OK | OGE | 2021-11-30 | 2025-11-30 |  |  | 151 | 151 | 151 | ER/NR | Battery/Storage |  | Interconnecting into OG&E's Ranch Road 345kV substation by tapping a 0.1 gen tie line into the existing Frontier II gen-tie line | 2018-10-26 |  | FACILITY STUDY STAGE
GEN-2018-071 |  | DISIS-2018-002 | 04 SOUTHEAST | Kay | OK | OGE | 2021-11-30 | 2025-11-30 |  |  | 151 | 151 | 151 | ER/NR | Battery/Storage |  | Interconnecting into OG&E's Ranch Road 345kV substation by tapping a 0.1 gen tie line into the existing Frontier II gen-tie line | 2018-10-25 |  | FACILITY STUDY STAGE
GEN-2018-069 |  | DISIS-2018-002 | 01 NORTH | Wibaux | MT | WAPA | 2020-12-31 | 2025-06-01 |  |  | 125 | 125 | 125 | ER/NR | Wind |  | WAPA-UGP Mingusville 230kV | 2018-10-26 |  | FACILITY STUDY STAGE
GEN-2018-068 |  | DISIS-2018-002 | 02 NEBRASKA | Madison | NE | NPPD | 2022-09-01 | 2027-12-01 |  |  | 302.4 | 302.4 | 302.4 | ER/NR | Wind |  | Antelope - Hoskins 345 kV Substation | 2018-10-26 |  | FACILITY STUDY STAGE
GEN-2018-067 |  | DISIS-2018-002 | 01 NORTH | Williams | ND | MWEC | 2020-10-30 | 2026-10-30 |  |  | 255 | 255 | 255 | ER | Wind |  | 115kV Strandahl sub | 2018-10-25 |  | FACILITY STUDY STAGE
GEN-2018-065 |  | DISIS-2018-002 | 02 NEBRASKA | Madison | NE | NPPD | 2020-07-01 | 2027-12-01 |  |  | 19.8 | 19.8 | 19.8 | ER/NR | Wind |  | Antelope - Hoskins 345 kV Substation | 2018-10-24 |  | FACILITY STUDY STAGE
GEN-2018-064 |  | DISIS-2018-002 | 04 SOUTHEAST | Benton County | AR | GRDA | 2021-06-30 | 2025-12-31 |  |  | 80 | 80 | 80 | ER/NR | Solar |  | Tonnece Substation 69kV | 2018-10-24 |  | FACILITY STUDY STAGE
GEN-2018-063 |  | DISIS-2018-002 | 03 CENTRAL | Greene | MO | EDE | 2021-06-30 | 2026-12-31 |  |  | 57 | 57 | 57 | ER | Solar |  | Sedalia Marshfield Springfield Nichols Street 69kV circuit | 2018-10-23 |  | FACILITY STUDY STAGE
GEN-2018-060 |  | DISIS-2018-001 | 02 NEBRASKA | Webster | NE | NPPD | 2020-12-01 | 2026-12-31 |  |  | 50 | 50 | 50 | ER/NR | Wind |  | Axtell-Post Rock 345 kV | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-057 |  | DISIS-2018-001 | 03 CENTRAL | Sedgwick | KS | WERE | 2029-05-15 | 2029-05-15 |  |  | 203.4 | 203.4 | 203.4 | ER/NR | Solar |  | Gordon Evans 138kV | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-055 |  | DISIS-2018-001 | 04 SOUTHEAST | Grady | OK | AEP | 2020-12-31 | 2026-12-31 |  |  | 252 | 252 | 252 | ER/NR | Solar |  | Terry Road 345kV station (shared with Rush Springs Windfarm on a common gentie) | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-052 |  | DISIS-2018-001 | 05 SOUTHWEST | Lea | NM | SPS | 2021-12-31 | 2026-12-31 |  |  | 70 | 70 | 70 | ER | Battery/Storage |  | Roadrunner 115kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-050 |  | DISIS-2018-001 | 04 SOUTHEAST | Caddo | LA | AEP | 2021-12-31 | 2027-04-15 |  |  | 200 | 200 | 200 | ER | Solar |  | Longwood 345kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-049 |  | DISIS-2018-001 | 03 CENTRAL | Sumner | KS | ITCGP | 2021-12-31 | 2027-04-01 |  |  | 120 | 120 | 120 | ER | Solar |  | Thistle 345kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-048 |  | DISIS-2018-001 | 04 SOUTHEAST | Caddo | OK | OGE | 2021-12-31 | 2027-12-15 |  |  | 300 | 300 | 300 | ER | Solar |  | Pecan Creek 345kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-043 |  | DISIS-2018-001 | 02 NEBRASKA | Burt | NE | OPPD | 2021-12-31 | 2028-12-15 |  |  | 500 | 500 | 500 | ER | Solar |  | Ft. Calhoun - Raun 345 kV Line Break | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-037 |  | DISIS-2018-001 | 02 NEBRASKA | Douglas | NE | OPPD | 2024-12-31 | 2030-05-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Looping in OPPD (S1211) (S1220) (S1211) (S1299) 161kV | 2018-05-29 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2018-033 |  | DISIS-2018-001 | 02 NEBRASKA | Cass | NE | OPPD | 2023-12-31 | 2029-11-30 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Cass County 345kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2018-032 |  | DISIS-2018-001 | 03 CENTRAL | McPhearson | KS | WERE | 2021-12-01 | 2029-05-01 |  |  | 310 | 310 | 310 | ER | Wind |  | Neosho 345kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2018-031 |  | DISIS-2018-001 | 03 CENTRAL | Jackson | MO | INDN | 2024-12-31 | 2028-05-31 |  |  | 50 | 50 | 50 | ER | Battery/Storage |  | Blue Valley 161kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-029 |  | DISIS-2018-001 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2023-10-15 | 2028-05-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Horseshoe Lake 138kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-028 |  | DISIS-2018-001 | 04 SOUTHEAST | Tulsa | OK | AEP | 2023-10-15 | 2028-05-31 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Tulsa North 138kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-027 |  | DISIS-2018-001 | 04 SOUTHEAST | Tulsa | OK | AEP | 2024-12-31 | 2028-05-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Tulsa Power Station 138kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-026 |  | DISIS-2018-001 | 04 SOUTHEAST | Canadian | OK | OGE | 2023-10-15 | 2026-05-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Mustang 138kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-025 |  | DISIS-2018-001 | 02 NEBRASKA | Washington | NE | OPPD | 2023-10-15 | 2028-11-30 |  |  | 200 | 200 | 200 | ER | Battery/Storage |  | Fort Calhoun 345kV Substation | 2018-05-29 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2018-024 |  | DISIS-2018-001 | 04 SOUTHEAST | Muskogee | OK | OGE | 2023-10-15 | 2028-12-31 |  |  | 100 | 100 | 100 | ER | Battery/Storage |  | Canadian River-Muskogee and Muskogee-Seminole 345kV | 2018-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-021 |  | DISIS-2018-001 | 04 SOUTHEAST | Washita | OK | AEP | 2023-12-01 | 2024-12-31 |  |  | 74.1 | 74.1 | 74.1 | ER/NR | Solar |  | Chisholm-Gracemont 345kV Line | 2018-05-24 |  | IA PENDING
GEN-2018-015 |  | DISIS-2018-001 | 05 SOUTHWEST | Paducah | TX | SPS | 2021-10-31 | 2027-11-01 |  |  | 252 | 252 | 252 | ER/NR | Solar |  | Tuco-Oklaunion 345kV Line | 2018-04-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-013 |  | DISIS-2018-001 | 03 CENTRAL | Dickinson | KS | WERE | 2024-12-30 | 2026-12-31 |  |  | 74.1 | 74.1 | 74.1 | ER | Wind |  | Abilene Energy Center-Northview 115kV Line | 2018-04-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-011 |  | DISIS-2018-001 | 04 SOUTHEAST | Kingfisher | OK | WFEC | 2020-12-01 | 2027-12-31 |  |  | 74.1 | 74.1 | 74.1 | ER/NR | Battery/Storage |  | Dover 138 kV Switching Station | 2018-04-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-010 |  | DISIS-2018-001 | 01 NORTH | Montrail | ND | BEPC | 2021-12-01 | 2026-12-31 |  |  | 74.1 | 74.1 | 74.1 | ER/NR | Battery/Storage |  | Neset 230kV Substation | 2018-04-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-009 |  | DISIS-2018-001 | 03 CENTRAL | Seward/Meade | KS | SUNC | 2025-07-15 | 2028-12-31 |  |  | 150 | 150 | 150 | ER | Wind |  | Cimarron 115kV Substation | 2018-04-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-004 |  | DISIS-2018-001 | 05 SOUTHWEST | Lea | NM | SPS | 2019-12-31 | 2027-03-01 |  |  | 74.99 | 74.99 | 74.99 | ER | Solar |  | T14 Circuit 115kV line | 2018-04-26 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2018-003 |  | DISIS-2018-001 | 04 SOUTHEAST | Bowie | TX | AEP | 2021-12-31 | 2027-06-01 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | North Boston-Bann 138kV Line | 2018-04-25 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-239 | IFS-2017-002-76 | DISIS-2017-002 | 05 SOUTHWEST | Yoakum | TX | SPS | 2023-06-01 | 2026-05-01 |  |  | 300 | 300 | 300 | ER | Solar |  | Mahoney 230kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-234 | IFS-2017-002-73 | DISIS-2017-002 | 02 NEBRASKA | Greeley | NE | NPPD | 2019-12-31 | 2024-12-31 |  |  | 115 | 115 | 115 | ER | Wind |  | Spalding to North Loup 115kV | 2017-11-06 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-233 | IFS-2017-002-72 | DISIS-2017-002 | 04 SOUTHEAST | Grady | OK | OGE | 2020-12-01 | 2027-12-31 |  |  | 215 | 215 | 215 | ER/NR | Wind |  | Minco 345kV | 2017-11-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-232 | IFS-2017-002-71 | DISIS-2017-002 | 04 SOUTHEAST | Bryan County | OK | OGE | 2020-06-01 | 2026-03-31 |  |  | 52.2 | 52.2 | 52.2 | ER/NR | Solar |  | Brown 138kV Substation | 2017-11-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-231 | IFS-2017-002-70 | DISIS-2017-002 | 04 SOUTHEAST | Franklin County | AR | OGE | 2020-06-01 | 2026-06-01 |  |  | 72.5 | 72.5 | 72.5 | ER/NR | Solar |  | Branch 161kV Substation | 2017-11-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-230 | IFS-2017-002-69 | DISIS-2017-002 | 04 SOUTHEAST | Lincoln County | OK | OGE | 2020-06-01 | 2026-05-01 |  |  | 72.5 | 72.5 | 72.5 | ER/NR | Solar |  | Tryon 138kV Substation | 2017-11-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-227 | IFS-2017-002-67 | DISIS-2017-002 | 03 CENTRAL | Sedwick County | KS | WERE | 2020-12-31 | 2029-05-15 |  |  | 201.6 | 201.6 | 201.6 | ER/NR | Battery/Storage |  | Gordon Evans 138kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-226 | IFS-2017-002-66 | DISIS-2017-002 | 03 CENTRAL | Sedgwick County | KS | WERE | 2020-12-01 | 2029-05-15 |  |  | 201.6 | 201.6 | 201.6 | ER/NR | Solar |  | Gordon Evans 138kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-222 | IFS-2017-002-64 | DISIS-2017-002 | 01 NORTH | Denison | IA | WAPA | 2020-10-06 | 2027-02-02 |  |  | 180 | 180 | 180 | ER | Wind |  | Denison 230kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-221 | IFS-2017-002-63 | DISIS-2017-002 | 03 CENTRAL | Sedgwick | KS | WERE | 2020-12-31 | 2029-03-30 |  |  | 152 | 152 | 152 | ER/NR | Battery/Storage |  | Buffalo Flats 345kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-220 | IFS-2017-002-62 | DISIS-2017-002 | 03 CENTRAL | Sedgwick | KS | WERE | 2020-12-01 | 2029-12-31 |  |  | 201.6 | 201.6 | 201.6 | ER/NR | Solar |  | Buffalo Flats 345kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-215 | IFS-2017-002-60 | DISIS-2017-002 | 01 NORTH | Ward | ND | BEPC | 2020-12-01 | 2030-12-31 |  |  | 100 | 100 | 100 | ER/NR | Wind |  | Logan 230kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-214 | IFS-2017-002-59 | DISIS-2017-002 | 01 NORTH | Ward | ND | BEPC | 2020-12-01 | 2030-12-31 |  |  | 100 | 100 | 100 | ER/NR | Wind |  | Logan 230kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-210 | IFS-2017-002-57 | DISIS-2017-002 | 02 NEBRASKA | Cedar | NE | NPPD | 2021-12-01 | 2026-12-01 |  |  | 310 | 310 | 310 | ER | Hybrid | Solar | McCool 345kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2017-203 | IFS-2017-002-55 | DISIS-2017-002 | 04 SOUTHEAST | Grant/Kay | OK | OGE | 2023-07-01 | 2026-12-31 |  |  | 210 | 210 | 210 | ER | Hybrid | Solar | Renfrow 345kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2017-201 | IFS-2017-002-53 | DISIS-2017-002 | 02 NEBRASKA | Wayne County | NE | NPPD | 2022-12-01 | 2028-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Hoskins 345kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-198 | IFS-2017-002-50 | DISIS-2017-002 | 02 NEBRASKA | Omaha | NE | OPPD | 2022-12-01 | 2026-05-31 |  |  | 11.64 | 11.64 | 11.64 | ER | Battery/Storage |  | Jones St. No 1201 69kV substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-196 | IFS-2017-002-49 | DISIS-2017-002 | 03 CENTRAL | Johnson | KS | KCPL | 2020-12-01 | 2030-12-01 |  |  | 128 | 128 | 128 | ER/NR | Battery/Storage |  | West Gardner 345kV | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-195 | IFS-2017-002-48 | DISIS-2017-002 | 03 CENTRAL | Johnson | KS | KCPL | 2020-12-01 | 2030-12-01 |  |  | 500.4 | 500.4 | 500.4 | ER/NR | Solar |  | West Gardner 345kV | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-188 | IFS-2017-002-44 | DISIS-2017-002 | 03 CENTRAL | Barry | MO | EDE | 2020-12-31 | 2026-06-15 |  |  | 130 | 130 | 130 | ER | Solar |  | Asbury 161 kV | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-187 | IFS-2017-002-43 | DISIS-2017-002 | 05 SOUTHWEST | Terry | TX | SPS | 2020-12-31 | 2026-06-01 |  |  | 150 | 150 | 150 | ER | Solar |  | Flatland 115 kV Substation | 2017-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-184 | IFS-2017-002-42 | DISIS-2017-002 | 03 CENTRAL | Hodgeman/Ford | KS | KCPL | 2021-12-01 | 2029-06-01 |  |  | 400 | 400 | 400 | ER/NR | Solar |  | Nashua-St. Joe 345kV | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-183 | IFS-2017-002-41 | DISIS-2017-002 | 03 CENTRAL | Hodgeman/Ford | KS | KCPL | 2021-12-01 | 2029-06-01 |  |  | 400 | 400 | 400 | ER/NR | Wind |  | Nashua-St. Joe 345kV | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-182 | IFS-2017-002-40 | DISIS-2017-002 | 02 NEBRASKA | Lancaster | NE | NPPD | 2020-12-01 | 2025-02-04 |  |  | 128 | 128 | 128 | ER/NR | Wind |  | Tobias 345kV Substation | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-181 | IFS-2017-002-39 | DISIS-2017-002 | 02 NEBRASKA | Lancaster | NE | NPPD | 2020-12-01 | 2024-12-08 |  |  | 300 | 300 | 300 | ER/NR | Wind |  | Tobias 345kV Substation | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-178 | IFS-2017-002-37 | DISIS-2017-002 | 04 SOUTHEAST | Garfield | OK | OGE | 2020-12-31 | 2025-12-01 |  |  | 52 | 52 | 52 | ER/NR | Battery/Storage |  | Woodring 345kV Substation | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-175 | IFS-2017-002-36 | DISIS-2017-002 | 01 NORTH | Turner | SD | WAPA | 2023-09-30 | 2026-12-01 |  |  | 300 | 300 | 300 | ER | Wind |  | Vfodnes-Utica Jct. 230kV | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-173 | IFS-2017-002-35 | DISIS-2017-002 | 04 SOUTHEAST | Stephen | OK | AEP | 2020-12-01 | 2027-12-31 |  |  | 50 | 50 | 50 | ER/NR | Solar |  | Lawton Eastside - Terry Road 345kV | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-172 | IFS-2017-002-34 | DISIS-2017-002 | 04 SOUTHEAST | Stephen | OK | AEP | 2020-12-01 | 2027-12-31 |  |  | 50 | 50 | 50 | ER/NR | Solar |  | Lawton Eastside - Terry Road 345kV | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-171 | IFS-2017-002-33 | DISIS-2017-002 | 04 SOUTHEAST | Stephen | OK | AEP | 2020-12-01 | 2027-12-31 |  |  | 150 | 150 | 150 | ER/NR | Solar |  | Lawton Eastside - Terry Road 345kV | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-164 | IFS-2017-002-28 | DISIS-2017-002 | 04 SOUTHEAST | Garfield | OK | OGE | 2020-12-01 | 2025-12-31 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Woodring 345kV Substation | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-158 | IFS-2017-002-27 | DISIS-2017-002 | 05 SOUTHWEST | Parmer/Castro | TX | SPS | 2020-12-31 | 2026-08-30 |  |  | 265 | 265 | 265 | ER | Wind |  | Tolk 230kV Substation | 2017-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-151 | IFS-2017-002-23 | DISIS-2017-002 | 05 SOUTHWEST | Crosby | TX | SPS | 2020-10-31 | 2026-10-15 |  |  | 300 | 300 | 300 | ER | Wind |  | TUCO-Oklaunion 345kV | 2017-11-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-150 | IFS-2017-002-22 | DISIS-2017-002 | 04 SOUTHEAST | Grady | OK | OGE | 2020-12-01 | 2026-12-31 |  |  | 250 | 250 | 250 | ER/NR | Solar |  | Minco 345kV | 2017-11-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-149 | IFS-2017-002-21 | DISIS-2017-002 | 04 SOUTHEAST | Johnston | OK | OGE | 2020-12-01 | 2027-12-31 |  |  | 258 | 258 | 258 | ER/NR | Wind |  | Johnson County 345kV Substation | 2017-11-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-146 | IFS-2017-002-19 | DISIS-2017-002 | 05 SOUTHWEST | Castro | TX | SPS | 2020-10-31 | 2026-10-15 |  |  | 151.8 | 151.8 | 151.8 | ER | Wind |  | Deaf Smith-Plant X 230kV | 2017-11-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-144 | IFS-2017-002-18 | DISIS-2017-002 | 02 NEBRASKA | Holt, Antelope, Wheeler | NE | NPPD | 2021-12-31 | 2025-12-31 |  |  | 200 | 200 | 200 | ER | Wind |  | Holt County 345kV | 2017-11-27 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-141 | IFS-2017-002-17 | DISIS-2017-002 | 04 SOUTHEAST | Wagoner | OK | AEP | 2020-12-01 | 2027-12-31 |  |  | 241.7 | 241.7 | 241.7 | ER/NR | Solar |  | Clarksville 345kV Switching Station | 2017-11-22 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-140 | IFS-2017-002-16 | DISIS-2017-002 | 04 SOUTHEAST | Wagoner | OK | AEP | 2020-12-01 | 2027-12-31 |  |  | 160 | 160 | 160 | ER/NR | Solar |  | Clarksville 345kV Switching Station | 2017-11-22 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-137 | IFS-2017-002-15 | DISIS-2017-002 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2020-12-01 | 2028-12-31 |  |  | 295 | 295 | 295 | ER/NR | Wind |  | Arcadia 345kV | 2017-11-22 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-134 | IFS-2017-002-14 | DISIS-2017-002 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2020-12-01 | 2028-12-31 |  |  | 250 | 250 | 250 | ER/NR | Wind |  | Arcadia 345kV | 2017-11-22 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-133 | IFS-2017-002-13 | DISIS-2017-002 | 04 SOUTHEAST | Oklahoma | OK | OGE | 2020-12-01 | 2028-12-31 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Arcadia 345kV | 2017-11-22 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-131 | IFS-2017-002-11 | DISIS-2017-002 | 03 CENTRAL | Wilson | KS | WERE | 2020-12-01 | 2026-02-01 |  |  | 29.6 | 29.6 | 29.6 | ER/NR | Battery/Storage |  | Altoona- NE Parson 138kV | 2017-11-22 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2017-121 | IFS-2017-002-08 | DISIS-2017-002 | 03 CENTRAL | Sumner | KS | WERE | 2021-12-01 | 2026-12-01 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Sumner 138kV | 2017-11-17 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-120 | IFS-2017-002-07 | DISIS-2017-002 | 03 CENTRAL | Dickinson/Marion | KS | WERE | 2027-05-01 | 2027-12-31 |  |  | 260 | 260 | 260 | ER | Wind |  | Abilene Energy Center-Northview 115kV | 2017-11-17 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-119 | IFS-2017-002-06 | DISIS-2017-002 | 03 CENTRAL | Cloud/Mitchell | KS | SUNC | 2024-05-01 | 2027-12-31 |  |  | 180 | 180 | 180 | ER | Wind |  | Elm Creek 345kV substation | 2017-11-17 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-117 | IFS-2017-002-05 | DISIS-2017-002 | 04 SOUTHEAST | Canadian | OK | WFEC | 2020-12-01 | 2026-12-01 |  |  | 19.8 | 19.8 | 19.8 | ER/NR | Battery/Storage |  | El Reno SW 138kV | 2017-11-17 |  | IA FULLY EXECUTED/ON SUSPENSION
GEN-2017-115 | IFS-2017-002-04 | DISIS-2017-002 | 03 CENTRAL | Atchinson/Nodaway | MO | KCPL | 2027-05-01 | 2026-12-31 |  |  | 244 | 244 | 244 | ER | Wind |  | Holt County 345 kV | 2017-11-10 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-108 | IFS-2017-002-02 | DISIS-2017-002 | 03 CENTRAL | Henry County | MO | KCPL | 2022-12-01 | 2027-03-01 |  |  | 400 | 400 | 400 | ER/NR | Solar |  | Stillwell - Clinton 161kV Line | 2017-08-26 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-105 | IFS-2017-002-01 | DISIS-2017-002 | 02 NEBRASKA | Burt County | NE | OPPD | 2018-12-15 | 2026-12-20 |  |  | 75 | 75 | 75 | ER/NR | Wind |  | Tekamah - Raun 161 kV Line | 2017-07-12 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-100 | IFS-2017-001-20 | DISIS-2017-001 | 05 SOUTHWEST | Texas County | OK | SPS | 2019-12-31 | 2025-12-01 |  |  | 102.6 | 102.6 | 102.6 | ER/NR | Solar |  | Texas County 115kV | 2017-05-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-097 | IFS-2017-001-24 | DISIS-2017-001 | 01 NORTH | Pennington County | SD | WAPA | 2022-01-09 | 2024-06-29 |  |  | 128 | 128 | 128 | ER | Solar |  | Underwood 115 kV Sub | 2017-05-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-094 | IFS-2017-001-31 | DISIS-2017-001 | 01 NORTH | Wessington/Hand Counties | SD | WAPA | 2020-10-06 | 2023-11-01 |  |  | 200 | 200 | 200 | ER | Wind |  | Fort Thompson-Huron 230 kV | 2017-05-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-092 | IFS-2017-001-04 | DISIS-2017-001 | 04 SOUTHEAST | Muskogee County | OK | OGE | 2023-06-01 | 2025-12-31 |  |  | 200 | 200 | 200 | ER | Solar |  | Canadian River-Muskogee and Muskogee-Seminole 345kV | 2017-05-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-086 | IFS-2017-001-10 | DISIS-2017-001 | 03 CENTRAL | Harper County | KS | WERE | 2021-12-01 | 2025-03-01 |  |  | 150 | 150 | 150 | ER | Wind |  | Viola 345kV | 2017-05-25 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-082 | IFS-2017-001-02 | DISIS-2017-001 | 03 CENTRAL | Barton/Jasper Counties | MO | EDE | 2020-07-01 | 2020-12-31 |  |  | 149.4 | 149.4 | 149.4 | ER | Wind |  | Asbury Plant 161 kV | 2017-05-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-077 | IFS-2017-001-18 | DISIS-2017-001 | 04 SOUTHEAST | Mayes County | OK | AEP | 2021-12-01 | 2025-08-08 |  |  | 124.7 | 124.7 | 124.7 | ER | Solar |  | Explorer Claremore Tap EXCLART4 | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-076 | IFS-2017-001-17 | DISIS-2017-001 | 04 SOUTHEAST | Benton County | AR | AEP | 2021-12-01 | 2024-12-01 |  |  | 52.2 | 52.2 | 52.2 | ER | Solar |  | Chamber Springs 161kV sub | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-075 | IFS-2017-001-16 | DISIS-2017-001 | 04 SOUTHEAST | Johnston County | OK | OGE | 2021-12-01 | 2026-12-01 |  |  | 200 | 200 | 200 | ER | Solar |  | Hugo-Sunnyside 345 kV | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-074 | IFS-2017-001-15 | DISIS-2017-001 | 04 SOUTHEAST | Mayes County | OK | AEP | 2021-12-01 | 2025-08-08 |  |  | 72.5 | 72.5 | 72.5 | ER | Solar |  | Pryor Junction 138kV sub | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-073 | IFS-2017-001-14 | DISIS-2017-001 | 04 SOUTHEAST | Mayes County | OK | GRDA | 2021-12-01 | 2025-09-01 |  |  | 72.5 | 72.5 | 72.5 | ER | Solar |  | Dry Gulch 161kV sub | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-072 | IFS-2017-001-37 | DISIS-2017-001 | 04 SOUTHEAST | Payne County | OK | OGE | 2021-12-01 | 2025-12-01 |  |  | 52.2 | 52.2 | 52.2 | ER | Solar |  | Greenwood 138kV sub | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-071 | IFS-2017-001-36 | DISIS-2017-001 | 04 SOUTHEAST | Payne County | OK | OGE | 2021-12-01 | 2025-12-01 |  |  | 124.7 | 124.7 | 124.7 | ER | Solar |  | Greenwood 138kV sub | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-068 | IFS-2017-001-26 | DISIS-2017-001 | 03 CENTRAL | Sumner County | KS | WERE | 2020-12-31 | 2028-12-15 |  |  | 103.5 | 103.5 | 103.5 | ER/NR | Solar |  | Gordon Evans 138kV Substation | 2017-05-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-061 | IFS-2017-001-25 | DISIS-2017-001 | 04 SOUTHEAST | Mayes County | OK | GRDA | 2021-12-01 | 2025-09-01 |  |  | 101.5 | 101.5 | 101.5 | ER | Solar |  | GRDA1 to CLARMR 5 161kV line | 2017-05-28 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-060 | IFS-2017-001-01 | DISIS-2017-001 | 03 CENTRAL | Barton County | MO | EDE | 2020-09-01 | 2021-04-21 |  |  | 149.4 | 149.4 | 149.4 | ER | Wind |  | LaRussell Energy Center 161kV | 2017-05-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-057 | IFS-2017-001-13 | DISIS-2017-001 | 04 SOUTHEAST | Caddo Parish | LA | AEP | 2021-12-01 | 2025-02-28 |  |  | 72.5 | 72.5 | 72.5 | ER | Solar |  | Hosston 69kV | 2017-05-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-048 | IFS-2017-001-34 | DISIS-2017-001 | 01 NORTH | Williams County | ND | BEPC | 2024-08-30 | 2026-12-31 |  |  | 300 | 300 | 300 | ER | Wind |  | Neset 230 kV Substation | 2017-05-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-047 | IFS-2017-001-19 | DISIS-2017-001 | 05 SOUTHWEST | Beaver County | OK | SPS | 2019-12-31 | 2024-12-27 |  |  | 102 | 102 | 102 | ER/NR | Wind |  | Bull Creek 115 kV substation | 2017-05-18 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-040 | IFS-2017-001-03 | DISIS-2017-001 | 04 SOUTHEAST | Ochiltree County | TX | OGE | 2020-06-01 | 2025-12-31 |  |  | 200.1 | 200.1 | 200.1 | ER | Solar |  | Canadian River-Muskogee and Muskogee-Seminole 345kV | 2017-05-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-036 | IFS-2017-001-23 | DISIS-2017-001 | 04 SOUTHEAST | Kiowa County | OK | AEP | 2022-12-01 | 2024-12-01 |  |  | 100 | 100 | 100 | ER | Solar |  | Snyder - Cache 138 kV | 2017-05-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-033 | IFS-2017-001-28 | DISIS-2017-001 | 05 SOUTHWEST | Baylor County | TX | AEP | 2020-12-31 | 2024-12-23 |  |  | 200 | 200 | 200 | ER | Wind |  | Oklaunion 345 kV sub | 2017-05-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-027 | IFS-2017-001-33 | DISIS-2017-001 | 04 SOUTHEAST | Carter County | OK | OGE | 2021-11-01 | 2021-12-21 |  |  | 140 | 140 | 140 | ER | Wind |  | Pooleville-Ratliff (Carter County) 138kV | 2017-05-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-023 | IFS-2017-001-22 | DISIS-2017-001 | 04 SOUTHEAST | Choctaw County | OK | WFEC |  | 2026-06-01 |  |  | 85 | 85 | 85 | ER/NR | Solar |  | Hugo Power Plant 138 kV Sub | 2017-05-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-022 | IFS-2017-001-21 | DISIS-2017-001 | 03 CENTRAL | Wilson County | KS | WERE | 2019-12-01 | 2025-06-01 |  |  | 65 | 65 | 65 | ER/NR | Solar |  | Altoona- NE Parson 138kV | 2017-05-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-018 | IFS-2017-001-27 | DISIS-2017-001 | 03 CENTRAL | Barber County | KS | ITCGP | 2020-12-31 | 2025-04-30 |  |  | 189 | 189 | 189 | ER/NR | Solar |  | Thistle 345 kV sub | 2017-05-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-014 | IFS-2017-001-29 | DISIS-2017-001 | 01 NORTH | Haakon County | SD | WAPA | 2020-12-01 | 2027-12-01 |  |  | 300 | 300 | 300 | ER | Wind |  | Philip Tap 230 kV | 2017-05-22 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-011 | IFS-2017-001-06 | DISIS-2017-001 | 04 SOUTHEAST | Ellis County | OK | OGE | 2019-12-31 | 2026-12-31 |  |  | 151.8 | 151.8 | 151.8 | ER | Solar |  | Badger-Woodward EHV Dbl Ckt 345kV | 2017-05-17 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-010 | IFS-2017-001-12 | DISIS-2017-001 | 01 NORTH | Bowman County | ND | BEPC | 2022-10-31 | 2025-12-12 |  |  | 200.1 | 200.1 | 200.1 | ER | Wind |  | Rhame 230 kV Sub | 2017-04-14 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2017-009 | IFS-2017-001-39 | DISIS-2017-001 | 03 CENTRAL | Neoshoe County | KS | WERE | 2020-10-31 | 2021-05-01 |  |  | 302 | 302 | 302 | ER | Wind |  | Neosho - Caney River 345 kV | 2017-04-14 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2017-005 | IFS-2017-001-11 | DISIS-2017-001 | 03 CENTRAL | Bourbon and Crawford Counties | OK | WERE | 2020-12-31 | 2021-12-13 |  |  | 190 | 190 | 190 | ER | Wind |  | Marmaton - Litchfield 161 kV | 2017-04-14 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION | Interim IGIA effective 3/3/2021 - AB
GEN-2017-004 | IFS-2017-001-05 | DISIS-2017-001 | 03 CENTRAL | Cloud County | KS | ITCGP | 2021-12-31 | 2027-11-30 |  |  | 201.6 | 201.6 | 201.6 | ER | Wind |  | Elm Creek - Summit 345 kV | 2017-04-14 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-177 | IFS-2016-002-60 | DISIS-2016-002-1 | 05 SOUTHWEST | Gaines | TX | SPS |  | 2021-07-28 |  |  | 17 | 14.4 | 17 | ER | Thermal | Gas Turbine | XTO-Cornell 115 kV station | 2017-01-23 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-176 | IFS-2016-002-67 | DISIS-2016-002-1 | 03 CENTRAL | Nemaha County | KS | WERE | 2019-12-31 | 2021-12-06 |  |  | 302 | 302 | 302 | ER | Wind |  | Stranger Creek 345kV | 2016-12-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-174 | IFS-2016-002-19 | DISIS-2016-002-1 | 03 CENTRAL | Nemaha | KS | WERE | 2019-09-15 | 2020-11-18 |  |  | 302 | 302 | 302 | ER | Wind |  | Stranger Creek 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-167 | IFS-2016-002-02 | DISIS-2016-002-1 | 04 SOUTHEAST | Caddo Parish | LA | AEP | 2023-09-01 | 2024-12-01 |  |  | 73.5 | 73.5 | 73.5 | ER/NR | Solar |  | Lieberman - North Benton 138 kV Line | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-160 | IFS-2016-002-04 | DISIS-2016-002-1 | 03 CENTRAL | Ellis | KS | MIDW | 2023-10-02 | 2026-12-31 |  |  | 20 | 20 | 20 | ER/NR | Battery/Storage |  | Post Rock 230kV | 2016-11-21 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-153 | IFS-2016-002-11 | DISIS-2016-002-1 | 03 CENTRAL | Harper County | KS | WERE | 2019-10-30 | 2024-12-31 |  |  | 134 | 134 | 134 | ER | Wind |  | Viola 345kV | 2016-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-151 | IFS-2016-002-62 | DISIS-2016-002-1 | 01 NORTH | Burke | ND | BEPC | 2019-09-15 | 2020-12-22 |  |  | 202 | 202 | 202 | ER | Wind |  | Tande 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-150 | IFS-2016-002-15 | DISIS-2016-002-1 | 03 CENTRAL | Nemaha | KS | WERE | 2022-09-22 | 2023-12-07 |  |  | 302 | 302 | 302 | ER | Wind |  | Stranger Creek 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-149 | IFS-2016-002-14 | DISIS-2016-002-1 | 03 CENTRAL | Washington | KS | WERE | 2019-09-15 | 2023-12-07 |  |  | 302 | 302 | 302 | ER | Wind |  | Stranger Creek 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-147 | IFS-2016-002-33 | DISIS-2016-002-1 | 02 NEBRASKA | Cheyenne | NE | Tri-State | 2019-09-15 | 2024-06-28 |  |  | 40 | 40 | 40 | ER | Solar |  | Sidney 115 kV Sub | 2016-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-146 | IFS-2016-002-56 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 175 | 175 | 175 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-145 | IFS-2016-002-55 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 175 | 175 | 175 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-142 | IFS-2016-002-52 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 350 | 350 | 350 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-141 | IFS-2016-002-51 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 350 | 350 | 350 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-139 | IFS-2016-002-49 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 100 | 100 | 100 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-138 | IFS-2016-002-48 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 187.5 | 187.5 | 187.5 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-137 | IFS-2016-002-47 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 187.5 | 187.5 | 187.5 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-134 | IFS-2016-002-44 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 187.5 | 187.5 | 187.5 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-133 | IFS-2016-002-43 | DISIS-2016-002-1 | 04 SOUTHEAST | Texas | OK | AEP | 2020-09-01 | 2025-12-31 |  |  | 187.5 | 187.1 | 187.5 | ER | Wind |  | Riverside 345kV Substation | 2016-11-29 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-132 | IFS-2016-002-61 | DISIS-2016-002-1 | 04 SOUTHEAST | Roger Mills | OK | AEP | 2017-12-31 | 2020-06-05 |  |  | 6.1 | 6.1 | 6.1 | ER | Wind |  | Sweetwater 230kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-131 | IFS-2016-002-37 | DISIS-2016-002-1 | 04 SOUTHEAST | Grady | OK | OGE | 2017-12-31 | 2021-10-25 |  |  | 2.5 | 2.5 | 2.5 | ER | Wind |  | Minco 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-130 | IFS-2016-002-21 | DISIS-2016-002-1 | 01 NORTH | Mercer | ND | BEPC | 2019-09-15 | 2024-12-27 |  |  | 202 | 202 | 202 | ER | Wind |  | Leland Olds 345 kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-128 | IFS-2016-002-36 | DISIS-2016-002-1 | 04 SOUTHEAST | Alfalfa | OK | OGE | 2019-09-15 | 2026-12-31 |  |  | 176 | 176 | 176 | ER | Wind |  | Woodring 345kV | 2016-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-126 | IFS-2016-002-06 | DISIS-2016-002-1 | 04 SOUTHEAST | Murray | OK | OGE | 2019-12-31 | 2021-11-24 |  |  | 172.5 | 172.5 | 172.5 | ER/NR | Wind |  | Arbuckle 138kV substation | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-125 | IFS-2016-002-29 | DISIS-2016-002-1 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2019-12-31 | 2020-12-31 |  |  | 74 | 74 | 74 | ER | Wind |  | Eddy County-Tolk (Crossroads) 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-124 | IFS-2016-002-28 | DISIS-2016-002-1 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2019-12-31 | 2020-12-31 |  |  | 150 | 150 | 150 | ER | Wind |  | Eddy County-Tolk (Crossroads) 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-123 | IFS-2016-002-27 | DISIS-2016-002-1 | 05 SOUTHWEST | Roosevelt | NM | SPS | 2019-12-31 | 2020-12-31 |  |  | 298 | 298 | 298 | ER | Wind |  | Eddy County-Tolk (Crossroads) 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-121 | IFS-2016-002-26 | DISIS-2016-002-1 | 05 SOUTHWEST | Lea | NM | SPS | 2022-10-01 | 2024-12-31 |  |  | 110 | 110 | 110 | ER | Solar |  | Roadrunner 115kV | 2016-11-22 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-119 | IFS-2016-002-10 | DISIS-2016-002-1 | 04 SOUTHEAST | Kingfisher | OK | OGE | 2020-05-15 | 2025-12-31 |  |  | 600 | 600 | 600 | ER | Wind |  | Spring Creek-Sooner 345kV | 2016-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-118 | IFS-2016-002-05 | DISIS-2016-002-1 | 04 SOUTHEAST | Kingfisher | OK | WFEC | 2021-05-15 | 2021-09-10 |  |  | 288 | 288 | 288 | ER | Wind |  | Dover Switchyard 138 kV Line | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-115 | IFS-2016-002-24 | DISIS-2016-002-1 | 03 CENTRAL | Atchison | MO | GMO | 2020-11-16 | 2021-03-02 |  |  | 300 | 300 | 300 | ER | Wind |  | Nebraska City-Mullen Creek (Holt County MO) 345kV | 2016-11-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-111 | IFS-2016-002-18 | DISIS-2016-002-1 | 03 CENTRAL | McPherson | KS | Evergy | 2019-09-15 | 2027-01-15 |  |  | 302 | 302 | 302 | ER | Wind |  | Reno - Summit 345kV | 2016-11-30 |  | IA FULLY EXECUTED/ON SCHEDULE | Suspension Start Date of 3/24/2021
GEN-2016-102 | IFS-2016-002-01 | DISIS-2016-002-1 | 04 SOUTHEAST | Pontotoc | OK | OGE | 2023-11-01 | 2024-12-01 |  |  | 150.9 | 150.9 | 150.9 | ER/NR | Wind |  | Blue River 138kV | 2016-11-07 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-097 | IFS-2016-002-31 | DISIS-2016-002-1 | 04 SOUTHEAST | Caddo | OK | AEP | 2020-09-01 | 2024-01-01 |  |  | 100 | 100 | 100 | ER/NR | Wind |  | Tap Southwestern-Fletcher Tap 138kV | 2016-10-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-095 | IFS-2016-002-32 | DISIS-2016-002-1 | 04 SOUTHEAST | Caddo | OK | AEP | 2020-09-01 | 2024-04-22 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Gracemont-Lawton East Side 345kV | 2020-12-01 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-094 | IFS-2016-002-25 | DISIS-2016-002-1 | 01 NORTH | Hyde | SD | WAPA | 2020-10-01 | 2024-01-24 |  |  | 200 | 200 | 200 | ER | Wind |  | Tap Ft Thompson - Oahe 230kV Line (Single Circuit) | 2016-10-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-091 | IFS-2016-002-22 | DISIS-2016-002-1 | 04 SOUTHEAST | Caddo | OK | AEP | 2020-05-06 | 2022-01-08 |  |  | 303.6 | 303.6 | 303.6 | ER | Wind |  | Gracemont-Lawton East Side 345kV | 2016-10-03 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-087 | IFS-2016-002-59 | DISIS-2016-002-1 | 01 NORTH | Campbell | SD | WAPA | 2019-11-15 | 2026-12-31 |  |  | 98.9 | 98.9 | 98.9 | ER | Wind |  | Bismark-Glenham 230 kV line | 2016-07-25 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-075 | IFS-2016-001-21 | DISIS-2016-001-3 | 02 NEBRASKA | Holt | NE | WAPA | 2017-12-31 | 2024-12-31 |  |  | 50 | 50 | 50 | ER | Wind |  | Fort Thompson-Grand Island (Grand Prairie) 345kV | 2016-03-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-074 | IFS-2016-002-57 | DISIS-2016-002-1 | 02 NEBRASKA | Custer | NE | NPPD | 2020-10-30 | 2027-07-01 |  |  | 200 | 200 | 200 | ER | Wind |  | Sweetwater 345kV | 2016-04-14 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-071 | IFS-2016-001-19 | DISIS-2016-001-3 | 04 SOUTHEAST | Kay | OK | OGE | 2018-09-30 | 2027-02-27 |  |  | 200.1 | 200.1 | 200.1 | ER | Wind |  | Middleton Tap 138kV Substation | 2016-03-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-070 | IFS-2016-001-18 | DISIS-2016-001-3 | 05 SOUTHWEST | Carson | TX | SPS | 2016-11-01 | 2020-12-11 |  |  | 5.3 | 5.3 | 5.3 | ER | Wind |  | Martin 115 kV Substation | 2016-03-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-068 | IFS-2016-001-40 | DISIS-2016-001-3 | 04 SOUTHEAST | Garfield | OK | OGE | 2020-09-18 | 2020-12-15 |  |  | 250 | 250 | 250 | ER | Wind |  | Woodring 345kV | 2016-03-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-067 | IFS-2016-001-33 | DISIS-2016-001-3 | 03 CENTRAL | Thomas | KS | SUNC | 2017-11-01 | 2019-07-24 |  |  | 73.6 | 73.6 | 73.6 | ER | Wind |  | Mingo 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-061 | IFS-2016-001-15 | DISIS-2016-001-3 | 04 SOUTHEAST | Garfield/Noble | OK | OGE | 2017-12-01 | 2020-11-21 |  |  | 250.7 | 250.7 | 250.7 | ER | Wind |  | Sooner-Woodring 345 kV line | 2016-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-057 | IFS-2016-001-35 | DISIS-2016-001-3 | 04 SOUTHEAST | Cimarron, Texas County | OK | OGE | 2018-08-31 | 2022-03-18 |  |  | 499.1 | 499.1 | 499.1 | ER | Wind |  | Mathewson 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-051 | IFS-2016-001-13 | DISIS-2016-001-3 | 04 SOUTHEAST | Custer | OK | AEP |  | 2020-12-18 |  |  | 9.8 | 9.8 | 9.8 | ER | Wind |  | Clinton Junction-Weatherford Southeast 138kV | 2016-03-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-050 | IFS-2016-001-42 | DISIS-2016-001-3 | 02 NEBRASKA | Webster Co | NE | NPPD | 2017-12-01 | 2021-12-09 |  |  | 250.7 | 250.7 | 250.7 | ER | Wind |  | Axtell â€“ Post Rock 345 kV | 2016-03-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-047 | IFS-2016-001-22 | DISIS-2016-001-3 | 04 SOUTHEAST | Canadian | OK | OGE | 2017-12-31 | 2018-03-24 |  |  | 24 | 8 | 24 | ER | Thermal | CT | Mustang 69kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-046 | IFS-2016-001-12 | DISIS-2016-001-3 | 03 CENTRAL | Ford County | KS | SUNC | 2018-12-01 | 2021-12-23 |  |  | 299 | 299 | 299 | ER | Wind |  | Clark County-Ironwood 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-045 | IFS-2016-001-34 | DISIS-2016-001-3 | 04 SOUTHEAST | Cimarron, Texas County | OK | OGE | 2018-08-31 | 2022-03-18 |  |  | 499.1 | 499.1 | 499.1 | ER | Wind |  | Mathewson 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-043 | IFS-2016-001-36 | DISIS-2016-001-3 | 02 NEBRASKA | Wayne County | NE | NPPD | 2018-09-01 | 2020-06-27 |  |  | 230 | 230 | 230 | ER | Wind |  | Hoskins 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-037 | IFS-2017-001-32 | DISIS-2017-001 | 04 SOUTHEAST | Washita County | OK | AEP | 2021-06-01 | 2023-03-21 |  |  | 300 | 300 | 300 | ER | Wind |  | Chisholm-Gracemont 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-036 | IFS-2016-002-42 | DISIS-2016-002-1 | 01 NORTH | Chippewa County | MN | WAPA | 2018-11-17 | 2018-12-30 |  |  | 44.6 | 44.6 | 44.6 | ER | Wind |  | Granite Falls 115kV substation | 2016-03-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-032 | IFS-2016-001-11 | DISIS-2016-001-3 | 04 SOUTHEAST | Kingfisher Co | OK | OGE | 2023-02-01 | 2024-04-11 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Crescent Substation 138 kV | 2016-03-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-031 | IFS-2016-001-10 | DISIS-2016-001-3 | 04 SOUTHEAST | Kay County | OK | OGE | 2016-11-30 | 2016-12-17 |  |  | 1.5 | 1.5 | 1.5 | ER | Wind |  | Rose Hill (Open Sky)-Sooner (Ranch Road) 345kV | 2016-03-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-030 | IFS-2016-001-26 | DISIS-2016-001-3 | 04 SOUTHEAST | Johnston Co | OK | OGE | 2021-08-28 | 2026-03-31 |  |  | 100 | 100 | 100 | ER/NR | Solar |  | Brown 138kV | 2016-03-30 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-028 | IFS-2016-001-38 | DISIS-2016-001-3 | 04 SOUTHEAST | Le Flore Co | OK | AEP | 2018-12-31 | 2019-12-27 |  |  | 100 | 100 | 100 | ER | Wind |  | Clayton 138 kV Sub | 2016-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-022 | IFS-2016-001-29 | DISIS-2016-001-3 | 04 SOUTHEAST | Newkirk, Kay County | OK | OGE | 2017-12-31 | 2020-12-10 |  |  | 151.8 | 151.8 | 151.8 | ER | Wind |  | Rose Hill (Open Sky)-Sooner (Ranch Road) 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-021 | IFS-2016-001-31 | DISIS-2016-001-3 | 02 NEBRASKA | Dixon County | NE | NPPD | 2018-12-01 | 2022-03-09 |  |  | 298.47 | 298.47 | 298.47 | ER | Wind |  | Hoskins 345kV | 2016-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-020 | IFS-2016-001-27 | DISIS-2016-001-3 | 04 SOUTHEAST | Woodward County | OK | WFEC | 2018-12-31 | 2020-12-18 |  |  | 148.4 | 148.4 | 148.4 | ER | Wind |  | Moreland 138kV Substation | 2016-04-01 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-017 | IFS-2016-001-08 | DISIS-2016-001-3 | 01 NORTH | Hyde County | SD | BEPC | 2017-12-01 | 2020-11-23 |  |  | 250.24 | 250.24 | 250.24 | ER | Wind |  | Chappelle Creek 345kV | 2016-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-014 | IFS-2016-001-04 | DISIS-2016-001-3 | 03 CENTRAL | Joplin | MO | EDE | 2003-04-25 | 2020-04-30 |  |  | 10 | 10 | 10 | ER | Thermal | CT | LaRussell Energy Center 161kV | 2016-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-013 | IFS-2016-001-03 | DISIS-2016-001-3 | 03 CENTRAL | Joplin | MO | EDE | 2003-04-25 | 2020-04-30 |  |  | 10 | 10 | 10 | ER | Thermal | CT | LaRussell Energy Center 161kV | 2016-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-009 | IFS-2016-001-02 | DISIS-2016-001-3 | 03 CENTRAL | Ponca City | OK | OGE | 2018-09-30 | 2020-11-18 |  |  | 29 | 29 | 29 | ER | Thermal | Steam Turbine | Osage 69 kV Sub | 2016-03-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2016-004 | IFS-2016-001-25 | DISIS-2016-001-3 | 01 NORTH | Oliver | ND | BEPC | 2022-10-05 | 2025-12-31 |  |  | 202 | 202 | 202 | ER/NR | Wind |  | Basin Electric 230 kV | 2016-03-10 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2016-003 | IFS-2016-001-45 | DISIS-2016-001-3 | 04 SOUTHEAST | Ellis | OK | OGE | 2017-12-31 | 2022-12-21 |  |  | 250.4 | 250.4 | 250.4 | ER | Wind |  | Badger-Woodward EHV Dbl Ckt 345kV | 2016-03-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-096 | IFS-2015-002-43 | DISIS-2015-002-7 | 01 NORTH | Hettinger County | ND | BEPC | 2017-12-31 | 2016-12-29 |  |  | 150 | 150 | 150 | ER | Wind |  | Brady 230kV substation | 2015-10-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-090 | IFS-2015-002-21 | DISIS-2015-002-7 | 03 CENTRAL | Pratt | KS | WERE | 2017-12-01 | 2018-12-14 |  |  | 220 | 220 | 220 | ER | Wind |  | Thistle-Wichita Dbl Ckt (Buffalo Flats) 345kV | 2015-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-089 | IFS-2016-001-05 | DISIS-2016-001-3 | 01 NORTH | Bon Homme | SD | WAPA | 2017-06-30 | 2020-04-22 |  |  | 200 | 200 | 200 | ER | Wind |  | Utica 230 kV Substation | 2015-10-13 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-088 | IFS-2015-002-32 | DISIS-2015-002-7 | 02 NEBRASKA | Saline | NE | NPPD | 2019-01-01 | 2020-12-29 |  |  | 300 | 300 | 300 | ER/NR | Wind |  | Tobias 345kV Substation | 2015-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-082 | IFS-2016-001-28 | DISIS-2016-001-3 | 05 SOUTHWEST | Beaver | OK | OGE | 2017-12-01 | 2020-11-25 |  |  | 200 | 200 | 200 | ER | Wind |  | Beaver County - Woodward EHV Dbl Ckt (Badger) 345kV | 2015-09-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-073 | IFS-2015-002-20 | DISIS-2015-002-7 | 03 CENTRAL | Lyon County | KS | WERE | 2018-12-31 | 2019-12-19 |  |  | 200.1 | 200.1 | 200.1 | ER/NR | Wind |  | Emporia 345kV | 2015-09-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-069 | IFS-2015-002-06 | DISIS-2015-002-7 | 03 CENTRAL | Dickenson / Marion Counties | KS | WERE | 2017-12-01 | 2018-12-17 |  |  | 300 | 300 | 300 | ER | Wind |  | Union Ridge 230kV | 2015-09-21 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-066 | IFS-2015-002-38 | DISIS-2015-002-7 | 04 SOUTHEAST | Pawnee | OK | OGE | 2017-12-01 | 2025-12-31 |  |  | 248.4 | 248.4 | 248.4 | ER | Wind |  | Sooner - Cleveland 345kV | 2015-10-07 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2015-065 | IFS-2015-002-19 | DISIS-2015-002-7 | 03 CENTRAL | Thomas County | KS | SUNC | 2017-11-01 | 2019-07-01 |  |  | 202.4 | 202.4 | 202.4 | ER | Wind |  | Mingo 345kV | 2015-10-07 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-064 | IFS-2015-002-18 | DISIS-2015-002-7 | 03 CENTRAL | Thomas County | KS | SUNC | 2017-11-01 | 2020-03-26 |  |  | 197.8 | 197.8 | 197.8 | ER | Wind |  | Mingo 115kV | 2015-10-07 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-063 | IFS-2015-002-16 | DISIS-2015-002-7 | 04 SOUTHEAST | Kingfisher County | OK | OGE | 2017-12-01 | 2018-01-01 |  |  | 300 | 300 | 300 | ER | Wind |  | Woodring-Matthewson 345kV | 2015-10-06 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-062 | IFS-2015-002-15 | DISIS-2015-002-7 | 04 SOUTHEAST | Garfield County | OK | OGE | 2016-03-01 | 2024-08-27 |  |  | 4.5 | 4.5 | 4.5 | ER | Wind |  | Breckinridge 138kV | 2015-10-06 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-057 | IFS-2015-002-33 | DISIS-2015-002-7 | 04 SOUTHEAST | Grady County | OK | OGE | 2016-12-01 | 2018-12-22 |  |  | 100 | 100 | 100 | ER | Wind |  | Minco 345kV | 2015-10-06 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-052 | IFS-2015-002-03 | DISIS-2015-002-7 | 03 CENTRAL | Sumner | KS | WERE | 2017-12-01 | 2025-06-01 |  |  | 300 | 300 | 300 | ER | Wind |  | Open Sky-Rose Hill 345kV | 2015-10-05 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2015-048 | IFS-2015-002-11 | DISIS-2015-002-7 | 04 SOUTHEAST | Major County, OK | OK | OGE | 2017-12-01 | 2021-04-14 |  |  | 200 | 200 | 200 | ER | Wind |  | Cleo Corner 138kV | 2015-10-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-047 | IFS-2015-002-02 | DISIS-2015-002-7 | 04 SOUTHEAST | Noble County | OK | OGE | 2017-12-01 | 2018-01-01 |  |  | 300 | 300 | 300 | ER | Wind |  | Sooner 345kV | 2015-10-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-046 | IFS-2015-002-46 | DISIS-2015-002-7 | 01 NORTH | Williams County | ND | BEPC | 2017-12-01 | 2021-05-27 |  |  | 300 | 300 | 300 | ER | Wind |  | Tande 345kV | 2015-10-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-045 | IFS-2015-002-10 | DISIS-2015-002-7 | 04 SOUTHEAST | Grady County | OK | AEP | 2017-12-01 | 2020-02-02 |  |  | 20 | 20 | 20 | ER | Battery/Storage |  | Lawton East Side-Sunnyside (Terry Road) 345kV | 2015-10-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-041 | IFS-2015-002-41 | DISIS-2016-001 | 05 SOUTHWEST | Hale County | TX | SPS | 2015-07-01 | 2019-10-19 |  |  | 5 | 5 | 0 | ER | Thermal | CT | TUCO 345kV | 2015-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-036 | IFS-2016-001-44 | DISIS-2016-001-3 | 04 SOUTHEAST | Johnston County | OK | OGE | 2017-12-31 | 2020-12-13 |  |  | 303.6 | 303.6 | 303.6 | ER | Wind |  | Johnston County 345kV | 2015-09-10 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-034 | IFS-2015-002-08 | DISIS-2015-002-7 | 04 SOUTHEAST | Kay County | OK | OGE | 2017-10-31 | 2020-12-10 |  |  | 200 | 200 | 200 | ER | Wind |  | Rose Hill (Open Sky)-Sooner (Ranch Road) 345kV | 2015-08-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-025 | IFS-2015-001-03 | DISIS-2015-001-4 | 03 CENTRAL | Pratt | KS | WERE | 2016-12-31 | 2016-12-19 |  |  | 220 | 220 | 220 | ER | Wind |  | Tap Thistle â€“ Wichita 345kV Dbl CKT | 2015-03-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-024 | IFS-2015-001-02 | DISIS-2015-001-4 | 03 CENTRAL | Pratt County | KS | WERE | 2016-12-31 | 2016-12-09 |  |  | 220 | 220 | 220 | ER | Wind |  | Thistle-Wichita Dbl Ckt (Buffalo Flats) 345kV | 2015-03-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-023 | IFS-2015-001-08 | DISIS-2015-001-4 | 02 NEBRASKA | Antelope & Wheeler County | NE | NPPD | 2019-12-31 | 2022-11-16 |  |  | 300.7 | 300.7 | 300.7 | ER/NR | Wind |  | Grand Prairie-Grand Island (Holt County NE) 345kV | 2015-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-021 | IFS-2015-001-16 | DISIS-2015-001-4 | 03 CENTRAL | Stanton | KS | SUNC | 2016-12-31 | 2020-04-07 |  |  | 20 | 20 | 20 | ER/NR | Solar |  | Johnson Corner 115kV | 2015-04-01 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-016 | IFS-2015-001-05 | DISIS-2015-001-4 | 03 CENTRAL | Allen County | KS | KCPL | 2017-12-31 | 2019-09-11 |  |  | 200 | 200 | 200 | ER/NR | Wind |  | Tap Marmaton - Centerville 161kV | 2015-03-20 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-015 | IFS-2015-001-14 | DISIS-2015-001-4 | 04 SOUTHEAST | Grant County | OK | OGE | 2016-07-31 | 2017-12-08 |  |  | 154.56 | 154.56 | 154.56 | ER/NR | Wind |  | Tap Medford Tap â€“ Coyote 138kV | 2015-03-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-014 | IFS-2015-001-20 | DISIS-2015-001-4 | 05 SOUTHWEST | Cochran County | TX | SPS | 2016-12-01 | 2018-12-15 |  |  | 150 | 150 | 150 | ER | Wind |  | Tap Cochran - Lehman 115kV substation | 2015-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-013 | IFS-2015-001-18 | DISIS-2015-001-4 | 04 SOUTHEAST | Kiowa County | OK | WFEC | 2016-12-01 | 2024-05-23 |  |  | 120 | 120 | 120 | ER/NR | Solar |  | Snyder 138kV | 2015-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-007 | IFS-2015-001-01 | DISIS-2015-001-4 | 02 NEBRASKA | Wayne County | NE | NPPD | 2019-11-08 | 2019-12-31 |  |  | 160 | 160 | 160 | ER | Wind |  | Hoskins 345kV | 2015-03-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-005 | IFS-2015-001-04 | DISIS-2015-001-4 | 03 CENTRAL | DeKalb County | MO | GMO | 2017-12-31 | 2016-12-16 |  |  | 200.1 | 200.1 | 200.1 | ER | Wind |  | Mullen Creek-Sibley (Ketchum) 345kV | 2015-03-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2015-001 | IFS-2015-001-15 | DISIS-2015-001-4 | 04 SOUTHEAST | Kay | OK | OGE | 2016-12-31 | 2016-12-17 |  |  | 200 | 200 | 200 | ER | Wind |  | Rose Hill (Open Sky)-Sooner (Ranch Road) 345kV | 2015-03-04 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-064 | IFS-2014-002-24 | DISIS-2014-002-6 | 04 SOUTHEAST | Garfield | OK | OGE | 2016-12-01 | 2018-12-21 |  |  | 248.4 | 248.4 | 248.4 | ER | Wind |  | Otter 138kV | 2014-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-057 | IFS-2014-002-22 | DISIS-2014-002-6 | 04 SOUTHEAST | Grady | OK | AEP | 2016-12-31 | 2016-12-01 |  |  | 249.9 | 249.9 | 249.9 | ER | Wind |  | Lawton East Side-Sunnyside (Terry Road) 345kV | 2014-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-056 | IFS-2014-002-21 | DISIS-2014-002-6 | 04 SOUTHEAST | Canadian | OK | OGE | 2016-12-31 | 2018-12-22 |  |  | 250 | 250 | 250 | ER | Wind |  | Minco 345kV | 2014-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-040 | IFS-2014-002-14 | DISIS-2014-002-6 | 05 SOUTHWEST | Castro | TX | SPS | 2016-09-01 | 2016-12-30 |  |  | 320 | 320 | 320 | ER | Wind |  | Castro 115kV | 2014-09-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-035 | IFS-2014-002-12 | DISIS-2014-002-6 | 05 SOUTHWEST | Chaves | NM | SPS | 2016-12-31 | 2023-04-24 |  |  | 30 | 30 | 30 | ER | Solar |  | Chaves County 115kV | 2014-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-034 | IFS-2014-002-11 | DISIS-2014-002-6 | 05 SOUTHWEST | Chaves | NM | SPS | 2016-12-31 | 2016-10-21 |  |  | 70 | 70 | 70 | ER | Solar |  | Chaves County 115kV | 2014-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-033 | IFS-2014-002-10 | DISIS-2014-002-6 | 05 SOUTHWEST | Chaves | NM | SPS | 2016-12-31 | 2016-08-25 |  |  | 70 | 70 | 70 | ER | Solar |  | Chaves County 115kV | 2014-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-032 | IFS-2014-002-09 | DISIS-2014-002-6 | 02 NEBRASKA | Antelope | NE | NPPD | 2015-10-01 | 2014-05-01 |  |  | 10.2 | 10.2 | 10.2 | ER/NR | Wind |  | Meadow Grove 230kV | 2014-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-031 | IFS-2014-002-08 | DISIS-2014-002-6 | 02 NEBRASKA | Antelope County | NE | NPPD | 2015-10-01 | 2016-03-30 |  |  | 35.8 | 35.8 | 35.8 | ER/NR | Wind |  | Meadow Grove 230kV | 2014-09-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-028 | IFS-2014-002-07 | DISIS-2014-002-6 | 03 CENTRAL | Cherokee County | KS | EDE | 2016-01-01 | 2016-04-01 |  |  | 50 | 0 | 50 | ER | Thermal | CC | Riverton 161kV | 2014-09-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-025 | IFS-2014-002-05 | DISIS-2014-002-6 | 03 CENTRAL | Rush | KS | MIDW | 2015-10-15 | 2015-12-01 |  |  | 2.42 | 2.42 | 2.42 | ER | Wind |  | Tap Nekoma - Bazine (Walnut Creek) 69kV | 2014-09-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-021 | IFS-2014-002-04 | DISIS-2014-002-6 | 03 CENTRAL | Atchison | MO | GMO | 2016-12-01 | 2017-11-07 |  |  | 300 | 300 | 300 | ER/NR | Wind |  | Nebraska City-Mullen Creek (Holt County MO) 345kV | 2014-09-02 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-020 | IFS-2014-002-03 | DISIS-2014-002-6 | 04 SOUTHEAST | Grady | OK | AEP | 2014-12-31 | 2017-10-10 |  |  | 100 | 100 | 100 | ER/NR | Wind |  | Tuttle 138kV | 2014-07-14 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-013 | IFS-2014-001-07 | DISIS-2014-001-1 | 02 NEBRASKA | Antelope / Boone | NE | NPPD | 2014-12-31 | 2015-12-18 |  |  | 73.5 | 73.5 | 73.5 | ER/NR | Wind |  | Meadow Grove 230kV | 2014-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-005 | IFS-2014-001-05 | DISIS-2014-001-1 | 04 SOUTHEAST | Caddo | OK | OGE |  | 2015-06-01 |  |  | 5.7 | 5.7 | 5.7 | ER | Wind |  | Minco 345kV | 2014-02-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-004 | IFS-2014-001-04 | DISIS-2014-001-1 | 02 NEBRASKA | Jefferson | NE | NPPD |  | 2013-10-29 |  |  | 3.96 | 3.96 | 3.96 | ER | Wind |  | Steele City 115kV | 2014-02-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-002 | IFS-2014-001-02 | DISIS-2014-001-1 | 04 SOUTHEAST | Dewey | OK | OGE | 2014-12-31 | 2015-04-08 |  |  | 10.5 | 10.5 | 10.5 | ER | Wind |  | Tatonga 345kV | 2014-02-18 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-001IS | IFS-2015-001-21 | DISIS-2015-002 Prior Queued | 01 NORTH | Butte | SD | WAPA | 2015-12-15 | 2020-09-24 |  |  | 103.24 | 103.24 | 103.24 | ER | Wind |  | Sulphur 115kV | 2015-11-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2014-001 | IFS-2014-001-08 | DISIS-2014-001-1 | 03 CENTRAL | Marion | KS | WERE | 2014-07-15 | 2023-08-11 |  |  | 200.6 | 200.6 | 200.6 | ER | Wind |  | Tap Wichita - Emporia Energy Center 345kV | 2014-01-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-033 | IFS-2013-002-07 | DISIS-2013-002-2 | 03 CENTRAL | Ellis | KS | MIDW | 2015-12-31 | 2016-02-27 |  |  | 28 | 28 | 28 | ER/NR | Thermal | Gas | Goodman Energy Center 115kV | 2013-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-032 | IFS-2013-002-06 | DISIS-2013-002-2 | 02 NEBRASKA | Antelope | NE | NPPD | 2016-12-31 | 2018-12-20 |  |  | 202.5 | 202.5 | 202.5 | ER | Wind |  | Antelope 115kV | 2013-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-029 | IFS-2013-002-04 | DISIS-2013-002-2 | 04 SOUTHEAST | Grant | OK | OGE | 2015-12-15 | 2016-04-08 |  |  | 299 | 299 | 299 | ER | Wind |  | Renfrow 345kV | 2013-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-028 | IFS-2013-002-03 | DISIS-2013-002-2 | 04 SOUTHEAST | Mayes | OK | GRDA | 2016-04-16 | 2017-12-23 |  |  | 538 | 495 | 538 | ER | Thermal | Gas | Tap N Tulsa - GRDA 1 345kV | 2013-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-027 | IFS-2014-002-02 | DISIS-2014-002-6 | 05 SOUTHWEST | Bailey | TX | SPS | 2016-03-31 | 2018-12-10 |  |  | 148.4 | 148.4 | 148.4 | ER/NR | Wind |  | Tolk - Yoakum 230kV | 2013-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-022 | IFS-2013-002-02 | DISIS-2013-002-2 | 05 SOUTHWEST | Quay | NM | SPS | 2015-05-01 | 2016-12-07 |  |  | 25 | 25 | 25 | ER/NR | Solar |  | Norton 115kV Switching Station | 2013-09-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-019 | IFS-2013-002-01 | DISIS-2013-002-2 | 02 NEBRASKA | Lancaster | NE | NPPD | 2014-06-30 | 2026-12-01 |  |  | 73.6 | 73.6 | 73.6 | ER/NR | Hybrid | Wind/Solar | Monolith 115kV | 2013-04-17 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2013-016 | IFS-2013-001-03 | DISIS-2013-001-4 | 05 SOUTHWEST | Hale | TX | SPS | 2016-12-01 | 2019-10-19 |  |  | 203 | 191 | 203 | ER | Thermal | CT | TUCO 345kV | 2013-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-012 |  | DISIS-2013-001-4 | 04 SOUTHEAST | Logan County | OK | OGE | 2014-11-30 | 2014-08-11 |  |  | 147 | 68 | 147 | ER | Thermal | Gas | Redbud 345kV | 2013-03-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-011 | IFS-2013-001-02 | DISIS-2013-001-4 | 04 SOUTHEAST | Hempstead | AR | AEP |  | 2012-12-18 |  |  | 30 | 40 | 30 | ER | Thermal | Coal | Turk 138kV | 2013-03-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-008 |  | DISIS-2013-001-4 | 02 NEBRASKA | Jefferson | NE | NPPD | 2013-12-31 | 2013-12-31 |  |  | 1.2 | 1.2 | 1.2 | ER | Wind |  | Steele City 115kV | 2013-03-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-007 |  | DISIS-2013-001-4 | 04 SOUTHEAST | Murray | OK | OGE | 2014-12-31 | 2015-11-23 |  |  | 100 | 100 | 100 | ER/NR | Wind |  | Tap Prices Falls - Carter 138kV | 2013-03-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2013-002 | IFS-2013-001-01 | DISIS-2013-001-4 | 02 NEBRASKA | Lancaster | NE | NPPD | 2013-12-31 | 2026-12-01 |  |  | 50.6 | 50.6 | 50.6 | ER/NR | Hybrid | Wind/Solar | Monolith 115kV | 2013-03-01 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2012-044 |  |  |  | Crawford | KS | WERE | 2013-11-30 | 2013-11-01 |  |  | 2 | 2 | 2 | ER | Thermal | Gas | Sheffield 69kV | 2012-12-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-041 |  | DISIS-2012-002-6 | 04 SOUTHEAST | Kay | OK | OGE | 2015-04-15 | 2015-04-15 |  |  | 121.5 | 85.3 | 121.5 | ER | Thermal | CT | Rose Hill (Open Sky)-Sooner (Ranch Road) 345kV | 2012-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-037 |  | DISIS-2012-002-6 | 05 SOUTHWEST | Hale | TX | SPS | 2015-03-01 | 2015-03-01 |  |  | 203 | 196 | 203 | ER | Thermal | CT | TUCO 345kV | 2012-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-036 |  | DISIS-2012-002-6 | 05 SOUTHWEST | Yoakum | TX | SPS | 2013-06-01 | 2013-03-01 |  |  | 7 | 7 | 7 | ER | Thermal | CT | Mustang 230kV | 2012-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-035 |  | DISIS-2012-002-6 | 05 SOUTHWEST | Yoakum | TX | SPS | 2013-06-01 | 2015-04-01 |  |  | 7 | 7 | 7 | ER | Thermal | CT | Mustang 230kV | 2012-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-034 |  | DISIS-2012-002-6 | 05 SOUTHWEST | Yoakum | TX | SPS | 2013-06-01 | 2015-04-01 |  |  | 7 | 7 | 7 | ER | Thermal | CT | Mustang 230kV | 2012-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-033 |  | DISIS-2012-002-6 | 04 SOUTHEAST | Garfield | OK | OGE | 2014-12-01 | 2015-09-01 |  |  | 98.82 | 98.82 | 98.82 | ER | Wind |  | Breckinridge 138kV | 2012-09-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-032 |  | DISIS-2012-002-6 | 04 SOUTHEAST | Kay | OK | OGE | 2014-11-30 | 2015-06-30 |  |  | 299 | 299 | 299 | ER | Wind |  | Rose Hill-(Ranch Road) Sooner (Open Sky) 345kV | 2012-09-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-028 |  | DISIS-2012-002-6 | 04 SOUTHEAST | Washita | OK | WFEC | 2014-12-01 | 2015-12-22 |  |  | 74 | 74 | 74 | ER | Wind |  | Gotebo 69kV | 2012-09-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-024 | IFS-2012-002-01 | DISIS-2012-002-6 | 03 CENTRAL | Ford | KS | SUNC | 2015-12-31 | 2017-06-01 |  |  | 180 | 180 | 180 | ER | Wind |  | Clark County 345kV | 2012-09-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-021 |  | DISIS-2012-002-6 | 02 NEBRASKA | Lincoln | NE | LES | 2013-08-01 | 2013-12-01 |  |  | 4.8 | 4.8 | 4.8 | ER | Thermal | Gas | Terry Bundy Generating Station 115kV | 2012-09-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-020 |  | DISIS-2012-002-6 | 05 SOUTHWEST | Abernathy County | TX | SPS | 2015-09-30 | 2019-06-28 |  |  | 478 | 478 | 478 | ER | Wind |  | TUCO 230kV | 2012-09-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-007 |  | DISIS-2012-001-4 | 03 CENTRAL | Grant County | KS | SUNC | 2014-04-01 | 2014-04-15 |  |  | 120 | 120 | 120 | ER/NR | Thermal | Gas | Rubart 115kV | 2012-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-004 |  | DISIS-2012-001-4 | 04 SOUTHEAST | Carter County | OK | OGE | 2013-12-31 | 2014-11-21 |  |  | 40.8 | 40.8 | 40.8 | ER/NR | Wind |  | Pooleville-Ratliff (Carter County) 138kV | 2012-03-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2012-001 |  | DISIS-2012-001-4 | 05 SOUTHWEST | Lynn County Texas | TX | SPS | 2012-11-30 | 2012-12-21 |  |  | 61.2 | 61.2 | 61.2 | ER | Wind |  | Tap Grassland Â- Borden County 230 kv | 2012-03-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-057 |  | DISIS-2011-002-6 | 03 CENTRAL | Sumner County | KS | WERE | 2013-12-31 | 2015-12-30 |  |  | 150 | 150 | 150 | ER | Wind |  | Creswell 138kV | 2011-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-056B |  | DISIS-2011-002-6 | 02 NEBRASKA | North Platte - Lexington | NE | NPPD | 2012-06-30 | 2012-10-31 |  |  | 4.5 | 4.5 | 4.5 | ER | Hydro |  | John 2 115kV | 2012-03-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-056A |  | DISIS-2011-002-6 | 02 NEBRASKA | North Platte - Lexington | NE | NPPD | 2012-06-30 | 2012-10-31 |  |  | 3.6 | 3.6 | 3.6 | ER | Hydro |  | John 1 115kV | 2012-03-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-056 |  | DISIS-2011-002-6 | 02 NEBRASKA | North Platte - Lexington | NE | NPPD | 2012-06-30 | 2012-10-31 |  |  | 3.6 | 3.6 | 3.6 | ER | Hydro |  | Jeffrey 115kV | 2011-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-054 |  | DISIS-2011-002-6 | 04 SOUTHEAST | Canadian County | OK | OGE | 2013-11-30 | 2014-12-31 |  |  | 300 | 300 | 300 | ER | Wind |  | Cimarron 345kV | 2011-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-050 |  | DISIS-2011-002-6 | 04 SOUTHEAST | Grady County | OK | AEP | 2013-12-31 | 2016-12-13 |  |  | 108 | 108 | 108 | ER | Wind |  | Tap Rush Springs Â- Marlow 138kV | 2011-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-048 |  | DISIS-2011-002-6 | 05 SOUTHWEST | Denver City | TX | SPS | 2013-03-01 | 2013-03-01 |  |  | 175 | 165 | 175 | ER/NR | Thermal | CT | Mustang 230kV | 2011-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-046 |  | DISIS-2011-002-6 | 05 SOUTHWEST | Quay County | NM | SPS | 2013-06-01 | 2013-09-05 |  |  | 23 | 23 | 23 | ER | Thermal | CT | Tucumcari 115kV | 2011-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-045 |  | DISIS-2011-002-6 | 05 SOUTHWEST | Lubbock | TX | SPS | 2013-06-01 | 2013-05-01 |  |  | 205 | 180 | 205 | ER | Thermal | NG/CT | Jones 230kV | 2011-09-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-040 |  | DISIS-2011-002-6 | 04 SOUTHEAST | Murray County | OK | OGE | 2012-12-31 | 2014-11-21 |  |  | 111 | 111 | 111 | ER/NR | Wind |  | Pooleville-Ratliff (Carter County) 138kV | 2011-09-16 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-037 |  | DISIS-2011-002-6 | 04 SOUTHEAST | Apache | OK | WFEC | 2012-01-01 | 2013-02-05 |  |  | 6.6 | 6.6 | 6.6 | ER | Wind |  | Blue Canyon 5 138kV | 2011-07-01 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-027 |  | DISIS-2011-001-8 | 02 NEBRASKA | Winside | NE | NPPD | 2012-12-31 | 2018-12-17 |  |  | 120 | 120 | 120 | ER/NR | Wind |  | Wakefield 230kV | 2011-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-025 |  | DISIS-2011-001-8 | 05 SOUTHWEST | Lorenzo | TX | SPS | 2012-06-30 | 2018-12-15 |  |  | 79.96 | 79.96 | 79.96 | ER | Wind |  | Tap Floyd County - Crosby County 115kV | 2011-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-022 |  | DISIS-2011-001-8 | 05 SOUTHWEST | Hansford | TX | SPS | 2012-12-31 | 2022-09-08 |  |  | 299 | 299 | 299 | ER | Wind |  | Hitchland 345kV | 2011-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-020 |  | DISIS-2011-001-8 | 04 SOUTHEAST | Ellis | OK | OGE | 2012-12-31 | 2027-10-31 |  |  | 165.6 | 165.6 | 165.6 | ER/NR | Wind |  | Woodward EHV 345kV | 2011-03-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2011-019 |  | DISIS-2011-001-8 | 04 SOUTHEAST | Woodward County | OK | OGE | 2012-12-31 | 2027-12-31 |  |  | 175 | 175 | 175 | ER/NR | Wind |  | Woodward EHV 345kV | 2011-03-31 |  | IA FULLY EXECUTED/ON SCHEDULE
GEN-2011-018 |  | DISIS-2011-001-8 | 02 NEBRASKA | Jefferson County | NE | NPPD | 2013-12-01 | 2013-12-31 |  |  | 73.6 | 73.6 | 73.6 | ER/NR | Wind |  | Steele City 115kV | 2011-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-014 |  | DISIS-2011-001-8 | 05 SOUTHWEST | Beaver County | OK | OGE | 2013-12-31 | 2016-12-20 |  |  | 198 | 198 | 198 | ER | Wind |  | Beaver CountyÂ-Woodward EHV Dbl Ckt (Badger) 345kV | 2011-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-011 |  | DISIS-2011-001-8 | 03 CENTRAL | Weston | MO | KCPL | 2010-12-31 | 2012-06-05 |  |  | 50 | 50 | 50 | ER | Thermal | Coal | Iatan 345kV | 2011-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-010 |  | DISIS-2011-001-8 | 04 SOUTHEAST | Caddo County | OK | OGE | 2012-12-01 | 2012-10-01 |  |  | 100.8 | 100.8 | 100.8 | ER | Wind |  | Minco 345kV | 2011-03-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2011-008 |  | DISIS-2011-001-8 | 03 CENTRAL | Clark County | KS | SUNC | 2015-12-01 | 2016-12-21 |  |  | 600 | 600 | 600 | ER | Wind |  | Clark County 345kV | 2011-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-057 |  | DISIS-2011-001-8 | 03 CENTRAL | Lincoln County | KS | MIDW | 2012-08-01 | 2012-09-28 |  |  | 201 | 201 | 201 | ER/NR | Wind |  | Rice County 230kV | 2010-10-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-055 |  | DISIS-2011-001-8 | 04 SOUTHEAST | Sand Springs | OK | AEP | 2011-12-31 | 2013-02-27 |  |  | 4.5 | 4.5 | 4.5 | ER | Thermal | Gas | Wekiwa 138kV | 2010-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-051 |  | DISIS-2010-002-6 | 02 NEBRASKA | Dixon County | NE | NPPD | 2012-12-15 | 2018-12-17 |  |  | 200 | 200 | 200 | ER | Wind |  | Wakefield 230kV | 2010-09-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-040 |  | DISIS-2010-002-6 | 04 SOUTHEAST | Canadian County | OK | OGE | 2011-11-30 | 2012-11-23 |  |  | 300 | 300 | 300 | ER | Wind |  | Cimarron 345kV | 2010-08-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-036 |  | DISIS-2010-002-6 | 03 CENTRAL | Douglas County | KS | WERE | 2012-08-01 | 2012-08-01 |  |  | 4.6 | 4.6 | 4.6 | ER | Hydro |  | 6th Street 115kV | 2010-06-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-014 |  | DISIS-2010-001-8 | 05 SOUTHWEST | Hansford County | TX | SPS | 2013-12-31 | 2022-12-31 |  |  | 358.8 | 358.8 | 358.8 | ER | Wind |  | Hitchland 345kV | 2010-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-011 |  | DISIS-2010-001-8 | 04 SOUTHEAST | Dewey County | OK | OGE | 2011-12-31 | 2012-02-28 |  |  | 29.7 | 29.7 | 29.7 | ER | Wind |  | Tatonga 345kV | 2010-03-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-009 |  | DISIS-2010-001-8 | 03 CENTRAL | Gray County | KS | SUNC | 2011-12-01 | 2012-12-31 |  |  | 165.6 | 165.6 | 165.6 | ER | Wind |  | Buckner 345kV | 2010-03-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-006 |  | DISIS-2010-001-8 | 05 SOUTHWEST | Lubbock | TX | SPS | 2012-06-01 | 2011-06-30 |  |  | 205 | 180 | 205 | ER | Thermal | Gas | Jones 230kV | 2010-03-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-005 |  | DISIS-2010-001-8 | 03 CENTRAL | Harper County | KS | WERE | 2012-12-01 | 2021-12-31 |  |  | 299.2 | 299.2 | 299.2 | ER | Wind |  | Viola 345kV | 2010-03-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-003 |  | DISIS-2010-001-8 | 03 CENTRAL | Coffey County | KS | WERE | 2011-12-31 | 2014-07-31 |  |  | 99.5 | 99.5 | 99.5 | ER | Wind |  | Waverly 345kV | 2010-03-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2010-001 |  | DISIS-2010-002-6 | 05 SOUTHWEST | Beaver County | OK | OGE | 2012-01-01 | 2015-05-15 |  |  | 300 | 300 | 300 | ER | Wind |  | Hitchland-Woodward EHV Dbl Ckt (Beaver County) 345kV | 2010-03-03 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2009-040 |  | DISIS-2010-001-8 | 03 CENTRAL | Marshall County | KS | WERE | 2012-12-31 | 2016-09-03 |  |  | 72 | 72 | 72 | ER | Wind |  | Tap Smittyville - Knob Hill 115KV | 2009-08-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2009-025 |  | DISIS-2009-001-6 | 04 SOUTHEAST | Kay County | OK | OGE | 2011-12-31 | 2012-11-01 |  |  | 59.8 | 59.8 | 59.8 | ER | Wind |  | TAP Deer Creek â€“ Sinclair 69kV | 2009-06-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2009-020 |  | DISIS-2010-001-8 | 03 CENTRAL | Rush County | KS | MIDW | 2011-12-31 | 2015-10-15 |  |  | 48.3 | 48.3 | 48.3 | ER | Wind |  | Tap Nekoma - Bazine (Walnut Creek) 69kV | 2009-04-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2009-008 |  | DISIS-2010-001-8 | 03 CENTRAL | Ness County | KS | MIDW | 2011-09-01 | 2015-12-01 |  |  | 198.69 | 198.69 | 198.69 | ER | Wind |  | South Hays 230kV | 2009-03-10 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-129 |  | DISIS-2009-001-6 | 03 CENTRAL | Cass County | MO | MIPU | 2009-05-01 | 2002-02-15 |  |  | 72 | 643 | 675 | ER | Thermal | CT | Pleasant Hill 161kV | 2008-12-12 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-124 |  | DISIS-2009-001-6 | 03 CENTRAL | Ford County | KS | SUNC | 2016-01-01 | 2017-02-28 |  |  | 200.1 | 200.1 | 200.1 | ER | Wind |  | Clark County-Spearville Ckt 1 (Ironwood) 345kV | 2008-11-14 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-123N |  | DISIS-2010-001-8 | 02 NEBRASKA | Webster County | NE | NPPD | 2016-12-31 | 2017-11-16 |  |  | 89.66 | 89.66 | 89.66 | ER | Wind |  | Tap Pauline - Hildreth (Rosemont) 115kV | 2008-11-12 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-119O |  | ICS-2008-001 Prior Queued | 02 NEBRASKA | Richardson County | NE | OPPD | 2009-12-31 |  |  |  | 60 | 60 | 60 | ER | Wind |  | S1399 161kV | 2008-10-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-098 |  | DISIS-2010-001-8 | 03 CENTRAL | Coffey County | KS | WERE | 2011-12-31 | 2015-11-30 |  |  | 99.5 | 99.5 | 99.5 | ER | Wind |  | Waverly 345kV | 2008-08-22 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-092 |  | DISIS-2009-001-6 | 03 CENTRAL | Ellis County | KS | MIDW | 2011-12-01 | 2015-11-30 |  |  | 200.5 | 200.5 | 200.5 | ER | Wind |  | Post Rock 230kV | 2008-08-18 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-086N02 |  | DISIS-2009-001-6 | 02 NEBRASKA | Antelope County | NE | NPPD |  | 2014-12-31 |  |  | 201 | 201 | 201 | ER | Wind |  | Meadow Grove 230kV | 2008-08-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-079 |  | DISIS-2009-001-6 | 03 CENTRAL | Gray County | KS | MKEC | 2010-12-01 | 2011-11-02 |  |  | 98.9 | 98.9 | 98.9 | ER | Wind |  | Crooked Creek 115kV | 2008-07-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-051 |  | DISIS-2009-001-6 | 05 SOUTHWEST | Oldham County | TX | SPS | 2010-12-31 | 2014-12-31 |  |  | 161 | 161 | 161 | ER | Wind |  | Potter County 345kV | 2008-05-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-047 |  | DISIS-2010-001-8 | 05 SOUTHWEST | Beaver County | OK | OGE | 2012-12-31 | 2014-12-31 |  |  | 263.13 | 263.13 | 263.13 | ER | Wind |  | Hitchland-Woodward EHV Dbl Ckt (Beaver County) 345kV | 2008-05-16 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-044 |  | DISIS-2010-001-8 | 04 SOUTHEAST | Dewey County | OK | OGE | 2011-12-01 | 2012-02-28 |  |  | 197.8 | 197.8 | 197.8 | ER | Wind |  | Tatonga 345kV | 2008-05-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-037 |  | DISIS-2010-001-8 | 04 SOUTHEAST | Commanche County | OK | WFEC | 2011-11-30 | 2011-12-17 |  |  | 99 | 99 | 99 | ER | Wind |  | Tap Washita - Blue Canyon Wind 138kV | 2008-05-12 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-023 |  | DISIS-2009-001-6 | 04 SOUTHEAST | Washita County | OK | AEP | 2010-12-01 | 2012-11-30 |  |  | 150 | 150 | 150 | ER | Wind |  | Hobart Junction 138kV | 2008-03-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-022 |  | DISIS-2010-001-8 | 05 SOUTHWEST | Chaves County | NM | SPS | 2011-09-01 | 2015-11-15 |  |  | 299.65 | 299.65 | 299.65 | ER | Wind |  | Eddy County-Tolk (Crossroads) 345kV | 2008-03-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-021 |  |  |  | Coffey County | KS | WERE | 2011-05-16 | 2011-05-16 |  |  | 42 | 42 | 42 | ER | Thermal | Nuclear | Wolf Creek 345kV | 2008-03-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-018 |  | ICS-2008-001-6 | 03 CENTRAL | Finney County | KS | SPS | 2012-12-31 | 2013-12-13 |  |  | 250 | 250 | 250 | ER | Wind |  | Finney 345kV | 2008-03-17 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-013 |  | ICS-2008-001-6 | 04 SOUTHEAST | Garfield County | OK | OGE | 2010-10-01 | 2012-12-07 |  |  | 300 | 300 | 300 | ER | Wind |  | Hunter 345kV | 2008-02-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-006 |  |  |  | Caddo Parish | LA | AEP | 2010-06-01 | 2010-06-16 |  |  | 30 | 20 | 30 | ER | Thermal | Gas | Arsenal Hill 138kV | 2008-01-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-005 |  |  |  | Mayes County | OK | GRDA | 2009-01-09 | 2009-09-02 |  |  | 16 | 16 | 16 | ER | Hydro |  |  | 2008-01-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-003 |  | ICS-2008-001-6 | 04 SOUTHEAST | Woodward | OK | OGE | 2009-08-31 | 2009-12-14 |  |  | 101.2 | 101.2 | 101.2 | ER | Wind |  | Woodward EHV 138kV | 2008-01-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2008-002 |  |  |  | Platte County | MO | KACP | 2009-01-01 | 2009-04-12 |  |  | 65 | 65 | 65 | ER | Thermal | Coal |  | 2008-01-22 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-062 |  | ICS-2008-001-6 | 04 SOUTHEAST | Harper County | OK | OGE | 2011-12-31 | 2016-12-21 |  |  | 424 | 424 | 424 | ER | Wind |  | Woodward EHV 345kV | 2007-12-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-052 |  | ICS-2008-001-6 | 04 SOUTHEAST | Caddo County | OK | WFEC | 2009-05-01 | 2009-07-01 |  |  | 150 | 150 | 150 | ER | Thermal | Gas | Anadarko 138kV | 2007-11-09 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-050 |  | ICS-2008-001-6 | 04 SOUTHEAST | Woodward County | OK | OGE | 2009-10-01 | 2010-12-23 |  |  | 151.8 | 151.8 | 151.8 | ER | Wind |  | Woodward EHV 138kV | 2007-10-22 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-046 |  | ICS-2008-001-6 | 05 SOUTHWEST | Texas County | OK | SPS | 2011-12-31 | 2015-12-15 |  |  | 200 | 200 | 200 | ER | Wind |  | Hitchland 115kV | 2007-10-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-044 |  | ICS-2008-001-6 | 04 SOUTHEAST | Blaine County | OK | OGE | 2009-12-01 | 2014-12-31 |  |  | 299.2 | 299.2 | 299.2 | ER | Wind |  | Tatonga 345kV | 2007-10-02 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-043 |  | ICS-2008-001-6 | 04 SOUTHEAST | Grady County | OK | OGE | 2009-12-01 | 2010-11-01 |  |  | 200 | 200 | 200 | ER | Wind |  | Minco 345kV | 2007-10-02 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-040 |  | DISIS-2009-001-6 | 03 CENTRAL | Gray County | KS | SUNC | 2010-12-15 | 2012-06-09 |  |  | 131.1 | 131.1 | 131.1 | ER | Wind |  | Buckner 345kV | 2007-09-25 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-025 |  | ICS-2008-001-6 | 03 CENTRAL | Barber County | KS | WERE | 2009-12-31 | 2012-10-01 |  |  | 299.2 | 299.2 | 299.2 | ER | Wind |  | Viola 345kV | 2007-05-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-021 |  | ICS-2008-001-6 | 04 SOUTHEAST | Dewey County | OK | OGE | 2009-08-01 | 2014-12-31 |  |  | 198.9 | 198.9 | 198.9 | ER | Wind |  | Tatonga 345kV | 2007-05-09 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2007-011N08 |  | ICS-2008-001 Prior Queued | 02 NEBRASKA | Knox County | NE | NPPD | 2009-01-01 |  |  |  | 81 | 81 | 81 | ER | Wind |  | Bloomfield 115kV | 2007-03-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-046 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Dewey | OK | OGE | 2009-12-31 | 2011-06-06 |  |  | 129.6 | 129.6 | 129.6 | ER | Wind |  | Dewey 138kV | 2006-12-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-044N |  | DISIS-2009-001-6 | 02 NEBRASKA | Petersburg | NE | NPPD | 2010-01-01 | 2011-12-31 |  |  | 40.5 | 40.5 | 40.5 | ER | Wind |  | North Petersburg 115kV | 2006-12-04 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-044 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Hansford | TX | SPS | 2010-10-01 | 2022-12-31 |  |  | 370 | 370 | 370 | ER | Wind |  | Hitchland 345kV | 2006-12-04 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-043 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Beckham County | OK | AEP | 2008-08-01 | 2009-12-15 |  |  | 99 | 99 | 99 | ER | Wind |  | Sweetwater 230kV | 2006-11-17 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-038N019 |  | ICS-2008-001 Prior Queued | 02 NEBRASKA | Boone County | NE | NPPD | 2011-05-01 | 2011-10-31 |  |  | 80 | 80 | 80 | ER | Wind |  | Petersburg North 115kV | 2006-10-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-038N005 |  | ICS-2008-001 Prior Queued | 02 NEBRASKA | Custer County | NE | NPPD | 2010-12-01 | 2012-12-31 |  |  | 80 | 80 | 80 | ER | Wind |  | Broken Bow 115kV | 2006-10-17 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-037N1 |  | DISIS-2009-001-6 | 02 NEBRASKA | Custer County | NE | NPPD | 2010-01-01 | 2014-12-31 |  |  | 75 | 75 | 75 | ER | Wind |  | Broken Bow 115kV | 2006-10-03 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-035 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Beckham County | OK | AEP | 2008-12-01 | 2012-04-27 |  |  | 132 | 132 | 132 | ER | Wind |  | Sweetwater 230kV | 2006-08-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-031 |  |  | 03 CENTRAL | Ellis County | KS | MIDW | 2008-06-01 | 2008-06-01 |  |  | 75.6 | 75.6 | 75.6 | ER | Thermal | Gas | Knoll 115kV | 2006-08-16 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-028 |  |  |  | Lyon | KS | WERE | 2009-05-01 | 2009-06-01 |  |  | 360 | 300 | 360 | ER | Thermal | Gas | Emporia 345kV | 2006-08-11 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-027 |  |  |  | Lyon | KS | WERE | 2008-05-01 | 2008-06-01 |  |  | 380 | 310 | 380 | ER | Thermal | Gas | Emporia 345kV | 2006-08-11 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-026 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Lea | NM | SPS | 2008-06-01 | 2008-06-01 |  |  | 604 | 604 | 604 | ER | Thermal | Gas | Hobbs 230kV & Hobbs 115kV | 2006-07-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-024S |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Harper | OK | WFEC | 2007-12-31 | 2008-12-31 |  |  | 18.9 | 18.9 | 18.9 | ER | Wind |  | Buffalo Bear Tap 69kV | 2006-07-07 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-021 |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Barber County | KS | ITCGP | 2008-05-31 | 2008-12-01 |  |  | 94 | 94 | 94 | ER | Wind |  | Flat Ridge Tap 138kV | 2006-06-21 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-020S |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Hansford | TX | SPS | 2007-09-01 | 2012-03-01 |  |  | 20 | 20 | 20 | ER | Wind |  | DWS Frisco 115kV | 2010-12-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-020N |  | ICS-2008-001 Prior Queued | 02 NEBRASKA | Bloomfield | NE | NPPD | 2009-01-01 |  |  |  | 42 | 42 | 42 | ER | Wind |  | Bloomfield 115kV | 2006-06-20 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-019 |  |  |  | Greene | MO | SPRM | 2010-06-01 | 2011-01-01 |  |  | 275 | 275 | 275 | ER | Thermal | Coal |  | 2006-06-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-018 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Hale | TX | SPS | 2007-06-01 | 2011-03-22 |  |  | 168.1 | 168.1 | 168.1 | ER | Thermal | CT | TUCO 230kV | 2010-06-01 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-015 |  |  | 05 SOUTHWEST | Denver City | TX | SPS | 2007-04-01 | 2007-06-01 |  |  | 150 | 150 | 150 | ER | Thermal | Gas | Mustang 230kV | 2006-04-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-010 |  |  | 04 SOUTHEAST | Hempstead Co. | AR | AEP | 2011-06-01 | 2012-12-20 |  |  | 620 | 610 | 620 | ER | Thermal | Coal | Turk 138kV | 2006-02-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-008 |  |  |  | Caddo Prsh. | LA | AEP | 2008-06-01 | 2010-06-26 |  |  | 550 | 490 | 550 | ER | Thermal | Gas | Arsenal Hill 138kV | 2006-02-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2006-002 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Beckham | OK | AEP | 2006-12-31 | 2010-12-28 |  |  | 100.8 | 100.8 | 100.8 | ER | Wind |  | Sweetwater 230kV | 2006-01-09 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2005-024 |  |  |  | Tulsa County | OK | AEP | 2007-06-01 | 2007-03-22 |  |  | 181 | 172 | 181 | ER | Thermal | Gas |  | 2005-12-13 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2005-022 |  |  |  | Caddo County | OK | AEP | 2007-06-01 | 2007-12-27 |  |  | 177 | 168 | 177 | ER | Thermal | Gas |  | 2005-12-13 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2005-013 |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Elk County | KS | WERE | 2007-11-01 | 2011-07-05 |  |  | 199.8 | 199.8 | 199.8 | ER | Wind |  | Caney River 345kV | 2005-08-22 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2005-012 |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Ford County | KS | SUNC | 2015-12-31 | 2012-09-01 |  |  | 248.4 | 248.4 | 248.4 | ER | Wind |  | Clark County-Spearville Ckt 1 (Ironwood) 345kV | 2005-08-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2005-008 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Harper County | OK | OGE | 2007-07-31 | 2007-06-30 |  |  | 120 | 120 | 120 | ER | Wind |  | Woodward 138kV | 2005-04-01 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2005-003 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Caddo & Kiowa Counties | OK | WFEC | 2005-12-01 | 2005-12-15 |  |  | 30.6 | 30.6 | 30.6 | ER | Wind |  | Washita 138kV | 2005-01-21 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-023N |  | ICS-2008-001 Prior Queued | 02 NEBRASKA | Columbus | NE | NPPD | 2009-01-01 |  |  |  | 75 | 75 | 75 | ER | Thermal | Coal | Columbus Co 115kV | 2004-11-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-023 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Apache | OK | WFEC | 2005-12-01 | 2005-12-15 |  |  | 20.6 | 20.6 | 20.6 | ER | Wind |  | Washita 138kV | 2004-10-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-022N |  |  |  | Hastings | NE | NPPD | 2005-01-01 |  |  |  | 11 | 11 | 11 | ER | Thermal |  |  | 2004-10-20 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-020 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Custer County | OK | AEP | 2005-12-31 | 2006-01-01 |  |  | 27 | 27 | 27 | ER | Wind |  | Clinton Junction-Weatherford Southeast 138kV | 2004-10-08 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-019N |  |  |  | Colfax County | NE | NPPD | 2005-01-01 |  |  |  | 0.1 | 0.1 | 0.1 | ER | Thermal | Gas |  | 2004-10-04 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-018N1 |  |  |  | Brownsville | NE | NPPD | 2005-01-01 |  |  |  | 22 | 22 | 22 | ER | Thermal | Nuclear |  | 2004-09-20 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-017N |  |  |  | Columbus | NE | NPPD | 2007-01-01 |  |  |  | 5 | 5 | 5 | ER | Hydro |  |  | 2004-09-13 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-017 |  |  | 03 CENTRAL | Riverton SE Cherokee Cnty | KS | EDE | 2007-01-01 |  |  |  | 250 | 250 | 250 | ER/NR | Thermal | CT/ST | Riverton 161kV | 2004-08-23 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-015 |  |  | 05 SOUTHWEST | Denver City/Yoakum | TX | SPS | 2006-04-01 | 2006-04-01 |  |  | 150 | 150 | 150 | ER | Thermal | CT |  | 2004-07-12 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-014 |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Edwards | KS | MKEC | 2005-11-15 | 2012-12-31 |  |  | 152 | 152 | 152 | ER | Wind |  | Spearville 230kV | 2004-04-22 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-008 |  |  | 03 CENTRAL | Platte County | MO | KCPL | 2009-06-01 | 2012-06-05 |  |  | 850 | 850 | 850 | ER | Thermal | Coal |  | 2004-03-26 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2004-002O |  |  |  | Washington County | NE | OPPD | 2007-01-01 |  |  |  | 48 | 48 | 48 | ER | Thermal | Nuclear |  | 2004-01-21 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-022 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Custer/Wasita | OK | AEP | 2004-12-31 | 2006-01-01 |  |  | 120 | 120 | 120 | ER | Wind |  | Clinton Junction-Weatherford Southeast 138kV | 2003-12-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-021N |  | ICS-2008-001 Prior Queued | 02 NEBRASKA | Ainsworth | NE | NPPD | 2005-10-01 |  |  |  | 75 | 75 | 75 | ER | Wind |  | Ainsworth Wind Tap 115kV | 2003-12-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-020 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Carson County | TX | SPS | 2007-06-01 | 2012-08-01 |  |  | 159.1 | 159.1 | 159.1 | ER | Wind |  | Martin 115kV | 2003-12-29 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-019 |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Salina NC Ellsworth Cnty | KS | MIDW | 2006-11-01 | 2006-11-01 |  |  | 249.3 | 249.3 | 249.3 | ER | Wind |  | Smoky Hills Tap 230kV | 2003-11-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-017N |  |  |  | Brownsville | NE | NPPD | 2007-01-01 |  |  |  | 50 | 50 | 50 | ER | Thermal | Nuclear |  | 2003-10-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-008O |  |  |  | Otoe County | NE | OPPD | 2009-05-01 |  |  |  | 700 | 700 | 700 | ER | Thermal | Coal |  | 2003-07-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-006A |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Cloud County | KS | MKEC |  |  |  |  | 201 | 201 | 201 | ER | Wind |  | Elm Creek 230kV | 2003-07-09 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-005 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Apache | OK | WFEC | 2006-12-01 |  |  |  | 99 | 99 | 99 | ER | Wind |  | Anadarko - Paradise (Blue Canyon) 138kV | 2003-06-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2003-004 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Apache | OK | WFEC | 2005-12-01 | 2005-12-15 |  |  | 100 | 100 | 100 | ER | Wind |  | Washita 138kV | 2003-06-05 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-025A |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Spearville | KS | MKEC | 2006-06-01 |  |  |  | 100.5 | 100.5 | 100.5 | ER | Wind |  | Spearville 230kV | 2002-10-31 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-023N |  |  |  | Harmony | NE | NPPD |  |  |  |  | 0.8 | 0.8 | 0.8 | ER | Wind |  | Harmony 115kV | 2002-09-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-022 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Oldham County (Wildorado) | TX | SPS | 2006-12-15 |  |  |  | 239.2 | 239.2 | 239.2 | ER | Wind |  | Bushland 230kV | 2002-09-12 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-009 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Hansford County | TX | SPS | 2006-09-30 | 2006-09-30 |  |  | 67.2 | 67.2 | 67.2 | ER | Wind |  | Hansford 115kV | 2002-07-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-008 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Hansford County | TX | SPS | 2007-11-01 | 2008-12-30 |  |  | 240 | 240 | 240 | ER | Wind |  | Hitchland 345kV | 2002-07-19 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-005 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Hammon | OK | WFEC | 2006-12-31 | 2008-12-31 |  |  | 123 | 123 | 123 | ER | Wind |  | Red Hills Tap 138kV | 2002-04-28 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-004N |  |  |  | Grand Island | NE | NPPD | 2003-12-01 |  |  |  | 80 | 80 | 80 | ER | Thermal | Gas |  | 2002-04-16 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2002-004 |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Beaumont SE Butler Cnty | KS | WERE | 2003-09-30 | 2005-12-15 |  |  | 153 | 153 | 153 | ER | Wind |  | Latham 345kV | 2002-04-12 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-040 |  |  | 03 CENTRAL | LaRussell Energy Ctr. | MO | EDE | 2003-06-01 | 2003-04-24 |  |  | 50 | 50 | 50 | ER | Thermal | CT | LaRussell Energy Center 161kV | 2001-11-27 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-039M |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Wichita County | KS | SUNC | 2008-12-01 |  |  |  | 100 | 100 | 100 | ER | Wind |  | Central Plains Tap 115kV | 2001-11-01 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-039A |  | ICS-2008-001 Prior Queued | 03 CENTRAL | Kiowa County | KS | MKEC |  |  |  |  | 104 | 104 | 104 | ER | Wind |  | Shooting Star Tap 115kV | 2001-10-30 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-037 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Woodward | OK | OGE | 2002-10-01 | 2003-11-12 |  |  | 102 | 102 | 102 | ER | Wind |  | FPL Moreland Tap 138kV | 2001-10-18 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-033 |  | ICS-2008-001 Prior Queued | 05 SOUTHWEST | Chaves County (Melrose) | NM | SPS | 2002-10-01 | 2005-12-22 |  |  | 120 | 120 | 120 | ER | Wind |  | San Juan Tap 230kV | 2001-09-17 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-030 |  |  | 03 CENTRAL | LaRussell Energy Center | MO | EDE | 2003-06-01 | 2003-04-25 |  |  | 50 | 50 | 50 | ER | Thermal | CT | LaRussell Energy Center 161kV | 2001-09-04 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-029N |  |  |  | Beatrice | NE | NPPD | 2005-01-01 | 2005-01-01 |  |  | 250 | 250 | 250 | ER | Thermal | Gas |  | 2001-08-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-026 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Meers | OK | WFEC | 2003-10-01 | 2003-10-01 |  |  | 74.25 | 74.25 | 74.25 | ER | Wind |  | Washita 138kV | 2001-07-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-024 |  |  |  | Washington County | AR | AEP | 2007-05-01 | 2007-07-01 |  |  | 630 | 580 | 630 | ER | Thermal | CT | SWEPCO Tontitown 161kV Substation | 2001-07-09 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-018 |  |  |  | Neosho County | KS | WERE | 2002-01-01 | 2002-01-01 |  |  | 47 | 47 | 47 | ER | Thermal | Gas | Chanute NW Neosho Cnty By Tioga Sub | 2001-05-15 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION
GEN-2001-014 |  | ICS-2008-001 Prior Queued | 04 SOUTHEAST | Sleeping Bear | OK | WFEC | 2007-06-30 | 2007-04-15 |  |  | 94.5 | 94.5 | 94.5 | ER | Wind |  | Ft Supply 138kV | 2001-04-24 |  | IA FULLY EXECUTED/COMMERCIAL OPERATION